## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Pavement Drains - Rev B | itp |  |  |  |  | ITP - Pavement Drains - Rev B
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
note | Standard / Specification - Downer
note | Verifying Document - Construction Pack
note | Frequency - Submit 10 days prior to commencement of works
note | Activity - H
note | By - PE
checkpoint | 3.01.02 - Survey Setout
note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
note | Standard / Specification - Downer
note | Verifying Document - Survey Records
note | Frequency - Prior to Works
note | Activity - H
note | By - SV
checkpoint | 3.01.03 - Approved Construction Drawings
note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
note | Standard / Specification - Downer
note | Verifying Document - IFC Drawings
note | Frequency - Prior to works start
note | Activity - H
note | By - PE
checkpoint | 3.01.04 - Topographic surveys for measurement
note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
note | Standard / Specification - PS 2.2.12
note | Verifying Document - As-built
note | Frequency - Prior to works and Post Works
note | Activity - H
note | By - PE
checkpoint | 3.01.05 - Permits
note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
note | Standard / Specification - ITP Register
note | Verifying Document - ITP Sign Off
note | Frequency - Prior to commencement of construction activity
note | Activity - R
note | By - SE
checkpoint | 3.01.06 - Stakeholder Management
note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
note | Standard / Specification - Project Stakeholder Management Plan
note | Verifying Document - ITP Sign Off
note | Frequency - Prior to Construction with continue updates throughout the works
note | Activity - R
note | By - SE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Pavement Pipes
note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 100mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
note | Standard / Specification - GWS 3.2.1
note | Verifying Document - Datasheet
note | Frequency - Prior to installation
note | Activity - C
note | By - SE
checkpoint | 4.01.02 - Pavement Drainage Aggregate (20/40)
note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/5 including gradings
note | Standard / Specification - GWS 3.2.2 & 3.4
note | Verifying Document - PSD, CR
note | Frequency - Prior to installation
note | Activity - C
note | By - SE
checkpoint | 4.01.03 - Filter Cloth
note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
note | Standard / Specification - GWS 3.2.3
note | Verifying Document - Datasheet
note | Frequency - Every 1,000m3. At least two weeks prior to works.
note | Activity - C
note | By - SE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
note | Standard / Specification - GWS 3.2.2
note | Verifying Document - Site Record
note | Frequency - Prior to backfilling
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.02 - Trench Backfill
note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through
note | Standard / Specification - GWS 3.3
note | Verifying Document - Site Record
note | Frequency - Each trench
note | Activity - I
note | By - SE
checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each pavement drainage system to enable flushing of the system once the earthworks are complete.
note | Standard / Specification - GWS 3.6
note | Verifying Document - Site Records
note | Frequency - Each Subsoil Line
note | Activity - I
note | By - SE
checkpoint | 5.01.04 - Subsoil Flushing
note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
note | Standard / Specification - GWS 3.6
note | Verifying Document - Site Records
note | Frequency - On completion of earthworks
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.05 - Survey
note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - SV
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Construction Record Compilation
note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - SE
checkpoint | 6.01.02 - Survey Records
note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - SV
checkpoint | 6.01.03 - Redline Drawings
note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
note | Standard / Specification - Downer
note | Verifying Document - Redlines
note | Frequency - Post construction
note | Activity - H
note | By - PE
checkpoint | 6.01.04 - Defect, Snag and Punch List
note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
note | Standard / Specification - Downer
note | Verifying Document - Register
note | Frequency - Post construction
note | Activity - H
note | By - PE
checkpoint | 6.01.05 - Photos
note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
note | Standard / Specification - Downer
note | Verifying Document - Photo Records
note | Frequency - Post construction
note | Activity - H
note | By - SE