## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Tunnel Roof Section - |  |  |  |  | Yes | QA - Tunnel Roof Sections Checklist | 03f1f74c-ab24-480b-aba0-5af84945134a
checkpoint-status |  |  | checkpoint | Substrate is ready to receive the sika S felt, all voids filled
checkpoint-status |  |  | checkpoint | Place the Sika S felt Geo mat
checkpoint-status |  |  | checkpoint | Sika plan WP1100-20 HL placed and laps welded
checkpoint-status |  |  | checkpoint | Sika plan WP1100-20 HL welded to water bars
checkpoint-status |  |  | checkpoint | EFVM test completed and any required repairs completed
checkpoint-status |  |  | checkpoint | Protection layer placed
checklist-sectioned |  |  | checklist | Joint Sealant QA - |  |  |  |  | Yes | QA - New Joint Sealant V1 Checklist | 0555c94e-61eb-4bc9-8a50-c16cb17a3cf2
checkpoint-group |  |  | section | General Details
checkpoint-no-status |  |  | checkpoint | Details Correct
text | 3373ea35-3213-4e40-b03e-73910a1fe75f |  | textbox | Job Name:
text | a5a8d6e9-954f-45e7-b32a-8343e67ee47b |  | textbox | Job Number:
checkpoint-group |  |  | section | General Information
checkpoint-no-status |  |  | checkpoint | Details Recorded
text | f5bb60cb-b154-45aa-a503-9051e1e04572 |  | textbox | Work Crew:
label | 84b9576f-20f7-40d4-aa4b-9c05d0b84a7c |  | note | Weather Conditions:
select | 31432d2d-f1f7-477d-aa41-dcd69ec60df3 |  | dropdown | Morning | Cloudy,Overcast,Rain,Sunny
select | 3cd8ffd5-e34d-46f3-9ad5-7fc605009cb6 |  | dropdown | Afternoon | Cloudy,Overcast,Rain,Sunny
checkpoint-group |  |  | section | Joint Preparation
checkpoint-status |  |  | checkpoint | Existing sealant removed?
checkpoint-status |  |  | checkpoint | Joint edges ground clean?
checkpoint-status |  |  | checkpoint | Joint edges clean and free of defects?
checkpoint-group |  |  | section | Joint Sealing
checkpoint-status |  |  | checkpoint | PEF rod installed?
checkpoint-status |  |  | checkpoint | Bond breaker tape installed?
checkpoint-status |  |  | checkpoint | Masked either side of joint?
checkpoint-status |  |  | checkpoint | Primer applied?
text | 8e215890-985f-43e0-a400-21205e386400 |  | textbox | Primer type:
text | 70a7fe6a-1dfe-4732-a981-748f32cabb1b |  | textbox | Batch number(s):
checkpoint-status |  |  | checkpoint | Sealant applied?
text | d82e871f-d170-4284-af99-2bc21d524881 |  | textbox | Sealant type:
text | b2545601-0cd1-45c8-a6a4-da06a2bc02a7 |  | textbox | Batch number(s):
label | eceacc2f-38b5-4768-b02d-28cbfd71369c |  | note | Joint size and length
checkpoint-status |  |  | checkpoint | Joint size and length measured
boolean | 3c3a647c-c438-41ca-9e65-016caa0a7b8e |  | tickbox | 5mm x 5mm
text | 7203ccb3-dd1b-4728-8709-82ca17896993 |  | textbox | Length:
text | 80edf338-4779-40ca-b0e3-b1bdd145eb9f |  | textbox | Location:
boolean | 4118f366-a73c-412f-8ed8-7f7299ac7399 |  | tickbox | 10mm x 10mm
text | 32486c98-f455-4560-9f60-ad8fa844872f |  | textbox | Length:
text | 79bd34fb-01d4-4133-b9b5-751cb999d9d2 |  | textbox | Location:
boolean | 685fe7ab-3ad3-4280-a85c-573a38a655b3 |  | tickbox | 15mm x 12mm
text | 9e4675b1-af5f-41a6-89cc-78f93719828a |  | textbox | Length:
text | 46fd90e0-2ea2-4277-b9f7-3821f8fcbbaf |  | textbox | Location:
boolean | 300e764a-74f6-4c8c-9280-230e162f2f67 |  | tickbox | 20mm x 12mm
text | 18f07ee8-1bb2-4926-ae4e-5486ca286ff7 |  | textbox | Length:
text | c16cf270-9b2d-4233-9d3f-9cbddb070531 |  | textbox | Location:
boolean | 6ff94d33-34bd-4aa0-8a4d-1b2cbceffcc3 |  | tickbox | 25mm x 12.5mm
text | b2d9bdd1-77d0-4067-9e63-30be2a4be424 |  | textbox | Length:
text | 2df3dd06-b833-4bbd-bb30-ffbf6e9e090c |  | textbox | Location:
boolean | d496d3ad-79c8-4ec3-b174-9d8839de9727 |  | tickbox | 30mm x 15mm
text | f4692fbf-b565-4912-a39e-0120a2964c58 |  | textbox | Length:
text | f7361507-a30d-4dd1-8a28-971f323219fd |  | textbox | Location:
boolean | be8c4e10-55ac-4023-ad8c-fd6139982504 |  | tickbox | 35mm x 17.5mm
text | a64d2694-0136-483c-afd6-eab58ad6fd16 |  | textbox | Length:
text | eabfa412-9325-487b-99c1-73184df955a0 |  | textbox | Location:
boolean | b56df302-a39d-465b-9e31-aeac08e58303 |  | tickbox | 40mm x 20mm
text | d034a927-7cb4-4bb9-9aeb-f93b5b2fbd28 |  | textbox | Length:
text | 480812dc-ab6c-4d0c-896b-cca564b74cc2 |  | textbox | Location:
text | 45ee21df-38bb-488d-851d-00364e91dacd |  | textbox | Other:
checkpoint-group |  |  | section | Environmental
checkpoint-status |  |  | checkpoint | All waste removed from site?
checkpoint-group |  |  | section | Final Sign Off
checkpoint-status |  |  | checkpoint | Completed to specification?
checkpoint-status |  |  | checkpoint | Joints free from defects?
checkpoint-status |  |  | checkpoint | Sansom Supervisor Sign Off
text | 5b344ba0-083b-4283-b058-19ec3ea50f25 |  | textbox | Full Name:
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Client Sign Off (if required)
text | fdbef03f-7d08-477e-93a9-88f1e64e6f9a |  | textbox | Full Name:
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Concrete Repair Checklist |  |  |  |  | Yes | QA - Concrete Repair Checklist | 0b125568-2017-432f-8829-55fd48fd3f7c
checkpoint-group |  |  | section | SB1 Dicore Supports
checkpoint-status |  |  | checkpoint | Marking holes
checkpoint-status |  |  | checkpoint | Drilling 150mm deep
checkpoint-status |  |  | checkpoint | Cleaning holes
checkpoint-status |  |  | checkpoint | Fitting bolts
checkpoint-status |  |  | checkpoint | Fitting plate
checkpoint-status |  |  | checkpoint | Bolt tension
checkpoint-group |  |  | section | M12 Hangers
checkpoint-status |  |  | checkpoint | Hole location
checkpoint-status |  |  | checkpoint | Hole depth 380mm
checkpoint-status |  |  | checkpoint | Cutting 380mm
checkpoint-status |  |  | checkpoint | Chip out 20mm deep
checkpoint-status |  |  | checkpoint | Fit bolt, washer, nut, pour epoxy under plate, tighten nut
checklist-flat |  |  | checklist | C1 Tunnel Stub Sign Off |  |  |  |  | Yes | QA - C1 Tunnel Stub Sign Off | 0cbf8187-a2d7-44d8-9f42-6b6f38bddc9d
checkpoint-status |  |  | checkpoint | Substrate and all voids prepped
checkpoint-status |  |  | checkpoint | Sikaproof A is tied into the water bars where required
checkpoint-status |  |  | checkpoint | Sikaproof P areas are primed
checkpoint-status |  |  | checkpoint | Sikaproof P is installed and tied into the water bars where required
checkpoint-status |  |  | checkpoint | All external tapes are in place where required and geotextile protection in place
checkpoint-status |  |  | checkpoint | Roof geotextile in place to receive the sikaplan 1100-20H
checkpoint-status |  |  | checkpoint | Sikaplan 1100-20H placed and welded to the water bars where required
checkpoint-status |  |  | checkpoint | EFVM test completed and any required repairs done
checkpoint-status |  |  | checkpoint | Geotextile protection placed to receive the backfill material
checklist-flat |  |  | checklist | Preprufe 300R beams and underfloor |  |  |  |  | Yes | QA - Preprufe 300R Beams and Underfloor Checklist | 1ba4554a-bd4d-4ef6-a032-9b2067496ea0
checkpoint-status |  |  | checkpoint | Area Specified Below
checkpoint-status |  |  | checkpoint | Geotextile to substrate
checkpoint-status |  |  | checkpoint | Preprufe placed all laps taped Preprufe bedded into LM 300 on top of piles
checkpoint-status |  |  | checkpoint | Adcor 500 T placed around top of pile
checkpoint-status |  |  | checkpoint | Swell seal WA placed around all pile bars
checklist-sectioned |  |  | checklist | Date: |  |  |  |  | Yes | QA - Mapei QA Checklist | 2ed5a22c-bb6b-493f-994d-356167b7b859
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 91dbb664-c66f-4f94-ba32-7d967933fdc1 |  | textbox | Date of Application:
text | 51b35cdb-8089-47f4-b04d-3139ac7bdf7a |  | textbox | Application area:
text | 4dce4875-035d-46e1-80d8-9e5ad10fd68c |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Product used (Name – Quantity – Correct labeling – Batch Date – Expiry Date): (product must have been be stored in a dry place in temperatures between +8 degrees Celsius - + 35 degrees Celsius)
checkpoint-group |  |  | section | Setup
checkpoint-status |  |  | checkpoint | Confirm testing regimes, types, and frequency required by the project engineer
checkpoint-status |  |  | checkpoint | Confirm the design drawings are current
checkpoint-status |  |  | checkpoint | Ensure that all tooling is available
checkpoint-status |  |  | checkpoint | Check that all personnel on site are aware of their individual responsibilities and know what they are doing.
checkpoint-status |  |  | checkpoint | Protect all surrounding areas from damage
checkpoint-status |  |  | checkpoint | Have all necessary personal protection equipment on site and in use
checkpoint-status |  |  | checkpoint | Take photos of each step of the operation
checkpoint-group |  |  | section | Environment
checkpoint-status |  |  | checkpoint | Check and record ambient temperature (Must be between +8 degrees Celsius and + 35 degrees Celsius)
text | ea5e9912-28d1-4608-9459-64e3bd3b9b29 |  | textbox |  |  |  | Degrees Celsius
checkpoint-status |  |  | checkpoint | Check and record substrate temperature (Must be between +8 degrees Celsius and + 35 degrees Celsius)
text | ad610474-dec3-4c42-b4b3-8fe4e1638633 |  | textbox |  |  |  | Degrees Celsius
checkpoint-status |  |  | checkpoint | Check and record air humidity (Be aware of Dew Point, especially in the mornings, evenings and at any other time there may have been a sudden increase or decrease in air temperature)
checkpoint-status |  |  | checkpoint | Check RH of substrate it should not be damp, it should not be above 75% RH it should not be subject to rising damp. If dampness is present then consult with Mapei for an appropriate solution
checkpoint-group |  |  | section | Substrate
checkpoint-status |  |  | checkpoint | Checked to be structurally sound
checkpoint-status |  |  | checkpoint | Checked to be dry and dust free
checkpoint-status |  |  | checkpoint | Checked to be free of all contamination
checkpoint-status |  |  | checkpoint | Checked to ensure concrete has a tensile strength - 1.5MPa
checkpoint-status |  |  | checkpoint | Rusted steel work cleaned to bright finish and treated with Mapefer 1k
checkpoint-status |  |  | checkpoint | Carry out any required repair work to the concrete host substrate using Mapegrout T60, Mapegrout Hi-Flow SP, or Adesilex PG 1 depending on the nature of the repair work being undertaken. Allow adequate curing of items prior to installation of the Mapewrap system
checkpoint-status |  |  | checkpoint | Ensure there are no sharp edges or sharp protrusions in the substrate that could damage the application – External corners must be rounded to a radius not less than 20mm
checkpoint-status |  |  | checkpoint | Cracks wider than 0.3mm repaired with Epojet LV
label | 4245ae92-d50c-4a4e-818d-30ab0faf4269 |  | note | Take Photos
checkpoint-group |  |  | section | Substrate preparation
checkpoint-status |  |  | checkpoint | Substrate must be freshly exposed and have a slight surface texture (around 80 grit). It must not have a polished finish
checkpoint-status |  |  | checkpoint | Substrate must be free of all resulting loose and unsound materials. Check for any chalkiness to the concrete surface using a scrape test and if the substrate is chalky then this part of the surface must be removed to provide a structurally sound bond face
checkpoint-status |  |  | checkpoint | Existing soft materials must be removed and if it appears the substrate is of low compressive strength then this must be reported to the installation team foreman for further action and instruction before proceeding, this should include a consultation with the project engineer
checkpoint-status |  |  | checkpoint | Ensure external corners are rounded to a radius of not less than 20mm
checkpoint-status |  |  | checkpoint | Mechanically remove any sharp protrusions or surfaces. Ensure the substrate is smooth and has no sudden changes of plane (must not exceed 1mm)
checkpoint-status |  |  | checkpoint | Check for any pin holes or voids in the prepared substrate, these must be repaired and smoothed prior to the installation of the wrap using products from the Mapegrout range or, if immediate repair work is required, use Adesilex PG 1 or Adesilex PG 2
checkpoint-status |  |  | checkpoint | Accurately mark out positions for Mapewrap to be applied as per Engineers drawings. Any variations of the orientation of the fabric of more than 5 must be reported to the project engineer
label | 58e09c8d-a087-496f-aa68-a521613c5565 |  | note | Take Photos
checkpoint-group |  |  | section | Preparation of Materials
checkpoint-status |  |  | checkpoint | Ensure Mapewrap is cut to exactly the required length. It must be stored in a clean & dry area and be temperature conditioned before use
checkpoint-status |  |  | checkpoint | Check for damage to Mapewrap (damaged materials must not be used)
checkpoint-status |  |  | checkpoint | Mapewrap Primer 1 SP must be temperature conditioned and mixed at correct ratio being 3:1 (A:B) by weight for 1-2 minutes with a slow speed mixer until a homogenous mix is achieved
checkpoint-status |  |  | checkpoint | Mapewrap Primer 1 SP used within its recommended pot life (60 minutes @ +23 Degrees Celsius )
checkpoint-status |  |  | checkpoint | Mapewrap 31 SP epoxy saturant must be temperature conditioned and mixed at correct ratio being 3:1 (A:B) by weight with a slow speed mixer until a homogenous mix is achieved
checkpoint-status |  |  | checkpoint | Mapewrap 31 SP is used within its recommended pot life (60 minutes @ +23 Degrees Celsius )
label | 7be52c32-dca9-48bb-894a-51063b1f06ab |  | note | Take Photos
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Clearly define, label, and note application area. Accurately site measure each area and calculate the estimated consumption rates for the materials to be used recording these on the consumption chart. Monitor and record the actual consumption rates of the materials used and ensure the estimated and actual consumption rates are in line with each other. Any variations must be investigated, noted, and reported to management
checkpoint-status |  |  | checkpoint | Provide adequate temporary coverings to surfaces in the surrounding surfaces to protect against dropping and spillage of the resin based products being used.
checkpoint-status |  |  | checkpoint | Correctly prepare substrate priming it with Mapewrap Primer 1 SP using a brush or a roller. Depending on the absorbency of the substrate a second primer coat may be required
checkpoint-status |  |  | checkpoint | Install Adesilex PG 1 to all concrete substrate areas that require smoothing or have pin holes. The follow on application of the Wrap must occur while the Adesilex PG 1 is still freshly applied (within 12 hours of the Adesilex PG 1 being applied). Should application of resin based products be required over Adesilex PG 1 that is beyond its fresh time then the Adesilex PG 1 must have its top surface ground then wiped with Isopropyl Alcohol ensuring all resulting dust has been removed. Any areas where concrete has been exposed during this process will require further priming with MapeWrap Primer 1 SP. Should the Adesilex PG 1 have a oily, waxy, or greasy feel to it then do not proceed with the follow on installation and instead report to management for further instructions
checkpoint-status |  |  | checkpoint | Apply a roller coat of MapeWrap 31 SP to the substrate to provide an even coat of product to the area being treated (refer to consumption chart)
checkpoint-status |  |  | checkpoint | Saturate Mapewrap with Mapewrap 31 SP (refer consumption chart)
checkpoint-status |  |  | checkpoint | nstall Mapewrap as per orientation in Engineers drawing, constant pressure applied over the Mapewrap smoothing by hand and including using a ribbed roller to ensure the fabric is impregnated with the resin and any entrapped air is removed. Always roll in the direction of the fibre never across it as there is a risk that the roller used could damage the fibre. If required apply another roller coat of MapeWrap 31 SP
checkpoint-status |  |  | checkpoint | Thoroughly check any entrapped air is removed and complete a visual inspection to ensure there is no evidence of dry fibres. Any potential issues identified must be immediately reported to the project foreman for further action
checkpoint-status |  |  | checkpoint | Misalignment of the direction of the fabric of more than 5 degrees to the Engineers drawing must be reported to the Engineer for evaluation and acceptance
checkpoint-status |  |  | checkpoint | Laps must be staggered and not in line with each other (unless otherwise directed by the Engineer) the minimum overlap for laps in the direction of the fabric is 200mm, the side laps for Uni-directional fabric can be butt jointed
checkpoint-status |  |  | checkpoint | When the final layer of Wrap has been applied and if a layer of sand is required to be applied as a mechanical key for the follow on protective and/or aesthetic coatings then the broadcasting of sand is to be carried out as a separate process once the MapeWrap 31 SP used to saturate the last layer of wrap has tacked off but before the fresh time of the top layer has expired
checkpoint-status |  |  | checkpoint | At all times during the process keep samples of resins mixed and wrap used for further analysis if required. Label and record these samples including the date mixed, the application area and keep them in the same area as the application being undertaken at that time until cured after which these are to be kept safely stored.
label | 1669a418-013c-411b-8d40-033b3740ce9d |  | note | Take Photos
checkpoint-group |  |  | section | Testing (All results to be recorded and forwarded to the Engineer)
checkpoint-status |  |  | checkpoint | Perform both a visual and acoustic tapping test of the installed Mapewrap to check for voids 24 hours after installation.
checkpoint-status |  |  | checkpoint | Carry out any other tests required as has been directed by the project engineer
checkpoint-status |  |  | checkpoint | Keep and tag samples of materials used at a minimum of a daily basis or as directed by the project engineer for future testing and analysis.
text | 2590b3e9-6564-4d67-837f-4732550ab2e1 |  | textbox | Signed: |  |  | Qualified Supervisor
text | 0203b503-134b-44a5-83c9-fe96c1961619 |  | textbox | Name:
text | 699a4d74-4ade-489b-ba66-2618c9dff833 |  | textbox | Date:
checklist-flat |  |  | checklist | Matacryl Checklist |  |  |  |  | Yes | QA - Matacryl Checklist | 34ab8bc8-57fb-4782-8d68-45b1b9701a58
checkpoint-status |  | checkpoint-status must be display normal but was flat | checkpoint | Surface Preparation
checkpoint-status |  |  | checkpoint | Primer
checkpoint-status |  |  | checkpoint | Coating 1st layer
checkpoint-status |  |  | checkpoint | Coating 2nd layer
checkpoint-status |  |  | checkpoint | Coating 3rd layer
checklist-flat | a89ea8ab-d63c-4227-b0c8-fb0ce5e545f8 |  | checklist | Document: |  |  |  |  | Yes | Document Attach | 3864513d-368a-46b5-b7e6-cc760c7a465b
checkpoint-status | 700d5cd3-d75b-4707-b6f5-7eb22e64b1b2 |  | checkpoint | Document Attached
checklist-flat |  |  | checklist | Head Wall Bituthene 3000 |  |  |  |  | Yes | QA - Head Wall Bituthene 3000 Checklist | 40466439-daac-4f5e-8d1a-536d40398b97
checkpoint-status |  |  | checkpoint | Substrate and all voids filled
checkpoint-status |  |  | checkpoint | Substrate primed ready to receive the Bituthene 3000
checkpoint-status |  |  | checkpoint | Bituthene 3000 placed on the prepped area
checkpoint-status |  |  | checkpoint | Laps sealed with Liquid Membrane
checkpoint-status |  |  | checkpoint | Coreflute protection placed
checklist-sectioned |  |  | checklist | Tanking - Underfloor Checklist |  |  |  |  | Yes | QA - Tanking - Underfloor Checklist | 428281f0-ecf4-4b17-a9d3-b8c880f7c694
checkpoint-group |  |  | section | Pre-installation QA
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked and referenced
text | 4dd61b41-1e18-406c-822b-88ba53a0d930 |  | textbox | Relevant drawings & revisions for reference:
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Installation QA
checkpoint-status |  |  | checkpoint | Product being used input
select | 4560de98-7339-4444-b33c-227cb409044c |  | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
checkpoint-status |  |  | checkpoint | Location where being applied input.
text | 20d893f0-1c05-40c7-8e2e-f8e3ff9da96a |  | textbox | Area:
checkpoint-status |  |  | checkpoint | Geotextile in place if required
checkpoint-status |  |  | checkpoint | All laps to manufacturer's specifications.
checkpoint-status |  |  | checkpoint | (Voltex DS only) DPC must be removed 100mm minimum for lapping
checkpoint-status |  |  | checkpoint | Penetrations are detailed as to manufacturer's specification
checkpoint-status |  |  | checkpoint | All water stops installed
checkpoint-status |  |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status |  |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-group |  |  | section | Completion / Handover
checkpoint-status |  |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
holdpoint |  |  | signoff | Raise Remedial / Request Review
checklist-flat |  |  | checklist | Vertical Stitch Checklist |  |  |  |  | Yes | QA - Vertical Stitch Checklist | 51daa244-43eb-4744-b5cb-489b4a0ed137
checkpoint-status |  |  | checkpoint | Work area/substrate is clean, dry and ready to start
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Photograph(s) taken of substrate
checkpoint-status |  |  | checkpoint | Joint width measured
checkpoint-status |  |  | checkpoint | Photograph(s) taken of installed backing (before protection board is installed)
checkpoint-status |  |  | checkpoint | Protection board installed
checkpoint-status |  |  | checkpoint | Photograph(s) of protection board
checkpoint-status |  |  | checkpoint | All joint sealant installed correctly, checked & reviewed - as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
checklist-flat |  |  | checklist | CRL Underfloor QA Check List |  |  |  |  | Yes | QA - (CRL) Underfloor Checklist | 5499cdf5-7287-4772-be31-1efe685d61a9
checkpoint-status |  | checkpoint-status must be display normal but was flat | checkpoint | Gridlines
text | 18e4decb-e742-4623-90e1-00150060fa57 | Hidden property width:50 | textbox |  |  | ( | ) to
text | ce6f519e-67b5-4807-83a5-b93d0f68dfcb | Hidden property width:50 | textbox |  |  | ( | )
checkpoint-status |  |  | checkpoint | Site concrete poured and accepted
checkpoint-status |  |  | checkpoint | Geotextile placed
checkpoint-status |  |  | checkpoint | Sikaproof A placed
checkpoint-status |  |  | checkpoint | All laps taped with sikaproof tape 150
checkpoint-status |  |  | checkpoint | All piles detailed as per the specification
checkpoint-status |  |  | checkpoint | All waterstops and injection hoses have been placed
checkpoint-status |  |  | checkpoint | Waterbars have been installed where required
checkpoint-status |  |  | checkpoint | Final inspection and hand over
checklist-sectioned |  |  | checklist | Waterstop RX Checklist -Zone / Grids: |  |  |  |  | Yes | QA - (10 Madden St) - Waterstop RX Checklist | 562ef34d-c040-43a4-97a8-b098500aa1cf
checkpoint-group |  |  | section | Surface Preparation
checkpoint-status |  |  | checkpoint | Surface clean
checkpoint-status |  |  | checkpoint | Rust removed
checkpoint-status |  |  | checkpoint | Suitable surface profile
checkpoint-status |  |  | checkpoint | Standing water ice or snow
checkpoint-status |  |  | checkpoint | WB Adhesive turn black
checkpoint-status |  |  | checkpoint | WB Adhesive 6+ hours old
checkpoint-status |  |  | checkpoint | WB Adhesive wide enough
checkpoint-status |  |  | checkpoint | WB Adhesive continuous
checkpoint-status |  |  | checkpoint | WB Adhesive frozen
text | 4e3fdd68-5544-4be7-8967-63f5acd1eafa |  | textbox | Other adhesive name
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Removable forms used
checkpoint-status |  |  | checkpoint | Entire length engaged
checkpoint-status |  |  | checkpoint | Mechanical fasteners
checkpoint-status |  |  | checkpoint | Ends tightly butted
checkpoint-status |  |  | checkpoint | Ends overlapped
checkpoint-status |  |  | checkpoint | Correct Waterstop being used
select | dbb7e8f9-b7ec-44d7-a384-83364eb46bfb |  | dropdown | Waterstop RX being used: | 50m Concrete Cover (Akwaswell 3.8" bead), 75mm Concrete Cover (Akwastop),50mm Concrete Cover (RX 102),75mm Concrete Cover (RX 101)
checkpoint-status |  |  | checkpoint | Voids between concrete and waterstop
checkpoint-status |  |  | checkpoint | Prematrurely hydrated
checkpoint-status |  |  | checkpoint | Placed in keyway
checkpoint-status |  |  | checkpoint | Proper type for conditions
checkpoint-status |  |  | checkpoint | RX grid pattern or protection slab
checkpoint-group |  |  | section | Penetrations
checkpoint-status |  |  | checkpoint | RX around PVC pipes
text | fb80873d-26f4-46d4-bd15-4640cd68dafe |  | textbox | TYPE
checkpoint-status |  |  | checkpoint | RX 102 at 100mm between pipes
checkpoint-status |  |  | checkpoint | Waterstop RX continuous
checkpoint-status |  |  | checkpoint | Ends tightly butted
checkpoint-status |  |  | checkpoint | Adhesive used:
text | 05266e1b-2d48-4192-9925-c35a1112ac65 |  | textbox | Name
checkpoint-status |  |  | checkpoint | Tiewire used
checkpoint-status |  |  | checkpoint | Proper concrete cover
checkpoint-status |  |  | checkpoint | On both sleeve & penetration
checkpoint-group |  |  | section | Pile Caps and Grade Beams
checkpoint-status |  |  | checkpoint | Above waterproofing
checkpoint-status |  |  | checkpoint | Rebar encircled
checkpoint-status |  |  | checkpoint | Waterstop continuous
checkpoint-status |  |  | checkpoint | Ends tightly butted
checkpoint-status |  |  | checkpoint | Proper concrete cover
checkpoint-group |  |  | section | Completion / Handover
checkpoint-status |  |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
holdpoint |  |  | signoff | Raise Remedial / Request Review
checklist-flat |  |  | checklist | Fuko Hose/Water Bar Tunnel Wall/Roof Installation - |  |  |  |  | Yes | QA - Fuko Hose/Water Bar Tunnel Wall/Roof Installation Checklist | 58600011-3d76-4723-855c-1d7fe0765195
checkpoint-status |  |  | checkpoint | Substrate clean and ready to receive the fuko hose
checkpoint-status |  |  | checkpoint | Fuko hose placed
checkpoint-status |  |  | checkpoint | Water bar taped ready for form work
checkpoint-status |  |  | checkpoint | Water bar adhered to form work ready for the concrete
checkpoint-status |  |  | checkpoint | Concrete poured by others
checkpoint-status |  |  | checkpoint | Sign Off
checklist-flat |  |  | checklist | Sikaproof P wall application |  |  |  |  | Yes | QA - Sikaproof P Wall Application Checklist | 5a1e9ef6-256f-4f0d-aa4c-53797b2faaee
checkpoint-status |  |  | checkpoint | Details completed
text | 60eab515-74b1-4774-8901-d390c11b0583 |  | textbox | Pour :
text | 000f694b-5650-41be-ac5a-d4e433866779 |  | textbox | Tunnel :
text | 1c370eb6-d17b-41d9-ab8a-340a02cf799a |  | textbox | Wall :
checkpoint-status |  |  | checkpoint | Check Substrate are all voids filled
checkpoint-status |  |  | checkpoint | Prime the substrate
checkpoint-status |  |  | checkpoint | Apply the sikaproof P
checkpoint-status |  |  | checkpoint | Tape laps with sikaproof EX tape 150
checkpoint-status |  |  | checkpoint | Place termination bar as per the specification where required
checkpoint-status |  |  | checkpoint | Protection layer placed
checkpoint-status |  |  | checkpoint | Final inspection and sign off
checklist-flat |  |  | checklist | Plunge columns infill slab - |  |  |  |  | Yes | QA - Plunge Columns Infill Slab Checklist | 677b238a-6b86-44e5-8ce3-050e1b913900
checkpoint-status |  |  | checkpoint | Gridlines location
checkpoint-status |  |  | checkpoint | Site concrete poured and handover
checkpoint-status |  |  | checkpoint | Geotextile placed
checkpoint-status |  |  | checkpoint | Sikaproof A placed
checkpoint-status |  |  | checkpoint | Place two lines of sika Fix tape 50 and sika swell S2 as per(10.3.21) in the specification
checkpoint-status |  |  | checkpoint | Place termination bar and sarnatape 200
checkpoint-status |  |  | checkpoint | Fix the injection hose in place
checkpoint-status |  |  | checkpoint | Infill slab poured
checkpoint-status |  |  | checkpoint | Sika icosit and Ethafoam installed
checkpoint-status |  |  | checkpoint | Final inspection and handover
checklist-sectioned |  |  | checklist | Hydrotech |  |  |  |  | Yes | QA - Hydrotech Checklist | 69928bf5-5775-4994-9750-bfdd8afa7cb9
checkpoint-group |  |  | section | Project Details
checkpoint-status |  |  | checkpoint | Details Complete:
text | 4814c0c1-0357-481c-90a6-c9ce22df1840 |  | textbox | Project Name:
text | 2bc5e0a0-b73c-477d-a9c4-d76db1a056c5 |  | textbox | Project Address:
text | 8f94c09f-615b-47d3-943e-63a75dcc56e9 |  | textbox | Certified Installer of Hydrotech:
text | b500c2bb-5194-41f8-96ba-ae792c8b222a |  | textbox | Main Contractor:
text | ba2a47c8-6c9e-4645-8d2f-4b748d27c14d |  | textbox | Project Manager:
text | 8ed5fddf-605a-4606-a4d8-5a4c8e380a24 |  | textbox | Project Manager Contact Details:
text | 1f5c4a6a-59d7-4b3b-b140-021e1ad31019 |  | textbox | Key Contact with Main Contractor:
text | d62df92b-ac8a-428a-aede-923fb1c9833a |  | textbox | Total Estimate Quantity of Hydrotech |  |  | m2
text | 345c4458-b1d7-40d6-81d5-2548484f8f88 |  | textbox | Estimated Start Date:
text | 44cc5e73-6805-4d03-b8be-d7258c569c80 |  | textbox | Type of Situation Hydotech is being used in
radio | 88890bf2-02d0-405f-bd6f-3163c8eae4ae |  | radio | Type of Situation Hydrotech is being used in | Blue Roof,Deck,Green,Inverted
text | 47218686-33b3-48b8-aaad-4b819e6de75e |  | textbox | Confirm type of Balas to be used:
button | 1e26ac97-d238-48ce-bc8e-57cc7dcdd075 |  | button | Is this going to be staged work? | No,Yes
text | dee69b5a-40f1-48c8-82bc-beb061c110db |  | textbox | If yes, please provide brief description:
radio | 5ec3be0d-b76f-4d2b-b38b-0cea93948aab |  | radio | How will this be applied? | Both,Pail,Via Kettle
button | d7f3f36e-cf47-4982-85f5-dbd924dd45a6 |  | button | Is the site aware of the size of the Kettle? | No,Yes
button | dc52ad53-bb72-4816-b21f-00b564a9090e |  | button | Is the Site aware of the Hot Works? | No,Yes
button | 1292a33f-7543-4b02-9dc9-2fb3faef5415 |  | button | All parties are aware of the relevant PPE? | No,Yes
checkpoint-group |  |  | section | Substrate Acceptance
checkpoint-status |  |  | checkpoint | Substrate Accepted
button | b9e15bab-befa-4c70-96e9-ac3ff3daa713 |  | button | Is the substrate acceptable being dust & dirt free? | No,Yes
button | 5f697cc6-0923-4103-b0a2-a078a9b9d07e |  | button | Is the substrate acceptable being completely dry | No,Yes
button | adacc18d-75bb-439a-96c7-450f9ab0a367 |  | button | The substrate doesn't exceed the maximum degree in slope to apply | No,Yes
button | fac016e7-93d1-4508-b748-66fd6301a101 |  | button | Substrate bonding test has been completed | No,Yes
button | 57567e29-3aad-40d1-85f5-06495783829d |  | button | Substrate bond test was acceptable | No,Yes
checkpoint-group |  |  | section | Installation of Hydrotech
checkpoint-status |  |  | checkpoint | Installaton Complete
button | c44664e4-4616-4b84-a2e3-69490b653234 |  | button | Weather forecast is acceptable to commence application of Hydrotech | No,Yes
button | 1ebc4b1d-413a-423a-925c-994a6494c6db |  | button | All penetrations have been identified and agreed to | No,Yes
button | 1dbab93d-736b-49cd-8d5f-871fbab643c9 |  | button | All penetrations involved in Hydrotech are detailed accordingly a per specification | No,Yes
button | 252050cb-3cbe-436a-9543-256fc94421ad |  | button | All upstands control joints and penetrations have been identified and prepped (NOTE: Upstands require min 150mm vertically and 75mm horizontally with flex flash x reinforcing) | No,Yes
button | 48323f8a-1dc5-4a96-be40-fbbda95bd90c |  | button | All upstands and details completed | No,Yes
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Installation complete
button | b86d1d88-0ea8-4c70-a439-3fa7398d2229 |  | button | 1st coat of Hydrotech has been successsfully applicated underte correct weather conditions | No,Yes
button | 72636cc9-eec6-4bce-b3f1-4e10cb75b05b |  | button | Evidence of 1st coat being consistently 3mm thick has been provided | No,Yes
button | 8e46de25-3978-4e51-90b7-d4810be9f2ed |  | button | Reinforcement has been successfully embedded into 1st layer of Hydrotech | No,Yes
button | a1313e9e-f42b-4fd1-b6fc-3d1d87eaa35b |  | button | Reinforcement layers has had all air pockets removed | No,Yes
button | 236c45e8-b7ac-4864-89a6-8b939cee4aa3 |  | button | 2nd layer of Hydrotech has been successfully applied | No,Yes
button | 08759f22-4da4-4b5d-ba9f-6364dbe62217 |  | button | Apply protect sheet as final layer | No,Yes
button | 522a09fd-079b-42e4-b0a3-48e362f49f2e |  | button | Check overall thickness and provide evidence using a hydrotech depth gauge being 8mm+ | No,Yes
button | 99117fcf-90c0-4055-83a7-6d28f9dea647 |  | button | Commence istallation of Balas | No,Yes
checklist-sectioned |  |  | checklist | Preprufe Tanking Walls (Vertical) - |  |  |  |  | Yes | QA - Preprufe Tanking Walls (Vertical) Checklist | 6d6205a8-e9e8-4587-9a88-e76b70f6b3a5
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Work area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous substrate/opening acceptable
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | Area (grid lines)
checkpoint-status |  |  | checkpoint | Join wall (vertical) sheets to the underfloor tanking
checkpoint-status |  |  | checkpoint | Tape all laps
checkpoint-status |  |  | checkpoint | Dress Preprufe into ground beam locations
checkpoint-status |  |  | checkpoint | Place adcor 500 T in all construction joints
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area and item left clean and tidy
checkpoint-status |  |  | checkpoint | Final Sign Off
checklist-flat |  |  | checklist | Preprufe 300R walls |  |  |  |  | Yes | QA - Preprufe 300R Walls Checklist | 6f7a5c8e-c173-4846-bdd0-a3418cf13003
checkpoint-status |  |  | checkpoint | Area Specified Below
checkpoint-status |  |  | checkpoint | Geotextile to walls
checkpoint-status |  |  | checkpoint | Preprufe to walls
checkpoint-status |  |  | checkpoint | All laps taped
checklist-sectioned |  |  | checklist | Tanking - Wall Pre-Construction Checklist |  |  |  |  | Yes | QA - Tanking - Wall Pre-Construction Checklist | 73225eb6-37c2-4f1f-9ed7-62c3382365d9
checkpoint-group |  |  | section | Pre-installation QA
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked and referenced
text | af5388dc-956e-48a0-857b-57b98cec6ccd |  | textbox | Relevant drawings & revisions for reference:
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Installation QA
checkpoint-status |  |  | checkpoint | Product being used input
select | b72cd824-5e41-43c9-9e22-dbda330cecdf |  | dropdown | Product name | Other, Preprufe,Voltex
checkpoint-status |  |  | checkpoint | Location where being applied input.
text | d1e4dce7-6853-4dea-bfcd-6a312e2836ee |  | textbox | Area:
checkpoint-status |  |  | checkpoint | Geotextile or coreflute or drainage gecell in place if required
checkpoint-status |  |  | checkpoint | All laps to manufacturer's specifications.
checkpoint-status |  |  | checkpoint | (Voltex DS only) DPC must be removed 100mm minimum for lapping
checkpoint-status |  |  | checkpoint | All water stops installed
checkpoint-status |  |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status |  |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-group |  |  | section | Completion / Handover
checkpoint-status |  |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
holdpoint |  |  | signoff | Raise Remedial / Request Review
checklist-flat |  |  | checklist | Preprufe 300 R Plus Underfloor-Commercial Bay |  |  |  |  | Yes | QA - Preprufe 300 R Plus Underfloor Checklist | 740b3efd-c00c-4def-9e63-7c2166ef2781
checkpoint-status |  | checkpoint-status must be display normal but was flat | checkpoint | Underfloor Area
text | ee4158c3-591d-46af-894b-6e94c4f5330c |  | textbox |  |  | Gridlines
text | 81caa8c0-841f-4c2d-92de-8f81fafd1af8 |  | textbox |  |  | To Grindlines
checkpoint-status |  |  | checkpoint | Site Concrete Handover
checkpoint-status |  |  | checkpoint | Surface Preparation
checkpoint-status |  |  | checkpoint | Lay the sheets out and lap to the specification, provide a 300mm lapping tail at any point of future membrane tie in points
checkpoint-status |  |  | checkpoint | Roll all laps with approved roller
checkpoint-status |  |  | checkpoint | Field Cut Laps- All Field cut laps to be done as per the specification (Detail 10.3.31)
checkpoint-status |  |  | checkpoint | All piles to be detailed as per the specification (Detail 10.3.20)
checkpoint-status |  |  | checkpoint | Construction Joints- All construction joints to be nominated and have Preprufe CJ Tape placed at these locations
checkpoint-status |  |  | checkpoint | Final inspection before hand over, any damage repaired as per the manufacture’s specification (Detail 10.3.37
checkpoint-status |  |  | checkpoint | Reviewed By
checklist-flat | 55406b0a-402b-4a7d-958e-3b4edbbd9769 |  | checklist | Voltex - Area: |  |  |  |  | Yes | QA - Tanking Voltex | 7eaaf799-dabe-4da7-ba47-26abdaa1652b
checkpoint-status | a26521ff-b199-4217-be26-e25129e02542 |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 5814a185-d712-4583-9733-274609cba1c7 |  | checkpoint | Form work acceptable
checkpoint-status | 39031a50-45a5-4c82-8d76-0f70770e546f |  | checkpoint | Voltex installed to wall as per specification
checkpoint-status | 04efb5c2-3c9e-40fd-9e92-39829055a321 |  | checkpoint | Penetration(s) detailed and photo(s) taken of each
checkpoint-status | 741a724b-29b5-408e-b854-8435d5113357 |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat |  |  | checklist | Voltex to Wall Checklist |  |  |  |  | Yes | QA - Voltex to Wall Checklist | 7eb9c84a-2de6-4608-b6c9-b63417ab679b
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-status |  |  | checkpoint | Is lap from capping beam acessable/acceptable
checkpoint-status |  |  | checkpoint | Voltex installed to wall as per specification
checkpoint-status |  |  | checkpoint | Rx Waterbar 101t/bentoseal installed to piles/capping beam
checkpoint-status |  |  | checkpoint | Penetration(s) detailed?
boolean | 8caca995-a7db-4de0-a324-fa6e025b27aa |  | tickbox | Photo taken of each
checkpoint-status |  |  | checkpoint | Area left clean, tidy and rubbish removed
checklist-flat |  |  | checklist | Site Visit Date: |  |  |  |  | Yes | Add Site Visit Checklist | 86054438-e637-435d-8891-501d03e7d9da
checkpoint-status |  |  | checkpoint | Details entered
text | 86734274-df38-49b0-b1c4-5753692d3e5f |  | textbox | Site visit performed by
text | bf0dcb60-603b-45ad-8c14-89a34ae09823 |  | textbox | Site visit completed with / attendees
text | a3cbb780-db9d-4af0-9389-4e957665ad99 |  | textbox | Description of area
checkpoint-status |  |  | checkpoint | Photos taken
checkpoint-status |  |  | checkpoint | General observations and comments
checklist-sectioned |  |  | checklist | Ground Beam Tanking - |  |  |  |  | Yes | QA - Ground Beam Tanking V1 Checklist | 8ce58a64-e1dd-4252-a062-c2019e9aa77c
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Work area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous substrate/opening acceptable
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | Area (grid lines)
checkpoint-status |  |  | checkpoint | Pile tops sealed with epoxy
checkpoint-status |  |  | checkpoint | Preprufe placed and laps taped with Preprufe bedded into LM 3000 on top of piles
checkpoint-status |  |  | checkpoint | Adcor 500 T placed around the top of the pile
checkpoint-status |  |  | checkpoint | Swell seal WA placed around all pile bars
checkpoint-status |  |  | checkpoint | Preprufe lapped and taped to the DPM
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area and item left clean and tidy
checkpoint-status |  |  | checkpoint | Final Sign Off
checklist-flat |  |  | checklist | Swellite Checklist |  |  |  |  | Yes | QA - Swelltite Checklist | 9ba95021-60c8-406b-bcb5-9ae815a3f020
checkpoint-status |  | checkpoint-status must be display normal but was flat | checkpoint | Check the substrate (are there any voids that need filling, if precast panels are all the joints filled).
checkpoint-status |  |  | checkpoint | Check and clean the voltex flap for the swelltite
checkpoint-status |  |  | checkpoint | Apply glue to the wall ready for the swelltite
checkpoint-status |  |  | checkpoint | Place water stoppage granules along the wall floor junction
checkpoint-status |  |  | checkpoint | Measure and cut the drops of swelltite
checkpoint-status |  |  | checkpoint | Hang the drops of swelltite straight
checkpoint-status |  |  | checkpoint | Complete penetrations
checkpoint-status |  |  | checkpoint | Tape the laps
checkpoint-status |  |  | checkpoint | Place the termination bar
checkpoint-status |  |  | checkpoint | Apply cetcoat
checkpoint-status |  |  | checkpoint | Hang protection layer
checkpoint-status |  |  | checkpoint | Complete QA forms
checklist-sectioned |  |  | checklist | Volclay Waterproofing Warranty Request |  |  |  |  | Yes | Warranty Req - Volclay Waterproofing | 9f81f0a9-1b54-4c45-a317-94045598ffec
checkpoint-group |  |  | section | Project Info
checkpoint-status |  |  | checkpoint
text | f32b72be-1c85-4a8b-a4dc-0ae6df8f82df |  | textbox | PROJECT ADDRESS:
text | b7779284-2d4a-4778-9810-6e5d5f7c3919 |  | textbox | PROJECT SIZE (sq m):
text | aaa3f1b7-5b45-45aa-92eb-12c48a2afd56 |  | textbox | PROJECT START DATE:
text | e527bea2-e167-4c47-b9da-f66ed47f0e1b |  | textbox | COMPLETION DATE:
radio | ee80ea34-466c-4746-9416-ee4b6c98f844 |  | radio | HYDROSTATIC HEAD (select one “x”): | No,Yes
text | 256de86b-3466-49a4-8772-5c8c3443d622 |  | textbox | If yes, how many metres?
radio | 0b7ae8aa-953d-49f0-a23e-7eb758d2e373 |  | radio | WARRANTY TYPE (select one “x”): | Product,System
checkpoint-group |  |  | section | OWNER/BUILDER INFORMATION
checkpoint-status |  |  | checkpoint
radio | 66f6a60e-8306-45e6-ab21-41fe5796e631 |  | radio | OWNER/BUILDER INFORMATION (Please indicate which) | Builder,Owner
text | ad991127-23e1-4247-bb3a-8ecc77bc9545 |  | textbox | NAME:
text | 4e903f17-d8d3-4418-b381-8012566631ee |  | textbox | CONTACT:
text | f221abf2-869d-4128-b29b-8ab70ffd0472 |  | textbox | ADDRESS:
text | bc38cd6c-7c52-4af3-b580-662862ba8d5a |  | textbox | PHONE:
text | a60622dd-49fa-4bc2-b089-161cf9c23233 |  | textbox | FAX:
text | ffd53a22-c2ca-4c2f-a6fc-0e4018129992 |  | textbox | EMAIL:
checkpoint-group |  |  | section | APPLICATOR INFORMATION
checkpoint-status |  |  | checkpoint
text | 1e4dac24-bbd7-4a30-a6f1-7e7cd78620cd |  | textbox | APPLICATOR:
text | 95dfa2fa-a05c-47bd-abf1-c9fdb70944ad |  | textbox | CONTACT:
text | 8a1d3dc0-5b45-43fb-8e3a-93097872d480 |  | textbox | ADDRESS:
text | 6dc5bfed-d5d6-429b-ac52-f17f821e426d |  | textbox | PHONE:
text | ce47cbfe-e057-41a2-849a-8b569d44ba4a |  | textbox | FAX:
text | 0a6198cb-076d-4733-a25c-a5cb7f6bebdf |  | textbox | EMAIL:
checkpoint-group |  |  | section | LIST QUANTITY OF FOLLOWING PRODUCTS USED:
checkpoint-status |  |  | checkpoint
label | 521e9da6-768c-4448-b8f4-28a165598d55 |  | note | (Provide sq m, linear metres, litres used) MUST BE COMPLETED
checkpoint-status |  |  | checkpoint | STRATASEAL
boolean | 6329fa78-ff75-4c38-addb-ba8ab46fc93e |  | tickbox | Hot Rubber
checkpoint-status |  |  | checkpoint | SWELLTITE
boolean | 1635afd9-e4d3-4dcb-9d18-24eb29e3f529 |  | tickbox | Swelltite
checkpoint-status |  |  | checkpoint | VOLTEX
boolean | a8cdd8eb-961c-4aa8-a6da-24cee45e14da |  | tickbox | Reg
boolean | 32050cd9-1e23-4183-97e5-ff5d18ccc5cd |  | tickbox | DS
boolean | 06ac9098-3b61-403e-8fe4-3ab7b32a3df5 |  | tickbox | DS/SWR
checkpoint-status |  |  | checkpoint | WATERSTOP-RX
boolean | a5060015-d804-4e33-82a4-116bc61a7c43 |  | tickbox | RX-101
boolean | e70c0d35-07a7-4f7c-baff-c4f95080c065 |  | tickbox | RX-101T
boolean | 53647d95-f281-49de-b301-4e6773fe35b8 |  | tickbox | RX-102
boolean | 125f030b-a495-4e99-a259-c2780b33ce91 |  | tickbox | Cetseal
boolean | 1c7107e7-c0d6-4e78-9d03-9f7002a8bd47 |  | tickbox | Revofix (Mesh)
checkpoint-status |  |  | checkpoint | AQUADRAIN
boolean | 6ab1000c-3d98-42c9-91a4-9adf819effd4 |  | tickbox | 15x
boolean | a047d817-1c21-4b29-a344-b3537d23a704 |  | tickbox | GS310
checkpoint-status |  |  | checkpoint | ULTRASEAL
boolean | 6d6a8127-d73d-44bb-b5db-f24eeebd4ceb |  | tickbox | BT
boolean | 81c3ff04-2adb-45d8-9bfb-5de980d82e45 |  | tickbox | SP
checkpoint-status |  |  | checkpoint | ACCESSORIES
boolean | b85e2793-dfcb-4df9-8b35-b9eb52566304 |  | tickbox | AKWASEAL
boolean | 931839ef-0fb1-488c-9fac-1191d4ada73b |  | tickbox | AKWASTOP
boolean | 55ae410c-ad56-4cd5-9b25-c3edccaa6719 |  | tickbox | BENTOGROUT
boolean | 40e80fe7-0724-4183-ae90-ec6e49b60930 |  | tickbox | BENTOSEAL
boolean | 62d947ed-2533-49e1-8787-3f9995d500d0 |  | tickbox | CETCOAT
boolean | 9f5c06aa-f7b9-497b-b73c-46a0c53b4e09 |  | tickbox | ENVIROSHEET
boolean | cdd3f01b-1704-4346-9b66-945c1f4e5c0f |  | tickbox | ENVIROSHEET LT
boolean | 22bff79f-64e9-4512-9d24-bac157a01252 |  | tickbox | HYDROBAR TUBES
boolean | 166c7d49-b453-4f58-b25f-c0b7eb068122 |  | tickbox | WATERSTOPPAGE
checkpoint-status |  |  | checkpoint | “x” PROJECT TYPE:
boolean | 7b34f4a9-af79-4c10-86de-453cb24410e1 |  | tickbox | Residential
boolean | ee8d4d38-18f8-4048-83ca-e370052bbfd9 |  | tickbox | Apartment
boolean | 6224c1e2-cf6b-4c71-af64-06eb866ee51d |  | tickbox | Commercial Bldg
boolean | fbf99511-d844-422f-97d9-eaeee1ef921c |  | tickbox | Roading
boolean | b6d8bb30-84e7-42d0-bbbc-d186badf5676 |  | tickbox | Educational
boolean | 6599f1c8-c1a4-400b-bb57-8cf1256ea7c3 |  | tickbox | Civil
boolean | 838ba0a5-da86-4c59-afe2-2fea62cf4dab |  | tickbox | Sports facility
boolean | 56920cf8-4def-4e99-96f9-e7490b59af0b |  | tickbox | Hospital
boolean | c55bac9f-4bb0-479f-9c3b-29e23be34833 |  | tickbox | Hotel
checkpoint-status |  |  | checkpoint | “x” CONSTRUCTION APPLICATION(S): (Tick as many as apply) MUST BE COMPLETED
boolean | 2bd51208-c788-423a-abde-3aac82871bb8 |  | tickbox | Backfilled Walls
boolean | 3ad3d041-e3ed-4099-abb4-03d69256ba7c |  | tickbox | Precast Panel
boolean | 3a2b64f5-dc2f-4aad-9f18-bb776fe2135d |  | tickbox | Contiguous Pile Shotcrete
boolean | 5b0254a3-9515-41ae-ac54-c15ae61e29bd |  | tickbox | Insitu Poured Concrete
boolean | 6c5bcde0-5d16-4e31-8bff-75b2bcc84942 |  | tickbox | Grout Injection
boolean | a6e263dc-b9ee-4acd-bbe4-ee2fb4f79b04 |  | tickbox | Injection (urethane)
boolean | 25611f27-2b76-448b-b016-f2684b29557b |  | tickbox | Footings
boolean | ee194a17-de01-42e8-b939-0ddcf6a984fc |  | tickbox | Lift pits
boolean | 0b6bdae1-80da-4d39-ac43-62c0e6cfd5a6 |  | tickbox | Masonry Block Wall
boolean | 6c109d0a-c613-4b19-ae83-5412a1e3848f |  | tickbox | Foundations
boolean | b55ae52a-48f9-4dd0-b830-5c9528eb4f4b |  | tickbox | Plaza Deck
boolean | d9e1b549-b4fc-434c-b481-3d83e6609eab |  | tickbox | Green Roof
boolean | fc016961-8fcb-4fec-a1fe-63fecb8d4130 |  | tickbox | Secant Pile
boolean | 1dcc9401-30e7-4703-b4e4-6e7b9570b52b |  | tickbox | Sheet Piling
boolean | 1c48469d-bdd7-42fb-8eac-4bec60eb85f6 |  | tickbox | Underslab
boolean | 693def54-562b-498f-9002-3934fc11d8be |  | tickbox | Shotcrete Piled Wall
boolean | 73076562-cb41-4837-be99-0d7a498f4a66 |  | tickbox | Split Slab
boolean | 8fee7d17-1dab-41e5-abe7-cfc4e4ee5250 |  | tickbox | Tunnel
boolean | 4fd7c3ca-f65b-4e33-ab11-500d08ae86da |  | tickbox | Underslab
text | 587a602c-9603-4c23-922f-f30bdf56b6c8 |  | textbox | OTHER (Please state)
label | 54c09681-3e68-4ee2-a2c5-c1fc5ac857c1 |  | note | *** Please remember to attach all relevant Quality Assurance photographs*** *** Please note areas on the request that must be completed***
checklist-sectioned |  |  | checklist | Hydrotech Checklist |  |  |  |  | Yes | QA - Hydrotech Checklist (Simple) | a4138519-b009-4020-87ea-1ee7f3366227
checkpoint-group |  |  | section | Substrate Acceptance
checkpoint-status |  |  | checkpoint | Is the area accessible/acceptable?
checkpoint-status |  |  | checkpoint | Is the substrate dust & dirt free?
checkpoint-status |  |  | checkpoint | Is the substrate completely dry
checkpoint-status |  |  | checkpoint | Has the approved primer been applied to substrate
checkpoint-status |  |  | checkpoint | Are substrate falls as per specification
checkpoint-status |  |  | checkpoint | Substrate bonding test has been completed
checkpoint-status |  |  | checkpoint | Substrate bond test was acceptable (if no, seek advice from Allco)
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | All penetrations involved in Hydrotech are detailed accordingly as per specification
checkpoint-status |  |  | checkpoint | All upstands and details completed
checkpoint-status |  |  | checkpoint | 1st coat of Hydrotech has been successsfully applicated underte correct weather conditions
checkpoint-status |  |  | checkpoint | Evidence of 1st coat being consistently 3mm thick has been provided
checkpoint-status |  |  | checkpoint | Reinforcement (Flex Flash F) has been successfully embedded into 1st layer of Hydrotech
checkpoint-status |  |  | checkpoint | 2nd layer of Hydrotech has been successfully applied consistently at 3mm
checkpoint-status |  |  | checkpoint | Apply protection sheet as final layer
checkpoint-status |  |  | checkpoint | Check overall thickness and provide evidence using a hydrotech depth gauge being 8.5mm+
checkpoint-status |  |  | checkpoint | ILD Test Completed
checkpoint-status |  |  | checkpoint | Ballast Installation
checkpoint-status |  |  | checkpoint | XPS board being installed. Correct thickness used.
checklist-sectioned |  |  | checklist | Tanking - Beam and Capping Beam Remedial |  |  |  |  | Yes | QA - Tanking - Beam and Capping Beam Remedial Checklist | a63a53c1-11c6-426c-980e-ddef1218c3f8
checkpoint-group |  |  | section | Pre-installation QA
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked and referenced
text | 09d77e74-a713-4c58-b1cf-6d91a86ed48e |  | textbox | Relevant drawings & revisions for reference:
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Installation QA
checkpoint-status |  |  | checkpoint | Product being used input
select | 6a898b34-6793-4ce8-81ea-982684e4fa60 |  | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
checkpoint-status |  |  | checkpoint | Location where being applied input.
text | 3e9dc8b7-b40c-41fc-a0ba-a33b6838f8cf |  | textbox | Area or pile or beam number:
checkpoint-status |  |  | checkpoint | Protection core flute installed
checkpoint-status |  |  | checkpoint | LM to beam/capping beam/pile
checkpoint-status |  |  | checkpoint | Preprufe embedded to LM
checkpoint-status |  |  | checkpoint | Preprufe installation and all laps and lap tapes done as per manufacturers requirements
checkpoint-status |  |  | checkpoint | All water stops installed
checkpoint-status |  |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status |  |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-group |  |  | section | Completion / Handover
checkpoint-status |  |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
holdpoint |  |  | signoff | Raise Remedial / Request Review
checklist-flat |  |  | checklist | Joint Sealant Checklist |  |  |  |  | Yes | QA - Joint Sealant V1 Checklist | abda218e-1a1a-4e0a-8b60-5479c847bed4
checkpoint-status |  |  | checkpoint | Weather conditions recorded
text | e3e2ac99-0ae8-4ebd-90b4-ce03bc92da5f |  | textbox | Morning
text | 067fd0e4-a365-48de-bdb6-0d6e1314ff05 |  | textbox | Afternoon
checkpoint-status |  |  | checkpoint | Existing sealant removed
checkpoint-status |  |  | checkpoint | Joint edges ground clean
checkpoint-status |  |  | checkpoint | Joint edges clean and free of defects
checkpoint-status |  |  | checkpoint | Joint size between 10 and 40mm wide
checkpoint-status |  |  | checkpoint | PEF rod installed?
checkpoint-status |  |  | checkpoint | Expansion tape installed?
checkpoint-status |  |  | checkpoint | Bond breaker tape installed?
checkpoint-status |  |  | checkpoint | Masked either side of joint?
checkpoint-status |  |  | checkpoint | Primer applied
text | d1c15d5b-0d24-499b-8f8c-f34d5fa85544 |  | textbox | Primer type
text | 7de9421b-8005-4fbe-bf98-81be998a5297 |  | textbox | Batch number (s)
checkpoint-status |  |  | checkpoint | Sealant applied
text | ad261df3-c52a-4d4d-8045-c724b350c2b5 |  | textbox | Sealant type
text | b78e372d-a27e-4c2a-a26a-c17c4e64c7d6 |  | textbox | Batch number (s)
checkpoint-status |  |  | checkpoint | All joint sealant installed correctly, checked & reviewed - as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
checklist-sectioned |  |  | checklist | Crack Injection |  |  |  |  | Yes | QA - Crack Injection Checklist | ada85130-52f3-4194-b2c4-aa5841d7926d
checkpoint-group |  |  | section | Checks
checkpoint-status |  |  | checkpoint | Identity the type of crack and the method of injection required (Polyurethane, Epoxy, Acrylic gel)
checkpoint-status |  |  | checkpoint | Identify if the crack needs to be injected via sirface ports or drilled in borepackers
checkpoint-status |  |  | checkpoint | Mark out ports and borepacker holes
checkpoint-status |  |  | checkpoint | Drill holes and place borepackers
checkpoint-status |  |  | checkpoint | Form surface ports and place surface seal over the crack
checkpoint-status |  |  | checkpoint | Mix and inject material to manufactures specification
checkpoint-status |  |  | checkpoint | Manual injection with caulking gun
checkpoint-status |  |  | checkpoint | Single compenent injection pump
checkpoint-status |  |  | checkpoint | Two component injection pump
checkpoint-status |  |  | checkpoint | Injection clean up
checkpoint-status |  |  | checkpoint | Complete QA documents
checklist-flat |  |  | checklist | F&P - Joint Sealant Checklist |  |  |  |  | Yes | QA - (Fisher&Paykel) - Joint Sealant Checklist | b0619394-d79f-43cc-96e0-4d488c078a11
checkpoint-status |  |  | checkpoint | Panel Joint 10 - 40mm
checkpoint-status |  |  | checkpoint | Substrate Acceptable
checkpoint-status |  |  | checkpoint | Adhesion Testing completed
holdpoint |  |  | signoff | Raise Remedial / Request Sign-Off
checkpoint-status |  |  | checkpoint | Joint sealing - PEF rod installed
checkpoint-status |  |  | checkpoint | Joint sealing - Bond breaker tape installed
checkpoint-status |  |  | checkpoint | Joint sealing - masked either side of joint
checkpoint-status |  |  | checkpoint | Primer applied
select | f250e0f9-a525-4a93-8ede-5d69b610b98d |  | dropdown | Primer Type: | OTHER, Sika Activator-205, Sika Primer-215, TREMprime Silicone Metal Primer, TREMprime Silicone Porous Primer,Sika Primer-3 N
checkpoint-status |  |  | checkpoint | Batch number photographed or input
text | 8d1060c0-b83f-462b-bfe6-89539110a354 |  | textbox | Batch Number:
checkpoint-status |  |  | checkpoint | Sealant applied
select | 75472127-429d-49f0-ae96-3f905b1961a0 |  | dropdown | Sealant Type: | Dymonic FC, OTHER, Sika Blackseal-1, Sika Firerate, SikaHyflex-250 Façade, Sikaflex AT-Façade, Sikaflex MS, Sikaflex Tank N, Sikaflex-400 Fire,Sikaflex-11 FC
checkpoint-status |  |  | checkpoint | Batch number photographed or input
text | 8fc5d202-c596-4f56-b869-59b93f260370 |  | textbox | Batch Number:
checkpoint-status |  |  | checkpoint | Joint Sealant installed correctly, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Site Area - Clean & Tidy
checklist-flat |  |  | checklist | Preprufe 160 Wall Installation |  |  |  |  | Yes | QA - Preprufe 160 Wall Installation Checklist | b3330640-5adc-4c76-b47e-faac8243e199
checkpoint-status |  | checkpoint-status must be display normal but was flat | checkpoint | Underfloor Area
text | ee4158c3-591d-46af-894b-6e94c4f5330c |  | textbox |  |  | Wall Section Grid Line
text | 81caa8c0-841f-4c2d-92de-8f81fafd1af8 |  | textbox |  |  | To Grid Line
checkpoint-status |  |  | checkpoint | Wall hand over as per manufacturers requirements (Flat, Smooth and Plumb)
checkpoint-status |  |  | checkpoint | All Materials Batch
text | 3b041ac3-6e01-4446-a572-f70fcfdc0818 |  | textbox | Batch Numbers:
text | 86735d40-c516-4fed-a6a3-6b8cb6a9bf73 |  | textbox
text | 0864acef-3ad3-4cfc-8028-cac66ed8680a |  | textbox
text | 67d6cd01-3d82-49a7-8763-274bdaebc12e |  | textbox
checkpoint-status |  |  | checkpoint | Protection Core Flute
text | 9ebc5473-5c9b-481a-abfe-9d1447421638 |  | textbox | Installed:
checkpoint-status |  |  | checkpoint | Recorded Temperatures
text | ee8ab58b-5166-4788-97cb-0134ad57a675 |  | textbox | Substrate
text | 462ee049-d234-4abc-917d-aaa28a3c4332 |  | textbox | Ambient
checkpoint-status |  |  | checkpoint | Preprufe Installation and all laps and lap tapes done as per manufacturers requirements
checkpoint-status |  |  | checkpoint | All water stops installed
checkpoint-status |  |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements Take Photos and release To other trades
checkpoint-status |  |  | checkpoint | Preform Work and Pour Final inspection once other trades are finished. Do any required repairs Take photos
checklist-flat |  |  | checklist | Horizontal Stitch Checklist |  |  |  |  | Yes | QA - Horizontal Stitch Checklist | c5e2a07e-97f8-421b-b78b-0395953d5ce0
checkpoint-status |  |  | checkpoint | Work area/substrate is clean, dry and ready to start
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Photograph(s) taken of substrate
checkpoint-status |  |  | checkpoint | Joint width measured
checkpoint-status |  |  | checkpoint | Photograph(s) taken of installed backing (showing sealant)
checkpoint-status |  |  | checkpoint | All joint sealant installed correctly, checked & reviewed - as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
checklist-sectioned |  |  | checklist | Membrane Checklist |  |  |  |  | Yes | QA - Membrane Checklist | c69eceb3-3e8f-4116-9bf7-ecd10129fff6
checkpoint-group |  |  | section | Checks
checkpoint-status |  |  | checkpoint
text | f32b72be-1c85-4a8b-a4dc-0ae6df8f82df |  | textbox | Location:
text | b5bf87b6-db4b-4929-9f45-ce6fb2a67880 |  | textbox | Grid Line:
text | 43e7346d-a5bb-4b85-850f-eb63172e8a50 |  | textbox | Grid Line:
checkpoint-status |  |  | checkpoint | Substrate
checkpoint-status |  |  | checkpoint | Fillets
checkpoint-status |  |  | checkpoint | Flashings
checkpoint-status |  |  | checkpoint | Outlets
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Primer
button | 6d8ea6a4-b4a2-4c27-af04-0dbb7c153151 |  | button | Batch completed | No,Yes
button | db1eda6e-468f-4d57-956b-a6e7604fd469 |  | button | 80mm side lap | No,Yes
button | 8c2ea70e-0f61-4eef-9f60-4446cbefa772 |  | button | 100mm end lap | No,Yes
checkpoint-status |  |  | checkpoint | 1st Layer
button | dd241f46-111e-4a45-aa74-9033a32ce391 |  | button | Batch Completed | No,Yes
button | faf4731a-a12b-4d26-9530-65663b25b77f |  | button | 80mm side lap | No,Yes
button | 2bfc1f01-ee9b-4b37-b77b-2997cba86685 |  | button | 100mm end lap | No,Yes
checkpoint-status |  |  | checkpoint | 2nd Layer
button | 00430a57-050b-4440-bf7b-8a85ab8f6963 |  | button | Batch completed | No,Yes
button | 4ccb7bce-6c74-47a9-b946-f35f46b36378 |  | button | 80mm side lap | No,Yes
button | 56a45469-aa02-40b1-a0dd-71b4922b8754 |  | button | 100mm end lap | No,Yes
checkpoint-status |  |  | checkpoint | EFVM Test or Flood Test
button | f45a317d-7cb0-443a-9dc6-fae0d4fcde00 |  | button | Batch completed | No,Yes
button | 38d1718c-757d-4195-90f0-d6c14208ad11 |  | button | 80mm side lap | No,Yes
button | 34e72513-3deb-4917-92fa-8b2136841999 |  | button | 100mm end lap | No,Yes
checklist-sectioned |  |  | checklist | Preprufe Tanking Underfloor - |  |  |  |  | Yes | QA - Preprufe Tanking Underfloor Checklist | d419c2cb-cc76-4012-ba4a-747aa13bb6ba
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Work area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous substrate/opening acceptable
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | Area (grid lines)
checkpoint-status |  |  | checkpoint | Pile tops sealed with epoxy
checkpoint-status |  |  | checkpoint | Preprufe placed and laps taped with Preprufe bedded into LM 3000 on top of piles
checkpoint-status |  |  | checkpoint | Adcor 500 T placed around top of pile
checkpoint-status |  |  | checkpoint | Swell seal WA placed around all pile bars
checkpoint-status |  |  | checkpoint | CJ tape placed at construction joint locations
checkpoint-status |  |  | checkpoint | Preprufe lapped and tapped to the DPM
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area and item left clean and tidy
checkpoint-status |  |  | checkpoint | Final Sign Off
checklist-sectioned |  |  | checklist | Pile - |  |  |  |  | Yes | QA - Pile Cap Detailing Checklist | d4b6b96a-5569-436b-96fc-eb1610381a1e
checkpoint-group |  |  | section | Steps
checkpoint-status |  |  | checkpoint | Pile Cap Handover
checkpoint-status |  |  | checkpoint | Diameter
text | ee4158c3-591d-46af-894b-6e94c4f5330c |  | textbox |  |  | Specified diameter of pile
text | 81caa8c0-841f-4c2d-92de-8f81fafd1af8 |  | textbox |  |  | Actual diameter of pile
checkpoint-status |  |  | checkpoint | Surface Preparation (type) (Grind Flush only)
checkpoint-status |  |  | checkpoint | No Breakdown included
label | 58317d78-4f67-4077-902f-4fd51e624351 |  | note | (If required, request Site Instruction)
checkpoint-status |  |  | checkpoint | CEM 100 Grout
checkpoint-status |  |  | checkpoint | EP 75 Epoxy
checkpoint-status |  |  | checkpoint | LM 3000 Bedding
checkpoint-status |  |  | checkpoint | Bituthene 3000 - (Side of Pile)
checkpoint-status |  |  | checkpoint | Termination Bar
checkpoint-status |  |  | checkpoint | LM 3000 Termination
checkpoint-status |  |  | checkpoint | Protection Placed
checkpoint-status |  |  | checkpoint | Backfilled with Site Concrete (By Others)
checkpoint-status |  |  | checkpoint | Bituthene 3000 cut, patched (Detailing)
checkpoint-status |  |  | checkpoint | Bituthene 3000 & Preprufe Tape (Top of Pile)
checkpoint-status |  |  | checkpoint | LM 3000 to reinforcing bars
checkpoint-status |  |  | checkpoint | Swellseal - Mastic (10mm Bead) To Bars
checkpoint-status |  |  | checkpoint | Adcor 500T (75mm min cover) with Swellseal Mastic
checkpoint-status |  |  | checkpoint | S Felt Protection
checkpoint-status |  |  | checkpoint | Preprufe 300 lapped
checkpoint-status |  |  | checkpoint | Sealed with LM 3000
checkpoint-status |  |  | checkpoint | Concrete poured on (By Others)
checkpoint-status |  |  | checkpoint | Pile Cap No:
checkpoint-status |  |  | checkpoint | Reviewed by:
checklist-sectioned |  |  | checklist | Tanking - Pile Remedial Checklist |  |  |  |  | Yes | QA - Tanking - Pile Remedial Checklist | d672ee24-3816-420b-9268-3d731e67805c
checkpoint-group |  |  | section | Pre-installation QA
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked and referenced
text | 3b298c73-38ee-4d6e-95f4-fab23f015cbe |  | textbox | Relevant drawings & revisions for reference:
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Installation QA
checkpoint-status |  |  | checkpoint | Product being used input
select | 51012b58-62ac-419d-9018-57e2ccbf9d6c |  | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
checkpoint-status |  |  | checkpoint | Location where being applied input.
text | 1b1bc4c9-c797-409a-83f4-e0abf79539fe |  | textbox | Area or pile number:
checkpoint-status |  |  | checkpoint | Protection core flute installed
checkpoint-status |  |  | checkpoint | LM to pile
checkpoint-status |  |  | checkpoint | Preprufe embedded to LM
checkpoint-status |  |  | checkpoint | Preprufe installation and all laps and lap tapes done as per manufacturers requirements
checkpoint-status |  |  | checkpoint | All water stops installed
checkpoint-status |  |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status |  |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-group |  |  | section | Completion / Handover
checkpoint-status |  |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
holdpoint |  |  | signoff | Raise Remedial / Request Review
checklist-sectioned |  |  | checklist | Tanking - Underfloor Checklist |  |  |  |  | Yes | Tanking - Underfloor Checklist | ddb2f01b-cf7d-4cfe-8d0e-0691112cf318
checkpoint-group |  |  | section | Pre-installation QA
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked and referenced
text | 4dd61b41-1e18-406c-822b-88ba53a0d930 |  | textbox | Relevant drawings & revisions for reference:
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Installation QA
checkpoint-status |  |  | checkpoint | Product being used input
select | 4560de98-7339-4444-b33c-227cb409044c |  | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
checkpoint-status |  |  | checkpoint | Location where being applied input.
text | 20d893f0-1c05-40c7-8e2e-f8e3ff9da96a |  | textbox | Area:
checkpoint-status |  |  | checkpoint | Geotextile in place if required
checkpoint-status |  |  | checkpoint | All laps to manufacturer's specifications.
checkpoint-status |  |  | checkpoint | (Voltex DS only) DPC must be removed 100mm minimum for lapping
checkpoint-status |  |  | checkpoint | Penetrations are detailed as to manufacturer's specification
checkpoint-status |  |  | checkpoint | All water stops installed
checkpoint-status |  |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status |  |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-group |  |  | section | Completion / Handover
checkpoint-status |  |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
holdpoint |  |  | signoff | Raise Remedial / Request Review
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | e51c83eb-7065-4666-be13-f0d992ab059c
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  | Invalid dependant | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  | Invalid dependant | signoff | Request Variation Signoff
checklist-flat |  |  | checklist | Voltex to GB. Date/Area: |  |  |  |  | Yes | QA - Voltex to Ground Beams | ec20a3af-e6e7-4b39-88ec-fa7edb5a8f12
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-status |  |  | checkpoint | Form work acceptable
checkpoint-status |  |  | checkpoint | Voltex installed to wall as per specification
checkpoint-status |  |  | checkpoint | Penetration(s) detailed and photo(s) taken of each
checkpoint-status |  |  | checkpoint | Area left clean, tidy and rubbish removed
checkpoint-status |  |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-sectioned |  |  | checklist | Pile Detail Checklist |  |  |  |  | Yes | QA - Pile Detailing Checklist | ee2269f2-961f-4f1d-bca3-a72e6374c405
checkpoint-group |  |  | section | Checks
checkpoint-status |  |  | checkpoint | Pile number and handover / Specified size and actual size
checkpoint-status |  |  | checkpoint | Pile preparation Grind / water blast
checkpoint-status |  |  | checkpoint | Two layers of sikadur-32 along the top of the pile for a total of 2mm thickness minimum
checkpoint-status |  |  | checkpoint | Install Sarna Tape 200 to the face of the pile extending down 100mm leave the release paper on the top half
checkpoint-status |  |  | checkpoint | Secure the bottom edge of the saran tape with termination bar sealed with Sikadur-31
checkpoint-status |  |  | checkpoint | Sikaswell A waterstop placed between the sikaproof A and the steel reinforcing
checkpoint-status |  |  | checkpoint | Sikaswell A wrapped around all perimeter reinforcing bars
checklist-sectioned |  |  | checklist | Coreflex Pre-Installation Checklist |  |  |  |  | Yes | QA - Coreflex Pre-Installation Checklist | f18e5130-8d01-4964-ae0e-8c814c3c7f84
checkpoint-group |  |  | section | Pre-Installation Meeting
checkpoint-status |  |  | checkpoint | Installer information input
text | d9c63a1b-632e-4adc-be57-4250b663c7a2 |  | textbox | Name
text | c7f8e538-ae16-4eae-a3c4-cdc4628eed72 |  | textbox | Email
checkpoint-status |  |  | checkpoint | Installer has signed on screen
checkpoint-group |  |  | section | General Substrate Requirements
checkpoint-status |  |  | checkpoint | Concrete substrate must be uniform smooth finish with 19mm max sized aggregate to be used
checkpoint-status |  |  | checkpoint | No sharp edge aggregate to protrude through the smooth substrate layer.
checkpoint-status |  |  | checkpoint | Acceptable weather for application.
checkpoint-status |  |  | checkpoint | Substrate must be free of debris (windy conditions need to be accounted for)
checkpoint-status |  |  | checkpoint | No standing water to be present where application is to take place
checkpoint-status |  |  | checkpoint | No ice to be present
checkpoint-status |  |  | checkpoint | Weather forecase must be monitored to ensure substrate doesn't become compromised
checklist-sectioned |  |  | checklist | Tanking - Wall Post-Construction |  |  |  |  | Yes | QA - Tanking - Wall Post-Construction Checklist | f9dd3dd5-1332-43ac-afbb-0a58c7640b02
checkpoint-group |  |  | section | Pre-installation QA
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked and referenced
text | 7701fb48-4769-4353-b72a-ffdad594269b |  | textbox | Relevant drawings & revisions for reference:
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Installation QA
checkpoint-status |  |  | checkpoint | Product being used input
select | 6e0b0b81-af62-4e96-b652-c75549c9fb66 |  | dropdown | Product name | Bituthene 3000, Other,Swelltite
checkpoint-status |  |  | checkpoint | Location where being applied input.
text | 50905c3f-3854-4476-a7e9-691c38484fde |  | textbox | Area:
checkpoint-status |  |  | checkpoint | Check the substrate (are there any voids that need filling, if precast panels are all the joints filled).
checkpoint-status |  |  | checkpoint | Check and clean flap.
checkpoint-status |  |  | checkpoint | Material installed as per manufacturer's specification.
checkpoint-status |  |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status |  |  | checkpoint | Complete penetrations
checkpoint-status |  |  | checkpoint | Tape the laps
checkpoint-status |  |  | checkpoint | Place the termination bar
checkpoint-status |  |  | checkpoint | Cetcoat applied
checkpoint-status |  |  | checkpoint | Protection layer installed
checkpoint-status |  |  | checkpoint | Drainage installed and 100mm away from wall
checkpoint-group |  |  | section | Completion / Handover
checkpoint-status |  |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
holdpoint |  |  | signoff | Raise Remedial / Request Review