## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Colphene Uni NG Capping Beam
section | Details
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | SOW description entered
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate Acceptance
button | Blinding installed to acceptable surface uniformity (photos attached below) | Yes,No
button | Pile tops prepared to acceptable surface uniformity (photos attached below) | Yes,No
button | Substrate free from pooling or ponding water (photos attached below) | Yes,No
checkpoint | Colphene Uni NG Around Pile
button | Colphene Uni NG installed tightly around pile (photos attached below) | Yes,No
checkpoint | Epoxy Fillet
button | Epoxy fillet of Alsan EPM installed to junction of pile over Colphene Uni NG (photos attached below) | Yes,No
checkpoint | Junction Reinforcement
button | Reinforcement strip of Colphene Uni NG fully torched to corner junction of capping beam. Half width of reinforcement will sit inside formwork, half width outside formwork. (photos attached below) | Yes,No
select | Reinforcement width of Colphene Uni NG | 200mm,300mm,400mm,500mm,Greater than 500mm
checkpoint | Flashing Over Pile
button | Alsan Flashing with Alsan reinforcement over pile and lapped onto membrane around pile (photos attached below) | Yes,No
select | Lap size of flashing Colphene Uni NG | 50mm,100mm,150mm,200mm
checkpoint | Torching to Side of Capping Beam
button | Concrete of acceptable surface uniformity to install fully torched membrane (photos attached below) | Yes,No
button | Colphene Uni NG fully torched to side of capping beam (Record batch and install photos) | Yes,No
button | Sopradrain 20 drainage cell installed to side of capping beam (Record batch and install photos) | Yes,No
checkpoint | Gasket Installation
select | Gasket responsibility | Bravada,Client,N/A
button | If Bravada responsibility, is gasket installed to manufacturer's specification? (Record batch and install photos) | Yes,No
checkpoint | Area completed to manufacturer's specification? - photos attached below