## Template
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Instruction to CONQA | Checklist Name
Beon - Lauriston Solar Farm J#40140
Frame Construction
|  |  |  | Frame Construction | please add: | Frame Construction
Floor, Duct Penetrations and Vents
|  |  |  | Floor, Duct Penetrations and Vents | please add: | Floor, Duct Penetrations and Vents
Cable Support
Cable Support
|  |  |  | Cable Support | please add: | Cable Support
Cable Support ITR's
|  |  | Cable Tray | ITR-E-02B Cable Supports Above Ground | please add: | ITR-E-02B Cable Supports Above Ground
|  |  | Cable Transit | ITR-E-02C Cable Transits | please add: | ITR-E-02C Cable Transits
Earthing
Earthing Checklist
|  |  |  | Earthing | please add: | Earthing
Copper Bar
|  |  |  | ITR-E-12 Electrical Earthing | please add: | ITR-E-12 Electrical Earthing
|  |  |  | ITR-E-40 Bus Bar | please add: | ITR-E-40 Bus Bar
|  |  |  | ITR-E-63 Cable Lug Installation | please add: | ITR-E-63 Cable Lug Installation
Cubicles
|  |  |  | ITR-E-12 Electrical Earthing | please add: | ITR-E-12 Electrical Earthing
|  |  |  | ITR-E-40 Bus Bar | please add: | ITR-E-40 Bus Bar
|  |  |  | ITR-E-63 Cable Lug Installation | please add: | ITR-E-63 Cable Lug Installation
Other Earthing
|  |  |  | ITR-E-12 Electrical Earthing | please add: | ITR-E-12 Electrical Earthing
|  |  |  | ITR-E-40 Bus Bar | please add: | ITR-E-40 Bus Bar
|  |  |  | ITR-E-63 Cable Lug Installation | please add: | ITR-E-63 Cable Lug Installation
Lighting, Power & Data
Lighting
|  |  | Control Room & Emergency Lighting | ITR-E-64 General Lighting | please add: | ITR-E-64 General Lighting
|  |  | Switchroom and Emergency Lighting | ITR-E-64 General Lighting | please add: | ITR-E-64 General Lighting
|  |  | External Lights | ITR-E-64 General Lighting | please add: | ITR-E-64 General Lighting
|  |  | Exit Lights | ITR-E-64 General Lighting | please add: | ITR-E-64 General Lighting
|  |  | Flood Lights | ITR-E-64 General Lighting | please add: | ITR-E-64 General Lighting
Power
|  |  | Control Room Socket Outlet 1PH | ITR-E-01 General Electrical Equipment | please add: | ITR-E-01 General Electrical Equipment
|  |  | Switchroom Socket Outlet 1PH | ITR-E-01 General Electrical Equipment | please add: | ITR-E-01 General Electrical Equipment
|  |  | External Control Room Socket 1PH | ITR-E-01 General Electrical Equipment | please add: | ITR-E-01 General Electrical Equipment
|  |  | External Control Room Outlet 3PH | ITR-E-01 General Electrical Equipment | please add: | ITR-E-01 General Electrical Equipment
|  |  | Switchroom Outlet 3PH | ITR-E-01 General Electrical Equipment | please add: | ITR-E-01 General Electrical Equipment
HVAC
|  |  | AC01 | ITR-E-68 HVAC System | please add: | ITR-E-68 HVAC System
|  |  | AC02 | ITR-E-68 HVAC System | please add: | ITR-E-68 HVAC System
|  |  | AC03 | ITR-E-68 HVAC System | please add: | ITR-E-68 HVAC System
|  |  | AC04 | ITR-E-68 HVAC System | please add: | ITR-E-68 HVAC System
Fire Protection
|  |  | Fire Detection System | ITR-E-69 Fire Detection System | please add: | ITR-E-69 Fire Detection System
|  |  | FIP- Fire Indication Panel | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
Equipment and Install
Switchboards
|  |  | J01 - Incomer 1 | ITR-E-34 Low Voltage Switch Board | please add: | ITR-E-34 Low Voltage Switch Board
|  |  | J02 - Incomer 2 | ITR-E-34 Low Voltage Switch Board | please add: | ITR-E-34 Low Voltage Switch Board
|  |  | J03 - Incomer 3 | ITR-E-34 Low Voltage Switch Board | please add: | ITR-E-34 Low Voltage Switch Board
|  |  | J04 - Bus Earth and Bus VT | ITR-E-34 Low Voltage Switch Board | please add: | ITR-E-34 Low Voltage Switch Board
|  |  | J05 - Feeder 1 | ITR-E-34 Low Voltage Switch Board | please add: | ITR-E-34 Low Voltage Switch Board
|  |  | J06 - Feeder 2 | ITR-E-34 Low Voltage Switch Board | please add: | ITR-E-34 Low Voltage Switch Board
|  |  | J07 - Feeder 3 | ITR-E-34 Low Voltage Switch Board | please add: | ITR-E-34 Low Voltage Switch Board
|  |  | J08 - HF Feeder | ITR-E-34 Low Voltage Switch Board | please add: | ITR-E-34 Low Voltage Switch Board
|  |  | AC1 - AC Main Switchboard | ITR-E-34 Low Voltage Switch Board | please add: | ITR-E-34 Low Voltage Switch Board
Distribution Boards
|  |  | AC2 - AC Distribution Board | ITR-E-03 Entec - Distribution Board Installation | please add: | ITR-E-03 Entec - Distribution Board Installation
|  |  |  | ITR-E-04 Schedule of Test Results DB | please add: | ITR-E-04 Schedule of Test Results DB
Control Panels
|  |  | PPC - PPC Cabinet | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
|  |  | FS1 - Metering Cubicle | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
|  |  | FS2 - EA Protection Cubicle | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
|  |  | FS3 - Beon Protection Cubicle | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
|  |  | FS6 - Beon Metering and RTU Cabinet | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
|  |  | FS7 - Beon Metering and RTU Cabinet | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
|  |  | FS8 - Dispatch Cubicle/Genisis | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
|  |  | FS9 - OPUSV Comms Cubicle | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
|  |  | FS10 - OPUSV Comms Cubicle | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
|  |  | FS11 - FRV Cubicle (ISOTROL) | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
|  |  | GPS - GPS Antenna Earthing Interface Enclosure | ITR-E-06 Control Panel | please add: | ITR-E-06 Control Panel
Batteries
|  |  | DC11 - X String DC Distribution and Battery Charger | ITR-E-03 Entec - Distribution Board Installation | please add: | ITR-E-03 Entec - Distribution Board Installation
|  |  |  | ITR-E-04 Schedule of Test Results DB | please add: | ITR-E-04 Schedule of Test Results DB
|  |  | DC21 - Y String DC Distribution and Battery Charger | ITR-E-03 Entec - Distribution Board Installation | please add: | ITR-E-03 Entec - Distribution Board Installation
|  |  |  | ITR-E-04 Schedule of Test Results DB | please add: | ITR-E-04 Schedule of Test Results DB
Stairs and Platform
|  |  |  | Stairs and Platforms | please add: | Stairs and Platforms
Final Approval
|  |  | CoC | Certificate of compliance (COC) | please add: | Certificate of compliance (COC)
|  |  | Final Checklist | ITR-E-67 Final Checklist for PPR | please add: | ITR-E-67 Final Checklist for PPR
|  |  | Test Equipment | (Tester Name) | please add: | Test Equipment Details:
|  |  |  | (Tester Name) | please add: | Test Equipment Details:
|  |  |  | (Tester Name) | please add: | Test Equipment Details:
Cables
Control Cables
|  |  | C1 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C2 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C3 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C4 | 2.5mm2 8C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C5 | 2.5mm2 12C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C6 | 2.5mm2 12C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C7 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C9 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C10 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C11 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C12 | 2.5mm2 8C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C13 | 2.5mm2 12C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C14 | 2.5mm2 12C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C15 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C17 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C18 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C19 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C20 | 2.5mm2 8C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C21 | 2.5mm2 12C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C22 | 2.5mm2 12C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C23 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C25 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C26 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C27 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C28 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C29 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C30 | 2.5mm2 12C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C32 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C33 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C34 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C35 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C36 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C37 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C38 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C39 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C41 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C42 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C43 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C44 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C45 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C46 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C48 | 6mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C49 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C50 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C51 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C52 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C53 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C55 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C56 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C57 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C58 | 12C Data cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C59 | 2.5mm2 2C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C60 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C61 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C62 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C64 | 12C Data cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C65 | 35mm2 4C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C66 | 16mm2 4C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C67 | 10mm2 4C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C68 | 10mm2 4C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C69 | 2.5mm2 2C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C70 | 2.5mm2 2C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C71 | 2.5mm2 2C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C73 | 12C Data cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C74 | 35mm2 1C HFS/PVC (Red) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C75 | 35mm2 1C HFS/PVC (Blk) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C76 | 35mm2 1C HFS/PVC (Red) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C77 | 35mm2 1C HFS/PVC (Blk) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C78 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C79 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C80 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C83 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C84 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C85 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C88 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C89 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C90 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C91 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C92 | 35mm2 1C HFS/PVC (Red) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C93 | 35mm2 1C HFS/PVC (Blk) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C94 | 35mm2 1C HFS/PVC (Red) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C95 | 35mm2 1C HFS/PVC (Blk) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C96 | 2.5mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C97 | 2.5mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C99 | 12C Data cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C100 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C101 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C102 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C105 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C106 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C107 | 6mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C111 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C112 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C113 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C114 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C115 | 35mm2 1C HFS/PVC (Red) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C116 | 35mm2 1C HFS/PVC (Blk) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C117 | 35mm2 1C HFS/PVC (Red) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C118 | 35mm2 1C HFS/PVC (Blk) |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C119 | 2.5mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C120 | 2.5mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C122 | 2.5mm2 8C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C124 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C125 | 2C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C127 | 2.5mm2 8C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C128 | 2.5mm2 4C PVC/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C129 | 2.5mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C130 | 2.5mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C131 | 2.5mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C132 | 4C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C133 | 4C Data Cable PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C134 | 2.5mm2 2C XLPE/HFS |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C136 | 2.5mm2 2C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C137 | 2.5mm2 2C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C138 | 2.5mm2 2C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C139 | 2.5mm2 2C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | C140 | 2.5mm2 2C+E XLPE/PVC |  | ITR-E-05 - Low Voltage and Control Cable
COMMS Cables
|  |  | COM1 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM2 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM3 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM4 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM5 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM6 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM7 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM8 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM9 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM10 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM11 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM12 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM15 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM16 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM17 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM18 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM19 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM20 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM21 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM22 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM23 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM24 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM25 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM26 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM27 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM28 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM29 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM32 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM33 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM34 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM35 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM36 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM37 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM38 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM39 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM40 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM41 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM42 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM43 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM44 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM45 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM46 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM47 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM50 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM51 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM54 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM55 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM60 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM61 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM62 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM63 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM64 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM65 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM66 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM67 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM68 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM69 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM70 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM71 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM72 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM73 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM74 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM75 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM76 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM77 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM78 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM79 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM80 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM81 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM82 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM83 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM84 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM85 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM86 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM87 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM88 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM89 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM90 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM91 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM92 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM93 | COAXIAL CABLE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM94 | COAXIAL CABLE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM95 | COAXIAL CABLE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM97 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM98 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM99 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM100 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM101 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM102 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM103 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM104 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM105 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM106 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM107 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM108 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM109 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM110 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM111 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM112 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM113 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM114 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM115 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM116 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM117 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM118 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM119 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM120 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM121 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM122 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM124 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM125 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM126 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM127 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM128 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM129 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM130 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM131 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM132 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM133 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM134 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM135 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM136 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM137 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM138 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM139 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM140 | 8 CORE CAT6 - SOLID CORE U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM141 | 8 CORE SCREENED CAT6 - STRANDED U/UTP |  | ITR-E-29 Cat 6 Communication Cable
|  |  | COM150 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM151 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM152 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM153 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM154 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM155 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM156 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM157 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM158 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM159 | OM4 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM160 | OM3 LOOSE TUBE FIBRE OPTIC CABLE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM161 | OM3 LOOSE TUBE FIBRE OPTIC CABLE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM162 | 8 CORE PVC-SCR-PVC |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM181 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM182 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM183 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM184 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM185 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM187 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM188 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM189 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM191 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM192 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM193 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM194 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM195 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM197 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM198 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM199 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM201 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM202 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM203 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM204 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM206 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM207 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM208 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM211 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM212 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM213 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM214 | OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS1/01 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS1/02 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS1/03 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS1/04 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS1/05 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS2/01 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS2/02 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS2/03 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS2/04 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS2/05 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS3/01 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS3/02 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS3/03 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS3/04 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS3/05 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS4/01 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS4/02 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS4/03 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS4/04 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS4/05 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS5/01 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS5/02 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS5/03 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS5/04 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS6/01 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS6/02 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS6/03 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS6/04 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS7/01 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS7/02 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS7/03 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS7/04 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS7/05 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS8/01 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS8/02 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS8/03 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS8/04 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
|  |  | COM/STS8/05 | OS2 OPTIC FIBRE |  | ITR-E-05 - Low Voltage and Control Cable
Note on G17: Johno Carswell: May need extra details around copper bar. Customise the ITR perhaps?
Note on G21: Johno Carswell: May need extra details around copper bar. Customise the ITR perhaps?
Note on G25: Johno Carswell: May need extra details around copper bar. Customise the ITR perhaps?

## Checklist
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name
checklist | ITR-E-64 General Lighting
Checkpoint | General Lighting
textbox | Manufacturer:
textbox | Model No:
textbox | Serial and Tag Numbers:
button | Check equipment and nameplate details are correct and in accordance with the data sheet and Equipment Schedule. | Yes,N/A
button | No mechanical damage and paintwork in good condition. | Yes,N/A
button | Operation of emergency lighting fixtures checked | Yes,N/A
button | Mounting arrangement and degree unit is installed is correct | Yes,N/A
button | External cabling is correctly installed and labelled. | Yes,N/A
button | Battery run-down test per manufacturers specification | Yes,N/A
button | Power / load balance on distribution board checked | Yes,N/A
button | Operation of remote lighting control checked | Yes,N/A
button | All spare entries blanked off with correct plugs. | Yes,N/A
button | Check item is suitably rated for area (E.g. IP rating, Ex rating) | Yes,N/A
button | Conforms to Specifications and Drawings. | Yes,N/A
button | Insulation resistance of final sub-circuits checked | Yes,N/A
button | Operation of photo-electric cell control checked | Yes,N/A
button | Lighting pole is adequately earthed | Yes,N/A
button | Circuit ID fitted to all light switches | Yes,N/A
button | All fittings correctly labelled | Yes,N/A
button | All switching tested and confirmed as correct (two way, intermediate, on/off/auto etc | Yes,N/A
mandatory photo | Insert Photo
button | As-Built drawings completed | Yes,N/A
checkpoint | Lux Levels
button | Lux levels meet minimum client specifications. (Closed door and measure lux level at darkest point of personnel accessible area) | Yes,N/A
textbox | Lux Results:
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-01 General Electrical Equipment
checkpoint | General Electrical Equipment
textbox | Tag Numbers:
button | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule. | Yes,N/A
button | No mechanical damage and paintwork in good condition. | Yes,N/A
button | Installation is clean and tidy | Yes,N/A
button | Mounting arrangement correct | Yes,N/A
button | All internal cabling and wiring correctly installed and labelled. | Yes,N/A
button | External cabling is correctly installed and labelled. | Yes,N/A
button | Check that Equipment is correctly earthed. | Yes,N/A
button | Check gland, plate, frame & door earth continuity | Yes,N/A
button | All spare entries blanked off with correct plugs. | Yes,N/A
button | Check item is suitably rated for area (E.g. IP rating, Ex rating) | Yes,N/A
button | Conforms to Specifications and Drawings. | Yes,N/A
mandatory photo | Insert Photo
button | As-builts complete. | Yes,N/A
checkpoint | Electrical Checks
textbox | Record test results: Insulation Resistance, Continuity, Bonding, Other. |  |  | MegaOhms
signoff | Installed by:
checklist | ITR-E-69 Fire Detection System
checkpoint | Fire Detection System
button | Fire Panel ITR has been completed | Yes,N/A
textbox | Tag Numbers:
button | Smoke alarms have been installed as per specification | Yes,N/A
button | Smoke alarms are ALL operational | Yes,N/A
button | Alarm speaker has been installed per specifications | Yes,N/A
button | Alarm speaker is operational | Yes,N/A
button | Fire alarm beacon has been installed per specification | Yes,N/A
button | Fire alarm beacon is operational | Yes,N/A
button | Manual call point has been installed per specification | Yes,N/A
button | Manual call point is operational | Yes,N/A
button | Installations are all unobstructed | Yes,N/A
button | No mechanical damage and paintwork in good condition. | Yes,N/A
button | All installations have identification tags | Yes,N/A
button | All internal cabling and wiring correctly installed and labelled. | Yes,N/A
button | E.O.L has been installed as is operational | Yes,N/A
textbox | Other fire system installations have been installed correctly:
button | As-builts complete. | Yes,N/A
checkpoint | Functional Check
textbox | Selt test:
textbox | Alarm Operation:
textbox | Fault relay operation:
textbox | Measured output (clear path):
textbox | Measured output (blocked path):
textbox | Measured output (filter in place):
checkpoint | Upload QA pack from fire alarm installers
textbox | Confirm ENTEC witness of installers testing
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-06 Control Panel
checkpoint | Control Panel
button | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule. | Yes,N/A
button | Check holding down/mounting arrangement is correct. | Yes,N/A
button | Check for mechanical damage. | Yes,N/A
button | Check tightness of circuit connections. | Yes,N/A
button | All internal cabling and wiring is correctly numbered, colour coded and terminated | Yes,N/A
button | Ammeter scale and current transformer correct. | Yes,N/A
button | Check internals for cleanliness. | Yes,N/A
button | Check manual operation of selector switches, MCB, push buttons, etc. | Yes,N/A
button | Incoming cables correctly glanded, terminated and labelled. Unused entries sealed with correct plug | Yes,N/A
button | Heaters correctly installed. | Yes,N/A
button | Fuse rating correct. | Yes,N/A
mandatory photo | Insert Photo
button | As-builts complete. | Yes,N/A
checkpoint | Electrical Checks
textbox | Record test results: Insulation Resistance, Continuity, Bonding, Other.
signoff | Installed by:
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-03 Entec - Distribution Board Installation
checkpoint - Mandatory photo | Distribution Board Installation
button | Inspect for mechanical damage from freight and handling | Yes,N/A
button | Check tag number is in accordance with Electrical Equipment List, Document No. and nameplate details correct. | Yes,N/A
button | Check type, size and number of breakers is correct as per drawings | Yes,N/A
button | Ensure there is no visible damage to the equipment and all meters, LED indicators, switches and fittings are in good order. | Yes,N/A
button | Confirm main isolator operates with associated switches and auxiliaries | Yes,N/A
button | Check equipment panel external and internal earthing connections are securely fitted and properly terminated on the cabinet protective earth bar. | Yes,N/A
button | Check DB, sub circuits, DB Legend and internal cables correctly labelled. As Built drawings complete | Yes,N/A
button | Check sealing of all cable penetration (where applicable). | Yes,N/A
button | Active, Neutral and Earth bar properly identified and labelled | Yes,N/A
button | Confirm panel is readily accessible for inspection and maintenance. | Yes,N/A
checkpoint | Test Results
textbox | Insulation Resistance (Eg. P-P, P-N, P-E, N-E) |  |  | MegaOhms
textbox | Earth Continuity |  |  | Ohms
textbox | Earth Bond |  |  | Ohms
textbox | Fault Loop Impedance, PSSC.
textbox | RCD Test results (1/2x I, 1x I, 5x I)
textbox | Voltage and Phase Rotation
button | As-builts complete. | Yes,N/A
signoff | Installed by:
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-04 Schedule of Test Results DB
checkpoint | Upload completed ITR scans
signoff | Installed by:
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-34 Low Voltage Switch Board
Checkpoint | Low Voltage Switch Board
button | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule. | Yes,N/A
button | Check holding down/mounting arrangement is correct. | Yes,N/A
button | Check for mechanical damage. | Yes,N/A
button | Confirm that all temporary supports, jumpers and ties have been removed. | Yes,N/A
button | Incoming cables correctly installed, terminated and supported. | Yes,N/A
button | Phase identification correct. | Yes,N/A
button | Confirm that padlocking facilities are provided and operate correctly allowing all circuit breakers to be locked in the open position and safety shutters locked in the closed position. | Yes,N/A
button | Confirm all cubicle doors can be opened without obstruction and minimum required clearances are retained | Yes,N/A
textbox | Bus bar alignment to manufacturer's specification and connecting links tight to specified torque.
button | Confirm components, fuses etc. correctly sized and identified as per design drawings and Single Line Diagrams. | Yes,N/A
button | Instruments, indication lamps and interlocks correct. | Yes,N/A
button | Ammeter and current transformer correctly installed. | Yes,N/A
button | Check internals for cleanliness. | Yes,N/A
button | Check that Switchboard is correctly earthed. Check door, escutcheon, gland plate, gland and frame. | Yes,N/A
textbox | Test and confirm the earth resistance between switchboard and local earth system is less than 0.5ohms
button | All internal cabling and wiring neat, correct, and undamaged. | Yes,N/A
button | Unused cable entry sealed. | Yes,N/A
button | Heaters correctly installed. | Yes,N/A
button | Confirm that all insulating bushings and barriers are satisfactory. | Yes,N/A
Checkpoint | Check Busbar insulation resistance between earth and phases. For a duration of 60 seconds with the following voltages. System KV Test V (dc) Min IR Reading <1.0 500 10 MΩ <2.5 1000 50 MΩ < 4.6 2500 100 MΩ >4.6 5000 250 MΩ
textbox | L1 - Earth |  |  | mega ohms
textbox | L2 - Earth |  |  | mega ohms
textbox | L3 - Earth |  |  | mega ohms
textbox | L1 - L2 |  |  | mega ohms
textbox | L1 - L3 |  |  | mega ohms
textbox | L2 - L3 |  |  | mega ohms
textbox | N - Earth |  |  | mega ohms
mandatory photo | Insert Photo
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-68 HVAC System
checkpoint | HVAC System
textbox | Model:
textbox | Manufacturer:
textbox | Serial and Tag Numbers:
button | No mechanical damage and paintwork is in good condition | Yes,N/A
button | Operation of units verified | Yes,N/A
button | Mounting arrangement is correct | Yes,N/A
button | External cabling is correctly installed and labelled | Yes,N/A
button | HVAC unit isolator is installed and operational | Yes,N/A
button | Remote holders are installed with remotes inside them | Yes,N/A
button | Units are labelled with appropriate ID’s | Yes,N/A
button | Check item is suitably rated for area (E.g. IP rating, Ex rating) | Yes,N/A
button | Conforms to Specifications and Drawings | Yes,N/A
button | Any applicable control system configuration has been checked and is functional as per design | Yes,N/A
checkpoint | Upload QA pack from HVAC installers
textbox | Confirm ENTEC witness of installers testing
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-32 Battery
Checkpoint | Batteries
button | Check equipment and nameplate details are correct in accordance with the data sheet and drawings | Yes,N/A
button | Transportation packing and plugs removed | Yes,N/A
button | Battery cells correctly rated and numbered accordingly | Yes,N/A
button | All cells correctly mounted, links tight and shrouds fitted | Yes,N/A
button | Internal cables correctly installed | Yes,N/A
button | Protection of live parts correct and adequate | Yes,N/A
button | Electrolyte level correct in each cell | Yes,N/A
button | Check specific gravity in each battery cell | Yes,N/A
button | Check cleanliness of cells and battery racks | Yes,N/A
button | Verify approved grease applied to battery terminals | Yes,N/A
button | Earthing correct and tight | Yes,N/A
textbox | Verify polarity correct per drawings and record voltage
textbox | Perservation as per supplier instructions
button | Leave equipment with any isolators and/or circuit breakers switched and locked in the off position | Yes,N/A
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-02B Cable Supports Above Ground
checkpoint | Cable Supports Above Ground
button | Verify cable support has been installed as per relevant drawings, and is correct size and type. | Yes,N/A
button | Check all machined parts cut or drilled have no rough edges, have been de-burred & protected by cold galvanising to restore the previous protection. | Yes,N/A
button | All covers fitted if applicable. | Yes,N/A
button | Check cable support structures are adequately fixed and present no hazard to personnel. | Yes,N/A
button | Welded support brackets have been wire-brushed and painted to completion. | Yes,N/A
button | Splice plates, barriers, earthing system secure. | Yes,N/A
button | Trays / ladders, supports, brackets not interfering with other disciplines. | Yes,N/A
button | Check bends do not exceed the maximum cable bending radius. | Yes,N/A
button | Cables have adequate mechanical protection as and where required. | Yes,N/A
button | Inspect for system rigidity, and check levels to correct plane. | Yes,N/A
button | Earth bonding straps have been fitted to any sections that are split, hinged or flexible. | Yes,N/A
button | Tray bonded to structure at correct locations. | Yes,N/A
button | Earth bonding continuity tested – record result: | Yes,N/A
button | As-builts complete. | Yes,N/A
signoff | Installed by:
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-02C Cable Transits
checkbox | Cable Transits
button | Transit frame installed as per drawings. | Yes,N/A
button | Transit frame identification marked correctly and visible. | Yes,N/A
button | Frame correctly packed with correct sized blocks and infills. | Yes,N/A
button | Correct stay plates fitted (non-ferrous for single core power cables.) | Yes,N/A
button | Rated insulation installed to transit (where required.) | Yes,N/A
button | Cables entering and leaving transits adequately supported and protected. | Yes,N/A
button | Cables pass through frames without strain on blocks. | Yes,N/A
button | All cables identified on both sides of transit and visible. | Yes,N/A
button | As-builts complete. | Yes,N/A
signoff | Installed by:
signoff | Client Representative:
checklist | Cable Test Record
checkpoint | Upload completed ITR scans
checklist | Certificate of compliance (COC)
checkpoint | Please upload Certificate of Compliance here when complete (COC)
checklist | ITR-E-67 Final Checklist for PPR
checkpoint | Interior Checklist
button | All floor, wall & ceiling penetrations sealed. | Yes,N/A
button | All equipment has been installed | Yes,N/A
button | All loose items in panels have been secured or removed | Yes,N/A
button | Illuminated exit signs installed & operational | Yes,N/A
button | All doors and locks operational (including emergency) | Yes,N/A
button | Ensure each cable has an ID tag | Yes,N/A
button | Distribution board legend inside door | Yes,N/A
button | All appropriate signage and labelling are visible – warning stickers | Yes,N/A
button | Panels and boards have appropriate ID tags on exterior | Yes,N/A
button | All doors secured through secondary means, e.g. taped shut or tied to gland plate | Yes,N/A
button | All panels and boards locked | Yes,N/A
button | Room Interior is clean and suitable for presentation to client | Yes,N/A
checkpoint-mandatory photo | Upload photo of interior
checkpoint | Misc Equipment Supplied by Entec
button | Fire Extingishers x2 | Yes,N/A
button | Fire Extinguishers are bubble wrapped and safely secured for transportation | Yes,N/A
button | First Aid Kit | Yes,N/A
button | HVAC Controllers | Yes,N/A
button | Desk and chairs | Yes,N/A
button | Equipment cupboard | Yes,N/A
button | LV rescue kit | Yes,N/A
button | Emergency Eye wash station | Yes,N/A
checkpoint | Exterior Checklist
button | Container Exterior is undamaged, e.g. paintwork intact | Yes,N/A
button | Earth Boss correctly installed and connected | Yes,N/A
button | Stairs have been verified to correctly suit container | Yes,N/A
button | Stairs are available and ready for transportation | Yes,N/A
checkpoint-mandatory photo | Upload photo of exterior
checkpoint | Final Checklist
button | All other ITR’s have been completed | Yes,N/A
button | As-Built drawings completed and signed off | Yes,N/A
button | All keys available handed to client representataive or project manager | Yes,N/A
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | Test Equipment Details:
checkpoint | Details
textbox | Make
textbox | Model
textbox | Serial No
textbox | Calibration Expiry Date
checklist | ITR-E-12 Electrical Earthing |  | ITR-E-12 Electrical Earthing
checkpoint | Electrical earthing system installation
button | Confirm earth grid layout, earth conductors/connections and number of earth electrodes is in accordance with drawings, drawings as-built | Yes,N/A
button | Ensure that all metal work is earthed as required. | Yes,N/A
button | Check welding of earth bosses and associated surface finish. | Yes,N/A
button | Ensure that earth cables/conductors/electrodes have adequate mechanical protection i.e. conduits, tobys, kick-plates etc at points of high exposure. | Yes,N/A
button | Ensure that brazing or welding of all joints has been completed correctly. | Yes,N/A
button | Ensure that adequate corrosion and weather protection has been installed around all connections, joints, lugs, cad (thermal) welds and earth bosses | Yes,N/A
button | All earth bosses and studs tight and fitted with shake proof washers and coated with protective coating. | Yes,N/A
button | Check cable terminations/joints to ensure that all lugs/barrels have been crimped correctly. | Yes,N/A
button | Check that all bi-metal connections have been performed correctly to manufacturer’s requirements. | Yes,N/A
button | Ensure that the earth cables to the main earth electrodes are terminated at each end of the main earth bar. | Yes,N/A
button | Ensure that earth cable identification markings are in place. | Yes,N/A
button | Ensure that earth connections are not multi-coiled or ‘pig-tailed’ but are terminated as straight as possible. | Yes,N/A
button | Check earth bar fixings, mounting points and terminations are tight and secure and conform to project specification (if applicable) | Yes,N/A
checkpoint | Test Results
textbox | Earth continuity test results (Earth bar to Electrode, Grid, etc - please specify)
textbox | 3-Wire earth test results (If applicable).
textbox | Earth grid test results (if applicable). (HV earth grid, LV earth grid, combined earth grids)
checklist | ITR-E-11 Generator Package (LV)
checkpoint | Generator Package (LV)
button | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule. | Yes,N/A
button | No mechanical damage and paintwork in good condition. | Yes,N/A
button | Check terminal boxes and glanding correct. | Yes,N/A
button | Instruments correctly installed. | Yes,N/A
button | Heaters correctly installed. | Yes,N/A
button | Check unit for cleanliness. | Yes,N/A
button | Check manual operation of selector switches, MCB, push buttons etc. | Yes,N/A
button | External cabling correctly installed. | Yes,N/A
button | Protection of live parts adequate. | Yes,N/A
button | Main terminal box complete and terminations correct torque. | Yes,N/A
button | Ensure direction of rotation is clearly marked. | Yes,N/A
button | Check gasket and seals are not damaged. | Yes,N/A
button | Unused cable entries are correctly sealed. | Yes,N/A
button | As-builts complete | Yes,N/A
checkpoint | Electrical Checks
textbox | Record test results: Insulation Resistance, Continuity, Bonding, Other.
textbox | Heater circuit insulation resistance:
signoff | Installed by:
signoff | Client Representative:
checklist | Frame Construction
checkpoint | Frame Construction
button | Baseplate layout as per drawing specififcation | Yes,N/A
mandatory photo | Photo of Baseplate
button | Removeable Padeyes in place | Yes,N/A
mandatory photo | Photo of removeable padeyes
button | Floor/room layout as per drawing | Yes,N/A
mandatory photo | Photo of floor/room layout
button | Compressed cement board used | Yes,N/A
mandatory photo | Photo of floor board
button | Frame construction adhering to all general steel work notes as per latest drawings | Yes,N/A
button | Baseplate is free from damage and paintwork is intact | Yes,N/A
checkpoint | Add QA pack from blast and paint
checkpoint | Add QA pack from fabricators
button | As-Built drawings completed and signed off | Yes,N/A
signoff | Frame Construction checked by:
signoff | Client Representative:
checklist | Floor, Duct Penetrations and Vents
checkpoint | Floor, Duct Penetrations and Vents
button | Floor cable penetrations arrangement as per latest drawings | Yes,N/A
mandatory photo | Photo of floor cable penetrations
button | Battery Cabinet Ventilations as per drawings | Yes,N/A
mandatory photo | Photo of battery cabinet ventilation points
button | Fresh air intake installed for the control room as per drawings. | Yes,N/A
mandatory photo | Photo of fresh air intake
button | Ventilation point for the switchroom insatlledas per drawings | Yes,N/A
mandatory photo | Photo of ventilation point
button | Switch board arc vent installed and located as per drawings | Yes,N/A
mandatory photo | Photo of switchboard arc
button | Warning signs installed | Yes,N/A
mandatory photo | Photo of warning signs
Textbox | Deflection Check - (+/-) 1mm tolerance in any 1 metre radius & a tolerance of (+/-) 3mm over the length of the switchroom. Record results:
button | As-Built drawings completed and signed off | Yes,N/A
signoff | Floor, Duct Penetrations checked by:
signoff | Client Representative:
checklist | Cable Support
checkpoint | Cable Support
button | Cable ladder installed | Yes,N/A
mandatory photo | Photo of cable ladder
button | Vertical UT-3 Uni tray installed where required to allow cable access into cabinets | Yes,N/A
mandatory photo | Photo of tray
button | Fibre/comms duct insatlled | Yes,N/A
mandatory photo | Photo of fibre/comms duct
button | Fire wall penetrations go through fire sleeves | Yes,N/A
mandatory photo | Photo of fire wall penetrations
signoff | Cable Supports checked by:
signoff | Client Representative:
checklist | Earthing
checkpoint | Earthing
button | 50mmx10mm copper earth bar installed on cable ladder as per design | Yes,N/A
mandatory photo | Photo of copper bar
button | All cubicles connected to earth bar using 35mm2 Cu earth bond | Yes,N/A
mandatory photo | Photo of cubicles connected to earth bar
button | All doors have flat tinned copper braid earth straps fitted | Yes,N/A
mandatory photo | Photo of doors with copper braid
button | Earth bar penetrates floor | Yes,N/A
mandatory photo | Photo of earth bar
button | As-Built drawings completed and signed off | Yes,N/A
signoff | Earthing checked by:
signoff | Client Representative:
checklist | ITR-E-40 Bus Bar
checkpoint | Bus Bar
button | Check entire Bus Bar and confirm there is no damage | Yes,N/A
note | Please attatch photo of Bus Bar
button | Bus Bar alignment is correct | Yes,N/A
button | Confirm all jointing bolts are present and have been torque tested in accordance with the manufacturer and design requirements. Acceptable Bus Bar Torque Settings: Bolt: M6 M8 M10 M12 M16 Torque: 10Nm 20Nm 30Nm 40Nm 60Nm | Yes,N/A
button | Confirm all transit packing and preservation materials have been removed. | Yes,N/A
button | Confirm Bus Bar clearances conform to manufactures and design requirements. | Yes,N/A
button | Confirm all Bus Bars are secure within the supports. | Yes,N/A
textbox | Record the total number of bus bar joints.
checkpoint | Test Results:
textbox | Results:
signoff | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-63 Cable Lug Installation
checkpoint | Cable lug
button | Appropriate lug for cable size has been used. | Yes,N/A
button | Lug has been correctly seated with no loose copper strands outside of lug. | Yes,N/A
button | Lug has been crimped with 60 tonne crimper. | Yes,N/A
button | Joint sealing paste has been correctly applied to the contact surface of lug | Yes,N/A
checkpoint | Bolts
button | Bolt has been torqued to manufacturers requirements | Yes,N/A
note | If no manufacturer torque spec, use torques below. M8-20NM, M10-40NM, M12-70NM.
textbox | Manufacturers torque requirement (if applicable)
checkpoint | Test Results
textbox | Continuity test results
textbox | Ductor test results if applicable
checkpoint | Test Equipment Used
textbox | Description
textbox | Manufacturer
textbox | Model No:
textbox | Serial No:
signoff | All relevant signatures (Installed by, Approved by, Client Representative)
checklist | Lighting, Power and Data
checkpoint | Lighting Power and Data
button | Internal and external lighting installed as per drawings
button | Exit and emergency lighting installed as per drawing
button | Power and data installed as per drawing
button | As-Built drawings completed and signed off
signoff | Lighting, Power and Data checked by:
signoff | Client Representative:
checklist | Stairs and Platforms
checkpoint | Stairs and Platforms
button | Stair and platform frames as per drawings with 38mm FRP Grating for platform and PT6 stair treads 275mm wide
mandatory photo | Photo of stairs and platform frames
button | Edge of each step and edge of platform has high contrast, non-slip proprietary nosing
mandatory photo | Photo of nosing
button | Handrail system installed either side of the steps and around edges of platforms
mandatory photo | Photo of handrails
button | As-Built drawings completed and signed off
signoff | Stairs and Platforms checked by:
signoff | Client Representative:
checklist-flat | ITR-E-05 - Low Voltage and Control Cable
checkpoint | Low Voltage Cable
button | Verify cable type, size, colour code and tags are in accordance with the Cable Schedule. | Yes,N/A
button | Check dressing / cleating, cable undamaged | Yes,N/A
button | Bending radius satisfactory | Yes,N/A
button | Check cable cores correctly identified and labelled. | Yes,N/A
button | Cable terminated with correct lugs and crimped with the correct die. | Yes,N/A
button | Check Armour / Screen correctly made off. | Yes,N/A
button | Check armour continuity / earthing is maintained by the correct use of serrated washers and / or earth tags (if applicable) | Yes,N/A
textbox | From:
textbox | To:
button | Glanding / Locknuts correctly installed. | Yes,N/A
textbox | Gland type - from: |  | Haz. Area Rating
textbox | Haz. Area Cert Details.
textbox | Gland type - to: |  | Haz. Area Rating
textbox | Haz. Area Cert Details.
textbox | Confirm spare cores and shields are terminated and conform to drawings and client spec.
checkpoint | Electrical Checks
textbox | Record test results: Insulation Resistance, Continuity, Bonding, Other.
signoff | Installed by:
signoff | Client Representative:
checklist-flat | ITR-I-21A - Instrument and Control Cables
checkpoint | Instrument Cable
button | Verify cable type, size, colour code and tags are in accordance with the Cable Schedule. | Yes,N/A
button | Check dressing / cleating, cable undamaged | Yes,N/A
button | Bending radius satisfactory | Yes,N/A
button | Check cable cores correctly identified and labelled. | Yes,N/A
button | Cable terminated with correct lugs and crimped with the correct die. | Yes,N/A
button | Check Armour / Screen correctly made off. | Yes,N/A
button | Check armour continuity / earthing is maintained by the correct use of serrated washers and / or earth tags (if applicable) | Yes,N/A
textbox | From:
textbox | To:
button | Glanding / Locknuts correctly installed. | Yes,N/A
textbox | Gland type - from: |  | Haz. Area Rating
textbox | Haz. Area Cert Details.
textbox | Gland type - to: |  | Haz. Area Rating
textbox | Haz. Area Cert Details.
textbox | Confirm spare cores and shields are terminated and conform to drawings and client spec.
checkpoint | Electrical Checks
textbox | Record test results: Insulation Resistance, Continuity, Bonding, Other.
signoff | Installed by:
signoff | Client Representative:
checklist-flat | ITR-E-29 Cat 6 Communication Cable
checkpoint | Common to all circuits
button | check cable for damage | Yes, N/A
button | Check cable is correctly identified and labelled | Yes, N/A
button | Check glanding/locknuts correctly installed | Yes, N/A
button | Confirm cable routing and segregation is correct | Yes, N/A
button | Confirm to and from destination as per design. | Yes, N/A
checkpoint | Data Circuits
button | Check cable terminated with correct crimps | Yes, N/A
button | Check sheild/screen correctly made off | Yes, N/A
button | Check Cat6 end-to-end certification (outlet and cable) | Yes, N/A
signoff | Installed by: | Yes, N/A
signoff | Client Representative: | Yes, N/A