## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITR-E-64 General Lighting
section | Details
checkpoint | General Lighting
textbox | Manufacturer:
textbox | Model No:
textbox | Serial and Tag Numbers:
button | Check equipment and nameplate details are correct and in accordance with the data sheet and Equipment Schedule. | Yes,N/A
button | No mechanical damage and paintwork in good condition. | Yes,N/A
button | Operation of emergency lighting fixtures checked | Yes,N/A
button | Mounting arrangement and degree unit is installed is correct | Yes,N/A
button | External cabling is correctly installed and labelled. | Yes,N/A
button | Battery run-down test per manufacturers specification | Yes,N/A
button | Power / load balance on distribution board checked | Yes,N/A
button | Operation of remote lighting control checked | Yes,N/A
button | All spare entries blanked off with correct plugs. | Yes,N/A
button | Check item is suitably rated for area (E.g. IP rating, Ex rating) | Yes,N/A
button | Conforms to Specifications and Drawings. | Yes,N/A
button | Insulation resistance of final sub-circuits checked | Yes,N/A
button | Operation of photo-electric cell control checked | Yes,N/A
button | Lighting pole is adequately earthed | Yes,N/A
button | Circuit ID fitted to all light switches | Yes,N/A
button | All fittings correctly labelled | Yes,N/A
button | All switching tested and confirmed as correct (two way, intermediate, on/off/auto etc | Yes,N/A
checkpoint | Insert Photo
button | As-Built drawings completed | Yes,N/A
checkpoint | Lux Levels
button | Lux levels meet minimum client specifications. (Closed door and measure lux level at darkest point of personnel accessible area) | Yes,N/A
textbox | Lux Results:
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-01 General Electrical Equipment
section | Details
checkpoint | General Electrical Equipment
textbox | Tag Numbers:
button | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule. | Yes,N/A
button | No mechanical damage and paintwork in good condition. | Yes,N/A
button | Installation is clean and tidy | Yes,N/A
button | Mounting arrangement correct | Yes,N/A
button | All internal cabling and wiring correctly installed and labelled. | Yes,N/A
button | External cabling is correctly installed and labelled. | Yes,N/A
button | Check that Equipment is correctly earthed. | Yes,N/A
button | Check gland, plate, frame & door earth continuity | Yes,N/A
button | All spare entries blanked off with correct plugs. | Yes,N/A
button | Check item is suitably rated for area (E.g. IP rating, Ex rating) | Yes,N/A
button | Conforms to Specifications and Drawings. | Yes,N/A
checkpoint | Insert Photo
button | As-builts complete. | Yes,N/A
checkpoint | Electrical Checks
textbox | Record test results: Insulation Resistance, Continuity, Bonding, Other. |  |  | MegaOhms
holdpoint | Installed by:
checklist | ITR-E-69 Fire Detection System
section | Details
checkpoint | Fire Detection System
button | Fire Panel ITR has been completed | Yes,N/A
textbox | Tag Numbers:
button | Smoke alarms have been installed as per specification | Yes,N/A
button | Smoke alarms are ALL operational | Yes,N/A
button | Alarm speaker has been installed per specifications | Yes,N/A
button | Alarm speaker is operational | Yes,N/A
button | Fire alarm beacon has been installed per specification | Yes,N/A
button | Fire alarm beacon is operational | Yes,N/A
button | Manual call point has been installed per specification | Yes,N/A
button | Manual call point is operational | Yes,N/A
button | Installations are all unobstructed | Yes,N/A
button | No mechanical damage and paintwork in good condition. | Yes,N/A
button | All installations have identification tags | Yes,N/A
button | All internal cabling and wiring correctly installed and labelled. | Yes,N/A
button | E.O.L has been installed as is operational | Yes,N/A
textbox | Other fire system installations have been installed correctly:
button | As-builts complete. | Yes,N/A
checkpoint | Functional Check
textbox | Selt test:
textbox | Alarm Operation:
textbox | Fault relay operation:
textbox | Measured output (clear path):
textbox | Measured output (blocked path):
textbox | Measured output (filter in place):
checkpoint | Upload QA pack from fire alarm installers
textbox | Confirm ENTEC witness of installers testing
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-06 Control Panel
section | Details
checkpoint | Control Panel
button | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule. | Yes,N/A
button | Check holding down/mounting arrangement is correct. | Yes,N/A
button | Check for mechanical damage. | Yes,N/A
button | Check tightness of circuit connections. | Yes,N/A
button | All internal cabling and wiring is correctly numbered, colour coded and terminated | Yes,N/A
button | Ammeter scale and current transformer correct. | Yes,N/A
button | Check internals for cleanliness. | Yes,N/A
button | Check manual operation of selector switches, MCB, push buttons, etc. | Yes,N/A
button | Incoming cables correctly glanded, terminated and labelled. Unused entries sealed with correct plug | Yes,N/A
button | Heaters correctly installed. | Yes,N/A
button | Fuse rating correct. | Yes,N/A
checkpoint | Insert Photo
button | As-builts complete. | Yes,N/A
checkpoint | Electrical Checks
textbox | Record test results: Insulation Resistance, Continuity, Bonding, Other.
holdpoint | Installed by:
checkpoint | Add applicable signatures
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-03 Entec - Distribution Board Installation
section | Details
checkpoint | Distribution Board Installation
button | Inspect for mechanical damage from freight and handling | Yes,N/A
button | Check tag number is in accordance with Electrical Equipment List, Document No. and nameplate details correct. | Yes,N/A
button | Check type, size and number of breakers is correct as per drawings | Yes,N/A
button | Ensure there is no visible damage to the equipment and all meters, LED indicators, switches and fittings are in good order. | Yes,N/A
button | Confirm main isolator operates with associated switches and auxiliaries | Yes,N/A
button | Check equipment panel external and internal earthing connections are securely fitted and properly terminated on the cabinet protective earth bar. | Yes,N/A
button | Check DB, sub circuits, DB Legend and internal cables correctly labelled. As Built drawings complete | Yes,N/A
button | Check sealing of all cable penetration (where applicable). | Yes,N/A
button | Active, Neutral and Earth bar properly identified and labelled | Yes,N/A
button | Confirm panel is readily accessible for inspection and maintenance. | Yes,N/A
checkpoint | Test Results
textbox | Insulation Resistance (Eg. P-P, P-N, P-E, N-E) |  |  | MegaOhms
textbox | Earth Continuity |  |  | Ohms
textbox | Earth Bond |  |  | Ohms
textbox | Fault Loop Impedance, PSSC.
textbox | RCD Test results (1/2x I, 1x I, 5x I)
textbox | Voltage and Phase Rotation
button | As-builts complete. | Yes,N/A
holdpoint | Installed by:
checkpoint | Add applicable signatures
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-04 Schedule of Test Results DB
section | Details
checkpoint | Upload completed ITR scans
holdpoint | Installed by:
checkpoint | Add applicable signatures
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-34 Low Voltage Switch Board
section | Details
checkpoint | Low Voltage Switch Board
button | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule. | Yes,N/A
button | Check holding down/mounting arrangement is correct. | Yes,N/A
button | Check for mechanical damage. | Yes,N/A
button | Confirm that all temporary supports, jumpers and ties have been removed. | Yes,N/A
button | Incoming cables correctly installed, terminated and supported. | Yes,N/A
button | Phase identification correct. | Yes,N/A
button | Confirm that padlocking facilities are provided and operate correctly allowing all circuit breakers to be locked in the open position and safety shutters locked in the closed position. | Yes,N/A
button | Confirm all cubicle doors can be opened without obstruction and minimum required clearances are retained | Yes,N/A
textbox | Bus bar alignment to manufacturer's specification and connecting links tight to specified torque.
button | Confirm components, fuses etc. correctly sized and identified as per design drawings and Single Line Diagrams. | Yes,N/A
button | Instruments, indication lamps and interlocks correct. | Yes,N/A
button | Ammeter and current transformer correctly installed. | Yes,N/A
button | Check internals for cleanliness. | Yes,N/A
button | Check that Switchboard is correctly earthed. Check door, escutcheon, gland plate, gland and frame. | Yes,N/A
textbox | Test and confirm the earth resistance between switchboard and local earth system is less than 0.5ohms
button | All internal cabling and wiring neat, correct, and undamaged. | Yes,N/A
button | Unused cable entry sealed. | Yes,N/A
button | Heaters correctly installed. | Yes,N/A
button | Confirm that all insulating bushings and barriers are satisfactory. | Yes,N/A
checkpoint | Check Busbar insulation resistance between earth and phases. For a duration of 60 seconds with the following voltages.
label | – – – – – – – – – – – – – – –
label | System KV ¦¦ Test V (dc) ¦¦ Min IR Reading
label | – – – – – – – – – – – – – – –
label | < 1.0 ¦¦ 500 ¦¦ 10 MΩ
label | < 2.5 ¦¦ 1000 ¦¦ 50 MΩ
label | < 4.6 ¦¦ 2500 ¦¦ 100 MΩ
label | > 4.6 ¦¦ 5000 ¦¦ 250 MΩ
label | – – – – – – – – – – – – – – –
textbox | L1 - Earth |  |  | mega ohms
textbox | L2 - Earth |  |  | mega ohms
textbox | L3 - Earth |  |  | mega ohms
textbox | L1 - L2 |  |  | mega ohms
textbox | L1 - L3 |  |  | mega ohms
textbox | L2 - L3 |  |  | mega ohms
textbox | N - Earth |  |  | mega ohms
checkpoint | Insert Photo
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-68 HVAC System
section | Details
checkpoint | HVAC System
textbox | Model:
textbox | Manufacturer:
textbox | Serial and Tag Numbers:
button | No mechanical damage and paintwork is in good condition | Yes,N/A
button | Operation of units verified | Yes,N/A
button | Mounting arrangement is correct | Yes,N/A
button | External cabling is correctly installed and labelled | Yes,N/A
button | HVAC unit isolator is installed and operational | Yes,N/A
button | Remote holders are installed with remotes inside them | Yes,N/A
button | Units are labelled with appropriate ID’s | Yes,N/A
button | Check item is suitably rated for area (E.g. IP rating, Ex rating) | Yes,N/A
button | Conforms to Specifications and Drawings | Yes,N/A
button | Any applicable control system configuration has been checked and is functional as per design | Yes,N/A
checkpoint | Upload QA pack from HVAC installers
textbox | Confirm ENTEC witness of installers testing
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-32 Battery
section | Details
checkpoint | Batteries
button | Check equipment and nameplate details are correct in accordance with the data sheet and drawings | Yes,N/A
button | Transportation packing and plugs removed | Yes,N/A
button | Battery cells correctly rated and numbered accordingly | Yes,N/A
button | All cells correctly mounted, links tight and shrouds fitted | Yes,N/A
button | Internal cables correctly installed | Yes,N/A
button | Protection of live parts correct and adequate | Yes,N/A
button | Electrolyte level correct in each cell | Yes,N/A
button | Check specific gravity in each battery cell | Yes,N/A
button | Check cleanliness of cells and battery racks | Yes,N/A
button | Verify approved grease applied to battery terminals | Yes,N/A
button | Earthing correct and tight | Yes,N/A
textbox | Verify polarity correct per drawings and record voltage
textbox | Perservation as per supplier instructions
button | Leave equipment with any isolators and/or circuit breakers switched and locked in the off position | Yes,N/A
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-02B Cable Supports Above Ground
section | Details
checkpoint | Cable Supports Above Ground
button | Verify cable support has been installed as per relevant drawings, and is correct size and type. | Yes,N/A
button | Check all machined parts cut or drilled have no rough edges, have been de-burred & protected by cold galvanising to restore the previous protection. | Yes,N/A
button | All covers fitted if applicable. | Yes,N/A
button | Check cable support structures are adequately fixed and present no hazard to personnel. | Yes,N/A
button | Welded support brackets have been wire-brushed and painted to completion. | Yes,N/A
button | Splice plates, barriers, earthing system secure. | Yes,N/A
button | Trays / ladders, supports, brackets not interfering with other disciplines. | Yes,N/A
button | Check bends do not exceed the maximum cable bending radius. | Yes,N/A
button | Cables have adequate mechanical protection as and where required. | Yes,N/A
button | Inspect for system rigidity, and check levels to correct plane. | Yes,N/A
button | Earth bonding straps have been fitted to any sections that are split, hinged or flexible. | Yes,N/A
button | Tray bonded to structure at correct locations. | Yes,N/A
button | Earth bonding continuity tested – record result: | Yes,N/A
button | As-builts complete. | Yes,N/A
holdpoint | Installed by:
checkpoint | Add applicable signatures
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-02C Cable Transits
section | Details
checkpoint | Cable Transits
button | Transit frame installed as per drawings. | Yes,N/A
button | Transit frame identification marked correctly and visible. | Yes,N/A
button | Frame correctly packed with correct sized blocks and infills. | Yes,N/A
button | Correct stay plates fitted (non-ferrous for single core power cables.) | Yes,N/A
button | Rated insulation installed to transit (where required.) | Yes,N/A
button | Cables entering and leaving transits adequately supported and protected. | Yes,N/A
button | Cables pass through frames without strain on blocks. | Yes,N/A
button | All cables identified on both sides of transit and visible. | Yes,N/A
button | As-builts complete. | Yes,N/A
holdpoint | Installed by:
checkpoint | Client Representative
holdpoint | Client Representative:
checklist | ITR-E-67 Final Checklist for PPR
section | Details
checkpoint | Interior Checklist
button | All floor, wall & ceiling penetrations sealed. | Yes,N/A
button | All equipment has been installed | Yes,N/A
button | All loose items in panels have been secured or removed | Yes,N/A
button | Illuminated exit signs installed & operational | Yes,N/A
button | All doors and locks operational (including emergency) | Yes,N/A
button | Ensure each cable has an ID tag | Yes,N/A
button | Distribution board legend inside door | Yes,N/A
button | All appropriate signage and labelling are visible – warning stickers | Yes,N/A
button | Panels and boards have appropriate ID tags on exterior | Yes,N/A
button | All doors secured through secondary means, e.g. taped shut or tied to gland plate | Yes,N/A
button | All panels and boards locked | Yes,N/A
button | Room Interior is clean and suitable for presentation to client | Yes,N/A
checkpoint | Upload photo of interior
checkpoint | Misc Equipment Supplied by Entec
button | Fire Extingishers x2 | Yes,N/A
button | Fire Extinguishers are bubble wrapped and safely secured for transportation | Yes,N/A
button | First Aid Kit | Yes,N/A
button | HVAC Controllers | Yes,N/A
button | Desk and chairs | Yes,N/A
button | Equipment cupboard | Yes,N/A
button | LV rescue kit | Yes,N/A
button | Emergency Eye wash station | Yes,N/A
checkpoint | Exterior Checklist
button | Container Exterior is undamaged, e.g. paintwork intact | Yes,N/A
button | Earth Boss correctly installed and connected | Yes,N/A
button | Stairs have been verified to correctly suit container | Yes,N/A
button | Stairs are available and ready for transportation | Yes,N/A
checkpoint | Upload photo of exterior
checkpoint | Final Checklist
button | All other ITR’s have been completed | Yes,N/A
button | As-Built drawings completed and signed off | Yes,N/A
button | All keys available handed to client representataive or project manager | Yes,N/A
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-12 Electrical Earthing
section | Details
checkpoint | Electrical earthing system installation
button | Confirm earth grid layout, earth conductors/connections and number of earth electrodes is in accordance with drawings, drawings as-built | Yes,N/A
button | Ensure that all metal work is earthed as required. | Yes,N/A
button | Check welding of earth bosses and associated surface finish. | Yes,N/A
button | Ensure that earth cables/conductors/electrodes have adequate mechanical protection i.e. conduits, tobys, kick-plates etc at points of high exposure. | Yes,N/A
button | Ensure that brazing or welding of all joints has been completed correctly. | Yes,N/A
button | Ensure that adequate corrosion and weather protection has been installed around all connections, joints, lugs, cad (thermal) welds and earth bosses | Yes,N/A
button | All earth bosses and studs tight and fitted with shake proof washers and coated with protective coating. | Yes,N/A
button | Check cable terminations/joints to ensure that all lugs/barrels have been crimped correctly. | Yes,N/A
button | Check that all bi-metal connections have been performed correctly to manufacturer’s requirements. | Yes,N/A
button | Ensure that the earth cables to the main earth electrodes are terminated at each end of the main earth bar. | Yes,N/A
button | Ensure that earth cable identification markings are in place. | Yes,N/A
button | Ensure that earth connections are not multi-coiled or ‘pig-tailed’ but are terminated as straight as possible. | Yes,N/A
button | Check earth bar fixings, mounting points and terminations are tight and secure and conform to project specification (if applicable) | Yes,N/A
checkpoint | Test Results
textbox | Earth continuity test results (Earth bar to Electrode, Grid, etc - please specify)
textbox | 3-Wire earth test results (If applicable).
textbox | Earth grid test results (if applicable). (HV earth grid, LV earth grid, combined earth grids)
checklist | ITR-E-11 Generator Package (LV)
section | Details
checkpoint | Generator Package (LV)
button | Check equipment and nameplate details are correct and in accordance with the data sheet and equipment schedule. | Yes,N/A
button | No mechanical damage and paintwork in good condition. | Yes,N/A
button | Check terminal boxes and glanding correct. | Yes,N/A
button | Instruments correctly installed. | Yes,N/A
button | Heaters correctly installed. | Yes,N/A
button | Check unit for cleanliness. | Yes,N/A
button | Check manual operation of selector switches, MCB, push buttons etc. | Yes,N/A
button | External cabling correctly installed. | Yes,N/A
button | Protection of live parts adequate. | Yes,N/A
button | Main terminal box complete and terminations correct torque. | Yes,N/A
button | Ensure direction of rotation is clearly marked. | Yes,N/A
button | Check gasket and seals are not damaged. | Yes,N/A
button | Unused cable entries are correctly sealed. | Yes,N/A
button | As-builts complete | Yes,N/A
checkpoint | Electrical Checks
textbox | Record test results: Insulation Resistance, Continuity, Bonding, Other.
textbox | Heater circuit insulation resistance:
holdpoint | Installed by:
checkpoint | Client Representative
holdpoint | Client Representative:
checklist | Frame Construction
section | Details
checkpoint | Frame Construction
button | Baseplate layout as per drawing specififcation | Yes,N/A
checkpoint | Photo of Baseplate
button | Removeable Padeyes in place | Yes,N/A
checkpoint | Photo of removeable padeyes
button | Floor/room layout as per drawing | Yes,N/A
checkpoint | Photo of floor/room layout
button | Compressed cement board used | Yes,N/A
checkpoint | Photo of floor board
button | Frame construction adhering to all general steel work notes as per latest drawings | Yes,N/A
button | Baseplate is free from damage and paintwork is intact | Yes,N/A
checkpoint | Add QA pack from blast and paint
checkpoint | Add QA pack from fabricators
button | As-Built drawings completed and signed off | Yes,N/A
holdpoint | Frame Construction checked by:
checkpoint | Client Representative
holdpoint | Client Representative:
checklist | Floor, Duct Penetrations and Vents
section | Details
checkpoint | Floor, Duct Penetrations and Vents
button | Floor cable penetrations arrangement as per latest drawings | Yes,N/A
checkpoint | Photo of floor cable penetrations
button | Battery Cabinet Ventilations as per drawings | Yes,N/A
checkpoint | Photo of battery cabinet ventilation points
button | Fresh air intake installed for the control room as per drawings. | Yes,N/A
checkpoint | Photo of fresh air intake
button | Ventilation point for the switchroom insatlledas per drawings | Yes,N/A
checkpoint | Photo of ventilation point
button | Switch board arc vent installed and located as per drawings | Yes,N/A
checkpoint | Photo of switchboard arc
button | Warning signs installed | Yes,N/A
checkpoint | Photo of warning signs
textbox | Deflection Check - (+/-) 1mm tolerance in any 1 metre radius & a tolerance of (+/-) 3mm over the length of the switchroom. Record results:
button | As-Built drawings completed and signed off | Yes,N/A
holdpoint | Floor, Duct Penetrations checked by:
checkpoint | Client Representative
holdpoint | Client Representative:
checklist | Cable Support
section | Details
checkpoint | Cable Support
button | Cable ladder installed | Yes,N/A
checkpoint | Photo of cable ladder
button | Vertical UT-3 Uni tray installed where required to allow cable access into cabinets | Yes,N/A
checkpoint | Photo of tray
button | Fibre/comms duct insatlled | Yes,N/A
checkpoint | Photo of fibre/comms duct
button | Fire wall penetrations go through fire sleeves | Yes,N/A
checkpoint | Photo of fire wall penetrations
holdpoint | Cable Supports checked by:
checkpoint | Client Representative
holdpoint | Client Representative:
checklist | Earthing
section | Details
checkpoint | Earthing
button | 50mmx10mm copper earth bar installed on cable ladder as per design | Yes,N/A
checkpoint | Photo of copper bar
button | All cubicles connected to earth bar using 35mm2 Cu earth bond | Yes,N/A
checkpoint | Photo of cubicles connected to earth bar
button | All doors have flat tinned copper braid earth straps fitted | Yes,N/A
checkpoint | Photo of doors with copper braid
button | Earth bar penetrates floor | Yes,N/A
checkpoint | Photo of earth bar
button | As-Built drawings completed and signed off | Yes,N/A
holdpoint | Earthing checked by:
checkpoint | Client Representative
holdpoint | Client Representative:
checklist | ITR-E-40 Bus Bar
section | Details
checkpoint | Bus Bar
button | Check entire Bus Bar and confirm there is no damage | Yes,N/A
label | Please attatch photo of Bus Bar
button | Bus Bar alignment is correct | Yes,N/A
label | Acceptable Bus Bar Torque Settings:
label | ○ Bolt: M6 M8 M10 M12 M16
label | ○ Torque: 10Nm 20Nm 30Nm 40Nm 60Nm
button | Confirm all jointing bolts are present and have been torque tested in accordance with the manufacturer and design requirements. | Yes,N/A
button | Confirm all transit packing and preservation materials have been removed. | Yes,N/A
button | Confirm Bus Bar clearances conform to manufactures and design requirements. | Yes,N/A
button | Confirm all Bus Bars are secure within the supports. | Yes,N/A
textbox | Record the total number of bus bar joints.
checkpoint | Test Results:
textbox | Results:
holdpoint | Add applicable signatures (e.g Electrician, Inspector, Client Representative)
checklist | ITR-E-63 Cable Lug Installation
section | Details
checkpoint | Cable lug
button | Appropriate lug for cable size has been used. | Yes,N/A
button | Lug has been correctly seated with no loose copper strands outside of lug. | Yes,N/A
button | Lug has been crimped with 60 tonne crimper. | Yes,N/A
button | Joint sealing paste has been correctly applied to the contact surface of lug | Yes,N/A
checkpoint | Bolts
button | Bolt has been torqued to manufacturers requirements | Yes,N/A
label | If no manufacturer torque spec, use torques below. M8-20NM, M10-40NM, M12-70NM.
textbox | Manufacturers torque requirement (if applicable)
checkpoint | Test Results
textbox | Continuity test results
textbox | Ductor test results if applicable
checkpoint | Test Equipment Used
textbox | Description
textbox | Manufacturer
textbox | Model No:
textbox | Serial No:
holdpoint | All relevant signatures (Installed by, Approved by, Client Representative)
checklist | Lighting, Power and Data
section | Details
checkpoint | Lighting Power and Data
button | Internal and external lighting installed as per drawings | Yes,N/A
button | Exit and emergency lighting installed as per drawing | Yes,N/A
button | Power and data installed as per drawing | Yes,N/A
button | As-Built drawings completed and signed off | Yes,N/A
holdpoint | Lighting, Power and Data checked by:
checkpoint | Client Representative
holdpoint | Client Representative:
checklist | Stairs and Platforms
section | Details
checkpoint | Stairs and Platforms
button | Stair and platform frames as per drawings with 38mm FRP Grating for platform and PT6 stair treads 275mm wide | Yes,N/A
checkpoint | Photo of stairs and platform frames
button | Edge of each step and edge of platform has high contrast, non-slip proprietary nosing | Yes,N/A
checkpoint | Photo of nosing
button | Handrail system installed either side of the steps and around edges of platforms | Yes,N/A
checkpoint | Photo of handrails
button | As-Built drawings completed and signed off | Yes,N/A
holdpoint | Stairs and Platforms checked by:
checkpoint | Client Representative
holdpoint | Client Representative:
checklist | ITR-E-05 - Low Voltage and Control Cable
section | Details
checkpoint | Low Voltage Cable
button | Verify cable type, size, colour code and tags are in accordance with the Cable Schedule. | Yes,N/A
button | Check dressing / cleating, cable undamaged | Yes,N/A
button | Bending radius satisfactory | Yes,N/A
button | Check cable cores correctly identified and labelled. | Yes,N/A
button | Cable terminated with correct lugs and crimped with the correct die. | Yes,N/A
button | Check Armour / Screen correctly made off. | Yes,N/A
button | Check armour continuity / earthing is maintained by the correct use of serrated washers and / or earth tags (if applicable) | Yes,N/A
textbox | From:
textbox | To:
button | Glanding / Locknuts correctly installed. | Yes,N/A
textbox | Gland type - from: |  | Haz. Area Rating
textbox | Haz. Area Cert Details.
textbox | Gland type - to: |  | Haz. Area Rating
textbox | Haz. Area Cert Details.
textbox | Confirm spare cores and shields are terminated and conform to drawings and client spec.
checkpoint | Electrical Checks
textbox | Record test results: Insulation Resistance, Continuity, Bonding, Other.
holdpoint | Installed by:
checkpoint | Client Representative
holdpoint | Client Representative:
checklist | ITR-I-21A - Instrument and Control Cables
section | Details
checkpoint | Instrument Cable
button | Verify cable type, size, colour code and tags are in accordance with the Cable Schedule. | Yes,N/A
button | Check dressing / cleating, cable undamaged | Yes,N/A
button | Bending radius satisfactory | Yes,N/A
button | Check cable cores correctly identified and labelled. | Yes,N/A
button | Cable terminated with correct lugs and crimped with the correct die. | Yes,N/A
button | Check Armour / Screen correctly made off. | Yes,N/A
button | Check armour continuity / earthing is maintained by the correct use of serrated washers and / or earth tags (if applicable) | Yes,N/A
textbox | From:
textbox | To:
button | Glanding / Locknuts correctly installed. | Yes,N/A
textbox | Gland type - from: |  | Haz. Area Rating
textbox | Haz. Area Cert Details.
textbox | Gland type - to: |  | Haz. Area Rating
textbox | Haz. Area Cert Details.
textbox | Confirm spare cores and shields are terminated and conform to drawings and client spec.
checkpoint | Electrical Checks
textbox | Record test results: Insulation Resistance, Continuity, Bonding, Other.
holdpoint | Installed by:
checkpoint | Client Representative
holdpoint | Client Representative:
checklist | ITR-E-29 Cat 6 Communication Cable
section | Details
checkpoint | Common to all circuits
button | check cable for damage | Yes,N/A
button | Check cable is correctly identified and labelled | Yes,N/A
button | Check glanding/locknuts correctly installed | Yes,N/A
button | Confirm cable routing and segregation is correct | Yes,N/A
button | Confirm to and from destination as per design. | Yes,N/A
checkpoint | Data Circuits
button | Check cable terminated with correct crimps | Yes,N/A
button | Check sheild/screen correctly made off | Yes,N/A
button | Check Cat6 end-to-end certification (outlet and cable) | Yes,N/A
holdpoint | Installed by:
checkpoint | Client Representative
holdpoint | Client Representative: