## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
Frame Construction | checklist |  |  | Tier 1: Frame Construction
Floor, Duct Penetrations and Vents | checklist |  |  | Tier 1: Floor, Duct Penetrations and Vents
| step |  |  | Tier 1: Cable Support
Cable Support | checklist |  |  | Tier 2: Cable Support.
| step |  |  | Tier 2: Cable Support ITR's
ITR-E-02B Cable Supports Above Ground | checklist |  |  | Tier 3: Cable Tray
ITR-E-02C Cable Transits | checklist |  |  | Tier 3: Cable Transit
| step |  |  | Tier 1: Earthing
Earthing | checklist |  |  | Tier 2: Earthing Checklist
| step |  |  | Tier 2: Copper Bar
ITR-E-12 Electrical Earthing | checklist |  |  | Tier 3: Electrical Earthing
ITR-E-40 Bus Bar | checklist |  |  | Tier 3: Bus Bar
ITR-E-63 Cable Lug Installation | checklist |  |  | Tier 3: Cable Lug Installation
| step |  |  | Tier 2: Cubicles
ITR-E-12 Electrical Earthing | checklist |  |  | Tier 3: Electrical Earthing
ITR-E-40 Bus Bar | checklist |  |  | Tier 3: Bus Bar
ITR-E-63 Cable Lug Installation | checklist |  |  | Tier 3: Cable Lug Installation
| step |  |  | Tier 2: Other Earthing
ITR-E-12 Electrical Earthing | checklist |  |  | Tier 3: Electrical Earthing
ITR-E-40 Bus Bar | checklist |  |  | Tier 3: Bus Bar
ITR-E-63 Cable Lug Installation | checklist |  |  | Tier 3: Cable Lug Installation
| step |  |  | Tier 1: Lighting, Power & Data
| step |  |  | Tier 2: Lighting
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Control Room & Emergency Lighting
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Switchroom and Emergency Lighting
ITR-E-64 General Lighting | checklist |  |  | Tier 3: External Lights
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Exit Lights
ITR-E-64 General Lighting | checklist |  |  | Tier 3: Flood Lights
| step |  |  | Tier 2: Power
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: Control Room Socket Outlet 1PH
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: Switchroom Socket Outlet 1PH
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: External Control Room Socket 1PH
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: External Control Room Outlet 3PH
ITR-E-01 General Electrical Equipment | checklist |  |  | Tier 3: Switchroom Outlet 3PH
| step |  |  | Tier 1: HVAC
ITR-E-68 HVAC System | checklist |  |  | Tier 2: AC01
ITR-E-68 HVAC System | checklist |  |  | Tier 2: AC02
ITR-E-68 HVAC System | checklist |  |  | Tier 2: AC03
ITR-E-68 HVAC System | checklist |  |  | Tier 2: AC04
| step |  |  | Tier 1: Fire Protection
ITR-E-69 Fire Detection System | checklist |  |  | Tier 2: Fire Detection System
ITR-E-06 Control Panel | checklist |  |  | Tier 2: FIP- Fire Indication Panel
| step |  |  | Tier 1: Equipment and Install
| step |  |  | Tier 2: Switchboards
ITR-E-34 Low Voltage Switch Board | checklist |  |  | Tier 3: J01 - Incomer 1
ITR-E-34 Low Voltage Switch Board | checklist |  |  | Tier 3: J02 - Incomer 2
ITR-E-34 Low Voltage Switch Board | checklist |  |  | Tier 3: J03 - Incomer 3
ITR-E-34 Low Voltage Switch Board | checklist |  |  | Tier 3: J04 - Bus Earth and Bus VT
ITR-E-34 Low Voltage Switch Board | checklist |  |  | Tier 3: J05 - Feeder 1
ITR-E-34 Low Voltage Switch Board | checklist |  |  | Tier 3: J06 - Feeder 2
ITR-E-34 Low Voltage Switch Board | checklist |  |  | Tier 3: J07 - Feeder 3
ITR-E-34 Low Voltage Switch Board | checklist |  |  | Tier 3: J08 - HF Feeder
ITR-E-34 Low Voltage Switch Board | checklist |  |  | Tier 3: AC1 - AC Main Switchboard
| step |  |  | Tier 2: Distribution Boards
| step |  |  | Tier 3: AC2 - AC Distribution Board
ITR-E-03 Entec - Distribution Board Installation | checklist |  |  | Tier 4: Distribution Board Installation
ITR-E-04 Schedule of Test Results DB | checklist |  |  | Tier 4: Schedule of Test Results DB
| step |  |  | Tier 2: Control Panels
ITR-E-06 Control Panel | checklist |  |  | Tier 3: PPC - PPC Cabinet
ITR-E-06 Control Panel | checklist |  |  | Tier 3: FS1 - Metering Cubicle
ITR-E-06 Control Panel | checklist |  |  | Tier 3: FS2 - EA Protection Cubicle
ITR-E-06 Control Panel | checklist |  |  | Tier 3: FS3 - Beon Protection Cubicle
ITR-E-06 Control Panel | checklist |  |  | Tier 3: FS6 - Beon Metering and RTU Cabinet
ITR-E-06 Control Panel | checklist |  |  | Tier 3: FS7 - Beon Metering and RTU Cabinet
ITR-E-06 Control Panel | checklist |  |  | Tier 3: FS8 - Dispatch Cubicle/Genisis
ITR-E-06 Control Panel | checklist |  |  | Tier 3: FS9 - OPUSV Comms Cubicle
ITR-E-06 Control Panel | checklist |  |  | Tier 3: FS10 - OPUSV Comms Cubicle
ITR-E-06 Control Panel | checklist |  |  | Tier 3: FS11 - FRV Cubicle (ISOTROL)
ITR-E-06 Control Panel | checklist |  |  | Tier 3: GPS - GPS Antenna Earthing Interface Enclosure
| step |  |  | Tier 2: Batteries
| step |  |  | Tier 3: DC11 - X String DC Distribution and Battery Charger
ITR-E-03 Entec - Distribution Board Installation | checklist |  |  | Tier 4: Distribution Board Installation
ITR-E-04 Schedule of Test Results DB | checklist |  |  | Tier 4: Schedule of Test Results DB
| step |  |  | Tier 3: DC21 - Y String DC Distribution and Battery Charger
ITR-E-03 Entec - Distribution Board Installation | checklist |  |  | Tier 4: Distribution Board Installation
ITR-E-04 Schedule of Test Results DB | checklist |  |  | Tier 4: Schedule of Test Results DB
Stairs and Platforms | checklist |  |  | Tier 1: Stairs and Platform
| step |  |  | Tier 1: Final Approval
Certificate of compliance (COC) | checklist |  |  | Tier 2: CoC
ITR-E-67 Final Checklist for PPR | checklist |  |  | Tier 2: Final Checklist
| step |  |  | Tier 2: Test Equipment
Test Equipment Details: | checklist |  |  | Tier 3: (Tester Name)
Test Equipment Details: | checklist |  |  | Tier 3: (Tester Name)
Test Equipment Details: | checklist |  |  | Tier 3: (Tester Name)
| step |  |  | Tier 1: Cables
| step |  |  | Tier 2: Control Cables
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C1; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C2; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C3; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C4; Tier 4: 2.5mm2 8C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C5; Tier 4: 2.5mm2 12C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C6; Tier 4: 2.5mm2 12C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C7; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C9; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C10; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C11; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C12; Tier 4: 2.5mm2 8C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C13; Tier 4: 2.5mm2 12C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C14; Tier 4: 2.5mm2 12C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C15; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C17; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C18; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C19; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C20; Tier 4: 2.5mm2 8C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C21; Tier 4: 2.5mm2 12C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C22; Tier 4: 2.5mm2 12C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C23; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C25; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C26; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C27; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C28; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C29; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C30; Tier 4: 2.5mm2 12C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C32; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C33; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C34; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C35; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C36; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C37; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C38; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C39; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C41; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C42; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C43; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C44; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C45; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C46; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C48; Tier 4: 6mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C49; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C50; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C51; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C52; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C53; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C55; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C56; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C57; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C58; Tier 4: 12C Data cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C59; Tier 4: 2.5mm2 2C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C60; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C61; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C62; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C64; Tier 4: 12C Data cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C65; Tier 4: 35mm2 4C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C66; Tier 4: 16mm2 4C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C67; Tier 4: 10mm2 4C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C68; Tier 4: 10mm2 4C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C69; Tier 4: 2.5mm2 2C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C70; Tier 4: 2.5mm2 2C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C71; Tier 4: 2.5mm2 2C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C73; Tier 4: 12C Data cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C74; Tier 4: 35mm2 1C HFS/PVC (Red)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C75; Tier 4: 35mm2 1C HFS/PVC (Blk)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C76; Tier 4: 35mm2 1C HFS/PVC (Red)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C77; Tier 4: 35mm2 1C HFS/PVC (Blk)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C78; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C79; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C80; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C83; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C84; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C85; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C88; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C89; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C90; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C91; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C92; Tier 4: 35mm2 1C HFS/PVC (Red)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C93; Tier 4: 35mm2 1C HFS/PVC (Blk)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C94; Tier 4: 35mm2 1C HFS/PVC (Red)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C95; Tier 4: 35mm2 1C HFS/PVC (Blk)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C96; Tier 4: 2.5mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C97; Tier 4: 2.5mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C99; Tier 4: 12C Data cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C100; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C101; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C102; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C105; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C106; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C107; Tier 4: 6mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C111; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C112; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C113; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C114; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C115; Tier 4: 35mm2 1C HFS/PVC (Red)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C116; Tier 4: 35mm2 1C HFS/PVC (Blk)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C117; Tier 4: 35mm2 1C HFS/PVC (Red)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C118; Tier 4: 35mm2 1C HFS/PVC (Blk)
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C119; Tier 4: 2.5mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C120; Tier 4: 2.5mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C122; Tier 4: 2.5mm2 8C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C124; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C125; Tier 4: 2C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C127; Tier 4: 2.5mm2 8C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C128; Tier 4: 2.5mm2 4C PVC/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C129; Tier 4: 2.5mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C130; Tier 4: 2.5mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C131; Tier 4: 2.5mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C132; Tier 4: 4C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C133; Tier 4: 4C Data Cable PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C134; Tier 4: 2.5mm2 2C XLPE/HFS
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C136; Tier 4: 2.5mm2 2C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C137; Tier 4: 2.5mm2 2C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C138; Tier 4: 2.5mm2 2C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C139; Tier 4: 2.5mm2 2C+E XLPE/PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: C140; Tier 4: 2.5mm2 2C+E XLPE/PVC
| step |  |  | Tier 2: COMMS Cables
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM1; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM2; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM3; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM4; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM5; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM6; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM7; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM8; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM9; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM10; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM11; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM12; Tier 4: OM4 OPTIC FIBRE
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM15; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM16; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM17; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM18; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM19; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM20; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM21; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM22; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM23; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM24; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM25; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM26; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM27; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM28; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM29; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM32; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM33; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM34; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM35; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM36; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM37; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM38; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM39; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM40; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM41; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM42; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM43; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM44; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM45; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM46; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM47; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM50; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM51; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM54; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM55; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM60; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM61; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM62; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM63; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM64; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM65; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM66; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM67; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM68; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM69; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM70; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM71; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM72; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM73; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM74; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM75; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM76; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM77; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM78; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM79; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM80; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM81; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM82; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM83; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM84; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM85; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM86; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM87; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM88; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM89; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM90; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM91; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM92; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM93; Tier 4: COAXIAL CABLE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM94; Tier 4: COAXIAL CABLE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM95; Tier 4: COAXIAL CABLE
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM97; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM98; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM99; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM100; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM101; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM102; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM103; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM104; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM105; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM106; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM107; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM108; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM109; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM110; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM111; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM112; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM113; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM114; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM115; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM116; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM117; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM118; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM119; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM120; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM121; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM122; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM124; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM125; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM126; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM127; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM128; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM129; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM130; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM131; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM132; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM133; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM134; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM135; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM136; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM137; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM138; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM139; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM140; Tier 4: 8 CORE CAT6 - SOLID CORE U/UTP
ITR-E-29 Cat 6 Communication Cable | checklist |  |  | Tier 3: COM141; Tier 4: 8 CORE SCREENED CAT6 - STRANDED U/UTP
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM150; Tier 4: OM4 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM151; Tier 4: OM4 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM152; Tier 4: OM4 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM153; Tier 4: OM4 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM154; Tier 4: OM4 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM155; Tier 4: OM4 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM156; Tier 4: OM4 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM157; Tier 4: OM4 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM158; Tier 4: OM4 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM159; Tier 4: OM4 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM160; Tier 4: OM3 LOOSE TUBE FIBRE OPTIC CABLE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM161; Tier 4: OM3 LOOSE TUBE FIBRE OPTIC CABLE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM162; Tier 4: 8 CORE PVC-SCR-PVC
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM181; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM182; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM183; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM184; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM185; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM187; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM188; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM189; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM191; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM192; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM193; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM194; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM195; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM197; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM198; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM199; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM201; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM202; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM203; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM204; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM206; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM207; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM208; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM211; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM212; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM213; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM214; Tier 4: OS2 GRP (GLASS RE-INFORCED PLASTIC) OFC 12F CORE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS1/01; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS1/02; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS1/03; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS1/04; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS1/05; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS2/01; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS2/02; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS2/03; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS2/04; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS2/05; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS3/01; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS3/02; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS3/03; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS3/04; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS3/05; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS4/01; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS4/02; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS4/03; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS4/04; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS4/05; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS5/01; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS5/02; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS5/03; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS5/04; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS6/01; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS6/02; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS6/03; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS6/04; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS7/01; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS7/02; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS7/03; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS7/04; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS7/05; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS8/01; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS8/02; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS8/03; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS8/04; Tier 4: OS2 OPTIC FIBRE
ITR-E-05 - Low Voltage and Control Cable | checklist |  |  | Tier 3: COM/STS8/05; Tier 4: OS2 OPTIC FIBRE
Note on A12: Johno Carswell: May need extra details around copper bar. Customise the ITR perhaps?
Note on A16: Johno Carswell: May need extra details around copper bar. Customise the ITR perhaps?
Note on A20: Johno Carswell: May need extra details around copper bar. Customise the ITR perhaps?