## Checklist Templates
Id | Type | Name | Values | Prompting Name
f0957faf-0027-511e-8f48-bb3e5b0db63c | checklist | 01C-SDC-TMP-CON-ITP-007a - 3 - Jumpform |  | 01C-SDC-TMP-CON-ITP-007a - 3 - Jumpform
14709687-ca49-585c-9e2d-bc7e071165a5 | section | Prior to Reinforcement
03ca3302-54ea-5fe6-9601-628d70a483a5 | checkpoint | Confirm Jump No Seq and bottom and top RLs of proposed pour
51402eb2-ae72-5c2d-a581-6bac310dfde6 | textbox | Jump No Sequence
02f23e48-87d6-507c-b8e9-c6a88597fc7a | textbox | Bottom of Proposed Wall RL
8b65fcba-6344-577a-95e6-980670abccd1 | textbox | Top of Proposed Wall RL
0131d1e5-9829-5ae5-9777-fddd091bd9c3 | checkpoint | Surveyor to complete survey of concrete walls below to confirm if walls need to be adjusted. Attach confirmation survey has been issued to formwork contractor via Aconex
68b1ccb4-f460-5ab1-a75b-553c75d0fc8f | textbox | Aconex Correspondence No.
6a2d26db-eb97-5c65-a2e2-59d27a2d77cc | checkpoint | Lift Requirements - Review formwork blockouts for lift openings and door thresholds in accordance with architectural elevations and lift shop drawings
de1cd537-8464-507e-bdff-c0f2bb8184ed | checkpoint | Formwork Requirements - Confirm that all reboxes, couplers, shear key pockets and cast in plates to internal shutter as per structural engineer detail
f46aa660-47cf-5320-90a6-461ec8d60422 | checkpoint | Attach Sign Off from form worker contractor confirming all works completed and clear access for handover to steel fixers
4f585971-b5f0-56eb-b5ac-e2aa9bea7876 | section | Prior to Closing Shutters
b338461b-2c19-59cb-a2e4-51dea582f0c8 | checkpoint | Lift Requirements - Confirm any block out / penetrations required for lift buttons and indicators has been cast in by Form Worker
2b333bef-1ef0-5309-abc8-11acba4f56a3 | checkpoint | Confirm all outside reboxes & couplers are installed to required SSL + cover levels
9e2abf08-bc49-568e-8b0d-cbdcc6b231e1 | checkpoint | Attach electrical contractors ITP to confirm any required conduit cast ins are completed
91f28ca2-219c-5bfa-ae71-27cf862a43a7 | checkpoint | Attach reinforcement installer’s ITP
3bc44e94-e608-5f08-81cb-7f38d623571a | checkpoint | Reinforcement Checks (Refer Structural Engineers Drawings for Reference):
e7e68324-bcab-5573-8e93-210cce932bd4 | note | Reinforcement cover sufficient
2be8e629-aa9c-5e79-9054-2b740d1a57ee | note | Lap Length of bars sufficient
48bd83df-ac5f-5da9-aaca-72bd54684c32 | note | Starter bar length to next pour correct
43f96e07-3667-5d3d-86fd-ce324fad6495 | note | Lace bars installed to reboxes
92f8ba57-613d-5704-9f76-19ec4029f68d | checkpoint | Attach structural engineer’s inspection report
fd9cd6d6-111d-5ff3-89b0-16611eaa843d | checkpoint | Attach verification that structural engineer’s inspection report has been closed out to allow concrete pour
9fc82d7a-a558-562f-8736-c7d4f3eda8d6 | checkpoint | Attach photos of all works completed prior to closing shutters
a59e4763-4d27-52b9-87a4-635cae6dd022 | section | During Concrete Pouring
01bd6b09-ae5a-5128-9a4b-c5752317b4a2 | checkpoint | Confirm Concrete ordered is correct
510cdbe8-8db7-538d-a942-980f4beefc41 | textbox | MPa/mix design
cef213ee-84d7-51dd-9b80-b97468219d61 | checkpoint | Confirm pour height with concrete Contractor prior to pouring
a2ee5ee3-3a15-5d47-b73c-131915c9e0af | checkpoint | Attach form worker’s jumpform ITP
8eeb1ec6-cfd7-5ec3-98f0-cde5b6a70494 | checkpoint | Attach concrete place contractor’s ITP
da3045fb-c496-52e3-b307-9e695cad6a1a | checkpoint | Confirm concrete tester onsite to take samples and ensure correct pour location is recorded
0301ea4b-308b-5297-9f96-80e10dd13369 | section | Prior to Jumping
fb529313-bcdb-57c7-845e-f762c5e663f9 | checkpoint | Attach concrete test result to confirm min 15 MPa has been reached
4cce810a-f264-5392-86d8-62229acfe779 | checkpoint | Attach form worker’s Permit to Energise Jumpform.
11f6ad46-257b-5f13-b106-6b4dfc224c03 | note | Note exclusion zone below and all penetrations to be blocked up and secure and any temporary services (hydraulic/electrical/static line) disconnected inside trailing decks
16ebbe46-fe50-59f6-96e4-8c3f6085cb39 | section | After Jumping
6fc758a6-7e52-591e-8798-f956b4171a46 | checkpoint | Form Worker to ensure that all z bar holes and jumpform pockets within the lift shaft has been patched and infilled in accordance with structural engineer drawings
a5de8e97-6d7d-504d-90dc-7763000f1b77 | checkpoint | Attach concrete test results 28d and confirm compliance with engineer requirements
9c4d0f4e-3eb0-5a30-8ef8-9432339f53a8 | checkpoint | Permit to Re-seat jumpform received (attach to ITP)
7791678c-beec-5f8b-abd9-6119ac21c60c | checkpoint | Surveyor to survey finished concrete walls (attach as-built to ITP)
3543a7eb-a7dc-52c4-a19a-4f7f8f5b4e0e | signoff | Final ITP Review & Sign-off by Project Engineer
bba22c24-8156-5c7b-acf0-fc3d64c69738 | checklist | 101C-SDC-TMP-CON-ITP-007 - 2- Concrete Columns Walls Verticals |  | 101C-SDC-TMP-CON-ITP-007 - 2- Concrete Columns Walls Verticals
e895f0c4-445d-5222-83aa-ee6b071b56fa | section | Prior to Concrete Pour
5ba4bfda-bc99-56cf-8b8b-2996c4f9926f | checkpoint | Current Drawing Status - Refer Aconex Document Register for latest approved Shop Drawings. Record drawings used at time of pour on ITP.
8212b539-cd4f-5577-8e24-cde7cadf435e | textbox | Architectural Drawings
9525446e-d822-5373-a025-b3ff69bf5704 | textbox | Structural Drawings
535fe087-6741-5432-99b5-8b5bd1d668f1 | checkpoint | Ensure survey of column/wall positions are completed prior to commencing formwork
1181ac05-c6a5-5bc7-9c93-9e35cbd517a6 | note | Attach surveyors as-built records to ITP
67880d0a-c7c0-503a-8574-c26af3170bd4 | checkpoint | Reinforcement - Check Starter bars from previous pour installed in correct position (compare against survey points)
6fa61a94-96db-5ff6-a543-755820891e1a | checkpoint | Reinforcement - Check for correct bar sizes and lap lengths between starter bars (top & bottom)
3902c60f-0f95-575f-a26e-2703689b150c | checkpoint | Cast-in Services - Electrical subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design. Attach Contractors ITP
025eba38-756a-5f48-81d5-b24cbee885c5 | checkpoint | Cast-in Services - Hydraulics subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
c2d57c76-36ed-5a08-8267-6e7225fc89ac | checkpoint | Cast-in Services - Mechanical subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
18de01a4-f42c-5901-afdf-25618335b566 | checkpoint | Cast-in Services - Fire Subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
8f061269-5e8f-57f9-a105-62da81d836df | checkpoint | Cast-in Services - Security Subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design
55bcc9e7-4508-50c4-999a-66d8c5c4c9aa | checkpoint | Confirm strength and mix design of concrete ordered with subcontractor prior to pour
e2392b00-e6cb-5a51-8a2a-2a77c8e07c4b | textbox | Concrete Mix Design:
e502b10d-edc8-544c-b0eb-c56a1aad439f | checkpoint | Structural Engineer Sign-off - Foreman and subcontractor to sign off engineer’s report to verify that all work to be rectified was checked for compliance prior to pour
ef21bfda-3e60-5169-b596-cebf04ae4aad | note | Attach engineers inspection report and verification of rectification items being closed out.
e8a4bcc9-d32e-5f1d-ac6b-949038bf6b85 | checkpoint | Formwork Compliance - Confirm formwork is checked to achieve Class 2 finish to concrete:
3a93e62d-4b35-5058-8a98-4dcd75ec50a2 | tickbox | Formwork is clean and free of debris
27f9719b-8318-58ee-a64a-ba2a4f2bc4d4 | tickbox | No lipping of formwork between sheets
97222634-f5b3-5bfc-a4b9-bb08014a530c | tickbox | Fillets installed at all corners
93aef68f-4499-5ea3-8e2e-b386ba441593 | tickbox | Form ties are installed at even spacing
fda4eb4c-8d85-56c3-b72d-bf16096a64be | tickbox | Check for correct reo cover at shutters
3d1004c4-dd9c-5151-9af4-4d2b3025a3c1 | tickbox | Splayed columns are at correct degrees per Architectural/Structural drawings
a023a578-da63-5c4c-9d10-904381e00fd9 | checkpoint | Area cleaned of all excess formwork, sawdust at base of columns, reo, and debris prior to pour
d26c5200-b798-5a1b-8336-ba20b6936d9c | checkpoint | Attach formworkers ITP for column and wall formworking
a996aa4a-fd5b-5dc7-9d9f-1d40416795b1 | checkpoint | Attach Steelfixers ITP for Column and wall reinforcement
2855ee05-1267-5a52-b798-36451d292a8f | section | During Concrete Pour
a996b133-8d9b-53cc-af5e-c4d995eba206 | checkpoint | Concrete Placement Checklist
1b98de59-d17f-5afc-88c7-b191e7ce5752 | tickbox | Structural Engineer & Formwork Engineer Sign-off Received
d5dfff6a-4133-5297-8624-bb4fb087cf0c | tickbox | Confirm Delivery Docket References correct mix design
50bdef93-0732-56eb-9b5e-e6f5997d3539 | tickbox | Plant and Equipment checklist completed on concrete pump and lines
b5e23c22-d0f6-5c73-ace4-90ad93375d9a | tickbox | Confirm concrete tester on-site and correct location of concrete pour provided to them for test results
d4db1014-9b4b-5670-87f1-e038c416b2c7 | note | 7, 28 & 56 day compressive test results to be issued by batch plant
f9088664-a151-577d-abf9-6d232344a425 | note | Batch plant to issue monthly dry shrinkage test results
b73bee09-e61c-5e56-8b55-431389362db1 | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
80f59b43-15d6-5b35-8916-516d07afe598 | tickbox | Form Worker
a24b20a5-b078-5691-bdf1-3a7e0310a014 | tickbox | Electrician
c7498df1-2e83-5f27-bbe5-5dd8c14f2062 | tickbox | Plumber
045bea43-ef93-5c37-a70b-d767e5e3c0c3 | checkpoint | Ensure only rubber tipped vibrators are used and care is taken not to damage shutters
1b98fc0c-6352-5fbe-9adb-d3da0b8f3f8c | checkpoint | Ensure Form Worker labour is available to clean up any slurry runs at bottom of walls, immediately after pour for off form finishes.
77a27c32-7ee6-590f-8452-e5ff1e97b5c6 | checkpoint | Attach Concrete Place contractors ITP
0c36bc32-cf0c-5072-977b-380ad8510aaa | section | After Concrete Pour
9fb23d0e-0d1e-57cc-9c15-048ba7235eb7 | checkpoint | Curing - Approved curing compound to be applied to columns following removal of formwork as required.
1f774416-47c1-5414-ad4e-41fec77d84f0 | checkpoint | Confirm tolerance of finished concrete surfaces:
2f82a0a6-22f5-5790-8419-6e5c3ba5917b | note | 5mm+/- in correct position
5c321c38-d145-551c-a30c-87290edfbf01 | note | 5mm +/- from 3.0m straight edges.
a1a15c84-31a4-56a0-a2b0-e39c6e15e7e6 | note | 5mm +/- from plumb.
54d3cdd2-0c38-5c30-8a62-c92cc82fbdde | checkpoint | As-Built Survey - Confirm Surveyor is out next day to carry out survey of finished concrete. Attach As Built Survey Plan
234214fc-15c4-57c6-93e1-2a16b3f5124f | checkpoint | Concrete Test Results - Obtain all concrete test results. Confirm strength achieved after:
1f5986f6-3a4c-561f-861d-6357c8d03c6c | textbox | 7 Days MPa
b5affa46-7af9-5f5b-98b8-9f58c3a7f11c | textbox | 28 Days MPa
32f818c2-e3c3-5979-8176-de537e4796de | textbox | 56 Days MPa
35ac4bcc-f65d-56f1-9972-e66071f55c23 | checkpoint | All non-conformances closed out
95da422e-fade-5c59-b042-7bc47be521a6 | signoff | Final ITP Review & Sign-off by Project Engineer
692f11a4-9c13-5e75-a505-645bd8a1fd1e | checklist | 101C-SDC-TMP-CON-ITP-007b - 3 - Stairs FRP Works |  | 101C-SDC-TMP-CON-ITP-007b - 3 - Stairs FRP Works
e895f0c4-445d-5222-83aa-ee6b071b56fa | section | Prior to Concrete Pour
53a4e09b-da64-5382-9972-a06d81e557e3 | checkpoint | Confirm bottom, mid & top of stair RL's on Architectural Concrete Outlines.
3c333b2e-8c59-5cea-9bd6-995e5e5278dd | textbox | Bottom Landing RL
6268699c-bbf8-5b2d-b60b-6c91d3b7d452 | textbox | Mid Landing RL
7200af5a-dbde-5e1e-a6fb-251f67252f38 | textbox | Top Landing RL
1070e070-8762-52b5-8163-d97616889960 | checkpoint | Confirm Re-boxes/cast-in bars are installed to correct heights at landings, based on nominated design RL's.
a5d8848b-99b7-5ce5-bc68-b8d9d6f2968e | checkpoint | Confirm any starter bars on landings for dividing walls, etc… are installed as per Structural Drawings
678ad173-8ebb-532b-ab4c-6a7ef4eff6b6 | checkpoint | Check for reinforcement cover as per Structural Drawings.
3d315b18-7758-50f8-989c-6e7a2fee29cb | note | Cover requirement generally 30mm
0bcac4cd-00c8-5ec5-af47-92b4b9e2bd9c | checkpoint | Confirm all cast in elements installed (eg, stair handrails, etc…)
caa37a77-0509-5eb0-8e63-66cd29d4e003 | checkpoint | Confirm all formwork is clean and free of debris.
008f933d-b076-578b-85e3-18ee9c16226c | checkpoint | Confirm any conventional parts of stairs have been formed in accordance with the relevant shop drawings and standards.
d5770c7b-4996-5b2a-b994-b3894dd14abf | note | Statutory Requirements (Dimensions in mm): Riser: Min. 115, Max. 190 Going: Min. 240, Max. 355 Ensure consistency
17ec3654-8c20-5f06-bb0c-3208a041b0b0 | checkpoint | Confirm cast-in of anti-slip items if required (eg, carborundum powder, stair nosings, etc…);
4685b9e2-81f4-54b7-8f57-70d5cd7089d2 | checkpoint | Obtain certificate from Structural Engineer prior to concrete pour and attached completed Inspection Report.
6626c3ce-5d25-5a28-a138-c902250b1eac | checkpoint | Confirm MPa, slump and agg. size of concrete prior to ordering.
b8c2026a-2175-5b8d-aff1-5efde45b01d8 | textbox | Concrete Mpa/Mix Design
37255657-064d-553e-8a7e-c073495e2932 | checkpoint | Obtain subcontractors ITP (Steel Fixer) & attach to ITP
7405efd4-e864-533b-bdb8-4e36a2df192d | checkpoint | Obtain subcontractors ITP (Form Worker) & attach to ITP
2855ee05-1267-5a52-b798-36451d292a8f | section | During Concrete Pour
695edd83-2bbc-520b-927e-901f85d80a14 | checkpoint | If the stairs are being used as access to a leading deck, ensure alternative access is established prior to pouring.
0ebd1812-9009-5f0c-a6df-e4b64203a568 | checkpoint | Confirm concrete tester onsite during concrete pour, and the following tests have been requested.
1df64493-478e-5d8e-9f03-72aebec291be | note | 7 Day
672a0c94-2891-5426-a6cd-ac2ccde9cdba | note | 28 Day
4856696c-b869-5e48-9b65-241e9f43325b | note | Ensure concrete tester is aware of pour locations
b73bee09-e61c-5e56-8b55-431389362db1 | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
cc4294a7-8a69-5f86-8f2d-974e66cea6ae | tickbox | Form Worker
86538ad7-9fc1-5b9b-a13e-ec09b8a2f4de | tickbox | Electrician
0488c9dd-4037-5d80-a06f-5237a5736306 | tickbox | Plumber / Fire services
84260027-4fbc-5c5f-aafc-ae9858443195 | checkpoint | Ensure concreters have correct finishing tools (eg, carborundum powder, etc…).
03eaaf7a-25a4-5c60-abf8-0d3245aaa038 | checkpoint | Ensure only rubber tipped vibrators are used to prevent formwork damage.
2f58ffd1-86f9-5c30-b991-1c4c1f94d0de | checkpoint | Obtain Subcontractors ITP (Concretor) & attach to this ITP
9f644f6a-af2c-5b5b-a395-8bb6784abc9d | checkpoint | Ensure Form Worker labour is available to clean up any slurry runs at bottom of stairs, immediately after pour.
0c36bc32-cf0c-5072-977b-380ad8510aaa | section | After Concrete Pour
1f774416-47c1-5414-ad4e-41fec77d84f0 | checkpoint | Confirm tolerance of finished concrete surfaces:
b56e6619-857a-5c66-8962-bf3d63a08444 | note | 6mm +/- from design RL
c499d97b-f322-5fb7-993d-8cbbe0ad1873 | note | 6mm +/- from 3.0m straight edges.
6f0b642b-097f-5dd1-a01a-8fb6189a8529 | checkpoint | If an as-built survey is required, confirm Surveyor is out next day to carry out survey of finished concrete. Attach As built Survey Plan
22a9295a-a3fb-5647-8476-347469c13ca7 | checkpoint | Obtain all concrete tests at 7 days. Attach to ITP
24390ce6-c799-50dc-918a-2e7ec4d213e2 | checkpoint | Obtain all concrete tests at 28 days. Attach to ITP
00237665-de82-5d74-8b32-4d8f3713f8cc | signoff | Final ITP Review & Sign-off by Project Engineer
ed8b12e6-9cfb-5118-b392-c2f5473e3c11 | checklist | 101C-SDC-TMP-CON-ITP-008 - 3 - Suspended Concrete Slab |  | 101C-SDC-TMP-CON-ITP-008 - 3 - Suspended Concrete Slab
295f5594-f977-5cf3-a95e-1b914b0e80c5 | section | Prior to Formwork Deck Handover
5ba4bfda-bc99-56cf-8b8b-2996c4f9926f | checkpoint | Current Drawing Status - Refer Aconex Document Register for latest approved Shop Drawings. Record drawings used at time of pour on ITP.
414a16c9-2639-5e6c-a7e0-d5bd95d1a1b2 | textbox | Architectural Drawings
64b36330-3896-594a-8a03-fea7244cd31d | textbox | Structural Drawings
2dbeafe4-65f8-590f-a07c-dd1d8baa5d09 | checkpoint | Concrete Mix Design
d2a3248f-b14a-5d59-99dc-49bd2ea3a66d | textbox | Confirm Mix Design
41c99b98-0067-5b53-98db-86509393965f | checkpoint | Set-out - Surveyor set out slab grids to allow formwork construction
bf140f59-99b4-5b36-96dd-09ee09530581 | checkpoint | Survey & Set-out of formwork correct. Check correct heights for formwork soffit, Top of Concrete (TOC) and falls
f4cce657-83ef-543b-8341-1965af65a402 | note | Attach Surveyor Formwork As-Built to ITP
8e1a66ad-611f-5f80-9a67-1faca5fe1a19 | checkpoint | Site Instructions - Copies of design changes, emails and site advices and the like to be attached.
100f5dfe-8ec5-59b9-910c-f68c280a8190 | checkpoint | Bondek (where applicable) - Back propping installed for pre pour and deflection & gaps sealed to prevent dripping
e0fe376b-a421-5e7a-882b-8c272a18b689 | checkpoint | Structural Steel Sign off from Steel installer and Structural Engineer (where applicable for bondek slabs)
1a7b7757-785d-5271-a047-9317f30cb7cc | checkpoint | Formwork Sign-off - Area cleaned of all excess formwork, sawdust, reo and debris prior to pour. Safe Access to deck available.materials before handover deck
caca8116-cf42-5015-b1a0-9143a8395eb9 | note | Attach formworkers ITP (referencing all hobs, steps, cast-ins, HDB's, bearing strips, polystyrene, fillets, etc… installed correctly)
e895f0c4-445d-5222-83aa-ee6b071b56fa | section | Prior to Concrete Pour
dfa84113-61be-5071-a599-4bfa7da4d22e | checkpoint | Structural Compliance - Engineers approval for concrete placement required with list of defects to be completed
da6340f8-c775-55da-95ed-ff85d07b1b95 | note | Attach structural engineers inspection report and evidence of close-out
718b0a37-0bd9-5d17-b022-13f4506ee88c | checkpoint | Formwork Engineers Sign-off - Attach Sign-off
bc6540fd-d9b4-5bb0-903f-90a9e8eb0ee3 | checkpoint | Post Tensioning - Check Subcontractor ITP complete, and attach to this ITP.
14d9e1fd-3501-5226-a3bc-f01df740ab71 | checkpoint | Screen Needle Cast-in's - Inspect all screen needles are installed in accordance with relevant shop drawings
90bcdc10-a2cb-5816-8a8f-646586fefef7 | note | Attach sign-off from Formworker
5e6c0c26-c34c-5155-82d8-95ade4979701 | checkpoint | Curtain Wall Bracket Cast-in's - Inspect all Curtain wall brackets/rebates are installed in accordance with relevant shop drawings. Surveyor to confirm locations are correct.
3b8ee292-84cf-53f9-b316-0ba3bccd1b41 | note | Attach Curtain Wall subcontractors sign-off & ITP from formworker
fbf3fa70-7e97-51f1-84c5-a73c5ecf2ebb | checkpoint | Crane/Hoist Bracket Cast-in's - Inspect all hoist and crane brackets are installed in accordance with relevant shop drawings. Surveyor to confirm locations are correct.
7af1ed1e-1c1b-57d0-b260-f29d39cfedfc | note | Hoist and Crane contractor to inspect and sign-off cast-in position.
fb2866ee-56ac-59c4-8bf3-33914cc7ebf4 | checkpoint | Temporary Penetrations - Inspect formwork penetrations in accordance with temporary works design. Surveyor to confirm locations are correct.
0c469f09-ebc8-59d0-b762-2ae84293d11d | note | Temporary Penetrations may include: formwork hoist, concrete boom, etc…
adb4d0e8-65a6-5de3-ac58-c795f4505cad | checkpoint | In-Slab Services - Electrical subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
20504b08-0515-5b97-8bbb-92856bce0c8c | checkpoint | In-Slab Services - Hydraulic subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
09a073b7-597f-507f-a4c5-18c36fd14628 | checkpoint | In-Slab Services - Mechanical subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
712acdc7-b4a7-52f0-a901-c68540c44cdc | checkpoint | In-Slab Services - Fire Subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
236453d7-a578-5c50-93a0-18a68dbd4dc6 | checkpoint | In-Slab Services - Security Subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
57f69192-958a-57f3-8f3c-a9e497f8f688 | checkpoint | Formwork Cast-ins - All timber fillets, drip grooves, Rebates, and proprietary shear connectors installed as required
c7e06a37-79f9-5353-8059-3f145d6d5f46 | checkpoint | Starter Bars - Confirm all starter bars for walls and columns installed as required per structural and architectural drawings and survey pins
d00e631c-e50c-574a-9aa3-68412fd9553a | checkpoint | Water Stops - Confirm installation of any proprietary water stops as required (ie; at CJ’s, etc…)
855ff8fa-6730-557a-8e52-d106ec75c5bb | checkpoint | Reinforcement Cover - Check top RLs for all reinforcement, ensuring adequate concrete cover. Confirm with Concreter. Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits.
d514d25d-afda-56c2-8c36-6209bbcfd564 | checkpoint | Attach Reinforcement contractors ITP
dcb336a8-fd09-5bfa-873f-07af8cbbf30f | checkpoint | Concrete Falls - Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary
b46d41a8-a2f6-5a67-a3cb-589bf5128ea3 | note | Cross-check the following drawings: See Hydraulic, Architectural Concrete Outlines and Structural drawings
37c28923-04ce-5966-8fbd-571b16e9c359 | checkpoint | Cleaning of Deck - Clean off decks and beams prior to pour and ensure all exposed off-form soffits are free of any dust, stains, and rust marks. Hose down if necessary.
2855ee05-1267-5a52-b798-36451d292a8f | section | During Concrete Pour
a996b133-8d9b-53cc-af5e-c4d995eba206 | checkpoint | Concrete Placement Checklist
a8cc6a45-5839-5efc-8114-c275f597ccd4 | tickbox | Structural Engineer & Formwork Engineer Sign-off Received
cc282e2e-0a8a-53d7-8509-60b3247b8396 | tickbox | Confirm Delivery Docket References correct mix design
70a5305c-d905-57b1-9576-84907c01aa12 | tickbox | Plant and equipment checklist completed on concrete pump and lines
fd542543-8855-5fc8-9478-f16a999c8b62 | tickbox | Confirm concrete tester on-site and correct location of concrete pour provided to them for test results
efd491ba-0a05-58ff-87af-b27f9097431b | note | 1, 4, 7, 28 & 56 day compressive test results to be issued by batch plant
f8f5594c-c38c-5d78-a8b6-38ab0fa98b6c | checkpoint | Concrete Finish - Ensure concrete contractor is aware of required concrete surface finish.
c1e85569-9cbf-50e3-9b95-e4470c2fbcbc | checkpoint | Slab Curing - Check cured when bleed water stops and able to access slab without marking and also amount used complies
14e178fb-fe69-52a0-91f6-30076e8b4f0a | checkpoint | Concrete Falls - Confirm concrete has falls to drainage points in slab.
e1d73840-aa9f-57a4-b903-c73dee258910 | checkpoint | Attach Concrete Place Contractors ITP
a2dc03bb-a611-5d28-91e4-bf1fb10f9020 | checkpoint | Trade Representatives - Ensure a representative from each of the following is on site and witnessing the pour:
158e4fe0-f043-5003-8978-c52840fb3055 | tickbox | Form Worker
9b437c7e-a121-5e39-82d9-f3da15ff1195 | tickbox | Electrician
281e0d71-ebf6-5950-8500-3260adc89826 | tickbox | Plumber
81f29997-bbcc-5986-aece-fa078c429731 | tickbox | Post Tensioner
2192aa73-f6ba-58af-8c61-4895a7d428fb | checkpoint | Confirm Form Worker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry.
0c36bc32-cf0c-5072-977b-380ad8510aaa | section | After Concrete Pour
08728e08-995c-50af-a2ec-d7e14671870a | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete. Attach As built Survey Plan.
f886350e-a086-5135-9a70-b777886af386 | checkpoint | Confirm tolerance of finished concrete surfaces are as follows:
face7fb6-ab6d-5c94-837f-569ba0859243 | note | 6mm +/- from design RL
a2342f2a-44dd-5caf-9dae-727bb7d88ed6 | note | 6mm +/- from 3.0m straight edges
1495d922-a480-534f-b717-6368bad185b9 | checkpoint | Exposed Concrete Finish - Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610 (Class 1, 2 or 3)
73a62edd-f785-5a3d-9a66-3aa541d7b88b | checkpoint | Concrete Test Results - Note test results on ITP and attach:
e21d473f-6711-5330-b779-31ec2e2d4259 | textbox | 1 Day
16cd5736-3c0d-5d08-9e27-1df61d0cb2f4 | textbox | 4 Day
a9ec48f5-2664-5170-8410-9484e3767dcd | textbox | 7 Day
4ba85b4c-7e76-5cb7-8b48-b59b3a6f79e7 | textbox | 28 Day
3d932226-c9fa-5f7a-b3ab-393eef268526 | textbox | 56 Day
a376cbd5-1e22-5251-a5f8-f870a953ef4e | checkpoint | Initial Stressing - Concrete has achieved required strength MPa (10 MPa and confirmed by Concrete contractor)
3fde47b1-83ee-5b0d-a635-1aeaaf6e5f29 | note | Concrete Contractor must issue Concrete test results, verbal not accepted
41f18e67-7d4a-5d5a-bb7e-80b7411ea4ea | checkpoint | Final Stressing - Concrete has achieved required strength Mpa (22 Mpa and confirmed by concrete contractor)
fb420cbd-4d1c-531a-b340-8329ceb1ceb0 | note | Concrete Contractor must issue Concrete test results, verbal not accepted
14b415dd-206b-51ad-b6fb-ce3037f86b3e | checkpoint | Stressing Sign-off - Before stripping can commence final stress complete, Ducts grouted and PT supervisor issues verification records
b0d0a74d-cc56-5c59-a817-3330d3757394 | note | Attach Post Tension Contractors ITP
77c98c2f-53b9-58f0-b5d3-8207838ca4b1 | checkpoint | Extension Records Approval - Engineer approval of extension records following final stress
82c227c8-9b47-50fb-a877-577c22bf013c | textbox | Record date when props were removed if not given approval by engineer
9d87b967-2d49-5717-80ce-42ebdedfe8b2 | checkpoint | All non-conformances closed out and accepted by Structural Engineer and Architect.
d36b933e-9fa1-5bbc-9958-546e8775e762 | signoff | Final ITP Review & Sign-off by Project Engineer
f6a5c7af-f1b9-507f-a362-917e1f217e43 | checklist | Drawings / Documents |  | Drawings / Documents
4bc77cd6-9d40-51f4-8256-9a9a5678f72e | checkpoint | Approved Drawing Available
930650b9-75c9-5801-a4ac-91ee5b7ba5ea | checklist | Equipment Delivery Verification |  | Equipment Delivery Verification
6e0cfacf-0d3c-5f02-a166-0621d86748f2 | checkpoint | Sighted by Scentre Group
9ae1e040-7347-5de9-ba64-2ddbe16e0fdb | checklist | Fit Off |  | Fit Off
65bb7672-4129-578f-b8fb-8cf65df069fa | checkpoint | Approved for Sheeting/Closure
58c21034-a47c-56f0-916f-740cf50ca21b | checkpoint | Fit Off Complete
284fff2a-2f33-5df4-b719-243b5d703ba4 | checklist | Framing/Sheeting |  | Framing/Sheeting
1530de07-be34-5ea4-9be0-034b905e4913 | section | Survey/Wall Framing
23e408dd-5135-5585-8838-3938629743f7 | checkpoint | Confirm set-out of walls in correct locations & cross check with surveyors grids.
bf593cf7-e545-5d09-9b0b-ec0e6373d66f | textbox | Confirm wall set-out plan/revision used for set-out
a16d87db-338a-538f-a086-c2dff04f4e24 | checkpoint | Confirm that 1m benchmark has been reviewed and agreed. Ensure it is marked on most relevant permanent structure.
172e069e-c65b-54dc-b5a7-1c15435da685 | note | Attach photo of 1m benchmark for reference.
9d89ff1b-c508-5ac3-bd00-4946b21dcaac | checkpoint | Review wall types are installed correctly per architectural wall type details.
b3289e54-f7f4-5040-ae16-579651fe5a19 | checkpoint | Review wet area framing to ensure square and plumb to take tiling.
2475c618-869c-5955-91b7-ed342460614d | checkpoint | Strengthening Requirements - Confirm all noggins, trimming blocks and struts have been appropriately installed to support the following items (Min. 12mm structural plywood). Ensure to cross check relevant drawings:
2c5a047b-960f-5c5f-aa3a-0cb88c8cc8cb | note | Appliances (Wall mounted dryers, etc…)
c1b1f60c-6dc9-5f9a-8745-995ef2938d45 | note | Bathroom Accessories (Robe hooks, towel rails, shower shelves, toilet roll holders, adaptable handrails, etc…)
925b3429-826e-5c1e-b9d5-42f3bd35a048 | note | Bathroom Furniture (Mirror Cabinets, Vanity Basins, shower roses, etc…)
3d0db52b-01eb-5cce-8cbf-3a3679aa89de | note | Services (pendant lighting, display screens, TV areas, etc…)
adce8afe-bf59-540f-a059-012355501f0e | checkpoint | Adaptable Apartments - Check blocking installed to cater for post adaptation layouts
1f6ff53a-205c-5f4d-9e46-ea4d22ee9c5f | checkpoint | Confirm that all framing is square at corners (check top, middle & bottom of frame junctions)
08416204-8429-568e-afd7-c9fa6e7deb30 | checkpoint | Confirm studs not bridging or touching hydraulic pipes, mechanical units, columns in intertenancy walls or lift shaft walls to ensure vibration is not transferred through walls
f50e86d9-dd83-5f11-aa50-b871c9ce3f96 | checkpoint | Deflection Requirements - Ensure gap is present (10-15mm) at top of stud inside head track
7dc97a50-13d3-5d72-a8a4-3e023ea7fc7a | checkpoint | Joinery Openings - check gaps between framing to joinery + wall finishes will fit (5mm tolerance)
a9f86b22-e357-52ed-8b42-f7e8c3cec071 | checkpoint | Stud Spacing - Spot check studwork is spaced at 600mm maximum per Architectural Specification. Check additional studwork reinforcement at openings (ie; double studwork).
39866e90-f81a-57a8-a328-13140080c264 | note | Staggered Studs (if required) - to be installed at 300mm centres alternating per architectural specification
800c99ae-fb54-518e-8b80-7904c5f20f9d | checkpoint | Movement Joints - check walls are discontinued where they pass over building movement joints.
0fb9cac1-74f6-5835-97fe-e2f3275bfea0 | checkpoint | Services Risers - Ensure stud and trackwork is kept a minimum of 20mm away from vertical services within risers per acoustic specification
7b5c79f8-64ee-516a-84e0-855baefc7c2d | checkpoint | Engineered Designs - Spot check any engineered framing designs and attached engineers review and sign-off on system.
62a0e57d-2239-53a4-ac18-f77d094f5587 | section | Wall Sheeting
120a946f-ec6f-599e-bb9b-b8960ce99ed1 | checkpoint | Confirm acoustic/thermal insulation installed to achieve design ratings
9214adb6-d2ff-5660-8c6b-148031b3d64c | note | Cross check product ratings against architectural insulation plans
89c41d83-a979-5103-9f52-baa51290c96e | checkpoint | Confirm there is a minimum of 45mm cavity (or 20mm where double sheeted with recessed skirting shown both sides of wall) between the residential intertenancy wall studwork per Acoustic Details/Wall type Plans
4dd07011-91a4-5458-83e3-bb6a7828e05b | checkpoint | Confirm door frames are installed vertical and plumb and at correct height.
6dd1553e-b07f-5f38-8ad6-7ad960f7ad18 | note | Check metal door frames in wet areas are outside of membrane zone (ie; notched accordingly).
fdf1f2cb-3f25-5dac-8ad1-e2d57b621fdf | checkpoint | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting walls
cf6a3ad0-9bac-535e-bb27-643a2e2def4c | signoff | Review & Sign-off by Acoustic Consultant
3406cd78-db00-5dcb-bfaa-92bc3b90dba2 | checkpoint | Check plasterboard sheets installed with 10-15mm gap at top and bottom to allow for deflection and fire sealant.
f70875dd-ec8f-5405-a8b4-37e1f96d5b9a | checkpoint | Control Joints - Ensure controls joints installed in wall runs larger than 12m in length.
ac438481-ab6e-51d7-9fcb-8324a93b993c | checkpoint | Check correct plasterboard linings installed (type and thickness) per architectural wall types
3ffd3315-cf0c-5aa2-a990-9022ef15a0b5 | checkpoint | Ensure sheets are staggered on multiple sheet layer walls. Stagger all sheet joints by minimum 200mm per architectural specification.
1fcf115e-b487-5f8b-8f9d-3eb3e9c1ee8a | checkpoint | Confirm plasterboard lining installed to wet areas are sealed up to concrete soffit on both sides of wall where adjacent to habitable rooms.
9736503d-c21f-51e6-96ba-c5b04f89b1fc | checkpoint | Confirm all services penetrations through wet area walls adjacent to habitable rooms are sealed and caulked for acoustic performance.
2e46ccf7-7f4f-5172-a94e-48007bf168d3 | note | Check that mechanical flex ducts are not passing through walls - to be rigid ductwork or sleave installed over.
1eaaba03-6b1a-5154-a302-05cc6d20387e | checkpoint | Check intertenancy walls extend to façade panels, leave 10-15mm gap and caulked with fire sealant.
c36a4af9-d9b8-548b-9b4c-a4ee2b6c587b | signoff | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting
ee010fbd-1046-56c5-b493-1d37862a0f5a | section | Sheeting Ceilings
1f688c69-de7d-5db6-9592-47ca2fce1731 | checkpoint | Confirm ceiling insulation complete where applicable
94e08ce9-c2d6-58ed-a243-14d3407f27c2 | checkpoint | Confirm provisions made in ceiling framing for access panels and air grilles were required by architectural RCP
7fdffaac-406b-5801-bef2-6361fc7b31f7 | note | Spot check access panels installed to allow access to fire dampers and mechanical fans
036d84fe-11bd-5ad9-ab55-b8fa4ef58f5a | checkpoint | Confirm ceiling framing bulkheads are square and level
4e88e007-6712-548b-af61-90634071bf08 | checkpoint | Confirm furring channels do not clash with other services (eg; downlights, access panels, mechanical exhaust, sprinkler heads, etc…).
6d815a4b-f7ea-50d6-8d30-a42333b3b1fe | checkpoint | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting
82729cd5-dd85-5ad5-8e66-822a52f5bab6 | signoff | Review & Sign-off by Acoustic Consultant
e217164f-af7e-5616-bd19-3343bb541cc7 | checkpoint | HOLD POINT - Confirm BCA consultant inspection of services penetrations through fire rated walls prior to sheeting ceilings
894062ba-2286-5c42-97a3-5edb7e8965e2 | signoff | Review & Sign-off by BCA consultant
f2dee40a-a9fb-576d-a20a-9675ba9b5e42 | checkpoint | Confirm Plasterboard fixings are at correct intervals
47cc8396-5364-55eb-8c95-5ebafa007f1a | note | For painted surfaces, screw fixing onto sheeted frames should be max 400mm spacing. Refer to Manufacturer’s Installation guide
53c9c7bc-564d-5ce9-8daa-a26dc6b32637 | checkpoint | Confirm Villaboard/FC (wet area) fixings are of the correct intervals
be026fdc-1154-5e26-8d0d-16328c8b72b7 | note | For 9mm Villaboard/FC: Tiled wall screw fixings must be max 150mm spacing. Stud centres to be 400mm. Refer to Manufacturer’s Installation guide
49327a45-bf8d-5b9f-bcb8-d2eef0571ecf | checkpoint | Control Joints - Ensure ceiling bays are not larger than 10m x 7m without a joint or wall break.
1f79f360-0ac1-56e2-8b33-690dce63e2a6 | checkpoint | Attach Subcontractor ITP for the Works
c76b51ab-6264-5b4b-ab7d-fd597107fe72 | checkpoint | HOLD POINT - OK to proceed to painting
b4d64f56-0ea4-5b50-a1c8-90071a066939 | note | All defects completed?
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
731c5a83-9e8c-56bc-8a93-11110847dcef | checklist | Level Compliance |  | Level Compliance
a41e79a4-7f72-5f55-8786-436198c5996a | section | Fire Rated Plasterboard Compliance
7c6e7729-f341-5150-9cf6-7f5a10583dba | checkpoint | Attach Manufacturer Inspection Report for the level
19c4b854-f4c7-533d-ad9e-d27db011ed47 | checkpoint | Confirm all outstanding items have been closed out
1dcf1d61-3fff-5e6b-9d6d-1ac14ad15322 | signoff | HOLD POINT - Attach Close-out Confirmation & Photos
36938e10-e0fc-5dc3-bb4d-2631c4ef88a1 | section | BCA Compliance
d8990e0a-d3a7-5776-b5ac-a53f996c067a | checkpoint | Attach BCA consultant fire compliance inspection report for the level
17659379-d4fa-4ef0-beb4-a7d71b436e2c | checkpoint | Confirm all outstanding items have been closed out
0ce5d74e-1434-5e56-a191-118d4e0290f9 | signoff | HOLD POINT - Attach Close-out Confirmation & Photos
f1cc1083-7799-5321-92f5-429a392ffd2f | section | Acoustic Compliance
47609e99-82df-5220-a259-29403d261744 | checkpoint | Attach Acoustic Consultant Inspection Report for the level
ab349b97-4861-455f-a927-c0031cd3e0d3 | checkpoint | Confirm all outstanding items have been closed out
dced4df1-76aa-5350-8767-ff330427bd32 | signoff | HOLD POINT - Attach Close-out Confirmation & Photos
7410247b-6cb7-5ac5-89fe-8933345d8f96 | checklist | Rough In |  | Rough In
1a3a7a37-3b0d-55d1-a54a-28e5deae7542 | checkpoint | Rough In Complete
68578234-762e-519f-bcca-532b1d0b8897 | checklist | SDC-TMP-CON-CHK-013 - B - Void-Riser Closures |  | SDC-TMP-CON-CHK-013 - B - Void-Riser Closures
674045f6-1811-58fe-b909-b838b50d6fb9 | section | Void/Riser Information
8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint | Details
0a851e7e-9fdc-54c0-9d78-75a3866dfd6d | textbox | Location of works
8e64d65d-5cf5-5996-89f3-35729946d8bc | textbox | Floor/Level
bff878db-f23f-5638-8dae-2729d422ddec | textbox | Riser/Void Reference #
53dfffaa-c1b2-5070-99f6-9d8e42b3fdae | section | PRE-CLOSURE
5eda8520-35b8-5b64-bcfb-e05834aab6c0 | checkpoint | Electrical
ed3ca5bd-ca61-538e-be9c-a80ace300a77 | note | ACTIVITY: Electrical services
bb0c17f0-d6a4-582d-accc-334baa7f7dd5 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
ca261955-6124-5a29-9307-680aa333ac8f | signoff | Subcontractor/Consultant Signoff
4626e0e9-f132-5211-8a3b-572771fd2c23 | checkpoint | Mechanical
7e3d5c21-721c-5f10-93d9-dd56dfd04598 | note | ACTIVITY: Mechanical services
b3e4112c-9522-527a-8312-43aeec0d7484 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
63c06ab2-385a-5295-833e-d1cc808390bf | signoff | Subcontractor/Consultant Signoff
8cde4215-2128-5176-88bf-1b9292e62799 | checkpoint | Plumbing
6ff207e2-9ad8-5526-8abf-90b30fcf37f0 | note | ACTIVITY: Plumbing services
045af96b-848d-5bab-978c-0113707bb246 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
1114a46a-5773-5910-b2ac-ab04f9c5c75f | signoff | Subcontractor/Consultant Signoff
6fcc9299-d65a-579a-a73a-5cd4b959f824 | checkpoint | Fire Dampers
18e56a68-aee2-53d9-a697-32c104067a95 | note | ACTIVITY: Fire dampers installed
be09255d-6f5d-58f3-a218-a2cea0d666fb | note | REQUIREMENT: Fire dampers have been installed in accordance with Australian Standards, drawings and specification
021d7010-f484-5f0e-88fa-b23d9464758f | signoff | Subcontractor/Consultant Signoff
ef955797-bb0d-581e-ad8f-cdcccec5167f | checkpoint | Fire Services
0c745462-c39c-54b7-abb5-33fb98f49c2c | note | ACTIVITY: Fire services
5d1e275a-ff8c-583b-845e-d1cf8d6592e8 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
6bd8de6a-ef2c-5d36-bcb3-274d42be31d4 | signoff | Subcontractor/Consultant Signoff
74ec88cb-324f-562b-8366-92adfb76bc5a | checkpoint | Plasterboard Trade
2def0b4e-2bec-515d-98c9-13173f4d9f86 | note | ACTIVITY: Riser Construction
35347ca0-8b1f-5ab4-9415-7cf9029382e6 | note | REQUIREMENT: Riser construction and sealing has been completed in accordance with the drawings and manufactures guidelines
90a26ca7-975f-5f6d-8640-4ffd09a22101 | signoff | Subcontractor/Consultant Signoff
a0698adb-adac-5ae4-8135-6a0b50fb8bf7 | checkpoint | Fire Protection
e64d72fb-ddd5-54a6-9613-704512de951c | note | ACTIVITY: Fire Spray
fb8c9aa0-1238-5dda-a666-911a2c1b88a2 | note | REQUIREMENT: Has been completed in accordance with the drawings and specifications to services & structural elements
893c336f-97f9-5b70-a5ac-37df76fa1c47 | signoff | Subcontractor/Consultant Signoff
fd26e2a4-96f8-5680-878b-9a0801bf78e5 | checkpoint | Structural
a2c00c59-cf34-5f19-806c-68c227ae2a64 | note | ACTIVITY: AECOM Engineer
cc68cd98-5c3e-5560-8096-c8dfdde71c0a | note | REQUIREMENT: New Structural elements have been inspected and signed off prior to closing void/riser
eb5406d9-514d-5f55-9f7f-8f3a06a9cb5f | signoff | Subcontractor/Consultant Signoff
bb881818-3c86-5830-bce8-defa8a1d3906 | checkpoint | SDC Builder
15c6061f-90b6-5485-b44c-135fe0e72143 | note | ACTIVITY: Pre-Closure Photos
89559dcb-7f86-598b-a980-04c685aaf080 | note | REQUIREMENT: Attach photos for record of riser internals pre-closure.
23f868fa-85d2-5e62-a476-c053d0679cbb | signoff | Subcontractor/Consultant Signoff
0641b5bd-4539-5e41-86c8-d846851f2be2 | section | POST-CLOSURE
7e86647e-3212-52e6-82b4-bc6467720616 | checkpoint | Acoustic
211af32d-80ed-510f-a856-6ee94198847a | note | ACTIVITY: Inspection
46e95309-96ad-57de-817e-5e7ed55650c7 | note | REQUIREMENT: Acoustic inspection carried out where required of riser construction & insulation. Attach report.
e511fa89-ebbb-52a8-ba59-9855dd3ef121 | signoff | Subcontractor/Consultant Signoff
855621a4-2f21-5aef-a16f-6e7f0dee9f12 | checkpoint | BCA
be310d74-87d8-58cd-b53b-5ed627b5a624 | note | ACTIVITY: Inspection
b9f72734-ac01-5ef3-b049-e350f84491b2 | note | REQUIREMENT: BCA Compliance inspection carried out on riser construction and services penetrating where required. Attach report.
86c98323-cbad-5472-b985-dadb4ad96b9a | signoff | Subcontractor/Consultant Signoff
51cd79a8-35c2-557c-a9d3-b3abeb51ec76 | checkpoint | Scentre Group Consultants
b28506f4-68d2-5626-a5b1-b1dc1dc3af57 | note | ACTIVITY: Defects
bf893f0e-a776-5eb6-9773-cef955ac1b5d | note | REQUIREMENT: All defects identified during SDC and consultant inspections have been rectified
82bd51c3-ea41-5971-984a-2ad0b7160a09 | signoff | Subcontractor/Consultant Signoff
036eb850-7bf1-591d-aeba-77b443cf9716 | checkpoint | Final SDC Review & Sign-off:
56eae728-9f58-599a-9ef2-8e79a5ba9d92 | note | The Void/Riser cannot be closed off until ALL sections above have signed off
fa35e456-d74b-5039-adb6-ba057493523d | textbox | Name:
4c7943a6-7231-507c-a580-0ba6fded9705 | date | Date:
1223a7af-ece6-5d8a-b4d8-512c3c67f999 | signoff | Signature:
5d9eac43-a20a-58d4-bb7e-7572843c389d | checklist | SDC-TMP-CON-ITP-006 - 4 – Pits, Pads and Strip Footings |  | SDC-TMP-CON-ITP-006 - 4 – Pits, Pads and Strip Footings
2f9bce0e-f342-5d28-97b0-6393c8a55b69 | checkpoint | Prior to Concrete Pour - Attach markup structural plan identifying footings relevant to this ITP
5cbc8690-cff0-55e9-8cca-b705cdef437a | checkpoint | Prior to Concrete Pour - Confirm surveyor has provided setout for pad footing excavation (attach survey setout plan)
5436674b-8e8a-5e6b-b10c-cba6a6bf7fb7 | checkpoint | Prior to Concrete Pour - Attach Geotech engineer bearing certification confirming approval of substrate complying with engineer’s requirements
1c991607-4f56-555a-89b1-9b45f1738387 | checkpoint | Prior to Concrete Pour - Confirm that either pre- applied membrane or Forecoin plastic has been installed to comply with electrolysis study (attach photos)
56029564-4096-5e57-9d07-bdb38a0b4660 | checkpoint | Prior to Concrete Pour - Confirm excavation is free of debris and loose materials to walls and floor prior to handover (attach photos)
0d58d1b2-c79f-5215-88e2-0cc362dfda8d | checkpoint | Prior to Concrete Pour - Attach reinforcement contractors ITP (incl AEFAC Accredited installer signoff of any drill and epoxy bars to comply with structural engineer details)
c4c66113-3c19-5714-af47-52d082b8f135 | checkpoint | Prior to Concrete Pour - Confirm wall starter bars have been installed in accordance with surveyor setout and architectural outline drawings.
b7a7ce8f-94bd-564f-a988-100948dba2c9 | checkpoint | Prior to Concrete Pour - Attach signoff from CFT Column contractor inspection approval of starter bars, castins and hold down bolts
689e3c27-65a8-5151-9c67-3d9e745f6bd1 | checkpoint | Prior to Concrete Pour - Attach waterproofing contractors ITP confirm tanking waterproofing and PVC water bar has been installed(attach waterproofing ITP)
5b05355e-515b-50fd-a85f-da522e94e86f | checkpoint | Prior to Concrete Pour - Confirm that waterproofing consultant has inspected works and defects closed out
393b9469-2ff9-5e2c-a713-4c2800a8b1d1 | checkpoint | Prior to Concrete Pour - Attach hydraulic contractor's ITP confirming completion of any cast in as per hydraulic drawings
36c2f93a-d172-5030-ac87-a7b742d72372 | checkpoint | Prior to Concrete Pour - Attach formwork ITP/Signoff that all formwork to kicker has been completed (sump, hobs, edge boards etc)
23f9823d-9165-5cbc-b486-45bec2c97cb3 | checkpoint | Prior to Concrete Pour - Attach structural engineer’s inspection report
0bae1477-c557-5713-9c1c-ab264bc81b77 | checkpoint | Prior to Concrete Pour - Attach verification that structural engineer’s inspection report has been closed out to allow concrete pour
03664712-ddd0-5227-a828-de0e778194e9 | checkpoint | Prior to Concrete Pour - Confirm concrete place contractor's order complies with engineer's strength of concrete, waterproofing additive and testing requirements
705f0048-4a1b-55cf-a516-2c79242e1568 | checkpoint | Prior to Concrete Place - Attach photo of formwork setting the level for concrete place contractor
a40d7920-2900-5a09-9d3a-c075149f15fb | checkpoint | Prior to Concrete Pour - Attach concrete place contractor’s ITP
ecfe7831-c974-5fc6-a6c6-a2bc6ff39ff0 | checkpoint | After Concrete Pour - Confirm RL of poured footing complies with design RLs
18b2f80b-a9dc-5dc5-84fc-4ef33e8b2fac | checkpoint | After Concrete Pour - Confirm integrals falls have been completed in concrete to sump
d1268640-08dd-5ff8-831f-cfa97381e791 | checkpoint | After Concrete Pour - Attach concrete test results and confirm compliance with engineer requirements
137abde5-83cd-5168-8e4e-54503cda813f | checkpoint | Signoffs - Site Engineer to signoff ITP has been completed
1c58e575-642e-591d-a72e-03542ab08ffd | signoff | Signoff by Site Engineer
82b25620-11d2-5998-81ad-7c3846b7c749 | checkpoint | Signoffs - Project Engineer to review and confirm ITP has been completed
df67adf2-4fc5-5a7f-a46c-4c434bcbae4c | signoff | Signoff by Project Engineer
ab703c7d-344b-55a2-b416-d63f349afedd | checklist | SDC-TMP-CON-ITP-009 - 3 – RC Slab on Grade |  | SDC-TMP-CON-ITP-009 - 3 – RC Slab on Grade
1016cafd-6acf-571f-ac71-3cb8a976bf9e | checkpoint | Prior to Reinforcement: Attach Markup to confirm proposed pour zone
c746958f-18c2-5b88-9267-282c5f2ff901 | checkpoint | Prior to Reinforcement: Ensure detailed excavation is complete (Attach Excavation Contractor’s ITP)
f3366dfd-be73-517e-88c1-d99b51a3b6bf | checkpoint | Prior to Reinforcement: Confirm inground drainage and pit works has been completed and backfilled (Attach photos/confirmation)
5d52083a-02b1-5f2c-b7d9-29acec531ac3 | checkpoint | Prior to Reinforcement: Confirm that substation earthing rods have been drilled, as AS Built red line survey (If applicable)
d0ddcecc-e0ad-532b-bc76-5e76697c7162 | checkpoint | Prior to Reinforcement: Confirm min 100mm subsoil drainage has been installed as per geotechnical requirements (attach contractor’s ITP)
157ad683-bed3-56ab-97ef-51297160451f | checkpoint | Prior to Reinforcement: Confirm Surveyor has provided set outs/ benchmarks (Attach survey)
836f1ac7-3a33-5e1f-a567-3bc0592b1dae | checkpoint | Prior to Reinforcement: Confirm vapor barrier installed over subbase (Attach photos and confirm signed off by concrete place ITP)
4e697d51-962b-566c-bcd0-d76b289fb6e2 | checkpoint | Prior to Concrete Pour: Attach formwork contractor’s ITP (including setdowns, hobs, Construction/key/movement joints, ect.)
a70fb6bd-eaf5-505a-99e2-58527cbe5552 | checkpoint | Prior to Concrete Pour: Attach Structural Engineers inspection report
7afc412e-ba5c-52a8-97ea-0b5df4b87d47 | checkpoint | Prior to Concrete Pour: Attach Verification that structural engineer’s inspection report has been closed out to allow concrete pour (Attach Photos)
cd89edb7-fd58-5b38-94c8-3f0b6b2a3fda | checkpoint | Prior to Concrete Pour: Attach reinforcement contractor’s ITP
6d802568-2619-55e4-aac7-1cf8c6aca57c | checkpoint | Prior to Concrete Pour: Attach Hydraulic ITP (inground drainage and pipework)
d8dcf4a0-b680-5249-8a34-a308ac4896b2 | checkpoint | Prior to Concrete Pour: Attach Electrical ITP (Cast in conduits – if applicable)
78bdbd68-2c65-59de-ba08-e001107f40e0 | checkpoint | During Concrete Pour: Attach Concrete place contractor’s ITP (including Ableflex)
139a7b0b-3f18-5520-9495-79eb677d9440 | checkpoint | After Concrete Pour: Confirm falls have been completed in concrete pour in accordance to architectural drawings
099c4975-b6b9-5b67-af16-0ea6e4436487 | checkpoint | After Concrete Pour: Attach Concrete test results and confirm compliance with engineer requirements
68778255-61cf-56c8-81ab-23491075806f | checkpoint | After Concrete Pour: Confirm saw cuts installed as per engineer’s drawings
e3e5caf5-ca8b-5cac-8f12-0107ce5f41d6 | checkpoint | Signoffs: Site Engineer to signoff ITP has been completed
65719930-6c62-5d71-b865-8649e3555c77 | signoff | Signoff by Site Engineer
8c89fabc-4a87-55c4-80f0-00a867ff6e56 | checkpoint | Signoffs: Project Engineer to review and confirm ITP has been completed
8e6f285f-0a26-541f-a696-99853c5fa269 | signoff | Signoff by Project Engineer
d6dd6cc9-7451-53c8-9afb-ac79a715be16 | checklist | Services Rough-in - Electrical |  | Services Rough-in - Electrical
3528a5e7-cde5-54eb-b84e-652dd8e9ec14 | section | Fire Rating
b336a5cc-1f0b-5508-8087-99deabab0b3e | checkpoint | Check 1m benchmark has been set and agreed for services installation heights
7afed001-59d6-5b53-a56b-7de50e2b8ce3 | note | Attach Photo of benchmark for reference
4f146de2-db5d-5e8f-8220-8d0f600dad4e | checkpoint | Ensure services are installed neatly through fire rated walls
d5881ddf-179f-5400-a7c5-9ed443b6b10d | note | Sheet areas of wall where services are to penetrate first (ie; above entry door), then install services to avoid non-compliances with sheeting.
760c0529-6ae4-5c7f-9580-2e3ba34f0f77 | checkpoint | Confirm any cable/conduit penetrating the fire rated walls are sealed on both sides with intumescent fire mastic (conned around cable/penetration)
c2b705f5-5c03-5b9e-bd89-7c3455bfdba1 | checkpoint | Confirm at least 100mm separation between cables/conduits and any other services (200mm form fire dampers) where passing through a fire rated wall.
058cee0a-42e2-5230-8e5e-d947f7b1c68b | checkpoint | Intubatt (Fibre Board Products) used with services
c4d93b3c-5b87-50ec-89ef-de685c471497 | tickbox | Ensure fixings at 200mm centres and washers are visible
438afe03-fd3d-5445-91ab-a5734c7c6059 | tickbox | Ensure exposed edges of the board are covered with sealant to prevent deterioration over time
5904a1f0-34eb-5d08-ad78-b8aa8ec14280 | tickbox | Ensure where service penetrates the board that fire wrap and sealant are used to close any gaps
8d70d19b-64c9-559f-8d46-2047aa8ffb26 | tickbox | Attach photos of compliant installation
c59a31dc-26a0-5b0d-b6ad-6f2b88229aaa | checkpoint | Retro-Fit Fire Collars - Ensure correct size collar for service and that hole around services is sealed (coned) with fire rated sealant prior to installation.
ae8c4b8d-f435-5772-9706-4bd241df1f7b | note | Ensure an Acrylic Sealant is used (not intumescent sealant) when installing around fire collars
df6e5841-5ce9-5f8c-b11e-7827512350e5 | checkpoint | Fire Rated GPO Boxes - Check installation within fire rated walls is compliant
4b00e6e0-2e02-5bcd-8a81-5befcf610533 | note | Max 3mm gap allowed between plasterboard lining and edge of box. Ensure gap is sealed with fire rated caulking.
7f9c2cfd-9728-54bf-beac-2e2b433b369f | checkpoint | Confirm statuatory fire labels are installed adjacent services prior to sheeting. Attach photos for record.
514ad138-da5b-5416-8092-cb6eba8038b1 | section | Electrical Services
6902eb34-5ec2-5ee1-9ac9-8c8b7458143b | checkpoint | Confirm Latest Electrical Lighting & Power Plans are being used with Contractor (Refer Aconex)
d812a557-7e33-55de-b6ad-3a663c861d04 | textbox | Record Plan numbers and revisions
908a5fde-b2ed-5833-86fd-d7faf4cdb8e1 | checkpoint | Typical Electrical Services Rough-in Heights - Spot check each room as follows (centre line of fitting):
779dc2cc-26e7-5dc4-8366-ed81ec379637 | note | Internal GPO's/TV/DATA Points - 300mm AFFL
13c98c9a-ed4c-5c72-a807-1b408742ff46 | note | Internal Light Switches - 1000mm AFFL
c3478372-3bff-51e5-af5b-07a975af818f | note | Home Automation Screen - 1500mm AFFL
a792e140-2981-5af4-ab7f-42bf770cfa3a | note | External Balcony GPO - 650mm AFFL
4ebdd7b3-f717-52f5-96d4-d546576b48a0 | note | External Balcony Lights - 2100mm AFFL
62734545-5508-5dfb-acd3-500577424064 | note | Interface with Joinery Elements - Check against joinery shop drawings to ensure correct location/height
ce4d13b1-6c61-5f49-9775-27bd830645bf | textbox | Record any deviations from typical heights and reasons why.
cd2f5312-0555-550f-8a29-a3242120ee52 | checkpoint | Services Installations - Complete visual check that all wiring for GPO/DATA/TV Points & Light Switches are installed
f91f32a2-d8d7-56f9-b303-b55caff41e6d | textbox | Record any deviations from plans and reasons why.
368ff721-b597-5c97-9b4d-867418284612 | checkpoint | Confirm correct allocation of lighting quantities per architectural RCP drawings and rough-in installed
a5763d0e-2372-5a5a-9aa1-9043b9c9a92a | checkpoint | Confirm NBN cables have been roughed in to correct location & no 90 degree bends in conduit, sweeping bends only.
18507d56-0560-51cf-99c9-eabb0fa51ada | checkpoint | Confirm distribution board has been roughed in to correct location
889e914f-640a-5532-a03e-368f0d9a9e13 | checkpoint | Confirm intercom & home automation wiring in place
53b1d202-ae64-5edd-b5ba-37d89cfaa022 | checkpoint | Confirm power provisions to all kitchen appliances per kitchen shop drawings
2ca74d80-5715-5457-948f-ff4406d5f631 | checkpoint | Confirm minimum 50mm separation between power and data cables (or physical insulated barrier installed). Check minimum 25mm separation between power and gas/water services.
f8c78140-3b73-5c36-8903-057d5f38afae | checkpoint | Confirm Installation of earthquake bracing as required by standard
74e43698-3c35-571c-b024-9b935a9fbfc3 | checkpoint | Confirm adaptable apartment future provisons installed if applicable
6d5e73eb-71d6-5ebb-a7d2-6890e280a7d1 | checkpoint | Services Checking Consultant Inspection Completed prior to Sheeting
84a3209d-f36c-5120-86b0-9900349d9ea1 | signoff | HOLD POINT - Confirm Inspection items closed & Photos attached
b18fcc20-250c-59ee-8c63-45e5fedab012 | checkpoint | Attach Subcontractor ITP
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
e0f6157f-4296-564f-a623-f92224000210 | checklist | Services Rough-in - Fire |  | Services Rough-in - Fire
3528a5e7-cde5-54eb-b84e-652dd8e9ec14 | section | Fire Rating
b336a5cc-1f0b-5508-8087-99deabab0b3e | checkpoint | Check 1m benchmark has been set and agreed for services installation heights
beb33093-babb-5585-a7c2-623a5152e203 | note | Attach Photo of benchmark for reference
4f146de2-db5d-5e8f-8220-8d0f600dad4e | checkpoint | Ensure services are installed neatly through fire rated walls
576fb1f0-a52f-5131-8206-2bc11d1653ad | note | Sheet areas of wall where services are to penetrate first (ie; above entry door), then install services to avoid non-compliances with sheeting.
5669f247-c260-5896-9a08-9146627fe462 | checkpoint | Confirm any cables penetrating the fire rated walls are sealed on both sides with intumescent fire mastic (conned around cables)
2d854f48-63e3-50d7-a158-47f97621e00d | checkpoint | Confirm at least 100mm separation between fire services and any other services (200mm form fire dampers) where passing through a fire rated wall.
058cee0a-42e2-5230-8e5e-d947f7b1c68b | checkpoint | Intubatt (Fibre Board Products) used with services
fe5e220b-9906-5ce3-beeb-d05b781bcccb | tickbox | Ensure fixings at 200mm centres and washers are visible
17f29fce-a7ce-5288-a9d0-52f2697cd9e1 | tickbox | Ensure exposed edges of the board are covered with sealant to prevent deterioration over time
4748f237-0db1-5c5a-bc14-00deccc1bf5b | tickbox | Ensure where service penetrates the board that fire wrap and sealant are used to close any gaps
401ce086-d0e9-5470-834b-4d23f194e950 | tickbox | Attach photos of compliant installation
c59a31dc-26a0-5b0d-b6ad-6f2b88229aaa | checkpoint | Retro-Fit Fire Collars - Ensure correct size collar for service and that hole around services is sealed (coned) with fire rated sealant prior to installation.
ebef81c7-f5dd-54f1-944e-dfab217f76c8 | note | Ensure an Acrylic Sealant is used (not intumescent sealant) when installing around fire collars
8158399f-f65f-5649-93cc-fd1097fdc58d | checkpoint | Check copper or steel pipes penetrating fire walls have fire wrap installed with at least 3 stainless cable ties.
42d95255-538e-5c0f-bdc2-f5da1ef3638e | note | Ensure fire caulking is used to close any gaps around the pipe (coned) at the wall penetration prior and post wrap installation.
7f9c2cfd-9728-54bf-beac-2e2b433b369f | checkpoint | Confirm statuatory fire labels are installed adjacent services prior to sheeting. Attach photos for record.
ef955797-bb0d-581e-ad8f-cdcccec5167f | section | Fire Services
cd2f3467-7930-5634-887c-0ec718c363b5 | checkpoint | Confirm Latest Wet & Dry Fire Plans are being used with Contractor (Refer Aconex)
7ecfb319-7c1d-50ab-b36d-834cbf59c84e | textbox | Record Plan numbers and revisions
4625eb51-35a4-545b-9b40-7a32192eb49f | checkpoint | Service Installations - Complete visual check to confirm all Wet & Dry fire services rough-in is installed per plans (also reference Architectural RCP).
5ee3463b-feaf-56fa-9b12-7b0556a026b3 | textbox | Record any deviations from plans and reasons why.
161d880d-9376-5765-bf7f-f15814012a9f | checkpoint | Confirm all fire sprinkler pipes are charged so any leaks can be identified now and in the future.
01ab428e-7546-5a14-b126-17edfddb0a1a | checkpoint | Confirm any sprinkler pipes penetrating to the balcony are sealed at the external wall/window subhead.
561f6b53-979e-5f25-87a9-1bc152989b20 | checkpoint | Review sprinkler head and detector placement to ensure there are no obstructions to coverage.
21799f0d-c206-50fa-b132-29399a13071e | checkpoint | Confirm that pipework pressure, choke and hydrostatic testing has been completed.
82fadacb-b82b-5f6e-9045-ff8495cf8961 | note | Pipes should be left under test for a minimum of 2hrs at 1400kPa. Provide time stamped before and after photos where relevant of pressure gauges.
dc069644-1ad7-500f-842d-eaf3269b30ba | signoff | HOLD POINT - Contractor to sign off on testing. Attach test sheet
74e43698-3c35-571c-b024-9b935a9fbfc3 | checkpoint | Confirm adaptable apartment future provisons installed if applicable
6d5e73eb-71d6-5ebb-a7d2-6890e280a7d1 | checkpoint | Services Checking Consultant Inspection Completed prior to Sheeting
fdf94e49-1b18-5bf5-9f85-87dfcc6402cd | signoff | HOLD POINT - Confirm Inspection items closed & photos attached
b18fcc20-250c-59ee-8c63-45e5fedab012 | checkpoint | Attach Subcontractor ITP
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
d8e5c926-ee9d-56bc-9462-79c8c86b4ee0 | checklist | Services Rough-in - Hydraulic |  | Services Rough-in - Hydraulic
3528a5e7-cde5-54eb-b84e-652dd8e9ec14 | section | Fire Rating
b336a5cc-1f0b-5508-8087-99deabab0b3e | checkpoint | Check 1m benchmark has been set and agreed for services installation heights
e7267c22-8cdd-5d47-bf41-3ba15f08212f | note | Attach Photo of benchmark for reference
4f146de2-db5d-5e8f-8220-8d0f600dad4e | checkpoint | Ensure services are installed neatly through fire rated walls
9a5c0fe2-5299-5d06-b7ff-df0b4f7fbae3 | note | Sheet areas of wall where services are to penetrate first (ie; above entry door), then install services to avoid non-compliances with sheeting.
42d308e3-033b-506d-bf73-ec0b8dacc9f4 | checkpoint | Confirm any PEX pipes penetrating the fire rated walls are sealed on both sides with intumescent fire mastic (conned around pipe)
e969e220-bf31-512a-81de-da2e530242e0 | checkpoint | Confirm at least 100mm separation between hydraulic services and any other services (200mm form fire dampers) where passing through a fire rated wall.
058cee0a-42e2-5230-8e5e-d947f7b1c68b | checkpoint | Intubatt (Fibre Board Products) used with services
598abdc4-a399-5a71-b20f-638e00a05dee | tickbox | Ensure fixings at 200mm centres and washers are visible
6a58a552-05c3-51d0-9966-56246a35abc3 | tickbox | Ensure exposed edges of the board are covered with sealant to prevent deterioration over time
5ffcb0b1-e6c9-59dd-af7b-eabbc7ea6842 | tickbox | Ensure where service penetrates the board that fire wrap and sealant are used to close any gaps
f5b81974-5868-51a9-b5c7-799bef02eec3 | tickbox | Attach photos of compliant installation
c59a31dc-26a0-5b0d-b6ad-6f2b88229aaa | checkpoint | Retro-Fit Fire Collars - Ensure correct size collar for service and that hole around services is sealed (coned) with fire rated sealant prior to installation.
854869bc-0f75-53c0-bf3a-b6c28ee9059b | note | Ensure an Acrylic Sealant is used (not intumescent sealant) when installing around fire collars
8158399f-f65f-5649-93cc-fd1097fdc58d | checkpoint | Check copper or steel pipes penetrating fire walls have fire wrap installed with at least 3 stainless cable ties.
0fa55a4b-8569-5e3a-9192-f31429519747 | note | Ensure fire caulking is used to close any gaps around the pipe (coned) at the wall penetration prior and post wrap installation.
7f9c2cfd-9728-54bf-beac-2e2b433b369f | checkpoint | Confirm statuatory fire labels are installed adjacent services prior to sheeting. Attach photos for record.
a02749e8-d080-5a42-a5f6-01bc24ed22a8 | section | Hydraulic Services
5f08cc99-08e7-505e-8af3-256e7c528509 | checkpoint | Confirm Latest Hydraulic drainage and pressure Plans are being used with Contractor (Refer Aconex)
f708ea5d-5824-54da-aa63-fab4650c80a4 | textbox | Record Plan numbers and revisions
48e410e7-62dd-53e0-9d05-6396f5c05137 | checkpoint | Service Installations - Complete visual check to confirm all hydraulic drainage and pressure services are installed per plans.
31f0fd10-73e6-51d0-ba8d-252ac1abf618 | textbox | Record any deviations from plans and reasons why.
46abcb0e-9bf4-523d-8c46-74ac0c78bf9a | checkpoint | Typical Hydraulic Services Rough-in Heights - Spot check each room as follows (centre line of fitting):
d1c779c5-ec22-5ef6-bb04-90602aa980ee | note | External Balcony Tap - 450mm AFFL
d3093e54-ef8b-5cc8-8373-346bcd3b1e76 | note | External Balcony Gas Point - 450mm AFFL
566ece95-4b30-5f66-9854-58e0d3d5109f | note | Bathroom & Kitchens - Refer to apartment specific plans to confirm correct rough-in heights
74ba63ea-3e3b-50ea-8268-5414ad0c2937 | textbox | Record any deviations from typical heights and reasons why.
a0fb0d86-d8d9-5385-8000-1827f3cf3dd0 | checkpoint | Review hot water supply is on the left hand side and cold water supply on the right hand side to:
46727441-fe75-5a4f-9926-6e656a2d4746 | tickbox | Kitchen
ec0c21bc-dad6-51ba-9629-2cd307702058 | tickbox | Bathrooms
5b891851-766d-523c-ae2a-3cd2c7dce68c | tickbox | Laundry
b28034ce-4274-5a04-a25a-005fe1d08527 | checkpoint | Confirm A/C tundish location has been supplied and trap prefilled
6c77e616-37de-5756-b051-b6a66ae30a87 | checkpoint | Confirm all in-wall hydraulic PC items installed (ie; in-built cisterns, mixer bodies, etc…)
66a72e52-e99a-584f-ba5f-33e9e0cef746 | checkpoint | Confirm all supply pipes are charged so any leaks can be identified now and in the future.
21799f0d-c206-50fa-b132-29399a13071e | checkpoint | Confirm that pipework pressure, choke and hydrostatic testing has been completed.
3c67276d-9bcd-5d4f-96c8-81e16e2f5780 | note | Pipes should be left under test at 1500kPa (where applicable) for a minimum of 2hrs per the hydraulic specification. Provide time stamped before and after photos where relevant of pressure gauges.
dc069644-1ad7-500f-842d-eaf3269b30ba | signoff | HOLD POINT - Contractor to sign off on testing. Attach test sheet
a74725a6-d237-5e00-bfa5-acd5a4cd160a | checkpoint | Check minimum 25mm separation between gas/water services and power.
7bddcb0b-4ee0-5ab2-b5ec-7e17e6a8c398 | checkpoint | Check that any operable valves or equipment (ie; PAPA Valve or TMV) behind walls or ceilings have a suitable access panel installed adjacent.
96f8dcdf-f000-573a-b1cc-85c36b636126 | checkpoint | Geberit Supertube - Complete visual check to ensure correct fittings are being used (search website link below for fitting types and install location reference). Review any horizontal pipe runs with 0% fall do not exceed 6m (which is the max. allowed by system).
dfe628e1-020a-566f-a34e-6d68adffeabb | note | Website Link: https://www.geberit.com.au/products/piping-systems-for-building-drainage/geberit-supertube/
cc8d2f26-deda-574b-8a1e-6654aa1be324 | checkpoint | Confirm drainage points are capped off prior to fit-out trades commencing to prevent blockages from construction debris.
74e43698-3c35-571c-b024-9b935a9fbfc3 | checkpoint | Confirm adaptable apartment future provisons installed if applicable
6d5e73eb-71d6-5ebb-a7d2-6890e280a7d1 | checkpoint | Services Checking Consultant Inspection Completed prior to Sheeting
fdf94e49-1b18-5bf5-9f85-87dfcc6402cd | signoff | HOLD POINT - Confirm Inspection items closed & photos attached
b18fcc20-250c-59ee-8c63-45e5fedab012 | checkpoint | Attach Subcontractor ITP
52f1a2fe-7101-5616-8138-9d86de7a62b9 | section | Hydraulic Services - Acoustic Requirements
9a35aee1-b96d-50b0-b407-7afefae21d50 | checkpoint | Confirm PEX pipes running through studwork have gromets or silcone installed locally to prevent water hammer noise and damages.
9142f893-8ee6-5cde-a093-67d097714ed1 | checkpoint | Confirm no pipework is fixed to plasterboard or bridging cavities - should be fixed to studwork or blocking timbers.
45fd8307-17d0-5d6a-99aa-ba940d80b9fa | checkpoint | Review pipe clamps to ensure they have resilient foam sleeves installed to prevent vibration and noise transfer to structure.
b569fd29-a6e1-57ff-a844-4dfecf715911 | checkpoint | Pipe Lagging - Complete checks as listed below:
2b0ce341-9c51-5fb6-8a87-8ba32409895c | tickbox | Review all waste and stormwater pipes located in risers and ceilings are lagged.
65570c29-c963-5c3f-aa05-743a2ddbc36e | tickbox | Pipes running within 1.5m of A/C return air grille locations are to be double lagged.
d4ee96ec-21d1-52b2-aa0e-b1dc525c0f28 | tickbox | Review pipework lagging is overlapped 50mm at lagging joints.
934cbd40-80d0-5a84-8f4e-c107e232d94c | tickbox | Where lagged pipes penetrate slabs, walls and risers, ensure lagging is flanged with 50mm overlap where it meets the penetrating surface.
565c73aa-7de2-5ef1-b663-df25f7b49cec | tickbox | Review lagging around pipes is clear of any part of the structure (ie; walls, ceilings, slabs, framework, other services, etc…).
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
ae97223f-d91c-53dd-b5d9-ae021f1f6e3a | checklist | Services Rough-in - Mechanical |  | Services Rough-in - Mechanical
3528a5e7-cde5-54eb-b84e-652dd8e9ec14 | section | Fire Rating
b336a5cc-1f0b-5508-8087-99deabab0b3e | checkpoint | Check 1m benchmark has been set and agreed for services installation heights
134ba068-cab4-544a-a0dc-a8f2d4574c56 | note | Attach Photo of benchmark for reference
4f146de2-db5d-5e8f-8220-8d0f600dad4e | checkpoint | Ensure services are installed neatly through fire rated walls
b7245cb5-f668-578e-b014-cbd1104435ba | note | Sheet areas of wall where services are to penetrate first (ie; above entry door), then install services to avoid non-compliances with sheeting.
5414dd65-1f33-5e6d-8269-602db51aed83 | checkpoint | Confirm any Mechanical cable/conduit penetrating the fire rated walls are sealed on both sides with intumescent fire mastic (conned around cable/penetration)
9ca51392-c28a-5230-ba38-02b634107fc8 | checkpoint | Confirm at least 100mm separation between mechanical cables/conduits and any other services (200mm form fire dampers) where passing through a fire rated wall.
37275155-b700-5805-8946-15fc5ad2468f | checkpoint | Fire Damper Checklist:
7df87678-4a66-5419-bbac-f7a6749a563e | tickbox | Ensure fire dampers installed at least 200mm away from other services where penetrating a fire rated wall
deecf89a-935d-5d3b-89fa-4d5a33ab64bd | tickbox | Ensure inside of damper penetration is lined ans sealed with fire rated plasterboard prior to damper installation
a4e8af8c-37e2-5bbe-a3d4-099386dc63c8 | tickbox | Ensure two layers of fire rated plasterboard installed each side of wall for damper installation (if not install additional layer locally as required)
5458cc57-9515-5d9d-baba-a549a91c8bf9 | tickbox | Ensure provision for access (panels) installed for future damper inspection (both within ceiling and connecting ductwork)
7d9ae72c-ccb4-56e5-bf60-e43aa853eb73 | tickbox | Ensure flanges installed around all 4 sides of damper and no gaps visible.
35821289-786a-515f-a363-cc752d1eeaf5 | tickbox | Fire Damper Approval - Check installation against data sheet/test report from contractor
99b55464-9453-531f-9245-135a7c708fa8 | tickbox | Attach photos of compliant installation
058cee0a-42e2-5230-8e5e-d947f7b1c68b | checkpoint | Intubatt (Fibre Board Products) used with services
68081307-edf4-5f9f-9246-98c465111678 | tickbox | Ensure fixings at 200mm centres and washers are visible
eb096967-089e-5d19-a6e3-d3c96ea4a4be | tickbox | Ensure exposed edges of the board are covered with sealant to prevent deterioration over time
cfbbbeb1-0634-523d-b2f7-bec2f816192d | tickbox | Ensure where service penetrates the board that fire wrap and sealant are used to close any gaps
d817a04f-ab8f-533e-a064-d2491d3c6c38 | tickbox | Attach photos of compliant installation
c59a31dc-26a0-5b0d-b6ad-6f2b88229aaa | checkpoint | Retro-Fit Fire Collars - Ensure correct size collar for service and that hole around services is sealed (coned) with fire rated sealant prior to installation.
4666d3fb-d599-547a-a5c3-790f5453a1ee | note | Ensure an Acrylic Sealant is used (not intumescent sealant) when installing around fire collars
7f9c2cfd-9728-54bf-beac-2e2b433b369f | checkpoint | Confirm statuatory fire labels are installed adjacent services prior to sheeting. Attach photos for record.
5f3005de-2df6-566a-b171-ae1b623eab6e | section | Mechanical Services
d6472393-0551-5722-9126-3f5b6524a4d6 | checkpoint | Confirm Latest Mechanical Plans are being used with Contractor (Refer Aconex)
7c09b471-927d-5280-a9a7-b4ed2e91f80d | textbox | Record Plan numbers and revisions
72a73587-3b83-5f9e-85ee-ee3be815180f | checkpoint | Complete visual check that all flexible and ridgid ductwork has been installed per plans (also reference architectural RCP for future grille locations).
aab2feb3-3942-5d37-bf7a-47f35723a004 | note | Review to ensure no damages - take photos for record.
fb5465f7-2316-56a6-b7de-51b251df04cb | note | Review support straps to flexible ductwork are installed evenly to prevent restrictions
7fd21b55-0877-5ec3-b953-11844558b906 | textbox | Record any deviations from plans and reasons why.
822228f0-71cc-5d29-af10-8af352773365 | checkpoint | Confirm wiring of AC controls are located per architectural requirements
5544a5cc-5b20-56aa-8eb2-86c9b0a2f01a | note | Refer to drawing: FJMT-A-61500 & specific apartment plan on Aconex for guidance
d3ec89ab-3a31-551d-a995-084c29f763ff | checkpoint | Typical Mechanical Services Rough-in Heights - Spot check each room as follows:
70e61f7f-6603-507e-a4e6-d5916eb7dd66 | note | A/C Control & Thermostat - 75mm below home automation unit to top of controller where applicable
9cddc2b6-633d-515d-bd14-b2918d020931 | note | A/C Control & Thermostat - 75mm above light switch to bottom of controller where applicable
579e13fd-f30a-5b23-b6e9-4dad2210635a | textbox | Record any deviations from typical heights and reasons why.
2d9dbbf1-2689-5880-9ef9-e1dd7e755f63 | checkpoint | Review connections between flexible and ridgid ducting to ensure mechanically fixed and sealed.
522969ae-aedd-5442-b3f0-d6043d16c136 | checkpoint | Review connection between ductwork and façade to ensure mechanically fixed, sealed and a canvas connection is used to allow movement.
53a9309f-a8ab-598f-8af7-773b1f5f114d | note | Plenum box should be installed to curtain wall panel prior to installation to ensure properly sealed
6dc2b7df-404c-5901-90df-d10777b7f08d | checkpoint | Review Electrical Panel and Filter locations to FCUs to ensure they are not blocked and are accessible.
20a96969-3ade-56cb-a869-fad84b0759b0 | checkpoint | Review condensate drains and trays have been connected to hydraulic drainage and water tested to check for leaks.
72b7f7b4-8972-5fe3-8927-9a91639aaa4a | note | Check that condensate drain pipes have positive fall all the way to tundish point & 25mm air gap above tundish visible. Attach photos for record.
e6f0fed3-78c4-5897-be70-f78db9068a8d | checkpoint | Confirm refrigerant testing of lines completed prior to sheeting to check for leaks.
f1e07d8d-0791-5d9a-83d1-12fd1ba2ed38 | signoff | HOLD POINT - Contractor to sign off on testing. Attach test sheet
cc6da23b-6e42-5500-8801-e1cadf4d4431 | checkpoint | Review thermal insulation installed on refrigerant lines from the riser all the way to the FCU connection point.
f8c78140-3b73-5c36-8903-057d5f38afae | checkpoint | Confirm Installation of earthquake bracing as required by standard
74e43698-3c35-571c-b024-9b935a9fbfc3 | checkpoint | Confirm adaptable apartment future provisons installed if applicable
6d5e73eb-71d6-5ebb-a7d2-6890e280a7d1 | checkpoint | Services Checking Consultant Inspection Completed prior to Sheeting
84a3209d-f36c-5120-86b0-9900349d9ea1 | signoff | HOLD POINT - Confirm Inspection items closed & Photos attached
b18fcc20-250c-59ee-8c63-45e5fedab012 | checkpoint | Attach Subcontractor ITP
3e3fe827-5274-5883-80c1-21d7537e0434 | section | Mechanical Services - Acoustic Requirements
b9e59725-b5c3-5537-991f-18b37ca8037c | checkpoint | Confirm flexible ductwork is acoustically rated (ie. Inner flex is perforated and insulation lining between inner and outer flex).
86efce0a-7c20-5bac-854f-91fc56998cce | checkpoint | Review AC Fan Coil Unit (FCU) has vibration isolation (rubber) mounts or springs installed
00b74992-f637-5637-b12d-b5fab0f7a1a9 | checkpoint | Review Toilet/Laundry/Kitchen Exhaust fans have vibration islation (rubber) mounts or springs installed
1225cb5f-c4d7-58ae-bb3d-d732e059bfe5 | checkpoint | Review where flexible ductwork passes through full height acoustic walls (eg. Wet areas) - ensure wrapped in sheet metal and caulked (max. 10-15mm gap around service)
a6b3f612-f213-5429-ac4d-b021759f3611 | checkpoint | Review ductwork joints to ensure sealed properly (with "Emer-seal" joint sealant) to prevent noise resulting from air leakage
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
9a1978f3-b206-5cf8-a66a-bccb68e6e79e | checklist | SYS - 101C - Framing/Sheeting (Smoke Curtain Bulkhead) |  | 101C - Framing/Sheeting (Smoke Curtain Bulkhead)
1530de07-be34-5ea4-9be0-034b905e4913 | section | Survey/Wall Framing
23e408dd-5135-5585-8838-3938629743f7 | checkpoint | Confirm set-out of walls in correct locations & cross check with surveyors grids.
bf593cf7-e545-5d09-9b0b-ec0e6373d66f | textbox | Confirm wall set-out plan/revision used for set-out
a16d87db-338a-538f-a086-c2dff04f4e24 | checkpoint | Confirm that 1m benchmark has been reviewed and agreed. Ensure it is marked on most relevant permanent structure.
172e069e-c65b-54dc-b5a7-1c15435da685 | note | Attach photo of 1m benchmark for reference.
9d89ff1b-c508-5ac3-bd00-4946b21dcaac | checkpoint | Review wall types are installed correctly per architectural wall type details.
b3289e54-f7f4-5040-ae16-579651fe5a19 | checkpoint | Review wet area framing to ensure square and plumb to take tiling.
2475c618-869c-5955-91b7-ed342460614d | checkpoint | Strengthening Requirements - Confirm all noggins, trimming blocks and struts have been appropriately installed to support the following items (Min. 12mm structural plywood). Ensure to cross check relevant drawings:
2c5a047b-960f-5c5f-aa3a-0cb88c8cc8cb | note | Appliances (Wall mounted dryers, etc…)
c1b1f60c-6dc9-5f9a-8745-995ef2938d45 | note | Bathroom Accessories (Robe hooks, towel rails, shower shelves, toilet roll holders, adaptable handrails, etc…)
925b3429-826e-5c1e-b9d5-42f3bd35a048 | note | Bathroom Furniture (Mirror Cabinets, Vanity Basins, shower roses, etc…)
3d0db52b-01eb-5cce-8cbf-3a3679aa89de | note | Services (pendant lighting, display screens, TV areas, etc…)
adce8afe-bf59-540f-a059-012355501f0e | checkpoint | Adaptable Apartments - Check blocking installed to cater for post adaptation layouts
1f6ff53a-205c-5f4d-9e46-ea4d22ee9c5f | checkpoint | Confirm that all framing is square at corners (check top, middle & bottom of frame junctions)
08416204-8429-568e-afd7-c9fa6e7deb30 | checkpoint | Confirm studs not bridging or touching hydraulic pipes, mechanical units, columns in intertenancy walls or lift shaft walls to ensure vibration is not transferred through walls
f50e86d9-dd83-5f11-aa50-b871c9ce3f96 | checkpoint | Deflection Requirements - Ensure gap is present (10-15mm) at top of stud inside head track
7dc97a50-13d3-5d72-a8a4-3e023ea7fc7a | checkpoint | Joinery Openings - check gaps between framing to joinery + wall finishes will fit (5mm tolerance)
a9f86b22-e357-52ed-8b42-f7e8c3cec071 | checkpoint | Stud Spacing - Spot check studwork is spaced at 600mm maximum per Architectural Specification. Check additional studwork reinforcement at openings (ie; double studwork).
39866e90-f81a-57a8-a328-13140080c264 | note | Staggered Studs (if required) - to be installed at 300mm centres alternating per architectural specification
800c99ae-fb54-518e-8b80-7904c5f20f9d | checkpoint | Movement Joints - check walls are discontinued where they pass over building movement joints.
0fb9cac1-74f6-5835-97fe-e2f3275bfea0 | checkpoint | Services Risers - Ensure stud and trackwork is kept a minimum of 20mm away from vertical services within risers per acoustic specification
7b5c79f8-64ee-516a-84e0-855baefc7c2d | checkpoint | Engineered Designs - Spot check any engineered framing designs and attached engineers review and sign-off on system.
62a0e57d-2239-53a4-ac18-f77d094f5587 | section | Wall Sheeting
120a946f-ec6f-599e-bb9b-b8960ce99ed1 | checkpoint | Confirm acoustic/thermal insulation installed to achieve design ratings
9214adb6-d2ff-5660-8c6b-148031b3d64c | note | Cross check product ratings against architectural insulation plans
89c41d83-a979-5103-9f52-baa51290c96e | checkpoint | Confirm there is a minimum of 45mm cavity between the residential intertenancy wall studwork per Acoustic Details/Wall type Plans
4dd07011-91a4-5458-83e3-bb6a7828e05b | checkpoint | Confirm door frames are installed vertical and plumb and at correct height.
6dd1553e-b07f-5f38-8ad6-7ad960f7ad18 | note | Check metal door frames in wet areas are outside of membrane zone (ie; notched accordingly).
3406cd78-db00-5dcb-bfaa-92bc3b90dba2 | checkpoint | Check plasterboard sheets installed with 10-15mm gap at top and bottom to allow for deflection and fire sealant.
f70875dd-ec8f-5405-a8b4-37e1f96d5b9a | checkpoint | Control Joints - Ensure controls joints installed in wall runs larger than 12m in length.
ac438481-ab6e-51d7-9fcb-8324a93b993c | checkpoint | Check correct plasterboard linings installed (type and thickness) per architectural wall types
3ffd3315-cf0c-5aa2-a990-9022ef15a0b5 | checkpoint | Ensure sheets are staggered on multiple sheet layer walls. Stagger all sheet joints by minimum 200mm per architectural specification.
1fcf115e-b487-5f8b-8f9d-3eb3e9c1ee8a | checkpoint | Confirm plasterboard lining installed to wet areas are sealed up to concrete soffit on both sides of wall where adjacent to habitable rooms.
9736503d-c21f-51e6-96ba-c5b04f89b1fc | checkpoint | Confirm all services penetrations through wet area walls adjacent to habitable rooms are sealed and caulked for acoustic performance.
96d52f5c-7544-55be-9e69-90b3c809c056 | note | Check that mechanical flex ducts are not passing through walls - to be rigid ductwork or sleave installed over.
1eaaba03-6b1a-5154-a302-05cc6d20387e | checkpoint | Check intertenancy walls extend to façade panels, leave 10-15mm gap and caulked with fire sealant.
c36a4af9-d9b8-548b-9b4c-a4ee2b6c587b | signoff | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting
ee010fbd-1046-56c5-b493-1d37862a0f5a | section | Sheeting Ceilings
1f688c69-de7d-5db6-9592-47ca2fce1731 | checkpoint | Confirm ceiling insulation complete where applicable
94e08ce9-c2d6-58ed-a243-14d3407f27c2 | checkpoint | Confirm provisions made in ceiling framing for access panels and air grilles were required by architectural RCP
7fdffaac-406b-5801-bef2-6361fc7b31f7 | note | Spot check access panels installed to allow access to fire dampers and mechanical fans
036d84fe-11bd-5ad9-ab55-b8fa4ef58f5a | checkpoint | Confirm ceiling framing bulkheads are square and level
4e88e007-6712-548b-af61-90634071bf08 | checkpoint | Confirm furring channels do not clash with other services (eg; downlights, access panels, mechanical exhaust, sprinkler heads, etc…).
49327a45-bf8d-5b9f-bcb8-d2eef0571ecf | checkpoint | Control Joints - Ensure ceiling bays are not larger than 10m x 7m without a joint or wall break.
1f79f360-0ac1-56e2-8b33-690dce63e2a6 | checkpoint | Attach Subcontractor ITP for the Works
6d815a4b-f7ea-50d6-8d30-a42333b3b1fe | checkpoint | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting
82729cd5-dd85-5ad5-8e66-822a52f5bab6 | signoff | Review & Sign-off by Acoustic Consultant
e217164f-af7e-5616-bd19-3343bb541cc7 | checkpoint | HOLD POINT - Confirm BCA consultant inspection of services penetrations through fire rated walls prior to sheeting ceilings
894062ba-2286-5c42-97a3-5edb7e8965e2 | signoff | Review & Sign-off by BCA consultant
e410058d-18d5-5fb6-9e6e-bf433190f335 | checkpoint | Final Sign-off Complete
5a99335f-7104-52cf-97ec-719a396ae60e | signoff | Final ITP Review & Sign-off by Project Engineer
37097c02-392c-49b2-b20a-43207590c4e1 | checklist | Tiling - External Balcony Paver System |  | Tiling - External Balcony Paver System
8f4e99c4-29e8-4961-a099-08b7270885ef | section | Prior to Works
3be028be-8acc-44b0-87ab-60e39eb82671 | checkpoint | Confirm Series and Scheme of finish for unit/work area
901f0188-f158-554a-9e7c-60c1cff03775 | textbox | Record Colour scheme of apartment/work area:
4c82bf91-5440-4134-8559-0b4d287e0348 | checkpoint | Confirm site pavers/tiles match approved samples.
d5704167-3795-5b2b-9a89-769a6593a41b | note | Review against Aconex Sample form, attach photos.
8a71efe5-e9f7-4180-992f-791c3c2a6bbd | checkpoint | Confirm that all floor wastes & overflows are plugged during tiling works to prevent debris entering.
7673398c-5412-4a25-b2ce-2f204219a709 | checkpoint | Confirm that concrete has adequate falls to floor waste, and there are no puddles remaining after flood tests.
8e734350-a357-528f-a06d-6a7bec2e8f4c | note | Ensure min. 1:100 Falls achieved on balconies.
a4217a2f-7d24-469b-b4a4-e302ef8d7f1a | checkpoint | Ensure Polypads are configured into correct shape and size for placement.
efef41f6-cd3a-4592-a9cb-5a7ddb07120a | section | During Works
11c3aa9e-2605-4c5f-aedb-e824070c9478 | checkpoint | Confirm height of polypads is aligned to sliding door threshold (ie; flush transition).
882d419a-d65a-490d-976a-63449b9da457 | checkpoint | Ensure quality of tile installation is maintained, i.e. Alignment & Consistency of joints, Minimization of scratches & damage, no loose or ‘rocking’ pavers.
6461525d-e7b1-4855-9028-0d641a1a26c2 | section | After Works
efd6c2d4-b299-47b6-a912-58522bda901b | checkpoint | Visually inspect all floor wastes and confirm each one is clean and clear.
248abbea-4da5-4d08-9b74-41aa21470258 | checkpoint | Attach Subcontractor ITP
8aa5e200-6681-48f2-be37-0bae7702509a | section | Sign-off
ee547114-1f40-4a5d-bcf8-048ccb5f90a3 | checkpoint | Subcontractor Sign-off
69201f98-1d74-4cb1-8e23-db93aa978be1 | signoff | Subcontractor Sign-off
f7398cc9-082e-436f-9b30-9938ddf43be6 | checkpoint | SDC Sign-off
1cf74916-2aa9-4c23-993a-8f4db2b66929 | signoff | SDC Sign-off
2f147193-c8f3-438c-a60a-8798ecbc618c | checklist | Tiling - Internal Areas |  | Tiling - Internal Areas
a7e11e69-1bd1-4bb6-96a1-dd913e9fe258 | section | Prior to Works
01b73e27-5f5c-4414-a102-e2ffec01108e | checkpoint | Confirm Scheme of finish for apartment from Residential Finishes Schedule. Check tile being used matches’ schedule.
cebbdc76-8f37-544b-bca9-e5156ea44a0e | textbox | Record Colour scheme of apartment/work area:
540fade3-83a1-426a-be14-4b6ab5dbc606 | checkpoint | Confirm Tile Set out with tiler prior to tiling from the architectural bathroom plans.
ee760d43-c1b8-52cc-9cfd-197d72c4e7e8 | textbox | Record plan showing set-out. Ensure tiler has the latest plans from ACONEX.
0aa783dd-d4b7-478d-8c0f-a958186e7194 | checkpoint | Confirm tiles are from the same batch
d0c1c6dc-277d-559f-b007-27ee782f63d1 | note | record photos of tile boxes where available
4a50ae70-13b5-462b-9153-f495a532390c | checkpoint | Confirm Tiles Floor Finish Level (FFL)
633f1884-8e44-5e87-a0be-e073ccf913f7 | note | Record FFL being tiled (high point at door threshold).
25a117f8-f69d-4d61-b758-933a447ce692 | checkpoint | Confirm all floor wastes are plugged during tiling works to prevent debris entering.
d408abce-f6d7-4363-b0b8-119f3b457efa | checkpoint | Ensure Acoustic Matt installed where required per architectural insulation plans & acoustic report prior to works.
3eacd1f3-1985-5aab-98c0-81dcb24e9eaa | note | Record photos of the matt installation
46c3d393-8a5b-4952-8265-e2a7b85048b7 | checkpoint | Ensure associated works for under floor heating installed as required prior to completing tiling.
916337c2-7511-59eb-a5d6-19b46196f8cb | note | Record photos of the under floor heating installation
ba73cb0b-d0d4-4831-8ca2-26b2b3b164dd | section | During Works
a6cd986b-8251-479f-b9d7-51527f533cfc | checkpoint | Confirm sand/cement screed ratio is as per AS.
6f5aa75a-32f4-5423-a258-94cda8d3c28f | note | Ratio - 1:4 (1 Cement / 4 Sand)
58dff994-ffa7-4ba2-ac7d-abdbbd1fbcc1 | checkpoint | Confirm minimum 25mm tile bed at floor waste (can be less if engineered screed).
d7a3db56-73bb-4ca8-833d-392bd1dd70a1 | checkpoint | Confirm tile bed thickness at door threshold will allow finished tile to be aligned with FFL.
bcd47f10-8e1d-4fad-80a6-f90e24e3ab1e | checkpoint | Screed curing times – verify with tiler that screed has cured for suitable amount of time prior to tiling.
465af7b7-633e-49a5-99d1-b689c7b5a001 | signoff | Sign-off Hold Point – tiler to sign-off screed suitable to take tiling.
87326d3a-8f31-49f8-bde5-3063a22061ac | checkpoint | Moisture Barrier – confirm this has been applied over top of tile screed prior to tiling application.
68ff83e2-0f71-48f8-9450-5f7a7905b2f1 | signoff | Record product being used and verify curing times adhered as well. Tiler to sign-off on curing prior to tiling.
e04f9bc8-b3cf-43ef-b4d7-11a2d595f5f8 | checkpoint | Confirm installation of floor wastes is flush with or 1mm below floor tile level.
1841eb27-51b5-4125-8a04-db4b52ffb36a | checkpoint | Stop wall and floor tiles 2-3mm short of edges and fill with resilient caulking compound.
b2b3880d-60f7-4dd1-be55-c6e39b79db55 | checkpoint | Confirm that floor waste (normal/smart) and strip drain is installed correctly per design drawings. Ensure grout line of tiles within floor waste line up with main floor.
4b35cb80-9517-4f81-9aea-fd9df62acfef | checkpoint | Confirm tiles are set out per architectural design drawings. Check large format tile joints align with stone joints where detailed on bathroom plans.
4d4bfa7f-1361-507f-b0fa-f91260d66694 | note | Check against tile set-out points.
d5be5c9e-4263-4066-a8bd-d4641b556fee | section | After Works
db5bb573-f6ad-4f28-a182-347ff683fb38 | checkpoint | Visually inspect all floor wastes, and confirm each one is clean and clear
5adc7afa-372e-4740-aa8b-b607aa5a9c89 | checkpoint | Floor tiles laid to falls – min 1:100 in main bathroom. Check min. 1:80 falls in shower.
d40459cb-6914-4357-a107-5990e5282b6b | checkpoint | Confirm all joints are aligned and lipping of tiles does not exceed the requirements in the architectural specification.
a406949c-d7e9-5fda-86c2-504fb2d1ffd0 | note | Lipping requirements: - Unpolished Tiles 1.5mm - Polished Tiles (less than 300x300mm): 0.5mm - Polished Tiles (greater than 300x300mm): 1.5mm
47a1567f-1674-43c6-9f91-da7bc82f605c | checkpoint | Confirm colour of grout is consistent and uniform.
f0e4472d-fea9-4140-b4b0-f9d81fbf5a91 | checkpoint | Confirm all tile edges line up and are plumb. Also check curved tile walls meet the required radius shown on bathroom layout plans.
d7b466e8-e1e6-43ed-b22e-928f699aa4fd | checkpoint | Confirm all silicon jointing provided to all floor/wall tile junctions.
daa006a5-111d-5c7f-9677-66acfe1492f8 | note | Confirm all excess silicon is removed from tiles and adjoining surfaces.
3ec414c3-a31b-443f-afd1-eb6e24536d62 | checkpoint | Review large format stone wall tiling to ensure vein matching per architectural bathroom elevation plans.
7462efbf-3c98-47c4-9f21-9b68a6c0c50f | checkpoint | Attach Subcontractor ITP
fce1f405-becf-432f-abf2-709e01cf8a77 | section | Sign-off
bff17719-990f-4b14-9fec-58f04ec0ff93 | checkpoint | Subcontractor Sign-off
6d8853bb-d025-4dd3-bb42-5a629e2c59be | signoff | Subcontractor Sign-off
7184c526-7ca3-4fd9-8315-6eec0a76dad3 | checkpoint | SDC Sign-off
f45bac4d-bcf9-4477-9b94-555862509d76 | signoff | SDC Sign-off
d6800b2d-0fc9-52cf-a374-aa69082d6bcc | checklist | Waterproofing - Balcony Areas |  | Waterproofing - Balcony Areas
6107e48c-eca3-5f07-91e4-be2679c46a44 | section | Prior to Works
8c97525e-9acd-5dec-9911-0defcb005f52 | checkpoint | Substrate - Review to ensure any voids or protrusions are filled and removed to provide smooth surface.
aafbcaf5-d7fd-56e4-8bff-0dd201cf45ea | note | Also ensure substrate is clean and free of any water, dust and debris.
85a015df-86fe-594a-83bd-1d3a0a27ab2c | checkpoint | Verify with Plumber that their drainage works are completed prior to membrane commencement.
9c1426b6-1e17-53b6-80aa-a57366e9b85b | note | Attach Subcontractor ITP where relevant.
f435001a-afea-5481-ab9e-16cce2f58cf7 | checkpoint | Concrete Cracks - Review substrate for any cracking. Up to 2mm cracks fill with Polyurethane sealant. Above 2mm to be chased, cleaned and primed, then sealant applied.
91a5bec7-5fad-561e-88ef-d86803fc0a3e | checkpoint | Falls - Review concrete substrate to ensure min. 1:100 falls achieved and falling to floor wastes.
6eb4055d-0000-5a69-b942-472452654fb5 | checkpoint | Floor Wastes - Review puddle flange to ensure it is recessed and flush with floor substrate. The PVC flange should be lightly sanded to promote membrane adhersion.
634197fc-c18b-5384-8e21-ff0495218176 | note | Also check internal of floor wastes to ensure free from debris prior to waterproofing.
2927c872-b826-586b-aa0e-f8f141406ca1 | checkpoint | Overflow Points - Review overflow points are installed correctly per plans (min. x2 per balcony) and pipework is proud of slab surface by min. 30mm.
e8c7bba6-2373-5b97-99a1-b7fad1e53bc6 | note | Check overflow points are connected below to curtain wall façade and not blocked.
712524e4-2a53-5143-8558-d2fb6acfbed8 | checkpoint | Substrate Moisture Content - Verify that waterproofing contractor has tested moisture content of concrete substrate and is happy to proceed with works (ie; below 5%).
87bdd2e8-c290-5903-91c8-c7c53520cf25 | textbox | Record moisture meter reading.
7c376bae-53f2-533a-902f-862246d8d991 | signoff | Subcontractor to sign-off on substrate.
7efc1321-c66a-5c1b-b913-b8eb60633901 | checkpoint | Waterproofing Materials - Confirm approved waterproofing materials are being used for the works.
11167f47-5cd4-58e7-b1e1-a7e488507ca7 | note | Waterproofing Primer: Sikalastic PU Primer. Waterproofing Membrane: Sikalastic 488
6c55705c-ab61-5cfc-b210-9de1a66112df | checkpoint | Record product batch/serial numbers for tracking of any future defects.
8eee4c46-766d-5b88-b052-c225396a3dfc | textbox | Batch/Serial Numbers:
aa4a7fb2-9caa-5f52-8999-e3e165f1eab8 | checkpoint | HOLD POINT INSPECTION - Organise membrane consultants, regulated designer (FJC), membrane suppliers or PCA to inspect substrate to ensure prepared in accordance with design & specifications.
ea3806cf-9e2f-5750-8a2d-0218268021e6 | note | Attach record of inspection where applicable.
92080ba3-ff4e-5b82-a821-91dd29d1a5ca | section | During Works
75333f7c-7a4f-47e2-a421-2777087f0573 | checkpoint | Ambient Conditions - Membrane Works
584b1fa7-78d1-4483-8976-69fa96f63b1c | textbox | Record the ambient temperature information during membrane installation:
0fdd36de-056f-5765-8fe3-c9f513a54a84 | textbox | Record the Commencement date/time of the application:
0418f02d-96a4-55e4-8cb0-457bd9609efe | textbox | Record the Finish date/time of the application:
1e9df0c4-7089-5c50-ace4-1efb121939a3 | checkpoint | Sealant/Bond Breakers - Confirm applied to all wall/floor and wall/wall junctions as well as around any services penetrations and wall fixings (ie; screw fixings, etc…). Surfaces should be primed prior to application of sealant/bond breakers.
2592abdf-5bd7-5a36-ac96-e0517f020e52 | note | Check to ensure gaps not more than 20mm wide/deep for sealant application. Min. fillet of sealant should be 5mm. Record photos of the installation.
f6fb3cc1-a0b1-4668-9d5f-addea3926036 | checkpoint | HOLD POINT INSPECTION - Organise membrane consultants, regulated designer (FJC), membrane suppliers or PCA to inspect priming and sealant/bond breakers to ensure they are installed in accordance with design & specifications.
c416869b-7e4a-46ec-be51-167be2e4f7e9 | note | Attach record of inspection where applicable.
49aa3d9d-b632-50d7-9526-3ed84122bd37 | checkpoint | Floor Membrane - Confirm 1x coat of primer (Sikalastic PU Primer - 3hr curing time prior to membrane application) & 2x coats of membrane (Sikalastic 488 - requires 24hrs curing time between coats).
53046c6e-e9ba-590f-a2d1-73bd81270820 | note | Attach progress photos of completed membrane works. Ensure no membrane on top of exposed elements (ie; curtain wall, etc…). Ensure balcony access is barricaded with signage to prevent damage from other trades.
027c4588-7b36-5e3b-af0c-0c9fa7d5975c | checkpoint | Membrane Skirting Upturn - ensure membrane applied 150mm up wall from structural floor level per standards.
88232dcb-f808-52e0-a447-d11f955bd1b1 | checkpoint | Wall Membrane - confirm membrane applied to wall substrate where taps installed (under finishes) and around curtain wall to slab junctions.
9aabeaec-1e8e-5689-b0df-8b46c689506b | note | Attach progress photos of completed membrane works.
688443b4-64a0-5344-b18a-a80a5ffc1b61 | section | After Works
d15dfc75-9a37-57bf-8301-5d54386b9db3 | checkpoint | Flood Testing: Block floor waste points & overflows and fill balcony to internal hob height and leave for 24hrs.
8100ecfc-03af-57a1-8bc3-c463e9d0da67 | note | Verify that final coat of membrane has had appropriate curing time (refer curring time notes in ITP above) prior to Flood testing.
b58aaf5a-8f4c-5ccb-a5be-176aa95db80b | note | Mark water level at start of flood testing to verify for any leaks/drops in water level. Attach before and after photos with time/date stamps.
317cf292-3992-5f46-a4ad-59882d64e301 | checkpoint | HOLD POINT - verification of Flood Testing Results - Any leaks Found?
06fbce03-448b-5cee-8575-c97ca465e5ef | textbox | Note: if any leaks identified (if so re-membrane and test)?
a8b871d0-3dae-53c2-af55-7a4caff5a556 | signoff | Contractor to sign-off on flood testing results once passed.
8bd82640-dba8-5aff-b2ca-cf1adf578461 | checkpoint | Attach subcontractor ITP
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
d1b539e7-2a1b-569f-ab87-a9f58dfc0bb0 | checklist | Waterproofing - Internal Areas |  | Waterproofing - Internal Areas
6107e48c-eca3-5f07-91e4-be2679c46a44 | section | Prior to Works
7a2195be-540a-4703-bc2e-93d672f301fa | checkpoint | Product Summary Notes
e6e9dcb6-43c6-478a-8678-d8ad36b83146 | note | Residential: - WPM 750 sheet membrane to bathroom floors (Primer is CA 750) - WPM 002 liquid membrane to bathroom walls, laundry floors and walls (Primer is WPM 265) Commercial bathrooms: - WPM 002 to floors and walls for retail and commercial amenities (Primer is WPM 265)
8c97525e-9acd-5dec-9911-0defcb005f52 | checkpoint | Substrate - Review to ensure any voids or protrusions are filled and removed to provide smooth surface.
4d63cdbc-890c-5ef4-8e18-ac56fa361dcf | note | Also ensure substrate is clean and free of any water, dust and debris.
85a015df-86fe-594a-83bd-1d3a0a27ab2c | checkpoint | Verify with Plumber that their drainage works are completed prior to membrane commencement.
030b00d6-0583-570d-bf8a-b78f9cbf4bc9 | note | Attach Subcontractor ITP where relevant.
ffcb1cf6-400e-4c86-9dc6-72ad6b221d6e | checkpoint | Confirm that the company/worker installing the membrane is an accredited applicator (ie; for Ardex Products).
7b7f6013-914d-5c31-8b97-11a69398d946 | note | Record Accredited Applicators Details.
f435001a-afea-5481-ab9e-16cce2f58cf7 | checkpoint | Concrete Cracks - Review substrate for any cracking. Up to 2mm cracks fill with Polyurethane sealant. Above 2mm to be chased, cleaned and primed, then sealant applied.
bd8b4aa7-5a25-49df-aa76-b86ea0eb8e8d | note | ARDEX WPM 750 Sheet Membrane - damaged concrete sections from 2mm - 30mm to be patched with ARDEX A 46 (curing takes roughly 2 days per 5mm thickness) ARDEX WPM 002 Liquid Membrane - cracks 2mm or less (seal and prime with ARDEX WPM 265 prior to applying membrane). Cracks greater than 2mm (apply bead of neutral cure silicone into the crack and extend 6mm either side, then ensure a piece of 190mm wide ARDEX Deckweb is installed between the WPM 002 membrane layers). This process can also be applied to movement and construction joints.
52027135-68db-5c84-aecc-f57d6fee27f1 | checkpoint | Falls - Review concrete substrate to ensure min. 1:100 falls achieved and falling to floor wastes (1:80 falls in shower area).
6eb4055d-0000-5a69-b942-472452654fb5 | checkpoint | Floor Wastes - Review puddle flange to ensure it is recessed and flush with floor substrate. The PVC flange should be lightly sanded to promote membrane adhersion.
7e061a74-3c14-5ebe-8c19-2d9305e23947 | note | Also check internal of floor wastes to ensure free from debris prior to waterproofing.
712524e4-2a53-5143-8558-d2fb6acfbed8 | checkpoint | Substrate Moisture Content - Verify that waterproofing contractor has tested moisture content of concrete substrate and is happy to proceed with works (ie; below 5%).
f19430e9-14ac-597a-a4c3-ddced1877f52 | textbox | Record moisture meter reading.
7c376bae-53f2-533a-902f-862246d8d991 | signoff | Subcontractor to sign-off on substrate.
c06b9ba6-a458-504f-abf1-823bbed5f2a0 | checkpoint | Waterstop Angles - Check angles installed in correct position at wet area entry doors and showers.
89b42d98-89ec-5ee0-a401-cdf10bf79637 | note | Also check angles are installed at correct heights based of agreed 1m mark from FFL.
7efc1321-c66a-5c1b-b913-b8eb60633901 | checkpoint | Waterproofing Materials - Confirm approved waterproofing materials are being used for the works.
2c891f04-75ab-5849-a8e2-53bae99c183d | note | Refer product summary notes at start of ITP.
6c55705c-ab61-5cfc-b210-9de1a66112df | checkpoint | Record product batch/serial numbers for tracking of any future defects.
4375daa9-92fa-5c55-a010-4bf0372a9793 | textbox | Batch/Serial Numbers:
aa4a7fb2-9caa-5f52-8999-e3e165f1eab8 | checkpoint | Membrane Supplier Inspection - Confirm membrane supplier inspection of substrate to ensure prepared in accordance with specification.
9b12d4e0-a7e9-5700-8696-2d2fd591989f | note | Attach record of inspection where applicable.
92080ba3-ff4e-5b82-a821-91dd29d1a5ca | section | During Works
da573360-6118-4a62-9854-8a73767b9f63 | checkpoint | Ambient Conditions - Membrane Works
27400227-6a32-4b03-bec0-94225ccc9396 | textbox | Record the ambient temperature information during membrane installation:
7f622d75-d2ee-47ea-876d-2f08faf43d41 | textbox | Record the Commencement date/time of the application:
a6debd9c-1c55-51a6-9a9a-9cf76a2ac80d | textbox | Record the Finish date/time of the application:
36ec831f-8251-496f-b094-729c667750e1 | checkpoint | Priming Works - Confirm 1x coat of primer applied to approved substrate.
d3291dfa-d182-4b06-b856-d7fa0763ef9d | note | ARDEX CA 750 (for sheet membranes) - curring time 30min up to 4hrs prior to application of the sheet membrane pending ambient temperature conditions. ARDEX WPM 265 (for liquid membranes) - curring time 30min - 1hr prior to application of the membrane. Plastic PVC pipes should be primed with a solvent based plumbers pink primer.
d1daee1b-1022-5ce0-b4f6-c9525cb979f0 | note | Record Photos of primer installation once completed.
1e9df0c4-7089-5c50-ace4-1efb121939a3 | checkpoint | Sealant/Bond Breakers - Confirm applied to all wall/floor and wall/wall junctions as well as around any services penetrations and wall fixings (ie; screw fixings, etc…). Surfaces should be primed prior to application of sealant/bond breakers.
dd20848c-d9bb-5237-8f43-0939edac2661 | note | Waterproofing Sealant: ARDEX ST neutral cure silicone sealant recommended (Where possible, the silicone should be at a 2:1 ratio (width:depth). Width and the depth of the joint should be minimum 5mm. Maximum joint width is 30mm and depth 15mm. For joints greater than 10mm deep a backing rod should be used). Waterproofing Bond Breakers: ARDEX STB/STA Tape (for sheet membranes WPM 750) or ARDEX Deckweb woven cloth reinforcement (for liquid membranes WPM 002) to be installed at floor to wall junctions. 190mm wide ARDEX Deckweb strip to be installed between first and second coats.
408a3379-65df-5bf1-9e54-ddc2248550ba | note | Record Photos of Sealant/Bond Breaker installation once completed.
7e12607c-6acf-489f-b49c-6c6c1f76d354 | checkpoint | HOLD POINT INSPECTION - Organise membrane consultants, regulated designer (FJC), membrane suppliers or PCA to inspect priming and sealant/bond breakers to ensure they are installed in accordance with design & specifications.
b43b5af4-b0d6-5410-bed0-fd2198876152 | note | Attach record of inspection where applicable.
cac60b72-5534-5c96-85ae-faf2f1d817bd | checkpoint | Floor Membrane Works (Sheet Membrane - WPM 750) - Ensure installed in accordance with manufacturers specifications:
fb12a935-1ece-4b23-9540-ea4c949233fd | tickbox | Ensure sheets are overlapping on all ends min. 40mm
d1333f64-65d1-51d5-bca1-c544390fd3fd | tickbox | Ensure sheets are extended up walls min. 150mm above FFL (ie; overall approx. 200mm).
10740b6c-1820-50e3-81f9-4171fac103c0 | tickbox | Ensure there are no air pockets trapped below the membrane.
3e1aac82-a6b5-5a50-bad4-b090d7e81217 | tickbox | Ensure there is no membrane on top of exposed floor angles.
3dcc9f1d-29ad-5ed6-9454-30c3f1802e6c | tickbox | Ensure Membrane has cured for min. 1hr post installation before water testing/tiling.
a95c6670-e264-5499-9c1c-4cac62bf1d0f | note | Attach progress photos of completed membrane works. Ensure doorway is barricaded with signage to prevent damage from other trades.
144b8d55-edbf-424c-ab75-226e32e16708 | checkpoint | Floor Membrane Works (Liquid Membrane - WPM 002) - Ensure installed in accordance with manufacturers specifications:
9f6c1413-a37a-53fd-9e56-097618cf571f | tickbox | Ensure 2x coats of membrane applied to floors - 2hrs curring time between coats.
61303b9d-09c9-5367-8d66-2982f8fcc2af | tickbox | Ensure membrane extends up walls at least 100mm above FFL (ie; overall approx 150mm).
6113381c-9fc9-5e8d-a488-001f855d3913 | tickbox | Ensure there is no membrane on top of exposed floor angles.
5db33667-6583-5b97-b7f0-4c1fb4d136b8 | tickbox | Ensure 1st and 2nd coats of membrane are applied in opposite directions.
94827995-a86b-5070-b2c9-7bc5da1c9a70 | tickbox | Ensure membrane has cured for min. 48hrs post installation before water testing/tiling.
20f2e454-f35f-57ba-8fcf-dcc78c48a527 | note | Attach progress photos of completed membrane works. Ensure doorway is barricaded with signage to prevent damage from other trades.
d757db58-9b35-5be3-b59d-0a53aae43614 | checkpoint | Wall Membrane Works (Liquide Membrane - WPM 002) - Ensure installed in accordance with manufactures specifications:
768c4c63-1837-5ed7-880c-f005a6011367 | tickbox | Confirm wall membrane applied to whole shower area (at least 100mm above shower rose or full height of wall if ceiling mounted rose), around bath and basin areas.
09734480-a41a-5e62-a298-80c5be4edeb5 | tickbox | Confirm ARDEX STB/STA Tape installed at junction of sheet and liquid membrane if lapping these products.
57f15cc6-49da-5ed0-954c-5ff42cd743ea | tickbox | Ensure there is no membrane on hardware or fixtures.
b681cd9e-3ee3-5cc1-a1ee-9978ee5b0027 | tickbox | Ensure all gaps around wall penetrations are sealed and membraned appropriately.
ac9686cc-2586-5384-b331-dc5d7a675b3e | note | Attach progress photos of completed membrane works.
688443b4-64a0-5344-b18a-a80a5ffc1b61 | section | After Works
2c3764a5-6602-57da-af17-349b6ac0a4fb | checkpoint | Flood Testing: Block floor waste points and fill room to door angle height and leave for 24hrs.
d79e90a6-42d1-5837-8f83-dd7d8e288dc8 | note | Verify that final coat of membrane has had appropriate curing time (refer curring time notes in ITP above) prior to Flood testing.
87c35dd0-5c12-5cb2-947e-59e1ba276380 | note | Mark water level at start of flood testing to verify for any leaks/drops in water level. Attach before and after photos with time/date stamps.
317cf292-3992-5f46-a4ad-59882d64e301 | checkpoint | HOLD POINT - verification of Flood Testing Results - Any leaks Found?
9347b08c-9c7b-5a57-b3a1-123253873a91 | textbox | Note: if any leaks identified (if so re-membrane and test)?
a8b871d0-3dae-53c2-af55-7a4caff5a556 | signoff | Contractor to sign-off on flood testing results once passed.
8bd82640-dba8-5aff-b2ca-cf1adf578461 | checkpoint | Attach subcontractor ITP
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off