## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
63c071a4-8691-5d62-82c7-906aea997a3f | checklist | Waterproofing - Balcony Areas |  | Waterproofing - Balcony Areas
6107e48c-eca3-5f07-91e4-be2679c46a44 | section | Prior to Works
8c97525e-9acd-5dec-9911-0defcb005f52 | checkpoint | Substrate - Review to ensure any voids or protrusions are filled and removed and ensure surface is prepared to take membrane (lightly sanded to promote adhesion)
19e171da-1973-52c2-824f-539b46134bbe | note | Also ensure substrate is clean and free of any water, dust and debris.
85a015df-86fe-594a-83bd-1d3a0a27ab2c | checkpoint | Verify with Plumber that their drainage works are completed prior to membrane commencement.
c38f5a78-fbaa-5942-bb3b-0098c6b8d89a | note | Attach Subcontractor ITP where relevant.
f435001a-afea-5481-ab9e-16cce2f58cf7 | checkpoint | Concrete Cracks - Review substrate for any cracking. Up to 2mm cracks fill with Polyurethane sealant. Above 2mm to be chased, cleaned and primed, then sealant applied.
91a5bec7-5fad-561e-88ef-d86803fc0a3e | checkpoint | Falls - Review concrete substrate to ensure min. 1:100 falls achieved and falling to floor wastes.
6eb4055d-0000-5a69-b942-472452654fb5 | checkpoint | Floor Wastes - Review puddle flange to ensure it is recessed and flush with floor substrate. The PVC flange should be lightly sanded to promote membrane adhersion.
37a01a3d-dff5-5797-ad34-a52868febae2 | note | Also check internal of floor wastes to ensure free from debris prior to waterproofing.
2927c872-b826-586b-aa0e-f8f141406ca1 | checkpoint | Overflow Points - Review overflow points are installed correctly per plans (min. x2 per balcony) and pipework is proud of slab surface by min. 30mm.
99ac1ea6-a0b1-57ef-80a9-9aabbba87852 | note | Check overflow points are connected below to curtain wall façade and not blocked.
712524e4-2a53-5143-8558-d2fb6acfbed8 | checkpoint | Substrate Moisture Content - Verify that waterproofing contractor has tested moisture content of concrete substrate and is happy to proceed with works (ie; below 5%).
360a10fa-ca0b-580b-befd-bb7ec6e8057a | textbox | Record moisture meter reading.
7c376bae-53f2-533a-902f-862246d8d991 | signoff | Subcontractor to sign-off on substrate.
7efc1321-c66a-5c1b-b913-b8eb60633901 | checkpoint | Waterproofing Materials - Confirm approved waterproofing materials are being used for the works.
634c5298-97a0-541f-ac32-71b2c07ab2f7 | note | Waterproofing Primer: Sikalastic PU Primer. Waterproofing Membrane: Sikalastic 488
6c55705c-ab61-5cfc-b210-9de1a66112df | checkpoint | Record product batch/serial numbers for tracking of any future defects.
7dafab42-df09-5cb4-9548-4b0f4c395d76 | textbox | Batch/Serial Numbers:
aa4a7fb2-9caa-5f52-8999-e3e165f1eab8 | checkpoint | HOLD POINT INSPECTION - Organise membrane consultants, regulated designer (FJC), membrane suppliers or PCA to inspect substrate to ensure prepared in accordance with design & specifications.
195177ea-ef02-513e-ba70-f0dc82125b2b | note | Attach record of inspection where applicable.
92080ba3-ff4e-5b82-a821-91dd29d1a5ca | section | During Works
7eab99ce-1783-482e-bb49-bb3c37678cbc | checkpoint | Ambient Conditions - Membrane Works
a1eedb97-a785-4e9b-8c82-72bbe2022fe9 | textbox | Record the ambient temperature information during membrane installation:
3de6f4cc-d289-5bac-9482-eadc45465338 | textbox | Record the Commencement date/time of the application:
4e32346e-2e5a-5914-bcc8-46830bb0b127 | textbox | Record the Finish date/time of the application:
1e9df0c4-7089-5c50-ace4-1efb121939a3 | checkpoint | Sealant/Bond Breakers - Confirm applied to all wall/floor and wall/wall junctions as well as around any services penetrations and wall fixings (ie; screw fixings, etc…). Surfaces should be primed prior to application of sealant/bond breakers.
54a0fd2f-1518-50bf-a8a4-0b9b238e0719 | note | Waterproofing Sealant: Nitroseal PU250 or PU400 (Check to ensure gaps not more than 20mm wide/deep for sealant application. Min. fillet of sealant should be 5mm). Bond Breaker: Nitroband Tape (ensure surface primed prior to install and overlapping at joints 150mm each side).
0fdd36de-056f-5765-8fe3-c9f513a54a84 | note | Check to ensure gaps not more than 20mm wide/deep for sealant application. Min. fillet of sealant should be 5mm. Record photos of the installation.
672a239f-90d1-4744-88bd-3a52e2de7be1 | checkpoint | HOLD POINT INSPECTION - Organise membrane consultants, regulated designer (FJC), membrane suppliers or PCA to inspect priming and sealant/bond breakers to ensure they are installed in accordance with design & specifications.
53046c6e-e9ba-590f-a2d1-73bd81270820 | note | Attach record of inspection where applicable.
49aa3d9d-b632-50d7-9526-3ed84122bd37 | checkpoint | Floor Membrane - Confirm 1x coat of primer (Sikalastic PU Primer - 3hr curing time prior to membrane application) & 2x coats of membrane (Sikalastic 488 - requires 24hrs curing time between coats).
b7856673-7c18-51e6-ba41-b57c6ed2557f | note | Attach progress photos of completed membrane works. Ensure no membrane on top of exposed elements (ie; curtain wall, etc…). Ensure balcony access is barricaded with signage to prevent damage from other trades.
027c4588-7b36-5e3b-af0c-0c9fa7d5975c | checkpoint | Membrane Skirting Upturn - ensure membrane applied 150mm up wall from structural floor level per standards.
88232dcb-f808-52e0-a447-d11f955bd1b1 | checkpoint | Wall Membrane - confirm membrane applied to wall substrate where taps installed (under finishes) and around curtain wall to slab junctions.
fb553774-6bab-5687-b702-c47629beec7c | note | Attach progress photos of completed membrane works.
688443b4-64a0-5344-b18a-a80a5ffc1b61 | section | After Works
d15dfc75-9a37-57bf-8301-5d54386b9db3 | checkpoint | Flood Testing: Block floor waste points & overflows and fill balcony to internal hob height and leave for 24hrs.
5ebf07ee-48f4-5ba4-bee5-89912732e6bb | note | Verify that final coat of membrane has had appropriate curing time (refer curring time notes in ITP above) prior to Flood testing.
d72ddf45-f8d7-5c08-9d18-6b6e2ac3f029 | note | Mark water level at start of flood testing to verify for any leaks/drops in water level. Attach before and after photos with time/date stamps.
317cf292-3992-5f46-a4ad-59882d64e301 | checkpoint | HOLD POINT - verification of Flood Testing Results - Any leaks Found?
d1c5791e-407f-51c0-b95a-0027665c89a0 | textbox | Note: if any leaks identified (if so re-membrane and test)?
a8b871d0-3dae-53c2-af55-7a4caff5a556 | signoff | Contractor to sign-off on flood testing results once passed.
8bd82640-dba8-5aff-b2ca-cf1adf578461 | checkpoint | Attach subcontractor ITP
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off