## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
f3040815-f88f-58c2-982a-09e5f7872883 | checklist | 04.12 - Ground Surface Treatment | itp | 04.12 - Ground Surface Treatment
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
fef421ff-1b2e-5740-80e4-75fc0b9a92ad | checkpoint | Testing for acid sulfate potential and reporting of test results shall be carried out on all excavated material and exposed cuttings on the Site which could reasonably be expected to have a possible acid sulfate potential.
32d45279-6d05-546c-a0ac-847226668f32 | note | Acceptance Criteria & Frequency (Project Specific) - Field pH testing As per National Acid Sulfate Soils Guidance
3cc9318f-bd7f-5df0-b6f0-b2dce1fc7e6f | note | Check Item - Hold Point 5
ffcce926-26cb-5537-af41-310b001fbb90 | note | Reference - MRTS04 Cl. 10.1.4 Table A2
0ddc893f-0f12-514c-ae3e-d0cb294f8492 | signoff | HOLD POINT
cf0a6d46-25e0-5d1b-9d7a-6a66d9b7db23 | checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
4caab747-244c-52af-b8f0-61733301355e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
47dc84b4-547a-5b45-9e92-09b0feffdeb2 | note | Check Item - Check Item
13df82e1-d237-5322-aa29-72fce1c06b09 | note | Reference - MRTS04 Cl. 12.2.1.1
cb89603d-bc62-5d87-b3b3-579a4280954e | checkpoint | Holes and localised depressions filled with similar material to the surrounding ground surface or material specified and compacted in accordance with Cl. 15
0ad7d230-16f6-5b62-9a00-219c8bd948b4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6676ff17-465d-5e77-a0f5-f9611c3819cb | note | Check Item - Check Item
79caac8c-a266-5b0a-880f-d8cf7a8b78fe | note | Reference - MRTS04 Cl. 12.2.1.2
730a2cf9-360c-52ad-9e60-b13cf7674bf7 | checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim
af671017-4e9a-5778-8a97-03f7d6fa4f79 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8e84ce28-553f-5e04-860e-90326effcae4 | note | Check Item - Hold Point 4
36cc2d85-c916-500c-802b-0f606b69bd7b | note | Reference - MRTS04 Cl. 9.4
33246af5-e23b-5f64-9317-7cd56254a2d0 | signoff | HOLD POINT
5925ff81-54ea-5c49-8c39-b7150fef1831 | checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl. 15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a maximum depth of 300mm using appropriate methods. Material below this depth shall be assesed under Clause 9.2.
fa0c7538-bb21-5bed-afa9-a1b599be0b96 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
525e6ac0-c7e2-5371-a1a8-efe7859eb200 | note | Check Item - Check Item
32038070-dc6b-5655-a4d7-f9db6201bb20 | note | Reference - MRTS04 Cl. 12.2.1.3
72668b6f-35c8-549d-87dc-bb5106709c99 | checkpoint | Relative Compaction - AS 1289.5.4.1 or AS 1289.5.7.1 After any clearing and grubbing, stripping of Topsoil and replacement of Unsuitable Material, the exposed ground surface on which an Embankment is to be placed shall, as a minimum, be scarified and re-compacted to a depth of at least 150 mm
9cfad661-5842-5c00-839c-140a1d25692c | note | Acceptance Criteria & Frequency (Project Specific) - CV 95% minimum - 1 tests per 500 m2 (min 1 per lot)
5873b74a-7cb5-59e5-bcd5-292f18a7139f | note | Check Item - Test
86312a87-1d83-59fc-ad35-dbf19ae37fec | note | Reference - MRTS04 Table 15.3(b) App. A
| checkpoint | 32408.01P Backfill with Rockfill to unsuitable (Provisional Qty, as directed)
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
83c308d8-6254-5d54-90c2-3c6b0b0d925d | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
b2fa6d79-456a-51d5-b01a-9baaa7d85ae6 | textbox | Print Name:
4a7f172b-def5-5133-bfd0-94253d5129fe | date | Date:
638c6fa7-4215-509f-a0a2-7aff24f38737 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
7c45a26f-1578-5379-9030-21c63fda9bf2 | textbox | Print Name:
01afcf9c-f500-5b54-b7ea-dd85358e1636 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off