## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | FEL SM Weekly Site Checklist |  | FEL SM Weekly Site Checklist | 4406dc62-fb9b-4004-bdee-2789c1defa6e
| section | Monday
| checkpoint | Prestart Meeting with Team
| checkpoint | Health Check
| checkpoint | Review Tasks for the week
| checkpoint | Identify Targets Including Hours
| checkpoint | Approve hours by 9AM for previous week
| checkpoint | Sign off Subcontractor Hours & Submit
| checkpoint | Review SWMS
| checkpoint | Site Toolbox Meeting
| checkpoint | SSSP in Order
| section | Tuesday
| checkpoint | Follow up outstanding RFI's with PM
| section | Wednesday
| checkpoint | Review Roadblocks & Follow Up if still unresolved
| checkpoint | QAs up to date
| section | Thursday
| checkpoint | Weekly planner filled out for week ahead
| checkpoint | Roadblocks identified and actioned
| checkpoint | Materials organized for week ahead
| checkpoint | Plans printed with any relevant notes added
| section | Friday
| checkpoint | Submit Toolbox minutes to main contractor and FEL office
| checkpoint | Job Cards up to date and submitted
| checkpoint | Team tasks for week ahead filled out on whiteboard