## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP 02 - Suspended Ceilings |  |  |  |  | Yes | ITP 02 - Suspended Ceilings - Rev A | 89492b51-b6c9-4339-8012-7813c9303072
checkpoint-status |  |  | checkpoint | 1 - Frame ceilings
label | acf629b7-eb87-5864-a500-dac5b50580c0 |  | note | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | 9e8b52a1-d144-55f0-9f11-5175a5f7af05 |  | note | ○ Refer to Lendlease CiDD – All Alerts and Guidelines for Suspended Ceilings
label | 85eae55e-66a7-501e-8626-caeb150b8681 |  | note | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | 11c136f4-4d32-5514-bbac-757da59eefa0 |  | note | ○ Studco installation guide. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000
label | d3ef19b2-5496-5ff5-bd74-2812fe9dc482 |  | note | Frequency - Each location
label | 1bc662ae-af92-5392-895c-15e07107a023 |  | note | Verification Records/Comments - Visual Checklist
label | c63b1cff-384b-519c-ba4e-2caad4ce09f0 |  | note | Inspection By: Subcontractor - S
label | 0e6d6ac0-1a50-5dc2-9920-c3bc02eab0cf |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 2 - Bulkhead framing
label | a87d65e1-8a3f-52c0-ab03-1358d2ce5bef |  | note | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | 080ea742-f3a4-57d6-92d4-be6761b748be |  | note | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | dceb9fa0-68fe-5e0b-8c6f-b061a2fff6f8 |  | note | ○ Studco installation guide. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000
label | 562b94fc-8dd0-5cf6-8c72-eb4bc1cdda29 |  | note | Frequency - Each location
label | 39affa5d-edd3-5a8c-9959-684267742d1a |  | note | Verification Records/Comments - Visual Checklist
label | a205338a-671f-5c9b-bcfd-e8df7a7dd20f |  | note | Inspection By: Subcontractor - S
label | 8b9e5b2b-7dde-51ca-94ff-0fd5217e132d |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 3 - Trim out access panels
label | 91605d68-f9cf-59c8-8012-60e6a8668b84 |  | note | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | a19ca0cd-afdb-5552-a733-a0619220319e |  | note | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | eebe0b7d-c526-587e-bb6c-a57b624586e5 |  | note | ○ Architectural Specification – 0531 – Suspended Ceiling Australian Standard - AS1530.4:2014
label | 8d4db2b0-447b-595f-b502-6cc6289fee1d |  | note | Frequency - Each location
label | ef1e8f42-2e31-505e-8b82-6c3411cc3637 |  | note | Verification Records/Comments - Visual Checklist
label | 554a7b6e-136a-51ec-ac6b-0fa49bfce171 |  | note | Inspection By: Subcontractor - S
label | eeffac6d-a862-5941-8d3c-fc2aa062cc47 |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 4 - Insulation to ceilings
label | 1660244a-5f7d-5d19-af97-167482f288ae |  | note | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | 783f91eb-59e5-5fee-800f-3a6d2cbb7579 |  | note | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | cfae7cee-ef01-5e4a-9961-27fc6452c574 |  | note | ○ Batts insulation installation guide Architectural Specification – 0819 Insulation and barriers Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 :1999, AS/NZS1530 Part 1: 1994
label | f03ec498-9a73-59ed-b641-51ed45d08058 |  | note | Frequency - Each location
label | 6685c543-cad9-5cf3-a8fd-4e4d705db349 |  | note | Verification Records/Comments - Visual Checklist
label | 1d9f83ea-4080-5107-8f9d-bed2441fb514 |  | note | Inspection By: Subcontractor - S
label | 80cc58f6-0dfd-5694-a2de-c4925f7f8b8d |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 5 - Service Check for pre-installation of sheets
label | 66c652f7-316f-5c22-9a44-727abb29cc03 |  | note | Reference Documents - Service Sign-off checklist
label | 478ae052-04b6-5a2e-b4d0-3517de580194 |  | note | Acceptance Criteria - All service checklists are signed off by relevant trades
label | c5cf083f-24b4-5e27-8d0f-1da30459fa40 |  | note | Frequency - Each location
label | cdfe27da-1465-549e-9413-054c5c68dff6 |  | note | Verification Records/Comments - Visual Checklist
label | b0d6d702-3002-5e6c-b3b3-0db5c53db6fc |  | note | Inspection By: Subcontractor - S
label | 0e161222-a371-59e5-9fa5-3d18fd326a35 |  | note | Inspection By: Lendlease - HP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Sheets to ceiling
label | 3f0dfc89-b47c-54e1-b2a0-d5b903670958 |  | note | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | eaa2f23a-34bf-54d4-ad7a-05253240857f |  | note | ○ Refer to Lendlease CiDD – All Alerts and Guidelines for Suspended Ceilings
label | b90f075b-6824-55f9-981a-4735e2af3d21 |  | note | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | b6e4eb5c-e69b-57d6-bc48-4d7695185d17 |  | note | ○ Studco installation guide. Architectural Specification – 0819 Insulation and barriers Australian Standard AS/NZS 2785:2000
label | 68dd1ff4-0b95-536f-99ad-5af6240e215c |  | note | Frequency - Each location
label | c79003c3-2d36-505d-a9e5-d9278249ae09 |  | note | Verification Records/Comments - Visual Checklist
label | 4a1df2e4-3aa0-5e72-be41-3539b25611d1 |  | note | Inspection By: Subcontractor - S
label | 7a47d16a-89d3-5b4f-a0e1-0a469f00b35a |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 7 - Stopping to ceilings
label | a1e35499-50cd-54b4-99b4-6efe691cf7e8 |  | note | Reference Documents - Refer to Lendlease CiDD - Alerts and Guidelines for Setting Compounds for Plasterboard
label | b1a9071c-e985-53f5-9ae5-c0b63ae85a3f |  | note | Acceptance Criteria - Boral installation manual revision 2016. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000
label | 6fec0015-6d1e-5935-ad97-c2180b9959b4 |  | note | Frequency - Each location
label | 3051e5b2-3cc3-5c82-a21f-ca195d14b304 |  | note | Verification Records/Comments - Visual Checklist
label | 3f74e3ad-5318-5a98-bd57-4df13c3af672 |  | note | Inspection By: Subcontractor - S
label | 00d343db-4ef6-56b4-82ac-f07ce2a225ee |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 8 - Sanding to ceilings
label | 03c05462-6013-5a53-8795-c31fc680a7a8 |  | note | Acceptance Criteria - Boral installation manual revision 2016. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000
label | de97ed3c-a4f8-5a56-86e4-54706d305180 |  | note | Frequency - Each location
label | cdcd3bfb-d913-55a0-9ab3-43a97c7c81d0 |  | note | Verification Records/Comments - Visual Checklist
label | 1ba0643d-9056-594d-b936-278028ef9955 |  | note | Inspection By: Subcontractor - S
label | 34c9def2-db1c-58fe-9d9c-d32ae09c3d4e |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 9 - Fit access hatch frame
label | c25b6b0c-5653-59d2-bc92-b5848c168489 |  | note | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | f1d2dc4c-baab-56ee-a152-d0922cd90f57 |  | note | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | 8da6ab2f-ea80-51bd-a4a8-2746227d16fd |  | note | ○ Architectural Specification – 0531 – Suspended Ceiling Australian Standard - AS1530.4:2014
label | b98fe40d-ccc0-5107-a5d2-93cfcfe5da2e |  | note | Frequency - Each location
label | ce52648a-3615-5395-a27b-392ffc930d25 |  | note | Verification Records/Comments - Visual Checklist
label | 166b71fe-e31b-547e-b6b6-b784c227da44 |  | note | Inspection By: Subcontractor - S
label | feafc565-cc3b-5930-b47b-a9d131523661 |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 10 - Cut out for lights
label | 9500b8d5-ddcb-599f-adae-99b1f5dae88f |  | note | Reference Documents - Architect drawings
label | 9cb523b9-a097-533c-833c-765ad9f08299 |  | note | Acceptance Criteria - Reflected Ceiling Plan approved by Lendlease
label | e38a52ef-0b18-575e-b275-caf2c06180ff |  | note | Frequency - Each location
label | 5e2d1844-ba0a-56e0-bf2a-b95328a565ab |  | note | Verification Records/Comments - Visual Checklist
label | 97eb8c4f-6abf-596f-bafb-0c55db16cf8d |  | note | Inspection By: Subcontractor - S
label | 7e9cfb53-e84a-5267-92eb-b1ebe1b9bab0 |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 11 - Clean up
label | b669e144-9915-5ba9-a122-2ce4da736c7a |  | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | 54287364-9413-5810-9368-6aed17f4240b |  | note | Frequency - Each location
label | e68ed761-127a-5f25-9040-521eb7fa1912 |  | note | Verification Records/Comments - Visual Checklist
label | e91f5e64-3de1-591d-bc79-2835cc72e673 |  | note | Inspection By: Lendlease - R
checkpoint-status |  |  | checkpoint | 12 - Check ceilings for patching
label | a8964d16-458e-589b-879e-ba5c290df8ec |  | note | Reference Documents - Architect drawings
label | ee05a25e-036f-52c9-9ab0-23dfa759e975 |  | note | Acceptance Criteria - Reflected Ceiling Plan approved by Lendlease
label | cb809776-67de-53cf-89d3-24cf392f017d |  | note | Frequency - Each unit
label | a6357295-2a11-5d01-916a-f1237be0792f |  | note | Verification Records/Comments - Visual Checklist
label | 345c5093-0caf-52e0-bcc9-1851377a62b3 |  | note | Inspection By: Subcontractor - S
label | 323fd036-f450-57c1-9b59-9a548f00934b |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 13 - Materials Receipt Inspection
label | 2aee6676-ffb4-5377-b2a3-99d28c69dd7b |  | note | Reference Documents - Refer to ITP No: 3 Incoming Goods
checkpoint-no-status |  |  | checkpoint | Comments:
date | 2f8bcc5d-3b62-5abf-84b9-2426843bf505 |  | date | Date of Inspection:
text | 49866b50-8a28-553d-9360-ca780def32b8 |  | textbox | Carried out by:
checklist-flat |  |  | checklist | ITP 01 - Partition Walls |  |  |  |  | Yes | ITP 01 - Partition Walls - Rev A | a7c560ae-c88a-4bf0-976a-cafd31f64e33
checkpoint-status |  |  | checkpoint | 1 - Set out walls
label | a7ba4a3b-4953-5df1-9588-f174f20a82ca |  | note | Reference Documents - Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE_1)
label | 4a2c72de-2be2-5042-87c3-1025ee6c07de |  | note | Acceptance Criteria - Partition Plan and Partition Wall Details approved by Lendlease.
label | 3c313f44-4bcd-5006-874a-6d60aaa2d306 |  | note | ○ Architectural Specification – 0522 Partitions And Linings Australian Standard: AS/NZS 4600:2005, AS/NS 1170:2002
label | 4dc2a2d3-670b-5401-ab47-63e6041500f4 |  | note | Frequency - Each location
label | 97ea3f7e-bbc3-5774-bc59-bfdd9e58ae6d |  | note | Verification Records/Comments - Visual Checklist
label | 48ca4862-9206-5047-8ec7-a8ef2fbe53be |  | note | Inspection By: Subcontractor - S
label | 0028327e-9895-5862-bb00-65fef75c8165 |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 3 - Metal stud wall frame
label | fc8c1455-b92a-5f18-bcee-17776431638b |  | note | Reference Documents - Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE_1)
label | d163346c-1182-530b-b5a5-9469c3eb22cd |  | note | ○ Refer to Lendlease CiDD for All Alerts and Guidelines for Smoke doors and Baffle
label | a9ca42f7-2281-5f48-a98f-14db83b39501 |  | note | Acceptance Criteria - Partition Plan and Partition Wall Details approved by Lendlease.
label | 7a7077ab-4a29-51df-8828-e1574a11d5f7 |  | note | ○ Architectural Specification – 0522 Partitions And Linings Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005, AS/NS 1170:2002
label | b385f95a-875e-5202-ac9b-70fa78927d39 |  | note | Frequency - Each location
label | 282df1d5-cc0c-5008-8e63-7a0eabfe6c58 |  | note | Verification Records/Comments - Visual Checklist
label | 843085d1-df2d-54d4-9af5-289087f4ba0b |  | note | Inspection By: Subcontractor - S
label | 6b8e7573-8b8a-5b26-b7b9-bdf0c191aab7 |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 4 - Noggins
label | f2c1541c-99a3-536b-8318-6796f6a2dbfc |  | note | Acceptance Criteria - As per scope of work.
label | 7e9dbd9a-67fd-53c2-981a-547b35a0be05 |  | note | ○ Studco Wall design & installation manual Volume 3.2 Architectural Specification – 0522 Partitions And Linings Australian Standard: AS/NZS 4600:2005, AS/NS 1170:2002
label | 63ecb77a-ac09-535b-a50a-9d88325d4f04 |  | note | Frequency - Each location
label | f21aa33b-16d1-5c50-a63e-668e9192b685 |  | note | Verification Records/Comments - Visual Checklist
label | 43454b26-cc68-500b-a863-cc059d2df70d |  | note | Inspection By: Subcontractor - S
label | b7f4966f-16ad-55e6-818e-33def118b7fd |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 5 - Check no screws in deflection head
label | 8776d5de-31b4-53e8-9945-aa0c62a6d4d2 |  | note | Acceptance Criteria - No screws in deflection head
label | 05c689bf-f4da-5df9-ac1d-f05d628044ec |  | note | Frequency - Each location
label | 65d5276f-f988-5c74-bbf0-02afc80cb957 |  | note | Verification Records/Comments - Visual Checklist
label | 53d36a0d-2bc1-527a-b6b1-79b9285276d4 |  | note | Inspection By: Subcontractor - S
label | 167bdd9c-43f6-5716-b397-995df5dc2de4 |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 6 - Service Check for pre-installation of sheets
label | ebc27dd6-596b-5831-807d-c20ff8e6d549 |  | note | Reference Documents - Service Sign- off checklist
label | 1b0d7d8c-57e3-55bd-ae51-4aadeaba1b57 |  | note | Acceptance Criteria - All service checklists are signed off by relevant trades
label | 98afbaae-077a-5290-a5ea-6d6852ed44ce |  | note | Frequency - Each location
label | cbda3bd2-c768-5a72-8edb-c69fb4b504b8 |  | note | Verification Records/Comments - Visual Checklist
label | f4dd9026-2bf1-50d7-8bba-b662d401af31 |  | note | Inspection By: Subcontractor - S
label | 9aa62d55-45e5-56ba-86a2-f4e0e7a94cc8 |  | note | Inspection By: Lendlease - HP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Sheet all walls
label | 2a020916-4e59-54d6-bca0-2293d9f3d28a |  | note | Reference Documents - Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE_1)
label | 02ee5a5d-dacf-5e68-98f5-1e0472a4ec0a |  | note | ○ Refer to Lendlease CiDD for All
label | 4558bc63-dbff-53b2-9336-7832272f624d |  | note | ○ Alerts and Guidelines for Fibre Cement and Smoke doors and Baffle
label | 27f17306-d3cb-53e9-a748-8a3a03709597 |  | note | Acceptance Criteria - Partition Plan and Partition Wall Details approved by Lendlease.
label | 00ff8271-8b2b-5ae9-bb11-450a23709db1 |  | note | ○ Check wall types before installation (F/R, Acoustic, Wet Area, PBD etc).
label | 635da5c1-8dbc-5b72-bf5d-f0feb331b577 |  | note | ○ Architectural Specification – 0522 Partitions And Linings Boral installation manual revision 2016. Batts insulation installation guide. Australian Standard: AS/NZS 2589.1:1997
label | f4e7db85-db41-5038-be6c-25d2fbe81634 |  | note | Frequency - Each location
label | dffa697a-23ea-5012-a588-818b93c23921 |  | note | Verification Records/Comments - Visual Checklist
label | c3a93999-1404-53a9-a98d-afe9d2fef3e6 |  | note | Inspection By: Subcontractor - S
label | 9cd625ca-ed81-581c-9246-06ebe4d4787c |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 8 - Caulking
label | 37f37d9c-6c03-58b2-83d1-afddad491fc7 |  | note | Acceptance Criteria - Boral installation manual revision 2016 Australian Standard: AS 1530.4-2014, AS4072.1-2005, AS1157-1972
label | 8b16eb69-bfef-5589-ba34-52a8eae3bc2e |  | note | Frequency - Each location
label | 571c22e9-22bf-5135-8f92-40102c17ed40 |  | note | Verification Records/Comments - Visual Checklist
label | 7a00282b-b870-5ccc-a937-423fe37c1158 |  | note | Inspection By: Subcontractor - S
label | 8742c2d3-0e57-5cd0-b796-406183f63873 |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 9 - Check insulation in walls
label | 056084f6-5488-5cb9-a51a-f1c3b8564e4b |  | note | Reference Documents - Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE_1)
label | d463c80a-5dc2-5f8c-a3a8-1abb6916a35e |  | note | Acceptance Criteria - Partition Plan and Partition Wall Details approved by Lendlease.
label | 9101b65e-4279-5987-9f31-19c789b6a232 |  | note | ○ Batts Insulation Installation Guidelines Architectural Specification – 0819 Insulation and Barriers Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1:1994
label | 352563b8-2c6d-5793-a3c3-c2cbba108234 |  | note | Frequency - Each location
label | 276a34b6-182a-58d6-b878-5baeb7ffe8d1 |  | note | Verification Records/Comments - Visual Checklist
label | 43e131db-3968-54e2-951e-1c22eb585a8c |  | note | Inspection By: Subcontractor - S
label | c26515b2-ab16-5faf-b41c-73062ab75bf1 |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 10 - Stopping to walls
label | e35e4aa9-c570-553f-be0d-6ecb28de252f |  | note | Reference Documents - Refer to Lendlease CiDD - Alerts and Guidelines for Setting Compounds for Plasterboard
label | 6268e785-4e25-579f-b714-4df8ac56b2cb |  | note | Acceptance Criteria - Boral installation manual revision 2016. Australian Standard: AS/NZS 2589.1:1997
label | 4d538f5c-b7d8-5876-afb4-c7ae02342cec |  | note | Frequency - Each location
label | f55fd946-6056-561d-aef3-2a3ebd08f2c6 |  | note | Verification Records/Comments - Visual Checklist
label | e8ed296a-fce4-5488-af8f-d449a9594a4e |  | note | Inspection By: Subcontractor - S
label | 9bd60efb-f50b-56be-a610-d9913284a093 |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 11 - Sanding to walls
label | ad54d46a-a3b5-5bbd-b297-33e5508ba15f |  | note | Acceptance Criteria - Boral installation manual revision 2016. Australian Standard: AS/NZS 2589.1:1997
label | 2eca54d9-fde0-578a-ba68-878ddc93d438 |  | note | Frequency - Each location
label | fab50a8e-876f-5f4d-aa0d-98f158f4c5a5 |  | note | Verification Records/Comments - Visual Checklist
label | b7714894-c831-5e39-94a6-23c1f083e588 |  | note | Inspection By: Subcontractor - S
label | 9427616b-1750-5d55-92be-3469106d839c |  | note | Inspection By: Lendlease - S
checkpoint-status |  |  | checkpoint | 12 - Clean up / Check walls for patching / Materials Receipt Inspection
label | 58268509-74cd-533f-998a-30dde11a3f90 |  | note | Reference Documents - Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE_1)
label | d1d83138-154a-5b52-a55a-27fb9535e37e |  | note | ○ Refer to ITP No: 5 Incoming Goods
label | 7f18cdaf-29c6-50a2-a126-b30612144177 |  | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | a6cecd99-d5fa-576c-a2bc-c20ed23bc770 |  | note | ○ Partition Plan and Partition Wall Details approved by Lendlease.
label | 8cad6224-a491-5f50-8c52-e3117e8ce202 |  | note | Frequency - Each location
label | 341c6875-8acd-52ca-85c2-22bd6c8556bf |  | note | Verification Records/Comments - Visual Checklist
label | cede2e10-4aab-5f19-a7f2-786471be9ed0 |  | note | Inspection By: Subcontractor - S
label | fb016109-15f1-5433-b7a0-121a1f257458 |  | note | Inspection By: Lendlease - R
checkpoint-no-status |  |  | checkpoint | Comments:
date | 1d23aa7a-30cc-5fec-80d6-1c561bc47706 |  | date | Date of Inspection:
text | c458e479-8ec1-5f8b-9a37-3708a3e7d854 |  | textbox | Carried out by: