## Ultratherm Xtreme roofs
Rooflogic Xtreme Fibertitre Roofing System AWL
Pre Start
Area Accessible
Edge protection in place
Structure and substrate has been handedover by LTM. No check of falls by SWP
Base Deck
Base deck installed as per agreed scope with lts
All penetration boxes and pipes to be installed through the base deck
Approved diaphragm fixings used
Base deck screwed off at every purlin and every pan
Base deck stiched along side-laps at 300mm centres
VCL
Is the substrate clean, dry clear of swarf
All areas covered and sheets lapped 100mm min
All holes/penetrations pactehd and watertight
Stonewool 150mm Insulation above VCL
Surface is dry prior to install
VCL has been checked for no damage
600mm wide stonewool insulation installed above tall wall
Joints flush (no gaps between boards)
Gutter edge flashing installed
Roof board HDP mechanically fixed
Surface is dry prior to install
Roof boards Installed tight and in brick pattern
orrect length screw with laod washer
Insulation Board installed tight and no gaps
Installed as per wind uplift fixing plan
ILD system
Conductive continuity mesh installed
Roof board HDP Adhered with 600 board bond glue
Roof boards Installed tight and in brick pattern
Correct glue Armac 600u
glue Installed as per suppliers specifcation Spray Armac 600u Board Bond 30mm wide beads continuously as 100mm centres.
Fibertite
Surface clean and free from debris
Adhesive installed to substrate the width of the roll
Laying of membrane into the adhesive and Correct glue Armac 400u
Laping on adjacent membrane to be minimum of 75mm
Broom/rolling of membrane into adhesive
Wipe and clean of laps prior to welding
Test weld with welding machine
Probe of seam with QA hook
ILD test
Fiberclad Flashings
Installed correctly accordnig to specifications
Fixings and welding done according to specifications and details
Probe of weld with QA hook
Review and Sign off
All installation work complete, checked and reviwed as per specification
FCC project manager sign off

## Ultratherm Xtreme gutters
Rooflogic Ultratherm Xtreme tappered gutter
Pre Start
Area Accessible
Edge protection in place
Steel plate gutter liner installed by others
Steel plate gutter liner
Gutter liner installed signed off and handed over
Outlet holes cut into base
VCL
Is the substrate clean, dry clear of swarf
Prime steel deck with SA primer
All areas covered and sheets lapped 100mm min
All holes/penetrations pactehd and watertight
Stonewool Insulation above VCL
Surface is dry prior to install
VCL has been checked for no damage
600mm wide stonewool insulation installed above tall wall
Joints flush (no gaps between boards)
PIR Insulation
Surface is dry prior to install
VCL has been checked for no damage
Gutter edge flashing installed
Prime top of VCL with SA primer
Install board bond adhesive
Insulation Board installed tight and no gaps
ILD system
PIR insualtion linked with conductive metal tape
Conductive continuity Ribbon installed at 1200mm centres
Roof board HDP
Install board bond to PIR board
Roof boards Installed tight
Install RL roof outlet to sit flush at roof board
Fibertite XT
Surface clean and free from debris
Adhesive installed to substrate the width of the roll
Laying of membrane into the adhesive
Laping on adjacent membrane to be minimum of 75mm
Broom/rolling of membrane into adhesive
Wipe and clean of laps prior to welding
Test weld with welding machine
Probe of seam with QA hook
ILD test
Fiberclad Flashings
Installed correctly accordnig to specifications
Fixings and welding done according to specifications and details
Probe of weld with QA hook
Review and Sign off
All installation work complete, checked and reviwed as per specification
FCC project manager sign off

## FT Hybrid system
Rooflogic Fibertite hybrid system
Pre Start
Area Accessible
Edge protection in place
Substrate clean and clear of debris and moss/mould
Concrete substrate
Free from holes & lumps of concrete
Outlet holes cut into base
Bitumen Base sheet
Is the substrate clean, dry and clear
Install FTR SBS Adhesive
Install Bitumen base sheet into adhesive with 80mm min laps
Roll/broom of membrane into adhesive
Hot air weld any laps
Probe of laps with QA hook
Fibertite XT
Surface clean and free from debris
Adhesive installed to base sheet the width of the roll
Laying of membrane into the adhesive
Laping on adjacent membrane to be minimum of 75mm
Broom/rolling of membrane into adhesive
Wipe and clean of laps prior to welding
Test weld with welding machine
Probe of seam with QA hook
ILD test
Fiberclad Flashings
Installed correctly accordnig to specifications
Fixings and welding done according to specifications and details
Probe of weld with QA hook
Review and Sign off
All installation work complete, checked and reviwed as per specification
FCC project manager sign off

## FT over ply
Rooflogic Fibertite over plywood
Pre Start
Area Accessible
Edge protection in place
Substrate clean and clear of debris and moss/mould
Plywood substrate
Fixed off at correct centres
No damage to substare
install ILD SS Mesh over substrate
Roof board HDP
Roof boards Installed tight and in brick pattern
Correct length screw with laod washer
Installed as per wind uplift fixing plan
Fibertite XT
Surface clean and free from debris
Adhesive installed to base sheet the width of the roll
Laying of membrane into the adhesive
Laping on adjacent membrane to be minimum of 75mm
Broom/rolling of membrane into adhesive
Wipe and clean of laps prior to welding
Test weld with welding machine
Probe of seam with QA hook
ILD test
Fiberclad Flashings
Installed correctly accordnig to specifications
Fixings and welding done according to specifications and details
Probe of weld with QA hook
Review and Sign off
All installation work complete, checked and reviwed as per specification
FCC project manager sign off