## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Level Sign Off |  |  |  |  | Yes | Level Sign Off | 0c1ad502-99b2-4af1-a1d9-6a28ecad77b2
checkpoint-status |  |  | checkpoint | Details complete
text | 8b7e8f0d-559e-5229-ac3f-d01e4c660ed3 |  | textbox | Date:
text | 5c2acaa6-d203-547f-ba98-c23d766c50b1 |  | textbox | Level:
checkpoint-status |  |  | checkpoint | Builder Sign Off
label | 2476659d-1555-50b1-9222-6ca5f86ad093 |  | note | In signing the below, you agree and acknowledge that on this level:
label | a5a6afed-b335-5389-9b6a-2ffc55543916 |  | note | All props have been removed
label | 413343e6-e6ce-5a04-91c1-bf14cd530b79 |  | note | All grouting has been completed
label | 706bd6e5-78db-553e-aa01-ebb54b9143f4 |  | note | All patching has been completed
label | 5134b595-b898-51bd-91c8-3a74811419de |  | note | All sealing has been completed
label | 9cb61bd0-36bf-56eb-a481-1fc1c17fe7c9 |  | note | All issued defects have been completed
holdpoint |  |  | signoff | BUILDER SIGNATURE (MUST INCLUDE NAME)
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details | 1e41987d-4df5-4e7b-a13d-e48dca009a0e
checkpoint-status |  |  | checkpoint | Project details entered below
text | bc4a0823-b279-5923-953c-bc595508a8cb |  | textbox | Job Number
text | 160e97a1-566e-5108-a6b7-b2b3c70f639c |  | textbox | Project Name
text | b373959a-7e48-53e1-9bc6-2cda54e6c378 |  | textbox | Site Address
text | 89ba1af6-4e9b-5857-bf34-8b397e3feb14 |  | textbox | Builder
text | 854264ef-e25a-539c-a747-347eec1ebc54 |  | textbox | Euro Precast Project Manager
text | 8909309d-7b03-5c68-bbf4-24bd37a81318 |  | textbox | Euro Precast Lead Draftsperson
text | 0ffffe63-cea1-5e70-9625-7fe68b5906a0 |  | textbox | Euro Precast Installer
checkpoint-status |  |  | checkpoint | Grouts submitted for approval (UPLOAD TDS and SDS for each grout submitted)
checkpoint-status |  |  | checkpoint | Have submitted grouts been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Caulking products submitted for approval (UPLOAD TDS and SDS for each caulking product submitted)
checkpoint-status |  |  | checkpoint | Have submitted caulking products been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Patching products submitted for approval (UPLOAD TDS and SDS for each patching product submitted)
checkpoint-status |  |  | checkpoint | Have patching products been approved? (UPLOAD copy of approval)
checklist-sectioned |  |  | checklist | Delivery / Installation Day Checklist |  |  |  |  | Yes | Delivery / Installation Day Checklist | 29383169-99ac-4f46-8c4c-114b7a4d8fde
checkpoint-group |  |  | section | HOLD POINT - Confirmation of slab strength
checkpoint-status |  |  | checkpoint | Has the slab reached the minimum strength required (UPLOAD copy of concrete slab test result)
label | c9bbf854-3550-5dcf-b99e-2aa2642a158e |  | note | 12MPa for cast-in anchors and 20MPa for post installed anchors
checkpoint-group |  |  | section | Prestart / Start-up
checkpoint-status |  |  | checkpoint | Date of Installation
checkpoint-status |  |  | checkpoint | Installation team completing the install today
label | 2e9de6a9-8443-50b6-8719-3f96e702f0c9 |  | note | List names in comments
checkpoint-status |  |  | checkpoint | Exclusion Zone is set up (PHOTO REQUIRED of the exclusion zone)
checkpoint-status |  |  | checkpoint | Plant & Equipment prestart/logbooks filled out (PHOTO REQUIRED of logbooks)
checkpoint-status |  |  | checkpoint | Toolbox Talk / Pre-Start has been completed (PHOTO REQUIRED of talk)
checkpoint-group |  |  | section | Summary of the day
checkpoint-status |  |  | checkpoint | Hours worked
select | 78d03587-565c-5bab-926a-b4740dbf00a7 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 3c43c761-e0cc-5dda-a17e-e255c537b145 |  | dropdown | Time finished on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-status |  |  | checkpoint | Elements Installed today
label | 4d0b8069-eb4f-5b81-95fc-08e191d04ec9 |  | note | COMMENT below if number of elements installed doesn't match the Load Lists in the Safe Load Declarations
select | 2ada973d-8803-5f88-8f23-e67ec388aa3e |  | dropdown | How many elements were installed today? | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34, 35, 36, 37, 38, 39, 40
checkpoint-status |  |  | checkpoint | Were there any delays?
label | 87faf9ba-5e3f-5b3d-aaee-0a556769d8b7 |  | note | COMMENT below in enough detail to explain the delay and what caused it. Add PHOTO if it helps record the delay.
select | d3140643-7f44-5203-8eb3-18b5642f0f44 |  | dropdown | How long was the delay? | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr
select | 58046ee7-6a2f-55a4-9755-818c7abe3b68 |  | dropdown | How many installers were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
select | ede201f0-4afc-511e-b34f-570146242cef |  | dropdown | How many trucks were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
checkpoint-status |  |  | checkpoint | Builder sign-off
label | f4a9c5b1-6546-51e0-a12c-90fcd787c5e0 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)
checklist-sectioned |  |  | checklist | Variation works completed |  |  |  |  | Yes | Add New Variation | 3336da1a-1ef7-4132-b5da-47a394c554cd
checkpoint-group |  |  | section | Works completed
checkpoint-status |  |  | checkpoint | Details entered below
text | c1876c5e-9363-593c-8eae-090e7e67aabe |  | textbox | Date:
text | e48c2ef2-7c9a-5f60-8588-3bb024bff947 |  | textbox | Name of people who completed the works:
select | b90eac2f-d675-5854-8254-d73c31208848 |  | dropdown | Time started at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 9c1bc354-2aa7-5474-b55a-79c1d825e492 |  | dropdown | Time finished at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
text | 4a6b40d7-361f-5737-b1e5-ea343ebf6761 |  | textbox | Consumables used:
text | 89b4f543-41c5-5f1f-8493-03d9b87fa0e2 |  | textbox | Summary of works completed
checkpoint-group |  |  | section | Builder sign-off
checkpoint-status |  |  | checkpoint | Builder sign-off
label | 26b61b0b-0ae9-5937-9b1f-38d7a598bfd9 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)
checklist-flat |  |  | checklist | Safe Load Declaration Checklist |  |  |  |  | Yes | Safe Load Declaration Checklist | ab62791b-6e64-41df-a915-dbfebf3780c5
checkpoint-status |  |  | checkpoint | Details complete
text | abb08659-914e-5939-8385-bb6666376ee9 |  | textbox | Date:
text | f631cf62-ede5-59c3-b583-0da3638291ee |  | textbox | Time truck arrived at Factory:
text | a8a721f5-61c3-5f91-8b71-905b04d0c226 |  | textbox | Time truck departed Factory:
text | f5d5b5ec-efb6-5b0b-94fb-f54892a29fff |  | textbox | Project Name:
text | b3a4c639-214e-5396-8ad3-2f4c44ba2d4e |  | textbox | Delivery Address:
text | 27d98810-1d9e-5a35-833d-057acf9428b0 |  | textbox | Transport Company:
text | 8d642f0d-fbc2-5193-8958-3a55940778ac |  | textbox | Truck Registration #
text | 33863c76-b0f7-5b8c-867b-934da075c45b |  | textbox | Trailer Registration
select | 20a688a2-78eb-5b81-9e7a-eb64177cbbf0 |  | dropdown | Trailer Type: | Drop Deck, Drop Deck No Frame, Flat Top, Layover, Super Layover, Commission
checkpoint-status |  |  | checkpoint | Upload photo of Load List used for load
checkpoint-status |  |  | checkpoint | Upload photos of both sides of loaded truck (after being chained down)
checkpoint-status |  |  | checkpoint | Load Declaration
label | 0c12d926-aea0-5cfe-a35a-d32ce06234dd |  | note | In signing below, you agree and acknowledge that:
label | 36c05e88-67c0-5e08-b998-35a297a5aa72 |  | note | You are not permitted to leave the Euro Precast factory unless a Safe Load Declaration has been completed
label | 59e6fb14-6fc2-5327-8508-6b78ffadb51e |  | note | You have been provided with a copy of the load list that indicates individual element weights and total approximate load weight (excluding trailer/frame weight)
label | 33f720fe-9e45-5a24-83f1-f78cf85630de |  | note | You have chained down all units/elements in a safe and secure manner and in accordance with the latest published government/industry best practice guidance material
label | a81d86ff-767f-5272-8c2a-e6c29250d8cd |  | note | You will abide by all safety rules, PPE requirements and client instructions on the project site at all times.
label | dcaf70ef-c61c-5226-bb66-adb5999d9435 |  | note | You as an individual, the truck, the trailer and load comply with the latest requirements of the Heavy Vehicle National Law and Regulations (HVNL)
holdpoint |  |  | signoff | Driver Signature (must include Company)
checklist-flat |  |  | checklist | Grout Testing Checklist |  |  |  |  | Yes | Grout Testing Checklist | c7ab256b-a428-42c0-8a59-92bf994a4916
checkpoint-status |  |  | checkpoint | To organise grout testing, call Construction Sciences. Primary contact is Michael Hardcastle on 0429 791 069. Secondary contact is Joshua Borg on 0429 790 444
text | eb722c43-9578-5232-9b65-00f759be767e |  | textbox | Date:
text | cfe0abd9-00bd-5536-a57e-e165bb3a3691 |  | textbox | Project Name:
text | eebe3498-74bf-5f44-a1f2-5cc3617db90a |  | textbox | Time of test:
text | 2b95881c-50fb-51f2-8815-dd03f5eab2aa |  | textbox | Grouts tested:
checkpoint-status |  |  | checkpoint | Upload grout test results
checklist-sectioned |  |  | checklist | Manufacturing Checklist |  |  |  |  | Yes | Manufacturing Checklist | d345c0c8-7844-475c-af65-ee1297ade0e0
checkpoint-group |  |  | section | Manufacturing Documents
checkpoint-status |  |  | checkpoint | IFC Element Drawing
checkpoint-status |  |  | checkpoint | Euro Precast Primary Lifting and Propping Certification
checkpoint-status |  |  | checkpoint | Secondary Lifting Certification
checkpoint-group |  |  | section | Pre-Pour Checks
checkpoint-status |  |  | checkpoint | Mould check
boolean | dca07b31-2303-50bb-aee8-adba4f7840b7 |  | tickbox | Mould clean with release oil applied correctly
boolean | 2433b0bf-082e-5c0a-8f6d-0e227a3b72b9 |  | tickbox | Primary & diagonal dimensions checked
boolean | 92e4ceb7-0ed0-5dc8-93db-dfc0cb2624bb |  | tickbox | Openings Checked and Correct
boolean | 8cea46e1-78ed-5ec4-a1cc-c9ecea4ca0da |  | tickbox | Rebates, Architectural Grooves Installed Correctly
boolean | 9a14f796-ea03-522e-bee1-2158a9886050 |  | tickbox | Formwork chamfers installed correctly where required
checkpoint-status |  |  | checkpoint | Reinforcing check
boolean | d37dd29b-dbf9-589c-8fab-a8f949065358 |  | tickbox | Correct Size and Type
boolean | 262316b2-5dc8-5030-a1f2-71cf14b18c89 |  | tickbox | Laps and Splices correct
boolean | d282d5c8-6610-5f7e-80e0-aae771013b2a |  | tickbox | Cover Checked
boolean | 39cc27aa-7f8e-5a39-b453-8c3edd58b9b8 |  | tickbox | Spacing Checked
checkpoint-status |  |  | checkpoint | Cast in items check
boolean | f0671980-34d0-5518-b519-19513ede9727 |  | tickbox | Ferrules/Inserts installed, checked and correct
boolean | 8b98fdcc-6340-56f1-9275-17df18cf9858 |  | tickbox | Starter Bars inserted, checked and correct
boolean | 86ab28ec-8041-5aa8-b6f3-18d291dd1b25 |  | tickbox | Lifting anchors installed, checked and correct
checkpoint-status |  |  | checkpoint | Check Minimum Cover
checkpoint-status |  |  | checkpoint | ID Tag installed in non-visible face
checkpoint-status |  |  | checkpoint | Pre-Pour checks completed and approval given to pour Element
label | dd19783d-ab46-58ee-9bb0-f30d1a611b81 |  | note | Upload sufficient number of photos of element
checkpoint-status |  |  | checkpoint | Upload photo of signed pre-pour check of shop drawing
checkpoint-group |  |  | section | Concrete Pour Checks
checkpoint-status |  |  | checkpoint | Concrete Strength correct as per design
boolean | 32be6cbc-fe9e-5dc8-bbb8-14ead5ba71af |  | tickbox | All Concrete Dockets Attached
text | c7f4c1ce-f05d-529c-8c88-d0938ecf2935 |  | textbox | Date element was cast
checkpoint-group |  |  | section | Post-Pour / Pre Delivery Checks
checkpoint-status |  |  | checkpoint | Visual Check
boolean | ee98a9fe-0085-5c8c-81c3-f6a7271f3d8d |  | tickbox | Does the finish meet class 2 as per AS3610
boolean | 74e8261e-f34b-5e54-83a6-0cbae306f94f |  | tickbox | Chamfers clean, neat and on all required edges
boolean | c08c5fd5-14fd-568f-b444-aefc89f7ad14 |  | tickbox | Lifting anchors checked and approved
boolean | 2418c445-de30-539e-bfe0-7d120d03e748 |  | tickbox | Critical fitments / fixtures checked and approved
boolean | cea1a7e1-3a0a-5fe2-8a0e-6c7a1e913ba6 |  | tickbox | Openings (formwork removed)
boolean | 1d7fc1c6-d38e-52d5-bc40-8daec5c37f76 |  | tickbox | Nailplates / Recesses etc removed
checkpoint-status |  |  | checkpoint | Any Strongbacks Installed where required
checkpoint-status |  |  | checkpoint | Element free from defects that will impact structural integrity or durability?
label | e3fa68f6-f049-5ee6-867c-bd16a34ec960 |  | note | If 'FLAG', raise NCR and notify EP Project Manager to discuss with builder
boolean | 0ea0bd34-31b1-528e-91b5-df673501f135 |  | tickbox | If NCR raised, take photo of completed approved works
checkpoint-status |  |  | checkpoint | All Post Pour Works complete - Element Checked, Approved and Ready for delivery
checkpoint-group |  |  | section | Concrete Test Results
checkpoint-status |  |  | checkpoint | Concrete Test Result attached
label | 8abe6c28-110e-5158-b001-f7af6a6c5673 |  | note | Upload actual test result OR a test result of the same mix design from the same day
checklist-sectioned |  |  | checklist | Installation Checklist |  |  |  |  | Yes | Installation Checklist | fa9e77ad-398b-485e-86d5-5f6ea095a3e0
checkpoint-group |  |  | section | Element Install & Grouting
checkpoint-status |  |  | checkpoint | Bedding grout placed and finished as per project requirements
boolean | f35a015c-a7c5-5e72-b3c0-f1d2f643089a |  | tickbox | Bedding grout (trowelable) used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | be66fcda-3418-5f56-a849-c68c2faefaf0 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 13820dd0-c5ff-55f9-8df5-12a9765cb004 |  | tickbox | Grout bed sufficient to ensure full coverage (PHOTO REQUIRED of grout bed prior to landing element)
checkpoint-status |  |  | checkpoint | Element installed to (PHOTO REQUIRED to show survey pins and spirit level bubble):
boolean | 449b627d-d390-5c67-9f54-c718876a88c7 |  | tickbox | Survey Pins
boolean | 5e61a5c5-4fc8-5a74-8466-e29d35a6cc0f |  | tickbox | Within 5mm of vertical plumb
boolean | 5eebb43a-e842-5ef7-87f0-9917d0348752 |  | tickbox | Face alignment within 5mm
checkpoint-status |  |  | checkpoint | Element propped as per Euro Precast PEDS (PHOTO REQUIRED of element propped)
boolean | f7172c76-62ad-5c80-beaa-6bb5c20aea5d |  | tickbox | Prop bolts installed with tool to ensure locking mechanism can't be removed by hand
checkpoint-status |  |  | checkpoint | Dowel tube (flowable) grout placed and finished as per project requirements
boolean | 0e5243ed-4fa4-5b70-b76d-d4112eb6a4b9 |  | tickbox | Dowel tube grout used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | 2675b456-6c19-5ef3-96b9-1c0de43d4735 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 5c5aeb76-5858-5a1a-b1e9-1dc78d0a5711 |  | tickbox | Dowel tubes filled to top of tubes
checkpoint-status |  |  | checkpoint | Is there any transport or erection damage that needs to be fixed (PHOTO REQUIRED of damaged area)
label | 400c6786-eafa-5d39-b711-d41fedab13a1 |  | note | If there is damage, mark as FAIL. Once the damage is repaired, take another photo (PHOTO REQUIRED) and then change the status to PASS
checkpoint-status |  |  | checkpoint | Area has been cleaned from grout and rubbish (PHOTO REQUIRED of the area before leaving)
checkpoint-group |  |  | section | Element Caulking
checkpoint-status |  |  | checkpoint | Element caulked as per project requirements
boolean | 956d9c13-50b2-59ce-a105-48c87cf328c6 |  | tickbox | Caulking product used as per element/project requirements (PHOTO REQUIRED of caulking product used)
boolean | 3e55a4cd-dd1c-5606-95fa-5982bd73b11c |  | tickbox | Open or closed cell backing rod used? (SPECIFY in comments section below)
boolean | 1ff932ba-aa03-5c58-90cf-2c48d6acaaca |  | tickbox | Caulking installed and checked (PHOTO REQUIRED of caulked joint/s)
checkpoint-group |  |  | section | HOLD POINT - Confirmation that Props can be removed
checkpoint-status |  |  | checkpoint | Has the Builder given us written confirmation that props can be removed (UPLOAD copy of correspondence)
checkpoint-status |  |  | checkpoint | PHOTO REQUIRED of element after the props have been removed
checkpoint-group |  |  | section | Basic Patch
checkpoint-status |  |  | checkpoint | Have the lifting anchors been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the prop points been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the grout tubes been patching as per project requirements
checkpoint-group |  |  | section | Final Finish
checkpoint-status |  |  | checkpoint | Has all outstanding patching been completed (PHOTO REQUIRED of all visible faces of element)