## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Installation Checklist |  |  |  |  | Yes | Installation Checklist | 11edcbe9-fefd-48cb-84d6-d02ea8157d3c
checkpoint-group |  |  | section | Element Install & Grouting
checkpoint-status |  |  | checkpoint | Bedding grout placed and finished as per project requirements
boolean | f35a015c-a7c5-5e72-b3c0-f1d2f643089a |  | tickbox | Bedding grout (trowelable) used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | be66fcda-3418-5f56-a849-c68c2faefaf0 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 13820dd0-c5ff-55f9-8df5-12a9765cb004 |  | tickbox | Grout bed sufficient to ensure full coverage (PHOTO REQUIRED of grout bed prior to landing element)
checkpoint-status |  |  | checkpoint | Element installed to (PHOTO REQUIRED to show survey pins and spirit level bubble):
boolean | 449b627d-d390-5c67-9f54-c718876a88c7 |  | tickbox | Survey Pins
boolean | 5e61a5c5-4fc8-5a74-8466-e29d35a6cc0f |  | tickbox | Within 5mm of vertical plumb
boolean | 5eebb43a-e842-5ef7-87f0-9917d0348752 |  | tickbox | Face alignment within 5mm
checkpoint-status |  |  | checkpoint | Element propped as per Euro Precast PEDS (PHOTO REQUIRED of element propped)
boolean | f7172c76-62ad-5c80-beaa-6bb5c20aea5d |  | tickbox | Prop bolts installed with tool to ensure locking mechanism can't be removed by hand
checkpoint-status |  |  | checkpoint | Dowel tube (flowable) grout placed and finished as per project requirements
boolean | 0e5243ed-4fa4-5b70-b76d-d4112eb6a4b9 |  | tickbox | Dowel tube grout used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | 2675b456-6c19-5ef3-96b9-1c0de43d4735 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 5c5aeb76-5858-5a1a-b1e9-1dc78d0a5711 |  | tickbox | Dowel tubes filled to top of tubes
checkpoint-status |  |  | checkpoint | Is there any transport or erection damage that needs to be fixed (PHOTO REQUIRED of damaged area)
label | 400c6786-eafa-5d39-b711-d41fedab13a1 |  | note | If there is damage, mark as FAIL. Once the damage is repaired, take another photo (PHOTO REQUIRED) and then change the status to PASS
checkpoint-status |  |  | checkpoint | Area has been cleaned from grout and rubbish (PHOTO REQUIRED of the area before leaving)
checkpoint-group |  |  | section | Element Caulking
checkpoint-status |  |  | checkpoint | Element caulked as per project requirements
boolean | 956d9c13-50b2-59ce-a105-48c87cf328c6 |  | tickbox | Caulking product used as per element/project requirements (PHOTO REQUIRED of caulking product used)
boolean | 3e55a4cd-dd1c-5606-95fa-5982bd73b11c |  | tickbox | Open or closed cell backing rod used? (SPECIFY in comments section below)
boolean | 1ff932ba-aa03-5c58-90cf-2c48d6acaaca |  | tickbox | Caulking installed and checked (PHOTO REQUIRED of caulked joint/s)
checkpoint-group |  |  | section | HOLD POINT - Confirmation that Props can be removed
checkpoint-status |  |  | checkpoint | Has the Builder given us written confirmation that props can be removed (UPLOAD copy of correspondence)
checkpoint-status |  |  | checkpoint | PHOTO REQUIRED of element after the props have been removed
checkpoint-group |  |  | section | Basic Patch
checkpoint-status |  |  | checkpoint | Have the lifting anchors been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the prop points been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the grout tubes been patching as per project requirements
checkpoint-group |  |  | section | Final Finish
checkpoint-status |  |  | checkpoint | Has all outstanding patching been completed (PHOTO REQUIRED of all visible faces of element)
checklist-flat |  |  | checklist | Level Sign Off |  |  |  |  | Yes | Level Sign Off | 32d1f802-8a60-45b4-9f3c-ce495643f73d
checkpoint-status |  |  | checkpoint | Details complete
text | 9f496b3a-806d-5796-8de5-6e001766f898 |  | textbox | Date:
text | 69ae4da1-40db-5ef9-8bae-631e969a4060 |  | textbox | Level:
checkpoint-status |  |  | checkpoint | Builder Sign Off
label | 173bcbb1-0e45-5ea0-be40-b744b1eec13e |  | note | In signing the below, you agree and acknowledge that on this level:
label | 742ea013-7409-5c3f-ac0b-4dd8cb250955 |  | note | All props have been removed
label | c6d8d620-4b21-59db-8333-4617078c3f9e |  | note | All grouting has been completed
label | 276b155c-9ed1-5740-923e-c25f9170f225 |  | note | All patching has been completed
label | bc5121e8-71de-5dd8-894d-c29eb0fec096 |  | note | All sealing has been completed
label | 85744470-c8e7-5200-8e31-85d7b27d6a8d |  | note | All issued defects have been completed
holdpoint |  |  | signoff | BUILDER SIGNATURE (MUST INCLUDE NAME)
checklist-sectioned |  |  | checklist | Manufacturing Checklist |  |  |  |  | Yes | Manufacturing Checklist | 9c55bb2f-c185-48a0-b038-6cb48107786d
checkpoint-group |  |  | section | Manufacturing Documents
checkpoint-status |  |  | checkpoint | IFC Element Drawing
checkpoint-status |  |  | checkpoint | Euro Precast Primary Lifting and Propping Certification
checkpoint-status |  |  | checkpoint | Secondary Lifting Certification
checkpoint-group |  |  | section | Pre-Pour Checks
checkpoint-status |  |  | checkpoint | Mould check
boolean | 26b4210e-613b-504a-9c7c-609bcae9652e |  | tickbox | Mould clean with release oil applied correctly
boolean | 59ee17ac-6962-597e-8cfa-3bc972f28d12 |  | tickbox | Primary & diagonal dimensions checked
boolean | 5bf8d6f1-5702-5b9b-a567-2f04ef9982c0 |  | tickbox | Openings Checked and Correct
boolean | 5d420510-381d-55aa-b365-a0fa49d10dab |  | tickbox | Rebates, Architectural Grooves Installed Correctly
boolean | 272367ec-3fd8-5870-a89d-127c25a1952b |  | tickbox | Formwork chamfers installed correctly where required
checkpoint-status |  |  | checkpoint | Reinforcing check
boolean | c14242fa-ee42-5381-8d82-02d690a824a0 |  | tickbox | Correct Size and Type
boolean | 0cef57bd-4e54-5e31-9cd1-85cf812be990 |  | tickbox | Laps and Splices correct
boolean | e2462d31-766f-5139-90bf-7ab8c8ae331f |  | tickbox | Cover Checked
boolean | bc700fc1-a056-58bf-bdc3-17ccf8525580 |  | tickbox | Spacing Checked
checkpoint-status |  |  | checkpoint | Cast in items check
boolean | 20d571c6-086e-5097-9419-2118d55b5228 |  | tickbox | Ferrules/Inserts installed, checked and correct
boolean | 3b024470-8313-58b8-bbc7-9a464bf53666 |  | tickbox | Starter Bars inserted, checked and correct
boolean | 23c269de-f5f0-55ee-b9b2-fcac269d4369 |  | tickbox | Lifting anchors installed, checked and correct
checkpoint-status |  |  | checkpoint | Check Minimum Cover
checkpoint-status |  |  | checkpoint | ID Tag installed in non-visible face
checkpoint-status |  |  | checkpoint | Pre-Pour checks completed and approval given to pour Element
label | 65c9f104-92f1-5eeb-b12c-b7c25b721452 |  | note | Upload sufficient number of photos of element
checkpoint-status |  |  | checkpoint | Upload photo of signed pre-pour check of shop drawing
checkpoint-group |  |  | section | Concrete Pour Checks
checkpoint-status |  |  | checkpoint | Concrete Strength correct as per design
boolean | 885e4741-b260-59df-8e95-9c69ca818f19 |  | tickbox | All Concrete Dockets Attached
text | 0045cb55-3dd9-538c-908a-dded09b83ebd |  | textbox | Date element was cast
checkpoint-group |  |  | section | Post-Pour / Pre Delivery Checks
checkpoint-status |  |  | checkpoint | Visual Check
boolean | 3b124a8d-06aa-57d8-a86d-97545c08e5b3 |  | tickbox | Does the finish meet class 2 as per AS3610
boolean | 0c5f4735-12cb-5179-9fd0-9763d87c6d4d |  | tickbox | Chamfers clean, neat and on all required edges
boolean | 0ebe7d16-39ad-51e8-9182-257c7681e21c |  | tickbox | Lifting anchors checked and approved
boolean | ae70d21d-afe4-5a75-b6b9-315542203795 |  | tickbox | Critical fitments / fixtures checked and approved
boolean | de5f4ad9-0b31-5f37-917a-d5a13f041bde |  | tickbox | Openings (formwork removed)
boolean | 123ad4b6-a1ce-5cc2-97fc-65a389251984 |  | tickbox | Nailplates / Recesses etc removed
checkpoint-status |  |  | checkpoint | Any Strongbacks Installed where required
checkpoint-status |  |  | checkpoint | Element free from defects that will impact structural integrity or durability?
label | 78f6c911-5994-5475-9779-7b11e7739ca4 |  | note | If 'FLAG', raise NCR and notify EP Project Manager to discuss with builder
boolean | 84ad458a-e0b4-5959-9c71-6f602ab190fa |  | tickbox | If NCR raised, take photo of completed approved works
checkpoint-status |  |  | checkpoint | All Post Pour Works complete - Element Checked, Approved and Ready for delivery
checkpoint-group |  |  | section | Concrete Test Results
checkpoint-status |  |  | checkpoint | Concrete Test Result attached
label | dde75374-9ca7-5deb-b202-95291bccd856 |  | note | Upload actual test result OR a test result of the same mix design from the same day
checklist-sectioned |  |  | checklist | Variation works completed |  |  |  |  | Yes | Add New Variation | 9eccf974-b39a-424c-8352-96a84a2a9bc5
checkpoint-group |  |  | section | Works completed
checkpoint-status |  |  | checkpoint | Details entered below
text | c1876c5e-9363-593c-8eae-090e7e67aabe |  | textbox | Date:
text | e48c2ef2-7c9a-5f60-8588-3bb024bff947 |  | textbox | Name of people who completed the works:
select | b90eac2f-d675-5854-8254-d73c31208848 |  | dropdown | Time started at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 9c1bc354-2aa7-5474-b55a-79c1d825e492 |  | dropdown | Time finished at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
text | 4a6b40d7-361f-5737-b1e5-ea343ebf6761 |  | textbox | Consumables used:
text | 89b4f543-41c5-5f1f-8493-03d9b87fa0e2 |  | textbox | Summary of works completed
checkpoint-group |  |  | section | Builder sign-off
checkpoint-status |  |  | checkpoint | Builder sign-off
label | 26b61b0b-0ae9-5937-9b1f-38d7a598bfd9 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)
checklist-flat |  |  | checklist | Grout Testing Checklist |  |  |  |  | Yes | Grout Testing Checklist | c3c6dcbc-4cff-4c9e-b256-97243bb23c9f
checkpoint-status |  |  | checkpoint | To organise grout testing, call Construction Sciences. Primary contact is Michael Hardcastle on 0429 791 069. Secondary contact is Joshua Borg on 0429 790 444
text | 36fc5395-ca50-5180-8bb0-0061beb90b5f |  | textbox | Date:
text | 9d8dab2f-20e1-59db-abd2-052e6ea0aa3d |  | textbox | Project Name:
text | 65a8beea-dbca-5fec-ba55-b6b6c1a3259b |  | textbox | Time of test:
text | 02998de0-53f0-5987-8624-fbe0f819aa82 |  | textbox | Grouts tested:
checkpoint-status |  |  | checkpoint | Upload grout test results
checklist-sectioned |  |  | checklist | Delivery / Installation Day Checklist |  |  |  |  | Yes | Delivery / Installation Day Checklist | cb3633dd-0e56-47ae-9060-191bc31b36e4
checkpoint-group |  |  | section | HOLD POINT - Confirmation of slab strength
checkpoint-status |  |  | checkpoint | Has the slab reached the minimum strength required (UPLOAD copy of concrete slab test result)
label | c9bbf854-3550-5dcf-b99e-2aa2642a158e |  | note | 12MPa for cast-in anchors and 20MPa for post installed anchors
checkpoint-group |  |  | section | Prestart / Start-up
checkpoint-status |  |  | checkpoint | Date of Installation
checkpoint-status |  |  | checkpoint | Installation team completing the install today
label | 2e9de6a9-8443-50b6-8719-3f96e702f0c9 |  | note | List names in comments
checkpoint-status |  |  | checkpoint | Exclusion Zone is set up (PHOTO REQUIRED of the exclusion zone)
checkpoint-status |  |  | checkpoint | Plant & Equipment prestart/logbooks filled out (PHOTO REQUIRED of logbooks)
checkpoint-status |  |  | checkpoint | Toolbox Talk / Pre-Start has been completed (PHOTO REQUIRED of talk)
checkpoint-group |  |  | section | Summary of the day
checkpoint-status |  |  | checkpoint | Hours worked
select | 78d03587-565c-5bab-926a-b4740dbf00a7 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 3c43c761-e0cc-5dda-a17e-e255c537b145 |  | dropdown | Time finished on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-status |  |  | checkpoint | Elements Installed today
label | 4d0b8069-eb4f-5b81-95fc-08e191d04ec9 |  | note | COMMENT below if number of elements installed doesn't match the Load Lists in the Safe Load Declarations
select | 2ada973d-8803-5f88-8f23-e67ec388aa3e |  | dropdown | How many elements were installed today? | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34, 35, 36, 37, 38, 39, 40
checkpoint-status |  |  | checkpoint | Were there any delays?
label | 87faf9ba-5e3f-5b3d-aaee-0a556769d8b7 |  | note | COMMENT below in enough detail to explain the delay and what caused it. Add PHOTO if it helps record the delay.
select | d3140643-7f44-5203-8eb3-18b5642f0f44 |  | dropdown | How long was the delay? | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr
select | 58046ee7-6a2f-55a4-9755-818c7abe3b68 |  | dropdown | How many installers were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
select | ede201f0-4afc-511e-b34f-570146242cef |  | dropdown | How many trucks were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
checkpoint-status |  |  | checkpoint | Builder sign-off
label | f4a9c5b1-6546-51e0-a12c-90fcd787c5e0 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)
checklist-flat |  |  | checklist | Safe Load Declaration Checklist |  |  |  |  | Yes | Safe Load Declaration Checklist | cce5d90e-3d5d-456a-9298-2aa13398d407
checkpoint-status |  |  | checkpoint | Details complete
text | b04b042c-446a-50a5-9d2d-68f7e8c24f95 |  | textbox | Date:
text | d93fd580-fd5f-5b87-9733-7dd1ed3ef4f8 |  | textbox | Time truck arrived at Factory:
text | ccd4ae79-5214-5ced-ab90-8a9beb75af17 |  | textbox | Time truck departed Factory:
text | 66617271-b3db-5e73-a367-a6adeb189253 |  | textbox | Transport Company:
text | f4a92464-4ddf-5dc5-96a1-80e76d86a16a |  | textbox | Truck Registration #
text | 1d54ad52-a509-5d02-83ea-a413c8fb8a38 |  | textbox | Trailer Registration
select | a5cab4a8-aab0-5735-b9a0-9f43437544da |  | dropdown | Trailer Type: | Drop Deck, Drop Deck No Frame, Flat Top, Layover, Super Layover, Commission
checkpoint-status |  |  | checkpoint | Upload photo of Load List used for load
checkpoint-status |  |  | checkpoint | Upload photos of both sides of loaded truck (after being chained down)
checkpoint-status |  |  | checkpoint | Load Declaration
label | c375310f-5f4f-58ab-9efe-d7d0885f171a |  | note | In signing below, you agree and acknowledge that:
label | e2031acb-ecdc-580d-b6b2-21664fbceced |  | note | You are not permitted to leave the Euro Precast factory unless a Safe Load Declaration has been completed
label | 740c8ca2-2517-536d-92a4-43efe888471b |  | note | You have been provided with a copy of the load list that indicates individual element weights and total approximate load weight (excluding trailer/frame weight)
label | dfb2c7e8-e330-56ea-b1cb-444bf28770cf |  | note | You have chained down all units/elements in a safe and secure manner and in accordance with the latest published government/industry best practice guidance material
label | b248911b-3093-5150-ab16-c9289277609a |  | note | You will abide by all safety rules, PPE requirements and client instructions on the project site at all times.
label | 0831ae1a-3388-5167-bdf9-facf5bad8aea |  | note | You as an individual, the truck, the trailer and load comply with the latest requirements of the Heavy Vehicle National Law and Regulations (HVNL)
holdpoint |  |  | signoff | Driver Signature (must include Company)
checklist-flat |  |  | checklist | Daily Diary / Timesheet |  |  |  |  | Yes | Daily Diary / Timesheet | d080a989-0099-44aa-b7a2-6b92f7dcc0b6
checkpoint-status |  |  | checkpoint | Site 1: Details entered below
text | 1ad7fd5b-f483-52f2-bf41-366edb8cf1a5 |  | textbox | Site 1:
select | 3283074c-f435-59d8-af89-5ef3b5b58b44 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 0d39d4c6-8c53-50eb-bc5a-b3c54595b318 |  | dropdown | Time left site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-no-status |  |  | checkpoint | Site 1: Activities completed
boolean | da6b25c8-048d-578b-93ca-a1fd932f22e5 |  | tickbox | Set out
select | c5b9f449-e4fe-5183-b76e-976bd613e8aa |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 7f55ad03-b585-5ccc-a27b-d358eb4e98f7 |  | tickbox | Panel Install
select | b4e2ba41-29bd-5039-84e7-509948aefd9c |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 5677d03b-5c96-5262-b247-5a6330151858 |  | tickbox | Patching
select | cb1fe062-62a3-5931-af27-0ea4bac2ba24 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 8a10197a-d7ef-5278-aba0-f94bfdc95a82 |  | tickbox | Joint Sealing
select | 8c527ac7-82e7-559d-8432-4564d14d9692 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 0f58b199-0501-512b-98d4-f6f739a77383 |  | tickbox | Prop Removal
select | 2c1175dd-eb70-583c-971f-f322c57fa884 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
text | 0e7ce790-f6c9-5581-831f-6ea5756c546a |  | textbox | Other (add in comments)
select | b1880b57-6895-519c-94a7-4b149906a81f |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
checkpoint-status |  |  | checkpoint | Site 2: Details entered below
text | a1e2321e-adc2-51f2-b8ec-2792df8ee1aa |  | textbox | Site 2:
select | 938b1e27-d9f2-55e3-a2f1-ba0e1238eb8a |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | c42d48a7-b3f1-5e47-9334-261f320b7a44 |  | dropdown | Time left site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-no-status |  |  | checkpoint | Site 2: Activities completed
boolean | c36774f4-22ae-5b80-80c7-07223d922931 |  | tickbox | Set out
select | 73639f2d-decb-5110-afb8-e79fce83d7f5 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | be5cbbdf-25a4-5aee-af19-09412c97bfb5 |  | tickbox | Panel Install
select | 78b220c7-4436-588b-97e4-82baab61a487 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 391beb77-0df1-514f-b6b7-ed1c3ca8ce35 |  | tickbox | Patching
select | c255d6a8-1cd1-5fa4-8cc3-e531a93c8e9c |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 49f9833e-c8b2-5e2f-8001-54ca946824b3 |  | tickbox | Joint Sealing
select | 6d43a9ee-5314-54df-8c1b-76fbe82cc1e5 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | a38a36ff-d2a2-55a1-b554-99503a3f9b0a |  | tickbox | Prop Removal
select | cce9655d-83c3-52e6-a062-3cf0c35abdde |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
text | 6401eb5c-6a7b-59ae-8122-78c38004d45e |  | textbox | Other (add in comments)
select | 892597f6-a952-5d5c-890a-1147d08c18b3 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
checkpoint-status |  |  | checkpoint | Site 3: Details entered below
text | 39721ac9-8f2a-5d70-81f5-5ddc127eb561 |  | textbox | Site 3:
select | a415c417-ad5f-5e50-8c62-faf36d69fff1 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | d46e5559-ab97-548f-b6c9-c8110fa9b83a |  | dropdown | Time left site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-no-status |  |  | checkpoint | Site 3: Activities completed
boolean | 15200abd-8a61-5927-b28e-7b122b678b4c |  | tickbox | Set out
select | 83b0b635-ce97-594e-829b-97fbf4687b79 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | e69e478e-4b8e-5143-9f50-ea69b83826ff |  | tickbox | Panel Install
select | f8f614ac-2ad2-57e4-832a-301a5dc376e2 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | ce89ae2a-7360-5e2e-b82d-890018c090d9 |  | tickbox | Patching
select | 8dd338a8-fe44-5ee2-bbad-a97986bd5f1e |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 25ed1258-8f20-5aa9-90c8-e984e8414f17 |  | tickbox | Joint Sealing
select | 6530773d-58b5-5f2a-aa6d-97334446fcd2 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 99b4faaa-1814-513e-ac42-1e806507a4a3 |  | tickbox | Prop Removal
select | ffab0817-43d4-56b0-b20a-5ce99ae7a3e1 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
text | 280b4252-0c99-5d52-bdb2-0db5ee337d71 |  | textbox | Other (add in comments)
select | 0d59aa19-cbfe-55df-b96a-3863d77b5eb0 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
checkpoint-status |  |  | checkpoint | Site 4: Details entered below
text | 4b5bc98e-8a24-5e51-a859-c1b50be6f823 |  | textbox | Site 4:
select | 0a4d3604-321e-583b-9ee9-b208ec86be44 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | b9c2db32-77b0-590a-b056-c37f46df16b2 |  | dropdown | Time left site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-no-status |  |  | checkpoint | Site 4: Activities completed
boolean | 195709dd-15dd-51f4-bbde-21976512f56e |  | tickbox | Set out
select | 64ca3cef-f47b-5f32-ad07-9c5dde7e33da |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | ff079e22-0f97-5dd6-8ec6-edd91d177f97 |  | tickbox | Panel Install
select | ed6bd6d9-cdbb-5cc4-ab5c-86756611875a |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | c75650ee-1c5a-5b79-bd84-301f925c2f13 |  | tickbox | Patching
select | b6a1a6ea-80e2-5da4-b421-6f4e42429bec |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 595d4282-92e7-516e-9184-2aef97a3365b |  | tickbox | Joint Sealing
select | 6d2e6657-2b9f-5bd8-b933-efb17205c2d9 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 867613f9-241d-518b-a29c-9d32a0adbf30 |  | tickbox | Prop Removal
select | 1c7a5b73-33d9-5109-b6f6-2b09869c2a42 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
text | 9a4416e4-7d65-5673-980f-ef9e68fa0ccb |  | textbox | Other (add in comments)
select | 29bfe30a-0b91-5384-88f4-72175c2fcac4 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
checkpoint-status |  |  | checkpoint | Euro Precast Employee signoff
checkpoint-status |  |  | checkpoint | Euro Precast Manager signoff
holdpoint |  |  | signoff | Add signature
checkpoint-status |  |  | checkpoint | When complete please send timesheet as report to jane@europrecast.com
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details | d88ac137-82fe-4fd9-8be1-c94742994c89
checkpoint-status |  |  | checkpoint | Project details entered below
text | 91782e05-b650-55f8-990f-f0d1ae824e83 |  | textbox | Job Number
text | fb77cc12-7e93-59fe-9b2c-37569aec696c |  | textbox | Project Name
text | ab182ac0-3c23-51c9-9c8f-03c8285aa433 |  | textbox | Site Address
text | de7bb080-aa1e-5b3c-82fa-9788d6ba20df |  | textbox | Builder
text | 10b255a8-2cb9-5c10-8c41-58a2693e7fe7 |  | textbox | Euro Precast Project Manager
text | 55b41161-c356-5458-8aa8-3b6cad2c174c |  | textbox | Euro Precast Lead Draftsperson
text | 58b30239-bdee-51bf-b130-48f5bf41af9f |  | textbox | Euro Precast Installer
checkpoint-status |  |  | checkpoint | Grouts submitted for approval (UPLOAD TDS and SDS for each grout submitted)
checkpoint-status |  |  | checkpoint | Have submitted grouts been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Caulking products submitted for approval (UPLOAD TDS and SDS for each caulking product submitted)
checkpoint-status |  |  | checkpoint | Have submitted caulking products been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Patching products submitted for approval (UPLOAD TDS and SDS for each patching product submitted)
checkpoint-status |  |  | checkpoint | Have patching products been approved? (UPLOAD copy of approval)