## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Level Sign Off |  |  |  |  | Yes | Level Sign Off | 016dd6b3-0361-41e7-8c02-d95d28abb820
checkpoint-status |  |  | checkpoint | Details complete
text | 580d13b0-4755-5306-b9f2-611db0b24c40 |  | textbox | Date:
text | 3e58d01b-121e-5618-ac76-802e6a37d667 |  | textbox | Level:
checkpoint-status |  |  | checkpoint | Builder Sign Off
label | d17f422e-6838-58ed-9762-a16b9c187371 |  | note | In signing the below, you agree and acknowledge that on this level:
label | 089573c7-ec61-5015-8aae-eeab0326c709 |  | note | All props have been removed
label | cacc3bff-8ed5-5132-b183-4d61029e9e88 |  | note | All grouting has been completed
label | 92d2c407-7389-5438-bafc-c8bd46aa2ea4 |  | note | All patching has been completed
label | 9042f24c-e4b2-5a88-a931-84aafbebb3da |  | note | All sealing has been completed
label | f2119281-3a83-5793-8aeb-bd38999ab9a6 |  | note | All issued defects have been completed
holdpoint |  |  | signoff | BUILDER SIGNATURE (MUST INCLUDE NAME)
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details | 362f7f00-e67f-474b-95fb-b217e9648305
checkpoint-status |  |  | checkpoint | Project details entered below
text | 2ab247ea-36ee-5b18-9bd8-3ea11841528c |  | textbox | Job Number
text | 2254a3dd-44f8-5e42-8251-7f1a832705f1 |  | textbox | Project Name
text | 861d4438-d495-5218-b738-deef672abf22 |  | textbox | Site Address
text | cdd026a9-4c6b-5ec6-9eb0-21d6474d3d9c |  | textbox | Builder
text | f244e110-8eff-58c6-947d-9d730cbf84cf |  | textbox | Euro Precast Project Manager
text | 8ad99696-f7b8-5317-b32d-df0e6965d184 |  | textbox | Euro Precast Lead Draftsperson
text | 07cfa4bb-f64b-563f-b4f5-b01c8cc2ba61 |  | textbox | Euro Precast Installer
checkpoint-status |  |  | checkpoint | Grouts submitted for approval (UPLOAD TDS and SDS for each grout submitted)
checkpoint-status |  |  | checkpoint | Have submitted grouts been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Caulking products submitted for approval (UPLOAD TDS and SDS for each caulking product submitted)
checkpoint-status |  |  | checkpoint | Have submitted caulking products been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Patching products submitted for approval (UPLOAD TDS and SDS for each patching product submitted)
checkpoint-status |  |  | checkpoint | Have patching products been approved? (UPLOAD copy of approval)
checklist-sectioned |  |  | checklist | Installation Checklist |  |  |  |  | Yes | Installation Checklist | 518b8abe-9f32-4fc3-bb2f-94d5c4ef9b3e
checkpoint-group |  |  | section | Element Install & Grouting
checkpoint-status |  |  | checkpoint | Bedding grout placed and finished as per project requirements
boolean | f35a015c-a7c5-5e72-b3c0-f1d2f643089a |  | tickbox | Bedding grout (trowelable) used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | be66fcda-3418-5f56-a849-c68c2faefaf0 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 13820dd0-c5ff-55f9-8df5-12a9765cb004 |  | tickbox | Grout bed sufficient to ensure full coverage (PHOTO REQUIRED of grout bed prior to landing element)
checkpoint-status |  |  | checkpoint | Element installed to (PHOTO REQUIRED to show survey pins and spirit level bubble):
boolean | 449b627d-d390-5c67-9f54-c718876a88c7 |  | tickbox | Survey Pins
boolean | 5e61a5c5-4fc8-5a74-8466-e29d35a6cc0f |  | tickbox | Within 5mm of vertical plumb
boolean | 5eebb43a-e842-5ef7-87f0-9917d0348752 |  | tickbox | Face alignment within 5mm
checkpoint-status |  |  | checkpoint | Element propped as per Euro Precast PEDS (PHOTO REQUIRED of element propped)
boolean | f7172c76-62ad-5c80-beaa-6bb5c20aea5d |  | tickbox | Prop bolts installed with tool to ensure locking mechanism can't be removed by hand
checkpoint-status |  |  | checkpoint | Dowel tube (flowable) grout placed and finished as per project requirements
boolean | 0e5243ed-4fa4-5b70-b76d-d4112eb6a4b9 |  | tickbox | Dowel tube grout used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | 2675b456-6c19-5ef3-96b9-1c0de43d4735 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 5c5aeb76-5858-5a1a-b1e9-1dc78d0a5711 |  | tickbox | Dowel tubes filled to top of tubes
checkpoint-status |  |  | checkpoint | Is there any transport or erection damage that needs to be fixed (PHOTO REQUIRED of damaged area)
label | 400c6786-eafa-5d39-b711-d41fedab13a1 |  | note | If there is damage, mark as FAIL. Once the damage is repaired, take another photo (PHOTO REQUIRED) and then change the status to PASS
checkpoint-status |  |  | checkpoint | Area has been cleaned from grout and rubbish (PHOTO REQUIRED of the area before leaving)
checkpoint-group |  |  | section | Element Caulking
checkpoint-status |  |  | checkpoint | Element caulked as per project requirements
boolean | 956d9c13-50b2-59ce-a105-48c87cf328c6 |  | tickbox | Caulking product used as per element/project requirements (PHOTO REQUIRED of caulking product used)
boolean | 3e55a4cd-dd1c-5606-95fa-5982bd73b11c |  | tickbox | Open or closed cell backing rod used? (SPECIFY in comments section below)
boolean | 1ff932ba-aa03-5c58-90cf-2c48d6acaaca |  | tickbox | Caulking installed and checked (PHOTO REQUIRED of caulked joint/s)
checkpoint-group |  |  | section | HOLD POINT - Confirmation that Props can be removed
checkpoint-status |  |  | checkpoint | Has the Builder given us written confirmation that props can be removed (UPLOAD copy of correspondence)
checkpoint-status |  |  | checkpoint | PHOTO REQUIRED of element after the props have been removed
checkpoint-group |  |  | section | Basic Patch
checkpoint-status |  |  | checkpoint | Have the lifting anchors been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the prop points been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the grout tubes been patching as per project requirements
checkpoint-group |  |  | section | Final Finish
checkpoint-status |  |  | checkpoint | Has all outstanding patching been completed (PHOTO REQUIRED of all visible faces of element)
checklist-flat |  |  | checklist | Safe Load Declaration Checklist |  |  |  |  | Yes | Safe Load Declaration Checklist | 58eae75f-68ce-49a5-a7e1-0db2350346e1
checkpoint-status |  |  | checkpoint | Details complete
text | 4a0ea7a7-f400-580b-8a12-fca0dc822afb |  | textbox | Date:
text | 421a329d-8c8b-5d87-9f22-6f7e6060f629 |  | textbox | Time truck arrived at Factory:
text | 6ff7fb72-c534-52c4-95ed-0109450bb5f2 |  | textbox | Time truck departed Factory:
text | 168da996-915d-5d93-bb3e-dcda0078f39f |  | textbox | Project Name:
text | bb8244b9-e638-5373-a6ab-b751fd0aece1 |  | textbox | Delivery Address:
text | a4b8b03a-9330-5411-a087-9854d9198013 |  | textbox | Transport Company:
text | c17f3192-3791-512d-ba7d-7b7902580d55 |  | textbox | Truck Registration #
text | b78e0172-dbd1-52b4-a1f4-dd6890765407 |  | textbox | Trailer Registration
select | 7e8e7a9d-5d13-5d2d-a145-cf9ed1fb173a |  | dropdown | Trailer Type: | Drop Deck, Drop Deck No Frame, Flat Top, Layover, Super Layover, Commission
checkpoint-status |  |  | checkpoint | Upload photo of Load List used for load
checkpoint-status |  |  | checkpoint | Upload photos of both sides of loaded truck (after being chained down)
checkpoint-status |  |  | checkpoint | Load Declaration
label | 914c9622-d832-5156-a7a6-32d2420af4b1 |  | note | In signing below, you agree and acknowledge that:
label | 589ec2e7-c9df-51b6-b9fc-6a47dfc498e3 |  | note | You are not permitted to leave the Euro Precast factory unless a Safe Load Declaration has been completed
label | f7073ae6-afcb-502d-b2fe-6bf430625a92 |  | note | You have been provided with a copy of the load list that indicates individual element weights and total approximate load weight (excluding trailer/frame weight)
label | 722c92cb-1b4d-5ef8-b42b-92beabdc1249 |  | note | You have chained down all units/elements in a safe and secure manner and in accordance with the latest published government/industry best practice guidance material
label | 3907f8f9-f947-5b42-baa6-16e22d4e8b46 |  | note | You will abide by all safety rules, PPE requirements and client instructions on the project site at all times.
label | ec7fda71-e9bb-5e09-8fd5-9a668f66f73b |  | note | You as an individual, the truck, the trailer and load comply with the latest requirements of the Heavy Vehicle National Law and Regulations (HVNL)
holdpoint |  |  | signoff | Driver Signature (must include Company)
checklist-sectioned |  |  | checklist | Variation works completed |  |  |  |  | Yes | Add New Variation | bde3907d-a6ac-4b51-80af-b6c453489683
checkpoint-group |  |  | section | Works completed
checkpoint-status |  |  | checkpoint | Details entered below
text | c1876c5e-9363-593c-8eae-090e7e67aabe |  | textbox | Date:
text | e48c2ef2-7c9a-5f60-8588-3bb024bff947 |  | textbox | Name of people who completed the works:
select | b90eac2f-d675-5854-8254-d73c31208848 |  | dropdown | Time started at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 9c1bc354-2aa7-5474-b55a-79c1d825e492 |  | dropdown | Time finished at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
text | 4a6b40d7-361f-5737-b1e5-ea343ebf6761 |  | textbox | Consumables used:
text | 89b4f543-41c5-5f1f-8493-03d9b87fa0e2 |  | textbox | Summary of works completed
checkpoint-group |  |  | section | Builder sign-off
checkpoint-status |  |  | checkpoint | Builder sign-off
label | 26b61b0b-0ae9-5937-9b1f-38d7a598bfd9 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)
checklist-sectioned |  |  | checklist | Manufacturing Checklist |  |  |  |  | Yes | Manufacturing Checklist | c516b060-d3a6-4326-9f40-01bdf2ff8366
checkpoint-group |  |  | section | Manufacturing Documents
checkpoint-status |  |  | checkpoint | IFC Element Drawing
checkpoint-status |  |  | checkpoint | Euro Precast Primary Lifting and Propping Certification
checkpoint-status |  |  | checkpoint | Secondary Lifting Certification
checkpoint-group |  |  | section | Pre-Pour Checks
checkpoint-status |  |  | checkpoint | Mould check
boolean | b64a398c-28fd-5555-8661-9af38c7bc4a9 |  | tickbox | Mould clean with release oil applied correctly
boolean | 6c46bdb0-e840-51d5-a688-66a134d93d34 |  | tickbox | Primary & diagonal dimensions checked
boolean | a550011b-397f-5330-90c4-03dbd01a21d8 |  | tickbox | Openings Checked and Correct
boolean | 197f4bb2-7ee9-5961-9865-915fe30c81e7 |  | tickbox | Rebates, Architectural Grooves Installed Correctly
boolean | 1b217da5-5ba3-55e5-8f0c-bbc4301969fc |  | tickbox | Formwork chamfers installed correctly where required
checkpoint-status |  |  | checkpoint | Reinforcing check
boolean | 3edf23b5-a659-5344-b638-7f7e7e147cce |  | tickbox | Correct Size and Type
boolean | 714cc6f1-ee0a-53ae-adc3-455f6d3640c7 |  | tickbox | Laps and Splices correct
boolean | 420001f3-6ebf-5b78-9b9b-383beb6a5f0e |  | tickbox | Cover Checked
boolean | bd8c9c57-cd45-5789-a14b-7660cd8fdad9 |  | tickbox | Spacing Checked
checkpoint-status |  |  | checkpoint | Cast in items check
boolean | ed3a3ef9-4378-58ff-b05c-8267637f7702 |  | tickbox | Ferrules/Inserts installed, checked and correct
boolean | cdcbf639-145d-5e4b-ad5b-e129f7562be2 |  | tickbox | Starter Bars inserted, checked and correct
boolean | ee440e9e-072b-5ff5-9eb4-052a0277907b |  | tickbox | Lifting anchors installed, checked and correct
checkpoint-status |  |  | checkpoint | Check Minimum Cover
checkpoint-status |  |  | checkpoint | ID Tag installed in non-visible face
checkpoint-status |  |  | checkpoint | Pre-Pour checks completed and approval given to pour Element
label | c370ed5b-0299-5447-b684-0141197260ba |  | note | Upload sufficient number of photos of element
checkpoint-status |  |  | checkpoint | Upload photo of signed pre-pour check of shop drawing
checkpoint-group |  |  | section | Concrete Pour Checks
checkpoint-status |  |  | checkpoint | Concrete Strength correct as per design
boolean | f1481934-f8d4-595b-969d-7eb0e5e431f5 |  | tickbox | All Concrete Dockets Attached
text | 8413ffd3-cbe5-56a5-9ba6-739328537b90 |  | textbox | Date element was cast
checkpoint-group |  |  | section | Post-Pour / Pre Delivery Checks
checkpoint-status |  |  | checkpoint | Visual Check
boolean | 4702a492-5f41-546c-b8da-599715b35b53 |  | tickbox | Does the finish meet class 2 as per AS3610
boolean | 53de7a67-ecb3-5b98-83e2-6cfe7222d3ee |  | tickbox | Chamfers clean, neat and on all required edges
boolean | 94df9ae4-5ed5-5d0f-9b32-373a187ac293 |  | tickbox | Lifting anchors checked and approved
boolean | a6ab8c51-f524-5a47-bc0e-5a718014da59 |  | tickbox | Critical fitments / fixtures checked and approved
boolean | 2ee3e421-a966-52ed-b5f6-0c3a8e5e60d2 |  | tickbox | Openings (formwork removed)
boolean | 9ad6cf08-9bcd-5a8d-911b-cce109a8fde1 |  | tickbox | Nailplates / Recesses etc removed
checkpoint-status |  |  | checkpoint | Any Strongbacks Installed where required
checkpoint-status |  |  | checkpoint | Element free from defects that will impact structural integrity or durability?
label | 1217ea3c-241b-59fe-b7e5-1616ec1504cc |  | note | If 'FLAG', raise NCR and notify EP Project Manager to discuss with builder
boolean | 7503d4d6-da81-54ff-9dae-a435c5bc6ad7 |  | tickbox | If NCR raised, take photo of completed approved works
checkpoint-status |  |  | checkpoint | All Post Pour Works complete - Element Checked, Approved and Ready for delivery
checkpoint-group |  |  | section | Concrete Test Results
checkpoint-status |  |  | checkpoint | Concrete Test Result attached
label | 3fd358a3-f7b0-585a-bde0-7186e9df6856 |  | note | Upload actual test result OR a test result of the same mix design from the same day
checklist-flat |  |  | checklist | Grout Testing Checklist |  |  |  |  | Yes | Grout Testing Checklist | e8bcda84-2927-417c-9070-23b09ef7aae8
checkpoint-status |  |  | checkpoint | To organise grout testing, call Construction Sciences. Primary contact is Michael Hardcastle on 0429 791 069. Secondary contact is Joshua Borg on 0429 790 444
text | a6750dd7-c7b5-5aaf-a5cb-907a8a9dc76e |  | textbox | Date:
text | 262fe00d-cde5-5976-90ae-49b364c99b88 |  | textbox | Project Name:
text | 61f0281a-6cd3-5a51-9131-04107f81b809 |  | textbox | Time of test:
text | 8e6f4a80-471f-5dfb-b499-cdeed488f69e |  | textbox | Grouts tested:
checkpoint-status |  |  | checkpoint | Upload grout test results
checklist-sectioned |  |  | checklist | Delivery / Installation Day Checklist |  |  |  |  | Yes | Delivery / Installation Day Checklist | e9a73c1c-d3e7-4eec-bfb9-df4a8d62b80e
checkpoint-group |  |  | section | HOLD POINT - Confirmation of slab strength
checkpoint-status |  |  | checkpoint | Has the slab reached the minimum strength required (UPLOAD copy of concrete slab test result)
label | c9bbf854-3550-5dcf-b99e-2aa2642a158e |  | note | 12MPa for cast-in anchors and 20MPa for post installed anchors
checkpoint-group |  |  | section | Prestart / Start-up
checkpoint-status |  |  | checkpoint | Date of Installation
checkpoint-status |  |  | checkpoint | Installation team completing the install today
label | 2e9de6a9-8443-50b6-8719-3f96e702f0c9 |  | note | List names in comments
checkpoint-status |  |  | checkpoint | Exclusion Zone is set up (PHOTO REQUIRED of the exclusion zone)
checkpoint-status |  |  | checkpoint | Plant & Equipment prestart/logbooks filled out (PHOTO REQUIRED of logbooks)
checkpoint-status |  |  | checkpoint | Toolbox Talk / Pre-Start has been completed (PHOTO REQUIRED of talk)
checkpoint-group |  |  | section | Summary of the day
checkpoint-status |  |  | checkpoint | Hours worked
select | 78d03587-565c-5bab-926a-b4740dbf00a7 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 3c43c761-e0cc-5dda-a17e-e255c537b145 |  | dropdown | Time finished on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-status |  |  | checkpoint | Elements Installed today
label | 4d0b8069-eb4f-5b81-95fc-08e191d04ec9 |  | note | COMMENT below if number of elements installed doesn't match the Load Lists in the Safe Load Declarations
select | 2ada973d-8803-5f88-8f23-e67ec388aa3e |  | dropdown | How many elements were installed today? | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34, 35, 36, 37, 38, 39, 40
checkpoint-status |  |  | checkpoint | Were there any delays?
label | 87faf9ba-5e3f-5b3d-aaee-0a556769d8b7 |  | note | COMMENT below in enough detail to explain the delay and what caused it. Add PHOTO if it helps record the delay.
select | d3140643-7f44-5203-8eb3-18b5642f0f44 |  | dropdown | How long was the delay? | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr
select | 58046ee7-6a2f-55a4-9755-818c7abe3b68 |  | dropdown | How many installers were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
select | ede201f0-4afc-511e-b34f-570146242cef |  | dropdown | How many trucks were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
checkpoint-status |  |  | checkpoint | Builder sign-off
label | f4a9c5b1-6546-51e0-a12c-90fcd787c5e0 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)