## Table 1
Inspection and Test Plan – In situ Kerb and Channel
Project no. |  | CC0374 | Project name |  |  | Pakenham Road Upgrade |  |  | Date |  | 2023-10-18 |  |  | Approved by |  |  | Damian Hagebols
ITP no. | 1630-P200-SYM-QAC- ITP-0022 |  | Revision date |  |  | 18/10/2023 |  | Plant and equipment used
Lot no. |  |  | Location (chainages, detailed description or marked up plan)
Attach Dockets, Certificates and QA Documents to ITP
[11 empty] | Verification of acceptance by | [6 empty] | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
[11 empty] | Symal |  |  |  |  | Superintendent
Item no. | Activity |  |  |  | Ref docs | Acceptance criteria |  |  |  | Freq | Key |  | Resp |  | Initial/ date | Key | Sign/ date
1.0 Pre-start activities
1.1 | Supply of Premixed Concrete for Kerb Extrusion |  |  |  | DoT Clause 703.05 (b) 703.11 |  Concrete is minimum or equal 320kg cementitious material or geopolymer binder per m3. No slump or compressive strength requirements.  Where kerb and channel is placed and compacted with internal vibration between previously placed formwork: Concrete is N32 Portland or 32 MPa geopolymer concrete standard strength grade. |  |  |  | Prior to start of works | R |  | SE |  |  |  |  | Mix Design
1.2 | Hot or Cold Weather Concreting |  |  |  | DoT 610.17 (a) | Any proposed hot or cold weathering procedure is submitted at least 2 weeks from placement and approved by the Superintendent. |  |  |  | Prior to start of works | R |  | SE |  |  | W |  | Proposed Procedure
2.0 Setting Out
2.1 | Setting Out |  |  |  | DoT Clause 703.17 IFC Design | Superintendent has reviewed and confirmed the set out. Work is constructed as per the set-out line, level, cross-sectional profiles on the drawings. |  |  |  | Each lot | H |  | SE |  |  | H |  | Survey Set out
3.0 Construction
3.1 | Ambient Weather for Concreting |  |  |  | DoT Clause 703.09 610.17 |  Freshly finished concrete is protected from sun, wind, rain until curing is completed. Further protection is considered for more extreme.  Concrete temperature right before placing is between 10°C and 32°C.  Evaporation rate is less than 0.50kg/m2 per hour. |  |  |  | Each lot | S |  | SE
3.2 | Machine extrusion or Slip Form |  |  |  | DoT Clause 703.23 |  Datum for grade/alignment is established. |  |  |  | Each lot | S |  | SE |  |  |  |  | Delivery Dockets
[11 empty] | Verification of acceptance by | [6 empty] | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
[11 empty] | Symal |  |  |  |  | Superintendent
Item no. | Activity |  |  |  | Ref docs | Acceptance criteria |  |  |  | Freq | Key |  | Resp |  | Initial/ date | Key | Sign/ date
 Concrete is fed to the machine at a uniform rate, free of surface pitting >5mm and honeycombed patches. And satisfactorily compacted and dense.  When combining fixed forms and extruded work with similar mixes, the concrete in the fixed form section is compacted with internal vibration for a satisfactory compacted mass of concrete.
3.3 | Profile transitions and Matching Existing Sections |  |  |  | DoT Clause 703.24 SD2102 |  When joining new and existing kerb, profile transitions follow SD2102 and should appear identical to the existing sections. |  |  |  | Each lot | I |  | SE
3.4 | Surface Finish (Exposed Surface) Edgings |  |  |  | DoT Clause 703.25 | Edgings are rendered and have a steel trowel finish.  Rendering applied within 30m of placing/extruding.  Mortar used is 2 parts fines, 1 part cement, and sufficient water for a suitable consistency.  Rendering thickness is less than 3mm.  Exposed surfaces have a steel trowel finish. |  |  |  | Each lot | S |  | SE
3.5 | Surface Finish (Exposed Surface) |  |  |  | DoT Clause 703.25 | Finished product is neat and of uniform colour.  Edges are sharp and clean, and bullnoses are regular and of uniform appearance.  Discoloured concrete is cleaned/replaced.  Permanently hidden concrete surfaces including footpaths, edgings, concrete surfacing have a class 4 finish.  All other concrete elements have a class 3 finish for external surface and a class 4 finish for permanently hidden surface. |  |  |  | Each lot | I |  | SE
3.6 | Joints (Edgings-Transverse) |  |  |  | DoT Clause 703.26 |  Transverse joints are built at right angles to back of edgings at intervals less than 2.5m.  Extruded edging installation does not damage or distort adjacent surfaces.  Fixed form edgings templates are removed as soon as practicable after finishing placement.  The guillotine (extruding) or template (fixed) cuts between 40% to 70% of the are of section. In both cases the resultant slot in the edging shall be tooled to a depth of 20 mm to produce a neat groove not less than 5 mm wide on the exposed |  |  |  | Each lot | S |  | SE
[11 empty] | Verification of acceptance by | [6 empty] | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
[11 empty] | Symal |  |  |  |  | Superintendent
Item no. | Activity |  |  |  | Ref docs | Acceptance criteria |  |  |  | Freq | Key |  | Resp |  | Initial/ date | Key | Sign/ date
surfaces, following which a vertical cut shall be made through the base of the groove to a depth not less than 50 mm from the surface.
3.7 | Joints (Edgings-Expansion) |  |  |  | DoT Clause 703.26 (a) (ii) |  Expansion joints are placed at junctions with bridges and are 15mm wide filled with cork or bituminous impregnated particle board strips extending for the full width/depth of edging.  Fillers are placed before concrete is placed and held firmly during placement. |  |  |  | Each lot | R |  | SE
3.8 | Curing & Protection of Concrete |  |  |  | DoT Clause 703.10 703.27 | All concrete work is:  Cured continuously with either water, wet hessian, or curing compound (AS3799) for at least 7 days. Except concrete edgings which is at least 3 days.  Protected from early loading (4 days): Pedestrians, animals, vehicles, and rain or other cause. |  |  |  | Each lot | S |  | SE
3.9 | Marking of conduit positions |  |  |  | DoT Clause 703.28 | Existing conduit under edgings are marked up above the conduit with a suitable identification. |  |  |  | Each lot | I |  | SE
3.1 | Concrete Cracking |  |  |  | DoT Clause 703.30 |  Concrete has no surface crack more than 0.2mm. NCR is raised for cracking more than 0.2mm.  Cracked sections are removed and replaced or repaired as directed by the superintendent. |  |  |  | Each lot | I |  | SE
3.11 | Repair of Damaged Kerb and Channel |  |  |  | DoT Clause 703.30 | Damaged kerb concrete repairs shall be carried out using a method and materials accepted by the Superintendent. Kerb channel and edgings shall have a length at least 1m removed and replaced with a section: (a) Constructed on compacted bedding. (b) Dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and, (c) Shaped and finished with curved trowels to match the profile and surface finish of adjoining sections |  |  |  | Each lot | I |  | SE |  |  | R
3.12 | Paving |  |  |  | DoT Clause 703.15 | Concrete paving including footpaths, edgings, other surfacing’s are shaped to match existing fixtures, e.g., pit covers, edgings and vehicle crossings, within 5 mm.
[11 empty] | Verification of acceptance by | [6 empty] | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
[11 empty] | Symal |  |  |  |  | Superintendent
Item no. | Activity |  |  |  | Ref docs | Acceptance criteria |  |  |  | Freq | Key |  | Resp |  | Initial/ date | Key | Sign/ date
4.0 Completion
4.1 | As Built Survey |  |  |  | DoT Clause 703.15 | Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point. |  |  |  | Each lot | R I |  | SE |  |  | R
5.0 Work Lot Close Out
5.1 | Product Non-Conformance |  |  |  | QMP | All Product Non-Conformance(s) recorded and closed (if applicable) |  |  |  | Each lot | R |  | SE |  |  |  |  | NCR No:……………… NCR reports
5.2 | Quality Representative to check the above criteria and records to confirm |  |  |  | QMP Lot Records | All above criteria met, and records identified attached. |  |  |  | Each lot | R |  | SE |  |  |  |  | Completed Checklist (if applicable) and reports and other compliance records attached.
Works complete (signer SS) |  |  |  | Date works complete
Lot conforms (signer PE) |  |  |  | Date lot closed |  |  | NCR/s no. raised |  |  |  |  | Date NCR closed for this lot
Responsibility (Resp.) Key: PM-Project Manager, PE-Project Engineer, SE- Site Engineer, CS-Civil Superintendent, SS-Site Supervisor, SV-Surveyor, CR-Client Representative SI - Superintendent Inspection Key: W – Witness, H – Hold Point, S – Surveillance, R – Review Point, I – Inspection Point