## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0022 In Situ Kerb and Channel | itp |  |  |  |  | 1630-P200-SYM-QAC-ITP-0022 In Situ Kerb and Channel
section | ITP Details
checkpoint | ITP Details
label | ITP No. - 1630-SYM-QAC-ITP-0022
label | Rev No. - 00
label | Date of Issue - 31/10/2023
label | ITP Type -
section | 1.0 Pre-start activities
checkpoint | 1.1 - Supply of Premixed Concrete for Kerb Extrusion
label | Ref docs - DoT Clause 703.05 (b), 703.11
label | Acceptance criteria - Concrete is minimum or equal 320kg cementitious material or geopolymer binder per m3. No slump or compressive strength requirements.
label | ○ Where kerb and channel is placed and compacted with internal vibration between previously placed formwork: Concrete is N32 Portland or 32 MPa geopolymer concrete standard strength grade.
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Mix Design
checkpoint | 1.2 - Hot or Cold Weather Concreting
label | Ref docs - DoT 610.17 (a)
label | Acceptance criteria - Any proposed hot or cold weathering procedure is submitted at least 2 weeks from placement and approved by the Superintendent.
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE
label | SI Key - W
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Proposed Procedure
section | 2.0 Setting Out
checkpoint | 2.1 - Setting Out
label | Ref docs - DoT Clause 703.17 IFC Design
label | Acceptance criteria - Superintendent has reviewed and confirmed the set out. Work is constructed as per the set-out line, level, cross-sectional profiles on the drawings.
label | Freq - Each lot
label | Key - H
label | Resp - SE
label | SI Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Survey Set out
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Construction
checkpoint | 3.1 - Ambient Weather for Concreting
label | Ref docs - DoT Clause 703.09, 610.17
label | Acceptance criteria - Freshly finished concrete is protected from sun, wind, rain until curing is completed. Further protection is considered for more extreme.
label | ○ Concrete temperature right before placing is between 10°C and 32°C.
label | ○ Evaporation rate is less than 0.50kg/m2 per hour.
label | Freq - Each lot
label | Key - S
label | Resp - SE
checkpoint | 3.2 - Machine extrusion or Slip Form
label | Ref docs - DoT Clause 703.23
label | Acceptance criteria - Datum for grade/alignment is established.
label | ○ Concrete is fed to the machine at a uniform rate, free of surface pitting >5mm and honeycombed patches. And satisfactorily compacted and dense.
label | ○ When combining fixed forms and extruded work with similar mixes, the concrete in the fixed form section is compacted with internal vibration for a satisfactory compacted mass of concrete.
label | Freq - Each lot
label | Key - S
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Delivery Dockets
checkpoint | 3.3 - Profile transitions and Matching Existing Sections
label | Ref docs - DoT Clause 703.24 SD2102
label | Acceptance criteria - When joining new and existing kerb, profile transitions follow SD2102 and should appear identical to the existing sections.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 3.4 - Surface Finish (Exposed Surface) Edgings
label | Ref docs - DoT Clause 703.25
label | Acceptance criteria - Edgings are rendered and have a steel trowel finish.
label | ○ Rendering applied within 30m of placing/extruding.
label | ○ Mortar used is 2 parts fines, 1 part cement, and sufficient water for a suitable consistency.
label | ○ Rendering thickness is less than 3mm.
label | ○ Exposed surfaces have a steel trowel finish.
label | Freq - Each lot
label | Key - S
label | Resp - SE
checkpoint | 3.5 - Surface Finish (Exposed Surface)
label | Ref docs - DoT Clause 703.25
label | Acceptance criteria - Finished product is neat and of uniform colour.
label | ○ Edges are sharp and clean, and bullnoses are regular and of uniform appearance.
label | ○ Discoloured concrete is cleaned/replaced.
label | ○ Permanently hidden concrete surfaces including footpaths, edgings, concrete surfacing have a class 4 finish.
label | ○ All other concrete elements have a class 3 finish for external surface and a class 4 finish for permanently hidden surface.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 3.6 - Joints (Edgings-Transverse)
label | Ref docs - DoT Clause 703.26
label | Acceptance criteria - Transverse joints are built at right angles to back of edgings at intervals less than 2.5m.
label | ○ Extruded edging installation does not damage or distort adjacent surfaces.
label | ○ Fixed form edgings templates are removed as soon as practicable after finishing placement.
label | ○ The guillotine (extruding) or template (fixed) cuts between 40% to 70% of the are of section. In both cases the resultant slot in the edging shall be tooled to a depth of 20 mm to produce a neat groove not less than 5 mm wide on the exposed surfaces, following which a vertical cut shall be made through the base of the groove to a depth not less than 50 mm from the surface.
label | Freq - Each lot
label | Key - S
label | Resp - SE
checkpoint | 3.7 - Joints (Edgings-Expansion)
label | Ref docs - DoT Clause 703.26 (a) (ii)
label | Acceptance criteria - Expansion joints are placed at junctions with bridges and are 15mm wide filled with cork or bituminous impregnated particle board strips extending for the full width/depth of edging.
label | ○ Fillers are placed before concrete is placed and held firmly during placement.
label | Freq - Each lot
label | Key - R
label | Resp - SE
checkpoint | 3.8 - Curing & Protection of Concrete
label | Ref docs - DoT Clause 703.10, 703.27
label | Acceptance criteria - All concrete work is:
label | ○ Cured continuously with either water, wet hessian, or curing compound (AS3799) for at least 7 days. Except concrete edgings which is at least 3 days.
label | ○ Protected from early loading (4 days): Pedestrians, animals, vehicles, and rain or other cause.
label | Freq - Each lot
label | Key - S
label | Resp - SE
checkpoint | 3.9 - Marking of conduit positions
label | Ref docs - DoT Clause 703.28
label | Acceptance criteria - Existing conduit under edgings are marked up above the conduit with a suitable identification.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 3.10 - Concrete Cracking
label | Ref docs - DoT Clause 703.30
label | Acceptance criteria - Concrete has no surface crack more than 0.2mm. NCR is raised for cracking more than 0.2mm.
label | ○ Cracked sections are removed and replaced or repaired as directed by the superintendent.
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 3.11 - Repair of Damaged Kerb and Channel
label | Ref docs - DoT Clause 703.30
label | Acceptance criteria - Damaged kerb concrete repairs shall be carried out using a method and materials accepted by the Superintendent.
label | Kerb channel and edgings shall have a length at least 1m removed and replaced with a section:
label | (a) Constructed on compacted bedding.
label | (b) Dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and,
label | (c) Shaped and finished with curved trowels to match the profile and surface finish of adjoining sections
label | Freq - Each lot
label | Key - I
label | Resp - SE
label | SI Key - R
checkpoint | 3.12 - Paving
label | Ref docs - DoT Clause 703.15
label | Acceptance criteria - Concrete paving including footpaths, edgings, other surfacing’s are shaped to match existing fixtures, e.g., pit covers, edgings and vehicle crossings, within 5 mm.
section | 4.0 Completion
checkpoint | 4.1 - As Built Survey
label | Ref docs - DoT Clause 703.15
label | Acceptance criteria - Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm.
label | ○ Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
label | Freq - Each lot
label | Key - R, I
label | Resp - SE
label | SI Key - R
section | 5.0 Work Lot Close Out
checkpoint | 5.1 - Product Non-Conformance
label | Ref docs - QMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
textbox | NCR No:
label | ○ NCR reports
checkpoint | 5.2 - Quality Representative to check the above criteria and records to confirm
label | Ref docs - QMP Lot Records
label | Acceptance criteria - All above criteria met, and records identified attached.
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.