## ITP - 112
Earthworks Overarching Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0112 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 5 – CONSTRUCTION ACTIVITY – EARTHWORKS AND FILL (EXCLUDING MSE WALL)
5.01 | Structural Fill
5.05.01 | Compaction Methodology | Details of the plant shall be submitted to the Engineer and given in the Contractors methodology. All construction shall be carried out in accordance with TNZ F/1 | PS 15.5.4 | Methodology | Before Works | R | PE
5.01.01 | Structural Fill Plateau Testing | The Contractor shall undertake 'plateau' trial compaction tests to confirm the methodology of constructing the fill. This should be carried out according to TNZ F/1: 1997. The plateau density tests shall be undertaken on 20m test strips with the compaction plant that will be used on site. | PS 15.5.4 PS 15.5.5 | Site Notes | Three tests per stockpile per piece of Compaction Plant | HP | ENG
5.02 | Erosion and Sedimentation Control
5.02.01 | Erosion and Sedimentation Control Methodology | The Contractor shall provide a methodology of how they will implement and manage sediment control. This plan shall be submitted to the Engineer for approval. | PS 15.5.2 | Methodology | Prior to Earthworks | HP | ENG
5.02.02 | Erosion and Sedimentation Control Implementation and Removal | The Contractor shall construct and maintain all erosion and sediment control measures for the duration of the contract. Erosion and sediment control measures will not be removed from site until the site is fully stabilised. | PS 15.5.2 | Site Notes | During Construction | M | SE
5.06 | Earthworks Completion
5.06.01 | Compaction Acceptance | The Contractor shall supply copies of test results, certificates, etc. to the Engineer to confirm that materials or works comply with the specified requirements before commencing work or progressing to the next phase of construction. | PS 15.5.5 | Notice of Acceptance | Seven days before commencing work or progressing to the next phase of construction. | HP | ENG

## ITP - 113
Earthworks Excavation and Subgrade Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0113 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 5 – CONSTRUCTION ACTIVITY – EARTHWORKS AND FILL (EXCLUDING MSE WALL)
5.03 | Excavation and subgrade suitability
5.03.01 | Type U Material Stripping | Vegetation, Organic Soils, and Contaminated material shall be stripped and stockpiling separately from each other and other fill types. | 15.2.2 | Site Notes | During Construction | M | SE
5.03.02 | Stripped Material | All stripped material shall be stockpiled and managed as per the requirements of this specification. | PS 15.5.3 | Site Notes | During Construction | M | SE
5.03.03 | Subgrade Suitability | The subgrade below the proposed foundation and road alignment shall be impact rolled with a minimum roller weight of 3300kg/m drum and then inspected to assess any soft spots or unsuitable subgrade soils. | PS 15.5.3 | Site Notes | Prior to Filling | I | SE
5.03.04 | Plate bearing test | Subgrade improvement shall be verified by Plate Bearing tests in accordance with NZS 4431:2022 and DIN 18134. Plate bearing test results shall be reported to the Engineer for acceptance prior to placement of Structural Fill | PS 15.5.3 | Plate Bearing Test Results | Prior to Placement of Structural Fill | I | SE
5.03.05 | Soft or loose zones | Soft or loose zones shall be undercut and replaced with structural fill compacted in layers in accordance with this specification. | PS 15.5.3 | Site Notes | When Encountered | I | SE
5.03.06 | Earthworks Grading | All earthworks including excavations and cuts shall be graded adequately so that water ponding does not occur. | PS 15.5.3 | Site Notes | During Construction | M | SE
5.03.07 | Subgrade Surface Finishing Inspection | The subgrade surface finishing shall be fully completed prior to hold point inspection and commencement of sub-base construction. | PS 15.5.3 | Approval Notice | Prior to commencement of Filling | HP | ENG

## ITP - 115
Rip Rap Installation and Backfill Inspection and Test Plan
Project: Homer Tunnel Avalanche Shelter
DS2676-DOW-ITP-CV-0115 - Rev 0
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 14 – CONSTRUCTION ACTIVITY – SCOUR PROTECTION
14.01 | Rip Rap Installation and Backfill
14.01.01 | Unsuitable Foundation Materials | All unsuitable foundation material shall be excavated down to suitable firm material, or as directed by the Engineer. | PS 24.2.3 | Site Records | Upon Occurrence | R | PE
14.01.02 | Approval to Place of Rip-Rap Rock | Placement of rip-rap rock shall not proceed without the Engineer’s approval. | PS 24.2.5 | Approval | Prior to Placement | HP | ENG
14.01.03 | Placement of Rip-Rap Rock | The rock shall be placed by hydraulic excavator to form a well interlocking mass with a minimum of voids. The grading of the rock shall be maintained throughout the rip-rap layer, with larger rocks interspersed with smaller ones. Elongated rocks are to be placed with their long dimension approximately horizontal and preferably dipped slightly inward. Rocks must have at least a 3-point bearing on underlying rocks, without including the bearing on small void filling rocks. | PS 24.2.5 | Site Records | During Installation | R | PE
14.01.04 | Rip Rap Shape Control | The Contractor shall maintain control of his earthworks to ensure the following shape tolerances are achieved: a) Horizontal tolerance ± 200mm for rock rip-rap layer. b) Vertical tolerance ± 250mm for rock rip-rap layer. | PS 24.2.2 | Survey | Each Location | I | SV
14.01.05 | Rip Rap Finish | The finished rip rap surface shall present uniform toe and top of slope lines where applicable and the finished slope profile. | PS 24.2.2 | Site Records | Each Location | I | PE
14.01.06 | Backfill (Talus) | The Contractor shall cover the rip rap with a 500mm layer of talus material recovered from the site. | PS 24.2.6 | Site Records | Each Location | I | PE