## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2676-DOW-ITP-CV-0112-Earthworks Overarching | itp |  |  |  |  | DS2676-DOW-ITP-CV-0112-Earthworks Overarching Rev 0
section | 5.01 Structural Fill
checkpoint | 5.05.01 Compaction Methodology
label | Acceptance / Conformance Criteria - Details of the plant shall be submitted to the Engineer and given in the Contractors methodology. All construction shall be carried out in accordance with TNZ F/1
label | Standard / Specification - PS 15.5.4
label | Verifying Document - Methodology
label | Frequency - Before Works
label | Activity - R
label | By - PE
checkpoint | 5.05.02 Structural Fill Plateau Testing
label | Acceptance / Conformance Criteria - The Contractor shall undertake 'plateau' trial compaction tests to confirm the methodology of constructing the fill. This should be carried out according to TNZ F/1: 1997. The plateau density tests shall be undertaken on 20m test strips with the compaction plant that will be used on site.
label | Standard / Specification - PS 15.5.4, PS 15.5.5
label | Verifying Document - Site Notes
label | Frequency - Three tests per stockpile per piece of Compaction Plant
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 5.02 Erosion and Sedimentation Control
checkpoint | 5.02.01 Erosion and Sedimentation Control Methodology
label | Acceptance / Conformance Criteria - The Contractor shall provide a methodology of how they will implement and manage sediment control. This plan shall be submitted to the Engineer for approval.
label | Standard / Specification - PS 15.5.2
label | Verifying Document - Methodology
label | Frequency - Prior to Earthworks
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.02 Erosion and Sedimentation Control Implementation and Removal
label | Acceptance / Conformance Criteria - The Contractor shall construct and maintain all erosion and sediment control measures for the duration of the contract. Erosion and sediment control measures will not be removed from site until the site is fully stabilised.
label | Standard / Specification - PS 15.5.2
label | Verifying Document - Site Notes
label | Frequency - During Construction
label | Activity - M
label | By - SE
section | 5.06 Earthworks Completion
checkpoint | 5.06.01 Compaction Acceptance
label | Acceptance / Conformance Criteria - The Contractor shall supply copies of test results, certificates, etc. to the Engineer to confirm that materials or works comply with the specified requirements before commencing work or progressing to the next phase of construction.
label | Standard / Specification - PS 15.5.5
label | Verifying Document - Notice of Acceptance
label | Frequency - Seven days before commencing work or progressing to the next phase of construction.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2676-DOW-ITP-CV-0113-Earthworks Excavation and Subgrade | itp |  |  |  |  | DS2676-DOW-ITP-CV-0113-Earthworks Excavation and Subgrade Rev 0
section | 5.03 Excavation and subgrade suitability
checkpoint | 5.03.01 Type U Material Stripping
label | Acceptance / Conformance Criteria - Vegetation, Organic Soils, and Contaminated material shall be stripped and stockpiling separately from each other and other fill types.
label | Standard / Specification - 15.2.2
label | Verifying Document - Site Notes
label | Frequency - During Construction
label | Activity - M
label | By - SE
checkpoint | 5.03.02 Stripped Material
label | Acceptance / Conformance Criteria - All stripped material shall be stockpiled and managed as per the requirements of this specification.
label | Standard / Specification - PS 15.5.3
label | Verifying Document - Site Notes
label | Frequency - During Construction
label | Activity - M
label | By - SE
checkpoint | 5.03.03 Subgrade Suitability
label | Acceptance / Conformance Criteria - The subgrade below the proposed foundation and road alignment shall be impact rolled with a minimum roller weight of 3300kg/m drum and then inspected to assess any soft spots or unsuitable subgrade soils.
label | Standard / Specification - PS 15.5.3
label | Verifying Document - Site Notes
label | Frequency - Prior to Filling
label | Activity - I
label | By - SE
checkpoint | 5.03.04 Plate bearing test
label | Acceptance / Conformance Criteria - Subgrade improvement shall be verified by Plate Bearing tests in accordance with NZS 4431:2022 and DIN 18134. Plate bearing test results shall be reported to the Engineer for acceptance prior to placement of Structural Fill
label | Standard / Specification - PS 15.5.3
label | Verifying Document - Plate Bearing Test Results
label | Frequency - Prior to Placement of Structural Fill
label | Activity - I
label | By - SE
checkpoint | 5.03.05 Soft or loose zones
label | Acceptance / Conformance Criteria - Soft or loose zones shall be undercut and replaced with structural fill compacted in layers in accordance with this specification.
label | Standard / Specification - PS 15.5.3
label | Verifying Document - Site Notes
label | Frequency - When Encountered
label | Activity - I
label | By - SE
checkpoint | 5.03.06 Earthworks Grading
label | Acceptance / Conformance Criteria - All earthworks including excavations and cuts shall be graded adequately so that water ponding does not occur.
label | Standard / Specification - PS 15.5.3
label | Verifying Document - Site Notes
label | Frequency - During Construction
label | Activity - M
label | By - SE
checkpoint | 5.03.07 Subgrade Surface Finishing Inspection
label | Acceptance / Conformance Criteria - The subgrade surface finishing shall be fully completed prior to hold point inspection and commencement of sub-base construction.
label | Standard / Specification - PS 15.5.3
label | Verifying Document - Approval Notice
label | Frequency - Prior to commencement of Filling
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2676-DOW-ITP-CV-0115-Rip Rap Installation and Backfill | itp |  |  |  |  | DS2676-DOW-ITP-CV-0115-Rip Rap Installation and Backfill Rev 0
section | 14.01 Rip Rap Installation and Backfill
checkpoint | 14.01.01 Unsuitable Foundation Materials
label | Acceptance / Conformance Criteria - All unsuitable foundation material shall be excavated down to suitable firm material, or as directed by the Engineer.
label | Standard / Specification - PS 24.2.3
label | Verifying Document - Site Records
label | Frequency - Upon Occurrence
label | Activity - R
label | By - PE
checkpoint | 14.01.02 Approval to Place of Rip-Rap Rock
label | Acceptance / Conformance Criteria - Placement of rip-rap rock shall not proceed without the Engineer’s approval.
label | Standard / Specification - PS 24.2.5
label | Verifying Document - Approval
label | Frequency - Prior to Placement
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.01.03 Placement of Rip-Rap Rock
label | Acceptance / Conformance Criteria - The rock shall be placed by hydraulic excavator to form a well interlocking mass with a minimum of voids. The grading of the rock shall be maintained throughout the rip-rap layer, with larger rocks interspersed with smaller ones. Elongated rocks are to be placed with their long dimension approximately horizontal and preferably dipped slightly inward. Rocks must have at least a 3-point bearing on underlying rocks, without including the bearing on small void filling rocks.
label | Standard / Specification - PS 24.2.5
label | Verifying Document - Site Records
label | Frequency - During Installation
label | Activity - R
label | By - PE
checkpoint | 14.01.04 Rip Rap Shape Control
label | Acceptance / Conformance Criteria - The Contractor shall maintain control of his earthworks to ensure the following shape tolerances are achieved:
label | a) Horizontal tolerance ± 200mm for rock rip-rap layer.
label | b) Vertical tolerance ± 250mm for rock rip-rap layer.
label | Standard / Specification - PS 24.2.2
label | Verifying Document - Survey
label | Frequency - Each Location
label | Activity - I
label | By - SV
checkpoint | 14.01.05 Rip Rap Finish
label | Acceptance / Conformance Criteria - The finished rip rap surface shall present uniform toe and top of slope lines where applicable and the finished slope profile.
label | Standard / Specification - PS 24.2.2
label | Verifying Document - Site Records
label | Frequency - Each Location
label | Activity - I
label | By - PE
checkpoint | 14.01.06 Backfill (Talus)
label | Acceptance / Conformance Criteria - The Contractor shall cover the rip rap with a 500mm layer of talus material recovered from the site.
label | Standard / Specification - PS 24.2.6
label | Verifying Document - Site Records
label | Frequency - Each Location
label | Activity - I
label | By - PE