## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP
section | Job Approval Documents/Construction Documents
checkpoint | Received Construction drawing from Client
checkpoint | Shop drawings Prepared, reviewed and updated. Issued "As For Construction"
label | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint-no-status | Formwork
checkpoint-no-status | Reinforcement (Reo)
checkpoint-no-status | Embedded Items and their placement
checkpoint-no-status | Lift Procedure
checkpoint-no-status | Concreting (mix design)
section | Test on Concrete (requests and approvals)
checkpoint-no-status | Request From Client
checkpoint-no-status | Test schedule and Test Results
section | Transport 01
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 02
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Other Documentations
checkpoint-no-status | Special Instructions
checkpoint-no-status | Other
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
bool | Set out
bool | Core Holes
bool | Install dowels
checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings.
checkpoint | Grouting and sealing
checkpoint | Remove back propping when instructed by consulting Engineers.
section | Final Inspection
checkpoint-no-status | Final Inspection
bool | Tank Pit
bool | Internal Slab
bool | Tank Lid
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist (Tank Base)
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Continuous Water Stop - Superwell 47B as per the manufacture specification
bool | Refer the instructions from manufacturer
bool | Place the water stop as per the drawing
bool | check the position, alignment of the water stop after the concrete
checkpoint | Concrete cover check 50mm
checkpoint | Concrete thickness (200mm)
checkpoint | Panel width double check 100% accuracy, alignment check
textbox | Panel width:
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Reinforcement (Reo) placed, cleaned, tightened
bool | Curing Procedure arranged
bool | Photo Taken
checklist | Installers Checklist (Tank Base)
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item - Continuous Water Stop - Superwell 47B as per the manufacture specification
bool | Refer the instructions from manufacturer
bool | Place the water stop as per the drawing
bool | check the position, alignment of the water stop after the concrete
checkpoint-no-status | ID Plate
textbox | ID Plate:
section | Pre-Pour Check Approvals
checkpoint-no-status | Final Inspection
bool | Formwork Check -Panel Dimensions & DOUBLE CHECK
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
bool | Concrete cover Check 50mm
checkpoint | Reinforcement Check
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
bool | QA - Concrete N40 Panel Mix - Special Adjustments
bool | QA - All main & other requirement to do Concreting -DOUBLE CHECK
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint-no-status | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist (Tank Wall)
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - FF,NF Lifters Correct - Position, Size, Orientation -Use 4 x 5t -240mm long foot anchors, Part No: 'P525240
checkpoint | Embedded Item - 14Nos of GROUT TUBE Dia50mm 200mm long- Position, Size, Orientation
checkpoint | Embedded Item - check positioning of the Continuous Water Stop before concreting the walls
checkpoint | Concrete cover check 50mm
checkpoint | Concrete thickness (150mm)
checkpoint | Panel width double check 100% accuracy, alignment check
textbox | Panel width:
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Reinforcement (Reo) placed, cleaned, tightened
bool | Curing Procedure arranged
bool | Photo Taken
checklist | Installers Checklist (Tank Wall)
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item - FF,NF Lifters Correct - Position,Size,Orientation -Use 4 x 5t -240mm long foot anchors, Part No: 'P525240
checkpoint | Embedded Item - 14Nos of GROUT TUBE Dia50mm 200mm long- Position,Size,Orientation
checkpoint | Embedded Item - check positioning of the Continuous Water Stop before concreting the walls
checkpoint-no-status | ID Plate
textbox | ID Plate:
section | Pre-Pour Check Approvals
checkpoint-no-status | Pre-Pour Check Approvals
bool | Formwork Check -Panel Dimensions & DOUBLE CHECK
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
bool | Concrete cover Check 50mm
checkpoint | Reinforcement Check
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
bool | QA - Concrete N40 Panel Mix - Special Adjustments
bool | QA - All main & other requirement to do Concreting -DOUBLE CHECK
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint-no-status | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist (Internal Slab)
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - FF,NF Lifters Correct - Position, Size, Orientation - Use 4 x 5t -170mm long foot anchors, Part No: 'P525170'
checkpoint | Embedded Item - Any details given from Engineer on fixing Water pump
checkpoint | Concrete cover check 50mm
checkpoint | Concrete thickness (200mm)
checkpoint-no-status | Concrete slope - Any details given from Engineer
checkpoint | Panel width double check 100% accuracy, alignment check
textbox | Panel width:
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Reinforcement (Reo) placed, cleaned, tightened
bool | Curing Procedure arranged
bool | Photo Taken
checklist | Installers Checklist (Internal Slab)
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item - FF,NF Lifters Correct - Position, Size, Orientation - Use 4 x 5t -170mm long foot anchors, Part No: 'P525170'
checkpoint | Embedded Item - Any details given from Engineer on fixing Water pump
checkpoint | Concrete slope - Any details given from Engineer
checkpoint-no-status | ID Plate
textbox | ID Plate:
section | Pre-Pour Check Approvals
checkpoint-no-status | Pre-Pour Check Approvals
bool | Formwork Check -Panel Dimensions & DOUBLE CHECK
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
bool | Concrete cover Check 50mm
checkpoint | Reinforcement Check
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
bool | QA - Concrete N40 Panel Mix - Special Adjustments
bool | QA - All main & other requirement to do Concreting -DOUBLE CHECK
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint-no-status | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist (Tank Lid)
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - FF,NF Lifters Correct - Position, Size, Orientation -Use 4 x 5t -170mm long foot anchors, Part No: 'P525170
checkpoint | Concrete cover check 50mm
checkpoint | Concrete thickness (200mm)
checkpoint-no-status | Any arrangement on placing the galvanized lovers - Any details given from Engineer
checkpoint | Panel width double check 100% accuracy, alignment check
textbox | Panel width:
checkpoint | Formwork Check - Magnets are 100% Secure, All supports , Ties, Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Reinforcement (Reo) placed, cleaned, tightened
bool | Curing Procedure arranged
bool | Photo Taken
checklist | Installers Checklist (Tank Lid)
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item - FF,NF Lifters Correct - Position, Size, Orientation -Use 4 x 5t -170mm long foot anchors, Part No: 'P525170
checkpoint | Any arrangement on placing the galvanized lovers - Any details given from Engineer
checkpoint-no-status | ID Plate
textbox | ID Plate:
section | Pre-Pour Check Approvals
checkpoint-no-status | Pre-Pour Check Approvals
bool | Formwork Check -Panel Dimensions & DOUBLE CHECK
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
bool | Concrete cover Check 50mm
checkpoint | Reinforcement Check
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
bool | QA - Concrete N40 Panel Mix - Special Adjustments
bool | QA - All main & other requirement to do Concreting -DOUBLE CHECK
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint-no-status | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Curing Procedure arranged