## Table 1
[5 empty] | Inspection and Test Plan - Control and Supervision of the Works | [17 empty] | Doc ID: FH-ZU2-QU-ITP052 REV: A
Client: Melbourne Airport | [7 empty] | Contract No: CP14038-01 | [10 empty] | Prepared By: Jamal Khodr
Project: Taxiway Zulu | [13 empty] | Reviewed By: Marco Poggenberg | [8 empty] | Date:
Construction Process: Temporary Works - General | [13 empty] | Approved By: Jordan Nicolaou | [8 empty] | Date:
Specifications: Temporary Works Design Process Matrix
Structure / Component: Temporary Works
Lot No: |  | Lot Details: | [9 empty] | Lot size/Quantity: |  |  |  |  | Date:
Item No. |  | Task/Activity Description |  | Inspection/Test | [13 empty] | HP/ WP/ AP/ IP/ TP SCP |  |  | Responsibility | Checked by:
|  |  |  | Frequency |  |  | Acceptance Criteria |  |  | Reference Documents |  | Inspection/ Test Method |  | Record of conformity | [6 empty] | Project Engineer Principal’s Rep. Surveyor Foreman | Principal’s Rep. |  |  | FH | Date
1 |  | Temporary Works - Design Phase
1.1 |  | Review Temporary Works Design Process Matrix |  | Prior to commencing activity |  |  | Confirm extent of temporary works required by reviewing the Temporary Works Design Process Matrix. |  |  | Temporary Works Design Process Matrix |  | Verify |  | Drawings and drawing registers |  |  |  | HP* |  |  | Site Engineer/Project Engineer
1.2 |  | Submission of Risk Assessment for relevant Temporary Works |  | Prior to commencing activity |  |  | Confirm the level of risk assessment documentation required for temporary works |  |  | Temporary Works Design Process Matrix |  | Verify |  | Risk Assessment |  |  |  | HP* |  |  | Site Engineer/Project Engineer
1.3 |  | Submission of Temporary Works Brief for Temporary Works Designer |  | Prior to commencing activity |  |  | Completion of the temporary works design brief to highlight the scope and required design/deliverables for temporary works designer. |  |  | Temporary Works Design Process Matrix Drawings |  | Verify |  | Temporary Works Design Brief |  |  |  | HP* |  |  | Site Engineer/Project Engineer
1.4 |  | Submission of IFC Temporary Works Design Documentation |  | Prior to commencing activity |  |  | Submission of temporary works design documentation. Including but not limited to:  Construction methodology  Plans and details  Calculations  Geotechnical reports  Lift plans  Material specifications  Testing (as required)  Inspection criteria/plan |  |  | Temporary Works Design Documentation Drawings |  | Verify |  | Construction Methodology Plans and details Calculations Geotechnical report Lift plans Testing Sequence Drawings |  |  |  | HP* |  |  | Site Engineer/Project Engineer
1.5 |  | Review Subcontractor WMS / ITC (if applicable) |  | Prior to commencing activity |  |  | Submission and review of subcontractor WMS / ITC and confirm alignment with temporary works design documentation |  |  | Temporary Works Design Documentation |  | Verify |  | ITC WMS |  |  |  | HP* |  |  | Site Engineer/Project Engineer
1.6 |  | Designer Certification check as Profession Engineer (NER / RPEV) – as required |  | Prior to commencing activity |  |  | Confirmation of Designers credentials on the National Engineering Register (NER) and/or Register of Professional Engineers Victoria (RPEV) |  |  | Temporary Works Design Process Matrix |  | Verify |  | NER RPEV |  |  |  | HP* |  |  | Site Engineer/Project Engineer
1.7 |  | Designer Validator Certification check as Profession Engineer (NER / RPEV) |  | Prior to commencing activity |  |  | Confirmation of Designer Validators credentials on the National Engineering Register (NER) and/or Register of Professional Engineers Victoria (RPEV) |  |  | Temporary Works Design Process Matrix |  | Verify |  | NER RPEV |  |  |  | HP* |  |  | Site Engineer/Project Engineer
1.8 |  | Update of relevant Safe Work Method Statement |  | Prior to commencing activity |  |  | Verification of updated SWMs demonstrating relevant safety controls / mitigations to eliminate hazards |  |  | Temporary Works Design Process Matrix |  | Verify |  | SWMS |  |  |  | HP* |  |  | Site Engineer/Project Engineer
2 |  | Construction / Site Implementation
2.1 |  | Check for correct documentation |  | Prior to commencing activity |  |  | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings. - all drawings are the latest revision. |  |  | Approved Temporary Works Design Documentation |  | Verify |  | Drawings and drawing registers |  |  |  | HP* |  |  | Project Engineer
2.2 |  | Procurement of Temporary Works Material |  | Each Lot |  |  | Ensure all required materials are procured in accordance to approved shop drawing specifications / requirements. |  |  | Approved Temporary Works Design Shop Drawings |  | Verify |  | This ITP signed |  |  |  | WP |  |  | Site Engineer/Project Engineer
2.3 |  | Certification of Compliance |  | Each Lot |  |  | Provide manufacturer’s Certificate of Compliance against temporary works drawings. |  |  | Approved Temporary Works Design Shop Drawings |  | Verify |  | Supplier’s Certificate of Compliance |  |  |  | HP* |  |  | Site Engineer/Project Engineer
2.4 |  | Implementation of all measures and controls |  | Prior to commencing activity |  |  | All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP. |  |  | PSP, EMP, TMP, JSEA, SWMS, WP |  | Visual Inspection |  | This ITP signed |  |  |  | WP |  |  | Site Engineer/Project Engineer
2.5 |  | Ground support check |  | Prior to commencing activity |  |  | Confirmation of ground conditions comply with the expected ground conditions as per geotechnical report / structural drawings. |  |  | Approved Temporary Works Design Documentation |  | Test Report |  | Inspection report Geotechnical report |  |  |  | HP* |  |  | Site Engineer/Project Engineer
2.6 |  | Survey Checks |  | Prior to commencing activity |  |  | Survey set out to be completed for all assets |  |  | Approved Temporary Works Design Shop Drawings |  | Verify |  | This ITP signed |  |  |  | HP* |  |  | Project Engineer / Surveyor
2.7 |  | Permit to Construct Temporary Works |  | Each Lot |  |  | Verification of work described has been inspected and approval is given to construct in accordance with the temporary works design, detailed construction methodology, inspection and test plans, and risk assessment. |  |  | Construction Methodology Sequence Drawings |  | Visual Inspection |  | Temporary works permit to construct, apply load and remove Subcontractors ITC |  |  |  | HP* |  |  | Temporary Works Coordinator Project Engineer
2.8 |  | Permit to Apply Load to Temporary Works |  | Each Lot |  |  | Verification the temporary works described have been constructed in accordance with the temporary works design, detailed construction methodology, inspection and test plans, risk assessment and all required checks carried out. Any minor non-conformances between construction and design are to be noted. |  |  | Construction Methodology Sequence Drawings |  | Visual Inspection |  | Temporary works permit to construct, apply load and remove Subcontractors ITC |  |  |  | HP* |  |  | Temporary Works Coordinator Project Engineer
2.9 |  | Routine Inspections (time, weather event, etc.) where applicable |  | Each Lot |  |  | Evidence that routine inspections as defined by the temporary work are undertaken (where applicable). |  |  | Approved Temporary Works Design Documentation |  | Visual Inspection |  | Inspection Report Subcontractors ITC |  |  |  | IP |  |  | Temporary Works Coordinator Project Engineer
2.1 |  | Permit to Remove Temporary Works |  | Each Lot |  |  | All necessary checks have been completed and the temporary works described may be removed in accordance with the detailed construction methodology, risk assessment and inspection and test plans. |  |  | Construction Methodology Sequence Drawings |  | Visual Inspection |  | Subcontractors ITC |  |  |  | HP* |  |  | Temporary Works Coordinator Project Engineer
2.11 |  | Demobilisation and tidy |  | Each Lot |  |  | Ensure no remaining material is left behind and housekeeping completed. |  |  | N/A |  | Visual Inspection |  | Site Inspection |  |  |  | WP |  |  | Site Engineer/Project Engineer
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
[6 empty] | Inspection and Test Plan - Control and Supervision of the Works | [17 empty] | Doc ID: FH-ZU2-QU-ITP052 REV: A
| Client: Melbourne Airport | [7 empty] | Contract No: CP14038-01 | [10 empty] | Prepared By: Jamal Khodr
| Project: Taxiway Zulu | [13 empty] | Reviewed By: Marco Poggenberg | [8 empty] | Date:
| Construction Process: Temporary Works - General | [13 empty] | Approved By: Jordan Nicolaou | [8 empty] | Date:
Specifications: Temporary Works Design Process Matrix
Structure / Component: Temporary Works
Legend:
| HP |  | Hold Point | Work shall not proceed past the HP until released by the Principal’s Representative | [6 empty] | IP |  | Inspection point |  |  | Formal Inspection to be done and recorded
| HP* |  | Fulton Hogan Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [6 empty] | TP |  | Test Point |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point | An inspection which must be witnessed by the Principal’s Representative | [6 empty] | SCP |  | Survey conformance point |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point | Written or verbal approval given by the Principal’s Representative
Notes