## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP052 - Temporary Works - General | itp |  |  |  |  | FH-ZU2-QU-ITP052 - Temporary Works - General - Rev 0
section | 1.0 - Temporary Works - Design Phase
checkpoint | 1.1 - Review Temporary Works Design Process Matrix
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Confirm extent of temporary works required by reviewing the Temporary Works Design Process Matrix.
label | Reference Documents - Temporary Works Design Process Matrix
label | Inspection/Test Method - Verify
label | Record of conformity - Drawings and drawing registers
label | HP*
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 1.2 - Submission of Risk Assessment for relevant Temporary Works
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Confirm the level of risk assessment documentation required for temporary works
label | Reference Documents - Temporary Works Design Process Matrix
label | Inspection/Test Method - Verify
label | Record of conformity - Risk Assessment
label | HP*
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 1.3 - Submission of Temporary Works Brief for Temporary Works Designer
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Completion of the temporary works design brief to highlight the scope and required design/deliverables for temporary works designer.
label | Reference Documents - Temporary Works Design Process Matrix Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Temporary Works Design Brief
label | HP*
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 1.4 - Submission of IFC Temporary Works Design Documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Submission of temporary works design documentation. Including but not limited to:
label | ○ Construction methodology
label | ○ Plans and details
label | ○ Calculations
label | ○ Geotechnical reports
label | ○ Lift plans
label | ○ Material specifications
label | ○ Testing (as required)
label | ○ Inspection criteria/plan
label | Reference Documents - Temporary Works Design Documentation Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Construction Methodology
label | ○ Plans and details
label | ○ Calculations
label | ○ Geotechnical report
label | ○ Lift plans Testing
label | ○ Sequence Drawings
label | HP*
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 1.5 - Review Subcontractor WMS / ITC (if applicable)
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Submission and review of subcontractor WMS / ITC and confirm alignment with temporary works design documentation
label | Reference Documents - Temporary Works Design Documentation
label | Inspection/Test Method - Verify
label | Record of conformity - ITC WMS
label | HP*
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 1.6 - Designer Certification check as Profession Engineer (NER / RPEV) – as required
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Confirmation of Designers credentials on the National Engineering Register (NER) and/or Register of Professional Engineers Victoria (RPEV)
label | Reference Documents - Temporary Works Design Process Matrix
label | Inspection/Test Method - Verify
label | Record of conformity - NER RPEV
label | HP*
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 1.7 - Designer Validator Certification check as Profession Engineer (NER / RPEV)
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Confirmation of Designer Validators credentials on the National Engineering Register (NER) and/or Register of Professional Engineers Victoria (RPEV)
label | Reference Documents - Temporary Works Design Process Matrix
label | Inspection/Test Method - Verify
label | Record of conformity - NER RPEV
label | HP*
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 1.8 - Update of relevant Safe Work Method Statement
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Verification of updated SWMs demonstrating relevant safety controls / mitigations to eliminate hazards
label | Reference Documents - Temporary Works Design Process Matrix
label | Inspection/Test Method - Verify
label | Record of conformity - SWMS
label | HP*
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
section | 2.0 - Construction / Site Implementation
checkpoint | 2.1 - Check for correct documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings.
label | – all drawings are the latest revision.
label | Reference Documents - Approved Temporary Works Design Documentation
label | Inspection/Test Method - Verify
label | Record of conformity - Drawings and drawing registers
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 2.2 - Procurement of Temporary Works Material
label | Frequency - Each Lot
label | Acceptance Criteria - Ensure all required materials are procured in accordance to approved shop drawing specifications / requirements.
label | Reference Documents - Approved Temporary Works Design Shop Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 2.3 - Certification of Compliance
label | Frequency - Each Lot
label | Acceptance Criteria - Provide manufacturer’s Certificate of Compliance against temporary works drawings.
label | Reference Documents - Approved Temporary Works Design Shop Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Supplier’s Certificate of Compliance
label | HP*
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 2.4 - Implementation of all measures and controls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 2.5 - Ground support check
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Confirmation of ground conditions comply with the expected ground conditions as per geotechnical report / structural drawings.
label | Reference Documents - Approved Temporary Works Design Documentation
label | Inspection/Test Method - Test Report
label | Record of conformity - Inspection report, Geotechnical report
label | HP*
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | 2.6 - Survey Checks
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Survey set out to be completed for all assets
label | Reference Documents - Approved Temporary Works Design Shop Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer / Surveyor
date | Date Completed:
checkpoint | 2.7 - Permit to Construct Temporary Works
label | Frequency - Each Lot
label | Acceptance Criteria - Verification of work described has been inspected and approval is given to construct in accordance with the temporary works design, detailed construction methodology, inspection and test plans, and risk assessment.
label | Reference Documents - Construction Methodology, Sequence Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Temporary works permit to construct, apply load and remove, Subcontractors ITC
label | HP*
label | Responsibility - Temporary Works Coordinator, Project Engineer
date | Date Completed:
checkpoint | 2.8 - Permit to Apply Load to Temporary Works
label | Frequency - Each Lot
label | Acceptance Criteria - Verification the temporary works described have been constructed in accordance with the temporary works design, detailed construction methodology, inspection and test plans, risk assessment and all required checks carried out.
label | ○ Any minor non-conformances between construction and design are to be noted.
label | Reference Documents - Construction Methodology, Sequence Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Temporary works permit to construct, apply load and remove, Subcontractors ITC
label | HP*
label | Responsibility - Temporary Works Coordinator, Project Engineer
date | Date Completed:
checkpoint | 2.9 - Routine Inspections (time, weather event, etc.) where applicable
label | Frequency - Each Lot
label | Acceptance Criteria - Evidence that routine inspections as defined by the temporary work are undertaken (where applicable).
label | Reference Documents - Approved Temporary Works Design Documentation
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Inspection Report, Subcontractors ITC
label | IP
label | Responsibility - Temporary Works Coordinator, Project Engineer
date | Date Completed:
checkpoint | 2.10 - Permit to Remove Temporary Works
label | Frequency - Each Lot
label | Acceptance Criteria - All necessary checks have been completed and the temporary works described may be removed in accordance with the detailed construction methodology, risk assessment and inspection and test plans.
label | Reference Documents - Construction Methodology, Sequence Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Subcontractors ITC
label | HP*
label | Responsibility - Temporary Works Coordinator, Project Engineer
date | Date Completed:
checkpoint | 2.11 - Demobilisation and tidy
label | Frequency - Each Lot
label | Acceptance Criteria - Ensure no remaining material is left behind and housekeeping completed.
label | Reference Documents - N/A
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Site Inspection
label | WP
label | Responsibility - Site Engineer/Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: