## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Preliminary Activities and Materials Approval |  |  |  |  | Yes | Preliminary Activities and Materials Approval | 9ed74550-4c29-4082-aa62-216789ed802c
checkpoint-group |  |  | section | Preliminary Activities (Approved by Client)
checkpoint-status |  |  | checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint-status |  |  | checkpoint | Permacast Project Quality Management Plan
checkpoint-status |  |  | checkpoint | Inspection & Test Plan
checkpoint-status |  |  | checkpoint | MDR Index
checkpoint-status |  |  | checkpoint | Work Method Statement (WMS) - Prestress
checkpoint-status |  |  | checkpoint | Work Method Statement (WMS) - Curing
checkpoint-status |  |  | checkpoint | Concrete Repair Methodology
checkpoint-status |  |  | checkpoint | Shop Drawings
checkpoint-status |  |  | checkpoint | Test Panel Prepared and Inspected by Client
checkpoint-status |  |  | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
checkpoint-group |  |  | section | Concrete
checkpoint-status |  |  | checkpoint | S50 Concrete Mix Design Approved by Client
label | c4151f15-51e3-527d-88a8-307e94ff7ad8 |  | note | Supplier : WA Premix
label | dabaace1-08a9-58fa-aa40-da7ce46e0a20 |  | note | Mix Code: BH1447 (S50/14/200)
label | 25b1c8ac-cf21-5c93-bce2-b1ae140ff05a |  | note | Slump : 200 ± 40
checkpoint-status |  |  | checkpoint | S65 Concrete Mix Design Approved by Client
label | 6e348a2b-4bad-5622-90b3-de6b35e3c43b |  | note | Supplier : WA Premix
label | 94d74f6a-619a-5c90-a723-455b1d1b37cb |  | note | Mix Code: BH3500 (S65/14/200)
label | 5258d1da-e742-56f5-aa4c-d42374ced07c |  | note | Slump : 200 ± 40
checkpoint-group |  |  | section | Steel Reinforcement
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-status |  |  | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
checkpoint-group |  |  | section | Prestressing Tendons
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-status |  |  | checkpoint | Ensure that all Coil Numbers are recorded
checkpoint-status |  |  | checkpoint | Stressing Calculations Submitted and Approved by Client for Works
checkpoint-status |  |  | checkpoint | Stressing Jack Calibration Certificates
checkpoint-group |  |  | section | Lifting Anchors
checkpoint-status |  |  | checkpoint | Lifting Design Approved by Client
checkpoint-status |  |  | checkpoint | Lifting Devices Approved by Client
checkpoint-status |  |  | checkpoint | Inspection of Delivery for Completeness and Quality
checkpoint-group |  |  | section | Cast-in Items and Ferrules
checkpoint-status |  |  | checkpoint | All Cast in Materials Approved
checkpoint-status |  |  | checkpoint | Inspection of Delivery for Completeness and Quality
checklist-sectioned |  |  | checklist | Precast Beams |  |  |  |  | Yes | Precast Beams | e97358fa-2377-44e1-877e-f45517c41779
checkpoint-group |  |  | section | Pre-Pour Checklist
checkpoint-status |  |  | checkpoint | Pre-Pour Checklist completed
text | feb11ee9-38d0-5f78-9aec-c2a0335d9ae1 |  | textbox | Cast Number | 1
text | 462fc7ff-ab37-5244-8a8a-6bcbaecc8188 |  | textbox | Bridge Name | 3
text | a80d311a-efe9-56a4-afb9-6856791c9e44 |  | textbox | Precast Beam 1 | 4
text | 823b9c2a-ef6f-5927-9bc8-f814b57de018 |  | textbox | Precast Beam 2 | 5
text | 584be65a-0fe9-55d4-a941-6fcefb5ac17d |  | textbox | Mould Beam 1
text | 2cd17773-ea04-53ed-9e68-9027cff77eb7 |  | textbox | Mould Beam 2
checkpoint-status |  |  | checkpoint | Shop Drawings approved for Works
checkpoint-status |  |  | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | 5b5eaaa1-3176-58b0-b852-f68a83036c80 |  | note | Length
label | 79cc9aca-c700-54a3-8777-9a22ab44e34e |  | note | Width
label | 00541c54-e87b-547c-8ff0-d36cab028634 |  | note | Height
label | 22e9b6d0-908b-548e-bbaf-0df3b95ba91d |  | note | Straightness
label | abb63dd2-92ae-5dbd-a2c0-741c92ebb62c |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Mould Surface Checked
label | be6abb0e-fa67-556d-bf79-a8f5a1629a9f |  | note | Cleaned
label | e93388c8-e36c-5759-bb84-535c5ce8a7d4 |  | note | Sealed
label | e9f0ff83-6e8a-54da-a9ff-ff669ddaf24e |  | note | Rubbers in Place
label | fbb56918-2107-525d-93cc-78db91cb6247 |  | note | Oiled
label | a28bb857-37fd-51a8-9df8-c3affd3d0b05 |  | note | Chamfers in Place
checkpoint-status |  |  | checkpoint | Reinforcement in Accordance with Drawings
label | d3a42fde-15f7-5b2f-862b-0e3237623cad |  | note | Reinforcement size
label | 9bbb36cf-e58f-54c7-8626-0c5ecd5ef8c1 |  | note | Lap Length
label | 969cd379-eae7-5cba-9c30-828eff02ee32 |  | note | Splicing
label | 1ae98a6a-d0db-5e6d-8733-d53bad24989a |  | note | Bar Chairs
checkpoint-status |  |  | checkpoint | Cover maintained and within tolerance
checkpoint-status |  |  | checkpoint | All Cast-in Items are installed in accordance with Drawings
label | b4b0102e-faaa-525a-b3b6-1edaf32a8330 |  | note | Cast-in Items
label | 0186b523-2c54-51fd-819f-545f2605dc0a |  | note | Fittings
label | 01d3282c-3006-5a7f-b00e-b2b6960b152c |  | note | Lifters Position and Type
checkpoint-status |  |  | checkpoint | Earthing and Bonding Terminals are bolted to the mould (if required)
checkpoint-status |  |  | checkpoint | Welding between Earthing Connectors is 100mm
checkpoint-status |  |  | checkpoint | (Arc Weldable Cable only) Cable is fixed with Tie Wire to Prevent Movement
checkpoint-status |  |  | checkpoint | Earthing Bars are Marked in each Beam (Protruding Bar only)
text | 484e1537-987c-5b21-b8c9-4d243a3f6a11 |  | textbox | Conductor Continuity Test Completed before and after Cage is Placed in Mould
text | f1817ad9-1f45-5826-8d93-7f1077329238 |  | textbox | Multiple Tests Completed (Diagonal Opposite Corners)
text | f415f31d-f9a2-531a-bd10-11912a1f8187 |  | textbox | Approved Equipment Used in Works
text | 6e4605a9-5ce0-538f-930d-73266843ddaa |  | textbox | Maximum 0.01 Ohm achieved
text | 4752416e-e419-5a96-8d84-fd5fdc69e669 |  | textbox | Results before and after Cage Placement in Mould Recorded
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Prestressing Strands
text | 66a82201-23f4-51d7-a368-e53f5bbf0ea2 |  | textbox | Enter Coil Number Used for this Cast
label | 0b54f0b3-b35f-553b-9578-867062de1539 |  | note | Sag Load all Strand
label | e14fa12b-cb06-50c9-874a-4c0d2f5b58cf |  | note | Multi-Stress as per Pre-stressing Procedures
checkpoint-status |  |  | checkpoint | All Temperature Loggers are installed as per Approved WMS
label | cd123de3-3b78-5043-a787-2ea55828b372 |  | note | Every 25m
label | f9380904-c159-5bb7-9267-8322140cbf6b |  | note | 1 x End Block Mid-Diaphragm
label | 2496c6f3-000a-57d2-99fe-00aa2ae268e0 |  | note | 1 x Within Cover Zone
label | feaf7541-e8d9-501a-b540-20427e271196 |  | note | 1 x Within Tent/Tarp Enclosure (Outside concrete)
label | 0de214af-4574-5d20-a9c3-2e1b5067abb3 |  | note | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
checkpoint-status |  |  | checkpoint | Ensure All temperature Loggers are Working (Check App)
checkpoint-status |  |  | checkpoint | Prepare Stressing Records and Submit to Client for Review
holdpoint |  |  | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint-status |  |  | checkpoint | QA Engineer Check Completed by
checkpoint-status |  |  | checkpoint | Client Inspector (if present)
checkpoint-group |  |  | section | Supervisor Release
checkpoint-status |  |  | checkpoint | Supervisor Release to Engineering Team
checkpoint-group |  |  | section | Casting Checklist
checkpoint-status |  |  | checkpoint | Casting Information
text | 2c3552e3-0253-5c2d-9546-e54a4290e4c9 |  | textbox | Cast Date | 2
checkpoint-status |  |  | checkpoint | Concrete Delivery Dockets
text | 1efc6d88-801d-5b25-b687-1f7644ce7e7c |  | textbox | Concrete Delivery Docket 1 | 8
text | edbd3677-eb85-5ebd-9652-9532bf659776 |  | textbox | Concrete Delivery Docket 2 | 9
text | eeea2211-8987-5392-bffa-beef4e678c3e |  | textbox | Concrete Delivery Docket 3 | 10
text | 82fa92cb-cec5-508a-a1b6-2d0dffdbc726 |  | textbox | Concrete Delivery Docket 4 | 11
text | bf0d9121-d02d-5343-b9ea-d035158c8c75 |  | textbox | Concrete Delivery Docket 5 | 12
text | f067919b-f1e5-525c-b69a-4092146eccff |  | textbox | Concrete Delivery Docket 6 | 13
checkpoint-status |  |  | checkpoint | Total Concrete Volume
text | 7c5179e1-477d-5cde-a8ab-440ea900be4b |  | textbox | Volume (m3) | 7
checkpoint-status |  |  | checkpoint | Mix Design Verified (BH1447 - S50 or BH3500 - S65)
label | 0dec9b66-fbd5-59cb-88ca-afbe8daa9ef6 |  | note | Concrete Mix Strength (Mpa)
checkpoint-status |  |  | checkpoint | Ambient Temperature within Limits
label | ee3c19dd-0c4a-50b0-9cdf-f15558180b66 |  | note | 5 - 38°C
checkpoint-status |  |  | checkpoint | Concrete Temperature
label | 50adf2d9-5c85-5d03-8d97-c68459b46f2e |  | note | max 32°C
checkpoint-status |  |  | checkpoint | Slump within Allowable Tolerance
text | cd25b9bb-6aab-5568-a5e7-c182f15c41e9 |  | textbox | Slump 1 | 14
text | 7fb64c4a-2d50-5ff1-b015-fa17814b4cb8 |  | textbox | Slump 2 | 15
label | d7c12a97-7008-53c2-979c-3f06770a7e3a |  | note | 200 ± 40mm
checkpoint-status |  |  | checkpoint | Truck Tested for strength
text | 52885768-8499-5180-8c42-83b8deb055d8 |  | textbox | Test Report Reference Number 1
text | 19f4c507-2152-5567-a8b0-a4ad4bd6f17c |  | textbox | Test Report Reference Number 2
checkpoint-status |  |  | checkpoint | Time Lag Between Trucks (< 20min)
checkpoint-status |  |  | checkpoint | Concrete Placed within 90min from Batching Plant
checkpoint-status |  |  | checkpoint | No Free Fall During Pour (< 2m)
checkpoint-status |  |  | checkpoint | Required Finish Applied as per Drawings
checkpoint-status |  |  | checkpoint | Concrete Covered Overnight
checkpoint-status |  |  | checkpoint | Cylinders Stored next to Bed
checkpoint-group |  |  | section | Stripping Checklist
checkpoint-status |  |  | checkpoint | Date Stripped
text | 8a7cb46c-f8d9-5e26-8ec9-3b066aa35fe7 |  | textbox | Enter Date
checkpoint-status |  |  | checkpoint | Concrete Cylinders Crushed and Submitted to Client
text | f926ab92-dcd3-5aed-b74f-bca793d716df |  | textbox | Stripping Strength | 16
label | 2dccb228-502b-527c-bf0f-096e658dce4f |  | note | Strength = Reading / 7.851
holdpoint |  |  | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint-status |  |  | checkpoint | Lifting Strength Achieved
checkpoint-status |  |  | checkpoint | Product Clearly Labelled
checkpoint-status |  |  | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | d3f04dd1-4382-5e3a-86df-0508760e8b9a |  | note | Length
label | 6a3b2137-d905-5e8a-ae38-241eb64d09c9 |  | note | Width
label | 71c71598-1d7e-5197-8677-8018b7deed29 |  | note | Height
label | d26441fc-675e-5476-913e-46175e3a2bc1 |  | note | Straightness
label | 01075e25-ffd8-59fb-b89c-de91a7ac94b1 |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Specified Finish Achieved
checkpoint-status |  |  | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
label | e907ecb7-9d3e-5224-8eb1-dc32965507e0 |  | note | Cast-in Items
label | 0995bc93-a264-5e32-a67e-758e04dab69f |  | note | Fittings
label | 758cc7b2-1e6a-5fde-874e-d74d34116b13 |  | note | Lifters Position and Type
checkpoint-status |  |  | checkpoint | Lifted and Handled as per Drawings
checkpoint-status |  |  | checkpoint | Storage/Stacking as per Approved Plan
checkpoint-status |  |  | checkpoint | Curing as per Approved Methodology
checkpoint-status |  |  | checkpoint | Post-Pour Works Completed (As Required)
text | f8825b90-e0d4-59ad-92fe-fb44580dcfd0 |  | textbox | Strands are Cut Flush
text | cf35d38c-d230-5012-b97d-8593c4239990 |  | textbox | Strands Bulbs as per Drawing
text | 69fc3ab5-acde-569e-b5f0-4a803107e4b0 |  | textbox | Starter Bars are Bent as Required
text | cfe9717e-1719-5805-bbf7-076c9a51ceb6 |  | textbox | All Drain Holes are Clean
text | 0a5aa227-58f7-52b1-b07b-dc199e965dda |  | textbox | All Miscellaneous Items are Completed
checkpoint-status |  |  | checkpoint | Survey Hog of Beams (Dumpy)
text | 6ac58ee9-6fdb-509c-b86d-94eb876031bf |  | textbox | First Reading (Once Stripped)
text | 77caa2c0-7984-5f5c-8b4e-629c821a243b |  | textbox | Second Reading (if required)
text | a39c3a9c-fc59-57bd-9711-763c0e4eedf2 |  | textbox | Final Reading (Prior to Delivery)
checkpoint-status |  |  | checkpoint | Temperature Logging Completed and Conforming. Attach Results
checkpoint-status |  |  | checkpoint | Electrical Conductivity Verified Post Cast and Results Matching Previous Results
checkpoint-group |  |  | section | Any Defect Identified
checkpoint-status |  |  | checkpoint | Punchlisting Completed
checkpoint-status |  |  | checkpoint | Repairs Required (if applicable)
checkpoint-status |  |  | checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint-status |  |  | checkpoint | Any NCR Required (if applicable)
checkpoint-status |  |  | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
checkpoint-group |  |  | section | As-Built Drawings
checkpoint-status |  |  | checkpoint | As-Built Drawings Completed, Stamped and Attached
checkpoint-group |  |  | section | Concrete Strength Test Report
checkpoint-status |  |  | checkpoint | Concrete Strength Test Report Received
text | b979e69a-80c6-5d3b-9861-3c6053321b53 |  | textbox | Concrete Test Report Number 1
text | 55e87823-8adb-506e-a596-11036a79f9b3 |  | textbox | 7 Day Strength (1) | 17
text | bb70a92d-4cdd-518b-8fe6-0606eb13f8ae |  | textbox | 7 Day Strength (2) | 18
text | 2ffdafed-9d2a-5fa4-9fc2-fa857ebfff2d |  | textbox | 28 Day Strength (3) | 19
text | 5e420b2f-474e-5b4e-bda9-1f8a44e4ab1d |  | textbox | 28 Day Strength (4) | 20
text | 1af5e1bf-ef48-5f34-abc2-adfdc54a5f55 |  | textbox | 28 Day Strength (5) | 21
text | 7d471555-3756-5bc2-9bbb-1fbf2d7bd755 |  | textbox | 28 Day Strength (6) | 22
checkpoint-group |  |  | section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
checkpoint-status |  |  | checkpoint | Completed by
checkpoint-status |  |  | checkpoint | Reviewed by
holdpoint |  |  | signoff | (INTERNAL HOLD POINT)
checkpoint-status |  |  | checkpoint | Client Representative (if applicable)