## Folder Structure
External Tile Cladding QA - Jimmy Point Apartment
Elevation | Level
East | 1
| 2 | External Tile Cladding Checklist
| 3 | External Tile Cladding Checklist
| 4 | External Tile Cladding Checklist
West | 1 | External Tile Cladding Checklist
| 2 | External Tile Cladding Checklist
| 3 | External Tile Cladding Checklist
| 4 | External Tile Cladding Checklist
South East | 1 | External Tile Cladding Checklist
| 2 | External Tile Cladding Checklist
| 3 | External Tile Cladding Checklist
| 4 | External Tile Cladding Checklist
South West | 1 | External Tile Cladding Checklist
| 2 | External Tile Cladding Checklist
| 3 | External Tile Cladding Checklist
| 4 | External Tile Cladding Checklist
North | 1 | External Tile Cladding Checklist
| 2 | External Tile Cladding Checklist
| 3 | External Tile Cladding Checklist
| 4 | External Tile Cladding Checklist
South | 1 | External Tile Cladding Checklist
| 2 | External Tile Cladding Checklist
| 3 | External Tile Cladding Checklist
| 4 | External Tile Cladding Checklist

## Checklists
Checklist | External Tile Cladding Checklist
Section | Substrate inspection
checkpoint | Check for visible cracks
Assess if wall out of plumb/square not more than 50mm on concrete and 15mm on timber
No damage on waterproofing
Section | Setting Out
Checkpoint | RL provided by main contractor
Control of horizontal and vertical lines
Control of Plumb Line
Setting out follows shop drawings in accordance to RL
Section | Sub-structure Installation
Subsection | Fixing rail to concrete with M6 Hilti HUS3H Anchor
Min Embedment 40mm
Min Concrete Edge Distance 50mm
Max Spacing 600mm c/c
Max Cantilever of Rails 150mm
Subsection | Fixing rail to timber with 8G Class 4 Tek Screw
Min Embedment 50mm
Min Timber Edge Distance 21mm
Max Spacing 400mm c/c
Max Cantilever of Rails 150mm
Subsection | Fixing rail to Structural Steel with Hilti X-U P8 Nail (Galvanised)
Max spacing 400mm c/c
Min Steel Embedment 6mm
Max Cantilever of Rails 150mm
Subsection | Fixing Tile Deflection Head Aluminium Plate to Timber with 8G Class 4 Tek Screw
Plate Size: 100x50x5mm
Max Spacing 1000mm c/c
Check Point | Proclima Extoseal applied for every fixing point to all substrate
Min 5mm, Max 50mm HDPE Packers to Concrete
Min 5mm, Max 15mm HDPE Packers to Timber
Section | Flashing Installation
Unequal Angle (UA 1115) Flashing Installed
Interstorey Flashing Installed
External Corner Flashing installed
Internal Corner Flashing Installed
Z extrusion and L angle Installed
Seismic Joint Flashings (Top Hat) Installed
Section | Tempio Tiles Installation
Checkpoint | Setting out according to shop drawing
No chipping / damage / crack
Tiles installed are fix properly and not moving or rattling
All flashing proud 5mm from finish tile face
5mm gap in between tiles and flashings
2-3mm gap tile joint
9mm tile joint to external mitre corners
10mm tile joint to seismic joint
25mm joint between tile flashings to adjacent finishings
Section | Final Clean
Checkpoint | Clean all debris and stain
Clean all visible marks
Section | Sign Off
Check Point | Sign Off and Handover
Section | Grout and Silicone
Checkpoint | Tiles adhesive cured and clean properly
Grout work properly into all joint
Silicon applied and tolled to a neat continuously finish
Section | Final check and Sign off