## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | aa122d60-a2e5-42eb-8b0e-95d046aee1ae |  | checklist | Checklist (General) |  |  |  |  | Yes | Checklist (General) | 261cbb0a-cf1c-4090-b2cc-23737ba5cf4a
checkpoint-group | d53d6127-a6e0-4820-8689-7f500de72701 |  | section | Substrate inspection
checkpoint-status | 0b124a73-7c3a-4075-acb3-00bd2127636c |  | checkpoint | Tileslate underlay installed and cleaned
checkpoint-status | 4eb96d63-4437-4836-827a-33520c8273da |  | checkpoint | Substrate has no damages or cracks
checkpoint-status | 8d822fa7-3ba8-46c6-aee2-e63328fdb2df |  | checkpoint | Holes and penetration filled
checkpoint-status | 9651d619-8a1f-417c-9a42-9eab6eb3aa0e |  | checkpoint | FFL confirmed and correct height
checkpoint-status | 808b3488-9383-4a45-9583-3c27836b5533 |  | checkpoint | Wall Square and Plumb
checkpoint-group | 4e7d745d-66ef-4161-b393-ca9acc381d0f |  | section | Waterproofing
checkpoint-status | 0c46077f-18c3-4ca4-92c1-68c66a4af3c3 |  | checkpoint | Ardex Multiprime Primer to all relevant substrate
checkpoint-status | d1de468d-0b41-4dd4-9d4b-cd900d2a33d6 |  | checkpoint | Apply Ardex STB tape to all changes plane, penetration, and floor waste area
checkpoint-status | bcb9ea0b-3384-4259-a88c-34ba24909d20 |  | checkpoint | Apply WPM 002 waterproofing (2 coats)
checkpoint-group | e77d0d4c-9cd1-4fb6-a123-12d96591075d |  | section | Tiling
checkpoint-status | 3f083d84-62a9-41a9-95a8-9cd73fb01836 |  | checkpoint | Setting out tiles according to construction drawing / Site confirmation
checkpoint-status | 4873f447-f930-4ec4-9197-ca525d967a79 |  | checkpoint | Primer applied prior to tiling
checkpoint-status | 7e569cfe-b704-4991-8c2c-5c5a9fac5d62 |  | checkpoint | Full coverage of tiles with adhesive
checkpoint-status | 299ffef5-88e0-4936-8a63-f29e0ac8c31a |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status | 3ddbf505-2574-4af0-a5c8-b77bd7e154a3 |  | checkpoint | Finishing trims & transition bars edge alignment
checkpoint-status | 366003b0-810a-421c-af8b-f3684e10eb70 |  | checkpoint | Skirting Tile Installed at 150mm
checkpoint-group | 777de4ee-b447-4106-807a-05ea581135c6 |  | section | Grout and Silicone
checkpoint-status | fa924f3c-07c3-4a69-a008-95648ca7444a |  | checkpoint | Tiles adhesive cured and clean properly
checkpoint-status | 0f1bebef-30aa-414c-9d2b-c41f534af67e |  | checkpoint | Grout work properly into all joint
checkpoint-status | 71661c0a-ff6c-4071-95f5-ccd6edec70f2 |  | checkpoint | Silicon applied and rolled to a neat finish
checkpoint-group | facff294-e72e-4082-a1e9-0a5a1cba32c8 |  | section | Final check and Sign off
checkpoint-status | a82e95ff-e87f-491a-87b6-3763892bcc29 |  | checkpoint | Tiling Completed
holdpoint | 7e504361-cceb-4d14-92b1-c0c4dcc6d25d |  | signoff | Sign off and Handover