## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | feb660f9-9eb5-484f-a451-429c03d49fb4 |  | checklist | Checklist (General) |  |  |  |  | Yes | Checklist (General) | 81cda786-5ea6-4b86-9100-f5adbd33a2f6
checkpoint-group | dd146c10-3f75-4166-95df-3a6a2898bf3c |  | section | Substrate inspection
checkpoint-status | f98fb8c8-dcf8-48a8-b7b0-fbda7858e13f |  | checkpoint | Substrate has no damages and sound
checkpoint-status | 871cfcdd-e90e-4ee1-a643-15d103302a55 |  | checkpoint | Holes and penetration filled
checkpoint-status | 36386ed8-030d-4feb-b8d3-7c8cd737882f |  | checkpoint | Floor grinded or free from any latent, contaminants or cracks
checkpoint-status | 21f810d4-cd2f-43fb-a4a5-07be87973286 |  | checkpoint | FFL confirmed and Screed to correct height
checkpoint-status | 48e65a1a-57a8-47f4-9810-58d796dbede7 |  | checkpoint | Wall Square and Plumb
checkpoint-group | 67d2a344-b48a-4e5e-bd61-284a23a63e0c |  | section | Waterproofing
checkpoint-status | 6b28775b-7651-4aba-aecb-6cbff0101fb1 |  | checkpoint | Ardex Multiprime Primer to all relevant substrate
checkpoint-status | cdb6a231-ab89-4703-a368-b34351a25b5d |  | checkpoint | Apply Ardex STB tape to all changes plane, penetration, and floor waste area
checkpoint-status | a3a43a22-8be5-43f2-85c0-3b2a477ee986 |  | checkpoint | WPM 002 waterproofing
checkpoint-group | c4548d7f-dd91-4738-a012-3ca209b710f3 |  | section | Tiling
checkpoint-status | 4e82f284-6aeb-464a-9f93-e2aa4bc53f9e |  | checkpoint | Setting out tiles according to construction drawing / Site confirmation
checkpoint-status | 9054097c-0eaa-46e7-8523-297e4913ffc6 |  | checkpoint | Primer applied prior to tiling
checkpoint-status | 6d21ca1f-7205-4777-a1cd-368b564449ee |  | checkpoint | Full coverage of tiles with adhesive
checkpoint-status | 7ecd91f6-f510-476d-94d2-c3b15aaabd2d |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status | d7efe61a-e423-4169-a048-d592df569099 |  | checkpoint | Finishing trims & transition bars edge alignment
checkpoint-status | 1690dc02-5e16-4742-8da9-a61bdeebefe7 |  | checkpoint | Skirting Tile Installed at 150mm
checkpoint-group | f3dd7b7c-b048-43c5-91a3-466ddfd731c0 |  | section | Grout and Silicone
checkpoint-status | 13b6331f-8b3b-431c-b249-64e19e6e9206 |  | checkpoint | Tiles adhesive cured and clean properly
checkpoint-status | d1d25685-90ff-467f-a240-981f974dcf9e |  | checkpoint | Grout work properly into all joint
checkpoint-status | efa9de35-62de-4a4e-be1f-101d918820c8 |  | checkpoint | Silicon applied and rolled to a neat finish
checkpoint-group | 18217b31-46a6-43d5-abc5-22b93da17909 |  | section | Final check and Sign off
checkpoint-status | 6d6a6cdd-e405-4b23-9351-06913e3469e0 |  | checkpoint | Tiling Completed
checkpoint-status | 102362bd-e5a0-42ad-9222-450c3f130102 |  | checkpoint | Sign off and Handover
checklist-sectioned | 380aa6eb-5bc3-4075-b531-139277838fcd |  | checklist | Area: |  |  |  |  | Yes | QA - External Cladding Checklist | c8dea159-066f-4ead-980d-4bbdacb69c72
checkpoint-group | 08f34a14-88c3-4e9d-8339-dd922f3afc3a |  | section | Details
checkpoint-status | bad42a01-a796-458b-bf48-b330050f19a6 |  | checkpoint | Details input
text | e40c82c6-e5eb-4aed-87f9-b8a75a40bd30 |  | textbox | Zone ref:
text | e0b28828-d2f8-465e-8d5d-18f1bc52deb3 |  | textbox | Gridline ref:
button | befedffd-69df-493a-96d6-d04bf1b33505 |  | button |  | Timber,Concrete,Steel
text | 6cac8fc1-1f6a-4d76-a405-5480895fba5a |  | textbox | Commenced date:
text | 439cf439-bfd4-4c73-838a-631f8b52ac1c |  | textbox | Completed date:
checkpoint-group | 3605e713-80a1-4ca5-891c-534d70edc0d9 |  | section | Substrate Inspection
checkpoint-status | e59922a6-74dd-49c5-a3a9-f482f78fe541 |  | checkpoint | New concrete to be min 28 days
checkpoint-status | 9d8e77e1-010e-4f68-b1da-49a8c47aaf66 |  | checkpoint | Deflection Criteria within 1/360
checkpoint-status | 60df524f-830c-4fff-bb21-b859b19f748e |  | checkpoint | No surface damages
checkpoint-status | 115f89d0-82af-4ff8-83af-eeb14baece8a |  | checkpoint | Prior work completed including fire baton/mullion
checkpoint-status | c7f3ab63-fcfd-4554-bbef-245b006ea13a |  | checkpoint | Check for visible cracks
checkpoint-status | 89136991-3f0f-4ec6-a8da-2c3406eed201 |  | checkpoint | Clean and free from contamination
checkpoint-status | a74c4640-c1be-4d9c-9d71-3b3f3a362b3d |  | checkpoint | Waterproofing done prior to installation
checkpoint-status | 87726834-281d-4eb1-a97c-9e178de18213 |  | checkpoint | Difference between concrete and timber substrate finish level
checkpoint-status | 24bfb5cc-96cc-4a02-ab69-b0609dab235d |  | checkpoint | Position of nogs on timber wall aligned with bracket position
checkpoint-status | 19bba660-b0df-42aa-8056-9eff2e4bd0f1 |  | checkpoint | Locate all GL, RL, Setout Point, Window Finish Line, Seismic Joint Position, and Control/Movement Joint.
checkpoint-group | c4b54585-ce88-428c-96e0-005565167fa2 |  | section | Substrate Preparation
checkpoint-status | edef7332-28d6-488c-a079-ba4eee537440 |  | checkpoint | Patch any damages waterproofing material with approved material
checkpoint-status | 4000d1fd-fef6-480c-8b06-3d19d7843a5a |  | checkpoint | All visible fixing points need to be covered with waterproofing sheet
checkpoint-status | 5e655f3d-ff4d-4d1f-bc21-8ebed482f5d2 |  | checkpoint | Re-assess if wall out of plumb/square and if bracket and T-section can accommodate the issue
checkpoint-group | fee9c19a-30c7-47e1-aad2-a51f48315b74 |  | section | Setting Out
checkpoint-status | 30a47151-4365-485f-8257-ee9e6841268b |  | checkpoint | RL and GL provided by surveyor
checkpoint-status | ecebaa40-a736-47da-aa2a-1d647b01bbc6 |  | checkpoint | Window finish line given by Thermosash
checkpoint-status | 03331365-02cc-40a2-bc8d-7931c9c59c90 |  | checkpoint | Check and verified in every Zone area
checkpoint-status | 77e1e895-fa1b-406e-a0ce-446ace513fd6 |  | checkpoint | Control of horizontal and vertical lines
checkpoint-status | fdea0340-0e94-410a-a8a1-843318fe2365 |  | checkpoint | Control of Plumb Line
checkpoint-group | 65128844-bd8d-4e4b-ad70-1fdaa9f1c2ea |  | section | Sub-structure Installation
checkpoint-status | eaaddba4-d97a-410d-848f-239b97e2089d |  | checkpoint | As per shop drawing
checkpoint-status | 3b02c0cc-719a-44ef-a3c0-54cd3e0c428f |  | checkpoint | L-Bracket to be installed onto nogs
checkpoint-status | 4c7657ff-f486-46dc-9dd5-3ce7c9a78a4a |  | checkpoint | L-Bracket max 1500mm c/c Vertically
checkpoint-status | 613152c9-c597-4c00-9412-f65df479acb1 |  | checkpoint | L-Bracket max 600mm c/c horizontally
checkpoint-status | 3e54d544-572e-4e8c-b186-159a299f8ce6 |  | checkpoint | Fix to timber with 14gx75 Screw
checkpoint-status | 6a0c0a1f-501d-46cb-ab43-427a264e5487 |  | checkpoint | Fix to concrete with HUS 8x75 screw
checkpoint-status | 91dc9c85-2eed-4975-b70b-fc16f90a1ec1 |  | checkpoint | Fix to metal with 12G24TPI Tek Screw
checkpoint-status | 8708e57f-c242-41c1-a415-3ee2e2954f0c |  | checkpoint | Fix T-Section and Top hat with 12G Tek Screw
checkpoint-status | 75dd18d6-522a-4333-bfb9-efea405809c1 |  | checkpoint | Fix Tempio clips with 12G Tek Screw
checkpoint-status | c6e85ab2-45d9-43bb-8253-c4f952acd987 |  | checkpoint | Finish of Top Hat to plumb with window line
checkpoint-status | 22bf0f2e-3a40-4c05-898b-510a19d73b85 |  | checkpoint | Do not connect in between inter-storey deflection area
checkpoint-status | 2adb5c2f-b911-4ce8-9383-325b0958fec1 |  | checkpoint | Install rain screen flashing on Lv 03 and Lv 05 inter-storey deflection
checkpoint-group | dac9410f-27e0-4c42-8905-46aabc3f3ac9 |  | section | Terracotta Tiles Installation
checkpoint-status | 23ab9a77-82be-49b8-87c2-fb54e6e1789a |  | checkpoint | Setting out according to GL, FFL, Window finish line
checkpoint-status | 320f2d22-f3e1-4f66-b1d2-0882a5b26036 |  | checkpoint | Position of terracotta according to zoning plan and coding plan
checkpoint-status | 8fdbd9a3-5e3c-4f0f-9f58-8d1eae925fce |  | checkpoint | Break in between inter-storey deflection
checkpoint-status | 72954ba6-c60d-4608-97c5-7a223e557871 |  | checkpoint | Spacing in between tile to be 10mm with 2mm tolerance
checkpoint-status | 3a54cfe6-c3f2-413d-b980-0e0d94d0b2fe |  | checkpoint | Spacing in between inter-storey deflection to be 30mm with 2mm tolerance
checkpoint-status | 4d33c5a8-51cd-4229-b5ff-21f112359ddb |  | checkpoint | Fix with min 4nos of clips per tile
checkpoint-status | 071ca0e3-a207-45f7-a000-e2f9cda88da6 |  | checkpoint | Cross check dimension with GL and window line
checkpoint-status | 6ebeb494-cd52-4664-95cc-d8a3de348ec5 |  | checkpoint | Sharp edges shall be filled
checkpoint-status | dcfc320e-f6e0-4b77-aa06-947a29cd5d3c |  | checkpoint | Shims or packers used to adjust plumb level
checkpoint-status | 2adaf1aa-09e5-46a4-9672-aa147b16d1a1 |  | checkpoint | Each Zone done to be QA and signed off by TTP supervisor
checkpoint-group | a10cb4d9-3cb8-48b7-870a-67f1f7a9ae3f |  | section | Final Clean
checkpoint-status | ccc2ad84-d1b7-4e00-ae5f-cf49a3963a7d |  | checkpoint | Clean all debris and stain
checkpoint-status | 22149fa4-cdd8-466b-9118-0ff2a4787277 |  | checkpoint | Clean all visible marks
checkpoint-status | ee5004dd-1d81-43f6-9c33-3d6c094b1ad1 |  | checkpoint | Touch up where necessary
checkpoint-group | 673f8230-ff0d-4ecb-9baa-96ea9a8a8de8 |  | section | Final Check
checkpoint-status | ce3f3773-4b65-4997-ab36-0b33584e552f |  | checkpoint | Inspection
checkpoint-status | 5dac9902-fd79-4c0e-aa6c-790110ea476a |  | checkpoint | Sign Off