## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 2e8f47f7-ec31-4393-9a05-3457e5e57bdb |  | checklist | External Tile Cladding Checklist |  |  |  |  | Yes | External Tile Cladding Checklist | 1640de65-e5a6-422f-846b-aeb790766bba
checkpoint-group | 32acab55-ad1b-4e8a-ad7c-a6e797056dd1 |  | section | Substrate inspection
checkpoint-status | fc75c26c-5998-41bb-af2a-ecbdb5bc43c8 |  | checkpoint | Check for visible cracks
checkpoint-status | 7b2c7724-220a-4747-9cf1-0ed21163d208 |  | checkpoint | Assess if wall out of plumb/square and if packers can accommodate the issue
checkpoint-status | 8db387a5-1c33-4e05-9127-a8ab5c7d8051 |  | checkpoint | No damage on waterproofing
checkpoint-group | 2e4e4d75-5d3b-470a-ba69-2f8de560e948 |  | section | Setting Out
checkpoint-status | 08845e68-b8dd-48f2-83a4-f13f05c3a72d |  | checkpoint | RL provided by main contractor
checkpoint-status | 12d324a5-3e99-41a2-bd5a-e9da63901e83 |  | checkpoint | Control of horizontal and vertical lines
checkpoint-status | 9b0c469e-9571-4273-a5de-22617ef0cabc |  | checkpoint | Control of Plumb Line
checkpoint-status | 3ed11537-cb3b-44d1-acd3-d869f03a57fe |  | checkpoint | Setting out follows shop drawings
checkpoint-group | 004e4c83-2ff9-4ee4-8392-0a0beb698a10 |  | section | Sub-structure Installation
checkpoint-status | df50127c-1736-436b-b535-c63a17432b7e |  | checkpoint | Fixing rail to concrete with M8 Stainless Steel Concrete Screw
label | 760defa0-6176-5be2-b54c-bf8fe356ea7d |  | note | Min Embedment 50mm
label | 5fc02b28-c0e5-5bdf-b4f5-ee50b65d8cc1 |  | note | Min Edge Distance 45mm
label | ef919551-3f5a-5100-af6a-ecc4a89ebe58 |  | note | Max Spacing 1000mm
checkpoint-status | 27581fb1-207f-493f-9dad-e515cdccade2 |  | checkpoint | Fixing rail to timber with 12G Tek Screw
label | 7414cc47-b8d2-58ac-94ce-dbcbd0386c2e |  | note | Min Embedment 45mm
label | 00658e1c-b16c-5d96-9a2c-bbb93235fbf6 |  | note | Min Edge Distance 25mm
label | 695265a5-0468-5e9a-ad17-49502d154db6 |  | note | Max Spacing 1000mm
checkpoint-status | 4c2626cc-325f-4cf8-88b1-96cb8435363a |  | checkpoint | Fixing rail to Flatbar with 8G Tek Screw
label | ff4acb60-9520-5ca2-8168-985bf95c2faf |  | note | Max Spacing 1000mm
label | c9027f13-0eec-5eb9-811d-be2c4887c970 |  | note | Overhang 80mm
checkpoint-status | 158acea7-f098-40e2-bc07-82295cecc3d0 |  | checkpoint | Fixing Flatbar to concrete with M8 Stainless Steel Concrete Screw
label | 63c8507a-cd53-5111-a1c5-f7d27bc98905 |  | note | Min Embedment 50mm
label | 7d33ac86-38c4-5096-966b-de278896ff3f |  | note | Min Edge Distance 45mm
label | a1c800f8-67b0-579e-86b6-cfc5494fc52e |  | note | Max Spacing 600mm
checkpoint-status | 95d98f88-07ad-4c9d-bb4f-72b205226f40 |  | checkpoint | Fixing Soffit L-Bracket to concrete with M8 Stainless Steel Concrete Screw
label | a967fc8e-0339-5c89-ae4b-49b376198ede |  | note | Min Embedment 50mm
label | de257b08-8146-55db-8f11-0510083c6a33 |  | note | Min Edge Distance 45mm
checkpoint-status | 0fcd3848-e14a-4396-9d19-3bd80e78a125 |  | checkpoint | Fixing Soffit L-Bracket to timber with 12G Tek Screw
label | 5e33f92e-ccea-5aed-a8be-2766e4e42289 |  | note | Min Embedment 45mm
label | b5bc79d8-6bd9-572d-b236-f6ffbba7de86 |  | note | Min Edge Distance 25mm
checkpoint-status | 35e0f8d5-9495-42cb-ae29-8f15c222100f |  | checkpoint | Vaporbond silicone sealant applied for every fixing to substrate
checkpoint-status | 4d060253-09b1-4a65-92ef-5f653623d2c2 |  | checkpoint | Bottom drip flashing installed
checkpoint-group | 6267b4ec-8e86-4969-91d8-75666f606800 |  | section | Tempio Tiles Installation
checkpoint-status | 72789d6b-62a6-4fb8-97e5-a634b298b36a |  | checkpoint | Setting out according to shop drawing
checkpoint-status | 5c677a55-8bdb-47b4-a18c-3419db98aee7 |  | checkpoint | No chipping / damage / crack
checkpoint-status | 6b31eec8-c337-4a6a-8073-49a7ffad7f38 |  | checkpoint | Tiles installed are fix properly and not moving or rattling
checkpoint-group | 505f03a3-03b7-4e5b-a91e-048ca99a9b64 |  | section | Final Clean
checkpoint-status | 20ae6f89-0499-42b5-9399-464a14158766 |  | checkpoint | Clean all debris and stain
checkpoint-status | 7866eac0-39e8-47b7-a52f-2d4f86c24d7b |  | checkpoint | Clean all visible marks
checkpoint-group | c8aeb9cf-6b6c-4f31-84dd-bf9056c89c63 |  | section | Sign Off
checkpoint-status | 76c08d08-5fae-4edc-804f-52405a5831fa |  | checkpoint | Sign Off and Handover
checklist-sectioned | f24f811c-28ca-4d39-8835-32ee5af52506 |  | checklist | Bathroom Checklist |  |  |  |  | Yes | Bathroom Checklist | 885f146b-1620-4f01-a3b2-0eb73db8882a
checkpoint-group | b4a9ae54-60c6-4f22-b493-a5111a6cee9f |  | section | Substrate inspection
checkpoint-status | 9cf68d47-d2d0-4cbe-9eff-af22c2957c24 |  | checkpoint | All prior works done
checkpoint-status | 8a52ffef-4aeb-4c90-a6ae-645b5be2363d |  | checkpoint | Substrate has no damages and sound
checkpoint-status | f420f012-93c4-4b82-8cb5-971d63c3bec6 |  | checkpoint | Floor grinded or free from any latent, contaminants or cracks
checkpoint-status | e9448cbf-f134-4a53-971f-1a88544a2c5f |  | checkpoint | Wall Square and Plumb
checkpoint-status | 59ffa807-bb63-4398-9a99-903414d9005c |  | checkpoint | Wall stopped and lined
checkpoint-status | 89847b65-d49a-4fda-b236-510fdbd8938d |  | checkpoint | Ceiling installed
checkpoint-group | 384128f8-40bb-4a4a-bd80-313b5db1d9a7 |  | section | Screed works to shower floor
checkpoint-status | 6fb8f388-2013-4d7c-94f5-16277d1c0736 |  | checkpoint | Planicrete and Mapecem Slurry applied prior screeding as a bonding agent
checkpoint-status | 63ffe591-102c-48c6-9251-67d41bd1a913 |  | checkpoint | Mix no 3 Sand to Mapecem 3: 1 ratio
checkpoint-status | 3b3937c8-3aa4-4c13-a393-4352575b9618 |  | checkpoint | FFL confirmed and Screed to correct height
checkpoint-status | 43e4d21e-62fa-4d75-9eb3-c498cd7f8977 |  | checkpoint | No loose sand on top of screed
checkpoint-group | 7df2497d-5e8d-4739-aafd-9a8778ba098b |  | section | Soundproofing
checkpoint-status | aeddb693-2844-4b32-af72-5d8ad0a773a3 |  | checkpoint | Primer Applied
checkpoint-status | 0fcea62d-e8ca-45bb-a17f-c7a7f0311b5f |  | checkpoint | PE Foam tape to all relevant substrate
checkpoint-status | 4982e567-4d7a-4739-9711-ea85416be7ad |  | checkpoint | Installed Soundproofing
checkpoint-group | 23957c30-4805-4607-837a-49b733f17bb7 |  | section | Floor Levelling
checkpoint-status | c25efcf3-3730-43fc-bf12-6ce856797d52 |  | checkpoint | Underfloor Heating Installed and tested
checkpoint-status | c87f58aa-6d46-4c28-8e5e-c75e888dc9a6 |  | checkpoint | Apply floor levelling compound (FLC) max 5mm thickness on top to cover under floor heating cables
checkpoint-group | c01eb4ef-b728-4233-880b-7f9e34b037c3 |  | section | Waterproofing
checkpoint-status | 73b1741e-af4f-42c9-aef6-10c7330cb5e3 |  | checkpoint | Apply Mapeband SA/ Mapeband Easy to all changes plane, penetration, and floor waste area
checkpoint-status | a74093a4-e7f8-430c-a450-7340729e910e |  | checkpoint | Primer 3296 to all relevant substrate
checkpoint-status | 489eb52e-52cb-43e2-8c97-c7c0872ed2d4 |  | checkpoint | Aqua Defence waterproofing 1st coat
checkpoint-status | bf06cc84-4ea3-4cb6-8a5a-df813d013897 |  | checkpoint | Aqua Defence waterproofing 2nd coat
checkpoint-status | d905b466-6169-4129-941c-c4155c718878 |  | checkpoint | Waterproofing to Vanity Splashbacks done
checkpoint-status | 5fdc4960-4ab6-44c3-9ba9-80b1f6a4b382 |  | checkpoint | Waterproofing full heights to shower walls
checkpoint-status | 572b1daa-d44d-4760-b556-753d2000d078 |  | checkpoint | Water test performed and passed
checkpoint-group | 1960045f-3edc-4463-a031-8aa4a0b48e8e |  | section | Tiling
checkpoint-status | 376c8f8d-04ec-4cf6-befd-e6875ce0e4b0 |  | checkpoint | Setting out tiles according to construction drawing / Site confirmation
checkpoint-status | 1fce6450-eaa1-4d03-b89d-8f3f066d7ea8 |  | checkpoint | Primer applied prior to tiling
checkpoint-status | 7ac67777-ca81-40aa-9ed1-490b3ad3f2ba |  | checkpoint | Full coverage of tiles with adhesive
checkpoint-status | 58edbd96-4bdd-4a82-825a-a1203cc9699d |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status | 7642bd1c-e944-4a5e-8802-ccdbfd491168 |  | checkpoint | Finishing trims & transition bars edge alignment
checkpoint-status | a98dd1aa-c003-484c-986f-e1eef013d400 |  | checkpoint | Skirting Tile Installed
checkpoint-status | 0a26451a-dd51-436d-99a6-1d9a227a702b |  | checkpoint | Vanity Splashbacks Tile Installed
checkpoint-status | 45411619-4c68-4a2c-98f9-d7ad1f43700f |  | checkpoint | Feature wall tile installed
checkpoint-group | fd24dc63-13af-4259-ae14-d4f4da1dc192 |  | section | Grout and Silicone
checkpoint-status | 71422129-0cdd-4c59-bfa8-b2b5bc39b912 |  | checkpoint | Tiles adhesive cured and clean properly
checkpoint-status | abd5beed-2be7-4317-8341-35cecaac77f1 |  | checkpoint | Grout work properly into all joint
checkpoint-status | a06e6c45-c9e9-4cd3-97a6-4486e2eb48dd |  | checkpoint | Excess grout cleaned properly
checkpoint-status | 5c918bc3-7fe5-4c44-b070-a1c05d4d8fb3 |  | checkpoint | Silicon applied to a neat continuous finish
checkpoint-status | 119f7145-4b5f-482b-8016-3c4e2e0f0c21 |  | checkpoint | Excess silicone cleaned properly
checkpoint-group | 60341101-37db-44b2-ab2e-e75f35d6920c |  | section | Final check and Sign off
checkpoint-status | d2ae48c7-025a-40ea-83af-9e2f985ade1c |  | checkpoint | Tiling Completed
checkpoint-status | 63032859-aaff-4ddc-aa2d-6c08d885b39f |  | checkpoint | Final clean done
checkpoint-status | 8d32a018-d340-44c4-88c3-24db396f69d9 |  | checkpoint | Photo Taken of Completed Area
holdpoint | 914e1649-8397-4875-b34a-2107b66e4266 |  | signoff | Sign off and Handover
checklist-sectioned | 5b9f113a-09e2-4741-8af5-4c593b1e58ef |  | checklist | External Tile Cladding Checklist |  |  |  |  | Yes | External Tile Cladding Checklist v2 (22-06-22) | b37865b2-2438-4a3b-88be-3f2650ed86c4
checkpoint-group | 3de35096-a032-4da0-8156-0cea4f15384b |  | section | Substrate inspection
checkpoint-status | 6c00fc1e-3e0b-4c62-938c-eefdcf012bb0 |  | checkpoint | Check for visible cracks
checkpoint-status | 5b067061-7a4a-4328-bc69-6607edeeef2c |  | checkpoint | Assess if wall out of plumb/square and if packers can accommodate the issue
checkpoint-status | 03c37384-955d-40af-b706-6db23a5ce1bd |  | checkpoint | No damage on waterproofing
checkpoint-group | a068b3c9-9ae6-4fee-aeff-1a9f9d89d66e |  | section | Setting Out
checkpoint-status | 4028c439-1b35-4a4d-bea4-8cf243436564 |  | checkpoint | RL provided by main contractor
checkpoint-status | 3cfa7433-2b86-4c51-85cc-cd5499c8d5a5 |  | checkpoint | Control of horizontal and vertical lines
checkpoint-status | ad8ed8c2-013b-4a6f-baf5-0c170b63960c |  | checkpoint | Control of Plumb Line
checkpoint-status | 9ad21508-fe0c-4b30-a574-0a8874121ef5 |  | checkpoint | Setting out follows shop drawings
checkpoint-group | 3cc1620f-4616-4355-ba57-28da28b17c31 |  | section | Sub-structure Installation
checkpoint-status | df6f06f5-9472-4a7f-b4f1-8fddc16c6bbc |  | checkpoint | Fixing rail to concrete with M8 Stainless Steel Concrete Screw
label | e862ee8a-081e-5e13-a1d9-bc9761525944 |  | note | Min Embedment 50mm
label | 16ae1f99-32a7-5ba7-9dde-a81695caff36 |  | note | Min Edge Distance 45mm
label | 14483475-7b2a-5afd-941e-32476ac84713 |  | note | Max Spacing 1000mm
checkpoint-status | 61e9fb96-afe5-42fa-9f82-f46acc6015cc |  | checkpoint | Fixing rail to timber with 12G Tek Screw
label | bcf5a9f7-4c39-547f-a7e6-856d7ebeeaf8 |  | note | Min Embedment 45mm
label | 169ac28b-18c5-5a25-bbe4-d4ad41111c1d |  | note | Min Edge Distance 25mm
label | 8ac48b77-ce88-5102-a686-7a04afce2320 |  | note | Max Spacing 1000mm
checkpoint-status | d5f3d672-63ea-48cd-ba9c-96a70b69fce8 |  | checkpoint | Fixing rail to Flatbar with 8G Tek Screw
label | 4db8989c-fe29-5a1e-96fb-3e183a6091c3 |  | note | Max Spacing 600mm
checkpoint-status | dbc572df-6dfd-46e6-b646-aba4eedfc7ce |  | checkpoint | Fixing Flatbar to concrete with M8 Stainless Steel Concrete Screw
label | 31622cff-5549-5fed-9b4c-e84b157e5750 |  | note | Min Embedment 50mm
label | 2e0a249a-09b8-5ee5-8ebf-ccf5c0f7c478 |  | note | Min Edge Distance 45mm
label | 33859300-e02a-5404-9347-750bc692bd29 |  | note | Max Spacing 1000mm
checkpoint-status | 05505525-9847-4b68-b2d4-6e43c77cf996 |  | checkpoint | Fixing Soffit L-Bracket to concrete with M8 Stainless Steel Concrete Screw
label | 2bbcc945-887a-5c51-abb2-1b772abcd93f |  | note | Min Embedment 50mm
label | 3c40d17b-c9e8-5c5d-91a8-a60ca6b896af |  | note | Min Edge Distance 45mm
checkpoint-status | 7372079a-405e-4b15-abe0-feefc7eadac9 |  | checkpoint | Fixing Soffit L-Bracket to timber with 12G Tek Screw
label | 168f16ff-1c49-554e-bb79-f1e907d163f5 |  | note | Min Embedment 45mm
label | 706fcda9-a9ae-5117-984f-c2085ce4aa79 |  | note | Min Edge Distance 25mm
checkpoint-status | a9cd6470-f501-4b49-8185-881ec54e3314 |  | checkpoint | Vaporbond silicone sealant applied for every fixing to substrate
checkpoint-status | 5b2214b1-fd57-4e93-a02e-04165474c64b |  | checkpoint | Bottom drip flashing installed
checkpoint-group | fde28efb-4f0a-4d53-9764-c9db91073b10 |  | section | Tempio Tiles Installation
checkpoint-status | 844b66b8-97b6-46c0-9c4d-095f08e21fa1 |  | checkpoint | Setting out according to shop drawing
checkpoint-status | b9d69e01-bb2c-4f03-a789-199df53dad55 |  | checkpoint | No chipping / damage / crack
checkpoint-status | b273ab43-3b02-408f-90c4-6cb1dbef78eb |  | checkpoint | Tiles installed are fix properly and not moving or rattling
checkpoint-group | baea926c-7aae-4ea0-8198-f8e0b8fb444c |  | section | Final Clean
checkpoint-status | 578a136f-d0a7-47f2-ae05-401fa15b918d |  | checkpoint | Clean all debris and stain
checkpoint-status | 7069abc9-4e7c-4be4-baf3-7cab260c4443 |  | checkpoint | Clean all visible marks
checkpoint-group | 92ae09ba-c177-411a-be38-d348cb1ad93a |  | section | Sign Off
checkpoint-status | 0ffec8dc-95d2-4630-bab6-4c1fb032a14e |  | checkpoint | Sign Off and Handover
checklist-sectioned | 1b0f22c0-4f79-4d9e-b63e-bdc21f4a46da |  | checklist | Toilets Checklist |  |  |  |  | Yes | Toilets Checklist | f544af51-e235-436e-8e00-d515e2010617
checkpoint-group | 31efdeae-80a6-4ac8-8df2-bcc675a1068a |  | section | Substrate inspection
checkpoint-status | 0edd7d7a-51b9-41ec-9719-3a54e6d42a52 |  | checkpoint | All prior works done
checkpoint-status | f0e7fdcd-448c-461a-abf8-38d3c5468ca3 |  | checkpoint | Substrate has no damages and sound
checkpoint-status | 7cc7706f-df24-4784-8478-cabce7524bbd |  | checkpoint | Floor grinded or free from any latent, contaminants or cracks
checkpoint-status | 485902bf-c74c-4c01-a366-e4653f3d744b |  | checkpoint | Wall Square and Plumb
checkpoint-status | fd5f8e83-1c30-4f63-b9ea-af801d5cbc21 |  | checkpoint | Wall stopped and lined
checkpoint-status | 4ebbd3c7-0c08-4e1b-a9c9-6cb69b43cfd4 |  | checkpoint | Ceiling installed
checkpoint-group | a1622d06-307b-430f-a524-50ba4177abda |  | section | Soundproofing
checkpoint-status | c39d8448-c5e1-40c8-b573-f05b9c6f357f |  | checkpoint | Primer Applied
checkpoint-status | 37579de4-4598-435e-a8dc-220b071b801a |  | checkpoint | PE Foam tape to all relevant substrate
checkpoint-status | aee282fd-5478-416e-b32d-6731287ff62b |  | checkpoint | Installed Soundproofing
checkpoint-group | 824f3f97-94a1-4909-a23a-35b4019b45c7 |  | section | Floor Levelling
checkpoint-status | c5304dfb-2234-4090-9a6f-075e74ea1a09 |  | checkpoint | Underfloor Heating Installed and tested
checkpoint-status | d65faddc-c8e4-45cd-b9fb-10030acf57d3 |  | checkpoint | Apply floor levelling compound (FLC) max 5mm thickness on top to cover under floor heating cables
checkpoint-group | 0d133d37-00c3-457f-ae4b-b3424f721df8 |  | section | Waterproofing
checkpoint-status | f9d0e37c-3b0c-4c5a-ab54-f595e9258c00 |  | checkpoint | Apply Mapeband SA/ Mapeband Easy to all changes plane, penetration, and floor waste area
checkpoint-status | 661300b4-40b7-4cb4-ae12-ba4bc98df273 |  | checkpoint | Primer 3296 to all relevant substrate
checkpoint-status | f1d907a9-152f-4ad6-9887-aa70ba7ade7a |  | checkpoint | Aqua Defence waterproofing 1st coat
checkpoint-status | e4151eeb-a764-4ac6-8ef6-a2850098cbb1 |  | checkpoint | Aqua Defence waterproofing 2nd coat
checkpoint-status | 415fa478-a984-4ca3-adad-6acfe135b2ff |  | checkpoint | Waterproofing to Vanity Splashbacks done
checkpoint-status | 63571367-d23c-4dd8-952b-c387a71a02b2 |  | checkpoint | Waterproofing full heights to shower walls
checkpoint-status | 84fd7901-d371-4507-b2f9-2870d84a3a21 |  | checkpoint | Water test performed and passed
checkpoint-group | da2b1bed-0632-489e-a3bf-2302e7838e9e |  | section | Tiling
checkpoint-status | 325383e6-d9ef-4c1c-ae0c-cd300cbe5bf3 |  | checkpoint | Setting out tiles according to construction drawing / Site confirmation
checkpoint-status | 93dde31b-569e-466f-b73e-c97b52ba3432 |  | checkpoint | Primer applied prior to tiling
checkpoint-status | 9626940d-cc0a-4358-aa47-77e803c9c8df |  | checkpoint | Full coverage of tiles with adhesive
checkpoint-status | c005a13b-ec4e-4f53-8354-3a86a6d906fb |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status | c92694a2-78d3-4871-bd6d-a143cc56060c |  | checkpoint | Finishing trims & transition bars edge alignment
checkpoint-group | 91544b51-651b-436a-9ad6-e97b80fc52bb |  | section | Grout and Silicone
checkpoint-status | 79c74f25-f70e-49bd-af1a-97a13d860c1d |  | checkpoint | Tiles adhesive cured and clean properly
checkpoint-status | 2bd36887-b536-45c5-9866-efeec590fabb |  | checkpoint | Grout work properly into all joint
checkpoint-status | dfe0030a-cf95-4ac4-94d0-40e1a7de3c0f |  | checkpoint | Excess grout cleaned properly
checkpoint-status | 1a35a413-73b2-44f0-ab93-a40994769346 |  | checkpoint | Silicon applied to a neat continuous finish
checkpoint-status | 78460fd0-4d6d-494f-b820-505f5f2102a3 |  | checkpoint | Excess silicone cleaned properly
checkpoint-group | 143b592a-4b57-4115-9676-3121a22ebd6b |  | section | Final check and Sign off
checkpoint-status | bf0ebfde-aa5f-4cea-b5ee-8f8c2d3ba6ac |  | checkpoint | Tiling Completed
checkpoint-status | f9db8613-f17c-4c05-b465-33a3f718005c |  | checkpoint | Final clean done
checkpoint-status | d76f7ef2-903f-4f72-a75d-7c9504547524 |  | checkpoint | Photo Taken of Completed Area
holdpoint | 27b46059-3261-4ed5-8e39-04273cb673b7 |  | signoff | Sign off and Handover
checklist-sectioned | 0a5c8c82-6684-4794-bb67-93e8df887fe6 |  | checklist | Balcony Checklist |  |  |  |  | Yes | Balcony Checklist | fab5cbd2-76f2-4d6e-82e0-86992ee91059
checkpoint-group | fbaea9ef-c6f6-4ba3-9741-2beed0852a61 |  | section | Substrate Inspection
checkpoint-status | cd901c12-0b12-4f3c-b648-2f4f069b5b10 |  | checkpoint | All prior works done
checkpoint-status | 3cc337e6-8c49-48f8-afe5-3ab4926f5364 |  | checkpoint | Waterproofing completed
checkpoint-group | b829c6d1-fa05-40b8-ba96-d47eded3fdbc |  | section | Balcony Deck Tiling
checkpoint-status | 47f1f59c-ce64-4143-9dd2-ce1e42655b50 |  | checkpoint | Setting out tiles according to construction drawing / Site confirmation
checkpoint-status | 681c5885-faa2-48de-bca1-c37029fe9fa4 |  | checkpoint | Nurajack NM used with Nurajack Maxi Leveller, Spacer and appropriated shims
checkpoint-status | 9dc66a25-62a7-4c06-8dba-e9629757b94e |  | checkpoint | Tile lippiness checked and to acceptable standard
checkpoint-status | 9119d05e-345a-4353-8655-0653a964497b |  | checkpoint | Tile interlocked with each others, stable and not moving/rocking
checkpoint-group | b1696213-2984-41e1-aa29-a08faf2fc3d8 |  | section | Final check and Sign off
checkpoint-status | 4181d230-f8b6-42c9-9ba4-a376a2c63b12 |  | checkpoint | Tiling Completed
checkpoint-status | aad80ce6-c466-4d71-9fec-49140af9fd50 |  | checkpoint | Photo Taken of Completed Area
holdpoint | dc216c4d-b088-4685-986d-01255ac35ee1 |  | signoff | Sign off and Handover