## Zoning
East Elevation | West Elevation | North Elevation | South Elevation
EZ01 | WZ01 | NZ01 | SZ01
EZ02 | WZ02 | NZ02 | SZ02
EZ03 | WZ03 | NZ03 | SZ03
EZ04 | WZ04 | NZ04 | SZ04
EZ05 | WZ05 | NZ05 | SZ05
EZ06 | WZ06 | NZ06 | SZ06
EZ07 | WZ07 | NZ07 | SZ07
EZ08 | WZ08 | NZ08 | SZ08
EZ09 | WZ09 | NZ09 | SZ09
EZ10 | WZ10 | NZ10 | SZ10
EZ11 | WZ11 | NZ11 | SZ11
EZ12 | WZ12 | NZ12 | SZ12
EZ13 | WZ13 | NZ13 | SZ13
EZ14 | WZ14 | NZ14 | SZ14
EZ15 | WZ15 | NZ15 | SZ15
EZ16 | WZ16 | NZ16 | SZ16
EZ17 | WZ17 | NZ17
EZ18 | WZ18 | NZ18
EZ19 | WZ19 | NZ19
EZ20 | WZ20 | NZ20
EZ21 | WZ21
EZ22 | WZ22
EZ23 | WZ23
EZ24 | WZ24
EZ25 | WZ25
EZ26 | WZ26
EZ27 | WZ27
EZ28 | WZ28
EZ29 | WZ29
EZ30 | WZ30
EZ31 | WZ31
EZ32 | WZ32
WZ33
WZ34
WZ35
WZ36

## Checklist
Checklist
Section | Rails Installation
No damages on waterproofing (visual inspection)
Datum and Survey line confirm. Setting out of Bricks confirmed
8g Tek Screw x 2 Horizontal Rails To Top Hat, max 600mm c/c
Check for rails plumbness (random points)
Check for rails levelness (random points)
Check for rail cantilever not more than 150mm
Powdercoat black rails used on Ground floor and under window sill
Hold Point | Substructure Sign off
Section | Brick to Click Installation
Brick install and free from damage
No major deformation in bricks
Rails is not exposed after brick install
Correct Color used on elevation
E01 - Colour Erdfeur
E02 - Color Kohleglanz
E03 - Color Kornbeige
E04 - Color Erdfeur , 37mm thick
External Mitre Corner Check
Internal Mitre corners check
All penetration to brick checks
Sika WS 605 S Sealant to external corners mitre edge
Brick gaps not more than 3mm
Hold Point | Brick Works Sign Off
Section | Final Checks
All Bricks Installed
Bricks free from any damages
Brick free from any debris
Final joint inspection
Hold Point | Sign off and handover