## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Bath Street Stormwater Renewal |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561466 |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council |  |  |  |  | B | Report by Breach | PE | Project Engineer | Nathan Bullin | NB
Contract Number: | 9240 |  |  |  |  | C | Check | CR | Cust. Representative | Rolly Hill | RH
Area/ Sub-System: | Zone 4/ Zone 3 |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[6 empty] | E | Examine | MC | Material Controller
ITP Number: | 4003 |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Installation of DN750 WC main from WCMH-5 to WCMH-4 |  |  |  |  | I | Inspection | PM | Project Manager | Mike Kemp | MK
Discipline: | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | Bath Street Upgrades Project - Specification Attachment A3 - Structural Concrete Specification Attachment B - Earthworks Reinstatement + Dewatering Standard Specification Attachment D - Concrete for Minor Works Standard Specification |  |  |  |  | O | Operation | QE | Quality Engineer | Calisa McLeary | CM
[6 empty] | R | Review | QM | QA Manager
Drawings: | C4201, C4200, S1301, C7000, S7001 |  |  |  |  | S | Subcontractor | SP | Supervisor | Mike Henderson James Howard | MH JH
[6 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Nathan Bullin |  | Date: | 2024-08-13 |  | W | Witness Point | SV | Surveyor | Eroni Vari | EV
Quality Specified: | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
3.1 | Material Delivery | Inspect for damage and wear, Confirm items are correct as per drawings and Specifications | -Pipes shall be DN600 Class 4 RCRRJ - Items are approved as per contract specification - DCC approved | Photos, delivery docket, MDD results for backfill materials (if required) | On Delivery | Visual | C | SV/QE
3.2 | Set out | Set out completed by an approved surveyor marked allignment | Allignment set out matches drawings or aggreed by the Engineer | Survey marks, photos | Prior to commencement of works | Visual, Instrumental | H | SV/SP/QE/PE

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Trench Excavation | - excavate to achieve required depth to invert as per C4200 - Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length | - Allow 100mm for bedding - Allow for minimum cover of 750mm. | Photos, measurement checks | During Installation | Visual | C | SP/QE/CM
4.2 | Geotextile | Install Bidim A29 or approved equivalient around bedding, haunch, overlay zone and trench fill up to the subbase. | Geotextile not damged during pipe installation and backfilling | photos | During Installation | Visual | C | SP/QE
4.3 | Foundation | Scala tests on base of trench | minimum of 2 blows per 100mm | test results | During installation, per 20m | Visual, On site test | H | SP/QE
4.4 | Install Pipe | - Pipe installed to grade as per drawing C4200 | - Pipe not damaged during installation - pipe installed to grade within tolerances specification GP 3.1.8 | Photos, Grade check sheet, Survey of position for asbuilt | During installation | Visual, instrumental | C | SP/QE
4.5 | Embedment zone | -Embedment material shall be AP20 or approved by the Engineer in writing | - min 100mm bedding - 150mm overlay | Photos | During Installation | Visual, measurement check | C | SP/QE
4.6 | Bacfill and Compact | - Backfill in 200mm layers of compacted material - Compaction testing one test every two layers as required - conductive signal strip to be laid at 300mm above pipe | 95% MDD in roads, paths, and pavements | Photos, Compaction test results | During Installation, compaction testing per 50m of pipeline or per straight section of pipeline | Visual, On Site test | H | SP/QE
4.7 | Reinstatement - 326 Floor | -DPM inplace -HD12 @ 250 ctrs, 600mm lond embedded 150mm. -Place SE72 mesh -follow detail 33 at change in floor level. -Pour 25mPa concrete | steel installed and poured in accordance with drawings. | Site Report | During installation, prior to pours. | Engineers Inspection | H, I | CR/PE
4.8 | Reinstatement - Carrigeway | - Match existing pavement thickness or minimum of 35mm. - Minimum depth of 250mm 28 day strength 20MPa concrete, R20 steel installed at 500mm ctrs, 250mm embedment and 250mm into excavation, placement of 665 steel mesh, coarse broom finish. -Place a tack coat. - Mix to be NZTA M/10: AC10 - Bandage seal | Asphalt installed as per the design | Photos | During Installation | Visual, Prepour inspection | C | PE/SP/QE
4.9 | Reinstatement - Footpath | - Match existing pavement thickness or minimum of 35mm. - minimum 75mm of basecourse. - Place a tack coat of 0.2-0.5 L/m². - Mix to be DG7 Asphaltic Concrete. - Bandage Seal | Asphalt installed as per the design | Photos | During Installation | Visual | C | PE/SP/QE
4.10 | Reinstatement - Kerb and Channel | - Length a minimum of 1m. - match existing grade. - Concrete strength 20MPa -Vertical joints at 3m intervals. | - Tolerances for kerb and channel and paving edge beam shall be +5mm vertically and E16+3mm horizontally. The deviation from a 4m straight edge shall not exceed 3mm | Photos |  | Visual, Pre Pour inspection | C | PE/SP/QE

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1 | CCTV | CCTV inspection to confirm pipeline conforms with specification | Pipeline will fail is any of the following is visible: - pipe misalignment or deformation more than 5% of the pipe diameter - dips or ponding of water inside the pipe - defects such as open joints, potruding laterals, cracked barrels, or similar | Test Records, CCTV footage | Every section of pipe completed | On-Site Test | H | SP/QE/CM/CR
5.2 | Leak Testing | Tested in the presence of the Engineer or their representative testing in accordance with AS/NZS 2566.2 Section 6.4 | Engineer Approval | Test Records | Every section of pipe installed | On-Site Test | H | SP/QE/CM/CR
5.3 | Red pen markups | Complete mark up of any changes from supplied drawings |  |  | After completion of pipe section |  |  | SP/QE/CM
5.4 | As built |  | Engineer Approval | QA records | at completion | Asbuilt drawings | H | PE/PM/SV
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: