## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-4001 - Brick Barrel Corbel Connection | itp |  |  |  |  | ITP-4001 - Brick Barrel Corbel Connection
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Pipes shall be DN750 Class 4 RCRRJ
label | ○ Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket, MDD results for backfill materials (if required)
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SV/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawings, 2D data and linework provided or aggreed with the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Visual, Instrumental
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/SP/QE/CM
holdpoint | HOLD POINT
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to achieve required depth to invert as per C4200, C4300, C4301
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of Trench to be even across width and length
label | Acceptance Criteria - Allow 100mm for bedding
label | ○ Allow for minimum cover of 750mm.
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE/CM
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - minimum of 2 blows per 100mm
label | Verifying Document - test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - Visual, On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.3 - Install corbell
label | Inspection Point: Quality Control Activity - pre pour inspection
label | Acceptance Criteria - Engineers approval to proceed
label | Verifying Document - Pre pour inspection form
label | Frequency - Prior to pour
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - I
label | Inspection: By (Role Key) - CR
checkpoint | 4.4 - Install Pipe
label | Inspection Point: Quality Control Activity - Pipe installed to grade as per drawing C4200, C4300, C4301
label | Acceptance Criteria - Pipe not damaged during installation
label | ○ Pipe installed to grade within tolerances specification GP 3.1.8
label | ○ Pipe installed at approved angle
label | Verifying Document - Photos, Grade check sheet, Survey of position for asbuilt
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, instrumental
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.5 - Embedment zone
label | Inspection Point: Quality Control Activity - Embedment material shall be AP20 or approved by the Engineer in writing
label | Acceptance Criteria - min 100mm bedding
label | ○ 150mm overlay
label | Verifying Document - Photos
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, measurement check
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | ○ Conductive signal strip to be laid at …mm cover
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - As built
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - QA records
label | Frequency - at completion
label | Inspection Type (Visual, other) - H
label | Inspection: Key - CM/PM
holdpoint | HOLD POINT
checklist | ITP-4002 - WCMH-5 | itp |  |  |  |  | ITP-4002 - WCMH-5
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket, MDD results for backfill materials
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawings or aggreed with the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Visual, Instrumental
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/SP/QE/PE
holdpoint | HOLD POINT
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4200
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of Trench to be even across width and length
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By (Role Key) - SP/QE/PE
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base
label | Acceptance Criteria - minimum of 2 blows per 100mm
label | Verifying Document - test results
label | Frequency - One off
label | Inspection Type (Visual, other) - Visual, On site test
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.3 - Bedding
label | Inspection Point: Quality Control Activity - Bedding minimum 75mm compacted material
label | Acceptance Criteria - Bedding to comply with requirements
label | Verifying Document - Photo
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, Measurement Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.4 - Chamber Installation
label | Inspection Point: Quality Control Activity - Chambers installed true to the design level
label | Acceptance Criteria - Final levels are in accordance with the drawings or within tolerance and agreed with the Engineer
label | Verifying Document - Photos
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, instrumental
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.5 - Benching
label | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days. All benching and sloping surfaces on manhole floor shall be rendered in 20mm thick 1:3 mortar
label | ○ Benching shape to have smooth transitions at bends and junctions
label | Acceptance Criteria - Benching built up to the specifications
label | Verifying Document - Photos
label | Frequency - During benching contruction
label | Inspection Type (Visual, other) - Visual, measurement check
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CR
holdpoint | HOLD POINT
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Leak Testing
label | Inspection Point: Quality Control Activity - Manholes to be water tested up to within 150mm of the concrete lid level.
label | Acceptance Criteria - The amount of water leakage from chamber under test shall not exceed 1/300 of the volume of the chamber during a 30 minute period
label | Verifying Document - Photos, test records
label | Frequency - For every manhole
label | Inspection Type (Visual, other) - Test, visual
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/PE/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - As built
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - QA records
label | Frequency - at completion
label | Inspection Type (Visual, other) - Asbuilt drawings
label | Inspection: Key - H
label | Inspection: By (Role Key) - PE/PM/SV
holdpoint | HOLD POINT
checklist | ITP-4003 - DN750 WC main WCMH-5 to WCMH-4 | itp |  |  |  |  | ITP-4003 - DN750 WC main WCMH-5 to WCMH-4
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Pipes shall be DN600 Class 4 RCRRJ
label | ○ Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket, MDD results for backfill materials (if required)
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SV/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawings or aggreed by the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Visual, Instrumental
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/SP/QE/PE
holdpoint | HOLD POINT
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to achieve required depth to invert as per C4200
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of Trench to be even across width and length
label | Acceptance Criteria - Allow 100mm for bedding
label | ○ Allow for minimum cover of 750mm.
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE/CM
checkpoint | 4.2 - Geotextile
label | Inspection Point: Quality Control Activity - Install Bidim A29 or approved equivalient around bedding, haunch, overlay zone and trench fill up to the subbase.
label | Acceptance Criteria - Geotextile not damged during pipe installation and backfilling
label | Verifying Document - photos
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.3 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - minimum of 2 blows per 100mm
label | Verifying Document - test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - Visual, On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.4 - Install Pipe
label | Inspection Point: Quality Control Activity - Pipe installed to grade as per drawing C4200
label | Acceptance Criteria - Pipe not damaged during installation
label | ○ Pipe installed to grade within tolerances specification GP 3.1.8
label | Verifying Document - Photos, Grade check sheet, Survey of position for asbuilt
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, instrumental
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.5 - Embedment zone
label | Inspection Point: Quality Control Activity - Embedment material shall be AP20 or approved by the Engineer in writing
label | Acceptance Criteria - min 100mm bedding
label | ○ 150mm overlay
label | Verifying Document - Photos
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, measurement check
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.6 - Bacfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | ○ Conductive signal strip to be laid at 300mm above pipe
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.7 - Reinstatement - 326 Floor
label | Inspection Point: Quality Control Activity - DPM inplace
label | ○ HD12 @ 250 ctrs, 600mm lond embedded 150mm.
label | ○ Place SE72 mesh
label | ○ Follow detail 33 at change in floor level.
label | ○ Pour 25mPa concrete
label | Acceptance Criteria - steel installed and poured in accordance with drawings.
label | Verifying Document - Site Report
label | Frequency - During installation, prior to pours.
label | Inspection Type (Visual, other) - Engineers Inspection
label | Inspection: Key - H, I
label | Inspection: By (Role Key) - CR/PE
holdpoint | HOLD POINT
checkpoint | 4.8 - Reinstatement - Carrigeway
label | Inspection Point: Quality Control Activity - Match existing pavement thickness or minimum of 35mm.
label | ○ Minimum depth of 250mm 28 day strength 20MPa concrete, R20 steel installed at 500mm ctrs, 250mm embedment and 250mm into excavation, placement of 665 steel mesh, coarse broom finish.
label | ○ Place a tack coat.
label | ○ Mix to be NZTA M/10: AC10
label | ○ Bandage seal
label | Acceptance Criteria - Asphalt installed as per the design
label | Verifying Document - Photos
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, Prepour inspection
label | Inspection: Key - C
label | Inspection: By (Role Key) - PE/SP/QE
checkpoint | 4.9 - Reinstatement - Footpath
label | Inspection Point: Quality Control Activity - Match existing pavement thickness or minimum of 35mm.
label | ○ Minimum 75mm of basecourse.
label | ○ Place a tack coat of 0.2-0.5 L/m².
label | ○ Mix to be DG7 Asphaltic Concrete.
label | ○ Bandage Seal
label | Acceptance Criteria - Asphalt installed as per the design
label | Verifying Document - Photos
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - PE/SP/QE
checkpoint | 4.10 - Reinstatement - Kerb and Channel
label | Inspection Point: Quality Control Activity - Length a minimum of 1m.
label | ○ Match existing grade.
label | ○ Concrete strength 20MPa
label | ○ Vertical joints at 3m intervals.
label | Acceptance Criteria - Tolerances for kerb and channel and paving edge beam shall be +5mm vertically and E16+3mm horizontally. The deviation from a 4m straight edge shall not exceed 3mm
label | Verifying Document - Photos
label | Inspection Type (Visual, other) - Visual, Pre Pour inspection
label | Inspection: Key - C
label | Inspection: By (Role Key) - PE/SP/QE
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - CCTV
label | Inspection Point: Quality Control Activity - CCTV inspection to confirm pipeline conforms with specification
label | Acceptance Criteria - Pipeline will fail is any of the following is visible:
label | ○ Pipe misalignment or deformation more than 5% of the pipe diameter
label | ○ Dips or ponding of water inside the pipe
label | ○ Defects such as open joints, potruding laterals, cracked barrels, or similar
label | Verifying Document - Test Records, CCTV footage
label | Frequency - Every section of pipe completed
label | Inspection Type (Visual, other) - On-Site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Leak Testing
label | Inspection Point: Quality Control Activity - Tested in the presence of the Engineer or their representative testing in accordance with AS/NZS 2566.2 Section 6.4
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Test Records
label | Frequency - Every section of pipe installed
label | Inspection Type (Visual, other) - On-Site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.3 - Red pen markups
label | Inspection Point: Quality Control Activity - Complete mark up of any changes from supplied drawings
label | Frequency - After completion of pipe section
label | Inspection Type (Visual, other) -
label | Inspection: By (Role Key) - SP/QE/CM
checkpoint | 5.4 - As built
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - QA records
label | Frequency - at completion
label | Inspection Type (Visual, other) - Asbuilt drawings
label | Inspection: Key - H
label | Inspection: By (Role Key) - PE/PM/SV
holdpoint | HOLD POINT