## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1211-001 ITP Stormwater Rev 0 | itp |  |  |  |  | DN1211-001 ITP Stormwater Rev 0
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JSEA to the Engineer before works
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 5 days prior to commencement of works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.02.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.02 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.02.03 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.03 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.02.04 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Concrete pipes
label | Acceptance / Conformance Criteria - RC pipes shall comply with AS/NZS 4058 for the class nominated on the drawings.
label | ○ Pipes shall be rubber ring jointed unless otherwise shown on the drawings and rubber rings shall comply with AS1646.
label | Standard / Specification - Aurecon Civil Spec Section 17.11.1
label | Verifying Document - Material Certificate / Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - DES
checkpoint | 4.01.02 - uPVC pipes
label | Acceptance / Conformance Criteria - uPVC pipes shall comply either with AS/NZS 1254 or AS/NZS 1260 and have the minimum strength as detailed on drawings
label | ○ Pipe joints to be factory‐made spigot and socket, flexible type
label | Standard / Specification - Aurecon Civil Spec Section 17.11.3
label | Verifying Document - Material Certificate / Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - DES
checkpoint | 4.01.03 - PE Pipe – Profile Wall
label | Acceptance / Conformance Criteria - PE pipe to be used in gravity situations shall be PE100 Profile Wall pipe to AS/NZS 5065.
label | Standard / Specification - Aurecon Civil Spec Section 17.11.2
label | Verifying Document - Material Certificate / Datasheets
label | Frequency - Prior to works
label | Verification Activity: Activity - R
label | Verification Activity: By - DES
checkpoint | 4.01.04 - Other Specialised Materials
label | Acceptance / Conformance Criteria - All other pipes and pipe fittings supplied as per drawings, including:
label | ○ Any Mortar Lined Mild Steel (MLMS) pipes manufactured from arc buttwelded steel tube with external black HDPE coating. Pipes joints to be flanged, welded hemispherical joints or jointed with welding bands.
label | ○ Gibault Joints assembled as per manufacturers recommendations
label | ○ Flanged Joints made with moulded rubber gaskets or jointing rings as per spec. All proprietary products supplied and installed as per manufacturers instructions.
label | Standard / Specification - Aurecon Civil Spec 17.11.5,17.11.6
label | Verifying Document - Material Certificate / QA Sheets
label | Frequency - Prior to Use
label | Verification Activity: Activity - R
label | Verification Activity: By - DES
checkpoint | 4.01.05 - Concrete
label | Acceptance / Conformance Criteria - Any structural concrete or mortar mix requirements as per Section 14 of this civil spec.
label | ○ Site concrete used for pipe bedding to be 1 part cement to 7 parts AP20 with water as required to produce firm, moist mix with min 10MPa 28‐day strength
label | ○ Arrange pre‐pour inspection with Engineer 1 day prior
label | Standard / Specification - Aurecon Civil Spec Section 14,17.11.7
label | Verifying Document - Supplier Records, Concrete Dockets
label | Frequency - As required
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.01.06 - Pipe Bedding and Backfill Material
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
label | Standard / Specification - Aurecon Civil Spec 17.12.15 TNZ M/4 Asset Owner Specifications
label | Verifying Document - Material Certificate / QA Sheets
label | Frequency - Prior to Use
label | Verification Activity: Activity - H
label | Verification Activity: By - DES
checkpoint | 4.01.07 - Catchpits, manholes, and drainage structures
label | Acceptance / Conformance Criteria - Manhole, catchpit & service pit frames and covers supplied and set to correct grade and finished level as per drawing details.Pre‐cast items manufactured and supplied as per NZ standards. Manhole segments to be minimum 20Mpa
label | ○ Manhole/service biscuits to be level with top of subbase.
label | ○ Re‐entrant corners require trimmer bars as detailed on drawings
label | Standard / Specification - Aurecon Civil Spec; Section 17.11.16-18
label | Verifying Document - QA Checksheet and Supplier Records
label | Frequency - Prior to place pavement concrete
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 4.01.08 - Step Irons - Access Ladders
label | Acceptance / Conformance Criteria - Check if amended by Drawings to be Type 316 Stainless Steel or Plastic Coated.
label | ○ Otherwise, Step irons shall be “safety type” 24mm dia mild steel to the dimension shown on the Drawings, galvanised after fabrication at the rate of 0.7 kg/m2.
label | ○ Installation shall generally comply with section 5.7 of AS/NZS 1657 except that ladder cages shall not be fitted
label | Standard / Specification - Aurecon Civil Spec Section 17.11.19
label | Verifying Document - Supplier Records and QA checksheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | SECTION 5 – CONSTRUCTION ACTIVITY – DRAINAGE INSTALLATION
checkpoint | 5.01.01 - Protecton of Piplines
label | Acceptance / Conformance Criteria - During construction, the Contractor shall be responsible for the protection of all existing and new pipework.
label | Standard / Specification - Downer
label | Verifying Document - QA Checksheet
label | Frequency - Daily
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 5.01.02 - Depth of Cover
label | Acceptance / Conformance Criteria - The minimum cover as detailed on the drawings.
label | ○ If minimum cover cannot be achieved notify Engineer and provide adequate protection to the satisfaction of the Engineer.
label | Standard / Specification - Aurecon Civil Spec Section 17.13.17
label | Verifying Document - Site Record
label | Frequency - During Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 5.01.03 - Length of Open Trench
label | Acceptance / Conformance Criteria - The length of open trench shall not exceed the greater of one manhole length or 30m and when offsite this open trench shall be reduced to a maximum length of not more than 10 metres.
label | Standard / Specification - Aurecon Civil Spec Section 17.13.3
label | Verifying Document - QA Checksheet
label | Frequency - Daily
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 5.01.04 - Trench Dimensions
label | Acceptance / Conformance Criteria - Excavate trench to lines, levels, width and gradients shown on drawings.
label | ○ Trench of sufficient width to permit installation of all materials and fittings.
label | ○ Pipes minimum 100mm from trench wall.
label | ○ Trench width <600mm pipe diameter at top of pipe level.
label | Standard / Specification - Aurecon Civil Spec Section 17.13.4
label | Verifying Document - QA Checksheet
label | Frequency - Every 10m
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 5.01.05 - Keeping the Excavation Free of Water
label | Acceptance / Conformance Criteria - Subsoil water shall be kept below the metal foundation
label | Standard / Specification - Aurecon Civil Spec Section 17.13.5
label | Verifying Document - Site Record
label | Frequency - Daily
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 5.01.06 - Trench Subgrade
label | Acceptance / Conformance Criteria - Trench subgrade to be inspected to assess if suitable for pipe laying or construction to proceed. Advise Engineer if unsuitable
label | Standard / Specification - Aurecon Civil Spec Section 17.13.9
label | Verifying Document - QA Checksheet
label | Frequency - Prior to pipe laying
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.02.01 - Line and Level
label | Acceptance / Conformance Criteria - Pipes laid to line +/‐25mm, grade and invert level shown on drawings. Lateral tolerance +/‐25mm from centreline between manholes or change in grade.
label | ○ Engineer notified prior to pipe laying.
label | ○ No pipe laying shall be carried out without Engineer being notified 24 hours prior
label | Standard / Specification - Aurecon Civil Spec Section 17.13.16
label | Verifying Document - QA Checksheet
label | Frequency - Before Backfill
label | Verification Activity: Activity - HP
label | Verification Activity: By - DES
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.02 - Cleanliness
label | Acceptance / Conformance Criteria - Internal pipe walls shall be kept clean and free of all dirt, rubbish and water. Spigots, sockets, rubber rings, etc. shall be thoroughly cleaned before jointing.
label | ○ Pipe condition inspected prior to laying and line checked prior to backfilling
label | Standard / Specification - Aurecon Civil Spec Section 17.13.16
label | Verifying Document - QA Checksheet
label | Frequency - Before Backfill
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.02.03 - Bedding and Haunching
label | Acceptance / Conformance Criteria - AP<12 granular bedding material.
label | ○ Any sand used must be clean and well‐graded
label | ○ Bedding and Haunching ‐ Clegg Hammer test minimum CIV of 12.
label | ○ Results to be attached to checklist with photos.
label | Standard / Specification - Aurecon Civil Spec 17.13.15
label | Verifying Document - QA Checksheet
label | Frequency - Every 10m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.02.04 - Backfill Placement
label | Acceptance / Conformance Criteria - Subbase quality AP65 granular backfill material to be used. Backfill and compact in 200mm layers.
label | ○ Clegg Hammer test minimum CIV of 25.
label | ○ Results and photos to be attached to checklist with photos.
label | Standard / Specification - Aurecon Civil Spec 17.13.15
label | Verifying Document - QA Checksheet
label | Frequency - Every 10m, in 1m lifts
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.03.01 - Alignment
label | Acceptance / Conformance Criteria - Structures shall be positioned within 50mm horizontally of the location specified. All structures shall be watertight.
label | Standard / Specification - Aurecon Civil Spec 17.13.18
label | Verifying Document - Survey
label | Frequency - Each Manhole / Sump
label | Verification Activity: Activity - C
label | Verification Activity: By - SV
checkpoint | 5.03.03 - Drainage Structure Bedding
label | Acceptance / Conformance Criteria - Unless specified otherwise, all catchpits, manholes and other stormwater structures shall be founded on a minimum 150 mm bedding.
label | Standard / Specification - Aurecon Civil Spec 17.13.18
label | Verifying Document - Site Records
label | Frequency - Each Structure
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 5.03.04 - Structure Backfill Testing
label | Acceptance / Conformance Criteria - Subbase quality AP65 granular backfill material to be used. Backfill and compact in 200mm layers.
label | ○ Clegg Hammer test minimum CIV of 25.
label | ○ Results and photos to be attached to checklist with photos.
label | Standard / Specification - Aurecon Civil Spec 17.13.18
label | Verifying Document - QA Checksheet
label | Frequency - One test every two layers per manhole
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 5.03.05 - Pipe Penetrations
label | Acceptance / Conformance Criteria - Pipe penetrations shall be formed by drilling holes around the line of cut before knocking the section out.
label | Standard / Specification - Aurecon Civil Spec 17.13.18
label | Verifying Document - Photo
label | Frequency - Each Structure
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.03.06 - Benching
label | Acceptance / Conformance Criteria - The concrete shall be rendered to a smooth finish and shall slope towards the channel. Particular care shall be taken to create smooth transitions at bends and junctions. Benching is to be in accordance with the drawings.
label | Standard / Specification - Aurecon Civil Spec 17.13.18
label | Verifying Document - Photo
label | Frequency - Each Structure
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.03.07 - Corbels
label | Acceptance / Conformance Criteria - Pipes shall be haunched and surrounded with concrete to a minimum distance of 200mm from the outside of the manhole in accordance with the drawings.
label | Standard / Specification - Aurecon Civil Spec 17.13.18
label | Verifying Document - Photo
label | Frequency - Each Pipe Entry
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.03.08 - Pipe ends
label | Acceptance / Conformance Criteria - Pipe ends shall finish approximately 50mm beyond the inside wall and be plastered with cement mortar or encased in benching concrete in accordance with the drawings.
label | Standard / Specification - Aurecon Civil Spec 17.13.18
label | Verifying Document - Photo
label | Frequency - Each Pipe Entry
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.04.01 - Pipeline Testing
label | Acceptance / Conformance Criteria - Pressure test wastewater and stormwater pipes; PVC, steel, GRP, ductile iron and PE pipelines, rising mains and connections for water tightness.
label | ○ As‐built location of all manholes, surface level of manhole lids, depth to invert of outlet pipes, junction locations relative to downstream manholes
label | ○ The Test must be witnessed by the Engineer or their representative. A record of all tests shall be made and forwarded to the Engineer within 24 hours of test completion.
label | Standard / Specification - Aurecon Civil Spec Section 17.12.22 NZS 2566.2; Section 6.3.4.1 & 6.3.4.2
label | Verifying Document - Test Report
label | Frequency - Each Pipeline
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.04.03 - CCTV Inspection
label | Acceptance / Conformance Criteria - Lines fully flushed immediately prior to CCTV inspection.
label | ○ Inspect pipelines for correct line and grade between manholes. Pipes to be checked for visible infiltration and debris. CCTV submitted and reviewed by Engineer.
label | Standard / Specification - Aurecon Civil Spec Section 17.12.23 NZS 2566.2; Section 6.3.4.1 & 6.3.4.2
label | Verifying Document - CCTV Logsheet and Video
label | Frequency - Each Pipeline
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.04.04 - Manhole Testing
label | Acceptance / Conformance Criteria - Manholes and pipelines shall be checked for infiltration. Visible leakage in manholes and pipelines shall be rectified prior to acceptance.
label | ○ Stormwater Manholes shall be free of visible faults or permeable zones and jointing or penetration repairs shall be to best trade standards
label | Standard / Specification - Aurecon Civil Spec Section 17.12.22 NZS 2566.2; Section 6.3.4.1 & 6.3.4.2
label | Verifying Document - Test Report
label | Frequency - Each Pipeline
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Construction Record Compilation
label | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.01.02 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 6.01.03 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 6.01.04 - Defect, Snag and Punch List
label | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | Standard / Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checklist | DN1211-CHK-001 Stormwater Drainage Quality Check Sheet | itp |  |  |  |  | DN1211-CHK-001 Stormwater Drainage Quality Check Sheet
section | Materials
checkpoint | Materials available and comply with specs (all materials)
label | Comments - Sent to design engineer for review
section | Excavation
checkpoint | Has the permit to excavate been completed
label | Comments - Services clearly identified (Both KR and DNZ)
label | ○ NUO standover on site if required
checkpoint | Set out complete
label | Comments - As per IFC Civil Drawings
checkpoint | Protection of existing pipelines / utilities
checkpoint | Trench excavation to line, level and grade
label | Comments - Every 10m
label | ○ To lines, levels, gradient as shown on drawings
label | ○ Sufficient width to permit installation, pipes minimum 100mm from trench wall
label | ○ Width ,<600mm greater than pipe diameter
checkpoint | Trench excavation open length
label | Comments - Not to exceed manhole length or 30m
checkpoint | Materials removed and stock piled
checkpoint | Bottom of trench foundation condition
label | Comments - Water ingress kept below bedding level
label | ○ Subgrade suitable for pipe laying
checkpoint | Over excavation required?
label | Comments - Engineer to be notified and approval received prior to undercut.
holdpoint | HOLD POINT
section | Pipe Installation
checkpoint | Hold point
label | Comments - Engineer to be notified 24hrs prior to pipe laying
holdpoint | HOLD POINT
checkpoint | Pipes transported to site , stored and lifted correctly to prevent damage
checkpoint | Trench shield/Benched/battered
label | Comments - If the trench is deeper than 1.5m
checkpoint | Line and level
label | Comments -
textbox | Design:
textbox | Achieved:
checkpoint | Cleanliness and condition
label | Comments - Internal pipe and joints clean and free of dirt/debris
label | ○ Pipe condition inspected prior to backfilling
checkpoint | Bedding and Haunching
label | Comments - AP<12 granular bedding material
label | ○ Clegg hammer tests (every 10m, min CIV 12)
label | ○ Clegg Results:
checkpoint | Temporary capping of end of pipes
checkpoint | Backfill Placement
label | Comments - AP>40 granular bedding material
label | ○ Clegg hammer tests (every 10m, min CIV 25)
label | ○ Compacted in 200mm layers
textbox | Clegg Results:
section | Manhole Installation
checkpoint | Alignment
label | Comments - Correct position (<50mm)
label | ○ Vertical
checkpoint | Bedding
label | Comments - Bedding material – min 150mm
label | ○ Clegg hammer tests (min CIV 12)
textbox | Clegg Results:
checkpoint | Backfill Placement
label | Comments - AP>40 granular bedding material
label | ○ Clegg hammer tests (min CIV 25)
label | ○ Compacted in 200mm layers
textbox | Clegg Results:
checkpoint | Penetrations
label | Comments - Formed by cutting or drilling prior to knocking section out
checkpoint | Pipe Ends
label | Comments - Finished approx. 50mm beyond inside wall
label | ○ Plastered with cement mortar or encased in benching concrete
checkpoint | Corbels
label | Comments - Pipes haunched and surrounded by concrete by >200mm from manhole
checkpoint | Benching
label | Comments - Smooth finish, graded to channel, in accordance with drawings
checkpoint | Works completed as per design requirements and work area is ready to be handed over for sign-off
holdpoint | Signed by Sub contractor Representative
checkpoint | Final Approvals
textbox | DNZ Check - Name:
date | DNZ Check - Date:
textbox | Engineer / Consultant - Name:
date | Engineer / Consultant - Date:
holdpoint | Sign-Off