## ITP-002
|  |  | Inspection and Test Plan - Bored Piling | [7 empty] | Document # ITP-002
Revision : 1
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Spout Creek Bridge Replacement |  | Cast-in-place socketed piles (with permanent casing) |  | Name: | Jarrod Rodrigues | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: |  | DOT33479 |  | Specifications: VicRoads Standard Sections 608, 610, 611
|  |  |  | Structure / Component: Piles at Bridge Abutment |  | Signed: |  | Signed: |  |  | Signed:
|  |  |  | Location: Great Ocean Road |  | Date: | 2024-07-25 | Date: | 2024-08-05 |  | Date: | 2024-08-05
Lot No: | 1 |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings. | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP | QMP, TMP, JSEA, SWMS, WP | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Materials |  | Prior to commencing any activity | The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS. Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing. Ensure that materials on-site are sufficient for the completion of works. | Design Drawings, VR Section 610 & 611 | Document Review | ITP Signed, Test Certificates, Material Data Sheets. | HP | Project Engineer/ Superintendent |  |  | N/A
2 | Construction Works
2.1 | Indentification of Services |  | Prior to commencing any activity | Ensure any underground service locations have been identified and marker on-site. Ensure any required approvals/permits have been received by service authorities prior to commencing works. | DBYD | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.2 | Set Out of Piles |  | Each Lot | The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. | Design Drawings & Survey Data | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.3 | Protection of Adjacent Piles |  | Each Lot | No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained the strength of 15 Mpa. | VR Section 608.05 | Visual Inspection | ITP Signed | WP | Project Engineer | N/A |  | N/A
2.4 | Inspection of Piles |  | Each Lot | The rock sockets should be constructed in full-time presence of a Geotechnical Engineer who can confirm that the design sub-surface strength parameters are appropriate and provide advice if unexpected conditions are encountered. Following formation of the socket, the pile shall be de‑watered to enable inspection by the Superintendent (or the Contractor’s geotechnical representative in design and construct contracts) of the geology of the sides and base of the socket and to ensure that the base is free of debris. Reinforcement and/or concrete shall not be placed prior to this inspection. | VR Section 608.04 Design Drawings | Visual inspection | ITP Signed | HP | Project Engineer/ Geotechnical Engineer/ Superintendent
2.5 | Placement of Steel Reinforcement |  | Each Lot | Ensure steel reinforcement complies with the relevant specification and design drawings. Spacers and supports to be placed at intervals less than 2m along cages to ensure minimum cover. Ensure 75mm cover on all reinforcement unless noted otherwise on the design drawings. Ensure 75mm cover to CHS steel casing as denoted on the design drawings. | VR Sections 608 & 611 / Design Drawings | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.6 | Placement of Concrete |  | Each Lot | Ensure concrete being used for bored piles complies with the relevant specification and design drawings. During concreting, the outlet of the tremie pipe or pump discharge hose shall be kept a minimum of 2m below the top surface of the concrete at all times. If water is in the socket, the socket shall be backfilled with concrete tremied from the base of the hole. Concreting shall be continued until sound concrete appears a minimum of 400mm above the required cut-off level. The pile concrete shall not be cut back to its required level until a mimimum of 24 hours after completion of placement of concrete. Concrete placed under water shall be self compacting concrete (SCC) in accordance with the requirements of clause 610.07, clause 610.13 and clause 610.18(c). The concrete shall be of such consistency, and shall be placed in such a manner, that pockets of air or water or ground materials are not entrapped in the concrete, and the space between the reinforcement and the side walls of the hole are completely filled with compacted concrete. | VR Section 608.07 / Design Drawings | Visual inspection | ITP Signed | HP | Project Engineer | N/A |  | N/A
3 | Quality Control Testing
3.1 | Concrete Testing |  | Each Lot | All concrete shall be sampled and tested in accordance with AS 1012. The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard. | VR Section 610.16 | Test Point | ITP Signed | HP* | Project Engineer | N/A |  | N/A
3.2 | Pile Integrity Testing |  | First six piles followed by every third pile thereafter. | Integrity testing shall be carried out in accordance with test methods specifed in AS 2159. All testing shall be undertaken by a prequalified consultant in accordance with the VR scheme for prequalificaiton and approval of the Superintendent. The contractor shall provide details of the pile testing consultant to the Superintendent for review at least 2 weeks prior to the testing. Integrity testing shall not be carried out until the concrete has achieved a compressive strength of 25MPa and not before 7 days after casting of the pile. | VR Section 608.08 | Test Point | ITP Signed | HP | Project Engineer/ Superintendent |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.