## ITP-008
|  |  | Inspection and Test Plan - Crushed Rock Class 3 | [7 empty] | Document # ITP-008
Client: | DTP |  | Construction Process: | Placement of Crushed Rock |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Spout Creek Bridge Replacement |  | Specifications: | VicRoads Specifications Section 173, 204, 304 & 812 |  | Name | Jarrod Rodrigues | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT33479 |  | Structure / Component: | Earthworks/Civil |  | Signed: |  | Signed: |  |  | Signed:
|  |  | Location: | Great Ocean Road |  | Date: | 2024-07-31 | Date: | 2024-08-05 |  | Date: | 2024-08-05
Lot No: |  |  | Lot Title: |  | Location: From ( ) to ( ) |  |  | Lot Size/ Quantity: |  |  | Lot Opened Date:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to Commencing | Ensure that all employees and subcontractors are using the correct, complete and most up-to-date revision of the design drawings. | Drawings and Drawings Register | Visual Inspection | Signed ITP | HP* | Site Engineer | N/A |  | N/A
1.2 | Material Mix Design |  | Prior to Commencing | Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175. | Cl.812.04 | Document review | Mix Design Approval | HP | Site Engineer & Superintendent |  |  | N/A
1.3 | Implementation of all measures and controls |  | Prior to Commencing | All necessary measures and controls are being implemented, that is: EMP, ECP, ERA, QMP, SWMS. | IFC Drawings EMP, ECP, ERA, QMP, SWMS. | Document review & Site inspection | Signed ITP | HP* | Site Engineer / Site Foreman | N/A
2 | Placing Fill
2.1 | Transverse Joints |  | Check prior to placing material | Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres | VicRoads Spec. Cl.304.08 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.2 | Longitudinal Joints |  | Check prior to placing material | Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane. | VicRoads Spec. Cl.304.08 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.3 | Lot Size |  | Check prior to placing material | A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser. | VicRoads Spec. Cl.304.09 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.3 | Layer Thickness |  | Each Lot | The maximum thickness of any pavement base layer shall not exceed 150mm and the maximum thickness of any subbase layer shall not exceed 200mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material. | VicRoads Spec. Cl.304.09 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.4 | Proof Roll |  | Proof roll each layer | No visible deformation or spinging in presence of Superintendent's representative. Proof rolling plant to comply with requirements of Cl. 173.03. | VicRoads Spec. Cl. 173 | Site Inspection | Signed ITP | HP/ WP | Site Engineer & Superintendent |  |  | N/A
3 | Testing Requirements
3.1 | Determine Testing Scale & Initial testing frequency |  | Prior to Testing | Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement. Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111. | VicRoads Spec. Table 204.161 VicRoads Spec. Cl.304.11 Cl.304.12 | Document Review/ Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.2 | Compaction Testing |  | Every lot, every second lot (reduced frequency) | Characteristic Value of Density Ratio for Subbase:- > 98.0% (Scale A) 6 lot test Initial FrequencyTest No. ________- > 97.0% | VicRoads Spec. Cl.304.09 | Site Inspection | ITP Signed, Test Reports | TP | Site Engineer | N/A |  | N/A
3.3 | Material Grading - Post Compaction |  | Every lot, every second lot (reduced frequency) | Post compaction material grading results must comply with the following: - Class 4: N/A - Class 3 - As per Table 304.101 VR Spec. - Class 2 - As per Table 304.101 - VR Spec. | VicRoads Spec. Cl.304.11 Table 304.111 | Test Point | ITP Signed, Test Reports | TP | Site Engineer | N/A |  | N/A
3.4 | Plasticity Index - Post Compaction |  | Every lot, every second lot (reduced frequency) | Post compaction PI results must comply with the following: - Class 4: N/A - Class 3: 0 to 10. - Class 2 - 0 to 6. | VicRoads Spec. Cl.304.11 Table 304.113 | Test Point | Test Records | TP | Site Engineer | N/A |  | N/A
3.5 | Survey Conformance |  | At completion | Layer to be finished smooth and uniform surface and after compaction shall conform within the following limits: Shape: No point deviation > 8mm from 3m straight edge in any direction. Surface level tolerance: Range x = +6, -10mm. Max S = 10mm | VicRoads Spec. Table 304.071 Table 304.072 | Survey | Test Records | SCP | Site Engineer/ Surveyor | N/A |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent