## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Concrete Inspection Sheet |  | Concrete Inspection Sheet |  | 4eeef0f5-a5b7-4e0a-a650-8efdacf3bc90
| section | Formwork
| checkpoint | Adequately braced and supported
| checkpoint | Grout tight
| checkpoint | Correct dimensions
| checkpoint | Cleaned and oiled
| checkpoint | Formed surfaces straight
| checkpoint | Major penetrations located
| checkpoint | Embedded items located
| checkpoint | Correct for specified surface finish
| checkpoint | Adequate seating for precast units
| checkpoint | Permit to load obtained
| section | Reinforcement
| checkpoint | Reinforcement content and size
| checkpoint | Confirm correct grade and markings
| checkpoint | Placement, tolerance, clearance
| checkpoint | Rigidity and cover
| checkpoint | Clean steel
| checkpoint | Lap length and location
| checkpoint | Starters/dowels correctly located
| section | Construction joints
| checkpoint | Location
| checkpoint | Roughened
| checkpoint | Clean
| checkpoint | Water bar placed if specified
| section | Post pour
| checkpoint | Correct mix ordered
| checkpoint | Independent survey - check off critical survey points
| checkpoint | Engineers rep notified
| section | Wet concrete checks
| checkpoint | Correct mix delivered
| checkpoint | Slump/flow targets
| checkpoint | Compliance cylinders taken
| checkpoint | Site cured cylinders taken
| checkpoint | Concrete vibrated
| checkpoint | Finished level: finished to grout check/ angle fillet worked to
| checkpoint | Surface to required finish eg u2, u4
| checkpoint | Retarded applied at end of the pour
| checkpoint | Curing applied (type)
| checkpoint | Concrete supply dockets collected
| section | Post concrete inspection
| checkpoint | Curing carried out correctly
| checkpoint | Concrete strength for striking
| checkpoint | Concrete strength for backfilling
| checkpoint | Preparation of construction joints completed
| checkpoint | Blow holes, tie bar holes filled
| checkpoint | Inspection of surfaces & any authorised repairs have been completed
| checkpoint | As-built complete
| section | Sign off
| checkpoint | Pre pour checked and accepted
| checklist | Quality Control Checklist - Reinforced Concrete Piles |  | Quality Control Checklist - Reinforced Concrete Piles |  | 8dce06b9-9eee-4302-bf17-8fe3a2a7ccbf
| section | 1.0 Preliminary Inspections and Tests
| checkpoint | 1.1 Design and Drawings are of 100% Detail Design Status
7f488894-42b0-54e0-9dd5-d8b67bd905e2 | note | HP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 Construction methodology
4f902149-0c38-57bb-b33d-3b9bfdc9672f | note | HP
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Approved Materials
| checkpoint | 2.1 Reinforcing Cages
58f4e046-fc24-5a9d-9be7-16433a7e3fd9 | note | HP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Welding
f33d062e-3188-558f-83a9-51bd7fedca51 | note | HP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Concrete Mix Design
1ffae852-9726-5c76-8e34-dd1b0877bae6 | note | HP
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 Set-out
| checkpoint | 3.1 Set out and survey
bb0dec92-50d3-5c4b-8ec7-d263bc7786f7 | note | HP
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 Construction Stage
| checkpoint | 4.1 Reinforcing cages
6dad3f77-1c36-5c99-b3ef-1cc6413db76b | note | RR
| checkpoint | 4.2 Concrete Delivery
1603bf1f-698e-5ebe-87c8-881185988190 | note | RR
| checkpoint | 4.3 Pile Installation/ Founding level
2f522a47-b4aa-5671-afd8-3642315e3633 | note | HP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 Concrete Placing
bdfdc1e5-7294-55af-8438-e0e36bd500a2 | note | RR
| section | 5.0 Completion Inspections and Tests
| checkpoint | 5.1 Warranty and producer statements requested in specs compliance information
29d3152a-a0e5-500f-be69-6ba26e077f3e | note | HP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 Complete set of As-built information
df6ff84f-3bcf-57c6-9bdd-b21d7f43d267 | note | RR
| section | Work Completed
| checkpoint | Work Completed - SDC
0980130a-538d-5716-8ae4-dc1ae427bf26 | note | The above items have been inspected and are in accordance with the drawings and specifications. All documentation as required by Specification is included in this Lot.
e4bc9366-cdfa-5433-820c-906f3897284f | textbox | Name:
a6b3232a-f09d-5097-82e6-c67a952de324 | textbox | Position Title:
08b48a70-f525-514e-97bf-673fda84e952 | textbox | Company:
| signoff | Add Signature
| checkpoint | Work Completed - UCC
8ddccd8e-8ab6-5e7c-bd26-6cb07cea2197 | note | The above items have been inspected and are in accordance with the drawings and specifications. All documentation as required by Specification is included in this Lot.
bdc268fe-79e1-53ab-a510-41adcade9b88 | textbox | Name:
d7bbd5dc-b66e-526d-8229-507b54964ce0 | textbox | Position Title:
c6639f74-5c1a-5a19-8c5b-571369d769ab | textbox | Company:
| signoff | Add Signature
| checklist | SDC-ITP-J7893 - Reinforced Concrete Piling |  | SDC-ITP-J7893 - Reinforced Concrete Piling |  | be33393e-5587-4112-862b-69ea7bbad74d
| section | 1.0 - Preliminary Inspections and Tests
| checkpoint | 1.1 - Design and Drawings are of 100% Detail Design Status
1577c375-3128-5bdf-965b-b5ddd88a4b9c | note | Responsibility - Spiral Drillers Engineer
ea2480f8-a0ac-5980-95a2-d24a6ed3e44d | note | Spec Reference - N.A
17a3ef00-4f8a-567f-810b-f79c46f9d82a | note | Conformance Criteria Summary - Latest Issue Design Drawings issued via email
b95b1378-1ca3-5ed7-86c6-e158d8d924e9 | note | Method - Document review/ document control
aedb75c5-9892-5650-888c-963dc0d9f48e | note | Frequency - Prior to Start of work
dcd64d88-24aa-5cdf-9884-9e5d7d9ca700 | note | Hold/Witness Requirements: SD C - HP
d6df719b-db2d-56fa-9a59-1dc2aca2d598 | note | Hold/Witness Requirements: UC C - IP
ea7f4c66-3b5e-5624-8acb-1a43c5bf8774 | note | Records or Checklist Reference - SD Quality Control Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.1. 1b - Submittal of construction methodology
fd0a740d-940d-5351-b8fa-f415197da9d1 | note | Responsibility - Spiral Drillers
a7ed6df4-57da-5b3d-bca7-41a7a3ce37a4 | note | Spec Reference - Project Memo Section 2.1.iii
0412310f-8b32-5fcb-81b0-14caeb6d586d | note | Conformance Criteria Summary - Include: Equipment, Pile construction methodology, delivery and storage of material, safe work area, pile concrete & sand placement.
682c81a7-f943-54e6-9c6e-dcd7b7dbb81e | note | Method - Document review
fd3693ee-9f38-507d-8c25-2bf2dde2a14b | note | Frequency - Prior to Start of work
c276f19c-02c0-55b5-a0eb-e542e1f223e1 | note | Hold/Witness Requirements: SD C - HP
e21e3c6a-1095-54a7-abfe-0bc50454b6db | note | Hold/Witness Requirements: UC C - HP
c003744b-9332-55ce-929d-98f3f6ffad00 | note | Hold/Witness Requirements: C MTL - HP
7b6b2f1c-93b9-55ec-aa86-5fc118330472 | note | Records or Checklist Reference - Approved ITP
| signoff | AUTHORITY HOLDPOINT
| section | Approved Materials
| checkpoint | 2.1 - Reinforcing Cage
1fe85267-afa6-5123-bdfe-5fcff306ec04 | note | Responsibility - Spiral Drillers
48660cd2-2a15-56bf-ac61-ce4c8eb78046 | note | Conformance Criteria Summary - Mill Certifications
91531272-7c73-50d0-adb8-c277ca236909 | note | Send notice in advance request for inspections
2c536acf-8f02-505e-adf9-02f327421c0e | note | 7.8.3 Micro-Alloying MA 300E or Grade 500E steel
16fdecc6-a5ec-5f4a-a3f3-50b83f120402 | note | Reinforcing as per approved detail sheets.
043f4918-eabc-5591-9f75-cc0deef5de25 | note | Reinforcing to comply with AS/NZS 4671 & NZS3109.
ca6afe6f-de5c-5a08-9dd1-315cfe27a685 | note | Any cutting, bending or welding of reinforcing on site to be approved in writing by the design engineer.
9f15dc62-987c-5080-bd95-431588aa2db2 | note | Method - Detail Sheets approved by structural engineer prior to manufacture; Mill certificates for reinforcing cages used; Engineer to inspect constructed cages.
34c22919-55fb-5380-9d23-01f4c07d7192 | note | Frequency - Per pile type intended to be constructed; Prior to manufacture; Once arrived on site
60bf7ba6-7f80-5403-a388-3c3b8991cfa8 | note | Hold/Witness Requirements: SD C - HP
26d76d54-383f-58cd-b66f-6d56c2e006f4 | note | Hold/Witness Requirements: UC C - RR
9add9095-194a-50f2-806e-85b1581d1a87 | note | Hold/Witness Requirements: C MTL - RR
6d066c33-84e8-5703-a470-35c2fd18642c | note | Records or Checklist Reference - Delivery Dockets SD Pile cards Reinforcing Mill cert testing
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Concrete mix design
5118544a-18e9-59a5-976f-8b306aed2831 | note | Responsibility - Spiral Drillers
c75104b8-ed53-5da6-b942-0a8108af3b04 | note | Conformance Criteria Summary - Submit proposed concrete mix design in advance of concrete been placed on site
b0b72194-340c-5fbf-9f5a-2cfe18544981 | note | Concrete batching plant will keep records to prove ongoing suitability of plant and mix design, production tests and delivery.
0e362bd4-3df9-5bb9-b41b-b6988190adb6 | note | Concrete mix design to comply with NZS3104.
f9a3b685-ce05-5e1a-b836-b48ac7d3f113 | note | Maximum permittable aggregate size to be 19mm.
222d0dc4-f26d-5e27-b110-c1f18ec5fddc | note | Mixing design intended strength to be 35MPa and meeting the requirements for exposure classification B2.
6b74b5e6-0d74-580e-aaa5-27b06fe5c003 | note | Method - Concrete mix design Submitted to the engineer prior to concrete being placed.
02ab015b-681a-5ad5-81f2-a1a1a2da74b4 | note | Frequency - Prior to concrete being placed
67f023c7-e00e-58c9-ace9-4c114b28565a | note | Hold/Witness Requirements: SD C - HP
b7a2759f-072a-510c-bc31-363d7c781ccc | note | Hold/Witness Requirements: UC C - HP
24737138-884f-533b-8fad-35afda8f3758 | note | Hold/Witness Requirements: C MTL - RR
2f9e1ea6-f672-5b23-814c-85acd5465ea9 | note | Records or Checklist Reference - Written confirmation for acceptance of mix design. SDC QA - Concrete pile schedule Certificates, testing records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Welding
770af9b6-c34e-5242-9f14-7680357775d5 | note | Responsibility - Spiral Drillers
0e3dd740-f0f9-5338-b39c-0c02da6dbf0c | note | Spec Reference - AS/NZS 1554.1. NZS 4781.
58f062bc-306b-5705-a171-3b1c614b7123 | note | Conformance Criteria Summary - Welders WPS form in AS/NZS 1554.1
b54d99e4-8ac8-5048-bbda-f3bd00477e6f | note | Individual welders qualified to the WPS, AS/NZS 2980 Welder Certificate
4a708048-4d74-5405-9784-1dbdd2b909b4 | note | Method - Welding WPS Certification of each welder
19fab2f9-74e0-5ff0-ade6-6e97fb4bbcdf | note | Frequency - Prior to Start of work
e0b9dcc3-7d03-5bbb-b712-6a55eca8a3ad | note | Hold/Witness Requirements: SD C - HP
83e2b9a6-8e6b-5338-8396-d802b0202ed8 | note | Hold/Witness Requirements: UC C - HP
0931d769-11a9-5bce-a4b8-1f89eaccff98 | note | Hold/Witness Requirements: C MTL - RR
fd1dd531-fee7-53a0-aad8-85d4e25b8297 | note | Records or Checklist Reference - Welding records and certificates Current welding qualification
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 - Setting Out
| checkpoint | 3.1 - Set out and survey
80a04b59-86fa-5999-97f3-0887e8a632a5 | note | Responsibility - United Civil Construction
effed9da-16bc-5bc3-a9db-2e0a9bdd3cc2 | note | Spec Reference - Project drawings ASG Piling Specification Rev G – Section 1.13
425157dd-6928-5c2e-bd53-df778135bb3e | note | Conformance Criteria Summary - UCC to set out pile centre lines on guide frames installed by SDC. Set out requirements will vary from location but will be required on multiple occasions. Setout gridlines to be within +- 3mm of design position.
055cf504-4cb2-5b38-9c2e-3716bd08ee8f | note | UCC to provide several benchmark pegs along the alignment that are checked frequently to ensure accuracy.
c5fc093d-6e84-51da-be3f-6f5ee64ef55f | note | SDC will be responsible for offsets taken from the pile set out location.
a49b832e-80a6-58f5-b620-bf21e49314e9 | note | Method - Registered surveyor Inspection and Set out
08072cba-aeda-58ff-9351-2dbf7054bcde | note | Frequency - Each Pile position.
ac3bb272-de4d-505b-a58e-2a0d0dc4e6a6 | note | Hold/Witness Requirements: SD C - HP
7861f8af-fff1-5d94-929b-dd9c375df063 | note | Hold/Witness Requirements: UC C - IP
f4505f60-74be-5270-b202-3b3358b37a51 | note | Hold/Witness Requirements: C MTL - IP
b559126c-f2d7-501f-9979-6c6f4793f033 | note | Records or Checklist Reference - SD Quality Control Checklist Set out report for tolerance As-built Survey Monitoring of benchmarks.
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 Construction Stage
| checkpoint | 4.1 - Reinforcing Cages
b01c59aa-9f49-5c92-8a00-7308c4d33254 | note | Responsibility - Spiral Drillers
8bb417d1-d1e9-5ab9-8b87-6e790367a133 | note | Spec Reference - SESOC Section 1.10
935da510-a93f-519a-a0e3-5c2b4901e3de | note | Conformance Criteria Summary - Stack reinforcing cages on suitable supports on firm ground, in a manner to eliminate excessive handling stresses or other damage.
fac26b58-48b4-50ba-bf51-918ecaa73a6f | note | Reject and replace reinforcing cages that are not as per the detail sheets.
335f9dec-674d-5711-86b7-41aba5124e9e | note | Compile delivery dockets for reference to mill certs.
7fc67873-9be7-5819-afd7-3be96ac4dcfd | note | Method - Each delivery
cc700e13-2e05-5679-a82b-6bb27cd36e8e | note | Frequency - Each delivery
8dbdb6d2-0b41-5058-9d8b-efe9bd566094 | note | Hold/Witness Requirements: SD C - HP
a40bbd3d-bb56-545a-b6c0-27ea222233e3 | note | Hold/Witness Requirements: UC C - IP
ce9243e2-83ca-592b-81b9-6ca87eedbe19 | note | Hold/Witness Requirements: C MTL - IP
97a7e4e9-5e9f-5a3b-b053-252bdb8b5448 | note | Records or Checklist Reference - Structural engineer inspection of reinforcing cages SD Pile QA sheet Delivery dockets.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Concrete Dockets
d007aa50-7a89-5c7a-bd4f-6f2c2c6b75ab | note | Responsibility - Spiral Drillers
59f00747-2c3c-55b4-a9dc-73befa8443e8 | note | Spec Reference - Approved Mix design document.
48750680-2601-5606-914f-015ca7bd819e | note | Conformance Criteria Summary - Mix design on delivery docket matches the approved mix design.
d7164393-9a21-539a-9959-e9ecb49c662f | note | On site material testing to confirm mix design characteristics are achieved.
b900330b-a621-515e-a51a-c21665a73b3e | note | Method - Slump Tests & Concrete dockets.
75223d76-81bb-53ff-8169-20bea4f5dc9f | note | Frequency - Each Concrete truck.
25945071-6c21-5ac5-b8f8-5d4585b16340 | note | Hold/Witness Requirements: SD C - HP
0f2ac820-26fc-52c6-9202-795fa901ff0e | note | Hold/Witness Requirements: UC C - RR
b3546982-e4ef-57fd-9da1-834e3b0d8f71 | note | Hold/Witness Requirements: C MTL - RR
86f04f3a-f1db-502a-8155-303b6c72ad0d | note | Records or Checklist Reference - SD Concrete pour QA Sheet Concrete testing report.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Pile installation/ founding level.
d9e4a2ac-8a0e-59cf-b8ef-fe863697ec40 | note | Responsibility - Spiral Drillers/ UCC
9bd29a95-d549-52ec-aafb-0b9e4176e4f5 | note | Conformance Criteria Summary - Tolerances
fbf6670f-ce71-5926-84fc-741cff811370 | note | The centre of the pile head at the design level of the head shall be within 75mm of its lateral position and 25mm of its vertical position. The pile shall be within 1:100 of its design. Do not force incorrectly placed piles into their correct position after they have been placed.
5e8b0db7-863e-5567-bcf0-20496a1b94f8 | note | Pile as built survey to be completed by United Civil Construction
6df76cd9-b047-5d0f-9b26-0975bdde0c88 | note | Founding Material: Where required, the Engineer to be present to verify that the founding material is suitable material to satisfy design intent.
472b43bd-1338-5fac-90fe-29718bb31055 | note | Method - Position of pile: 75mm horizontal, 25mm vertical and 1:75 of its design; Piles shall achieve a minimum founding resistance Outlined in IFC Drawings; Cut off level to be +25, - 25mm
0e782f68-1513-5090-90a9-f5faf788ff93 | note | Frequency - Each pile
71252e8a-c577-5f09-8099-a8cc5d66961f | note | Hold/Witness Requirements: SD C - HP
68cabcdc-326f-5b12-9702-1c46c5353e34 | note | Hold/Witness Requirements: UC C - HP
c2affd35-1b71-5200-bed1-659aef761eaa | note | Hold/Witness Requirements: C MTL - IP
ecc0605c-c0ef-5d82-9ac7-a0284237c778 | note | Records or Checklist Reference - SD Pile Card Geotechnical Engineer inspection record.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Concrete placing
b690921a-3902-552f-9f30-38882c93e6e0 | note | Responsibility - Spiral Drillers
e394c876-a2a5-513f-a95a-39b83be1a3b4 | note | Conformance Criteria Summary - Each pile is to be checked before each pour for any groundwater or contaminates in the pile
cc5e1337-672f-5ab3-8934-93cd912ede0d | note | Daily concrete pour record to approved checklist
7d7d1d5e-4097-541f-84eb-45d886e14360 | note | Concrete docket to be submitted each pour Testing
f8d24f9a-becf-5f6e-8c8d-4e23a03999c7 | note | Carry out 7 and 28 days testing ; Standard cylinders for each 50m3. 1 at 7 days, 2 at 28 days; 1 slump test per load
34b38fa4-3446-5e58-827c-338356255976 | note | Concrete to be poured in a manner that avoids hitting the reinforcing cage. Poured central down the pile hole. Concrete to be tested in an IANZ Accredited lab.
d540a4b7-588b-553d-ab3d-a99a30f8df14 | note | Depth to top of concrete, placement time and method to be recorded for each truck.
6a16b038-d13a-576e-8e6e-31131a6c5d28 | note | WET METHOD: Where water inflow present and dewatering not possible. Piles to be tremie poured. Tremie embedment to be min 1.5m and maximum 10.0m. Vermiculite travelling plug of min 300mm length to used prior to concrete introduction.
38dcb8de-4e14-5337-85f2-5daeb0839960 | note | Method - Concrete dockets, Test results And Pile cards
487a9113-8531-5e86-a772-94779d9a6152 | note | Frequency - Every 50m3 or minimum of 1 per day; Each pile to be inspected before pouring concrete
986955df-47de-56db-8adf-bbede6d552c3 | note | Hold/Witness Requirements: SD C - HP
5c0b4968-bd80-5220-abc0-2963a3a0fa33 | note | Hold/Witness Requirements: UC C - IP/RR
0b2116e7-8fa7-5bca-9cdb-748e517c0983 | note | Hold/Witness Requirements: C MTL - IP/RR
a5fd9886-0e10-5c69-a6d5-67db7c4f49f7 | note | Records or Checklist Reference - Concrete dockets and laboratory test results SD Concrete QA Card.
| signoff | AUTHORITY HOLDPOINT
| section | Completion
| checkpoint | 5.1 - As- built pile survey
1cabfc2e-c469-5ff6-92b4-8373f0c9230c | note | Responsibility - United Civil/ Spiral Drillers
6ca97b55-953f-5ea7-813d-d695a5ce497b | note | Conformance Criteria Summary - All piles installed are within the required tolerances as shown in the construction specification and drawings.
c9952458-2b99-5bd1-bc79-6306ee612ddc | note | +-75mm horizontal tolerance
95225bff-4d8e-5f31-a432-a0f156fe3dd9 | note | +- 25mm vertical tolerance
8b65a161-0786-5fdb-8460-b0684884d1c1 | note | Method - As-built survey completed by a registered surveyor
29205446-a37f-5b1b-bd92-b1b753765f66 | note | Frequency - Upon completion of pile installation
ce005d51-7223-5725-9783-f13d3ade174a | note | Records or Checklist Reference - Complete As-built document referring position to design positions.
| checkpoint | 5.2 - Warranty and code of compliance
524cea47-d15a-5413-b8bd-93a8e7562185 | note | Responsibility - Spiral Drillers
09d58717-648e-5b33-b94b-2f763effcad1 | note | Conformance Criteria Summary - Documented evidence Certificate, warranty or Producers statement Warranty meets spec requirements Commence warranty from date of practical completion
d8d27633-dd2a-5d67-83e0-d7989fad1326 | note | Spiral Drillers will issue a Producer Statement for the entirety of their contracted works upon completion.
800c9390-d365-5ef5-934b-eea05d834d9c | note | Method - Record review
08889554-8956-5fc6-865a-591653db9eb7 | note | Frequency - once
e52bc089-e6f0-58a0-a4dc-5fca76ca9a17 | note | Hold/Witness Requirements: SD C - HP
2fe607d9-297c-5f07-8644-dc92b0cd10f2 | note | Hold/Witness Requirements: UC C - HP
cffa1d45-8a45-52d7-bf11-738cada696ae | note | Hold/Witness Requirements: C MTL - RR
| signoff | AUTHORITY HOLDPOINT