## Checklist Templates
Id | Type | Name | Values | Prompting Name
4037c88f-621f-49b6-94a2-0eed50d5ee32 | checklist | Balcony Waterproofing |  | Balcony
06d05785-1c2f-4739-8393-55271147f864 | section | Details
4b618226-23fb-42de-a549-209218704e4a | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
856556c7-cc2e-59d6-8b6e-1e66b538a428 | note | Attach relevant photos
1aa22e83-d6ab-43ff-876d-770d08ae8355 | checkpoint | WP details listed at architectural drawings for clarifications are followed.
72336cfd-a249-587d-b850-3f02b17bc4fa | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
b64f66ae-0551-5c67-92bd-46153302872b | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
ec7519e9-e603-527d-8ce5-8e7e2873b110 | tickbox | Ensure no high points or crevices are in the substrate
e7643fb2-a9c9-55eb-b374-9a0583b37792 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
7caf4416-6ca8-4a78-88f6-ad4c0d85eab2 | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
1c34d841-9fcb-55f6-ac22-2aae01fe0916 | note | Attach relevant photos
5553791a-995c-483a-815f-a4035cbe6db9 | checkpoint | Prime substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
1c1ef9bf-d96b-5853-b850-0210b5d9398f | note | Attach relevant photos
58eb007b-6129-467d-8d22-e1c2c76e83c5 | checkpoint | Seal all corners, joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant - Apply selected sealant as per datasheet & application guidelines
c4fd6714-ca9f-5a5b-873d-9886aa494303 | note | Attach relevant photos
75aaaa91-b7f6-4a28-b46c-9759ecea32e2 | checkpoint | Balustrade base i.e shoe base or angle base installed & grouted with structural grout (as required)
f9aab34a-a5fd-5e81-828c-242d7f7d80c8 | note | Joint between bttom of base & substrate to be no greater than 10mm with continuous bead of caulking
33752e88-84ac-4fcb-a88a-54b560a21889 | checkpoint | Overflow at the ends of balustrades in place
693750ca-1d51-5812-b9da-fa1bc9ffcd7f | note | Approximate width of over floor to be 50mm
0eb0e12b-57da-5ac7-8253-ed49c4842a5e | note | Height of overflow must be lower than the bttom of subsill
cfe95b4a-6b1a-5c0f-85b0-95a370ee1d92 | note | Angle to be installed between end of base & wall with top of angle to be at FFL
0addc9c5-55dd-4f98-bd5d-632af6c05f05 | checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
23cae9de-68ce-474b-9c56-0a94b7e3621a | checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
6003c0d3-f098-5660-bfc4-3cfd7a785f15 | note | Attach relevant photos
5bcb26e7-a2f6-4265-a0a8-d1950582dad5 | checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
0d81df48-b365-4322-aa42-b8c3170b23a5 | checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
110520bc-ce20-5d31-9c00-286e69bacda1 | note | Attach relevant photos
c418f841-77c1-4686-a790-6878212df62c | checkpoint | Dry day for second coat (if required).
182499e2-164a-4da3-b253-faa9fced79ce | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
ba914fad-bb77-55fc-b8b6-58b5233d5ffc | note | Attach relevant photos
c6ff645d-0491-42e0-8c5a-474e5d656a10 | checkpoint | Attach photos for the drainage conduit.
10fcab2e-5276-52ca-826b-424d08236ed0 | note | Attach relevant photos
eeb4d4f8-c64c-472f-b332-1aae1bed69c4 | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
bad47760-71bc-51c5-a59b-28f14f1543eb | note | Attach relevant photos
ccc37f2a-b279-419d-a7ba-b5a0b93661e4 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
f0ad8ab3-e8da-5ebb-9113-b9df88605676 | note | HOLDPOINT - Once all above items have been signed off work may proceed
10d89586-d3f7-4ba0-97ca-4821b7698e4a | checklist | Balcony Waterproofing (+Apply Polyguard) |  | Balcony
bd381b56-2481-4700-b408-9ba5a8a076dc | section | Details
6ff68e17-bbdb-4f2d-ba90-c23beafde8f0 | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
d5f0b788-72bc-51a4-baa1-2502d8c3e515 | note | Attach relevant photos
01623f21-c8e6-45d0-82e1-abbca9db7426 | checkpoint | WP details listed at architectural drawings for clarifications are followed.
eaca6cd6-75ef-5ab9-bc83-c013c460bdfa | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
ecc54bca-4bae-556d-888a-3d92f5a42dd9 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
e84f0bf0-3ac7-5195-87db-865c4efe73ea | tickbox | Ensure no high points or crevices are in the substrate
b17b6e80-c675-5520-b647-e9bcd9c1bb66 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
cd16dabb-25d7-47af-81a8-6c4c89185493 | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
b1c3725d-99ef-54fe-97cc-4c1b3337fe48 | note | Attach relevant photos
104442a4-bcaf-4e72-accb-26642e87a9e4 | checkpoint | Prime substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
29cfeb35-e18e-5325-a42d-e5c1bf95dc6e | note | Attach relevant photos
5552ed4d-6345-4573-af9c-635a7b5a3887 | checkpoint | Seal all corners, joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant - Apply selected sealant as per datasheet & application guidelines
1e6ad2da-0338-5cc5-841b-be9833f25bb5 | note | Attach relevant photos
101ef1b9-c65d-4e63-8847-da7f256536d9 | checkpoint | Balustrade base i.e shoe base or angle base installed & grouted with structural grout (as required)
922c709a-b1b9-58cb-a0bb-36cd16ab554c | note | Joint between bttom of base & substrate to be no greater than 10mm with continuous bead of caulking
2692f0ed-9465-4053-8bad-e1627b8f35f0 | checkpoint | Overflow at the ends of balustrades in place
2e2812b6-d305-5b16-84d5-5bfce5c1f8cc | note | Approximate width of over floor to be 50mm
94225d53-8fb7-57a6-b414-6487c52ed1e6 | note | Height of overflow must be lower than the bttom of subsill
ebd3ded3-173f-5a03-aeb1-c99ff1364b20 | note | Angle to be installed between end of base & wall with top of angle to be at FFL
7d0bdd84-81f6-42b9-9002-5a32c5296d9d | checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
1b3aaf84-a1e8-4916-b9eb-357aa470cba1 | checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
00dd4ebf-6fa9-50d2-97a1-e1b2f97f03bd | note | Attach relevant photos
7e8f6438-5a52-4325-8b5f-b85874975d51 | checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
4f535449-8911-4aeb-b9db-5d436ff44618 | checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
c339e873-e893-53a1-a5b5-5f237b506f8b | note | Attach relevant photos
88efd542-5125-4672-a740-1d236f825d37 | checkpoint | Dry day for second coat (if required).
17220715-7bc6-4a01-a99a-1eb04b5e0520 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
40c60128-d659-519d-9d51-73854012849b | note | Attach relevant photos
787731ab-458c-46be-93d3-61e09d9ea716 | checkpoint | Apply polyguard protective UV topcoat. Apply selected topcoat at a rate of 0.2-0.6kg/m2 in one coat as per data sheet and application guidelines
f7765cb5-3b5c-40f5-b478-ca24aa027221 | checkpoint | Attach photos for the drainage conduit.
b3992298-f2e0-5e26-9206-2959c7683f0c | note | Attach relevant photos
ee3fac26-31f0-4fff-af73-9627f952dd78 | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
2746683a-d136-526b-94c4-0a3fe2271e00 | note | Attach relevant photos
6f170e84-ebce-433b-9af7-6e10e6e83265 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
574e1d47-bed5-5445-b290-c855549fc827 | note | HOLDPOINT - Once all above items have been signed off work may proceed
ba653985-2a59-4ae5-8af2-7bd9b8257945 | checklist | Fire Sprinkler Tanks Waterproofing |  | Fire Sprinkler Tanks Waterproofing
bdc4b36b-ca0e-48f7-a402-b5e969a63f38 | section | Details
bad58d1b-1abd-46d3-ae62-a15453a73642 | checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
156e8ed6-b01a-52a4-8997-5af01483cd07 | note | Attach relevant photos
df8d1f0d-f34c-53d9-8b7b-eacd04e216a3 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
f1b2ca0e-4021-5b77-9c84-3acd04c6e859 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
4286c4f7-1f8c-5443-8d8b-1558702bd37d | tickbox | Ensure no high points or crevices are in the substrate
d92e5bd9-0f2f-5802-b15a-76c86032439a | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
93bfc40f-8ac3-4ba8-a550-631c005e0f58 | checkpoint | Fatra Fatrafol 807 PVC membrane to be used. - Apply selected membrane as per datasheet & application guidelines
a6314d4a-97b8-5e69-81d4-d4c116758e67 | note | Attach relevant photos
90e99298-a4e4-479d-80bb-608cf1b2c7ea | checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
06203cab-f276-59e7-a5f7-02dffede67ed | note | Attach relevant photos
2553440d-9244-4474-8776-cdacf95a8806 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
85c3b6dc-9286-530e-b92a-a07598a2a7cc | note | Attach relevant photos
d98644a0-436f-47a4-b94e-6f496de961e2 | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
dab8e160-f85d-5f75-93a2-13a673914e8f | note | Attach relevant photos
154717c9-a2e1-484f-ac80-a50e07f27997 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
589e224f-5fc3-5131-aa04-977ad5198c58 | note | HOLDPOINT - Once all above items have been signed off work may proceed
ccd8f7ab-64c9-4a15-b3a8-2be846c2a671 | checklist | Fire Sprinkler Tanks Waterproofing (Balconies) |  | Fire Sprinkler Tanks Waterproofing (Balconies)
54679bea-3327-40d4-bea1-931f70cddc1b | section | Details
c2778334-16ea-422a-9d7b-ffe825bd9fd6 | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
618cd0cb-3b26-51c5-8501-dd5fb0a7cd49 | note | Attach relevant photos
b7ffdc23-6876-5ad3-86fd-d5c19b12d8ea | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
5b23ed49-5c51-53b8-8f8b-0e165d5eab1a | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
82ac6a22-2c43-5534-bd2d-f5533fc1db71 | tickbox | Ensure no high points or crevices are in the substrate
f7f747eb-8455-5278-a194-4dc6b0940005 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
b509022d-6a7e-4938-a0a1-73adc087cdd4 | checkpoint | Fatra Fatrafol 807 PVC membrane to be used. - Apply selected membrane as per datasheet & application guidelines
24b104e7-cf74-5b1e-b761-1a6d97e72324 | note | Attach relevant photos
41f60294-1c38-4b2d-bebc-8824dedc640e | checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
0e7dec4e-1f0e-5298-b7d1-67f6b07d39fa | note | Attach relevant photos
be405ad4-18c4-4ce8-8453-0d52b7705c72 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
1b317abf-4bd3-5741-9ce6-9c69201c34ac | note | Attach relevant photos
d2d03964-2cf0-4e5e-9a56-dba5b59d5128 | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
2a344501-205c-585c-8f54-d57bb26cc4f6 | note | Attach relevant photos
82652d14-cd5b-43e7-83fd-57d88dce7b3b | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
56a67b86-7fe3-5a22-bfce-57c6c8e6eca8 | note | HOLDPOINT - Once all above items have been signed off work may proceed
26cf9e6a-c422-43ee-b303-a03e6a4e82bb | checklist | Garbage Chutes Waterproofing |  | Garbage Chutes Waterproofing
f6e0ae2e-5801-40fd-a67a-c88161b1bb51 | section | Details
7a423ba1-0bc8-435e-944e-b6e3c833dc0c | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
8cdd03e0-c9ec-593f-9ac4-02228a1093dd | note | Attach relevant photos
94ce87c0-2c52-5290-9ebf-5d5f1001d918 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
7519cf6a-cdd6-5f02-8e96-32e6376b6849 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
1c228c0b-6bc5-5b57-af76-06f8af9ccd02 | tickbox | Ensure no high points or crevices are in the substrate
ee6c09bf-f25e-57b2-842f-a9102ea454b1 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
e9564dca-3f71-4128-a619-ca5395cdfaed | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
be0fa04d-001d-52d7-8d2f-64a3ac9bb690 | note | Attach relevant photos
e72e9f20-efcd-4b87-8303-d74d9a0afe90 | checkpoint | Primer substrate (walls and floors) with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
5050e6a4-5209-50a5-b258-ef9a62fbabb9 | note | Attach relevant photos
0f3ec1fa-b988-4ba5-84b4-bc513476b8df | checkpoint | Apply angles to builders FFL as required.
d358d49f-3a4c-5192-8ed6-cb64befc970f | note | Attach relevant photos
cabc17a6-93e5-4002-ba48-e96c2e912fe0 | checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
44b47ddd-3c07-5fd8-968c-148ed2834050 | note | Attach relevant photos
0313c7f6-7abc-439d-a602-0341075f0c44 | checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
50aea0d3-c995-5d83-920d-c4813e4b9f36 | note | Attach relevant photos
c6c060aa-59db-46b4-a2b3-1054fd300d61 | checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
cb41c522-058d-5176-b210-7cac00889b5e | note | Attach relevant photos
70b26b63-9b2c-45f9-9ab5-62ee9d5b417d | checkpoint | Dry day for second coat (if required).
2de622bc-c463-5156-a80d-b682534d6b3f | note | Attach relevant photos
2e36d78a-3897-46b7-b136-ef24b99fef4e | checkpoint | Apply 2 coats of Polybit Hybrid 150 waterbased polyurethane membrane on walls as required. - Apply selected membrane at a rate of 1.0 litres/m2 per coat as per datasheet & application guidelines
bfca29cf-e3b7-570d-9912-b2799f0d29ec | note | Attach relevant photos
3a7eb6d0-24f8-479b-b5d2-e19f75f6d8c2 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
8e8c9948-ae37-53a6-ae21-60879fa76248 | note | Attach relevant photos
aae663fd-1e77-42aa-abbe-629ea58baba8 | checkpoint | Conduct a flood test to garbage chute area.
e3b6d25b-696a-598a-b39c-e2ba701713d0 | note | Attach relevant photos
af4a6e78-bf0d-4a43-b7bc-48a7c1ac7d25 | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
532da9c2-eca7-5558-bcf2-01eecb21c6cb | note | Attach relevant photos
fc74e3d0-a1a8-4808-94eb-eccef4e861a2 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
317f2f80-593e-5d80-a7cf-6514bc819d74 | note | HOLDPOINT - Once all above items have been signed off work may proceed
6b285c3f-25fd-4f2b-9a13-9efb838da74a | checklist | Garbage Rooms Waterproofing |  | Garbage Rooms Waterproofing
c676b537-3c87-4c31-9ef9-57cb0e01c77c | section | Details
d4b070da-0af6-4856-8d93-802ea435d585 | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
6e238a24-6270-55a4-a321-447e6bf2ea1b | note | Attach relevant photos
3626ff78-421a-5d05-808a-41ef890297b3 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
8fb38cb4-c696-54e6-b9a4-d1dde248ac6b | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
1bd31220-bf90-5a17-bafb-d7351bd22bbe | tickbox | Ensure no high points or crevices are in the substrate
bcd4179a-fbce-5e3d-b062-e7de8c002715 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
3d85e076-5c52-43af-a8ad-bac4a5406dc0 | checkpoint | Apply 1st coat of Duromix Hibuild WBE epoxy primer to walls and floors - Apply selected primer at a rate of 1.5m2/L as per datasheet & application guidelines
b98ab1ff-a7aa-517d-b3fc-f9d6cdae83f2 | note | Attach relevant photos
5baf2d6e-4007-495c-b25b-8fb575886ed9 | checkpoint | Apply 2nd coat of Duromix Hibuild WBE epoxy primer to walls and floors - Apply selected primer at a rate of 1.5m2/L as per datasheet & application guidelines
7ebef34a-a824-5f86-b091-5f30073233b5 | note | Attach relevant photos
31b93a09-9fee-4ecc-85ee-0afe64de82a3 | checkpoint | Apply 1st coat of Duropoxy SLR100 epoxy top coat to walls and floors - Apply selected top coat a a rate of 6.6m2/L as per datasheet & application guidelines
258d3652-2bfd-5d31-8d5b-e7190f3fec95 | note | Attach relevant photos
067f7ad4-f698-4af4-8011-e370d8385442 | checkpoint | Apply 2nd coat of Duropoxy SLR100 epoxy top coat to walls and floors - Apply selected top coat a a rate of 6.6m2/L as per datasheet & application guidelines
4a970ce7-3839-517c-8125-8f14d8c86c94 | note | Attach relevant photos
4a2abf3a-cf6a-471c-a98c-4eaa6317c72b | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
bfcf14a5-5084-5ded-98b1-d01fe68a7f39 | note | Attach relevant photos
7a972496-c0bc-49c3-89c5-a5847edbae0d | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
f28c3c5c-ab8a-50d6-a70e-7611d592241a | note | Attach relevant photos
fa323e09-c97a-4370-b8ce-d089403cbef0 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
84014454-c303-532f-9b6a-d7d28fd43664 | note | HOLDPOINT - Once all above items have been signed off work may proceed
ae2c3118-881a-43b5-b9bd-6844a8d8b6b0 | checklist | Hobs |  | Hobs
18ea2235-fe15-420f-bbb6-434ff2c3de24 | section | Details
c4d9ee23-9c73-475b-9c03-313796ff49ae | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
654cb9b2-c554-568c-b87c-46f30adc0070 | note | Attach relevant photos
409404ed-1a68-54db-9043-ec695b6c9678 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
3e85a6f1-a1c7-5b86-89dc-c54fa3e8d731 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
f4e2a84c-b4e1-4e8d-a388-f2d41e41a6c7 | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
533b44db-9eff-5c68-8202-f96731f82cc6 | note | Attach relevant photos
7b5bd2c9-4b20-4236-8ceb-4fe3a6bc47a0 | checkpoint | Primer substrate with Polybit Hydrapoxy/polyprime - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
84d1e1b5-1c14-54ab-97b2-def9a71d1ef3 | note | Attach relevant photos
77b1ee6c-5073-4cf4-8dad-10acb83c4c6e | checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
5211b916-8851-5614-81c8-c39f3322b700 | note | Attach relevant photos
c1aa1051-c6ed-4e93-81ca-e20e139a4235 | checkpoint | Apply 1st coat of Polybit Hydraguard - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
c7f98c93-8a7e-5ccb-80bb-f93ed2e2ea04 | note | Attach relevant photos
aaa66cd7-576b-449d-b50e-7655d93f1162 | checkpoint | Apply 2nd coat of Polybit Hydraguard - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
5b6dd23f-6990-56b2-9595-b1a6ef95bc78 | note | Attach relevant photos
69344249-350e-4381-b2bd-ff867f1cf1b0 | checkpoint | Dry day for second coat (if required).
e2467b2b-a7d9-4264-919e-8a3991ee0f26 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
446e64af-abd5-5ca6-944e-a94f7e165793 | note | Attach relevant photos
5fdefbd3-016f-4e78-a967-4031372696f7 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
d8773ddc-760b-5644-8d64-2f56a48c385b | note | HOLDPOINT - Once all above items have been signed off work may proceed
e0de795b-c545-490f-9fd1-e9bea67385a8 | checklist | Internal Wet Area (Bathrooms & Laundries) Waterproofing |  | Internal Wet Area (Bathrooms & Laundries) Waterproofing
a3a763f2-c0f9-4975-b418-77b4877e89c5 | section | Details
50da72f4-bc8a-4c5a-9f4d-45e447121e2b | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
5dc06aab-f3dc-5c71-84a7-c8a1937c9f3a | note | Attach relevant photos
f1ee4240-48b5-58df-a934-5a3af481d078 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
ddbbd6b1-695b-597e-a2b5-56197e099fb5 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
92fd4e7f-1fef-5cd9-9d93-09ecc9317d77 | tickbox | Ensure no high points or crevices are in the substrate
745e8c73-2bb7-50b8-8c00-8daba36a3382 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
caa7f5f8-8894-469d-b62c-784518087a38 | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
3ddb40c7-ccbc-56a8-8487-9014696c5a3d | note | Attach relevant photos
078e30e9-4859-5137-8cda-7dcdc589159e | tickbox | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
c40ef002-259e-589f-8d7c-94815adb9df3 | tickbox | Shower Angles in correct position & level
32c5ea1b-1ec0-59a9-af7f-69ff95b98464 | tickbox | Door Angle is in correct position & level
7f0a526d-977f-5868-9193-5152fb77059e | tickbox | Door & Shower Angle are 3mm guage aluminium
ff0d65c5-ad6b-5db8-bd32-4040330164e8 | tickbox | Ensure humidity, temperature & moisture are in accordance with manufactuer's recommendations
ad0e9cdc-ec3c-48a6-b8f0-597d36078ede | checkpoint | Primer substrate (walls and floors) with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
28ba6432-4c9a-5765-b5f8-769fd191740a | note | Attach relevant photos
4f1ef3ca-c19e-493c-88ab-28d945fb7af6 | checkpoint | Apply angles to builders FFL as required.
61a6bc4e-4ab8-5f86-a529-0505cb1e21fb | note | Attach relevant photos
f3d50d68-1489-4267-80a5-faa9e727489c | checkpoint | Seal all joints and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
608ad85f-220a-568b-b3fc-9c41f34327e4 | note | Attach relevant photos
4a44ee99-abc3-46c2-9c74-3100623b2e7a | checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
a78aa99a-afb5-533e-b39a-067c43922cdb | note | All floor wastes membranes to be turned down into floor waste
6e0f3f3d-a007-4b48-b57f-01a4311a03c8 | checkpoint | Waterproof walls of shower section up to ceiling. Seal taps & the like. 2x coats required.
f34bc68a-39ea-531c-a92a-8a849c3964f3 | tickbox | Min 150mm kicker has been waterproofed (do width of roller 230mm)
a4502496-5030-5a71-aab7-c7dffdc8b142 | tickbox | Min 1500mm past shower screen has been waterproofed.
b1f9a997-6c93-595e-94cf-c4518e310610 | tickbox | Waterproof all shower & adjacent walls
7f26eb97-eb2f-58c2-9edd-394677093eb5 | tickbox | Ensure humidity, temperature & moisture are in accordance with manufactuer's recommendations
1fed3905-6548-530d-9125-c61349dd7ca8 | note | Attach relevant photos
9f756cb3-2704-4a7d-971a-11b4270f0e30 | checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
c6877689-d288-589a-be17-7a1fd72f1596 | note | Attach relevant photos
c7c52bf8-75c2-41bd-83c1-fd2d93a93f90 | checkpoint | Dry day for second coat (if required).
8b25d080-a852-59a8-a40b-42de52eb158f | note | Attach relevant photos
d0887e58-c437-4941-9faa-4afb62775139 | checkpoint | Apply 2 coats of Polybit Hybrid 150 waterbased polyurethane membrane on walls as required. - Apply selected membrane at a rate of 1.0 litres/m2 per coat as per datasheet & application guidelines
f40cf110-f15f-582f-bd12-2c99d76d91bc | note | Attach relevant photos
7105cda0-deb1-45aa-b3fc-ca9ce677e1a7 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
f01e3e66-0387-59b0-9c92-3fd8627e1b92 | note | Attach relevant photos
98e55a72-b581-4099-80c5-ad072daf242b | checkpoint | Conduct a flood test to internal wet area.
f26465c4-ac1b-56b2-b36b-c6df4408d25f | note | Attach relevant photos
d80fc8b9-03f3-4f41-acb0-c5de6774c0fe | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
c44f7cb7-4dac-5c40-9e93-abc272245b51 | note | Attach relevant photos
0361de2b-a800-42fb-988f-299359088744 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
99e1c5ad-6d7d-5fa6-bbc3-dea13b1e8652 | note | HOLDPOINT - Once all above items have been signed off work may proceed
57ca3572-95d6-40a2-9175-3c37df8c5921 | checklist | Internal Wet Areas |  | Internal Wet Areas
153bf66e-6949-4c0a-8da3-3295de21d52b | section | Details
e528f82d-e9f0-445f-8200-33c88cf9ff59 | checkpoint | Area barricaded off to allow no access to internal wet areas with signs posted/ visible to include date of application, "No access waterproofing work in progress"
39c68206-496a-5851-bc3f-aa53fd4682a5 | note | Attach relevant photos
f8c38984-6904-5322-9e36-99d12c73da33 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
345f876b-4863-5e7c-a2ee-1677950df155 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
6efaed94-abfb-57a1-8edc-daa0ea93afe0 | tickbox | Ensure no high points or crevices are in the substrate
f1d8a8c9-7cf4-5470-a9ff-7b35830c8ec8 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
7425ce43-a605-44d7-be8d-70ffebb9f38f | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
c22e1673-e624-54d9-afe0-8d378f056ed8 | note | Attach relevant photos
efa1e8f6-fed1-42d0-b8fb-ce043f1eb65d | checkpoint | Primer substrate with Polybit Hydrapoxy/polyprime - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
983068d4-52f3-4802-9ba7-257db2173b30 | checkpoint | Install alluminium waterstops to door entries and showers as per builder's FFL.
52bae93b-9469-5c46-9cec-b2b9817151d8 | note | Attach relevant photos
80962e00-83d4-4a59-9b26-517848589bec | checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
8fc52780-0867-5858-bc81-287228abd735 | note | Attach relevant photos
ca71c104-63c3-4915-b6bb-cbe7bdfaa1d1 | checkpoint | Apply 1st coat of Polybit Hydraguard on floors - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
a2f0dc47-9e46-54fd-90d5-0c4f867b8205 | note | Attach relevant photos
3f565a9d-1224-4929-b317-69e817998192 | checkpoint | Apply 2nd coat of Polybit Hydraguard on floors - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
4914c4bf-bcc8-52be-8d09-4df597c8e2cb | note | Attach relevant photos
f2ca00c3-68e5-4cb2-b003-12339a0fd5e0 | checkpoint | Dry day for second coat (if required).
6fe3ba51-4375-5230-9a53-20c67419a4fe | note | Apply Polybit Hybrid 150 to walls where required as per data sheet and application guidelines.
eff69d84-90b9-4e6b-8869-ac046478b6ae | checkpoint | Flood test for a minimum of 24 hours.
72587a87-5037-4260-bed9-97581efad29d | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
ae85212d-9ed0-5c07-adc5-ac5436181317 | note | Attach relevant photos
1ba158de-ef55-4aea-9628-24f798c3251e | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
5ad0e72e-8174-5134-bd30-a3dc9349190b | note | HOLDPOINT - Once all above items have been signed off work may proceed
93d935a8-7e07-4d39-8b2b-4bba5e679651 | checklist | Lift Pits Waterproofing |  | Lift Pits Waterproofing
4336410c-e02b-4057-968e-e1aef9878a69 | section | Details
47793507-e560-4c1f-9eb3-8c4cc85e202a | checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
d8dab5e6-69fa-5f38-8c55-53f3fba28840 | note | Attach relevant photos
426ca9cb-1e4f-5f6f-b0c3-089178765fb5 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
9098df1e-3c95-5aaf-8b5f-0db063ed8533 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
dbe606e2-4e1c-5e77-959f-98adb96ad970 | tickbox | Ensure no high points or crevices are in the substrate
7b7561f6-5df5-55a7-bb4b-55c8d2c93317 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
10a31051-c4ff-409c-b411-5d2ccdabf12c | checkpoint | Dampen the surface to ensure the highest level of adhesion
d973ccfd-8969-5388-9a79-3ebb61606eaf | note | Attach relevant photos
4a62b662-d124-4123-85ca-a7bb82e4f1f9 | checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
1413a629-9d16-566c-b63b-9a458b890ecb | note | Attach relevant photos
c01daee9-4078-4e8c-b3c0-5cf9627ae2ac | checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
e4fa2326-e34b-5647-8146-f2b5b2920a2f | note | Attach relevant photos
fb2ce705-fb90-433d-9727-00711ee67685 | checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
e5bd7796-f56a-5ad1-89a1-e11599031968 | note | Attach relevant photos
b1d01d7e-9981-4ec0-85a6-06d86c0d14d0 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
a93135db-b2ee-5d74-a943-efe7513e24e6 | note | Attach relevant photos
802f63d8-4b18-4ee5-9b50-099937d2ba6b | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
468e2d4a-aa6d-5821-bff1-3a1fc6f04693 | note | Attach relevant photos
dca915ab-0ad1-41b0-8fc8-cd685c84128f | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
8740d69f-7591-5bdc-bf4d-1984ff416a2f | note | HOLDPOINT - Once all above items have been signed off work may proceed
771e9194-8c6b-42d5-90bf-1d501d763a36 | checklist | Lift Pits Waterproofing (Balconies) |  | Lift Pits Waterproofing (Balconies)
ae6b1d33-0e48-4fcf-82a6-0f115787e3e2 | section | Details
0157ea94-de8c-40dc-8ef1-96767c6f34d4 | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
786a0625-de7c-5d04-b9a6-4f769d1cf176 | note | Attach relevant photos
79bc0d86-c8bd-5bec-a0bf-831323d7c612 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
bfdfaf6e-bd63-526a-a545-eca9eaf58542 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
93f31261-4a0b-54f2-a4f6-4656d275a891 | tickbox | Ensure no high points or crevices are in the substrate
e6de808d-0a3d-5e64-9462-f22864e16d44 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
06c5cb76-b281-406f-9709-9192f2962631 | checkpoint | Dampen the surface to ensure the highest level of adhesion
a28dfc17-236c-5b7b-a1ae-619b01c6ca02 | note | Attach relevant photos
420d7a76-4c24-4e4c-897e-9956f277b66a | checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
608cb168-e48a-56e5-ada7-2fa7fcf8dd84 | note | Attach relevant photos
b7d1fb80-a0c9-4828-af9e-7f26ca256d46 | checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
e0ebeaf1-eca9-5ea4-bce7-e4f93e97a1a9 | note | Attach relevant photos
605df4ab-a2a1-4979-823e-dff6019843b0 | checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
8bef1233-c619-556e-9c1e-83a0d0a5814a | note | Attach relevant photos
bfc126d3-5258-47fe-81f0-694648b77d59 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
008c3a2e-bfe8-5344-b231-df774f60d23c | note | Attach relevant photos
d1af5e6c-0f3c-467d-ba90-89d8fc220d7d | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
f2c02edc-258d-5e23-b3f5-6366996c6b33 | note | Attach relevant photos
8c6cdbf0-2746-41df-89c1-2e130fa60781 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
72fc6902-e94e-5137-b9a0-745aab4c56b2 | note | HOLDPOINT - Once all above items have been signed off work may proceed
db0dcba1-1e74-405a-a058-8e6b8f0a0865 | checklist | Planter Box Waterproofing |  | Planter Box Waterproofing
5576c946-31d8-424f-ae4f-4723bc9f02d0 | section | Details
2dec68d8-6fc2-4431-a418-e6d8f1163119 | checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
e01e53cc-ad92-59eb-b2b0-00e5f3f8593a | note | Attach relevant photos
14722a94-8c0f-4771-82f9-06c39565c76e | checkpoint | WP details listed at architectural drawings for clarifications are followed.
81fddd2b-ea51-419c-915e-00610e47baae | checkpoint | All floor should be with proper falls towards the floor waste with a min. 1:100 slope.
c7b16b37-cccc-5f1b-87c6-eb508feb4e57 | note | Attach relevant photos
620fc33e-6089-5fd5-ac4d-25935c1f0159 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
407b2518-1f50-549d-b73b-2b6389bc4940 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
974501b2-78f3-5f21-a468-763c47b77e59 | tickbox | Ensure no high points or crevices are in the substrate
57ac126f-0877-56f4-a9e7-25abcd06c366 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
dcf53de5-e2a4-4058-b19c-2c5d3be45764 | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
de3df8f5-cebe-5384-ab31-f76be9fb49ef | note | Attach relevant photos
20e23f94-742a-4752-9a5f-031942eb7063 | checkpoint | Primer substrate with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
5fac33f2-9184-53a8-8ae5-e8f0340666e1 | note | Attach relevant photos
fb1b034f-fadf-470d-922a-b3ed01932482 | checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
c5760f62-aeca-521a-b5b7-e8ea263d711c | note | Attach relevant photos
cbf07c61-346b-4e66-939a-41bbfc626ef6 | checkpoint | Apply 1st coat of Polybit Hydraguard AR100 on floors and walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
610d4a35-3346-5aed-aeba-0b2c0406da1c | note | Attach relevant photos
2250ef48-148a-4224-b7ea-761970a90659 | checkpoint | Apply 2nd coat of Polybit Hydraguard AR100 on floors and walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
78d2a3fb-a161-5f0d-9e80-157d8e498e35 | note | Attach relevant photos
55fa7482-b7e6-4593-8d51-56c5b6573143 | checkpoint | Dry day for second coat (if required).
faf1565e-c063-47b6-bf70-0786b592644c | checkpoint | Attatch photos for the drainage conduit.
319dc49a-c3d1-53a7-ac66-a6e123c3fe5e | note | Attach relevant photos
d6f0a798-4b47-4cb7-b12b-aebb06feb7f8 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
87353b04-373e-59f5-b7f8-f26862ceeeee | note | Attach relevant photos
37ab5b9d-b88d-4906-bb70-29ccae05ed21 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
338803ff-97fa-5d30-8ebb-8117b2d03e71 | note | HOLDPOINT - Once all above items have been signed off work may proceed
4b75d077-5b77-4102-80de-261bd5eed95d | checklist | Roof, Terraces & Walkways Waterproofing |  | Roof, Terraces & Walkways Waterproofing
6dea808a-e89d-465f-9cba-a42c21bed598 | section | Details
2b82ee09-3a55-4e03-b75c-00f99714635f | checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
a67462f1-a32a-59b9-be37-a9bb627262c4 | note | Attach relevant photos
06b0f987-13d4-4cb9-9e88-e469b8f6ae33 | checkpoint | WP details listed at architectural drawings for clarifications are followed.
38d55bf1-7c57-4385-890b-35da411210dd | checkpoint | All floor should be with proper falls towards the floor waste with a min. 1:100 slope.
de2ece94-fac4-5e97-bb27-487fe729ed04 | note | Attach relevant photos
fe2ae9b9-3784-441a-916d-8a937b96dfe6 | checkpoint | WPM must be applied around the linear drains (grated drains) before adding the leveling screed.
43810d17-1886-5c89-885d-a15af2e9dfee | note | Attach relevant photos
5d67dd9a-da67-5e08-b063-8eb215225273 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
68162f17-178e-5c4b-9cb8-32b997c2b403 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
58669368-1beb-50c8-97e8-86c01108b3b3 | tickbox | Ensure no high points or crevices are in the substrate
0d99a3c0-9596-5728-859d-197cedce79bb | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
648b4933-a6d1-4955-85a0-167c71ea3592 | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
77322d2a-7b87-5d8c-aa1d-c129e5bbf92a | note | Attach relevant photos
b4b39446-950f-48d1-86a0-cc8b9c9e7c42 | checkpoint | Primer substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
01f509f6-c4c9-578d-a9af-9c50e5fa2a3b | note | Attach relevant photos
62dfa6fa-1152-4dc1-a567-8b446e6292b3 | checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
9441e22a-84b9-5194-9fb0-e2b833890cc0 | note | Attach relevant photos
64baee6b-e95b-4b44-ad4a-c8e9f5d84ed0 | checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup up and over external hobs. - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
c2c452a8-33e9-5807-94a7-1e7a2230cd0b | note | Attach relevant photos
cca746a7-9e45-48a1-a00f-824d70e879d3 | checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup up and over external hobs - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
62502bbd-509f-5036-93b4-e153f5aaf738 | note | Attach relevant photos
a5b89a36-216c-44a5-bfc9-7ab8c9b87f79 | checkpoint | Dry day for second coat (if required).
973a7aa0-3a8f-51b6-b294-c15e005f3c30 | note | Attach relevant photos
2ab9d95f-e1cf-42e1-a465-5724324f5103 | checkpoint | Apply PolyGuard protective UV top coat. - Apply selected top coat at a rate of 0.2-0.6 kg/m2 in one or two coats, depending on traffic conditions as per datasheet & application guidelines
36ee632e-3046-4ad9-9f7c-2c0a86b88834 | checkpoint | the WPM must be terminated at the specified height outlined in the wind classification report Via saw cut reglet or other WPM termination method specified at AS 4654.2, or can be overlap by approved elastomeric weather-resist coating by min. 150mm.
91f2b2c6-ff59-5098-827b-a134d29fd29c | note | Attach relevant photos
f8205bd5-3109-4724-8187-a90c6fc79688 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
61c04cdd-18cd-5a64-8639-ecb16d7aa63c | note | Attach relevant photos
229cb861-f8d8-4ae4-9c9e-49ff9ada5ede | checkpoint | Attatch photos for the drainage conduit.
0f65ff48-8c9c-5731-a4e4-5db26f9f32ed | note | Attach relevant photos
6f483516-618e-4fd9-ab69-83cc15ffe43f | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
64605137-5c11-570b-bbb5-b1bdaff85b8d | note | Attach relevant photos
a7af71c0-c7e6-440d-9eb3-5447a5656d70 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
57cca08e-22e9-558f-b11b-5f771c7568d0 | note | HOLDPOINT - Once all above items have been signed off work may proceed
118ead40-d651-4ee3-ac0a-259f9c7c6d13 | checklist | Slab Edges Waterproofing |  | Slab Edge
d00230f2-d127-4884-89f7-786889b78546 | section | Details
f2bcf9d3-565e-4b0e-9ecb-56479dd7712f | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
e9914a7a-9fcb-5c60-a587-78c3b860dc58 | note | Attach relevant photos
86c5bc29-5274-5f62-9836-3cdc464f9eb3 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
85307a91-82c9-5804-ab7b-7195d697b3d8 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
21ed29e8-ae9e-5ed7-bc81-8357d538c735 | tickbox | Ensure no high points or crevices are in the substrate
ef6b8bb0-5dd8-5910-8f75-57b269d8e1cb | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
70ffb250-a993-474c-89e2-0c1a21cbfce1 | checkpoint | Dampen the surface to ensure the highest level of adhesion as required
4651f4f4-e721-5c2e-ab2e-85f2bd5729ee | note | Attach relevant photos
8580b602-91c7-4b7a-9cb3-a52f27b0533c | checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines & ensure WPM to be extened and terminated inside the drip groove.
f7de61fd-b674-5f26-8c5b-cb9bc2cfe4dd | note | Attach relevant photos
19bab399-c71f-4580-930b-fb93d46143c2 | checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines & ensure WPM to be extened and terminated inside the drip groove.
6932a8de-66d2-5228-9c0e-fcf58e60cc4b | note | Attach relevant photos
9a2df918-c3b5-43f0-a297-f336cc649e62 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
99c435ef-c575-5c73-a9cb-f7ba6dc97312 | note | Attach relevant photos
9940940e-49f0-4749-a29b-e4ed486d7f4c | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
fb465a61-2ba6-5577-ad16-b0756ef0012b | note | Attach relevant photos
5e043af5-06a7-44b5-8df9-fce123b9fb7e | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
915b4118-51c0-58da-9f0c-b22d4e21dcad | note | HOLDPOINT - Once all above items have been signed off work may proceed
6cd6285f-c6c6-43c2-a28a-1c73c1e2b6d1 | checklist | Stormwater Tanks Waterproofing |  | Stormwater Tanks Waterproofing
d0155b52-feed-4359-b5f0-482377773df0 | section | Details
e162c486-dc02-4e7e-bd9e-906da7701e87 | checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
6c4adf96-bba7-52cb-bb98-540eff861e4c | note | Attach relevant photos
2e36e6a3-ac07-561a-a4f6-341ac812c495 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
064f227e-5824-5149-bd5b-2c9011cb550c | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
ed9a3fa2-a398-5330-a960-03554025c745 | tickbox | Ensure no high points or crevices are in the substrate
ce38e8e9-5c20-5edb-a845-2034693e5f66 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
ffd3f174-8acc-4ac0-90f6-213740baa7d0 | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
7378c051-3228-5dca-a3ec-54cbbab7778a | note | Attach relevant photos
271dc61d-50e6-4baa-92d4-71e506f127da | checkpoint | Seal all joints and penetrations with Polybit HydraFlex FC polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
2afbbd00-c3ca-5b0f-8880-c5066cd30394 | note | Attach relevant photos
1469e870-b086-4b02-8142-29cf6442ab6a | checkpoint | Dampen the surface to ensure the highest level of adhesion as required
1749593f-2a79-590b-95b3-65301c9e7dfc | note | Attach relevant photos
2c3d06b9-8c07-4149-8305-5e100ef50f06 | checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
439b847a-0ca5-5ee7-8059-b0195f5ca15a | note | Attach relevant photos
a83e6291-4331-43e4-a3a3-6a1d802cf70b | checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
45aa05e2-75db-5eba-9706-cdc6e94e7dec | note | Attach relevant photos
9ca468c0-b761-416a-9fa9-b4ff2a6d76aa | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
41390b98-7787-553d-ab73-e5e21bd53b4d | note | Attach relevant photos
ac4b3a81-2f7f-4840-a12d-57f198a92d8c | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
29298784-e64c-5978-a058-4ec5ccb7b95b | note | Attach relevant photos
e35ff680-1657-4717-b33a-b39f7709da34 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
7f328b9a-347d-57b4-bbe9-27bafab2d417 | note | HOLDPOINT - Once all above items have been signed off work may proceed
8d478843-e860-4d87-8dea-958254c35470 | checklist | Stormwater Tanks Waterproofing (Balconies) |  | Stormwater Tanks Waterproofing (Balconies)
68eee327-3d16-4740-aef2-ebc9b60c0b64 | section | Details
8f23b07e-d730-4524-a7d3-0ee5f12ca522 | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
f3682b06-1c4c-56bb-a5fa-caac31db9df0 | note | Attach relevant photos
3da7ffea-7bf6-53f3-97c3-aa0ece1ee561 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
8937af7e-9fdc-58cc-8d68-084e00fbb4e6 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
c0993a0d-4cd6-5cd2-9305-e7537bd03ebb | tickbox | Ensure no high points or crevices are in the substrate
c6b46245-8528-5f72-965e-1d958744820e | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
203d2736-c941-4bcc-9ace-976997d8b77a | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
201eedbf-2d95-5dad-b0a3-ba43c4797f93 | note | Attach relevant photos
741ceab3-2f31-4ad8-b058-f609d03fd59f | checkpoint | Seal all joints and penetrations with Polybit HydraFlex FC polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
8dbd447e-ab56-5d85-8601-f31d53c28541 | note | Attach relevant photos
324c8533-92bb-46e1-8c35-2cde6e2fea33 | checkpoint | Dampen the surface to ensure the highest level of adhesion as required
d0eac1f5-fd45-5d9d-8e34-cc782304517b | note | Attach relevant photos
771b6e86-f5c7-4893-b78c-d2d6567bda0b | checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
ba22e30e-4307-51c1-831c-51f56a2a71a2 | note | Attach relevant photos
fc4d33ef-3108-48cf-8b46-3b881614167d | checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
60eec6fa-9e9e-5462-9401-087f06f965a3 | note | Attach relevant photos
e292576c-05d8-4e5e-aa1c-67a6f5d93e95 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
bfad9fd3-2f14-5e74-8889-8168eb2e1089 | note | Attach relevant photos
b1d9510c-57a0-46f6-80a6-d7aa4e186870 | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
c446ab1f-fdf5-5e58-b09a-7afe63e2feaa | note | Attach relevant photos
0c29ebe1-3eaa-4f42-9a0a-999f7cb699d1 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
3a4655bc-d647-5107-998c-21bfbfe76b0d | note | HOLDPOINT - Once all above items have been signed off work may proceed
6990da27-ceac-4f7e-b5be-1d394dc5d477 | checklist | Waste/Bin Rooms |  | Waste/Bin Rooms
3a5d6b69-92c2-4012-885f-8ccb4f105ed4 | section | Details
3ab9d3e6-e462-457a-b081-b819b5efd14c | checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
2452e514-e803-589e-a838-77308e89be01 | note | Attach relevant photos
15743099-aed7-5056-bc33-158153c9b03b | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
3c3458ec-be2d-568e-b8c4-355f494ec469 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
9643e0d4-444f-4bfe-878f-d8636b9aefc8 | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
7f6c8a92-c2a5-5a18-aa80-b8a81b00db40 | note | Attach relevant photos
1ae00763-6e65-4b1b-91a0-e0ac7cf6c6fe | checkpoint | Primer substrate with Polybit Hydrapoxy- Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
66ce6582-7359-5c70-b2b8-939b7beb04d5 | note | Attach relevant photos
59aebfb7-3923-5893-8671-3f2930c4dc0e | note | Attach relevant photos
486c58f3-e6e9-4743-9495-1087cfe15590 | checkpoint | Apply 1st coat of Polybit Hydrapoxy flooring on floors and walls as per datasheet & application guidelines
4a028eee-15dd-5cf2-8a4c-216e2f89aa2b | note | Attach relevant photos
57d0dc62-95da-4015-a928-a69d5f43517c | checkpoint | Apply 2nd coat of Polybit Hydrapoxy flooring on walls and floors - Apply selected membrane as per datasheet & application guidelines
65f4a63f-fc75-5097-8482-8bcdd3459bb7 | note | Attach relevant photos
5e9b083e-bb53-4099-859c-1418f7791fbf | checkpoint | Dry day for second coat (if required).
d9c7f1c8-b02b-5bbb-8b3c-4cb186437e86 | note | Attach relevant photos
7ff68f44-7508-4eb5-a4c0-455cc137e1b0 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
c09e0f40-5711-55cf-8667-bb0c0d76e603 | note | HOLDPOINT - Once all above items have been signed off work may proceed