## Sheet1
10 Waterfront Promenade Shell Cove- GrowthBuilt
Lift Pits
Basment
Internal Wet Areas
Service rooms
Fire sprinkler tanks
Ground floor
external common areas
Internal Wet Areas
planter boxes
Level 1
Hobs
Internal Wet Areas
Balcony
planter boxes
102
Hobs
Internal Wet Areas
``
Planter boxes
103
Hobs
Internal Wet Areas
Balcony
planter boxes
104
Hobs
Internal Wet Areas
Balcony
Planter boxes
105
Hobs
Internal Wet Areas
Balcony
planter boxes
106
Hobs
Internal Wet Areas
Balcony
planter boxes
107
Hobs
Internal Wet Areas
Balcony
planter boxes
108
Hobs
Internal Wet Areas
Balcony
planter boxes
109
Hobs
Internal Wet Areas
Balcony
Planter boxes
110
Hobs
Internal Wet Areas
Balcony
Planter boxes
111
Hobs
Internal Wet Areas
Balcony
Planter boxes
112
Hobs
Internal Wet Areas
Balcony
Planter boxes
113
Hobs
Internal Wet Areas
Balcony
Planter boxes
114
Hobs
Internal Wet Areas
Balcony
Planter boxes
115
Hobs
Internal Wet Areas
Balcony
Planter boxes
116
Hobs
Internal Wet Areas
Balcony
Planter boxes
117
Hobs
Internal Wet Areas
Balcony
Planter boxes
118
Hobs
Internal Wet Areas
Balcony
Planter boxes
119
Hobs
Internal Wet Areas
Balcony
Planter boxes
120
Hobs
Internal Wet Areas
Balcony
Planter boxes
121
Hobs
Internal Wet Areas
Balcony
Planter boxes
122
Hobs
Internal Wet Areas
Balcony
Planter boxes
123
Hobs
Internal Wet Areas
Balcony
Planter boxes
124
Hobs
Internal Wet Areas
Balcony
Planter boxes
125
Hobs
Internal Wet Areas
Balcony
Planter boxes
126
Hobs
Internal Wet Areas
Balcony
Planter boxes
127
Hobs
Internal Wet Areas
Balcony
Planter boxes
128
Hobs
Internal Wet Areas
Balcony
Planter boxes
129
Hobs
Internal Wet Areas
Balcony
Planter boxes
130
Hobs
Internal Wet Areas
Balcony
Planter boxes
131
Hobs
Internal Wet Areas
Balcony
Planter boxes
132
Hobs
Internal Wet Areas
Balcony
Planter boxes
133
Hobs
Internal Wet Areas
Balcony
Planter boxes
134
Hobs
Internal Wet Areas
Balcony
Planter boxes
135
Hobs
Internal Wet Areas
Balcony
Planter boxes
136
Hobs
Internal Wet Areas
Balcony
Planter boxes
137
Hobs
Internal Wet Areas
Balcony
Planter boxes
138
Hobs
Internal Wet Areas
Balcony
Planter boxes
|  | 139 | Hobs
Internal Wet Areas
Balcony
Planter boxes
Level 2
|  | 201 | Hobs
Internal Wet Areas
Balcony
planter boxes
202
Hobs
Internal Wet Areas
Balcony
Planter boxes
203
Hobs
Internal Wet Areas
Balcony
planter boxes
204
Hobs
Internal Wet Areas
Balcony
Planter boxes
205
Hobs
Internal Wet Areas
Balcony
planter boxes
206
Hobs
Internal Wet Areas
Balcony
planter boxes
207
Hobs
Internal Wet Areas
Balcony
planter boxes
208
Hobs
Internal Wet Areas
Balcony
planter boxes
209
Hobs
Internal Wet Areas
Balcony
Planter boxes
210
Hobs
Internal Wet Areas
Balcony
Planter boxes
211
Hobs
Internal Wet Areas
Balcony
Planter boxes
212
Hobs
Internal Wet Areas
Balcony
Planter boxes
213
Hobs
Internal Wet Areas
Balcony
Planter boxes
214
Hobs
Internal Wet Areas
Balcony
Planter boxes
215
Hobs
Internal Wet Areas
Balcony
Planter boxes
216
Hobs
Internal Wet Areas
Balcony
Planter boxes
217
Hobs
Internal Wet Areas
Balcony
Planter boxes
218
Hobs
Internal Wet Areas
Balcony
Planter boxes
219
Hobs
Internal Wet Areas
Balcony
Planter boxes
220
Hobs
Internal Wet Areas
Balcony
Planter boxes
221
Hobs
Internal Wet Areas
Balcony
Planter boxes
222
Hobs
Internal Wet Areas
Balcony
Planter boxes
223
Hobs
Internal Wet Areas
Balcony
Planter boxes
224
Hobs
Internal Wet Areas
Balcony
Planter boxes
225
Hobs
Internal Wet Areas
Balcony
Planter boxes
226
Hobs
Internal Wet Areas
Balcony
Planter boxes
227
Hobs
Internal Wet Areas
Balcony
Planter boxes
228
Hobs
Internal Wet Areas
Balcony
Planter boxes
229
Hobs
Internal Wet Areas
Balcony
Planter boxes
230
Hobs
Internal Wet Areas
Balcony
Planter boxes
231
Hobs
Internal Wet Areas
Balcony
Planter boxes
232
Hobs
Internal Wet Areas
Balcony
Planter boxes
233
Hobs
Internal Wet Areas
Balcony
Planter boxes
234
Hobs
Internal Wet Areas
Balcony
Planter boxes
235
Hobs
Internal Wet Areas
Balcony
Planter boxes
236
Hobs
Internal Wet Areas
Balcony
Planter boxes
237
Hobs
Internal Wet Areas
Balcony
Planter boxes
238
Hobs
Internal Wet Areas
Balcony
Planter boxes
|  | 239 | Hobs
Internal Wet Areas
Balcony
Planter boxes
Level 3
|  | 301 | Hobs
Internal Wet Areas
Balcony
planter boxes
302
Hobs
Internal Wet Areas
Balcony
Planter boxes
303
Hobs
Internal Wet Areas
Balcony
planter boxes
304
Hobs
Internal Wet Areas
Balcony
Planter boxes
305
Hobs
Internal Wet Areas
Balcony
planter boxes
306
Hobs
Internal Wet Areas
Balcony
planter boxes
307
Hobs
Internal Wet Areas
Balcony
planter boxes
308
Hobs
Internal Wet Areas
Balcony
planter boxes
309
Hobs
Internal Wet Areas
Balcony
Planter boxes
310
Hobs
Internal Wet Areas
Balcony
Planter boxes
311
Hobs
Internal Wet Areas
Balcony
Planter boxes
312
Hobs
Internal Wet Areas
Balcony
Planter boxes
313
Hobs
Internal Wet Areas
Balcony
Planter boxes
314
Hobs
Internal Wet Areas
Balcony
Planter boxes
315
Hobs
Internal Wet Areas
Balcony
Planter boxes
316
Hobs
Internal Wet Areas
Balcony
Planter boxes
317
Hobs
Internal Wet Areas
Balcony
Planter boxes
318
Hobs
Internal Wet Areas
Balcony
Planter boxes
319
Hobs
Internal Wet Areas
Balcony
Planter boxes
320
Hobs
Internal Wet Areas
Balcony
Planter boxes
321
Hobs
Internal Wet Areas
Balcony
Planter boxes
322
Hobs
Internal Wet Areas
Balcony
Planter boxes
323
Hobs
Internal Wet Areas
Balcony
Planter boxes
324
Hobs
Internal Wet Areas
Balcony
Planter boxes
325
Hobs
Internal Wet Areas
Balcony
Planter boxes
326
Hobs
Internal Wet Areas
Balcony
Planter boxes
327
Hobs
Internal Wet Areas
Balcony
Planter boxes
328
Hobs
Internal Wet Areas
Balcony
Planter boxes
329
Hobs
Internal Wet Areas
Balcony
Planter boxes
330
Hobs
Internal Wet Areas
Balcony
Planter boxes
331
Hobs
Internal Wet Areas
Balcony
Planter boxes
332
Hobs
Internal Wet Areas
Balcony
Planter boxes
333
Hobs
Internal Wet Areas
Balcony
Planter boxes
334
Hobs
Internal Wet Areas
Balcony
Planter boxes
335
Hobs
Internal Wet Areas
Balcony
Planter boxes
336
Hobs
Internal Wet Areas
Balcony
Planter boxes
337
Hobs
Internal Wet Areas
Balcony
Planter boxes
338
Hobs
Internal Wet Areas
Balcony
Planter boxes
|  | 339 | Hobs
Internal Wet Areas
Balcony
Planter boxes
Level 4
401
Hobs
Laundry
Internal Wet Areas
Exposed roofs
402
Hobs
Laundry
Internal Wet Areas
Exposed roofs
403
Hobs
Laundry
Internal Wet Areas
Exposed roofs
404
Hobs
Laundry
Internal Wet Areas
Exposed roofs
405
Hobs
Laundry
Internal Wet Areas
Exposed roofs
406
Hobs
Laundry
Internal Wet Areas
Exposed roofs
407
Hobs
Laundry
Internal Wet Areas
Exposed roofs
408
Hobs
Laundry
Internal Wet Areas
Exposed roofs
409
Hobs
Laundry
Internal Wet Areas
Exposed roofs
410
Hobs
Laundry
Internal Wet Areas
Exposed roofs
411
Hobs
Laundry
Internal Wet Areas
Exposed roofs
412
Hobs
Laundry
Internal Wet Areas
Exposed roofs
413
Hobs
Laundry
Internal Wet Areas
Exposed roofs
414
Hobs
Laundry
Internal Wet Areas
Exposed roofs
415
Hobs
Laundry
Internal Wet Areas
Exposed roofs
Level 5
501
Hobs
Laundry
Internal Wet Areas
Balcony
502
Hobs
Laundry
Internal Wet Areas
Balcony
503
Hobs
Laundry
Internal Wet Areas
Balcony
504
Hobs
Laundry
Internal Wet Areas
Balcony
505
Hobs
Laundry
Internal Wet Areas
Balcony
506
Hobs
Laundry
Internal Wet Areas
Balcony
507
Hobs
Laundry
Internal Wet Areas
Balcony
508
Hobs
Laundry
Internal Wet Areas
Balcony
509
Hobs
Laundry
Internal Wet Areas
Balcony
510
Hobs
Laundry
Internal Wet Areas
Balcony
511
Hobs
Laundry
Internal Wet Areas
Balcony
512
Hobs
Laundry
Internal Wet Areas
Balcony
513
Hobs
Laundry
Internal Wet Areas
Balcony
514
Hobs
Laundry
Internal Wet Areas
Balcony
515
Hobs
Laundry
Internal Wet Areas
Balcony
516
Hobs
Laundry
Internal Wet Areas
Balcony
517
Hobs
Laundry
Internal Wet Areas
Balcony
518
Hobs
Laundry
Internal Wet Areas
Balcony
519
Hobs
Laundry
Internal Wet Areas
Balcony
520
Hobs
Laundry
Internal Wet Areas
Balcony
521
Hobs
Laundry
Internal Wet Areas
Balcony
522
Hobs
Laundry
Internal Wet Areas
Balcony
523
Hobs
Laundry
Internal Wet Areas
Balcony
Level 6
601
Hobs
Laundry
Internal Wet Areas
Balcony
602
Hobs
Laundry
Internal Wet Areas
Balcony
603
Hobs
Laundry
Internal Wet Areas
Balcony
604
Hobs
Laundry
Internal Wet Areas
Balcony
605
Hobs
Laundry
Internal Wet Areas
Balcony
606
Hobs
Laundry
Internal Wet Areas
Balcony
607
Hobs
Laundry
Internal Wet Areas
Balcony
608
Hobs
Laundry
Internal Wet Areas
Balcony
609
Hobs
Laundry
Internal Wet Areas
Balcony
610
Hobs
Laundry
Internal Wet Areas
Balcony
611
Hobs
Laundry
Internal Wet Areas
Balcony
612
Hobs
Laundry
Internal Wet Areas
Balcony
613
Hobs
Laundry
Internal Wet Areas
Balcony
614
Hobs
Laundry
Internal Wet Areas
Balcony
615
Hobs
Laundry
Internal Wet Areas
Balcony
616
Hobs
Laundry
Internal Wet Areas
Balcony
617
Hobs
Laundry
Internal Wet Areas
Balcony
618
Hobs
Laundry
Internal Wet Areas
Balcony
619
Hobs
Laundry
Internal Wet Areas
Balcony
620
Hobs
Laundry
Internal Wet Areas
Balcony
621
Hobs
Laundry
Internal Wet Areas
Balcony
622
Hobs
Laundry
Internal Wet Areas
Balcony
623
Hobs
Laundry
Internal Wet Areas
Balcony
Level 7
701
Hobs
Laundry
Internal Wet Areas
Balcony
702
Hobs
Laundry
Internal Wet Areas
Balcony
703
Hobs
Laundry
Internal Wet Areas
Balcony
704
Hobs
Laundry
Internal Wet Areas
Balcony
705
Hobs
Laundry
Internal Wet Areas
Balcony
706
Hobs
Laundry
Internal Wet Areas
Balcony
707
Hobs
Laundry
Internal Wet Areas
Balcony
708
Hobs
Laundry
Internal Wet Areas
Balcony
709
Hobs
Laundry
Internal Wet Areas
Balcony
710
Hobs
Laundry
Internal Wet Areas
Balcony
711
Hobs
Laundry
Internal Wet Areas
Balcony
Level 8
801
Hobs
Laundry
Internal Wet Areas
Balcony
802
Hobs
Laundry
Internal Wet Areas
Balcony
803
Hobs
Laundry
Internal Wet Areas
Balcony
804
Hobs
Laundry
Internal Wet Areas
Balcony
805
Hobs
Laundry
Internal Wet Areas
Balcony
806
Hobs
Laundry
Internal Wet Areas
Balcony
807
Hobs
Laundry
Internal Wet Areas
Balcony
808
Hobs
Laundry
Internal Wet Areas
Balcony
809
Hobs
Laundry
Internal Wet Areas
Balcony
810
Hobs
Laundry
Internal Wet Areas
Balcony
811
Hobs
Laundry
Internal Wet Areas
Balcony
Level 9
901
Hobs
Laundry
Internal Wet Areas
Balcony
902
Hobs
Laundry
Internal Wet Areas
Balcony
903
Hobs
Laundry
Internal Wet Areas
Balcony
904
Hobs
Laundry
Internal Wet Areas
Balcony
905
Hobs
Laundry
Internal Wet Areas
Balcony
906
Hobs
Laundry
Internal Wet Areas
Balcony
907
Hobs
Laundry
Internal Wet Areas
Balcony
908
Hobs
Laundry
Internal Wet Areas
Balcony
909
Hobs
Laundry
Internal Wet Areas
Balcony
910
Hobs
Laundry
Internal Wet Areas
Balcony
911
Hobs
Laundry
Internal Wet Areas
Balcony
Level 10
1001
Hobs
Laundry
Internal Wet Areas
Balcony
1002
Hobs
Laundry
Internal Wet Areas
Balcony
1003
Hobs
Laundry
Internal Wet Areas
Balcony
1004
Hobs
Laundry
Internal Wet Areas
Balcony
1005
Hobs
Laundry
Internal Wet Areas
Balcony
1006
Hobs
Laundry
Internal Wet Areas
Balcony
1007
Hobs
Laundry
Internal Wet Areas
Balcony
1008
Hobs
Laundry
Internal Wet Areas
Balcony
1009
Hobs
Laundry
Internal Wet Areas
Balcony
Pool area
Planter boxes
external areas
Swimming pool
Level 11
|  | Roof | Exposed roof

## Resources
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name
checklist | Roof, Terraces & Walkways Waterproofing |  |  |  |  | Yes | Roof, Terraces & Walkways Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
checkpoint | WP details listed at architectural drawings for clarifications are followed.
checkpoint | All floor should be with proper falls towards the floor waste with a min. 1:100 slope.
note | Attach relevant photos
checkpoint | WPM must be applied around the linear drains (grated drains) before adding the leveling screed.
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup up and over external hobs. - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup up and over external hobs - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
note | Attach relevant photos
checkpoint | Apply PolyGuard protective UV top coat. - Apply selected top coat at a rate of 0.2-0.6 kg/m2 in one or two coats, depending on traffic conditions as per datasheet & application guidelines
checkpoint | the WPM must be terminated at the specified height outlined in the wind classification report Via saw cut reglet or other WPM termination method specified at AS 4654.2, or can be overlap by approved elastomeric weather-resist coating by min. 150mm.
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Attatch photos for the drainage conduit.
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Lift Pits Waterproofing (Balconies) |  |  |  |  | Yes | Lift Pits Waterproofing (Balconies)
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Dampen the surface to ensure the highest level of adhesion
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Balcony |  |  |  |  | Yes | Balcony Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
checkpoint | WP details listed at architectural drawings for clarifications are followed.
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Prime substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all corners, joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Balustrade base i.e shoe base or angle base installed & grouted with structural grout (as required)
note | Joint between bttom of base & substrate to be no greater than 10mm with continuous bead of caulking
checkpoint | Overflow at the ends of balustrades in place
note | Approximate width of over floor to be 50mm
note | Height of overflow must be lower than the bttom of subsill
note | Angle to be installed between end of base & wall with top of angle to be at FFL
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Attatch photos for the drainage conduit.
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Internal Wet Area (Bathrooms & Laundries) Waterproofing |  |  |  |  | Yes | Internal Wet Area (Bathrooms & Laundries) Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
tickbox | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
tickbox | Shower Angles in correct position & level
tickbox | Door Angle is in correct position & level
tickbox | Door & Shower Angle are 3mm guage aluminium
tickbox | Ensure humidity, temperature & moisture are in accordance with manufactuer's recommendations
checkpoint | Primer substrate (walls and floors) with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply angles to builders FFL as required.
note | Attach relevant photos
checkpoint | Seal all joints and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | All floor wastes membranes to be turned down into floor waste
checkpoint | Waterproof walls of shower section up to ceiling. Seal taps & the like. 2x coats required.
tickbox | Min 150mm kicker has been waterproofed (do width of roller 230mm)
tickbox | Min 1500mm past shower screen has been waterproofed.
tickbox | Waterproof all shower & adjacent walls
tickbox | Ensure humidity, temperature & moisture are in accordance with manufactuer's recommendations
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
note | Attach relevant photos
checkpoint | Apply 2 coats of Polybit Hybrid 150 waterbased polyurethane membrane on walls as required. - Apply selected membrane at a rate of 1.0 litres/m2 per coat as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Conduct a flood test to internal wet area.
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Lift Pits Waterproofing |  |  |  |  | Yes | Lift Pits Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Dampen the surface to ensure the highest level of adhesion
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Fire Sprinkler Tanks Waterproofing |  |  |  |  | Yes | Fire Sprinkler Tanks Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Fatra Fatrafol 807 PVC membrane to be used. - Apply selected membrane as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Stormwater Tanks Waterproofing |  |  |  |  | Yes | Stormwater Tanks Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all joints and penetrations with Polybit HydraFlex FC polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dampen the surface to ensure the highest level of adhesion as required
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Planter Box Waterproofing |  |  |  |  | Yes | Planter Box Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
checkpoint | WP details listed at architectural drawings for clarifications are followed.
checkpoint | All floor should be with proper falls towards the floor waste with a min. 1:100 slope.
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard AR100 on floors and walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard AR100 on floors and walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
checkpoint | Attatch photos for the drainage conduit.
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Fire Sprinkler Tanks Waterproofing (Balconies) |  |  |  |  | Yes | Fire Sprinkler Tanks Waterproofing (Balconies)
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Fatra Fatrafol 807 PVC membrane to be used. - Apply selected membrane as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Garbage Chutes Waterproofing |  |  |  |  | Yes | Garbage Chutes Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate (walls and floors) with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply angles to builders FFL as required.
note | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
note | Attach relevant photos
checkpoint | Apply 2 coats of Polybit Hybrid 150 waterbased polyurethane membrane on walls as required. - Apply selected membrane at a rate of 1.0 litres/m2 per coat as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Conduct a flood test to garbage chute area.
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Hobs |  |  |  |  | Yes | Hobs
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy/polyprime - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Stormwater Tanks Waterproofing (Balconies) |  |  |  |  | Yes | Stormwater Tanks Waterproofing (Balconies)
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all joints and penetrations with Polybit HydraFlex FC polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dampen the surface to ensure the highest level of adhesion as required
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Internal Wet Areas |  |  |  |  | Yes | Internal Wet Areas
section | Details
checkpoint | Area barricaded off to allow no access to internal wet areas with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy/polyprime - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
checkpoint | Install alluminium waterstops to door entries and showers as per builder's FFL.
note | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard on floors - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard on floors - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
note | Apply Polybit Hybrid 150 to walls where required as per data sheet and application guidelines.
checkpoint | Flood test for a minimum of 24 hours.
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Waste/Bin Rooms |  |  |  |  | Yes | Waste/Bin Rooms
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy- Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydrapoxy flooring on floors and walls as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydrapoxy flooring on walls and floors - Apply selected membrane as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Slab Edge |  |  |  |  | Yes | Slab Edges Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Dampen the surface to ensure the highest level of adhesion as required
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines & ensure WPM to be extened and terminated inside the drip groove.
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines & ensure WPM to be extened and terminated inside the drip groove.
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Garbage Rooms Waterproofing |  |  |  |  | Yes | Garbage Rooms Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply 1st coat of Duromix Hibuild WBE epoxy primer to walls and floors - Apply selected primer at a rate of 1.5m2/L as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Duromix Hibuild WBE epoxy primer to walls and floors - Apply selected primer at a rate of 1.5m2/L as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Duropoxy SLR100 epoxy top coat to walls and floors - Apply selected top coat a a rate of 6.6m2/L as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Duropoxy SLR100 epoxy top coat to walls and floors - Apply selected top coat a a rate of 6.6m2/L as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed