## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Roof, Terraces & Walkways Waterproofing |  |  |  |  | Yes | Roof, Terraces & Walkways Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
checkpoint | WP details listed at architectural drawings for clarifications are followed.
checkpoint | All floor should be with proper falls towards the floor waste with a min. 1:100 slope.
note | Attach relevant photos
checkpoint | WPM must be applied around the linear drains (grated drains) before adding the leveling screed.
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup up and over external hobs. - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup up and over external hobs - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
note | Attach relevant photos
checkpoint | Apply PolyGuard protective UV top coat. - Apply selected top coat at a rate of 0.2-0.6 kg/m2 in one or two coats, depending on traffic conditions as per datasheet & application guidelines
checkpoint | the WPM must be terminated at the specified height outlined in the wind classification report Via saw cut reglet or other WPM termination method specified at AS 4654.2, or can be overlap by approved elastomeric weather-resist coating by min. 150mm.
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Attatch photos for the drainage conduit.
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Lift Pits Waterproofing (Balconies) |  |  |  |  | Yes | Lift Pits Waterproofing (Balconies)
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Dampen the surface to ensure the highest level of adhesion
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Balcony |  |  |  |  | Yes | Balcony Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
checkpoint | WP details listed at architectural drawings for clarifications are followed.
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Prime substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all corners, joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Balustrade base i.e shoe base or angle base installed & grouted with structural grout (as required)
note | Joint between bttom of base & substrate to be no greater than 10mm with continuous bead of caulking
checkpoint | Overflow at the ends of balustrades in place
note | Approximate width of over floor to be 50mm
note | Height of overflow must be lower than the bttom of subsill
note | Angle to be installed between end of base & wall with top of angle to be at FFL
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Attatch photos for the drainage conduit.
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Internal Wet Area (Bathrooms & Laundries) Waterproofing |  |  |  |  | Yes | Internal Wet Area (Bathrooms & Laundries) Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
tickbox | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
tickbox | Shower Angles in correct position & level
tickbox | Door Angle is in correct position & level
tickbox | Door & Shower Angle are 3mm guage aluminium
tickbox | Ensure humidity, temperature & moisture are in accordance with manufactuer's recommendations
checkpoint | Primer substrate (walls and floors) with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply angles to builders FFL as required.
note | Attach relevant photos
checkpoint | Seal all joints and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | All floor wastes membranes to be turned down into floor waste
checkpoint | Waterproof walls of shower section up to ceiling. Seal taps & the like. 2x coats required.
tickbox | Min 150mm kicker has been waterproofed (do width of roller 230mm)
tickbox | Min 1500mm past shower screen has been waterproofed.
tickbox | Waterproof all shower & adjacent walls
tickbox | Ensure humidity, temperature & moisture are in accordance with manufactuer's recommendations
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
note | Attach relevant photos
checkpoint | Apply 2 coats of Polybit Hybrid 150 waterbased polyurethane membrane on walls as required. - Apply selected membrane at a rate of 1.0 litres/m2 per coat as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Conduct a flood test to internal wet area.
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Lift Pits Waterproofing |  |  |  |  | Yes | Lift Pits Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Dampen the surface to ensure the highest level of adhesion
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Fire Sprinkler Tanks Waterproofing |  |  |  |  | Yes | Fire Sprinkler Tanks Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Fatra Fatrafol 807 PVC membrane to be used. - Apply selected membrane as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Stormwater Tanks Waterproofing |  |  |  |  | Yes | Stormwater Tanks Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all joints and penetrations with Polybit HydraFlex FC polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dampen the surface to ensure the highest level of adhesion as required
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Planter Box Waterproofing |  |  |  |  | Yes | Planter Box Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
checkpoint | WP details listed at architectural drawings for clarifications are followed.
checkpoint | All floor should be with proper falls towards the floor waste with a min. 1:100 slope.
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard AR100 on floors and walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard AR100 on floors and walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
checkpoint | Attatch photos for the drainage conduit.
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Fire Sprinkler Tanks Waterproofing (Balconies) |  |  |  |  | Yes | Fire Sprinkler Tanks Waterproofing (Balconies)
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Fatra Fatrafol 807 PVC membrane to be used. - Apply selected membrane as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Garbage Chutes Waterproofing |  |  |  |  | Yes | Garbage Chutes Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate (walls and floors) with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply angles to builders FFL as required.
note | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
note | Attach relevant photos
checkpoint | Apply 2 coats of Polybit Hybrid 150 waterbased polyurethane membrane on walls as required. - Apply selected membrane at a rate of 1.0 litres/m2 per coat as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Conduct a flood test to garbage chute area.
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Hobs |  |  |  |  | Yes | Hobs
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy/polyprime - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Stormwater Tanks Waterproofing (Balconies) |  |  |  |  | Yes | Stormwater Tanks Waterproofing (Balconies)
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Seal all joints and penetrations with Polybit HydraFlex FC polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dampen the surface to ensure the highest level of adhesion as required
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Internal Wet Areas |  |  |  |  | Yes | Internal Wet Areas
section | Details
checkpoint | Area barricaded off to allow no access to internal wet areas with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy/polyprime - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
checkpoint | Install alluminium waterstops to door entries and showers as per builder's FFL.
note | Attach relevant photos
checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydraguard on floors - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydraguard on floors - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
note | Apply Polybit Hybrid 150 to walls where required as per data sheet and application guidelines.
checkpoint | Flood test for a minimum of 24 hours.
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Waste/Bin Rooms |  |  |  |  | Yes | Waste/Bin Rooms
section | Details
checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Primer substrate with Polybit Hydrapoxy- Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
note | Attach relevant photos
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydrapoxy flooring on floors and walls as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydrapoxy flooring on walls and floors - Apply selected membrane as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Dry day for second coat (if required).
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Slab Edge |  |  |  |  | Yes | Slab Edges Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Dampen the surface to ensure the highest level of adhesion as required
note | Attach relevant photos
checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines & ensure WPM to be extened and terminated inside the drip groove.
note | Attach relevant photos
checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines & ensure WPM to be extened and terminated inside the drip groove.
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist | Garbage Rooms Waterproofing |  |  |  |  | Yes | Garbage Rooms Waterproofing
section | Details
checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
note | Attach relevant photos
tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
tickbox | Ensure no high points or crevices are in the substrate
tickbox | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint | Apply 1st coat of Duromix Hibuild WBE epoxy primer to walls and floors - Apply selected primer at a rate of 1.5m2/L as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Duromix Hibuild WBE epoxy primer to walls and floors - Apply selected primer at a rate of 1.5m2/L as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 1st coat of Duropoxy SLR100 epoxy top coat to walls and floors - Apply selected top coat a a rate of 6.6m2/L as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Apply 2nd coat of Duropoxy SLR100 epoxy top coat to walls and floors - Apply selected top coat a a rate of 6.6m2/L as per datasheet & application guidelines
note | Attach relevant photos
checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
note | Attach relevant photos
checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
note | Attach relevant photos
checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
note | HOLDPOINT - Once all above items have been signed off work may proceed