## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | GFPS-AU - Electrofusion Installation Checklist |  | GFPS-AU - Electrofusion Installation Checklist | 502cc8d3-a392-4741-a0ad-02c4145a792c
| section | Details
| checkpoint-no-value | General Details
7985d927-869e-5fa3-aa1c-b0de39b4c29e | date | Installation Date:
1c4a1da0-0029-5ffb-873d-52685f2cd4aa | textbox | Welder’s Name:
| checkpoint | Preparation, Inspection & Materials
4ad68916-af6a-53e6-89b6-9a8d40b40866 | textbox | Pipe and fitting Batch No recorded?
86f33ea1-a46d-5c80-9b9b-075fa62e86b4 | button | Has the pipe been prepared (cleaned, inspected for dimensions and surface, cut square, deburred) and its condition (ovality, reversion) checked? | Yes,No
c41aad72-f27a-557c-8cda-87eaa7c8144e | button | Has the fitting been inspected (SDR range checked, condition confirmed) and the peeling length measured, marked, and executed with a sharp blade? | Yes,No
| checkpoint | Installation and Welding
c811c33b-2615-5b13-a3bf-9faaf339026d | button | Have the peeled areas been cleaned, insertion depth marked, and pipe insertion verified for proper alignment and annular gap? (add photo) | Yes,No
6d9fcd7a-4836-5aed-891f-7a65564c8c1d | button | Has the electrofusion welding process been completed according to the manufacturer's instructions without error messages? (add photo) | Yes,No
| checkpoint | Post-Weld Inspection
fd92a702-4442-56d4-860c-56d0e4e11da1 | button | After welding, has the joint been thoroughly inspected for overall quality, including uniform appearance, proper alignment, and adherence to specifications without visible defects? (add photo) | Yes,No
3f5be22c-4cbc-552d-b535-889a63f1be44 | button | Has a pressure test been performed on the welded joint to ensure its integrity and leak-free performance? (add photo) | Yes,No
| checklist | ITP 01 - Soft Landscaping - Landscaping |  | ITP 01 - Soft Landscaping - Landscaping | 8d69d398-e63e-4221-9865-8b8df5d6d4a0
| section | ON-STRUCTURE GARDEN BED & PLANTER INFILL
| checkpoint | 1 - Installation of Insulation Layer (for Green Roof Only)
543b2962-47cf-51ef-af6a-83d9c26f0a6a | note | Acceptance Criteria: 20mm insulation layer correctly installed, inspected, and approved by foreman. Photo evidence and docket.
e905ec88-48f3-55b8-88b6-2cb8e671e077 | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 2 - Installation of Coreflute
9b5897ba-9038-5c5d-acb6-7bfca0e6e81e | note | Acceptance Criteria: Coreflute installed as per specifications, inspected, and approved by foreman. Photo evidence.
aafbca35-7871-5637-b89f-76b58303a153 | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 3 - Geo-fabric Laying
77b15081-bbb8-512b-ae13-bbbdef382a69 | note | Acceptance Criteria: Geo-fabric properly laid out, inspected, and approved by foreman. Photo evidence.
a728fdf8-9aa9-5c32-9098-4c023b845617 | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 4 - Drainage Cell Installation
1748c9e1-670a-5f18-bc98-bae1e4a929a8 | note | Acceptance Criteria: Drainage cells installed correctly, inspected, and approved by foreman. Photo evidence.
c42b3a0b-7201-566e-a1a0-55afd90b3c57 | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 5 - Soil and Mulch Type Verification
30f7f94d-f5d5-5b56-86c7-0f53d32dc94a | note | Acceptance Criteria: Soil and mulch added to specified levels, correct type, inspected, and approved by foreman. Docket to be retained.
f084746d-4f93-5049-b509-32964d4adc92 | note | Assignees and Verification Method: Internal - Surveillance
| section | PLANTING
| checkpoint | 1 - Delivered Plant Health Inspection
7e29785b-85bd-5144-8a96-5adbf3baf0f7 | note | Acceptance Criteria: Health and accuracy verified, approved by foreman.
8df6d975-e520-563d-b5e1-fa0b4693cb87 | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 2 - Verification of Plant Layout According to Design
206b0d8f-d2ce-58f0-a5e3-a4a190969963 | note | Acceptance Criteria: Plant placement matches the design plans, approved by foreman and client.
8ca15587-6834-559a-9f62-fe79f72c20d2 | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 3 - Tree Securing and Stability Inspection
897b3a61-2af4-5a1c-8f4a-001d47f78b97 | note | Acceptance Criteria: Anchoring methods inspected, approved by foreman.
2881f69d-7944-534f-ab00-2511665e6d42 | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 4 - Installation and Inspection of Tree Inspection Risers
5a48ac0b-c217-5118-8aad-50187306aab7 | note | Acceptance Criteria: One inspection riser per tree within planters installed and inspected for compliance with specifications.
b606729f-a840-5f56-8dae-7e719e7c02e0 | note | Assignees and Verification Method: Internal - Surveillance
| section | HANDOVER
| checkpoint | 1 - ITP and Handover Approval
31a83834-7d83-5245-86f9-8520180e32eb | note | Acceptance Criteria: ITP reviewed with client, all sections signed off.
e3d489f6-caa0-5d87-9cdf-67fc0f65a1b5 | note | Assignees and Verification Method: Internal - Surveillance, Client - Surveillance
| checklist | ITP 01 - Soft Landscaping - Preliminary |  | ITP 01 - Soft Landscaping - Preliminary | c73fc23b-8760-4587-8bd7-724762281b81
| section | PRELIMINARY APPROVALS
| checkpoint | 1 - Insulation, Drainage Cell, and Geo-fabric Approval
a50a8b81-a876-544e-98fa-d2e906c2fa37 | note | Acceptance Criteria: Insulation, drainage cells, and geofabric specs submitted and approved per project requirements.
d0ea69ae-4696-5a59-acbe-15373a05f5d5 | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 2 - Soil Quality Testing
71e53065-6ef9-5051-bd02-e46e75c86e6a | note | Acceptance Criteria: Test results documented and approved.
6ac988da-c25a-5f4a-beb7-d91da6ee7f6b | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 3 - Mulch Type Approval
63ae51c8-5e3e-5073-bd07-630c3ccc8eaf | note | Acceptance Criteria: Mulch type sample and data sheet approved.
a5590f18-b99f-5eed-8586-4398fb7db907 | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 4 - Plant Substitution Approval
75bcfe5f-eeb5-521c-9e86-cf89b31289ce | note | Acceptance Criteria: Substitutes listed and approved.
13a3b320-c81d-57db-afd8-a3381b938e59 | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 5 - Nursery Visit with Architect for Plant Selection
0c49efcc-ea2f-52f5-b3a1-5ceae048da87 | note | Acceptance Criteria: Plants inspected and selection approved by the architect.
2e291e52-ad13-5aeb-9dae-e6ffcb78f96d | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checklist | ITP 02 - Various Planters (Fascade Planters/Proprietary Planters) | itp | ITP 02 - Various Planters (Fascade Planters/Proprietary Planters) | bdb5825d-10c1-4c45-b640-1ed05063c4dd
| section | PRELIMINARY APPROVALS
| checkpoint | 1 - Shop Drawings Approval
de4ec093-4ae3-5fb1-9cf4-d1d5e9c2d76e | note | Acceptance Criteria: All shop drawings submitted and approved.
8449799d-d7bb-5e59-89f9-26fa57243b50 | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 2 - Physical Samples Approval / Selections of Material including Color
46d6a72d-8689-5a74-85a3-7db11316b758 | note | Acceptance Criteria: Physical samples, material types, and color selections submitted and approved.
8f676717-36db-5dfb-b622-edbbe170a50b | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 3 - Approval of Pedestal for Planters
e275ea69-c57f-5e57-ad3c-fd76e037c196 | note | Acceptance Criteria: Specifications for pedestals, including design, load capacity, and materials, submitted and approved.
6cecd53f-9402-50e5-ba83-4b6a7750dac9 | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| section | DELIVERED GOODS INSPECTION
| checkpoint | 1 - Verification of Delivered Items Against Shop Drawings
af03eff3-4527-5470-9aa2-62ddf973c478 | note | Acceptance Criteria: Delivered items match the approved shop drawings, verified by foreman with photographic evidence.
4d792815-626f-5c63-9906-ba1b2517a798 | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 2 - Confirmation of Delivered Goods Quantities
ede91b4c-d14f-509a-9d8f-882aaa74c62d | note | Acceptance Criteria: Quantities of delivered goods align with documented requirements, confirmed by foreman's sign-off.
b2df83b9-a701-5859-b133-4116a68e79bc | note | Assignees and Verification Method: Internal - Surveillance
| section | INSTALLATION INSPECTION
| checkpoint | 1 - Compliance of Fixings on Shop Drawings
2e49221c-9f55-5f3f-a15a-7d0df9dcb6a7 | note | Acceptance Criteria: Installation of fixings verified against shop drawings, approved by foreman.
ceaa3ba4-39f1-5941-bcae-d5782cb70f39 | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 2 - Completion and Testing of Waterproofing
a71bf010-0352-5b58-a464-92a7810a8d74 | note | Acceptance Criteria: Waterproofing finished as per design and successfully tested, with foreman's approval.
2c0a21b3-9fe6-5398-9028-768394f14e35 | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 3 - Security of Planter Installations
269efb1d-75a4-50d1-8e94-12b5f95fc3c3 | note | Acceptance Criteria: Planters secured correctly as per installation guidelines, confirmed by foreman's sign-off.
1e9b8fb5-73c5-5ed6-8d4c-05e14d922812 | note | Assignees and Verification Method: Internal - Surveillance
| section | HANDOVER
| checkpoint | 1 - ITP and Handover Approval
d632da20-72eb-59fd-9d65-89a5ba08d747 | note | Acceptance Criteria: ITP reviewed with client, all sections signed off.
2aafa6ca-edb6-50b1-81a8-21dfec55ffef | note | Assignees and Verification Method: Internal - Hold Point, Client - Hold Point
| signoff | HOLD POINT
| checklist | ITP 04 - Irrigation | itp | ITP 04 - Irrigation | 18906d78-8c63-446b-9596-a404b809030a
| section | PRELIMINARY APPROVALS
| checkpoint | 1 - Design Review and Approval
4ad9ce0e-b184-59c3-9583-7e7860dab499 | note | Acceptance Criteria: Irrigation design drawing has been approved - ensure design meets plumbing requirements and is suitable for intended irrigation needs. Review by licensed plumber and sign off by client.
ba678110-c559-5ca4-85fe-d0d4957b8614 | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 2 - Material Review and Approval
48910b94-4298-598a-84d1-98576b216639 | note | Acceptance Criteria: Irrigation material samples and material types have been approved
175fded9-bc84-51cc-a02d-159ec79607af | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 3 - Coordination and Permit Acquisition for Live Area Work
44dd6e86-edc9-5f29-9e17-654b8f1bea79 | note | Acceptance Criteria: All necessary permits for work within live areas obtained. Compliance with zoning and site work plans documented through coordination efforts.
2992e66f-a752-59a7-b92a-f5f7e229587d | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| section | MATERIAL INSPECTION
| checkpoint | 1 - Inspection of Delivered Materials
bd804dbf-4421-5f75-9e97-ed81004c5e82 | note | Acceptance Criteria: Upon delivery of piping, fittings, valves, and other materials. Check for damage, ensure specifications (size, material type) match the project requirements, and materials meet approvals.
c0d1e62b-cd2d-5bcc-ab6d-9633488700e2 | note | Assignees and Verification Method: Internal - Surveillance
| section | PENETRATIONS
| checkpoint | 1 - Review of Scanning Reports for Area Penetration
6f7ad92c-b62c-5877-a024-a6c4b6301a4e | note | Acceptance Criteria: Scanning reports for areas to be penetrated are reviewed to ensure avoidance of existing services and structural elements.
05017ec0-4c57-5f65-b6d9-39736007a854 | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 2 - Engineering Approval
6d9a1ed5-7ec3-5068-85ab-c1e4a2882378 | note | Acceptance Criteria: Obtain approval from a licensed engineer for all proposed penetrations, ensuring they do not compromise structural integrity or interfere with other building services.
31c8c7d2-23ee-53dc-bd2a-2f597d408a7d | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 3 - Penetration Execution (Peno)
119e4a82-b9c3-599a-8d96-13025e3a186f | note | Acceptance Criteria: Proceed with penetrations only after engineering approval and successful scanning.
8365609a-5228-5e08-913b-782c4f0d5af8 | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 4 - Waterproofing Coordination
acfbab36-17cf-5629-8996-ffdbd2e820eb | note | Acceptance Criteria: Verify waterproofing has been completed by the designated contractor and ensure its integration with our scope of work is documented.
1be91ed1-8985-5e89-9b18-84122852d742 | note | Assignees and Verification Method: Internal - Surveillance
| section | IRRIGATION INSTALLATION
| checkpoint | 1 - Rough-In Plumbing Installation
fc13fb1a-09b3-591e-8660-8d66f1422983 | note | Acceptance Criteria: Poly pipework for water points is installed according to approved design, securely and correctly. Installation is visually inspected and approved by site plumber.
5f7d6012-75be-5321-9509-8ecfb90c2405 | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| checkpoint | 2 - Vertical Cabling for Irrigation Control
6cc90ef2-b4a2-5bf7-9931-55788df2cb6a | note | Acceptance Criteria: Ensure vertical cabling to centralized controllers is installed using scissor lifts or similar equipment under strict safety controls, with all installations matching the design.
5afe074b-4544-52e2-90ba-20d6612fe6bd | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 3 - Dripline Irrigation System Installation
0799a116-4658-5d4a-aef1-af829e26a66b | note | Acceptance Criteria: Dripline system is installed as per design, with secure placement and proper connection to water sources. System passes visual inspection, ensuring it's ready for testing.
931295bc-e72f-5bbf-b77f-95503f90177e | note | Assignees and Verification Method: Internal - Surveillance
| checkpoint | 4 - System Testing and Commissioning
61647b87-41a3-5728-9d99-50e7d1eaa447 | note | Acceptance Criteria: The irrigation system undergoes pressure testing for leaks and functional testing of automation. Testing results meet project standards, ensuring system is operational and effective.
40f178c1-b5e0-5b98-abe8-d715f790fa3d | note | Assignees and Verification Method: Internal - Hold Point
| signoff | HOLD POINT
| section | HANDOVER
| checkpoint | 1 - ITP and Handover Approval
74dc665a-166f-5ca8-9420-9ad5e0c1691d | note | Acceptance Criteria: ITP reviewed with client, all sections signed off.
543c0744-d5c3-58a5-bef1-7d8936bc99fd | note | Assignees and Verification Method: Client - Surveillance, Internal - Surveillance
| checklist | ITP-05 - Planter Fabrication (TRJ) |  | ITP-05 - Planter Fabrication (TRJ) | c1898ebe-423c-4d51-81c3-27aae5b0a9b2
| section | Fabrication Inspection
| checkpoint | 1 - Type of Planter
346ec907-fce4-5500-a256-166216843605 | textbox | Type of Planter:
1c861542-df5d-5a96-86d1-7b12dd0c62b5 | note | Acceptance Criteria: Note the type of planter being inspected by project code.
| checkpoint | 2 - Shop Drawings Approval
22da40c1-375e-5a92-b4cb-6807f96d7a6b | note | Acceptance Criteria: All shop drawings submitted and approved.
| checkpoint | 3 - Physical Samples Approval / Selections of Material including Color
ea39ac15-1fa8-54d2-b725-ad3e64076a29 | note | Acceptance Criteria: Physical samples, material types, and color selections submitted and approved including Prototype.
| checkpoint | 4 - TRJ Inspection Completion
3a90569e-1cef-5c55-8ab2-4ed0033baddd | note | Acceptance Criteria: TRJ inspection report confirms quantity, measurements, thickness, and weld quality as per approved shop drawings.
| checkpoint | 5 - Paint Quality and Application
2bebe57b-6b2a-50d0-86a7-06b52b36d796 | note | Acceptance Criteria: The color and application of paint are correct, matching design specifications without defects.
| checkpoint | 6 - Waterproofing Verification and Water Test
5a01bd7f-58eb-524b-bd7c-1735d1928408 | note | Acceptance Criteria: Waterproofing is correctly applied and has passed water testing for leaks and durability.
| checkpoint | 7 - Quantity of Production Verification
1499cf8b-d749-56c3-97ba-b1ce300a4ca9 | note | Acceptance Criteria: The quantity of produced planters aligns with the order specifications.