## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | SITE WORKS - UNDERGROUND SERVICES BLOCK A
section | Details
checkpoint | CORRECT QUANTITIES OF PIT INSTALLED AS PER UPDATED ELECTRICAL DRAWINGS
checkpoint | CORRECT QUANTITIES OF DUCTING INSTALLED AS PER UPDATED ELECTRICAL DRAWINGS
checkpoint | DUCTING INSTALLED BETWEEN MAIN EARTHING PEGS
checkpoint | DUCTING INSTALLED TO BOLLARD LIGHTS
checkpoint | MAG SLAB AND DANGER TAPE INSTALLED ABOVE POWER DUCTING AND MEETS SPECIFICATION
checkpoint | COMMS DUCTING INSTALLED INCLUDING DANGER TAPE
checkpoint | DRAW TAPE INSTALLED AS REQUIRED
checkpoint | SUFFICIENT FINES/SAP 7 IS LAID OVER DUCTING AND MEETS SPECIFICATION
checkpoint | UNDERGROUND PITS INSTALLED, LEVELLED AND DUCTING IS SEALED
checklist | BUILDING - EXTERIOR LIGHTING/POWER BLOCK B
section | Details
checkpoint | EXTERNAL BOLLARD CARPARK LIGHTS ARE CABLLED VIA DUCTING AND TO SUTIABLE LOCATION
checkpoint | INSIDE CARPARK LIGHTING CIRCUITS CABLED BACK BOARD
checkpoint | CABLING OF EXTERIOR LIGHTING COMPLETE
checkpoint | LIGHT FITTINGS CLEANED AND SEALED AGAINST WATER INGRESS
checkpoint | CONCRETE PAD INSTALLED BY BUILDERS AND PLUMBED
checkpoint | BOLLARD LIGHT INSTALLED, PLUMBED AND COMPLETED
checkpoint | POLE CAGE HOLE DUG BY BUILDER TO MANUFACTURES SPECIFICATION
checkpoint | POLE LIGHTS CAGES INSTALLED TO CORRECT HEIGHT
checkpoint | CAGE SITS PLUM AND READY FOR CONCRETE
checkpoint | POLE LIGHT INSTALLED, LEVELLED AND COMPLETED
checkpoint | APPROVED GENERATOR SUPPLY CABLE INSTALLED TO LOCATION
checkpoint | GENERATOR SUPPLY CABLE TERMINATED TO CHANGE OVER SWITCH
checkpoint | APRROVED GENERATOR SOCKET INSTALLED AND LABELLED ON EXTERNAL WALL
checkpoint | GENERATOR SOCKET IS TESTED AND CONFORMED IS WORKING CORRECTLY AS PER DESIGN
checklist | COMMUNAL AND RISER AREAS
section | Details
checkpoint | WOOD EYE ANCHORS INSTALLED AND CORRECTLY FIXED ONTO TIMBER/CONCRETE WALLS
checkpoint | SUFFICIENT CATENERY WIRE SUPPORTS INSTALLED AT APPROX 1.2M INTERVALS
checkpoint | CATENRY WIRES INSTALLED AT HIGH LEVEL AND MEETS CLEARENCE FROM OTHER SERVICES
checkpoint | TURNBUCKLES IS TIGHTENED AND CATENERY WIRE IS WELL SECURED
checkpoint | CABLE TRAY INSTALLED IN CORIDOORS AS PER DRAWINGS
checkpoint | CABLE TRAY INSTALLED AS PER SERVICE LAYOUT IN RISER
checkpoint | CABLE TRAY IS BONDED AND MEETS SPECIFICATION
checkpoint | SUB-CIRCUIT CABLES INSTALLED AS PER UPDATED ELECTRICAL DRAWING
checkpoint | SUB-CIRCUIT CABLE NEATLY DRESSED ON CATNERY WIRES AND HILTI CLIPS
checkpoint | SUB-MAINS CABLE INSTALLED NEATLY ON TRAY AND HILTI CLIPS INTO APARTMENTS
checkpoint | CONDUIT INSTALLED NEATLY WHERE REQUIRED
checkpoint | COMMUNAL AND STAIRCASE SENSORS CABLED BACK TO DB-LL
checkpoint | LIGHTING CIRCUITS CABLED BACK TO DB-LL FOR EACH FLOOR AND STAIRCASE
checkpoint | POWER CIRCUITS CABLED BACK TO DB-LL FOR EACH FLOOR
checkpoint | LIGHTS AND SENSORS INSTALLED AS PER RCP
checkpoint | EMERGENCY LIGHTS INSTALLED AND LABELLED
checkpoint | POWER OUTLETS INSTALLED AND LABELLED
checkpoint | LIGHTS AND SENSORS INSTALLED
checkpoint | LIGHTS INSTALLED AND COMPLETED
checkpoint | SENSORS INSTALLED AND COMPLETED
checkpoint | EMERGECY LIGHTS INSTALLED AND COMPLETED
checkpoint | POWER POINTS INSTALLED AND COMPLETED
checklist | APARTMENT 1ST FIX
section | Details
checkpoint | SETOUT + FLUSHBOXES INSTALLED/COMPLETE AS PER ARCHITECTURAL/SC SET OUT
checkpoint | KTICHEN SET OUT CONFIMRED AND FLUSH BOXES INSTALLED AS PER ELEVATION AND SC
checkpoint | HILTI CLIPS INSTALLED ALONG CABLE ROUTE
checkpoint | LIGHTING PREWIRED AS PER APARTMENT TYPE LAYOUT
checkpoint | POWER CABLE INSTALLED AS PER APARTMENT TYPE LAYOUT
checkpoint | LIGHTING AND POWER FEEDS CONTINEOUS BACK TO APARTMENT DB
checkpoint | CABLES PROTECTED WITH FLEXIABLE CONDUIT INTO WALLS
checkpoint | SUB MAINS INSTALLED AND CLEAR FROM OTHER SERVIES
checkpoint | SUB MAINS CABLE TILED NEATLY ON HILTI CLIPS
checkpoint | SUB CIRCUITS CABLE TIED NEATLY ON HILTI CLIPS
checkpoint | EARTH CABLE INSTALLED FOR KITCHEN, LAUNDRY AND SHOWER TRAY
checkpoint | SHOWER TRAY BONDED AND COMPLETED BEFORE PRE LINE
checkpoint | EARTH CABLE BROUGHT OUT THROUGH TIMBER TO CORRECT LOCATION AS ELEVATION
checkpoint | CEILING STRUCTURE BONDED
checkpoint | APARTMENT DB INSTALLED AS PER AGREED LOCATION
checklist | APARTMENT 2ND FIX
section | Details
checkpoint | EQUIPMENT APPLIANCE ISOLATORS INSTALLED COMPLETED
checkpoint | KITCHEN OUTLETS INSTALLED AND COMPLETED
checkpoint | HWC KIT INSTALLED AND COMPLETED
checkpoint | LIGHT SWITCHES INSTALLED AND COMPLETED
checkpoint | POWER OUTLETS INSTALLED AND COMPLETED
checkpoint | LIGHTS INSTALLED AND COMPLETED
checkpoint | KITCHEN/CEILING AND LAUNDRY SINK BONDED
checkpoint | APARTMENT PRE-LIVENING TEST COMPLETED AND ADDED TO DROP BOX
checkpoint | APARTMENT SUB CIRCUTIS TEST COMPLETED AND ADDED TO DROP BOX
checkpoint | BONDING TEST COMPLETED AND ADDED TO DROP BOX
checkpoint | APARTMENT SUB MAINS TERMINATED
checkpoint | SUB MAINS PRE-LIVENING CHECK COMPLETED AND ADDED TO DROP BOX
checkpoint | SUB-MAINS POST-LIVENING CHECK COMPLETED AND ADDED TO DROP BOX
checkpoint | AS-BUILT UPDATED AND COMPLETED
checklist | COMMS ROOM
section | Details
checkpoint | CONDUITS INSTALLED TO LIGHTS, LIGHT SWITCH AND POWER OUTLETS
checkpoint | CONDUITS INSTALLED NEATLY ON CEILING AND WALLS
checkpoint | CONDUITS A CLEAR FROM OTHER SERVICES AND MEETS SPECIFICATON
checkpoint | CABLING INSTALLED AS PER DB SCHEDULE
checkpoint | LIGHTS INSTALLED
checkpoint | POWER OUTLETS TESTED AND LABELLED
checkpoint | LIGHT SWITCH LABELLED AND WORKING CORRECTLY TO SENSOR AND LIGHTS
checkpoint | TEST RESULTS ENTERED ONTO COMMISSIONING TESTSHEET
checklist | MSB ROOM
section | Details
checkpoint | CABLE TRAY INSTALLED AS PER DRAWINGS
checkpoint | CONDUITS INSTALLED TO LIGHTS, LIGHT SWITCH AND POWER OUTLETS
checkpoint | CONDUITS INSTALLED NEATLY ON CEILING AND WALLS
checkpoint | CONDUITS A CLEAR FROM OTHER SERVICES AND MEETS SPECIFICATON
checkpoint | CABLING INSTALLED AS PER DB SCHEDULE
checkpoint | EMERGENCY LIGHTS INSTALLED, TERMINATED AND LABELLED
checkpoint | LIGHTS INSTALLED AND WORKING VIA SENSOR
checkpoint | POWER OUTLETS TESTED AND LABELLED
checkpoint | LIGHT SWITCH LABELLED AND WORKING CORRECTLY TO SENSOR AND LIGHTS
checkpoint | TEST RESULTS ENTERED ONTO COMMISSIONING TESTSHEET
checklist | MOBILITITY SCOOTER, WASTE ROOM & FIRE ALARM PUMP ROOM
section | Details
checkpoint | CONDUITS INSTALLED TO LIGHT, LIGHT SWITCH AND POWER OUTLET
checkpoint | CONDUITS INSTALLED NEATLY ON CEILING AND WALLS
checkpoint | CONDUITS A CLEAR FROM OTHER SERVICES AND MEETS SPECIFICATON
checkpoint | CABLING INSTALLED AS PER DB SCHEDULE FOR FAP
checkpoint | LIGHTS INSTALLED AND WORKING
checkpoint | POWER OUTLETS TESTED AND LABELLED
checkpoint | LIGHT SWITCH'S LABELLED AND WORKING CORRECTLY TO LIGHT
checklist | COMMUNAL ROOM 1ST FIX
section | Details
checkpoint | SETOUT + FLUSHBOXES INSTALLED/COMPLETE AS PER ARCHITECTURAL/SC SET OUT
checkpoint | KTICHEN SET OUT CONFIMRED AND FLUSH BOXES INSTALLED AS PER ELEVATION AND SC
checkpoint | HILTI CLIPS INSTALLED ALONG CABLE ROUTE
checkpoint | LIGHTING PREWIRED AS PER APARTMENT TYPE LAYOUT
checkpoint | POWER CABLE INSTALLED AS PER APARTMENT TYPE LAYOUT
checkpoint | LIGHTING AND POWER FEEDS CONTINEOUS BACK TO APARTMENT DB
checkpoint | CABLES PROTECTED WITH FLEXIABLE CONDUIT INTO WALLS
checkpoint | SUB MAINS INSTALLED AND CLEAR FROM OTHER SERVIES
checkpoint | SUB MAINS CABLE TILED NEATLY ON HILTI CLIPS
checkpoint | SUB CIRCUITS CABLE TIED NEATLY ON HILTI CLIPS
checkpoint | EARTH CABLE INSTALLED FOR KITCHEN, LAUNDRY AND SHOWER TRAY
checkpoint | SHOWER TRAY BONDED AND COMPLETED BEFORE PRE LINE
checkpoint | EARTH CABLE BROUGHT OUT THROUGH TIMBER TO CORRECT LOCATION AS ELEVATION
checkpoint | CEILING STRUCTURE BONDED
checkpoint | APARTMENT DB INSTALLED AS PER AGREED LOCATION
checklist | COMMUNAL ROOM 2ND FIX
section | Details
checkpoint | EQUIPMENT APPLIANCE ISOLATRS INSTALLED COMPLETED
checkpoint | KITCHEN OUTLETS INSTALLED AND COMPLETED
checkpoint | HWC KIT INSTALLED AND COMPLETED
checkpoint | LIGHT SWITCHES INSTALLED AND COMPLETED
checkpoint | POWER OUTLETS INSTALLED AND COMPLETED
checkpoint | LIGHTS INSTALLED AND COMPLETED
checkpoint | KITCHEN/CEILING AND LAUNDRY SINK BONDED
checkpoint | APARTMENT PRE-LIVENING TEST COMPLETED AND ADDED TO DROP BOX
checkpoint | APARTMENT SUB CIRCUTIS TEST COMPLETED AND ADDED TO DROP BOX
checkpoint | BONDING TEST COMPLETED AND ADDED TO DROP BOX
checkpoint | APARTMENT SUB MAINS TERMINATED
checkpoint | SUB MAINS PRE-LIVENING CHECK COMPLETED AND ADDED TO DROP BOX
checkpoint | SUB-MAINS POST-LIVENING CHECK COMPLETED AND ADDED TO DROP BOX
checkpoint | AS-BUILT UPDATED AND COMPLETED
checklist | DISTRIBUTION BOARD - MAIN SWITCHBOARD
section | Details
checkpoint | MAIN SWITCHBOARD INSTALLED ON TIMBER PLINTH AND SECURED
checkpoint | COMPRESSION GLANDS INSTALLED AND SECURE FOR CABLE ENTRY
checkpoint | NEW MAINS CABLE INSTALLED, LUGGED, TERMINATED
checkpoint | SUB-MAINS CABLE INSTALLED, LUGGED, TERMINATED
checkpoint | MAIN EARTH CABLE LUGGED, BOLTED AND HAS A MAIN EARTH TAG INSTALLED
checkpoint | MEN LINK IS INSTALLED AND CONFIMED
checkpoint | SUFFICIENT EARTH STAKE INSTALLED AND MAIN EARTH GROUND READING IS GOOD
checkpoint | MAIN EARTH INSPECTION PITS INSTALLED AND AT CORRECT HEIGHT AND COMPLETED
checkpoint | STRUCTURAL BONDING CABLE TERMINATED AT SWITCHBOARD
checkpoint | MAIN SWITCHBOARD IS CLEAN OF ALL DEBRI AND MARKS
checklist | DISTRIBUTION BOARD
section | Details
checkpoint | DISTRIBUTION BOARD INSTALLATION COMPLETED AND SECURELY MOUNTED
checkpoint | SUB-MAINS CABLE TERMINATED
checkpoint | APARTMENT SUB-MAINS CABLE TERMINATED INCLUDING LABELLING TO ALL CORES
checkpoint | SUB-MAINS EARTH AND NEUTRAL LUGGED AND TERMINATED
checkpoint | GENERATOR OUTLET CABLE INSTALLED AS PER SC
checkpoint | GENERATOR OUTLETS INSTALLED AS PER SC
checkpoint | LIFT POWER INSTALLED AS PER SLD
checkpoint | FAP INSTALLED AS PER SLD
checkpoint | STRUCTURAL BONDING CABLE TERMINATED AT SWITCHBOARD
checkpoint | SUB-CIRCUITS CABLE TERMINATED INTO LANDLORD
checkpoint | DISTRIBUTION BOARD TEST SHEET COMPLETED
checkpoint | CLEAN OF ALL DEBRI AND MARKS
checklist | COMMISSIONING
section | Details
checkpoint | VISUAL INSPECTION
checkpoint | CONTINUITY OF CICUIT PROTECTIVE CONDUCTORS
checkpoint | CONTINUITY OF BONDING CONDUCTORS
checkpoint | POLARITY
checkpoint | INSULATION RESISTANCE
checkpoint | EARTH FAULT LOOP IMPEDANCE
checkpoint | PFC
checkpoint | RCD
checklist | BUILDING STRUCTURAL BONDING
section | Details
checkpoint | BUILDING STRUCTURAL BOND INSTALLED AND COMPLETED TO AS/NZS 3000;2007
checkpoint | RISER CABLE TRAY BONDED AND COMPLETED TO AS/NZS 3000:2007
checkpoint | SPRINKLER PIPE BONDED AND COMPLETED TO AS/NZS 3000;2007
checkpoint | PLUMBERS COPPER PIPE BONDED AND COMPLETED TO AS/NZS 3000;2007