## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | UNDERGROUND SERVICES, EXTERIOR LIGHTING POWER AND CONTAINMENT
section | Details
checkpoint | DUCTING INSTALLED AS REQUIRED
checkpoint | ALL CONDUIT INSTALLED AS SHOWN
checkpoint | ALL EXTERIOR LIGHTING CABLED
checkpoint | ALL EXTERIOR LIGHTING INSTALLED
checkpoint | ALL EXTERIOR POWER CABLED
checkpoint | ALL EXTERIOR POWER INSTALLED
checklist | 1ST FIX
section | Details
checkpoint | SETTING OUT
checkpoint | INSTALLATION OF CATENARY WIRES
checkpoint | VOLT DROP CALCULATIONS WORKED OUT PRIOR TO COMMENCEMENT OF CABLING
checkpoint | LIGHTING CABLING INSTALLED AND LABELLED AS PER PLANS
checkpoint | LIGHTING CONTROL CABLING INSTALLED AND LABELLED AS PER PLANS
checkpoint | EMERGENCY LIGHTING CABLING INSTALLED AND LABELLED AS PER PLANS
checkpoint | POWER CABLING INSTALLED AND LABELLED AS PER PLANS
checkpoint | BONDING CABLING INSTALLED AND LABELLED AS PER PLANS
checkpoint | DATA CABLING INSTALLED AND LABELLED AS PER PLANS
checkpoint | DATA CABLING IN WAREHOUSE
checkpoint | AV CABLING INSTALLED AND LABELLED AS PER PLANS
checkpoint | DATA CABLES ARE RUN ON A SEPARATE CAT WIRE, VELCRO TIED IN 24 DATA CABLES PER BUNDLE
checkpoint | FLUSH BOXES MOUNTED AS PER ARCHITECTURAL ELEVATION
checkpoint | FLUSH BOXES FOR ISOLATORS INSTALLED ABOVE BENCH OR AT ACCESSIABLE LOCATION TO APPLIANCE
checkpoint | FEED AND SWITCH WIRES INSTALLED AND CONFIMRED FOR LIGHTING
checkpoint | FIRE RATED FLUSH BOXES INSTALLED WHERE APPLICABLE
checkpoint | ACCOUSTIC BOXES INSTALLED WHERE APPLICABLE
checkpoint | DEEP MOUNTING BLOCKS INSTALLED ON TRUNKING FOR COMPLIANCE WITH DATA WARRANTY
checkpoint | HOTWATER CABLE INSTALLED AND LOCATION CONFIMRED WITH PLUMBER
checkpoint | APPLIANCE ISOLATORS INSTALLED A/B OR AT ACCESSIBLE LOCATION
checkpoint | SWITCH LOCATIONS CONFIRMED AND IS ACCESSIABLE UPON ENTRY TO ROOM
checkpoint | ALL CABLES ARE CABLE TIED NEATLY ON CATENARY WIRES AND MEETS SPECIFICATION
checkpoint | FEATURE LIGHTING NOG MARKED AND INSTALLED
checkpoint | FLOORBOXES MARKED AND PENETRATIONS COMPLETE
checkpoint | BOOK DATA WARRANTY SITE VISIT
checklist | 2ND FIX
section | Details
checkpoint | LIGHT SWITCHES INSTALLED, LEVELLED, LABELLED AND LIVE
checkpoint | LCP PANEL IS FITTED OFF AND LIGHTS ARE SWITCHING CORRECTLY.
checkpoint | SENSORS INSTALLED
checkpoint | SURFACE SOCKETS FITTED OFF FOR PAN FITTINGS, DOWNLIGHTS AND EMERGENCY LIGHTS
checkpoint | SURFACE SOCKETS ARE LABELLED TO ALLOCATED CIRCUITS CORRECTLY
checkpoint | PAN FITTINGS, DOWNLIGHTS AND EMERGENCY LIGHTS ARE INSTALLED IN CORRECT LOCATIONS.
checkpoint | EMERGENCY LIGHTS INSTALLED, LABELLED, LIVE AND WORKING CORRECTLY.
checkpoint | FEATURE LIGHTS INSTALLED SECURLY SUSPENDED OR SURFACE MOUNT ONTO PLY BEHINF CEILING GRID
checkpoint | POWER OUTLETS INSTALLED, LEVELLED, LABELLED AND LIVE
checkpoint | ISOLATION SWITCHES INSTALLED LEVELLED, LABELLED AND LIVE
checkpoint | APPLIANCES CONNECTED
checkpoint | DATA OUTLETS INSTALLED, LEVELLED, LABELLED AND TESTED.
checkpoint | DATA OUTLETS IN WAREHOUSE INSTALLED, LEVELLED, LABELLED AND TESTED.
checkpoint | CEILING GRID/SINKS/ BUILDING STRUCTURE IS BONDED AND TEST RESULTS < 0.5 OHMS TO DB
checkpoint | INSTALLATION OF FLOOR BOXES
checklist | DISTRIBUTION BOARD DB2
section | Details
checkpoint | SUBMAIN FROM MSB INSTALLED AS PER PLANS AND SPECIFICATION
checkpoint | CABLE TRAY/TRUNKING INSTALLED ABOVE DB FOR SUB CIRCUITS AND NEW SUB MAINS.
checkpoint | SUB CIRCUITS TIED AND DRESSSED NEATLY ON CAT WIRE/CABLE TRAY/TRUNKING
checkpoint | SUBCIRCUITS TERMINATED INCLUDING LABELLING/FERRULES TO ALL CORES
checkpoint | EARTHING/BONDING TERMINATED
checkpoint | STRUCTURAL BONDING CABLE TERMINATED AT SWITCHBOARD.
checkpoint | DB SCHEDULE COMPLETED
checkpoint | DISTRIBUTION BOARD TEST SHEET COMPLETED
checkpoint | DB SCHEDULE INSTALLED
checkpoint | CLEAN OF ALL DEBRIS AND MARKS
checkpoint | DISTRIBUTION BOARD MADE AS PER SHOP DRAWINGS
checkpoint | NABERS METERING INSTALLED
checkpoint | NABERS METERING CABLED AND COMMISSIONED
checklist | COMMISSIONING - DISTRIBUTION BOARD DB2
section | Details
checkpoint | SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
checkpoint | DB SCHEDULE COMPLETED, INSTALLED INTO DB AND ADDED TO DROPBOX
checkpoint | DISTRIBUTION BOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
checkpoint | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX
checkpoint | DISTRIBUTION BOARD CHECK SHEET COMPLETED AND ADDED TO DROPBOX
checkpoint | EARTHING TEST SHEET COMPLETED AND ADDED TO DROPBOX
checkpoint | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
checkpoint | TIMECLOCK TEST SHEET COMPLETED AND ADDED TO DROPBOX
checkpoint | BOARD FREE FROM DEBRIS, NO MARKS, ALL ACCESSORIES INSTALLED
checkpoint | LABELLING COMPLETED ON ALL FIELD OUTLETS, SWITCHES AND ISOLATORS ETC
checkpoint | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
checkpoint | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX
checkpoint | TEST - CONTINUITY OF CIRCUIT PROTECTIVE CONDUCTOR
checkpoint | TEST - CONTINUIT OF BONDING
checkpoint | TEST - INSULATION RESISTANCE
checkpoint | TEST - POLARITY
checkpoint | TEST - EARTH FAULT LOOP IMPEDANCE
checkpoint | TEST - PFC
checkpoint | TEST - RCD
checklist | COMMS CABINET
section | Details
checkpoint | COMMS CABINET MOUNTED AT AGREED LOCATION
checkpoint | ALL DATA OUTLETS ARE FITTED OFF AND LABELLED.
checkpoint | ALL DATA CABLES TERMINATED INTO PATCH PANEL
checkpoint | ALL DATA CABLES ARE TESTED AND LABELLED CORRECTLY
checkpoint | FRONT OF PATCH PANELS ARE LABELLED CORRECTLY TO FIELD OUTELTS AND CONFIRMED
checkpoint | BOOK WARRANTY INSPECTION