## ITP COVER PAGE
Ducting & Pit Inspcection and Test Plan
Project: Wellesley St Bus Interchange - WSBI
Number and Revision: DN1211 - DN1211-ITP-014 - Rev For Review-00
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Wellesley St Bus Interchange - WSBI |  |  |  |  | ITP Number: |  |  | DN1211-ITP-014
Project Number: |  |  | DN1211 |  |  |  |  | ITP Status: |  |  | For Review
ITP Description: |  |  | Pavement Quality Concrete (PQC) |  |  |  |  | Revision: | 1000 |  | For Review-00
Contract Number: |  |  | WSBI |  |  |  |  | Drawing Sets:
Customer: |  |  | Auckland Transport |  |  |  |  | Specification:
Quality Specified:
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | For Review | 2025-02-27 |  | R.Collier |  | Compiled draft |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | DES | Designer
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer CM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) |  | AT/MSQA | [5 empty] | Client (If Applicable) |  | AT/MSQA

## ITP
[7 empty] | ITP- | Earthworks (Excavation, Subgrade and Sub-Base)
[7 empty] | Project- | WSBI - 1211
[7 empty] | ITP No.- | ITP-008
[7 empty] | Revision- | Rev-01
Item No. | Inspection and Test Point | Acceptance/Conformance criteria | Standard/Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Engineer Rep Signature (Blank as req.) | MSQA (Blank as req.) | Comments/Closeout Details
SECTION 3 - PRE CONTRUCTION (P&G/ESTABLISHMENT)
3.1 | Mix Design | Details of the proposed mix which include the following: materials sources, test certificates and specified results, 7-day and 28-day compressive and flexural strength results for proposed mixes. PQC mix design requirements below or as approved: ‐ Nominal aggregate size 19mm, GP Portland cement as per NZS 3122 ‐ Target slump of 80mm +/‐20mm for truck mixes, 120mm +/‐30mm for pump mixes; ‐ Target flexural strength of 5.0MPa at 28 days (min 4.8MPa) and 4.5Mpa at 7 days; ‐ Entrained air content of 1.5‐2.0%; ‐ Black oxide and McCallum red chip aggregate % content to be confirmed by landscape architect following preparation of sample panels); ‐ Aggregate source properties as per spec; target aggregate particle size distribution (PSD) as specified in Table 11‐1 and supplied within production tolerances in Table 11‐2 | Aurecon Civil Spec; Section 10.3 NZS 3121, NZS 3122 | Mix Design Report Approval and Supplier QA (source properties) | Each Mix prior to Use | H | SE |  |  | W | H
SECTION 4 - MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.1 | Exposed Aggregate Concrete | Areas designated for exposed aggregate finish as per ITP Item 8.1 and subject to additional concrete mix design requirements: -Crushed or pebble/round aggregates, gap graded (source properties as per NZS 3121). - Colour and target exposure depth to be confirmed following preparation of sample panels (0.6mm minimum texture depth) | NZS 3114 | Each Mix prior to Use | Mix Design Report and Trial | H | SE |  |  | W | H
4.2 | Concrete Joint Materials | Dowel bars (rounds), mesh, reinforcing, formwork sections, plate edging, and crack inducers installed full length of slab as per drawings. Joint fillers and sealants supplied as per drawing. Joint seal with Dow Corning 888 silicone joint sealant (grey) or equivalent approved. Test for surface adhesion as part of construction trial. Sealant colour to match colour of jointing mortar | Aurecon Civil Spec; Section 10.3 AS/NZS 4671 | Initial products/ alternatives to be proposed | Mill certs and material supply records | W | SE |  |  | _ | I
4.3 | Construction Trial | Construction trial of at least 3No. adjacent slabs prior to main slab construction. QA checks incorporated in Pre Pour and Post Pour Inspection submitted for Engineer's Approval of the construction quality; placing, compaction and finishing | Aurecon Civil Spec; Section 10.6.3 | Three adjacent slabs, prior to commencemen | QA Sheet Photos | H | SE |  |  | H | H
4.4 | Pre‐pour inspection | Engineer to be notified 24 hours prior pour, and pre pour inspection records to be readily available for inspection upon request. | Civil Spec Section 10.4.1 | Pre Pour Inspection for each sectio | _ | H | SE |  |  | W | I
SECTION 5 - CONSTRUCTION ACTIVITY
| Subgrade preparation | Subgrade to be prepared as per ITP-003 Subgrade to be +0/-30mm CIV Clegg ≥ 10 CIV All utility conduits to be lowered to below Subgrade level unless written authorisation from the Engineer received. Proof roll to be undertaken with a Fully loaded 6 wheeler truck (10 tonnes) to check for any visible deflection. Where deflection is noted the Engineer is to be notified. | Aurecon Civil Spec 6.1 | Clegg dipsheet and visual onsite inspection by Aurecon Engineer | 1 Clegg per 10m and Site observation pass by Aurecon engineer | H | SE |  |  | R | W
| Lean Mix appliciation | Lean mix to have Minimum 28 day crompressive strength of 5Mpa and not greater than 10Mpa Lean mix to be not to be placed in temperatures exceeding 30 degrees in the shade. Lean mix layer to have micro cracking induced through means of rolling prior to placement of PQC layer. As per DN1211-Aurecon-RFI-R-0102 200 Micro thick Polythene sheeting to be placed overlapping beneath concrete slabs | Aurecon Civil Spec 10.3 | Photos of Polythene sheeting | Once during | H | SE |  |  | R | W
5.1 | Concrete Placement | Maximum temperature of 30°C when placed Survey pins set for level control and stringline checked prior to pour. Concrete to vibrated in‐situ to ensure good compaction, especially at joints. Concrete depth to be no less than design thickness and FL within tolerance of +/‐5mm Post‐compaction and screeding; Light broom finished at right angles to direction of traffic. Exposed aggregate finish as specified on architectural drawings (refer spec) | Aurecon Civil Spec Section 10.5.3 | Stringline checks/Survey before and Post pour. On site review and QA sheet | Before and During each pour lot | W | SV |  |  | _ | I
5.2 | Flexural Strength | The flexural strength of concrete produced shall be measured by testing 4No. flexural beams; 2No. at 7 days and 2No. 28 days. Testing results submitted to Engineer which to confirm minimum 4.8MPa achieved. Testing to be complete by IANZ lab. | Aurecon Civil Spec; Section 10.5.8 | QA Sheet Truck dockets IANZ Lab Reports | Every 50m3 / daily | W | SE |  |  | R | R
SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.1 | Concrete density testing | Acceptance of pavement with respect to density shall be based upon the results of density tests carried out on flexural test beams, and on 6 cores with 28 days of age cut from a pavement lot by the Contractor in accordance with AS1012.12.1. If the ratio of the core density to the average density of the flexural test beams exceeds 98.5%, then the lot shall be deemed to comply with density requirements. If the ratio of the core density to the average density of the flexural test beams is less than 97.0%, then the lot shall be deemed to be nonconforming with respect to density requirements. Testing to be complete by IANZ lab. | Aurecon Civil Spec; Section 10.6.5 | 6No. Cores from 1 lot at locations approved by the Engineer | QA Sheet IANZ Lab Reports | W | PE |  |  | R | R
6.2 | Finish Tolerances | Concrete curing for at least 5 days. Form removal after at least 12 hours. Post Pour Inspection to be submitted for Engineer's acknowledgement showing finished concrete is within tolerances (Surface Level +/‐5mm), and construction joints have been inspected prior to paving Surface smoothness checked with 3.0m straight edge, no deviation greater than 3mm (5mm for LABI) to ensure no areas will pond water. Sawcut contraction joints 1/4 to 1/3 depth of slab and seal as per drawings (every 10m or as specified). Apply compressible joint filler at exposed faces as required for subsequent pours | Aurecon Civil Spec; Section 10.5.8 | Post Pour Inspection for each section Survey corner of each slab and along crown at 300mm spacing | As‐Built final surface QA Sheet | H | SV |  |  | W | H
6.3 | Architectural Finishing and Sealing | Light acid wash exposed concrete pavement surfaces with muriatic acid to remove stains and prep surface for sealing. Opportunity for architect/Engineers Rep to review clean surface prior to final sealing. Concrete pavements to be sealed with "MIS Stone Age Wetlook penetrating sealer", applied at per manufacturer's instructions | Aurecon Civil Spec; Section 10.5.5,10.5.6 | Prior to final sealing | Visual Check | W | SE |  |  | I | I
6.4 | Survey Record | Installation of works under contract completed compliant in accordance with all relevant regulations, COP and standards | Design Specification / Downer | QA Checksheet Redlines | Post Construction | H | ENG |  |  | H | R
6.5 | Redline Drawings | Ensure all items have been installed create a Redline Drawings for Asbuilt creation noting all changes with RFI numbers and departures in red pen | Downer | Redlines | Post Construction | H | ENG |  |  | H | R
6.6 | Defect, Snag and Punch List | Update the project defects, snag and punch list register | Downer | Redlines | Post Construction | H | ENG |  |  | H | R
SECTION 7 - SIGN OFF
|  | Customer Release Granted: |  | ☐ Yes | ☐ No | Date:
Certificate Number: