## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1211-008 ITP Pavement Quality Concrete (PQC) | itp |  |  |  |  | DN1211-008 ITP Pavement Quality Concrete (PQC) Rev 1
section | SECTION 3 - PRE CONTRUCTION (P&G/ESTABLISHMENT)
checkpoint | 3.1 - Mix Design
label | Acceptance / Conformance Criteria - Details of the proposed mix which include the following: Materials sources, test certificates and specified results, 7-day and 28-day compressive and flexural strength results for proposed mixes.
label | ○ PQC mix design requirements below or as approved:
label | — Nominal aggregate size 19mm, GP Portland cement as per NZS 3122
label | — Target slump of 80mm +/‐20mm for truck mixes, 120mm +/‐30mm for pump mixes;
label | — Target flexural strength of 5.0MPa at 28 days (min 4.8MPa) and 4.5Mpa at 7 days;
label | — Entrained air content of 1.5‐2.0%;
label | — Black oxide and McCallum red chip aggregate % content to be confirmed by landscape architect following preparation of sample panels);
label | — Aggregate source properties as per spec; target aggregate particle size distribution (PSD) as specified in Table 11‐1 and supplied within production tolerances in Table 11‐2
label | Standard / Specification - Aurecon Civil Spec; Section 10.3 NZS 3121, NZS 3122
label | Verifying Document - Mix Design Report Approval and Supplier QA (source properties)
label | Frequency - Each Mix prior to Use
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Engineer Rep Signature (Blank as req.) - W
label | MSQA (Blank as req.) - H
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 - MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.1 - Exposed Aggregate Concrete
label | Acceptance / Conformance Criteria - Areas designated for exposed aggregate finish as per ITP Item 8.1 and subject to additional concrete mix design requirements:
label | — Crushed or pebble/round aggregates, gap graded (source properties as per NZS 3121).
label | — Colour and target exposure depth to be confirmed following preparation of sample panels (0.6mm minimum texture depth)
label | Standard / Specification - NZS 3114
label | Verifying Document - Each Mix prior to Use
label | Frequency - Mix Design Report and Trial
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Engineer Rep Signature (Blank as req.) - W
label | MSQA (Blank as req.) - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Concrete Joint Materials
label | Acceptance / Conformance Criteria - Dowel bars (rounds), mesh, reinforcing, formwork sections, plate edging, and crack inducers installed full length of slab as per drawings.
label | ○ Joint fillers and sealants supplied as per drawing. Joint seal with Dow Corning 888 silicone joint sealant (grey) or equivalent approved. Test for surface adhesion as part of construction trial.
label | ○ Sealant colour to match colour of jointing mortar
label | Standard / Specification - Aurecon Civil Spec; Section 10.3 AS/NZS 4671
label | Verifying Document - Initial products / alternatives to be proposed
label | Frequency - Mill certs and material supply records
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
label | MSQA (Blank as req.) - I
checkpoint | 4.3 - Construction Trial
label | Acceptance / Conformance Criteria - Construction trial of at least 3No. adjacent slabs prior to main slab construction. QA checks incorporated in Pre Pour and Post Pour Inspection submitted for Engineer's Approval of the construction quality; placing, compaction and finishing
label | Standard / Specification - Aurecon Civil Spec; Section 10.6.3
label | Verifying Document - Three adjacent slabs, prior to commencement
label | Frequency - QA Sheet, Photos
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Engineer Rep Signature (Blank as req.) - H
label | MSQA (Blank as req.) - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Pre‐pour inspection
label | Acceptance / Conformance Criteria - Engineer to be notified 24 hours prior pour, and pre pour inspection records to be readily available for inspection upon request.
label | Standard / Specification - Civil Spec Section 10.4.1
label | Verifying Document - Pre Pour Inspection for each section
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Engineer Rep Signature (Blank as req.) - W
label | MSQA (Blank as req.) - I
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 - CONSTRUCTION ACTIVITY
checkpoint | Subgrade preparation
label | Acceptance / Conformance Criteria - Subgrade to be prepared as per ITP-003
label | ○ Subgrade to be +0/-30mm
label | ○ CIV Clegg ≥ 10 CIV
label | ○ All utility conduits to be lowered to below Subgrade level unless written authorisation from the Engineer received.
label | ○ Proof roll to be undertaken with a Fully loaded 6 wheeler truck (10 tonnes) to check for any visible deflection. Where deflection is noted the Engineer is to be notified.
label | Standard / Specification - Aurecon Civil Spec 6.1
label | Verifying Document - Clegg dipsheet and visual onsite inspection by Aurecon Engineer
label | Frequency - 1 Clegg per 10m and Site observation pass by Aurecon engineer
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Engineer Rep Signature (Blank as req.) - R
label | MSQA (Blank as req.) - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Lean Mix appliciation
label | Acceptance / Conformance Criteria - Lean mix to have Minimum 28 day crompressive strength of 5Mpa and not greater than 10Mpa
label | ○ Lean mix to be not to be placed in temperatures exceeding 30 degrees in the shade.
label | ○ Lean mix layer to have micro cracking induced through means of rolling prior to placement of PQC layer. As per DN1211-Aurecon-RFI-R-0102
label | ○ 200 Micro thick Polythene sheeting to be placed overlapping beneath concrete slabs
label | Standard / Specification - Aurecon Civil Spec 10.3
label | Verifying Document - Photos of Polythene sheeting
label | Frequency - Once during
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Engineer Rep Signature (Blank as req.) - R
label | MSQA (Blank as req.) - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1 - Concrete Placement
label | Acceptance / Conformance Criteria - Maximum temperature of 30°C when placed
label | Survey pins set for level control and stringline checked prior to pour.
label | Concrete to vibrated in‐situ to ensure good compaction, especially at joints. Concrete depth to be no less than design thickness and FL within tolerance of +/‐5mm Post‐compaction and screeding; Light broom finished at right angles to direction of traffic. Exposed aggregate finish as specified on architectural drawings (refer spec)
label | Standard / Specification - Aurecon Civil Spec Section 10.5.3
label | Verifying Document - Stringline checks/Survey before and Post pour. On site review and QA sheet
label | Frequency - Before and During each pour lot
label | Verification Activity: Activity - W
label | Verification Activity: By - SV
label | MSQA (Blank as req.) - I
checkpoint | 5.2 - Flexural Strength
label | Acceptance / Conformance Criteria - The flexural strength of concrete produced shall be measured by testing 4No. flexural beams; 2No. at 7 days and 2No. 28 days.
label | ○ Testing results submitted to Engineer which to confirm minimum 4.8MPa achieved. Testing to be complete by IANZ lab.
label | Standard / Specification - Aurecon Civil Spec; Section 10.5.8
label | Verifying Document - QA Sheet, Truck dockets, IANZ Lab Reports
label | Frequency - Every 50m3 / daily
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
label | Engineer Rep Signature (Blank as req.) - R
label | MSQA (Blank as req.) - R
section | SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.1 - Concrete density testing
label | Acceptance / Conformance Criteria - Acceptance of pavement with respect to density shall be based upon the results of density tests carried out on flexural test beams, and on 6 cores with 28 days of age cut from a pavement lot by the Contractor in accordance with AS1012.12.1. If the ratio of the core density to the average density of the flexural test beams exceeds 98.5%, then the lot shall be deemed to comply with density requirements. If the ratio of the core density to the average density of the flexural test beams is less than 97.0%, then the lot shall be deemed to be nonconforming with respect to density requirements. Testing to be complete by IANZ lab.
label | Standard / Specification - Aurecon Civil Spec; Section 10.6.5
label | Verifying Document - 6No. Cores from 1 lot at locations approved by the Engineer
label | Frequency - QA Sheet, IANZ Lab Reports
label | Verification Activity: Activity - W
label | Verification Activity: By - PE
label | Engineer Rep Signature (Blank as req.) - R
label | MSQA (Blank as req.) - R
checkpoint | 6.2 - Finish Tolerances
label | Acceptance / Conformance Criteria - Concrete curing for at least 5 days. Form removal after at least 12 hours.
label | ○ Post Pour Inspection to be submitted for Engineer's acknowledgement showing finished concrete is within tolerances (Surface Level +/‐5mm), and construction joints have been inspected prior to paving
label | ○ Surface smoothness checked with 3.0m straight edge, no deviation greater than 3mm (5mm for LABI) to ensure no areas will pond water. Sawcut contraction joints 1/4 to 1/3 depth of slab and seal as per drawings (every 10m or as specified). Apply compressible joint filler at exposed faces as required for subsequent pours
label | Standard / Specification - Aurecon Civil Spec; Section 10.5.8
label | Verifying Document - Post Pour Inspection for each section, Survey corner of each slab and along crown at 300mm spacing
label | Frequency - As‐Built final surface, QA Sheet
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
label | Engineer Rep Signature (Blank as req.) - W
label | MSQA (Blank as req.) - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Architectural Finishing and Sealing
label | Acceptance / Conformance Criteria - Light acid wash exposed concrete pavement surfaces with muriatic acid to remove stains and prep surface for sealing. Opportunity for architect/Engineers Rep to review clean surface prior to final sealing. Concrete pavements to be sealed with "MIS Stone Age Wetlook penetrating sealer", applied at per manufacturer's instructions
label | Standard / Specification - Aurecon Civil Spec; Section 10.5.5,10.5.6
label | Verifying Document - Prior to final sealing
label | Frequency - Visual Check
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
label | Engineer Rep Signature (Blank as req.) - I
label | MSQA (Blank as req.) - I
checkpoint | 6.4 - Survey Record
label | Acceptance / Conformance Criteria - Installation of works under contract completed compliant in accordance with all relevant regulations, COP and standards
label | Standard / Specification - Design Specification / Downer
label | Verifying Document - QA Checksheet, Redlines
label | Frequency - Post Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
label | Engineer Rep Signature (Blank as req.) - H
label | MSQA (Blank as req.) - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.5 - Redline Drawings
label | Acceptance / Conformance Criteria - Ensure all items have been installed create a Redline Drawings for Asbuilt creation noting all changes with RFI numbers and departures in red pen
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
label | Engineer Rep Signature (Blank as req.) - H
label | MSQA (Blank as req.) - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.6 - Defect, Snag and Punch List
label | Acceptance / Conformance Criteria - Update the project defects, snag and punch list register
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
label | Engineer Rep Signature (Blank as req.) - H
label | MSQA (Blank as req.) - R
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 7 - SIGN OFF
checkpoint | SIGN OFF
button | Customer Release Granted: | Yes,No
textbox | Acceptance/Conformance criteria - Certificate Number:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature