## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
c716d943-121c-4d91-bc26-6c885728eec9 | checklist | FHC-ITP-001 - Subgrade Preparation Burwood Rev 2 | itp | FHC-ITP-001 - Subgrade Preparation Burwood
ec75d139-169b-4eb7-8234-2947c8fa3612 | section | Preliminary Works
4258af24-9bfd-44f4-8834-66accd2e0b04 | checkpoint | 1.1 Check for correct documentation
361aa0a7-2f34-5f1c-9ed3-b83589a2a113 | note | FREQUENCY: Prior to commencing any activity
b80ca035-8fc4-5e1f-a4cc-711f4e4160b8 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
f33d258d-3007-5885-b2a3-18afd7ce761f | note | — using the correct and complete set of drawings
552fea3b-c0cb-5a10-9070-ca457ab30a75 | note | — all drawings are the latest revision
b206a2e4-c107-518e-be69-26d3439dd131 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
757bfb05-d156-5086-85be-b6f7b6fdf1b0 | note | INSPECTION/TEST METHOD: Visual inspection
8f6529bf-b119-5e2f-a421-d9bd1ca6921c | note | RECORD OF CONFORMITY: This ITP signed off
b4c7566c-153f-5416-82d1-9ac04f091dc1 | note | WP
dcef1541-0c8d-5b56-9aff-ae575f7faa7c | note | RESPONSIBILITY: Fulton Hogan
fa3d8bb2-607a-5944-9a02-7fa99de90fc0 | textbox | Date Completed:
04b8cfc9-e2a1-4512-92b2-b6d97b5e2985 | checkpoint | 1.2 Implementation of all measures and controls
400e1a62-8a65-55c3-9f1c-f5511a1dd478 | note | FREQUENCY: Prior to commencing any activity
52233ab4-af2a-502f-aa3d-22997a6afeb0 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
573fdc4a-95d7-5473-8dae-87ae3ce44782 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
17cd4c8e-2099-5167-ae1c-ff0905cba86f | note | INSPECTION/TEST METHOD: Visual Inspection
86ec0840-8168-5c2f-9aff-a5253b0ad919 | note | RECORD OF CONFORMITY: This ITP signed off
7f04910d-8ad8-5a1d-8c2a-cce8d261a3fa | note | WP
40cc8245-6b49-5e7a-be52-e2db54cbfd86 | note | RESPONSIBILITY: Fulton Hogan
c239149f-c31b-52b8-a237-39dbcdf9f7b7 | textbox | Date Completed:
bf1873b7-3169-420c-a63a-c1bbc43c5ce9 | checkpoint | 1.3 Selection and approval of Disposal Site
b8c0b816-d799-5982-ad38-a14db53f69bb | note | FREQUENCY: Prior to commencing any activity
2d2f5769-3a35-54f9-b98d-cb5fda28144c | note | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accorance with Yarra Trams site classification report.
8e2c690f-177c-5a12-b776-83c8d94da8e0 | note | ○ It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
df911640-48cf-55a7-b88e-77bc2d8aac33 | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019-ST-0033 CL. 4.2.1.5.
1fdf0248-7f03-57d1-a4d4-2974a48260c4 | note | INSPECTION/TEST METHOD: Verify
362d8c88-e7b4-5773-b794-10b1b1e776ab | note | RECORD OF CONFORMITY: This ITP signed off
0b70cb9b-6cee-5d06-83f9-3ce813676110 | note | WP
2bb0cf4d-becf-5784-823e-b364f14d510c | note | RESPONSIBILITY: Fulton Hogan
26b8077a-1721-536d-84f4-f303ff2d8798 | textbox | Date Completed:
5c3be3ff-48b5-4764-95a9-5aff6e969fb2 | section | Construction Works
c5744b05-44f7-4f64-81b3-c0638d72c436 | checkpoint | 2.1 Excavation
a74576bb-1704-58b5-8560-2a229403d0a3 | note | FREQUENCY: Each lot
8324f7b9-d4d4-5c6d-b2dc-cea1bcc91e5b | note | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task.
3c1ab3dc-c772-5396-a440-c23f1a3645a1 | note | ○ Excavation operations shall not disturb areas outside the limit of works
edcb118d-fe8f-5a6d-b33d-ba09a578806e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4. Subgrade Preparation Work Procedure
2ec85188-d4ae-554c-ae86-930cef0de797 | note | INSPECTION/TEST METHOD: Verify
acf64156-d519-5ee0-a65c-804291d73746 | note | RECORD OF CONFORMITY: This ITP Signed Off
474e5574-9862-56e0-b551-9d1033c1bd26 | note | IP
f6525264-c74c-557d-b888-a4afec5fef14 | note | RESPONSIBILITY: Fulton Hogan
1d65cffa-2674-5102-93de-ee6bfc8c7393 | textbox | Date Completed:
98ecf792-7eda-42a5-9a13-3edad4348c9d | checkpoint | 2.2 Inspection of Subgrade Material
f8a47c21-099d-5fc1-9576-ea53ec4f8885 | note | FREQUENCY: Each lot
51c1d616-1618-507a-a8c5-ded5a63b82b8 | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
1105b608-aa9a-5b40-a86f-90cb200f7ba4 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
18be2017-f10e-5caa-8050-4c1c17001ba8 | note | INSPECTION/TEST METHOD: Verify
b78c3c56-9c6c-571a-bbd2-268700fc38fc | note | RECORD OF CONFORMITY: This ITP Signed Off
a0a64efb-4465-5c76-b796-5f263019019a | note | HP
b7c96ba9-7086-5db0-8184-3fb6b102240e | note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams Superintendent
60839232-1a95-5da8-b667-2e3f6f1c100a | textbox | Date Completed:
2575fe52-e43c-4637-b9c9-57d64ade2d1e | signoff | AUTHORITY HOLDPOINT
8c52f49c-2140-4c5e-aa7d-7a23d7322f65 | checkpoint | 2.3 Width and Level conformity
ced968a4-8464-55a8-b49e-4839dff373f2 | note | FREQUENCY: Each Lot
10f3b97a-4c2e-5acd-86e3-ea9d6555fd2d | note | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings. No point in the general surface shall vary more than 12mm from a 3m straight edge.
264ac497-168e-52af-b3d2-910b42797584 | note | ○ Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
618ed934-366f-5762-9468-4b0b84ea968b | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
5dd752a8-e4d1-5baa-8a45-b9ced3e2260d | note | INSPECTION/TEST METHOD: Survey Report
a88b86ef-328c-5afd-8a43-6441fed56195 | note | RECORD OF CONFORMITY: Survey Record
5239c7e3-b527-5be2-919a-77df33d81f4b | note | IP
4c6b6177-c7a6-5080-978f-44ee643d376f | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
cf193c1e-1858-5dda-a1a1-59da4e14686b | textbox | Date Completed:
dd97c262-3f71-4aa4-8f05-551f5cabecea | checkpoint | Final Inspection
d2214c86-7cb7-5172-830b-446e4ca655f8 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
eaa2435f-6570-519c-885b-08409c311e81 | textbox | Print Name:
e2a5f02c-fd06-50ce-9120-1d4b58907e22 | textbox | Position:
dbdd2a58-a529-5002-be35-8f763a7c1f60 | textbox | Date:
cf0f8642-945a-4b43-93d3-e0c9265605fc | checklist | FHC-ITP-002 - Feeder conduits and pits Burwood Rev 2 | itp | FHC-ITP-002 - Feeder conduits and pits Burwood
de75d546-6e7b-48a2-8d0c-885ae2546834 | section | Preliminary Works
7cb5621f-eb68-4906-be2d-585874f91fa7 | checkpoint | 1.1 Check for correct documentation
771d4eac-4bae-56a3-aac8-64d60b3595e3 | note | FREQUENCY: Prior to commencing any activity
d440ce3b-c36a-5175-a2aa-ed65c20871eb | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
986cccc6-1761-5b96-b61e-c698aef50da4 | note | — using the correct and complete set of drawings
9c94887a-e452-5059-87da-e981bf33e299 | note | — all drawings are the latest revision
b20ac7db-e37e-5ded-9a22-11721493e6d7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
4878c357-a785-5ded-97a7-d6747477a1e3 | note | INSPECTION/TEST METHOD: Visual inspection
ffb044b8-f13a-5afb-beef-88a5e36cfc6d | note | RECORD OF CONFORMITY: This ITP signed off
7525634f-f315-5d0a-900b-3fd49fa4475a | note | HP*
20206769-818c-582d-8e51-69bf62d5e340 | note | RESPONSIBILITY: Fulton Hogan Engineer
cb0eed3c-d2a9-508b-8b71-7a274714a486 | textbox | Date Completed:
fe56cf2c-37bf-4f54-8743-e8211297356b | checkpoint | 1.2 Implementation of all measures and controls
ef4dc67c-df68-5ac5-a15b-cdb8405c750b | note | FREQUENCY: Prior to commencing any activity
788dedef-36d5-5e87-a478-545bf5c58597 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
f0829242-4c97-50e8-ab6c-2ee8ab17a047 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
0a7d2146-b1fb-5fb1-b453-efda59672ec9 | note | INSPECTION/TEST METHOD: Visual Inspection
e8794a1b-ff61-5c2c-a816-a5bcd5a2f331 | note | RECORD OF CONFORMITY: This ITP signed off
2fe18bb5-4fb3-5ba5-874f-b280347647d7 | note | HP*
e6223ee7-a19f-5d60-90e1-c5c8651c0f99 | note | RESPONSIBILITY: Fulton Hogan Engineer
8520636a-75eb-5b74-83ea-326e1aefc821 | textbox | Date Completed:
3329a766-d10a-48e6-930e-61903313f3fd | checkpoint | 1.3 Materials
357522e3-37a5-5028-9fa9-a46ee3e50d01 | note | FREQUENCY: Per Batch
04379ded-8366-51fd-9497-f7860a9457e4 | note | ACCEPTANCE CRITERIA: Electrical supply conduit to be Orange
091c0bef-e7ac-5630-b237-a7fad3729ee5 | note | ○ Heavy Duty 100mm diameter UPVC
2cca0407-4232-5cb6-8f95-aaba9df56bb4 | note | ○ Modula Stakka pits to be used for feeder pit, entry for conduits to be cut with hole saw
50045299-7d4c-502c-8a6d-f88ff3d6c34d | note | ○ All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
b9eee56b-a17d-5524-9b13-35b5ee2e0fb7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4 AS 2053
71a6be96-36ac-501c-b4af-3f4cb4746824 | note | INSPECTION/TEST METHOD: Verify
b125dffc-2ba6-51ef-a8df-55b6d0adab76 | note | RECORD OF CONFORMITY: This ITP signed
e510a93e-bc26-5c78-ae13-434fe65b470d | note | HP*
2431651f-dee9-5e0c-b017-284accace572 | note | RESPONSIBILITY: Fulton Hogan Engineer
46c7a3a8-262d-5246-8087-facfc1c70851 | textbox | Date Completed:
93c03e12-5b92-4292-a5a3-4b141a90ba59 | section | Construction Works
88edc27f-af95-4ac8-8275-fe627cfe9f9b | checkpoint | 2.1 Survey set-out
f5016e00-5d2c-5cd1-aaa1-305bf6fef8d6 | note | FREQUENCY: As required
cb9d75df-99dc-542a-b4ea-0898e622c775 | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
85dd86cd-0f6e-5a6d-85f3-dbba267094b3 | note | ○ Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
07f3d0fa-83ce-54f4-a751-18eda7ed76ca | note | REFERENCE DOCUMENTS: Work procedure
96fcd049-5251-5ea5-84a3-b8bca1be23b5 | note | INSPECTION/TEST METHOD: Verify
4013d93c-8252-547d-864f-e09cb3c11952 | note | RECORD OF CONFORMITY: This ITP signed
e97a3ba0-b37d-5c06-aada-b11d8e57f5b4 | note | HP*
3834b0e8-389b-5a1c-a35c-1c72d6a6e90e | note | RESPONSIBILITY: Fulton Hogan Engineer
3378b9eb-91ed-5b45-be29-beefe30d6bb3 | textbox | Date Completed:
263a3f43-114a-4a3a-9ecd-8947be90cb8d | checkpoint | 2.2 Excavation and Trenching
78d60463-bb05-5ef5-8542-0dffe9507e60 | note | FREQUENCY: Prior to Installation
b950a728-9053-580e-b431-1dbbd3e98a9f | note | ACCEPTANCE CRITERIA: Minimum cover for underground conduits shall be 600mm
40e64ee9-0835-5c8a-a24a-11bdf18597c6 | note | ○Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
c694428e-f789-5453-b736-5d5d0e3f9351 | note | ○ Trench shall maintain a minimum clearance of 300mm from all existing services where possible
98d8ee56-9628-5d02-93b5-bb6f397e635e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
ce550c15-7a97-5887-adcb-386d29b26975 | note | INSPECTION/TEST METHOD: Verify
8bdaf2b4-a7de-55d3-aa0e-2dd255145949 | note | RECORD OF CONFORMITY: This ITP signed
8a3cc2e8-7bf4-508a-9c2e-94488ba952a5 | note | WP
553b1df2-bb0f-5c57-b769-819dde1b0ed7 | note | RESPONSIBILITY: Fulton Hogan Engineer
670141db-b4ab-5cde-8182-a601ea3112dc | textbox | Date Completed:
2d2b0f3f-d101-4dfc-a5d9-587d00e39352 | checkpoint | 2.3 Installation of Conduits and pits
356b52c9-c894-51cb-b1d4-7aaa9d1772fb | note | FREQUENCY: Each Lot
ecc8f1d2-1222-5652-b54a-2ca1609f41e6 | note | ACCEPTANCE CRITERIA: Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
141d5fa1-cbc4-5b4f-8edf-ccccefd324cb | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand
12913cf6-72ec-579b-8952-97f6a52c9a39 | note | ○ Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
3af84d4f-b65a-5b9f-8398-3d3371d7b881 | note | ○ Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
eb0a408f-607d-5ff7-bcfc-965aaeef7f9f | note | ○ Conduits shall not be subject to construction loadings
6c19f6be-c0aa-5edd-bdc7-beafc0bec68d | note | ○ Pits shall be constructed as to allow for class D rated covers
16a5182d-d04f-5230-93e9-3609976d99a5 | note | ○ Bottom of lowest conduit shall maintain a minimum 100mm above pit floor, a 50mm gap between conduits shall be maintained as they enter pit face.
5c7ace37-73c3-50b4-a0e5-e20c74b76379 | note | ○ Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mm beyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
e386b949-a999-531a-80aa-2e802776e0cb | note | ○ Conduits shal be placed a minimum of 100mm above pit floor
75b4009d-6af3-5223-b3d1-0ff29cf4450d | note | ○ Conduits installed for future connections shall be installed to the track Margin
0ce7fee9-d3ae-54ea-85e0-5861c3e951b9 | note | ○ 100mm of concrete around and under pit lid
7c59d054-a608-557c-b652-01021da016ba | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
cff8b7a7-a3cf-5d68-ad10-b257e1e3d2af | note | INSPECTION/TEST METHOD: Visual inspection
b4e6ad10-d9b7-53f6-bdbd-0523288685ef | note | RECORD OF CONFORMITY: This ITP signed
d1894bc5-7e67-5b29-9152-0e4e6779d1d3 | note | WP
1962dfdf-b87c-5e8e-9aa8-c2d9261cbb9f | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
6c0ef185-b40e-5314-a1f8-c1b748d2a4ee | textbox | Date Completed:
b2d0236e-9bac-4cb2-aa7b-c0573c84cbd5 | checkpoint | 2.4 Inspection of conduit installation
79e04f98-9039-5fe3-8e4a-b1881cc156f2 | note | FREQUENCY: Each Lot
b3887d33-3f80-5d5a-8a14-6e3af87bc2a2 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
c1717617-08a5-5a3b-b885-e643e29036d5 | note | REFERENCE DOCUMENTS: Work procedure
b73ed255-bed8-5ca0-989f-688df6bc4547 | note | INSPECTION/TEST METHOD: Visual Inspection
0a5d6ac9-0593-5a71-9816-dd55ed119588 | note | RECORD OF CONFORMITY: This ITP Signed
5d150c1e-cc7c-5478-b425-54b41489ed35 | note | HP
d5afdf89-83a4-55f8-8462-04d4dae2a02a | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
f5d61f1e-2405-5325-a2de-2d75a459c533 | textbox | Date Completed:
33ed9895-1ae5-42f3-9cfa-b47f5cf3034a | signoff | AUTHORITY HOLDPOINT
32e393ff-e72f-4121-8834-238e54344402 | checkpoint | 2.5 Back Fill of Trenches
19785170-ba2c-5740-bb4e-0919f82326f4 | note | FREQUENCY: Each Lot
946e322f-0390-5945-b65a-c978108cb6a1 | note | ACCEPTANCE CRITERIA: Backfilling (Only to be used for road crossing trenches)
c0cc6ac4-6e36-5116-9972-3407b4ffc9b5 | note | — conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
e19a441f-33f0-5c51-8547-c12cb020344d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
f5c9981f-5325-58b5-84b5-1ea08c5ae3f8 | note | INSPECTION/TEST METHOD: Verify
d341b9ee-ebff-52d5-bbce-62dadf1c03d5 | note | RECORD OF CONFORMITY: This ITP signed
d7f38f27-b8ca-52e7-98fb-36932a142512 | note | WP
c7b8d685-9bac-55ac-a73b-5152a5533fb0 | note | RESPONSIBILITY: Fulton Hogan Engineer
0f52a3c2-b4ae-588c-afb8-51d488458a28 | textbox | Date Completed:
f0f2638f-1849-4935-85ca-55ad97820138 | checkpoint | 2.6 Installation of Draw Cords
2fcb5654-f130-5744-914b-d916d6af2b2e | note | FREQUENCY: Each Lot
6f5c7b2f-67f9-5295-a08d-3807b5840d70 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'
c149b2d4-0000-57b1-99ff-715664925c00 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
59ebfcf4-f2d8-5a96-b463-b18206d3d73c | note | INSPECTION/TEST METHOD: Verify
9edade1f-67e9-50dd-8acd-93b9d752ab15 | note | RECORD OF CONFORMITY: This ITP signed
9f80a4f9-c795-525a-b894-36940987b3ee | note | WP
ea530612-939f-5d72-88c7-73c4a6408e1c | note | RESPONSIBILITY: Fulton Hogan Engineer
a52418cb-ecc6-5536-84d7-4cd60154c042 | textbox | Date Completed:
aaea3719-c983-4889-97f2-42a0d6aca108 | checkpoint | 2.7 Compaction
0dceca71-6a60-5d5f-a50e-50eb95f7e188 | note | FREQUENCY: Each Lot
330aef00-0a34-593d-857b-547d29872f5d | note | ACCEPTANCE CRITERIA: Bedding and backfill material to be compacted using mechanical plant
ae26a490-a74b-5f4e-a6cf-25fe9e617a05 | note | ○ During compaction optimum moisture content of bedding and select fill is within 85% to 115%
d75f4800-1391-59e2-af67-64bd203ea578 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
a0133492-0a6b-5b80-b151-d7277f0e5599 | note | INSPECTION/TEST METHOD: Verify
d2a4a0ea-36d4-55ad-a22e-d9e86555d53d | note | RECORD OF CONFORMITY: This ITP signed
66b7922d-d587-511f-a9a5-cb0bf246aadb | note | IP
aec39cef-58ac-5c53-8cd5-3f12f72393bb | note | RESPONSIBILITY: Fulton Hogan Engineer
00f9af28-497f-573f-821c-c19b006a08da | textbox | Date Completed:
42e2b236-dfd9-4201-ab09-c56614e74755 | checkpoint | Final Inspection
3a8f0fea-7686-53ea-acb9-bcd0ff926463 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3df19550-c71c-5000-b548-ff80c0c2ac30 | textbox | Print Name:
3d37b3dc-30c6-55e1-b4a8-9d1a67f093cd | textbox | Position:
7cae748f-2d88-5484-95b6-0914fa3d3446 | textbox | Date:
2f034e1f-4aa0-4f72-86c5-86682d38a437 | checklist | FHC-ITP-003 - Track Placement Burwood Rev 2 | itp | FHC-ITP-003 - Track Placement Burwood
df451d90-425f-4814-86f9-ee3aff6b93e2 | section | Preliminary Works
b8afc2a0-bef4-47a8-a5c4-b0e400023c0a | checkpoint | 1.1 Check for Correct Documentation
03f5310d-b7ab-5679-966d-0c44866a8bbc | note | FREQUENCY: Prior to Commencing Works
a6d84128-1133-5eff-b5ac-5f74ea0dfaa3 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
fd4674f7-4168-55d8-9ed3-6612c84be730 | note | REFERENCE DOCUMENTS: Design Drawings and Register
410cf573-c908-5b4d-8ac5-cc0e5316970d | note | INSPECTION/TEST METHOD: Visual Inspection
4750f40e-5f46-5e1b-abb4-3ceeba05afcb | note | RECORD OF CONFORMITY: This ITP Signed Off
cd7c4153-404e-50bc-9f06-0673ce557222 | note | HP*
4c5e9b1d-e80e-50cd-bd91-35d16724c249 | note | RESPONSIBILITY: Fulton Hogan Engineer
92e41a6c-fedf-5416-bdfe-ea554ca0938a | textbox | Date Completed:
099ef020-4a47-4d06-b06c-849c6d0c3fc8 | checkpoint | 1.2 Check Materials
7c918883-1808-5a67-bac8-e4b653db8027 | note | FREQUENCY: Prior to Commencing Works
bb52ffa7-66ab-5269-ad19-0fe97a34b71c | note | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
9c8bf744-ced4-536f-bb93-ac938c3781f6 | note | ○ Check condition of rail sleepers
45797956-1f6e-5954-b3b0-bd2cc853bab4 | note | ○ Ensure rail jewellery is of sound condition
e1e081a3-5144-5477-8d7a-d562e9dbf862 | note | REFERENCE DOCUMENTS: AS 1085
a2a63f41-5bff-5766-bc43-21895bb720bf | note | INSPECTION/TEST METHOD: Visual Inspection
fda35593-4923-5267-8a58-bdd97e85967b | note | RECORD OF CONFORMITY: This ITP Signed Off
72b45a03-d16d-582b-9986-310c13c8316f | note | HP*
7b56dc67-3385-5c8a-a8ef-21027b8ed438 | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
a369a8d1-3d27-5f32-9f2f-9addb591f3b8 | textbox | Date Completed:
c152883e-ab5d-4715-92f7-7c6d908c9f28 | checkpoint | 1.3 Check Special Works Components
cdfb0c2f-0571-5746-ae79-b8acf0d78791 | note | FREQUENCY: Prior to Commencing Works
6755c692-20e9-51f7-9358-1fa069825816 | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
287e5895-fb57-5a99-87cb-52b23761eb61 | note | ○ Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails. Superintendent to visit yard from intial inspection of the rail and fabrication plans.
fc9b2c07-aeab-5a1d-b736-cbb9fdc7aae5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
1c1b02a8-2417-5398-9de2-2ac60dd589df | note | INSPECTION/TEST METHOD: Verify
0049aa54-f679-51dd-904f-8ece24993346 | note | RECORD OF CONFORMITY: This ITP Signed Off
51298ffb-eb20-5e2d-9d3b-52de3135c834 | note | IP
9ad645a5-26d5-5d58-8191-a72c24a35df8 | note | RESPONSIBILITY: Fulton Hogan Engineer
5f7da373-1530-5ebb-82f0-416ce7db4ece | textbox | Date Completed:
8fe46e05-30f8-4907-97d8-23b49bcd7d71 | checkpoint | 1.4 Check Curved rail
70b7bf13-7825-590a-aa17-4a304c6c4401 | note | FREQUENCY: Prior to Commencing Works
13b6ff93-b930-595e-8ca6-e13ca9606d06 | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
3943afb5-aaf0-5734-920b-0640fba87362 | note | ○ Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails.
63baea11-b335-5a82-a874-eedb651d54b1 | note | ○ This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
4f3971d1-7e7f-5300-90ce-588452f70543 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
16daefe3-02a9-524b-8812-0f2a4c3add51 | note | INSPECTION/TEST METHOD: Verify
29b90249-5547-5805-9b48-2433b25b0f24 | note | RECORD OF CONFORMITY: This ITP Signed Off
ed8cc4a2-92e1-5737-ba57-0b6250f9adb9 | note | HP*
ce364539-4b16-5ace-a769-3c282acb93df | note | RESPONSIBILITY: Fulton Hogan Engineer
7e59961e-be85-5a13-ac9b-46f17c9b3434 | textbox | Date Completed:
d1216e07-58df-4963-884c-7a2e6733b5ec | checkpoint | 1.5 Welders Qualifications
d74d9eab-6224-5b4c-a0d1-4d6b7bd78f6a | note | FREQUENCY: Prior to Commencing Works
2a6d881f-0c4d-53ab-b059-c9e6a21f2f45 | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements;
91350249-0960-5d50-b143-f57029250500 | note | ○ TLIW2012 Grind Rails
73884127-4e0b-5c68-b7d1-fa2e937d50c3 | note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
3240ae1c-c93d-5845-9bf9-fc24db9da745 | note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
0c0c9a3f-efc6-54ac-b06c-9e5b494f117e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
834d1066-58e7-541a-9fe0-da3b11337705 | note | INSPECTION/TEST METHOD: Verify
da9ec5dc-d4a0-5f2a-abc7-69fc8eae9745 | note | RECORD OF CONFORMITY: This ITP Signed Off
f5489d55-bc49-50b7-8c22-f9ffc61955d7 | note | HP*
b0b80b74-efc7-53be-9fe2-7f008c431bdd | note | RESPONSIBILITY: Fulton Hogan Engineer
48fa55c8-71be-598d-9669-326dd50cfa35 | textbox | Date Completed:
55842b26-8f94-42ef-a640-3829a6b99390 | checkpoint | 1.6 Ultrasonic Testers Qualifications
5c7a4f8b-f887-5538-931d-f896f7c6d81b | note | FREQUENCY: Prior to Commencing Works
4c172668-1c95-5a80-881d-f9c21b091fe3 | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
5163d0a2-77ed-5eb4-83bb-61fa93a88743 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
b8dd84fa-527b-51f2-8c46-ec346d0cd8b1 | note | INSPECTION/TEST METHOD: Verify
d249b41a-f177-5bfe-9690-248c3a793f29 | note | RECORD OF CONFORMITY: This ITP Signed Off
64d9e3a7-fefe-5b5e-870c-9d824b91b527 | note | HP*
be582278-9aa2-5ded-822c-d9fd8da92b7f | note | RESPONSIBILITY: Fulton Hogan Engineer
693d3042-cd49-5d29-a2a0-52459c459d09 | textbox | Date Completed:
e42f3711-d823-42f8-84eb-29ac3cc5c662 | section | Construction Works
f709b9ca-dabe-4442-9445-07f398703001 | checkpoint | 2.1 Installation of Sleeper
08147f77-4fe8-53ec-9a71-3d54ab462858 | note | FREQUENCY: Each Lot
a7871ad8-53e4-5635-a78b-0adada867929 | note | ACCEPTANCE CRITERIA: Dual block sleepers shall be installed at 3000mm intervals, toelrance of +/- 50mm in placement
cc77d4c3-31d6-5446-a875-8245ef32a50c | note | ○ Dual block sleepers shall also comply with the design offsets at each chainage
6cf3ec10-1520-5e7f-87ba-c6e3a67adc69 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
b29fbfc2-3708-5c4c-ac53-6988ab93414f | note | INSPECTION/TEST METHOD: Visual Inspection
aa8cd8e4-c665-5dc1-9de7-aea1ffca82c2 | note | RECORD OF CONFORMITY: This ITP Signed Off
b5ce1bf0-34db-5d8d-8616-977e868dbf97 | note | IP
9e9916ec-5a3a-5d24-b96a-04f5f5669791 | note | RESPONSIBILITY: Fulton Hogan Engineer
30686c17-88b0-5ae6-a145-02fad3079841 | textbox | Date Completed:
de54bd36-ef01-45e3-8f6b-63f9530dcf76 | checkpoint | 2.2 Placement of Rail
e1f54eb7-02f5-565d-8158-c0f2fd4efb07 | note | FREQUENCY: Each Lot
3dbe3a7c-c7ad-5a1f-9ad6-34d2c48f1c65 | note | ACCEPTANCE CRITERIA: Ensure rail strings conform to rail plan
d6d97091-f494-5470-b19a-6fd12f793247 | note | ○ All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
fbab4f9c-541a-5d51-96f3-183098b2fa13 | note | ○ Bottom of rail and bearing surface shall be clean of foreign materials before laying
2e259beb-277f-5dc4-98ec-953b90e24825 | note | ○ Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
bdce70af-4f00-57a1-974f-8e619f82cc8f | note | ○ Geometry tolerances as follows:
e480cb70-8bbe-5040-a3d3-d247974211cc | note | — Centreline location: +/- 3mm
1d336a92-56fe-5711-a746-dd74084e798d | note | — Level: +/- 3mm
ee1997d7-4865-58d7-bf33-c87557967823 | note | — Line measured (>10m chord): +/- 3mm
ce8177d5-fdf7-5a95-81f8-dc160a12d4dd | note | — Twist (3.5m chord): +/- 2mm
51ced704-38cd-5785-ae59-6df04a0625a2 | note | — Cant: +/- 3mm
d00b6848-752d-55b3-b7e1-25903f3087d5 | note | — Gauge (open track): +3mm, -0mm
1a30647f-e46d-5069-a37a-1cf57e4f86dd | note | — Gauge,Turnouts (opposite crossings):+2, -0mm
dd7ca67d-92c3-5cc1-81eb-64515b85fb26 | note | — Gauge, Diamonds and ‘H’ Crossings:+2, -0mm
f8417034-9f7a-574f-b613-919629c303c0 | note | ○ Note: Cant shall be applied uniformly over transitions
2c021ea6-aebd-547e-bc82-72541d6c8a7a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
1e99397d-8451-5e3e-8844-47c5404eed3e | note | INSPECTION/TEST METHOD: Visual Inspection
439cf8df-2b1e-5d10-836c-39bdcdd30c65 | note | RECORD OF CONFORMITY: Completion of track charts
14d45ff5-ab61-5b28-8582-05d4e27d767c | note | HP*
ea6b4b26-6fce-57f0-8c78-0d9a8c952140 | note | RESPONSIBILITY: Fulton Hogan Engineer
e3ef6543-0c5d-5b9e-bf30-74f602aa8ec4 | textbox | Date Completed:
6867e67d-ceed-4c20-a94c-d41f20063d3e | checkpoint | 2.3 Placement of Jewellery
76c06bb3-70f5-50d5-ba84-cf6e66855446 | note | FREQUENCY: Each Lot
915bf1a7-65d8-53bc-8eed-784216108a87 | note | ACCEPTANCE CRITERIA: Each sleeper shall be fastened to track with approved jewellery and rail clips
272f5391-7035-5274-9718-b1bb7cb0465c | note | ○ Clips shall be installed with panpuller or equivalent
442d5527-9607-5766-8e63-5c7a7e4377ac | note | ○ All fasteners shall be sealed as per agreed method with Yarra Trams
42f89a23-a559-5c08-bad8-be1c8c901304 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
c1b198f1-c275-5183-8873-1f102b790fe6 | note | INSPECTION/TEST METHOD: Visual Inspection
5dac1c38-0d87-5aca-b76e-de28c2776a72 | note | RECORD OF CONFORMITY: This ITP Signed Off
8de4940c-8cf8-59b3-a616-041478186ea4 | note | WP
f0c78446-01b1-51bf-8b32-8add15829c45 | note | RESPONSIBILITY: Fulton Hogan Engineer
246b2922-7434-5ca8-9d46-70bf39b0a5e5 | textbox | Date Completed:
3232e5b3-8879-49e5-a1fe-0366fae60133 | checkpoint | 2.4 Rail End Preparation
43e8754a-6ef4-553d-b14f-be64d13ac770 | note | FREQUENCY: Each Lot
25486adb-3c53-5110-867c-b0f7803f1bdf | note | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
88c87f3e-1503-53e7-baef-9500e0d7f084 | note | ○ Minimum closure length from proximity of welds shall be 2m
3d84ab3d-835a-5b67-8a83-dfb5f6d0d376 | note | ○ Rail end conditions shall match (i.e flame cut - flame cut)
69f5f38d-ac7d-5fa8-8a05-263a7c706f8a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
ad47dca7-35dd-51d0-9c26-e41db9410bc1 | note | INSPECTION/TEST METHOD: Visual Inspection
29b8eede-455e-515d-a13c-9382f1e964d1 | note | RECORD OF CONFORMITY: This ITP Signed Off
35d328a2-ef5d-5007-a8d1-6fba3d616221 | note | WP
ce53e856-a466-5393-84b2-0abe1e17e96c | note | RESPONSIBILITY: Fulton Hogan Engineer
8b1c666d-d237-5592-8182-6f9d53effb03 | textbox | Date Completed:
b2f3670c-4c17-4b3d-a1d7-e6c48010d1f2 | checkpoint | 2.5 Welding of Rail
994e82bf-daab-50b0-ab69-d766fa47fc0a | note | FREQUENCY: Each Weld
65ff98e5-0925-5ede-814c-5b2a5b0bc35c | note | ACCEPTANCE CRITERIA: Joints shall be square across the track
db223579-00db-50c1-b371-a4a2b5827a80 | note | ○ Maximum skew at square joints shall be 65mm
40e1cb7c-18f8-52b0-b2ce-33bc625ad72d | note | ○ Portions shall match rail type (i.e HHR, Ordinary)
51376024-b5d2-59da-9df4-d4000fa0c310 | note | ○ Welds shall not be within:
1b42ba81-a285-57f9-b897-f110643497f9 | note | — 3m of another weld
1f5fe4ac-1e44-59e7-9a5e-e7d5abcc646c | note | — 3m of a rail end
27a21298-20a2-5308-80fd-1267cedabe58 | note | — 1.5m of a glued insulation joint assembly
ecb7005e-bbe5-5832-8f6a-be4fddf800e9 | note | ○ Field welds shall be +/- 50mm from centre of bay between sleepers
51bdaea0-65c8-5681-b610-964800de4488 | note | ○ Weld Return forms shall be completed by qualified welder
809f787f-9d40-5958-968a-ba2924ad8c7b | note | ○ Welds shall be grinded after 1 hour
bd545e77-18bb-5f96-b9ae-6863d161e5dc | note | ○ Welds shall be free of water
0f90103b-ab5e-556c-8850-df7f0a2b822f | note | ○ Post grinding, welds shall be cleaned for visual inspection
969f6c6f-9d93-5b1d-8655-561566ccefd7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
94e3c48a-f75b-5a2a-8923-ec0af96b3c4f | note | INSPECTION/TEST METHOD: Visual Inspection
a31ed55a-4e21-52fe-b116-7e14d63b5a15 | note | RECORD OF CONFORMITY: This ITP Signed Off
877b08c1-e29c-5039-9138-13a42c32d969 | note | TP
18720032-0a30-51ca-be6b-87f76afd3ad8 | note | RESPONSIBILITY: Fulton Hogan Engineer
7f6fd7d3-20a7-5119-969d-d00f9823314e | textbox | Date Completed:
56dcf703-97d1-48f8-9eb8-1d672f7ca073 | checkpoint | 2.6 Grinding & Cleaning Welds
edd9661b-f707-5d12-adf6-d1137d74c5fc | note | FREQUENCY: Each Weld
d2a5a6b1-d06d-59d6-821f-041c70895f40 | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
2bf76b97-be4b-5337-80d6-7283c0d5e525 | note | ○ Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
a4da7728-d892-5122-a20c-61fa6db54b7c | note | ○ The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
c8f6fcbb-308b-54b0-89a9-7fcee76efe0f | note | ○ Weld Test Results to be provided by FH to Yarra Trams.
e5d3a7c9-7cda-5167-a563-eea218f85d70 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
bb1336cf-a03e-5f9d-b586-97fb41cc9349 | note | INSPECTION/TEST METHOD: Visual Inspection
2edfa65f-5184-5ca7-bab5-158130a54eae | note | RECORD OF CONFORMITY: This ITP Signed Off
01781ce7-a855-5465-a672-07ab94611066 | note | IP
898c64f5-51b1-5bf0-b0f8-6fcb259e25b2 | note | RESPONSIBILITY: Fulton Hogan Engineer
690a41d3-8097-5e9f-9881-0c3ae35b2249 | textbox | Date Completed:
7735bc62-05bc-4474-8f8a-2d6d795227f0 | checkpoint | 2.7 Track Adjustment
e3a1be53-c158-5e04-8e83-146b46a1171e | note | FREQUENCY: When required
8f158bc1-1fa6-5c15-bea9-32381da1b716 | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths, which shall be measured with an approved type of thermometer.
474e34c4-65dd-5151-a0da-6bf5e719682d | note | ○ In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
30606297-0cc1-590b-b51e-279deb308a65 | note | ○ Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
4bde4dc0-32f8-59fd-9e65-084e62e9efc5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C, STD T9008
9ea7be54-fb26-514c-8137-718ef3e2dd1d | note | INSPECTION/TEST METHOD: Visual Inspection
33b2deec-d3ea-5e77-b7b8-a2ce4f538779 | note | RECORD OF CONFORMITY: This ITP Signed Off
23ab5775-d56d-5da7-8118-f4611d88e9a4 | note | IP
33c3d495-546e-5840-b3b9-33e301962d02 | note | RESPONSIBILITY: Fulton Hogan Engineer
d8757e5b-1d8a-58d5-a4a6-16b41aabf4ea | textbox | Date Completed:
ce7fee4d-9e0a-49b1-91ec-53f427ebb9ad | checkpoint | 2.8 Track Bonds
210d04d7-78ce-579f-b1fe-5ecaeef1ec5b | note | FREQUENCY: Each Lot
bf93a5fa-adcd-58c2-9be3-f73f6975d15f | note | ACCEPTANCE CRITERIA: Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
6c84aa69-8522-5343-8ee7-5ab604f63179 | note | ○ Ensure bonds are sealed as per agreed method with Yarra Trams
94223d94-492b-56ea-8ec8-400d2a224e35 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C, Design Drawings
24cc7466-cef0-5bbb-9240-9682c43a7623 | note | INSPECTION/TEST METHOD: Inspection / Test Method
8b158aec-8f2d-5e50-a25a-06d7890b557b | note | RECORD OF CONFORMITY: This ITP Signed Off
4059a063-647f-5087-b525-214969c3a687 | note | IP
8a9a8d49-e5db-5b5f-a3a7-8af59a0aeb88 | note | RESPONSIBILITY: Fulton Hogan Engineer
05c0603d-c748-51bb-b469-c4fe5c5fc556 | textbox | Date Completed:
aa9b3172-058a-4984-8376-36725dcd3035 | section | Testing
8970a9a2-5878-413e-8c3d-f36d136f44a9 | checkpoint | 3.1 Track Testing
a26d64f1-4966-5fb1-9530-cae80e75b84d | note | FREQUENCY: Each Weld
df1018fe-dd8f-5415-93c5-6fac2fa416e7 | note | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator
d01d665a-72aa-53a0-9eba-cb37e8d722d8 | note | ○ Failed welds shall be cut out and replaced
08295f92-85e3-5e10-9a77-2e56a67795e0 | note | ○ Testing documentation shall be recorded and supplied to the superintendent
8d3ddff9-5d47-5da2-833b-8b41c46170c5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
1cbf51f8-12fd-5d43-a43d-2d6da9d320b5 | note | INSPECTION/TEST METHOD: Inspection / Test Method
5ee64f66-0c9c-57ce-90da-8451afa7ed33 | note | RECORD OF CONFORMITY: This ITP Signed Off
d786e126-a6f9-56bb-811c-1805020204e1 | note | TP
3ce73f8a-ccbf-5140-a020-b4688cafb074 | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
13847ec7-c766-524a-8ebf-8944c401567b | textbox | Date Completed:
d025fd70-b8c7-4efa-ab0b-61f2a2973f53 | checkpoint | Final Inspection
d3ce7ba5-295f-5beb-bada-afc494ef1468 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
6f3358f3-561b-5f6d-b0d0-b420362c4706 | textbox | Print Name:
7db21242-2128-5a85-b37f-73117fda2f0c | textbox | Position:
33bb8e9e-022d-5971-86a4-c404217c03b4 | textbox | Date:
f3b9900a-b63b-46b7-afda-3a98ac65d963 | checklist | FHC-ITP-004 - Concrete Track Slab Pour Burwood Rev 2 | itp | FHC-ITP-004 - Concrete Track Slab Pour Burwood
f51e14d8-da98-4cfa-adc4-2b44c8ea4005 | section | Preliminary Works
4623f6d2-8cdf-4949-bad5-3bb69fe863da | checkpoint | 1.1 Check for correct documentation
d1fef0b8-eca5-5ab4-8b27-e7fd867a23e3 | note | FREQUENCY: Prior to commencing any activity
d309a234-b52f-56cd-b085-67bbd0eb1b58 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
746ce471-d420-522d-bf6f-94085ae668fa | note | — using the correct and complete set of drawings
24ac6d37-a83f-5f3d-b23c-e2570139dd45 | note | — all drawings are the latest revision
900d1acd-83d6-5858-916e-05d9cdb37551 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
031032e2-b794-513d-b459-786f6a3b1077 | note | INSPECTION/TEST METHOD: Visual inspection
cbe5f99e-1e5e-50b0-b148-bdb3b2f65720 | note | RECORD OF CONFORMITY: This ITP signed off
96fa0d11-1379-50ee-adf8-dc5a84dc1bea | note | HP*
49f7213a-b6f4-5471-960c-fa27eba804f5 | note | RESPONSIBILITY: Fulton Hogan Engineer
6bcd9bf0-c37f-543f-ae1c-ea3246815e2e | textbox | Date Completed:
cb915c8e-e667-4afe-847d-1f0332cc4b2d | checkpoint | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project
74b55b64-23cd-58fe-b694-71f5131a45b1 | note | FREQUENCY: Prior to first concrete pour
41fe3713-8458-522f-9aa6-1cdc65e70256 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
84eca0fb-6190-550a-8680-8339c6be7b70 | note | ○ Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
bc7b5aa6-f8e7-55f0-95d2-99e58c603286 | note | ○ Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
18146542-085a-59e9-9809-88670fa3af58 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
7bfcdaa7-f0a5-5732-9f6f-b2a77280911a | note | INSPECTION/TEST METHOD: Verify
7206ea24-ea9d-5023-af62-5d030f7ba8ed | note | RECORD OF CONFORMITY: Mix Design ITP
b70a43ba-8d85-56d0-896e-f741f0f1b445 | note | HP*
bc7605ea-50d0-515f-bea0-05bdd44273d9 | note | RESPONSIBILITY: FH Engineer / Superintendent
0562b0ef-e83c-562c-a3ed-dfdf57385838 | textbox | Date Completed:
13c91fee-9a6a-4fbd-9bfb-a74faed734e4 | section | Construction Works
7a725d0b-1809-47ab-9689-e33c445d3cb9 | checkpoint | 2.1 Weather Monitoring
b6c85018-ce81-5ff2-b56e-6f45026243ab | note | FREQUENCY: Prior to start
d057f27e-ed3d-5653-a562-606b3480b460 | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
f608a6e1-faf8-5e79-9882-a3bb7d190bc9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
64acfaf0-3c01-5bec-b349-c2257aee48eb | note | INSPECTION/TEST METHOD: Verify
54efb057-9755-514a-85d4-d1b3fbfd280b | note | RECORD OF CONFORMITY: This ITP signed off
2401eb77-787c-51f5-b6e0-7679830c0e05 | note | HP
02f2a0a8-ac84-52f8-b0bd-957e0375315a | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
6a52d73d-bad1-53e5-9d3c-9c9340f2a8e0 | textbox | Date Completed:
d608e8e9-0179-4226-8ff3-710c68f367ad | signoff | AUTHORITY HOLDPOINT
c88d5709-8e57-401a-9da9-a8aa953b9a49 | checkpoint | 2.2 Surface Preperation
8304a82f-d6f1-5be9-a053-8767cc0d874b | note | FREQUENCY: Prior to start
30e8e5e3-9281-5e37-83d1-242db539632b | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thouroughly cleaned of all foreign and loose matter prior to pour
b48fa2cc-ba19-5df9-93d0-7658eae1aa96 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
b5d8b3b4-fba6-55c8-ab50-84629a806fe1 | note | INSPECTION/TEST METHOD: Verify
b32be451-645a-570e-acb0-e6732be01a20 | note | RECORD OF CONFORMITY: This ITP signed off
c0827053-2853-5540-a6b3-08bdcba861d3 | note | IP
973ccbdf-2dc1-5fbc-8ede-9f4e211fb162 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
1d408db9-f9d2-5a9d-b84a-611ece6e6b23 | textbox | Date Completed:
e9157aaf-2d5f-4aa3-9626-b707f21fca41 | checkpoint | 2.3 Setting Out
d100e058-1ed9-589d-816b-138cbbfb7112 | note | FREQUENCY: Prior to start
e0faf934-6c09-5635-8c67-9bd99511ead6 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications. No survey/level pegs to be removed by any persons until completion of works.
1ae7a415-22c1-558f-b38f-d710f4ddeffb | note | ○ Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
6aee0e5b-40ff-5d58-a7d2-f4ffd955387c | note | REFERENCE DOCUMENTS: CE-019-ST-0033
5038d782-b637-53a0-bc9d-0385e26c7bc7 | note | INSPECTION/TEST METHOD: Verify
e61484d4-5846-552f-8d29-bbf6e0153b7c | note | RECORD OF CONFORMITY: This ITP signed off
9f0518e9-a04c-5f92-a974-e7ae405669b3 | note | IP
6867b876-053d-5bd3-bff2-9df55e1cd604 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
6f91221a-92c3-57cf-a0ef-adfd950566d2 | textbox | Date Completed:
59a0d91b-f4fa-4a9e-a9bf-152101a58b6a | checkpoint | 2.4 Formwork
927c8ad1-e336-5d64-b98e-a7e065e76412 | note | FREQUENCY: Prior to start
9644b035-7b85-505c-a745-fa4600433d51 | note | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
f3fec1db-ff78-5371-8349-e70bda9e8f4b | note | ○ The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
7fe418e4-512d-509b-a565-36a040f64f9e | note | ○ Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
b0e9726c-72f8-5d06-acbb-2419f497f269 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
f554f7d6-bae2-5d6d-ac18-1c51a3273fd5 | note | INSPECTION/TEST METHOD: Verify
4892a354-baa7-573b-88de-98372ffb9268 | note | RECORD OF CONFORMITY: This ITP signed off
c5eac337-a0c2-5fd2-8ed2-ebea7b05ee20 | note | WP
89487b9b-7c14-5566-968a-f8cf7cf30cf3 | note | RESPONSIBILITY: Fulton Hogan Engineer
a2d4d302-cb33-51b8-82e4-3b5cc989f5ef | textbox | Date Completed:
269ca59f-a9ff-4a96-ac3d-4a9fe80d167f | checkpoint | 2.5 Reinforcement
a4553b4f-e0da-5d08-ada8-dd10b517e3c5 | note | FREQUENCY: Where Required
65a5de6c-ccdf-5976-98c3-ab344f77d4c7 | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
9c27f38d-4078-551f-80ac-81481456283f | note | ○ All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
02113662-b143-546e-8e8f-5fdb83ff9029 | note | ○ Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
083b7e9b-2b3c-582b-a711-9714aa5d8f2a | note | ○ Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
bee6b493-e6d7-5752-a813-0885d130f5e2 | note | ○ Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
d097f83b-e78d-50b5-85bf-bb4f79bfe972 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
3e062bda-c852-504f-a92f-501a9384f968 | note | INSPECTION/TEST METHOD: Verify
ed601a78-1864-5354-a875-1c422e5dd888 | note | RECORD OF CONFORMITY: This ITP signed off
7ca74aba-2925-52ed-b552-1ed142c4a61a | note | IP
59650726-9a0b-52df-9432-3809f309f578 | note | RESPONSIBILITY: Fulton Hogan Engineer
aba86b2d-75c4-5db3-acfa-c2336fdfcfc3 | textbox | Date Completed:
a1b2275f-bd66-4bc9-9c43-e3938546d522 | checkpoint | 2.6 Dowels
be575f7f-6f33-5289-9bb3-150d239c8665 | note | FREQUENCY: Where Required
905ea946-2767-5d76-a494-ca433175cfc3 | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
69dede86-99cf-5f21-91a4-43f936087935 | note | ○ All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
9cc6a30c-f4f1-5d88-8616-867f1773faf4 | note | ○ Dowels shall be clean and free from mill scale, loose rust or oil.
feb9fb2e-07d3-58ce-b63a-ef3432338f8b | note | ○ Ensure that all dowels are securely held in their correct position until the concrete has set.
d4794ac7-23f3-5b40-b6b3-2b9fef226663 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
deac7c0c-85d2-5250-8d5d-81cec66babde | note | INSPECTION/TEST METHOD: Verify
09625fb2-cede-53e1-93bf-0a6eaff78446 | note | RECORD OF CONFORMITY: This ITP signed off
927dc7ec-96b8-5f20-a4e9-b4140be87ab9 | note | IP
2df62b64-1135-527a-92b0-99f0c62b37ac | note | RESPONSIBILITY: Fulton Hogan Engineer
aee1704b-8984-5f5e-bf07-5a8fdc16017b | textbox | Date Completed:
3ba91437-72cb-412b-bbc3-f4c0fbe908f3 | checkpoint | 2.7 Pre Pour Inspection
297f88dd-859c-5472-b617-ed1494ff5881 | note | FREQUENCY: Prior to start
322336a4-35a9-59a8-b867-9683b191e3c1 | note | ACCEPTANCE CRITERIA: Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
7daa75a8-842a-5c80-94f4-606d7639b19b | note | ○ Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
06614c30-7c1e-588d-b83f-f12a8f36596d | note | ○ Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
f24b66ee-b5ed-5afe-b012-9ada964442f7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
f1df2449-4189-5c0a-9b7c-bfe6925844fc | note | INSPECTION/TEST METHOD: Inspection / Test Method
244379bd-e72b-50bc-8da9-99a4212234e1 | note | RECORD OF CONFORMITY: FH Track Inspection
18c46426-e96f-51b3-a795-83ac045795b6 | note | HP
64ef34da-3c6d-5070-95dc-00c2a59a346b | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
859bee6a-5e4c-5b75-b218-80d1e7939ea1 | textbox | Date Completed:
95c7f2f9-1a2d-44e0-8bcf-23c17846d419 | signoff | AUTHORITY HOLDPOINT
14aba434-c80c-480a-b881-9608f9a140e5 | checkpoint | 2.8 Carry out sampling of concrete
8ffe5893-18b0-5c18-ae63-d8bb6e614e7e | note | FREQUENCY: Each concrete pour
e810fff1-baef-5f3b-ad5c-680813f45380 | note | ACCEPTANCE CRITERIA: Slump:
cc37841e-c60d-5fa3-9741-581b57708730 | note | ○ Concrete Slump shall be 100mm +/-20
2ec0c0f2-c7e4-543e-975f-66347b8b36e3 | note | Compressive Strength:
1ede6e36-fe00-586c-a52e-00d1558ea698 | note | ○ Shall be measured in accordance with CE-019-ST-0033
2e73d857-4d41-537a-b6df-ef8a30ce5385 | note | ○ Testing frquency =
5db8340a-372e-580c-9516-6eb3d9a0647e | note | — 0-50m3, 1 sample
bfb50f32-8b1d-5c46-afe8-11ae719d624e | note | — 50-100m3, 2 samples
f748e3c8-9ce0-5dbb-a282-1a41da564f3c | note | — 100m3+, 3 samples
fa476251-c4e9-595c-9c99-637542ece76d | note | Each sample shall consist of 4 cylinders
3d90a124-02e0-519b-a963-c286eeb2e94e | note | Test Results will be provided to the Superintendent
e4c93d53-8194-567b-84de-c4d922830f8d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
0c50ac8a-1de0-51ea-98f6-c30e99106b57 | note | INSPECTION/TEST METHOD: Verify
9dd6d6ca-a1de-5b9e-9bc6-11d323dbc501 | note | RECORD OF CONFORMITY: Concrete supplier test sheet
909f2d62-46df-5b30-8529-1d249b1576ee | note | TP
287c003a-a7bc-5c86-b2b4-78718c355062 | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendent
52a69575-384e-5dcd-9c78-daed676f0a9e | textbox | Date Completed:
3e3067b3-db60-412c-ad73-b836d97b0831 | checkpoint | 2.9 Concrete Placement
13db42d0-9436-5a60-b49a-6ecb97e225f2 | note | FREQUENCY: Each Lot
bada1b08-421a-55c9-bb35-91436ab06122 | note | ACCEPTANCE CRITERIA: Ensure formwork is clean
cd64dd69-81bd-5ebe-8c0c-85f7541d2cbb | note | ○ Concrete shall be entirely discharged 60 minutes after batching,
29da4d6a-1885-574f-ac6f-e7b2c62be4f4 | note | ○ Ensure that pouring does not occur from a height greater than 1200mm
bc5969d9-a7e6-5c37-8a11-ec249ac96b44 | note | ○ Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
a7fe7a1e-0e69-50f7-b0f2-dfd4632af5bc | note | ○ The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
834701e9-1e43-5760-a028-60c4b073bb2e | note | ○ There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
e5e2dd3b-227c-5306-949d-9f986187c2cd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
d24f7b98-602d-5f1b-a546-3cf3d15fbab8 | note | INSPECTION/TEST METHOD: Visual Inspection
86da8d77-89ef-586f-8d02-9d65312a4f04 | note | RECORD OF CONFORMITY: This ITP signed off
736e9a65-ae8d-5026-88fe-3476380c6f33 | note | WP
2ae14714-1a4c-52d5-a224-270163815d96 | note | RESPONSIBILITY: Fulton Hogan Engineer
4b83b0fd-709a-53ce-88d7-6d95649145bf | textbox | Date Completed:
52c3204e-e00f-4a6e-83ff-76ff0a4d4bba | checkpoint | 2.10 Compaction
1f12a427-a771-5677-81b0-067893629284 | note | FREQUENCY: Each Lot
6f1e3aac-5e67-5dbb-a018-f8b2ba509170 | note | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator
bb3957a5-84e9-5e6b-a52d-031503ec3cdb | note | ○ Vibration shall take place until exposed concrete surface is free from air voids
5c72dc47-1c15-5b8b-bf8f-a4df9ca5aafc | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
45e3811c-200c-5a54-a2f0-a4ca7b08c2ad | note | INSPECTION/TEST METHOD: Visual inspection
9a34ef80-c3ef-57c6-a1f8-61715bdaa47a | note | RECORD OF CONFORMITY: This ITP signed off
1e828a73-6e33-509a-9e1d-fbe1f91afe37 | note | IP
8bbf9436-2d5e-5ec2-ad59-6a8c6e858efd | note | RESPONSIBILITY: Fulton Hogan Engineer
3a95399b-1183-5765-ace4-844e42d3f3c4 | textbox | Date Completed:
ff7a91fe-213b-4c99-bae2-c1aca260eab2 | checkpoint | 2.11 Record location of each batch
5ea9d92b-bedc-52f3-9637-54a52c9a8711 | note | FREQUENCY: Each concrete pour
fa27e711-f554-5d90-bced-67aacb14aeb6 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
39efa2bb-fcbd-54cf-a2ef-5ae62072504e | note | REFERENCE DOCUMENTS: CE-019-ST-0033
252e86e9-1eb3-5655-9199-9429cc68de46 | note | INSPECTION/TEST METHOD: Checklist
4175f0e4-7814-5e7d-b342-c152b9f59181 | note | RECORD OF CONFORMITY: This ITP signed off
fbd04156-16ab-54c5-9e1b-8a84d3e57586 | note | IP
666cdfd2-09ab-5d33-8cde-276a160f5231 | note | RESPONSIBILITY: Fulton Hogan Engineer
d118f987-7a69-544e-a8c7-fd2e6ca12df4 | textbox | Date Completed:
60cc643c-bf76-4d00-919c-0bbb6892535d | checkpoint | 2.12 Curing
49fc2096-46d2-5a37-87d5-b584f3e481a9 | note | FREQUENCY: Each concrete pour
86b1096c-b210-53d9-8cb4-60e0a67ce307 | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
d08d04b1-ffb9-58b3-bb11-e0177655b313 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
81bd0075-4cb0-5358-a2bd-68722367d795 | note | INSPECTION/TEST METHOD: Checklist
baf44eca-eef1-5451-a592-59fb4d9d4475 | note | RECORD OF CONFORMITY: This ITP signed off
9ce01a19-fac2-51d4-bc1e-f319bc98f8f7 | note | IP
6d1eda0b-7068-5000-b063-7ccd3181d843 | note | RESPONSIBILITY: Fulton Hogan Engineer
3450d6aa-2bfb-5f88-b1bb-6aa0071b223a | textbox | Date Completed:
7528eab3-5532-4a7e-915f-b531d0d2d392 | checkpoint | 2.13 Tolerances
c8d95fed-1059-5992-857d-4528b7cb00cc | note | FREQUENCY: Each concrete pour
aaa273c7-62c8-54dd-8fb8-7f8608a056e6 | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
84fd29c2-5f87-5270-a8b9-0ff3156ef297 | note | ○ Plan dimension of slab +10,-10mm
b53b96ed-5556-501d-a998-84704bfbaef7 | note | ○ Thickness of slab +10,-10mm
6943d12b-0877-5aa5-b70a-9b661fcf908e | note | ○ Cover to reinforcement +5,-3mm
4932564d-39e2-5f1b-99b3-1e6f4e30dddf | note | ○ Finished level of slab +3,-3mm
cf2df360-d914-55c4-902c-d4f2d6e86101 | note | ○ Foundation level of slab +0,-20mm
4f065a25-c475-52b0-9d6e-37d197ea07fb | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
5721ba2e-08ac-5ffa-ac1f-4f76a9c1119b | note | INSPECTION/TEST METHOD: Checklist
30bdf991-d6c0-5d43-9916-efd8086383d4 | note | RECORD OF CONFORMITY: This ITP signed off
97e3fce5-a6fa-5e60-bf43-224f5e4dbd97 | note | IP
6d5a6e41-1f26-5cb9-80a9-96ad328cd1f2 | note | RESPONSIBILITY: Fulton Hogan Engineer
87415774-7c95-52ad-853e-0b6dfaf0ad91 | textbox | Date Completed:
91e345c9-5793-465a-9160-1219f4daf5c3 | checkpoint | 2.14 Slab finish
f3246afa-baf9-50e9-9ace-83105259adaf | note | FREQUENCY: Where applicable - if track is Type 1 structure
5a4a5656-2843-5951-97be-e1bfccf2ddb9 | note | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities. All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections. A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C - This is only applicable for T-rail/Vignole rail profiles. The slab surfaces shall be broomed to provide a non-slip finish.
a2be6a39-7795-5dce-abd5-a14b4ba2f2f1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
0a47d67f-977c-579a-8d3b-c7b075a604d9 | note | INSPECTION/TEST METHOD: Checklist
466a3abf-6a5f-5574-a14f-977b2349b49a | note | RECORD OF CONFORMITY: This ITP signed off
9ec164f6-242d-5423-a409-a28a4b4d2ac1 | note | IP
0b31ee8c-916c-5d84-a697-6370ecbd6e6c | note | RESPONSIBILITY: Fulton Hogan Engineer
19ec648e-c65a-5e51-b85a-65d68592eb8f | textbox | Date Completed:
4a3ef7a4-cb00-44ae-be67-2d802a9d06c4 | checkpoint | 2.15 Post Pour Inspection
a78f440c-9519-59fd-bb37-071c99a89fca | note | FREQUENCY: Each Lot
f9ac857c-29e7-5e39-a084-0af4bdea24ce | note | ACCEPTANCE CRITERIA: Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
b3fb2fa9-1365-5882-9ec8-2d67c05f7e61 | note | ○ Ensure no defects are present in slab
b432fa7c-e234-5dd9-b81b-a6afc0b989fb | note | ○ Complete Fulton Hogan Post Pour Checklist
1b884170-053f-5476-ab7e-2b27c6b6a4e6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
b00d9fd9-7b54-570f-8929-6678c8cefb3b | note | INSPECTION/TEST METHOD: Visual Inspection
0e0a4a24-7ebc-5028-bf39-b0940f402859 | note | RECORD OF CONFORMITY: Post pour checklist
dc6542dc-fb09-54de-8477-084b2d9b6bce | note | IP
e45cee7b-5609-51d8-80e7-af0faff3bb8a | note | RESPONSIBILITY: Fulton Hogan Engineer
350b5963-195d-524a-9b70-0abb48eb34e8 | textbox | Date Completed:
3a92030e-91c9-43df-a189-1368a0561541 | checkpoint | Final Inspection
635c4dd2-4cfe-556f-9c1d-215327dfcb93 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
90f9541f-e818-5a38-bc36-e1dfb0592e32 | textbox | Print Name:
986c200b-03df-551c-9e7f-51c1c646fc28 | textbox | Position:
a877f273-52d7-5e1b-be1a-74663afca57a | textbox | Date:
f7a60ef6-852c-443f-bd03-bd5194469103 | checklist | FHC-ITP-005 - Subsurface Drainage Burwood Rev 2 | itp | FHC-ITP-005 - Subsurface Drainage Burwood
bd2a7ac2-cbe1-4e2f-911b-1bd2985c85a7 | section | Preliminary Works
dea0712a-a460-4ef0-8765-dabaad680ae4 | checkpoint | 1.1 Check for correct documentation
6129fe7f-e546-5d75-8161-abedf43a1f36 | note | FREQUENCY: Prior to commencing any activity
e078597e-a482-5e89-8f90-e1202dcc1342 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
77fa9793-40b0-5aac-9dd5-368d7df7d3a5 | note | — using the correct and complete set of drawings
0fa65a44-1856-5634-a67b-9395a569039c | note | — all drawings are the latest revision
ed5c3f1e-8dd8-58a6-8b7b-9f4cdcb98f02 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
718f24c8-9980-54ab-86ba-3d5842d639b5 | note | INSPECTION/TEST METHOD: Visual inspection
a3a26bae-7e68-523c-8825-c56d7d8e0019 | note | RECORD OF CONFORMITY: This ITP signed off
ad6f2ecf-7e79-5d35-9538-ce2ad07fe6ea | note | HP*
18f8b215-1606-52d8-9dc8-d6d2c04752a6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
dc26342e-e4ea-55ee-bc08-65dbf080bbbc | textbox | Date Completed:
d4bb9c37-6a42-4643-a182-a543aaf6177a | checkpoint | 1.2 Implementation of all measures and controls
f3478471-40cf-50e3-8295-3ef28cdb46b4 | note | FREQUENCY: Prior to commencing any activity
67515c36-6e1a-5f9a-a47c-9a48f3d2c301 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
9b04c62b-1b36-5e3e-a035-fdc0b2d4ce82 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
b4eb855e-1331-5126-bdef-23bc24d67963 | note | INSPECTION/TEST METHOD: Visual Inspection
544d1c9a-bb66-53df-8ca4-ba3713244968 | note | RECORD OF CONFORMITY: This ITP signed off
6c60a88c-d48d-5d06-9f3b-40618e36512a | note | HP*
abac98f9-b488-55f7-95eb-4272dfff2897 | note | RESPONSIBILITY: Site Engineer / Site Foreman
06dd4ca5-1149-5a67-9214-8f14eae063a7 | textbox | Date Completed:
b4423775-5ce8-4e3d-bdef-738d125c3f8e | checkpoint | 1.3 Placement of no fines concrete
31358b06-2746-5f2b-ae19-2b6e26efaac1 | note | FREQUENCY: Prior to works commencing
a6426830-77df-5e98-80a9-55a5cd1cafae | note | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures
dc4b28ca-4127-5e14-bda4-114d48e84020 | note | REFERENCE DOCUMENTS: 702.09(g)
eb39f922-3a6a-52ef-a263-22a40dbe26db | note | INSPECTION/TEST METHOD: Verify
b594893a-6795-5281-95d9-670457fead7c | note | RECORD OF CONFORMITY: This ITP signed off
16e7bf95-69fc-597b-b3aa-816dd0287cf1 | note | HP
54802e26-df6c-5d3d-b908-94086d49045e | note | RESPONSIBILITY: Site Engineer/ Superintendent
682c3ba4-1d01-5003-a4fe-2f2a7cb22e41 | textbox | Date Completed:
7c6a5cda-15fb-48c2-896d-a8d92fddae47 | signoff | AUTHORITY HOLDPOINT
3bceb1de-6f52-4576-b321-cca598f26385 | checkpoint | 1.4 Material Classification
2553f600-c98b-5c45-9ccc-c2150fd599a0 | note | FREQUENCY: Each Lot
788a80d5-1440-53e7-ac31-0740a6bf2d4e | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 corrugated perforated plastic pipe - with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
c36743e6-2e2e-5cd9-91cb-550202fe4a6e | note | ○ Granular filter material for bedding and backfill: Trench backfilled and bedded with specified material on drawings
ab78bae6-7d97-5115-9dd0-8f14816a99c0 | note | ○ Geotextiles; Shall comply with Cl 702.06.
df79aa8e-f895-571f-9b55-54556618d7c2 | note | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of IFC Drawings
28a68eed-4eba-531b-b7d7-0581fb0826c1 | note | ○ Flushout risers: constructed to the detail of IFC Drawings
f370ef53-d399-577f-93d3-a79124a8f7ec | note | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
218ae7d1-806b-5555-8cbe-e453c08e318a | note | INSPECTION/TEST METHOD: Verify
f34c1121-89d2-579b-a3b9-663f65f6d6aa | note | RECORD OF CONFORMITY: This ITP signed off
1b76ad93-34ea-5671-bb7d-693bde30756b | note | WP
f23e9189-1dbe-511c-bcec-17e4854e9349 | note | RESPONSIBILITY: Site Engineer
00c591f3-3055-5e75-a561-7ca20340005c | textbox | Date Completed:
10eacdbb-2f24-460f-8dde-3d09b2e90cb5 | section | Construction Works
2cd5eb95-8348-48fd-87de-f1117179bb7f | checkpoint | 2.1 Excavation Permit
6f09185c-7825-517e-be5e-3974df6ea35b | note | FREQUENCY: Each lot
25830790-47ab-5909-9c8a-d966607ec952 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
8d1ae741-f769-5775-9c3d-bc9c7b167060 | note | ○ Plant and equipment shall be appropriate for the task.
2448dd67-bf7d-5c7c-af92-d9f7ed67dc28 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
b052978e-8b0f-538e-bbfe-14272dd7dbdd | note | REFERENCE DOCUMENTS: Excavation permit
9d5f579f-4ad8-5dbe-9873-67d5d18b3c85 | note | INSPECTION/TEST METHOD: Verify
50cb6dc6-864e-586b-b170-c0afc592c434 | note | RECORD OF CONFORMITY: This ITP Signed Off
4095b8e2-80ab-5885-97e4-d0e265755be6 | note | HP*
c65365a4-f2e0-5ba0-b45d-56b730707e88 | note | RESPONSIBILITY: Site Engineer
d2585f21-5baf-5653-8400-e47944ac0460 | textbox | Date Completed:
8908067e-8671-4473-bd7f-6ce9f58bf603 | checkpoint | 2.2 Excavation of Trench
450ac7c7-65bc-5a56-8619-bf383ddd6d42 | note | FREQUENCY: Each Lot
c520f6e7-25fb-54ad-8a04-75d5d69fb5d6 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
3520d245-f8f9-511c-814f-bf45aaf69977 | note | REFERENCE DOCUMENTS: 702.08
4c5a72ec-88fb-5a5a-a876-5ce4b8627078 | note | INSPECTION/TEST METHOD: Visual Inspection
8d9d9a44-27c9-59b2-8683-3d75ee6b956a | note | RECORD OF CONFORMITY: This ITP signed off
f751341f-2e58-54d8-b91e-7b16cd751683 | note | HP
b08f3e78-462b-58df-94c0-e598e326cfc7 | note | RESPONSIBILITY: Site Engineer/ Superintendent
65bd87ae-ecae-5023-80cb-b7aefc6b862d | textbox | Date Completed:
a5c204ed-9a61-4eeb-ab46-f984a19eb33a | signoff | AUTHORITY HOLDPOINT
8f5170e3-2ac0-43ab-95af-56e620848647 | checkpoint | 2.3 Placement of bedding
6abef592-a7fc-579e-b0e6-e238d3a4e187 | note | FREQUENCY: Each Lot
a4c28de1-3c2e-594f-88b0-be75cfaf33db | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
a6068dc0-7ab2-5064-af5d-a957566e8faa | note | REFERENCE DOCUMENTS: 702.09 (c )
0c38efcb-7b0b-5eea-a7c1-53a93672bdcd | note | INSPECTION/TEST METHOD: Visual Inspection
115bb729-d065-5f49-baac-7a0461dfbb68 | note | RECORD OF CONFORMITY: This ITP signed off
009c5b05-710b-5c9f-82f9-6372214b6197 | note | IP
6c927d79-5c59-5cd7-bf75-08f7bf8d0ebf | note | RESPONSIBILITY: Site Engineer / Site Foreman
960be361-b490-5f0c-9a19-d7e70fc76d14 | textbox | Date Completed:
abef574f-0c5d-49bd-82c5-493835a95ef8 | checkpoint | 2.4 Placing pipes and geofabric (if required)
3a96fa5f-a41e-5e37-a9e5-b519597f4954 | note | FREQUENCY: Each Lot
d9541dbf-ea09-58f1-ab73-a003c4f56122 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
457dc17a-271c-5ad8-ba88-fbcb2d5897e4 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
a222c6ed-cb47-5a47-ba51-fbb0f6baa46e | note | REFERENCE DOCUMENTS: 702.09
f53ec10e-d290-54fa-a539-8b0edf8c7536 | note | INSPECTION/TEST METHOD: Visual Inspection
5b2f6ad5-c909-5cd3-893b-615559577dc2 | note | RECORD OF CONFORMITY: This ITP signed off
0bf681a2-2c65-514f-84d2-bc7cd5fe2437 | note | HP
6d2df7d6-65fb-5f5a-bd37-8bd65cf96d32 | note | RESPONSIBILITY: Site Engineer / Site Foreman
98d48ab0-f55a-5c29-830c-4402fe60ce93 | textbox | Date Completed:
7357f8f1-d24a-47c7-b8a8-b7a5f7da1f8f | signoff | AUTHORITY HOLDPOINT
63271f3b-8e9e-4c38-943e-dc8a6cbc2d11 | checkpoint | 2.5 Placement of backfill
62424450-ec61-5f44-aa40-34112825d40a | note | FREQUENCY: Each Lot
1fd0852c-d4b7-56cb-a6c3-ff04cc92f3bd | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
8b8831bf-e547-5292-a0f4-a11b978bb749 | note | REFERENCE DOCUMENTS: 702.09 (g)
5467dd8c-b53d-5ab4-a19f-d27288c985d5 | note | INSPECTION/TEST METHOD: Visual inspection
87df1548-d0f4-5418-ad4a-bd49e11d563e | note | RECORD OF CONFORMITY: This ITP signed off
d641fae1-d486-5872-b23c-e22c37c55c86 | note | IP
1523e48e-91c9-58e7-aeb9-0587f4cbaa68 | note | RESPONSIBILITY: Site Engineer / Site Foreman
d763626c-6bd7-55e7-9219-4accb2ea886f | textbox | Date Completed:
a05467ca-5749-4c74-bb77-7e62bdc3913e | checkpoint | 2.6 Install Pits and Flushouts
9d5fe0e6-bbb7-5d9e-b550-1fd5c42b3949 | note | FREQUENCY: Each Lot
8aa7bbe4-1368-5dd1-b8cc-9d9f8414ba6c | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
21e27d2d-c2fb-537f-8c68-82d6ef72482c | note | REFERENCE DOCUMENTS: 702.1
37a0d9b8-1379-5cdc-a5de-b86991f6c816 | note | INSPECTION/TEST METHOD: Verify
af41c642-4794-5b73-980a-82b7aa6946b5 | note | RECORD OF CONFORMITY: This ITP signed off
c044af30-ad69-5742-bcfb-eed47fe6fb4f | note | WP
38034a0b-a94e-58cc-86cd-f7d1e234a538 | note | RESPONSIBILITY: Site Engineer / Site Foreman
1b623279-85e4-5bdc-bb49-2e70346c1807 | textbox | Date Completed:
a8daf58b-4dc8-485d-81c9-164029883408 | checkpoint | Final Inspection
c2b2800a-9e2a-5d81-83a9-c73be0efa3bb | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
65196a14-b8eb-5197-a50e-22645555b4a3 | textbox | Print Name:
b3cf2e53-86ff-50f4-9286-cf7844154ef4 | textbox | Position:
515d0663-0322-5acf-8c6e-ab489a0e7fd3 | textbox | Date:
46e5ea48-5474-49ac-9a05-29c9e20b67aa | checklist | FHC-ITP-006 - Kerb and Channel Burwood Rev 2 | itp | FHC-ITP-006 - Kerb and Channel Burwood
5a7c7b8f-bdf9-4a77-977c-0998b98d1a72 | section | Preliminary Works
50cef530-fa3e-4d49-9c24-b9beae1bb017 | checkpoint | 1.1 Check for correct documentation
973c0b00-719b-5e5b-9677-25948db7304c | note | FREQUENCY: Prior to commencing any activity
0deb37e4-9210-580f-9fca-a6525f501963 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
c3561504-e022-5712-b687-29a9aee497e8 | note | — using the correct and complete set of drawings
6c47fda5-fd47-5c83-9b60-4dff0b11259f | note | — all drawings are the latest revision
624886ce-c0b2-56c2-b446-2484f3cd4e2b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
59730c34-abff-50cc-948f-861ddbb84429 | note | INSPECTION/TEST METHOD: Visual inspection
1da3b0b7-01b0-5719-9ba4-fe0893db5118 | note | RECORD OF CONFORMITY: ITP Signed
9278c57d-d212-5019-9aa8-79156375819e | note | HP*
4f8ef4d7-7dbb-568c-80f3-0b07effb5ff4 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
e13fe700-8e4d-5a11-9997-0725d33f5ed7 | textbox | Date Completed:
e4dd704b-01bd-45db-8129-b139e5a35db8 | checkpoint | 1.2 Implementation of all measures and controls
022bbdd3-fb71-547d-b561-40a3fca2e03d | note | FREQUENCY: Prior to commencing any activity
31cc8358-5f1e-5bfd-a8d8-2c2540aaa630 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
92b86d4f-9e8b-5408-adaf-3955def1452e | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
32617fbb-06a3-52dd-a66d-48611acf36ab | note | INSPECTION/TEST METHOD: Visual inspection
04bb8f73-6419-5f6c-b2fb-4663ac39f8c0 | note | RECORD OF CONFORMITY: ITP Signed
005a920d-9a23-51cc-8220-9a896a36a80d | note | HP*
ad6b989b-0e9a-59c5-90a4-f994b72691e7 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
94801e06-727c-5652-a6ff-09e5ea1487c7 | textbox | Date Completed:
711f42e2-6883-4e45-996a-ea9c139ecb25 | section | Construction Works
37e1f6b4-81f1-41e9-ba84-16ded9d7552d | checkpoint | 2.1 Setting Out
7ca13f67-6dcf-59e8-a42f-2242b0ec96c6 | note | FREQUENCY: Prior to start
797bafe3-1c2b-5144-b5e2-b5e8610468fc | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
8637b49d-98cc-5fc5-8a66-e5cedccf8737 | note | REFERENCE DOCUMENTS: 703.17
26cc4c28-8332-56bf-9c16-5a2a99349064 | note | INSPECTION/TEST METHOD: Verify
42a55f12-d3b6-525c-b495-b764589f34ec | note | RECORD OF CONFORMITY: ITP Signed
d8ac4a10-3983-55ea-abd0-b9f91eabc04a | note | HP
fb0b822d-b209-5975-b034-c48538420e1d | note | RESPONSIBILITY: Site Engineer/ Superintendent
39c62d55-08ca-5d6f-bf54-bcbc87b31ffc | textbox | Date Completed:
cb73b59d-a00b-4cb0-b9a2-ba6989ea5b9c | signoff | AUTHORITY HOLDPOINT
20ac01d8-c985-442a-9852-5a578ea4d500 | checkpoint | 2.2 Temporary Drainage Provisions
99bd8772-4bbc-5b98-ba6e-5642c87dd006 | note | FREQUENCY: If Required
a8d8f528-22ce-5f5c-8732-b2cd4ba93e6b | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
d279af97-424b-5335-a987-3ec3706765eb | note | REFERENCE DOCUMENTS: 703.18
45da9073-6c0d-54e4-8372-8264e77d2bd3 | note | INSPECTION/TEST METHOD: Visual inspection
fb8bdcad-638b-5e72-8eab-eb184e597d8e | note | RECORD OF CONFORMITY: ITP Signed
7785b82b-a4d4-53e8-831f-2fd0478fd2f7 | note | WP
c7027cd2-99e6-5803-83e7-38d83f9017ee | note | RESPONSIBILITY: Site Engineer/ Site Foreman
1ac80e0c-2289-5890-9305-23e8505d9bf1 | textbox | Date Completed:
7957b5cd-c5b7-491e-bebb-bd9d8604f743 | checkpoint | 2.3 Bedding
7e8d3447-37fb-5cd3-8c9f-764e65699171 | note | FREQUENCY: Each lot
e144aff8-844b-5484-8ff4-6cda37da41b2 | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
f91293ed-8268-529d-bd55-78e0572917fc | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used and compacted to a thickness of not less than 100mm.
89f633e2-a8b9-511d-b0da-9a8232843e27 | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
756955cd-068f-501e-9ca6-8088e4bda8a3 | note | REFERENCE DOCUMENTS: 703.21
3ad663aa-7a81-523f-8a2d-d57d00a63335 | note | INSPECTION/TEST METHOD: Visual inspection
7149e5cb-24a9-5e9e-a350-3fe499a33c0b | note | RECORD OF CONFORMITY: ITP Signed
1dce0f9f-50cf-56cd-b1e2-be194c1e99c2 | note | WP
f1bc2047-96f5-54f8-886f-9a513aae0ffd | note | RESPONSIBILITY: Site Engineer/ Superintendent
5f9d5a49-5f05-5937-9fa1-b093d0cd516a | textbox | Date Completed:
5de11b9f-8932-4da4-8b9a-161a2398082c | checkpoint | 2.4 Pre-concrete check
229093b4-0490-53b5-a558-f577d9b06678 | note | FREQUENCY: Each lot
86ad0e9e-c67e-5105-b423-5363aef0a5f1 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
df7fe3ad-4799-5a32-858c-5c6b968e5e77 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
d74a3812-af50-5b35-a729-efd2df37df75 | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
ce1ad120-1625-56be-9f7b-de75712acf57 | note | REFERENCE DOCUMENTS: 703.08, 610.17(a)(b)(c)
176824a7-8277-5d3e-9389-2ffee941eab7 | note | INSPECTION/TEST METHOD: Verify
b7f94307-b5e2-58b4-b4e3-70997e6e9634 | note | RECORD OF CONFORMITY: ITP Signed
408dc851-b2f5-5c95-a970-041faa598b13 | textbox | Ambient Temperature |  |  | °C
fbcb1771-360b-5296-a014-a93f1f947e23 | textbox | Concrete Temperature |  |  | °C
13eae2f4-ac4d-5c12-97ee-1ff23cca3ae4 | note | HP
32ca5841-9dc8-5b37-82f7-ad09bf3ad8af | note | RESPONSIBILITY: Site Engineer/ Superintendent
fc71729a-a887-5e22-a05a-d85f498ed007 | textbox | Date Completed:
e88682eb-c26c-4c33-8e96-2625c58c934f | signoff | AUTHORITY HOLDPOINT
5894b389-3024-47a7-ac4b-fd4754ed7e70 | checkpoint | 2.5 Concrete Placement
ad38bb9f-bc21-5aa0-93bc-30f9627aa266 | note | FREQUENCY: Each lot
97ec10d4-1614-5a45-aa79-0bc24aed950c | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
e33bb382-9530-5031-898b-f2a922ef1c28 | note | REFERENCE DOCUMENTS: VicRoads Spec 703.23
7b6094d2-62f4-577c-9b65-ec6150233a9e | note | INSPECTION/TEST METHOD: Site Inspection
2e3346e8-63ea-5312-bd53-ed7ed92e3128 | note | RECORD OF CONFORMITY: ITP Signed
9b2c5dc7-76de-58b7-b884-439c594dc10c | note | IP
35a10ea1-b77b-525a-b7fd-e8f608153957 | note | RESPONSIBILITY: Site Engineer
f73fd015-dd65-5223-b84f-5818c1e797bc | textbox | Date Completed:
fb47fff3-2e36-421b-8e7d-08a6a8514a7c | checkpoint | 2.6 Finish Surfaces
55bc75a4-f7be-5d91-bfdf-045958023245 | note | FREQUENCY: Each Lot
1bef35cc-4ca3-50dc-8a37-ff222918716f | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
afd37f1e-749e-541e-a668-2c008a265b9b | note | ○ Concrete to have a neat appearance and uniform colour.
96fdeb27-4d35-5309-8dd7-37f1570cf3d7 | note | REFERENCE DOCUMENTS: 703.25
610bbdba-f507-5371-bfed-a1a6eaac4506 | note | INSPECTION/TEST METHOD: Visual inspection
da251a88-ea0b-5236-b854-b7e743d000c9 | note | RECORD OF CONFORMITY: ITP Signed
5f9dbf6c-56e0-5944-a377-edef6f15f82a | note | IP
b4e46961-ee99-5a31-9651-85fe386fa347 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
7ec2181a-5c0a-5c2d-9a1d-3a16feb36405 | textbox | Date Completed:
373fcb2c-49a5-44ec-be42-c70d1a884795 | checkpoint | 2.7 Tolerances
2eb8a574-60de-5472-9094-8d6e568c9074 | note | FREQUENCY: Each Lot
3467b609-b053-5b6f-895c-ad7ba62ced72 | note | ACCEPTANCE CRITERIA: Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of ‑0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
d4b602ea-68e8-5e4c-b1ee-162f67f6994a | note | REFERENCE DOCUMENTS: 703.15(b)
1d554c77-c5bc-5129-a462-6ce8572f17cd | note | INSPECTION/TEST METHOD: Verify
06aadc52-a50f-5e04-b0ed-a53fce9ff8a0 | note | RECORD OF CONFORMITY: ITP Signed
c9868579-f7ec-5f06-b55e-5087acc7d681 | note | SCP
642310dc-80e5-5fac-b3da-59de3dd00294 | note | RESPONSIBILITY: Site Engineer/ Surveyor
ad193fe8-4d47-5d08-a982-00fcfee68f4a | textbox | Date Completed:
63ff9ccc-8af2-4130-bf4f-65515ca41d0b | checkpoint | 2.8 Joints
0180cf08-84d8-5e18-b085-0c4661d0b317 | note | FREQUENCY: Each joint
796fc91f-993f-5f34-a8d1-467ec41a0fba | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
ea59fcdf-2872-535e-866b-52d8b4b01fef | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
88c7000e-949a-5637-a11f-b4ccc0098cb4 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
bb2886cb-cefa-5b36-8fe2-77a0d5c6acaa | note | REFERENCE DOCUMENTS: 703.26
39adb2f2-1715-5432-ae88-ed75779121ed | note | INSPECTION/TEST METHOD: Verify
2d3626ae-a040-5966-9fbb-90cb8ba464ec | note | RECORD OF CONFORMITY: ITP Signed
b732285a-becf-5cea-a4d2-664bcdd488f0 | note | IP
f06548f3-b0c9-5ce5-a48a-f1a0dcacb739 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
714db9ba-fe30-5c2b-afad-8774a3cf7487 | textbox | Date Completed:
eb2c6135-1e62-4641-8229-90ba2e373409 | checkpoint | 2.9 Backfilling
57cea812-79ba-554d-b30c-46ac219c42e2 | note | FREQUENCY: Each Lot
3f78751e-e7b9-5fc4-ac1b-53fbf8bf2a55 | note | ACCEPTANCE CRITERIA: Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
a6072b29-69a2-5392-b7c3-17434668c3e3 | note | REFERENCE DOCUMENTS: 703.29
3512c904-2a47-5d1a-a35d-7465b61115d6 | note | INSPECTION/TEST METHOD: Verify
4034a540-5f19-5f0c-b628-430d7295f82d | note | RECORD OF CONFORMITY: ITP Signed
c3894a4b-8eae-50e8-8f9f-f35e93fac160 | note | IP
051d9551-0387-5a06-9a29-314284e5d28c | note | RESPONSIBILITY: Site Engineer
71f2bc33-9161-5eda-8ac7-69de1cce1e96 | textbox | Date Completed:
4ab907b7-7d52-48f1-a304-d52738c46431 | checkpoint | Final Inspection
52086245-8274-5535-9c80-c987fac982e6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
649be40c-7be1-5f99-848d-4068aad6685f | textbox | Print Name:
32d66c9a-6dce-5be6-bc6e-79ca961e14d6 | textbox | Position:
ed6b0ff5-d1b5-51fa-a824-a4e813858ea5 | textbox | Date:
5200c5cb-62ae-4a38-921e-2ae11714ac18 | checklist | FHC-ITP-007 - Structural Concrete Construction Burwood Rev 2 | itp | FHC-ITP-007 - Structural Concrete Construction Burwood
8f5dd0b3-5779-4b3b-b48d-84451c38c621 | section | Design and Submissions
97891f41-1543-458f-aa0f-e15200702854 | checkpoint | 1.1 Check for correct documentation
41769392-19df-5422-a675-98e3e8caf3b3 | note | FREQUENCY: Prior to commencing any activity
3116adbc-3882-55a1-bda3-c8a93d3985f6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
083e2178-c03d-56fa-9a53-723c75c72d11 | note | — using the correct and complete set of drawings
1ed12c0f-ea29-59e9-ad95-832b34f318b1 | note | — all drawings are the latest revision
5fbc3c81-a601-56f3-8e36-eec97e639cef | note | REFERENCE DOCUMENTS: Drawings and drawing registers
055310d2-b09a-54b1-a75a-bd19d2ef9ba3 | note | INSPECTION/TEST METHOD: Visual inspection
14e8b123-b1be-51da-b713-a9a9647a1661 | note | RECORD OF CONFORMITY: This ITP signed
deb9e716-5485-5957-a4d5-0cb8941c7100 | note | HP*
3a434c65-44d0-567c-aad1-d097b01f048f | note | RESPONSIBILITY: Fulton Hogan Engineer
74bb04b1-dafb-57b4-8bf0-8024e948775b | textbox | Date Completed:
ff3f64bc-e53f-4ad8-a85d-6801337dbcd8 | checkpoint | 1.2 Implementation of all measures and controls
e4815e4f-fb74-591c-b7ef-b34140b3780f | note | FREQUENCY: Prior to commencing any activity
d4e34307-9330-520c-a7ab-49327750ffb3 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
cdde6043-29b4-5c15-9cad-1447c09255d0 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
17ff58df-8920-5589-98e8-c27809f38889 | note | INSPECTION/TEST METHOD: Visual Inspection
939d1b1e-c751-5442-b391-e18bd4c17e99 | note | RECORD OF CONFORMITY: This ITP signed
2179005f-e413-5c48-ab7f-875d8b26ad6a | note | HP*
a88302b6-73c3-5daa-8155-68f6bfa1a0a7 | note | RESPONSIBILITY: Fulton Hogan Engineer
49d0b4cc-5e72-5ede-81b3-e3f5a8498e48 | textbox | Date Completed:
69ccf789-7d33-4392-a738-130ed64e111d | checkpoint | 1.3 Approval of mix design
db964045-088d-54e2-8d7f-07a1bf949aff | note | FREQUENCY: Prior to the first concrete pour
a1ad2320-4417-5975-8395-2f8618998900 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
56f91102-add3-59b9-bc28-80ac9b937ec4 | note | REFERENCE DOCUMENTS: 610.07
7f972ccb-1a62-5cbb-8a9d-6b4bf042181d | note | INSPECTION/TEST METHOD: Verify
84016902-1c56-5ba1-a8ca-f69eb9df9669 | note | RECORD OF CONFORMITY: This ITP signed
ab142c7a-780d-5d27-8428-19ac4577724b | note | IP
e7139a9a-1e6d-52d6-97a7-86e43f1b872e | note | RESPONSIBILITY: Fulton Hogan Engineer
40c1cec4-e969-5d3d-b837-990b47ff59af | textbox | Date Completed:
a498cc64-d804-46e4-b8bf-5c9c65e34aff | checkpoint | 1.4 Reinforcement schedule
7b28a565-1678-5d4d-8e7a-7308943e1728 | note | FREQUENCY: Prior to concrete pour
824c0f98-78e5-5899-9b16-94fe5a1403b6 | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
5c1156f4-eff5-51b1-8538-f66dc7bf437d | note | REFERENCE DOCUMENTS: 611.04
2ded6270-25f7-5eb5-a91e-b527812696a3 | note | INSPECTION/TEST METHOD: Verify
0f51b676-c3c8-5bee-9311-1d76d1ec5a7e | note | RECORD OF CONFORMITY: This ITP signed
19e7cba7-84f3-5ee3-92fd-44df1efcf599 | note | IP
a86dcd64-16db-55b2-b0a8-fa97393df9f8 | note | RESPONSIBILITY: Fulton Hogan Engineer
426a402e-6c82-58e3-81c0-792c3accd762 | textbox | Date Completed:
fb8df60f-f242-478f-bd4b-cb3c77716403 | section | Construction/Erection of Formwork
fa6545c7-600e-4fb1-9e74-8cf4bf248c1d | checkpoint | 2.1 Excavation
00926b20-4126-5651-8203-7653e8f86aaf | note | FREQUENCY: Prior to concrete pour
d2140cdc-f09e-5925-b29f-cbe1aa99e1b8 | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
540bf212-90e0-50fa-9c0b-0487729b392a | note | REFERENCE DOCUMENTS: Contract Drawings
bd83ede7-d642-56d5-9fc8-7f975bfb88bb | note | INSPECTION/TEST METHOD: Inspect
d866fc65-d3b5-5be2-a6f2-0b1fd22f6ee2 | note | RECORD OF CONFORMITY: This ITP signed
b83e5957-f58a-5fb0-8606-90e01c9a8fc9 | note | IP
08b644aa-4814-5580-b524-c48746dfef70 | note | RESPONSIBILITY: Fulton Hogan Engineer
8ca5bfef-7a6c-5c91-8717-d601fb76b0f5 | textbox | Date Completed:
48fe7792-688b-4bc1-8524-53d63e701ba3 | checkpoint | 2.2 Construction Methodology
370607b9-9676-51ab-bd84-285dd678675a | note | FREQUENCY: Prior to erection
5296165e-7125-5e19-9d1e-4e6bd4aee4ec | note | ACCEPTANCE CRITERIA: Constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
9b2882cb-c4ea-5af9-b7dd-5f9047a34120 | note | REFERENCE DOCUMENTS: 614.04, 614.06
77073377-0886-5334-b724-2a7204b8bc32 | note | INSPECTION/TEST METHOD: Verify
32f8dc68-a8f2-58bc-bc37-f0822325c6ad | note | RECORD OF CONFORMITY: This ITP signed
af92335c-a21b-5fab-9885-af2c44b967ec | note | IP
28588d49-d447-5715-8137-4630330a71f7 | note | RESPONSIBILITY: Fulton Hogan Engineer
7cd660d8-b1d0-55ea-82f0-af37c380fc25 | textbox | Date Completed:
c6f7b846-8925-4c74-88e1-eb778bd21ecb | section | Pre-Pour Planning and Inspection
1ecccf65-d48e-4174-adbc-f5ba3f24b93d | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
f6eb0f59-4c12-5b55-9815-7d8a5555208c | note | FREQUENCY: Prior to concrete pour
8b6d1822-f05f-5936-ba05-234727675f58 | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent.
bf616724-7ec1-52c9-a4ad-08b089d47d34 | note | ○ Hold Point released by the Superintendent.
1e930b39-affe-554e-a9cc-f0cd3802f405 | note | REFERENCE DOCUMENTS: 602.03
f2c62dc1-e601-5709-b4a7-ab977887c917 | note | INSPECTION/TEST METHOD: Verify
95227461-4ff0-5f72-b1fd-53cab1015d2e | note | RECORD OF CONFORMITY: This ITP signed
cbdedc97-5f70-557b-a3ae-19bbf2563e84 | note | HP
0bc7f7b0-8dbb-5d71-a78a-7d5ec81ae61c | note | RESPONSIBILITY: Fulton Hogan / Superintendent
d358ab96-7bd7-5ce8-945a-73232826b061 | textbox | Date Completed:
ce8532f3-83e9-4c67-8454-bcd72ce516cb | signoff | AUTHORITY HOLDPOINT
12c1d390-7163-4086-bcd3-ad08043f2075 | checkpoint | 3.2 Formwork levels and position
206fbe85-0931-53ae-adda-36c1230027a7 | note | FREQUENCY: Prior to concrete pour
4a70d264-1edc-53ea-b4d7-26ec6b29632c | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
756e4344-7f92-5084-9d91-0735527912a4 | note | REFERENCE DOCUMENTS: 614.06
590c50ae-abb6-5ebc-a267-dd6338c47e3e | note | INSPECTION/TEST METHOD: Verify
f7e52c0f-a18d-544c-a918-4bb99ccda841 | note | RECORD OF CONFORMITY: This ITP signed
b4cef772-f283-5d9d-bc69-4f7a6bb31f09 | note | HP*
5ea0cf9a-b4a6-5339-bd4c-513c0a99ab20 | note | RESPONSIBILITY: Fulton Hogan Engineer
ef948f11-8820-5eda-b1a5-6a62c7a71e42 | textbox | Date Completed:
08606365-57a2-4f76-a0cd-b974bc49c44f | checkpoint | 3.3 Location of splices
67e55951-051a-537f-9801-a69961507ddd | note | FREQUENCY: Schedule Review
23068de3-c50f-56d4-87a9-82a561eda42e | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
543df2d7-4da1-58c0-b9de-af51aaba2fc1 | note | REFERENCE DOCUMENTS: 611.11
57ff4186-6afd-58ec-8a5c-bacfa61f5f70 | note | INSPECTION/TEST METHOD: Inspect
4f2b75eb-7de6-5899-9a11-5d15ed7f7bda | note | RECORD OF CONFORMITY: This ITP signed
bc4d725f-30e4-52f3-b995-1ae71bedb924 | note | IP
a8ebe49e-cd1c-57ba-9c9b-70959d14da64 | note | RESPONSIBILITY: Fulton Hogan
3673c87a-b8fe-5cf7-a3bf-259ea325d569 | textbox | Date Completed:
e71a15be-cff3-4d99-ad91-7f8bf3182a5a | checkpoint | 3.4 Cleaning formwork
b1687b3a-8b4c-57ff-853f-40b39c5ad2ca | note | FREQUENCY: Each concrete pour
19b7ee3f-e589-531d-9db4-eb4ff39fdaff | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
fef81618-7ae2-5efd-9333-f018e4e40ee9 | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
e0804e9e-57f5-5f15-82c4-7402275da419 | note | INSPECTION/TEST METHOD: Verify
ba4afc79-5dcf-5639-a2fe-47389ae44523 | note | RECORD OF CONFORMITY: This ITP signed
44e7230b-7772-5171-9c47-636b7a45627a | note | IP
994ce878-ad61-5d06-a1b1-b8c1cd72d60f | note | RESPONSIBILITY: Fulton Hogan
31ed9e3d-639c-5269-b983-eb1b305f62a6 | textbox | Date Completed:
2e06a8b9-558e-47e8-9d89-638eba071b1b | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
de1ca640-0476-5f8a-a6a9-e6ae0f22bac2 | note | FREQUENCY: Prior to concrete pour
63db0e7e-2331-5240-a0c3-82d4d7382f09 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement and embedments comply with the project drawings and specifications.
d1baa62e-12e2-58a9-8be3-f09437c1b110 | note | ○ Pre-pour checklist completed and signed.
54514918-6436-5352-950e-57e34d543aad | note | REFERENCE DOCUMENTS: 610.18 (a)
d542752e-86b1-5932-acea-990ffe631f2f | note | INSPECTION/TEST METHOD: Verify
933fe430-4b62-5606-923b-7e1baed60372 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
51a68000-f569-5b4a-a357-80bc1a6d2cac | note | HP
71587882-9304-5bfb-a59d-e543b3bb2b8b | note | RESPONSIBILITY: Fulton Hogan / Superintendent
0d7dced2-b83a-5823-aac6-8018e3c80019 | textbox | Date Completed:
81eefaf1-4cf4-4e0f-a627-59191cf8414a | signoff | AUTHORITY HOLDPOINT
36ff5bc9-1edb-4f4e-b6a0-243cde753fe7 | checkpoint | 3.6 Monitoring weather
f282e470-3c54-57a2-aa6d-4cd7b6c0a4ca | note | FREQUENCY: Prior to concrete pour
8ac5350e-6e18-5678-9f78-a4ea67617747 | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
884538b6-ffc1-566e-b858-92626f32f3aa | note | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
6a645a04-b8dd-5561-b668-fe5a9c118850 | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
5d8088ea-cb6b-5801-8fa2-03263cbcc466 | note | INSPECTION/TEST METHOD: Verify
609a4f09-a23f-54ec-8ede-400e0fbb27ca | note | RECORD OF CONFORMITY: This ITP signed
a1975dce-5592-5022-95c9-af4c5d412e8f | note | IP
6433b237-aaff-5022-abe0-8bfb038e8327 | note | RESPONSIBILITY: Fulton Hogan
b9d06a60-bb71-56f9-9964-6e6439a39cef | textbox | Date Completed:
625cc498-f30a-4c02-8f54-9c457c6f5975 | section | Placing and Finishing Concrete
09abd938-c306-498a-a38d-d0518560eb19 | checkpoint | 4.1 Carry out sampling of concrete
0eb4177c-695c-5e86-bd49-64a11d008e6f | note | FREQUENCY: Each concrete pour
027f6c07-72e3-5bed-bfe9-b4fdf5338eda | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
ef6b6742-b5a1-5f6c-b959-14766fa51b66 | note | REFERENCE DOCUMENTS: 610.16
d9ccf6a3-8fac-5cc3-b29e-71ae0385403c | note | INSPECTION/TEST METHOD: Checklist
131e4738-dee4-5de8-ab75-a6e851ecb199 | note | RECORD OF CONFORMITY: This ITP signed
89faa7ab-c8f8-59a6-8272-1bf2f5f39127 | note | IP
fe265446-cdde-56da-b2ba-ede16096ecc5 | note | RESPONSIBILITY: Fulton Hogan
56e0cf5d-4cbb-5332-a348-3c2ca03f8cd4 | textbox | Date Completed:
e64e0766-4759-4fa4-aece-f87eed379686 | checkpoint | 4.2 Discharge time
81d72a8f-6382-5192-a69b-c034b7a64161 | note | FREQUENCY: Each concrete pour
51c2101a-0b29-59f0-bde6-851d025f87ef | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
63d1cab8-d7ba-5a89-80f3-492c68a580fc | note | REFERENCE DOCUMENTS:
eb7bb624-507b-510d-8eb3-5764b6a467b7 | note | INSPECTION/TEST METHOD: Verify
7984fc74-60ff-5d79-93cc-db14ca9665f8 | note | RECORD OF CONFORMITY: This ITP signed
5ec25c0a-7b39-5596-bc6e-974042a8adb5 | note | IP
dbe29789-ae8c-5e3d-a23b-eca713874672 | note | RESPONSIBILITY: Fulton Hogan
58254a9e-3fbe-50a6-8c75-e6b90e4adafc | textbox | Date Completed:
58ab8c13-177c-427b-a78f-6d9c58e38a06 | checkpoint | 4.3 Methodology of placement (structural)
7d9ae6cc-0855-5c3b-abdd-537133d0c6ab | note | FREQUENCY: Each concrete pour
aeeebdd1-c342-5a47-8f1c-28eb183c052a | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
633439c6-56bf-5ccc-8e13-651536fc883d | note | ○ Concrete shall not be moved horizontally by vibrators
f86fa6a2-c3ed-5683-b815-5d4fa2448776 | note | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
12c3a6b9-5324-57d0-b757-e04d6bede237 | note | REFERENCE DOCUMENTS: 610.18
af9d3597-ca99-5213-b00e-d6c547a88d41 | note | INSPECTION/TEST METHOD: Verify
b4323351-b9e7-55f7-91fa-86050ce12a01 | note | RECORD OF CONFORMITY: This ITP signed
81cb35f5-a0ae-56d6-a03f-9223c7b56fc2 | note | IP
6fe41f54-07ff-5b60-a30d-2877c410e796 | note | RESPONSIBILITY: Fulton Hogan
32f23ce3-24c9-5348-8fe6-eb1eb00ebbbb | textbox | Date Completed:
81bf5ae2-1a17-44ac-b5cc-f3ab507bd195 | section | Post-Pour Details and Inspection
0d6ef90b-c613-48e6-acd4-259b549d13c0 | checkpoint | 5.1 Curing
33f06df3-3949-5bfd-8aa3-d298be484a5b | note | FREQUENCY: Each concrete pour
bc41e6d6-9110-58a5-a363-50653ef5e438 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
bfae94dd-287d-535d-bd42-b494ebe44a65 | note | REFERENCE DOCUMENTS: 610.23
81e2c52c-5db0-5452-8fc6-8ba2a55c7c04 | note | INSPECTION/TEST METHOD: Verify
2f82a035-9aca-569b-a508-ff128243d8d2 | note | RECORD OF CONFORMITY: This ITP signed
8e602d16-8c88-5c2a-802e-5f2f82d4e25a | note | IP
6fe7fe33-9b10-5747-9512-ed1eff79a335 | note | RESPONSIBILITY: Fulton Hogan
c39cfb7f-1d1b-59b9-ab19-a6b02df76fdb | textbox | Date Completed:
2039f394-d0e4-49c2-afc0-eaabb968824e | checkpoint | 5.2 Formwork removal
a5f884ea-2d3c-5a25-a64e-f2f4c96463e5 | note | FREQUENCY: Each concrete pour
848664c0-0911-5ed4-95cf-927ce9b51235 | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
2b2bf978-d654-5b95-9212-fb2a757769ec | note | REFERENCE DOCUMENTS: 610.25
10302149-adb1-5f12-b102-6e585819d0f6 | note | INSPECTION/TEST METHOD: Verify
7ca9fc0f-994c-5c05-82d5-f04def596478 | note | RECORD OF CONFORMITY: This ITP signed
83802599-fe02-56ed-930a-792264b53d46 | note | IP
a92c3902-fc4d-5d71-ae77-a4237e76dbfe | note | RESPONSIBILITY: Fulton Hogan
1c839de2-eee1-53f3-a81a-0d1e506ab572 | textbox | Date Completed:
a654bca6-b4c0-4b27-a0b3-6238d5a9636b | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
6a5f5a1a-0450-5185-8caa-89ec3ec5e901 | note | FREQUENCY: Each concrete pour
1411f134-29fe-53f3-a997-7b675c2f004c | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
90b02894-8cd0-5f07-95db-66a07d21de57 | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5, 607.06
c3ae653f-5f14-57ca-b47f-7514e4a0ec80 | note | INSPECTION/TEST METHOD: Verify
0152fe38-fba7-5301-9047-5173e14ca3de | note | RECORD OF CONFORMITY: This ITP signed
757b2162-0268-50e1-911b-1dad0cb0caa1 | note | IP
b32a4fa6-a591-5437-b726-9dc1fb141920 | note | RESPONSIBILITY: Fulton Hogan
3c68a3e6-5496-5a7d-83a4-9a8f0932b1c1 | textbox | Date Completed:
a8f1eb8c-597b-4eaa-b9d0-1144bfcdd5f6 | checkpoint | 5.4 Concrete Sampling and Testing
ec97131d-1781-5662-a5d4-c17e98093fd9 | note | FREQUENCY: Prior to lot closure
5e9832d6-938c-504b-ac9e-ccc8a6879e65 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
19634078-a624-5451-b485-59a8c1413332 | note | REFERENCE DOCUMENTS: 610.16
4cbbe119-d45d-5cd1-9dce-6624c55af6c9 | note | INSPECTION/TEST METHOD: Verify
22f35d91-b939-5981-b961-1fff5c637c1e | note | RECORD OF CONFORMITY: Test Reports
0f1a0598-c9c9-5978-9a7f-851e6ef86b5d | note | TP
9b2c6a5f-5110-5dd1-bd7d-280afd00307f | note | RESPONSIBILITY: Fulton Hogan
9718f8cc-40f1-5ed2-83f2-aa948a0aeca4 | textbox | Date Completed:
870c983d-a0d7-496b-a7ff-f0efdb103208 | checkpoint | 5.5 As Built Drawings
675c5a41-abe3-565c-aa6a-1b9481a35f64 | note | FREQUENCY: Prior to lot closure
a48bf5f1-cd01-5163-9c12-ba4d4b11c81b | note | ACCEPTANCE CRITERIA: Recorded on red line mark-up drawings
257fa0ef-dc1e-57e6-ab21-ed98b3f557f2 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
3a4b80f1-6e76-5a3f-ac12-2a4003329459 | note | INSPECTION/TEST METHOD: Verify
d5c32c9d-6b69-5e56-86dd-275a047d4496 | note | RECORD OF CONFORMITY: This ITP signed
661c2338-8344-537b-a5e6-a6da313ad2ca | note | IP
603e2c3d-1e01-5eda-bf50-5829fbca0c3a | note | RESPONSIBILITY: Fulton Hogan
cc86290c-2e25-5ab8-abb3-09881bd24124 | textbox | Date Completed:
3e7f2c10-9077-4e35-827b-e912fbc22ad1 | checkpoint | Final Inspection
6ce0b11d-0642-5a7b-816b-8b9ef2f80de6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
31c39d75-9511-5649-aec8-a3ce8c7a5bbf | textbox | Print Name:
c29b3ae0-10b7-5543-9879-07fd9b02d692 | textbox | Position:
385a3357-6ac8-5817-844b-71d912ca720a | textbox | Date: