## Master List Templates
Id | Type | Name | Values | Prompting Name
f2fde9e7-9c31-4b6a-b1b5-5c987f27409a | checklist | Contract HoldPoint Checklist |  | Contract HoldPoint Checklist
96a78813-95b0-48fa-9a93-357ec9a1b8cb | checkpoint | Holdpoint Release
e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 | textbox | Enter Name
1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b | textbox | Enter Description
60a1eb35-e850-40c9-a4b9-af7b0196da59 | signoff | Contract Holdpoint Release
b314e121-8c94-48c9-bbe8-c6f019a8f561 | checklist | ITP-001 - Subgrade Preparation Rev2 |  | ITP-001 - Subgrade Preparation Rev2
92735ee7-00d4-4047-b531-1157dd1ffab2 | section | Preliminary Works
8aa120f7-5d64-41d8-a81c-d1dee6f35f05 | checkpoint | 1.1 - Check for correct documentation
45188c88-c52b-57af-b3b7-03ffb2fa8f30 | note | FREQUENCY: Prior to commencing any activity
55e0b00f-b175-5332-9d35-8d2ea8fd0fda | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
43ba18bb-5e67-5b1d-a0d6-f4dfd23fa27d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
cae04579-468a-5bb0-bcbb-188f602e5329 | note | INSPECTION/TEST METHOD: Visual inspection
15d4dbc5-9fd7-5653-89ab-df14a395fcae | note | RECORD OF CONFORMITY: This ITP signed off
44705a3e-a804-5ef6-bd00-c3a1b5801b76 | note | WP
77cc26f7-3555-5973-83aa-3e09b928ae51 | note | RESPONSIBILITY: Fulton Hogan
b0ce8c95-decf-5071-bb9c-7112e16c0c02 | textbox | Date Completed:
c1deca52-bf51-465b-a0ca-c6f0eaa74d09 | checkpoint | 1.2 - Implementation of all measures and controls
bba017b4-8f81-5c61-8c44-f5d8cb094182 | note | FREQUENCY: Prior to commencing any activity
9120371d-d575-5d35-babf-69ea8bded992 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
aa908750-6bad-52a7-b547-cbbaf48c1487 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
b5e9cb4f-3b12-5054-a26b-6a13f91dfa58 | note | INSPECTION/TEST METHOD: Visual Inspection
874839a3-bf07-5f70-aee1-bd340fd598a7 | note | RECORD OF CONFORMITY: This ITP signed off
88e4c18a-b299-5358-b7b1-f0d3ddf5adc1 | note | WP
87f0a977-25a9-5acb-b28a-466cc1433823 | note | RESPONSIBILITY: Fulton Hogan
751321f2-27c7-51ae-9c8f-a44d48accc4c | textbox | Date Completed:
7e640079-d376-4885-9402-3fa9ad0544c7 | checkpoint | 1.3 - Selection and approval of Disposal Site
9cb26a5b-8903-5b22-9685-09c730343609 | note | FREQUENCY: Prior to commencing any activity
67c61ce2-8eac-5a1a-9265-4122e349bae2 | note | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accordance with Yarra Trams site classification report. It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
5ed4e0c4-0358-592c-ab96-6b7db0e4f962 | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019- ST-0033 CL. 4.2.1.5.
a91157d9-da51-5096-b8d9-f25d2a95b07d | note | INSPECTION/TEST METHOD: Verify
840d1327-464c-5e0f-bf9c-0b174666cae7 | note | RECORD OF CONFORMITY: This ITP signed off
b1d0dc7a-d5d3-58a7-bcb8-10f370d9d38b | note | WP
53c3aeff-b9eb-552f-9fa7-fa7614d171b2 | note | RESPONSIBILITY: Fulton Hogan
416f0ccd-cc2e-5d38-b3bc-6ec260c9f0b7 | textbox | Date Completed:
4dd63ab3-dd6b-4529-9b9b-dd6f5f3c7794 | section | Construction Works
a0b41a9b-f81b-4ed8-b6cd-3dbd76ae77bd | checkpoint | 2.1 - Excavation
5dafd1cc-eb05-5463-a582-b13de1af5907 | note | FREQUENCY: Each lot
a338bb55-9b70-51b0-ad00-da39de2e595f | note | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of works
bf0d3fa9-f92b-5dd5-8c6e-ff8e54386b6f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4. Subgrade Preparation Work Procedure
bc767fb1-3969-50a2-b592-64172ca170ea | note | INSPECTION/TEST METHOD: Verify
77f22b39-80c6-532b-8add-3c3a0073877d | note | RECORD OF CONFORMITY: This ITP Signed Off
3240cc15-9d09-54aa-86f3-87a34ff7ba81 | note | IP
2bf90b48-ba07-57d7-9dfb-23536a96f782 | note | RESPONSIBILITY: Fulton Hogan
6da904e9-ee0a-5b76-ac22-f75341946855 | textbox | Date Completed:
0207bb47-3385-4a28-a899-6f3a63f201ee | checkpoint | 2.2 - Reinstatement of bonds
96e709ff-698e-5f3e-8024-5af4d199a873 | note | FREQUENCY:
d84ba202-6a80-507e-ac30-7e6e715dda43 | note | ACCEPTANCE CRITERIA: Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables. All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
eb176fda-5b9a-522e-9824-b0cb052f5bf5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
212381da-8a54-561b-8012-27623ff5f5c4 | note | INSPECTION/TEST METHOD: Verify
3d6cd25a-a502-53c7-acbd-84fb464c4175 | note | RECORD OF CONFORMITY: This ITP Signed Off
9fe48eaf-dfd2-53d4-a56c-5787003855b0 | note | IP
6e521760-12a5-566c-a298-7e6113cd9f22 | note | RESPONSIBILITY: Fulton Hogan
a4d2f4b7-c5d2-53f8-a65e-e823ddfab736 | textbox | Date Completed:
616761f3-455c-4949-85c9-645e8d1dfd16 | checkpoint | 2.3 - Inspection of Subgrade Material
576eb2d8-a672-5a4f-9081-312eb8e5fc3e | note | FREQUENCY: Each lot
2d2796c2-c1ed-5a62-aa52-9ce2626eda06 | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
047d2ad4-f790-5158-a697-a0cb0123e5f7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
35a3a40a-bd2d-5df2-bd64-6fe6802f96d8 | note | INSPECTION/TEST METHOD: Verify
3a007820-922f-57b9-9070-a9892866b1a2 | note | RECORD OF CONFORMITY: This ITP Signed Off
8e7fff5c-a388-5e73-af58-37279c679e42 | note | HP
c2abe582-1979-5c5d-984d-f454996ca911 | note | RESPONSIBILITY: Fulton Hogan Engineer & Yarra Trams Superintendent
b56f1584-fd36-5878-940d-7f33e1d23eaa | textbox | Date Completed:
67fb1652-94c5-4358-922a-2618c31553a4 | signoff | Authority holdpoint
bcd29c89-3f91-4435-87a7-bc7878d471e7 | checkpoint | 2.4 - Width and Level conformity
4e71c4f6-a39e-5344-945d-99f2452efa35 | note | FREQUENCY: Each Lot
752dc8fe-1994-5dc5-9516-3f518929d091 | note | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings. No point in the general surface shall vary more than 12mm from a 3m straight edge. Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
659f292c-4e11-58f6-87c5-625d56098bea | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
d306a058-1fa8-5b7d-aa90-2f7a27fc7a14 | note | INSPECTION/TEST METHOD: Survey Report
2552991b-495c-57e1-a371-4ca5a52bd262 | note | RECORD OF CONFORMITY: Survey Record
54cc9d94-6e86-534f-89ee-f5d16efaacba | note | IP
fccf15a3-d2b7-5ff9-972c-d9dda69557f8 | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
442e49be-7cbb-532c-b42d-621f0ccc41c3 | textbox | Date Completed:
50d8f268-73e5-4b7f-ac48-71a44a9a7497 | checkpoint | Final Inspection
75654e3b-f502-5dbd-af74-d2dc98ede34a | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a69e878b-32cf-5909-b04e-d062802050ec | textbox | Print Name:
36759aa4-7b2a-5d81-8b7c-d0fcc420108b | textbox | Position:
a1625a23-a2b3-58ac-a423-4d707d7d2454 | textbox | Date:
5dad7ec0-5a2a-44e1-8e93-4b0f83edd146 | checklist | ITP-002 - Feeder conduits and pits Rev2 |  | ITP-002 - Feeder conduits and pits Rev2
8aef01c2-8302-4b66-aaa0-7cfc9e3ea3f3 | section | Preliminary Works
078b9a38-5f90-4077-8609-dfd03d43bf0b | checkpoint | 1.1 - Check for correct documentation
d51dd484-9c6d-5853-b8aa-b9db28924a95 | note | FREQUENCY: Prior to commencing any activity
d9a1b59a-b349-594e-84d5-f8d76dafd64f | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
bd529b6a-8653-58b5-9f43-5b588c99c963 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6dfac36e-0b0a-5f25-9daf-d74ce2720bb5 | note | INSPECTION/TEST METHOD: Visual inspection
43c464c7-ca22-5ee3-8d5a-e8eccaf7aa1f | note | RECORD OF CONFORMITY: This ITP signed off
85ebb617-aae5-5c30-9e46-1fa332216229 | note | HP*
c920840b-32a8-58c2-94e3-b2da315adcfe | note | RESPONSIBILITY: Fulton Hogan Engineer
25cc67f6-8fa8-543b-ab4f-28a618b7ff52 | textbox | Date Completed:
905f422e-df0e-477a-a591-6cd067bb2239 | checkpoint | 1.2 - Implementation of all measures and controls
27e5a31c-f489-5daa-afda-a574f4f0fc05 | note | FREQUENCY: Prior to commencing any activity
3a037c4e-663e-5ab4-a5f0-2b809d2383b0 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
75c43fb9-f7c8-55c6-8a40-a869e21e7cce | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
03c168b1-b530-5624-b639-2ee34ec329b0 | note | INSPECTION/TEST METHOD: Visual Inspection
1178321b-b6b1-5494-a825-d516a2740650 | note | RECORD OF CONFORMITY: This ITP signed off
d86abb2f-af58-5e6b-9b24-9dde622bdd27 | note | HP*
9fdf781a-7964-56b1-9b78-d02d90c81bf9 | note | RESPONSIBILITY: Fulton Hogan Engineer
fb4bd187-bf60-5262-aa0b-3992c55f2233 | textbox | Date Completed:
0f9645e0-e9ad-40ac-87ad-b552f95a4dbd | checkpoint | 1.3 - Materials
f3233e4b-fed9-5267-b276-e798ead44f25 | note | FREQUENCY: Per Batch
80f2cc42-40a0-5877-a6dd-f2c93f08f382 | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be Orange • Heavy Duty 100mm diameter UPVC •Modula Stakka pits to be used for feeder pit, entry for conduits to be cut with hole saw •All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
57429af1-2504-55d4-bac6-79e8c8376bf0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4 AS 2053
97ece864-7cdc-5590-972e-9fbf88d4159d | note | INSPECTION/TEST METHOD: Verify
3aeebf58-74e5-521d-b3ed-5e5800b830a3 | note | RECORD OF CONFORMITY: This ITP signed
5e399b9b-85d8-52cc-8162-89589d9a1853 | note | HP*
c886d838-6476-5d54-af10-1dfb8f175886 | note | RESPONSIBILITY: Fulton Hogan Engineer
23606c3b-7e04-5583-b276-e7abd00b490e | textbox | Date Completed:
e1b57d4d-6752-4528-9434-ff0322f14be6 | section | Construction Works
f26712d4-8a67-488a-bc16-4a4fb2783da5 | checkpoint | 2.1 - Survey set-out
d4621f17-83dc-5ec3-8be0-d5c5bff87a0a | note | FREQUENCY: As required
b40990ca-90d0-58aa-a302-ec08ea1b45d2 | note | ACCEPTANCE CRITERIA: • Work is set out in accordance with drawings. • Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
acc81278-9c82-5777-8604-6356d9730b40 | note | REFERENCE DOCUMENTS: Work procedure
6fb1735a-c1a5-5ff6-8a23-0174678b6489 | note | INSPECTION/TEST METHOD: Verify
47ffc079-c89c-56fc-b657-8f0446d83d78 | note | RECORD OF CONFORMITY: This ITP signed
51c8e4df-01c7-50a3-8b7a-1692369bd1e1 | note | HP*
aa92b1c7-6f58-5f34-b2f9-863393a3b7fd | note | RESPONSIBILITY: Fulton Hogan Engineer
3617d15f-48c3-5141-8207-8ea4ad584e80 | textbox | Date Completed:
5c3b09f9-5694-4f4d-a5d8-b9d0250297f0 | checkpoint | 2.2 - Excavation and Trenching
5195388b-b415-583d-9f8a-1075787dab9c | note | FREQUENCY: Prior to Installation
5a3b164e-f14f-5cbd-beea-53935f060e54 | note | ACCEPTANCE CRITERIA: • Minimum cover for underground conduits shall be 600mm • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
9bfae568-b3b6-5ede-ac29-ae153a04cdce | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
1381b0c0-64c8-5f2e-a2f2-89363b1de9b1 | note | INSPECTION/TEST METHOD: Verify
da1bedd7-9329-56a6-b52b-f231955e9274 | note | RECORD OF CONFORMITY: This ITP signed
714b1fa0-5d96-5b53-a09e-0a83e8ac4067 | note | WP
e43c850e-a56d-5c21-9858-cf22d41c80cd | note | RESPONSIBILITY: Fulton Hogan Engineer
80a407f1-269a-523f-a35e-9819efd7ac47 | textbox | Date Completed:
c18b7741-da4c-486f-86f1-8c9a5dbdba56 | checkpoint | 2.3 - Installation of Conduits and pits
59f317ee-f69b-5cfb-bc33-c4ffef6a2cfb | note | FREQUENCY: Each Lot
705c6f9c-f73f-50a5-ac7d-34f7bd058c06 | note | ACCEPTANCE CRITERIA: • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
7864db51-ed20-5439-9338-91188ee2452a | note | Conduit shall be embedded in not less than 50mm sand and covered by
4644165f-7ef7-5db6-9d8e-9a53adf7c186 | note | >50mm - 75mm< sand
a5576bc8-a83d-505b-8414-82ef7b0572c1 | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
6e519764-3a05-5565-a93a-9dd19fb666a0 | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
f5b40ae3-3e12-5116-b6c6-a18a868bc205 | note | • Conduits shall not be subject to construction loadings
f2865fcf-3759-599b-9659-fe56c93ac02b | note | • Pits shall be constructed as to allow for class D rated covers
bd1ae1a6-99fa-5aca-90b4-d6b1e3a1a053 | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor, a 50mm gap between conduits shall be maintained as they enter pit face.
b6079c11-5857-5d94-9a64-418cd2d23f2c | note | • Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mm beyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
79ad57fe-6052-5d9a-9d54-404aea514051 | note | • Conduits shall be placed a minimum of 100mm above pit floor
b40bd866-6d16-55b4-b9a2-2cdc30d2a02e | note | • Conduits installed for future connections shall be installed to the track Margin
a25b6ab1-4553-5bf2-bc83-c1d11185d972 | note | • 100mm of concrete around and under pit lid
5a7e9c26-2e6f-5fb1-a867-9fc91beb85da | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
bdb991ef-92df-5cb4-9ce1-dbefe7bf031e | note | INSPECTION/TEST METHOD: Visual inspection
96907488-a721-5a3a-895f-997e61564d9e | note | RECORD OF CONFORMITY: This ITP signed
367ef7dc-f8b3-5821-ba9c-fbb3220785b9 | note | WP
37a4b8a1-58f1-5d4a-a021-f7f441232491 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
fb223460-d9b5-5582-8acb-d579847aed2f | textbox | Date Completed:
b3f383df-aa05-4b2b-bdf2-c9e47e93b19b | checkpoint | 2.4 - Inspection of conduit installation
7eeea24d-5f10-5a2f-88e0-e4243a7d1a4e | note | FREQUENCY: Each Lot
5ce68162-4e36-5a8a-9d69-580608fcd6b7 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
a2976cf9-6bda-5f2e-a37a-15104961d302 | note | REFERENCE DOCUMENTS: Work procedure
32abdd24-8ce1-5851-b2eb-3856299d993f | note | INSPECTION/TEST METHOD: Visual Inspection
44823288-e7af-5497-9420-7619cf4a1a62 | note | RECORD OF CONFORMITY: This ITP Signed
fdef59a4-c710-593d-999b-fe39b7f05707 | note | *HP
2c5acbe8-ace8-571b-875a-9289025cc9ea | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
5d3d0e3c-6c18-52c5-9471-3ea1a2cfe6ef | textbox | Date Completed:
56aa524c-0e02-4ee9-83ee-20cac1859af8 | checkpoint | 2.5 - Backfill of Trenches
ec1541c4-c2a8-5294-950d-ca3d8a447c7b | note | FREQUENCY: Each Lot
d386fbc1-cc06-5bff-bac5-f52649917a27 | note | ACCEPTANCE CRITERIA: • Backfilling (Only to be used for road crossing trenches) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
734bf98c-f71d-5686-8029-66df36e4e2ed | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
21afa69d-217f-5a08-89d4-53415482fdc2 | note | INSPECTION/TEST METHOD: Verify
d7d35586-77a0-5504-bc20-b4e3132a5367 | note | RECORD OF CONFORMITY: This ITP signed
4256365c-84e6-5a58-99cc-e94700b7972e | note | WP
fa636460-20bf-5746-8f95-25840d46ba5b | note | RESPONSIBILITY: Fulton Hogan Engineer
59b9d26d-1034-50e0-a21f-399cc1d329be | textbox | Date Completed:
1350a87e-99e1-4b8e-99f2-a961540213d4 | checkpoint | 2.6 - Installation of Draw Cords
e4264c8c-2c06-5553-b9f0-4e0deb2ed7ec | note | FREQUENCY: Each Lot
92764ba0-38df-5353-9b65-62d03a243064 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'
39d907d1-de65-5bca-80f4-4e37faff9aa1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
6d7a2af3-0330-5af2-86de-98656a29f440 | note | INSPECTION/TEST METHOD: Verify
71fdc941-35c3-585c-9ea8-68253dd4656f | note | RECORD OF CONFORMITY: This ITP signed
cd070514-a63e-5273-8452-f565b2eec374 | note | WP
8d3e36bb-f303-5fa3-ba8b-90b24c065af5 | note | RESPONSIBILITY: Fulton Hogan Engineer
c35af4aa-28b5-52da-92aa-2870d0b3f634 | textbox | Date Completed:
c97c5d79-e370-46bb-9b2f-1f2df001dcc0 | checkpoint | 2.7 - Compaction
79ec26a0-8d61-5b17-bce7-5f0b49dd4e88 | note | FREQUENCY: Each Lot
4cbb1931-060b-5e0d-8153-28848408f7e4 | note | ACCEPTANCE CRITERIA: • Bedding and backfill material to be compacted using mechanical plant During compaction optimum moisture content of bedding and select fill is within 85% to 115%
8ccd19af-2f12-56fc-bd46-34f0b00bc6c7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
bebcea1d-c15a-524d-93c3-1dc3e4068bff | note | INSPECTION/TEST METHOD: Verify
7b629d97-6a0e-5eeb-aac0-064529a370c4 | note | RECORD OF CONFORMITY: This ITP signed
f643d678-fd04-581a-ad48-f84f8486438e | note | IP
3f92c428-d6c8-58db-9470-dfbc2e44184c | note | RESPONSIBILITY: Fulton Hogan Engineer
e83d6940-d37c-5b8c-883f-27df6430c8bf | textbox | Date Completed:
c4f33e45-de55-44a6-8c32-6d0b8e912850 | checkpoint | 2.8 - Feeder Pits & Pit Lids
2eff92ae-1e2c-532b-9a12-f14a64a3a23e | note | FREQUENCY: Each Lot
3b4a4b01-a703-578f-8e3e-70e839873e57 | note | ACCEPTANCE CRITERIA: • Feeder Pits constructed and installed as per drawings
0943805a-59b5-52e5-b08d-4e0fa3be7a95 | note | • All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar
9378cceb-3f25-5740-92e6-db4e73c9a47f | note | • Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
420676b4-90f8-5ecf-a24f-5ad57d6714ef | note | • Gatic pit lids shall be filled with structural grade concrete.
e8b57501-98d0-58be-9f08-13586c50f3d4 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
38888b6f-ed35-5855-af46-c722d56f4597 | note | INSPECTION/TEST METHOD: Verify
bb5f0b9a-82f9-5207-8af1-c60b85e7e64c | note | RECORD OF CONFORMITY: This ITP signed
7e6e3025-7f8d-58fc-b14a-e6b911d3b4f0 | note | WP
448a0cdd-d744-5cd2-bd05-b5e342ac6fb9 | note | RESPONSIBILITY: Fulton Hogan Engineer
8f616542-944d-57fd-88a8-6e5f13899074 | textbox | Date Completed:
b5b069e0-627c-4ece-bb90-ffd38e39ca68 | checkpoint | Final Inspection
c830c928-6a42-50e5-bf4f-a3ad780a3359 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
3d46f1f4-facf-568e-8c10-8ac93b238201 | textbox | Print Name:
705c52d1-f37a-5f5d-8226-cc38137ef254 | textbox | Position:
92527a12-74dd-58d9-bad4-efeb991d8dd5 | textbox | Date:
47906b50-33c5-4d76-a8c1-d5539885dce7 | checklist | ITP-003 - Electrical and Communication Conduit Rev2 |  | ITP-003 - Electrical and Communication Conduit Rev2
31176222-5868-42a6-bb6f-70b3fa7bc207 | section | Preliminary Works
c4076e9f-5b28-437a-aa27-ae85b621c52f | checkpoint | 1.1 - Check for correct documentation
f37cf723-2f76-53d9-94e9-2e96fff13d88 | note | FREQUENCY: Prior to commencing any activity
ae645317-a5ad-589f-905a-71c064836b2a | note | ACCEPTANCE CRITERIA: Employees and subcontractors shall be issued with the most current and complete construction drawings
a50bafcc-8b88-5fe0-afe0-a620d24bb08a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
74d178c9-73e1-5003-8b2b-93943c629d79 | note | INSPECTION/TEST METHOD: Visual inspection
a068f500-591b-5867-853b-ad3090b869f6 | note | RECORD OF CONFORMITY: This ITP signed off
b37978f2-6fa2-53cb-abd9-d5776574be22 | note | HP*
82064103-dee7-567e-85ea-c82a8b233bff | note | RESPONSIBILITY: Fulton Hogan Engineer
da404d0c-65f9-5333-ba6a-b33234c60693 | textbox | Date Completed:
69c305eb-d475-4543-9b12-45328c843a66 | checkpoint | 1.2 - Implementation of all measures and controls
ae913ecc-9439-5ad4-9a0a-027f004c3416 | note | FREQUENCY: Prior to commencing any activity
8574ffb5-8b67-5cf0-8efb-268d21f481ad | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
aa8c78e1-e348-5e3a-a8fd-6db13c054eb1 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
bd534ec6-fa6c-5d01-8507-9a37bba98e63 | note | INSPECTION/TEST METHOD: Visual Inspection
c39abd1a-9de1-5533-84ff-a29f3e6277c4 | note | RECORD OF CONFORMITY: This ITP signed off
937796af-5546-5fbe-92ed-09ffc2513c2d | note | HP*
b22b05e2-8a17-5fcf-90b3-99535c764dd8 | note | RESPONSIBILITY: Fulton Hogan Engineer
a0cb0867-664b-5a56-8dcb-926d53c9c6d8 | textbox | Date Completed:
9eb92c43-4630-4ea5-ae2b-f7e214a055db | checkpoint | 1.3 - Materials
dc176250-0282-5527-af6b-0055d60ed351 | note | FREQUENCY: Per Batch
b1913a11-7022-5da0-a291-1f77b0f15742 | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be Orange and rigid HD UPVC of sizes as required. • Communications conduit to be White and rigid UPVC of either 32 or 50mm size or larger as required.
5928abd0-863d-583e-bc69-3ca4dd91da16 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.1 AS 2053
6e77ad37-ef14-5bac-9031-5e1f7dfd7b6f | note | INSPECTION/TEST METHOD: Verify
911b61fd-3340-58ac-8390-b7b975cab988 | note | RECORD OF CONFORMITY: This ITP signed
e12ca152-124e-5c61-883f-228b0edfbaab | note | HP*
080f4a39-e2ab-517e-9775-b1bc89c2285d | note | RESPONSIBILITY: Fulton Hogan Engineer
013729c2-7255-56a0-a988-f7273795f1fb | textbox | Date Completed:
8f8dad74-0b7f-4230-92a1-d59f9f1bc4d2 | section | Construction Works
159bdd7b-b662-4a7a-a299-3a4c728efc71 | checkpoint | 2.1 - Survey set-out
60d591cb-05a7-5cf2-9f0d-64252dccf918 | note | FREQUENCY: As required
b2c92a45-2d8a-507a-83dc-4a62bbe33d6b | note | ACCEPTANCE CRITERIA: • Work is set out in accordance with drawings.
b80e7a36-72f3-5606-9cb0-99534f07df78 | note | REFERENCE DOCUMENTS: Work procedure
dae80f44-de96-5808-b6bc-3caa90fb1eb2 | note | INSPECTION/TEST METHOD: Verify
799ab4c8-6484-51b5-aed3-dc59e36e9198 | note | RECORD OF CONFORMITY: This ITP signed
6adaf214-c4a7-5836-9915-aa873f33cb9b | note | HP*
cbf7c7fe-53a3-53e7-b632-1f3e4c968129 | note | RESPONSIBILITY: Fulton Hogan Engineer
c00cf6e3-28c4-51b9-bcf4-5653a40fe34b | textbox | Date Completed:
507a3076-d057-42e7-b6a2-f1193eaf3dd5 | checkpoint | 2.2 - Excavation and Trenching
35447bc8-77dc-5774-8394-590bc5ad78f6 | note | FREQUENCY: Prior to Installation
b56623b1-ce6f-5d67-bf05-87746c51be9e | note | ACCEPTANCE CRITERIA: • Minimum cover for underground conduits shall be 600mm • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
84d38c2b-edeb-5fb7-8ee2-b6adf38a1050 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
ee7ce9e2-79e2-58f3-9dad-5135a2b0f85f | note | INSPECTION/TEST METHOD: Verify
23afe5bd-1722-533a-84f4-4beeb3fe80e4 | note | RECORD OF CONFORMITY: This ITP signed
ae99b891-6b48-5254-afda-942081f0bf53 | note | WP
e76fe0b8-541f-5d1a-8f0a-8ec87117c0fd | note | RESPONSIBILITY: Fulton Hogan Engineer
7f3920c8-7c54-5e4a-b6d9-1a21c5ea977e | textbox | Date Completed:
a2e74203-22e8-4fad-a248-ebbefc8fce75 | checkpoint | 2.3 - Installation of Conduits and pits
b40e944e-dfc4-530e-8b33-02f0e89515d4 | note | FREQUENCY: Each Lot
d9043b88-a333-5e2f-b1d9-b7774872441e | note | ACCEPTANCE CRITERIA: • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
a7d158d7-6b4d-585d-9ea6-cd77a1c454f2 | note | Conduit shall be embedded in not less than 50mm sand and covered by
cd52ca9e-13ac-507b-8ea9-1bf86352807c | note | >50mm - 75mm< sand
023cd43d-5c8e-51fc-b26e-36c8f6cb33d2 | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
6d837a21-8ea3-5e12-be7e-c63b46deed3b | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
ab1979e5-c80c-5c01-bd97-4ae0e9ba776c | note | • Conduits shall not be subject to construction loadings
f5afc207-2756-5e47-bf7f-08f577e10c7e | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor
dcf0571d-1608-5677-8491-bb35d544fd70 | note | • Conduits shall be capped with UPVC electrical caps
81847ff6-2342-5bbb-ab13-7b7ba57d21a2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
0b03f992-28dc-508b-b642-98740e54a9e5 | note | INSPECTION/TEST METHOD: Visual inspection
4972551c-b706-512a-a01e-f5d680e7d8cf | note | RECORD OF CONFORMITY: This ITP signed
ce55d0e6-3eda-5d45-a9b9-8d1583abf411 | note | WP
8c4e53d4-4f65-5b9d-b012-356dc59f8e7c | note | RESPONSIBILITY: Fulton Hogan Engineer/ YT
385fa5e9-e597-5960-bc0c-8b25cceb837d | textbox | Date Completed:
1ac0b196-096a-4e8f-99cb-89e32ff4e5ff | checkpoint | 2.4 - Inspection of conduit installation
bdaa746e-a432-51ab-a931-840fc43f6791 | note | FREQUENCY: Each Lot
69d453be-573c-598d-845e-95b7efaad486 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
3edd8ea6-d590-5bfc-952d-242663fb550c | note | REFERENCE DOCUMENTS: Work procedure
f8f08e89-f712-56da-849e-28563f6fb8e8 | note | INSPECTION/TEST METHOD: Visual Inspection
9c654764-ecca-5323-8240-2b169b3ab393 | note | RECORD OF CONFORMITY: This ITP Signed
66a072a3-6977-5c71-9e5e-ad9624d525ff | note | *HP
abfd7e95-0bf6-5027-a6f4-c83f14e18476 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
35494e49-1d21-5a9a-9a17-37272c298f28 | textbox | Date Completed:
fb1d7401-50d1-414a-b0f7-3ee86dd4e8ec | checkpoint | 2.5 - Backfill of Trenches
db9899f3-a206-55d3-9e9b-071958316181 | note | FREQUENCY: Each Lot
eca85508-0a4a-5cce-983d-729edd60ad9b | note | ACCEPTANCE CRITERIA: • Backfilling (for trenching or road crossings) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction using handheld mechanical plant
64016342-46c1-5f7d-a686-34e7563db3a8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
66ab2d74-64e6-5164-9ee1-9f4973ea3b47 | note | INSPECTION/TEST METHOD: Verify
0d91d238-b4ce-5903-bce2-c7c44f2f19de | note | RECORD OF CONFORMITY: This ITP signed
eee7953d-a751-5398-80bd-c400383657fd | note | IP
d243be8e-4e36-5cc7-848b-e056fdfcaefe | note | RESPONSIBILITY: Fulton Hogan Engineer
cb574033-cbc4-5a9c-ad03-71a398cf2618 | textbox | Date Completed:
dadde7ac-36de-4ff7-8e37-74bf8d880fd4 | checkpoint | 2.6 - Installation of Draw Cords
3656be04-ed75-5de1-91b1-a734d9bdde60 | note | FREQUENCY: Each Lot
5b6e178a-9419-56f6-a88c-6d3e3d309614 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit, material to be used shall be 6mm 'telstra rope'
97ef5f82-d9b8-582c-9600-70b4f8fd90fd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
93007efc-86a5-5a3e-9d28-c7e23bc4cae1 | note | INSPECTION/TEST METHOD: Verify
cd8e3906-b84c-565b-b574-0a0d761e2f8e | note | RECORD OF CONFORMITY: This ITP signed
8452fc5c-cd0c-5ec9-bee0-22ad94954821 | note | IP
777b7c52-4da8-56ff-908c-79a98ff1d2e4 | note | RESPONSIBILITY: Fulton Hogan Engineer
ffe26cc6-1bd4-542e-b7fe-6c8d804154b6 | textbox | Date Completed:
38a5c65a-99d4-4a15-b1ba-20091fa98c60 | checkpoint | 2.7 - Compaction
d26efa9a-710c-580a-a6e0-1381a2b1ed36 | note | FREQUENCY: Each Lot
f199c0c6-7ddd-5f98-84ff-3acc41d92a08 | note | ACCEPTANCE CRITERIA: During compaction optimum moisture content of bedding and select fill is within 85% to 115% as provided by suppliers
0e7898a2-ba62-5def-b2c7-0b567f51f71d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
241c05f9-45af-5382-9ac5-552c469484b3 | note | INSPECTION/TEST METHOD: Verify
7f6171fa-4efd-5595-9f2d-82095df6d6f2 | note | RECORD OF CONFORMITY: This ITP signed
43a0280e-d7bf-57c3-b278-537d3bdfe116 | note | HP*
bb277407-16c6-578f-96d2-607e81a90df8 | note | RESPONSIBILITY: Fulton Hogan Engineer
0c9d4779-cf39-5a1e-a6ba-f2a69a952eba | textbox | Date Completed:
71feae13-4c38-4bef-ba49-95dfcf092fba | checkpoint | Final Inspection
4f331889-36c4-5a9e-bc2f-7a66ecd1d5af | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
18d00a23-909a-5255-846d-69678ec738a3 | textbox | Print Name:
f726574b-0634-56b8-b804-75d6385ae977 | textbox | Position:
4bfa6c5e-99c8-5d4c-8cd3-dacd49324069 | textbox | Date:
61b0af87-1424-4859-b3d0-cf322d0d5c7a | checklist | ITP-004a - Class 2 Base Course Placement Rev2 |  | ITP-004a - Class 2 Base Course Placement Rev2
0dcded0f-6911-427a-b297-aeb69d34c2d7 | section | Preliminary Works
aa9057b8-6923-4779-808b-6ce9e42f2c4f | checkpoint | 1.1 - Check for correct documentation
eef91d5a-f837-5839-930f-5473b2497aab | note | FREQUENCY: Prior to commencing any activity
84db9e43-3dd8-5df6-be5f-62c69ddde189 | note | ACCEPTANCE CRITERIA: Ensure that employees and subcontractors are using the most current and complete set of construction drawings.
d02c4a52-4474-5194-910b-4c7161923dcc | note | REFERENCE DOCUMENTS: Drawings and drawing registers
30c0e7a3-73f5-5b72-a7eb-f13a26e15dbd | note | INSPECTION/TEST METHOD: Visual inspection
5a4ac37e-af0a-5ead-8598-72047698c2c1 | note | RECORD OF CONFORMITY: This ITP signed
62535004-9aa8-594f-8daa-aa3f02596fa3 | note | HP*
ece700da-f66e-586c-9256-f71cfc6ec07b | note | RESPONSIBILITY: FH Engineer
b0384619-674c-5c6c-985e-58ee3d37a1f6 | textbox | Date Completed:
b8dfa60f-643e-424c-bbc8-40d0ef911d3f | checkpoint | 1.2 - Implementation of all measures and controls
fc7dcc62-2082-5c5c-8cc1-52bc0a723c98 | note | FREQUENCY: Prior to commencing any activity
1a680cde-7660-5501-bb79-5ddc5578053f | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
e7851ce6-2936-5ed5-b5be-65dee865138e | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
0b551fb5-d5b9-58c4-8844-af21ff81c2f1 | note | INSPECTION/TEST METHOD: Verify
5ed90e30-9a9b-5a2f-9388-dc44e7a89477 | note | RECORD OF CONFORMITY: This ITP signed
a069b083-00bd-549c-9e05-30f28dfc61e2 | note | HP*
f0f6985b-2521-5b9d-98dc-a5d2c732ac7f | note | RESPONSIBILITY: FH Engineer
327a8ca3-d198-5ff9-a867-d6ba43fc9043 | textbox | Date Completed:
3ec7999d-fe67-4e4d-89df-5043215e03e6 | checkpoint | 1.3 - Material Compliance
e82ac387-ff02-5e15-ab93-3eefc5250091 | note | FREQUENCY: Prior to commencing any activity
1bf9ab70-5939-5955-a56f-ae13922abd44 | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
e904aa9d-c9fa-5645-a247-8ee3a53e8d93 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
a358e1e5-8eeb-5535-a9dc-f3f257f7f5c3 | note | INSPECTION/TEST METHOD: Document Review
eb0466f9-bd69-5d68-95f4-1046c3bfe706 | note | RECORD OF CONFORMITY: Test Reports from supplier
1dac424b-f976-5139-bb61-b381a7b925bc | note | HP*
ced59007-5c8b-5fc4-9c04-c979b360e1f6 | note | RESPONSIBILITY: FH Engineer
8adf8e0b-46ae-5575-bd2a-eaa29414b272 | textbox | Date Completed:
e2218d35-1110-4789-a69e-5876e619e25f | section | Construction Works
65b2037f-7e03-43ce-b996-a938436deb28 | checkpoint | 2.1 - Sub Base
8daeafc4-a682-5c4e-af73-522275246ecd | note | FREQUENCY: Each Lot
b888a4e1-9d3b-5cc3-902b-eaadd50ad384 | note | ACCEPTANCE CRITERIA: •Sub grade has been inspected, no visible ponding, springing presence, or visible deformation. •ITP-001 HP for subgrade inspection signed off
ba22bed7-ddc4-58b2-9505-94dfafbcf2cf | note | REFERENCE DOCUMENTS: VicRoads 173.03
66e97eea-806e-54e5-b4d2-0e243fd0e8db | note | INSPECTION/TEST METHOD: Inspection / Test Method
e174b0f7-6cd8-5d29-874f-38508af138f6 | note | RECORD OF CONFORMITY: This ITP signed
3d3aa363-9310-5347-8030-7fb946a02060 | note | HP*
7f97e0fb-e641-5fb2-84c6-dc5a3f07648a | note | RESPONSIBILITY: Fulton Hogan Engineer
1099080b-28cb-5b02-aff0-bdf51ef921dc | textbox | Date Completed:
ccd23935-1f11-4dfb-8437-9b4fc9e1c91c | checkpoint | 2.2 - Spreading material
9e2b7c62-1dc5-58c3-b5c9-67b03ea11e9a | note | FREQUENCY: Each lot
8f966443-2fd9-52c2-a085-1ce0f0d2b7d9 | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
ed078c52-eda9-5ee9-849c-3c8eeaed2936 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
187ad34a-5dec-5c13-b603-cb88931b35ae | note | INSPECTION/TEST METHOD: Visual Inspection
8d744c30-ed30-584f-a72c-401373f8cfc7 | note | RECORD OF CONFORMITY: This ITP signed off
28099315-bed7-5049-8c33-d3bce69d5758 | note | IP
eddcbe64-d787-5c47-99ae-67faa5c4d88c | note | RESPONSIBILITY: FH Engineer
65e3ad3b-761e-56a2-9fb1-1a5af70933ad | textbox | Date Completed:
e8aa4bbf-c360-4e34-bcea-1681091275fa | checkpoint | 2.3 - Compaction
5d7ad225-482c-597d-9110-863daa2445f7 | note | FREQUENCY: Each lot
dabf21ad-be7b-5980-8c10-68e910937fb3 | note | ACCEPTANCE CRITERIA: Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content. Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test. Compaction testing shall be carried out once per days production and shall comprise of three samples
b94ad6da-b02f-5a95-854f-fb0045334c40 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
96f757bd-8e2c-5c0d-bb6d-135467a3032d | note | INSPECTION/TEST METHOD: Visual Inspection
1a326134-5b92-5d5d-937d-561080adccf0 | note | RECORD OF CONFORMITY: Test Results
fc686ef0-37a9-562d-b112-dcfbaa564523 | note | TP
58387605-66b9-52cd-82e4-bcfa483a3bd2 | note | RESPONSIBILITY: FH Engineer
f32ea8e2-a01f-5968-80a6-0c6e9b99fa3a | textbox | Date Completed:
f701963b-3aa8-415e-83ae-ee60218748ce | checkpoint | 2.4 - Level Checking and Conformance
475275c0-ac92-5903-abe8-352c2068a9a4 | note | FREQUENCY: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
bc73e642-60d7-59ef-b134-f4937154e1f3 | note | ACCEPTANCE CRITERIA: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
ab119d18-cb8c-5197-a5e9-c43f6801d4f3 | note | REFERENCE DOCUMENTS: Verify
5328e5bc-46fa-5a60-9297-617d1cf4ea83 | note | INSPECTION/TEST METHOD: This ITP signed off
de698c9b-1185-5d02-8800-6059665c9de0 | note | RECORD OF CONFORMITY: IP
b173bd24-e549-5951-a7b7-2eee0d9a4f28 | note | FH Engineer
d3fc8745-778b-5c1a-8b80-8fa72dc44efa | note | RESPONSIBILITY: N/A
11fe45d4-30a7-5de7-8745-e29cb13176b8 | textbox | Date Completed:
c85ac2be-0fd2-4780-b5fc-567c81c47969 | checkpoint | 2.5 - Finished surface
f7166abb-ad84-5d87-affb-0f1e1122a1b0 | note | FREQUENCY: Each lot
7433e2e8-359c-50fd-9d34-47f24856ec75 | note | ACCEPTANCE CRITERIA: Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
c3c4ecdb-915b-5342-994d-27176ae51f97 | note | REFERENCE DOCUMENTS: •CE-019-ST- 0033 CL4.2.2.8 •Contract drawings
254a6555-18b0-5c68-b418-7d974169d062 | note | INSPECTION/TEST METHOD: Visual inspection
db50be59-4048-5051-a90d-119c974582c8 | note | RECORD OF CONFORMITY: This ITP signed off
c0aad2f6-6bda-54d9-ad08-36b1a9085c9b | note | SCP
066992cc-acb5-5974-96ee-5f62d6bf7713 | note | RESPONSIBILITY: Surveyor/ FH Engineer
a1daa22c-f86e-584b-a6bb-298e8ef9d48d | textbox | Date Completed:
d7bd8cb7-f657-4c48-93d6-b1745b4d9c0b | checkpoint | Final Inspection
00bf2141-6f55-5909-bd01-9750e86e105e | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
cb1f4194-31b5-5522-82d2-405c7f380264 | textbox | Print Name:
fa211b4d-6b05-51c2-ac9b-f724283170f4 | textbox | Position:
f049c979-d774-5cfd-8d1a-26564e4caf7f | textbox | Date:
7d7261fe-15da-4958-999c-0a311bebf277 | checklist | ITP-004b - Cement Treated Crush Rock Sub Base Rev2 |  | ITP-004b - Cement Treated Crush Rock Sub Base Rev2
2d7b8342-653a-41d7-8560-f48ed38a2bba | section | Preliminary Works
024a39ca-a139-4995-87e5-19ae019e4c54 | checkpoint | 1.1 - Check for correct documentation
b979d9aa-6a01-57f7-b64b-44610b82fecc | note | FREQUENCY: Prior to commencing any activity
9870f5cf-cfaf-5dba-b457-c668a7c550c4 | note | ACCEPTANCE CRITERIA: •Ensure that all employees and subcontractors are using the most current and complete design drawings
76c84cb3-7c1f-5e9a-ba2e-ed583e27bbd2 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
fe97673e-860b-5a8e-86c6-2f15c213662c | note | INSPECTION/TEST METHOD: Visual inspection
2621deaf-610f-5cd1-a82b-85b922385cb9 | note | RECORD OF CONFORMITY: This ITP signed
00ba2b62-1e42-5fe1-8118-ca1b3cca3cfc | note | HP*
cafc0b61-3dd1-522d-a5a8-8492d32229cf | note | RESPONSIBILITY: Fulton Hogan Engineer
30421942-5ed1-5cba-a24a-c8fdb6223279 | textbox | Date Completed:
38b9add4-d930-471c-875b-40b75f294906 | checkpoint | 1.2 - Implementation of all measures and controls
9969843f-fc55-5ffe-89b7-70184a77ce13 | note | FREQUENCY: Prior to commencing any activity
01573ea4-5ec8-5d86-a74e-a721e2fe8eb7 | note | ACCEPTANCE CRITERIA: •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
3083eff3-0da3-5fba-903d-21e59becd9b8 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
2f320348-f001-5b91-9e67-736279484241 | note | INSPECTION/TEST METHOD: Visual Inspection
c406ceb9-a796-580d-bccd-de6e3e773343 | note | RECORD OF CONFORMITY: This ITP signed
9a75c135-7e1f-57c3-bfc3-c44fe3bb2cbc | note | HP*
767668ad-c44d-5906-8136-e6bb37a40970 | note | RESPONSIBILITY: Fulton Hogan Engineer
dbbc1e78-a90f-590b-8829-c0c6d953c370 | textbox | Date Completed:
9c1a91b2-1c8c-4843-90af-74ee7295c8ba | checkpoint | 1.3 - Confirm CTCR is Appropriate Mix
ec19e46f-6476-51a3-9ee1-22721cc8407e | note | FREQUENCY: Prior to commencing any activity
2e9df7a5-2770-54a3-86e7-3247ff257886 | note | ACCEPTANCE CRITERIA: •Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product. •CTCR shall be tested in accordance with 815.141 by supplier
2127715f-9d09-5c78-ab52-7c9b6732fa3f | note | REFERENCE DOCUMENTS: Design Mix
b82d4654-3b95-51b5-8d79-3e1bded313ed | note | INSPECTION/TEST METHOD: Inspection
6de37178-036c-500d-9c73-2e312127e89b | note | RECORD OF CONFORMITY: This ITP signed
95df40be-2565-581f-a82e-913b1eb1387a | note | HP*
175600bf-c89a-57a9-829a-ed62cfd1375e | note | RESPONSIBILITY: Fulton Hogan Engineer
dc1c1b5e-908d-53c3-98bb-bb81c32d4148 | textbox | Date Completed:
6efd4fe2-bc3e-4648-ab49-6f80e86a7796 | section | Construction Works
fbda8ad6-3ca7-4b61-9c33-d6b699f703d8 | checkpoint | 2.1 - Sub Base
8743efbd-bd54-5179-8b2f-1df0f578bd89 | note | FREQUENCY: Each Lot
314edfb3-4aba-51cc-87eb-de74e0463355 | note | ACCEPTANCE CRITERIA: •Sub grade has been inspected, no visible ponding, springing presence, or visible deformation. •Proof Roll shall be conducted by plant compliant of 173.03
8f3112a7-cfc9-5a7a-b441-6587963245ea | note | REFERENCE DOCUMENTS: VicRoads 173.03
b305b37b-1a09-5f6f-a2e5-f614f36a9fba | note | INSPECTION/TEST METHOD: Inspection / Test Method
70bd699d-d974-54aa-8a71-5c5d6b448c37 | note | RECORD OF CONFORMITY: This ITP signed
42ee9c2a-e61f-54b3-9c63-e295db3db12d | note | HP
1ff63e5f-82c9-5653-b565-5186bfaed950 | note | RESPONSIBILITY: Fulton Hogan Engineer
9d3e2796-84e0-57ac-969b-5709d1c63152 | textbox | Date Completed:
b8c5fc30-d268-4d08-b2b8-2dbcedf0ccc9 | signoff | Authority holdpoint
87270b10-1274-48fd-b7bc-f7373d27fd8b | checkpoint | 2.2 - Moisture Content
8774b2ca-6d58-5916-b9c2-b10080f7702c | note | FREQUENCY: Each Lot
738fbb1f-947a-59d9-88ee-a30ac66a036f | note | ACCEPTANCE CRITERIA: •Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
dc7e1006-332f-52e0-89ef-8744e43a6b81 | note | REFERENCE DOCUMENTS: Vicroads 306.05
aa76258d-15f7-5dec-b42c-8d000b1f4a5e | note | INSPECTION/TEST METHOD: Inspection / Test Method
5f91932b-4875-5560-bdd5-a9869ffdc049 | note | RECORD OF CONFORMITY: Record of conformity
54061f89-7253-5242-87cd-b09aaae2484c | note | IP
81632bd8-3b97-5051-be66-e34577e5530c | note | RESPONSIBILITY: Fulton Hogan Engineer
a42ebae5-9e84-57a4-959f-ea1952ef4851 | textbox | Date Completed:
be302b2d-928a-4902-9709-149fe1ba3637 | checkpoint | 2.3 - Jointing
8410b6d2-8b08-50d8-8b21-9550cbc0b0d8 | note | FREQUENCY: Each Lot
ec70281c-1174-5ba6-be32-c062064f2b32 | note | ACCEPTANCE CRITERIA: •Material shall be spread to minimise number of joins
849bb7e5-af89-56e0-a70a-828ff9135513 | note | •transverse joints in adjoining paver runs shall be offset by >2m
d3f33619-9214-5996-a66e-d923606a3f5a | note | •Longitudinal joints shall be offset from each layer
a1d8117e-7b56-5819-b3d5-fb616c61839c | note | >150mm
a03edf84-9461-5735-a263-c70a6cb41bbc | note | •Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
730428fc-523c-5400-9e87-3ebd46c0f14c | note | REFERENCE DOCUMENTS: VicRoads 306.08
8d3c6204-dec9-58c1-9665-f8a66c52f4fc | note | INSPECTION/TEST METHOD: Visual inspection
91adcf2a-309d-54a5-a294-104fc92735a9 | note | RECORD OF CONFORMITY: This ITP signed
2e3c665e-54d0-50ea-9039-18d4351d6b72 | note | HP*
0b546cc6-aa3e-560d-8106-76caf2c6486e | note | RESPONSIBILITY: Fulton Hogan Engineer
62969414-c646-53c4-bb92-381d921ca92c | textbox | Date Completed:
fc8c2543-06ab-45a7-ac0e-7a1bbc090008 | checkpoint | 2.4 - Conformity with Drawings
4b4b77a3-c7a9-58b9-aefd-c89bfa91bd60 | note | FREQUENCY: Each Lot
8b372d5e-e242-5122-9cbb-b0f19545ee6f | note | ACCEPTANCE CRITERIA: •Pavement sub base shall be finished to smooth and uniform surface
e2aecb7e-74d5-575d-ad04-068e1e5ffd29 | note | •Surface of sub grade shall not lie more than 12mm below a 3m straightedge
e8475bfb-6f18-54d0-b8ce-fafc9416adcd | note | •Subgrade height shall lie within +15 to -25mm
a95f964e-7b85-561c-8e4d-f428143df434 | note | •Sub base height shall lie within +10 to -25mm
90cf01f7-33e1-5262-afe8-1295db124424 | note | REFERENCE DOCUMENTS: VicRoads 306.03 306.11
ea782bf8-5070-5599-bac2-17bf7c14e333 | note | INSPECTION/TEST METHOD: Visual inspection
fa89c1cd-6348-534a-bb0c-6acfa5b3e6a6 | note | RECORD OF CONFORMITY: This ITP signed
d789ab5b-50f9-532b-bbb0-d9c1dc464c82 | note | WP
64f8e23e-501e-5278-9110-b5b5e43d3c57 | note | RESPONSIBILITY: Fulton Hogan Engineer
0084edbb-1f9b-5765-9706-5c68078b7b57 | textbox | Date Completed:
5ebaa305-85a5-4add-bb85-15c93669bb2e | checkpoint | 2.5 - Curing
5f8cdfda-3f3d-5f4c-8aaf-e0761736d8ad | note | FREQUENCY: Each lot
1831e497-d46a-57d3-81e4-8cbed0a8fe56 | note | ACCEPTANCE CRITERIA: •The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane. •As per VicRoads, 4000m2 shall be maximum lot size •No trafficking before 24hrs unless approved by superintendent
ab299939-c62e-512a-916f-0d3068515f8f | note | REFERENCE DOCUMENTS: VicRoads 306.11
1a7e923d-f8c4-5bf4-a25c-a61cbd2e2580 | note | INSPECTION/TEST METHOD: Visual inspection
0a05f2f5-9117-52f5-a0fb-f2b8a73d51a9 | note | RECORD OF CONFORMITY: This ITP signed
b4f63502-ec89-5dea-802d-9cc70976b287 | note | IP
4057a548-26d3-5908-a2a6-aade18b7d452 | note | RESPONSIBILITY: Fulton Hogan Engineer
6a0f8167-f20a-5236-bdba-03f5fc7bf9f5 | textbox | Date Completed:
b3fb593c-6e8a-4b00-aefc-72ab6138eef7 | checkpoint | 2.6 - Compaction Testing
c0653381-983d-5f36-8057-481dc9e54989 | note | FREQUENCY: Each Lot
d5f02a96-a45d-51d5-9446-c15dd1f8fae4 | note | ACCEPTANCE CRITERIA: •CT material shall be placed, trimmed to level and compacted within allowable working time (306.091) •At completion of compaction, any segregation shall be rectified •>500m2 96% modified compaction 6tests <500m2 98% modified compaction 3 tests
a51049ac-3b77-5158-a378-627440286866 | note | REFERENCE DOCUMENTS: VicRoads 306.09 306.11
4fca6769-a0d3-53f2-bae1-12bd818f2bde | note | INSPECTION/TEST METHOD: Visual inspection
db02e54a-fc81-5dbe-8be6-2c1c1f295550 | note | RECORD OF CONFORMITY: This ITP signed
185b0ca0-212c-595d-9c67-894a76db742a | note | WP
875c0d4e-4207-565e-adf9-3faac60282bb | note | RESPONSIBILITY: Fulton Hogan Engineer
2779c6ea-8367-5f07-ae42-4f778ebbd858 | textbox | Date Completed:
c69ab091-cb63-4d3d-905c-d25aeeea708e | checkpoint | Final Inspection
98d167ad-83f6-5040-b39f-dcf0a76f0e85 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
bc93a8bf-6f8c-5243-801d-abefbf44d679 | textbox | Print Name:
918266b1-a04c-58b4-8e76-defcc838ef5f | textbox | Position:
5cc70b78-4fc2-51ca-ab5f-e7df651f4596 | textbox | Date:
ecaed04e-332b-4e70-8e7d-0d34d827131e | checklist | ITP-005 -Track Drains |  | ITP-005 -Track Drains
eac7f392-1c24-451e-bef2-a2ace5255a3b | section | Preliminary Works
f2051218-07ec-40f1-b3ca-1d75662d25ce | checkpoint | 1.1 Check for correct documentation
9e719214-6f4c-522a-a6cd-8392c44ccdb9 | note | FREQUENCY: Prior to commencing any activity
139d3e82-c1be-5d58-8955-208cf82d45a6 | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwarded to the superintendent
8f2a61a5-b312-5f92-8888-1b93eb7e5495 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
86c0aaa8-b18d-50b5-8605-5514dd478421 | note | INSPECTION/TEST METHOD: Visual inspection
86e70454-672b-53a3-8ed7-3869e180b07a | note | RECORD OF CONFORMITY: This ITP signed off
47ad83f4-0d5e-550a-b12d-bdf6ac4668c5 | note | HP*
44c17bdc-3d8a-5b41-8d12-6f82fb650741 | note | RESPONSIBILITY: Fulton Hogan Engineer
7c64b342-81bb-5d5d-b737-3664f9ccfe76 | textbox | Date Completed:
0f8b0809-12b8-4d9d-aa84-9c6f757c5bfd | checkpoint | 1.3 Materials Check
201b920b-fff7-53fb-a870-f2e6543c6a66 | note | FREQUENCY: Prior to commencing any activity
1b3ccf73-4750-56ad-84be-0170f69ad3b9 | note | ACCEPTANCE CRITERIA: Ensure drainage pipes are of correct classification and are without damage Check triangle drains are of adequate quality, and are design according Ri57A rail profile Ensure lid and j-bolts being used are in accordance with STD T9022
503fc156-3cab-59f1-aa1b-be63ee508c71 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A STD T9020 STD T9022
62c931ab-d295-583c-983f-44dd2009f59d | note | INSPECTION/TEST METHOD: Visual inspection Inspection Checklist
2cb56583-da6b-5213-9c22-b0c108412b4e | note | RECORD OF CONFORMITY: This ITP signed off Receivable Inspection Checklist
58d8df27-e9ff-5bfa-aa47-909e3008f527 | note | HP*
9d48d4d1-305c-57c6-ae7f-418261af225e | note | RESPONSIBILITY: Fulton Hogan Engineer
c613a3e8-8884-51fe-87c4-51d2ef2ada77 | textbox | Date Completed:
6b955491-33fa-4d74-bd51-491f6c27398a | checkpoint | 1.4 Bedding Sand
be7f4aa8-56d6-5470-b0ee-e2088df95052 | note | FREQUENCY: Prior to commencing any activity
0a61d9ee-c190-52d9-bfdb-20b31ec4de3b | note | ACCEPTANCE CRITERIA: The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following: Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities, Consisting of hard durable particles, and well graded.
12b85dcc-a727-5564-b1ca-04242d428bff | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
49d72c40-2574-5953-88aa-67494223445a | note | INSPECTION/TEST METHOD: Visual inspection
17698916-737c-595e-8736-0cf94fd3fc2a | note | RECORD OF CONFORMITY: This ITP signed off
f26b99bc-fcd7-5ad0-9536-25fae0c2836b | note | HP*
dcf78e96-d86b-5266-bdc7-61bb5d8b69dc | note | RESPONSIBILITY: Fulton Hogan Engineer
5b343919-49cc-5fbd-ba3b-98d52a0c3281 | textbox | Date Completed:
d1d4e554-e4fe-4411-91de-96068a99e672 | section | Construction Works
2c85e9c6-3137-4630-ba3c-e1dde5464374 | checkpoint | 2.1 Set out drainage
caaae469-153e-5cc3-acef-277af5c4474d | note | FREQUENCY: Prior to commencing any activity
ad9c3afa-56dd-5492-8e71-aaf93898aaa0 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent Track drain locations are to be identified and based off IFC drawings and sections.
9a68a058-3867-5080-9914-5aa1bbdf7b21 | note | REFERENCE DOCUMENTS: Design Drawings and Register
064b1ee0-969a-5c23-8298-a379df9fc504 | note | INSPECTION/TEST METHOD: Visual inspection
245db1aa-66ed-5cac-983d-38884a4e574c | note | RECORD OF CONFORMITY: This ITP signed off
425074ba-d042-5055-8167-1925612e9994 | note | HP*
bb1dbb91-5f3d-507d-aaad-1e4bfc4cf12d | note | RESPONSIBILITY: Fulton Hogan Engineer
01db7acf-86c9-5424-848b-934d6dbea948 | textbox | Date Completed:
86ddaf8d-b21d-4bce-89b3-0207d2e63957 | checkpoint | 2.2 Excavation (pipes)
bf991b72-e9f5-5704-ab45-3b2270b14b48 | note | FREQUENCY: Each Trench
7141dcb5-2981-53f6-bcdc-c847bc298ee6 | note | ACCEPTANCE CRITERIA: Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
0005575c-c604-5029-8a8e-a710b26761a6 | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
298cb14e-25f3-5992-b46e-cff5236cfceb | note | INSPECTION/TEST METHOD: Visual Inspection
34067c0e-3af7-5e54-8198-2bfb5e571e8b | note | RECORD OF CONFORMITY: This ITP signed off
049e91f2-9006-573a-b4d9-3522339d240d | note | IP
400cdc14-1eb5-5cdb-b30b-abdc5b532723 | note | RESPONSIBILITY: Fulton Hogan Engineer
e53e65d6-3f8c-5b04-9f51-3fb137c6a005 | textbox | Date Completed:
ceae9883-25a2-462b-ac45-ab3d538284f5 | checkpoint | 2.3 Bedding
73c9f0d8-b0bb-5508-81fc-60e8ae3c0a0f | note | FREQUENCY: Each lot
b2ce27e0-5219-5f2d-b51f-57e4b990dd9d | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
7f2bc204-3460-5ca9-bcda-a544d15b1647 | note | REFERENCE DOCUMENTS: STD T9021A
0687c0d7-ff21-519f-8601-7c9730189f4e | note | INSPECTION/TEST METHOD: Visual inspection
a2edf9f4-6b0c-5c5b-9eba-b35fd6d744bc | note | RECORD OF CONFORMITY: This ITP signed off
ad361632-a777-5d09-bc13-2b473ab9bef6 | note | IP
c32c9e71-a5da-5238-8370-7f0395f44ee7 | note | RESPONSIBILITY: Fulton Hogan Engineer
fd377ac5-3462-58d7-9325-b7c7059a283e | textbox | Date Completed:
038769a5-34f1-4317-9f47-f4cbcb11d8f1 | checkpoint | 2.4 Joining
a94f0cdc-9b05-5d9b-a208-2de8953bacac | note | FREQUENCY: Each lot
79f92300-c431-5b2d-880b-2d0916abf8dc | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends. UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
4b4afdd1-c36b-54d7-8dc5-1fcad749e3f4 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
a5b02335-b8ab-5e24-ae7a-edabbf4aa38c | note | INSPECTION/TEST METHOD: Verify
e3c9e811-2635-515f-b699-d5f5f7fc6df6 | note | RECORD OF CONFORMITY: This ITP signed off
0a1eb945-08ac-5d4d-8419-b374df341353 | note | IP
b7ee8190-0104-5e7d-9f61-fe91f31e1f6a | note | RESPONSIBILITY: Fulton Hogan Engineer
bcdf340a-0c97-5499-bcf1-73c35e1d851c | textbox | Date Completed:
7404b6b8-f380-44b6-8893-86e9ae3d5771 | checkpoint | 2.5 Track Drain Installation
bcb9e419-0c30-58e2-a589-911be6f63c8a | note | FREQUENCY: Each Lot
60775f54-b8b5-5e44-9f11-378cdc08e3fb | note | ACCEPTANCE CRITERIA: Track drains shall be welded to designated positions, and cleaned of all weld splatter . Weld shall be sealed after installation Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
af44239c-bc5a-5595-8463-f5e0465063f1 | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
17397136-4493-5a90-863b-4cc6073c7c5a | note | INSPECTION/TEST METHOD: Visual inspection
40d3ddd1-703b-5466-8cc0-e9748af75f69 | note | RECORD OF CONFORMITY: This ITP signed off
7712113a-ee3e-5cc8-ae7d-fc28660963f4 | note | IP
cff7c239-1375-5488-889d-acbc26e26f4a | note | RESPONSIBILITY: Fulton Hogan Engineer
04e22a8e-dbe6-5ea4-af6c-61d4fa3f8460 | textbox | Date Completed:
85285304-8566-4134-a131-ff0b566340b7 | checkpoint | 2.6 Points Drainage
fbd7ddc6-4b76-5d56-939b-a9497f761e8b | note | FREQUENCY: Where required
4fccfa6e-7221-5447-a2aa-4b4ffe8e22a7 | note | ACCEPTANCE CRITERIA: The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit. Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
8e137636-5107-5c62-8a9b-b5840eaa00b6 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304 STD T0305
fc87165e-8a07-53a6-a3a0-a3c04a4b3b6a | note | INSPECTION/TEST METHOD: Visual inspection
6d521cb0-cc98-5d40-b5de-d8192ef268ad | note | RECORD OF CONFORMITY: This ITP signed off
8e64e7f8-a85b-5db2-9a34-6f6d5a717f80 | note | IP
aef69ae8-9e63-59b0-a6f4-2a0837003fd7 | note | RESPONSIBILITY: Fulton Hogan Engineer
62b33a48-1ead-5979-b570-1158f4a4ff71 | textbox | Date Completed:
3a851b00-e731-45bc-84ec-31257adfb249 | checkpoint | 2.7 Concrete Pour
b0f20b78-72e1-5c15-b42c-20412d0cdc86 | note | FREQUENCY: Each Lot
5b83efcd-c52c-5e90-a3ce-8e2e42be8687 | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
a91e4d76-8c95-5912-a0e3-137ceaad966d | note | REFERENCE DOCUMENTS: STD T9021A
ba9b49a0-0288-577a-a42d-1ba812e56b5f | note | INSPECTION/TEST METHOD: Visual inspection
7de4930a-a1f4-5d1c-9d6e-829361583ee6 | note | RECORD OF CONFORMITY: This ITP Signed off
5d59bb42-4d3c-573a-97bf-b143f9e147d1 | note | IP
20ca46b3-6049-5f3c-8e6b-06ff285f9fd4 | note | RESPONSIBILITY: Fulton Hogan Engineer
635780ce-b909-5130-b541-a1e26f8c15fd | textbox | Date Completed:
8d012a0c-1f5e-4070-be78-d5e006f4ff97 | checkpoint | 2.8 Connection to local drainage
305ef7df-44af-5943-a00a-71b7279fa183 | note | FREQUENCY: Each Lot
cd115ee8-3add-5d8f-abd0-e570dc7d2a7e | note | ACCEPTANCE CRITERIA: Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority. The minimum pipe size shall be 150 mm.
cae01919-f869-5ebc-8777-eca12e7fe323 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
d79f1177-d76d-50df-8fd4-49977bd413b3 | note | INSPECTION/TEST METHOD: Visual inspection
2ac641e7-770a-5b33-9f41-0431d6fd0644 | note | RECORD OF CONFORMITY: This ITP Signed off
6bda4e3c-2d2e-584e-bb67-b8d1c8e77017 | note | IP
8c4fc595-790b-578a-aefc-5aaedb4a854c | note | RESPONSIBILITY: Fulton Hogan Engineer
087dcad1-d2f7-503d-971e-45f7e1db9f50 | textbox | Date Completed:
81b2f811-b347-4215-b94a-a67a53782d71 | checkpoint | Final Inspection
1bbceff5-f8d0-58c7-b622-91d67342ba2a | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
9cb10ab5-7b2a-5756-b173-077872aa5869 | textbox | Print Name:
23931154-332b-5613-8fa5-5dee83d1ee32 | textbox | Position:
965abdee-ad61-53de-b310-88c0839c6fad | textbox | Date:
727b69dd-b616-4163-8bb7-fdb597ea07f9 | checklist | ITP-006 - Track Placement Rev2 |  | ITP-006 - Track Placement Rev2
8880267c-a095-471a-9fb2-b5e410d97e74 | section | Preliminary Works
e401a622-281f-4b4e-a278-206d8a46ec72 | checkpoint | 1.1 - Check for Correct Documentation
cd29fb98-d34a-5d83-b67d-d4b33fd61046 | note | FREQUENCY: Prior to Commencing Works
964c440f-9bf0-529d-ab9e-4b6375494ce2 | note | ACCEPTANCE CRITERIA: •Ensure that all employees and contractors are using the most current and complete set of drawings
405f74cc-26c0-500b-9a62-a6d76810e729 | note | REFERENCE DOCUMENTS: Design Drawings and Register
9be3e37c-2c3c-5298-a0d9-a3c7a29c436f | note | INSPECTION/TEST METHOD: Visual Inspection
7e901ad5-b7d5-5a50-9e29-46bca7e72f31 | note | RECORD OF CONFORMITY: This ITP Signed Off
5e815861-37d7-5c6e-939c-d242661bbe85 | note | HP*
2f70d30f-0345-57bf-9c7b-f1fcdedcf44e | note | RESPONSIBILITY: Fulton Hogan Engineer
4b6c2314-b0cd-5349-b3b6-5602885559ee | textbox | Date Completed:
1b3976e9-5c71-4580-8c72-4d69ccb4ebbd | checkpoint | 1.2 - Check Materials
0b610a55-6723-5063-ba69-5697cf1f2c1c | note | FREQUENCY: Prior to Commencing Works
b657224c-619e-5f44-bec6-1095da352f2a | note | ACCEPTANCE CRITERIA: •Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used •Check condition of rail sleepers •Ensure rail jewellery is of sound condition
18386822-fe52-574d-b598-9e655687d446 | note | REFERENCE DOCUMENTS: AS 1085
78c574ce-6411-5123-91d2-7ac4a0cd74cf | note | INSPECTION/TEST METHOD: Visual Inspection
bb98e93b-fd93-579d-aa19-36096a3c1725 | note | RECORD OF CONFORMITY: This ITP Signed Off
7646fd20-86a1-5f5b-a71d-a98158afd41e | note | HP*
e599347c-b5a8-5639-84ee-c52ae83a24f4 | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
1874dca2-92d8-5d96-a892-6df537bf2f87 | textbox | Date Completed:
9ae86133-3c7b-49cd-a026-3dd54cc2e735 | checkpoint | 1.3 - Check Special Works Components
a05837b8-43de-57b7-ac96-144b1856913b | note | FREQUENCY: Prior to Commencing Works
474de2ce-c6c3-569d-b155-ada77142232b | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending. Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and separate rails. Superintendent to visit yard for initial inspection of the rail and fabrication plans.
25046c45-97b8-5a97-b1ee-b253816a8033 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
b4848578-6b52-5c59-9df4-81ef37018436 | note | INSPECTION/TEST METHOD: Verify
25358b36-35b1-59ad-a490-44c8057f65d8 | note | RECORD OF CONFORMITY: This ITP Signed Off
8eb15827-921f-5dec-b7f7-eb437cedee9f | note | IP
818b6dfc-fe63-5a0a-b5b6-f33114de415d | note | RESPONSIBILITY: Fulton Hogan Engineer
44ba37d0-09b1-519d-93a2-de488331cdd0 | textbox | Date Completed:
cab3bb1f-fe3c-4b73-bb11-11ba60f7af89 | checkpoint | 1.4 - Check Curved rail
d8d9ede7-59eb-5144-98d8-cbe9133fec94 | note | FREQUENCY: Prior to Commencing Works
17560a09-b7af-547d-82d4-fd31a8cb2a60 | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent. Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails. This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
5624175d-8b13-5288-93ad-2f6c5bdd1acf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
46f3f00a-f241-5e4f-b4ed-652e53db778c | note | INSPECTION/TEST METHOD: Verify
796e8825-225f-582b-a9fc-425c8a2a5d81 | note | RECORD OF CONFORMITY: This ITP Signed Off
c7b53874-548f-583c-a6e3-dd5cf9394af8 | note | HP*
314dfd77-d240-5839-b3bc-5341e0ab6949 | note | RESPONSIBILITY: Fulton Hogan Engineer
67209292-68cf-5abd-a0b1-5a80e5fd6d81 | textbox | Date Completed:
19d593a2-92c3-4796-a9c8-785fda0b5d29 | checkpoint | 1.5 - Welders Qualifications
e0e7d274-1fbc-5dd5-bf85-2fcdac646c56 | note | FREQUENCY: Prior to Commencing Works
64b0e2a3-5dd5-5ac2-b0a1-0981e4732c06 | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements; TLIW2012 Grind Rails TLIW3015 Weld Rails using Aluminothermic welding process TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
ea8adda3-63fb-5f59-ad0c-e4fd4349e786 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
6890baf7-b1db-52ae-8fc6-b3f084f8c88f | note | INSPECTION/TEST METHOD: Verify
80539802-dd39-52b5-9440-2328a95d320d | note | RECORD OF CONFORMITY: This ITP Signed Off
e8af5b79-190d-5f0a-acf8-878b8da4d60b | note | HP*
cfbe0754-e9ad-52b6-bbd6-d7292f8a052d | note | RESPONSIBILITY: Fulton Hogan Engineer
2d492f74-22fb-5fe6-ba5e-fb6e232c3bed | textbox | Date Completed:
4899bd3e-4728-49c9-8db7-10e7744c7ff7 | checkpoint | 1.6 - Ultrasonic Testers Qualifications
7d7a4e2f-26d7-576a-8eb5-abd6c83ee16a | note | FREQUENCY: Prior to Commencing Works
d8971465-e451-51fc-a459-5ee5ffa29b04 | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
1acb5bff-9e9d-5b6c-98d2-98c331de6e63 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
ebf347c9-33c6-59f1-8ddf-6c8cba71d1ef | note | INSPECTION/TEST METHOD: Verify
a4002dbf-9600-5737-a9ce-b8fe15253f85 | note | RECORD OF CONFORMITY: This ITP Signed Off
f2cc989a-cf12-5e51-b397-f481d693eae9 | note | HP*
3ef36531-d56e-5233-b8ef-1f6c0c3a9805 | note | RESPONSIBILITY: Fulton Hogan Engineer
a7d57174-9100-572b-aedf-8b48a3c2fbf9 | textbox | Date Completed:
ea49d8ff-41bb-4887-9557-ee411727a6cc | section | Construction Works
82a6623f-ead1-4f57-ba2e-5a17767688c1 | checkpoint | 2.1 - Installation of Sleeper
1af28c5d-5e85-5392-a3f2-7276b93771bd | note | FREQUENCY: Each Lot
96620156-a6c6-587b-abb8-5d8d6e3dc570 | note | ACCEPTANCE CRITERIA: •Dual block sleepers shall be installed at 700mm intervals, tolerance of +/- 50mm in placement •Dual block sleepers shall also comply with the design offsets at each chainage
d3bf5394-99c9-5011-8a1a-320c0bb233f6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
9e0723eb-45ae-59b3-bf47-728921b20db9 | note | INSPECTION/TEST METHOD: Visual Inspection
f8b5bc31-fbe2-5f96-b851-21ce47bac4e3 | note | RECORD OF CONFORMITY: This ITP Signed Off
dac7d3ee-aedc-5d75-8c93-5f1db2c2060d | note | IP
78caf6b1-d1d2-5794-84ca-c72246a12d9c | note | RESPONSIBILITY: Fulton Hogan Engineer
1ecc71d6-3820-5fa4-945d-82e6938ca330 | textbox | Date Completed:
b4313002-f592-46d8-bc80-c2fb194a402b | checkpoint | 2.2 - Placement of Rail
9e4882f9-95ed-576b-beb8-91423a4fe3da | note | FREQUENCY: Each Lot
81de4f35-0ec9-5fb4-b614-e440666d6b93 | note | ACCEPTANCE CRITERIA: •Ensure rail strings conform to rail plan
de65fa73-6f41-5de3-a756-9ad7b20704b0 | note | All track work, including points and crossings shall conform to alignment, offset, level and Can't as per design drawings and track charts
981ab85f-0749-51e4-9ac7-c2ace21994fd | note | •Bottom of rail and bearing surface shall be clean of foreign materials before laying
8fb10fb9-bdb0-586f-831d-7cac9c404e76 | note | •Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
19405d0b-67d1-5d59-8bab-27667942c77f | note | •Geometry tolerances as follows:
98fc0d85-612b-5263-b8ed-74652c7cd131 | note | - Centreline location: +/- 3mm
a7d4cfe0-8cec-5cce-90b6-de3bf1d4dce2 | note | - Level: +/- 3mm
16e1e851-1d87-56e2-86dd-366c0b925470 | note | - Line measured (>10m chord): +/- 3mm
431c5373-d5c1-5bbd-90d0-e3a09db40aa8 | note | - Twist (3.5m chord): +/- 2mm
7c96322b-25e7-5583-9442-b2b336132a45 | note | - Can't: +/- 3mm
d05bf438-e2ac-5f32-a190-9b9d12c17657 | note | - Gauge (open track): +3mm, -0mm
4c40abc0-c672-5baf-8a0a-33cac251b69e | note | -Gauge,Turnouts (opposite crossings):+2, -0mm
21e310b6-d87c-5063-b917-a002df5a8c3d | note | -Gauge, Diamonds and ‘H’ Crossings:+2, -0mm Note: Can't shall be applied uniformly over transitions
20e6cb06-1ef9-5f6c-9023-688f9e9c4111 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
ba0b22f6-106a-553f-aadc-f14711e8b518 | note | INSPECTION/TEST METHOD: Visual Inspection
2da2726e-2a7f-5618-a421-49359cde75dc | note | RECORD OF CONFORMITY: Completion of track charts
12d24ea5-3bd5-5a03-8140-e32dc1fd656d | note | HP*
17b2e038-7a96-5e65-9806-c142ddad861f | note | RESPONSIBILITY: Fulton Hogan Engineer
5e78a8a8-8835-58ce-9dc0-86c8a823770e | textbox | Date Completed:
b5d082f9-a636-44be-93df-66f796304f70 | checkpoint | 2.3 - Placement of Jewellery
db7ec983-05bd-5369-9920-18ed1f278787 | note | FREQUENCY: Each Lot
494eed0f-a9df-5deb-8dc1-32dad77dbf86 | note | ACCEPTANCE CRITERIA: •Each sleeper shall be fastened to track with approved jewellery and rail clips •Clips shall be installed with panpuller or equivalent •All fasteners shall be sealed as per agreed method with Yarra Trams
32f42f5d-e237-535f-b00c-789904d523df | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
bce1160d-b5d9-5515-913b-c9534819b257 | note | INSPECTION/TEST METHOD: Visual Inspection
eb193498-4949-54ae-a77c-36777da14e67 | note | RECORD OF CONFORMITY: This ITP Signed Off
636ee210-c86b-5509-b9e4-02b7982c18e3 | note | WP
9dbb0d67-d5d8-590a-a8d5-60a772a1502a | note | RESPONSIBILITY: Fulton Hogan Engineer
f97de18a-8d57-5b76-bc92-1bdfc0b109f6 | textbox | Date Completed:
110bf15f-1fa5-40bc-b29f-c0e355144d63 | checkpoint | 2.4 - Rail End Preparation
6104b9aa-139b-52c9-b8b2-d11585fe3d39 | note | FREQUENCY: Each Lot
5e2f5c5e-3418-57a7-be92-b75939ed7529 | note | ACCEPTANCE CRITERIA: •Rails shall be saw cut or flame cut •Minimum closure length from proximity of welds shall be 2m •Rail end conditions shall match (i.e flame cut - flame cut)
a2372a8d-9009-5b53-8cf1-5d3c03e14f5e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
8390e013-b665-5b70-bc4a-47baa14d1202 | note | INSPECTION/TEST METHOD: Visual Inspection
732e8c69-ef33-57b4-8578-3d11fecfeafe | note | RECORD OF CONFORMITY: This ITP Signed Off
cacab564-386e-50f7-b663-c2dcd3e8cdb2 | note | WP
cd5d3c55-8e0f-53ae-8bde-f28aac3ec574 | note | RESPONSIBILITY: Fulton Hogan Engineer
44dcc52e-22c2-5f2d-b271-efc15d91e30c | textbox | Date Completed:
cb9bdf51-ed60-406b-b20c-b3d2554ef2ae | checkpoint | 2.5 - Welding of Rail
085ca19e-ee90-5b7a-97da-68ff827dd62a | note | FREQUENCY: Each Weld
03439012-86e6-5fed-9cb7-7adf8df0c8f7 | note | ACCEPTANCE CRITERIA: •Joints shall be square across the track
09e398d6-d71d-54e4-bbc5-b0d624f4cc93 | note | •Maximum skew at square joints shall be 65mm
a47d6280-bb4b-5e8a-94ad-619801d5a930 | note | •Portions shall match rail type (i.e HHR, Ordinary)
1b21b353-c893-50f6-a8c8-dcf5373a6131 | note | •Welds shall not be within:
6a223772-158e-5892-9b7a-03485820596e | note | - 3m of another weld
1a9200c6-f296-5074-8d7f-d2f482b6e837 | note | - 3m of a rail end
d55c108e-8df0-579f-82ad-15d24551d9f4 | note | - 1.5m of a glued insulation joint assembly
979c87d8-47ec-5e19-b4cf-1f492c4d5f09 | note | •Field welds shall be +/- 50mm from centre of bay between sleepers
859ab0a3-f034-5519-b1de-b588eff41ee7 | note | •Weld Return forms shall be completed by qualified welder
51879caf-fd2f-5a94-9d21-b0de4e7c5536 | note | •Welds shall be grinded after 1 hour
b2840a06-bd4a-5e48-8b66-ea6c7acc96c6 | note | •Welds shall be free of water
69ad301a-5480-57f4-91da-cfc0931fdc68 | note | •Post grinding, welds shall be cleaned for visual inspection
77a27b10-9b9f-58fc-adf1-56a8937a0ba4 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
d19dfaa8-fffa-5dd2-b94b-beb24f507615 | note | INSPECTION/TEST METHOD: Visual Inspection
8d27ef80-1755-50a9-838a-161f0a766f2e | note | RECORD OF CONFORMITY: This ITP Signed Off
25f20dd3-680d-56a1-bb6c-766a45cdbff3 | note | TP
8c8a9d11-3b1b-55bb-b9ad-90a3a8e96be2 | note | RESPONSIBILITY: Fulton Hogan Engineer
ae31bbd2-3535-546c-ba33-3e567491aaf0 | textbox | Date Completed:
a8a7e9fa-2d44-4b24-b4da-d6f11661deb3 | checkpoint | 2.6 - Grinding & Cleaning Welds
42f38b73-3bbe-5328-8d15-301b92d305c7 | note | FREQUENCY: Each Weld
fe6226e5-599b-5a1d-b0e6-12f74a3c8320 | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld. Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
f40d88d2-6be6-51b2-a3a6-8a3edac56835 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
8257a3d5-91ea-5dfc-8bdd-adfc68fadbd3 | note | INSPECTION/TEST METHOD: Visual Inspection
3e837ce5-809f-5cbe-8357-864f9418656d | note | RECORD OF CONFORMITY: This ITP Signed Off
f0b9a9b9-3834-506c-91a2-7541746fda5f | note | IP
6be05ff1-c1a5-54dc-b3fe-2d436b2582fb | note | RESPONSIBILITY: Fulton Hogan Engineer
1b206d17-7851-5c0c-8231-36656b8334e2 | textbox | Date Completed:
8e374ad4-0f87-420c-911d-e7553c1fcfb8 | checkpoint | 2.7 - Track Adjustment
d52394ef-6a66-5064-8c70-c3fa92e7f587 | note | FREQUENCY: When required
227a89fc-aa63-5e0c-ad93-557efd7fca8c | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with an approved type of thermometer. In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep. Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
6b2dbab1-ddf0-522e-ad2b-c951b4e60017 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
7040af63-aeca-5e47-9d60-df450cc0663f | note | INSPECTION/TEST METHOD: Visual Inspection
82adc131-930c-58d4-892c-96e7167efc2b | note | RECORD OF CONFORMITY: This ITP Signed Off
5f587d22-36af-51ec-a184-1d25812a01e0 | note | IP
6ea11ca1-f9cf-515e-ae37-7dd760b43d07 | note | RESPONSIBILITY: Fulton Hogan Engineer
7d27f81b-26c7-5941-9008-ec501bbeb88f | textbox | Date Completed:
14cb2c02-5d84-4580-bba0-3f7c6409b65e | checkpoint | 2.8 - Track Bonds
5975dd3b-dec2-57c0-80c9-ae1b7f325f87 | note | FREQUENCY: Each Lot
5de95e3d-1f67-5565-a032-d12dc4ef76b6 | note | ACCEPTANCE CRITERIA: • Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications • Ensure bonds are sealed as per agreed method with Yarra Trams
9889d286-ae7d-50c0-9991-39ce083f0147 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
9debfd48-fb3e-561c-876e-6619de86e594 | note | INSPECTION/TEST METHOD: Inspection / Test Method
340bbcd5-17a1-5c10-944f-7bb469086b37 | note | RECORD OF CONFORMITY: This ITP Signed Off
adf4ffca-7a9d-50f3-b758-2206898c51ef | note | IP
0a8c29c6-b981-55d8-966d-85f05ecb592a | note | RESPONSIBILITY: Fulton Hogan Engineer
0a8cb9a4-9751-5404-a367-f625d5b1c4ed | textbox | Date Completed:
013a36bf-2ef1-4221-9de6-0b766c041b65 | section | Testing
e71cf6f0-3c03-4d02-ba35-4c297feda1e7 | checkpoint | 3.1 - Track Testing
f82612f6-b828-58a6-ad21-bb1c2e8f9a35 | note | FREQUENCY: Each Weld
8e013ac7-2c48-5646-a49c-f7a20c4f2144 | note | ACCEPTANCE CRITERIA: • All welds shall be tested by qualified NDT operator • Failed welds shall be cut out and replaced • Testing documentation shall be recorded and supplied to the superintendent
c3ddcd00-283b-5c3c-a779-6700f7f6fe9e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
af6273d3-11e0-51d7-928a-642776e445ea | note | INSPECTION/TEST METHOD: Inspection / Test Method
3df59ac5-37a3-5a51-bdcf-4ea290a0d340 | note | RECORD OF CONFORMITY: This ITP Signed Off
13bdb075-0886-5f92-a4f9-222340b31820 | note | TP
1102627a-fe53-5a67-9460-6bbc450d6eb3 | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
8960344a-fe92-5e6d-8ab2-73512c63d8fb | textbox | Date Completed:
c512471f-d2df-4b17-a9b7-d22552ce20ae | checkpoint | Final Inspection
6699681f-4c7a-5d96-9484-aef0f57c74e6 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f843731e-d52c-5835-a89d-28823de89ec9 | textbox | Print Name:
01296558-d969-5629-b097-9b16dbf63a4b | textbox | Position:
55e7840c-1f26-51a5-bbda-17567ffd309c | textbox | Date:
1ce6797f-d51e-4033-9607-d5923e46636c | checklist | ITP-007 - Concrete Track Slab Pour Rev2 |  | ITP-007 - Concrete Track Slab Pour
7573ddb6-51e4-4823-a3b1-1525b3f16f5f | section | Preliminary Works
95f4a151-8f9c-4ae3-baa9-5d62264affa6 | checkpoint | 1.1 - Check for correct documentation
ee857424-c0fb-538e-9f68-ac109d69fae2 | note | FREQUENCY: Prior to commencing any activity
df932296-2db0-550e-93ae-de804f34ba07 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
667f2216-43f3-54f3-b6a0-dc9bc4e425fe | note | - using the correct and complete set of drawings
280cc5bb-df7f-5b6c-9571-6d2989b9d460 | note | -all drawings are the latest revision
09b20c06-7140-5799-beb5-d3b19bfb8d0a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
7c7c3d8b-a184-5db6-a0a7-c50cd53ee161 | note | INSPECTION/TEST METHOD: Visual inspection
9cab7367-16df-52bc-8412-e8fc3db44066 | note | RECORD OF CONFORMITY: This ITP signed off
e2a570ba-2c5e-5b2f-8874-6069489c9f4b | note | HP*
1ba1ce18-77b8-503b-a515-a354ae2a7721 | note | RESPONSIBILITY: Fulton Hogan Engineer
c64fe870-941d-5743-8757-87fa80de2f78 | textbox | Date Completed:
b74895e9-1c0a-4413-8fe2-39f1007662a1 | checkpoint | 1.2 - Submission & Approval of Concrete Mix Design Prior to Commencement of Project
ff5b598d-4a85-5fe2-9675-943fc266d23f | note | FREQUENCY: Prior to first concrete pour
96b80d78-31d4-5f4c-a98f-e5c8695239b9 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
67137bfe-d298-5930-b25a-63052b392f41 | note | Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
722fef58-1b6a-5b00-8ad8-d3973623aa4a | note | Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
6752e1da-5584-56f9-8121-b04b8350c669 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
b100e7d1-1c41-5759-b4de-69fc8b8302bd | note | INSPECTION/TEST METHOD: Verify
2b063d62-76b9-596d-b6e7-139cdb3d6165 | note | RECORD OF CONFORMITY: Mix Design ITP
abfd35c4-34cc-5f79-bdd2-f3d5b0dc192a | note | HP*
0bf96026-6b55-5bb8-b787-af69bf130beb | note | RESPONSIBILITY: FH Engineer / Superintendent
515c8055-41fa-5e2d-a6de-d35cc164a2ce | textbox | Date Completed:
285581b7-4bd3-4240-8dac-82e6f3592690 | section | Construction Works
077e157d-05f0-4cbf-bb61-f5183db8a93c | checkpoint | 2.1 - Weather Monitoring
9b81781f-b0ec-5c27-86f9-8dc8974c5913 | note | FREQUENCY: Prior to start
59055cb9-0c5e-57b6-9141-8b765e0f1ef7 | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
be58d2ab-671f-525f-93b5-dfd05415f689 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
27fd0530-f40f-57ae-90aa-f8ca57f2627c | note | INSPECTION/TEST METHOD: Verify
37d938f4-3c87-543c-9215-3aa10d512b4c | note | RECORD OF CONFORMITY: This ITP signed off
682d2c61-dcc2-5c6c-bcfd-9e7f686e467e | note | HP
173ddbfd-e7bb-5357-816c-fa1b14570cea | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
709dd92a-1d37-53aa-b867-0a96d68804e4 | textbox | Date Completed:
cdb9a3fc-2b16-4d57-a1a8-db02cdef6a06 | signoff | Authority holdpoint
81c139af-a909-421f-b89a-30809d6f4564 | checkpoint | 2.2 - Surface Preparation
55d84d11-2861-5384-aee4-eecee09a62ab | note | FREQUENCY: Prior to start
346afd86-0f65-519d-ab61-2ec80e8a2820 | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thoroughly cleaned of all foreign and loose matter prior to pour
6a58cbc9-82c0-5090-9109-c3ee90082332 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
c49010e5-41b0-514f-80af-368a00ec17f3 | note | INSPECTION/TEST METHOD: Verify
dd742909-cee2-5d20-81eb-9f3fa0a01faa | note | RECORD OF CONFORMITY: This ITP signed off
636dce9e-7f3b-539d-bf18-29dac39b82cd | note | IP
59ae8e94-f00b-5a41-8909-c0c9ab87e715 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
23269c63-10e9-5332-a6ab-88b523c8b1f6 | textbox | Date Completed:
bacc303b-97ab-4a91-8a07-e5d28b68c8eb | checkpoint | 2.3 - Setting Out
88bac1e6-6379-50e9-8e62-d5bcdd126fe1 | note | FREQUENCY: Prior to start
5b847524-8eed-5288-a2d6-c062dc3596a4 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications. No survey/level pegs to be removed by any persons until completion of works.
c97d97a1-87a5-5947-9070-5ea26aa91a70 | note | Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
fcf77c11-eb57-5edb-b3f5-ba355a618de9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
3f132706-6d2f-513b-b2ad-5312fe152b08 | note | INSPECTION/TEST METHOD: Verify
2923c12d-8d2f-558c-a122-a4875ee3a04a | note | RECORD OF CONFORMITY: This ITP signed off
149b7d97-87f6-52d9-ace8-f04d4ed80062 | note | IP
bac245a9-264f-545c-82c7-1faff91d7395 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
7b1e6a40-043a-53b3-a7ff-a04c9626d75f | textbox | Date Completed:
afcdcadb-cf75-45d6-8dd7-2e7ee849dbcb | checkpoint | 2.4 - Formwork
dc92854c-cce3-55fc-adc8-3893dc98d871 | note | FREQUENCY: Prior to start
f99bb01d-d5d7-5dbb-aa06-9b63aa4f93a8 | note | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
e4575ac9-c560-5ec1-b628-c9dc42c2bacb | note | The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
0e3d0a05-828d-5443-a2e4-3ba857914cc0 | note | Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
785e66be-b1c4-54e5-b182-77b42835632e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
de7db1d9-7358-56f0-b3d8-0bf85a6a7f16 | note | INSPECTION/TEST METHOD: Verify
8c36e20d-cad7-57d5-8f86-83946eb61369 | note | RECORD OF CONFORMITY: This ITP signed off
6a4ba589-dd7a-5eec-9ab6-79275642de07 | note | WP
2cb850d7-5029-5829-ab94-11e2d44c9361 | note | RESPONSIBILITY: Fulton Hogan Engineer
34619dad-c35f-5b42-a9ac-fde25f581172 | textbox | Date Completed:
227f7cb0-a882-403b-b85b-c814e91bc347 | checkpoint | 2.5 - Reinforcement
fed8968b-ec9b-5fd3-97b5-64fdae48896c | note | FREQUENCY: Where Required
57500128-42c5-5782-a50c-fa651eb83896 | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
8e57bb31-1c5a-5e0b-b2e7-608e43197f89 | note | All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
f8042961-c72d-5f0c-9610-fbf49417b412 | note | Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and ied with wire at a maximum spacing of 500 mm.
5c9d6253-e208-5419-a9a4-5982ac1af5e7 | note | Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
53b6c89c-9d28-5e9d-8bfe-44e9129b7857 | note | Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
52de4106-4316-5729-b49b-71a3b0118468 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
bbc4abbe-5752-55fe-92dc-80b2641fa87b | note | INSPECTION/TEST METHOD: Verify
00277aa0-f849-5f09-b213-313a785413dd | note | RECORD OF CONFORMITY: This ITP signed off
7a69909d-9a27-564a-a2e9-120cc9744aab | note | IP
ec132ec0-988b-552a-829b-06f896cfaa72 | note | RESPONSIBILITY: Fulton Hogan Engineer
2ba1e866-0ed2-5976-bcca-dc9073e7d57d | textbox | Date Completed:
b99e4786-f44a-4073-8cec-6b06962c6d91 | checkpoint | 2.6 - Dowels
86f62947-55cf-5c24-bf41-2ad02ab7ab62 | note | FREQUENCY: Where Required
ad65bc98-efc3-5b94-b6f7-59af1ef28bff | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
1e3cc1b0-47dd-5403-8007-5bee65de76c5 | note | All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
a0566b04-6102-596e-b857-ffde4e0b3d86 | note | Dowels shall be clean and free from mill scale, loose rust or oil.
2810edff-3e7a-559f-b14a-22ce80d7111e | note | Ensure that all dowels are securely held in their correct position until the concrete has set.
52e4c036-868c-5c2f-a190-d5bce12e2610 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
ff0f2061-49f9-5ec1-8a90-02aacabbd8c5 | note | INSPECTION/TEST METHOD: Verify
6a6ce224-a5d7-5256-9738-6e704cc89d85 | note | RECORD OF CONFORMITY: This ITP signed off
407c16c9-735a-55a3-ae5b-f6309ba12de7 | note | IP
9a3a64ad-18d8-537e-8a15-28ec6425b0f3 | note | RESPONSIBILITY: Fulton Hogan Engineer
1b516b76-2e40-5ba6-b071-27f22884b08e | textbox | Date Completed:
c35ff610-a18d-4607-ba58-049848f0c7d5 | checkpoint | 2.7 - Pre Pour Inspection
de203b85-5c77-5ce8-89c6-6ea1d68e6453 | note | FREQUENCY: Prior to start
c0038681-3e78-5172-8b46-f4d1fd8f0631 | note | ACCEPTANCE CRITERIA: • Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180degree difference in gauge placement
c1124da6-e29a-5126-a8ed-20ccaaf43ab2 | note | Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
b42dab07-a8ca-5956-b377-b1625f874104 | note | Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
0d9f4777-c629-5b19-b3c4-66df6083016d | note | REFERENCE DOCUMENTS: CE-019-ST-0033
4ecc14e3-8935-5bfd-bfb1-1dc581703433 | note | INSPECTION/TEST METHOD: Inspection / Test Method
ae292319-e7e1-534b-9d0e-3588dd80850a | note | RECORD OF CONFORMITY: FH Track Inspection
453f01ad-c13a-51f8-9632-be2e6dcd1d99 | note | HP
c9856493-ae69-504c-bdc6-c38a92b98885 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
e8a3d328-941e-5c36-ad1c-27f42893ad70 | textbox | Date Completed:
dbbdf0fc-eb6e-4fd7-8968-94a2eedb6049 | signoff | Authority holdpoint
a2488d4f-f070-441f-b37f-0cca5d9c6fcc | checkpoint | 2.8 - Carry out sampling of concrete
99c66ec4-33a9-5770-8143-744c9f37199f | note | FREQUENCY: Each concrete pour
65686a19-5707-5b89-95a0-7bc137055684 | note | ACCEPTANCE CRITERIA: Slump:
57ef3a76-e9a3-5914-9352-74fd4b35e6fd | note | Concrete Slump shall be 75mm +/-20
ee5ee354-280c-506b-b24c-b4020872d612 | note | Compressive Strength:
1f54b83e-ae63-5ee6-92a1-3dabebf9b309 | note | Shall be measured in accordance with CE-019-ST- 0033
6d5429ea-44d6-5687-99c1-5de7c591fafb | note | • Testing frequency =
3b7fe8c1-80f0-5c86-ae7d-8b1801d24e15 | note | - 0-50m3, 1 sample
c401e829-1f36-50dc-bc4f-63075430e43b | note | - 50-100m3, 2 samples
dc32b76c-6750-502c-9438-d530dcae6383 | note | - 100m3 +, 3 samples
9c184d68-620a-55e7-be13-fae9627e379c | note | Each sample shall consist of 4 cylinders
c7c36110-b17b-5851-b662-e28ef124a17f | note | Test Results will be provided to the Superintendent
0a7326b7-dcb5-5035-a33a-0f99ab7b8361 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
2bc27874-6ef5-5482-9d5e-0890f15b8219 | note | INSPECTION/TEST METHOD: Verify
7b577220-9dc0-5802-95e3-6b79df573a86 | note | RECORD OF CONFORMITY: Concrete supplier test sheet
c45af8e7-a824-5ce1-85e8-fd33df8a5ceb | note | TP
20cc6289-d26f-507e-bffc-5f3b3e0d3000 | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendent
9c3b0335-8145-5073-ae07-5914f3e100a9 | textbox | Date Completed:
1fb87705-8d95-4ce6-8c42-11de6e92264a | checkpoint | 2.9 - Concrete Placement
b27d8f08-e2ce-5579-abc1-22502136fef2 | note | FREQUENCY: Each Lot
a2583a0a-6d66-5f5f-840b-0d17acaf5240 | note | ACCEPTANCE CRITERIA: Ensure formwork is clean
7a2b4018-d96d-5435-9234-23c1f82e3527 | note | Concrete shall be entirely discharged 60 minutes after batching,
94ae6b2e-e4ba-5aef-b8d4-939f6e08d06a | note | Ensure that pouring does not occur from a height greater than 1200mm
bd18e3c1-ce6a-5c36-b262-6bb899434a3d | note | Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
ae5dc2a6-41b3-5781-a807-2a1ed1e3b6fb | note | The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage
48854429-7daf-5eff-9b76-7297528a39a2 | note | There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
c2dc1fd6-5271-5df3-b76f-3d0b881192f2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
9e082f55-b5ff-5f44-8bba-4cdd551aa37e | note | INSPECTION/TEST METHOD: Visual Inspection
7c58e271-bd69-5f67-86ff-9bcf155d86b3 | note | RECORD OF CONFORMITY: This ITP signed off
93773ae1-ca10-51bc-b18e-b7499ed68496 | note | WP
10a48503-e40f-5e98-a738-05a64b161972 | note | RESPONSIBILITY: Fulton Hogan Engineer
595bf7b8-8439-5cae-9952-0d133f289b1f | textbox | Date Completed:
9559c3f6-a684-4549-ac56-818fece1d92e | checkpoint | 2.10 - Compaction
89cf7682-5439-5166-aff1-854b54d2f8ef | note | FREQUENCY: Each Lot
e6fbcb0f-9c1b-5f59-bb68-6179a22c6bd6 | note | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator
cdfdcb50-af60-5255-8224-e19d30366214 | note | Vibration shall take place until exposed concrete surface is free from air voids
9e17ef20-dc8a-5aeb-8487-bd043006e616 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
9f2c99ba-7590-557c-8430-673ac7e7ce5f | note | INSPECTION/TEST METHOD: Visual inspection
e2f3469e-9f67-5033-95b1-7a4094433224 | note | RECORD OF CONFORMITY: This ITP signed off
c6f2dc56-00f1-5a3a-aaab-56372a0aeeab | note | IP
aaf0f5e0-c8d9-593b-b7ba-43aaef90b1bd | note | RESPONSIBILITY: Fulton Hogan Engineer
145ff878-eef1-5dad-b0e9-b6fb390a3d25 | textbox | Date Completed:
1a0b6e06-10b6-4f93-bc5f-7e57634e7891 | checkpoint | 2.11 - Record location of each batch
ac5a70bf-b8a8-5326-bc88-8fa75edbd284 | note | FREQUENCY: Each concrete pour
ed1f0d35-040e-56ee-8dbd-4d6c54469f45 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
ed5cdaac-b529-5a01-9331-7e5413c0abce | note | REFERENCE DOCUMENTS: CE-019-ST-0033
d11e68a8-6bf8-5ac5-a917-1644ff3a9d3e | note | INSPECTION/TEST METHOD: Checklist
be03f9c8-e730-5227-a432-6016d190a0e6 | note | RECORD OF CONFORMITY: This ITP signed off
1a3467fe-58c3-51c4-9e87-9eb434cf15ee | note | IP
a0c3f4d3-f6a4-51e5-9ed5-c2dc1236bc7f | note | RESPONSIBILITY: Fulton Hogan Engineer
2e99c1d6-c3c0-5530-a0c2-a6802d7110bd | textbox | Date Completed:
becc21b1-ceb9-4418-aa74-644241e19c24 | checkpoint | 2.12 - Curing
3f8f2d4d-354e-5182-b897-b60e32865cc4 | note | FREQUENCY: Each concrete pour
4729015b-e57e-5c50-ab06-a1e81f4c11c3 | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming
1205bdef-7f37-5324-ba72-9e064244e4e2 | note | Concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (Concrete to surface).
c7cc748e-de7d-59ce-b67f-3714eeb51151 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
4d10fc7d-ad76-57a0-ad4c-d97d55eb7534 | note | INSPECTION/TEST METHOD: Checklist
bbbbf519-c6ce-5522-beee-4e6b0c6bfb00 | note | RECORD OF CONFORMITY: This ITP signed off
e0495389-9f3c-53f3-b39d-1b744b519214 | note | IP
0f5c7335-8ed5-55c9-822a-941bd33c4640 | note | RESPONSIBILITY: Fulton Hogan Engineer
3fccf8a6-8e27-5461-a658-d73212281cee | textbox | Date Completed:
e1306be6-50f6-4dde-a1e5-f90a65680b32 | checkpoint | 2.13 - Tolerances
5d7ac8c6-2daa-5f26-a0c5-19813130b1bd | note | FREQUENCY: Each concrete pour
0e73cf87-17ae-5e55-8f2e-40561a0af132 | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
b8d278a0-d66e-5bb7-8e50-68b4be681fba | note | Plan dimension of slab +10,-10mm
24594932-2d14-5681-975a-4d33369afe96 | note | Thickness of slab +10,-10mm
d0966fdc-fd4e-5acc-aa40-8289626a7ba4 | note | Cover to reinforcement +5,-3mm
a49151c7-37d7-5558-a336-7ffd745f35bb | note | Finished level of slab +3,-3mm
5ce53748-897a-5d74-a6c6-90d853c31636 | note | Foundation level of slab +0,-20mm
77686c58-859f-5516-b0ef-4cff54bb2969 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
2e73a78e-0cf3-591f-b00f-25919afef0a1 | note | INSPECTION/TEST METHOD: Checklist
1a7e3e41-09dd-55e7-9153-deef1b4ed9d3 | note | RECORD OF CONFORMITY: This ITP signed off
0903f12e-0075-5a34-8d15-bc1932e93d64 | note | IP
a1a9b94a-1518-5ea4-954b-ed5c1d79a4de | note | RESPONSIBILITY: Fulton Hogan Engineer
6f6e6220-b363-59e0-ba57-dd430d6e9a1a | textbox | Date Completed:
a0bca0b6-9fa8-4d36-9d6a-a3a9bc4ff942 | checkpoint | 2.14 - Slab finish
d3b36911-b163-52a8-9baa-c1f5f7f43a9f | note | FREQUENCY: Where applicable - if track is Type 1 structure
abc8befb-4ca7-57f5-9474-9a0c31f0212f | note | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities. All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections.
48a2f81c-556a-5be4-91a4-6e833833c8c0 | note | A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C.
c9b3c88b-5322-579f-8c4d-2c072a9458ab | note | The slab surfaces shall be broomed to provide a non- slip finish.
01579e79-f3a1-5660-bb58-004f150e4644 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
87ed8d9b-3b7d-5519-ac73-e39f7d3cb86d | note | INSPECTION/TEST METHOD: Checklist
a1526ff6-5af9-5067-b3ba-ca21fe997d40 | note | RECORD OF CONFORMITY: This ITP signed off
d4bdb06c-342e-50c4-80e4-9c7b6d78975d | note | IP
a1e03b47-f3a6-5145-9c8a-bc28c1f076a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
f0f41690-eafc-5958-93a1-de52182c0dc0 | textbox | Date Completed:
bb8c182e-c8e8-4e0b-9aef-cb20e89cd0ae | checkpoint | 2.15 - Post Pour Inspection
7cc1f174-4ba2-5ab6-b6d3-31e6893fd9ca | note | FREQUENCY: Each Lot
ddae189f-952b-558f-a474-eb2d2b7d10ab | note | ACCEPTANCE CRITERIA: • Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
b43f74ea-e40a-51b9-8a9d-a5896ec00ee0 | note | Ensure no defects are present in slab
0c14ab92-abc3-5d8b-b053-fe9581c071ca | note | Complete Fulton Hogan Post Pour Checklist
43608c17-a3bc-5364-b8bb-3ecf34f13d07 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
57cf9234-707f-5ae1-ae49-4d7a10d85bb5 | note | INSPECTION/TEST METHOD: Visual Inspection
02fa2d51-8844-528c-9d45-e27dc9d7c8d4 | note | RECORD OF CONFORMITY: Post pour checklist
5d3ef81b-e998-5d4b-bb79-4303d236a702 | note | IP
00006a23-488a-5239-89bb-6cb62837bff0 | note | RESPONSIBILITY: Fulton Hogan Engineer
2b7741f5-0dfd-5c63-8618-31604700b047 | textbox | Date Completed:
cb652dcf-ad5a-4982-9db4-f0865dbf0643 | checkpoint | Final Inspection
a85b2083-49c9-593c-905c-2d1b35e0cb24 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
03facfaa-e37c-5e08-8a88-8c3c7ab055b5 | textbox | Print Name:
aa29a5da-bd80-5f5c-b6c2-688a457dcfcf | textbox | Position:
bccc0b8b-2322-5347-a8e9-065cce305ec4 | textbox | Date:
ef9adb73-4025-4c46-b76c-9fd74476ae5e | checklist | ITP-009 - Site Survey |  | ITP-009 - Site Survey
27d38ee6-7096-4ac2-a0d6-39853269658e | section | Preliminary Works
958b804e-2684-4468-bef7-5939180f8782 | checkpoint | 1.1 Check for Correct Documentation
ff6ace04-9922-546d-8976-3e06dc5ee2bc | note | FREQUENCY: Prior to Commencing Any Activities
60129060-88e2-5013-8ff1-448c1ec17ca0 | note | ACCEPTANCE CRITERIA: •Ensure that all employees and subcontractors are using the most current and updated complete set of drawings
7e1bbb17-09b5-58ee-9024-bdacb5168d9f | note | REFERENCE DOCUMENTS: Design Drawings and Registers
27c69a3f-4567-5811-9a9a-1ba7e2999558 | note | INSPECTION/TEST METHOD: Visual Inspection
2ac2d28a-8b83-52ef-b5be-fa191013505c | note | RECORD OF CONFORMITY: This ITP Signed off
db8480bc-a597-58b1-ae1a-7d8acc0c0eaf | note | WP
86a70e5d-98c3-5dbd-899d-ce9e77937000 | note | RESPONSIBILITY: Fulton Hogan Engineer
a70d21b5-cceb-550f-99e4-646b8b8f1d95 | textbox | Date Completed:
56b8f698-22bf-46ac-b13d-32951dafca24 | checkpoint | 1.2 Implementation of All Measures and Controls
c1cd39ed-c47a-52fe-a314-dd4a369c79ec | note | FREQUENCY: Prior to Commencing Any Activities
6d5ea1cf-06f6-5c57-b5b8-f3207b68b1a3 | note | ACCEPTANCE CRITERIA: •All necessary measures and controls are implemented, including: SWMS, WP, TMP, EMP, PSP, PMP and QMP
4ea6ee31-211b-5fae-8c7e-810064e214c8 | note | REFERENCE DOCUMENTS: SWMS, WP, TMP, EMP, PSP, PMP, QMP
eeeb9014-3641-5e03-8e56-9c325ea6864b | note | INSPECTION/TEST METHOD: Visual Inspection
93a08f4a-41db-5d26-9b1c-074ef7b7133b | note | RECORD OF CONFORMITY: This ITP Signed off
457921e1-5219-50d8-b6ac-2c6a5ba3527b | note | WP
2715a98e-dabf-5342-869e-0f7b86f95ea3 | note | RESPONSIBILITY: Fulton Hogan Engineer
3796228a-6e73-5600-a5f7-4c947e7d597b | textbox | Date Completed:
71c9df2a-1cf5-4f55-8898-1ace8a255d20 | checkpoint | 1.3 Confirmation of Design Drawings
c7766e33-6cdd-5013-8390-2fc8e141e342 | note | FREQUENCY: Prior to construction activities
a013b26a-5341-5d88-ba78-08a90af967bd | note | ACCEPTANCE CRITERIA: •Surveyor shall validate RL points, kerb, pavement, platform and track dimensions, measurements and levels specified in design drawings based on bench marks and control points specified by superintendent •Superintendent shall be made aware of any discrepancy between design and actual values
eaac8b96-084a-5bfc-8db4-a9e45c241dbc | note | REFERENCE DOCUMENTS: Design Drawings and Registers TS 1313 cl4.2.5
45ceb344-1bf8-51c6-bbd2-cc90944c93dc | note | INSPECTION/TEST METHOD: Verify
02128d6e-618d-5b72-8cd3-1312eb548425 | note | RECORD OF CONFORMITY: This ITP Signed off
8258a5dc-8b3f-59a2-babe-f33d1c7b54e3 | note | HP*
1a5ed7b3-c3c0-57e0-909b-b79c474ee4ac | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
77e89f07-c37c-526e-bf0c-1b3d9533fe77 | textbox | Date Completed:
2febd351-12b5-4af4-94d9-e341bfecfdee | section | Construction Works
89ec485e-d888-469f-917f-68e738907db4 | checkpoint | 2.1 Set Out
778ed5bc-3017-55e6-8370-02eab34ce32a | note | FREQUENCY: Prior to start
33a63fee-2847-533c-8538-c54a0e862ef7 | note | ACCEPTANCE CRITERIA: •Tramway track shall be set out to an accuracy of +/- 3mm, based on bench marks and control points specified by superintendent design drawings
8cb9ba7e-ae21-5a6e-ab91-a8a6a83a3a84 | note | REFERENCE DOCUMENTS: VRIOGS 005.2 Pt1 cl4.0
d521a8f7-4b42-5d8f-ae67-8b95f357bdac | note | INSPECTION/TEST METHOD: Visual Inspection
a87a3f09-3a2b-517c-a64f-ec2e70d8e8cb | note | RECORD OF CONFORMITY: This ITP Signed off
4fa5fdf7-337d-5206-9e00-016933d7a618 | note | IP
bbe692c8-b801-5f56-b645-89e7afdcb770 | note | RESPONSIBILITY: Fulton Hogan Engineer
ce0de9f7-cfba-505f-8584-8eda970eb2b5 | textbox | Date Completed:
2d9a987b-76a2-4856-a98a-cb2bc7586075 | checkpoint | Final Inspection
05f25f34-af5e-594a-a75b-bf1401819c15 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f66262ef-f319-5007-b503-3ead941c7393 | textbox | Print Name:
6591a265-f154-5da5-81e1-8318aa7efc4a | textbox | Position:
6cc3d668-f717-5684-9642-64a5624e2de5 | textbox | Date:
d03f0845-e8cd-47ce-8852-ec86c20aece8 | checklist | ITP-010 - Kirby Welding |  | ITP-010 - Kirby Welding
6ce9e30f-12bc-45cd-9aa0-c09a091c93be | section | Preliminary Works
051f4121-146b-4d86-a108-0be9f86526f4 | checkpoint | 1.1 Check for Correct Documentation
c4135c7d-f290-5049-9631-86d7201e6f4e | note | FREQUENCY: Prior to Commencing Works
ad3b879e-b855-5f56-99a8-13b7e096f41e | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
cdeef963-9471-5f44-8d02-c41b531e3b95 | note | REFERENCE DOCUMENTS: Design Drawings and Register
6de449b4-fb10-5b05-ba4e-a4bc02977b0d | note | INSPECTION/TEST METHOD: Visual Inspection
e50a247c-39a1-553f-848b-0bc66b04ddb4 | note | RECORD OF CONFORMITY: This ITP Signed Off
7e8acf33-25ec-5d0d-8ab1-4c24fce13230 | note | HP*
1d0ca30a-a16f-5f72-b401-a7e636a607eb | note | RESPONSIBILITY: Fulton Hogan Engineer
149c0676-5a9d-5ea8-8273-bf05c5cd6d91 | textbox | Date Completed:
5771f382-d89a-4d14-8e9a-82b6b134021a | checkpoint | 1.2 Welders Qualifications
cfb90772-86e5-541b-8d67-8450eec546ad | note | FREQUENCY: Prior to Commencing Works
f0cce697-1374-5bd6-a950-64e893efa9f7 | note | ACCEPTANCE CRITERIA: Welders shall be trained and qualified for the brand and each type of weld used, e.g. standard gap, long preheat, short preheat, junction etc. Certification shall be provided to and approved by the Superintendent prior to commencement of welding.
00207a98-7ecd-567e-a888-429e8b150190 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C
e77cd084-179f-5674-80ad-e016b96493e2 | note | INSPECTION/TEST METHOD: Verify
fb3c56d2-4f35-5a76-92c1-abccbc18a108 | note | RECORD OF CONFORMITY: This ITP Signed Off
b3f2a0ec-bccc-5d29-8524-816665c1a93d | note | HP*
bb4df4b9-0bd1-5566-ad93-64848a82cf41 | note | RESPONSIBILITY: Fulton Hogan Engineer
afedd8f0-9aa0-59c2-bdc0-e76b2a2bce6d | textbox | Date Completed:
41f3b9be-f7da-43c2-a73f-9d4d28c8b696 | section | Construction Works
b5c2963f-0605-4e1d-84e4-1495201687ff | checkpoint | 2.1 Cutting Rail Ends
f0722c4e-e6e1-5b5c-8e14-f8e50ecf0147 | note | FREQUENCY: Each Weld
4be6dc8d-0666-59b9-a64c-b141b5d6d5b2 | note | ACCEPTANCE CRITERIA: Rail ends shall be saw or friction cut. The cut ends of each rail shall permit butting of the rail heads to within 1 mm across the full head of the rail. The prepared surfaces shall be visually inspected for cracks and reground if any are detected.
11c1640d-f60c-521a-874f-0753f7e36699 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.4.6 & Appendix C
b90a7230-d04d-5b1a-af0c-cda3a6b0cbac | note | INSPECTION/TEST METHOD: Inspect
7a36dbbc-db97-5c81-92f1-bb67330c58b5 | note | RECORD OF CONFORMITY: This ITP Signed Off
0276a335-eec4-5fa7-b0fb-8aff26bedec4 | note | IP
49f547d0-fe16-5599-9c9b-f8ddd084b264 | note | RESPONSIBILITY: Fulton Hogan Engineer
b0b63861-3f55-5156-9a67-7b630c849482 | textbox | Date Completed:
57b8639d-0bc6-431b-b2b3-14a40a05da14 | checkpoint | 2.2 Butting and Aligning Rail Ends
2efc677b-d2d8-5702-8dd5-e3fba854c8af | note | FREQUENCY: Each Weld
8baaaf2a-f69c-5243-9ecb-c8bc6eeed8a9 | note | ACCEPTANCE CRITERIA: Rail ends to be welded shall be butted together as closely as possible, preferably with no gap between rail heads. Care shall be taken to ensure that the rails are not pulled together excessively, forcing the feet of the two rails together and producing a peaked or high joint. Rail ends shall be butted and aligned, and assembled with base plate and spacer blocks, if applicable, prior to commencement of pre-heating.
5f96e2fb-6888-5aec-835e-ca46b76ed0c2 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
8ee5942f-e4c7-5a25-8e84-b5b57ff757e8 | note | INSPECTION/TEST METHOD: Inspect
0e1d7fcb-ce36-5f6d-b1b1-3bbdb179c93f | note | RECORD OF CONFORMITY: This ITP Signed Off
e2fa2f17-147b-52e6-b391-4064b5de6f17 | note | IP
36bd4369-06f9-5086-b685-6d1d3d11623e | note | RESPONSIBILITY: Fulton Hogan Engineer
002c4ff9-619b-5084-81ee-fbf05e1795ab | textbox | Date Completed:
cb88010c-b72e-4a28-85f6-9e8491681ac0 | checkpoint | 2.3 Preheating
6c62c2fe-d42a-5a9e-97d9-5572beb6a080 | note | FREQUENCY: Each Weld
b3eb1232-aea8-57cd-acd3-35420a2a38cf | note | ACCEPTANCE CRITERIA: A correctly adjusted, suitable oxy-LPG pre-heating torch shall be used. The preheating torch shall not be applied closer than 30 mm to the rails being pre-heated. Both sides of each rail end shall be evenly pre-heated from the rail ends to150 mm beyond the rail ends. Pre-heating shall be confined to the top surface of the foot of each rail and to half the height of the web. Preheating shall be such that during welding, the foot and web of the rail shall be at a temperature of between 270°C and 350°C
1a4a7a41-ba0f-5204-8017-19d83a96b559 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C
4da2f7ab-9e37-50d4-a862-0f5800769bb9 | note | INSPECTION/TEST METHOD: Inspect
94b02f7c-a747-567d-bc47-3b7fae7de6ce | note | RECORD OF CONFORMITY: This ITP Signed Off
6d9288b0-3412-55c3-9cf7-0344e447054b | note | IP
67418c94-9042-54f6-a518-feb429ea44be | note | RESPONSIBILITY: Fulton Hogan Engineer
81132e57-781b-5205-bf2a-cbcff8314f5d | textbox | Date Completed:
adf58520-86c4-47d1-a243-43a5f4a40ec7 | checkpoint | 2.4 Welding
8f4cc3d2-a15a-518b-9b41-956740ad4ca5 | note | FREQUENCY: Each Weld
1829aff1-1535-5897-8776-d50c66b5017a | note | ACCEPTANCE CRITERIA: Rails and components shall be clamped in position prior to welding. Welding of the joint shall be carried out as a continuous operation. A disruption to the procedure may require additional preheating. All weld ends shall be welded using an overlapping back welding technique over the weld for a minimum length of 20 mm to ensure that all craters are fully filled to the full cross section of the weld.
90fcbbc0-3804-5730-879c-5e8247854d51 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.9 & Appendix C
d9d08cf6-bbca-52d4-b0ea-fab0a1821a3c | note | INSPECTION/TEST METHOD: Verify
332d1979-a0c6-5e73-b709-32ed40318008 | note | RECORD OF CONFORMITY: This ITP Signed Off
b8e0de61-3036-5ade-ac71-a095d76dcdb8 | note | IP
962774ca-7607-56dd-b744-5c514ceaa794 | note | RESPONSIBILITY: Fulton Hogan Engineer
95e02d87-edb1-5bae-8a44-6801b27caa5e | textbox | Date Completed:
caf878d5-2a10-48be-96e6-cc7c32c804a6 | checkpoint | 2.5 Cooling Weld
be7c2430-8121-519c-9176-0d2b514e2c14 | note | FREQUENCY: Each Weld
744989a2-860a-5d48-96a8-2048873e0cf9 | note | ACCEPTANCE CRITERIA: The welded rails shall not be permitted to cool rapidly. Heat blankets shall be used to cover the welded portions of rails (i.e. web and foot on each side of the rail ends. The blankets shall extend a minimum distance of 300 mm beyond the extremities of the welds, i.e. minimum length 900 mm. The heat blanket shall remain in place for a minimum period of 15 minutes after completion of welding.
6a7e27bb-4680-55ad-9d4e-18db254b5370 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.9 & Appendix C
d4390b9d-dc49-54e2-8556-48dc7ff14243 | note | INSPECTION/TEST METHOD: Verify
7f204b56-e8eb-5c93-8177-83f965714724 | note | RECORD OF CONFORMITY: This ITP Signed Off
877bc161-443b-5464-92f0-4387635bf43f | note | IP
8b5d4aa0-58c0-53d1-8b4a-0356b18cb3e0 | note | RESPONSIBILITY: Fulton Hogan Engineer
f72a56f2-77ec-5891-a3a6-f12777ca2c82 | textbox | Date Completed:
c027ee32-7767-46d8-8976-f32f7b3be326 | checkpoint | 2.6 Grinding Weld
b6cbf54e-f1f9-51d9-9946-db15e1d8b585 | note | FREQUENCY: Each Weld
8464a60e-9d86-552f-bba3-7641318a691a | note | ACCEPTANCE CRITERIA: Grinding of the rail head, as applicable, shall be performed only after the rail head has cooled to below 50°C. A rail profile grinder shall be used to grind the rail head weld. A spindle (straight) or disc grinder shall be used to grind the rail check and groove. A 1 m straight edge shall be used while grinding the rail head (wheel running surfaces) to ensure a good straight surface and profile.
7175a633-6788-56ea-ae7e-681b0b57f0f2 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
8a597317-5d3c-5c47-8278-e7d90f64d1c6 | note | INSPECTION/TEST METHOD: Verify
3a4815cb-1c4b-51e4-8933-360072aacf19 | note | RECORD OF CONFORMITY: This ITP Signed Off
d975281f-616d-58b9-8e9d-7fbd653604c3 | note | IP
4e0d9898-d90d-578f-8a71-994e8fc98f2c | note | RESPONSIBILITY: Fulton Hogan Engineer
24c64d01-6b5b-5492-bd39-0e568e1209bc | textbox | Date Completed:
34d1791a-5010-4168-aa9d-ce9e84763fab | checkpoint | 2.7 Flushness of joints
3f8312d4-d8cf-5673-a90b-129972d94155 | note | FREQUENCY: Each Weld
84cb6a30-8bc8-50e2-94a7-9da79d06186b | note | ACCEPTANCE CRITERIA: Misalignment of rail heads on the running and gauge surfaces, due to different amounts of rail wear, shall be rectified by grinding. The slope of transition shall not be greater than 1:25. Misalignments of the groove and check not exceeding 3mm shall be rectified by grinding. The slope in transition shall not be greater than 1:10. Any grinding required to make joints flush shall extend to 500 mm each side of the joint
1ac262bc-c6fd-5c9f-aa4c-6c6cea28f828 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
a38b15e8-6693-5608-b52d-ed696ee3a8f2 | note | INSPECTION/TEST METHOD: Verify
59fedffe-b35e-5351-b462-3c69579240fa | note | RECORD OF CONFORMITY: This ITP Signed Off
b9bd3c31-63d9-57fb-82f0-a9190eccca59 | note | IP
c8e29fbd-a43a-536d-8cf1-15c4eb9f61d8 | note | RESPONSIBILITY: Fulton Hogan Engineer
be68efcf-f874-5b48-9ae0-5c03472fd780 | textbox | Date Completed:
6f153477-065b-4671-ac37-2cb8a80467f3 | section | Testing
d9408c89-b47c-4bf2-886c-b4e43a7be02b | checkpoint | 3.1 Weld Review
99a7f5de-dbd8-56ed-9ff7-d183c46bf2d6 | note | FREQUENCY: Each Weld
6676ea1b-79f1-5b7b-8d15-49bc1a1b226e | note | ACCEPTANCE CRITERIA: All welds shall be inspected by the Superintendent & Fulton Hogan Engineer; Unsatisfactory welds shall be cut out and replaced
4fe24971-21f1-584c-b853-e2bbc77dc753 | note | REFERENCE DOCUMENTS: Works Procedure
6540be9c-be9a-52ba-99c2-fd6a965fe788 | note | INSPECTION/TEST METHOD: Inspection
b2a6ae53-e3d5-5de0-94b8-a79ff9ff6ff5 | note | RECORD OF CONFORMITY: This ITP Signed Off
59dd73a0-f399-5e16-9eee-167b3970abd4 | note | TP
2004bc84-3009-5664-9660-1e39b03304ec | note | RESPONSIBILITY: Fulton Hogan Engineer
8ba95dd6-8f3b-5aa9-a18b-7502d08d0c08 | textbox | Date Completed:
1222cb7a-e022-4002-a00a-6b6987c55519 | checklist | ITP-012 - Signage Installation |  | ITP-012 - Signage Installation
a3504402-fb6e-4be1-9968-c9e4dc246c89 | section | Preliminary Works
59218fd9-56ec-447b-b971-319d8263f4f4 | checkpoint | 1.1 Check for correct documentation
5b55b167-d026-501c-8827-496e53cc2c99 | note | FREQUENCY: Prior to commencing any activity
a2bbe5c2-e40a-516b-8d6a-5bd338064f3d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
1dc872bc-603e-5c1f-8c2c-51ab396f3a31 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
d047aa87-a871-54e9-bba3-fbcef3254131 | note | INSPECTION/TEST METHOD: Visual inspection
997f144a-5452-5f6a-8496-46a3f5935a99 | note | RECORD OF CONFORMITY: This ITP signed off
c3ff9d1e-afe6-57f5-9f09-5fb7c9914da2 | note | WP
073c5a2e-9218-5b2e-a926-e7f0815dc495 | note | RESPONSIBILITY: Fulton Hogan Engineer
c246c574-34b4-5aa5-a1a4-0af831e4032f | textbox | Date Completed:
5a9a42c2-574c-49dc-8407-3a1c7c2b823b | checkpoint | 1.2 Implementation of all measures and controls
54d00be6-a510-5435-b05f-ef3b2bf18253 | note | FREQUENCY: Prior to commencing any activity
4451c61c-67b3-5309-bf9d-998b0a8153ee | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
0b24013b-7218-5674-a8b9-d5ddb4ec8cf1 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
35e74f4f-00d5-55c2-9ea8-9fae5c02b358 | note | INSPECTION/TEST METHOD: Visual Inspection
514978bb-6d92-5132-952c-f741fcb0a156 | note | RECORD OF CONFORMITY: This ITP signed off
7a686923-c73a-549b-9038-134e6f733e96 | note | WP
b580089b-ab1a-5576-97b1-86c2a82b4eb3 | note | RESPONSIBILITY: Fulton Hogan Engineer
f1adc6a5-3426-5078-a2f6-954f75314887 | textbox | Date Completed:
ff943067-b05f-430d-86e6-77d43279198e | checkpoint | 1.3 Signage Conformance
d6dfd112-7563-53ee-8ee0-b15d67538f0e | note | FREQUENCY: Before commencement of activity
757d46d8-9e93-5d69-9982-0547b32395a6 | note | ACCEPTANCE CRITERIA: Ensure sign size and image correspond with contract drawings and meets specification
838ef221-7600-57a7-b5e1-afc9721a8221 | note | REFERENCE DOCUMENTS: Drawings AS 1742
da6f0f2a-80a0-563f-8197-093ca535beff | note | INSPECTION/TEST METHOD: Verify
c710acb3-4ef5-50a4-bc63-aa4dd73fad7b | note | RECORD OF CONFORMITY: This ITP signed off
67ffedcb-e52d-5de5-a61d-17ed98f0fc0b | note | WP
2ea98616-5bd9-5484-ade0-860f258b5af3 | note | RESPONSIBILITY: Fulton Hogan Engineer
1aa05846-88a1-5db5-90f4-a3d91d1d4b5f | textbox | Date Completed:
f315cbe4-cfac-4c52-88c4-b0f5a40eb144 | checkpoint | 1.4 Service Identification
d3a40923-9164-54e3-a8be-1127e62894e4 | note | FREQUENCY: Prior to start
2859eaec-d183-5b60-abbb-1971ffaa4507 | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
4921dd9e-fc81-5235-ae02-d9a75879af53 | note | REFERENCE DOCUMENTS: DBYD
a2ca2c7c-6e74-529d-bb4c-98bc0c8513e1 | note | INSPECTION/TEST METHOD: Verify
96810005-6e0c-525b-a740-d4dd959435c5 | note | RECORD OF CONFORMITY: This ITP signed off
0165270b-667e-509e-95e9-15923e4bcebd | note | WP
9c78692b-6fd9-5653-b8ff-89ef15177f05 | note | RESPONSIBILITY: Fulton Hogan Engineer
8548e621-9ed6-5bc4-b52b-76359d87bf4c | textbox | Date Completed:
0442a90f-cd5e-4d48-8c8f-757f335c94a5 | section | Construction Works
f12adca8-db8f-4b1d-a87c-2799d8dc3816 | checkpoint | 2.1 Setting Out
490ef352-e2bb-5f23-82af-bc35fd975863 | note | FREQUENCY: Prior to start
d5c39923-eaa4-5bf7-8cf3-2cf39be4afb2 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
2d32d08c-77e3-5317-84f7-3323793b1ca4 | note | REFERENCE DOCUMENTS: Drawings
23e504d8-7158-531e-b6ed-55efe689fe60 | note | INSPECTION/TEST METHOD: Visual Inspection
2c7080b6-372e-554e-9702-97060ba4aa2e | note | RECORD OF CONFORMITY: This ITP signed off
91388a12-4cce-5e5f-9587-6e06242aaa5a | note | IP
8be419db-8384-5fc3-8b32-6e7c7b0259d6 | note | RESPONSIBILITY: Fulton Hogan Engineer
edd7d644-0a85-5a17-b369-a046513845d9 | textbox | Date Completed:
1c3cbc98-4927-40b4-ae31-81834e3636be | checkpoint | 2.2 Signage Install
001a8804-fc11-5e93-8de4-fad871ab7dba | note | FREQUENCY: Each Sign
8ce4d4de-dfc4-54f5-844b-cbae46592b04 | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position. Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
89cc30a2-29cb-55e3-a273-89117f2ed837 | note | REFERENCE DOCUMENTS: AS 1472 TS 1313 Drawings
399a2021-dcae-51db-8557-991ba0b867d8 | note | INSPECTION/TEST METHOD: Verify
c0eb98ee-56f6-53ea-a83a-8398da7e20fd | note | RECORD OF CONFORMITY: This ITP signed off
8ad17730-f3f4-5e2e-9204-44480e88a5f3 | note | WP
54413ac4-6ccd-5ddb-8472-611ddfaed9dd | note | RESPONSIBILITY: Fulton Hogan Engineer
7e44db39-f4a0-54c0-a2d2-e71983c52afd | textbox | Date Completed:
44b3c2fa-3d72-4db4-b802-56e8a2427706 | checkpoint | Final Inspection
a044ca53-f4b0-5c8d-acdc-77469c77b6a4 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
9fe4154e-b069-5888-9cfe-afd49da76428 | textbox | Print Name:
c90e1941-725a-5840-a525-5d9b21ac2cde | textbox | Position:
89a9edd3-9241-5394-bab0-064c79dd5fee | textbox | Date:
aaa6dbf5-cf25-4126-9ef5-dd082805c45c | checklist | ITP-014 - Bluestone Kerb Installation (MCC) |  | ITP-014 - Bluestone Kerb Installation (MCC)
2823aaee-1362-4792-93f9-179a7c3f7d3b | section | Preliminary Works
7c0e8567-8c47-48d5-99d9-faceb15a0103 | checkpoint | 1.1 Check for Correct Documentation
88036de9-7ada-5464-85b7-b679c7e3891e | note | FREQUENCY: Prior to Commencing Activity
b2e6c174-701c-571c-b0a8-4c8e5c56b2d5 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
38302d59-ddc4-595f-ba4a-9b2aa8397ce4 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
751797ce-b577-5ce9-b69a-db4d45c15c41 | note | INSPECTION/TEST METHOD: Visual Inspection
cce78733-5588-50de-be57-50ac3789ce18 | note | RECORD OF CONFORMITY: This ITP Signed off
49c3a646-1df9-5add-8228-e5d47f6900e5 | note | HP*
de51f12c-4f08-5e02-9e77-a6f4f6da252b | note | RESPONSIBILITY: Fulton Hogan Engineer
34bbfe26-e321-57c4-90a9-ee8b55c5af20 | textbox | Date Completed:
7320f1d3-a27f-43e8-b34f-de1de9ba4123 | checkpoint | 1.2 Implementation of all measures and controls
361113f3-84fb-5b87-82eb-4c9b21544828 | note | FREQUENCY: Prior to Commencing Activity
708cbc8d-fb46-5a50-8943-1ba09fae27d4 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
cb7fb956-6921-5cba-8bb0-d65aa8d29927 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
413db448-f729-5032-9a80-1b844c1929e6 | note | INSPECTION/TEST METHOD: Inspection
f8d6e1f3-caa6-5ddb-9083-dddb67d69860 | note | RECORD OF CONFORMITY: This ITP Signed off
a8bde62d-497b-5cb1-8435-e3534d0c440c | note | HP*
640d0896-6e76-57fb-8c09-feb4c2d5739b | note | RESPONSIBILITY: Fulton Hogan Engineer
3be7282b-72d7-5eea-a59c-f62a599a390c | textbox | Date Completed:
1a1d61a1-7b17-420d-a14d-96fbb268e9b9 | checkpoint | 1.3 Existing Bluestone Kerb Demolition
30f6f458-e137-5c4d-ade4-8e5225257661 | note | FREQUENCY: Each Lot
da606d4e-055f-5ae7-b652-9ffe5331fb9c | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone Bluestone shall be salvaged and re-used in new kerb alignment
1fefcf1c-4ea7-5dd8-9efe-86247802a13a | note | REFERENCE DOCUMENTS: Work Procedure
9bc7bbd8-778b-5f1a-9ab6-6c20bea90c83 | note | INSPECTION/TEST METHOD: Inspection
0e67b9b0-15e3-588d-ae43-daf61b8c28b1 | note | RECORD OF CONFORMITY: This ITP Signed off
3d0bc8eb-1a34-5568-b4f3-d7d925a16179 | note | IP
c848906e-758c-5263-9434-5e814428b2fd | note | RESPONSIBILITY: Fulton Hogan Engineer
a95c0d53-c25d-5a5f-9e7f-5f054228c9aa | textbox | Date Completed:
312baa09-c14c-46dd-b295-5e2f3e9df60c | checkpoint | 1.4 Setting out
e94980ea-8d29-5e02-a6a0-30f13f375372 | note | FREQUENCY: Each Lot
61ee84b1-729f-59e5-b4da-db59ee653aa8 | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans Alignment of new kerb shall be marked out using string line
bd4ed746-87f7-5573-8073-bacccf93399c | note | REFERENCE DOCUMENTS: Work Procedure
e092313f-9c6b-5af0-ae07-0f46fdfecaea | note | INSPECTION/TEST METHOD: Inspection
fb78a4dd-1947-5d6e-a3cd-4bea09650435 | note | RECORD OF CONFORMITY: This ITP Signed off
13a0e05e-4387-5bad-a8d9-05172c62f96c | note | HP*
b05f8309-8deb-513a-bdee-00a2142f20cf | note | RESPONSIBILITY: Fulton Hogan Engineer
5fad23b2-527d-5612-8adf-b6bc51511eb9 | textbox | Date Completed:
25305b7f-a4e6-4531-90d0-9e9052aef347 | section | Construction Works
d0ad7f30-7d55-4deb-884f-6b6bd19c96f3 | checkpoint | 2.1 Saw cut (if required)
39fe1332-6f05-5e21-9b2e-90531da2a94f | note | FREQUENCY: Each Lot
4ec90fa0-ffcf-5cd2-b47b-6f4803974f8d | note | ACCEPTANCE CRITERIA: Saw cuts shall be made to the following depth for existing asphalt pavements: - Footpath: Minimum 75mm - Roadway: Minimum 125mm Excavate to allow for design heights
e80053f8-492f-5662-9dac-00c4639e56c2 | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 2.0
72df02b5-bb95-5570-b8c3-139f6d3fe936 | note | INSPECTION/TEST METHOD: Visual Inspection
76eb9fca-68a7-5293-8af1-1a93d2a83d5b | note | RECORD OF CONFORMITY: This ITP Signed off
a0fe31b6-91e3-5672-a873-89c2c6cd34be | note | IP
45e26502-b55a-5cdc-9a97-831f2d38e4f4 | note | RESPONSIBILITY: Fulton Hogan Engineer
64f30b8f-88f7-5211-b601-10d285f7b784 | textbox | Date Completed:
212cca58-f25d-47b4-9b81-14f7530aa2e2 | checkpoint | 2.2 Concrete Placement and Setting
6e95ae52-be72-5a0b-8eef-b049d61dd8e3 | note | FREQUENCY: Each Lot
a87ba097-ef71-583f-abdc-d0a38e48478d | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar
c3e08ea0-0658-5c7c-b288-4102345d0539 | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
2b762a49-fcca-50c4-b0cf-331c84caa425 | note | INSPECTION/TEST METHOD: Visual Inspection
c667295e-304e-5fd2-9e6c-288ca9711e32 | note | RECORD OF CONFORMITY: This ITP Signed off
f03124bc-f0d7-523a-9869-5c5379157a30 | note | IP
3b4bc136-1efc-5027-8758-29ac8be0e860 | note | RESPONSIBILITY: Fulton Hogan Engineer
f068f975-84e8-579d-9fd2-e5f0875c84f2 | textbox | Date Completed:
fbfe8fae-f22f-494c-9467-f696f9ae5a78 | checkpoint | 2.3 Mortar Mix
c2488668-22fd-54ca-bd7d-193b1fe5e30b | note | FREQUENCY: Each Lot
ce510f21-dff7-5b9f-99f2-66203e047cbe | note | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following: - 16% cement - 16% stonedust - 67% blended wash sand - 1% lime ready mix grout
d8ac4772-aa1a-5987-81e8-a436bc6ccc95 | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 4 AS 3972 CoM SD 1P 50406
c38262b9-795b-5af8-a5ab-d60fd99d0737 | note | INSPECTION/TEST METHOD: Verify
c3bcea6d-e6bd-55ba-b97d-bec4ed7f55d9 | note | RECORD OF CONFORMITY: This ITP Signed off
599fbdb7-2358-5e0f-a086-cc445fe77c3c | note | IP
0ebbcf15-296b-5d56-bd33-73951a8bb5e6 | note | RESPONSIBILITY: Fulton Hogan Engineer
2db6f630-19e1-558d-a142-dd1bc8fabfad | textbox | Date Completed:
7f422229-6fbe-415d-9265-be7d128b6f38 | checkpoint | Final Inspection
b5c507e6-a4d8-502c-9ba2-49e49291973d | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
21b0693a-3131-59aa-9377-735d5461a9ea | textbox | Print Name:
438dd459-8e7d-5a2e-80cc-7e6f23da0581 | textbox | Position:
956ef8a0-e733-59a2-bd30-02ac69ebb754 | textbox | Date:
c363c2e6-1b72-4efc-aacc-74b399d8031c | checklist | ITP-015 - Energy Absorbing Bollards |  | ITP-015 - Energy Absorbing Bollards
e172fd22-06cb-44ba-8172-b884fd33bfe2 | section | Preliminary Works
36af9d91-ee2e-4bad-b057-7e9ed21d4953 | checkpoint | 1.1 Check for Correct Documentation
9f4f69df-d072-5720-bce3-18d43ae69cc8 | note | FREQUENCY: Prior to Commencing any Activity
1d44aacb-ef88-5260-aef7-c196b15acf73 | note | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
f351a2fb-d004-56f1-bca4-0da3b9ad82ea | note | REFERENCE DOCUMENTS: Design Drawings and Register
0aa4c29f-3be2-50b3-b4c8-f8a4b36afd58 | note | INSPECTION/TEST METHOD: Visual Inspection
efdfe11a-9fb4-51eb-87bc-3df25a98e36d | note | RECORD OF CONFORMITY: This ITP signed off
9b72c6e9-1439-5aee-af89-7847f77b83da | note | HP*
233b1c24-0237-5b79-a574-55e4e7d0900e | note | RESPONSIBILITY: Fulton Hogan Engineer
d5237858-faa4-5dc4-948d-d487d64d946a | textbox | Date Completed:
75824eca-e856-4de3-83ff-0d1a349ccaf2 | checkpoint | 1.2 Implementation of all measures and controls
38b41293-ac5b-58af-aae7-5eaf7571a213 | note | FREQUENCY: Prior to Commencing any Activity
5b764db0-ba0b-5269-8f66-edb9836a1604 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
dd875f2a-fe79-552e-90ba-d3109a820ad8 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
503b4015-7efc-5282-a49b-1e12122f2dfb | note | INSPECTION/TEST METHOD: Visual Inspection
aae83b35-00ab-5779-9504-be57d00e846a | note | RECORD OF CONFORMITY: This ITP signed off
a82a5ae0-a06a-5b9d-9d99-cba2ab3a83ad | note | IP
57439984-5d45-5a2a-8935-af9daebfdf9b | note | RESPONSIBILITY: Fulton Hogan Engineer
d82630c6-39b4-5301-ad86-05c5be65a069 | textbox | Date Completed:
f9a5c7d5-fee2-42cd-b7df-1f9b646d67ce | checkpoint | 1.3 Service Proving
310b8360-2283-58d5-bc5b-4ad38a579b8b | note | FREQUENCY: Prior to Commencing any Activity
659eb53a-0546-5c1d-a74c-fc192fb9a18c | note | ACCEPTANCE CRITERIA: Service locating shall be conducted in form of DBYD and service location
51d6886c-9b3e-5dc9-b52f-703e66043ddc | note | REFERENCE DOCUMENTS: DBYD Service Locator
3da7bbb6-5e16-5375-b114-91ca50519bc8 | note | INSPECTION/TEST METHOD: Verify
0ab53de5-6821-599f-9446-0092238049b2 | note | RECORD OF CONFORMITY: This ITP signed off
a6c79647-ce42-5a78-af67-068648b758d2 | note | HP*
8a3681c6-be37-5594-bc57-0cb2b085355f | note | RESPONSIBILITY: Fulton Hogan Engineer
18477a0a-3d4c-5baf-8b89-40b59560cc37 | textbox | Date Completed:
13be9a81-02f4-4ccd-a262-57793fbe58d6 | checkpoint | 1.4 Excavation Permit
540277f4-580d-595d-a8d1-18229d3536f9 | note | FREQUENCY: Prior to Commencing any Activity
c5cc9e19-28cd-5dce-93d0-60a790e6d11c | note | ACCEPTANCE CRITERIA: Ensure excavation permit has been obtained for the specified tasks
af6bca3d-8ce3-56d7-bc5b-9ed38a087347 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
dc4883ba-38a4-5b69-b6bb-a9ba7784ba17 | note | INSPECTION/TEST METHOD: Visual Inspection
bdd2fca9-92f7-5a0b-89b0-50d8be919953 | note | RECORD OF CONFORMITY: This ITP signed off
d8d8b0d9-f291-5832-be15-0b2dac49a5a9 | note | HP*
9ed95b37-6804-5a34-afa0-194134e0f1cc | note | RESPONSIBILITY: Fulton Hogan Engineer
ffa8b8dc-8600-538a-bcaf-e62c629b380c | textbox | Date Completed:
26848522-0c60-4e59-8c27-9e19938b02e7 | checkpoint | 1.5 Materials
b13102e7-4d36-5218-923a-5c11c326ba75 | note | FREQUENCY: Prior to Commencing any Activity
593d62ec-a13c-5915-bd08-06521e2e41d4 | note | ACCEPTANCE CRITERIA: All materials shall comply as per technical specification Ensure materials are not damaged
72fa504b-f5e3-549a-8332-0e4ddad1618a | note | REFERENCE DOCUMENTS: ASE TS
089f9c08-bd4a-581f-832e-3a1fea469878 | note | INSPECTION/TEST METHOD: Verify
1f4793b8-f897-55b9-aca5-118aa61d26a6 | note | RECORD OF CONFORMITY: This ITP signed off
e35374a2-214a-576d-84f6-dfea4624de7d | note | IP
11018413-7491-51e1-8546-4527280ab0f4 | note | RESPONSIBILITY: Fulton Hogan Engineer
2acae374-2ff7-5781-beef-698295de090b | textbox | Date Completed:
774823cb-bdec-4943-b97c-4c9a47726737 | checkpoint | 1.6 Setting Out
fea5aac5-e7c2-59e0-a0dd-0736823bae40 | note | FREQUENCY: Prior to Commencing any Activity
af697200-8074-53cd-883c-981d10865b5b | note | ACCEPTANCE CRITERIA: Ensure location of bollards conforms to design drawings Mark hole centre position at location
6d3088ce-4520-5ee4-9dec-0684d335221e | note | REFERENCE DOCUMENTS: ASE TS cl1.1
f506c76e-6b9e-5b39-83cd-873be1a6deb4 | note | INSPECTION/TEST METHOD: Visual Inspection
1e42c83e-a96d-566d-a186-a2e9783dd786 | note | RECORD OF CONFORMITY: This ITP signed off
49f6d2a7-1d57-583d-8af7-9ba7ae117d82 | note | WP
33510672-4bef-5f96-8279-4e56adf14fb9 | note | RESPONSIBILITY: Fulton Hogan Engineer
52b275a4-e79f-55f2-be3f-8491ea1bce0e | textbox | Date Completed:
9b0e8397-283d-493b-ac3c-ac3352b91ac5 | section | Construction Works
8655134f-3589-4149-997e-21c6fd8926ea | checkpoint | 2.1 Excavation
00174762-ad83-5413-812c-8b9ead00993d | note | FREQUENCY: Each lot
370141b6-755e-579f-b616-edadc853d745 | note | ACCEPTANCE CRITERIA: Care shall be taken in excavation Hole shall be minimum 600mm dia and 1000mm in depth
17baf021-ffe4-5760-a160-683bc0b82d8a | note | REFERENCE DOCUMENTS: ASE TS 2.2
569adde8-a081-5db3-81ce-2f577e456ac6 | note | INSPECTION/TEST METHOD: Visual Inspection
cef3e82b-1b36-53bf-b7b7-1b4185ce74ef | note | RECORD OF CONFORMITY: This ITP signed off
7ba44245-6fb6-554f-9899-aa7afefdc168 | note | IP
89ff7549-db8c-5d9c-a4fb-8e5c2c2fbc42 | note | RESPONSIBILITY: Fulton Hogan Engineer
41b8231c-27e4-5398-b35b-5af7e88dab46 | textbox | Date Completed:
2045e5aa-ff2e-429d-b9ec-3b257e810bd2 | checkpoint | 2.2 Placement of block
81780c18-7125-548f-af38-61247c8f6c3b | note | FREQUENCY: Each lot
42567b17-2afb-5ff4-86c1-deb15e6007c8 | note | ACCEPTANCE CRITERIA: Block (brick, wood, foam) shall be placed at hole base Ensure base is supported by solid ground, and block is level
63a81bd0-3717-51c2-abe0-51dfbc5d7c7d | note | REFERENCE DOCUMENTS: ASE TS 3.1
b8366b6e-f659-5039-a335-9c635b7d7903 | note | INSPECTION/TEST METHOD: Visual Inspection
9dafcee9-94fa-5f35-b15d-c5010dba393e | note | RECORD OF CONFORMITY: This ITP signed off
20f050ab-a20f-5965-824f-fca56436b3c0 | note | WP
f2667b32-edfd-5396-9a4a-0bbcb81c2028 | note | RESPONSIBILITY: Fulton Hogan Engineer
e1880d0b-4cc8-5fed-bc5d-319e71fe9e8f | textbox | Date Completed:
a0be6617-409e-4f22-ab8b-134c8baf4246 | checkpoint | 2.3 Installation of Cartridge
3b51db39-f597-57fc-9011-6abf4a4c3233 | note | FREQUENCY: Each lot
66f31a3e-9259-5529-ba32-d592314cda8f | note | ACCEPTANCE CRITERIA: EAB cartridge shall be placed on level block
ad5bf4e1-eaef-5dd2-bde3-53088542a664 | note | REFERENCE DOCUMENTS: ASE TS 4.1
83e9fac4-276c-5f21-8901-1208684807c2 | note | INSPECTION/TEST METHOD: Visual Inspection
51741062-097f-56a1-a03e-5d4c91db5954 | note | RECORD OF CONFORMITY: This ITP signed off
5cdb81ea-bc49-50c2-a48f-c5d7e61c7d9d | note | WP
2c3c11b4-273d-5d5d-9ad4-10795cff31d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
ef580cfb-01d3-5468-a57b-682a50142882 | textbox | Date Completed:
07ba979b-1ff8-47f4-aad9-7e9bc6a5dbdc | checkpoint | 2.4 Pre Pour Checklist
0d45af90-3c30-5030-9619-575a3c2dfc90 | note | FREQUENCY: Each lot
a5ea5f5b-b0e4-517c-b44f-fe4eedc336f6 | note | ACCEPTANCE CRITERIA: Ensure minimum clearances are provided, no foreign materials are present, and EAB cartridge is level
837ab97c-4e35-500d-b482-0a6d55035269 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
7f2a32ec-6f0e-5e71-a1a3-0a168ee13b20 | note | INSPECTION/TEST METHOD: Verify
fb7afaa3-2e52-5ac7-8e0f-1645b6c1c51c | note | RECORD OF CONFORMITY: This ITP signed off
72fc6f3f-adeb-545f-ba34-5d90d58fe230 | note | IP
0a02357a-35c5-5605-9720-298398a04cf6 | note | RESPONSIBILITY: Fulton Hogan Engineer
029f52f6-60c5-556e-83aa-9aead1095319 | textbox | Date Completed:
4dafe5d7-c730-44fb-b28b-75f784334d3e | checkpoint | 2.5 Installation of Concrete
0fa2d619-5293-5fdd-9e0d-d17b46a4c8a3 | note | FREQUENCY: Each lot
c54d81ac-2a54-5aa4-8d0b-60b2e871cc06 | note | ACCEPTANCE CRITERIA: 32MPa concrete shall be placed to cover reinforcement cartridge and fill hole Concrete shall be compacted by use of vibrator If surface pavers are to be used, allow 25mm gap from finished surface Ensure cartridge is level post compaction
ab12431b-8fc6-58e4-88a3-30042e5977f5 | note | REFERENCE DOCUMENTS: ASE TS 4.2
cde6445a-577f-5463-8d3a-f4a05b8b0012 | note | INSPECTION/TEST METHOD: Visual Inspection
7e920cdd-8ee2-5061-9a6f-f52227d0c293 | note | RECORD OF CONFORMITY: This ITP signed off
b8a1e715-2e58-58c0-b79a-ebd6d95c7c27 | note | IP
7920b3b1-9149-5fa5-9dd7-73d8fe2ed545 | note | RESPONSIBILITY: Fulton Hogan Engineer
a54fc4b9-8ed7-5948-ac35-24d297e063d7 | textbox | Date Completed:
b39c109d-3d50-4ab4-9af8-36dcc6944d78 | checkpoint | 2.6 Installation of Bollard
a310f99c-5879-5dec-b737-b189b1d3adf0 | note | FREQUENCY: Each lot
62a59d39-edb9-5d22-8801-e762cdef7b11 | note | ACCEPTANCE CRITERIA: Ensure bollard is installed, and bolts are tightened adequately Concrete, pavers or bitumen shall be finished to specified requirements
313f1b56-8b5c-5ddb-a49f-399a63a99d4b | note | REFERENCE DOCUMENTS: ASE TS 5.2
be9a29a2-b3f0-5911-a802-15d84f418bb0 | note | INSPECTION/TEST METHOD: Verify
b05a7ffb-3323-5830-b1ad-f8d1bb6e864a | note | RECORD OF CONFORMITY: This ITP signed off
44bdfa7f-602e-5d44-b4fa-6cdd8b5c121b | note | IP
c07446a4-7162-5267-a3ea-163668b807cd | note | RESPONSIBILITY: Fulton Hogan Engineer
106a18d8-2d93-5d12-83ed-c6efa7cf83ee | textbox | Date Completed:
f8408594-98b4-4b76-8a4b-7d901849428e | checkpoint | Final Inspection
7ddcd1ca-83e4-5c71-b725-aaaaffb44c48 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f8b1c20a-0f3a-5521-952f-4a1243a20c09 | textbox | Print Name:
2631b7fc-a95b-5d75-98a0-468fcabd2099 | textbox | Position:
dce930d2-37dd-5911-9be8-198c0c293b8e | textbox | Date:
4021f14a-48fd-40a8-acd1-152d16690d08 | checklist | ITP-016 - Platform Bluestone Kerb |  | ITP-016 - Platform Bluestone Kerb
80341959-40c4-4fad-b47a-fe6dbfbb360b | section | Preliminary Works
d0acd62d-23cb-49de-ac05-f87f51002f72 | checkpoint | 1.1 Check for Correct Documentation
a2548de4-5c7a-5e89-9e80-2d7280378a5b | note | FREQUENCY: Prior to Commencing Activity
442d5e1e-9fd7-5e37-950e-55fcffb2e3e1 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
35505b02-60af-5afd-b61f-c19eeca0be5c | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
9143e769-18d4-5f6c-9742-36481ea6b2e9 | note | INSPECTION/TEST METHOD: Visual Inspection
d039153c-c0d3-5735-ae27-aa3fa69c3def | note | RECORD OF CONFORMITY: This ITP Signed off
cb8db0b0-e55a-5f2e-82c4-49ae13dfb24f | note | HP*
d92a7554-2a30-5006-b8cd-62f895881157 | note | RESPONSIBILITY: Fulton Hogan Engineer
5f3928e1-26ac-5600-a0d3-73b3cb60dc66 | textbox | Date Completed:
e62ff21e-031d-4733-8578-51404186517e | checkpoint | 1.2 Implementation of all measures and controls
c5e2b3f9-2965-53b4-afe9-e493d8ee83b8 | note | FREQUENCY: Prior to Commencing Activity
339c9aec-e1bb-5253-9003-1fcc9f709fad | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
ae2f27a8-478f-5fdb-831e-026d28e7e734 | note | REFERENCE DOCUMENTS: Work Procedure
95158c27-b862-561b-8441-97dd15674345 | note | INSPECTION/TEST METHOD: Inspection
65f88381-ca6a-5755-be78-882effa1423e | note | RECORD OF CONFORMITY: This ITP Signed off
b10bd37c-75bf-50f1-80fa-a43a749d7193 | note | HP*
9524b755-9d3a-51fe-8db6-d0b9597ec82d | note | RESPONSIBILITY: Fulton Hogan Engineer
2bdeaf86-1d47-5722-92cf-07d202e7072f | textbox | Date Completed:
b477b789-8f1b-4afe-b7ee-c5b104163247 | checkpoint | 1.3 Check Condition of Material
7eda0ea8-ad97-5b89-a48a-ac656fd4232a | note | FREQUENCY: Prior to Commencing Activity
01105d52-b3ea-5761-bac6-dd3bf03d8c14 | note | ACCEPTANCE CRITERIA: All bluestones shall be inspected at delivery for visible damage
e13af6eb-7611-505a-ba14-ebbdd888c1ad | note | REFERENCE DOCUMENTS: Work Procedure
97b83582-6907-57c5-ba13-67611673cafb | note | INSPECTION/TEST METHOD: Inspection
ddd1b6b9-64a4-57a9-b441-768e51e3d9c9 | note | RECORD OF CONFORMITY: This ITP Signed off
16d40d2b-789b-501e-91e2-f8340e486580 | note | HP*
57bafc94-b97c-5e41-ac88-14aa6fbb2d20 | note | RESPONSIBILITY: Fulton Hogan Engineer
f9519560-6553-52d3-9b60-492c7daaa7ec | textbox | Date Completed:
548eb07d-8904-4aba-aeea-81025079e62e | checkpoint | 1.4 Lifting method
8f3009a4-2edd-52ac-9cfc-1e02160ce34a | note | FREQUENCY: Prior to Commencing Activity
90ae9b66-46f1-561d-8c60-cc54bbc42a1c | note | ACCEPTANCE CRITERIA: Bluestones can be moved with excavator and grabs/slings or with a vacuum lifter.
19893db3-0002-5118-97f8-849c6c5b0194 | note | REFERENCE DOCUMENTS: Work Procedure
78079a0a-a702-5928-8ea7-d349d3bbf6e5 | note | INSPECTION/TEST METHOD: Inspection
3671fafe-1116-51ca-aec6-5cd0297883a3 | note | RECORD OF CONFORMITY: This ITP Signed off
8e112798-fcb7-526b-aaf7-e3c541219a1a | note | HP*
31a022a9-699b-539e-953f-5b9ff456198f | note | RESPONSIBILITY: Fulton Hogan Engineer
934d19c9-41c9-5e6b-89cf-0af21b1ec1b3 | textbox | Date Completed:
81ce272e-1839-481c-a3c0-00f773f4d8b0 | section | Construction Works
6945bfc5-6823-4c3d-ac94-3a548b525cb2 | checkpoint | 2.1 Base Course
df2cdd04-a4f2-5928-90aa-5f8ba780d258 | note | FREQUENCY: Each Lot
43ad9c04-717c-5640-9e39-b678375ddeb9 | note | ACCEPTANCE CRITERIA: Class 2 compacted rock (98% modified density) shall be compacted to 100mm thickness. Soft or areas deemed unsatisfactory shall be removed and rectified
b93b58fa-66ad-5113-b713-91618255027b | note | REFERENCE DOCUMENTS: STD_T6111
d17ce53b-de0e-5ef6-8156-e2ad71292c7c | note | INSPECTION/TEST METHOD: Visual Inspection
c87e6fd0-dbd2-582a-b25e-52cef81b4c75 | note | RECORD OF CONFORMITY: This ITP Signed off
8fc9f920-8b21-5218-8918-f6ae4bc06758 | note | IP
9b7cb503-e4f7-50ea-980b-68dd7e806ccd | note | RESPONSIBILITY: Fulton Hogan Engineer
c701b563-1866-5592-8080-e20fe11ae464 | textbox | Date Completed:
002f722b-4cba-45c0-be4a-9592446b3b85 | checkpoint | 2.2 Concrete Placement
5467dda5-9d09-58f3-994c-9e90fb20cf45 | note | FREQUENCY: Each Lot
633c3079-ee33-503d-bda5-e211bd4afe2a | note | ACCEPTANCE CRITERIA: Bedding shall be >100mm 32MPa concrete with 6mm aggregate
8cf704b0-5737-5005-82da-87683f7dba8e | note | REFERENCE DOCUMENTS: STD_T6111
22ae1d88-2d57-5ffb-a0dc-12b0bef821cc | note | INSPECTION/TEST METHOD: Visual Inspection
8ee73d6e-0397-5c55-a6b2-94596a8eed37 | note | RECORD OF CONFORMITY: This ITP Signed off
1c7213a3-4ccb-56e4-bdbf-2c8d1cb69e83 | note | WP
93fe0ac8-55aa-57b7-93cc-c1bd48321385 | note | RESPONSIBILITY: Fulton Hogan Engineer
8238da5a-c039-5712-a107-b0af0b934838 | textbox | Date Completed:
d483adcc-c504-4c88-b1fd-21132ac600d0 | checkpoint | 2.3 Setting
9fda5c45-e6ec-5194-b171-903831e7b28c | note | FREQUENCY: Each Lot
b2335ecb-db47-5cf5-b465-58de02e444de | note | ACCEPTANCE CRITERIA: Tie rods shall be N12 (300mm long) and chemset 100mm into kerb, 2 per stone. Tie rods shall be installed with bond breaking compound specified by superintendent. Bluestone shall be laid 150mm below finished surface level
09a3f1a2-7d46-55a3-b243-35ca92c6ec67 | note | REFERENCE DOCUMENTS: STD_T6111
7ced3642-be25-5a53-a4ac-ead42286e5b7 | note | INSPECTION/TEST METHOD: Visual Inspection
4a0fafb2-a83e-5d70-b079-9c328f3e7dab | note | RECORD OF CONFORMITY: This ITP Signed off
a440a053-ede6-51ca-bcb2-bb82e3536669 | note | WP
8991cd87-206f-510b-b422-9ead3712fc67 | note | RESPONSIBILITY: Fulton Hogan Engineer
2c20f57c-be04-530d-a1d7-6e2055600b6b | textbox | Date Completed:
0088aed7-4fbe-41c7-a1b6-607df81ce210 | checkpoint | 2.4 Sealant
36b74be9-38aa-507a-8ca2-cf4c8ce5f647 | note | FREQUENCY: Each Lot
1602cc34-fb4d-5d7c-a864-d901185c7167 | note | ACCEPTANCE CRITERIA: Sealant at construction and expansion joints at back of kerb shall be 'Gun Grade THC 900' by Tremco, of black colour. Loose materials shall be removed as not to impair adhesions
7fed2930-1f76-511e-bcf7-a11431289edf | note | REFERENCE DOCUMENTS: Work Procedure
ad95e78f-3348-5e7b-94bd-d4095d4ce5c0 | note | INSPECTION/TEST METHOD: Visual Inspection
3f20adc4-5ada-5913-836b-4ef18b97912d | note | RECORD OF CONFORMITY: This ITP Signed off
2d09d70a-4586-5fbb-b669-26d88b4a706f | note | WP
54dff88f-bc42-5fe7-bec0-0ae5f83772a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
9bc4e390-4e92-59d6-8c5c-0a463a75bdd0 | textbox | Date Completed:
9965b26d-e31e-4414-99fc-c5881786f830 | checkpoint | 2.5 Platform line marking
130986b2-14da-50cb-bff4-ade747cbf2ac | note | FREQUENCY: Each Lot
3eec5748-9193-5020-b042-549c6ad13cbc | note | ACCEPTANCE CRITERIA: 50mm yellow lines shall be placed along the edge of platform, one on the top face and one on the front face of the kerb.
84f0efd7-39e7-5a49-b82e-bf5aaa6524d9 | note | REFERENCE DOCUMENTS: VRIOGS 005.3 Cl 7.9
4fc7bb84-e0b7-5e98-a0d5-d434727ff397 | note | INSPECTION/TEST METHOD: Visual Inspection
bab7fdfa-098f-5f80-aa59-2e6f0aba4996 | note | RECORD OF CONFORMITY: This ITP Signed off
3e2d50fb-91d0-559e-a125-5c4ae5572182 | note | WP
708737ac-7cd0-53d1-9bc7-f40a6c688a79 | note | RESPONSIBILITY: Fulton Hogan Engineer
887c1057-f440-5fe6-adde-27e80ae44a62 | textbox | Date Completed:
05db137c-415f-46a6-a565-031f66e844bc | checkpoint | Final Inspection
9edd7723-aab9-5b7b-9ab2-fb9dcd3b997d | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a4416711-96fb-5d71-972f-2db1cdd0a460 | textbox | Print Name:
61f72a9c-1db5-58d8-9a6c-3d0503e4ee78 | textbox | Position:
4f054cac-e682-539d-b1c0-60ee385087bb | textbox | Date:
e25de9b9-6ed1-4c2a-a425-b5f501e3686f | checklist | ITP-017 - Bluestone Paving Works |  | ITP-017 - Bluestone Paving Works
9c653a61-6004-4a61-9bbb-4d8a22309fb8 | section | Preliminary Works
9630952a-79fe-4e1f-9cc6-6e89fb6e0e94 | checkpoint | 1.1 Check for Correct Documentation
da852508-2839-5929-8d3a-115c3403a5b7 | note | FREQUENCY: Prior to Commencing any Activity
175ddb91-e267-5ba2-be28-7cfbe7335219 | note | ACCEPTANCE CRITERIA: Ensure all employees and subcontractors use all current and complete set of design drawings
ca961dac-661d-5b53-8257-89a892ca0357 | note | REFERENCE DOCUMENTS: Design Drawing and Registers
52a11ca3-ec01-5bcf-916d-cdcf44ae671d | note | INSPECTION/TEST METHOD: Visual Inspection
958f424a-381c-562a-a847-39027df1d2bb | note | RECORD OF CONFORMITY: This ITP Signed off
05940d70-10cc-5a27-ad9c-117ecd33011b | note | HP*
e126a03c-8c52-57cc-85d7-82cf610194d5 | note | RESPONSIBILITY: Fulton Hogan Engineer
ed547ee2-192b-5935-a332-fd88dd9d28fb | textbox | Date Completed:
f9513f63-413d-400d-a3d2-d53624c9ecd4 | checkpoint | 1.2 Implementation of all measures and controls
2b9c722f-1c2f-56fc-9d15-e5b2b9b6d497 | note | FREQUENCY: Prior to Commencing any Activity
c8ac200a-0987-5b1d-b120-8feb1378c5d1 | note | ACCEPTANCE CRITERIA: All necessary measures and controls shall be implemented, including: EMP, PSP, SWMS, TMP and WP
c8e087c6-751b-5797-8b1a-f8e6b9f5d3e7 | note | REFERENCE DOCUMENTS: EMP, TMP, PSP, SWMS, WP
76451bcc-5c01-5fa5-917a-1a5b3fe6e4b7 | note | INSPECTION/TEST METHOD: Visual Inspection
afec54ee-b630-5d42-b8e1-c603131b464c | note | RECORD OF CONFORMITY: This ITP Signed off
4937d070-9cd6-533b-805c-efefed4f7350 | note | HP*
70a5345f-9a59-5716-83c0-5030b411907d | note | RESPONSIBILITY: Fulton Hogan Engineer
5462603a-52ce-5cb9-ade1-2a604faac659 | textbox | Date Completed:
4baad907-dad8-4ec2-bcc8-c04d1f43da28 | checkpoint | 1.3 Check Materials
dbfad4f1-2dfd-58ca-b50b-f0f252b899f2 | note | FREQUENCY: Prior to Commencing any Activity
46d06369-6f5c-5770-82fa-3c8e1848b9fb | note | ACCEPTANCE CRITERIA: Inspect materials for any chips, cracks or other visible damage.
3aa662f4-028e-5782-98ef-724c023ba7ba | note | REFERENCE DOCUMENTS: Receivable Inspection Checklist
4b5b4347-d3cf-50fc-9be4-84f206ea61c1 | note | INSPECTION/TEST METHOD: Visual Inspection
37a4f2b5-14ab-58e5-b21f-4ca972b44f8f | note | RECORD OF CONFORMITY: This ITP Signed off
f8f24a4f-640e-5aa6-9afe-e4601fbb744e | note | HP*
cac8a09a-fecc-5802-9d83-102eb5d5eb12 | note | RESPONSIBILITY: Fulton Hogan Engineer
1eae1869-d569-5563-a1a0-2a57f4797868 | textbox | Date Completed:
f1472b87-ce40-425f-a00a-93773b90d8dd | section | Construction Works
63383330-6a63-4ec5-bec9-5440a10c9b8c | checkpoint | 2.1 Base preparation
8898c624-325f-5e92-b1c9-b9f66f71ca09 | note | FREQUENCY: Each lot
d7ab0d21-2052-5ef3-909c-c34df4663568 | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign materials and water pooling. Formed groove of 10x25mm in concrete face shall be filled with caulk
4c5d05b9-31a1-5b3e-ae76-4930fe1689bd | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
05b291b7-6421-5ef6-860e-99d78f4d0fbb | note | INSPECTION/TEST METHOD: Visual Inspection
d3d3e42f-237d-52c2-a33e-3bd96d253c94 | note | RECORD OF CONFORMITY: This ITP signed off
e3696ee3-363b-5ff4-b6d3-a19f28957d30 | note | WP
966f178a-8783-5942-9ae9-9363d49f46a6 | note | RESPONSIBILITY: Fulton Hogan Engineer
05f855de-b302-507a-9bdd-2573812be780 | textbox | Date Completed:
7c64a3ed-e2a9-49b3-a772-1bbd5c727820 | checkpoint | 2.3 Mortar Bed
40763fe9-0be8-5291-ad39-a68c2c0e71a6 | note | FREQUENCY: Each lot
1c267cc9-af08-5ea7-a52f-7c17403d3f1d | note | ACCEPTANCE CRITERIA: Mortar shall be applied at average thickness of 30mm to concrete base. All pavers shall be coated in mortar slurry on rear face before laying
d9b1b95e-da34-588b-ae56-0c1277258cc6 | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
0bd139bb-837e-5278-a65b-99ae5a854372 | note | INSPECTION/TEST METHOD: Visual Inspection
4ad10e17-0ea0-5752-a148-79591572f173 | note | RECORD OF CONFORMITY: This ITP Signed off
53051dd4-cebe-5d85-86ea-2f05dd295d80 | note | IP
e13db657-5d85-5879-8b70-5683d3e33b95 | note | RESPONSIBILITY: Fulton Hogan Engineer
8b14e489-3743-549c-ade7-443d15e58c7c | textbox | Date Completed:
a1380dcc-d3d6-4699-b47f-cca7e7ed7cba | checkpoint | 2.5 Cutting of Pavers
a3d3bb09-4527-52d2-84be-cbe84e67384e | note | FREQUENCY: Each lot
28ebcb66-d6f9-55c7-953b-825f7dbaa5f4 | note | ACCEPTANCE CRITERIA: Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
98955e67-a02c-5a59-b573-48e7aea516e5 | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
a5b4052f-77b5-50ae-bec9-df5698b39d2a | note | INSPECTION/TEST METHOD: Visual Inspection
72ce4eb5-a640-535e-9b5a-2a37d506d48a | note | RECORD OF CONFORMITY: This ITP Signed off
e4ad5e8e-9513-50f3-bf8e-7fab4c80ad55 | note | IP
86106bf2-0fcc-5965-bf44-0ab5c4633f86 | note | RESPONSIBILITY: Fulton Hogan Engineer
ed5560bb-68d1-5c79-8b9f-dcb64ae77b12 | textbox | Date Completed:
cfe890a3-1b78-4f1d-8ebd-319dfa7c5039 | checkpoint | 2.6 Curing
7eef6d4c-da3c-5469-9ce7-93776e6d82dc | note | FREQUENCY: Each lot
8141e62d-7ea1-5b60-8a4e-fefda6a46dc8 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic. Where required, ply shall be laid over area of works
c58f3e15-c489-5e13-804a-c2971fc08f0e | note | REFERENCE DOCUMENTS: Manufacturers Specifications
c0646f52-78df-5ae3-a893-e58d0d4967d0 | note | INSPECTION/TEST METHOD: Visual Inspection
e4266fb5-61b1-5a2b-8223-9998d11faca1 | note | RECORD OF CONFORMITY: This ITP Signed off
f2c2b2c7-37bf-5282-a020-a5097cb0ccca | note | IP
164e64a9-1e09-5a51-85b2-40f916e462bf | note | RESPONSIBILITY: Fulton Hogan Engineer
b0088dce-e5d6-5bb6-970a-7145ab28a5c5 | textbox | Date Completed:
d561adf7-334e-432f-b4f9-6da169e9b719 | checkpoint | 2.7 Grouting
2bd0ff4b-4353-566a-ac83-a3ff51e03452 | note | FREQUENCY: Each lot
6e8648d0-a067-5891-ab3d-3739adaf5fb8 | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using agreed colour and mixture
a4633d92-7e59-57f4-b214-161f0e47d6c0 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
1cbfa87d-7038-573d-9dcd-60aa305acb5b | note | INSPECTION/TEST METHOD: Visual Inspection
57053a4f-c69e-5334-ac1e-07a494a5b14d | note | RECORD OF CONFORMITY: This ITP Signed off
e163b2d5-6406-5b19-ae05-66ec66490bc9 | note | HP*
367cfa0a-e6ac-585e-9fa8-ac0e93215746 | note | RESPONSIBILITY: Fulton Hogan Engineer
b6adbf9a-c500-5cdc-992c-b64feddbd1fc | textbox | Date Completed:
d482e4d5-980c-43f6-bcc3-c269da74813e | section | Completion
5c258841-3f54-4b01-86c7-68e4d2be0262 | checkpoint | 3.1 Completion
9a9e700d-e0f7-571d-ade2-febc6408be5a | note | FREQUENCY: Each lot
f5a04fd5-a9ed-5687-9035-ddcc9cd607f2 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste. Bluestone pavement is free of mortar stains and cleaned to satisfaction
6b898521-1124-5796-9219-9a1de667a0a8 | note | REFERENCE DOCUMENTS: Visual Inspection
e3d700a1-20dd-595b-8f7d-3227be8cc470 | note | INSPECTION/TEST METHOD: Visual Inspection
1f5c5f8f-8b91-5710-abfd-f8664b91f3f5 | note | RECORD OF CONFORMITY: This ITP Signed off
397520c1-e255-5c50-baa1-538a9096df03 | note | IP
a6a50501-4ca5-592b-82ff-815316a4d1b2 | note | RESPONSIBILITY: Fulton Hogan Engineer
ba027320-2903-530e-a4ab-b8f253da3146 | textbox | Date Completed:
c44a7ce0-99e3-483b-9f37-908d07e37bba | checkpoint | Final Inspection
e89590e4-4186-5bf4-b60b-ab4eb7184e65 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a2c7b2e5-85c4-5e91-bcf6-968e75228cee | textbox | Print Name:
90f91f29-ca67-5965-a9c9-3aef5df87012 | textbox | Position:
efa56ab8-ad83-53ba-878b-c45b1d8905f9 | textbox | Date:
feaccad0-1cc6-4852-b305-10633d349c6e | checklist | ITP-019 - Fencing Installation |  | ITP-019 - Fencing Installation
4a42966f-d30b-4e74-80d8-628c0857a678 | section | Preliminary Works
aba07417-a9fa-4b0d-9419-7a41a5e10222 | checkpoint | 1.1 Check for correct documentation
86fde12f-5661-568a-a3df-36093d4a7645 | note | FREQUENCY: Prior to commencing any activity
790bbcc5-870b-500e-95f0-51685ba38c79 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
e30f1a54-fc0f-52c1-9bcc-3b9d0bc7af30 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
39f9a67f-3453-5f8e-a8a3-0e25ac221937 | note | INSPECTION/TEST METHOD: Visual inspection
fb67d309-1a47-5ed6-a6b4-936dc3c1951a | note | RECORD OF CONFORMITY: This ITP signed off
a92c3aac-bf91-5a0b-a83e-43fc7c3efaf4 | note | HP*
58ef852f-1386-5cb2-a0c7-ebd63118066e | note | RESPONSIBILITY: Fulton Hogan Engineer
bc6760f0-d553-591b-909e-35db646f8f1c | textbox | Date Completed:
39d5b15b-3a73-4bc2-b531-2c232f638ad8 | checkpoint | 1.2 Implementation of all measures and controls
e61787cd-986a-5b1e-83ad-acb6027d00be | note | FREQUENCY: Prior to commencing any activity
cdb43d3c-e5e5-5f75-8ec6-a6f5c8598c02 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
3037b6ce-4972-5164-9635-d013b4e09f6f | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
0323f1e8-eae6-5808-9cd4-68a11c805e68 | note | INSPECTION/TEST METHOD: Visual Inspection
2a7aae24-1d7a-5cf1-ba4b-190ba749da4c | note | RECORD OF CONFORMITY: This ITP signed off
ac0e4a7b-cecf-5973-9df8-4be7888d0df8 | note | HP*
4abdf5c3-9d8e-5f7a-95f1-a575878377ff | note | RESPONSIBILITY: Fulton Hogan Engineer
8a1ffe2e-5909-5aab-9ebc-4ed864513bbf | textbox | Date Completed:
3c0aec95-6a38-49c5-9b6a-5cfaa6bd3518 | checkpoint | 1.3 Check Materials
d4f7c5de-adf6-52e2-b396-1df50a565327 | note | FREQUENCY: Prior to commencing any activity
9d1b317a-8f11-5209-8556-3dfdc605ebf4 | note | ACCEPTANCE CRITERIA: Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish, linished, pickled and electropolished. Welding shall be in accordance with AS1554. Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000
e62792f1-0920-5a3c-b412-137e40f5e936 | note | REFERENCE DOCUMENTS: STD_T6000, CE-021-ST-0012, cl 4.3.1.4
8349d94e-5b0b-58b1-8201-a973a4eff7f1 | note | INSPECTION/TEST METHOD: Verify
a8069f06-f02b-5205-a94a-620353aaeba5 | note | RECORD OF CONFORMITY: This ITP signed off
024921b1-926b-5578-adb3-ab6c8988afd4 | note | HP*
4021779d-0ec2-5564-bbc1-4779540072fc | note | RESPONSIBILITY: Fulton Hogan Engineer
21941661-f36f-5959-83ae-9dcb0889f2a4 | textbox | Date Completed:
6ecc4b94-46aa-4405-9539-5ea73adfdafd | checkpoint | 1.4 Confirm Footings position
119b20df-c82b-5572-a8a6-8f74fa74330b | note | FREQUENCY: Prior to commencing any activity
4b0c3afe-1076-5efb-bf26-4834be217a75 | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
1f2a5d57-7c0d-54ad-9c8a-777f1427277b | note | REFERENCE DOCUMENTS: Construction Drawings
db3b173d-e600-5af0-8b8f-57ce054d1b64 | note | INSPECTION/TEST METHOD: Verify
7d00e8e7-cfd1-5916-bebf-43e9df0ec90c | note | RECORD OF CONFORMITY: This ITP signed off
efc3b4c3-42a4-5bac-8ffd-91e6f8f79b24 | note | HP*
a287fe8b-ca5a-5123-8eb7-099b5b298218 | note | RESPONSIBILITY: Fulton Hogan Engineer
c567e8bf-6014-5b36-986c-2a6c8bdae3b3 | textbox | Date Completed:
0d662e65-602e-4cb4-8fcd-f966f812bd1a | checkpoint | 1.5 Bonds
0824e45e-faf1-54bf-a5e9-05332fc4812a | note | FREQUENCY: Prior to commencing any activity
abaeef60-6b3b-541e-86a8-1c999bfa6af5 | note | ACCEPTANCE CRITERIA: Ensure fencing is isolated and earthed to achieve electrical isolation. Lug shall be fitted to baseplate at specified fencing location
67cab031-5460-511b-b332-1b781443aaf9 | note | REFERENCE DOCUMENTS: STD_T6000
a0d1634e-2e93-5b83-ad16-f526a88a8f2d | note | INSPECTION/TEST METHOD: Verify
6a0992a3-606e-534e-a697-9fa908b19acd | note | RECORD OF CONFORMITY: This ITP signed off
d5861211-1759-5f22-963c-e5a239fa3b73 | note | HP*
11c6fdfd-9856-503d-97d0-d581a1d34157 | note | RESPONSIBILITY: Fulton Hogan Engineer
924a1afb-4bb2-58d5-971c-190b794bb827 | textbox | Date Completed:
7d1e8369-e34e-4757-955a-bdd3f66716c9 | section | Construction Works
5cf3a7e8-5d12-4fd9-893a-7b79a38ed373 | checkpoint | 2.1 Footing Installation
530bfb72-3729-511b-8052-f3d982c87b0f | note | FREQUENCY: Prior to Asphalt
704d4e59-b220-5ee6-b75a-6ad49118df71 | note | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20. 4 M16 hot dipped galvanised bolts shall be chemset 175mm into embedment, per footing
ad8c0df6-4c16-5ae5-8d6e-f3afdaaeff09 | note | REFERENCE DOCUMENTS: STD_T6002
a7f280b7-7fc3-5f5c-a7b4-2e7a1224292a | note | INSPECTION/TEST METHOD: Verify
b49f42e4-f631-50e8-afc7-a131a343d2a3 | note | RECORD OF CONFORMITY: This ITP signed off
0a682e0b-3ec2-558d-9c14-c9b0a9ba5de9 | note | IP
eb1ceb8c-bd89-5f7c-b8cf-d6a1080ff909 | note | RESPONSIBILITY: Fulton Hogan Engineer
2d42928e-883a-56c7-9a51-f4bbc566137e | textbox | Date Completed:
7fcc8f7d-1b57-4ab2-ac1f-fcca80c31ead | checkpoint | 2.2 Post Installation
e91b5e1e-4cf0-5776-877f-86dc8eaa582d | note | FREQUENCY: Each Lot
12e277d0-2c90-5545-ba21-bd35fed3cd3b | note | ACCEPTANCE CRITERIA: Post shall be installed to designated height and level. Installed to footings with bolt assembly. All bolts shall be insulated from base plates, using non metallic sleeves and washers. The top of fence base plate shall be level with surrounding pavement.
3a4effde-9177-5ca0-94fc-a3040553d95a | note | REFERENCE DOCUMENTS: STD_T6002
153cc8b7-f8d1-5ecb-9ed0-2b69d63a01d5 | note | INSPECTION/TEST METHOD: Verify
cfb389bd-85db-536d-867e-b80081af4143 | note | RECORD OF CONFORMITY: This ITP signed off
a363507f-a075-5110-a4a4-e63c5deb26bf | note | IP
e4ea7d3a-812b-5317-8b03-5991acae9399 | note | RESPONSIBILITY: Fulton Hogan Engineer
fe4c4abf-f176-54af-885f-81902b63b048 | textbox | Date Completed:
2884354c-6021-46dc-bfea-6226b6d2392a | checkpoint | 2.3 Grout Installation
815ec29e-c34c-5b13-8cf6-076ab75cf170 | note | FREQUENCY: Each Lot
f0ef7231-df0c-5776-9e7e-fc5cc838ff9d | note | ACCEPTANCE CRITERIA: Footing surface shall be cleaned and roughened before application. 50mm of Non shrink dry pack grout shall be placed under base plate
576e5f0a-7aff-5280-aba7-e9fd972b3080 | note | REFERENCE DOCUMENTS: STD_T6002
b621e1ce-8a3d-5ca9-bdad-9a8694d3f8c4 | note | INSPECTION/TEST METHOD: Visual inspection
f66e8eae-6b03-568e-b3c1-e7926eb5b475 | note | RECORD OF CONFORMITY: This ITP signed off
63be8778-224d-5bda-92af-996de4b2989b | note | WP
63d168ea-ee15-576e-98bd-67b4f6a5ad19 | note | RESPONSIBILITY: Fulton Hogan Engineer
c2d01ad0-1d7f-5a32-868d-e994d13a5c22 | textbox | Date Completed:
c7610ba6-d217-4480-ab75-46866c30c725 | checkpoint | 2.4 Continuous Handrails
f83684e5-5b78-5aff-b474-e47fd2d260eb | note | FREQUENCY: Each Lot
1bd5f1df-9e65-5459-a34b-9a8b91e35988 | note | ACCEPTANCE CRITERIA: 5mm cap plate on handrail returns. All sections to be welded as per AS 1554. All sharp edges and welds to be ground back to smooth finish. Domed buttons to be welded on top of handrail 150mm from the post centreline.
ac8a3f30-b8a5-5b4e-8723-3451c4e5efe2 | note | REFERENCE DOCUMENTS: STD_T6001 & T6002
e0f42eb1-9502-589c-9e0e-7ceb0ad4b6d8 | note | INSPECTION/TEST METHOD: Verify
7d4259b4-64e9-5d61-9708-2130d18b6322 | note | RECORD OF CONFORMITY: This ITP signed off
24719845-0f5d-5dbc-a6c1-456eb527d3a6 | note | IP
c0aa6569-652c-59b1-8226-6a8a4e311f32 | note | RESPONSIBILITY: Fulton Hogan Engineer
e0c9178f-5e96-5a11-a91c-20dee2942434 | textbox | Date Completed:
a0ddcf8d-d95c-490f-a76b-cef4546e7154 | checkpoint | 2.5 Wire Rope Tensioners
4f0a7ef7-c213-5298-94f8-f2a9abeb90e9 | note | FREQUENCY: Each Lot
562a3c3f-1700-5c61-aa94-b4df2f78dba3 | note | ACCEPTANCE CRITERIA: Architectural wire rope cables to be inserted into ferrel on fence post and to be tensioned with tamper proof fastenings (Loctite 243 Threadlock)
9c8eea9b-d819-5d49-9fb3-3224faf7ade2 | note | REFERENCE DOCUMENTS: STD_T6000, T6001 & T6002
168a2387-8ca4-559e-bc90-151c5ceb1219 | note | INSPECTION/TEST METHOD: Verify
d2d139c7-d47c-5289-a6ab-fcb1c34e7515 | note | RECORD OF CONFORMITY: This ITP signed off
afb2e819-fee4-5464-b62f-1cb3f1d537c5 | note | IP
42bd34b4-c022-548e-b0be-64aad8546e64 | note | RESPONSIBILITY: Fulton Hogan Engineer
885fdd8e-5f5e-55e8-a44f-e962c1d9ec7f | textbox | Date Completed:
2fdf12ee-2167-4bdd-9472-05524417183a | checkpoint | Final Inspection
ad178de0-99db-537a-a948-ddedb327fef3 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
bf42e633-c6ad-5391-899e-322476b1386c | textbox | Print Name:
703c9e86-6dc3-5af9-9577-2ec2f819ea6c | textbox | Position:
9846a06d-672a-5758-93aa-65a24ca508a1 | textbox | Date:
144a62ff-d937-42c8-aed8-e070e93130b3 | checklist | ITP-020 - Exothermic Welding |  | ITP-020 - Exothermic Welding
1de85215-d329-45f4-91af-4cbfdb59cd35 | section | Preliminary Works
5b89e1c0-f82f-446b-abd8-3a322c5483a6 | checkpoint | 1.1 Check for correct documentation
5737a2e5-ab17-5742-af36-4c0929d81c87 | note | FREQUENCY: Prior to commencing any activity
555905d4-f59f-59f6-bb4b-bc9015110c63 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
d7e1a8d4-1fda-583b-aff3-450afc6ef321 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
15841062-e649-5bed-8773-1d08a8f7e184 | note | INSPECTION/TEST METHOD: Visual inspection
1e6025d9-1a6d-5444-af4d-c3930647b11e | note | RECORD OF CONFORMITY: This ITP signed off
8b34f132-1111-5e48-8dca-5cbfb7812037 | note | HP*
6cd44bb3-0168-5dcd-9081-09ddc2b8d537 | note | RESPONSIBILITY: Fulton Hogan Engineer
93a4d347-85d1-5229-be6d-c1c60ab675d3 | textbox | Date Completed:
8478ab02-ab79-4742-8802-10c6119e72f7 | checkpoint | 1.2 Implementation of all measures and controls
141cc903-1e99-5079-919b-8beaf2659c58 | note | FREQUENCY: Prior to commencing any activity
3d270118-7b9f-53f5-87f6-21bde4e48224 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP. Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit
24a13351-3266-54c0-bb1d-b58e7612f558 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e067120b-951e-5014-b441-cce06ebcfbc8 | note | INSPECTION/TEST METHOD: Visual Inspection
9aa47274-60f4-5a98-b690-66f7d48c9776 | note | RECORD OF CONFORMITY: This ITP signed off
82dee1d2-4ae3-5f2e-87f6-bd59ff3fee40 | note | IP
abc8ba22-f6fd-5eda-ac40-2184e81cb02c | note | RESPONSIBILITY: Fulton Hogan Engineer
69e0bd2a-602b-5efb-9aee-84dd05d3d085 | textbox | Date Completed:
9190b21a-5cc8-48ba-bcf9-058160918646 | checkpoint | 1.5 Materials Check
2e8d2da0-10c0-5337-8f47-32fe9b261f5d | note | FREQUENCY: Prior to commencing any activity
32eec5ba-ce2e-5b5c-a972-97a79726096f | note | ACCEPTANCE CRITERIA: Ensure the materials and equipment gathered are for the correct type of connection being made. Inspect the mould ID tag to ensure that it corresponds to the application, indicated by the following parameters:
6cd3cb08-6977-5108-8f13-939415c26a55 | note | 1. Mould part number:
e3085b7a-c123-5864-bcbe-cea63d3bfc62 | note | 2. Conductor size:
ff5a1219-8caf-58ea-b2ff-9f07ee5e84bf | note | 3. Welding material required
85203a54-acc5-5d52-bca5-7c3357c255bd | note | Check to ensure the graphite mould is not worn or broken, which could cause leakage of molten weld metal during the reaction.
d5c1916c-6153-52c4-80ca-f2ccbecaf5d3 | note | Ensure a working fire extinguisher is available within 10 metres of the working area.
480fce13-7862-5158-9f13-b3d7e89d6951 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
44704c48-abea-517c-a779-1e8fa4d0ed74 | note | INSPECTION/TEST METHOD: Visual inspection
1b5896b1-847b-55bc-a701-10fd71936bac | note | RECORD OF CONFORMITY: This ITP signed off
58a209ca-249a-5177-937e-376618bb6510 | note | HP*
ee240a90-4a30-5981-9d65-505e86dafa24 | note | RESPONSIBILITY: Fulton Hogan Engineer
5d4aa062-9b8f-5069-8a18-7f13014a7f58 | textbox | Date Completed:
37560977-beb2-4c13-9241-d0362dc8a225 | section | Construction Works
d585d52c-faeb-4325-9ce0-cdf114bcca4d | checkpoint | 2.1 Preparation
e05b7f0f-7739-5e5a-b823-799072a1c8f7 | note | FREQUENCY: Each Weld
51c919b1-c094-5481-b275-e1f5bcd0842a | note | ACCEPTANCE CRITERIA: Ensure the position of the conductors being welded is correct. Heat mould to ensure it is dry. Strip & clean conductors, ensure they are dry & clean.
41cdae8b-0e39-521f-902d-790581224b43 | note | REFERENCE DOCUMENTS: Design Drawings and Register
885bda41-4138-5f44-88e2-8fa4ac8ccb2c | note | INSPECTION/TEST METHOD: Visual inspection
663fdf37-3ac6-5cff-a954-b8b1397bf3b0 | note | RECORD OF CONFORMITY: This ITP signed off
0b0e2e67-87e7-589a-934c-2ca86e399977 | note | IP
5d8ff630-fd50-5355-8d00-c068f7f4763b | note | RESPONSIBILITY: Fulton Hogan Engineer
f6ccf044-bb96-54f0-b658-dcbb60541fce | textbox | Date Completed:
3959a5ef-0740-42fd-bf8d-ba3b9f85fc6e | checkpoint | 2.2 Welding
3f69303a-5f5a-5d8e-8340-6d2124b1dc4a | note | FREQUENCY: Each Weld
cdf94c59-85f5-5b28-a32f-358f1abb95d7 | note | ACCEPTANCE CRITERIA: Ensure conductors are correctly positioned in the mould, allowing the mould to close tightly. Ensure welding material has been inspected and is intact. Ensure reaction is completed and molten material has solidified (allow 30 seconds post ignition)
a8db93ee-8900-5f45-bd07-6394d484814c | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
bb2eb571-5e08-5997-a9d3-0bc8303aeb90 | note | INSPECTION/TEST METHOD: Verify
a7fcd6b7-4f18-5fe2-9865-2714d763e3da | note | RECORD OF CONFORMITY: This ITP signed off
6a81fced-e910-5354-b5c0-c03a6ef0cb9f | note | IP
0b60f5e4-906b-54ae-b9e7-6910cc6e0c52 | note | RESPONSIBILITY: Fulton Hogan Engineer
7f02524f-5c97-554b-ad4d-f9c6203bbc7b | textbox | Date Completed:
7b1c6888-4c2c-482c-9591-a0b245f7c0d2 | section | Testing
7cb79786-abe3-4e66-b6ba-49db04981b28 | checkpoint | 3.1 Weld Review
40886372-ffb2-5bc0-818d-02b1ba7496aa | note | FREQUENCY: Each lot
d0d9c1cf-e7c1-5b27-b32a-9db32aa6374d | note | ACCEPTANCE CRITERIA: Ensure weld is inspected and that a quality connection has been made. All welds shall be inspected a Fulton Hogan engineer.
2f0f6626-0e58-5812-b2d8-1bd286bbe3f9 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
a670037f-24d6-54d1-860f-a15486475ab8 | note | INSPECTION/TEST METHOD: Verify
883ffe5e-c3b9-5190-93b9-6fe79d9603cb | note | RECORD OF CONFORMITY: This ITP signed off
75ff4990-aac6-59e4-a5cd-a4a518682e0d | note | TP
e94d4a8e-7df4-5a0c-b636-646e348f6b2c | note | RESPONSIBILITY: Fulton Hogan Engineer
82c6b158-5f97-5091-acf3-45e22b985b6f | textbox | Date Completed:
48cf313d-e667-4c0d-a644-a09ff72e7668 | checkpoint | Final Inspection
5cb96962-5184-5919-afe6-94ac0528e8ea | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
e2a9991b-31f7-533b-bf6e-db9008abe381 | textbox | Print Name:
499aa2b6-8c69-56dd-8834-4c08ca22afcb | textbox | Position:
56e67e63-fc15-594a-829b-b897e3213996 | textbox | Date:
42c8acff-71af-4fb9-aea4-30fa0b4e2efe | checklist | ITP-025 - Platform Concrete Footing |  | ITP-025 - Platform Concrete Footing
41ca733f-34da-4447-bd2b-a38816e32f29 | section | Preliminary Works
0cf5f343-70e5-4d90-ab04-3b0a1b146991 | checkpoint | 1.1 Check for Correct Documentation
6a36c141-8362-57de-baf0-a15b4a1f93ce | note | FREQUENCY: Prior to Commencing any Activity
80313078-903e-5930-8aec-327d1c284dcc | note | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
ddc2d1fa-cb8b-5513-bfed-2453a32bbb92 | note | REFERENCE DOCUMENTS: Design Drawings and Register
cd78cdc5-e5b5-5bd7-bf97-8ad132a7d8ca | note | INSPECTION/TEST METHOD: Visual Inspection
a47b013f-027c-5e57-9494-d0fe92cb2368 | note | RECORD OF CONFORMITY: This ITP signed off
fa9514f3-778b-5d93-9e8e-dca761d41800 | note | HP*
6ada61db-0340-5e44-b377-86f5f78b542f | note | RESPONSIBILITY: Fulton Hogan Engineer
70fc659f-12c2-5ee4-be4c-a5d6495713f0 | textbox | Date Completed:
9f97b57a-11ef-4dfa-84e5-a84b321a6eec | checkpoint | 1.2 Implementation of all measures and controls
ad20030e-946a-5a72-b52d-4d3ced538247 | note | FREQUENCY: Prior to Commencing any Activity
65eb5c25-3647-5f8f-a6a6-c692ce081e0a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
e564021e-1ee5-5c85-9518-4a921f532fac | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e0cd75ef-ed59-5e26-a8dc-89fb62136bc3 | note | INSPECTION/TEST METHOD: Visual Inspection
884cd2bf-9f1e-5def-bca3-4adf8c634bcb | note | RECORD OF CONFORMITY: This ITP signed off
82a1edca-041a-5855-8b2f-9ad0dddedef3 | note | HP*
80d37b3d-695e-5728-b2da-189091ac09f1 | note | RESPONSIBILITY: Fulton Hogan Engineer
9b4237d2-c1c3-5b33-9ba5-723773d6bd0a | textbox | Date Completed:
f0a30300-e7e0-470e-841f-82b57e9c38b3 | checkpoint | 1.3 Setting Out
cb46810c-7805-5f65-be53-d5a2cfab48ca | note | FREQUENCY: Prior to Commencing any Activity
26d21657-ec54-526a-a40b-ecdfe75de39e | note | ACCEPTANCE CRITERIA: Ensure that position of footings has been correctly identified according to design drawings
67ab7e21-dbbe-5636-9f61-163e05571f15 | note | REFERENCE DOCUMENTS: Design Drawings and Register
cb790f6c-5704-53a5-b5f1-3f4abe1b0fe0 | note | INSPECTION/TEST METHOD: Visual Inspection
b804c4e1-55cb-51b5-882a-5fa89808c433 | note | RECORD OF CONFORMITY: This ITP signed off
d9f29269-e0df-507d-850a-ec1af5f53b63 | note | IP
4741c425-5531-5d83-8dec-d75e231ea5c9 | note | RESPONSIBILITY: Fulton Hogan Engineer
42612588-b5a6-5bfa-87d6-2a3ecab7d243 | textbox | Date Completed:
5e0b5595-ce2a-4b88-a878-ae48ccf0f3d0 | checkpoint | 1.4 Material Check
f8c4c644-f58e-56ab-8c16-8b7766ab9a48 | note | FREQUENCY: Prior to Commencing any Activity
21c25a39-6622-5cf8-bbdc-f406f7078129 | note | ACCEPTANCE CRITERIA: Ensure that materials have been correctly ordered based on the intended use. All bolts shall be hexagon head class 4.6, unless otherwise stated. Ensure bolts are of specified length and grade
8df893d0-2363-59d5-935f-2b76a8da71cb | note | REFERENCE DOCUMENTS: STD T6100
98f5744d-9217-5ac5-88c7-965326325ce4 | note | INSPECTION/TEST METHOD: Visual Inspection
a9d0ce9b-4e3c-5ee6-b07c-c5a02ca7722c | note | RECORD OF CONFORMITY: This ITP signed off
9fbeaa8e-a2a2-5b1e-b3b2-c213d077ceb1 | note | IP
ca7ada39-27d7-54cd-b736-0171d1a2ebfa | note | RESPONSIBILITY: Fulton Hogan Engineer
fbcd0aa7-2b13-545e-a5f5-658d0446137e | textbox | Date Completed:
9e2d8971-fc81-4aa5-b96c-4c6f6b87012c | checkpoint | 1.5 Concrete Slab Check
71d5d95b-f1cb-5c10-8152-56522d8ac720 | note | FREQUENCY: Prior to Commencing any Activity
c53b3eb5-d0e4-562a-a204-69e44d092de7 | note | ACCEPTANCE CRITERIA: Ensure recess has been provided in concrete at location of footings, ensure recess is to correct depth. Refer to Adshel specifications
36554759-e1d1-518e-9b72-79c2a107f4d3 | note | REFERENCE DOCUMENTS: STD T6102
c4908493-ec9f-5216-8b0d-68c73a19e4de | note | INSPECTION/TEST METHOD: Visual Inspection
66540f13-57bd-515d-aa76-397f98a84bd1 | note | RECORD OF CONFORMITY: This ITP signed off
352b4413-7a34-5f6a-8330-fddee7cd60d6 | note | IP
b0c23e8c-d3c3-5c88-8976-2b22250514d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
60688346-c119-5a5e-8482-2996e1675adc | textbox | Date Completed:
ca8baaf7-6371-4eef-aaa7-3bb3bf0c063b | section | Construction Works
422be50b-fec9-4e50-90d4-32506f06ba14 | checkpoint | 2.1 Bolt Installation
f69eb442-c6f0-5b65-a166-e30bcf58ab44 | note | FREQUENCY: Each lot
98f85a62-2937-57de-95a7-43fd31e9b20c | note | ACCEPTANCE CRITERIA: Install bolts as per specified minimum anchorage depth. Ensure anchorage procedure conforms to standard"
8afe35c3-22fc-5302-b743-72f91ff2bf33 | note | REFERENCE DOCUMENTS: STD T6102
93232f4c-0842-5a56-998c-762fae90c427 | note | INSPECTION/TEST METHOD: Visual Inspection
46eade24-def5-53ef-b7e8-62c81383e06d | note | RECORD OF CONFORMITY: This ITP signed off
58857e25-c735-582b-aaf8-92035f3df3bb | note | IP
86349776-bd7c-5e26-97bc-d7b7c5af79ed | note | RESPONSIBILITY: Fulton Hogan Engineer
ed8afd91-2676-5a20-9676-adcf55007aa3 | textbox | Date Completed:
29c34348-5f14-48f6-8b3f-6f68463d4392 | checkpoint | 2.2 Placement of non shrink grout
1d4dee20-e96f-5d9b-9552-a9d195b8a2c9 | note | FREQUENCY: Each lot
de240681-251e-529a-a69b-e4fb94f3a18b | note | ACCEPTANCE CRITERIA: Non shrink grout shall be placed between concrete pavement and base plate, at thickness >35-75<mm
83d01077-2aef-52fc-b77e-4eda79a6e9db | note | REFERENCE DOCUMENTS: STD T6100
b8da7315-8f16-54f7-bb52-6dac8b6e2aaa | note | INSPECTION/TEST METHOD: Visual Inspection
dc09ed1e-9319-54e1-8ed8-d64ead867202 | note | RECORD OF CONFORMITY: This ITP signed off
33aaed3a-9e87-56d0-b48a-d057a1e9af65 | note | IP
0680d148-37c4-5b87-9968-7cc2dc3794e1 | note | RESPONSIBILITY: Fulton Hogan Engineer
4627ba81-1703-586b-ab8d-33ddc4998cd0 | textbox | Date Completed:
687084c7-c21f-4bdf-ab21-6baf6640c9f9 | checkpoint | 2.3 Placement of Grout
20f14e68-7de9-5764-9a03-5caa40251058 | note | FREQUENCY: Each lot
14e09f59-1586-57c0-91eb-8613c916f250 | note | ACCEPTANCE CRITERIA: Grout shall be placed as to fill the gap between baseplate and level height of concrete
5aca15db-53a1-540b-b729-95028f89a9f1 | note | REFERENCE DOCUMENTS: STD T6100
e43cf61f-0cc5-5989-9dca-aa1ca12af140 | note | INSPECTION/TEST METHOD: Visual Inspection
91009604-3842-5c1c-8b93-6a47b72a5c07 | note | RECORD OF CONFORMITY: This ITP signed off
4cc2a084-bef2-5486-af6d-906cbee14e27 | note | IP
7645155d-9b39-56de-839e-ce1f1292033a | note | RESPONSIBILITY: Fulton Hogan Engineer
7417d717-42b4-5697-a78e-9edd4a52daf2 | textbox | Date Completed:
dc8e77d7-4cda-497b-b574-61c1ad9dad47 | checkpoint | 2.4 Pavement (if required)
d3254f0b-225a-5bfa-9b08-3b343fb9ebf6 | note | FREQUENCY: Each lot
63f41f09-7f56-5036-8afb-b53bdc17daf5 | note | ACCEPTANCE CRITERIA: Minimum depth of specified pavement shall be 50mm, ensure the bolt assembly is not covered by pavement
c1fd2181-cbfa-5069-a546-1b5d11a3eada | note | REFERENCE DOCUMENTS: STD T6100
053188d2-1cfe-5848-909b-ea3986ae52cd | note | INSPECTION/TEST METHOD: Visual Inspection
77169c7f-cbe5-5d44-9eca-fac25dc32b24 | note | RECORD OF CONFORMITY: This ITP signed off
9d34ae26-5120-5c0b-bd17-600f98d80b56 | note | IP
47cbe41a-7762-5efe-b26e-2b2b7a69b6bf | note | RESPONSIBILITY: Fulton Hogan Engineer
f30b7946-61df-51d9-8b19-e0b875b59575 | textbox | Date Completed:
0077eb53-bb02-4057-b92e-2be723e92f10 | checkpoint | Final Inspection
cb786e83-fd78-501b-9d58-5708e7634fe0 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
d5deb707-ab10-52c4-95ef-ca97eec9d8cd | textbox | Print Name:
e8daf0df-a571-575e-90ca-acd52e0df1c3 | textbox | Position:
76b7f067-1ecd-559f-bd03-a554293f44a1 | textbox | Date:
76779e58-1098-478f-a652-5807cc405494 | checklist | ITP-029 - TGSI Installation |  | ITP-029 - TGSI Installation
9d5f2181-a699-437b-9014-e9af1562ebe8 | section | Preliminary Works
72dec241-57cb-4be8-8df1-8997ab41ea73 | checkpoint | 1.1 Check for Correct Documentation
58512ea7-b77d-5e20-8a7b-475aeeafb400 | note | FREQUENCY: Prior to Commencing Activity
26a879f6-047e-591d-b091-6bea99caefdc | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
d8a5b310-bb4d-5a9b-a73a-ff0a13699629 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
eebee218-17ad-58a8-9eae-3dfd95b70389 | note | INSPECTION/TEST METHOD: Visual Inspection
3c0a9ed6-5091-57b2-81a7-639ad953fe84 | note | RECORD OF CONFORMITY: This ITP Signed off
0fb1f4d3-102e-5c60-a055-e8253610859e | note | HP*
50546b5b-7f3f-5967-bdad-49d9aec1b90f | note | RESPONSIBILITY: Fulton Hogan Engineer
73d98214-a900-568a-b724-26a5e8ab3999 | textbox | Date Completed:
054b5a87-a7c5-4727-8954-c54572c54629 | checkpoint | 1.2 Implementation of all measures and controls
040389a3-a39b-5d7e-87dd-cf3a8c928630 | note | FREQUENCY: Prior to Commencing Activity
74fbdbfe-2296-5d74-830c-17feae25274c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
850dea4a-3ce9-58a2-b077-07e0c1d65952 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
f040fcf1-e4f3-5314-bf50-eec8ac9ece07 | note | INSPECTION/TEST METHOD: Inspection
17074e00-8c2b-5829-a082-2c9b0aa1ad65 | note | RECORD OF CONFORMITY: This ITP Signed off
9cd76f2f-69f6-56c2-94e4-acdd4a66b2fb | note | IP
22b0733f-a1c9-5bbc-8610-d3c973b5f7fa | note | RESPONSIBILITY: Fulton Hogan Engineer
93786f4c-b348-52a9-9717-6ab2aae0ddc2 | textbox | Date Completed:
f5f47abd-4aae-4fdf-9719-e35a2a415e49 | checkpoint | 1.3 Check Materials
fc43b9d8-4a85-5760-a5c8-afaadb1d36b6 | note | FREQUENCY: Prior to Commencing Activity
58d25e05-90bd-5d00-935d-9f5818a6fa3f | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Bluestone / Granite Tactiles. Tactiles in asphalt areas shall be Pandatac Granite Tactiles.
708a5c66-ebfb-5386-bb52-e446a7b1eb7d | note | REFERENCE DOCUMENTS: Receivable Inspection List
dc14ded3-3911-5dce-bfa3-6abe545a9f77 | note | INSPECTION/TEST METHOD: Visual Inspection
7a2f3996-490e-51d8-8a7a-afd3380a1b1b | note | RECORD OF CONFORMITY: This ITP Signed off
050b8703-726a-55da-8263-610f63e7bd56 | note | HP*
7cb5ad01-8613-595c-b057-98adcbc89700 | note | RESPONSIBILITY: Fulton Hogan Engineer
80156d47-4943-54c0-bf0c-f36d15ea9cf4 | textbox | Date Completed:
92b9f671-f9e9-40b6-8b55-fd56429eceea | checkpoint | 1.4 Setting out
5c0690fc-fb8d-5252-83c2-7908c174a6f5 | note | FREQUENCY: Each Lot
f29f5923-6b5e-5350-8d3a-5c71d05f596a | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
185241d9-34a4-57e4-903b-cc38d329f1db | note | REFERENCE DOCUMENTS: Work Procedure
8873ab8a-58d4-581f-8fbc-231a17c26ca5 | note | INSPECTION/TEST METHOD: Inspection
98a06d18-bca3-583c-9cde-e79b235320a9 | note | RECORD OF CONFORMITY: This ITP Signed off
d003c7a7-c5f5-5cc2-80ed-487e2c5d3a01 | note | WP
4176e7be-6c24-523e-80c2-6230ce466a55 | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
844d0cd3-0a9d-59a8-a2f1-6b7732e9732e | textbox | Date Completed:
b5f632f7-d226-44c9-b023-d04adca08381 | section | Construction of Access Ramp Bluestone Footpath
63ed54f7-5f8a-4844-b14a-b3d4e897f19e | checkpoint | 2.1 Base preparation
bc295a75-ca07-5c7c-bb3b-d950a1849cd7 | note | FREQUENCY: Each lot
026356d3-860e-5bf7-88c3-f807c21faf54 | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
9a6d7c68-2897-5bd5-8b7b-5e610dc5d830 | note | REFERENCE DOCUMENTS: Dwg 1P50201
5ab8edea-1529-5cef-aebc-7ee1cb0a4b12 | note | INSPECTION/TEST METHOD: Visual Inspection
9aeeed16-682a-53c5-81fd-fc422cb53b41 | note | RECORD OF CONFORMITY: This ITP signed off
f9b7b0d8-129c-5f22-a7d8-e71a0f11965e | note | IP
745c0ee7-5d55-5fc1-9f5e-2a1999ea132d | note | RESPONSIBILITY: Fulton Hogan Engineer
970d87b0-c72e-5592-be1b-ab9e699dd0d4 | textbox | Date Completed:
0001697c-1d7a-4335-8f76-0bec0e304d44 | checkpoint | 2.2 Placement of bluestone pavers on mortar bed
142277e1-b7c3-562d-ba06-a975d6757590 | note | FREQUENCY: Each lot
fb029f77-0549-5f7c-b4c6-232eb3a47b31 | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402 on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying. Kerb access ramp wings shall be at an angle of 45° or as per design and the ramp gradient shall not exceed 1:8. Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
3cff16c3-a237-5170-8713-68c87968756f | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
f0b2a502-3a56-5470-ae1e-488939f79a3d | note | INSPECTION/TEST METHOD: Visual Inspection
6218e6eb-ff61-5258-9d83-99501f514ad2 | note | RECORD OF CONFORMITY: This ITP Signed off
bf02fa11-c03e-58f7-8f86-8df634856b9d | note | HP
f1f0efad-cb76-54eb-973c-c429564e3a27 | note | RESPONSIBILITY: Fulton Hogan Engineer
812fbfd2-bd44-54ec-8a31-2f52c034580c | textbox | Date Completed:
fe0e76c9-6bc6-4b8f-8aef-b5d256eed844 | signoff | REQUEST HOLD POINT SIGN OFF
d3ba9b27-d408-4820-bcbf-d59897a9a2b6 | checkpoint | 2.3 Curing
eafb2a3e-8d65-5689-97db-1d3856a63489 | note | FREQUENCY: Each lot
697d9fb7-53cb-50d0-9836-9fff5997f247 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic. Where required, ply shall be laid over area of works
018244ae-13e0-56c7-a0cb-00fb585d21b5 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
ae6191c5-b455-5596-9c1c-da2f30b1d483 | note | INSPECTION/TEST METHOD: Visual Inspection
66a69c17-6945-58e0-9b14-836394f552fc | note | RECORD OF CONFORMITY: This ITP Signed off
fb919fdd-51a1-50a6-8b39-ba4a30885ac3 | note | IP
3f475cb3-ec35-5e5a-bedc-85916a133eb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
5329c1e4-4b54-565d-9b5a-a88de1f51bc5 | textbox | Date Completed:
71b4ee5f-e481-4883-8714-4be2c8f9e29b | checkpoint | 2.4 Grouting
624d0230-f2ee-5d4d-b2ca-97774ce6a563 | note | FREQUENCY: Each lot
0410b7ca-d319-575a-a538-9d789043b9f4 | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using Lanko Durabed to specified mixture content. Grout shall be spread & clean appropriately as required.
2ac2d53e-425a-57ef-aa9c-8a50eb21cf13 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
0013bf4b-96ad-520d-9459-d33d207f0dae | note | INSPECTION/TEST METHOD: Visual Inspection
af2e5ce4-6b9d-5f8c-9752-00f05614ff0c | note | RECORD OF CONFORMITY: This ITP Signed off
317ba425-7186-54c1-a058-38eea202305c | note | HP*
e013bb63-1cb3-5764-9992-e926b6d0de98 | note | RESPONSIBILITY: Fulton Hogan Engineer
38609131-229b-5e95-b11c-3a08fd974abe | textbox | Date Completed:
2dddb408-4816-4aa0-a6cf-2c93686f9c1b | checkpoint | 2.5 Installation of Versatac Granite Tactiles and Granite Inlay
d2e20344-0a4f-5c08-b52f-761db9b6d38e | note | FREQUENCY: Each Lot
5b46034a-c1f4-5b7b-986a-a2ad9155b12e | note | ACCEPTANCE CRITERIA: Granite tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201 with surface deviation of under 5mm. Tactile Pavers shall be placed on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying. Tactiles shall be cut with a diamond blade and allow a 5mm grout.
5996e517-121a-5436-92f6-bda4c207319b | note | REFERENCE DOCUMENTS: Dwg 1P50201
d4e16df7-8a3d-5fbf-8c65-4b2fee305e75 | note | INSPECTION/TEST METHOD: Verify
5d57676b-5612-5bf0-8317-ad2d4a804c5c | note | RECORD OF CONFORMITY: This ITP Signed off
6f395c1f-bbad-57ae-ad12-3eff1bf7704d | note | HP
e5bd8232-8f33-573f-acf1-a05a38306b7e | note | RESPONSIBILITY: Fulton Hogan Engineer
cb41ed74-357c-5781-a1ed-baf819222a11 | textbox | Date Completed:
76c39ebc-62d0-4c3d-be2b-25f0c5964a49 | signoff | REQUEST HOLD POINT SIGN OFF
2c2f50b5-bb9a-4e45-9ba2-91ce89116d77 | section | Completion
ee7535d6-fbb5-4a6f-8fd4-5783b14a88ff | checkpoint | 3.1 Completion
382d5dd1-9e0b-53b0-93f5-1b3e3766919c | note | FREQUENCY: Each lot
5642da93-e1b9-5f43-ba90-7de163daf3d7 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste. Bluestone pavement is free of mortar stains and cleaned to satisfaction
77b89f3a-6712-5853-8e3d-e75aa01021cb | note | REFERENCE DOCUMENTS: Visual Inspection
b33e71e0-fbc5-51f4-9e9b-f853da82e949 | note | INSPECTION/TEST METHOD: Visual Inspection
4c407344-98db-5b2d-b9af-994897943ec1 | note | RECORD OF CONFORMITY: This ITP Signed off
eac5c9f3-89e9-509b-9737-7d2845ff7085 | note | IP
70e307a4-fced-5f79-b6f9-be82596888d7 | note | RESPONSIBILITY: Fulton Hogan Engineer
494d6bc7-7028-5fd9-807b-8116c1ac1716 | textbox | Date Completed:
fc4c4352-1444-4831-947b-04ed65da7e5a | checkpoint | Final Inspection
920badbf-d7cf-5263-a798-b907ed9a2c10 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
da5e0cbb-0608-5ba6-9d86-0fecb14305cc | textbox | Print Name:
9b7aa94a-118f-508d-be5f-eaed31536ef4 | textbox | Position:
3aedafbd-670b-5dee-89aa-3d6f4d1f5fe2 | textbox | Date:
80871329-bdcd-4bec-bc5b-7dbcc7b3791d | checklist | ITP-031 - Precast Stormwater Pipe Installation |  | ITP-031 - Precast Stormwater Pipe Installation
cb43fa44-2e2f-4f09-a104-2dc9bfefd580 | section | Preliminary Works
a2a3d341-e729-4e40-ad3a-6323202934eb | checkpoint | 1.1 Check for correct documentation
cdb385f3-3512-50b9-b475-c64ebf73e732 | note | FREQUENCY: Prior to commencing any activity
3223ec45-8b20-503c-be2e-f8e99623ea65 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
344bc3b2-8cf7-59ad-ad94-75c86b12ef54 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
485dd589-3c0b-543a-952e-a853f08dfe6d | note | INSPECTION/TEST METHOD: Visual inspection
a0eb09eb-9b24-5853-85dc-efcb2842ef6a | note | RECORD OF CONFORMITY: This ITP signed off
bc3de693-93aa-589b-bfa6-acf051b58987 | note | HP*
1b6d53a8-7c69-5bc2-a9ed-af1c5a97a653 | note | RESPONSIBILITY: Fulton Hogan Engineer
941b4ab1-2373-515d-a94c-eaaf196f9890 | textbox | Date Completed:
8b90be19-3f22-4b8e-ab5a-1a5838fa4d0e | checkpoint | 1.2 Implementation of all measures and controls
e546188b-8d64-593b-97d4-f1330b917fbf | note | FREQUENCY: Prior to commencing any activity
fe58b9cd-e1e4-5bb9-96ff-68562039ffaa | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
e0e5ea83-5b98-5c82-b570-3f1963bf0fb9 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
9c55124e-7aed-533e-bc2c-5c601641be2a | note | INSPECTION/TEST METHOD: Visual Inspection
07202c91-1ef7-50c2-870d-214470a7cb75 | note | RECORD OF CONFORMITY: This ITP signed off
3381c12c-3b65-5811-9468-e12bedf3932c | note | IP
d51edbab-c0dc-5806-9d8d-aba7630aafda | note | RESPONSIBILITY: Fulton Hogan Engineer
84074ef2-79a1-5e06-9502-20202539d8ec | textbox | Date Completed:
7451c7b7-9a9e-400f-8582-b9b4ee6c91f5 | checkpoint | 1.3 Pipe classification and delivery
6636086a-ff0a-5815-886c-3934b91f8126 | note | FREQUENCY: Each delivery
d8457e97-33d1-5fdc-81cb-81edd352653c | note | ACCEPTANCE CRITERIA: Pipes shall be of the size specified on the drawings and either: Socketed reinforced concrete to comply with AS 4058 - 2007, with rubber ring joints complying with AS1646 - 2007, or Fibre reinforced concrete including fittings, to comply with AS4139 - 2003. Condition and compliance of the pipe is to be inspected upon delivery.
4ad543a7-5c1c-5a36-9153-08a8179fd4de | note | REFERENCE DOCUMENTS: Cl 4.1; Appx 2: Cl 7.0; Dwg 1P50318
d731092f-ba4e-572d-9a53-99dadb855cc4 | note | INSPECTION/TEST METHOD: Visual Inspection
f8f56355-9f3e-5db8-9c85-0f268b41da80 | note | RECORD OF CONFORMITY: This ITP signed off
28613be2-7be2-50af-9b7f-130945927c20 | note | IP
810da3be-fd16-5996-9fc6-8777f77746ce | note | RESPONSIBILITY: Fulton Hogan Engineer
e2f36268-4752-5449-b990-874e5978eb43 | textbox | Date Completed:
8c14e83e-996b-4c28-89c5-1f0b86aff113 | checkpoint | 1.5 Backfill and bedding material classification
e28d78de-a8b0-5334-97a7-1d3e7b80ea31 | note | FREQUENCY: Prior to start
0ddb8a98-ced0-5ee7-b65f-dafcc28fd861 | note | ACCEPTANCE CRITERIA: All crushed rock used in the works shall be Class 2, 20mm nominal size. Sand shall conform with the requirements of AS2758 - 1998 and AS1141 - 1997 and shall have grading within the limits as defined in the code.
09477858-8880-57d1-b01e-1baea9e7059a | note | REFERENCE DOCUMENTS: Cl 18.0
6adb6493-bb3d-5675-8f7a-d08296b5bad5 | note | INSPECTION/TEST METHOD: Verify
1e3fb593-8b99-56e4-bb31-eb319f2b8fcf | note | RECORD OF CONFORMITY: Test reports from supplier
a5fd55e8-1d1c-5c45-a3dd-c19bd608ee9e | note | IP
54cc624b-4aac-5c79-97da-2e1579f73a0e | note | RESPONSIBILITY: Fulton Hogan Engineer
6e5f7b57-9f3b-58fc-9d21-ccc1d78a944e | textbox | Date Completed:
1652d220-3d6d-413f-9016-05fdfd080820 | section | Construction Works
c9dfcfed-faa1-478a-8a40-b4aa15fe3807 | checkpoint | 2.1 Set out drainage
3ade98a2-a1f1-5962-96c6-24143585ab97 | note | FREQUENCY: Prior to backfilling
8ebe8b22-50a9-5660-8108-0e355db0a2a4 | note | ACCEPTANCE CRITERIA: The line and level of all drainage lines and pits must be in accordance with the provided design drawings. The position of all drainage lines and pits are to be confirmed with the superintendent if ambiguity arises.
7f59848e-fcd8-5819-a790-806ae318cb3d | note | REFERENCE DOCUMENTS: Design Drawings Appx 2: Cl 8.0
1dbc62af-ede6-5d19-999f-db4c5072208a | note | INSPECTION/TEST METHOD: Survey Conformance Report
bef5083d-01e0-51bd-bbf0-44391cd55b75 | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off
d5efc9ec-1fd1-5641-bb73-25ab44d9ec21 | note | SCP
09f4a1c6-f2e4-5e6e-9684-bc84b2741af7 | note | RESPONSIBILITY: Fulton Hogan Engineer / Survey
283fa5a1-3d5e-5f25-ba55-15d07724b473 | textbox | Date Completed:
a97767c5-9bf1-4b3a-99fb-7d2767b2a5a6 | checkpoint | 2.2 Excavation
29979228-4ba5-59d5-aa15-c5431eb5b241 | note | FREQUENCY: Each trench
d15de657-eefb-5b55-b411-79be71ad78d3 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth greater than 75mm below the specified level of the invert of the pipe to allow for appropriate bedding. Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed. Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m. No stockpiles within 2m of end of the trench to reduce bearing pressure.
dfdff10a-bf31-5740-b6ff-568f0525f657 | note | REFERENCE DOCUMENTS: Appendix 2: Cl 8.0, Cl 9.0, Cl 11.0
376f4c1c-184d-5aa7-badd-196a474956ae | note | INSPECTION/TEST METHOD: Visual Inspection
e14fb186-30d6-555a-89a4-cf9f4ee492df | note | RECORD OF CONFORMITY: This ITP signed off
c16ecb21-eb9e-5b00-b2b1-a28f72944a0c | note | IP
30cf57c3-f7fb-508e-a143-4cdbc726b2ab | note | RESPONSIBILITY: Fulton Hogan Foreman
66ea3e69-e808-5bf1-911d-f613dbae3f18 | textbox | Date Completed:
0b96481b-6cff-4f9f-8320-aaf6b4111b90 | checkpoint | 2.3 Inspection of trench base
a5f6937d-9830-5a89-b76d-2ba4dbb060f2 | note | FREQUENCY: Each Lot
69b780c8-bb58-52ca-8015-55e547b04015 | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
fffe9e58-2185-5f52-8cc6-748167e45cbe | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0
d2995ae2-9497-5c33-9a30-fd59c5104be5 | note | INSPECTION/TEST METHOD: Visual Inspection
cc89e7d0-d6b2-5986-bf70-79dd231a6ccb | note | RECORD OF CONFORMITY: This ITP signed off
c43cff28-f122-5889-b092-abfd6fee1dd7 | note | IP
8404bc4a-4f50-5b16-ae22-f372a2214498 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccef1801-bf59-5aca-9f3d-bd75e78aeebe | textbox | Date Completed:
aa14746f-b4ac-44c6-ae43-e93fc970384f | checkpoint | 2.4 Placement of bedding material
bbe7347d-de94-50b0-81a8-b855607480c1 | note | FREQUENCY: Each Lot
9e147125-8df4-5016-8200-00f6db8b5206 | note | ACCEPTANCE CRITERIA: A 75mm minimum layer of consolidated sand shall be used to bed the pipes of the diameter specified on the drawings.
ad6afd50-f18d-55a7-b673-a0f6802cf2e8 | note | REFERENCE DOCUMENTS: Appx 2: Cl 9.0
9561e6f9-a877-5153-8e47-da823440fa48 | note | INSPECTION/TEST METHOD: Visual Inspection
056fb510-f9e5-5c6c-b736-6184d2dc948f | note | RECORD OF CONFORMITY: This ITP signed off
9fe5f03f-dd59-502e-94b1-1905b78a1405 | note | IP
4b9686e5-24c9-5ee8-aaaa-5e8fd24a2506 | note | RESPONSIBILITY: Fulton Hogan Foreman
4ffd3a91-b584-51d3-8c47-03af5d0567d0 | textbox | Date Completed:
dfdb1146-6342-4482-be2e-57b1e39aeb5e | checkpoint | 2.5 Placement of pipes
1847c87e-05eb-5a46-9b5e-61591b6f1cf1 | note | FREQUENCY: Each Lot
78db297f-9736-5dbc-b6de-df49dd95d25c | note | ACCEPTANCE CRITERIA: The pipes of the diameter specified on the drawings shall be laid on the bedding firmly for their entire length. All pipes shall be laid true to lines, level and grades, and shall be butted tightly together with lips. Rings must be in place between pipes and not dropped to be visible.
d3889d01-1343-56ec-913d-61852363bf69 | note | REFERENCE DOCUMENTS: Appx 2: Cl 9.0
6b959ded-69f6-539d-9996-03b9c12eceb7 | note | INSPECTION/TEST METHOD: Visual Inspection
3449efcf-80c3-5a6e-8aaa-0e392dc21a30 | note | RECORD OF CONFORMITY: This ITP signed off
62329db1-ded9-5bf4-8aba-367c89ce692d | note | IP
1268ef48-a80c-59bd-9d6c-990503fc0d24 | note | RESPONSIBILITY: Fulton Hogan Engineer
fe2e1a0d-8e05-5690-905c-54fd924f7d54 | textbox | Date Completed:
c5c21459-0294-4516-9404-c9714f85b0ce | checkpoint | 2.6 Sealing
a3bc3b0e-3c25-58a0-a4d2-1544ad711a27 | note | FREQUENCY: Each Lot
f58738ea-fcf8-50f4-bce4-03a839bcc261 | note | ACCEPTANCE CRITERIA: All pipes connections to pits shall be neatly made, and the ends of all pipes properly trimmed off and stopped with cement mortar.
d8e5e53b-17d0-5a6e-93de-968cc2f1bb8a | note | REFERENCE DOCUMENTS: Appx 2: Cl 12.0
ff9113be-1dc7-5dba-92bc-c02698608d15 | note | INSPECTION/TEST METHOD: Visual inspection
5f0a78a4-48dc-534b-81bd-23938637dd2c | note | RECORD OF CONFORMITY: This ITP signed off
2535a53d-ab42-52e6-b267-30991bebe6c3 | note | IP
3ee4f68c-9bd7-5aa0-84b8-015514975287 | note | RESPONSIBILITY: Fulton Hogan Foreman
f10727f6-d36c-5e8b-a901-32b692034e99 | textbox | Date Completed:
ccdb1fc8-038a-47b6-bd26-af6a42bf7357 | checkpoint | 2.7 Bandage Joint
c623ab40-df90-5c8d-8279-ae53ad4c9bd1 | note | FREQUENCY: Each Lot
f5e6bced-f5d5-586e-aa46-846778ab981e | note | ACCEPTANCE CRITERIA: Construction bandage must be constructed where 750mm pipe connects to existing in accordance with Melbourne Water standard 7251/08/420 with SL82 mesh and 40MPa concrete.
a1ad2f94-249c-5e36-ba40-80d67d7ce3d9 | note | REFERENCE DOCUMENTS: Melbourne Water Standard Drawing 7251/08/420
bc1edb9d-a705-53e9-be68-a8fd08baeb54 | note | INSPECTION/TEST METHOD: Visual inspection
0b5aa4e3-585d-5281-9327-fcdba8313a28 | note | RECORD OF CONFORMITY: This ITP signed off
caa311c7-185e-5ad7-85fd-eae1cf9bb93a | note | IP
b0617a17-ab1d-55c3-adcb-a2ff980b69af | note | RESPONSIBILITY: Fulton Hogan Engineer
0ee28f16-a922-578d-ab73-63c46a772df6 | textbox | Date Completed:
9c3e2911-c2c4-4d8d-8ca1-bf1524d8daf9 | checkpoint | 2.8 Inspection of Pipe Installation
350a1c87-2100-5cba-bd6f-1ff110ec486c | note | FREQUENCY: Each Lot
9ea370c5-ca53-5c78-b967-bef1e625ca7b | note | ACCEPTANCE CRITERIA: No further backfilling shall be done until the Council's Supervisor has inspected the work.
8b325c9f-b4e1-5448-a5cd-80a7a67cb9c4 | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
a63ca885-f223-5ffc-b872-a7a8da4a4506 | note | INSPECTION/TEST METHOD: Visual inspection
d4d7d5ba-9824-5438-8ff6-63081657a092 | note | RECORD OF CONFORMITY: This ITP signed off
5e014a38-e8d0-5272-a8a4-27d642c48893 | note | HP
6de879cd-f08a-59f6-9174-8ba2649ed7e1 | note | RESPONSIBILITY: Fulton Hogan Engineer / City of Melbourne Supervisor
bf3e9c8e-4144-5759-b858-65d2af2c03a2 | textbox | Date Completed:
a86a5ca1-724c-44cf-afd7-a2cea166302f | signoff | REQUEST HOLD POINT SIGN OFF
acca8e23-d483-4d37-86d4-952e4aa8a6bc | section | Testing
52af1f48-fac3-4548-b40e-b605207c3272 | checkpoint | 3.1 Crushed Rock Placement & Compaction
d550144e-abb4-5ebc-b5fb-5ad940bf7087 | note | FREQUENCY: Each Lot
1acbdd59-fec3-5d30-9ae7-0dad2f55866a | note | ACCEPTANCE CRITERIA: The trench shall be backfilled with Class 2 crushed rock to the springing line of the pipes immediately after completion of laying. Further backfilling shall be with layers of crushed rock, Class 2, no thicker than 150mm compacted to 95% Modified Relative Compaction.
acfa716b-e823-5685-916d-400da1bc343c | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
ae0cc798-69a0-5a82-be68-2317dfbb4cb6 | note | INSPECTION/TEST METHOD: Verify
d9356e2d-5908-5af6-87b3-f683a990f847 | note | RECORD OF CONFORMITY: This ITP signed off
14ae4068-d88a-5818-82dc-c06e9ef412bd | note | TP
33d10156-f16e-5610-be03-e42c64707863 | note | RESPONSIBILITY: Fulton Hogan Engineer
ac201eb2-56cb-55b2-8637-e60dc118db93 | textbox | Date Completed:
0dc87804-d4fe-4ff7-b887-513f06582e0b | checkpoint | 3.2 CCTV Inspection
11116eba-1ffe-5657-a4ea-dfdc706aadd3 | note | FREQUENCY: Each Lot
a3af7d5d-1d63-5f14-80b3-f278b2ccde80 | note | ACCEPTANCE CRITERIA: All drainage lines constructed beneath pavements are to be inspected by CCTV.
ae940c40-b7df-5357-8fa6-a468f0e93763 | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
751d2cde-3587-549a-91e0-aab80be65f3d | note | INSPECTION/TEST METHOD: Verify
709f5b6a-a5fb-5d2e-8ef1-090a285630f1 | note | RECORD OF CONFORMITY: This ITP signed off
8638d594-d8b6-5831-804f-5e4f6a18982b | note | TP
4d2da017-a61c-57a9-8fd6-d0b792a150cb | note | RESPONSIBILITY: Fulton Hogan Engineer
d6207561-9220-5a5e-a4f2-a885ede980fa | textbox | Date Completed:
98bce6ce-fec3-47bb-9fa4-13a9f670efb4 | checkpoint | Final Inspection
b70a0e05-4f4b-564f-9faa-aca495cc2f70 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
0355a40b-3d40-579a-a7d4-b951aacc73a4 | textbox | Print Name:
ff00e4c4-80f0-5e54-8c32-af0b733f9f11 | textbox | Position:
9f74a7a5-a468-55ec-972f-d221dca76024 | textbox | Date:
c5c88ae7-98b9-4060-a672-3dd414d8ef27 | checklist | ITP-032 - Orca Island Installation |  | ITP-032 - Orca Island Installation
85cf0213-5784-4b70-8a66-549d5f606344 | section | Preliminary Works
a7a6e5fc-0ece-47b6-9fa2-4a489c493b68 | checkpoint | 1.1 Check for Correct Documentation
59cfbaa8-a8b8-52cc-984e-418aa3abab55 | note | FREQUENCY: Prior to Commencing Activity
de752495-8dbe-5ce0-87e1-a214fcb25283 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
50739957-d3b7-5213-b2ac-6a55c57a6042 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
f051c969-1b2e-51a9-8e32-bbc81da0c353 | note | INSPECTION/TEST METHOD: Visual Inspection
e2561d01-0e6e-5723-8dd7-16cd6801f121 | note | RECORD OF CONFORMITY: This ITP Signed off
2b91a9dc-5f6e-527f-94ed-3df5bb0b7b36 | note | HP*
9d7a9c82-b320-54cd-8721-7022bd92d0c5 | note | RESPONSIBILITY: Fulton Hogan Engineer
daa30b17-1d35-5595-be4d-b98c19223f63 | textbox | Date Completed:
2c4f5d3e-e19a-4d76-aa8f-e4e72a16bdb6 | checkpoint | 1.2 Implementation of all measures and controls
18892569-6400-5e8e-bb15-8543283ff710 | note | FREQUENCY: Prior to Commencing Activity
7f5fcadd-e5e0-50e1-8af5-94146e8d3758 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
7b93c346-79ba-5028-a300-5d0a83c46dd4 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
a099a9a4-c5c5-58fd-b572-1bd66339343d | note | INSPECTION/TEST METHOD: Inspection
cc182ecc-16ab-5a93-b63b-fe364238659f | note | RECORD OF CONFORMITY: This ITP Signed off
9f57672d-303c-5434-b77a-1476ca4f6e20 | note | IP
d0072b76-bb7d-5738-98bc-36749a1027f2 | note | RESPONSIBILITY: Fulton Hogan Engineer
84731356-2d73-58f0-b197-bbb78e5cfb27 | textbox | Date Completed:
6c9c5be7-7b5b-4092-87f7-ebc12396b499 | checkpoint | 1.3 Check Materials
ab3bb1d0-5e1f-5ddc-be71-53f460185139 | note | FREQUENCY: Each Delivery
af0b7a77-2f2b-5ff7-b246-daf2154649a7 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
105381bf-c010-5bc1-afa7-841aab593d59 | note | REFERENCE DOCUMENTS: Receivable Inspection Checklist
c74c084a-5fbc-54bd-b858-f3c3725644ce | note | INSPECTION/TEST METHOD: Inspection
3bc0eaae-005d-54e2-8810-b2733cfe41a9 | note | RECORD OF CONFORMITY: This ITP Signed off
0c368bf9-522d-5cff-8be5-480fdcb7b9a4 | note | IP
a09df259-f857-5138-88b6-d246bb2f7afe | note | RESPONSIBILITY: Fulton Hogan Engineer
9f6b177f-7e9a-5ac6-9ac4-911b2682be50 | textbox | Date Completed:
ad863e19-1786-446c-85a6-f5500dec3653 | checkpoint | 1.4 Setting out
8363cd56-0c35-5fd4-9628-2e9389e84b0b | note | FREQUENCY: Each Lot
e35f60c7-5ba7-5436-818a-8f8a58359ef6 | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans Alignment of new separation kerb and islands shall be marked out using string line
609681cb-f391-53ee-b5e7-b0fe6ea37bf8 | note | REFERENCE DOCUMENTS: Work Procedure
e55fb4aa-546f-5a72-9747-077e2a8d7531 | note | INSPECTION/TEST METHOD: Inspection
3f21009f-a27a-53ed-8b6a-1b5f6d86c61d | note | RECORD OF CONFORMITY: This ITP Signed off
b7b83f67-5d8e-54e4-95fc-2fad2bd30483 | note | WP
4804fdc3-9edc-513e-b639-a7b775cd4426 | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
75fb96ee-80a6-5dbf-bb87-17dac0f4538e | textbox | Date Completed:
bddce686-383c-4e55-98ee-f10f01ee2c68 | section | Construction Works
91905c5a-b9b7-4914-a5c2-2595b0671442 | checkpoint | 2.1 Base Preparation
8c9a7879-2992-5855-a24a-85c5f715dcf4 | note | FREQUENCY: Each Lot
6c4e87ab-04a9-5db9-8793-719843610c6a | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign loose materials and water pooling. IF required glue foam tape to the road where channel will be placed to ensure containment of adhesive.
a897b5f9-184b-5e23-809e-12896cc2ca7e | note | REFERENCE DOCUMENTS: Orca Installation Guide
2f1ed3a6-dd2b-57b7-bd91-311d8b401644 | note | INSPECTION/TEST METHOD: Visual Inspection
ee121277-4464-51fb-a579-9d93956ec3b4 | note | RECORD OF CONFORMITY: This ITP Signed off
cc3d8ec2-59ea-59c0-a2c5-a24f46bb5dc3 | note | IP
4552939d-5805-5fd5-9343-366dd5f1f8f2 | note | RESPONSIBILITY: Fulton Hogan Engineer
638befcd-3f0b-5cd2-87d8-d7ccee31caac | textbox | Date Completed:
b3d49de4-d310-4462-9188-ef57e778a2e4 | checkpoint | 2.2 Preparation of Orca Polurethane (Adhesive Agent)
2426beb4-a069-589f-97d0-07ac63a56746 | note | FREQUENCY: Each Lot
9e61fb96-8f08-5768-b1c1-1059b835114d | note | ACCEPTANCE CRITERIA: Mix Orca Polyurethane as follows: - 2 parts of Part B Polyol Black - 1 part of Part A MDI Using a paint stirrer in a drill, stir for a minimum of 4 minutes. Once Part A & B have been mixed, add 1:1 Part C Rubber Compound in the mixed A+B compound and stir again for 2 minutes. Ensure even mix throughout the adhesive.
308d4521-d8d7-53e5-92ec-493f57ef816d | note | REFERENCE DOCUMENTS: Orca Installation Guide
d1956aef-160d-5e21-81b0-d9c6286274eb | note | INSPECTION/TEST METHOD: Visual Inspection
4ed7fec6-570b-51df-8146-841ab259ead4 | note | RECORD OF CONFORMITY: This ITP Signed off
3d6c3a94-8c20-5a9d-882d-1dffcf3891c0 | note | IP
a69cf8bc-1d2e-556d-b01f-52779f5da28c | note | RESPONSIBILITY: Fulton Hogan Engineer
b1adbf5b-413a-5118-9492-deae056494f3 | textbox | Date Completed:
a22e4f17-81a1-41ee-8a4f-5df05d5b498c | checkpoint | 2.3 Placement of Orca Polyurethane
3f93e246-1555-5ba5-b798-53dc8c80b7a5 | note | FREQUENCY: Each Lot
318cdded-0d31-5371-9830-88432aede8cf | note | ACCEPTANCE CRITERIA: Pour the Orca Polyurethane compound onto the road, spreading to a thickness of approximately 2mm.
ebb14c76-76a5-5f3c-9158-33b230ca9edc | note | REFERENCE DOCUMENTS: Orca Installation Guide
dfdcb997-e5bc-5f82-a102-ee5769427b95 | note | INSPECTION/TEST METHOD: Visual Inspection
c5784f2e-74fc-5be7-bcd2-63dbda4fd356 | note | RECORD OF CONFORMITY: This ITP Signed off
af043eca-3f1f-56dd-8a2a-6f4d08d15fdc | note | IP
30aa9523-c787-5d64-bf2b-53721d91f8a3 | note | RESPONSIBILITY: Fulton Hogan Engineer
8650bab4-bfe4-5567-bb11-0609e03c1bae | textbox | Date Completed:
e824f497-e4d6-4bd4-983f-d79a772833b9 | checkpoint | 2.4 Placement and Securement of Orca Island
2cd0053c-bd8d-5426-ad86-af06edf33814 | note | FREQUENCY: Each Lot
712e9f31-5a40-5aff-b5c5-d072b442d033 | note | ACCEPTANCE CRITERIA: Lay the island on the polyurethane material. Drill holes through island fixing hole into road surface, then screw island down securely with 12mm x 150mm coach screws and mudguard washer. Ensure screws are all the way down to secure island. Plastic plugs to be put in bolt holes.
2794af55-5736-5c9f-a490-38c5a376b4fd | note | REFERENCE DOCUMENTS: Orca Installation Guide
549d46d8-a420-5860-a7f5-84a95554dee5 | note | INSPECTION/TEST METHOD: Visual Inspection
6aed28a8-b3c6-5827-afe7-0fa44c7ffb48 | note | RECORD OF CONFORMITY: This ITP Signed off
d43ccbd0-db13-5199-aeab-a7eda4fcb2ac | note | IP
9f8345b7-a2ff-5f64-b712-470b59091b81 | note | RESPONSIBILITY: Fulton Hogan Engineer
bbe7fe02-d3cf-59ff-aba1-9c9dfadd0363 | textbox | Date Completed:
9d07b370-f253-4724-b615-ee430c262e98 | checkpoint | Final Inspection
31d3b027-31ec-5a5c-9892-35cd1a8c0dca | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
8bac44dd-5e18-5316-8fc2-ded1d7d59227 | textbox | Print Name:
93da29e9-afd7-5b14-88c3-f97695f4ebb1 | textbox | Position:
bfef5598-cac3-5682-bc07-3481aacfd539 | textbox | Date:
b9a3bbcf-ee0a-4fd2-aa2f-d22e69a2c7eb | checklist | ITP-033 - Insitu Concrete Pit |  | ITP-033 - Insitu Concrete Pit
646bbf3b-f00c-4265-9df6-fc3ffe83fa29 | section | Preliminary Works
816c912c-71f7-4b5c-a899-47cdacbc53c2 | checkpoint | 1.1 Check for correct documentation
d2990ba7-ada6-5dff-afab-1ae3beb16e7e | note | FREQUENCY: Prior to commencing any activity
63293069-7df6-5ec3-b1dd-751e8b83b91d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
6d13e60b-beab-5241-9770-0155b4bd607a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6f560b21-261e-5e7c-9849-f9b33ccec8bc | note | INSPECTION/TEST METHOD: Visual inspection
dab88ffd-4497-50e7-a52f-22399e3a2bf6 | note | RECORD OF CONFORMITY: This ITP signed off
038293bc-89e4-5919-94a5-4827d580315a | note | HP*
04f121a8-22a9-5a39-80a3-1e297b31d3b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
f6480e2b-b21a-5a60-806c-daf90c9e56d3 | textbox | Date Completed:
d689c02a-55ef-4e47-a8bf-27db1cc06bdb | checkpoint | 1.2 Implementation of all measures and controls
638c1463-12a8-5456-8c4c-26eaf673f9df | note | FREQUENCY: Prior to commencing any activity
aa74b322-eb0e-58c0-92c8-f63b86386a99 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
e8b3c9a0-7217-5b16-994a-3d677aca2c20 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
a38d568b-a126-5a43-b889-068eb26e5c00 | note | INSPECTION/TEST METHOD: Visual Inspection
6bdc116e-84e2-5358-9a2e-5f633e0b4a6d | note | RECORD OF CONFORMITY: This ITP signed off
73c4c175-3c36-5b31-9e93-c8779c8a3c29 | note | IP
799747d3-09c2-53b1-91d1-e0957c9ae2dd | note | RESPONSIBILITY: Fulton Hogan Engineer
664aa47f-c4b1-5f6d-af37-f745e228ac0c | textbox | Date Completed:
a2b67dfa-0e67-447e-b0bb-029d77de0c3e | checkpoint | 1.3 Pit material classification
52187fa1-7f56-55a4-94d4-b48ae8228cc4 | note | FREQUENCY: Each delivery
22f19105-e74c-5056-8576-d521d8d7f2c7 | note | ACCEPTANCE CRITERIA: Concrete used shall have a minimum strength of 32MPa and be. Steel fabric shall be SL82 reinforcement and conform with the requirements of AS4671-2001.
7710b1e0-cec9-55dd-8ff4-acf553536261 | note | REFERENCE DOCUMENTS: Dwg 1P50318
53d5aa47-b908-5db3-9dbe-4d199c5adc01 | note | INSPECTION/TEST METHOD: Visual Inspection
14d9745e-32a7-5edc-9973-1436e7babc4b | note | RECORD OF CONFORMITY: This ITP signed off
5c333421-a415-544b-a03b-344d095a2b64 | note | HP*
bc70b1dd-d03d-5a1f-a916-586d069a29a4 | note | RESPONSIBILITY: Fulton Hogan Engineer
067eb19b-2524-5ce2-8f93-5c85c823c8de | textbox | Date Completed:
9b2863ee-4f72-4a12-8c5a-df0fea285b1c | checkpoint | 1.4 Backfill and bedding material classification
efa19785-4b3d-58a2-af49-1eb78a3b3046 | note | FREQUENCY: Prior to start
78e0ca57-8f95-5955-a33d-d040d823cd70 | note | ACCEPTANCE CRITERIA: All crushed rock used in the works shall be Class 2, 20mm nominal size. Sand shall conform with the requirements of AS2758 - 1998 and AS1141 - 1997 and shall have grading within the limits as defined in the code.
60adfc2f-6599-5bf8-94e6-90bcb3f4b00d | note | REFERENCE DOCUMENTS: Cl 18.0
6e47baed-507d-5f60-adad-af102cdb2e28 | note | INSPECTION/TEST METHOD: Verify
a6782468-f064-5a2b-a3a1-7d92135769a3 | note | RECORD OF CONFORMITY: Test reports from supplier
17dc9f1f-7ef8-5aac-8b3e-26ee4fb88e02 | note | HP*
e4f4ebae-a019-533f-904d-8283d04ff9c5 | note | RESPONSIBILITY: Fulton Hogan Engineer
aae5d3a4-a4e8-57c4-8a21-ed7de60a8747 | textbox | Date Completed:
5b76516d-cced-4238-8319-96e7f28760b7 | section | Construction Works
12a3c39c-578c-4049-958d-665038e9bdbd | checkpoint | 2.1 Set out pit location
d01e5ea9-aa28-5be9-9f2d-a789d24b2810 | note | FREQUENCY: Prior to backfilling
ec261a44-49cb-5c84-9fc5-0c43e11f2dd8 | note | ACCEPTANCE CRITERIA: The line, level and location of all pits & structures must be in accordance with the provided design drawings. The position of all pits are to be confirmed with the superintendent if ambiguity arises from the drawings.
f6d52be1-d21b-5be8-9efb-308c8eadd428 | note | REFERENCE DOCUMENTS: Dwgs Appx 2: Cl 8.0
018895b1-d81b-5534-956a-0e98de49f6f5 | note | INSPECTION/TEST METHOD: Survey Conformance Report
8a6617fb-72cc-52c0-8978-22454a04befa | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off
e8d394bf-a8ad-5102-8af5-09588d3bf89f | note | WP
3a8f319a-ae62-5d04-8d41-c6dd1f36b38b | note | RESPONSIBILITY: Fulton Hogan Engineer
88edc0e5-f855-58f6-a2a1-049d89444b86 | textbox | Date Completed:
d16a4fcb-63bc-405a-adf6-0e99543fbd4f | checkpoint | 2.2 Excavation
edb206f1-efba-51d0-908e-cfb682d5b2c2 | note | FREQUENCY: Each trench
04606e24-96a4-5bdd-80ac-e8d90feb1c6c | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth greater than 75mm below the specified level of the invert of the pipe to allow for appropriate bedding. Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed. Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m. No stockpiles within 2m of end of the trench to reduce bearing pressure.
a24221a7-4bbf-597d-ba7a-f52c128627f2 | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0, Cl 9.0, Cl 11.0
bf157885-cdc9-505b-8789-90543c1ab74f | note | INSPECTION/TEST METHOD: Visual Inspection
4d1ff526-2648-5065-8b6e-f3abf7f10f84 | note | RECORD OF CONFORMITY: This ITP signed off
14389dbd-f4cd-56cc-b21d-bd56f0ac1e63 | note | IP
c4ed7ca7-e8d5-5423-8503-281d27c9d29c | note | RESPONSIBILITY: Fulton Hogan Foreman
425f52c2-dc6e-5bbd-b448-a1d0a6edbf4a | textbox | Date Completed:
2e664806-7cc3-4d6e-8ae3-0540f81e97d5 | checkpoint | 2.3 Inspection of trench base
ae5fb236-84ad-50db-bda2-052999efbded | note | FREQUENCY: Each Lot
55c13594-c890-509c-9e8b-60c301270cd4 | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
a738f250-d073-5130-8374-fd321a8334f2 | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0
b95d1139-9bb2-583b-8452-54c30ba3c6d5 | note | INSPECTION/TEST METHOD: Visual Inspection
21ff7196-04a1-5bd6-8ff5-109925bdc0b8 | note | RECORD OF CONFORMITY: This ITP signed off
6cb370ec-6a79-5d19-9924-dd36095f07d4 | note | IP
c501ec82-5ac1-5434-9174-b0c466f2bafb | note | RESPONSIBILITY: Fulton Hogan Engineer
24693771-460f-5093-be28-85a9ee305a42 | textbox | Date Completed:
30e06b91-471b-41ec-bd46-8c5f0aa9784d | checkpoint | 2.4 Placement of bedding material
26a66305-6d77-5fb2-a77e-6207e18a4384 | note | FREQUENCY: Each Lot
a605daeb-63fe-5055-a7a4-628c19507a3d | note | ACCEPTANCE CRITERIA: A 75mm minimum layer of compacted class 3 crushed rock shall be used under base of pit
fd47632d-c7fd-5171-b1ee-8cfc56bec5e6 | note | REFERENCE DOCUMENTS: Dwg ELPOD-2021-17
62698e4b-41a3-5ac8-a751-0ac570659e26 | note | INSPECTION/TEST METHOD: Visual Inspection
b3326d67-fb3e-5455-8f15-3d8b73e932ed | note | RECORD OF CONFORMITY: This ITP signed off
aa46cb81-973b-56ed-814e-eaba03bf59de | note | IP
8d4cf218-5f80-5e00-a634-c82cbca04dc9 | note | RESPONSIBILITY: Fulton Hogan Foreman
997ef97c-2e67-55bd-868a-dcbd41ad91c3 | textbox | Date Completed:
80dc04e1-6994-4848-8319-eaf5ff3bc1af | checkpoint | 2.5 Concrete pre-pour inspection
ea8c0afe-3f1d-505e-a26d-4e05faeb4137 | note | FREQUENCY: Each Lot
449a5ea6-468b-5dc4-b7db-806a8ffc1a47 | note | ACCEPTANCE CRITERIA: The site of the concrete pour for the cast in-situ pit shall be inspected by a client supervisor before proceeding. Reinforcement shall be check for correct cover & lap as per drawings
371828bd-af62-571d-8be8-558a2dfcd8a5 | note | REFERENCE DOCUMENTS: Dwg ELPOD-2021-17
ef24a2ff-6cb0-5e20-baf4-c95246d5d265 | note | INSPECTION/TEST METHOD: Visual Inspection
76118506-9aae-5621-9948-ab7c6ddbc99d | note | RECORD OF CONFORMITY: This ITP signed off
ff1f006c-76f3-5550-8186-b206a4c9e111 | note | WP
12a8556f-1599-5d28-9d68-f50b3b9d0ead | note | RESPONSIBILITY: Fulton Hogan Engineer / City of Melbourne Supervisor
f5f0cc6e-276e-5ada-9530-79b096e0d367 | textbox | Date Completed:
47efbf3e-a587-489c-8cef-40fd5995c832 | checkpoint | 2.6 Concrete pour and pit construction
0ff62b93-8da6-5522-be77-2d3704c5d182 | note | FREQUENCY: Each Lot
def4888d-7ed5-5d92-933a-807141feec8e | note | ACCEPTANCE CRITERIA: All pits are to be constructed in accordance with City of Melbourne's Drainage Specification 2012 and Standard Drawing 1P 50318. All pits are to be constructed in accordance with City of Melbourne's Drainage Specification 2012 and Standard Drawing 1P 50318. Pit should also be constructed in accordance with site specific drawings. The walls and slab of the pit shall be 150mm concrete reinforced with SL82 mesh placed centrally. Minimum concrete strength of 32MPa.
4ff4150f-d9fa-52c7-ab18-0284e00abc9b | note | REFERENCE DOCUMENTS: Cl 4.1, Dwg 1P50318
a6ee1354-8f7c-5207-9c10-4b8166b71b6d | note | INSPECTION/TEST METHOD: Visual inspection
1b39a138-b509-5b62-adce-17b399e188e6 | note | RECORD OF CONFORMITY: This ITP signed off
b6da5a3c-c1d4-5159-8374-354cdeb44198 | note | IP
8f4012ec-c34e-52a7-aa3e-2a3cf0d830a5 | note | RESPONSIBILITY: Fulton Hogan Engineer
d75493db-4e8f-5fa9-8948-972befe8d8d1 | textbox | Date Completed:
e8f172e9-04cd-44cf-8d8b-d5840b9edc41 | checkpoint | 2.7 Pit base shaped with concrete to match pipe invert
f7b0ff29-9899-5709-b2e9-3dbd0cb81ca2 | note | FREQUENCY: Each Lot
37e66c5d-6931-5e15-981d-ebcb2a91e20e | note | ACCEPTANCE CRITERIA: Construct as shown on Standard Drawing 1P50318
2ecf2ac4-b917-5d2a-863e-b6e1b09d1e95 | note | REFERENCE DOCUMENTS: Dwg 1P50318
59638440-a14c-5845-80de-5950a6ddfa17 | note | INSPECTION/TEST METHOD: Verify
c3a9914b-5bca-5ded-8756-2595a076eba3 | note | RECORD OF CONFORMITY: This ITP signed off
fccf87b7-b1c6-50e0-9796-88fe7f476534 | note | IP
98e4c6d8-3485-5eee-9743-5466adacc5e9 | note | RESPONSIBILITY: Fulton Hogan Engineer
6ac3f5ba-f4b1-59d8-bbfe-152f301b14aa | textbox | Date Completed:
6010dca2-a345-4382-815c-6ffd8d2528c1 | checkpoint | 2.8 Placement of pit covers
352f595b-ac23-56ca-8e4a-58a02442e51e | note | FREQUENCY: Each Lot
7bbd7b1e-aed8-5e00-abdb-e52c3b8eaafb | note | ACCEPTANCE CRITERIA: All pits shall be fitted with standard City of Melbourne covers specified on the drawings of appropriate class.
b6412b0a-3e1f-5192-a46a-f9ee4856761d | note | REFERENCE DOCUMENTS: Appx 2: Cl 12.4
e125a20d-a409-56e5-8b07-0d0d56f98c40 | note | INSPECTION/TEST METHOD: Verify
7659c38a-be9d-587f-88b4-9fa9978e5160 | note | RECORD OF CONFORMITY: This ITP signed off
44e5bb05-8228-53de-b643-c7fda1be682d | note | IP
fc4d5db1-1238-581c-9415-ba5177d1c0c9 | note | RESPONSIBILITY: Fulton Hogan Engineer
b307e88c-14d2-5d7f-888d-96f6554592ca | textbox | Date Completed:
b9ed2fa3-829c-4132-a728-8f41a71a85c4 | checkpoint | Final Inspection
7d0e95c0-1c3e-58ba-b54c-befa51eab828 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f39cbd64-9a05-5b33-b558-cf761ca1fdd9 | textbox | Print Name:
5a181708-1c96-5923-9c11-4e97db3564d6 | textbox | Position:
0c00c6ee-5226-566c-ac47-8d90c75f7190 | textbox | Date:
de86af6c-b39a-49c1-a9dd-950af0bdeb03 | checklist | ITP-034 - Safety Zone Construction |  | ITP-034 - Safety Zone Construction
592c053d-4de9-4506-8dda-832c102b4c8f | section | Preliminary Works
c32c0172-a1c0-46a4-b021-57207240eab9 | checkpoint | 1.1 Check for correct documentation
0fc069c3-8a9d-52b5-a723-d58e8e039d47 | note | FREQUENCY: Prior to Commencing Activity
ec4adba3-fe97-5e02-847f-1b169713e6c7 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
a8fce97a-0e78-58fe-8dbf-d52940da31fc | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
bfa90eb7-bf54-5484-b943-0dfa2e20d87d | note | INSPECTION/TEST METHOD: Visual Inspection
59457f23-7141-5d47-bd79-933af3af11c6 | note | RECORD OF CONFORMITY: This ITP Signed off
ef4bcf8a-9cee-5098-bb97-154007e55d23 | note | HP*
c8f62898-1f30-579e-81d7-d340f9a8de7c | note | RESPONSIBILITY: Fulton Hogan Engineer
ccf61aaa-8350-52da-8a46-f8682e51996e | textbox | Date Completed:
5214b235-c8ad-4fef-9db4-e8dd7f1a021b | checkpoint | 1.2 Implementation of all measures and controls
fca4106f-7482-5365-b02d-fe624cb043e6 | note | FREQUENCY: Prior to Commencing Activity
23733788-acf7-50e7-8d05-d43c78afbc29 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
61050be2-503c-5e9c-89e2-c8f20eaa2c08 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
f3759995-54c0-5dc9-a98d-a274902fbc98 | note | INSPECTION/TEST METHOD: Inspection
d9808507-6595-50d2-a1cb-a707ca4be3f2 | note | RECORD OF CONFORMITY: This ITP Signed off
fa980c01-1c2e-5296-ba07-4f869d577686 | note | IP
8b71d6e4-e095-5595-8f23-a25198fe0a66 | note | RESPONSIBILITY: Fulton Hogan Engineer
5d3b30d9-c8f3-5124-803a-4c452768c15c | textbox | Date Completed:
cb65326e-08f3-4d13-9700-34748f090501 | checkpoint | 1.3 Material classification
bcc1c52b-0370-572c-ae6d-0fe4d4b99fa4 | note | FREQUENCY: Each Delivery
9abfabb2-c969-51c3-8e43-717fc78dca2b | note | ACCEPTANCE CRITERIA: All kerb shall be inspected at delivery for visible damage. Ensure correct single panel Type A fencing & sleeves are being used and are free of damage.
4b8235b1-f359-5717-af71-d899cab72604 | note | REFERENCE DOCUMENTS: STF T6107
9904d9cd-7d4b-5027-8454-9e0741a6cd91 | note | INSPECTION/TEST METHOD: Inspection
de7c5b00-50c3-5061-bf01-64e986344444 | note | RECORD OF CONFORMITY: This ITP Signed off
baeb4500-b721-5948-9b0a-0b03db131bf2 | note | IP
a05e7f13-b47d-556d-96b9-ce8784cd6337 | note | RESPONSIBILITY: Fulton Hogan Engineer
5ab49eb0-efc2-55da-aca0-50bf3f8bf455 | textbox | Date Completed:
5361fbc1-13d3-47a4-ac64-4394e55e3185 | checkpoint | 1.3 Setting Out
1a2ab982-973d-5d83-a6e8-606e1887f37d | note | FREQUENCY: Each Lot
708050d5-a8c4-5004-8900-0cb624671cf5 | note | ACCEPTANCE CRITERIA: Line and level of kerb, fencing & linemarking shall be set and marked out according to the design and standard drawings.
37af523d-bf54-5d53-ac0c-94b13060f6de | note | REFERENCE DOCUMENTS: Design Drawings Dwg P15671
94aaa178-18fc-5ea2-a934-93a373ef2640 | note | INSPECTION/TEST METHOD: Inspection
900df7a1-6ee8-5d5c-8d00-6b8b00310a38 | note | RECORD OF CONFORMITY: This ITP Signed off
e1352696-9da5-515c-b9fe-8dda823e7e17 | note | WP
8f87863d-7e44-519d-a55d-c1110be9016f | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
50fe781f-0784-52af-bbd4-5576bbbaa7f6 | textbox | Date Completed:
76dc6b2a-c524-4f0f-9e4c-3f64cd7a521d | section | Installation of Concrete Kerb
c2c597d3-805c-44e7-ba42-3c76f61a44ac | checkpoint | 2.1 Base Preparation
81dac243-3175-5ddb-8bb1-8ca1b0eda300 | note | FREQUENCY: Each Lot
573f5f6a-b550-501b-99bf-699b87db47da | note | ACCEPTANCE CRITERIA: Pavement base shall be inspected to be solid free of loose materials.
74648c53-7a77-58be-adfd-692c85fba7b6 | note | REFERENCE DOCUMENTS: Dwg P15671
d9f7cbac-2559-5694-b4fb-489fe862907a | note | INSPECTION/TEST METHOD: Visual Inspection
dd179456-965a-5262-a092-8c46f58300c8 | note | RECORD OF CONFORMITY: This ITP Signed off
d0ebf45c-11a7-57c8-b0d1-06a25268c0de | note | IP
55ea7807-de49-5831-b4a8-0eacdcd881b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
cbae07f7-e235-559e-a0d5-6a3d3a00eefe | textbox | Date Completed:
b2c8db37-84b1-4d1c-8a64-461608f0bf6d | checkpoint | 2.2 Drilling of Holes
95ebc4af-41c4-5a55-8504-9ac24fffda38 | note | FREQUENCY: Each Lot
dfb44868-9816-58dc-af5d-d3084c61a2e8 | note | ACCEPTANCE CRITERIA: Location of holes drilled must align with the provided design drawings. Two holes per stone shall be drilled to an approximate depth of 130mm. The width of the hole drilled shall be minimum 4mm larger than the width of the pin to allow for Chemset material.
b211d74f-4380-55cd-a54b-dcfe42fbedae | note | REFERENCE DOCUMENTS: Dwg P15671
b4d8ee3c-3c18-5b99-8111-c47a4472f84f | note | INSPECTION/TEST METHOD: Visual Inspection
c0f1d7eb-479e-5f85-9b32-e3ef5d2c31f6 | note | RECORD OF CONFORMITY: This ITP Signed off
8487bee7-c608-5f7a-8252-151a62252e97 | note | IP
e9646013-db5d-5a5c-bbdf-c6e59ba6c86d | note | RESPONSIBILITY: Fulton Hogan Engineer
2daba6f7-b059-588b-bce9-dc6a0aa0a236 | textbox | Date Completed:
25b49dbe-e8a4-4003-b64f-6769eda84bb2 | checkpoint | 2.3 Placement of Kerb
cbbc7fe1-9c83-50d5-afb7-b2190b597323 | note | FREQUENCY: Each Lot
c001d2d9-fd9a-594a-ba8b-d4d38cf75c20 | note | ACCEPTANCE CRITERIA: Apply Chemset material and position kerb stones such that the pins sit in the holes allowing the stone to lie flat on the pavement.
e7399f23-f6bd-5a7d-a03e-ef8b33935d0b | note | REFERENCE DOCUMENTS: Dwg P15671
d67ff664-d461-5293-a2ab-9c3bfb7d13a5 | note | INSPECTION/TEST METHOD: Visual Inspection
6021cebf-35bb-5157-8071-b0e3a82ded04 | note | RECORD OF CONFORMITY: This ITP Signed off
abdc4403-8049-5977-a8a9-26bcc64e4b53 | note | IP
83b6cf50-c75c-50ac-893f-28ce235d7a5b | note | RESPONSIBILITY: Fulton Hogan Engineer
a4826c22-1842-50dc-92f1-d436fb9c75f7 | textbox | Date Completed:
5e9af24b-6a18-4eb4-832d-bfabcc2d3324 | section | Installation of Single Panel Guard Rail
bac37641-fd11-4bfa-a767-9560f5229b03 | checkpoint | 3.1 Installation of Rail Post Sleeves
913f1405-6715-5511-ab95-af09b6d9aef6 | note | FREQUENCY: Each Lot
d115328d-68f8-5337-b164-0e9210f8a0c9 | note | ACCEPTANCE CRITERIA: Location of post sleeve's must align with the provided design drawings & 2.4m spacing. Core two 100mm diameter, 300mm deep holes per panel at 2400mm centres. Insert post sleeve and secure using non-shrink structural grout.
cae17f7e-6158-5750-bcfe-e3b10fada6a9 | note | REFERENCE DOCUMENTS: Dwg P15671
135e1168-14e7-5a91-82df-a93ec5fdff14 | note | INSPECTION/TEST METHOD: Visual Inspection
aa24cbc8-d4db-5d56-8ad9-95f62d66d608 | note | RECORD OF CONFORMITY: This ITP Signed off
5fd1bab7-7b8b-5e14-9a41-207e3bc371bb | note | IP
869bfc51-ebc0-53a4-9774-1cc48477e078 | note | RESPONSIBILITY: Fulton Hogan Engineer
087a78dd-4cf1-5043-ae46-ffe9cf53baaa | textbox | Date Completed:
9750ec5f-1fb0-4e4d-acb5-41329d3cce55 | checkpoint | 3.2 Placement of Fencing Panel
ab80a9ff-c698-5d78-b3c6-0b0151d92d42 | note | FREQUENCY: Each Lot
244697dd-6d76-54d7-863e-b581a07c2d5d | note | ACCEPTANCE CRITERIA: Align fencing panel such that the posts sit securely in the installed post sleeves. Ensure fence panel is free of damage and is positioned in accordance with the design line and level.
9768a069-6d83-54cf-8384-4c416452c71e | note | REFERENCE DOCUMENTS: Design Drawing Dwg P15671
c1b00404-fc1a-5a27-a9d8-739f8f47f149 | note | INSPECTION/TEST METHOD: Visual Inspection
dd535384-0703-51ff-8836-9a226a10d492 | note | RECORD OF CONFORMITY: This ITP Signed off
bd13d590-95c5-5a26-be0f-e27a358c47ca | note | IP
41bb2732-1785-52d5-82b8-8942d76e0cad | note | RESPONSIBILITY: Fulton Hogan Engineer
ccc1de5d-4ffe-52f5-8a20-4347cd72f15c | textbox | Date Completed:
d4fa836e-4ee1-4f5b-b985-1fed84806a0a | section | Linemarking
268686da-d1ba-4589-99b6-a97b373a68c3 | checkpoint | 4.1 Linemarking
376d91c2-4301-575c-8fe7-53faf9174d33 | note | FREQUENCY: Each Lot
1af6d83f-1030-5fe2-b79b-e244bba53283 | note | ACCEPTANCE CRITERIA: Linemarking to be completed in accordance with design and standard drawings.
40f6c336-475f-50d0-8c1b-12e0a0cc8393 | note | REFERENCE DOCUMENTS: Design Drawings Dwg P15671
71482c99-e856-5500-ba96-68694b9df0e5 | note | INSPECTION/TEST METHOD: Visual Inspection
3ba0a6b3-9148-535a-8264-6220eb9daa9d | note | RECORD OF CONFORMITY: This ITP Signed off
717c228d-0020-53c1-afcb-2720934319c8 | note | IP
5734164f-925f-5655-b62b-3b23904445ec | note | RESPONSIBILITY: Fulton Hogan Engineer
03aada48-0183-5207-917f-8d4cd8c44572 | textbox | Date Completed:
f90328e9-877d-4a8e-9f8a-e86bfbb6f883 | checkpoint | Final Inspection
e1de1ee9-e9e2-5a8e-9b23-3bd8b7df9da5 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
1cc3aef9-c3bc-557c-befd-353b428987ed | textbox | Print Name:
754b0f78-c289-505c-99f5-10f7ba9a5274 | textbox | Position:
a2921bcd-2e25-5174-b756-098eae9ed6a3 | textbox | Date:
26cb2541-6f44-4ead-8bce-fc05ea3994db | checklist | ITP-035 - Kerb Access Ramp Asphalt Footpath |  | ITP-035 - Kerb Access Ramp Asphalt Footpath
ee591d63-d5a1-4949-b367-249005efe442 | section | Preliminary Works
dcf7ea66-bf3d-4c2e-8c00-b5f6e55cc594 | checkpoint | 1.1 Check for Correct Documentation
269c50c5-4335-55f2-ac6f-ce08f4fc37a2 | note | FREQUENCY: Prior to Commencing Activity
77af6e24-9151-5d13-ba57-c42ac783f492 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
30618744-9a56-51fa-8182-80a91779a366 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
f4df79ce-43a3-5c8e-81b8-cfee3e0fcae5 | note | INSPECTION/TEST METHOD: Visual Inspection
0619d166-deb3-5e8a-9fc3-5e55dbe86675 | note | RECORD OF CONFORMITY: This ITP Signed off
c123da8e-0eff-5219-b590-f52f8f9e8bf5 | note | HP*
f4def454-72c7-5039-9f1a-0f57a352cfaf | note | RESPONSIBILITY: Fulton Hogan Engineer
da10a0da-6aa5-5e2d-a744-634ade79f635 | textbox | Date Completed:
ade28501-ab03-49e7-9912-5bb448d38aad | checkpoint | 1.2 Implementation of all measures and controls
aeba95b4-3a17-5c88-b544-fbb6234856b2 | note | FREQUENCY: Prior to Commencing Activity
343a329a-9a31-56ce-96a2-f657c5dd77b5 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
e65b2830-cef6-51d8-8f5f-98ff17f8f2ad | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
7ff5a8e8-2a99-5c4e-92b4-31e3fe65dfeb | note | INSPECTION/TEST METHOD: Inspection
0f546919-5ade-53d4-85cd-2fbad021a06e | note | RECORD OF CONFORMITY: This ITP Signed off
ba3b6931-2be4-5426-9415-d3739884af79 | note | IP
327739f9-5412-5552-a528-197f83a088dd | note | RESPONSIBILITY: Fulton Hogan Engineer
c101e5b4-b4c4-5c0d-aaed-b62c6fd09001 | textbox | Date Completed:
c43b00d1-6ee1-434d-aee5-a4197382f1fd | checkpoint | 1.3 Existing Bluestone Kerb Demolition / Removal
63aa5d71-12ae-5a19-8194-f94d650ff5d1 | note | FREQUENCY: Each Lot
199e214c-c1f2-574f-af9c-cbbd6c150192 | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone (if applicable) Bluestone shall be salvaged and re-used in new kerb alignment where possible
c8d82dc9-03c2-540d-9bc4-d2a7c8330b67 | note | REFERENCE DOCUMENTS: Work Procedure
6f01147f-870f-5f04-a732-dfd276ee9907 | note | INSPECTION/TEST METHOD: Inspection
b30ccc84-9218-5fc3-a506-d4cad5c29c2c | note | RECORD OF CONFORMITY: This ITP Signed off
ebd94304-45e5-50c4-a673-25dc975d69dc | note | IP
a271eb68-6ef4-5bc0-990c-9ebc1b654b7d | note | RESPONSIBILITY: Fulton Hogan Engineer
30e9c808-b302-5c4f-840e-ab577a607ea4 | textbox | Date Completed:
3a4b20fa-2c0f-4abb-9e47-b27afb48e5d3 | checkpoint | 1.4 Check Materials
17bc89cb-f743-5d0a-8870-73a92af336d2 | note | FREQUENCY: Prior to Commencing Activity
10e3a094-a533-5662-807c-1833997a6f61 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Granite Tactiles. Granite inlay shall be 50mm wide x 40mm thick Spring White Granite Inlay.
8d676394-9d79-5f49-a4c8-472e57c25ea4 | note | REFERENCE DOCUMENTS: Receivable Inspection List
7442db3b-e6bf-5e0b-9606-258528ab1f27 | note | INSPECTION/TEST METHOD: Visual Inspection
a135e28d-9746-5571-9ae5-91d641514379 | note | RECORD OF CONFORMITY: This ITP Signed off
3d5801e0-0b5c-55f0-96ae-e54787c86615 | note | HP*
53a2386f-cac4-5db7-9c76-a7c5524c69d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
0fb8885a-5876-5074-bd8a-7740ad45997b | textbox | Date Completed:
e0ffc64d-1f7b-482c-92e8-514375da89c5 | checkpoint | 1.5 Setting out
3db4c3c4-8cab-5611-9d7a-2c6b11eb71ec | note | FREQUENCY: Each Lot
ae527ad0-9330-57bd-a3ca-5429f47629ee | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
73ef6965-526b-5b66-b8ea-c746597e9646 | note | REFERENCE DOCUMENTS: Work Procedure
fcef10d2-ebe5-569e-b6ba-5328c590dfec | note | INSPECTION/TEST METHOD: Inspection
de6f5fb2-8d39-59d9-8abd-f7d55d42f20d | note | RECORD OF CONFORMITY: This ITP Signed off
df210f57-6257-5faa-83f1-cd086162390b | note | WP
4c183b5d-2855-5068-989a-846d983c870b | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
a2e69996-dca1-5a08-a190-5b69839b60bb | textbox | Date Completed:
b1444a37-4b0f-4003-b880-5fc71fd49574 | section | Construction of Access Ramp Asphalt Footpath
68e7085c-a8f2-40b0-9482-bb0eedb7e5b7 | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
2cc31c67-71d9-5ffe-8afd-5d88d3a41105 | note | FREQUENCY: Each Lot
efec4ea2-75c5-549b-b2be-cf455fbaed8a | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels. Bluestone kerb shall be placed on a bed of low slump 20MPa concrete, minimum 75mm thickness. Formed groove of 10x25mm in concrete face shall be filled with caulk
ec0ca6b0-02e7-5205-b77e-cfe202aa76ae | note | REFERENCE DOCUMENTS: Dwg 1P50201
8981377f-f8f7-544a-b319-27ac1327632a | note | INSPECTION/TEST METHOD: Visual Inspection
d8f9045b-0ca2-5126-a21b-13a406077acc | note | RECORD OF CONFORMITY: This ITP Signed off
ffdb29a2-bb86-5657-8c6e-bc431105b9bf | note | IP
d79a940e-8808-572c-b08e-f1645fe02782 | note | RESPONSIBILITY: Fulton Hogan Engineer
e64188b9-5608-5e5d-b587-358f4c3bdcc4 | textbox | Date Completed:
f1ab9b20-1f03-41dd-aaf7-dc82de986846 | checkpoint | 2.2 Base preparation
a78f242e-276c-5cbf-b6f8-f067beead71b | note | FREQUENCY: Each lot
79801543-d9a5-5a97-8e02-a3bce7cab18d | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
78aa16c9-ef2c-5b7f-9108-869532fce6e7 | note | REFERENCE DOCUMENTS: Dwg 1P50201
7b09f44a-565c-575b-b899-f38531ba83a7 | note | INSPECTION/TEST METHOD: Visual Inspection
331a8893-dd6e-5474-9806-68b9476597ca | note | RECORD OF CONFORMITY: This ITP signed off
20a9d807-5e8b-5bfd-8671-fb64209c1b07 | note | IP
fba4ff62-cca0-5e3a-ab73-b309a6eb52bb | note | RESPONSIBILITY: Fulton Hogan Engineer
5bbcbd19-4182-5772-97a8-681d6023473f | textbox | Date Completed:
b47cedcf-ada7-45e3-9674-7d41a61bda12 | checkpoint | 2.3 Installation of Kerb & Gutter Blustones
47da9a64-ee82-58a9-b014-aab198dc4806 | note | FREQUENCY: Each lot
bf5e0ba8-97b9-5f18-ac49-397e5bef506e | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar.
bacfed7c-16c6-5d83-95e5-abb0ae0480df | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
7521dc29-fbd2-5066-92ba-0bee7084d7de | note | INSPECTION/TEST METHOD: Visual Inspection
ef3d88fd-327f-5924-96ef-e0a4d0b42aaa | note | RECORD OF CONFORMITY: This ITP Signed off
70e7f742-7b14-5493-9f07-340adefdf355 | note | IP
bbd3f038-93f9-54c3-b32a-3790b11babd2 | note | RESPONSIBILITY: Fulton Hogan Engineer
a82d928f-9e2b-55e8-a259-d2af5adf4dd4 | textbox | Date Completed:
845e7533-ab04-485f-8a4c-4ec0e91f84ca | checkpoint | 2.4 Asphalt placement
3ae8f9ac-ca4c-50fe-9ea3-305d8b264a0b | note | FREQUENCY: Each Lot
2482b55c-510f-5ea2-9133-e1d03bc5c413 | note | ACCEPTANCE CRITERIA: Asphalt ramp to match adjoint asphalt footpath and sit flush with channel at grade of ramp using 7mm type N hot mix asphalt. Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8.
f4648241-1193-5d13-a6ed-3ed43f209c8f | note | REFERENCE DOCUMENTS: Dwg 1P50200
39db275a-08f4-5014-92a7-f5428c9cdc32 | note | INSPECTION/TEST METHOD: Visual Inspection
6697926c-8549-5892-a76c-4a289c043502 | note | RECORD OF CONFORMITY: This ITP Signed off
a9a9a300-6586-5bb3-afec-d038e6d28f72 | note | IP
40ca199a-74c9-5f0b-a5b5-b5565dd13ec1 | note | RESPONSIBILITY: Fulton Hogan Engineer
aaab07b5-21f2-5661-99ae-2754b67ef078 | textbox | Date Completed:
dab9ad62-4b20-42c8-a898-301463f72471 | checkpoint | 2.5 Installation of Pandatac Granite Tactiles
8b7e0cb1-d6a5-595b-bafc-875a14b170e7 | note | FREQUENCY: Each Lot
4822926b-103f-5c48-9722-54682465514b | note | ACCEPTANCE CRITERIA: Granite tactiles shall be placed in accordance with Standard Drawing 1P50200 & drawings.
dd1903fa-2b65-57bb-acfe-5663594b9917 | note | REFERENCE DOCUMENTS: Dwg 1P50200
9d260bbd-3dce-5ba5-b926-c89f26867d51 | note | INSPECTION/TEST METHOD: Visual Inspection
468145c9-e7aa-5afd-88c4-d3fd4734d987 | note | RECORD OF CONFORMITY: This ITP Signed off
47f67a6d-ded6-5e3a-ae4d-748891b5e7fb | note | IP
4367f07a-bc04-5ec9-87b3-6f1ff9c39752 | note | RESPONSIBILITY: Fulton Hogan Engineer
4ce9a59a-0d13-53cd-a8bc-f26b7e2af66a | textbox | Date Completed:
bde4f4d3-6719-4e2a-82f9-514aa749ba74 | section | Completion
f72ab9ba-4731-4772-b832-c19688e50dee | checkpoint | 3.1 Completion
0388b6d0-5435-5b26-8347-ca86f4aec718 | note | FREQUENCY: Each lot
e4a3ee74-3488-5af5-a222-3d0ed3b96b3d | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste Bluestone kerb is free of mortar stains and cleaned to satisfaction.
3a97c709-a75f-547b-ab0f-f4e61204e75f | note | REFERENCE DOCUMENTS: Visual Inspection
0f546ba3-764c-5859-948c-b19dafff4dfd | note | INSPECTION/TEST METHOD: Visual Inspection
7bc8ea4d-fa3a-5c4f-a81b-3ed78e126645 | note | RECORD OF CONFORMITY: This ITP Signed off
a27f3b59-e2d1-5890-be1e-dcc0d5c08573 | note | IP
14bd36d8-a664-5bdf-bf6e-9640e862fe9b | note | RESPONSIBILITY: Fulton Hogan Engineer
34028fe8-e367-5e02-9460-fd8ff6c26f4d | textbox | Date Completed:
8e042ab4-897b-4c7e-9d1c-d9a731260d9e | checkpoint | Final Inspection
6285094f-aacd-5f3d-9b4f-1d2e792c841c | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
be1085f2-e4d7-579c-9d5d-5205917669a2 | textbox | Print Name:
7f8a57c8-06e5-5cc6-93c1-f3df770ae309 | textbox | Position:
e8f5ee14-63a2-530b-a9ce-127c470f5a85 | textbox | Date:
25d7565f-5736-496a-8704-c9660d16debf | checklist | ITP-036 - Kerb Access Ramp Bluestone Footpath |  | ITP-036 - Kerb Access Ramp Bluestone Footpath
0b3593f3-1c12-471b-9301-c32445cfa140 | section | Preliminary Works
688e3f50-14fc-44e3-aa1d-6ffbe222eb41 | checkpoint | 1.1 Check for Correct Documentation
52a82d19-ec0c-56e3-90c4-f85541b6c528 | note | FREQUENCY: Prior to Commencing Activity
0a74bd90-1b91-51c3-96db-97290d11357f | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
e6033190-16fe-5ebb-a278-a6b021d7c863 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
0fdcac02-c350-536b-8617-90423224d98e | note | INSPECTION/TEST METHOD: Visual Inspection
9b0e1498-cc0b-5d33-a429-c74a579f3985 | note | RECORD OF CONFORMITY: This ITP Signed off
bc19dbf7-f4b7-5be9-9480-03f3067b327f | note | HP*
584bd54e-daeb-55ae-9e8e-e8a581664b98 | note | RESPONSIBILITY: Fulton Hogan Engineer
61c4586d-1882-5917-9dda-b7d77e7a15bc | textbox | Date Completed:
039129e0-ad40-4bad-b51d-af42e7643145 | checkpoint | 1.2 Implementation of all measures and controls
49057b71-ecef-5b2f-a685-288fa05e769f | note | FREQUENCY: Prior to Commencing Activity
3220773b-998e-53ff-b214-9d46f72bd022 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
d6530e4a-d954-59d8-9f69-ef10724ae7c1 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
ec80cb64-7a70-5f74-b268-bbf5e4dfb0c2 | note | INSPECTION/TEST METHOD: Inspection
342425c4-f3da-5164-82aa-add7acece86b | note | RECORD OF CONFORMITY: This ITP Signed off
4d204ad3-588f-54f5-959f-727e514880d0 | note | IP
7ffd214e-0473-554c-8c0b-0a97f7501b02 | note | RESPONSIBILITY: Fulton Hogan Engineer
bac8af11-47ce-523d-badc-30aa39fba668 | textbox | Date Completed:
80babcc9-4562-413b-9284-021ef481d3de | checkpoint | 1.3 Existing Bluestone Kerb Demolition / Removal
ab0c6ec7-df48-5664-a433-c644aee7097a | note | FREQUENCY: Each Lot
7c6f569e-c681-5469-951c-b6f32b3ed29d | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone (if applicable) Bluestone shall be salvaged and re-used in new kerb alignment where possible
c6868cbc-1f85-568c-a273-ee239da2556b | note | REFERENCE DOCUMENTS: Work Procedure
452a9189-7249-5d0e-8fe5-757023656522 | note | INSPECTION/TEST METHOD: Inspection
39ff74cc-7862-538b-9637-2d74c8fa1de2 | note | RECORD OF CONFORMITY: This ITP Signed off
df2c841a-208d-5073-baf3-c1a411862826 | note | IP
87291d57-9dfb-5b79-b7e3-87f66f93b812 | note | RESPONSIBILITY: Fulton Hogan Engineer
4c661aaa-e156-5b1b-9818-5772d910b141 | textbox | Date Completed:
5cde3d72-e3b3-4672-9045-2ae97432a0af | checkpoint | 1.4 Check Materials
e327a5ce-2a04-56bf-9e63-07a6f66ae583 | note | FREQUENCY: Prior to Commencing Activity
e5114e7f-793d-5aeb-b212-7899edbb405b | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Granite Tactiles. Granite inlay shall be 50mm wide x 40mm thick Spring White Granite Inlay.
d60b0906-683a-57ef-b354-f6131a6f9d9c | note | REFERENCE DOCUMENTS: Receivable Inspection List
a3ccf43c-aa8d-5624-bc6f-e4af87cadb2b | note | INSPECTION/TEST METHOD: Visual Inspection
653f887a-2864-5a63-a889-9469047d19da | note | RECORD OF CONFORMITY: This ITP Signed off
72fce0d1-73d0-5bcb-9d91-d8ba1f59116b | note | HP*
4ae4f0a5-5855-5929-9a14-9aa4b40da0bb | note | RESPONSIBILITY: Fulton Hogan Engineer
299d7987-1b32-549b-a190-5a2466d28b74 | textbox | Date Completed:
3dbc03a7-a781-46f2-9167-b9f522085d07 | checkpoint | 1.5 Setting out
31a701b0-bbab-5283-a013-65a75375a2f3 | note | FREQUENCY: Each Lot
be7441cb-d317-5ac9-a567-905c33e984d1 | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
c80b481f-a8d3-523f-a117-681ae2f0a01d | note | REFERENCE DOCUMENTS: Work Procedure
56fb8338-2bc9-535d-aa08-90fa35be8064 | note | INSPECTION/TEST METHOD: Inspection
c488b3eb-16b9-599c-993c-bdc4d342f24c | note | RECORD OF CONFORMITY: This ITP Signed off
8ad4de1b-cec2-5e31-8c7f-9ed98ac861f2 | note | WP
d0c1e82b-8d20-531b-bfb5-1913a4e008cb | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
51a70221-b718-522e-b320-41d9f70a363a | textbox | Date Completed:
f153a454-fa28-4b14-b62b-23f76955f258 | section | Construction of Access Ramp Bluestone Footpath
7fba1661-5af5-4ece-a0ef-708857e702bf | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
0d1ff6d0-b93e-57a4-adb1-c002374bc45b | note | FREQUENCY: Each Lot
55d3a471-c121-5bbd-9f6f-44e019f57b38 | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels. Bluestone kerb shall be placed on a bed of low slump 20MPa concrete, minimum 75mm thickness. Formed groove of 10x25mm in concrete face shall be filled with caulk
22eaee7a-2294-5c7e-a5ba-5d072b5fe431 | note | REFERENCE DOCUMENTS: Dwg 1P50201
7f236e87-5ad0-5753-a780-441899617ca4 | note | INSPECTION/TEST METHOD: Visual Inspection
706a4b98-7524-538c-8659-9dc8bab16046 | note | RECORD OF CONFORMITY: This ITP Signed off
9ecc27c0-3db7-59e1-ad16-77d88ad763ac | note | IP
cebfa0cd-ffd2-56e3-9955-233ca351c406 | note | RESPONSIBILITY: Fulton Hogan Engineer
fc5c889d-fff5-535a-8fde-38ca6da7cfe6 | textbox | Date Completed:
042aa90c-a509-472f-b5ac-6d72ecd09ceb | checkpoint | 2.2 Base preparation
7df007d9-7ae9-5fd3-b023-82de931cfe8c | note | FREQUENCY: Each lot
aeca823e-e1d2-5390-8d6a-c1c0aed0f7e9 | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
76ef5fc8-1ddb-5638-aadc-d6fd4bee5f04 | note | REFERENCE DOCUMENTS: Dwg 1P50201
4ab996dc-a468-5533-8cb3-a0c63065891d | note | INSPECTION/TEST METHOD: Visual Inspection
d349eac5-20f1-5325-a65d-3967645a8e18 | note | RECORD OF CONFORMITY: This ITP signed off
126ef5e5-d3ec-5281-bacb-5f85e4df5b45 | note | IP
5542865a-c848-5c99-aaeb-edc79837339e | note | RESPONSIBILITY: Fulton Hogan Engineer
8ecbfcfa-0c61-56df-9f99-890fb8491392 | textbox | Date Completed:
3728a1ab-e6e2-4213-b04a-6465381b89f1 | checkpoint | 2.3 Installation of Kerb & Gutter Blustones
3ee56d97-6244-52f8-b626-dedb4d282e9c | note | FREQUENCY: Each lot
2f169779-f6ea-5dcb-b9ca-6c84a782f3fd | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar.
d96020f9-5fb3-58a3-8b02-aabd3172594f | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
e83e726c-2c9a-529a-bcf3-c055bba54cdb | note | INSPECTION/TEST METHOD: Visual Inspection
4ba37a8c-1618-5e0d-9e47-21b35b8d59a4 | note | RECORD OF CONFORMITY: This ITP Signed off
e033e206-77c1-5eaa-bfbb-61e99887aa1d | note | IP
8772d12f-73b6-53a5-8a33-3c84d68cf539 | note | RESPONSIBILITY: Fulton Hogan Engineer
10f67431-785f-5894-873d-1322f8c80891 | textbox | Date Completed:
1cc76863-1dcc-4b2c-b6af-d98c26bdbb59 | checkpoint | 2.4 Placement of bluestone pavers on mortar bed
63988fc2-7712-55a0-87b8-56793eba1d3c | note | FREQUENCY: Each lot
d4eb2237-1cb9-5ab9-8f02-8232163227d7 | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402 on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying Kerb access ramp wings shall be at an angle of 45° or as per design and the ramp gradient shall not exceed 1:8. Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
973179b1-9cb0-5536-ace3-d115afe3c676 | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
ad173cdf-6b60-5b28-8eff-84d93d5de3cf | note | INSPECTION/TEST METHOD: Visual Inspection
8376f787-b372-5107-902d-8167260aa378 | note | RECORD OF CONFORMITY: This ITP Signed off
effe72bb-0052-56b9-aa57-061e3965e23a | note | HP
9f1fc268-f65e-5a4b-9877-2764f5a6482c | note | RESPONSIBILITY: Fulton Hogan Engineer
628b10d1-9f77-5e22-9ee2-997cf6e4452a | textbox | Date Completed:
49f87046-fb34-4c98-b711-340be5f3b8bd | checkpoint | 2.5 Curing
d5ac25e0-f0ad-5752-a9e1-6a6266adcd8f | note | FREQUENCY: Each lot
6a36d447-30e5-5b37-ae96-33b18aaa5c22 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic Where required, ply shall be laid over area of works
d5bdb2c7-84ad-59c0-abfc-77aec2f77c41 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
736083fa-21c5-5cb5-b8bc-47d838a48aa7 | note | INSPECTION/TEST METHOD: Visual Inspection
f0f41911-799e-5ddb-be56-80e9aeeea1ad | note | RECORD OF CONFORMITY: This ITP Signed off
af9bc0ab-1618-5f93-a027-a3ab842d1275 | note | IP
33c88afc-cda9-59c9-beeb-6c4c5c447b6b | note | RESPONSIBILITY: Fulton Hogan Engineer
6bf64d62-09f9-58e8-a1cb-406e18404e0c | textbox | Date Completed:
bf4fa1c9-857f-4f9f-9db1-5c1dd779e5e1 | checkpoint | 2.6 Grouting
d19502a1-9960-5cec-bc53-009c2d977e62 | note | FREQUENCY: Each lot
7c515a70-dc99-5d8f-8e48-2bb3ecdb9fb8 | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using Lanko Durabed to specified mixture content. Grout shall be spread & clean appropriately as required.
2dafafdd-ae9c-58b2-bda1-7a51aad5c511 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
88dbcd67-b5b2-516f-b38f-828ddf17fb00 | note | INSPECTION/TEST METHOD: Visual Inspection
334fe15c-402b-5249-b75c-3ae13a316f6d | note | RECORD OF CONFORMITY: This ITP Signed off
8b25f0f1-80e5-5799-90d2-7db921648b47 | note | HP*
6114bd38-f29d-5d37-a89c-3eff7cf43448 | note | RESPONSIBILITY: Fulton Hogan Engineer
69045bf6-7f4c-52dd-8217-b7cef302796f | textbox | Date Completed:
486c5cac-73d1-4652-9665-0178fc5ef76e | checkpoint | 2.7 Installation of Versatac Granite Tactiles and Granite Inlay
4a83cfb9-5a64-5b66-9d18-7475ce6ff673 | note | FREQUENCY: Each Lot
5b5463ad-6499-5cfb-912d-ad1edaad7579 | note | ACCEPTANCE CRITERIA: Granite tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201 with surface deviation of under 5mm.
b64b0af9-12b7-5db3-be49-486c3d23a90f | note | REFERENCE DOCUMENTS: Dwg 1P50201
f14ebd65-f4cf-5f6e-a21e-7452d3f1a0fa | note | INSPECTION/TEST METHOD: Verify
a362edf4-2729-5f81-9603-3eeea2cd7c2c | note | RECORD OF CONFORMITY: This ITP Signed off
f9a31461-2dda-508d-bc15-b0accd859462 | note | HP
424d42bd-6df8-5c61-8f20-3df21f3653ac | note | RESPONSIBILITY: Fulton Hogan Engineer
a32b07ee-a476-58e3-97dc-bddfd37a0a19 | textbox | Date Completed:
f72932ed-29f9-4250-bfd4-50f5ea7cc1f4 | section | Completion
efefcfa7-dc38-4cac-b277-c7c189ae47dc | checkpoint | 4.1 Completion
87451054-568e-5756-be2b-c9decdbddd27 | note | FREQUENCY: Each lot
535a060e-b0e0-5a29-ae29-219c485f6502 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste Bluestone pavement is free of mortar stains and cleaned to satisfaction
d864fa9a-bacf-53c9-9deb-5bf0ca8c3c44 | note | REFERENCE DOCUMENTS: Visual Inspection
2d0a96b0-2057-5ca0-aa9e-08f9551d7a5e | note | INSPECTION/TEST METHOD: Visual Inspection
2a2402e2-84ee-5333-8167-d18ca640043c | note | RECORD OF CONFORMITY: This ITP Signed off
5cc4fe1d-22d7-5540-a9ba-2f7a1f41b6b2 | note | IP
dc1f0f4a-e91a-547a-90d3-138d09beaed3 | note | RESPONSIBILITY: Fulton Hogan Engineer
6e2b4d67-5d9e-5672-9845-2205c6eb2d9c | textbox | Date Completed:
ed32126a-613f-4a19-a7ea-e326df4104db | checkpoint | Final Inspection
5c8f6d1c-fc16-5ec6-84e5-58c8b623e131 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
dec04793-661d-57b6-a2b9-7c1562f14aa9 | textbox | Print Name:
210132a6-9b5d-5fd8-8f62-a36ef4d0da1d | textbox | Position:
be62c7f8-80d4-5ddf-ae58-6d043228323e | textbox | Date:
0f46140a-27c1-4bbf-937e-4c9ad125191f | checklist | ITP-037 - Structural Concrete Construction |  | ITP-037 - Structural Concrete Construction
d575f5c9-a786-44d0-a31d-29a6a1b4e233 | section | Design and Submissions
da981494-9ad0-4e44-8567-547038f554d0 | checkpoint | 1.1 Check for correct documentation
10867538-2aa7-41dc-a905-feb98750ae31 | note | FREQUENCY: Prior to commencing any activity
70251ed3-c36b-4277-bd8f-7b0c4ac06a74 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
1a34dcff-ca4c-4da8-a88a-0b9e0aab1f08 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
3e8d9101-7728-465d-adb2-7c76cf5e575d | note | INSPECTION/TEST METHOD: Visual inspection
dc226a37-d59e-4958-b256-4b8a527e0d3c | note | RECORD OF CONFORMITY: This ITP signed
8114c6d4-a80f-40ef-a0da-30b96f57f274 | note | HP*
909092ba-a767-4cba-9008-cdec4d57dace | note | RESPONSIBILITY: Fulton Hogan Engineer
d494c5d2-9033-4a1b-8144-95bd559ba962 | textbox | Date Completed:
29552d51-0fc2-4088-a3dd-be9c947006b2 | checkpoint | 1.2 Implementation of all measures and controls
d8f36d48-9962-4c11-8a15-7d999df5ca76 | note | FREQUENCY: Prior to commencing any activity
1a98fadb-e11f-4bcc-86af-9cd7bbf83a3a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
c3b1be3b-1703-493b-936f-dc2f67514e64 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
5a3fb175-cf79-4d83-a4fd-353f6458d1ce | note | INSPECTION/TEST METHOD: Visual inspection
d59f6772-8936-4438-9d02-ef523eb7656b | note | RECORD OF CONFORMITY: This ITP signed
78b91eb9-ca04-466b-b3c7-7122153101fb | note | HP*
15846b91-27de-45af-bd9d-0daea8be34d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
dd645d3e-2497-451d-817e-3ffcc1209b23 | textbox | Date Completed:
a81ad355-59ed-4d1e-a599-36bba3f5c122 | checkpoint | 1.3 Approval of Mix Design
8d91ba3a-9d85-4a85-85ae-680babdbd616 | note | FREQUENCY: Prior to the first concrete pour
fc25cefd-c662-41a9-b4d0-e769458d7e37 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
6b85be64-be52-463c-b0a5-9f8ffb37041c | note | REFERENCE DOCUMENTS: WP 01
d5568340-fffb-4d12-a036-97b56a6423c1 | note | INSPECTION/TEST METHOD: Verify
8ec1954b-9e02-4d19-8981-f7867be1cc14 | note | RECORD OF CONFORMITY: This ITP signed
7d4caa8a-a2aa-43b1-8c38-2f5c58a5930a | note | IP
71523cc5-8446-48f4-9720-257e5b2fdfad | note | RESPONSIBILITY: Fulton Hogan Engineer
f210001a-e554-4b5c-8585-7081985ff93c | textbox | Date Completed:
fa890ebc-d4f8-41f8-aeba-725e6b1649d5 | checkpoint | 1.4 Reinforcement schedule
1172d2ac-91f9-4908-b1b8-2b24e80307b4 | note | FREQUENCY: Prior to concrete pour
54916229-d0c5-4f70-ba81-1debdd380a5a | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
49c4c6a1-e6c8-4328-8a70-e6af441cce5c | note | REFERENCE DOCUMENTS: Cl 611.04
d3cf1a27-9d7a-43a6-90dc-bb0d48a656f8 | note | INSPECTION/TEST METHOD: Verify
eb0ef6a7-9a73-4f96-8bb9-e50809857fa6 | note | RECORD OF CONFORMITY: This ITP signed
02ba46be-f354-4e8f-8dde-7b625e79350a | note | IP
5a7f0fe7-6a20-4dae-b1a5-4c31f53a2587 | note | RESPONSIBILITY: Fulton Hogan Engineer
0debaf6f-ccff-4a20-9155-cae027c4bbf0 | textbox | Date Completed:
4750ff5e-1315-499a-acc9-e2177c2fadda | section | Construction/Erection of Formwork
f3259264-ba1d-4c93-a588-fa4217fb2c87 | checkpoint | 2.1 Excavation
51e06fc5-ffaf-448f-a38d-a74d37791560 | note | FREQUENCY: Prior to concrete pour
b5a651dc-36c3-48a1-940e-9a747899b365 | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
84618964-c7ba-48b4-abef-8210887395e7 | note | REFERENCE DOCUMENTS: WP 01
2e188f4d-254f-4954-9353-6b7f81e3d6bd | note | INSPECTION/TEST METHOD: Inspect
9f13ee02-7ac9-4802-8bd4-399943f83c21 | note | RECORD OF CONFORMITY: This ITP signed
4de7053c-b08b-48ad-a295-359b08c0bb75 | note | IP
57b50d8f-e89f-4815-b41e-9acab9a98b59 | note | RESPONSIBILITY: Fulton Hogan Engineer
9fbd4a04-e66b-4cb2-b84b-89265af6b4d0 | textbox | Date Completed:
f68dae86-0e60-4aca-afb1-9d4a46bce500 | checkpoint | 2.2 Construction Methodology
c1c38146-ca24-4e3f-9dc2-bce407701d48 | note | FREQUENCY: Prior to erection
1b9edb1c-bf60-4bad-b5b1-551e6bb31f17 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
9dcab8ae-c6ca-47bd-b1b0-a98b3e3dcc08 | note | REFERENCE DOCUMENTS: 614.04 614.06
45642352-0c3d-4801-9d6d-59b88a8ab8d3 | note | INSPECTION/TEST METHOD: Verify
9e1d047e-b6ac-4862-86af-d1c617e869a4 | note | RECORD OF CONFORMITY: This ITP signed
f892b8f4-de08-4d80-a1ea-f6a2de1dc750 | note | IP
37bcfb9f-df1d-4b65-9ed5-97d6816ded81 | note | RESPONSIBILITY: Fulton Hogan Engineer
4a31fa64-afb4-4f83-8b9d-f1946f4fb2eb | textbox | Date Completed:
50fc99c4-80f2-4d7f-b512-45742ad5d1d6 | section | Pre-pour Planning and Inspection
1d777fa8-7d16-4ba4-bbe9-9d358d6feddc | checkpoint | 3.1 Excavation/Foundation Blinding, sealing or foundation concrete
eb14d022-57f2-4465-8cb4-fc51e87e4011 | note | FREQUENCY: Prior to concrete pour
2a0fc54d-4095-476b-9b0f-6badd7c2e79c | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent.
4f66fdef-ee45-4197-9ba4-11650327bc57 | note | REFERENCE DOCUMENTS: 602.03
2d2d89cf-74b6-497b-b126-f495719f47fb | note | INSPECTION/TEST METHOD: Verify
84230696-cb8d-4b40-8b6d-d8d1d8fd03b2 | note | RECORD OF CONFORMITY: This ITP signed
f0892976-a7b2-4b72-8624-e9055d9c0894 | note | WP
b9973106-de6a-4555-aea4-9b8a85bfcbec | note | RESPONSIBILITY: Fulton Hogan / Yarra Trams
74cbae5d-c1aa-4cf1-96c1-c0b7b0c3e861 | textbox | Date Completed:
e296788d-4216-4088-948a-2269204f65be | checkpoint | 3.2 Formwork levels and position
199f3526-1b7d-4442-98fa-29aba31201d8 | note | FREQUENCY: Prior to concrete pour
a27e44bc-39e8-4799-99e0-c63fb6c3c1f6 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
7fb008c3-d125-4812-ab2d-8debe9991bb5 | note | REFERENCE DOCUMENTS: 614.06
6b81a006-1e43-40bb-a882-5337385865fc | note | INSPECTION/TEST METHOD: Verify
7d580410-24f2-4854-8795-3853bdf0bce8 | note | RECORD OF CONFORMITY: This ITP signed
cad34c7d-529f-4069-a50e-171ef9a87445 | note | SCP HP*
0b611445-ce8b-4d0b-ac64-17675477da5b | note | RESPONSIBILITY: Fulton Hogan Engineer
3049e76a-44ec-4296-9301-a7770640d07c | textbox | Date Completed:
689ea6a9-4e0e-4397-89bb-b79a64904aa5 | checkpoint | 3.3 Location of splices
ecbdbc35-07a6-4481-8400-aed20870e310 | note | FREQUENCY: Schedule Review
9584ef3c-87d5-4f8f-b49b-619368f06e5c | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained. Where necessary the reinforcement shall be spliced with 40 times nominal diameter of bar.
ea35f784-8d4f-439a-bc27-5a8006455aac | note | REFERENCE DOCUMENTS: WP 01 Cl6.3
df1abb3d-12a1-4382-a527-71401733ebc7 | note | INSPECTION/TEST METHOD: Inspect
e8d78836-3822-40a4-97bc-69b2d17e4c5d | note | RECORD OF CONFORMITY: This ITP signed
5b72d23d-a3bf-463e-9c9c-3d654d6fd56a | note | IP
f1d95388-0a9a-457d-8848-14eae698e999 | note | RESPONSIBILITY: Fulton Hogan
ab2d05cc-8862-4548-8bcb-43ee36d108f2 | textbox | Date Completed:
0cbf7c38-f6ec-48a0-921e-7c193cacd7bf | checkpoint | 3.4 Cleaning formwork
609d0b97-8e68-48fe-84a2-c6b56a260992 | note | FREQUENCY: Each concrete pour
cb921a9c-c882-42f3-9aa7-1276c6767701 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
4b7b46d3-5874-4041-b667-c26e8812c7da | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
601e95a7-8bed-4000-8222-7198f9479f31 | note | INSPECTION/TEST METHOD: Verify
3802176b-d9a0-4240-96db-546f21aec767 | note | RECORD OF CONFORMITY: This ITP signed
37c3186a-1ff1-4034-969c-18474fd50cdd | note | IP
7893a330-8b58-4cbc-9789-3a55a93fa853 | note | RESPONSIBILITY: Fulton Hogan
b4e7d19f-b8b5-49b6-945b-19e88f5689d1 | textbox | Date Completed:
71cbe3f3-f9f7-4be5-b3db-9504310f74e3 | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
b748eb38-a56a-4232-b4ee-e61f6c0fc32c | note | FREQUENCY: Prior to concrete pour
cf625bcb-f0c3-412b-a01c-896a604e5e05 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. CL01A Pre-pour Checklist completed and signed.
7231ba48-ffdc-440a-9cfe-683b5b8df7ba | note | REFERENCE DOCUMENTS: 610.18 (a)
3a18cdd7-19c1-4a24-8154-09856f3ec72b | note | INSPECTION/TEST METHOD: Verify
7f75eea5-6be8-408f-9a6c-0ef25179fc4c | note | RECORD OF CONFORMITY: This ITP signed and CL01A
950e7515-0e3d-484b-9639-33b1a9980992 | note | WP
dc1adc95-e5e2-4a74-9fb7-0efa8f8d9054 | note | RESPONSIBILITY: Fulton Hogan / Yarra Trams
02c48e7e-68ec-4a65-8993-3134c4042258 | textbox | Date Completed:
439e682e-8f3a-44e8-a2cc-559b038ecc67 | checkpoint | 3.6 Monitoring weather
f37f95db-5b9e-47b6-8155-7a28720f582b | note | FREQUENCY: Each concrete pour
9b490dac-4125-4c59-9827-2dde9e7bb6d9 | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5�C or > 35�C. All steel components that are in contact with the concrete shall be cooled to below 32�C before concrete is placed
088a0853-b3a2-4656-a0be-5160bd152e9f | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
7a3ae2e1-f4c5-4b5b-a833-bb5b4159c392 | note | INSPECTION/TEST METHOD: Verify
ba5be445-816f-49a7-8344-5425400070f5 | note | RECORD OF CONFORMITY: This ITP signed
8d4052a7-fdcc-4bc7-9104-885f089d0abd | note | IP
0b87ac01-ca86-4c70-853c-c86b39ef683a | note | RESPONSIBILITY: Fulton Hogan
ea983163-0d13-4104-90b7-da33d8ff6164 | textbox | Date Completed:
e9cbbc67-5aa7-45ca-a84b-356066a668e2 | section | Placing and Finishing Concrete
74bc0c79-9d18-414e-a2ae-86de5c92a327 | checkpoint | 4.1 Carry out sampling of concrete
94210c68-7d71-499e-af95-5cd0588b2330 | note | FREQUENCY: Each concrete pour
a24dad36-43cb-491e-aaaf-b2b411207e6d | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
8aafe55d-2ca0-4868-a43c-8296172e9896 | note | REFERENCE DOCUMENTS: 610.16
a88874ec-4067-4390-9e8e-a5d0177f051f | note | INSPECTION/TEST METHOD: Checklist
9eefb3bc-f6ed-4414-ae41-5c77224600c7 | note | RECORD OF CONFORMITY: This ITP signed
2bdcc4f7-7083-4981-9074-430bc84ab5a4 | note | IP
2397b2e3-d970-4dff-9661-fa4a8410800f | note | RESPONSIBILITY: Fulton Hogan
c99380d6-e94b-4da1-8a13-daaa91788992 | textbox | Date Completed:
ba5cbe3e-f445-40cd-affe-c88199666706 | checkpoint | 4.3 Discharge time
4770a92d-e167-43e2-a7c6-25d67c191a31 | note | FREQUENCY: Each concrete pour
5a04315d-fa77-4fe9-bf4d-a5d4536bd6b4 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
669fd7d7-f802-43e6-9706-0b029ab00ad6 | note | REFERENCE DOCUMENTS: WP 01 Cl 8.2
d9007967-9a29-488d-9e4f-6144609c3ba9 | note | INSPECTION/TEST METHOD: Checklist
13687bb9-8a77-41bf-a7ac-54447db447de | note | RECORD OF CONFORMITY: CL001B
0ccf7d5d-74a6-4be2-8742-c79361f17357 | note | IP
a23bcec7-2e92-4c96-b326-32b702bb985a | note | RESPONSIBILITY: Fulton Hogan
25b5e215-1d65-444b-86a4-23d902ba2eda | textbox | Date Completed:
dc2eb710-4cae-4dc0-89cc-c9592a559ae4 | checkpoint | 4.4 Methodology of placement
99a7812a-bf2f-4f1f-9838-53b73418ddce | note | FREQUENCY: Each concrete pour
b61867a1-da27-4f05-8029-5ed9cbee6f2a | note | ACCEPTANCE CRITERIA: Concrete shall be transported, handled and placed in a manner that will prevent segregation or loss of materials. Concrete shall not be moved horizontally by vibrators. In continuous pours the max. time lag between truckloads on site is 25 minutes
a6ba842c-2c3b-4799-97d2-cd5c967bee2e | note | REFERENCE DOCUMENTS: WP
2b6dc3ce-ca1f-4b64-afce-2d7df1e7365b | note | INSPECTION/TEST METHOD: Verify
52737135-c8d3-429e-a061-9f3e6bad66a7 | note | RECORD OF CONFORMITY: This ITP signed
611812ad-6d60-430f-ae18-a5681b743f6b | note | IP
bcf7f1d2-f359-4ad7-8f55-dda055d7373c | note | RESPONSIBILITY: Fulton Hogan
6c276df3-1a46-4bb6-bf38-ce0e33d0edb8 | textbox | Date Completed:
846d0d26-bc77-4081-b8fe-d4ae4d9f5578 | section | Post-pour Details and Inspection
55fb1338-223d-447d-8fb1-cdfc0abef791 | checkpoint | 5.1 Formwork removal
fec2e4ec-1278-4ab4-9fdf-921991224a92 | note | FREQUENCY: Each concrete pour
6d8f7ea9-34e1-4586-a9f0-8ea0d505fe1d | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
4b03cd99-d01b-4c2b-ab11-48df860813ba | note | REFERENCE DOCUMENTS: WP01 Cl9.1
b8ca32a5-923a-430d-ac1c-b200f3069acf | note | INSPECTION/TEST METHOD: Verify
0c722068-a64a-4a30-877b-cf3a3beb8e22 | note | RECORD OF CONFORMITY: This ITP signed
6ef0bc97-ad5b-408e-aeb9-e455018b6b49 | note | IP
fbb9408e-4703-437c-b067-dac0c5df424c | note | RESPONSIBILITY: Fulton Hogan
31ef9ff5-b4f0-44df-8f25-1a9701d87fbd | textbox | Date Completed:
e89fd0a5-ac00-4201-9fb2-247a40befe2b | checkpoint | 5.2 Cracks in the concrete
5741c699-a11d-473c-9180-da7b8ba361c3 | note | FREQUENCY: Each concrete pour
c37d79e2-d266-498b-bdf6-d0a3a47a9e8f | note | ACCEPTANCE CRITERIA: Cracks investigated and NCR raised. Repair procedure submitted to the Superintendent.
356e3446-b91e-4da2-801b-539b9b7cf0e8 | note | REFERENCE DOCUMENTS: WP01 Cl9.3
6e8b7c51-e079-45d8-8bb3-15471fd8f83a | note | INSPECTION/TEST METHOD: Inspect
406d124c-79e5-40fe-b324-57cd3271dd2e | note | RECORD OF CONFORMITY: This ITP signed
32440c5d-9a4d-42f7-bf25-8f996affe477 | note | IP
33d13f66-98ba-47ff-a88b-abc089727b62 | note | RESPONSIBILITY: Fulton Hogan
b1db2169-300b-42d2-acd0-951c3b3e97b3 | textbox | Date Completed:
0fef7945-b503-45c3-9dcc-c70433c56f61 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members
014adbfc-6a2d-42b1-b49f-4d200eca51c2 | note | FREQUENCY: Each concrete pour
0c8824eb-91a6-49d1-a342-c00b55705e2d | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
7f1dbae1-22a8-4c35-ba85-adeebb84fe2d | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5
579eb7b6-83d1-403a-8790-f3c3c42c2134 | note | INSPECTION/TEST METHOD: Verify
28b64429-f807-4fea-b76e-7d9ba188b694 | note | RECORD OF CONFORMITY: CL01C
6b91ffd7-a99c-4a2d-88a1-2be3e5f1cea5 | note | IP
dc6573ee-4984-4c80-95f2-5c649cc3be04 | note | RESPONSIBILITY: Fulton Hogan
1037217d-898e-4636-b9c7-5bcbbf673377 | textbox | Date Completed:
5ddc31b1-d05f-4d61-93d9-93b5f1005cde | checkpoint | 5.4 As Built Drawings
359350ea-b49e-4f06-9b95-3aed78d5582d | note | FREQUENCY: Prior to lot closure
e4f658af-cb4d-42c4-a570-a605aec8d134 | note | ACCEPTANCE CRITERIA: The location of the footing and centre of pole is recorded on as-built drawings
e132c869-780c-4e16-be05-5e4eb3e2dfe0 | note | REFERENCE DOCUMENTS: WP 023
1202cc4c-dc63-4e39-b68b-f6be6055f1b4 | note | INSPECTION/TEST METHOD: Verify
a9903378-0d18-4ec4-9000-7050f1c7da50 | note | RECORD OF CONFORMITY: This ITP signed
43864597-a625-47fb-ad47-9bcb6db1f8e2 | note | IP
33c3b749-9e66-4cec-bb44-083eea211906 | note | RESPONSIBILITY: Fulton Hogan
f079d1ac-08e9-498e-9d3f-91686240cc9e | textbox | Date Completed:
c81776ee-45bd-494f-9911-393ea39e4cee | checkpoint | 5.5 Concrete Sampling and Testing
a8f956eb-db6b-466c-8fc8-6c5df43a4e1f | note | FREQUENCY: Prior to lot closure
ffe36561-acf0-4c5a-b82a-9d65e1e8f259 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and slump
9561f75c-0127-4674-b85b-ffd506e252bd | note | REFERENCE DOCUMENTS: WP 01 Cl 9.4
62fa0a5d-5498-4fd0-875e-8a406181299f | note | INSPECTION/TEST METHOD: Verify
ab4d34e2-23ae-4fe7-adf6-59213078752d | note | RECORD OF CONFORMITY: This ITP signed
e171df6f-eb6e-424d-9626-51309c2bed87 | note | TP
53754690-b0d7-4e39-9b33-6213ef7d76dd | note | RESPONSIBILITY: Fulton Hogan
0c3226ad-e7c6-43f4-bc82-94e453c8b4cf | textbox | Date Completed:
1a5c7f58-ec4d-411d-b6c5-191a69c3b60b | checkpoint | 5.6 NCR
bfc30203-a341-406d-8b69-b51beaf862a8 | note | FREQUENCY: Prior to lot closure
20dbd986-833d-4878-b3c0-42a9e1d67de5 | note | ACCEPTANCE CRITERIA: Details of any NCRs to be recorded
4cffa78a-6147-4deb-9b9f-65479b9c4337 | note | REFERENCE DOCUMENTS: WP 01 Cl 9.3
083312ee-7d21-4319-82af-e069c75a5a36 | note | INSPECTION/TEST METHOD: Verify
b45ab1bd-cbc5-4b33-a2be-8d53801f1d1b | note | RECORD OF CONFORMITY: This ITP signed
34275254-0e59-49d4-a1d9-48b4d6a1978d | note | IP
ef85bace-4a80-4c8d-819d-f0274d38cc99 | note | RESPONSIBILITY: Fulton Hogan
07b4d4ac-cb4f-407c-8d80-90becfa23adb | textbox | Date Completed:
b09b4a8f-797d-4f3a-a0e6-648d2c395fc8 | checkpoint | Final Inspection
004c51ec-2ac6-4827-88d0-b834bdfe452c | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
6013fef4-8392-4d83-a4bd-4bbd762095f4 | textbox | Print Name:
398dd287-ae40-4d1f-ae1c-e085e7608eeb | textbox | Position:
3db5451c-d836-4585-8390-c9164ae31227 | textbox | Date:
d7ec063e-611c-4e9e-adaf-5f2074f7ccfe | checklist | ITP-039 Hot Mix Asphalt (Bridge Deck) |  | ITP-039 Hot Mix Asphalt (Bridge Deck)
58e1f488-9d19-4b78-9420-bacad103258e | section | Preliminary Works
57395820-d650-4079-bf35-1fef5d95984e | checkpoint | 1.1 Check for correct documentation
17ba1f8e-0582-5ffc-ae1d-8616c9d524c3 | note | Frequency: Prior to commencing any activity
39cdd592-1d88-5026-a1f7-ddc815570eeb | note | Acceptance Criteria: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
1ab25a50-1d40-5b2a-a022-aff9b234faea | note | Reference Documents: Drawings and drawing registers
dd0b25ba-5b46-53d7-8415-78996c2ad85b | note | Inspection / Test Method: Visual inspection
7d39613d-cd9f-5c96-925f-b84e83162cad | note | Record of conformity: This ITP signed
00c4a6fb-ebfe-5d3e-b8a3-22805c72e6a8 | note | HP*
8cbe38e8-dca3-5420-8bc2-752303769014 | note | Responsibility: Site Engineer/ Site Foreman
7a02144e-848d-5ace-a4ae-93c0e4b2abdd | textbox | Date Completed:
d93c7cad-5c00-473a-a8ff-8b0926e3b0fa | checkpoint | 1.2 Implementation of all measures and controls
26b0a905-b024-577f-81e7-5a00ecf766f0 | note | Frequency: Prior to commencing any activity
b2d12075-5d1e-572d-8432-6626b36ea630 | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
bfab76f9-4d1f-5497-ad0b-fa2a45dfe879 | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
46bdca6b-3494-59f9-a6cc-71bbc83afcdd | note | Inspection / Test Method: Visual Inspection
92ec21fd-8eb6-5723-9d39-899584e37c8a | note | Record of conformity: This ITP signed
eeaef569-f5ef-5fd7-a097-aebc34126250 | note | HP*
89e52b71-9f61-5b45-b8ad-3887dc54bd1d | note | Responsibility: Site Engineer/ Site Foreman
f49ca45d-f861-5d48-b27d-eab33926f184 | textbox | Date Completed:
317cbe30-2a21-4b06-b91d-2c5f2e6ba8b2 | checkpoint | 1.3 Service Identification
f18feb1f-4e35-5a45-a1f7-700859e29f39 | note | Frequency: Prior to start
65f86fd0-a846-5254-baae-9ebb01aa2663 | note | Acceptance Criteria: Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected
e3c639b2-051e-57cd-92ea-f0fdde74f9f2 | note | Reference Documents: ITP sign off
5d3aa8cf-0b22-5e16-8d4a-62d918e84954 | note | Inspection / Test Method: Verify
45ba84a8-76dc-51dd-9826-81bb911d77a1 | note | Record of conformity: This ITP signed
89d5eeef-42a3-5a73-8a06-1de693d6618c | note | HP*
114c1e2e-d56d-5ae1-b381-351aaa8391b9 | note | Responsibility: Site Engineer
d7dfacb5-4bf7-54b6-a507-b35bd40be8fd | textbox | Date Completed:
09ded1a6-0997-45c4-a2e0-c8d14a31ddc8 | section | Construction Works
a9399a36-386d-4937-9107-5dccf3723ccb | checkpoint | 2.1 Saw cutting
2d7721da-c1ee-51e7-9402-2b9df5464ead | note | Frequency: Where required
ae3f6b73-d61b-5183-a083-199bc2700619 | note | Acceptance Criteria: Extent and location of cuts to be clearly set out and checked prior to saw cutting
84127890-790d-5a00-9f99-46877d5adce5 | note | Reference Documents: ITP sign off
f77a5277-7bcd-5215-8dda-e11bcf983975 | note | Inspection / Test Method: Visual Inspection
b51907de-ed09-548d-84c8-4e09fc83641f | note | Record of conformity: This ITP signed
052f6fb5-f5ae-564e-b2b6-35da015494b0 | note | WP
d80f5403-6bc4-5dd8-b24a-929d13b30126 | note | Responsibility: Site Engineer
d4e709ea-59c8-589d-a463-b8fe757a1592 | textbox | Date Completed:
ada727d8-a332-4756-ad6b-1707afcbcf36 | checkpoint | 2.2 Excavation Permit
53bb1da5-bc41-5f3f-91f5-7516cbe456cc | note | Frequency: During excavation
3bb51f0b-6361-568d-ad21-35fb713cdc34 | note | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing.
181ab458-86fc-5c81-829c-ae9375b9015c | note | Plant and equipment shall be appropriate for the task
06458665-30a4-53af-b0e3-200d26533a9e | note | Excavation operations shall not disturb areas outside the limit of excavation
aa6ef954-9147-563f-b180-dbf23625dc5c | note | Reference Documents: VicRoads 204.06
60fedb0a-f65f-5dae-a972-97736dae32a7 | note | Inspection / Test Method: Visual Inspection
5e95ddb3-2be3-57b8-9a4b-4a10ef00507e | note | Record of conformity: This ITP signed
081f2658-c797-5d96-bc5f-8b6b273bff99 | note | HP*
8f9e4d2f-a152-505c-ba71-e325e47ba788 | note | Responsibility: Site Engineer
5d40a03d-848f-52ce-9218-9469ba46d038 | textbox | Date Completed:
457aabec-2288-4a7a-804f-09bbaaeb03ed | checkpoint | 2.5 Disposal of Material
dcd6300c-c8a1-57c1-89a8-93f75e9a2bba | note | Frequency: All times
121d42a5-a072-5d74-a17a-b15ec45e009a | note | Acceptance Criteria: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
0fb33536-2701-5cd8-9bff-92d9ba2fbbf6 | note | Reference Documents: ITP sign off
6dd6ef68-7a9f-53a1-8edc-4ea0e312beb4 | note | Inspection / Test Method: Visual Inspection
c19ee478-993d-53c4-b17d-af8ec41feacf | note | Record of conformity: This ITP signed
a1428dc8-2194-5cde-9764-0d6105a1218d | note | WP
d0da379e-9486-52d4-8c24-2d19ed9ccd74 | note | Responsibility: Site Engineer/ Site Foreman
9167c07f-3586-5cf9-b7c1-f8aa58c4e80b | textbox | Date Completed:
8cd30147-4604-4a58-9bb9-8f8243152aa9 | checkpoint | 2.6 Maintaining cleanliness of site
fb62a9c7-968b-54f9-9f2e-ed3dee3acb6d | note | Frequency: All times
92a2075e-416f-5d70-8475-f0a16f94b9c3 | note | Acceptance Criteria: Site and surrounding environment are to be maintained at a good standard of cleanliness
438865d6-1225-5041-b040-784574c07c05 | note | Reference Documents: ITP sign off
274e549a-5a31-5e0a-9760-d9a5265a5a2d | note | Inspection / Test Method: Visual Inspection
08872d04-8be9-5519-823d-d6252384ecdb | note | Record of conformity: This ITP signed
2f433bac-9267-52af-bd88-4d0bb0108266 | note | WP
c549f36c-6b30-509d-b384-eaeb25dcb315 | note | Responsibility: Site Engineer/ Site Foreman
056090ff-97ba-585d-919d-b522386d7fbd | textbox | Date Completed:
12802673-3a8f-4e13-8ff2-e920dac40a7a | checkpoint | Final Inspection
7bd34bdd-b334-51df-a05c-9dc3ce8c332d | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
b5c76705-5b68-5a61-8f7b-a409620f82ab | textbox | Print Name:
d7ac6532-547c-500b-b811-6f6d5ca15639 | textbox | Position:
3b4373c6-64ea-58b4-aeb9-e1e64c9cb098 | textbox | Date:
a7f1f03d-db95-4641-bc12-a3d0b45b2292 | checklist | ITP-040 Profiling |  | ITP-040 Profiling
a3145305-e412-4ecb-b98b-f9132961c192 | section | Preliminary Works
7cf6bd6a-4c44-447c-912f-6857ddf6d9df | checkpoint | 1.1 Check for correct documentation
97c54224-c447-5197-9069-e4495b0bedfa | note | Frequency: Prior to commencing any activity
6daecadc-f256-54de-a1e4-02d4b402b0a2 | note | Acceptance Criteria: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
59518539-7c59-5db8-aa89-76259c219fd6 | note | Reference Documents: Drawings and drawing registers
3107d175-5d2d-5513-b8dc-6c8c181ed93b | note | Inspection / Test Method: Visual inspection
84ee334e-7c0e-5015-a99b-26d982019d43 | note | Record of conformity: This ITP signed
e563d5d2-ce90-595d-b0eb-e7e70c5967a0 | note | HP*
621fde66-b294-5590-9cbf-910e7301f7e4 | note | Responsibility: Fulton Hogan Engineer
88d64e37-9477-511b-82e9-87c0f0e7503a | textbox | Date Completed:
d4e12744-a2f9-4876-9dc3-3b0a8a46d09f | checkpoint | 1.2 Implementation of all measures and controls
ac22608f-a399-51f6-9652-43729f65fd48 | note | Frequency: Prior to commencing any activity
91471fae-f9a6-5454-a42f-19e4b46952a2 | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
82b39f5d-abc9-5699-9f6f-973f81121f10 | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
6244853a-5390-576a-a62b-b03ebda2f286 | note | Inspection / Test Method: Visual Inspection
b778c2c7-28b8-51b0-b2b0-dc8bf28e535b | note | Record of conformity: This ITP signed
0c434e1f-be73-50b5-9640-a13dcabc33a3 | note | HP*
16439db9-b58c-59be-a752-8f7175f9f3fb | note | Responsibility: Fulton Hogan Engineer
0bede1d1-d38b-58e9-8e37-9594dc217b07 | textbox | Date Completed:
6fe56937-938d-425a-997f-beea7392fab2 | section | Construction Works
67cab5d9-09d0-44d2-946a-eefa468169e6 | checkpoint | 2.1 Profiling Works
4449d6a1-c799-50c9-adaf-79e36131d89b | note | Frequency: Each lot
48a4f441-7eaa-539b-a0b1-7f3440a35f02 | note | Acceptance Criteria: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
a26641c2-959a-53ef-b76a-748f2b5b087f | note | Reference Documents: 402.02
647162cb-a223-544b-8a45-828eaa202bbb | note | Inspection / Test Method: Visual Inspection
f016e26b-c0f7-59a4-8c0e-ec6e9f51f1dc | note | Record of conformity: This ITP signed
6f1fdb96-f7dc-50a4-90b7-c396d507f36e | note | WP
9c3814cd-0956-5f11-a2a3-15769a02c460 | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
7912f9aa-45a9-51be-bb84-48a979b3023c | textbox | Date Completed:
5b31bde6-386c-4dd6-b5cb-5a42c77678b6 | checkpoint | 3.2 Depth check
66fa1fdf-bde6-5679-9c88-1b3a528f8584 | note | Frequency: Each lot
602d82c0-6c6d-54dc-9278-19e7cab3cf3a | note | Acceptance Criteria: Ensure average depth of pavement removed is in accordance with relevant methodologies. Ensure a maximum of 50mm to be removed per pass. After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straight edge placed on the planed surface in any direction.
bf58295b-16a7-570b-b100-0b9c5aaa37a1 | note | Reference Documents: 402.02
229ffd84-1ac3-56f8-bc36-1d40fde0cdf6 | note | Inspection / Test Method: Visual Inspection
b5863a80-7f03-5443-83d0-34f1cc80aaf9 | note | Record of conformity: This ITP signed
ada234b2-e3d4-532a-a403-07d24d1f0a4d | note | WP
2a388f4a-960a-5c31-8cae-db469e23dbc9 | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
f14389a4-fa57-55c6-9ba4-6a21d5e72654 | textbox | Date Completed:
233c163b-51d1-4847-9780-8389d65d5e8a | checkpoint | 3.3 Temporary ramping (longitudinal)
0e4d81f8-239e-5698-9e73-7fd78eabfa4b | note | Frequency: Longitudinal edges
95e44ac4-5ff1-50e0-8d83-4801e8a5612d | note | Acceptance Criteria: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
ffb5a7d6-da2a-5cde-bbdb-29386b0a10f6 | note | Reference Documents: 402.05
830aeb40-de89-5cba-afa3-0171d6903e9d | note | Inspection / Test Method: Verify
bec4641a-1028-558f-bcae-f65a6b7fbde9 | note | Record of conformity: This ITP signed
95a47d7e-642e-5295-9e59-db63c3f57b2b | note | WP
22086039-271f-519d-b349-e076343ae56c | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
5d0360ba-baf5-5b7d-85b5-1e20dca8d77f | textbox | Date Completed:
060193d4-3b8e-414f-ad58-8123a12e8c65 | checkpoint | 3.4 Temporary ramping (transverse)
3902fe53-38e8-5c24-ac4c-bf5642cb297a | note | Frequency: Transverse Edges
0d87018c-74bd-599d-8904-d18b69c2a7f0 | note | Acceptance Criteria: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
2e10ada8-219a-506a-a78b-3d940bfeb200 | note | Reference Documents: 402.05
7780f9ca-021e-57fb-90f1-3298d0403068 | note | Inspection / Test Method: Verify
8962aa8a-0d94-568b-8c97-a1d0462721fb | note | Record of conformity: This ITP signed
40fcde4f-b4af-50ba-8102-1e9a8c12a237 | note | WP
71e948e6-ec5f-58d1-afbe-ac8474c3df1e | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
64f82dbd-01f0-5ca6-90f2-3b80447a5cce | textbox | Date Completed:
f774ef02-473d-4432-9df8-fb8ceeeebd3d | checkpoint | Final Inspection
2ba2d2e8-1642-53b2-ab2a-ecd625c182a7 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
d1b51efe-c36a-505a-afe1-6e7869c67307 | textbox | Print Name:
fc2ce66f-00d1-5efe-b4dc-0b122b8b2913 | textbox | Position:
e2f61699-30d0-5667-b70a-7377a6cc6773 | textbox | Date:
cf5d8f67-c4f7-4f90-8e94-28e1fd95058d | checklist | ITP-041 Platform Bonding |  | ITP-041 Platform Bonding
1e6336db-7636-4cf7-897f-0fbc25b5669b | section | Preliminary Works
65bba1f0-86fd-4d41-8b81-24ed89d546d6 | checkpoint | 1.1 Check for correct documentation
f0d695f3-e2c9-599f-b2d7-a68c7b35b268 | note | Frequency: Prior to commencing any activity
408d8b8d-702b-5fa9-9579-30443ecf3990 | note | Acceptance Criteria: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
0a7c81a4-9cf5-5e8f-8df1-34783a288cad | note | Reference Documents: Drawings and drawing registers
05f021e5-50a8-5f40-a7c2-0370470e9781 | note | Inspection / Test Method: Visual inspection
27791457-c17c-5076-8d14-c794e7ed01c3 | note | Record of conformity: This ITP signed off
f5ee5d25-b9b1-51ac-a144-e72b9a80ffb6 | note | HP*
0cbcc85b-0fde-50db-9757-24fbe5171fb8 | note | Responsibility: Fulton Hogan Engineer
6949b7ce-6331-5fc1-a294-a024ed9fce25 | textbox | Date Completed:
46fbf62a-88a8-49d9-a9ad-7646d1fb3b39 | checkpoint | 1.2 Implementation of all measures and controls
070861e3-a6b2-553e-bfb6-f92738a5820d | note | Frequency: Prior to commencing any activity
fba398d7-a525-5406-a07c-2c9e556cb3c8 | note | Acceptance Criteria: •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
75d5f00b-37c2-5ae0-a54d-017949ee2c18 | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
2465b4db-cdb4-5eca-81f4-de05bca12be2 | note | Inspection / Test Method: Visual Inspection
169e46be-a6d4-5ec5-87be-d018f403fe6d | note | Record of conformity: This ITP signed off
ef5064d6-dae1-5efd-8431-48f916405eef | note | HP*
695ca31c-3f5f-564c-b0f0-94636162e3c9 | note | Responsibility: Fulton Hogan Engineer
983c934b-0624-5ff6-b46d-92f61d19859c | textbox | Date Completed:
1178249e-6d8c-4173-9d98-0d496b617116 | checkpoint | 1.3 Check Materials
27f701d4-cda7-58ab-83f6-26b3cd475152 | note | Frequency: Prior to commencing any activity
3e8b6e8d-b4d9-527e-9360-d7c65ed961bf | note | Acceptance Criteria: •Confirm bonding cable material & size is correct and in accordance with design drawings. •Confirm correct mould type and size is used for required CAD weld connections.
a45389dd-cb1f-5f9f-a37a-28147b66b220 | note | Reference Documents: Construction Drawings
7cb87a0e-de6a-5784-b8cc-01a2ed7ad447 | note | Inspection / Test Method: Verify
08bc3802-cd39-5e9b-81a9-f62f9b95caf2 | note | Record of conformity: This ITP signed off
09c38494-1f7d-5bde-8dfc-2dfdcb5dca3d | note | HP*
1b184c99-0ada-5a99-be99-d29481f632a0 | note | Responsibility: Fulton Hogan Engineer
ff056964-54d4-5104-8414-4e745996102c | textbox | Date Completed:
97ced493-05f4-4b9b-9fa7-f09e5d5acfdd | checkpoint | 1.4 Bond setout
1ee10d2e-d9ab-5020-8d8d-fd1b82599a83 | note | Frequency: Prior to commencing any activity
c1dc2204-0c6a-5231-9b92-a5fcc42be3be | note | Acceptance Criteria: •Confirm bonding loop and connections are positioned in accordance with the most current and updated set of construction drawings. Ensure that all locations are reviewed by a Fulton Hogan engineer.
8344c9e0-5e6c-544e-ae83-3cbad8d2932f | note | Reference Documents: Construction Drawings
1521a5bd-11dc-5343-a398-fda096154edc | note | Inspection / Test Method: Verify
443c5621-ac2e-5a00-bdda-c849edc75142 | note | Record of conformity: This ITP signed off
b8886ebe-5ef9-520b-ae6c-786e3b58a6c8 | note | HP*
e796c78f-aff1-5272-ad28-8a76412eb71d | note | Responsibility: Fulton Hogan Engineer
aa639460-caf7-55be-b55c-5bff4d13858f | textbox | Date Completed:
fc792f1c-0397-4525-8257-952255aedbf4 | section | Construction Works
cda5ac32-8f9b-4d81-8c1c-c46f56fdbd90 | checkpoint | 2.1 Laying of Bonding Loop
f5c9fd36-7a73-5562-bce6-f6658481cd05 | note | Frequency: Prior to Asphalt
79c1d320-3e33-521e-a0d5-9f1d05ac3785 | note | Acceptance Criteria: Lay bonding loop in accordance with construction drawings such that it connects to the electric cabinet correctly.
10a774a4-ed22-5514-86f9-5e6fb11dd194 | note | Reference Documents: Construction Drawings
74056e8d-b4b6-5c03-9e0e-d9a20308d9b1 | note | Inspection / Test Method: Visual inspection
00231cda-a0b0-50db-b4eb-16f2feaa101b | note | Record of conformity: This ITP signed off
98eedbbd-35cc-5470-bf3b-c4d40b095048 | note | IP
7028de1d-d8f6-5542-bc0c-b572f13ff587 | note | Responsibility: Fulton Hogan Engineer
0d018288-6b48-57ac-9fb2-f239ee04c6b4 | textbox | Date Completed:
71cecf00-013f-4900-9e92-2d49a8f5bc9b | checkpoint | 2.2 Laying of Bonding Furniture Connections
bb8078a2-57d5-52c0-8f82-44938be8de15 | note | Frequency: Each Lot
f31c0c8c-8fed-54f1-b9c6-cd432403a34e | note | Acceptance Criteria: Ensure furniture connections align correctly with structure and are positioned in accordance with the design drawings.
f478eae6-a4d9-56e1-9593-4a971526b247 | textbox | No. of Furniture Connections:
33ce6aa3-5eb9-5d2e-ac49-58d1d686264d | textbox | Furniture Connection Cable Size:
b44beb1c-1309-55ec-b25d-10d15f1270f5 | note | Reference Documents: Construction Drawings
1ec69e40-1365-5626-a737-2abb1b64da97 | note | Inspection / Test Method: Visual inspection
1ff1e675-5957-5495-9215-b4879662568e | note | Record of conformity: This ITP signed off
26fb6910-8954-58d5-af60-f178dc0bcb76 | note | IP
f28393ee-3e32-51ef-bf69-00c7b511e52e | note | Responsibility: Fulton Hogan Engineer
d74e7d06-f5ca-5a80-967a-68288fa28bb2 | textbox | Date Completed:
4a9f7b31-e13c-447a-9856-07fac159dd96 | checkpoint | 2.3 CADWELD Furniture Connections to Bonding Loop
3227895b-1285-5000-89f8-13617925f5da | note | Frequency: Each Lot
2ae6e3da-32c1-561a-b53d-461de8ea749f | note | Acceptance Criteria: Ensure correct mould is used when CAD welding furniture connections to bonding loop.
84400cc3-a5e0-5c87-ae4e-2cb64f8fadcc | textbox | CAD Weld Mould Dimensions:
dec004e2-1ff3-573c-844a-b484f94de38d | note | Reference Documents: Eritech CADWELD Exothermic Welding Manual
9c38a405-c160-5853-a74e-6469ed31499e | note | Inspection / Test Method: Visual inspection
c844bd46-a958-5af1-814b-0ea39ae082af | note | Record of conformity: This ITP signed off
3b9ba9d4-718f-57cd-8630-cee855114410 | note | IP
af490d01-b97f-5e49-9775-625d4b1d3f70 | note | Responsibility: Fulton Hogan Engineer
d8695058-8268-52b6-939f-8407e43bae60 | textbox | Date Completed:
ef5a68df-e283-47b1-8292-a1212a3595d1 | section | Construction Works
a649df79-c25b-4c4c-9baf-109787494da4 | checkpoint | 2.3 Weld Review
1c2d0163-3522-541b-8e2b-a04ed7155703 | note | Frequency: Each Lot
d871c010-c72b-560f-a151-531ef514342a | note | Acceptance Criteria: Ensure each weld is inspected and that a quality connection has been made. All welds shall be inspected by a Fulton Hogan engineer.
ab9a4223-7bc4-52ba-9b88-e6edbafc022f | note | Reference Documents: Eritech CADWELD Exothermic Welding Manual
406c20ea-ec97-5be2-a7f1-b559a9e03d43 | note | Inspection / Test Method: Visual inspection
f4698237-90bf-517c-9bf8-d1e1e98d7aa5 | note | Record of conformity: This ITP signed off
7a0a7fa2-4019-5505-8f55-4fc653c643eb | note | TP
d1c5225c-a2e6-5dd9-9869-ed7b13e1b080 | note | Responsibility: Fulton Hogan Engineer
1fe9b24e-d706-519c-80cc-157f4bfce62b | textbox | Date Completed:

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
ba4ae876-2bfb-4ba4-a918-43f2d87fca8a | checklist | FHC-ITP-001 - Clearing & Grubbing Rev1 | itp | FHC-ITP-001 - Clearing & Grubbing Rev1
c0530741-d95d-49f7-bebf-0a23566e026f | section | 1 - Preliminary Works
9fdf6b43-e199-42f7-a9a2-26ce07abee48 | checkpoint | 1.1 Check for correct documentation
e6dcc3b2-7bd4-59f1-8ecf-a32c46b75c8b | note | FREQUENCY: Prior to commencing any activity
2ee7d7ee-e524-50ce-a010-e5708e703282 | note | – – – – – – – – –
3e3d8d32-38f6-509a-9997-7b38f6b0d061 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
9b9c1613-f6a6-5de7-98e8-4fcb5b941fe7 | note | – using the correct and complete set of drawings
d9e4fe8d-5d66-5ed8-b33d-22cce91d3b24 | note | – all drawings are the latest revision
31afcb3b-6298-5f66-9ff4-ca32c8f579e7 | note | – – – – – – – – –
d5e72b7a-54ae-595d-aead-561299797470 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
08ef7d71-8bef-5c9c-a16e-5df7bcb1891a | note | – – – – – – – – –
0b8d196a-bcc1-5ceb-82d4-727fb3c812eb | note | INSPECTION/TEST METHOD: Visual inspection
a9dec69d-feff-53cb-92b1-c4a72c398797 | note | – – – – – – – – –
bd84b761-de39-5a10-abfd-b35e9ae6621c | note | RECORD OF CONFORMITY: This ITP signed
de04cdd1-198f-559b-a4c3-dc2f4611ce20 | note | – – – – – – – – –
e988117e-1dc5-5ce0-901c-eac77af39cd4 | note | HP*
480f193b-9710-52c2-b77f-f21077ec4d7b | note | – – – – – – – – –
cced1872-34d3-56b4-9ad7-170f8e4ac9ef | note | RESPONSIBILITY: Site Engineer / Site Foreman
616e01a5-b035-5ce6-8090-ebcb9acd0585 | note | – – – – – – – – –
a328f2c8-4339-566e-8376-031b0cdf66c7 | textbox | DATE:
bdecfd44-1df4-4f63-b7c0-3c6f0fcca5c0 | checkpoint | 1.2 Implementation of all measures and controls
9fd2bb25-dacb-52c7-b5a5-2eb7464d6c28 | note | FREQUENCY: Prior to commencing any activity
c959a3ef-1a0b-516c-b2b9-e167d4be5360 | note | – – – – – – – – –
6f8c8813-772e-53fe-84b7-db89e72b7bdd | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
04e2edba-abf1-5c7b-adda-dfb03f656795 | note | – – – – – – – – –
1d58483c-7758-5305-8a21-980ac477eb63 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
0c0d7e07-102d-58a7-8b57-820cd4891d5d | note | – – – – – – – – –
07a8282c-d702-52a8-b216-6feefea46410 | note | INSPECTION/TEST METHOD: Visual Inspection
6313d90b-a090-5cb5-a04c-881fe26ceb4c | note | – – – – – – – – –
3bf85a14-a3b9-5008-8fe9-67cd1a526062 | note | RECORD OF CONFORMITY: This ITP signed
201540d4-721e-5571-bc37-8cf7491e5b0e | note | – – – – – – – – –
e4628c81-e831-5c4a-bd98-f19e372633a4 | note | HP*
cab8b83f-7c58-5f2e-9418-922c6a78b584 | note | – – – – – – – – –
a80f016d-cfae-5bed-a2a6-3f47dc65e24a | note | RESPONSIBILITY: Site Engineer / Site Foreman
ed0f0cc7-e6e4-5819-bb69-7cf80d6eb4e3 | note | – – – – – – – – –
4e92a369-e15e-5af6-9afa-c80012251155 | textbox | DATE:
f037e5ef-8888-4ac3-8ca2-886ce106da18 | checkpoint | 1.3 Flora & Fauna
10531a46-2b3a-5128-80e5-1763d9954e9a | note | FREQUENCY: Prior to commencing clearing
21b9eca3-425e-5858-939a-5a69f60bc87f | note | – – – – – – – – –
c23efd3b-7c9f-52e0-8b45-1123516b995b | note | ACCEPTANCE CRITERIA: A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
075374d5-0355-5b52-a144-569153941388 | note | – – – – – – – – –
ff9c7d45-1d12-5e5c-9bad-3e13b324b5ef | note | REFERENCE DOCUMENTS: EMP, ECP
3e2d524f-b070-5bb1-b3d9-8f9f584805e4 | note | – – – – – – – – –
b63167af-f00e-5922-93a1-55e8b44a0c3f | note | INSPECTION/TEST METHOD: Visual Inspection
a5599b5f-8bbf-59f3-a2a3-18ece91c60d6 | note | – – – – – – – – –
ceac9e93-d1f1-528f-960c-d0fc9b0049e0 | note | RECORD OF CONFORMITY: This ITP Signed off
44c1a4d7-d754-5c11-b26e-229e6aaf5985 | note | – – – – – – – – –
fa284fa2-86b7-515a-8682-6a1b0eae64fe | note | IP
cb9c857c-c4fa-58a7-ab38-f456275484e7 | note | – – – – – – – – –
7853dce5-b7c3-5b85-9d3c-427b66064862 | note | RESPONSIBILITY: Site Engineer / Site Foreman
37d3e7bc-1770-5428-a88e-80e047c9f564 | note | – – – – – – – – –
66d71182-fd05-575e-9df1-8c2775c7c7f7 | textbox | DATE:
7adbdf2b-808c-46b9-824e-a5a1ba65078e | checkpoint | 1.4 Permit to distrurb flora & fauna
ed47595c-f736-5251-8690-1c57998c78d6 | note | FREQUENCY: Prior to commencing clearing
b7a64e61-5c5f-5a0d-8879-7de0068990c9 | note | – – – – – – – – –
e2d096ba-a2b2-5361-a70f-21d6731afd70 | note | ACCEPTANCE CRITERIA: MRPA has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
d84a0d7b-6593-50be-ab5d-073bf94ce586 | note | – – – – – – – – –
044c902b-c957-5fd4-88f6-b5424c675b5c | note | REFERENCE DOCUMENTS: EMP, ECP
07d447aa-2ea1-58cf-b03f-8abf9c66011a | note | – – – – – – – – –
a777118d-8183-5a60-a4d5-e2837802e6c1 | note | INSPECTION/TEST METHOD: Visual Inspection
62d63af6-467b-5cba-aad6-3760a65ff3b8 | note | – – – – – – – – –
7bb066f2-5246-5d01-b96f-0fc3881d12cd | note | RECORD OF CONFORMITY: This ITP Signed off
1034e232-9e11-504d-aed6-a9a2227cda99 | note | – – – – – – – – –
6a28b432-8463-5058-851b-b7ccdffbf56e | note | IP
d7993762-39a4-5386-a7d8-6b14b275029f | note | – – – – – – – – –
43d77f28-559a-5b82-9c4d-e787d8b2dcc3 | note | RESPONSIBILITY: Project Engineer
332710ee-e96f-5745-8241-24121defe054 | note | – – – – – – – – –
031e3a0c-4937-5e25-b28e-565daba53e2a | textbox | DATE:
5160693d-94c3-4428-8cde-32afe4e1dd6e | section | 2 - Clear & Grub
ca634078-edfa-4f3b-832a-b01af9cc7100 | checkpoint | 2.1 Define work area
6da68e9a-a46e-53b6-a6f9-60593e0c9275 | note | FREQUENCY: Prior to commencing clearing
5daad66a-f98d-586f-9b1e-1d951ea855ba | note | – – – – – – – – –
503d3431-0523-5a27-9b60-31a808b7b101 | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
ef3ce60d-f8e5-524a-8131-0736cee1b7de | note | – – – – – – – – –
e18a0277-2322-5c45-a2d5-1724dd30dd6f | note | REFERENCE DOCUMENTS: 201.03
4c886041-5aae-5385-89a8-ed07f12d9d05 | note | – – – – – – – – –
c6f836e3-1812-51b6-9361-f12647e0cca6 | note | INSPECTION/TEST METHOD: Inspect
fded211f-48f6-53bd-b3d4-3d0964c20696 | note | – – – – – – – – –
7120e82e-1a48-5ef4-b038-8d4bc7b8f412 | note | RECORD OF CONFORMITY: This ITP Signed off
eba3aca0-3bd2-5a17-a8bc-e2dbefd2d2fb | note | – – – – – – – – –
5d7d65e5-890d-54db-8490-26e3512390e9 | note | WP
6b29bcdf-7406-503d-a672-3a1ef7a8fc39 | note | – – – – – – – – –
6519b0f7-f3a8-54de-9d61-2cd14c50243c | note | RESPONSIBILITY: Project Engineer/ Superintendent
49e252e0-22eb-52d6-9920-86baa96faf51 | note | – – – – – – – – –
8b4244a9-3198-5819-a058-5bcbfaae5356 | textbox | DATE:
48f3e74d-02e7-43ef-b9f8-dbbb9f7b4313 | checkpoint | 2.2 Joint Inspection to Mark vegetation or habitat to be removed
87974c1e-96ad-5313-bce6-e5bc6456c69a | note | FREQUENCY: Prior to commencing clearing
46c2ff38-95ed-5e28-bb8e-2f1f0c928112 | note | – – – – – – – – –
afd85d55-5b26-5149-a4e0-2f252d3198a7 | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent to confirm and clearly identify and mark trees to be removed, consistent with Appendix O Tree Assessment Report.
39b5550a-8fb3-5541-9dff-2223860c0b8b | note | – – – – – – – – –
9d67e721-8a9b-58b9-b3fe-e34f52ae79ac | note | REFERENCE DOCUMENTS: Drawings 201.10
cdc9cd79-b448-5d23-ba27-d60cef02c953 | note | – – – – – – – – –
7a1c5505-652c-50d9-bbda-ac05284a6709 | note | INSPECTION/TEST METHOD: Visual Inspection
74c2030f-f5f4-54bf-bcf8-69bb00cfe64a | note | – – – – – – – – –
c55b2145-9510-58c9-bbc5-11bda0719a61 | note | RECORD OF CONFORMITY: This ITP Signed off
17ca2834-5b07-59ef-ba22-2ec45ac5a0d2 | note | – – – – – – – – –
b95bfdb9-8be8-5386-a65d-195fcd46fef0 | note | HP
6f98968b-3106-5f42-b2d2-ec2a8b54c47a | note | – – – – – – – – –
d8f59f6c-fdc0-5d06-b4d1-a74614713356 | note | RESPONSIBILITY: Project Engineer/ Superintendent
08ae5427-9896-5418-870e-764616c3fe47 | note | – – – – – – – – –
c2f2c936-a140-55ed-8ddb-f1078a40ae81 | textbox | DATE:
c8f0aeb6-b1b0-4684-86e1-0cfd63750d51 | signoff | AUTHORITY HOLDPOINT
da37566c-8975-4fef-85e1-434e9ce9cc9f | checkpoint | 2.3 Identify No-go Zones
134d800e-6f57-546c-ae49-3e8320e400b6 | note | FREQUENCY: Prior to commencing clearing
7c282dac-d215-51de-ac8a-f885ef8544b8 | note | – – – – – – – – –
9db41c63-ffa6-57d3-a476-3adef6214d8a | note | ACCEPTANCE CRITERIA: Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing.
62bef960-b03e-59fb-90e0-5b8b6157aa0f | note | • Signage shall be erected outside the limit of the of the vegetation or the habitat site, at intervals no less than 20 metres apart or as per the SSEMP
053ad952-f6cd-560b-b98c-61c7ec7f577a | note | • Prior to any work onsite the contractor shall fence and sign all no go zone sites as per the EMP.
0704e285-5979-539c-bd48-d8aad039510a | note | • Any works required inside TPZ shall be completed under the supervision of an Arborist
b17a26de-52d3-5e20-97dc-a5ae60bfb415 | note | – – – – – – – – –
7b12b563-0640-5bd1-a382-3850cb7647b1 | note | REFERENCE DOCUMENTS: Drawings 201.10
d639f70d-238c-5301-afb6-791f5a0d981c | note | – – – – – – – – –
59b254f1-77d0-5897-8b5a-36e3e91851c1 | note | INSPECTION/TEST METHOD: Visual Inspection
298aba86-65f8-5f82-9573-e122f7c2f7cf | note | – – – – – – – – –
e4498b8e-7a23-5816-b176-298bc41e1d5b | note | RECORD OF CONFORMITY: This ITP Signed off
c272c779-9a1f-50a9-9302-6c11af58b966 | note | – – – – – – – – –
7be6c901-1964-59c2-a260-fc4cc775f548 | note | HP
19e146f7-a2ea-5e36-a14a-23302df07f0e | note | – – – – – – – – –
69c6c3f3-2a30-5bfe-982f-0b30479eb081 | note | RESPONSIBILITY: Project Engineer/ Superintendent
9ec4270e-fad1-55ba-a3a6-ffb93cc68e30 | note | – – – – – – – – –
0e9b1653-4ce7-5dd2-8f04-0c25911bd119 | textbox | DATE:
23d005e9-4e63-478c-ac40-124780ee7ca1 | signoff | AUTHORITY HOLDPOINT
e4ef2818-618a-4e66-801d-f7925642d9f2 | checkpoint | 2.4 Clear felling distances of trees are adequate.
592b2f1f-c709-5a4c-a3fa-fe976065be3b | note | FREQUENCY: Prior to commencing clearing
7ea0877a-9309-5d2d-8136-c1106311682d | note | – – – – – – – – –
b1a94292-9bbd-51ee-86f2-60ae8e72d9a2 | note | ACCEPTANCE CRITERIA: Ensure the clear distances are adequate and signage is inplace as planned. Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
a56c1a1a-d8e3-585f-8539-d1b03620f710 | note | – – – – – – – – –
e4359286-ba9e-58ad-ae55-06ecff95f337 | note | REFERENCE DOCUMENTS: 201.04
b71e1191-8567-5d6c-978f-b1bad408a5fe | note | – – – – – – – – –
c98db2d2-f1d0-552c-aac5-478d11c26611 | note | INSPECTION/TEST METHOD: Visual Inspection
eecf0993-a010-5671-8c86-ff251bfbe632 | note | – – – – – – – – –
84254679-574d-56ef-9a21-79a2632417d9 | note | RECORD OF CONFORMITY: This ITP Signed off
46dcaa6e-69c5-527b-83cf-61e130f47372 | note | – – – – – – – – –
caa74693-3f79-5db9-9f85-9840fb0168d3 | note | IP
a04eb3dc-19b7-593a-99e2-c6901db1dfc8 | note | – – – – – – – – –
92cb53fd-6157-5d85-b22f-82119ab8bac7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
72ca7e0c-81fc-511f-830c-119edd05ea60 | note | – – – – – – – – –
55c7a822-750d-5870-89cc-5c02ebf179a9 | textbox | DATE:
4180bedb-43dd-43c1-b146-a959733628e8 | checkpoint | 2.5 Clear and grub trees and vegetation
4542f0ec-e1ea-59be-860c-d3562a44e0bc | note | FREQUENCY: After clearing
f6c96c8a-c358-554f-bc9f-6933602af8cf | note | – – – – – – – – –
8deb6531-b71e-5193-8d1d-031596b2b0e3 | note | ACCEPTANCE CRITERIA: Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level
2eed7043-a229-5835-8978-ab2db9cbbe9a | note | • Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
6daa008e-19a8-5e15-965a-5d0ec7b4b9c1 | note | – – – – – – – – –
4a46a01a-0468-5571-86bf-b8d549f63640 | note | REFERENCE DOCUMENTS: 201.04, 201.05, 201.06
48752c64-1e1b-5804-a1cb-2aced2f3faca | note | – – – – – – – – –
e6e61541-e966-5317-a3e1-3a01bae3a6ec | note | INSPECTION/TEST METHOD: Visual Inspection
1cae2819-0200-5024-b403-6cffd323cc71 | note | – – – – – – – – –
3b3e2c5b-45c1-5c37-b14d-43d7817ae9e0 | note | RECORD OF CONFORMITY: This ITP Signed off
54d0c481-497c-5be2-9ad6-2a309264dd96 | note | – – – – – – – – –
583a71ff-f70f-57c5-bc24-fc2f26fb8cd0 | note | IP
91d243c4-2755-520f-a63c-5defee33184c | note | – – – – – – – – –
1806d1ce-c4d2-52b0-8832-9e276571546a | note | RESPONSIBILITY: Site Engineer / Site Foreman
e44def45-a733-5fd7-9659-e8ba9ae2cf8f | note | – – – – – – – – –
2579c934-a627-5117-b7af-29a033853a6b | textbox | DATE:
ee38f035-6480-4567-9785-1105297ecbb2 | checkpoint | 2.6 Backfill holes
b470abd3-7415-5620-b8e9-a0f4b773bca0 | note | FREQUENCY: After clearing
4f100dec-fb6b-5969-9a37-1aa4039c9973 | note | – – – – – – – – –
8ceb8397-9f1e-5c02-b61d-5b890e009403 | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material to the sorrounding material and compacted to the same degree to the sorrounding material.
7b22c81e-eaad-5778-b613-9e19a98dc3af | note | – – – – – – – – –
8b1c6c12-240d-5762-be2f-2eeace712a8c | note | REFERENCE DOCUMENTS: 201.05
32418262-180c-5f86-b098-cb09d277e9c7 | note | – – – – – – – – –
40636e84-61d9-51a9-9f1e-6aab8b0801d4 | note | INSPECTION/TEST METHOD: Visual Inspection
6f077f8e-8b1a-5c28-94b2-7f49625b4ceb | note | – – – – – – – – –
a0339b5c-f759-5586-914d-ac5a92057eff | note | RECORD OF CONFORMITY: This ITP Signed off
ba1e1343-1afb-5368-acf7-878c2e27ebdb | note | – – – – – – – – –
ba160bd9-cc38-5867-a934-299dc0387a42 | note | IP
6e103d06-87f2-5466-b90c-e414d4b96da7 | note | – – – – – – – – –
561e6775-d5c5-5399-a55f-c438701a3c02 | note | RESPONSIBILITY: Site Engineer / Site Foreman
97562b94-96d3-51b3-b3ad-29dc08214d94 | note | – – – – – – – – –
c5c84e88-9971-53b2-8969-e1ac0019bdb2 | textbox | DATE:
9a2da537-d59f-4d86-b902-72e0deff0e3d | checkpoint | 2.7 Dispose of Trees and vegetation
2dbdd7fb-65d3-5c68-8187-781a48b3c0a9 | note | FREQUENCY: After clearing
ce5b1f9b-2a8f-5b8c-9087-98b615ee384a | note | – – – – – – – – –
4a4126a7-2333-542b-bd50-db847acc526c | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
eb87b8e3-2a45-56bd-910f-fa9f8586ba60 | note | • Noxious weeds shall not be mulched.
d3366421-0331-5ad7-8d7c-642d4e3ad162 | note | – – – – – – – – –
53c48ae3-6343-51c5-a59e-ee764128f85b | note | REFERENCE DOCUMENTS: 201.07
ae1ba0c6-a9e8-527b-8d78-b86cd214e706 | note | – – – – – – – – –
66cc49bd-05e0-5ffe-bde0-de28f598461d | note | INSPECTION/TEST METHOD: Visual Inspection
3fa04dea-31ca-5321-ace6-18909bc1d5e9 | note | – – – – – – – – –
44e599cf-f9a9-58dd-ada5-a59135a116c4 | note | RECORD OF CONFORMITY: This ITP Signed off
0e9e5daf-e7e7-5138-b8ce-24ac6ca023de | note | – – – – – – – – –
1513332c-43dd-534d-bc77-54906d3d259c | note | IP
8b96b2b4-ac2b-595a-82b9-8adb69c16624 | note | – – – – – – – – –
4a23602b-3643-5eaa-af98-4b8da1e425c8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
5c3138dc-271a-5265-b031-c188a6a1332d | note | – – – – – – – – –
84569632-646d-5b5d-b0cb-81ae9be103fb | textbox | DATE:
b0e2d622-5404-4994-acfb-3e8818037260 | checkpoint | 2.8 Dispose of concrete, bituminous and other recyclable materials.
2350b3a6-e6a1-592d-8577-890a21bc33ff | note | FREQUENCY: After clearing
d82cf48e-f62c-5892-aecb-4cc13422cd1c | note | – – – – – – – – –
d0f48c83-d0ff-5c38-aa98-7f3fbe8c80a4 | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
4a22d1f6-6662-5236-b037-7dcb63504fdd | note | – – – – – – – – –
1562efd3-d415-50ad-a4dc-8091ac18f7a4 | note | REFERENCE DOCUMENTS: 201.07
e3fbb71a-7cae-521d-a187-445f6fbe1dd5 | note | – – – – – – – – –
b53da298-3f7c-57d7-b1c4-e734c73ed44c | note | INSPECTION/TEST METHOD: Visual Inspection
fbd09017-defe-5d73-a69b-1da55f75b408 | note | – – – – – – – – –
b1c7a30a-f6dd-5e3f-894d-0fffba9e8dfb | note | RECORD OF CONFORMITY: This ITP Signed off
3adb195b-b7bc-5bf9-a5bf-867bda716495 | note | – – – – – – – – –
8c9380a5-ea8b-5dc3-8ea0-bfff32bdb861 | note | IP
2b409cbc-3045-513e-9a9c-c6db324a33e8 | note | – – – – – – – – –
a0926efb-9cce-5942-8518-043dbb16a363 | note | RESPONSIBILITY: Site Engineer / Site Foreman
d045b675-9643-54d0-868d-bb69edfea71c | note | – – – – – – – – –
10849a2a-c5c8-555c-a55c-2eb066312b1a | textbox | DATE:
94e505fb-fb03-4514-8217-12cc61a98a51 | checkpoint | Final Inspection
819f7797-dc5f-5a7f-ac12-2f6c35598166 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
16042e92-16b2-5d74-b04e-b4421fe9f68f | textbox | Print Name:
71585eeb-c599-55d2-aa19-3632cb66053b | textbox | Position:
c0af52fb-e1d8-597d-8841-c07fea9d3771 | textbox | Date:
37f73aff-789a-4324-8f4e-e56d16fdc36a | checklist | FHC-ITP-007 - General Demolition Rev1 | itp | FHC-ITP-007 - General Demolition Rev1
9bf2e09d-e3ef-424f-a02d-94ff75667f6d | section | 1 - Preliminary Works
ea34fa49-f189-42c7-8aa1-65b9fe356268 | checkpoint | 1.1 Check for correct documentation
0f72f9a2-1d14-5144-a0a6-3c0b2bd0eca5 | note | FREQUENCY: Prior to commencing any activity
f76df822-5cf0-55c6-9df8-62c29a5e2f95 | note | – – – – – – – – –
58e6fb01-1ff3-5227-bec3-eb529e470894 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
416ed5b5-6a8f-5f4b-ad39-e0a4302fac85 | note | – using the correct and complete set of drawings
467dc81e-0273-5696-9ec3-32ce41b3a711 | note | – all drawings are the latest revision
77e1f763-8302-53ea-9292-936e11b363c9 | note | – – – – – – – – –
cf4bafab-fa68-532e-80b4-29286fefb1ab | note | REFERENCE DOCUMENTS: Drawings and drawing registers
d161bf70-3d0d-5994-a23c-1c79c2d52fb9 | note | – – – – – – – – –
e7db19ad-7657-587d-a2e1-2e42ab32aeab | note | INSPECTION/TEST METHOD: Visual inspection
f0034bd5-2a1d-5815-8d33-ac1f084a70a2 | note | – – – – – – – – –
c9947c19-fd05-5c7c-b730-7625832da873 | note | RECORD OF CONFORMITY: This ITP signed
c5e81e08-cf90-5675-9f4f-86ec44e27105 | note | – – – – – – – – –
59d1c252-7e89-5f95-a761-580f98fa3b6d | note | HP*
283d5dac-be26-55e0-bb15-9ad86d135e24 | note | – – – – – – – – –
933b828e-494d-559c-bc02-131162f70300 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
32213cc4-6b02-55d6-986c-fab8f46805fe | note | – – – – – – – – –
876e7062-4b46-5840-ab30-8584c958033b | textbox | DATE:
673e1b9d-7b05-4a9c-a208-f96f4c649777 | checkpoint | 1.2 Implementation of all measures and controls
157588e7-4e9d-5013-83a8-47f807e27a6e | note | FREQUENCY: Prior to commencing any activity
d55a82ba-fa29-5700-ba8a-fd5692b9023e | note | – – – – – – – – –
11e95d28-f20f-5aee-b355-74af2cc98c62 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
bc9f79f0-83f1-5a7d-a88c-310d1a32c2ad | note | – – – – – – – – –
ba4734c6-3167-5c9e-9ca4-be0c2898f969 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
8bf01cda-2a9b-59e3-a005-9f279967f047 | note | – – – – – – – – –
fb74c070-83da-5353-8038-6e31d19fcc82 | note | INSPECTION/TEST METHOD: Visual Inspection
d80fe129-0496-529d-a10b-092bb3e00af4 | note | – – – – – – – – –
a4d8a067-a992-5b36-8b59-f040c78facbd | note | RECORD OF CONFORMITY: This ITP signed
72855361-0a39-5328-ab70-e599364c3d70 | note | – – – – – – – – –
ad051910-3ff4-5c85-aed2-f61174cb54e1 | note | HP*
80efa676-393e-56f1-975e-f24909e8131b | note | – – – – – – – – –
18a06cef-789a-5fb5-b6bb-012aea173109 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
1b4b7501-dda6-55ee-81e9-229f9d1577c4 | note | – – – – – – – – –
e5f6cded-d755-5b3a-a0df-afb876c76fa0 | textbox | DATE:
def6fec9-58d4-4d37-9605-2af3a998c2b5 | checkpoint | 1.3 Service Identification
e1103ccb-bd88-5c70-a471-c79d929dc0b9 | note | FREQUENCY: Prior to start
397f1c9f-566f-5aa6-8a5e-b0e227f27ce5 | note | – – – – – – – – –
8be0d139-bd76-5bab-a29d-42aa4031a1e0 | note | ACCEPTANCE CRITERIA: Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected
e05d5724-37fa-5c92-909f-76c90ae73b5d | note | – – – – – – – – –
34dc70c9-44e3-56f7-a5fc-00023d21af47 | note | REFERENCE DOCUMENTS: ITP sign off
cc49ee4e-8ee6-5797-b3d1-3783e5fb677b | note | – – – – – – – – –
b404e4a1-d459-5ad6-93ed-12028160197c | note | INSPECTION/TEST METHOD: Verify
999142df-dfea-5518-baa0-ad564cf8988c | note | – – – – – – – – –
d07d97b1-3423-5a53-bd29-74c24f6359a6 | note | RECORD OF CONFORMITY: This ITP signed
8dc595f2-dbf1-51b8-8f26-ee67110d2d6b | note | – – – – – – – – –
db4a9c28-bddd-5e83-a9d3-d4e239e21ac6 | note | HP*
5ebe0087-0ca4-503f-bcc6-f555e62184f3 | note | – – – – – – – – –
e088aec7-fc3d-5605-8a6c-4a1b3316d579 | note | RESPONSIBILITY: Site Engineer
66c50d86-287b-5295-be6e-92d04dc7488a | note | – – – – – – – – –
668cadf2-10fe-5697-909c-65c8c5b4455b | textbox | DATE:
f655965b-a632-4be9-b13c-7da0d9c228b8 | section | 2 - Construction Works
306ddfac-5e68-4520-926e-baac0a7474e7 | checkpoint | 2.1 Saw cutting
3975ea70-7aaa-5fe2-a936-7c3c8692fcbf | note | FREQUENCY: Where required
41b42f77-1790-5c1c-82a7-55dbe28ff132 | note | – – – – – – – – –
e7259cda-b01c-569d-8123-3afc3b0a825e | note | ACCEPTANCE CRITERIA: Extent and location of cuts to be clearly set out and checked prior to saw cutting
6d465857-a9ef-5403-b202-1a3331445fc3 | note | – – – – – – – – –
41d7dffe-cae5-505a-94e7-a3327abcff41 | note | REFERENCE DOCUMENTS: ITP sign off
db05e12f-3304-586c-9f04-086a8e143955 | note | – – – – – – – – –
a9464622-2ffa-5d61-868e-1305119a70c3 | note | INSPECTION/TEST METHOD: Visual Inspection
65b0722e-efb7-5c16-8eff-91d35cb5b1fc | note | – – – – – – – – –
ec141b96-9380-5fa7-8dde-d717dbad77d2 | note | RECORD OF CONFORMITY: This ITP signed
5ab86197-d4e0-5a78-9edb-ea378ad5d1a0 | note | – – – – – – – – –
58ce03bb-9c3c-5668-ba02-90176bc82f2f | note | WP
a77ac859-3a2e-5344-9eb6-073ad064580c | note | – – – – – – – – –
09789328-89d8-5ee1-b99b-5f21d90702f0 | note | RESPONSIBILITY: Site Engineer
e86ae424-eed2-5649-8be4-b152c6eeae3c | note | – – – – – – – – –
af2b8f1c-e160-5b73-9ab6-bf6ea6ef9a9f | textbox | DATE:
04c5889a-659c-42d9-bbf7-45bf9c87a075 | checkpoint | 2.2 Excavation Permit
485f9eeb-b296-56cf-9ab2-a374f29aceb1 | note | FREQUENCY: During excavation
d9448555-6bba-5328-bbd1-4706a7ac5045 | note | – – – – – – – – –
49b4ca97-7930-56f4-9baa-8e4571ceb591 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
d5bd2dc7-fbc3-5e61-acf0-b942b7b5b717 | note | • Plant and equipment shall be appropriate for the task
111c56ef-3c2f-5340-9c95-fe69d361f024 | note | • Excavation operations shall not disturb areas outside the limit of excavation
79b790f5-ec66-5a72-aa23-947c7c006de5 | note | – – – – – – – – –
e2f7e0b6-d073-54f1-b309-3f1ce67d6836 | note | REFERENCE DOCUMENTS: VicRoads 204.06
3d4749f8-7a80-51d3-870a-64e931ce249f | note | – – – – – – – – –
0891bc1f-4038-5b41-800e-de94d28943da | note | INSPECTION/TEST METHOD: Visual Inspection
79267a45-256c-5759-b85c-a16d226f9903 | note | – – – – – – – – –
333aa471-5dbc-54ab-a765-18ed2a07048d | note | RECORD OF CONFORMITY: This ITP signed
e8dc3bb7-b5a5-5d06-b35e-ac149cc21650 | note | – – – – – – – – –
53020e10-3a6d-585b-9a8c-c476e625a75c | note | HP*
8d78e7d4-f2ff-5224-8594-e4fbc5763f17 | note | – – – – – – – – –
9f2caf17-82d0-545f-8502-ac7a020be727 | note | RESPONSIBILITY: Site Engineer
a92ca9bf-35f1-56c8-8242-00901fcebd17 | note | – – – – – – – – –
3def47db-3441-51ae-ac2f-a060cc518fc6 | textbox | DATE:
97fa912e-2cb6-4a83-89ad-cd70aa0b8e1b | checkpoint | 2.3 Redundant Pits
36fb3b1c-eae6-5820-ae94-cb0793b2a299 | note | FREQUENCY: After clearing
c507f9b5-e7c6-5203-b7d3-6e6ae6324700 | note | – – – – – – – – –
92281221-1092-5737-81a2-a21d64dcfb20 | note | ACCEPTANCE CRITERIA: Any redundant pits, are to be removed to a depth no less than 0.3m below the stripped surface or no less than 0.6m below finished subgrade (wichever is lesser)
af008e49-e8fe-581d-af28-9cb54af190c9 | note | • Seal any pipe openings with concrete and backfill pit area with material and compact to a density ratio of 95% (standard compactive effort)
1e2cffe0-e2fc-5215-952a-ef9cfac880a3 | note | – – – – – – – – –
0b23f1c4-e762-5ad2-94f0-5bae02400ba8 | note | REFERENCE DOCUMENTS: 201.05
bb04dbb0-4733-59bb-bb7f-8fcdbe481743 | note | – – – – – – – – –
a83f48f2-296d-5e63-a55d-d54bccf66a91 | note | INSPECTION/TEST METHOD: Visual Inspection
259e8c58-f690-5518-978d-9fa67e39cb4a | note | – – – – – – – – –
726635a3-9ddd-5967-8039-0f0a4416619f | note | RECORD OF CONFORMITY: This ITP Signed off
579e5cb9-7060-56d4-bb33-ec4104ba818a | note | – – – – – – – – –
40748e82-aa00-576b-82ff-5f7bba5e5bc2 | note | IP
d29f46e4-8917-5f9e-b757-71549540d485 | note | – – – – – – – – –
06f1ce32-2f41-539c-b3fc-589e086b3785 | note | RESPONSIBILITY: Site Engineer
ca00faf5-a9c3-52bd-bbb0-7cd6d4c301e8 | note | – – – – – – – – –
25ca9613-5677-5cbe-b3ac-609e6d631320 | textbox | DATE:
4225e98e-f644-45c0-8902-a135b798ebf7 | checkpoint | 2.4 Disposal of Material
ef5772e4-0433-5e06-81d7-f757ac7fec00 | note | FREQUENCY: All times
9cb4c39a-279c-5730-acc0-30f265f15b69 | note | – – – – – – – – –
2c846e98-17cf-517e-9814-71a7edf09974 | note | ACCEPTANCE CRITERIA: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
4fec8160-ca18-51ab-a15c-4d2a7b8e1783 | note | – – – – – – – – –
beca7b29-015a-5095-91a3-6045bab381f0 | note | REFERENCE DOCUMENTS: ITP sign off
c57049ec-7fd4-5501-8796-39e8d9fc4d70 | note | – – – – – – – – –
5a62a1fb-6ea1-5ae2-9a0c-e709a6740230 | note | INSPECTION/TEST METHOD: Visual Inspection
86546ea8-be2f-52a7-9234-406b4aa41c53 | note | – – – – – – – – –
7536f88c-2345-5407-87c1-41fdcb9e5227 | note | RECORD OF CONFORMITY: This ITP signed
4bfc516f-0e03-56c0-ad1f-929d21454ded | note | – – – – – – – – –
50882d5d-573a-5a06-bb09-8ba36d82b0a9 | note | WP
ee274132-5465-50d1-818b-367c73627372 | note | – – – – – – – – –
92153f2c-8ffa-57a1-8b9f-3850809d8c5b | note | RESPONSIBILITY: Site Engineer/ Site Foreman
5a100a65-14b5-530b-8070-13d225665b71 | note | – – – – – – – – –
8c5ee529-3f90-54b2-b1ff-6039c7b33b83 | textbox | DATE:
52c9b1e7-83bd-499e-bbfb-d216690ace57 | checkpoint | 2.5 Maintaining cleanliness of site
1588681b-1cb2-5444-a0c6-94d826203529 | note | FREQUENCY: All times
43b885d7-5618-547e-ae0d-7b6c77d7ffe5 | note | – – – – – – – – –
559a0e21-38cf-5ded-898b-22c1b5957d5e | note | ACCEPTANCE CRITERIA: Site and surrounding environment are to be maintained at a good standard of cleanliness
11c32e83-113b-57a1-a7b9-e90d3dad4072 | note | – – – – – – – – –
82ea3afc-4419-5621-9309-8c69c383b562 | note | REFERENCE DOCUMENTS: ITP sign off
a6ed21a4-d8ae-5fe3-95a5-ee5eabaa4b00 | note | – – – – – – – – –
5ea136f0-d79f-52a1-967d-714b7d89bb95 | note | INSPECTION/TEST METHOD: Visual Inspection
dba99ce8-a087-53e4-bd69-604690231c53 | note | – – – – – – – – –
5bee1d66-85c2-59ac-be7e-28486aa7f088 | note | RECORD OF CONFORMITY: This ITP signed
492e690b-ef91-5539-b11d-764920ab1d6e | note | – – – – – – – – –
f4c25ae4-b095-5f32-b543-8832505250cc | note | WP
3cc437d3-4be1-51f4-8ab9-f6521a2977cf | note | – – – – – – – – –
e5c8a9da-75e6-5106-9d26-e2a166062e3b | note | RESPONSIBILITY: Site Engineer/ Site Foreman
30329877-bef0-5a23-9ad9-4d016dd542ea | note | – – – – – – – – –
16bd66e4-d573-5c55-91e0-255b7f32090e | textbox | DATE:
877ebdd2-54a1-4c66-b6ad-627483a8f6a1 | checkpoint | Final Inspection
8bd27bb2-42ca-5ff5-a195-470bd8348ea7 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
80757c94-5e81-5f39-a568-a1f7b883a2e4 | textbox | Print Name:
67687b92-5daf-596e-9f86-75e68a16f1e9 | textbox | Position:
8379b47f-03bf-5a20-bf89-85ca4c0fd14a | textbox | Date:
25925808-5202-4950-848e-203edb7d38f5 | checklist | FHC-ITP-009 - Profiling Rev1 | itp | FHC-ITP-009 - Profiling Rev1
1ba3f875-9d56-425e-abb0-359a0ff3740c | section | 1 - Preliminary Works
f56dec5f-d880-4028-a18e-ce7127ea8e87 | checkpoint | 1.1 Check for correct documentation
37e3f3f7-9b75-543f-8642-32534a934c4c | note | FREQUENCY: Prior to commencing any activity
f650f803-f4db-5eb7-922e-256223948379 | note | – – – – – – – – –
a781ae37-008b-5f59-b407-9bb9cd3347da | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ce88abe1-2acf-5002-b8d1-172446068f7f | note | – using the correct and complete set of drawings
389726e2-b1de-5f00-8f04-592b06b78bae | note | – all drawings are the latest revision
fb047f76-7b0d-588b-939d-eda9c9d61470 | note | – – – – – – – – –
2e1183b8-1401-5393-b322-3e2de55d300d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
4e25534f-e155-57b3-9af2-dba9b0c9d15a | note | – – – – – – – – –
02b6563f-6ce0-516c-a21f-12a2e7472ab9 | note | INSPECTION/TEST METHOD: Visual inspection
dc1cadb3-893f-5dc5-bec8-6fc15cbf2b38 | note | – – – – – – – – –
6c54f80e-8a68-50d1-9a59-e0cd04ffbc9f | note | RECORD OF CONFORMITY: This ITP signed
3bb53a89-4aa8-54bb-b018-9545070a6400 | note | – – – – – – – – –
edadd599-767a-50d1-a8c2-b1a0da2d2915 | note | HP*
909026d4-57aa-58f1-a8e8-95f1d0829646 | note | – – – – – – – – –
9d5b84ca-6744-5fad-8aa4-5ae900df5e81 | note | RESPONSIBILITY: Fulton Hogan Engineer
73ecc649-0833-5d75-b0ec-acaa85a29a78 | note | – – – – – – – – –
3525b2fc-7751-5455-9a4b-59f7568ccc69 | textbox | DATE:
3be44d45-fdf0-4882-bdd6-c53f92ccbb59 | checkpoint | 1.2 Implementation of all measures and controls
33a60d83-9e4c-5933-b94e-6f3fe7aa4675 | note | FREQUENCY: Prior to commencing any activity
91b42757-7eab-5404-8ae7-691f441422c6 | note | – – – – – – – – –
bd5115c5-e056-58e4-ba2a-627f7b93ec1f | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
0f7fe5e1-df4f-5bff-9bba-0719c401ef23 | note | – – – – – – – – –
9d18e5bc-56a5-5b8b-ac65-7eb739fddabd | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
8eb491fd-a17c-58d3-bb97-417a6dc46729 | note | – – – – – – – – –
b8f5b7f0-52a0-56c5-97cd-262f2a88d80a | note | INSPECTION/TEST METHOD: Visual Inspection
0c22e704-a83a-5125-b085-216a39f0c294 | note | – – – – – – – – –
96d12a57-dd6f-5393-a9c3-b93b6d27e3ec | note | RECORD OF CONFORMITY: This ITP signed
d05ab78f-1d87-5fc1-b3e1-26805249d59f | note | – – – – – – – – –
9720cf8c-ee99-58ac-b9a0-c23ea914d36c | note | HP*
b75b8e31-3b08-5502-937a-1c56e5ad8f95 | note | – – – – – – – – –
7ca23df0-6907-5b80-a308-6d001cec9ae4 | note | RESPONSIBILITY: Fulton Hogan Engineer
077b6979-983c-529c-aebc-763df071ea05 | note | – – – – – – – – –
5fd8369c-c154-5676-bdf6-21736b6f7307 | textbox | DATE:
d90e9fd6-85ac-4d21-9715-285ff8f902e6 | section | 2 - Construction Works
f8ed8542-07c2-4802-8241-3c8de966a22d | checkpoint | 2.1 Profiling Works
855cc4d8-134d-50ba-ad9e-9e50a3646e1b | note | FREQUENCY: Each lot
2d3f5b6a-3259-576e-882b-1609145fa757 | note | – – – – – – – – –
cf4a4747-02b1-5ca4-ac64-4d1b346a2d5c | note | ACCEPTANCE CRITERIA: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
0d3d7ba1-ae87-5d16-b050-088618012bcf | note | – – – – – – – – –
f6cdeec9-d550-526b-be2b-239c4614ee16 | note | REFERENCE DOCUMENTS: 402.02
1582e131-4559-58e5-8054-8992e778e2bf | note | – – – – – – – – –
c2b0245d-c186-51b8-987c-d873225e6d31 | note | INSPECTION/TEST METHOD: Visual Inspection
069510ce-82ea-5476-8a5c-a6e15a05dee0 | note | – – – – – – – – –
2e8f6765-8ed3-5f10-aa1b-787bcbd065a0 | note | RECORD OF CONFORMITY: This ITP signed
b41d3239-e821-5512-9620-a8c47e1a8cf9 | note | – – – – – – – – –
7600376b-0286-55b8-a90e-d8b568a9a2ee | note | WP
807bb272-e139-553f-9939-5666024f4983 | note | – – – – – – – – –
f22bec51-a7a2-5478-8bce-226d0a724a63 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
6e5464a6-5775-5f15-b5fc-22d16a32542d | note | – – – – – – – – –
3631db8d-3c3a-5fd3-8a27-d496110a9c5c | textbox | DATE:
93732d02-fa8b-4ea8-a6c3-304501ce9fbb | checkpoint | 2.2 Depth check
f028dc51-b78f-569c-b4c9-67770c38c7d4 | note | FREQUENCY: Each lot
01262ee8-7c9a-5167-8ee2-86d7ee05125e | note | – – – – – – – – –
1046859c-a5d2-5ee0-8bbc-5f938e8f2a15 | note | ACCEPTANCE CRITERIA: Average depth of pavement to be removed shall be 40mm ensuring that all Wearing Course is removed.
d6681e6c-7a1b-5971-a70a-23b10375f4de | note | • After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
129c5933-9431-5dc9-99cb-05f887585f81 | note | – – – – – – – – –
9025001d-f9a4-5132-9fa7-0e6a96eaba84 | note | REFERENCE DOCUMENTS: 402.02
483cded1-c377-5596-b7a8-e56b0be5ec5a | note | – – – – – – – – –
5c2f8140-a021-5a59-ac70-924a9ef612fb | note | INSPECTION/TEST METHOD: Visual Inspection
f3f38846-4074-5148-b44f-f96c87f86d34 | note | – – – – – – – – –
7303a318-7ead-54e2-b8d2-24320166b4f0 | note | RECORD OF CONFORMITY: This ITP signed
bf29d175-bba8-5f8f-92de-616d3026935b | note | – – – – – – – – –
60d6b213-9271-5a38-adfe-b9d294b55edb | note | WP
d6f20a84-b5d6-5298-9ed3-63aa31b7e18a | note | – – – – – – – – –
7e8218fa-4c69-5e29-aa3b-f441900af5f9 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
a9423c87-63a3-50ff-bbd0-d13ade49c9a6 | note | – – – – – – – – –
c16548fb-ab9e-560a-ba95-f4dfd14866d8 | textbox | DATE:
f42c3bf7-bfb9-46be-808a-d6073febf6d0 | checkpoint | 2.3 Temporary ramping (longitudinal)
92e6abe2-aa75-588e-a270-1f046395c871 | note | FREQUENCY: Longitudinal edges
50ee1d2c-97d7-5492-a2c3-e8cd10a17ba4 | note | – – – – – – – – –
b40d66bf-a2e6-5fd4-bec7-45d64ea06a33 | note | ACCEPTANCE CRITERIA: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
6f17ae8b-4544-586d-8353-27ac34f3d153 | note | – – – – – – – – –
a5b96c4a-faf3-5566-baef-1ae385779370 | note | REFERENCE DOCUMENTS: 402.05
e12b089f-8c53-58a8-9f71-80169b887031 | note | – – – – – – – – –
7d900a94-7191-5213-b314-1138be25a085 | note | INSPECTION/TEST METHOD: Verify
86d388af-dd3e-504e-acaa-2e6d2ffddad8 | note | – – – – – – – – –
bd5e62bb-3d57-5400-91eb-b2fac7321f84 | note | RECORD OF CONFORMITY: This ITP signed
577bcc81-3626-5c5f-a0fd-aa3d0e7d271a | note | – – – – – – – – –
774913dc-0fac-5bc6-8d7c-185b0d9938fb | note | WP
b79178f7-febb-5a7a-b871-3f15461d8018 | note | – – – – – – – – –
3a092179-0d06-5b9b-af08-165768e8925e | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
0c32e7e7-6c76-5e47-a247-ea7f84808274 | note | – – – – – – – – –
6f0d9338-9431-5609-bbf4-94f28967d3f7 | textbox | DATE:
21ae6f7a-a63c-4ec9-8bd2-d5b994fcf838 | checkpoint | 2.4 Temporary ramping (transverse)
3c87277e-0466-5ed5-8f4d-2ec1dca71043 | note | FREQUENCY: Transverse Edges
ac3a009e-c9bf-52b4-9e2a-17fe9e4468cf | note | – – – – – – – – –
ce8707a0-2647-5c1b-94c4-0724556702d4 | note | ACCEPTANCE CRITERIA: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
56a60683-4432-53dd-adc0-7bdfcb66e806 | note | – – – – – – – – –
85da91d9-e41e-5156-9fe4-04eac171116f | note | REFERENCE DOCUMENTS: 402.05
0a4eed8f-e36e-52ad-bf51-9ee0eab868ec | note | – – – – – – – – –
059ef69c-ed8b-5d9f-b81a-d09d76fd75bf | note | INSPECTION/TEST METHOD: Verify
f6c3dab1-a7e4-55a6-9e43-9d1302769b3b | note | – – – – – – – – –
b2fb6024-039f-5e83-85f2-47d963975645 | note | RECORD OF CONFORMITY: This ITP signed
57ae7e9c-1ee7-5947-9b12-c391b4702662 | note | – – – – – – – – –
3e77961d-a8cc-508d-a7d5-4e7a682cb3b3 | note | WP
e5208f45-3874-58e9-a94e-191c6e7f4386 | note | – – – – – – – – –
4b31d486-88ec-5615-8a5a-23c9d620b3a9 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
f6bd7d6f-a47d-5b39-8457-81e5bd6bad4a | note | – – – – – – – – –
52ce282b-c8af-5e94-8573-66d9faf6b319 | textbox | DATE:
db6d38ac-7d2e-46bf-a3a0-9bee52e50ba1 | checkpoint | Final Inspection
cb75cc3c-40cc-5f69-a4a3-26523bba237f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
960cdc42-5ab7-5da9-a80c-b0717db9827b | textbox | Print Name:
c7481e6c-8beb-5681-9dbc-ad9294e88e1f | textbox | Position:
e13cad12-f9eb-5731-b983-e4660f2d3272 | textbox | Date:
6d0a8280-526e-4193-9121-abc2d20dfde8 | checklist | FHC-ITP-017 - Basin Construction | itp | FHC-ITP-017 - Basin Construction
e6c0c491-e3e8-4aba-be3e-98e6769ab487 | section | 1 - Preliminary Works
99bde36e-382d-4d92-b88e-ed79fec1a5d1 | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
30dd1ddf-b55f-5ab4-b452-3a259b166b6a | note | FREQUENCY: Prior to commencing
beb8ea39-7e73-590d-a415-4d572622ecbd | note | – – – – – – – – –
ae2116b2-4788-5b5c-b551-364825b762e7 | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
ee730313-6074-5e2a-a8cb-6b9afa9cd95a | note | – – – – – – – – –
6e57de3f-7452-5500-b8a1-42975388e5ae | note | REFERENCE DOCUMENTS: Drawings and drawing registers
e8d5d10a-0fb0-5735-a42b-5a89486ffc76 | note | – – – – – – – – –
6e632dba-d8e7-5698-84cc-e655b632873a | note | INSPECTION/TEST METHOD: Visual Inspection
427638e0-3314-5217-beb9-9e3ff3205893 | note | – – – – – – – – –
22d3bda6-dcf5-5e11-9835-cae765658c49 | note | RECORD OF CONFORMITY: This ITP Signed Off
581a2d37-2ec2-58a2-bf31-7036cc6e3d4d | note | – – – – – – – – –
4243f052-ad09-5189-8aa6-ae3852be397f | note | HP*
f9de18e8-1a44-5a25-a03b-5442727ff23b | note | – – – – – – – – –
0b242a26-d682-551c-bfd4-58724e779ab5 | note | RESPONSIBILITY: Site Engineer / Site Foreman
db708fc3-52fa-5059-a52c-59c35b26b95a | note | – – – – – – – – –
541382de-c603-535c-8d8c-078860fe7041 | textbox | DATE:
e6b4ef8f-1d22-400d-b06c-3531173e4d35 | checkpoint | 1.2 Implementation of all measures and controls
09b1ebef-b261-5aba-a5a4-c2a02101a045 | note | FREQUENCY: Prior to placement
10378b18-d1e2-5a15-9209-db85d7fa85bb | note | – – – – – – – – –
04c8ae45-faa5-59f8-8742-6d3760d569ca | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
34f3bcb3-3685-524a-a1d6-e900cabcb805 | note | – – – – – – – – –
d04f81a0-7570-587b-a296-8283d3ea17a4 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
e8745594-de7d-559f-8065-4499fade20ef | note | – – – – – – – – –
eb0531f7-d4eb-533e-b01e-65c8c40776bc | note | INSPECTION/TEST METHOD: Visual Inspection
33da72e0-6d7a-5aab-9b44-c3c68a639b82 | note | – – – – – – – – –
8ef052d8-c628-5a9c-a230-ba8ca678fa3d | note | RECORD OF CONFORMITY: This ITP Signed Off
fa90d05a-d993-512d-ade7-d270e4833e64 | note | – – – – – – – – –
4b182cbf-e125-5691-81bb-d0f1d2aec825 | note | HP*
0cad6511-933e-5b05-bdf0-cb08c9853765 | note | – – – – – – – – –
c7d05210-80d2-5dbd-a0e8-9d0832093046 | note | RESPONSIBILITY: Site Engineer / Site Foreman
306f2819-07a4-5cd7-a65b-00fb95d7bb74 | note | – – – – – – – – –
a7cca1ae-7e5f-5e18-90c3-de30835ecf8e | textbox | DATE:
7d6f9d55-54aa-41df-ab81-8e50f7ed1104 | checkpoint | 1.4 Excavation Permit
614f6477-f9a1-50ae-94bf-dcf4c1fcd892 | note | FREQUENCY: Each lot
c733ff39-40e5-5c32-af3e-193f948caa35 | note | – – – – – – – – –
1e55ad22-25a8-58ac-9ea2-bac3b28ac750 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
a18d7566-104f-596e-a763-86351a858728 | note | • Plant and equipment shall be appropriate for the task.
37ff24fe-2fc5-57da-a82c-efcbf16e7535 | note | • Excavation operations shall not disturb areas outside the limit of excavation
212930eb-98cc-5375-876f-1ff34022bbd3 | note | – – – – – – – – –
055539fc-00a8-5057-b645-6bb1386ef3e5 | note | REFERENCE DOCUMENTS: Excavation permit
b2ad11c3-a5df-5887-8195-c34a6d37fcee | note | – – – – – – – – –
713b5414-2df3-51a1-95ca-969189e35352 | note | INSPECTION/TEST METHOD: Verify
4bbddbd7-4096-5568-885e-a3b0a629d57a | note | – – – – – – – – –
8dd61349-6590-5f3d-9cf9-b6b9b87ca711 | note | RECORD OF CONFORMITY: This ITP Signed Off
eb587d5a-bfc1-5869-ac42-2d15ee619e0b | note | – – – – – – – – –
93221072-ba88-58e7-a3f9-150578074dd1 | note | HP*
8002a95d-5066-528e-8704-df6c24747c68 | note | – – – – – – – – –
f56bcdcb-bf72-572e-bed0-a2125de4efd0 | note | RESPONSIBILITY: Site Engineer
d5d0061d-ff0e-57e9-a733-3d265bd5f7cf | note | – – – – – – – – –
d5cdb1e5-9ea4-5af8-b06c-7d357c2f09d0 | textbox | DATE:
10cd3227-a617-4650-a29a-7b0d5fa30643 | section | 2 - Construction Works
41d1e6bc-22c0-4979-8c72-805befa790df | checkpoint | 2.1 Survey set-out
b7af4866-42f6-505d-ad7e-0c687f4db62f | note | FREQUENCY: Prior to commencing excavation
27768216-3b15-5bf8-8e61-be9ecaa5a6a5 | note | – – – – – – – – –
8e4a4afb-9698-5d34-8c87-2ffaa0feb6d2 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
12fb2f0d-d408-5a31-8552-78d17e618046 | note | – – – – – – – – –
a506b1ff-6529-5656-975e-bc2d41bb3cfe | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
daf12bbc-542b-58a2-932a-0ff83d987f65 | note | – – – – – – – – –
bdc34b1d-9cca-5565-8478-52fac96f5913 | note | INSPECTION/TEST METHOD: Site Inspection
7613d519-6142-5950-9249-decc00445cb4 | note | – – – – – – – – –
4ee5ef25-7dda-599c-9c64-717c249adf5e | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
660893a2-5952-547b-af6a-d35f3ecc5887 | note | – – – – – – – – –
7ee6df6e-92af-5601-829c-15c1b7f3bc33 | note | SCP
19798072-ef6e-5d9f-b052-8408c9f1a63a | note | – – – – – – – – –
03cd7097-31f6-56c2-99bb-bc23ed3774d6 | note | RESPONSIBILITY: Site Engineer/ Surveyor
1b92ab79-ee3b-5da2-9aeb-5f8267f2fa35 | note | – – – – – – – – –
7a78cf84-4e85-54ef-b156-eaa841ff487a | textbox | DATE:
5b5bbdc4-f1c0-4ab5-afae-5126574d8a1a | checkpoint | 2.2 In situ Material
64dee417-824c-5fae-8018-a8e465bf0519 | note | FREQUENCY: Initial
a5072124-704c-541a-b762-adb0696af1dd | note | – – – – – – – – –
9f481bc2-a2a3-506f-8af2-38192fdef9b9 | note | ACCEPTANCE CRITERIA: In situ material ripped and re-compacted to provide a smooth, stable working surface. Material to be free of debris, roots, sticks and sharp rocks/ boulders larger than 50mm
b66b9bcb-434e-55c2-b8cb-e5f5fa8751df | note | – – – – – – – – –
f0f46bfa-8ea5-51af-85a6-bbc9f0a9b06a | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
415ac554-c1d5-50cc-b711-a5cc9eb9c30d | note | – – – – – – – – –
ac977f05-ef14-52e7-a334-a920f2816f50 | note | INSPECTION/TEST METHOD: Visual Inspection
c74ecc97-ef11-59f6-9c58-fea9e88b00bf | note | – – – – – – – – –
595e4c77-67d9-5c36-9614-6fdec1e8c50d | note | RECORD OF CONFORMITY: This ITP Signed Off
4aa1d9f6-8e5c-58fd-a59e-1e2f26a07648 | note | – – – – – – – – –
100f276f-99b5-5b78-acb5-9ad1ad690c25 | note | IP
95fd97c7-c1d1-53d6-b2ed-a854e3c5cc58 | note | – – – – – – – – –
f743703e-8aa8-5f02-9f5d-9469a50e25bb | note | RESPONSIBILITY: Site Engineer
957d5e8f-1ffb-5fa4-8c38-c529a10c2a30 | note | – – – – – – – – –
3dcf013a-cca4-5af8-b7e5-3fb4e9e3d564 | textbox | DATE:
481349ce-c310-4bbb-9ed2-88d2efd9eeb6 | checkpoint | 2.3 Bentofix GCL Installation
3f39ec1f-6b36-50d8-b15e-1697599897bc | note | FREQUENCY: Prior to placement of Type A
cbc492ba-a7ce-5b2e-b27b-bda90698c91d | note | – – – – – – – – –
7bc95fc8-e705-5d2e-b9dc-aa26834be74d | note | ACCEPTANCE CRITERIA: Geotextile clay liner (GCL) shall be installed in accordance with the manufacturer's requirements
16770232-2d32-5ac3-befe-d1c7ced72fea | note | – – – – – – – – –
d587c446-5c27-57f4-8e34-1f332e57cec6 | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
99d31a02-9f4e-5e7e-96d5-f88cbbb0e8e7 | note | – – – – – – – – –
b7497e95-52cc-5e2d-8acc-f8d02e4e0480 | note | INSPECTION/TEST METHOD: Visual Inspection
0bc4e8c7-606f-53e7-820f-f0426a51d705 | note | – – – – – – – – –
cf3276c8-4401-511a-aabd-1d32fa185fc4 | note | RECORD OF CONFORMITY: This ITP Signed Off
a9aba8b4-6356-5771-8002-91a21ee900b8 | note | – – – – – – – – –
0b1c14c2-8a4d-598e-b549-afc4e3345a6a | note | IP
31d17b9c-d043-5253-8465-082822f281b5 | note | – – – – – – – – –
11d4ae4f-5508-5f63-be01-c2a0e03a17b1 | note | RESPONSIBILITY: Site Engineer
e71d89dd-7ba4-5035-adfa-2208984ce814 | note | – – – – – – – – –
fb9af42c-9fb2-5ba1-97ae-f564eca0b6db | textbox | DATE:
137f5d5a-8539-4648-b8df-9bc07720ec54 | checkpoint | 2.4 Type A Placement
036ef700-6aef-5f48-8cb3-4183efd166fc | note | FREQUENCY: Once GCL has been installed
2d66ef8c-c9d3-5c28-ad6a-f6875879b0d8 | note | – – – – – – – – –
5dd5bbe9-2f2a-5516-8d0c-cf85fd0f8920 | note | ACCEPTANCE CRITERIA: A minimum 300mm thick Type A fill layer shall be placed over the Bentofix GCL that has been installed
0c56b55a-0cb7-58f1-9f6d-173e746da0b1 | note | – – – – – – – – –
693ebc4c-0578-5799-b724-7b3976bcc90f | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
8c7dedcc-3928-534c-967a-a7a1eba387da | note | – – – – – – – – –
6fce0be3-3ae9-5339-87b5-eb5fc4ec6c7b | note | INSPECTION/TEST METHOD: Visual Inspection
7ff91649-7073-5dad-b740-219f2e088726 | note | – – – – – – – – –
857ee335-0eb3-59a4-bd3d-a1e877762e50 | note | RECORD OF CONFORMITY: This ITP Signed Off
e0e5c9b1-bf1b-53b2-954d-6ec2be0da39a | note | – – – – – – – – –
f3a8fa2e-7d4b-5d30-9e21-8a6cbb79804f | note | IP
6e435e29-0735-59b2-be1e-126514bd094a | note | – – – – – – – – –
49025779-aa40-5bd9-bc1b-2b187f2c9df4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ed5e3aaa-4caf-5800-94bb-22a3a733a52d | note | – – – – – – – – –
1204adaa-93e7-53cf-8c8c-1c3bf608994f | textbox | DATE:
b70ab601-ab89-4258-bbba-cd99b450ec5d | checkpoint | 2.5 Base Construction
cdbb20aa-2af0-50f9-92d7-7516639bf3bb | note | FREQUENCY: Once Type A fill layer has been installed
73aa4b14-3342-535e-bf7d-35a497146968 | note | – – – – – – – – –
54d69626-629d-5753-aa1f-d1320df3a9a2 | note | ACCEPTANCE CRITERIA: Provide a compacted 400mm thick hard base. Approximately 50% 300mm size. The remaining 50% made up of 0-100mm graded rock, premixed with 300 dia rocks and spread and tracked so as to form a compated base.
64c9b6a2-b03c-589b-a134-e623154e8be7 | note | – – – – – – – – –
017c794d-b008-50f0-8241-e56678f60faa | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
e10f1119-be10-5bee-a536-c13d7f5306cd | note | – – – – – – – – –
d5e9cb52-6c89-5469-87f1-24cfd453494c | note | INSPECTION/TEST METHOD: Visual Inspection
a3d773ba-cf2e-53a2-9fa8-7b94f8fda1d2 | note | – – – – – – – – –
12726355-806e-5b4a-85f8-67e36ccae6fa | note | RECORD OF CONFORMITY: This ITP Signed Off
66208f47-54c5-5036-b54f-1f17294ad38a | note | – – – – – – – – –
b9b46f88-6add-5264-8685-c74f2c840b36 | note | IP
d1476232-e1c8-5e83-b505-d517aa22bdb3 | note | – – – – – – – – –
87f419a3-30ba-58bb-807e-47558001972a | note | RESPONSIBILITY: Site Engineer / Site Foreman
e92bdadf-a872-5b98-a44d-3b147ac300a0 | note | – – – – – – – – –
3c394602-ac78-55db-97e5-f8a8397a6040 | textbox | DATE:
2dc5e54c-da18-4a29-b235-0df8f6d2e2b3 | checkpoint | Final Inspection
335720e1-91f5-5160-88cf-56a2d6e455df | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d4a79539-738b-50e3-92e3-8e72be1e5893 | textbox | Print Name:
392b584a-d875-58b2-8b2d-557e646c99e2 | textbox | Position:
a16d1ae5-4fb3-56e6-af82-665a203a0353 | textbox | Date:
019acf38-2d7a-4a6b-9dbf-839f81c0a8fd | checklist | ITP-01-001 - Clearing & Grubbing |  | ITP-01-001 - Clearing & Grubbing
f5e007e8-4ebb-441e-ac73-0944c817cebc | section | Preliminary Works
0b262d57-7ec1-4a18-9b00-cd258aa1d4f8 | checkpoint | 1.1 - Check for correct documentation
bd89e348-7884-56e7-bd40-2412ec6576ba | note | Frequency - Prior to commencing any activity
564ec8d6-58bf-509e-94e8-8ba54260af1f | note | Acceptance Criteria - Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
78be1907-74be-55f1-b851-d7ec80276f5f | note | Reference Documents - Drawings and drawing registers
2ddc205a-89cc-5d3e-b8d6-5281f495da82 | note | Inspection / Test Method - Visual inspection
d5411886-e720-5e08-866e-6ac65623c790 | note | Record of conformity - This ITP signed
1300e11f-9d06-570d-b5aa-b68edb0a6021 | note | HP*
7b2b02b9-7d91-57d9-b86a-dbb55f9af942 | note | Responsibility - Site Engineer / Site Foreman
2f1753f8-f71a-51b5-ab40-420e90def3f6 | textbox | Date Completed:
c7c54a36-0a8a-401a-9267-a6e6fdb5fefe | checkpoint | 1.2 - Implementation of all measures and controls
0a305825-b5f1-5231-9898-e6da808e75ea | note | Frequency - Prior to commencing any activity
480912d7-ede8-5920-b002-65087d61ea68 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
f3b8c7fb-aca7-54a2-849e-a6fd38e84735 | note | Reference Documents - OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
c89ebc9e-5ca4-5e90-a571-dcb0dba234f8 | note | Inspection / Test Method - Visual Inspection
9575c750-e34c-542d-be99-565addc9876a | note | Record of conformity - This ITP signed
3efc19c2-3323-5585-8ff8-339846d2eab3 | note | HP*
53889b77-8187-5882-8ff1-1500a81986de | note | Responsibility - Site Engineer / Site Foreman
71bcb6ba-644d-5784-9566-3a986c342582 | textbox | Date Completed:
d2557aa9-7c00-4a54-8ed9-eb27040edb3b | checkpoint | 1.3 - Flora & Fauna
905252fe-ab21-5ffc-98e6-37dd5605e05f | note | Frequency - Prior to commencing clearing
136bd5f4-bc9d-5edb-881c-997a961d7c12 | note | Acceptance Criteria - A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal;
c8e837e7-b3c7-572e-8d69-9e36af41df4c | note | has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
d120a853-0e44-5ee5-b188-f5efe864f83c | note | Reference Documents - EMP, ECP
0d85d696-cd38-531e-9ec7-7028e566bac6 | note | Inspection / Test Method - Visual Inspection
41623edf-df6b-560f-becf-18c9911f4b75 | note | Record of conformity - This ITP Signed off
acac03d8-0834-5f96-b753-99eea65bf671 | note | IP
c025985d-3507-5052-a8c5-3c613bc2d5be | note | Responsibility - Site Engineer / Site Foreman
91b94f9a-4af5-585f-bd49-d2531b5f6c2b | textbox | Date Completed:
fd20315b-8ba4-4122-b60c-4594587355ed | checkpoint | 1.4 - Permit to disturb flora & fauna
cac845a2-61c3-544d-b1a7-9f4af6e948e3 | note | Frequency - Prior to commencing clearing
34731c96-a45a-5e0e-a26a-ded6b31952f6 | note | Acceptance Criteria - MRPA has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
2b115397-efdd-5332-9374-5ffc79b7f2bb | note | Reference Documents - EMP, ECP
96d44a0a-7476-5512-b9c2-3f513df0387e | note | Inspection / Test Method - Visual Inspection
f2cd59c9-e8de-5b91-90c5-f05b7c6b8ed0 | note | Record of conformity - This ITP Signed off
7281fecd-f887-5fd2-9ca0-d1528e4423ca | note | IP
54c57205-c4c3-5ff3-ac46-8b048fc3014b | note | Responsibility - Project Engineer
90b5ab6f-5c50-5b12-83d1-bbc0faa6a849 | textbox | Date Completed:
a30e279f-f8e1-49e3-95ca-4f0b6a3786ad | section | Clear & Grub
6e87e5ad-8e1a-477e-b946-3134f4af43cd | checkpoint | 2.1 - Define work area
0a19cb29-3ddb-5251-9e34-150d8bffcaea | note | Frequency - Prior to commencing clearing
f6708062-e40e-5d19-b13e-1df53641f0f7 | note | Acceptance Criteria - The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
1fe41dc7-aecb-56fc-b169-e23b2b0b798a | note | Reference Documents - 201.03
ead00a30-e126-5779-b41b-92750776690a | note | Inspection / Test Method - Inspect
6e274979-15b4-5dab-82ff-ec36bdb8a407 | note | Record of conformity - This ITP Signed off
f9ab29fe-70d1-5fdb-afc9-04d8805ef48b | note | WP
69d320fc-aac2-538c-a76d-ca2fdd9688a6 | note | Responsibility - Project Engineer/ Superintendent
5e7c026c-9fa2-51a6-b93d-cc61689e7e67 | textbox | Date Completed:
5557cd23-4482-4302-bb51-b020d69210c5 | checkpoint | 2.2 - Joint Inspection to Mark vegetation or habitat to be removed
5f84f435-1baa-5048-87b3-e95d260d0b85 | note | Frequency - Prior to commencing clearing
c3b49538-77bd-54ed-beb2-83df54b60435 | note | Acceptance Criteria - Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent to confirm and clearly identify and mark trees to be removed, consistent with Appendix O Tree Assessment Report.
eb059527-5f20-569f-af48-d083624948f6 | note | Reference Documents - Drawings 201.10
5b422c18-9fbb-5761-aaa9-c3900f40eec2 | note | Inspection / Test Method - Visual Inspection
392f60db-e39f-5ae6-ba20-924fe0532431 | note | Record of conformity - This ITP Signed off
d3bb02de-fa70-5199-b8c7-08c42d8ac2a2 | note | HP
dedfcf7f-9479-575b-91cf-7fccd7abb61e | note | Responsibility - Project Engineer/ Superintendent
54d3da75-e001-554c-b720-6ebc3565e5c9 | textbox | Date Completed:
c94d8370-a5bd-4e48-8c26-60a70d1e2323 | signoff | AUTHORITY HOLDPOINT
5a3fb293-c16c-4e27-b3ca-8183c066b69d | checkpoint | 2.3 - Identify No-go Zones
f7a2d91e-7308-5601-93a6-f3fa600f8848 | note | Frequency - Prior to commencing clearing
048ca453-e0fd-5222-92c6-19909b030b5a | note | Acceptance Criteria - Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing.
096b7d06-5f2e-5f1b-835a-1b7cec6986e6 | note | Signage shall be erected outside the limit of the of the vegetation or the habitat site, at intervals no less than 20 metres apart or as per the SSEMP
c49e0250-f85c-5b19-86c8-4232db0276c6 | note | Prior to any work on site the contractor shall fence and sign all no go zone sites as per the EMP. Any works required inside TPZ shall be completed under the supervision of an Arborist
0cff771b-e000-5ede-a36e-0ca815fc9734 | note | Reference Documents - Drawings 201.10
cea9aed9-b528-5800-8e39-07fad0b49ce9 | note | Inspection / Test Method - Visual Inspection
bd724d34-b0e0-51a2-a590-be266bbb122a | note | Record of conformity - This ITP Signed off
b9f6372a-62b2-5ba1-9635-8db8517484ac | note | HP
1fb607a5-dc2a-575c-b29d-a1923b09ca89 | note | Responsibility - Project Engineer/ Superintendent
0f7d7b97-486a-5581-ac39-0a472269267f | textbox | Date Completed:
8449998c-e185-4354-a1de-3e41d0b3d1e5 | signoff | AUTHORITY HOLDPOINT
e66b8b00-ac4a-4941-9e12-5f737e4cda56 | checkpoint | 2.4 - Clear felling distances of trees are adequate.
55d3d8b0-4037-58fa-b19d-edb9fe17e058 | note | Frequency - Prior to commencing clearing
410f2be2-ea95-58c1-9a43-b78c763fd39b | note | Acceptance Criteria - Ensure the clear distances are adequate and signage is in place as planned.
5a2a9f1a-0377-557e-a0cb-16ea2426b3da | note | rees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
8cf364d8-542b-5579-b21e-56293691922a | note | Reference Documents - 201.04
50b24ec8-33cc-56ff-9b14-b7e3776f8767 | note | Inspection / Test Method - Visual Inspection
83d1cdd0-0d5d-5c3b-9636-49ad8b83badc | note | Record of conformity - This ITP Signed off
5cd01f32-9246-575b-a729-00d944882f65 | note | IP
fae539c1-bd10-5ad3-9754-0fb76d90de58 | note | Responsibility - Site Engineer / Site Foreman
f56fa78b-53c0-5d4c-9af4-73c7426210e4 | textbox | Date Completed:
bbaa191b-741f-4045-9c14-831f60f98ed4 | checkpoint | 2.5 - Clear and grub trees and vegetation
25864608-a9af-5ad9-a527-43f69006eee6 | note | Frequency - After clearing
ad9d50f0-9fc5-5375-8556-c235f01650fe | note | Acceptance Criteria - Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level.
cebc03f2-6238-585a-b901-a86fa4e6b308 | note | Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
9c796b09-a94e-5157-88c1-d486e6fd4edc | note | Reference Documents - 201.04 201.05 201.06
3cd1b3bf-e624-55f2-bf44-45602d573565 | note | Inspection / Test Method - Visual Inspection
abeb004f-9486-58ad-9ac8-fbf7962c25d6 | note | Record of conformity - This ITP Signed off
3464cf50-fb0c-5af9-80b2-2c2bd367325e | note | IP
f80ed28c-df23-55d4-bf74-2872f0111dfb | note | Responsibility - Site Engineer / Site Foreman
9b612f3a-7f71-5680-a0cf-6b1ad4e71ac6 | textbox | Date Completed:
1075fe8a-3f32-46be-963c-8359c74bd505 | checkpoint | 2.6 - Backfill holes
5f26f0fb-69e3-5a27-b49b-ec8f6f53daf7 | note | Frequency - After clearing
42570ca0-22f9-51cb-be92-763682dc8fc3 | note | Acceptance Criteria - Any holes produced from grubbing operations have been backfilled with similar material to the surrounding material and compacted to the same degree to the surrounding material.
2f91914d-c28f-5dd9-bfb4-b8028dfaa20c | note | Reference Documents - 201.05
aa930178-a6e5-5aec-af0a-3540f74a9fd8 | note | Inspection / Test Method - Visual Inspection
23e03883-c9d6-58d4-a55a-26a7d3b55a8e | note | Record of conformity - This ITP Signed off
1e9af68a-de5c-5769-ab63-9ad29b619fec | note | IP
dd49aac0-88dd-5bdf-ad64-055cbad4100f | note | Responsibility - Site Engineer / Site Foreman
c04d004d-fa08-58e9-9b8d-8f640af95a05 | textbox | Date Completed:
a84c0eef-75d4-40ac-8102-c1404caefb24 | checkpoint | 2.7 - Dispose of Trees and vegetation
faa904d2-6196-50c6-9443-3a11ca79ec19 | note | Frequency - After clearing
60e071bd-6a06-5813-9ad3-4152701519b7 | note | Acceptance Criteria - Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works. Noxious weeds shall not be mulched.
2f560c1e-2e3c-5c7d-8155-59fd9cda655c | note | Reference Documents - 201.07
8ff01d63-6c68-593d-a938-0221869ec28b | note | Inspection / Test Method - Visual Inspection
5c60b02e-3f5d-5291-b1f2-906bbf119e4b | note | Record of conformity - This ITP Signed off
67f2d782-09fe-5143-9ad8-5097c3ba463c | note | IP
c75b432a-3b35-538a-ab79-f17c17ade51c | note | Responsibility - Site Engineer / Site Foreman
4816208c-501e-5a8f-bfbf-a34c1420512f | textbox | Date Completed:
49bf6dde-6595-4c41-b524-78af4c83249f | checkpoint | 2.8 - Dispose of concrete, bituminous and other recyclable materials.
5967492b-75ec-51f9-90be-bcd870745bfe | note | Frequency - After clearing
6493c29d-d821-55f3-af31-1298c2cd3e8e | note | Acceptance Criteria - Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
8c70ed30-49b8-5c5f-a443-3bb3f4685487 | note | Reference Documents - 201.07
addf4b6b-447f-52ce-99a1-e2c5397f9888 | note | Inspection / Test Method - Visual Inspection
7285da64-a25e-51d3-aa31-f0f3378f5713 | note | Record of conformity - This ITP Signed off
b55572ac-b65d-5fe6-9ed5-5fe3e7016bb0 | note | IP
43b295ce-248a-5de3-af12-0dbdd5981289 | note | Responsibility - Site Engineer / Site Foreman
5b8f575f-b0b1-55f5-a7dc-6d8286bcade7 | textbox | Date Completed:
33786ec1-9252-4f83-ae8a-e824b4571869 | checkpoint | Final Inspection
b56c91c8-2347-5f07-aa18-5dd6eb55e617 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
0ac8fe03-0910-589e-adb2-6efdc2c116e5 | textbox | Print Name:
73667a27-48d5-5ad7-8d3b-03496a3f324a | textbox | Position:
225733e7-efe7-58b9-aa39-979bb370058f | textbox | Date:
46c50302-4461-4f30-a38c-5c5aa6731697 | checklist | ITP-01-002 - Stripping Topsoil & Topsoil Replacement |  | ITP-01-002 - Stripping Topsoil & Topsoil Replacement
89ff3f4f-d9b7-4c26-8fc0-a907a1677540 | section | Preliminary Works
b5d6277c-529a-46f2-9e2e-fb0f661ef4f7 | checkpoint | 1.1 - Check for correct documentation
d236f0fe-7f9b-50e3-ba70-bf4f90f301c9 | note | Frequency - Prior to commencing any activity
64bba1b2-e3b9-5bef-8857-45a38772dc73 | note | Acceptance Criteria - Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
263951d0-3880-5418-b097-275ffbd2b172 | note | Reference Documents - Drawings and drawing registers
18164fc9-f88f-52e8-ab33-9519e32d91ae | note | Inspection / Test Method - Visual inspection
a7087735-e698-5aa1-a30d-8e3279cafffd | note | Record of conformity - ITP Signed
e741ad62-2b60-5414-8cce-e1e07ff1c36b | note | HP*
bf633ebd-b25d-50bd-81c4-bfa0e2a0d35a | note | Responsibility - Site Engineer / Site Foreman
5c39b3e2-d67e-5dba-8f83-3da151f84ab9 | textbox | Date Completed:
d6f1f22f-1c2d-41af-accc-b3ec5997ac95 | checkpoint | 1.2 - Implementation of all measures and controls
931d6511-059b-5cb8-99df-368ccaa1b52b | note | Frequency - Prior to commencing any activity
e880cc3d-2550-5670-bfdf-c8a011d691c7 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
a24d895a-3e98-5ca3-b72a-effc5ef04e98 | note | Reference Documents - OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
8a2215af-93a9-5cab-8e48-ea4b215d2575 | note | Inspection / Test Method - Visual Inspection
07ce2aab-2022-536c-8b4a-c7d52aebc19f | note | Record of conformity - ITP Signed
fbe1407a-5dbd-5d43-aab9-bfcb9ec32462 | note | HP*
51b5160a-aae6-54a9-a980-dca714921c8c | note | Responsibility - Site Engineer / Site Foreman
68535341-73e1-5295-b703-1823b14bb6e1 | textbox | Date Completed:
ef010c08-3512-40ca-8699-177a5c7128b6 | checkpoint | 1.3 - Ensure correct materials are being used
f7e2daa3-4912-585f-add0-045c4ada6eb5 | note | Frequency - Prior to commencing any activity
fbaded1b-aa35-50af-ba84-c4092c48ac05 | note | Acceptance Criteria -Topsoil placed on formations and disturbed areas shall be capable of supporting healthy, full cover of grass growth, and contain organic material
b1ad368c-e118-57f5-8082-e8d2c58f8204 | note | -Topsoil material shall be free from subsoil, tree roots, clay balls, stones, rocks, rubbish, contaminants, weeds, pathogens and toxic levels of any element with a pH in the range of 5 to 8.
ee7d9c7c-71f5-57cc-aa19-d1ca0baceebc | note | -Imported topsoil shall conform to the material properties outlined in Table 720.042
d7900410-17a6-5b56-91c9-b045cebc72e0 | note | Reference Documents - 204.04a
614390c9-8552-5ba7-90e3-ae60641e27af | note | Inspection / Test Method - Verify
21146a98-4c72-5bc4-bd00-d390d5cb22cb | note | Record of conformity - ITP Signed Material Test Report (Import Only)
0281a840-4e27-52de-ac01-11896bf74805 | note | TP
38061e8d-3fe8-5a19-9f6a-46c541ac7786 | note | Responsibility - Site Engineer
533e8d8a-dee5-5489-a2f2-8c840409994c | textbox | Date Completed:
3e5014d7-5619-4987-bc59-d17f5a5c3723 | section | Stripping Topsoil
65038df4-fdde-4b6d-8d93-3d02416ea5de | checkpoint | 2.1 - Survey Set Out
e0f5c70d-30b2-5b2a-ad9d-4b38927f78a6 | note | Frequency - Prior to commencing stripping
17ce9205-74c8-560f-b72b-6949bd488142 | note | Acceptance Criteria - Area has been pegged out in accordance with the drawings
7f60742a-caca-5216-8274-01dcf812c67e | note | Reference Documents - Work Procedure
ea5933cf-27d5-5fa4-961f-b11ed55dfeb5 | note | Inspection / Test Method - Verify
eea17332-91b6-59a1-bac2-eaec1f149607 | note | Record of conformity - ITP Signed
a91fb59d-fc5e-5ad1-bd30-697c9b26477f | note | IP
b34d8820-103b-5363-9d71-788f735c64d5 | note | Responsibility - Site Engineer / Surveyor
e999f49c-d445-5f53-b460-eeee4e210123 | textbox | Date Completed:
8809c611-cad6-4cc0-8b12-2037feab5bba | checkpoint | 2.2 - Archaeological monitoring
064a7fb1-618c-5b15-b38f-388d453b9a64 | note | Frequency - Prior to commencing stripping
db0749d4-e2f8-5ecb-b1b1-c252b6f6e9c1 | note | Acceptance Criteria - The Contractor shall immediately notify the Superintendent if an archaeological site is encountered, or if any suspected artefacts are found.
93edcd44-2f5e-5d03-a7f4-d6a4c375abef | note | A ‘No-Go Zone’ shall be established for identified Cultural Heritage sites that are to be protected during the work under the Contract and in accordance with the CHMP
ad643a2c-40f9-5956-89ee-fc97e878f955 | note | Reference Documents - CHMP
060af56e-d52c-5bea-be6f-e84f95a8072d | note | Inspection / Test Method - Visual inspection
483b05b5-6c93-5e99-a984-0c079ceb7f3e | note | Record of conformity - ITP Signed
9364493d-2506-5250-9adf-0e8f1d80e886 | note | IP
87d7cfe9-9be9-555c-ab38-db5d691dcd39 | note | Responsibility - Site Engineer / Site Foreman
a42caf5b-39dc-55b1-a055-30cce2a5f293 | textbox | Date Completed:
926a250d-8aba-4b05-9121-5e07548afb80 | checkpoint | 2.3 - Excavation Permit
b24e15d0-4d85-501d-9652-106d430a5e3c | note | Frequency - Each lot
3f0505a6-0c6b-53c7-bb83-8ea4bbce4aae | note | Acceptance Criteria - An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
f4857fa6-f0b5-5001-a748-529cf71b8976 | note | Reference Documents - Excavation permit
48de7633-e6dd-5af2-87e7-cdad962a1706 | note | Inspection / Test Method - Verify
26b978c2-ff23-5ff1-ba5a-fc0e3ef26fec | note | Record of conformity - ITP Signed
464d6848-7a93-523d-bb83-020453ac438d | note | HP*
67e7d863-cb7b-5ca8-aaf3-00dea7f9965f | note | Responsibility - Site Engineer
7bfed9e1-927a-5482-93fd-984ebf2de69a | textbox | Date Completed:
c56e9ae2-f621-4894-b895-6a2c4438624b | checkpoint | 2.4 - Batter Lines
be94daa2-2278-5193-b1bb-0d973c476384 | note | Frequency - Each lot
4fbf5800-76aa-526d-9f76-a0607cb3a694 | note | Acceptance Criteria - Cut/Fill batters shall be constructed so that the batter point is not more than 10% of the batter height outside the calculated batter line.
803552b2-9d23-5a01-b0f0-661827df3ed1 | note | The dimensions of batter rounding shall be within 10% of the dimensions shown on the drawings.
d6f7753d-ac6e-5a63-9a1a-afdc6168fa4f | note | Reference Documents - 204.03j
e95de4a6-832b-5cdd-a9ca-e3dc8e5d5f57 | note | Inspection / Test Method - Verify
e2e2114b-2d61-59f4-8089-6722fb5ca8e6 | note | Record of conformity - ITP Signed
0f2fd6c9-d34f-559f-8dee-f92917275e85 | note | IP
007f8c0c-993c-5684-9c59-44826c25f328 | note | Responsibility - Site Engineer / Site Foreman
8feed011-5c08-5141-a67b-ab25268fe1cb | textbox | Date Completed:
8dc0fc35-c312-4675-94a8-4ac1d7a10f6c | checkpoint | 2.5 - Designation of stock pile area or disposal site
7c7781e4-51ed-530c-b380-61c9378c0b5b | note | Frequency - Prior to commencing stripping
3cf66cc4-baa0-5edd-9248-f607116df974 | note | Acceptance Criteria - An area for stockpiling has been designated or a disposal site identified
0b6bb715-4b8c-5b13-9b24-fa99a08dd7a1 | note | Reference Documents - 204.05c
62c97228-d1de-580f-b405-f6b058444209 | note | Inspection / Test Method - Visual Inspection
29cd3daf-d5a7-5d48-93f2-015f739b255e | note | Record of conformity - ITP Signed
9b0fc3f6-52c0-5a60-aa36-c10b4073aea6 | note | IP
fec0156a-4c54-553a-a0d0-eb0f56162321 | note | Responsibility - Site Engineer / Site Foreman
1f8a8e88-3ae0-5b64-993a-f356d4c97c4b | textbox | Date Completed:
b2dbd728-064e-4cbf-964e-ff99f83904ef | checkpoint | 2.6 - Weed treatment
d1bb05ca-2577-5d7b-8f0d-2ddf19114727 | note | Frequency - Prior to commencing stripping
9f8490d6-f731-5f2e-84d0-e5ee2293d75f | note | Acceptance Criteria - Site has been inspected for noxious weeds and weed treated if present
b1c20a91-b76f-5777-a91a-2f96eea2c2bc | note | Reference Documents - 204.05c
a9c6949a-3bdc-5b1e-b56a-43f31e856a37 | note | Inspection / Test Method - Visual Inspection
fa9b804e-b5f7-52c0-ae6b-b975b59c087b | note | Record of conformity - ITP Signed
87657163-a950-50ff-b1de-2bf6a74c3e45 | note | IP
a33c971f-56e9-5c52-9b47-2cce32709c19 | note | Responsibility - Site Engineer / Site Foreman
d24d6576-33cf-5872-b809-5dad7a7c110c | textbox | Date Completed:
2db32620-251b-4219-ae50-68655a02ea65 | checkpoint | 2.7 - Maintenance of stockpiles
8185ae25-4779-5fe8-b95c-21e4d24761e0 | note | Frequency - Each lot
821fe037-3903-5420-a50f-10c95e090990 | note | Acceptance Criteria - -Stockpiles maintained neatly and away from stormwater drains
7a355155-eabf-563e-8d43-5481887361f9 | note | -erosion controls in place
9e6c285b-a195-5553-8cd1-da3913862b60 | note | -stockpile treated to minimise spread of weeds and pathogens
70bfb1f5-6e8f-5635-a5f8-fc2d8b20e0ec | note | Reference Documents - 204.05c
59ba0f17-e8aa-507d-bf68-4bc9c38a1077 | note | Inspection / Test Method - Visual Inspection
8448922f-5cc5-5f5d-9645-2a923d682fb8 | note | Record of conformity - ITP Signed
cdc17b0f-725d-54da-aca8-8d934d29b481 | note | IP
1f31e8ac-75ed-585a-b79a-f500c25a78d1 | note | Responsibility - Site Engineer / Site Foreman
488ff022-7010-56a0-9ca3-35f85f1d1321 | textbox | Date Completed:
bac44aac-9222-4069-83f0-7c44b329e895 | section | Placing Topsoil
827ff3aa-ca1f-43bd-bacf-a248a3a315f3 | checkpoint | 3.1 - Surface finish of cut and fill batters
aa4c28cf-b1fd-5166-90fc-d7505e8ab086 | note | Frequency - Each lot
88b312d2-091f-53db-a015-3223e5b44caa | note | Acceptance Criteria - The surface of cut and fill batters to be topsoiled shall be textured by scarifying or horizontal grooving
f2bf55ce-d3d9-5bca-bac5-c871d90f689d | note | Reference Documents - Cl 204.06 (i)
3cbbc64f-a31c-5fb3-9e1d-db8470fb5b1d | note | Inspection / Test Method - Verify
1ab8366d-1c67-56cc-950b-2e5659feaf72 | note | Record of conformity - ITP Signed
b5d735aa-654e-561a-94ee-8adcb72f91fd | note | IP
1ead77b1-d444-5498-a58e-f9d47d58081f | note | Responsibility - Site Engineer / Site Foreman
1003da98-1f66-5a48-944f-695ea4d8f7d6 | textbox | Date Completed:
3a94eaf2-cb65-441c-a59d-6689574d9f98 | checkpoint | 3.2 - Topsoil Placement
de531f44-e8c2-593b-bdd2-36698ac74c54 | note | Frequency - Each lot
b88545c5-8e6b-500e-bdbc-b72883128a43 | note | Acceptance Criteria - Confirm underlying cut/fill areas comply with Cl204.03 before placing topsoil. All disturbed areas not paved or landscaped topsoiled to the following depths:
49b97b61-5aa2-5733-9db3-17f6334fd668 | note | • batter slopes > 2:1 = 50mm min
85329bda-f83f-5d82-b6c9-7bc8f285553d | note | • planting beds = 100mm min
c5c9e7e5-6cf4-52cb-8701-4ea746527b92 | note | • verge - 50mm outer edge to 20mm within 100mm of seal
dc1b9f47-5837-5767-a9b8-b674bc548ecb | note | • all other areas – 75mm min
d0cf1fa0-1f37-5d9b-acbd-d5369203a3cb | note | Reference Documents - Cl 204.17
e48d4e8c-7b11-53c5-ba6a-38cf38e98b96 | note | Inspection / Test Method - Visual Inspection
dcd7170d-4a48-59f1-a4f8-7a3989e62254 | note | Record of conformity - ITP Signed
3bc731cc-633b-51dc-a70a-88d68d3b8a9e | note | IP
d047f871-c9ca-5647-88af-7847ecfd32cd | note | Responsibility - Site Engineer / Site Foreman
c48c3fb7-9ba3-563d-be1e-0506b53046b6 | textbox | Date Completed:
612a793a-080d-4d4b-afc1-0836fb4fb4d9 | checkpoint | 3.3 - Surface level
056a4bf9-9c72-53d2-9732-e5a6f5bf1634 | note | Frequency - Each lot
276bf4bb-c23d-59a4-b1d4-d1721aef55cb | note | Acceptance Criteria - Area topsoiled spread, levelled, but not compacted (except verge area).
f4aa572b-0265-59ec-a753-e64cb50cd77e | note | Reference Documents - Cl 204.17
c67585f6-4315-532d-b67b-0bdc7dadf480 | note | Inspection / Test Method - Visual Inspection
33a503c4-0a8c-51ff-b6b3-faed7ba0e09c | note | Record of conformity - ITP Signed
0a656816-314b-56fd-8126-2ddc76b199f5 | note | IP
017b0390-3bff-5fcc-b713-0fb3b198b75d | note | Responsibility - Site Engineer / Site Foreman
427f8212-5a57-5baa-bf78-fb705adbf4a0 | textbox | Date Completed:
c53c11ca-28ab-467a-8afa-bec22023ed7d | checkpoint | Final Inspection
429846bf-6624-5216-8d5d-2244b51c9921 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
0379f4b6-6ef7-5c55-9186-b5aa4f081acc | textbox | Print Name:
62c52ad7-f6c6-569c-a5ae-cbf2d27e6dd9 | textbox | Position:
264171a2-cb34-5aec-a0c2-0c19ff34caa9 | textbox | Date:
9a4d7fcd-1aaf-40b1-983d-bbaa21f5d25b | checklist | ITP-01-003 - Subgrade Preparation |  | ITP-01-003 - Subgrade Preparation
404c5b32-9eb6-428d-b184-675f50cb08c7 | section | Preliminary Works
780a9212-a0e7-4d8d-9992-24dee347189c | checkpoint | 1.1 - Check for correct documentation
bef621a8-3594-5226-a996-b790440335d2 | note | Frequency - Prior to commencing any activity
add4db2e-a5ef-5979-8817-fdcb9366ac26 | note | Acceptance Criteria - Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
b056200c-a1bc-5bcd-8d37-b5bd55cb0907 | note | Reference Documents - Drawings and drawing registers
e13d4534-f17e-5ab1-acf8-9abd5b4dd2b1 | note | Inspection / Test Method - Visual inspection
78b77119-9794-5e93-abf8-f5896aa4e6f0 | note | Record of conformity - This ITP signed off
9928e177-307d-5d4f-8fff-5763d332b0d0 | note | HP*
0ffbe87a-9a3d-504e-bbec-2ae9596c79b7 | note | Responsibility - Site Engineer / Site Foreman
4fd4d60d-3ff1-528c-b97b-2934acbfea3c | textbox | Date Completed:
b3420fc8-e833-4ea8-b9ba-71a9b9668ebc | checkpoint | 1.2 - Implementation of all measures and controls
8985349b-3fc0-543f-b4e7-8d65b62de2c9 | note | Frequency - Prior to commencing any activity
8fcdecee-b51b-50cd-a146-590ab47bd7c7 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
da1d443e-6dd9-5639-8195-5dd85a865f31 | note | Reference Documents - OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
fdc15649-5949-5bb1-acf7-0a7fd5fde9d0 | note | Inspection / Test Method - Visual Inspection
59cc9259-2e65-5237-9070-82b33d9e4900 | note | Record of conformity - This ITP signed off
9d35677c-c12f-57e4-bd84-0447812154d7 | note | HP*
8d895e01-475f-5b84-8c8e-5406ac4248a4 | note | Responsibility - Site Engineer / Site Foreman
68cf4624-ae2e-5278-967f-7718e0897afe | textbox | Date Completed:
867d8ebe-bc08-4413-b94d-88f2af068646 | section | Construction Works
fc47885b-ead6-4f54-8dbb-b3d6ee843297 | checkpoint | 2.1 - Survey Set-Out
bc29a3a0-d29b-5171-a079-4cc24ef2ad73 | note | Frequency - Prior to commencement of excavation
83224eb5-7296-5053-9dc6-43c6d6d09cc2 | note | Acceptance Criteria - Area has been set out in accordance with the drawings
8bfd2227-d61f-51e2-8341-45001c29dc87 | note | Reference Documents - Drawings, Work Procedure
956910cb-b36d-5b28-a18d-48838dce78be | note | Inspection / Test Method - Verify
7232debf-d679-532f-87d1-f7e1a891d2b3 | note | Record of conformity - This ITP signed
ca2beb4a-2fdf-50df-95e2-27d37eeb80ed | note | IP
625976df-a940-5abd-9018-352f32275393 | note | Responsibility - Site Engineer/ Surveyor
2823ddb0-d408-5393-b225-573aa8807817 | textbox | Date Completed:
a9f29837-fafc-464a-9ac4-b0daaf10cf12 | checkpoint | 2.2 - Excavation Permit
5b39b057-c488-538c-9f85-5bd8298205c1 | note | Frequency - Each lot
d4b55de5-84d4-563f-939c-53a42a0f88d0 | note | Acceptance Criteria - An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
5945f7dd-5ce6-5cfe-9957-8a48a92b41a8 | note | Reference Documents - Excavation permit
7e3a00db-7e0e-5f82-8221-262f4d5327b0 | note | Inspection / Test Method - Verify
c5d339c6-aa7b-5b3b-a7d5-f74b432dd962 | note | Record of conformity - This ITP Signed Off
1b505f13-be16-54dc-8bbf-8b5f8c370d85 | note | HP*
08fe9ca2-b11c-59d4-b445-9aa39d44784e | note | Responsibility - Site Engineer
a5f3208b-01eb-5314-8dd0-3c672b9811ae | textbox | Date Completed:
5fe64964-972c-4e1a-9810-96dd1ef7dc3a | checkpoint | 2.3 - Subgrade Material Properties
9a5d49ce-e65d-5939-86f5-3e4b22b9d777 | note | Frequency - Each Lot
d2687624-42eb-55ec-bbc9-f01cad3959d4 | note | Acceptance Criteria - In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
5a95c0a3-89c1-5279-9ce6-a7aad9ba58ce | note | If parameter met rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
2c2dcc40-e37a-58fb-857f-b6dcdcbefeab | note | Reference Documents - 204.06 (e)
2dc6f849-175a-5e8f-a701-4dcdcb3b9c4e | note | Inspection / Test Method - Test Point
9c45d7c2-489b-5ca0-a0ae-095d0417600f | note | Record of conformity - Test Reports
3fd7b0f0-a2ce-5c8c-8db4-cb4b29f7700b | note | TP
0808374b-dc55-5344-8e66-537a4bb150fc | note | Responsibility - Site Engineer
267d631c-03b2-5bf5-9dec-dfd5ecaf31aa | textbox | Date Completed:
1709d785-d8a8-48c3-bfcc-53931ed7f537 | checkpoint | 2.4 - Inspection of Subgrade Material
a207ef0b-4fe6-5324-ac40-44bcb802582d | note | Frequency - Each lot
c05e08e3-7ef5-5081-9f08-3bedbcefcabf | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work.
bf34d270-ba9b-5823-a43f-d1217f11916f | note | The Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
ff9fc554-85b9-59a5-9de2-b07e3e566f6d | note | Reference Documents - 204.06 (c)
33c2cc9e-c261-5cc7-8731-b87e68014f23 | note | Inspection / Test Method - Verify
5080ad71-6861-5411-bfe8-f6fb183f5214 | note | Record of conformity - This ITP Signed Off
ed699b35-0143-5f40-8369-0d4a714867f6 | note | HP
0436fc93-e2ad-57d9-86a8-848f830b10c8 | note | Responsibility - Site Engineer/ Superintendent
ace74373-c60a-5bf8-9b3c-4d5106e4d65e | textbox | Date Completed:
13ac1b50-2b06-44a7-8d0d-7ab6817d1168 | signoff | AUTHORITY HOLDPOINT
1233c971-784d-4147-9e6a-8c7c8dcc2d84 | checkpoint | 2.5 - Material classified as silt
f1a47b9f-fd56-568c-ad92-9aeee0864d2b | note | Frequency - Prior to Commencing
bc976c93-1109-5dd1-90c6-bc15c58f6db9 | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilization to the satisfaction of the Superintendent
af0117f1-58a8-5552-bd64-77ccb6f4fee8 | note | Reference Documents - 204.04 (b)
c48c23b5-34bd-5d02-b6a6-834460f12dc1 | note | Inspection / Test Method - Document Review
2173c5b2-c8b5-59a1-a799-ff6db398a875 | note | Record of conformity - Superintendent satisfied with Stabilisation Signed ITP/ records
ca778f8e-ea0f-5f70-b7ad-f37c21cb1403 | note | HP
747164e0-7288-5ae4-81de-0eb711f248a0 | note | Responsibility - Site Engineer/ Superintendent
7e0bb1ae-5452-5544-8ca3-ffe231309208 | textbox | Date Completed:
f464873c-ec85-47ef-8af7-d94fbbbaee70 | signoff | AUTHORITY HOLDPOINT
3fdf2435-5933-4d22-9f1d-3e1acbb0e350 | checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
cf8b1cdf-2cff-5f71-bd88-3b341d2231cb | note | Frequency - Prior construction of the regulating layer
4a3f8212-73f4-588f-9c9d-cb53da215f37 | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
0d6aa1ad-53e4-59c2-97c2-ce996fa37a5f | note | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
c454eced-84d6-5071-abe9-789d44ba8add | note | Reference Documents - VicRoads Spec. Cl. 204.06(f)
d13700a4-cbca-5b07-ac2e-1596346b9519 | note | Inspection / Test Method - Site Inspection/ Document Review
d38dc5c1-8a96-52b4-b6b6-54fd6ef7e6a0 | note | Record of conformity - Superintendent acceptance Signed ITP
cd079605-7342-518c-9f4f-19fa6296aa1e | note | HP
6001e49b-5c88-57e9-9228-72718005f870 | note | Responsibility - Site Engineer/ Superintendent
febf964b-d15f-5399-bfe5-85ba5b86cfc1 | textbox | Date Completed:
13dc1825-b748-4b56-9952-9b34ce098158 | signoff | AUTHORITY HOLDPOINT
c4d999be-b45a-4ba7-9c84-c8f959978fd8 | checkpoint | 2.7 - Unsuitable Material
63d1edc4-4d21-5c94-bb93-d3f685b3d429 | note | Frequency - Each Lot
2f8e1fff-d3b0-5324-b1d8-4d1f5e80653e | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
3e73ed0a-96d0-5d66-b2fd-c0a12b86cd35 | note | Reference Documents - 204.07 (d)
e3cb068f-6843-5d7f-b514-23c091791b51 | note | Inspection / Test Method - Visual Inspection
fc1c4037-b4c7-5786-b38b-8a01785d93f0 | note | Record of conformity - This ITP Signed Off
b4bbb6fb-bec5-5ca4-b042-fd35c8a7c491 | note | HP
49f1a9c4-c12f-59d1-86ba-dab9eebb00d4 | note | Responsibility - Site Engineer/ Superintendent
ba2b6dcb-e1e2-554d-af0f-c9bc57d97a06 | textbox | Date Completed:
7030875e-a315-4fc9-9181-8cb209125d12 | signoff | AUTHORITY HOLDPOINT
8f839dfe-c679-41f4-b166-c411b35631b3 | checkpoint | 2.8 - Groundwater
775bfc8e-95bb-5633-887a-33ca2b22dbde | note | Frequency - Each Lot
bac5a63f-ce80-5050-8611-ff340190b12e | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review
2852f837-3e6e-56b5-96d3-fe03bce51943 | note | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
d2c43536-fb69-5a48-95cb-8a0594e9830a | note | Reference Documents - 204.06 (h)
008d4601-85bb-5929-a076-653670076b9a | note | Inspection / Test Method - Visual inspection
71647a81-aef1-5dda-95bc-bbb2a9c9d788 | note | Record of conformity - This ITP signed off
3ce9dbdf-12f3-5b1c-8d99-cd9ceabda65a | note | HP
8761873c-5d90-5133-9c60-3cc5c1c8213c | note | Responsibility - Site Engineer/ Superintendent
ad9102a4-9865-5f07-bce2-b2653d087543 | textbox | Date Completed:
aac64c98-a3f7-4b31-896d-c68000800edb | signoff | AUTHORITY HOLDPOINT
dcf06a27-d038-47e6-bc07-02243d645ce5 | checkpoint | 2.9 - Trimming and Level conformity
0997f206-87a2-5cb4-9e5d-a307d9a884aa | note | Frequency - Each Lot
c4498f0d-2701-587c-9c4b-79119ca13826 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
20462b6b-0e79-5103-bfe8-bab75b9cc24a | note | Level tolerances:
7d01a407-2ba4-5d0f-a285-73a531cf2df7 | note | Range x = +5, -15mm
e23cd2d7-fc4e-520f-81df-37f77e66f1d7 | note | Max S = 12 mm
b79f8f81-7660-58bd-9c42-04c1a344d812 | note | 80 measurements per lot (Scale A)
0c7e4243-3a1c-5b40-b923-4ac078312386 | note | Reference Documents - 204.03(f)(g)(h)
3cee8a0e-260a-560d-aa04-1c36ebb45fa9 | note | Inspection / Test Method - Survey Report
cab9ff73-dca8-58c1-8a2b-b2a74388a025 | note | Record of conformity - Survey Record
6d34a443-22b9-5ad2-86e1-c376cf1a437e | note | SCP
883acb9b-2743-5887-8255-a39538bcdc49 | note | Responsibility - Site Engineer/ Surveyor
60e75683-9bd4-5940-a22f-a7cbd733403f | textbox | Date Completed:
84d72b41-5fa5-4ce1-ac07-740445bdb271 | section | Testing
80de2d01-17bb-4c25-85be-8578599f3840 | checkpoint | 3.1 - Proof Rolling
15df99b6-471d-52ba-9e7a-203cc0e89ddc | note | Frequency - Each Lot
b305cc60-5441-579d-aeea-25a638ac1607 | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
fb949e9f-fc7b-5ee0-8ce0-99deaed71467 | note | Reference Documents - Section 173
15543cee-77bf-53b9-bc20-0b9fcd3a1686 | note | Inspection / Test Method - Visual Inspection
d7b7d2e4-f83a-5ff1-8b0c-42d66c7ba6ae | note | Record of conformity - This ITP signed off
26c94929-aea7-5712-a1a4-5f7c571e748f | note | HP* WP
fba3487d-c211-5f80-880d-27de5059bed4 | note | Responsibility - Site Engineer/ Superintendent
7376dcdf-e59e-5a7f-aa2b-0dfff8ed106f | textbox | Date Completed:
1be2e678-5b66-4a36-bf10-a7746ffc2697 | checkpoint | 3.2 - Compaction Testing
64e23468-cc68-57a3-a2b4-9e1da7d500f9 | note | Frequency - Each Lot
4bc67ed4-4dac-53ce-b11f-f8133bb1dc2b | note | Acceptance Criteria - Ripped and re-compacted material below Cut Floor Level = minimum compaction 99% MDD.
e8624f24-6d31-5b16-a9ed-298ec2574b76 | note | Type B Material placed within 400 mm of top of Type B Material = minimum compaction 99% MDD.
b489351a-753a-55ce-84b5-37407d16b05a | note | Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 97% MDD.
c8b20578-d18e-5e42-8328-c9f9e27407d3 | note | Reference Documents - Table 204.131
92411080-ac3a-5749-9cb1-bc14de7858a9 | note | Inspection / Test Method - Test Point
c84e76b1-3b64-5016-afc5-3636ac7c8a1a | note | Record of conformity - Test Records Lot Register
fe4c8efc-a1b3-5fbe-9e42-a74651dc2373 | note | TP
e881e866-8284-5ee0-9db3-76b044109459 | note | Responsibility - Site Engineer
31ad03b1-7bb3-544b-a62e-49cb47aa59e4 | textbox | Date Completed:
9f7021c4-ad74-47b1-9c6b-ca01f4855932 | checkpoint | Final Inspection
0174862a-1270-5923-aaa9-21a9d5401e43 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
eaa0c316-7b3d-54d7-b4f8-07d65e58fdb4 | textbox | Print Name:
39c3a4a6-1e20-5d1c-a081-f5f8b28da8cb | textbox | Position:
1c46fdae-f2e4-5b24-8e35-90fb16b8fa0e | textbox | Date:
6e9a27e6-d5a4-42f8-ae58-4883e08cd1aa | checklist | ITP-01-004 - Type A Fill Placement |  | ITP-01-004 - Type A Fill Placement
4fe80521-e3d3-49a0-9c96-efefba832d77 | section | 1 Preliminary Works
0a1320ac-a0c0-45b7-8585-087c6d032e8a | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
1d80702b-c627-52c9-9e6b-c40de1d817ba | note | FREQUENCY: Prior to commencing
9596493a-63b0-57a7-b3fc-7fa59d81e40d | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
79f03fa4-4e7e-5020-bac7-7142035acc1c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
3f30f679-38ed-5561-9006-47913e73819f | note | INSPECTION/TEST METHOD: Visual Inspection
5c45025c-8b95-5378-b361-ac8598423d72 | note | RECORD OF CONFORMITY: This ITP Signed Off
2ca6d13b-92ba-5b55-8222-da8a1e444f35 | note | HP*
06c6c4ff-d4c2-52ca-be3e-76f192734ce7 | note | RESPONSIBILITY: Site Engineer/Site Foreman
f46cde67-2f9c-5f03-8b04-eec8d14a3275 | textbox | DATE:
43bdd89d-a315-4c91-ae25-0493675dc677 | checkpoint | 1.2 Implementation of all measures and controls
389cd59a-d019-5859-92df-75960fb54bce | note | FREQUENCY: Prior to Placement/Each Lot
4480ddad-6d5f-5db2-9d85-e87795a6ec8d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
7089b5ad-43b4-5aba-b15c-a2506bc89e33 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
e09b9474-1a38-5806-9ffd-57e5635a1aa6 | note | INSPECTION/TEST METHOD: Visual Inspection
650ffaa9-0650-5667-9ae5-c61ed9e6d048 | note | RECORD OF CONFORMITY: This ITP Signed Off
60ec5b30-357f-539e-95f5-12f17f2d7e8e | note | HP*
97025764-2aac-52a0-ae9b-9f7defc803e3 | note | RESPONSIBILITY: Site Engineer/Site Foreman
04d65021-e6e5-513c-8028-c28a17f68596 | textbox | DATE:
a2b36ce1-f6d9-4e30-93b6-b0026a34170e | checkpoint | 1.3 Verify Material
78619239-b43c-517f-96c7-b32aa909d5d8 | note | FREQUENCY: Prior to Placement/Each Lot
8cc1729a-fb2b-5fe8-8915-44554904a46f | note | ACCEPTANCE CRITERIA: Obtain Material compliance data as per table 3020.052 from the supplier and submit to VRs for approvalIf material type is observed to be silt, approval from Superintendent is required to continue. Assigned CBR to be greater than 6% (<10%), swell is to be less than 1.5%, unless approved as expansive. Soil is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075. PI between 6 and 25. Permeability of less than 5X10^-9 for capping and verge material
b91ebdfe-1a64-53e4-a540-9486f7685d49 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(b) Cl. 204.06(c) Table 204.041 Table 3020.052
abc88adb-157f-5d4c-b646-945da82c827a | note | INSPECTION/TEST METHOD: Site Inspection
62d8b06e-cfe5-5b0c-a06f-cef9c9f8c026 | note | RECORD OF CONFORMITY: Test Record (If silt is observed)
a6e7f5d7-c3e4-55f1-bcc4-b42a9a887808 | note | HP
80bd4814-b9a1-5eb1-b57b-91a26cad8bba | note | RESPONSIBILITY: Site Engineer & Superintendent
ff5c89d0-2928-5c53-b20a-8f9a04be2198 | textbox | DATE:
7a3e587d-7f44-4541-a31a-76528e72b834 | signoff | HOLD POINT AUTHORITY
ac5283d3-2ac8-4703-8e46-56f2dfe12acd | checkpoint | 1.4 Excavation Permit
e87d10d5-9a25-53a6-9fec-08aac6756a02 | note | FREQUENCY: Each lot
9ac7d686-08e7-541d-8522-636524e8b374 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
66613cf5-b47f-5e64-82c6-82d35dc0f348 | note | REFERENCE DOCUMENTS: Excavation permit
3f632de2-ef14-50c2-ba56-fb63a8f689ff | note | INSPECTION/TEST METHOD: Verify
7a7fc93a-9602-5c28-a9e7-daefc6aab3ab | note | RECORD OF CONFORMITY: This ITP Signed Off
26ab5859-0987-5a25-b5e1-3734536a6332 | note | HP*
66f343a6-bd20-572a-9908-edfef171a6de | note | RESPONSIBILITY: Site Engineer
94040fe8-e05f-5b49-b2ce-f061b0030ca6 | textbox | DATE:
7e981381-a551-473a-be10-db275ea7a96a | section | 2 Construction Works
267ab9c5-4c3b-45dc-9366-5cac456e715b | checkpoint | 2.1 - Survey set-out
281709cd-dac1-5acb-981f-70bbf735be48 | note | FREQUENCY: Prior to Commencing Excavation
98fd4c65-9f22-52d1-b363-302e32c82b8c | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
02a0d5c5-772e-55fb-828a-0370c3f4dcbf | note | REFERENCE DOCUMENTS: Latest IFC Drawings
20be0a61-6eb0-57bb-bf01-35ca8c3cad20 | note | INSPECTION/TEST METHOD: Site Inspection
6b4a50fc-bb9d-55bb-9135-4b448d22392d | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
9357e2a7-8c15-5675-a8ac-40921ee80dc9 | note | SCP
74f2b85b-f2fc-5fcc-a7c9-1b6b21fb280e | note | RESPONSIBILITY: Site Engineer/Surveyor
13eccc7c-c8dc-5682-b98b-2ac735421884 | textbox | DATE:
2633d348-7158-4dcc-ae53-d8b02fbf5378 | checkpoint | 2.2 - Inspection of fill area
612c80cd-7412-5325-825b-81e041ffc584 | note | FREQUENCY: Each lot
9cd65d91-485e-547b-98e6-0675068a69b6 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
ed9698d1-a1e8-5332-9661-4c7ebf0b2635 | note | REFERENCE DOCUMENTS: 204.10 (b)
1770ecb0-58a4-5e9b-a7d7-e1dd332f3b40 | note | INSPECTION/TEST METHOD: Visual Inspection
3a201577-2940-56d9-9b1e-9c50c99dca1a | note | RECORD OF CONFORMITY: This ITP Signed Off
8bd55dc0-ea78-592c-a8bd-3c9bf28c6dbe | note | HP
6881f9f8-dccf-5734-96a5-eb2ad771269a | note | RESPONSIBILITY: Site Engineer/Superintendent
02536899-fdb0-5c50-839b-576306056ba7 | textbox | DATE:
43abd85f-c670-4600-a7f1-07f468cfe9e6 | signoff | HOLD POINT AUTHORITY
a9e1a3c2-89a3-4972-a703-9672c19f0c90 | checkpoint | 2.3 - Keyed fill layer
70bb5b70-91c9-5357-8065-e2f04f614336 | note | FREQUENCY: During Excavation
742e07f3-d25f-5886-872a-e390b49749e1 | note | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
cb78023e-7d5f-5513-ad6f-5622630612ff | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
3e64b401-2d40-5d5c-badc-2ec1226aa5ff | note | INSPECTION/TEST METHOD: Visual Inspection
2ca09dec-5de1-5dec-bb36-36be1f9a8963 | note | RECORD OF CONFORMITY: This ITP Signed Off
ed176737-5596-572c-92ae-4dcec3667198 | note | IP
a99f808e-f95b-583e-a559-415acc725161 | note | RESPONSIBILITY: Site Engineer
c1d9234d-7d42-5e19-8ac9-67507ab6f832 | textbox | DATE:
772dbbd1-46dd-45ba-b7dd-09b3143f5ef1 | checkpoint | 2.4 - Layer Thickness
20cd1f9b-16fa-5ab5-ba4f-ae4d2605fd38 | note | FREQUENCY: During Excavation
4960406f-c0a1-5c48-90fe-731ea5de8f5a | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
79c00b53-eb9a-5281-b41d-308e95d67e8f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
5f143a46-e5c9-5a01-9e70-62491f3a4be7 | note | INSPECTION/TEST METHOD: Visual Inspection
9bfc6fb8-28c8-50b9-9ea9-93ad9112ee0f | note | RECORD OF CONFORMITY: This ITP Signed Off
62ec1574-1918-5e48-911e-63ff2d1b5073 | note | IP
5a9d4c90-ad36-58a9-a12a-d475cd4a5d4c | note | RESPONSIBILITY: Site Engineer
ce4ea3b0-443b-5b76-a175-a283b1bfa5be | textbox | DATE:
d2557539-d1b3-4d8f-8968-7ce14b4d368f | checkpoint | 2.5 - Maximum Lot Size
fb40034d-7dd7-5436-8f58-579c61e51c33 | note | FREQUENCY: During Excavation
5f999427-e09b-5804-a59e-81021cb6855d | note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 5,000m2, whichever is lesser.
ed64c5f5-9076-5fe3-9ce6-5cc3b5141da7 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
eb5fb2b2-dc39-5598-a16a-a9ecd8fd852d | note | INSPECTION/TEST METHOD: Visual Inspection
2d280811-f2cd-5bd7-92c8-4004b50a6b3b | note | RECORD OF CONFORMITY: This ITP Signed Off
e66c334b-dc7e-5eba-8607-15d3694c04c6 | note | IP
8d5effbe-30d7-55f2-bae4-36872455c625 | note | RESPONSIBILITY: Site Engineer
4f9a4aa5-0b85-594b-909a-a983cd745ad8 | textbox | DATE:
d3dfd610-ef2c-4970-b3c9-3e738868a3ec | checkpoint | 2.6 - Type A Placement
20e3042e-e76c-5d51-a84a-f12ac3ae6c58 | note | FREQUENCY: Prior to Placement/Each Lot
7bf74b41-9eeb-543c-bbba-8546d4982333 | note | ACCEPTANCE CRITERIA: • Top of fill must be shaped and compacted to minimise damage due to wet weather note 12 on Pavement Details 009-0001 "Capping Material can be substituted for (3%) Cement treated Stab Sand in confined areas • Any rocky material present must be uniform throughout the layer • Each layer shall be kept generally parallel to the surface of subgrade
ee68a0a0-590f-552f-a7fb-43ec201a6ff2 | note | REFERENCE DOCUMENTS: 204.10 (d) (i). 204.10 (d) (ii). Table 3020.052
a20a1971-e442-5b2e-aeea-7952ebccaf03 | note | INSPECTION/TEST METHOD: Visual Inspection
5d6354c7-ce10-5da4-b4da-ee80b3692e65 | note | RECORD OF CONFORMITY: This ITP Signed Off
2963a6cc-f843-5863-8a71-fce8a4a414dd | note | IP
a69928ff-b866-5c87-becf-2c1f8a825e26 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f721d879-b535-57aa-baf9-4b545f7c9bfe | textbox | DATE:
38e257d5-b4ba-44ad-8681-8819fe0a84aa | checkpoint | 2.7 - Proof Roll
d1fecd8c-68ed-5b63-97ae-e18c4e20fb24 | note | FREQUENCY: Each lot
83827f27-c30f-51d6-b6b1-7b462e9f0dd2 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
2ae51dd2-0cce-5427-963c-9851820082b9 | note | REFERENCE DOCUMENTS: 173.03 204.12) 204.10 (b)
44ce20d6-b68c-5421-ba2e-e3fa1beb5fa2 | note | INSPECTION/TEST METHOD: Visual Inspection
bdaa2f9b-be2c-5483-8bb4-935278371b19 | note | RECORD OF CONFORMITY: This ITP Signed Off
d9258522-37c8-564f-9f53-c319eb5323de | note | WP
7b02fa91-808e-593b-a8c6-7c87725005ef | note | RESPONSIBILITY: Site Foreman/ Superintendent
3854c698-1402-5774-bbb2-06981c6c642f | textbox | DATE:
fff17039-0203-4dd8-8b86-34b278b15a3b | section | 3 Testing
b3722648-3ab5-4113-8430-750eee1926dc | checkpoint | 3.1 - Reduced Test Frequency
9572ce51-6249-5933-aee6-80a62159c190 | note | FREQUENCY: Each lot
b7a59077-28b2-5661-8b4f-55163e4bae74 | note | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
7fc81bab-ba6d-5ab9-8b05-81e7d0033833 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
15f57c8e-4ba5-542b-a076-c8f63db8ffb5 | note | INSPECTION/TEST METHOD: Test Record
a305fa77-79f7-5d0f-bcef-77bd4b722f95 | note | RECORD OF CONFORMITY: Test Records
f68ef692-347e-57c4-9dca-fa5fba85f202 | note | AP
6af59488-0494-5706-bbde-66627907eb30 | note | RESPONSIBILITY: Project Engineer
abdfdbb2-051b-586e-9415-c241c21e620a | textbox | DATE:
568fc12d-871f-49bf-9d70-27bffb091d84 | checkpoint | 3.2 - Compaction Testing
f92ce90b-0399-5c50-aedf-c3bc715cd36c | note | FREQUENCY: Each Lot
9c0322d7-12f2-59fb-aa2f-778096956d29 | note | ACCEPTANCE CRITERIA: Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B).
243119a1-fd85-5d49-9afb-b3c3c98abbfb | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
e15473dc-b585-56ea-b903-26d4d5f24eba | note | INSPECTION/TEST METHOD: Verify
e3a0bf57-3fcb-53e7-8977-011584534c9d | note | RECORD OF CONFORMITY: Compaction Test Records
a775d007-12fb-554d-985a-8688a8fe4e2e | note | TP
053209d2-64fb-5fb2-b490-9219a4cd09be | note | RESPONSIBILITY: Site Engineer
5fc01729-be38-5958-a6f5-fb7e9f93ea24 | textbox | DATE:
0061f83e-1903-4ac7-a1fe-280d7f67fb74 | checkpoint | 3.3 - Maximum Particle Size
12f20f81-50c5-56a5-91e8-8848ce7615fb | note | FREQUENCY: Each lot, unless reduced frequency has been approved
3025e7d1-559c-5575-a71d-2cb7ba56eabd | note | ACCEPTANCE CRITERIA: Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075
2739db4a-006d-5afd-96ea-5c60a53606b1 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141 Table 204.041
8973e705-0c2f-5a28-9481-5790c6c9f6dc | note | INSPECTION/TEST METHOD: Verify
83462207-ad52-50e9-ab9f-f64bcdb4e5c4 | note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
7cd1670e-d8ee-5703-a922-6c32e5f8ec04 | note | TP
db184e7b-1237-5433-8c11-990491a1e0cd | note | RESPONSIBILITY: Site Engineer
8b83fcca-fc9c-5724-899d-4f37eb79ac7e | textbox | DATE:
053b999e-f90b-474e-a074-bce28d4f3a6c | checkpoint | 3.4 - CBR/Swell
d8c235c2-00d2-5828-80bf-e719fcf551d9 | note | FREQUENCY: First lot then every Second thereafter
877d8772-a8d9-5c53-b7c7-1e523d2423e7 | note | ACCEPTANCE CRITERIA: CBR: ? 6%, Swell: ? 1.5% (Verge material less than 1.0%).
86cdb85f-86b5-5d95-a7bb-8d7d0239847b | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(i) Table 204.141 Table 204.041
ad4ff87b-eb80-5c63-a653-81b91679e583 | note | INSPECTION/TEST METHOD: Verify
b7f380d6-3fa2-5e14-b2b4-b59e941bdf43 | note | RECORD OF CONFORMITY: CBR/Swell Test Records
f78f9ab7-19ee-5330-9f7c-bae1d653bfa4 | note | TP
d77e5e2d-6ffa-5d2b-950f-366d1135fe2f | note | RESPONSIBILITY: Site Engineer
e8c0ec68-21cf-55e7-bf8f-e45c8feba752 | textbox | DATE:
4fbf0223-2ebd-4093-9006-425f8080de47 | checkpoint | 3.5 - Atterberg Limit Tests
04c912d0-7c60-5cd4-94c9-83d08b1651cb | note | FREQUENCY: Each lot, unless reduced frequency has been approved
bf62b5dc-46f5-5f85-aaee-73cad4a1e770 | note | ACCEPTANCE CRITERIA: PI between 6 and 25, PI x % passing through 0.425 to be less than 1000
31bb156d-4f5d-5b97-8a57-0a9beed6292c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141 Table 204.041
0220f754-3d86-5504-8b86-39f787428b0a | note | INSPECTION/TEST METHOD: Verify
c4dd6dd8-8405-5e97-9e6f-ee63216d6b8e | note | RECORD OF CONFORMITY: PI Test Records
4c822c55-c307-5d51-8531-fe9e3c4e2ace | note | TP
801e65ff-10bf-5cb1-83a1-d827dcc264fd | note | RESPONSIBILITY: Site Engineer
4d3c6dd1-1a17-5c20-8510-e111c2d4cd11 | textbox | DATE:
a01fb56d-d3d2-477e-b405-fb188421c9f1 | checkpoint | 3.6 - Permeability
e32c4fb4-469e-58f7-a3e1-b15e26b203bc | note | FREQUENCY: Each lot, unless reduced frequency has been approved
223f9a58-0893-5fa7-a746-563d0c8560dd | note | ACCEPTANCE CRITERIA: Permeability of less than 5X10^-9 for capping and verge material
d0dd47ba-82c5-5b24-aede-53b07ad9aacc | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141 Table 204.041
722e3c39-9450-54a9-9990-17dd6f535856 | note | INSPECTION/TEST METHOD: Verify
b40239fd-0434-5b53-a793-d6a831561129 | note | RECORD OF CONFORMITY: Permeability Test Records
758f7061-e36c-57e1-9703-c60f2cad2591 | note | TP
482e7a43-5717-5769-98b1-2c682066ce88 | note | RESPONSIBILITY: Site Engineer
074586f3-265b-522d-975f-9d7e6be4330b | textbox | DATE:
f7afee36-4893-4b7f-81bf-d5cc463e7940 | checkpoint | 3.7 - Material Property Testing (Scale B)
4368dc4c-a174-5e41-bd76-55e4fff76254 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
eb4e68cf-7934-5a8e-b88c-18f77ff9e29c | note | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
d79d1afa-52fb-5031-b4f3-99fd263759cf | note | REFERENCE DOCUMENTS: Cl 204.04 Cl204.14
41333fb4-cade-508d-9b18-09c7931d172e | note | INSPECTION/TEST METHOD: Verify
592ed8c0-b8e2-55e1-91cf-c15c4504b3b9 | note | RECORD OF CONFORMITY: NATA test report
7f58edd8-d6ca-574d-95b5-f09941c9c3ba | note | TP
f695020e-8e4e-5b53-a973-7c61da451cfe | note | RESPONSIBILITY: Site Engineer
1ddac59c-79a7-5c40-a87d-2b3676f938eb | textbox | DATE:
d6a30c2c-afe4-4a41-a994-53df6752f6da | checkpoint | 3.8 - Survey Conformance
3c6aff2d-794b-5aa7-93d0-145258fb6dce | note | FREQUENCY: Each lot
be632b6c-cfe8-5867-92d3-e1a6ff15789f | note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031 Scale B: Range x = +5,-25 Max S = 12mm 40 measurements per lot
9327e86c-59f3-589b-b184-e44978053e8c | note | REFERENCE DOCUMENTS: 204.03
720284d4-1692-5b80-9af7-fa49dd787dfa | note | INSPECTION/TEST METHOD: Survey conformance point
8552765b-18ef-5576-bef4-e07e1d4fcc30 | note | RECORD OF CONFORMITY: Survey report Lot Register
ab55face-74e8-5ce4-9cec-d4b65b069f94 | note | WP SCP
27b02448-aa73-5104-8ac2-c7d79d77d37e | note | RESPONSIBILITY: Site Engineer & Surveyor
d04e5afc-9713-5fdc-9802-a726d802c5b6 | textbox | DATE:
1811f7fa-7927-4d51-83ce-ed5aca5214e6 | checkpoint | Final Inspection
52ca83df-9578-5c1b-99ca-0ecc8b312d43 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
91494ac2-1926-57e6-864e-b824f107f39e | textbox | Print Name:
ef4d474e-19ef-5fe3-b46a-eb964379869c | textbox | Position:
19b784cd-fdb8-5034-9be2-3a76dee25617 | textbox | Date:
94926ae6-0d3b-4aca-9edc-bcd9d409f98f | checklist | ITP-01-005 - Class 2 Crushed Rock REV2 |  | ITP-01-005 - Class 2 Crushed Rock REV2
a21c740d-b529-4e69-a733-c2aba7c05e81 | section | 1 Preliminary Works
bc1704d2-7871-4003-8235-0f8d603f81fb | checkpoint | 1.1 Check for correct documentation
05f8c4c0-a099-5dbb-9bda-a5ab1efa3679 | note | FREQUENCY: Prior to commencing any activity
e9922ba3-e4c4-5e45-9811-587b98db4b15 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - Using the correct and complete set of drawings - All drawings are the latest revision
ef7de01b-6f7d-5ea6-ba13-b815d32418a9 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
b595df54-1e75-582d-b8a4-040b39d3bb04 | note | INSPECTION/TEST METHOD: Visual inspection
07f9a97b-5a75-5156-9cb5-587145820757 | note | RECORD OF CONFORMITY: This ITP signed
bd62549e-f2d7-50fe-9c1e-bb154f15035e | note | HP*
1fa855ed-3428-5aef-a7e2-bbe46b5c44ac | note | RESPONSIBILITY: Site Engineer / Site Foreman
e5c9c8c5-70f9-5dc6-8fe5-18cd2bcd1ec5 | textbox | DATE:
029e1649-a422-44a2-b280-6cfa4c095af9 | checkpoint | 1.2 Material Mix Design
dac700ee-5b87-5676-a501-8c1fd7a2cd9f | note | FREQUENCY: Prior to commencing any activity
39bd10e2-792e-5c1d-9430-5925881cec97 | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
ca3984b8-5cfa-5670-9914-310518c8b133 | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
e83df698-f364-56b5-a54a-3539828bed9b | note | INSPECTION/TEST METHOD: Document Review
d312fc3e-ea1f-58bd-a988-4a5c980217d8 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
60ab4d54-3cd9-5c41-ab6e-400f9bb1eeaf | note | HP*
3f5677a1-7f6d-5dff-a47d-a4118e1c1bf4 | note | RESPONSIBILITY: Site Engineer
9e5af922-c368-5bcb-92bb-a739c4ce52b2 | textbox | DATE:
59264d5b-a0a3-4695-9710-657c0471eaf9 | checkpoint | 1.3 Implementation of all measures and controls
14e88fa9-eec1-5fdb-8c70-a170977bb43b | note | FREQUENCY: Prior to commencing any activity
ac247238-a955-5701-9661-0dd49498f454 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
e81d3a4a-1c0d-5903-be93-ab458596c91e | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
365643fa-e2f2-5090-bf6c-b9086adac0b3 | note | INSPECTION/TEST METHOD: Visual Inspection
e147dd9c-9de5-5666-bb53-e38af9c01df1 | note | RECORD OF CONFORMITY: This ITP signed
3cfe5865-4dd8-505d-a1e5-d1c851000ce9 | note | HP*
8acdaeb3-6f51-5aca-bc11-21ade3e496f1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c1c21284-734f-5016-ac1b-47007f4933b1 | textbox | DATE:
6123b52c-1525-4f56-bc25-6d9321445e7d | section | 2 Construction Works
51f81d47-8fc1-41f2-8c73-6a1f42e34bba | checkpoint | 2.1 Transverse Joints
19448ab3-7563-5a62-a212-f9a8f843b542 | note | FREQUENCY: Check prior to placing material
1be2d7db-49fe-5a7e-8c55-074a8196d98f | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
fbeb872d-4d17-5f27-9667-23bf3ce78221 | note | REFERENCE DOCUMENTS: Cl.304.07 (a) Cl.304.07 (c)
3bf7be5a-67d7-58ef-a39a-419dc23b16d1 | note | INSPECTION/TEST METHOD: Visual Inspection
f4dde7c2-9373-592a-a838-04146d92b7f7 | note | RECORD OF CONFORMITY: This ITP signed off
1f060102-aedf-5e85-b675-4da068f8a50b | note | IP
0b64c0bf-6df3-5960-b185-3af81f95b1a6 | note | RESPONSIBILITY: Site Engineer
60c2af16-7029-58a3-b1d0-d9f1dc1e4713 | textbox | DATE:
8f5ce632-ebfe-4903-8090-d014d582e996 | checkpoint | 2.2 Longitudinal Joints
fdf5eec2-871f-5360-9a70-fc7134c307ea | note | FREQUENCY: Check prior to placing material
748ada3f-cb5f-5bf9-afa3-0f812760a89d | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
6cf88042-078e-5c36-9ea5-cc0943ab4fdd | note | Cl.304.07 (a) Cl.304.07 (d) Cl.304.07 (e)
8cbb680b-74ca-51d5-82b2-ac1197d6ee20 | note | INSPECTION/TEST METHOD: Visual Inspection
406d03aa-47e8-56ed-b8da-00a1c3d233ac | note | RECORD OF CONFORMITY: This ITP signed off
3806edeb-db70-5659-b23d-e4ef66eef616 | note | IP
8e5504f4-9a55-597c-8ca2-b8cd6e7508b5 | note | RESPONSIBILITY: Site Engineer
d5493024-b65a-5bf7-b772-3f10aee3afb9 | textbox | DATE:
a20b523a-b674-4532-af15-cac3cb683a22 | checkpoint | 2.3 Lot Size
10d77b69-4c0a-5cec-9b04-f88ee210cc84 | note | FREQUENCY: Check prior to placing material
0d5ad8fb-6613-5cfd-9d68-0ebd9bab4e61 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
625e6991-fd04-5305-a80d-280794a95dbc | note | REFERENCE DOCUMENTS: . Cl.304.08 (b)(ii) Table 304.111
45d98615-6b80-5626-8092-be567b5b1392 | note | INSPECTION/TEST METHOD: Site Inspection
36558657-4c63-511b-bbd9-77355ce95ae9 | note | RECORD OF CONFORMITY: Signed ITP
afea2fd5-1ce3-50d5-87e6-d60215eb17cb | note | IP
fd36eede-920d-52d8-8788-bb9a459976bc | note | RESPONSIBILITY: Site Engineer
240b5ea0-dfc5-5e6f-a406-23d460d997c4 | textbox | DATE:
b6c6de9d-c2f4-47f6-b106-5e40999d4b93 | checkpoint | 2.4 Layer Thickness
28dea2f0-63db-5093-8c49-3519063ab458 | note | FREQUENCY: Each Lot
99f5fbe4-4b8c-5cb9-ba4e-f19489986844 | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
5a3adbe8-8b38-5052-9449-0e21bc2e9361 | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v) Cl 304.08(b)(vi)
baaaec15-6682-5965-8ff6-9769dd9b225d | note | INSPECTION/TEST METHOD: Site Inspection
2810f2b7-c954-56ac-bff2-177aeca8ba28 | note | RECORD OF CONFORMITY: Signed ITP
bec5c835-b6f9-572b-b017-c0d09ddc0cc4 | note | IP
16efc7e5-3f61-5f2e-bbf1-956b7ea087b2 | note | RESPONSIBILITY: Site Engineer
c66e4828-5a7b-507f-8f5d-380d94f68bd3 | textbox | DATE:
adc66aed-9656-4fbb-bcf5-9d87fefffdf8 | checkpoint | 2.5 Proof Rolling
71b8c79e-ae78-5b80-af2f-3cd5d9924b5b | note | FREQUENCY: Proof Roll each layer
df86923f-0c1b-5f0a-9e05-4b72d4254ac6 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
87a73696-de65-5d80-9616-f700402b70c8 | note | REFERENCE DOCUMENTS: 173.03
8e4e1f02-a02d-5853-855d-08ba287456fe | note | INSPECTION/TEST METHOD: Visual inspection
f51ef316-0027-51e4-ab51-63610a50d8c9 | note | RECORD OF CONFORMITY: This ITP signed off
21b904e8-75d5-5664-8cb3-00d39aa862f1 | note | HP/ WP
655a4678-246c-5b73-829d-00b6ea217fde | note | RESPONSIBILITY: Site Engineer & Superintendent
efe6ad0b-dc1b-52d1-be5b-093a864d86fb | textbox | DATE:
5334bf85-301a-498e-9060-6bca70f2fd85 | signoff | REQUEST HOLD POINT SIGN OFF
98ef0fd3-11a5-4c1a-827e-b30e5ca4782e | section | 3 Testing Requirements
8d28a664-3ee8-4bda-ab2d-f7775f9d3f9d | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
dd6f0b51-1c18-5a0a-88fb-6f29f252d256 | note | FREQUENCY: Prior to Testing
a2861e16-89b5-5b7e-83b3-e91ea85bf787 | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement. Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
3efd6b6d-8678-57be-a4db-9e7ed69d91be | note | REFERENCE DOCUMENTS: Table 204.161 Cl.304.08 (a) Cl.304.11 (b) Cl.304.11 (c)(i) Table 304.111
cb1f4e45-4a7d-5fea-b55e-f20ac4bbe769 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
2862d69d-91a9-5d5d-9e20-7e6d68b82342 | note | RECORD OF CONFORMITY: Signed ITP
a7325f6f-3573-5b24-a1df-321050443979 | note | AP
9afd2a31-9d71-55ed-843a-c39adb1fa2b0 | note | RESPONSIBILITY: Project Engineer
1e433a3d-26a1-5a68-a883-a34546342ac7 | textbox | DATE:
1e2c05d1-f0a0-4805-8573-ce9c091554c2 | checkpoint | 3.2 Compaction Testing
e3cac7f3-869f-57ca-b566-32976584b7d5 | note | FREQUENCY: Every Lot Every second lot (reduced frequency)
601ca9ed-e3ca-566e-9401-3c81d0e48208 | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
b8180d27-39fc-56ac-bf30-255f9043d039 | note | REFERENCE DOCUMENTS: Cl304.08 Table 3040.061 Cl 304.11 (b) Table 304.111
46667137-b312-59e3-9372-ee65c092db29 | note | INSPECTION/TEST METHOD: Test point
ce975057-299d-5ab0-a0da-273d9f63e550 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
2d9224d1-4421-541d-9c33-367375fba44d | note | TP
231e744c-68ac-5881-a93e-cfac377b1b32 | note | RESPONSIBILITY: Site Engineer
584e93a3-4538-5556-b033-f0ec52157ff9 | textbox | DATE:
3bd75f97-f578-42b1-a025-805c59e894c1 | checkpoint | 3.3 Material Grading - Post Compaction (Class 2 & 3 Only)
1a314e5c-7c9d-5b5a-8525-6609caf6fcb5 | note | FREQUENCY: Every Lot Every second lot (reduced frequency)
7e7ba559-2a91-55ef-9a71-a4f5a06348ca | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following: Class 4 - N/A Class 3 - As per Table 304.101 - VR Spec. 304.10 Class 2 - As per Table 304.101 - VR Spec. 304.10
e7d14178-8eb4-5a18-888f-d786ac196264 | note | REFERENCE DOCUMENTS: Cl 304.101 Cl 304.111
760e9c7b-065d-53f1-8c4b-0c74e47d2bdb | note | INSPECTION/TEST METHOD: Test point
99d4e8b8-7a30-56e1-b2f6-86a807151d02 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
379d281e-02f6-5b29-92b5-3f5f78fa4439 | note | TP
83ffa691-10dd-50e7-84ec-1bb06fbb17df | note | RESPONSIBILITY: Site Engineer
2390029b-d584-51e8-ab49-22b9855743c9 | textbox | DATE:
e3eefc4a-7f95-4907-933f-9cea588b6e43 | checkpoint | 3.4 Plasticity Index - Post Compaction (Class 2 & 3 Only)
a5ade9ff-48fe-52d6-bfd4-fae81b917b14 | note | FREQUENCY: Every Lot Every second lot (reduced frequency)
1375b189-8ef2-5938-b88d-2e3552a1c559 | note | ACCEPTANCE CRITERIA: Post compaction PI results must be comply with the following: Class 4 - N/A Class 3 - 0 to 10 Class 2 - 0 to 6
1fdccc7d-2f41-5c43-b54e-37630b2430ab | note | REFERENCE DOCUMENTS: Cl 304.10 Cl 304.11 Table 304.103
224c7c36-e21b-578d-9dc2-4c4d0d9d56f3 | note | INSPECTION/TEST METHOD: Test point
7cdb5f0d-d5c5-5cdd-8ffb-0dc9cc84b3ff | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
011ca605-ecf2-56e0-827d-86cf246ad619 | note | TP
bfd8279d-d96f-5fc9-b05e-281c8cb83ff0 | note | RESPONSIBILITY: Site Engineer
98752a42-15bd-58ad-9105-6218235e8a86 | textbox | DATE:
8f14cfc7-85f7-401f-9740-5ce2e26b2fc1 | checkpoint | 3.5 Survey Conformance
10b56904-c885-5362-bee0-09bafd371328 | note | FREQUENCY: Each lot
a94b2961-1865-5678-aa3b-310c5c60b445 | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits: Shape: no point deviation > 8mm from 3m straight edge in any direction Surface level tolerances: Range x = +6, -10mm Max S = 10 mm 80 measurements per lot
ffeaee8d-76d7-531d-ae6e-94ad0d57bf77 | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings Table 304.062
7a2d90d0-c237-54d1-9491-f44ebe111fcf | note | INSPECTION/TEST METHOD: Survey
f66dbf5b-03e5-5d97-9791-89295f186f8d | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
11543cd3-e226-5952-9704-17884cf792c6 | note | SCP
441d3877-35fc-5c5a-b8e9-f99a583f4ac2 | note | RESPONSIBILITY: Site Engineer/ Surveyor
79da5bc7-37d1-5311-bc19-4ecd9ca073ae | textbox | DATE:
e797bdd0-a200-4450-bb53-52e6e821cbfc | checkpoint | Final Inspection
6e051aae-c0b7-5b37-9dd2-3f4383f67194 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
8286d333-b83e-524f-b353-e1ddf632a97a | textbox | Print Name:
e22af378-be17-5a6b-bd70-f908fa309791 | textbox | Position:
1c790e7e-901d-5424-9bb7-4202b033a53d | textbox | Date:
05a7b456-b15d-4488-a1f9-6cc249372210 | checklist | ITP-01-006 - Class 3 Crushed Rock REV2 |  | ITP-01-006 - Class 3 Crushed Rock REV2
5e868bf8-73f5-478b-bc65-273186a2db3b | section | 1 Preliminary Works
07accee2-e9f5-4913-a172-6bdeb17ebe5c | checkpoint | 1.1 Check for correct documentation
7d9eff47-abe0-569d-b35b-60faf2c616db | note | FREQUENCY: Prior to commencing any activity
dbdcd39a-6841-5427-9d46-98abbb3e4c0f | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - Using the correct and complete set of drawings - All drawings are the latest revision
eee4bdfd-ca1f-55c2-8fa8-ebf5ff8da0d7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
765f155e-443e-55f6-8a8a-561df20799ae | note | INSPECTION/TEST METHOD: Visual inspection
06e1b798-21f8-5ff1-92ca-7b2374be7769 | note | RECORD OF CONFORMITY: This ITP signed
e01e6d64-092a-570a-a75d-dee589d8a0a1 | note | HP*
6b475343-c883-5269-a1d9-6e79ad31bbca | note | RESPONSIBILITY: Site Engineer / Site Foreman
20550e41-9073-525f-ba17-4b14f91db006 | textbox | DATE:
08b2f78d-dbcb-4f75-8b67-e1b908f387ae | checkpoint | 1.2 Material Mix Design
22faee93-15b0-50f9-a39d-674a26b4adcb | note | FREQUENCY: Prior to commencing any activity
1cc1963d-847f-5871-8a50-23c765a4a192 | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
d2d252be-6706-5387-a833-5bcdeecebcf6 | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
9c59601f-b216-5873-9ff9-b5404c61066e | note | INSPECTION/TEST METHOD: Document Review
872e3c9a-2961-5a02-a89d-7a783cbc5316 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
5e1a635b-b069-530e-837d-3a8059da6c86 | note | HP*
fa75cf91-e32a-536b-9fd2-ce54675851e6 | note | RESPONSIBILITY: Site Engineer
28c40007-1ffe-51f0-a981-9ed4777a21e0 | textbox | DATE:
155c95c8-0361-4297-9bdf-1f8978d4c1cf | checkpoint | 1.3 Implementation of all measures and controls
a1893230-4004-5da7-bf8f-3134f3fc6dba | note | FREQUENCY: Prior to commencing any activity
93448543-54e4-57e6-87d8-5dd99937a470 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
4114b01e-0117-5c92-afd0-6473c8413dff | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
c70b4fc8-25fe-5d82-906d-2df8501fc1a1 | note | INSPECTION/TEST METHOD: Visual Inspection
fd43054c-db08-5131-93ff-c64285944e23 | note | RECORD OF CONFORMITY: This ITP signed
f267170f-01c3-50fd-bfe9-a2fc858bedcb | note | HP*
6cbbb654-66ab-51f4-858c-977fccc14106 | note | RESPONSIBILITY: Site Engineer / Site Foreman
37836363-d105-5842-b4c8-5259db64ca28 | textbox | DATE:
44177ca0-0cc7-42a0-8a88-e535e602c31d | section | 2 Construction Works
875cec8b-1cd1-4307-bacf-ea96def23c11 | checkpoint | 2.1 Transverse Joints
12abd2b1-3edd-56f1-93be-96265e82c41c | note | FREQUENCY: Check prior to placing material
1ecbb324-c2d2-5b7d-9df8-d41076fee722 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
dff962cf-c7bd-52c3-aac5-d1faec7b87fd | note | REFERENCE DOCUMENTS: Cl.304.07 (a) Cl.304.07 (c)
a8f5d6cd-0e8e-5e3d-b267-8bc4d99dc9cb | note | INSPECTION/TEST METHOD: Visual Inspection
a55b34d0-51bd-5840-b268-52bc996518b8 | note | RECORD OF CONFORMITY: This ITP signed off
c438eb89-6812-57bf-9f72-7978c940eb1a | note | IP
839a400b-f318-577e-b784-ff62fc28e1f2 | note | RESPONSIBILITY: Site Engineer
af20d00e-955c-557e-9e18-296e9596a353 | textbox | DATE:
279e02ad-865f-4c80-bcd3-6b3f694856a7 | checkpoint | 2.2 Longitudinal Joints+A21:N37
1d4685ef-33f6-52a4-bee5-7814ff1b79a1 | note | FREQUENCY: Check prior to placing material
69564153-ce46-5fd9-b0e6-4941f70404c6 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
02e7f98a-9e5c-5885-82a3-937da055f851 | note | REFERENCE DOCUMENTS: Cl.304.07 (a) Cl.304.07 (d) Cl.304.07 (e)
a61895e2-915d-595e-a8d2-0798cf3c8d8a | note | INSPECTION/TEST METHOD: Visual Inspection
5bf2605f-7611-5a4f-972f-ee63e2202238 | note | RECORD OF CONFORMITY: This ITP signed off
9acd1fa8-4d5a-55e1-9a84-753623ce2a5d | note | IP
697490fb-9fa3-5bea-b00b-a0ee0c83e201 | note | RESPONSIBILITY: Site Engineer
cbece145-611b-5547-aeb1-31e7ae1cd629 | textbox | DATE:
66b7e3d4-6987-41a5-bbd5-79ad61588d3e | checkpoint | 2.3 Lot Size
e80b58c2-2f63-54d0-be61-c97a3abf2825 | note | FREQUENCY: Check prior to placing material
3a015bdc-40ab-51c6-8878-58676714930b | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
c5fd1605-afcb-582c-be18-802f77cec0fb | note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
b88dda18-c888-5681-a466-82370b7ae7d2 | note | INSPECTION/TEST METHOD: Site Inspection
5b46cd42-957d-51d7-972b-9e224582af89 | note | RECORD OF CONFORMITY: Signed ITP
ea7a3081-1226-5eea-a948-8f86e48f36e0 | note | IP
c873decf-3c5f-5991-a4f2-cb09215f1ec6 | note | RESPONSIBILITY: Site Engineer
82c475df-41d7-56df-beb2-41e00ad3a4aa | textbox | DATE:
9c1c6d6b-c4db-4ce1-820c-7441c4a9cade | checkpoint | 2.4 Layer Thickness
15fc99b6-7fb4-5b50-8a22-c7fc046d7f7b | note | FREQUENCY: Each Lot
d623ab56-4af7-5a1a-9bb0-4fd9b77fac37 | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
09479b75-4f22-550f-90d1-1375377c9546 | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v) Cl 304.08(b)(vi)
3d07b0f5-380f-56da-a4b9-6b8a324c8d5b | note | INSPECTION/TEST METHOD: Site Inspection
b847f8a9-449c-5efc-b42d-9a973cb1e131 | note | RECORD OF CONFORMITY: Signed ITP
b9fa37c9-7b0e-5818-aaa7-e9ac8ab6f5da | note | IP
90410df3-95b3-5858-9d4f-54affbccc02e | note | RESPONSIBILITY: Site Engineer
64ae77a3-79d3-5f5d-8802-0802413a181b | textbox | DATE:
1914eca1-0c1a-4599-a736-627ff3455b0c | checkpoint | 2.5 Proof Rolling
a9359f24-27bf-5d3e-9c63-09cc613efffb | note | FREQUENCY: Proof Roll each layer
56a4ec21-364e-5509-9a9f-3d4e8ab9b95a | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
3de059bc-3695-5fdf-87f0-cb5307a5a191 | note | REFERENCE DOCUMENTS: 173.03
db168ee8-8491-51eb-baa9-d32dd608a2dc | note | INSPECTION/TEST METHOD: Visual inspection
4ebabdae-4ed7-5b54-b377-4d09ee5bcb43 | note | RECORD OF CONFORMITY: This ITP signed off
14094500-a40f-59a3-8586-0d0dda9268b1 | note | HP / WP
0a595e6c-9763-592d-9d83-351c94704073 | note | RESPONSIBILITY: Site Engineer & Superintendent
52a67175-982a-5c42-aa17-4f4552850079 | textbox | DATE:
d084a81c-8b76-40f7-8558-f6093cf817b8 | signoff | REQUEST HOLD POINT SIGN OFF
dfebc753-1a04-40c5-852d-422423a7fdd8 | section | 3 Testing Requirements
24214b87-6b13-4fa3-9a10-c9bebc2fb72e | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
c34d7a91-bcd1-536a-b4ec-8a94908d387c | note | FREQUENCY: Prior to Testing
0a10ea0c-8c94-5603-a92c-27fc2397280a | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement. Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
158f0a39-5708-5b70-9aa9-d73aa2fe9d2b | note | REFERENCE DOCUMENTS: Table 204.161 Cl.304.08 (a) Cl.304.11 (b) Cl.304.11 (c)(i) Table 304.111
3522c035-5b05-5676-a307-9e1c0dc3a6a3 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
4947fd71-c3e4-58a2-9423-9654c3b53e23 | note | RECORD OF CONFORMITY: Signed ITP
05d30cd8-5868-5d49-9e4c-dd137fb5ee18 | note | AP
2816a533-35e4-5058-ac64-cc1409021824 | note | RESPONSIBILITY: Project Engineer
12b18d49-3e99-56c9-b304-4535f314fbb0 | textbox | DATE:
27bc7113-1c34-47bf-a4c7-b22dc922f179 | checkpoint | 3.2 Compaction Testing
32e0a09d-e609-5a21-9dc4-62dd1c303175 | note | FREQUENCY: Every Lot Every second lot (reduced frequency)
f68a1c9b-b81f-5fca-95a2-3d50e8b1735d | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
10f60e58-0fe8-5583-ad54-b16300a7ef58 | note | REFERENCE DOCUMENTS: Cl304.08 Table 3040.061 Cl 304.11 (b) Table 304.111
3a7fcdb2-c414-55e6-a384-eacb416002ec | note | INSPECTION/TEST METHOD: Test point
3c5c618c-d8c1-5d70-8e54-c77dd2bce94a | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
a3f7f694-ced3-52ff-9d24-bcfb1966bb56 | note | TP
a33a0ad2-2134-54f3-8354-612d964426ca | note | RESPONSIBILITY: Site Engineer
3dedcf2b-cc2d-5ac1-ad27-cb4dd50506ee | textbox | DATE:
90204c3f-ad66-46b9-8840-dab5a468407d | checkpoint | 3.3 Material Grading - Post Compaction (Class 2 & 3 Only)
43fba6a8-fb63-5564-906f-9922959a0e4c | note | FREQUENCY: Every Lot Every second lot (reduced frequency)
1327a2ee-7c93-5876-a841-7a8940878c89 | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following: Class 4 - N/A Class 3 - As per Table 304.101 - VR Spec. 304.10 Class 2 - As per Table 304.101 - VR Spec. 304.10
a36a548d-7654-571d-87e7-e4c2ced18d8a | note | REFERENCE DOCUMENTS: Cl 304.101 Cl 304.111
54f55562-5433-515e-ada2-d49475e02137 | note | INSPECTION/TEST METHOD: Test point
8f7bdd95-719d-593a-8d18-599f036acf58 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
2b9ae6f5-b2ac-5c7f-9dfe-a50cadbe9db1 | note | TP
24d870af-9848-598e-9be8-d68377b09125 | note | RESPONSIBILITY: Site Engineer
4541dc5b-0e3b-5a22-b51a-f852edc1dcfc | textbox | DATE:
8ff0baa7-2ef0-47c7-bcb7-f45d7d4b3ea0 | checkpoint | 3.4 Plasticity Index - Post Compaction (Class 2 & 3 Only)
fa5541ac-b904-5ee2-85fb-640b4c406cf6 | note | FREQUENCY: Every Lot Every second lot (reduced frequency)
160c087c-0d9d-5c9c-a753-5fefdccdc443 | note | ACCEPTANCE CRITERIA: Post compaction PI results must be comply with the following: Class 4 - N/A Class 3 - 0 to 10 Class 2 - 0 to 6
6ce91986-bf5e-5db4-8288-2a3c05232331 | note | REFERENCE DOCUMENTS: Cl 304.10 Cl 304.11 Table 304.103
4d6f3bc2-c1d0-59e1-b657-8a0425f11de0 | note | INSPECTION/TEST METHOD: Test point
a4763105-9ae7-5a23-9511-91112a2ce75e | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
4625a480-06df-550a-9b36-a905bcfa9674 | note | TP
856b58f5-a0c8-5e9b-9ab5-6ccf885908c8 | note | RESPONSIBILITY: Site Engineer
a212515b-9d1e-5585-bf48-bc227482701c | textbox | DATE:
866bdc27-8f3a-4348-882f-d77c3f92e374 | checkpoint | 3.5 Survey Conformance
3490231b-403c-52e1-8d54-ba473d462b70 | note | FREQUENCY: Each lot
f7f53a23-5947-50a3-880e-35547b4cb120 | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits: Shape: no point deviation > 8mm from 3m straight edge in any direction Surface level tolerances: Range x = +6, -10mm Max S = 10 mm 80 measurements per lot
09ed468b-6823-5e69-8d6c-28e49120cbad | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings Table 304.062
2a36ef4a-d936-5661-945d-a429450384c0 | note | INSPECTION/TEST METHOD: Survey
c24f081b-e20a-5321-aa50-506294bbd75e | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
557f2aeb-0665-570e-9cf9-a83cb5826e5a | note | SCP
af576429-d717-5355-8413-95b52b061b29 | note | RESPONSIBILITY: Site Engineer/ Surveyor
51d01f44-517c-55ce-be39-20749f04f10c | textbox | DATE:
80cfa41b-87df-4271-af8d-91e3c03e4c23 | checkpoint | Final Inspection
e3e512e0-4ff4-5483-b6a1-50015c14e89c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1c682eb2-be2f-5de5-b7a3-519fc2b81001 | textbox | Print Name:
4674e94a-5543-53ad-bef2-654cf6d7ab38 | textbox | Position:
f8008470-7766-57b2-884a-3ffb97bbc48a | textbox | Date:
4e66af40-14d9-47b5-98e3-cd10dbc093c9 | checklist | ITP-01-008 - Stormwater Drainage (carparks) REV3 |  | ITP-01-008 - Stormwater Drainage
5baa144d-4bc1-480d-b292-a54ffd912e92 | section | 1 Preliminary Works
03b6a52e-d45b-439d-8ef0-c528d251e5dd | checkpoint | 1.1 Check for correct documentation
9f283b35-0b77-523a-9224-a09ac5eeeeb8 | note | FREQUENCY: Prior to commencing any activity
46e94045-628c-5962-a717-f096ad0f518c | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
6f94beab-5f94-5e44-bf46-70136f5a7e76 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
394ee94e-dee8-5227-a981-106b77aaaed2 | note | INSPECTION/TEST METHOD: Visual inspection
edd2aa73-f093-5ea3-905e-5e97038012aa | note | RECORD OF CONFORMITY: This ITP signed off
9bb18a89-ff26-5094-9106-f3ee02c0f2fa | note | HP*
c39324ef-38bb-564b-bb4e-308a7c079975 | note | RESPONSIBILITY: Site Engineer / Site Foreman
eba7edbc-06b8-5d50-8611-76f2cb5fd0fd | textbox | DATE:
3c18abec-6f8d-44e7-8984-0e3ad41ef311 | checkpoint | 1.2 Implementation of all measures and controls
df0e8237-8f65-57b3-afce-3d67d136a630 | note | FREQUENCY: Prior to commencing any activity
5b75c32b-bde5-5e8a-80cf-216f58a7782f | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
b0fec2c9-335c-555f-ac03-cba66b32a4c5 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
86815df4-271c-5cd4-937f-a52aa67f4fb3 | note | INSPECTION/TEST METHOD: Visual Inspection
779f4b9b-a95b-59c0-8335-c5a1ad84dfef | note | RECORD OF CONFORMITY: This ITP signed off
f4507e37-e5b9-5d3d-b655-547820126b89 | note | HP*
6d2baef7-b265-5809-b91a-74c42acb5ff0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
9fd60882-e247-5f0e-aa18-40c9be8c39b4 | textbox | DATE:
892a0e82-d91d-46f0-a1a6-e430b75efae3 | checkpoint | 1.3 Precast Materials acceptance
7b8cd178-0ce5-5817-a92f-5458bbc4e456 | note | FREQUENCY: Each Delivery
12187bf8-5b11-54d5-b122-7752d6da52d2 | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
ebbd656d-84b8-513c-9cc9-e637b42f8403 | note | REFERENCE DOCUMENTS: Cl. 701.05e
f3939593-e1e3-5297-9f84-922b5ec48f48 | note | INSPECTION/TEST METHOD: Visual Inspection
f23cf24c-dfda-553c-9d7f-e4d48b61cd8c | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
4a375c0c-17db-5553-94a4-0b65a32e7200 | note | IP
4eb0b2ea-b424-5865-af33-c5f692fe801a | note | RESPONSIBILITY: Site Engineer
53d4ac4b-dbc0-5075-98f1-41260a9c9623 | textbox | DATE:
b09d6978-1373-408b-be26-c2af609b2f16 | checkpoint | 1.4 Precast Pipe & Culvert Compliance
d04b75c0-c5de-5251-a50f-a8f9a922d133 | note | FREQUENCY: Prior to Commencing
2d9f5af0-33de-5f3e-b390-ae0de594d157 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619. Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058
f10f726b-96e6-5fb6-b3fc-da96fb987048 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619 Cl. 701.04 Cl. 701.05(a) AS4058 AS4680
4cedfce2-4c98-5f35-8918-2b3475620cd1 | note | INSPECTION/TEST METHOD: Document review & Site inspection
77724872-9f9e-5680-bc8a-41cdc56a6396 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist Manufacturer cetificate or accreditation
e4e83a75-0c12-5c0f-9780-6a8092aa4f0a | note | IP
ef431186-a383-54d9-9e23-cef5a27abb63 | note | RESPONSIBILITY: Site Engineer
d26f9c87-1c8c-5aea-8ec9-290068b9ff2b | textbox | DATE:
603533d8-bc2d-4662-a2c7-dea96e5faeb3 | checkpoint | 1.5 Precast Drainage Pit Compliance
f8290677-eabc-5c3a-a994-57009188bc59 | note | FREQUENCY: Prior to Commencing
ae84ae60-665d-5f9e-8eb9-b994a46840ba | note | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
f83c6a47-a6ae-5383-8800-7051d98f332d | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.610 Cl. 705.04 AS5100
48f9cd7f-d880-52da-b38a-f98a8adbce76 | note | INSPECTION/TEST METHOD: Document Review
4d662bc9-6858-5d45-b6cf-0fe695b1e960 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist Manufacturer cetificate or accreditation
7e69a082-4924-59ba-a348-affe04f98a97 | note | IP
ab0ba700-4318-54f2-a7af-c3898e7e4ee4 | note | RESPONSIBILITY: Site Engineer
ee397caf-ad31-59ce-a470-d7a0141d9761 | textbox | DATE:
c86138ec-cc07-4ff1-b36c-a9025e0b22ea | checkpoint | 1.6 Bedding material classification
8fb7453a-a9f2-50ef-9aeb-80f7c66a15d2 | note | FREQUENCY: Prior to start
3d64a215-0bcd-56df-97ef-af13aa91de53 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
6791f84f-33b5-5044-bda1-08d9d4dfc1f8 | note | REFERENCE DOCUMENTS: 701.09(d) 701.091 701.092
39484ae8-3431-50ac-89e8-21e045e39d12 | note | INSPECTION/TEST METHOD: Verify
6c237176-b65a-5b9c-8dd4-ef1f5656820c | note | RECORD OF CONFORMITY: Test Reports from supplier
20bfaaac-2a51-5683-b20c-c22d5695d667 | note | TP
6075d144-8e1b-5476-9e83-b9fd6f79d09b | note | RESPONSIBILITY: Site Engineer
b4e3866f-b9ab-5206-9c8c-201397484e7f | textbox | DATE:
dd45f018-aac1-4e4f-b669-65cc84b12bb2 | checkpoint | 1.7 Backfill material Classification
1fa86318-b3ca-5106-918e-c2ad6424de53 | note | FREQUENCY: Prior to start
326bca47-fe4c-5a50-aebb-9b2122d32d1a | note | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
00bf8ad0-e132-514f-a52a-40cff47b7cb5 | note | REFERENCE DOCUMENTS: 701.09(d) 701.091
59b98d76-7a6c-5881-8661-32096f94def8 | note | INSPECTION/TEST METHOD: Verify
1f8b6f9a-f637-5bd5-8d7e-d9899a4c2993 | note | RECORD OF CONFORMITY: Test Reports from supplier
f6db5d3b-7921-5956-92fd-e7b41d156fa6 | note | TP
364ade3c-399b-569c-aef8-738d40db0ffa | note | RESPONSIBILITY: Site Engineer
d290420d-558c-543d-a1ae-3e42a7252bfa | textbox | DATE:
91c06275-9781-4bd8-a0cb-81dbc14b3471 | checkpoint | 1.8 Mortar material classification
59c8c1f9-9760-5ae6-b9e5-7647bec05122 | note | FREQUENCY: Prior to start
3440972d-ef3c-5881-bd47-9b2438772822 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
8014fa1c-4771-52f0-b033-bccd5558bb92 | note | REFERENCE DOCUMENTS: 610.33
f997d762-c936-5041-8219-ba9b668e1d06 | note | INSPECTION/TEST METHOD: Verify
2c57a32c-25b6-5b5b-889a-f44b2127a5cb | note | RECORD OF CONFORMITY: Test Reports from supplier
078a8a5f-030d-530b-8416-0339c7afe040 | note | TP
459a5d01-8083-5635-9109-c764fb3726a0 | note | RESPONSIBILITY: Site Engineer
70e307d3-a962-5fe7-bfad-b0dff0ca9f37 | textbox | DATE:
0e36cb15-3648-435f-9095-2bad67bbe488 | section | 2 Construction Works
003bb3b0-4aad-44ce-969e-bf9fe2c24551 | checkpoint | 2.1 Excavation Permit
bf5f2e77-e246-52c8-8624-3ace5b613c6a | note | FREQUENCY: Each lot
160067e8-ae92-5308-b3dc-639afc5db816 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
6cfa3c71-20e2-57b9-8106-05f18ef801a1 | note | REFERENCE DOCUMENTS: Excavation permit
7c1aa0be-63ad-55f3-817c-cb18d44dc742 | note | INSPECTION/TEST METHOD: Verify
61713268-2ad1-5ab6-a505-5f5dc2d57ae3 | note | RECORD OF CONFORMITY: ITP Signed
fcf0f0d9-41cb-5b7b-b656-d535fe969218 | note | HP*
81ec6f62-e05e-5cf9-a16a-94e8cc9fe9ab | note | RESPONSIBILITY: Site Engineer
a88c79f2-d8a7-556d-b6bf-8893d42e63f3 | textbox | DATE:
f1ca4372-5784-4204-ae38-56f0061324a5 | checkpoint | 2.2 Set out drainage
e2760f42-ecba-576f-ba36-6832b3ddf75a | note | FREQUENCY: Prior to backfilling
0236c2d7-4aaa-539c-a512-04519e07be9c | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
87d729e8-702f-54ab-9d62-b4879e0e0379 | note | REFERENCE DOCUMENTS: Drawings 701.10
522245b1-21e3-5073-b49a-41e609026c57 | note | INSPECTION/TEST METHOD: Visual Inspection
d198e245-761e-55db-98d3-59a55c1bd612 | note | RECORD OF CONFORMITY: ITP Signed
d5ef70b9-824a-5c86-a199-5b6f06c80c31 | note | HP
b115f513-83c3-59a9-ad4c-8c3d91636310 | note | RESPONSIBILITY: Site Engineer/ Superintendent
a7c24dd3-46b5-51fa-baac-2569f4164e64 | textbox | DATE:
d33b24b1-5eb7-4602-a0c6-a3e7360244d5 | signoff | AUTHORITY HOLDPOINT
bc4e34b3-06dc-424c-aa0e-c0f95b5b640c | checkpoint | 2.3 Excacation (pipes)
ff20b796-cf25-5a87-a352-35873b338008 | note | FREQUENCY: Each Trench
4fe0d7c7-153a-556e-89a0-eba729783297 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 150mm minimum. Trench walls to be vertical where practical.
9f52686f-b41b-5027-bb17-a5132e58a4be | note | REFERENCE DOCUMENTS: CRG-0015
99ac277a-574c-518c-b958-b92f6a3509cb | note | INSPECTION/TEST METHOD: Visual Inspection
e05fa00e-e2a2-58c2-8944-371653ca40a9 | note | RECORD OF CONFORMITY: ITP Signed
d0e81a78-dca6-502c-af4d-d57a6e4b2814 | note | IP
f291a1c2-b724-55f1-a457-47e5c999b06e | note | RESPONSIBILITY: Site Foreman
aebc9d18-39ba-5972-98e9-2f08158340d5 | textbox | DATE:
aa7136e7-3a3f-42ba-9a69-e326b82ae6f2 | checkpoint | 2.4 Excacation (pits)
ad17f26a-698b-5b2f-99ad-a83c93a7340b | note | FREQUENCY: Each Pit
5a7a2bba-8ae9-5ef9-94c7-5f797c9a379b | note | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
141c0356-f755-59bd-9ce0-e7acd4093cb1 | note | REFERENCE DOCUMENTS: 705.05b
d1ba59f0-12b4-5305-9c77-169253ab2dc4 | note | INSPECTION/TEST METHOD: Visual Inspection
d4f23edd-5ced-56f3-8c93-8245bbab09cb | note | RECORD OF CONFORMITY: ITP Signed
f9aec424-249b-5ade-b607-ae35d53b1075 | note | IP
b4773521-c1e8-568e-b0a7-31b9590d8692 | note | RESPONSIBILITY: Site Foreman
8b0a8e04-e8c5-567d-ae52-8d36861b730d | textbox | DATE:
91791d07-1591-4469-a9a4-2465f2aa7c32 | checkpoint | 2.5 Compact base of trench
f88a3630-7bd1-5f20-939b-176deb58262e | note | FREQUENCY: Each Trench
c8fc8c20-8872-5d8f-8155-9f32189f0a9e | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
9eef874f-45fb-5941-ad62-5251ea100545 | note | REFERENCE DOCUMENTS: 701.15
b5ff553f-9524-5804-b574-92d66f005ea0 | note | INSPECTION/TEST METHOD: Visual Inspection
03f51a24-2d53-5eb7-953c-cf3706a7ebd4 | note | RECORD OF CONFORMITY: ITP Signed
a1613c9d-c629-54f6-b729-afd906036c34 | note | IP
ef640d30-e8f4-5465-92f4-825a1830c227 | note | RESPONSIBILITY: Site Engineer
cc2c4f42-f3b1-5617-bcba-fb17a5024e35 | textbox | DATE:
e91b2904-299a-4b87-b896-80c3971521a4 | checkpoint | 2.6 Place bedding material & compact
1206f42f-b889-5c93-aac4-2a30c806d4c8 | note | FREQUENCY: Each Trench
f26e68ef-b681-5ce8-898c-05a06d1bb446 | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
f4e9f0af-4f3e-54ea-a3f5-2d4c731d421d | note | REFERENCE DOCUMENTS: 701.20 701.20a
aa47e244-019b-560e-a07e-e6b000f24ea5 | note | INSPECTION/TEST METHOD: Visual Inspection
abc9fdeb-f127-5c2c-a9d6-e2dfd0d2105d | note | RECORD OF CONFORMITY: ITP Signed
a7ceeb86-8a0e-5ded-929c-636bcd3a2000 | note | IP
e2554a6f-3920-5d00-8923-6c072b772f25 | note | RESPONSIBILITY: Site Engineer
496555e8-c39b-5073-b41c-6ae4a61845dc | textbox | DATE:
3b4735e8-6f15-4b2f-b8b1-2ce743ee2946 | checkpoint | 2.7 Place pipes & precast pits
6629b681-62ae-5e11-97f6-420396a2d3ee | note | FREQUENCY: Each Line/Pit
eabde251-9bc3-56ef-adca-fc4dc05499b4 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
f8e4c485-a18f-55a5-a9ea-02c53db547d2 | note | REFERENCE DOCUMENTS: Drawings
2dd4d46f-677b-534f-9dd0-f65c0e4628b9 | note | INSPECTION/TEST METHOD: Visual Inspection
5c9fe752-3967-557a-bb60-25be51abd244 | note | RECORD OF CONFORMITY: ITP Signed
f4c78bb3-7410-5940-91fd-3c7205a5ee34 | note | IP
e97e56bf-01a9-5a79-9103-53eb0b37ffc4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
04e84208-3e63-5cab-8478-d477efed0942 | textbox | DATE:
93f3e7b8-137b-42f8-9a61-0c23f7d09120 | checkpoint | 2.8 Jointing pipe sections
9635acf5-219b-518e-b9c3-40daf2e26431 | note | FREQUENCY: Each Line
4f3daf60-1944-5b22-aabb-c09e0ad09850 | note | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
a5147bf0-c3c7-502a-a0bc-b89ebc31b400 | note | REFERENCE DOCUMENTS: 701.18
e639a679-32ad-5c4c-8aaf-280530c061e4 | note | INSPECTION/TEST METHOD: Visual Inspection
ba593de7-8cbe-5888-b473-7393bf0d2e9a | note | RECORD OF CONFORMITY: ITP Signed
e3cfb373-5b1e-5ed3-9812-830e0046b810 | note | IP
4f9ed3ea-fc95-5d62-99af-1bb8e74ca451 | note | RESPONSIBILITY: Site Engineer / Site Foreman
6138b8e5-33ac-5f4c-81da-e91050bc436b | textbox | DATE:
de8f05ce-5313-4f15-a37e-91a36c10518d | checkpoint | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
a0491d79-6b5b-5e9a-b1d3-5e2d45158615 | note | FREQUENCY: Each Pit
d137a1be-1281-5bf1-8bac-f2ac0fb4cb93 | note | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared. The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
81e61035-7e7a-5404-8802-104768ba3071 | note | REFERENCE DOCUMENTS: 610.32 701.17c
53b65dab-c245-51c4-8953-373faee05c83 | note | INSPECTION/TEST METHOD: Visual Inspection
efaedd23-8b1f-54e3-b3cd-40e49e68c981 | note | RECORD OF CONFORMITY: ITP Signed
0355118e-d244-5f03-b469-20f7e2c25d4c | note | WP
814d2ae0-646f-5e3e-bc4e-690a360d3efb | note | RESPONSIBILITY: Site Engineer / Site Foreman
a8d729ae-b391-5269-b098-adebbc18192a | textbox | DATE:
d3ec2e11-bfac-4259-9aca-343602b042cc | checkpoint | 2.10 Survey of laid pipe or pit
a5d708f6-204a-5e07-a179-e346c25ada0c | note | FREQUENCY: Prior to backfilling
2c2d461b-cb02-5a58-be5d-fa16fca1ec7d | note | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances: (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
44373dfb-5c62-5e8a-ada9-720e7e672d1b | note | REFERENCE DOCUMENTS: 701.1
157b26b3-ed50-5348-8994-179e387ee297 | note | INSPECTION/TEST METHOD: Survey Conformance Point
5589f883-eee1-584b-85bb-77d12fd47690 | note | RECORD OF CONFORMITY: ITP Signed
eaec33ed-7954-5b29-81d8-7a3b35caa771 | note | SCP
6f730dc9-5c56-5e74-962f-acaa9a9a06ff | note | RESPONSIBILITY: Site Engineer/ Surveyor
50f7b076-bc58-5ef8-8c26-6a2be218370c | textbox | DATE:
4a3f225f-97b6-485a-955e-26ddc5b58416 | checkpoint | 2.11 Haunching & compaction of bedding material
e560a505-39bc-53a6-b283-84dcf9d82ef3 | note | FREQUENCY: each lot
593c4f35-dcc1-507c-b550-41622c3af5ae | note | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height. Loose layer thickness <=150mm Compacted to refusal using hand held mechanical equipment. 1 lot = 150mm layer
292cc0e1-4849-5e58-8ad9-098ebf341e2d | note | REFERENCE DOCUMENTS: 701.16 701.20
b26280a2-dc97-53f1-8bf3-11a3963ec5e3 | note | INSPECTION/TEST METHOD: Visual Inspection
10757fc6-8494-53d7-8343-ed17479700df | note | RECORD OF CONFORMITY: ITP Signed
23dd943a-b640-5696-9906-fb3f9149d365 | note | WP
10c3ff5d-7200-5270-81a4-9b4ca3bb8e47 | note | RESPONSIBILITY: Site Engineer / Site Foreman
340b4dd2-4fbe-5769-a367-40fa3f03716c | textbox | DATE:
8be3fbd0-c94a-4b2f-88eb-0741e486e5e8 | checkpoint | 2.12 Place & compact backfill material over pipes
2bdca5ee-37b6-5d46-a352-758f651614ca | note | FREQUENCY: each lot
ab100fc3-c27d-5ce7-97eb-fd78bcaca8ee | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level Loose layer thickness <= 150mm. 1 lot = 150mm layer
94716e71-d331-565f-a1bd-4e5537664fe7 | note | REFERENCE DOCUMENTS: 701.19 701.20
d4600998-0bf5-5254-835d-3b6ff2d99ede | note | INSPECTION/TEST METHOD: Visual Inspection
e9892e30-8ca3-56b3-ad46-f19b82e648fd | note | RECORD OF CONFORMITY: ITP Signed
f646635a-f179-582b-88fd-b5c30b7f78a8 | note | IP
98aa868b-f6ea-574b-be8a-4c7c766a8aab | note | RESPONSIBILITY: Site Engineer / Site Foreman
92582e53-0a41-5eaa-becd-6cd480730340 | textbox | DATE:
9f30958c-4066-4afc-b389-ff95fff1a758 | checkpoint | 2.13 Place & compact backfill material around pits
bd005d01-53d7-5cb3-90ce-c8bd23998c71 | note | FREQUENCY: Each Pit
452edb54-ab14-5586-a91d-c0c6991d14f1 | note | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm. Compacted to refusal using hand held mechanical equipment.
25b6a3fc-9973-5b94-8e6d-cd57a36e7a2e | note | REFERENCE DOCUMENTS: 705.18
cb838126-d7c2-52d9-8e2d-16247951632c | note | INSPECTION/TEST METHOD: Visual Inspection
dd2a2672-83b3-5653-83e8-f95f0ad68320 | note | RECORD OF CONFORMITY: ITP Signed
361d3896-54e1-55c3-9cbf-a2d49932c0cd | note | IP
5b60e656-675d-56d8-9c78-615e62374a80 | note | RESPONSIBILITY: Site Engineer
aa0c75da-48cb-561e-bf91-a802c4c4365d | textbox | DATE:
ac22efca-e9e8-49b4-805b-93e204fd1fd6 | checkpoint | 2.14 Backfilling with cement stabilised sand
9b45834a-4bb7-537c-b43b-6d63849f790a | note | FREQUENCY: Each culvert
81d426df-9a35-540f-b720-c189cfc8c5a7 | note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
64dfa67d-f203-583e-8dfa-938d0b5d770b | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(a)
39b7718b-91d7-5ccf-a647-68d49325b280 | note | INSPECTION/TEST METHOD: Site Inspection
bf39f04f-dc42-53e1-a33e-95db14eaa03c | note | RECORD OF CONFORMITY: Superintendent approval ITP signed
f3769725-724b-5046-a2e3-909e727b1f75 | note | AP
883be798-a518-5f73-845b-90e988109562 | note | RESPONSIBILITY: Project Engineer / Superintendent
b94da77e-36eb-503d-aca2-cc1065e00f6c | textbox | DATE:
71c07087-bbd2-4107-a717-9f991715df05 | checkpoint | 2.15 Install step irons
a6ca672f-859e-5a9c-8eea-92c01586710c | note | FREQUENCY: Each Pit
8363f103-ede7-5c35-a930-bf0bbf50422b | note | ACCEPTANCE CRITERIA: For pits > 1m deep.
6572ac66-9a26-5bdf-b58a-4e79ad943c84 | note | REFERENCE DOCUMENTS: 705.12
1385f210-4d1a-55f5-a926-f61c2268865f | note | INSPECTION/TEST METHOD: Visual Inspection
0c88d0ed-a373-5ed0-9c6e-66730726620d | note | RECORD OF CONFORMITY: ITP Signed
b58828c9-932b-521b-b2ca-be7bfa31f6dd | note | IP
33a2cc02-3b51-50c5-91c7-1ca04981dc73 | note | RESPONSIBILITY: Site Engineer
8bebc892-7686-58cb-ae92-b74e256e7d85 | textbox | DATE:
9edf248b-bc4e-49c0-81af-479ac5f4efc9 | checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
29ab342f-d4e6-5f2a-bf3c-96c7fa49a3d8 | note | FREQUENCY: Each Pit
13575a6d-3843-5890-a25b-4f7d0b6d857b | note | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
f6530d9e-ab1c-51b1-9b9a-4c23e31c3bbb | note | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
4833b48b-482e-598b-b7b4-01905ea2c129 | note | INSPECTION/TEST METHOD: Visual Inspection
36b896af-5537-5616-9004-976a9a78d436 | note | RECORD OF CONFORMITY: ITP Signed
456af4e4-ed98-5080-8ada-aa36d3466a07 | note | IP
5da270f5-7692-5dd2-b31f-b96918b7602d | note | RESPONSIBILITY: Site Engineer
15bc67e5-47dd-5621-822a-072fdc43dfa9 | textbox | DATE:
4cd1a8ab-7ba5-4d0d-91ee-c6955ed961db | checkpoint | 2.17 Place pit covers
89fd0997-9438-592a-b7cd-873b6b5d4878 | note | FREQUENCY: Each Pit
899f2c28-9688-50ee-a095-c91c2ea12806 | note | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
361b2f93-04ba-555b-b536-4bf360d76a9a | note | REFERENCE DOCUMENTS: 705.17
9d920918-f302-59bc-ad79-e5f9a17b5e6c | note | INSPECTION/TEST METHOD: Visual Inspection
dcbe2b37-caac-53e0-b772-ed12e68f9607 | note | RECORD OF CONFORMITY: ITP Signed
20c43a5e-a01e-56d3-a072-b1c51a9f3e98 | note | IP
4d5765e9-e7fb-5937-9323-6b3bc4700f04 | note | RESPONSIBILITY: Site Engineer / Site Foreman
e4ed6a78-54d8-528c-8c12-98e7f6b7b185 | textbox | DATE:
f8670fb2-bcae-4db6-9247-049574c88f1d | checkpoint | 2.18 Repairs to damaged pipes and box culverts
5d5679d9-248d-5633-b953-1231d8570dd0 | note | FREQUENCY: Each damaged pipe or culvert
36afb3f8-ddfc-52f7-9361-8f2f4a1e0880 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures All repair procedures undertaken in accordance with Cl 701.25
0eda4649-cec1-5e98-85c6-c4dcc49ce7f0 | note | REFERENCE DOCUMENTS: 701.31a
0cef3e5b-8db0-53ee-b177-aeb0fbb5b74e | note | INSPECTION/TEST METHOD: Verify
57b826d2-d11f-596f-80c8-8c59ccd274e1 | note | RECORD OF CONFORMITY: ITP Signed
d1fd4f9a-bdba-5ce7-b0b1-15810c62946b | note | HP
ab3d4ec7-2bfe-57e9-b48c-172484c71041 | note | RESPONSIBILITY: Site Engineer/ Superintendent
1a1cb9da-8f1f-51b7-9102-be766d24d526 | textbox | DATE:
842108c6-4486-4a0d-a0a7-609fe5e8a0c5 | signoff | AUTHORITY HOLDPOINT
f7d91a67-a272-4197-8e8d-0f54630bb489 | section | 3 Testing & Completion
2c442a87-89ce-45bf-b6e4-1c7162de4f93 | checkpoint | 3.1 Compaction and moisture content of backfill & bedding material
16c373b2-d9d0-5822-95bb-6cb7444abf32 | note | FREQUENCY: at least 20% of all lots
e1ad2889-36c4-5a11-ac34-0e368df35de2 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 97% using standard compactive effort. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
fe391851-8399-5c2e-9572-346eefeeb60f | note | REFERENCE DOCUMENTS: 701.20a 701.20b
9b5f838b-621a-5eef-a306-eff5ee01c019 | note | INSPECTION/TEST METHOD: Verify
b953550d-d8d3-5252-b98a-b009a0ef26ad | note | RECORD OF CONFORMITY: Test Reports
130ea89a-ada0-5cae-8e98-7b80b5ba873d | note | TP
1d35dd96-8cbc-51e0-8f64-26ec82e601f2 | note | RESPONSIBILITY: Site Engineer
9d7a6472-d551-543e-936d-e542ae46b9e4 | textbox | DATE:
5a2e780b-1529-4075-a09e-ab2bfcad1caf | checkpoint | 3.2 CCTV inspection
97824328-269a-5596-b883-007a2866ea79 | note | FREQUENCY: each lot
5e636c7f-fb3d-534b-a8a7-58282e2a044d | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
0ac26cc6-73de-56a1-82c7-5eb757951086 | note | REFERENCE DOCUMENTS: 701.3
3f392fb1-b327-57f1-9732-cb3ab21e9164 | note | INSPECTION/TEST METHOD: Visual inspection
1ebd5bf8-7dd4-56fd-9445-6cb3d06df3bb | note | RECORD OF CONFORMITY: CCTV Report
730add16-36c9-5613-baeb-9b4df74220a0 | note | HP
10744acb-2309-5cfa-b32a-7a3d1b6c02c1 | note | RESPONSIBILITY: Site Engineer/ Superintendent
d429edc3-0d32-5fab-8952-7b766357d911 | textbox | DATE:
b448b48c-2e31-4c3c-8803-f3dfd18dcee2 | signoff | AUTHORITY HOLDPOINT
704a5078-c0c9-4b5c-a2bb-113d354daaa5 | checkpoint | 3.3 Flushing of pipes
4ae2e3a3-533e-5f30-aee7-d48bc4154751 | note | FREQUENCY: Each line
af6cf473-d8a9-5173-bcb0-3a94be6c98ea | note | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
123c29a7-9732-5b18-a83e-04ff47e36624 | note | REFERENCE DOCUMENTS: 701.28
7a4a2c8f-add3-5896-88dd-d750dc5f5a59 | note | INSPECTION/TEST METHOD: Verify
b51852ce-fdc1-5f2f-b538-79ac165f40bc | note | RECORD OF CONFORMITY: ITP Signed
091159f5-ed65-5789-9cee-300529d63285 | note | IP
24984a62-eabe-53e5-905f-d76d70d19e39 | note | RESPONSIBILITY: Site Engineer
3d175db1-529b-5ed8-8a0b-f22353ba8da5 | textbox | DATE:
dedc6620-dd69-4aff-be6c-1d488c760c2a | checkpoint | Final Inspection
6994517a-b967-55ae-88a7-5ccaea2004c6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b8d53c69-2680-558f-ad3e-905dc3a858d6 | textbox | Print Name:
2bbffbd2-e1b2-592b-9c5a-3fe6f426bbe4 | textbox | Position:
d9336a38-5da5-5b3e-b684-69a06053cab3 | textbox | Date:
ee0102d3-a25b-4c5e-b0f4-d82656a2b10f | checklist | ITP-01-009 - Culvert REV3 |  | ITP-01-009 - Culvert
6c164ea8-d6a3-4464-8f58-5e5bfd0f82f8 | section | 1 - Preliminary Works
fc2ef5ea-1c05-40ee-979b-30e94c6fa8de | checkpoint | 1.1 Check for correct documentation
e5153794-9835-5353-962b-3fa8b6097948 | note | FREQUENCY: Prior to commencing any activity
ddf0715d-de87-5eed-bdd6-4182940dc11d | note | – – – – – – – – –
2a8dfd7d-6193-52d4-8cc7-ee4dc3537781 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
038891a5-687c-5620-9175-f92f6e878b2e | note | – using the correct and complete set of drawings
c8d433cc-b183-58e8-a1e0-800f5cfe891a | note | – all drawings are the latest revision
4d75adf9-6241-56d7-9b44-f54968ece7b8 | note | – – – – – – – – –
38c0645f-d9e7-50b1-845c-93bb0d7611ff | note | REFERENCE DOCUMENTS: Drawings and drawing registers
927032b2-6bfb-57f2-98a7-c3ee4aff97e5 | note | – – – – – – – – –
befdeae6-1a94-5065-94a6-de7e80412f3e | note | INSPECTION/TEST METHOD: Visual inspection
d7746887-0c1b-5d26-afb4-feb989149699 | note | – – – – – – – – –
2f1bf3a9-f82e-5a55-89aa-372a228616b5 | note | RECORD OF CONFORMITY: This ITP signed off
49afc5cd-ca7f-5ead-9bc5-33de64ea92ff | note | – – – – – – – – –
151bce58-c2d1-5cac-ab22-761acc840028 | note | HP*
1c37c7c8-e50b-5fc0-ac43-1505ff74f069 | note | – – – – – – – – –
9c0dad76-05cc-56cc-8b76-9c6275117381 | note | RESPONSIBILITY: Site Engineer / Site Foreman
bff7cc03-069f-5e4e-9a46-13d2a31a8996 | note | – – – – – – – – –
e56d459d-2f5f-5624-a601-c3a2b3cdb4d1 | textbox | DATE:
63ae9438-d0b3-4853-917a-0a5d2536e9e7 | checkpoint | 1.2 Implementation of all measures and controls
c3f8161f-3e70-5945-81ea-a191981f4bd1 | note | FREQUENCY: Prior to commencing any activity
3079b2df-83d1-57d7-ad25-80a1b2a2d47d | note | – – – – – – – – –
4e61fcc5-ed44-5120-88fa-2a93271697d4 | note | ACCEPTANCE CRITERIA:
91cef3aa-18e9-59da-9d3f-5cfcdb82d19f | note | All necessary measures and controls are being implemented, that is:
657f3f66-50ec-5561-b7d6-c3eb2c15c16b | note | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
ef0a3428-c3dc-5d57-87ae-43bf768a4e3a | note | – – – – – – – – –
631c50a9-2489-5f01-b646-b9e6b4e9d9fb | note | REFERENCE DOCUMENTS:
ac8d1d96-8150-5acc-bb59-d62c97f5fab3 | note | OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
8ff4a6ee-d4b2-5cfe-862c-08963434925a | note | – – – – – – – – –
680b6729-762c-512d-95f3-1f9025161982 | note | INSPECTION/TEST METHOD: Visual Inspection
51fb7909-d5d5-50f7-b252-d5f7dbd534ed | note | – – – – – – – – –
9ec5ac24-1792-5a1e-af38-b30f0c6ad2be | note | RECORD OF CONFORMITY: This ITP signed off
8ca4301c-36ee-5261-97a5-95fc58170c11 | note | – – – – – – – – –
799fc19f-7b7f-5957-bbee-73829171bb5f | note | HP*
e0844446-6fba-5e97-ab6a-bd52135cbeb2 | note | – – – – – – – – –
90ed70c3-10a5-558e-9358-c283e0228ba4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
043d4f05-920d-5bc0-b6fa-43ece2a879c4 | note | – – – – – – – – –
099e81d0-86a1-52ca-b52a-47b02e38ec1f | textbox | DATE:
0973c662-741a-4b08-95ac-8fe21436f6bc | checkpoint | 1.3 Precast Materials Inspection
f4926811-bd81-50c6-82fc-b6aec8fc94ae | note | FREQUENCY: Each Delivery
5ac95bb6-4019-5f3f-9ce2-508996b763fb | note | – – – – – – – – –
c78b25fd-a57c-540c-b4d4-ff363d1bf05f | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
c0967e11-7be6-5c1f-92ab-6fb997760838 | note | – – – – – – – – –
42e09c51-b7fe-5bad-a903-85c7770e2d8c | note | REFERENCE DOCUMENTS: 619.08
6dc4e550-90fe-57c7-a51e-67a384df2286 | note | – – – – – – – – –
7f935f77-aa37-572f-97f0-2b3ff9c54264 | note | INSPECTION/TEST METHOD: Visual Inspection
bf5ef881-1e68-5b66-bec8-115986ea5b2a | note | – – – – – – – – –
4825dc10-fbf1-5d8c-8759-0c9aebd802da | note | RECORD OF CONFORMITY:
9a6364ab-2473-55ea-8608-84ddb67b42b7 | note | • This ITP signed
71eaad23-8e66-5cc5-a3ee-9ec0434d9637 | note | • Receival and Inspection Checklist
568ef3bd-dd4c-5f54-9c2d-b85962e8cdb5 | note | – – – – – – – – –
0d112c41-c506-5281-81ca-4db58c0997bb | note | IP
3a7cc7c4-81a6-5cd9-adb6-cb4c87fd8897 | note | – – – – – – – – –
b669c409-8531-5338-a28c-f33477ecc10b | note | RESPONSIBILITY: Site Engineer
fd990dd4-dadf-5dbd-b5d7-bd0989e98ce3 | note | – – – – – – – – –
14ad1f69-4b82-5d2c-bb24-880929300795 | textbox | DATE:
520a2a2f-cbd7-4f09-821d-5b46e76eaae5 | checkpoint | 1.4 Precast Pipe & Culvert Compliance
6e821746-cc1b-5bc7-914d-8f5b2e77cfdb | note | FREQUENCY: Prior to Commencing
ccc760cd-7678-5c27-8c56-2a2c45dd24e4 | note | – – – – – – – – –
6050d451-7f5b-5df9-9b00-e8f01428ee57 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
e3b0e304-878f-5823-ba4b-c76e8b92a3f8 | note | – – – – – – – – –
57da5adf-b6ca-530c-898c-0a70dce36932 | note | REFERENCE DOCUMENTS: VicRoads Spec.
ef36693f-0edb-51b5-a642-cfbbbac7f6a5 | note | • Cl.619
17354fc5-74c7-5ed4-95df-10d1f01917b2 | note | • 701.04
bc643332-c4dc-5d45-87d1-079487a52620 | note | • 701.05
42225f87-cf3a-553b-9a4e-f680eabe4b85 | note | – – – – – – – – –
aa1c3bc0-0298-5345-ae3f-0328268ae90c | note | INSPECTION/TEST METHOD: Document review & Site inspection
69671934-265e-5c64-bc00-2e8d270ae05e | note | – – – – – – – – –
52608022-106b-5192-91b6-8763703694d8 | note | RECORD OF CONFORMITY:
bf565a22-1c57-57f2-8f0d-0472375e78ee | note | • Receival & Inspection Checklist
d4db04d4-8e72-5f1c-8c5e-fedd8e6a1cf7 | note | • Manufacturer cetificate or accreditation
693ac70a-a2b9-5e9a-a608-2e993c2c9edf | note | – – – – – – – – –
8fe8aab8-1a73-5935-96b8-56dc99dd06b8 | note | IP
3f569bb0-4121-5da8-b9d7-87b7b597b939 | note | – – – – – – – – –
4d5b0a9a-7b81-5e77-9aac-65291a9dc805 | note | RESPONSIBILITY: Site Engineer
360f1a09-5c8a-5a50-b20d-6c0d37e09429 | note | – – – – – – – – –
601fa3d7-f8b8-51f2-b871-b1854d9fc7b3 | textbox | DATE:
8d9972c5-bedf-414f-b2ae-60f169580fb6 | checkpoint | 1.5 Bedding material classification
e0a73c46-56f8-574e-b7f5-ba7c6898228a | note | FREQUENCY: Prior to start
191c5aa1-2070-515e-84c1-69e133caf264 | note | – – – – – – – – –
6f3c452f-884d-5d42-a5d2-566d01d542ce | note | ACCEPTANCE CRITERIA:
1d99acf3-1b97-505e-ac36-1a96673c4e5b | note | Nominated material shall be free from perishable matter and conform with the requirements below:
cd25bd9d-3350-5e0a-9419-12e70c0e6dd1 | note | • 100% passing 19mm sieve.
ca012469-a137-5e6b-ae8e-78c806c157a6 | note | • 5%-40% passing 0.075mm.
5ba2b643-e5e1-51fe-b5f4-6f80a2b2b112 | note | • PI = 20 max.
8455dccb-985d-581a-af61-91d5f1cb78b7 | note | – – – – – – – – –
2711eafe-2714-507b-99fd-c7e2949f2ccd | note | REFERENCE DOCUMENTS:
67d92e97-1ed8-5fcb-9749-26b6d0f23ba3 | note | • 701.16
51244bb0-112f-5f0b-9999-12b3a84a4880 | note | • Table 701.091
33deba95-ce43-55f5-8b07-0ceab98f360a | note | • Table 701.092
7cd8ce99-948a-5846-aa6c-4b16062f340e | note | – – – – – – – – –
1ef51a6f-79b4-532a-9d9a-a44c00e7ef39 | note | INSPECTION/TEST METHOD: Verify
137f3df2-5fc3-54d5-9441-7e22376dbb09 | note | – – – – – – – – –
cc323da6-f6f8-5cc7-a78e-983579fa6cab | note | RECORD OF CONFORMITY: Test Reports from supplier
3a6feead-aa70-5ff8-8565-bb75916a9a8a | note | – – – – – – – – –
3bb42575-7a81-543c-b67c-2f7465db8d80 | note | TP
dc7ab95c-e67e-5a6d-912c-9a786bf44297 | note | – – – – – – – – –
d3b89869-a382-5bb1-92ea-41f506221b4f | note | RESPONSIBILITY: Site Engineer
cce1df4d-0aa7-51c6-9e29-c084093f948b | note | – – – – – – – – –
e4adaea1-1e5c-5472-9e30-7ee75cc8a492 | textbox | DATE:
a0a5ced1-a90d-42d3-bee3-d9507edbed3a | checkpoint | 1.6 Backfill material Classification
eb4fcd3e-e17e-5af3-b72b-b31f704add08 | note | FREQUENCY: Prior to start
285155c7-2840-5516-8140-974795001a3c | note | – – – – – – – – –
3b7a34ca-080f-5809-9811-6eba1abb0230 | note | ACCEPTANCE CRITERIA:
d8a1e7bc-3a26-501c-b5ad-712243ac2c15 | note | Nominated material shall be free from perishable matter and conform with the requirements below:
45cdbbdd-3071-50cb-b239-dbf3768aa779 | note | • 100% passing 37.5mm sieve.
e8ebc8ae-aa3a-5895-8d10-b5e8cbf5185e | note | • 5%-40% passing 0.075mm sieve.
3c5f4468-a1e3-5430-9fb7-fe3a1b95dfae | note | • PI = 20 max.
4468ffa4-c36d-5710-925b-3e14e2e12a0e | note | – – – – – – – – –
de2120f5-026b-56ac-aefb-d419239a4185 | note | REFERENCE DOCUMENTS:
00d0aca9-0b38-57ce-9ab1-5a2bb9d43460 | note | • 701.19
1f50c3ec-342a-5fbb-bbf0-cae8f03b6fed | note | • Table 701.091
dfb6d5f1-1f46-5a9c-a799-72832e0a51cc | note | • Table 701.092
d5c9e819-44bf-57ad-b0a1-299783f398cf | note | – – – – – – – – –
33190bda-ecfe-5ceb-96c1-a9413abe441f | note | INSPECTION/TEST METHOD: Verify
1132f3c9-d9ef-5393-8072-5d6417b9cfcc | note | – – – – – – – – –
9415fd92-3e9e-5e7e-9f47-cf5ee90875b5 | note | RECORD OF CONFORMITY: Test Reports from supplier
2cf3a90b-0154-5cdc-adbb-191b6e887d2c | note | – – – – – – – – –
91abd083-1b61-5a41-8b69-bd544669e6e8 | note | TP
ec9db20e-788a-5abd-9d51-b81b0f498fa5 | note | – – – – – – – – –
b5791d16-a0a2-5a3f-be52-747c865655e2 | note | RESPONSIBILITY: Site Engineer
56c03467-2616-53f0-96d5-6414e7d10ae9 | note | – – – – – – – – –
2d845294-29ce-5cce-a631-f7ddce6d3467 | textbox | DATE:
c1941bf1-3b04-4a8f-a286-d69d7f569fe3 | checkpoint | 1.7 Mortar material classification
1f5cb860-215d-5e31-a461-9430a6a13877 | note | FREQUENCY: Prior to start
9f7b3105-8c85-5b4b-b101-4f41e0d88c46 | note | – – – – – – – – –
27573e1b-bfdc-5423-9769-8850f62e4237 | note | ACCEPTANCE CRITERIA:
807cb483-9c41-5a20-96da-dc25f8078ba4 | note | • Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of not less than 40 Mpa. Only whole bags of material shall be used.
e85f5a1d-db5a-5500-b866-da2f975b517b | note | • Test certificates, material data sheets and health and safety data sheets shall be available for all materials.
0fcd433e-efc7-5b32-a175-a627256316c2 | note | • The mortar and grout applications shall be cured in accordance with the requirements of clause 610.23.
c5bc8b52-ed6c-5720-8005-aed7268fc715 | note | • Mortars and grouts shall be sampled and tested in accordance with the requirements of clause 610.28.
894bd7ef-9612-5048-82a4-c5456f4e1edb | note | – – – – – – – – –
cc4e8353-60d9-5cf2-9106-fee7b875b11f | note | REFERENCE DOCUMENTS: 610.33
693edbd8-304d-59f4-9cf6-025fad1dcb4e | note | – – – – – – – – –
6609ac1b-cea0-589a-98bc-747f178117dd | note | INSPECTION/TEST METHOD: Verify
991ab9d1-2208-52ea-9656-1596ab812b50 | note | – – – – – – – – –
255efe01-b7e6-5575-846a-a0b9cc8bfb11 | note | RECORD OF CONFORMITY: Test Reports from supplier
685587b8-8c0d-5111-8114-7ae8b695b04f | note | – – – – – – – – –
a0a1c825-7ebb-5943-abef-cd636d718065 | note | TP
1a57d856-b131-558a-8112-59a7d04a132c | note | – – – – – – – – –
0627268f-e696-54c5-b3b8-e9a08afcfcb0 | note | RESPONSIBILITY: Site Engineer
a172a4f4-14bd-54df-89eb-958ecb378dcb | note | – – – – – – – – –
42402b5a-9e84-51c4-a0b6-d3f7a4e7b4da | textbox | DATE:
3a557cd6-4131-46dc-bfc5-267e270597be | section | 2 - Construction Works
468db5f5-1d8b-48b5-a2ba-46a577f6a47a | checkpoint | 2.1 Excavation Permit
7697090e-fc8a-513d-890c-d4bfff121fe9 | note | FREQUENCY: Each lot
be0dc858-5ce7-5724-8f70-ce049de339c9 | note | – – – – – – – – –
d4ced8fc-96ca-579b-9f16-33be17f27702 | note | ACCEPTANCE CRITERIA:
f6dcda7e-c510-540c-91e8-e4b6062ba44c | note | • An excavation permit must be issued prior to any excavation commencing.
e739b472-5863-5ac4-9ba6-7c160294d6c7 | note | • Plant and equipment shall be appropriate for the task.
a2b56f2d-9093-5154-ab74-c6ecaa295d81 | note | • Excavation operations shall not disturb areas outside the limit of excavation.
49c30960-33c5-59aa-9a68-330a7b2e3023 | note | – – – – – – – – –
e20999e5-d280-5221-bf3f-ba7a39f9ac81 | note | REFERENCE DOCUMENTS: Excavation permit
dc260d78-4cad-5a46-98f5-87e372e99a13 | note | – – – – – – – – –
83a4fecd-aa62-5b31-8a20-b7fbada75a02 | note | INSPECTION/TEST METHOD: Verify
c6f94858-bc5d-5798-8892-9843af551b65 | note | – – – – – – – – –
162ef561-9fe6-59ab-ad49-dce67a9194b0 | note | RECORD OF CONFORMITY: ITP Signed
df4280a5-f125-5129-9298-08e57b2bf0e6 | note | – – – – – – – – –
10438fc8-b3fb-51d8-91db-21b6db501e99 | note | HP*
db5d171e-05da-5d78-ab2c-b4cf547d9403 | note | – – – – – – – – –
5098b6e1-173d-521b-97f5-4f45dd59c171 | note | RESPONSIBILITY: Site Engineer
139b180c-38e3-5260-981b-f51ad55eedbf | note | – – – – – – – – –
a6c4e2fb-c1a1-5978-8f05-bb6f1097cf42 | textbox | DATE:
6649224a-daf5-4564-8c71-96a12cd61594 | checkpoint | 2.2 Review
ce7705d9-d0bf-5d89-9764-6dfa702f9f41 | note | FREQUENCY: Prior to construction
608fc9d0-b5ac-55bb-97de-bd9b92abe1c7 | note | – – – – – – – – –
0ba5f11f-de52-582f-bd8d-adefc49477c0 | note | ACCEPTANCE CRITERIA:
61efe91c-2174-5384-83f0-e68ebff2d98b | note | Culvert construction shall not commence until the Contractor’s construction quality procedure and inspection and test plan(s) addressing all requirements of this section have been reviewed by the Superintendent.
60d4a0ea-d1fd-5192-b1c2-0a2a04e3c41b | note | – – – – – – – – –
eeb1c362-e6ae-5fd3-9e1e-614e22f5a873 | note | REFERENCE DOCUMENTS: 626.02
17ab478a-a3f6-5888-b5e6-996b60da38fc | note | – – – – – – – – –
8230f216-6228-5dfa-9f69-403ce06f491b | note | INSPECTION/TEST METHOD: Visual Inspection
35ef4a75-31d1-5269-8568-285e8eeb96d9 | note | – – – – – – – – –
9a413fb3-e271-5ef5-bb17-c9fe300257a7 | note | RECORD OF CONFORMITY: ITP Signed
38c452db-6128-52f4-88cb-2e0c127e3b63 | note | – – – – – – – – –
2c80aa8b-791d-585b-9ce5-a813569ec023 | note | HP
b855c5b9-c17f-53d4-af95-8156804bca7c | note | – – – – – – – – –
e1dabd91-6fcc-599f-a791-c32ed1acd4d8 | note | RESPONSIBILITY: Site Engineer / Superintendent
96924a0a-b187-5810-8567-6f87ffdb74e7 | note | – – – – – – – – –
1bb1fefb-f36f-5b3d-b560-99a404bbc42b | textbox | CLIENT:
046afce1-ceb3-5b9a-b536-71fe199e1061 | textbox | DATE:
8f5c1ae8-c257-4be5-afec-dc998fff980b | signoff | HOLD POINT AUTHORITY
9fa0012c-868d-40ca-8564-06764775b454 | checkpoint | 2.3 Diversion of Water
53a43e14-80c5-507b-bd79-7580f58132f4 | note | FREQUENCY: Prior to construction
2be80d62-85f6-593a-9b7e-527c93153892 | note | – – – – – – – – –
839c49ab-3ec7-5844-9c35-a5de39158afa | note | ACCEPTANCE CRITERIA:
5a787af8-aa71-5555-a270-2adfe03463c9 | note | Culvert construction shall not commence until water flow has been diverted to the satisfaction of the Superintendent. Pumping options shall not be used.
dd1fc38c-809d-527d-b56c-bec316c51dd5 | note | – – – – – – – – –
edce5bda-26fa-5946-b9e1-e1aa4d7eb130 | note | REFERENCE DOCUMENTS: 626.04
6aa56246-b6cc-5fa9-9c0d-34e7e0fa95d8 | note | – – – – – – – – –
e44dec14-fffa-5177-95af-da0b4fd81fc3 | note | INSPECTION/TEST METHOD: Visual Inspection
8f6c491b-f928-5695-b742-246dafa1cde6 | note | – – – – – – – – –
1237a1da-c8f0-5d40-bc01-6467c13ba6b0 | note | RECORD OF CONFORMITY: ITP Signed
21bb1e09-3fc4-5993-ac34-fe4d3cf01454 | note | – – – – – – – – –
87a321bf-51a2-565b-abde-6cd63484bcce | note | IP
eaebd451-db15-5c27-b68c-cfb6249e90bd | note | – – – – – – – – –
51e18efa-0272-54e5-9fe5-5d94f59ca56e | note | RESPONSIBILITY: Site Engineer
a81052d7-f207-529b-b0a1-95e1da5ff166 | note | – – – – – – – – –
a70540ab-9c48-5f64-ab65-ce35a21d9670 | textbox | DATE:
0f41ae75-53e0-4d17-8539-d4520bcd1e47 | checkpoint | 2.4 Conformity with Drawings
1d5824b8-f2ed-5142-8e58-1b2733e1c92e | note | FREQUENCY: Prior to excavation
fccc0731-a95d-51eb-8641-acd572b7fb8c | note | – – – – – – – – –
5096507a-8d69-5d64-8ffb-527e667bd089 | note | ACCEPTANCE CRITERIA:
23db33b5-2d5c-58bf-a245-7fe3422283e6 | note | Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
35bbdeeb-4dc7-59f5-8500-177dfd4e3e5f | note | – – – – – – – – –
9f15d36d-481f-5bd2-b269-eb7ffc8e78e7 | note | REFERENCE DOCUMENTS: 701.10
ac9013e5-9e06-514c-8b24-74bd95c2f7f1 | note | – – – – – – – – –
22702515-e7db-5e69-b810-beb1b3dd8cd1 | note | INSPECTION/TEST METHOD: Visual Inspection
8fab3197-cfd1-5128-ac57-739fd14f8223 | note | – – – – – – – – –
edd7aa8f-7521-598a-a9f2-cb1465ec2638 | note | RECORD OF CONFORMITY: ITP Signed
040a09c8-aada-5fce-a3b5-5eadd1c1beac | note | – – – – – – – – –
feb5d5b6-dbea-57a9-a335-48219556b260 | note | HP
a9b8f514-1000-5c40-8a14-b6fe5b120680 | note | – – – – – – – – –
54a4f9e9-a618-5413-8477-234d302de824 | note | RESPONSIBILITY: Site Engineer / Superintendent
1970199c-9ac7-5711-abea-bdf0a7faca17 | note | – – – – – – – – –
ee733e24-17ab-55c8-a716-7de56de4cb9b | textbox | CLIENT:
0ce25e8c-bfe9-5b65-89f6-67613cd10112 | textbox | DATE:
4b437a2b-b67a-4abf-998e-2acc1d143c87 | signoff | HOLD POINT AUTHORITY
cd382f45-8af7-4cbd-b5c8-529998ba5e33 | checkpoint | 2.5 Tolerances For Placement
90076b3f-021f-5a0e-981d-7eb79c95e5a0 | note | FREQUENCY: Prior to Backfilling
6ef19c65-1e20-5490-bcc1-4fd10b56d86f | note | – – – – – – – – –
27bfa08e-4010-5077-ad81-5092ed123292 | note | ACCEPTANCE CRITERIA:
c8adb5b5-c51c-5c09-a295-4ede0eaed40e | note | The culvert shall be constructed in the location, to the alignment, cross sectional shape, dimensions and levels shown on the drawings with the following tolerances:
65f40190-6566-5058-b73d-228e2d7caa36 | note | • Grade: 5 mm in 5 m (1 in 1000)
fa6da992-e942-50f7-88f6-09951d847773 | note | • Overall plan position: 50 mm
c0e74976-2872-5cc0-b508-f609e90f70f4 | note | • Gap between adjacent units: 12 mm maximum
d8961b2d-e2c4-5e0b-9326-f32fe790207c | note | • Step at joint between adjacent units: 12 mm maximum horizontal or vertical.
f3b53cf6-1dee-597f-b1f8-d9acb0c81884 | note | – – – – – – – – –
ceb8b140-c855-5d85-9a13-5128e45b3fcd | note | REFERENCE DOCUMENTS: Drawings 626.03
f11a2b6f-cef8-54be-b347-33e409749d98 | note | – – – – – – – – –
03bfb149-9109-5ce0-9f5a-068ff855995e | note | INSPECTION/TEST METHOD: Visual Inspection
2117b549-b1a6-5c10-8610-04135ac87fee | note | – – – – – – – – –
862485c3-0246-5eef-b52a-6fa043c2a1f8 | note | RECORD OF CONFORMITY: ITP Signed
3f5dcfa7-1d9f-5128-8306-bdaec184ce8b | note | – – – – – – – – –
3ae80613-c924-5e8b-92d8-c418146357b1 | note | IP
03dae323-ba18-5b70-9801-1b7cd3519e60 | note | – – – – – – – – –
7e1d9122-e2a9-58d6-a56f-910847e16e87 | note | RESPONSIBILITY: Site Foreman
8c806f1f-e257-57ee-b956-0c5289b250e4 | note | – – – – – – – – –
5168b39e-5991-5976-8fa2-25759ffa76d5 | textbox | DATE:
1de53f71-d555-44bd-98d0-f5a3df1ac1a4 | checkpoint | 2.6 Foundation Inspection
7fb72c1c-c5a8-530a-8043-782abdf48dd3 | note | FREQUENCY: Prior to Bedding
4280eab3-33e0-5ddd-a9c6-feb3dce17f3d | note | – – – – – – – – –
633a81be-4e47-5555-a963-e45570c52314 | note | ACCEPTANCE CRITERIA:
6776508c-e6a8-5d1d-9c42-b78d99a7ee51 | note | • Bedding for the cast-in-place concrete base slab shall consist of a compacted layer of 20 mm Class 3 crushed rock, of not less than 150 mm compacted thickness.
a2aee513-5ae4-5931-9a28-2d94c6d9d632 | note | • Where shown on the drawings, this material shall be placed on 40 mm Class 3 crushed rock spread in layers not exceeding 150 mm compacted thickness and compacted to achieve the required bearing pressure specified on the drawings.
d4c01ac9-1ed1-526d-be9a-46c3aa9d0f20 | note | • No bedding material shall be placed until the foundation or foundation materials have been inspected and approved by the Superintendent.
06f8f640-51c9-54fe-88d9-5ca818282140 | note | – – – – – – – – –
f6b76e37-22a4-5fdc-9492-6d076317d7e5 | note | REFERENCE DOCUMENTS: Drawings
fffb6fe7-9a1e-5820-b7c9-b95bcfde49cc | note | • 812
a768b9ab-08c9-5897-9daf-b9e987acaba1 | note | • 626.06
0128cf1b-ec6e-5a05-9ade-860b3f1d4ad3 | note | – – – – – – – – –
5acd5911-f607-52dd-be98-3be38a55bba0 | note | INSPECTION/TEST METHOD: Visual Inspection
b9dd9501-938a-5c2d-a579-b070bfd19de9 | note | – – – – – – – – –
781eaa0c-ba81-5579-8682-112215796a87 | note | RECORD OF CONFORMITY: ITP Signed
e92d37fd-e02f-5334-9f26-ffd3848b0b82 | note | – – – – – – – – –
a7a46307-28d8-584e-8b1f-0fed560e1f7f | note | HP
91795571-d5e0-5055-8ee2-0dc1a80af5be | note | – – – – – – – – –
00dd1659-0ddb-55f9-84df-b32db72ff2ce | note | RESPONSIBILITY: Site Engineer / Superintendent
6065717b-5ed5-5764-b611-142c6aae1a31 | note | – – – – – – – – –
409306e1-8b53-515f-bcb0-bc8ea37fcb31 | textbox | CLIENT:
4cef1350-dffd-5da6-b2fa-d025ee500c2f | textbox | DATE:
0609c974-96d4-4701-a39d-55c97e9c1927 | signoff | HOLD POINT AUTHORITY
f182e9f1-8084-4aa6-b401-bd0b6cf85f98 | checkpoint | 2.7 Cast in Place Blinding Concrete
f3ed0c7c-c1c7-5f1e-8345-c8ecab3efd05 | note | FREQUENCY: Prior to construction of blinding slab
75e79d0a-08db-5c8e-ad37-b29ed2c5cc8b | note | – – – – – – – – –
74963c30-5ffc-5da0-9650-e6b8bbe796a4 | note | ACCEPTANCE CRITERIA:
0e41fa7c-df58-5600-a534-dde880448253 | note | All cast?in?place concrete for culvert construction shall comply with the drawings and Section 610. Construction of the concrete blinding shall not commence until the bedding has been approved by the Superintendent.
1a8061ba-f72b-557d-811c-8294c53195fb | note | – – – – – – – – –
fbe08d8c-d656-595e-bf14-42690bfc5577 | note | REFERENCE DOCUMENTS: Drawings
2f5aeb83-839a-54d2-a87e-de8efc4affc7 | note | • 610
f9afd9bc-0d2e-5107-b9f2-819724c22953 | note | • 611
ae48d878-33e1-54a6-8574-e46bdcde64c5 | note | • 626.07
736bcaed-4878-5d2a-9884-81548c374b3b | note | – – – – – – – – –
cb97d348-35d1-58f4-9bed-42f26cc9cb37 | note | INSPECTION/TEST METHOD: Visual Inspection
6f975f67-b8d8-5eea-b62c-f46b61683645 | note | – – – – – – – – –
1e03ecd3-9d13-501c-a039-1c6a16228950 | note | RECORD OF CONFORMITY: ITP Signed
7ac80c05-3a36-537b-b15d-36d19e4968fd | note | – – – – – – – – –
f2ae1ef8-ee37-5c58-a3d3-29e7eece8783 | note | HP
ac487e4c-8d61-541a-9b29-1070b2bb07c2 | note | – – – – – – – – –
2994e88d-3a9d-5511-bcad-0188dcfdec78 | note | RESPONSIBILITY: Site Engineer / Superintendent
5ec1d141-86d3-5509-8116-e0f1b50aa41d | note | – – – – – – – – –
81b09079-9f3d-557d-912f-f550781f99a9 | textbox | CLIENT:
1ab8f8c4-a722-5b6b-a70d-f58c4ad984cb | textbox | DATE:
2baaee09-4d32-43b4-9e7d-7d957bb26f52 | signoff | HOLD POINT AUTHORITY
16e85d93-60fd-4c8e-b422-847bb72bf4b9 | checkpoint | 2.8 Cast in Place Structural Concrete
2be0a359-dd57-55c8-8676-63c749598223 | note | FREQUENCY: Prior to construction of concrete base slab
7a226a38-b9f2-5134-a3ab-018379294140 | note | – – – – – – – – –
47c659e2-8efb-54d9-b1c5-986a6eaf42d1 | note | ACCEPTANCE CRITERIA:
37095a9c-71cb-5c52-889e-8a9d87560cb0 | note | • All cast?in?place concrete for culvert construction shall comply with the drawings and Section 610. Steel reinforcement shall comply with the drawings and Section 611.
c3694516-968b-5cb2-ae1c-c4c4bcc8c098 | note | • Construction of the concrete base slab shall not commence until the pre-pour checklist and the reinforcement and form levels has been checked and approved by the Superintendent.
833e6f4f-5231-5346-9186-e84130e25633 | note | • Load Batch Traceability checklist shall be completed during pouring of structural concrete
e189b5fa-af89-521f-b349-694a0e92d7be | note | – – – – – – – – –
3fc2ff56-6ebb-5e84-84ea-48f4199f2a10 | note | REFERENCE DOCUMENTS: Drawings
abee4ca5-4b95-57d7-b398-780c0bce3b4c | note | • 610
7c9a39e6-0fc6-5276-85fa-16ec5a10eb17 | note | • 611
6e80ac37-e8a0-5bf3-b546-3c61358fccae | note | • 626.07
1609fd36-600a-5668-8666-ea7b9743121f | note | • Pre Pour Checklist
3043fe43-b4ae-52d0-87d7-50797096ac39 | note | • Load Batch Traceability
12224af1-ba89-51ea-952e-ac432be5040f | note | – – – – – – – – –
ef68913f-b2c2-50be-a1f7-c36475803601 | note | INSPECTION/TEST METHOD: Visual Inspection
653db63a-e1e5-5c04-8346-90225d169193 | note | – – – – – – – – –
e7dabce3-885f-5ba1-a1ba-257fe8bac3a0 | note | RECORD OF CONFORMITY:
052897d1-74bd-5900-91c6-999f055e115d | note | • ITP Signed
d841cf24-9d34-56c5-9312-881fc204d7b4 | note | • Completion of Pre-Pour Checklist & Load Batch Traceability Checklist
23b7ecd1-af3e-54de-81ca-e338ba7d761b | note | – – – – – – – – –
3e70249c-9e94-53d2-82fa-8b57c6662842 | note | HP
2c30f0c0-4315-531b-a4e7-cd9a9b572fe4 | note | – – – – – – – – –
aa78333f-9492-5487-8088-a2bd2eb10d2f | note | RESPONSIBILITY: Site Engineer / Superintendent
0bddd355-3e5c-5a8e-9cfb-54385e4f9d8c | note | – – – – – – – – –
bf5b22f8-1f62-5459-97a6-c24f48e7ece3 | textbox | CLIENT:
413cedbe-aa3a-54f1-841f-011c0ef07b18 | textbox | DATE:
7801e022-90d4-4a6d-9bed-5b2a6a2ab00a | signoff | HOLD POINT AUTHORITY
af21c4ae-6c68-4de9-a9d3-330c1df970fc | checkpoint | 2.9 Placement of Crown Units
88d041eb-b93c-55b1-9be8-33efa5658609 | note | FREQUENCY: During Construction
7e9c5128-a598-5fba-962b-e2ac425dc998 | note | – – – – – – – – –
7fe22286-7432-5e2a-a73a-bc021a1a6c7e | note | ACCEPTANCE CRITERIA:
050dd8a4-55b3-5763-9c14-9fd1c5231093 | note | • Immediately prior to placing crown units, including link slab units, the surfaces of the bearing areas which support the crown units or link slab units shall be cleaned, wetted and then covered with a sufficiently stiff cementitious mortar to give a continuous finished thickness not less than 5 mm and not more than 10 mm after the crown units or link slab units have been placed.
480a3bfa-2103-559c-ad74-bed800f9e204 | note | • The cementitious mortar shall comply with Clause 610.32 and shall be mixed with only sufficient water to a moist dry-pack consistency that can be displaced to provide an even bearing.
1093b736-4e7a-5cfb-9eab-3f9feec1a8b2 | note | • Cast-in lift anchors shall be cut off flush with the concrete substrate, and recesses filled to the surface with shrinkage compensating proprietary polymer modified cementitious mortar in accordance with Section 689.
01a42bfa-297a-5c49-9722-818dde6b517a | note | • All mortar joints shall be protected and cured in accordance with Section 610.
1ae81821-9f64-555e-8baa-f3c19671573e | note | – – – – – – – – –
0addf087-ec2d-5b12-ad93-f59291cbab47 | note | REFERENCE DOCUMENTS: Drawings
c88f47ee-bd26-5c59-8885-be593c0223f3 | note | • 610
4e358d22-5dfb-501b-ae65-0b1d34d85d57 | note | • 610.23
64f3d5d5-d16b-5140-afe2-7074588a4a2c | note | • 610.16
0eb4af56-b4e6-5fe8-b53e-93aa8e546e85 | note | • 610.32
5029ee4c-ff34-5c68-924c-5ab6a903c84a | note | • 689
19716274-33a4-55cb-95d4-530b6de54797 | note | • 626.08
d5c5f251-78f3-59c9-9895-f16f11c12b87 | note | – – – – – – – – –
fe3ce667-1727-5a72-81d9-a00acf8bf228 | note | INSPECTION/TEST METHOD: Visual Inspection
ce33ec51-07e2-51e9-ab7b-8c87f5c41548 | note | – – – – – – – – –
7bcc7a9a-4771-5bc8-bff6-963eeb5f8152 | note | RECORD OF CONFORMITY: ITP Signed
0e648b02-5bee-530f-a63e-718a684c892d | note | – – – – – – – – –
e7931941-6769-5004-b995-3ffe9899dddc | note | IP
c4c67c33-9d7e-563f-b2c8-1d8b6b570731 | note | – – – – – – – – –
1eb2e46f-3f24-52d8-93e7-2d8450538c8a | note | RESPONSIBILITY: Site Engineer / Site Foreman
fb27d805-9492-5e75-acde-6d4e62473531 | note | – – – – – – – – –
8565e880-49b1-542c-93c6-94816172f143 | textbox | DATE:
0e93cf85-76c7-4105-8948-4f92dd569364 | checkpoint | 2.10 Covering External Surface of Joints
666b1c34-5e2d-5c23-84b2-6176a585e86b | note | FREQUENCY: During Construction
bb4bb84c-2ef2-5f05-99a0-d371044a76cc | note | – – – – – – – – –
aef30ffa-18cc-5f14-a807-05d3419cde4e | note | ACCEPTANCE CRITERIA:
bd92a3fa-255f-5805-a753-fcc30d5a8e41 | note | • External surfaces of joints (top and sides) between adjacent units shall be covered full length with one layer strips of 150 mm wide synthetic nonwoven fabric, factory impregnated with a rubberised bitumen or a neutral petrolatum based compound.
b9785b28-d6f4-54dd-bfaa-79e8e875faed | note | • The fabric covers shall not be wrinkled and shall be applied on surfaces free of foreign matter in accordance with the manufacturer’s recommendations to ensure effective adhesion onto the outer surfaces of the adjacent units.
55b339ea-dff3-59ee-8ac7-ca47ee1d5793 | note | • In the case of multi-cell culverts, fabric covers are not required where the gap between adjacent cells is filled with cementitious mortar or grout which complies with Clause 610.32.
fa8c0d35-b579-5b39-bb0d-cd53e99b1aad | note | • The Contractor shall submit to the Superintendent for review all test certificates related to the supply of fabric cover material at least 14 days prior to commencement of installation.
c21c8cca-1d5d-56c7-b05d-535722786c76 | note | – – – – – – – – –
b693c3a2-9a2b-5e90-a034-7dc6292a7f9f | note | REFERENCE DOCUMENTS: Drawings
677025cd-86dc-5bc3-a6da-4d6bce7a26a0 | note | • 610.32
ae6cba64-0841-555e-8110-a8802804d3e4 | note | • 626.09
94b407b6-b54e-5f93-8774-e156caaba7fa | note | – – – – – – – – –
27c0acbb-bb32-50b4-adbd-0711c57434b0 | note | INSPECTION/TEST METHOD: Visual Inspection
3354533a-1654-5d2f-91d9-0dd6da224212 | note | – – – – – – – – –
56c08890-fe9c-5697-8fe4-fc7e6035fb04 | note | RECORD OF CONFORMITY: ITP Signed
1d941d44-f4fe-5b19-9615-6fc80620ab12 | note | – – – – – – – – –
92b42bd8-bebd-5186-9573-589e31f3dfbd | note | HP
39f9ce31-6711-57ff-9ba1-dff831ea8c8a | note | – – – – – – – – –
06edd7ff-a258-5dff-adbc-dececeb3a739 | note | RESPONSIBILITY: Site Engineer / Superintendent
79a0c193-bd09-5f12-bb9c-6f875dd309c9 | note | – – – – – – – – –
0cca612e-ab71-5629-9d88-310e429957c3 | textbox | CLIENT:
1501a008-53f1-594b-84eb-22fff3cebcc3 | textbox | DATE:
f3cc48de-f67e-4335-af41-610622a1bddd | signoff | HOLD POINT AUTHORITY
b562386b-7cae-4262-9a85-f4bde58b97bc | section | 3 - Testing & Completion
dec519eb-b1b9-4561-9e4e-d972782eb5ea | checkpoint | 3.1 Completion of Post-Pour checklist
16cee703-5bf6-5353-b379-1bb830469b55 | note | FREQUENCY: Each Strucutral Concrete Pour
4dd3360c-af8f-5083-8d99-58707a127fac | note | – – – – – – – – –
5f55a46d-2d93-5603-acca-996b5e0ac236 | note | ACCEPTANCE CRITERIA:
5a698765-ce29-5df5-b35d-e8ca672c811f | note | • Post structural concrete construction, FHC-ITP-009 Post Pour Checklist Rev 2 shall be completed prior to placement of crown units
e0484616-cc32-54fa-b4ca-f26e1e645ce3 | note | • Cover measurement of concrete shall be randomly selected at a number of exterior surface areas using a commercially available concrete cover meter in at least one 3 m2 test area for every 25 m2 or part thereof.
f85dce77-39a3-50de-b75e-2d359b2cd96f | note | • A minimum of 10 cover meter measurements shall be undertaken within the test area and the least distance from the reinforcement to the concrete surface recorded to the nearest millimetre.
033e1672-a58d-5a55-ac9c-0945fb03cb70 | note | – – – – – – – – –
2d22f0e5-7863-5c40-ae24-fb641629492e | note | REFERENCE DOCUMENTS:
93662f5b-eec7-5eaf-9007-a8635abf345a | note | • 610
46bfe02e-c4d7-52d6-8684-7bf992051f34 | note | • Post-Pour Checklist
4f7a47f1-f466-599f-9452-c9d969a7fedb | note | • 610.34
41bcdd6d-c278-5d84-8a7e-518d849775eb | note | – – – – – – – – –
0a1cc085-d2e9-5a99-a9a3-837bf15471dc | note | INSPECTION/TEST METHOD: Verify
d5b52868-1d0d-5c8f-9aa3-4384d7a2df16 | note | – – – – – – – – –
7f725aeb-f3d9-5080-99ea-7d9e7afa6b3e | note | RECORD OF CONFORMITY:
a330c8d9-8ca8-55ed-b319-7f4470c0de46 | note | • ITP Signed
0a0b742b-8f0e-5d85-bccc-dbe0334e694c | note | • Completion of Checklists
b39445b0-e7cd-5acd-9447-28d794b92828 | note | – – – – – – – – –
a21811f8-f8df-57c2-832b-c25a6adb4b35 | note | HP*
7164285a-d661-5e61-bb54-c9cea6cf98b2 | note | – – – – – – – – –
af34cbc9-2b4a-5366-975c-a672d7df139d | note | RESPONSIBILITY: Site Engineer
e36e6c82-590f-5c82-bad7-3474be2374f3 | note | – – – – – – – – –
6a6f18b1-8994-5aa1-9ba4-8e4371cb41f1 | textbox | DATE:
72af2ee9-7240-40df-ba17-168202f7cd9e | checkpoint | 3.2 Concrete Sampling and Testing
af2d1065-937d-556d-99f6-ba9ff50a3bd4 | note | FREQUENCY: Each Strucutral Concrete Pour
f1ba4f26-205d-5cd9-ba57-b42af3266657 | note | – – – – – – – – –
6bf020a8-707a-56b4-964e-c5970d4a1f2b | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for strength and slump
a59cdf86-832f-5e90-85a5-1cb56e06a305 | note | – – – – – – – – –
988f07a6-28b7-5bb4-93f3-64d28ff94dcd | note | REFERENCE DOCUMENTS: 610.16
ae7b71cb-6d2d-50b3-904c-02db93833242 | note | – – – – – – – – –
c2af8336-d5cf-5402-869d-d78135a636eb | note | INSPECTION/TEST METHOD: Verify
1b821372-4f47-5532-93ee-a601a5a00d0c | note | – – – – – – – – –
ea9e3138-9203-509e-9832-a8eca845b777 | note | RECORD OF CONFORMITY: Test Reports
d8ce6e8a-61e7-5997-9abc-e1e779613f04 | note | – – – – – – – – –
aab30722-b2e2-5ed9-90a1-c87026516615 | note | TP
413f2e0d-2faa-5075-8309-7cc03ba83a3a | note | – – – – – – – – –
31c634dd-bdfd-59b7-8a7e-5292aa05df2d | note | RESPONSIBILITY: Site Engineer
35cc0c94-343b-51e7-b379-c7aa70e404d6 | note | – – – – – – – – –
03554921-fc3e-530e-958e-c6b87d94a627 | textbox | DATE:
41e6f917-10cc-42a6-9384-532832c175d8 | checkpoint | 3.3 Compaction and moisture content of backfill & bedding material
d0fb023e-8d58-5827-8e7e-f186b62b09e3 | note | FREQUENCY: Each culvert
674046aa-c742-57db-864b-782f802c2258 | note | – – – – – – – – –
5a7a5835-4472-551f-86af-68d78d759273 | note | ACCEPTANCE CRITERIA:
4ec722cc-ca41-5111-9f7a-1736f48dcb9f | note | • Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested. The calculation of density and moisture ratios shall be based on standard compactive effort. Bedding shall be compacted to refusal using hand held mechanical equipment.
cf396ba8-d1d2-58b7-a977-c847eb16dbde | note | • Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
f5fab73d-965c-5a43-91ca-ee9ba7c834ca | note | • Backfill material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure.
ff1528a2-5d78-5b71-96a4-1fd5844b43b4 | note | • Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
846578af-0e34-512e-9dd8-59b30bf6a6b4 | note | – – – – – – – – –
5098ff29-f98a-5386-b5fb-cf43a4d596cf | note | REFERENCE DOCUMENTS: 701.20
edde5682-eb15-5871-a811-9f7fa5e24759 | note | – – – – – – – – –
8dc62c1f-bf13-52b4-9802-7ba45ebf3ee8 | note | INSPECTION/TEST METHOD: Verify
08796552-3898-57fb-829c-636552561c8e | note | – – – – – – – – –
cc0cf55e-6b19-5958-82ef-962a6035ca29 | note | RECORD OF CONFORMITY: Test Reports
b056aa12-baa8-51d4-b0b3-bf6a8f428844 | note | – – – – – – – – –
0ab665be-b3bd-53aa-80a3-653548b29d85 | note | TP
6ce623a1-c5b3-5dc2-9279-ea08429b1a0a | note | – – – – – – – – –
efa0647c-8c0f-5c40-992d-08086be6f4ad | note | RESPONSIBILITY: Site Engineer
727e8b70-7ac0-59d7-a5b5-3164d016a0c3 | note | – – – – – – – – –
3176597d-a989-53e2-be99-2ebecdb5a653 | textbox | DATE:
44423565-9f6b-44c6-b98c-52bf80046753 | checkpoint | Final Inspection
adf26729-c946-5df2-bb86-eb61dc8fa36d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
945ae3b5-2e7e-5a2f-866d-985364f0f9e0 | textbox | Print Name:
72585c2b-e606-5011-bc0d-e49e87eefbca | textbox | Position:
979a7ff8-5d1c-5b39-910e-80172e69d2a0 | textbox | Date:
b3601173-0b4b-472d-8149-81f80239c6be | checklist | ITP-01-012 - Hot Mix Asphalt | itp | ITP-01-012 - Hot Mix Asphalt
5b175352-ad03-48ee-a292-f5f1b6456d53 | section | 1 - Construction Works
124659e2-2522-4397-9f2b-6de9dad005fa | checkpoint | 1.1 Submission of Mix Design
29c094a8-404c-5312-a4a0-650e0ed1ad74 | note | FREQUENCY: Prior to commencing paving
ecebaf28-f3fe-52eb-86ad-c37787e4cdf7 | note | – – – – – – – – –
1147c0df-2adb-5391-9f16-1e00438d725b | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
60a791e5-71eb-5f83-a11d-b2bd3a7cedb5 | note | – – – – – – – – –
1238611f-ec76-5ae8-9c69-e8b05185f611 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
d047e967-812b-5e1b-8d96-daf1468619a3 | note | – – – – – – – – –
307c29e2-45c6-59ef-80d8-b8115c27d51d | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
9c81cfcf-df65-5c39-adad-d2d1dcca094a | note | – – – – – – – – –
37bef21e-49a7-5135-81d4-542abf9db240 | note | RECORD OF CONFORMITY:
927eb6e8-b96a-517d-8402-7eb929d8caad | note | • MRPA approval
70a3d10b-974a-5970-807e-a6218b76b3f5 | note | • Completed ITP
c0606a78-2ff0-5f74-80cb-8e0a21e373ed | note | – – – – – – – – –
3bf26433-1467-50e1-be3b-4e0078a20867 | note | HP
ed69b949-899b-58ad-8b97-9e273ba3e8b7 | note | – – – – – – – – –
99990c82-a914-5f6f-97a3-8aedc84709b3 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
480abe43-67c9-597a-b440-108ed320edb6 | note | – – – – – – – – –
fc409ad2-76df-5ed8-b036-b570f909e0da | textbox | DATE:
0a3cdb90-b668-4921-9646-7d7a03d984cb | signoff | HOLDPOINT AUTHORITY
ad626b2c-c240-47ae-bfdd-27719f1d8709 | checkpoint | 1.2 Implementation of all measures and controls
a4e8c951-4f23-5a61-adfd-daf9da815573 | note | FREQUENCY: Prior to commencing any activity
017521df-703e-5a7a-a8eb-72142d4ba42d | note | – – – – – – – – –
c9f1f38f-2867-5095-83de-0aefd516b247 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
e23edcb3-dc3d-5370-95f3-cafd01f9b489 | note | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
2131e201-0439-5afe-aa53-14bd48a35b2a | note | – – – – – – – – –
8d1ff110-7418-5b9d-87a2-31ba8065d4cf | note | REFERENCE DOCUMENTS:
cc86e8de-d81c-591b-b407-7f0ce2b34ce2 | note | • OHSCP
30d993f6-b572-5eb0-948c-9017ad713c24 | note | • PHSCP
121a1329-7f21-575e-9563-38f7faba8692 | note | • PCMP
70c449dc-e5e2-52b6-8871-9d7100362750 | note | • EMP
b7abf7ea-c3b3-5075-b9d0-5972dfe41c80 | note | • ECP
2f53a8a1-d655-5297-a1ae-b9080cc2da86 | note | • CEMP
1ca87cb8-fa53-531a-9c54-2704a52e9164 | note | • ERA
ab31b3f4-d2d7-5e49-ad64-701d6ff85bf8 | note | • QMP
86e4d363-8ff8-5529-bb4e-a2ecd6a05986 | note | • CHMP
0e2b15e5-be87-5a78-8527-eccbdde640dd | note | • SWMS
b4352b1e-84ad-5a7e-845d-d003ed7aa34a | note | – – – – – – – – –
b10095a1-6ad0-5391-8ef6-24a596fc4c16 | note | INSPECTION/TEST METHOD: Visual Inspection
54e68e64-837e-5110-af9d-5dfc623d0f56 | note | – – – – – – – – –
e377576a-41b1-5d46-9519-95216326fb7a | note | RECORD OF CONFORMITY: This ITP signed off
ef15d565-a98d-536b-8747-42ef8960da0d | note | – – – – – – – – –
50a867ce-c14a-5d1f-8161-18aa68640303 | note | HP*
30b148f6-bb56-5716-a6b4-ad274bd9a49f | note | – – – – – – – – –
ab88e507-552a-5dce-85fd-ba62e5f5ff17 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ba4e5383-1819-52ea-a1f7-0c8719ee9d10 | note | – – – – – – – – –
0314c7ab-eee5-51c1-82d4-cdff9753fab4 | textbox | DATE:
a160a4c6-d3a2-4173-953d-dd8c7480c893 | checkpoint | 1.3 Site Inspection and Base Condition
4099f398-61b7-5fad-a7b0-f707aa973b72 | note | FREQUENCY: Prior to commencing paving
ff73b72a-d82e-5f46-be07-988ad5f4cec4 | note | – – – – – – – – –
9190e90d-5c14-5efd-af15-5e695e941ffa | note | ACCEPTANCE CRITERIA:
ed045819-1e09-5f1a-ad13-3244730d4d19 | note | • Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
c2c6e985-1e2f-5235-a07a-c830208ffaee | note | – – – – – – – – –
cf05f1f4-78e1-58ef-877d-ceb131862590 | note | REFERENCE DOCUMENTS:
ab89485e-dcf2-5c27-8a61-c04c2a960b2e | note | • 407.17
b8a14d9f-861d-53da-acf2-21c7a3a2ca13 | note | • AS2150 10.1
4233d27a-9bf4-5594-a023-00eff9746dbf | note | • AS2150 10.3
2f486abb-838f-5d39-8717-d20f8e5763b5 | note | – – – – – – – – –
79537f51-5609-5886-bbe7-a4ad8ed46e82 | note | INSPECTION/TEST METHOD: Visual Inspection
8a0a6391-9caa-5765-a23c-b439a5066860 | note | – – – – – – – – –
e653011e-2b93-5146-960e-4561244a3af6 | note | RECORD OF CONFORMITY: ITP Signed
1f6195a1-0fc4-5ffc-8717-2944d91d4e09 | note | – – – – – – – – –
10a8159a-07c0-5787-a684-a4cbd570179b | note | WP
787e3736-9b0d-56ef-b3ef-210d5da7d2b8 | note | – – – – – – – – –
3c19aa79-f438-5bf0-9269-d3eed8967ffc | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
8d19fef3-aecb-5700-b18a-4a4b1bfd42e2 | note | – – – – – – – – –
6c19f76c-5ac6-5c19-acc5-50a4699f4ace | textbox | DATE:
08411941-0a27-4ad7-9cd6-e07f7676df0f | checkpoint | 1.4 Ambient Conditions for Placing
7f6da20c-12ee-5d9c-a8ab-0e77b8acc595 | note | FREQUENCY: Prior to commencing paving
b6c3b06f-00da-5dd4-bf31-f273cb6e8016 | note | – – – – – – – – –
e85435ec-31f1-525c-aff1-cbbf9c90f754 | note | ACCEPTANCE CRITERIA:
fe3170b6-08a9-5b6c-a40b-6d7a496079dd | note | • The majority of the surface area to be paved has a temperature greater than or equal to the following:
4f184351-0a8f-5c75-9c8d-4806dc365d0b | note | – Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
aaaf0ddc-9731-5c9a-9305-945aab8a3a76 | note | – Wearing Courses: 10°C for conventional binders or 15°C for PMBs
1165f871-705b-5ba9-bdb4-fe7f65e45005 | note | – – – – – – – – –
acec990c-12c5-5aa8-93df-faa0fdec0562 | note | REFERENCE DOCUMENTS: 407.13
046df9a6-a24d-524a-a35f-72b9d9e71355 | note | – – – – – – – – –
000d543d-f698-50ea-839e-d0b21c72816f | note | INSPECTION/TEST METHOD: Verify
cb9735cf-021a-5906-8500-5361613aea2f | note | – – – – – – – – –
bf35bc6a-0eb4-5894-aad5-08687378dd18 | note | RECORD OF CONFORMITY: Thermometer
3c623bb7-e59c-5d0e-a5aa-0479e23603be | note | – – – – – – – – –
38bdf6f0-4309-56f0-8b49-f74d3b91a5cb | note | IP
da62ac24-0673-5fe0-9a1f-cb134c45b03d | note | – – – – – – – – –
7c2b3baf-a9db-5723-978a-2cb323fd8383 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
8ec77be3-bbff-5fb1-8f35-3c723a2849ed | note | – – – – – – – – –
a968eed0-e483-5cad-84ef-252df1dadb25 | textbox | DATE:
39227127-9f8c-4695-ac20-41adbfffdecc | checkpoint | 1.5 Planning of Joints
f97a7412-d135-5c3c-bb25-0497fb8ccdb0 | note | FREQUENCY: Prior to commencing paving
aa9bf2f8-8c05-5741-bc67-c72b2e95cb5b | note | – – – – – – – – –
de0b4d98-1162-5fda-9d28-52356337c90e | note | ACCEPTANCE CRITERIA:
e6916dd4-2c34-5717-830f-75ac2ee29577 | note | • Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
ca2eb065-2f4f-54ef-a987-4ab694293e09 | note | – Transverse Joints Offset from layer to layer by at least 2m
3aac72d4-247b-5bf8-bc34-4a1a8e919975 | note | – Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane.
1d064512-9e4f-5332-8b2b-ea64d5df1cf0 | note | – Wearing course shall be on lane lines.
f861fd24-8e2d-5dc9-b65c-3ac585b3074c | note | – – – – – – – – –
0fd6a3a4-6e39-5d72-a33f-c47d2e5a9b96 | note | REFERENCE DOCUMENTS: 407.21 (b) & (c) Pavement Drawings
4f816a54-cf60-58b0-9693-03667172d408 | note | – – – – – – – – –
5e8e17d5-9be5-578d-a852-040abddeb1d1 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
24c3625f-27f8-5977-856e-b28228f37ecd | note | – – – – – – – – –
18e07dd6-bbe9-5645-b2e8-2b41f850f575 | note | RECORD OF CONFORMITY: Paving Plan
e1e03208-61c6-558d-8282-e164cb8a8ba6 | note | – – – – – – – – –
f2eaa9a1-c467-50a2-a304-1bcb8bdba43c | note | WP
dc253646-3bc6-5e25-a8bf-8dd0f3e2c0fb | note | – – – – – – – – –
7dbe5b6e-f0de-54f6-adda-ab13430f4c39 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
3d03fe0c-6e37-5b4a-a71d-fbd5f49b4689 | note | – – – – – – – – –
f94a1f41-1479-5009-b706-d6bcb8d25db1 | textbox | DATE:
78c915d4-4630-408a-b1a5-2f8f5b4c94f6 | checkpoint | 1.6 Longitudinal Joints with existing Pavement
5d09c24b-3ca0-5ff0-8197-ca7a3a0c6bda | note | FREQUENCY: Prior to commencing paving
abac7761-bef9-509e-9189-bd477ed96309 | note | – – – – – – – – –
b33dde71-b865-52ed-9617-657d23510b2a | note | ACCEPTANCE CRITERIA:
d71b377b-50c9-5045-b989-eb4a8103c3d5 | note | • Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
c81b16e9-5f56-50da-8667-e6398789efd0 | note | • Depth of step to be cut to the full depth of each indiviual layer.
bd0e0995-e422-534a-ba8b-7a0affc943c0 | note | – – – – – – – – –
232081c4-95db-5f17-abc0-d8214ac72e6c | note | REFERENCE DOCUMENTS: 407.16 (c) (d)(vii)
ea6c0470-4301-5e37-bf34-d470249d100c | note | – – – – – – – – –
22478e3c-75ac-5298-a6f5-3fae27ce1273 | note | INSPECTION/TEST METHOD: Visual Inspection
72174e3c-1230-5c70-ac95-e41901568a83 | note | – – – – – – – – –
63ddfcab-6156-5a3c-898e-17be43e8128c | note | RECORD OF CONFORMITY: ITP Signed
a8425320-a6ff-54ed-986e-483cb252667d | note | – – – – – – – – –
9830bc41-a6aa-5c89-ab65-f460845c5930 | note | WP
7295b59f-f29e-5a3b-9ab3-f1f4a1df657e | note | – – – – – – – – –
01d18cf6-7402-5a04-9253-85b2f70c9b5a | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
a01bf22a-875c-5fa3-be52-39f7e05677ce | note | – – – – – – – – –
38344a7f-83b9-55b0-b437-8398113147f9 | textbox | DATE:
cfd41798-9ff4-4553-826b-48cc9b30aa14 | section | 2 - Asphalt Placement works
cf85c623-fe57-436b-9a82-119f8425b302 | checkpoint | 2.1 Tack Coat
2ac593d0-1c9b-5544-b930-ef646016a1d0 | note | FREQUENCY: Prior to commencing paving
3a86475e-9d8a-56a9-94ac-74b94e610a44 | note | – – – – – – – – –
4c9f923c-cc50-5868-baf4-4018cf3af09b | note | ACCEPTANCE CRITERIA:
b8bc9ae8-8ecc-5868-bb00-3748e8234373 | note | • Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen) or 0.30 to 0.60 litres/m2 (30% bitumen content).
a0a07183-a9a9-5b67-adc3-a159a318e8bc | note | • This rate is to be doubled on joints and chases.
f0ec3cae-a785-5fa9-b764-cf9a666c90f5 | note | • Tack coat must be allowed to turn from brown to black before paving.
210695fc-fac0-58b4-8062-f2e81c4a0f72 | note | NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
920c9c0b-d010-549c-8b22-e232fd0d3ebc | note | – – – – – – – – –
820bb96e-c5c7-5ed6-a22d-944d5ed67b03 | note | REFERENCE DOCUMENTS: 407.15 AS2150 11
fb596147-04d3-517b-92b9-4ca327df2da5 | note | – – – – – – – – –
4248a05e-230a-5646-9c5a-5110cf426046 | note | INSPECTION/TEST METHOD: Visual Inspection
39fe2cfb-397d-51f3-8fd9-209b34ce04d3 | note | – – – – – – – – –
aa9e6ce2-96cd-501f-9e82-53c9837cc079 | note | RECORD OF CONFORMITY: Spray area
ae7ebfcf-434f-5249-a899-9f42e484ae37 | note | – – – – – – – – –
c4f20083-d2f1-5908-af39-116020bbe5b3 | note | WP
ef865534-7bad-50dc-a0e8-a00296585654 | note | – – – – – – – – –
64edf6da-e346-522a-b0e2-0ed482cb77c1 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
1f4dcf59-85af-527a-b9df-aa792ece5167 | note | – – – – – – – – –
0a141965-1b9c-5bdc-9a85-473020199ac7 | textbox | DATE:
f0dfe34d-c63f-45d0-84b6-fa8188809de5 | checkpoint | 2.2 Commencement of Placing
ae4c52b5-b282-5a69-941d-dd2494d75282 | note | FREQUENCY: Prior to commencing Paving
9b300790-9afc-5737-901f-8882cd8ec8d7 | note | – – – – – – – – –
470f1f1c-7296-5767-9827-057733cc00fb | note | ACCEPTANCE CRITERIA:
a2b5a434-4dff-5434-b74c-c39aacd47d84 | note | • The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
45943bbb-89f9-50a1-aa85-9d4fae224f20 | note | – – – – – – – – –
6770f80c-9323-5db3-9a0b-7b6dce1d12bf | note | REFERENCE DOCUMENTS: 407.18
64e58e8d-f407-57ba-b8a0-fe9ab85c55d4 | note | – – – – – – – – –
971ef63f-e702-5e6d-b445-17255fee1783 | note | INSPECTION/TEST METHOD: Visual Inspection
4388cb5b-4e04-546f-bd4f-069a387734d9 | note | – – – – – – – – –
ec49e5a6-3b43-5cc8-9d06-488db3b5fcf0 | note | RECORD OF CONFORMITY: ITP Signed
5ea4ac3d-e3f2-50a9-a864-8aa4b83cae15 | note | – – – – – – – – –
bce88dee-8d81-51d6-9210-ec9c4ea1fed7 | note | HP
6bd93787-7fdb-55f5-bbc9-403a9c273b93 | note | – – – – – – – – –
97b522fd-f53b-5004-9579-67a78ccd8a65 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
937a3114-49ad-5dc9-ab15-bd46b8f1a590 | note | – – – – – – – – –
ca3bb27c-db2f-5359-b748-e9fdcd5d03d0 | textbox | DATE:
4f871f9d-0bcf-4005-8773-4dc0b56a0dcc | signoff | HOLDPOINT AUTHORITY
ec2abd08-ae57-48c1-b2ba-a32fda59b843 | checkpoint | 2.3 Mix Design Confirmation
b1a90fdc-7fe5-51a4-af0d-ec6022b48f3f | note | FREQUENCY: Each lot
948d0982-cb21-519e-b03e-f5367eb45b2e | note | – – – – – – – – –
2985d26b-d852-5baa-846f-d4159c719c5e | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
4cc05292-2b07-53f6-866f-d21666e77c8b | note | – – – – – – – – –
6ef74c61-7802-51fb-b133-1b26a5918a57 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
7fb313ec-1e86-56da-a0be-6dd5f661ccea | note | – – – – – – – – –
83231ca2-7e56-50b0-81fd-899187ce0582 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
fca36186-6ae8-5745-b396-47dd93f27239 | note | – – – – – – – – –
16c57ab5-588d-5032-9e98-8016f60c60c0 | note | RECORD OF CONFORMITY:
514619cf-07f2-5813-8b8b-4422f5e76dbe | note | • Delivery docket
13dd8a8a-43b8-5c7f-a8e7-478980acfd4a | note | • Completed ITP
09ff9ea8-b7d1-5e82-a38c-a376faeec737 | note | – – – – – – – – –
221b2a01-870b-5697-a007-16997d73d735 | note | HP*
d5a54bf0-1c8b-5298-8a4e-87811beaf6d0 | note | – – – – – – – – –
1c7c58bc-44b0-5600-ac0b-4c4f19c34926 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
f06f912d-bccb-5bb7-874a-f8e856a29526 | note | – – – – – – – – –
1ed2b114-b507-5034-900f-9aba74681ed4 | textbox | DATE:
0d9df416-f508-4f7d-b717-c52521ba761b | checkpoint | 2.4 Delivery of Mix
9b0096c1-a3e3-5fd7-87fb-36bc281ba21f | note | FREQUENCY: Each load
2ac33532-ea11-5f19-86d2-08775c1a4f99 | note | – – – – – – – – –
e297552e-3144-5007-ac7f-462868b38186 | note | ACCEPTANCE CRITERIA:
c7e0126d-801b-50ec-81ef-cf0fd7b51903 | note | • Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
5250ae33-d044-5a3d-910d-bf932c894344 | note | – – – – – – – – –
f568248e-4a3e-5671-84af-3e7a13333d13 | note | REFERENCE DOCUMENTS:
506c05d8-d435-57cb-bd7f-2ceb86b39bf1 | note | • 407.16
85d2b4a1-7add-5434-b955-f3b4e2844742 | note | • Table 407.081
b18ab978-6d59-5cdb-a96d-76136bd4b2bf | note | – – – – – – – – –
268ec61f-af5f-50b4-bb2a-930e8869c219 | note | INSPECTION/TEST METHOD: Visual Inspection
641da8d5-0955-5922-8e1e-918d4640d0c2 | note | – – – – – – – – –
0df4d4cf-c6c7-5589-82e8-356b5e05557a | note | RECORD OF CONFORMITY: Delivery Docket
362f87d0-664c-5084-876e-bac5a8deba2a | note | – – – – – – – – –
71e4ab62-ec85-520b-932d-9d162d3ded4c | note | WP
06848562-5daf-539f-be7b-96a69318fb7e | note | – – – – – – – – –
c4c261d0-e546-5a59-aec6-fa8440c11832 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
e1cc8183-f8e8-5c40-9576-ef0b1cc2e498 | note | – – – – – – – – –
8717af4d-a720-50b9-ab65-388b20e5b6b5 | textbox | DATE:
6c6b6409-27d9-4ab8-99a8-817cb14cf042 | checkpoint | 2.5 Traceability
9a9977fe-eec4-5e62-b413-de06a0aec06b | note | FREQUENCY: Each lot
192af297-96a1-5032-8b93-366ddf7529a6 | note | – – – – – – – – –
449191a3-1cfd-5ba8-a0f2-acf0686659b8 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
21e8e4d1-dde2-5f18-a90f-fc7149d603dd | note | – – – – – – – – –
f0ab6691-8fef-5ad5-9ea8-178cacb14179 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
366fb0df-c48b-57e6-86a9-00c92e2c5db8 | note | – – – – – – – – –
dff37805-9399-50e4-89c7-6df46eb5630a | note | INSPECTION/TEST METHOD: Verify
f1e43f5c-2949-5fd6-86f8-260658b6be00 | note | – – – – – – – – –
bb5d1784-067f-50c7-aec1-333c5f930b2b | note | RECORD OF CONFORMITY: Daily Lot Record
cfb1d076-16a9-5901-90a9-5cda8af42695 | note | – – – – – – – – –
ae7acf06-1a28-5125-acb9-6aa4ba44f36c | note | IP
4b581fa0-afbf-5ad2-8d1f-1e6fc2d29b6d | note | – – – – – – – – –
d2e505da-4baf-57dc-95ce-6ed22f4cff1c | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
3265b962-002f-56a3-8bab-781136dca1c2 | note | – – – – – – – – –
af4764f5-edc4-5fbd-97c4-62fd1bc8aa3d | textbox | DATE:
1750c992-50d9-4804-8061-ac695b31c1d1 | checkpoint | 2.6 Layer Thickness and Level Control
c52646a4-5b69-5d87-bb0c-f440ebf7a4ae | note | FREQUENCY: Regularly during paving
20735ae3-28cd-5957-9782-36b5018cd79e | note | – – – – – – – – –
65cadb53-1c9d-51ae-9697-d133256ab74e | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
029ef6e4-4540-5c2b-b7ab-2f194aea0daf | note | – – – – – – – – –
47eb312b-36a7-524d-be9d-90c6200aae95 | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
836156c5-9eb6-5b53-b9f2-7148b78af849 | note | – – – – – – – – –
8e446fc4-37aa-55bd-b555-ca1f987b98de | note | INSPECTION/TEST METHOD: Verify
e2c88ee5-11d5-5cbd-a9ed-2199fb29ed3d | note | – – – – – – – – –
de0f8d83-353b-5732-be9d-cb019355cb02 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
dc8b6fa8-0614-5efd-b917-b60072a6fefc | note | – – – – – – – – –
b69844a3-fb31-5ad5-9389-4d9dfb491964 | note | WP
e3cc4e85-e873-5f54-a57c-a5a89b283b80 | note | – – – – – – – – –
99b11939-7d55-57a6-b802-9f169dd5476d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
8b4faf43-22ce-55c7-a803-e7e5fd860ba2 | note | – – – – – – – – –
55dfcb33-7c09-575c-ab4f-0e8cba14a701 | textbox | DATE:
5b51c042-1f01-4608-a0e1-8353a1336ed6 | checkpoint | 2.7 Paver Stoppages
e77d0086-99da-5c76-a3e1-a15d7b883f5e | note | FREQUENCY: If paver stops
489f1cb8-4c1e-53a4-b25f-2b7901f00a5e | note | – – – – – – – – –
9a909073-d872-5f8c-9253-0e1ee32ce8f9 | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
fad8bcff-36ed-5ca6-af9a-df70393a17ae | note | – – – – – – – – –
4acde0be-34a8-50f0-9b97-1300003fc7e5 | note | REFERENCE DOCUMENTS: 407.20 (c)
ba1bf981-8ee9-5fe9-b11b-c73b9816933a | note | – – – – – – – – –
d922c564-747d-592c-900d-4a377490744e | note | INSPECTION/TEST METHOD: Verify
e8a7fa59-8c63-5f08-a51c-bacd70ec8a56 | note | – – – – – – – – –
3fbb8817-405e-5791-819b-c0c8cfc26396 | note | RECORD OF CONFORMITY: Thermometer
c2d1f610-da98-5406-bb2b-8562e25a7d7b | note | – – – – – – – – –
98e4479d-0df5-5d68-b68b-7569ff06d365 | note | WP
f8d13a30-1cf5-5cf8-a5b3-3c318a2d089f | note | – – – – – – – – –
ecdfda5d-a43e-5dc5-9ac4-a2c089f5b0b4 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
f8739933-4085-5c15-bc73-431521368cac | note | – – – – – – – – –
9db3ade3-2961-5078-b4a2-247ba89ff2c7 | textbox | DATE:
0649d62b-1db1-4fdb-a727-59cb0e351769 | checkpoint | 2.8 Surface Finish of Wearing Course
962fab3e-9cfe-58f4-81db-cc4dabc3ea7b | note | FREQUENCY: During paving and after final roll
8914b5cf-56da-50b2-a561-ba762c8db8c2 | note | – – – – – – – – –
92962b22-56b0-5005-88ea-ae5bfd10d710 | note | ACCEPTANCE CRITERIA:
8ecd2f6e-a40d-565f-b7ac-2fecd2945a59 | note | • The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
b8229173-1f90-5ee5-9407-679d2c1278a6 | note | – – – – – – – – –
c905dcc3-00e4-5074-8552-dbf74138c419 | note | REFERENCE DOCUMENTS: 407.23 (a)(i)
f2d38afd-fa05-5f54-8d1b-3e35168501dd | note | – – – – – – – – –
430a0ce1-ba4f-564f-a96f-e48b446c0338 | note | INSPECTION/TEST METHOD: Visual Inspection
5dd61b96-7696-5307-8b4b-80c9cc6175d4 | note | – – – – – – – – –
f71061c9-b2d7-5c90-8b54-f35bfaab68d7 | note | RECORD OF CONFORMITY: ITP Signed
b3e84c50-5394-56ff-8b03-703c5d7ff795 | note | – – – – – – – – –
b7f90d44-3ae7-53ca-972a-65532f9b5eb5 | note | WP
3c92be2c-1e65-5a6d-953c-6b0bb6d1db2b | note | – – – – – – – – –
109155fe-812c-5917-81c2-f8b3f359c5d5 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
e777e637-ced8-5734-966e-d3865c74928a | note | – – – – – – – – –
75c093e6-d76a-596b-8160-da9a7509cd34 | textbox | DATE:
4b96a2e5-46b6-448e-8608-2979f87f3931 | checkpoint | 2.9 Kerb and Channel
12616377-eaf2-5d2a-bfe2-c761578e7a45 | note | FREQUENCY: During paving and after final roll
1488424b-263c-513b-8e06-94d2f65a0cdf | note | – – – – – – – – –
3d55be65-7703-5cc6-8ba5-1541d0d6b1c5 | note | ACCEPTANCE CRITERIA:
4d8cc7a8-c541-5c36-871f-c9de48335c2b | note | • The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
da1df541-f9ae-5d3e-b698-63625c810c29 | note | – – – – – – – – –
90f4d489-207d-50d6-95c2-d2aa3327de73 | note | REFERENCE DOCUMENTS: 407.23 (a)(ii)
af580426-68da-5f75-8950-0ea232ca416e | note | – – – – – – – – –
3d3b397e-7e5c-5a66-a93c-eb1539b02a73 | note | INSPECTION/TEST METHOD: Visual Inspection
41e7bdee-095a-58cc-b6b2-1ce4c61e5c86 | note | – – – – – – – – –
57eaf075-ce11-5c30-a934-467e67b2a60c | note | RECORD OF CONFORMITY: ITP Signed
d6784e13-0a8d-5575-8a2c-0431ff2202e6 | note | – – – – – – – – –
1dbae8f9-a887-53e8-8767-42b6e9ee8934 | note | WP
debe36b2-1366-5489-9f5b-700b7d231dc3 | note | – – – – – – – – –
4cd0a94f-6552-5801-84b0-76b081d043cb | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
4d08956e-4cfa-5540-9e22-211a5323f740 | note | – – – – – – – – –
912fd61d-677f-5069-aa08-51a12159b0f0 | textbox | DATE:
cbc86023-3055-40d1-885c-6bf239cf545e | checkpoint | 2.10 Alignment of layers not placed against concrete edge
cab7b0db-cacd-57fd-a70f-337d3150131a | note | FREQUENCY: During paving and at completion of work
45e5a546-7f36-5436-9a74-dbdda8f68bd8 | note | – – – – – – – – –
23b02e64-75b9-5d8e-b2e7-85b4df119749 | note | ACCEPTANCE CRITERIA:
b9e1ab42-c3cf-59e5-a006-6eba5ca65c42 | note | • The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
0722c5f3-7e24-5dd0-9a13-035f759dc1a1 | note | • The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
b2b3d865-be84-5292-bfff-6385eeb1cb28 | note | – – – – – – – – –
bddd90fe-c2c3-54f1-8d70-a80424c7b1e9 | note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
e1a298c5-8bfa-571f-94c0-010e2c4536ff | note | – – – – – – – – –
63ed1202-efb5-5a5e-9fd4-fe9db0e1ebcf | note | INSPECTION/TEST METHOD: Visual Inspection
dd76f99a-4367-5384-8d3a-0cbb7ca45615 | note | – – – – – – – – –
7278f38d-fe21-5db2-9db9-e660222d353b | note | RECORD OF CONFORMITY: ITP Signed
db331731-133a-5ed8-9f46-be9852bf8bd0 | note | – – – – – – – – –
776ad9d1-37c8-50fb-8098-099abbee28f0 | note | IP
baef90f1-2c7b-5b17-a20f-40a875f97cf2 | note | – – – – – – – – –
f702eab4-c8b5-5f3a-96ab-0765a6012863 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
ce932a8a-66f4-50aa-8adf-8014b627f661 | note | – – – – – – – – –
3a6282ee-8437-58d4-975d-7807bb85ee85 | textbox | DATE:
50252096-5703-4e08-b6f2-f8f38f1bd25a | checkpoint | 2.11 Width of layers not placed against concrete edge
6995c208-cd3c-54c0-beef-fe6d89024ee5 | note | FREQUENCY: During paving and at completion of work
244cfd20-3a30-52ec-b3a9-89057db4e66a | note | – – – – – – – – –
73307bbf-2be2-5a56-983f-6d6baa9a047e | note | ACCEPTANCE CRITERIA:
c55f2aed-4be9-5be8-83db-17427940dade | note | • The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
ff24132d-520e-5470-9a58-b977596fed9d | note | • The average width over any 300m shall not be less than the design or specified width
55df1c9c-3351-5691-af30-79974e701505 | note | – – – – – – – – –
98b18398-4c9a-50c3-9f6e-7eeb6eb69a2f | note | REFERENCE DOCUMENTS: 407.23 (a)(v)
0b78c962-1522-51d0-9d95-675581313759 | note | – – – – – – – – –
932c5c91-ad25-51a6-8ff4-3fa2a4735e60 | note | INSPECTION/TEST METHOD: Visual Inspection
46c96186-a5b9-5c68-947a-b0d27936c40e | note | – – – – – – – – –
7a8c8c25-5557-5204-840e-3942fcdede00 | note | RECORD OF CONFORMITY: ITP Signed
2d0ba386-99f5-5359-96c4-e3ba35543a8b | note | – – – – – – – – –
bc055fab-614c-56bb-b6e2-d7561258cb2d | note | IP
8ffd6d12-1844-5d3d-92e3-493c42a39e72 | note | – – – – – – – – –
30584ef4-f1f9-54de-b0ae-05cc4431ef7b | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
bcd16d8c-86f6-52dc-897c-ed429ca86acf | note | – – – – – – – – –
da563b2e-1fdf-5efe-afab-03911f2239f9 | textbox | DATE:
0eda2a80-db33-4ac5-b3cd-a2b4f92f24d6 | section | 3 - Testing
9a1e533f-8445-49fa-84a0-0469dc339940 | checkpoint | 3.1 Compaction
a7b8f224-a274-56d7-b128-46b854ea8186 | note | FREQUENCY: Per Lot
be472040-c660-5f04-9bca-e459510186c8 | note | – – – – – – – – –
2ce6a154-4924-55d6-9332-13d21b1d1363 | note | ACCEPTANCE CRITERIA:
2405c604-442c-5e22-8ed6-dd98566a6bc0 | note | • For layers <50mm, if characteristic density ratio is:
b1d2d540-a8db-5745-b6e0-940339960199 | note | ○ 94.0% or greater Accept lot
6aa2cfd2-7cf3-5b6d-843e-c5d6a2c85f39 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
a84462dd-4a6d-55f5-8a95-d513bb4ad6a2 | note | • For layers ≥50mm, if characteristic thickness is:
ef901927-ebad-594f-b328-fb437e8b1bb6 | note | ○ 96.0% or greater Accept lot
b77896fa-93dd-5b4d-8107-56052de936c2 | note | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
66d74c18-be24-5970-a814-18f990cafacd | note | – – – – – – – – –
058eb1e4-92b1-5c9b-93b9-21669c0e09bb | note | REFERENCE DOCUMENTS: Table 407.221
c6250fb1-415b-54bf-9d6f-bb1b59fca2f0 | note | – – – – – – – – –
5a4b9871-88b4-5272-aee9-d8d0c196479f | note | INSPECTION/TEST METHOD: Verify
4f22781a-0b80-5f31-8d8e-3d9f5768cb90 | note | – – – – – – – – –
10d65b1b-a54b-5542-898f-90cc816dbad4 | note | RECORD OF CONFORMITY: Test Report
315dfc89-e402-5fca-8121-fa2ef187d508 | note | – – – – – – – – –
a20866a3-f956-5725-9b03-b027067c83fd | note | TP
51e847c0-8f88-5b87-963b-d108cc09e8e9 | note | – – – – – – – – –
5f097fa5-3282-5bfa-865d-4e97b321bd33 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
f091beea-3e59-5882-927d-e4f12096bcd9 | note | – – – – – – – – –
6a560f85-296e-535f-928b-8f21c0be4577 | textbox | DATE:
9ed1e0cc-7272-4982-bee7-4c1b0a27cf54 | checkpoint | 3.2 Level Conformance
59694be8-28a1-50a6-b0f6-61c98b39daf8 | note | FREQUENCY: Per 4,000m2 at completion of work
2880cebe-41ae-5f31-a5b6-f68db77445c2 | note | – – – – – – – – –
3c7edb9f-6fbe-5c87-886e-69770b51253a | note | ACCEPTANCE CRITERIA:
2b3b37ef-2858-5522-bf50-3d3cfb1905d8 | note | • Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
e0fda814-a648-5841-9a56-5121aacc6647 | note | – – – – – – – – –
3e084596-dc44-562f-8c99-19d1bbde9a9d | note | REFERENCE DOCUMENTS: Table 407.232
5696131b-84b1-5d51-8401-023735a890bc | note | – – – – – – – – –
813d6b90-4b86-59fa-9330-5616ac031d03 | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
eacf1ea0-3cef-5cdc-b1d3-deed00b8fa13 | note | – – – – – – – – –
f102d904-3ce9-5937-bad6-a7d611861aa1 | note | RECORD OF CONFORMITY: Survey Conformance
513ee4e3-6588-5ddc-a7d5-5a3cd686e2c5 | note | – – – – – – – – –
027ce20a-2056-573b-a2e7-43ec2fe68ec3 | note | SCP
43346ffb-0933-54ce-9785-12feadbf23dc | note | – – – – – – – – –
54277394-5b28-54f3-96e3-25f438539034 | note | RESPONSIBILITY: Site Engineer/ Surveyor
1022b19d-8867-5a4c-9803-9eb5e2e1f5f2 | note | – – – – – – – – –
2f238132-202c-5b2a-a8e5-dadb7ca3142e | textbox | DATE:
5e7e4ea3-0add-491a-acd5-cddbfeaf7f57 | checkpoint | Final Inspection
c9153a6c-b29a-52ea-b605-4bad25cbd483 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f198689f-8dbe-5761-9e9e-cb3c2147f66b | textbox | Print Name:
5136b37d-8305-5bbb-8dc5-279b6d1e1ed9 | textbox | Position:
665b585b-c97d-5395-ad7d-33bfcd9ef8fd | textbox | Date:
a912783c-58c5-4156-8ff7-8d1de975d224 | checklist | ITP-01-013 - General Concrete Paving REV1 | itp | ITP-01-013 - General Concrete Paving
afc3a8d4-6b52-47fd-b420-305a49f67d8d | section | 1 - Preliminary Works
839e333f-a171-4800-8c9a-1c0e30aa4051 | checkpoint | 1.1 Check for correct documentation
2f864293-5186-5818-822f-caa418dbc522 | note | FREQUENCY: Prior to commencing any activity
37368119-bd0c-549d-9227-bb2e4f00e4c2 | note | – – – – – – – – –
b982ea22-ff5d-543f-85c3-c3fca99766b1 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a5d528f2-3371-56bc-b956-95a98512de8d | note | – using the correct and complete set of drawings
a3ea3010-2a99-514f-8165-abf0874440d4 | note | – all drawings are the latest revision
18fb404c-21f5-5975-a41c-0500d2424897 | note | – – – – – – – – –
717f6df1-034c-5581-ad07-1fc11d7428c0 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
13982a88-17ab-5747-829f-a6621bd303ec | note | – – – – – – – – –
8d344c32-be03-5ec4-95d3-d82df7263b6a | note | INSPECTION/TEST METHOD: Visual inspection
4c6683e4-b529-5e85-956a-9f1b40135154 | note | – – – – – – – – –
38d402c0-1aa8-5c1b-b9c6-660f6ef80383 | note | RECORD OF CONFORMITY: ITP Signed
0a141502-34b1-5d37-959d-2cc090b9e6e4 | note | – – – – – – – – –
acad8b53-ad71-59cb-8966-a9b7cad25ab5 | note | HP*
62111118-6353-58b4-a7e4-eb199f2ac47d | note | – – – – – – – – –
273cf630-6c46-5e0b-b781-a18b158883c0 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
8f5e14c9-4cda-5c46-9eeb-63a8346fdc81 | note | – – – – – – – – –
77c9f31c-1b8a-5d00-a06b-96acc7ddfacb | textbox | DATE:
9631d4d8-e02a-4129-96fb-f5192135de51 | checkpoint | 1.2 Implementation of all measures and controls
e440ed48-589e-57ef-8f6a-07f37f00fb5a | note | FREQUENCY: Prior to commencing any activity
0c52f036-fd1d-5aec-b90f-9f25c48f8f0d | note | – – – – – – – – –
0691f65e-003f-5248-85cd-7e762d8003c9 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
2b307e3c-30ed-5cad-8ce2-9d6a41808702 | note | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
81d54ec9-9949-558b-9918-801fde29f2f3 | note | – – – – – – – – –
80bd68ec-036b-5bb5-8ffb-c388e2609e23 | note | REFERENCE DOCUMENTS:
274214fb-4282-50f5-84c7-d6727346cc68 | note | • OHSCP
16f3e022-7601-554e-a691-ba5c6490156a | note | • PHSCP
fe8bb2b7-e41d-5072-bb7b-5b384a0a7aaf | note | • PCMP
8c6aa075-f9fa-571b-96e3-a27d26185f42 | note | • EMP
eb3e4997-f302-54ce-95d3-8df91a4b4d50 | note | • ECP
142f7adf-1a27-57ed-9fb3-8fc7b6a8fb65 | note | • CEMP
31e983de-3251-503f-9d6b-e18397374615 | note | • ERA
8ea0afb0-a3a1-5dd4-bc8a-c8f86b9dc75c | note | • QMP
a4983138-f166-54ce-bbe9-1df668ed229c | note | • CHMP
eb103922-33ff-5746-948b-91cf48d4a4e2 | note | • SWMS
932f5716-4730-56cc-b45d-f2d93f52cc0e | note | – – – – – – – – –
22369787-b3e2-50bb-86fd-93ec66039a04 | note | INSPECTION/TEST METHOD: Visual Inspection
0dad1227-9fad-56b8-b752-0d2146966553 | note | – – – – – – – – –
265a0a2d-b0e7-5533-81ce-6920649ab00a | note | RECORD OF CONFORMITY: ITP Signed
b17edd4d-a5f2-5247-b389-d161944a8de5 | note | – – – – – – – – –
d52daf57-eddc-5df5-b4dd-669eb739e610 | note | HP*
23184a34-1a8e-5eb9-9976-691562138ff9 | note | – – – – – – – – –
8ae41d70-aba6-59da-bf08-a6096ce16649 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
c31c3008-dbd0-5b40-844b-65176780c906 | note | – – – – – – – – –
c3c8c3be-4803-5a28-8b1b-31e5ed5a1022 | textbox | DATE:
8c1db759-9dfd-4629-8fea-fb066fd8cbf5 | checkpoint | 1.3 Submission & Approval of Concrete Mix Design
9fa8ae2a-65c9-52fd-9e60-a899165147c7 | note | FREQUENCY: Prior to first concrete pour
41a62a88-2525-5473-b262-6f2d11715acc | note | – – – – – – – – –
b9aa9235-f41c-5f4a-b384-e45800c4a2af | note | ACCEPTANCE CRITERIA:
cd2719e9-72fc-5bca-b148-58b3b918d34f | note | • The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
c2e6bc19-4191-5b20-86c8-f74cdd0903b8 | note | • Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
db6032b4-54d2-5e13-a2cb-f36a46a21cdf | note | – – – – – – – – –
dc7ecd68-ebd0-5211-b388-eef835956fcb | note | REFERENCE DOCUMENTS: 610.07(b)
e28f2509-50e7-5329-af21-2734b23e6037 | note | – – – – – – – – –
1f0d3cd2-a0c5-5780-b4b9-017f18af8685 | note | INSPECTION/TEST METHOD: Verify
3d8019ee-2240-55d2-9bca-149b5b223897 | note | – – – – – – – – –
5b0ef9cc-6a61-57c6-b536-5e9962278221 | note | RECORD OF CONFORMITY: ITP Signed, Mix design approval
09046f2d-f2cc-5f82-b763-d756fcdae28e | note | – – – – – – – – –
110319b5-8969-5e61-b216-8dcb78d288a3 | note | HP
4a251737-0772-55b2-b8b7-1105a9d3203e | note | – – – – – – – – –
be57ef3d-6d15-5aff-9018-f1503d6fa566 | note | RESPONSIBILITY: Site Engineer/ Superintendent
5ab7c57b-5d02-52da-96d0-1955cae86dc3 | note | – – – – – – – – –
45d5f187-9999-5d3f-a2a5-b92a7d164f8b | textbox | DATE:
089d0485-3cb5-4dad-83fa-76ce647af74b | signoff | HOLDPOINT AUTHORITY
139bd8b8-583a-40ef-9200-144ca76932d0 | section | 2 - Construction Works
7e5d8fb5-9123-4a4d-b880-83ddf60dee09 | checkpoint | 2.1 Setting Out
bc1ad804-4745-5b72-9fb4-c506a99a59bc | note | FREQUENCY: Prior to start
5e235627-bf98-5d71-b3c9-52ee5c147ed4 | note | – – – – – – – – –
8c1a671f-0430-5088-b8c6-8e87c1ad547c | note | ACCEPTANCE CRITERIA:
9b85abaa-19ce-51ff-b778-add8d2b6419c | note | • Set out work in accordance with drawings.
f645b472-7d0f-5d9c-82f3-93c055de2417 | note | • The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work.
809b4c3d-5550-5136-87b5-831ed85d48fc | note | • No survey/level pegs to be removed by any persons until completion of works.
9071c893-3f9a-52f9-b784-67e8421c1ba5 | note | – – – – – – – – –
182326fe-4b43-5517-a587-05ca770d1635 | note | REFERENCE DOCUMENTS: 703.17
2e729b19-7048-5447-9e92-c99c9142086d | note | – – – – – – – – –
fe47aa9d-68ef-584c-9057-565325e40b95 | note | INSPECTION/TEST METHOD: Verify
e80ee1c6-8cd2-5c2e-b8bf-1c9c8ceddf0c | note | – – – – – – – – –
c8c07cdc-d213-5b24-badc-ce56b25da008 | note | RECORD OF CONFORMITY: This ITP Signed
6cab57e2-b580-5248-8131-ba78a1a6c81b | note | – – – – – – – – –
cc8cea64-0123-5ab0-88ed-056913e3a278 | note | HP
0e5b1b76-0e9f-5f89-b367-e45d0add46d9 | note | – – – – – – – – –
5d6e72d1-c1a2-5863-99d7-ae79ae8c4bb7 | note | RESPONSIBILITY: Site Engineer/ Superintendent
7e72e5ed-931b-5026-a6cf-52daafaf580a | note | – – – – – – – – –
37f9ac12-65cf-5396-9f16-38f84231ad93 | textbox | DATE:
5b6a7668-bdde-4aae-9690-38bf7e55db82 | signoff | HOLDPOINT AUTHORITY
bc3a7ea2-ccd0-41cb-a941-68623bc5e6b2 | checkpoint | 2.2 Excavation Permit
f89ba820-1d2d-5a69-a108-a307469d253b | note | FREQUENCY: Each lot
eba424c0-3cb5-5f18-a0b2-f6c4ac96fb35 | note | – – – – – – – – –
41bfacd3-bc0b-540e-8603-0eb58b7e26d6 | note | ACCEPTANCE CRITERIA:
1624ae76-1279-56f1-8b87-8e7b434ed61b | note | • An excavation permit must be issued prior to any excavation commencing.
ffe4fb8c-9a1d-5887-bf13-555e6a1f738e | note | • Plant and equipment shall be appropriate for the task.
efa6eaf3-024a-5dbe-b883-e919b29452a4 | note | • Excavation operations shall not disturb areas outside the limit of excavation
e9d9d793-3e0b-5f1e-a682-54684ec5ef78 | note | – – – – – – – – –
f8b41497-a60f-589d-92f4-98fd96496ad8 | note | REFERENCE DOCUMENTS: Excavation permit
a0e98c81-4fb1-5b34-a714-2847d5b233a6 | note | – – – – – – – – –
06d126a2-09e2-5b70-9f96-5c42cea9de5f | note | INSPECTION/TEST METHOD: Verify
415361f6-0de4-5b97-8443-740bbbd3debc | note | – – – – – – – – –
41d90c88-7bf5-5ca9-8ea3-2b1ee0de9978 | note | RECORD OF CONFORMITY: ITP Signed
d58d235c-6a15-53df-9d23-8b6b3dd81da7 | note | – – – – – – – – –
cedd423d-78de-5e93-a2c3-1e12c37a842c | note | HP*
c380e3e6-e8a8-509b-9769-a93a86e5e3da | note | – – – – – – – – –
2703cbeb-125a-500b-af6f-97019ae76f2d | note | RESPONSIBILITY: Site Engineer
574755b4-b690-5ba7-8666-45e14d1776ed | note | – – – – – – – – –
424c0a94-d5fb-5ac0-8f4b-20d5c78b64f9 | textbox | DATE:
b5c216c8-f5c9-4a28-8773-0375cdd9b700 | checkpoint | 2.3 Excavation
7f90fc80-972f-5801-901d-41c7a58d6222 | note | FREQUENCY: Each Lot
d5ae63ea-cb6e-5280-b1e3-09465842a401 | note | – – – – – – – – –
ab5bde9e-9a98-5744-a119-927dd1f31ed8 | note | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
73d7aea5-4409-50d8-88b8-e486d86837f3 | note | – – – – – – – – –
d11097c0-133f-544d-9f59-1f15df11ada3 | note | REFERENCE DOCUMENTS: 703.20
8a900001-76f6-5487-bc3a-2adf5626c61b | note | – – – – – – – – –
3d22c9c3-4427-5429-abd7-09a93e5ca0e2 | note | INSPECTION/TEST METHOD: Verify
73833d15-41e6-5de0-ae48-60d2749a982b | note | – – – – – – – – –
926a0c90-f43d-5ab0-8df8-cdb92b973d49 | note | RECORD OF CONFORMITY: ITP Signed
e8f23562-7c8f-516f-949b-84724e6650a1 | note | – – – – – – – – –
0b351d49-6f5f-573d-a413-f53ebac32939 | note | IP
bc34ba96-b105-5d57-be28-9162f5b8ab84 | note | – – – – – – – – –
28590de4-96ba-57d2-95ca-5f007bdbcddd | note | RESPONSIBILITY: Site Engineer
b0197dd2-3db4-5f5d-8b19-b1b770bd1fde | note | – – – – – – – – –
64111d55-0378-5a9e-a5a8-b756e5f1e45d | textbox | DATE:
8e128bbf-3198-4a80-8247-15f2ba8bff0c | checkpoint | 2.4 Bedding
ce54ff69-383e-5f02-b34c-f745fc544e58 | note | FREQUENCY: Each Lot
6a63989c-7066-59cf-a1f4-09a213a7f991 | note | – – – – – – – – –
edc5b2e0-1a95-5050-8c6f-455f6ba6c2af | note | ACCEPTANCE CRITERIA:
b6c48c0c-5e3e-509d-a0a7-75ce6eca5032 | note | • All bedding material used shall be as follows:
2b73085d-83a8-5512-9d9a-f1d6828a84d0 | note | – 100mm thick layer of 20mm Class 3 crushed rock bedding for median infill
44155172-99da-56ee-983f-efa97c99c968 | note | – 150mm thick layer of 20mm Class 4 crushed rock bedding for footpath/pram crossing
70e3d98b-c562-507e-90f9-e023d3573d06 | note | – Bedding trimmed, moistened, and compacted as per Section 304
86714ed7-44e6-53a1-a3c6-b2df36c9334b | note | – – – – – – – – –
516c907c-083d-53fe-a27c-26d9b6829f2a | note | REFERENCE DOCUMENTS: 703.21 Drawings
9303aa52-5696-5e19-8a01-55b87dfa0710 | note | – – – – – – – – –
56e8d6ae-e414-5a98-b4d7-1c74a335fa69 | note | INSPECTION/TEST METHOD: Visual Inspection
63fa6eed-b91f-52ea-8138-83f2ef024c2a | note | – – – – – – – – –
cc83e8a1-f561-5fcb-9283-48800413340e | note | RECORD OF CONFORMITY: ITP Signed
63c3d3b2-d83c-5b74-8ac6-f935c28217a1 | note | – – – – – – – – –
cb5dfb51-bd69-5cef-bd25-1793f8ade980 | note | IP
c4f54b94-a0d5-5c67-8c98-8d658355e5e0 | note | – – – – – – – – –
ff5e2975-b85a-5860-940c-e13204aa5038 | note | RESPONSIBILITY: Site Foreman
2c186a52-1721-5b0a-80d2-5940602e64ab | note | – – – – – – – – –
7e1e4b94-193c-5ae2-90f2-fed6d2c74fe4 | textbox | DATE:
e42ea19f-3a71-49fd-a374-3383f1a022b9 | checkpoint | 2.5 Formwork
c2373a8e-5b60-53b0-b9b6-7eb523482f6e | note | FREQUENCY: Each Lot
80a977e6-8a39-554c-aead-a4d518f4eaa2 | note | – – – – – – – – –
2aba7a09-d8e2-5a15-9e24-38d08ae05108 | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
9b16834b-9ece-5cc5-935c-8afdaa9bbc7c | note | – – – – – – – – –
f4a48e9b-688c-5585-b4c9-e0b29549d28b | note | REFERENCE DOCUMENTS: 703.12 AS 3610
38e4611b-b3dd-5700-b444-a27c0e8cce51 | note | – – – – – – – – –
ac4e10ca-ab3b-5c8d-b91f-8191c06cf846 | note | INSPECTION/TEST METHOD: Verify
461fab84-3a10-5efa-89dd-839161e334e1 | note | – – – – – – – – –
18d50486-2f3f-58f3-804b-89a6c5408d2b | note | RECORD OF CONFORMITY: ITP Signed
946ebe01-6654-5e35-ade5-59584e5bb7d3 | note | – – – – – – – – –
65e2cb59-1cd3-5502-9549-8faa25120d69 | note | IP
b03a49c2-127a-5760-8c3d-ac555747b441 | note | – – – – – – – – –
2cd71061-ba73-5b3d-8799-8d21aa768661 | note | RESPONSIBILITY: Site Engineer
76c58d3e-60d1-5173-9182-f70b80359300 | note | – – – – – – – – –
bc29ec1a-f1ba-5a1c-9671-d7faf603d3db | textbox | DATE:
21816790-7a92-4970-921b-b6308681ee39 | checkpoint | 2.6 Reinforcement
09481010-ba8a-5671-8c94-59fdf086ec6a | note | FREQUENCY: Each Lot
c7ea7fe0-9ba6-57df-bd17-19623fee4923 | note | – – – – – – – – –
c459afe9-17fa-5ddd-9986-1376e2362c9c | note | ACCEPTANCE CRITERIA:
7f85dec9-97d7-5298-b559-9dd96ffb4e6b | note | • Reinforment used shall consist of SL82 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
f9048bf3-9bbb-5b81-9129-d80a0a8fe9e3 | note | • Reinforcement must comply with the requirements of AS/NZS 4671.
a263a646-e6d7-5e22-b8cb-f0b8aa28b224 | note | – – – – – – – – –
32c4fce0-a1ec-50eb-a5f1-c7c7dd9dbd1f | note | REFERENCE DOCUMENTS: 703.13
4c9a2963-8703-5803-888f-c5cfaa17e504 | note | – – – – – – – – –
87ba6a18-2ae0-5a54-9bef-02d6ac675da4 | note | INSPECTION/TEST METHOD: Verify
fb73455e-f60a-54bb-a85c-17921c9e15d4 | note | – – – – – – – – –
5beb7fc0-1082-5d30-a0a6-5c56b21a0bbe | note | RECORD OF CONFORMITY: ITP Signed
8988f9de-6c62-501d-8b1f-30a2792b6814 | note | – – – – – – – – –
399a42fe-9228-5096-abfa-239f84000bde | note | IP
04485b0d-3812-582c-a8ae-1a79e89e5d38 | note | – – – – – – – – –
eb0dc681-7d9f-5c22-a620-4f9e96f4e4c2 | note | RESPONSIBILITY: Site Engineer
5f9394be-ebe4-557c-ac23-5a1808d3ee60 | note | – – – – – – – – –
55bb12e3-8ec8-5ab8-9541-30147dd331a5 | textbox | DATE:
2190e8d2-9f10-4de1-8f8c-849a755192c1 | checkpoint | 2.7 Concrete Placement
de759c31-bf0a-5979-8768-9e43e1a38ee0 | note | FREQUENCY: Each Lot
07021a2f-2c16-5d21-a494-3fdb979910ac | note | – – – – – – – – –
23db72b4-87cb-5976-b253-d1bf79648f38 | note | ACCEPTANCE CRITERIA:
7d394be7-0adb-520d-9ecf-a1cfa02dfed0 | note | • Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
285cc484-8b0d-534a-8daf-80e46fa0b694 | note | • Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
8bb889d4-de59-5d40-af31-425169dabdbe | note | – N25 for median infills
3c68035d-6868-58f3-8fba-973fb0d94c34 | note | – N32 for pram crossings/footpath
cfeb5972-4314-5d3b-a190-462fa4cad1a6 | note | – – – – – – – – –
92914c26-e276-59a2-b69a-9b5b3174243a | note | REFERENCE DOCUMENTS:
043d3aea-3f1e-58bf-af5d-cf84d69d493a | note | • 703.05(a)
ea2d6b1f-2fb6-519d-9151-84b01c565fd0 | note | • 703.08
9188d270-1604-58db-a00b-47ddb4a1c777 | note | – – – – – – – – –
90debcfd-6c53-5603-806f-93b51f9b328d | note | INSPECTION/TEST METHOD: Visual Inspection
c4899a40-af0d-5fb6-b889-2cf511fe0ed5 | note | – – – – – – – – –
270948e5-c072-5a13-ab83-82d8f9ab36d0 | note | RECORD OF CONFORMITY: ITP Signed
08d37a53-d2c5-5590-8b0b-07528c407a13 | note | – – – – – – – – –
e5c03601-6702-56d5-892d-e3ab89cdfcee | note | IP
6d8c2c85-93c4-5af3-9c7b-c8b5bfa44f5a | note | – – – – – – – – –
5ad2d5d6-7fce-5daf-ad0a-4ee825012b8d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
de9c5067-915f-53c2-80d0-d3f67d045179 | note | – – – – – – – – –
737b62d9-d5e8-5587-9533-8550c676a04a | textbox | DATE:
a81baeee-8d1c-4485-964d-63ebe3a7a648 | checkpoint | 2.8 Record location of each batch
36874f84-dd20-56b4-b691-0e4abbe607f8 | note | FREQUENCY: Each concrete pour
4e5fa406-06a5-5da1-b21f-d27231dc4805 | note | – – – – – – – – –
44671083-ba12-5a4c-b3bb-12d8df55d22b | note | ACCEPTANCE CRITERIA:
0c2a9804-cd34-5f6e-88b4-0c63a5072a48 | note | • Batch location recorded on Load
12d64fb0-dd2c-5637-ba23-23ba1e92ef40 | note | • Batch Traceability Checklist
375ce461-8567-57c6-b3f0-cae2637820a9 | note | – – – – – – – – –
ed6606df-2661-5af2-a9fe-9429712fe30a | note | REFERENCE DOCUMENTS: 610.15 CL001D
4e917d05-b3f1-5d27-84f7-7d21e543e61d | note | – – – – – – – – –
03f5e05d-1639-502e-93da-65466829dd5f | note | INSPECTION/TEST METHOD: Checklist
5c5713c6-7682-5249-9aa6-f8089757a419 | note | – – – – – – – – –
da8c2cf9-3a20-53df-b3be-bddebb066330 | note | RECORD OF CONFORMITY: This ITP Signed
f2dacac5-e5ad-5e6e-ad74-b6830ccfb3c9 | note | – – – – – – – – –
ecd5ac09-42ac-5b44-a036-51469fe83f93 | note | IP
dbd7eeec-b4f4-53e6-87a5-671af20b1dec | note | – – – – – – – – –
e65830de-f5db-55bd-9e20-b338bdba3b82 | note | RESPONSIBILITY: Site Engineer
ce5c28d6-e069-50e7-a040-64879be253e7 | note | – – – – – – – – –
819edd36-b26e-5df1-8700-6a0c44e789cc | textbox | DATE:
ea8a0d73-d44d-430b-b201-b7e6a4c325c6 | checkpoint | 2.9 Surface Finish
b054f5c2-39dd-5d72-8488-8cead2606170 | note | FREQUENCY: Each Lot
b5c8cc32-6b94-5129-8246-788f5582afa3 | note | – – – – – – – – –
8957e3cb-5316-54d0-a4b5-7d6eda7991e7 | note | ACCEPTANCE CRITERIA:
7a4c5def-bd6d-5692-b4dc-f98c054932b3 | note | • Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
6a52b89e-ab5b-5c11-aaaa-740b9e450f33 | note | • Footpaths and other Surfacing shall be compelted with a wooden float.
20192bbc-3433-5124-ac74-19a8ce9d4f80 | note | – – – – – – – – –
d8362852-a6f2-5bb8-930b-e35f8cc9e3e4 | note | REFERENCE DOCUMENTS: 703.25
fa7fc057-7663-51df-8af5-a9ebc534fa55 | note | – – – – – – – – –
209767a7-6f2d-5f75-a802-9abe5711997f | note | INSPECTION/TEST METHOD: Visual Inspection
c74ca361-9b49-5c6d-a20d-292704d0123a | note | – – – – – – – – –
b13917c5-012a-5bf8-8cb0-db12d2012bbd | note | RECORD OF CONFORMITY: This ITP Signed
8d2c1e6b-b4a3-504b-a70c-c106acbfaa8e | note | – – – – – – – – –
17f95d6f-d93b-595d-b165-1232a797f330 | note | IP
eb7b4697-e472-5289-b74f-53d20006d0f2 | note | – – – – – – – – –
2a1b660d-520e-5cc6-ab47-2db97859e35f | note | RESPONSIBILITY: Fulton Hogan Engineer
74a069b1-02a1-57c8-98f6-2690e7cdabd9 | note | – – – – – – – – –
1318d6ef-bfcb-5df8-8fee-be77c74ef0a4 | textbox | DATE:
ee90bbb8-2206-484b-ad03-1a44d240fd5d | checkpoint | 2.10 Pram Crossings
c35e5b8d-3c21-5b4d-abe9-793cab44c3ef | note | FREQUENCY: Each Lot
204aca09-db13-56dc-a90c-6683d8b578ab | note | – – – – – – – – –
7feabea8-fc6f-5e8e-8307-e72bae94489e | note | ACCEPTANCE CRITERIA:
1e938ee7-bcdd-5b09-90f4-7ee3c60ba019 | note | • Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
a227be65-7315-538d-b2bc-e18d8c33ae73 | note | – For pram crossings within concrete kerb refer to Figure 24A of AS 1428.1
9637c94a-47ab-5c3d-8ccd-dd59e97a0212 | note | – Pram crossings within bluestone kerb shall be constructed as per relevant standard drawings (1P 50406 for City of Melbourne)
1cbb152a-3c81-5995-b7b8-d98f797852e7 | note | – – – – – – – – –
19b70a30-3b49-5fcd-bd70-7c58409e384b | note | REFERENCE DOCUMENTS: Figure 24A AS1428.1 SD 1P 50406
00bf7839-e48f-5db0-8e74-321480919712 | note | – – – – – – – – –
ca6921a4-f782-56d2-b5e2-3b8ae39056c9 | note | INSPECTION/TEST METHOD: Verify
92e110b6-b735-5287-86a7-1b7872250ffe | note | – – – – – – – – –
8572247f-9cb1-5600-bb56-af270f164261 | note | RECORD OF CONFORMITY: This ITP Signed
08237b92-ae3e-5669-a449-6a6f3dc36a6e | note | – – – – – – – – –
8f3ac418-1f39-5ebc-af06-ab0c343d3562 | note | IP
1561fc59-42e9-5ae0-9c18-b6cd5f42b49e | note | – – – – – – – – –
68a8e900-d9fd-5c05-b349-a9c3cea25ca3 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
97a1c4e1-7461-5d0f-87d7-4809a4a17d6f | note | – – – – – – – – –
f09996f4-3e7c-5dc6-900a-5e6d93f853cf | textbox | DATE:
b9470c08-f11a-4935-85e0-47936d822dea | checkpoint | 2.11 Joints
881b8cb0-ec92-5bed-86a3-dde144686246 | note | FREQUENCY: Each Joint
19d7ad30-3ba6-5e05-a037-d8766eb1eeae | note | – – – – – – – – –
ee10b61f-023c-5227-94b4-812ed80bc038 | note | ACCEPTANCE CRITERIA:
47ffd2ef-99cc-5cb1-baa6-b30a9b29faf6 | note | • Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
dcc20f27-7ef9-58b5-8010-d22b83804165 | note | • Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
c0a3d417-66dd-5f8a-ad62-6c5c3f88d61c | note | • Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
216a8f3a-0cd7-52f4-a136-ed30dadea16d | note | – – – – – – – – –
8d31262d-b631-543c-ac6c-e242a66a86fc | note | REFERENCE DOCUMENTS: 703.26
1eb8876a-457e-5ce5-aa66-8dd3ddae5f6c | note | – – – – – – – – –
1797a9f1-1f24-5b36-9e2b-6c78a008d3ee | note | INSPECTION/TEST METHOD: Visual Inspection
5113696c-f310-5a9e-b849-df3bac845fbe | note | – – – – – – – – –
f06227e3-b7a6-506f-bce8-6665645bba50 | note | RECORD OF CONFORMITY: This ITP Signed
ab9548fe-7ae2-502b-a5cd-91c003d12930 | note | – – – – – – – – –
11fb5dd3-c9b2-5b53-b737-b0c8e01d25a0 | note | IP
e5b928af-ab16-576e-ba73-e1c3ce7b19e3 | note | – – – – – – – – –
3a8ff513-d330-5819-bc4d-10d22a4a5744 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
cf0d1466-1271-5c54-ac15-14ade12926c6 | note | – – – – – – – – –
c83d6a78-8a3e-5068-a230-29574b1fcefe | textbox | DATE:
a863720b-ac47-416d-84e6-63c31e268edf | checkpoint | 2.12 Protection of concrete
59bb24cb-9fde-514d-8fc0-9671ed321f7a | note | FREQUENCY: Each Lot
488bbe92-ce96-5927-b496-f0c149e5060d | note | – – – – – – – – –
791f3b00-cf71-5be9-9b77-6aa3a4262435 | note | ACCEPTANCE CRITERIA:
6df1066b-6cca-59de-99f7-6d7cd2ce4dff | note | • All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
aa93ea42-ea8d-536c-a14c-f054a066c4e8 | note | • Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
1000556b-23d5-5571-a7e5-bce5f7671674 | note | – – – – – – – – –
84614ba3-eafa-52e4-bbf8-223f8ec39e14 | note | REFERENCE DOCUMENTS: 703.27
62edbeec-e665-52a2-93f3-de75de203acb | note | – – – – – – – – –
918084c3-64d1-5538-b6ba-7c49364e58d1 | note | INSPECTION/TEST METHOD: Verify
908e30a6-4107-5744-94f0-9b7bca1e21cf | note | – – – – – – – – –
2d8dff69-ba97-580f-925e-78a83f52dd8f | note | RECORD OF CONFORMITY: This ITP Signed
02449c92-906f-5a4a-b879-e07a66e8bf70 | note | – – – – – – – – –
559d6a35-7dd0-53b1-ae37-836d59443842 | note | IP
d0e4d44a-cad6-58f2-9fb8-2fb65b6f3ff4 | note | – – – – – – – – –
d642b60d-362e-5cf5-9358-50ab0cc5006e | note | RESPONSIBILITY: Site Foreman
771b881a-782b-58c7-9ea5-a69c8544d984 | note | – – – – – – – – –
d1987335-44d1-56f4-ac70-6a30619a5d03 | textbox | DATE:
5fe51662-628d-4716-b8f4-b8885a0193e7 | checkpoint | 2.13 Curing
74754a92-8842-5d80-a6de-81e0746336e8 | note | FREQUENCY: Each Lot
81f0abea-b8ed-5c3e-9e53-6fb7a29ddfcf | note | – – – – – – – – –
b4f53f69-061c-5d13-a503-cd5308cb2bf6 | note | ACCEPTANCE CRITERIA:
fee3d03e-c0a9-5206-88cd-0fc12199da10 | note | • Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
a1d6966d-e1bb-54d9-b699-20368cf04295 | note | • Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
e5b96768-8879-5cb8-84d4-a442fa92b7ca | note | – – – – – – – – –
42ec9e18-a0a0-509b-8bb7-5431a159bc62 | note | REFERENCE DOCUMENTS: 703.10
05ff3202-5d01-5f20-a551-174237efbedf | note | – – – – – – – – –
445744e2-6c7f-51f3-a5ab-94036b1a5a3d | note | INSPECTION/TEST METHOD: Verify
c49a7954-795c-57e6-a620-93d0d8bb7d07 | note | – – – – – – – – –
36304b85-5752-519d-8b54-7225990f1797 | note | RECORD OF CONFORMITY: This ITP Signed
cdccd648-85c3-5f34-8c3d-0ce77df538a3 | note | – – – – – – – – –
58daf427-3792-5e4a-ae89-75405ca18598 | note | IP
71c183db-1e9d-543a-b31e-82fe9d5f75a5 | note | – – – – – – – – –
68d14cb7-304c-51b0-b8a6-52dd2472b553 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
67f4adf6-f83e-531d-a9a7-5e6d23ff2d08 | note | – – – – – – – – –
066898b1-79d0-5f03-8dbe-20de76d83b89 | textbox | DATE:
44cea093-4c69-4454-b0b0-98bf53f37975 | section | 3 - Completion
f9e79773-cbac-4c17-b0be-06b1d5059cdd | checkpoint | 3.1 Carry out sampling of concrete - strength and consistency
ac156f22-c188-5ea7-91a7-95ed08aea55b | note | FREQUENCY: Each 50m3
5bda1dfa-f559-5059-9583-76f484bd6ee6 | note | – – – – – – – – –
a80338f5-4ec2-5aaa-981c-5c09c0fb9746 | note | ACCEPTANCE CRITERIA:
fc0d3536-c702-58b7-b793-88ead3db7125 | note | • Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
98cf0b60-d2bf-515d-994e-7d2a172de921 | note | • The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
a991b887-5fae-5979-8070-d5f9adf27cef | note | – – – – – – – – –
e3dae3cb-0db6-5616-adc8-438864f920b2 | note | REFERENCE DOCUMENTS:
ebfe410b-8bef-5219-b11b-bb4783d4f00d | note | • 703.11
c4867bcd-821d-5fcf-9296-f99e3fc8a9df | note | • CL001B
aee9e0ed-ad79-53a6-9678-dc35bd2a495e | note | • CL001C
a7773d58-249d-5d91-ae0a-4e774573a912 | note | – – – – – – – – –
9e901a2c-c7bf-5da3-87df-fc2bd3e028c0 | note | INSPECTION/TEST METHOD: Checklist
0bf09b68-852d-5fc8-a07e-7a570ee9c6f9 | note | – – – – – – – – –
5cdedec5-f26a-5f7c-b8c6-f7eef7d9a7bf | note | RECORD OF CONFORMITY: ITP Signed/Test Records
2142e700-ff78-5d55-9bfb-2334c7ff858f | note | – – – – – – – – –
d7567cea-d1af-53d1-bb87-cb45ddc57bfc | note | TP
5621f65a-41e1-5044-9623-3ef7d2052d30 | note | – – – – – – – – –
1258bc6e-3551-563b-9f70-83569d5fc408 | note | RESPONSIBILITY: Site Engineer
ca6b0d5f-08e0-5c42-acd9-5258825674fa | note | – – – – – – – – –
f39f86fc-7e75-5099-b1d1-42b87be7393a | textbox | DATE:
b40c1d7a-a31c-4c7f-98e8-702eba06bb31 | checkpoint | 3.2 Tolerances
7dc28aa3-794a-59b3-96aa-1c9e47dd146b | note | FREQUENCY: Each Lot
5a1fa0de-246a-5563-9511-618bc46347cc | note | – – – – – – – – –
3b028a31-7d81-557d-ab67-0c7958097954 | note | ACCEPTANCE CRITERIA:
bb3c6684-9ff8-5e9b-bb34-cf9ea1bf56d2 | note | • Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
0fe129e9-924e-588a-b7e6-70cdbc255672 | note | • Section dimensions shall be constructed within the following tolerances:
fe747b4e-f856-5d9d-8156-47695e8f1897 | note | – 5mm and 15mm for width; or
91336092-e9ce-5284-a0df-ba3aab35e05b | note | – ±3mm for dimensions less than 25mm.
7344d08b-d975-59fc-99d0-6a3042b8bf8e | note | – – – – – – – – –
f7c15a70-b344-5b92-926a-d1362131aecb | note | REFERENCE DOCUMENTS: 703.15 Drawings
236e3b48-0b8e-54f9-90a1-99a8c88742f4 | note | – – – – – – – – –
28af288c-15d1-5a6c-bb62-067a0f519c32 | note | INSPECTION/TEST METHOD: Visual Inspection
6401e5fa-6179-5bca-ac36-66e9815e3838 | note | – – – – – – – – –
4bfb2966-352b-57dd-b8a5-d5a2f59594f3 | note | RECORD OF CONFORMITY: This ITP Signed
88035ebe-bdf5-5744-a090-fc71191b3fa6 | note | – – – – – – – – –
0169d61f-5c4a-557a-8075-6de3ff7e1641 | note | IP
048e5042-bbca-5b87-b645-8c4f901f7ce6 | note | – – – – – – – – –
743e676f-00d8-5c81-a343-5663337b244d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
ea89f4a4-be13-5f22-bbae-8d1ece773462 | note | – – – – – – – – –
73865790-a697-51bf-985e-e86a7856c781 | textbox | DATE:
275ae3b3-a75c-4d3f-a154-0a5cd9cd12ba | checkpoint | 3.3 Backfilling
cbbb3dd7-b50c-583d-b4f5-04157473c133 | note | FREQUENCY: Each Lot
f709987d-9bb6-5ea3-aa75-8411368971cf | note | – – – – – – – – –
c09e252a-977d-5e8d-9b4f-bb3cd7b877cc | note | ACCEPTANCE CRITERIA:
0a9a943a-71d1-5aa2-a6c5-15e4e2d23151 | note | • After curing, no earlier than 3 days, backfilling shall be completed as per the below:
a7e59f14-f076-5ae8-b2cb-87a8038cfe3c | note | – Topsoil compacted in layers < 150mm
be1924ef-aa21-5a05-b9bd-b1810b4d05b7 | note | – Width ≥ 300mm behind edging to top of edging
d7ca5a2c-03f8-5392-bf06-482ee3f41e56 | note | – – – – – – – – –
07feede7-976f-5e2e-8602-eb4f1ace3b1e | note | REFERENCE DOCUMENTS: 703.29
ba94dc9f-9d3c-557f-899d-3ef2e5ceb123 | note | – – – – – – – – –
62064c0e-4fb0-508a-a33a-49f325372b80 | note | INSPECTION/TEST METHOD: Verify
eea5de39-c7ec-5394-a105-314e1f735143 | note | – – – – – – – – –
63b38e64-fbf8-5bcb-b22b-825e5e5c7473 | note | RECORD OF CONFORMITY: This ITP Signed
f7d83969-8b31-562b-b57d-d149c7d5bd2c | note | – – – – – – – – –
9d042842-33cb-584b-b149-cec4afdc4d5a | note | IP
d4a6f6c2-d98f-5a64-9495-c39aefbf3cae | note | – – – – – – – – –
34564532-f7c5-5a49-9a44-25f9f689d46d | note | RESPONSIBILITY: Site Foreman
ccc70557-5e2e-54af-9269-45993a405dc6 | note | – – – – – – – – –
f07f656f-9b7f-5471-b2da-e2a33b3d593e | textbox | DATE:
f1cba8b1-29c0-4895-ad36-7d69f7e383b9 | checkpoint | Final Inspection
8f39a6ef-0396-5481-8892-8086258fe3b6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7fbc1150-9838-5d5d-8ba4-282c26bcfcf1 | textbox | Print Name:
699f7617-2f3f-57b4-a1ec-9b4abdf6328f | textbox | Position:
fb089606-a9ae-592c-9503-cca77dd6eb26 | textbox | Date:
20b9460b-79d9-4e6e-973d-22865283359b | checklist | ITP-01-014 - Subsurface Drainage REV2 |  | ITP-01-014 - Subsurface Drainage
b0acebab-74c7-4be9-9bf7-eed012e52844 | section | 1 Preliminary Works
45af6e79-3f74-4ed7-83db-d13305bbf457 | checkpoint | 1.1 Check for correct documentation
6ac72633-e74c-55f4-8b00-f4cccd29ea73 | note | FREQUENCY: Prior to commencing any activity
4d9e7588-250e-5306-981a-5d58e14ebccd | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
fd743d1a-ca0b-5247-bf36-f9dc9c1894e7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
a8061d89-7dd6-5780-b0af-cdd4f467a7e2 | note | INSPECTION/TEST METHOD: Visual inspection
1a78ad32-dded-52ad-984a-6ea65a692318 | note | RECORD OF CONFORMITY: This ITP signed off
6cbd0f50-a9e5-52da-acc7-f4a575adede7 | note | HP*
d42dc423-d538-50b8-9ce2-fe8acd38d288 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f3419df2-3b2c-5430-a484-6b5d7f534098 | textbox | DATE:
601e6bb3-ba8c-4104-8ed8-476843f031cc | checkpoint | 1.2 Implementation of all measures and controls
7595e5ff-4c44-5e69-bbaf-d7d1d4e39acc | note | FREQUENCY: Prior to commencing any activity
821a767c-82b1-581e-9a89-3b20d97bd376 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
84a636b1-5745-5e4f-9e12-8d2d3d9a57b8 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
ff5db2e1-d4c8-5c3d-afd4-76122a572b08 | note | INSPECTION/TEST METHOD: Visual Inspection
18eb1be5-8603-596a-b19a-7cb04747bb01 | note | RECORD OF CONFORMITY: This ITP signed off
534e5fd9-5f92-5d48-a009-4149118cdf8e | note | HP*
5f0e06f3-259d-52ae-b24b-46a5952ddb08 | note | RESPONSIBILITY: Site Engineer / Site Foreman
349a2f60-fab1-5c41-9284-5dca6192fd9c | textbox | DATE:
c89dc685-31a0-49f5-b480-f516d235f576 | checkpoint | 1.3 Placement of no fines concrete
ce095a97-1672-5a82-aefe-00af120b5855 | note | FREQUENCY: Prior to works commencing
1e3b41fe-8c85-55b6-ac03-a4d637cf35a2 | note | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures
82d21735-bd89-5397-b4a7-15fd3cf13526 | note | REFERENCE DOCUMENTS: 702.09(g)
18670fb8-3195-5e53-ac2c-8468396b77ce | note | INSPECTION/TEST METHOD: Verify
a897a932-2542-58ca-ba3e-7a8f31a5b57e | note | RECORD OF CONFORMITY: This ITP signed off
a7deab34-88bb-56be-ab1a-72996d59bb69 | note | HP
94883122-221c-5247-9ec9-17416726921f | note | RESPONSIBILITY: Site Engineer / Superintendent
fc787cb1-2907-5bc4-ae27-d04ca25f4093 | textbox | DATE:
02d2a77a-a2f0-4c61-acd3-022ecb96bfe2 | signoff | REQUEST HOLD POINT SIGN OFF
af74dd13-033b-448d-b9a1-125f4f6f01e8 | checkpoint | 1.4 Material Classification
db0d64b6-d99f-569d-8865-d413e34afdc1 | note | FREQUENCY: Each Lot
dcc91817-e1ec-5995-9958-f02c8a45cadf | note | ACCEPTANCE CRITERIA: •Subsurface drainage pipes: 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2. •Granular filter material for bedding and backfill: Trench backfilled with no fines concrete filter medium complying with Cl 702.05 •Geotextiles: Shall comply with Cl 702.06. •Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611 •Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit •Flushout risers: constructed to the detail of SD 1631
7ff41ce5-2f8c-5b3e-b370-8944bcad0c21 | note | REFERENCE DOCUMENTS: 702.04 702.05 702.06
ec6ce9c3-7bcc-5272-9857-e59657faedc6 | note | INSPECTION/TEST METHOD: Verify
45b028cf-60c1-5bbb-963f-62a5cb96a6b6 | note | RECORD OF CONFORMITY: This ITP signed off
2afe6652-7b9a-50c2-88b3-ada2832528f5 | note | WP
332f7f0b-06c9-5448-a6af-ddd36e8ef4e0 | note | RESPONSIBILITY: Site Engineer
b627af59-e5b7-5e12-8840-408022103744 | textbox | DATE:
22ee974b-af87-4d89-822e-80c025595293 | section | 2 Construction Works
2e97c2b0-f7a4-49d7-810b-8a07b731a8d7 | checkpoint | 1.5 Excavation Permit
cfea4ab7-7432-568b-a484-e3ee085acdb2 | note | FREQUENCY: Each lot
f2e5230b-a66b-5e79-a612-a6d7cf683cfa | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
fe89bf37-6dce-502a-9a43-da392b912e6a | note | REFERENCE DOCUMENTS: Excavation permit
d5669173-7098-525a-a280-a3cc07f3fce8 | note | INSPECTION/TEST METHOD: Verify
187972c6-5af3-50f3-be72-f3c65614ea22 | note | RECORD OF CONFORMITY: This ITP Signed Off
31d06372-65ac-566d-b5b5-d890a5cdad7c | note | HP*
c64c6723-bfac-508e-94e0-ad944ab453d5 | note | RESPONSIBILITY: Site Engineer
ef21a9f5-0fcb-5ccc-87cc-e85575afc170 | textbox | DATE:
f124119b-3e57-4cf0-82f2-8b0083219b2e | checkpoint | 1.6 Excavation of Trench
f668ac52-4ebb-5333-8dd7-ca087889ccda | note | FREQUENCY: Each Lot
8d0f8f22-d1a6-5b6e-8299-a2413ab98222 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
1f9bac8c-4436-56e5-afb0-4e9ffa29fecb | note | REFERENCE DOCUMENTS: 702.08
aa8211da-26e5-5640-a428-88eb62223872 | note | INSPECTION/TEST METHOD: Visual Inspection
23cfcbc4-d356-55c9-af59-8dc723d79557 | note | RECORD OF CONFORMITY: This ITP signed off
d4bd067f-af44-57db-8a11-50f48c3d0bbe | note | HP
a553fe8d-2d81-5918-ad17-8d08ccb9d3ae | note | RESPONSIBILITY: Site Engineer / Superintendent
1630f3e3-e76f-5fa2-ba8d-096b98307e4f | textbox | DATE:
3e259d92-3135-4a1a-b36c-416e573e9438 | signoff | REQUEST HOLD POINT SIGN OFF
575e6a40-544d-447a-8edb-233184e3c433 | checkpoint | 1.7 Placement of bedding
096fa818-a35c-5087-abd9-9d5a2c7b0b3c | note | FREQUENCY: Each Lot
fa6695cc-7aa0-5694-b457-075586945635 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
98b51d5c-f1ef-532d-a475-b6605621d14d | note | REFERENCE DOCUMENTS: 702.09 (c)
6cc97b8c-59ff-57da-be4c-1a09bf09d03a | note | INSPECTION/TEST METHOD: Visual Inspection
9e84653e-0be9-5cba-a6a8-839ae95082e6 | note | RECORD OF CONFORMITY: This ITP signed off
a0c044cf-2e01-57ff-81ba-91d64c777f5d | note | IP
a2ae9793-373b-5b6c-9b01-687dad54cac6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
033933ac-6855-5481-8068-b9f73ae821b9 | textbox | DATE:
0e5bb1f2-7bf9-417a-a659-b4b2f2065a43 | checkpoint | 1.8 Placing pipes and geofabric (if required)
abdee7dd-3d02-5887-ab9d-dd53c013dd26 | note | FREQUENCY: Each Lot
043f82f6-12e9-5f39-9cc6-2fa34d0172d6 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe. If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
9d90d7c7-e0e8-53a2-9f94-2aa0e99e9169 | note | REFERENCE DOCUMENTS: 702.09
bda7cad8-5987-5257-993c-5a7032571c67 | note | INSPECTION/TEST METHOD: Visual Inspection
24eb4f5f-14ed-511e-8f6a-7dfe9992f1cf | note | RECORD OF CONFORMITY: This ITP signed off
b113a455-20c0-586e-acf3-ef2f6e5afb18 | note | WP
9086e9bc-d66b-55a3-812a-e90cc332c760 | note | RESPONSIBILITY: Site Engineer / Site Foreman
46bbdb27-2835-555c-8c68-fc76e87ccd10 | textbox | DATE:
98434b5c-97ea-4d98-825f-4f09bc1cd4d4 | checkpoint | 1.9 Placement of backfill
f81b72d5-a2fa-5a78-9397-0a01385908d4 | note | FREQUENCY: Each Lot
6a57a977-1acf-50d5-bfb7-885b601ed014 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
7c8d7c99-b974-5d3a-a249-c5e56f3e59cb | note | REFERENCE DOCUMENTS: 702.09 (g)
e6d8a5d1-d61b-5aa7-a6e4-fffa5ed22f3d | note | INSPECTION/TEST METHOD: Visual inspection
574af6f6-a573-5964-9fb4-3854267ac263 | note | RECORD OF CONFORMITY: This ITP signed off
57074a93-48a9-5b1a-aa49-95f526a556b9 | note | IP
771f9e3b-b79b-5247-b44a-356f8b1bf7de | note | RESPONSIBILITY: Site Engineer / Site Foreman
b957eef3-c93d-5496-9fe9-c917c251ac67 | textbox | DATE:
00c80675-1be0-4b48-85b6-3f7c27250e7c | checkpoint | 2 Install Pits and Flushouts
6b685745-a3e7-5c9a-8a6c-0acae278fcd8 | note | FREQUENCY: Each Lot
65409c47-d04e-5375-a857-13d32fee8e44 | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
7189ff78-034b-50b2-b295-03972695e07f | note | REFERENCE DOCUMENTS: 702.1
b142e32c-d548-5896-b8d7-1302aad352fa | note | INSPECTION/TEST METHOD: Verify
17552d86-3a27-5017-bef9-03d906147c27 | note | RECORD OF CONFORMITY: This ITP signed off
e5f4d06a-0b3f-5fa7-bfea-838bb78029be | note | WP
7bb71c93-0ed1-5542-a640-f5dc20b86466 | note | RESPONSIBILITY: Site Engineer / Site Foreman
863ba323-6632-5f66-851b-5462ebdf7447 | textbox | DATE:
ab5137d8-3edb-4981-9f07-529deee63a17 | checkpoint | 2.1 Flushing Test
852cd80c-dd7a-540e-a69f-3725e53fc98c | note | FREQUENCY: At completion of stage
1c0f8eba-88c8-5b83-9285-e56af90194c5 | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
c9afde3c-0c17-5dac-b052-4c5dd263f7e4 | note | REFERENCE DOCUMENTS: 702.09(h)
a9dd7844-e769-5e31-8af8-606c9689dda2 | note | INSPECTION/TEST METHOD: Site inspection
bc87f538-dedd-53b6-876e-6a042c38b07b | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
0731e7d1-429e-5411-a7ac-7b814a20db12 | note | WP
27c56c53-476c-50be-b0a9-1a12a241658b | note | RESPONSIBILITY: Superintendent / Site Engineer
bec2a326-9173-5565-b7d3-260a3b140c2f | textbox | DATE:
a9de04a9-49bc-4348-9773-0aceb7b2c8ed | checkpoint | 2.1 CCTV
53675e13-9037-5ee9-81c4-802592fc0e44 | note | FREQUENCY: At completion of stage
38a839e9-4420-580e-8bff-b895be7ea3bd | note | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt
68ab5bbc-764d-575d-8ca9-bbd8f601b32d | note | REFERENCE DOCUMENTS: 702.09(h)
3bb5636a-0f66-53fd-9c3b-e5e9c1e36bc7 | note | INSPECTION/TEST METHOD: Site inspection
bd61d5c6-804d-5deb-ae60-3a3dd4be605b | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
5f371f6f-d882-5b77-a498-27a68b7f5851 | note | HP
a24a6c34-f291-5803-9611-f498c9506435 | note | RESPONSIBILITY: Superintendent / Site Engineer
e1107e0b-1684-5b96-83d5-4ed984cb313a | textbox | DATE:
0000428a-0cc0-4a82-aa80-a7b1b43cf6a8 | signoff | REQUEST HOLD POINT SIGN OFF
1909ea7d-1240-45d3-a1e4-c66c3cb5f3cf | checkpoint | Final Inspection
c6f10f30-063f-53fd-8d2a-c4dfc505c570 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4b89a2d4-ee2e-540f-8b42-219e76155dcc | textbox | Print Name:
7f8eaad5-1e55-5f47-9d63-f8c76b9a0910 | textbox | Position:
e01f1799-ae34-5faa-9084-8c84980f15cc | textbox | Date:
61ff333d-e6e2-4b91-b4b3-d8d90630d028 | checklist | ITP-01-015 - Kerb and Channel REV2 | itp | ITP-01-015 - Kerb and Channel
923a474b-0471-4dfb-82b6-59eb6a33ad73 | section | 1 - Preliminary Works
116a5287-6124-4d7c-ac07-6187fcf931b0 | checkpoint | 1.1 Check for correct documentation
3179cddd-4997-50b2-a608-49171ebbb6f9 | note | FREQUENCY: Prior to commencing any activity
47fe795f-682f-50b4-8f46-c1b0ca8322af | note | – – – – – – – – –
82c50522-46f6-5eaa-ad3f-6bc69d014fec | note | ACCEPTANCE CRITERIA:
f97f83d8-11e0-5d32-8d1e-2f9022b74053 | note | Ensure that all employees and subcontractors are:
84f9aba9-78b9-5ca6-a98e-1e5c65582187 | note | – using the correct and complete set of drawings
d9ef8d30-edb8-59f6-b46e-d46953051b13 | note | – all drawings are the latest revision
5c3bdcef-d559-5d00-b1ab-99fd67f800fd | note | – – – – – – – – –
326271c5-9413-5dc8-8726-30a858a23306 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
5ee3ebba-b253-528b-ad6d-114fdcdf89b9 | note | – – – – – – – – –
1f8e2bd6-56ef-55f2-93eb-124bc6b214fe | note | INSPECTION/TEST METHOD: Visual inspection
59478ea8-fce8-583d-b0b7-77944fda6fa2 | note | – – – – – – – – –
7361ff30-70f3-5cfb-b825-c2b326d53b9f | note | RECORD OF CONFORMITY: ITP Signed
fd7b280b-ce7e-530e-901c-3230de51e2d8 | note | – – – – – – – – –
42ecd03d-0951-5d4d-b2d1-f46cd1b49a21 | note | HP*
9180dff6-9059-5113-b1e5-3f422b2d1d1e | note | – – – – – – – – –
baf92be7-5217-571e-8d00-d36685d8596e | note | RESPONSIBILITY: Site Engineer/Site Foreman
6cc8f18c-03fa-5eb7-ba68-e9d061c66d7b | note | – – – – – – – – –
786f1698-4c2f-5a83-9f82-f964512760d7 | textbox | DATE:
cbc267cb-14e8-48f6-8772-0a9216a3d054 | checkpoint | 1.2 Implementation of all measures and controls
285516fe-0898-51d9-a904-1b08f820e527 | note | FREQUENCY: Prior to commencing any activity
5b5655e6-7649-5a46-8c5d-2ddbb48182a6 | note | – – – – – – – – –
04b1cdd9-458e-52c2-8604-ab0ee4a9f0d1 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
d7b1f933-9456-5903-bf23-1160bb1a858f | note | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
08291bc6-9661-5f5e-a542-3c40cee08158 | note | – – – – – – – – –
37182077-bafb-5afa-b38a-8e9ca5c7db61 | note | REFERENCE DOCUMENTS:
8a4b178e-ba97-52c6-8c42-73b812ced57d | note | • OHSCP
a9027a0c-b53b-55eb-970f-0b5bd93fb1c5 | note | • PHSCP
a364ba00-ba6d-5d2c-93a2-c289b53310a4 | note | • PCMP
9a7a43b6-ae37-5176-a31c-e3315458bcb6 | note | • EMP
c250e223-2710-530f-83d0-4b1940b357fc | note | • ECP
7e1b619b-1c6f-592d-b721-db6aaaf5d85c | note | • CEMP
6ba1cffe-753a-5c12-b922-22844d49bb1a | note | • ERA
d38878d2-7d8b-5810-982e-320ac31a36aa | note | • QMP
51263849-a1f0-516e-b795-d5fe16198912 | note | • CHMP
97a412fa-68f7-5b14-8515-b9ff71910507 | note | • SWMS
60933118-76d7-5891-b62b-b97a623d797c | note | – – – – – – – – –
b78425ef-fd41-584e-9996-ba31f6985325 | note | INSPECTION/TEST METHOD: Visual inspection
1a8df1aa-0dbc-53d6-a960-b0a1421afdbd | note | – – – – – – – – –
0e4c09c2-3880-5fb6-addc-ee9ebfca1dca | note | RECORD OF CONFORMITY: ITP Signed
2aa6eb25-9054-5a2a-8463-120142308090 | note | – – – – – – – – –
f4843b99-c63d-5780-93c0-8f2a1a51494c | note | HP*
1e9bd65a-cf61-579f-805f-d48ef0bb2b1d | note | – – – – – – – – –
ab65acf8-6271-53ea-a8b6-8ab2474036db | note | RESPONSIBILITY: Site Engineer/ Site Foreman
048e8851-ea59-5690-9564-5cd8caa7ecdd | note | – – – – – – – – –
2a654421-7630-512c-9c38-8f42c7e1ee85 | textbox | DATE:
4d6e7d7d-76c1-48ad-af68-f9a6dda32539 | section | 2 - Construction Works
5ed806b8-aadd-450f-8399-bab78dfdc8d8 | checkpoint | 2.1 Setting Out
99376105-128e-570a-ae5e-b258ff708fd6 | note | FREQUENCY: Prior to start
0b7954db-7505-5cc7-8079-363c9e5a4b54 | note | – – – – – – – – –
9e4d2409-7c1a-5599-82fd-ed36895ee639 | note | ACCEPTANCE CRITERIA:
5beed5d4-8f68-58b4-97fd-89a4c502f602 | note | • Set out work in accordance with drawings.
97c6438c-a4fa-570d-8f3b-9955eecd17e9 | note | • The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work.
2182e2b0-7ee8-522e-8fce-12cdee86f97d | note | • No survey/level pegs to be removed by any persons until completion of works.
72c17f4f-c31d-5533-a712-99b45fdb0496 | note | – – – – – – – – –
4956d7a6-6189-52c7-8204-e1572c8d5dd0 | note | REFERENCE DOCUMENTS: 703.17
e35c96d6-ccf1-5e87-814d-41b10b55078f | note | – – – – – – – – –
94f41070-bfbb-58a8-846a-aefdd930b8b6 | note | INSPECTION/TEST METHOD: Verify
39c75f9c-d923-57f9-b936-5e45a8e01a78 | note | – – – – – – – – –
19da107e-52f2-5e01-aef7-66aeaa03e367 | note | RECORD OF CONFORMITY: ITP Signed
1224eab5-a4d0-51a5-85d2-74dff33dddb7 | note | – – – – – – – – –
0af4d001-b34e-5ffb-920b-22a821df1242 | note | HP
a5571b91-cd04-567a-9e00-4914fdc8f596 | note | – – – – – – – – –
7514c428-bbc5-532a-886b-46868b0a4d37 | note | RESPONSIBILITY: Site Engineer/Superintendent
70555868-b8bd-5910-b1f4-2dff37a61ec7 | note | – – – – – – – – –
115a4bb1-0850-5866-b6f7-b3ec28ac4e4f | textbox | DATE:
a6567fc8-5928-42a5-9a31-26ea4af06951 | signoff | AUTHORITY HOLDPOINT
acfeb59f-dfa1-4319-81c7-365029fd8981 | checkpoint | 2.2 Temporary Drainage Provisions
8de9cf11-58b2-59e1-8021-07059a27fcd6 | note | FREQUENCY: If Required
7264d2a4-1c76-5248-8e4a-0059937e3fad | note | – – – – – – – – –
c43dec96-30ac-55f2-8ecd-2e40c42274aa | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
303953f7-9fdd-5996-98c6-c4bf30653570 | note | – – – – – – – – –
152cf31b-814a-59a9-8650-401cc46c4755 | note | REFERENCE DOCUMENTS: 703.18
630deb1e-aa8d-56c8-8e65-9b1ae9d0f59b | note | – – – – – – – – –
71870797-e818-58e2-bbff-439ed92bbdd5 | note | INSPECTION/TEST METHOD: Visual inspection
f599d0cb-3e82-55eb-926c-9d9e0263357f | note | – – – – – – – – –
c3d005e7-5945-5ba4-a773-00f337f355cd | note | RECORD OF CONFORMITY: ITP Signed
b017a2b0-3ba6-58ab-b3f5-b8d83201d480 | note | – – – – – – – – –
02305ce1-ae81-543a-b27a-2aaf37fbae73 | note | WP
945edc27-7628-5d90-bc38-0d848b1f16fc | note | – – – – – – – – –
f4e0596b-fc56-5a59-b69d-268636c22df4 | note | RESPONSIBILITY: Site Engineer/Site Foreman
193703b4-1bc3-5009-bc6a-ef8ae1b20c50 | note | – – – – – – – – –
6c734c0c-7c4a-5599-b5c5-865ce24e8c86 | textbox | DATE:
47107bbe-15ca-40e0-91c2-8355aef194ab | checkpoint | 2.3 Bedding
795b1f7c-c77d-5ad3-a19c-6cd9e10fd55e | note | FREQUENCY: Each lot
d931de93-54f7-581b-8a87-f105fa15aabf | note | – – – – – – – – –
dd61e57a-99ee-55e0-bdf5-f0fb80bc7d7f | note | ACCEPTANCE CRITERIA:
1e36cabd-0833-5902-baa6-7eff82ab1a8c | note | • All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
0b349df6-2f49-550a-88eb-7525431d8986 | note | • Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
9bc8577a-e25a-5522-ab8b-b739273a03ec | note | • Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
aa9dd859-6418-57b3-ba92-89835a0fea76 | note | – – – – – – – – –
6c0bf856-d811-53f5-a0ad-3edab33bba98 | note | REFERENCE DOCUMENTS: 703.21
83d14e4f-c08f-5d16-9801-6c4d8dc25dae | note | – – – – – – – – –
1fd37065-8385-5825-8d57-c645e289fb73 | note | INSPECTION/TEST METHOD: Visual inspection
fbba145b-2bb1-5511-b166-acc3510b2e3a | note | – – – – – – – – –
9ba243f6-d6a2-5c37-9ba4-f73daa77f8d2 | note | RECORD OF CONFORMITY: ITP Signed
11b19ec1-d3cc-59c1-b932-ef4025b1082b | note | – – – – – – – – –
2fb1132e-20d9-5b49-a22f-6338fc730e08 | note | WP
22364be4-d7c4-5525-89b3-f1d930ddb7a0 | note | – – – – – – – – –
48427923-a90b-549f-8968-1772dfff3b74 | note | RESPONSIBILITY: Site Engineer/Superintendent
c33c04a7-8ac4-5953-aa18-5227f52b5952 | note | – – – – – – – – –
0356508b-c264-59f8-83f7-a932412e6445 | textbox | DATE:
f7c78d68-88b0-489b-aad5-7efc9eb4db33 | checkpoint | 2.4 Pre-concrete check
87cf548c-cef7-519b-b1dd-709b26df3403 | note | FREQUENCY: Each lot
17575ef4-6e66-59d6-bdb9-9eec0092affa | note | – – – – – – – – –
f963e868-31d7-5b00-9906-a92a2d1accb8 | note | ACCEPTANCE CRITERIA:
77912da6-e9e3-508d-bc05-672c3bda3850 | note | • Bedding shall be moist but shall have no free water on the surface.
d2681944-7309-5351-b481-f7d98674e08d | note | • Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
b2c6a479-c6cd-5fed-936f-0a95c927869a | note | • Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
b3075079-3acd-57c0-8315-eed42ec76f71 | note | – – – – – – – – –
1c7de6c3-2e8f-593b-a566-d3f30c291b44 | note | REFERENCE DOCUMENTS:
e9e850fc-d5b7-53a1-86bc-b284fad63f87 | note | • 703.08
bdaa239d-4070-55f5-9ec1-05151bf59010 | note | • 610.17(a)(b)(c)
986c1e63-7f37-528b-9e0f-0fff70abb5b0 | note | – – – – – – – – –
5e925569-f708-52b4-901e-138b51938e9f | note | INSPECTION/TEST METHOD: Verify
9a987498-10c5-5faf-aa7c-dca3ad84180b | note | – – – – – – – – –
7a6a1411-a6f1-528e-a38e-7e5703b58d7a | note | RECORD OF CONFORMITY:
d3c6d9a1-1b8e-5447-bf6a-74be42303a3d | note | • ITP Signed
def861b5-6e51-559c-b824-b09e88d0aa85 | textbox | Ambient Temperature |  |  | °C
d24cc1cd-c859-5035-a8a1-99a54ce2671b | textbox | Concrete Temperature |  |  | °C
cd3ea674-f089-599a-981e-a906fbc20eb9 | note | – – – – – – – – –
48c5a81e-99a8-5840-af3e-1330a94580a5 | note | HP*/ WP
fe663b28-8c16-5022-8241-b97ad670e7ae | note | – – – – – – – – –
5b236cc3-5457-50e1-83c3-7b3eef093048 | note | RESPONSIBILITY: Site Engineer/Superintendent
9d66bcb5-cc09-5ee2-bb75-01d5b49ccd6b | note | – – – – – – – – –
23102525-7e78-55e4-bb7f-ca8314fb75cf | textbox | DATE:
79d69159-565e-4c87-9439-c7501fb8b62a | checkpoint | 2.5 Concrete Placement
77e2e8e4-1c40-5899-ba3a-9d1ee026e083 | note | FREQUENCY: Each lot
1a2eb05e-bebe-5767-a71d-d9f574234843 | note | – – – – – – – – –
9acf2f08-268c-5045-87f5-e024802a833f | note | ACCEPTANCE CRITERIA:
375b0eb6-6c3d-56a2-941e-b67c0648277e | note | • Concrete is to be fed to extrusion machine at a uniform rate.
656b3ca7-afb1-5d5a-9bfe-93714d72d7cb | note | • Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
37305938-5a53-5158-8790-d1dbe15ebc14 | note | – – – – – – – – –
76b083a3-fb3e-537a-9e37-c34c27ce4763 | note | REFERENCE DOCUMENTS: VicRoads Spec 703.23
2f4107cd-414d-562a-bcc8-0c9f58427338 | note | – – – – – – – – –
6111543f-5d13-53ec-b442-a2cbfcafe642 | note | INSPECTION/TEST METHOD: Site Inspection
1667d225-343a-5410-a1cc-3d52aeb26569 | note | – – – – – – – – –
c4aa2be4-8e5e-52a5-99f1-84f54cad760b | note | RECORD OF CONFORMITY: ITP Signed
61454fa4-01c4-51f2-bc1a-a74ca2a2173e | note | – – – – – – – – –
e62d26d1-59cb-5ed8-858e-00226bb2b57d | note | IP
c61aa294-1a54-518c-8a53-924152deda0c | note | – – – – – – – – –
68ef0371-321f-5176-aa87-0249321aae18 | note | RESPONSIBILITY: Site Engineer
31732788-3d48-5c90-82be-e9189b4bb3d2 | note | – – – – – – – – –
03eb2d92-2ac0-5b9d-8e45-8c7fc6ce5286 | textbox | DATE:
39192785-eb2b-4b27-ae90-0e4d55c30495 | checkpoint | 2.6 Finish Surfaces
f7c84ddc-089b-55a0-b34b-6a4d4c98ef55 | note | FREQUENCY: Each Lot
e8231066-6fa6-56ec-a2d3-df8c6cebed23 | note | – – – – – – – – –
39673602-fdba-5e55-a0c5-d42881fa0639 | note | ACCEPTANCE CRITERIA:
778acf38-8f6a-56a8-82ba-80bf96bd0f9f | note | • Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
cfc0f582-7568-5774-835a-e3b466d8eee5 | note | • Concrete to have a neat appearance and uniform colour.
5d1d80c2-ce6a-565a-817e-8a565d4c8af8 | note | – – – – – – – – –
a77e56fa-2454-5116-91dd-cd2cc1da5661 | note | REFERENCE DOCUMENTS: 703.25
0efbd5c1-0a14-5345-be3b-b91c2d5a25ae | note | – – – – – – – – –
ca78f1b4-47fa-53ee-965f-a220d3cb55f1 | note | INSPECTION/TEST METHOD: Visual inspection
c5543b1e-783c-5c02-aa14-2f4b63417d84 | note | – – – – – – – – –
0507697d-fd15-5488-9368-fe906e78ce20 | note | RECORD OF CONFORMITY: ITP Signed
652c06a1-700f-5400-882d-86230635d27b | note | – – – – – – – – –
4b3be738-03d5-51cd-806d-8a05a3a2d8b0 | note | IP
a2518fa5-0da3-57b9-ba13-b6550b3d18e6 | note | – – – – – – – – –
a87bcd57-ed4b-5921-8325-1a4b2dc02989 | note | RESPONSIBILITY: Site Engineer/Site Foreman
c7bb4e88-235b-5689-9a71-38a0fc19493a | note | – – – – – – – – –
a2b2c0e2-88ab-5470-8fe4-295294c2d184 | textbox | DATE:
a6f462ea-8992-4a95-be1a-96255fdbe996 | checkpoint | 2.7 Tolerances
e4e79516-e96e-5457-82e0-75fffee616d3 | note | FREQUENCY: Each Lot
1b021aa7-0768-5888-b3a4-17f8237af795 | note | – – – – – – – – –
8c964ed0-dd58-5d37-8223-3f50d0ec766c | note | ACCEPTANCE CRITERIA:
9653830a-439a-5601-8089-b37554f50285 | note | • The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
63ebd15d-ee0a-5f70-a661-64e387ba3bd7 | note | • Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
94966519-5109-59d3-81ac-ca86c41a9364 | note | – – – – – – – – –
a4c4fdd9-6174-578d-9c6e-17514080fcb0 | note | REFERENCE DOCUMENTS: 703.15(b)
86fe6407-ddf3-5f17-a0a2-92a1bba300e6 | note | – – – – – – – – –
a7d76552-77be-5689-a522-d94e771d5f4f | note | INSPECTION/TEST METHOD: Verify
7b5c7d55-8a0c-56a4-89b5-de9699574c98 | note | – – – – – – – – –
2e5a3b70-fb16-552e-9b7f-6cea9b70a163 | note | RECORD OF CONFORMITY: ITP Signed
f1d61d08-72a6-5e9f-b92f-70233650b7ac | note | – – – – – – – – –
4bab7ee9-669c-52ab-abd3-4fb05657057a | note | SCP
f16da58c-8d0e-5b11-ae4b-14616dff5b63 | note | – – – – – – – – –
17c6d535-123b-5f49-9d1f-834b22e5b01b | note | RESPONSIBILITY: Site Engineer/Surveyor
3d7f2fc6-593c-52ee-828a-d0fc6fb1bfcf | note | – – – – – – – – –
c8a1f81b-ece5-5d75-804e-e1d051018a20 | textbox | DATE:
ea9a167f-6053-497a-aa98-decd040caec0 | checkpoint | 2.8 Joints
dd8311a3-34af-56a4-b6e9-fdbca5bded97 | note | FREQUENCY: Each joint
0e1b5ee7-b724-5c07-a8fa-d67dacf05ea7 | note | – – – – – – – – –
6ae8a76b-94f0-56a7-86d2-b2caeecaed16 | note | ACCEPTANCE CRITERIA:
919720a0-e57f-53bb-b394-c760e37b21f7 | note | • Transverse joints constructed at intervals not exceeding 2.5m.
28bc0b21-c880-5e86-96fc-dc3d9607541c | note | • Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
033e6f45-ca03-54bf-a5f6-eddcf81922e3 | note | • Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
5e6bbda5-80e5-5b5a-a256-f9309923bc76 | note | – – – – – – – – –
3de74643-be1b-561f-b20d-b348faf790e5 | note | REFERENCE DOCUMENTS: 703.26
aa2efb35-4f08-50d0-9de5-62aaa0341059 | note | – – – – – – – – –
0c90d9b1-df34-514c-8af4-85d2a3070be0 | note | INSPECTION/TEST METHOD: Verify
a3005506-01bc-55a8-826d-e7934f626422 | note | – – – – – – – – –
6750a96b-6b1e-5197-837e-eed58ad2578b | note | RECORD OF CONFORMITY: ITP Signed
e2940e69-875a-5bb8-ba89-0673ddda466f | note | – – – – – – – – –
5ef6f14a-e40a-54c4-b282-e97144575e9e | note | IP
bdd97178-2569-5634-a8fd-14c2c9377205 | note | – – – – – – – – –
fe0390a4-ab8f-5d9a-94a7-62a224efb3aa | note | RESPONSIBILITY: Site Engineer/Site Foreman
36bbe274-fc69-52b7-aaba-263e3053c762 | note | – – – – – – – – –
44fbd684-4381-5045-bdf6-aa67e0ab9315 | textbox | DATE:
4abb07ba-baaf-4b06-a931-6a16d6d0edaa | checkpoint | 2.9 Backfilling
62f790b8-dd9e-57a4-92b4-592a951264d6 | note | FREQUENCY: Each Lot
81b787be-325c-5452-a3be-a7c93d49e055 | note | – – – – – – – – –
7275ba63-b64b-5965-bc62-4fd336b9083f | note | ACCEPTANCE CRITERIA:
a93f71bc-c708-54b9-a11b-38b67db16cc7 | note | • Not earlier than 3 days after casting.
32d2f877-e1b0-516b-b9b9-f4d839262756 | note | • Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
4a59eafb-530f-58e8-b7dc-5a824de4ce8d | note | • Layers shall not exceed 150mm compacted depth.
b8ad4e96-648d-5e61-a22c-18fd74441e0e | note | – – – – – – – – –
d0e1c8aa-f515-52ea-8042-72a6ac9f079e | note | REFERENCE DOCUMENTS: 703.29
5f39f568-0984-57c5-ac9f-0e33d31f4231 | note | – – – – – – – – –
ad3dad96-fda4-5792-a295-194d29321f9b | note | INSPECTION/TEST METHOD: Verify
84cc21f9-ec29-5bd9-a933-15a02ebfe09c | note | – – – – – – – – –
84f63311-d919-5a79-bed5-9abec51b7bd9 | note | RECORD OF CONFORMITY: ITP Signed
6512b9d9-aa69-5eca-82dc-ce06220c5906 | note | – – – – – – – – –
d9be1a80-fcac-519c-9be8-da20945de284 | note | IP
df036153-834d-58ee-9597-b34ab9b0ea95 | note | – – – – – – – – –
36415fe5-7949-5cff-a1f5-111e8b6441bc | note | RESPONSIBILITY: Site Engineer
904f2578-291e-514d-883e-fd37daa908f2 | note | – – – – – – – – –
7bbe6b29-5b58-5a42-babf-a96f257f2dab | textbox | DATE:
43ed5109-64dc-4461-a206-32ee4db64761 | section | 3 - Completion
4ceb43a5-57b6-4793-be82-9986ea93ac03 | checkpoint | 3.1 Survey data captured for as-built purposes
3e42bc31-5606-59b4-8c6d-a222594e90af | note | FREQUENCY: Completion of each lot
9f67e6b6-27a3-59fa-bfa7-60e2f781312f | note | – – – – – – – – –
150e805b-35e6-58ef-ba89-69a8792c48d0 | note | ACCEPTANCE CRITERIA:
fd8ffaad-b394-55b6-83f6-6d02bf882b63 | note | • Survey to ensure and validate that all works meet level and location requirements.
e3cba506-595f-5150-8465-c694141f0e8f | note | • Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
39605d7e-68cb-54c7-a3a8-f01de8df7872 | note | • As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
b514b54e-694c-5fdf-8cea-14a16d6d2b24 | note | – – – – – – – – –
6e17bf46-130b-55e4-99cc-b4a583ea80bf | note | REFERENCE DOCUMENTS: IFC Drawings/survey records
f817dcfb-2f5b-5240-a7d9-ae516a4df63a | note | – – – – – – – – –
42655b4d-ab6c-5d62-882a-da5340afe690 | note | INSPECTION/TEST METHOD: Document review
482074db-aba8-5ab3-add5-bc7483ba230a | note | – – – – – – – – –
45302b6b-4335-5a9d-b985-9d9c750858d8 | note | RECORD OF CONFORMITY: As-built survey records
64bc98fc-7274-5bc1-b3c5-7230b93415a1 | note | – – – – – – – – –
e3f86ddc-86ef-5ed5-be9d-cceca27e39ca | note | SCP
fe70f206-2445-556d-89f6-496ad5611a07 | note | – – – – – – – – –
fd8a4c0f-7b4b-5ac7-b883-ff7ad3d2905f | note | RESPONSIBILITY: Project Engineer/Surveyor
58c9edb0-1eb7-5cf9-ab9d-0eee5efa84ee | note | – – – – – – – – –
d0c515f4-7326-5e62-bcb1-8105d0aa6cda | textbox | DATE:
2decc002-2fad-4b52-a094-9f23861e71eb | checkpoint | Final Inspection
d8e1e2b3-d30a-5fc1-8820-aa622f98b46f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5620cfc8-6933-50b6-8ecc-a654b6d8b708 | textbox | Print Name:
893b2fdc-6876-560e-a0a4-3ba4a391aa97 | textbox | Position:
a4813c44-38b5-53a0-b94a-671b4fba75ce | textbox | Date:
0fef8d15-1d72-4a19-bf56-8090d0643d98 | checklist | ITP-01-016 - Sign Installation | itp | ITP-01-016 - Sign Installation
e3ad40e2-5f2f-43cf-97bc-dab2c9b5948a | section | 1 - Preliminary Works
795ddd1b-107f-4ba5-bfd3-10f9f1c4f0b0 | checkpoint | 1.1 Check for correct documentation
51e3b70c-3f61-5c2b-b97a-36e19706f708 | note | FREQUENCY: Prior to commencing any activity
891c5d78-11bf-54c6-a840-8813f0488203 | note | – – – – – – – – –
9576380f-7158-5ce9-bc77-bec75862f4e4 | note | ACCEPTANCE CRITERIA:
cab9a320-7dc9-55e0-b4b6-a1dc7e6d7880 | note | Ensure that all employees and subcontractors are:
8d365867-9b64-5888-bccf-83c7618c41fc | note | – using the correct and complete set of drawings
d5901f0e-19fb-5ce2-b3b4-b9e8dc7665f3 | note | – all drawings are the latest revision
3d549842-b714-5f53-a4d5-75c9632efb9f | note | – – – – – – – – –
fd7da33d-473a-5b60-b4f2-11222a7482bb | note | REFERENCE DOCUMENTS: Drawings and drawing registers
18467e51-7388-5571-ba53-5ad54ac5d175 | note | – – – – – – – – –
1496020d-e189-545c-b28b-152b94a7a09e | note | INSPECTION/TEST METHOD: Visual inspection
6b0c9dd3-d55a-5811-a97d-00e0e21634ea | note | – – – – – – – – –
7456da33-9be9-5db5-b017-728f0732c178 | note | RECORD OF CONFORMITY: This ITP signed off
de473d16-4082-56e6-b966-bedaa85d86f1 | note | – – – – – – – – –
c6585874-7412-56cf-a1dc-1c997b78e10d | note | WP
2bc6b121-2f53-5e4c-b89d-add0cef88c12 | note | – – – – – – – – –
664b9068-20c5-564e-8080-1d591711a3a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
f46cf662-2b36-5ac4-989e-8dca020886a0 | note | – – – – – – – – –
be678264-869c-540c-8395-8be08127b611 | textbox | DATE:
10ffc8a7-242a-4b7b-9448-a899900d60fd | checkpoint | 1.2 Implementation of all measures and controls
52d72c97-dc49-5d75-a187-65a9bd47dc96 | note | FREQUENCY: Prior to commencing any activity
b5e5fbb3-3c1e-548b-ba49-a46a0832f175 | note | – – – – – – – – –
f2cc4786-b342-5884-b2b5-2fde197ba705 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
b5f5f3e6-8e9f-5852-8870-64984c408529 | note | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
d5edec13-4d02-52b5-95bc-2193b144f6a2 | note | – – – – – – – – –
7c11d800-b1c8-5772-a5c2-8ab692f421fa | note | REFERENCE DOCUMENTS:
14db8af1-1378-530b-aa40-65a8dfbcd2f2 | note | • OHSCP
83de7be4-e3b7-520e-a5a0-26b5a3cc0434 | note | • PHSCP
8ced8aea-90e1-575a-9453-7ab8d255c37d | note | • PCMP
2dae06d7-24c1-5fdc-bc65-858a1ec73eff | note | • EMP
37e83795-3242-5fde-9807-59d64d36bd22 | note | • ECP
65068e98-6812-521d-8fb2-b5ae92a817b1 | note | • CEMP
78ec2384-2891-567b-bc1c-52b7a2278163 | note | • ERA
5d0e353a-4eff-5cc4-9d7c-dded27d606ce | note | • QMP
fe5f7383-d29d-5a4c-ae0f-4c1816866eef | note | • CHMP
ca96472b-5571-5dc2-95cc-75883d426826 | note | • SWMS
34088ecf-c378-524b-9033-df2d44bb00b8 | note | – – – – – – – – –
adfb09ca-5a6d-5c33-958c-dd2ba03fad38 | note | INSPECTION/TEST METHOD: Visual Inspection
70dc62e8-fa83-541b-aade-3319f90650d0 | note | – – – – – – – – –
ff00d4cd-27bf-5f0f-babc-7a573c27f9c8 | note | RECORD OF CONFORMITY: This ITP signed off
1f405936-24c1-59d1-803d-66047184ce53 | note | – – – – – – – – –
22090f6e-fb67-5a44-8d30-73e80ca9cb18 | note | WP
0ac1687c-789c-53af-bd68-cff563888e62 | note | – – – – – – – – –
dbd977bc-5137-5eff-8a3f-8d5998153a59 | note | RESPONSIBILITY: Fulton Hogan Engineer
b8f3c7ab-d204-5bed-8eee-006bb1b33290 | note | – – – – – – – – –
aec57eaf-919a-5cb9-8334-9c5ae46cfe24 | textbox | DATE:
9aaaa209-a758-404d-9723-68dbfa800554 | checkpoint | 1.3 Signage Conformance
960b137f-08d5-50bf-8bd7-28367bcd866b | note | FREQUENCY: Before commencement of activity
b58bc039-4167-5742-bade-de01a7787740 | note | – – – – – – – – –
5ed4d1ba-27ee-58c6-bc06-9b5fb0573123 | note | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
418e8a3a-0a8d-5780-9d90-48613399713b | note | – – – – – – – – –
9a29e20f-3f68-5651-b0b9-aebc1eed5efc | note | REFERENCE DOCUMENTS: Drawings AS 1742
0fddc2ad-7544-5c75-ad31-c589582b9d0b | note | – – – – – – – – –
7f555a4d-9c44-5fed-bb7a-7749cc73fac0 | note | INSPECTION/TEST METHOD: Verify
0c184d97-fb7e-5276-ba6d-49e0ae9dfcb5 | note | – – – – – – – – –
9ba34cd5-d6c4-5f25-894a-99d4e5f2a953 | note | RECORD OF CONFORMITY: This ITP signed off
b896b82b-434c-5924-9ed6-ca4fcc9d3ad4 | note | – – – – – – – – –
75dcae04-e136-5e23-9f86-3958eaa7cf08 | note | WP
a81e8761-a75b-52f7-a681-7f03c859c01d | note | – – – – – – – – –
af61410d-631b-5bce-8e3f-16c995332799 | note | RESPONSIBILITY: Fulton Hogan Engineer
58bbb420-1721-522b-8f7d-4b035cc44457 | note | – – – – – – – – –
606de51f-d8c7-52c7-9188-1e847584c0d2 | textbox | DATE:
3760655f-59d6-4850-842d-cd06f5011321 | checkpoint | 1.4 Service Identification
78ce14a2-23aa-5467-aa3a-ea4c77bd6f2b | note | FREQUENCY: Prior to start
8ca6cc5f-10a8-5cf6-8712-002fe51f1a1c | note | – – – – – – – – –
c9fade48-cbd1-5a52-943b-4c05c73b2310 | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
79675450-1647-5b8b-b937-d4643bf940e6 | note | – – – – – – – – –
ba4e52a5-663b-5501-963e-44b104aca928 | note | REFERENCE DOCUMENTS: DBYD, Service chart
a99bbefb-8552-5a6a-b25d-3a4f049f3a6c | note | – – – – – – – – –
97ade055-6699-53ac-be35-8f7c321d6a40 | note | INSPECTION/TEST METHOD: Verify
6852fecf-9e66-51a9-949c-a5690e489f12 | note | – – – – – – – – –
387d3559-fd7b-5d4c-a858-9dbca93b5f4b | note | RECORD OF CONFORMITY: This ITP signed off
d7b9f0ab-895e-58dd-aa40-7382edf44dc0 | note | – – – – – – – – –
938d71d9-ed85-5f83-9f72-05e6e7448cf1 | note | WP
311dd70a-e24c-5fae-9815-01ff9cc5e406 | note | – – – – – – – – –
83bd3925-cd3b-57ee-a609-4b3898229c97 | note | RESPONSIBILITY: Fulton Hogan Engineer
7faede91-935c-5bc8-ae1d-74b6bc6e11cd | note | – – – – – – – – –
57cb20d5-d0ec-5b8f-8e2d-99b6cc696b2b | textbox | DATE:
43ed9759-debe-49f1-9e92-99659267547f | section | 2 - Construction Works
d4af30dc-e0de-4da9-8b1b-4b2309e1755f | checkpoint | 2.1 Setting Out
8cebf642-8656-5a0a-b1f6-861cb867ae27 | note | FREQUENCY: Prior to start
329bb629-e8f9-5687-9493-fbe56479597a | note | – – – – – – – – –
c116e78d-26dd-5f84-82f4-8c1020755e5b | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
39617d16-12f1-5c33-969e-9fb7fea466c5 | note | – – – – – – – – –
824d0334-c9d5-546c-9ee9-d6b09ad6f131 | note | REFERENCE DOCUMENTS: Drawings
a98dd9d8-30cf-54bd-8c8f-a4fd7d457db9 | note | – – – – – – – – –
582835ce-283b-5109-9216-f01cebec6870 | note | INSPECTION/TEST METHOD: Visual Inspection
1ad0f379-b79c-5abe-a08f-33a6e24b9a57 | note | – – – – – – – – –
c075f6d3-bb86-5093-86d9-2da63ee14906 | note | RECORD OF CONFORMITY: This ITP signed off
11fbbdb5-73a8-56cc-99f8-e4f6b34005e2 | note | – – – – – – – – –
163b7919-fe1b-5895-a6e8-dbdc91c62e72 | note | IP
02810ea5-e892-5921-b12c-0588645e37bf | note | – – – – – – – – –
5f41179e-3388-5780-ba93-8076f3d47716 | note | RESPONSIBILITY: Fulton Hogan Engineer
facd9c88-c157-59c7-86f1-966730202480 | note | – – – – – – – – –
452d5380-c86e-5993-aa00-f33135c163bd | textbox | DATE:
5bcd77aa-600b-4140-8180-ca35a57ce694 | checkpoint | 2.2 Post & Foundations
7ebfae48-2bf6-5c63-a61c-4002724e56e1 | note | FREQUENCY: Prior to Start
5af3fc1e-a262-52ae-ba07-ce9fb1cd13d1 | note | – – – – – – – – –
2c3e7302-9507-5f7f-b907-9fff97a941a7 | note | ACCEPTANCE CRITERIA:
285ab992-c274-5cce-ab77-619cea2f38f5 | note | • The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
9773f545-0f92-58ed-84f6-6ea2b62b3db6 | note | – – – – – – – – –
21947b50-b3ca-5cf0-a6c0-3ba76f850c31 | note | REFERENCE DOCUMENTS: 714.06
8371540c-7441-50b0-a124-099f3333b8a8 | note | – – – – – – – – –
eca7fc29-88ad-53ec-9813-cd44acf6effc | note | INSPECTION/TEST METHOD: Visual inspection
61696e1b-806f-577f-b2c8-d4589c1adfc0 | note | – – – – – – – – –
6368b685-0756-503a-a9ab-01c4f00ac6e4 | note | RECORD OF CONFORMITY: This ITP signed off
e9e76c41-3eef-5663-8c8d-5b4601728648 | note | – – – – – – – – –
26c618c4-3fc9-5765-905c-69328ec2e525 | note | HP
87c5fbd9-aa2a-5ae2-95ff-31a9f72f5095 | note | – – – – – – – – –
1166e3bd-748b-5651-b876-3baae13a9955 | note | RESPONSIBILITY: Superintendent
ab504a7d-f780-58f7-95b5-811cc972951c | note | – – – – – – – – –
37a76c0e-38f8-5bad-a4f2-6271adf10ec0 | textbox | DATE:
1ffdef35-aba1-47f4-8978-9462c629a8ad | signoff | HOLDPOINT AUTHORITY
51bcabb0-b331-45a1-af7f-3641d4ebbec9 | checkpoint | 2.3 Signage Install
00f3c27c-cc3f-5a84-9f22-6222f63135c8 | note | FREQUENCY: Each Sign
d39213d9-4fb2-5c26-a677-4a6ce52892e9 | note | – – – – – – – – –
d5899b33-6e3c-586d-940b-5e2a65f2cff1 | note | ACCEPTANCE CRITERIA:
2bcdd7b5-ee45-5d5f-b477-dcac32a1a0b2 | note | • Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
79c1a1a3-ed43-50c3-9eed-cab062ace2d2 | note | • Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
3884e992-5bfd-5603-a771-50d24dc17a55 | note | • Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
d3c26a56-5f36-5625-a430-2b57bfec2a38 | note | – – – – – – – – –
971f38fc-928b-5546-83f4-121ecafd8c32 | note | REFERENCE DOCUMENTS:
d8f8b302-4ae4-5099-b795-b5bb567e95c1 | note | • AS 1742
551d3c71-6778-570f-af57-d0cc3bab24d7 | note | • TS 1313
6d7516a4-3d7e-5b8c-b05d-bea5d63670b2 | note | • Drawings
914362da-dab8-5bfd-94b4-5ed4e701d54c | note | – – – – – – – – –
79043980-3dc2-5c12-98b3-e8478bf9a81e | note | INSPECTION/TEST METHOD: Verify
9fd9c4f2-0782-57bf-bd92-66333d338738 | note | – – – – – – – – –
b8b3c2a4-9ef7-5967-ad0c-c752def52b9f | note | RECORD OF CONFORMITY: This ITP signed off
e180e04d-82c1-56a9-9a4f-75c9cf634275 | note | – – – – – – – – –
bfee8e97-f128-5ac8-8199-b42cbbb5c20e | note | WP
181a2e9b-f23d-541f-8366-98c0d84087d7 | note | – – – – – – – – –
085f9f16-7d3c-5832-88fa-3669f6bd29b0 | note | RESPONSIBILITY: Fulton Hogan Engineer
4d0db9ed-81a1-5a7e-9e4d-6163ebbab5d5 | note | – – – – – – – – –
4f8ee4cb-2c77-5776-aa5f-6fdc5795db49 | textbox | DATE:
7c66d685-c03f-4cb8-a19d-64a2a9a01895 | checkpoint | Final Inspection
ece6394c-b71d-537e-8c82-1fab5d021e8e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e4cc82be-4b7b-50e8-8c3a-d5848831bb51 | textbox | Print Name:
d180c87b-3f22-564d-9cbe-4fdee2e4e5ac | textbox | Position:
eb7a406e-697d-5501-84e3-9a643e9e2f6a | textbox | Date:
c9ed9e08-a201-4c46-a65e-075ae30d801c | checklist | ITP-01-018 - Landscaping | itp | ITP-01-018 - Landscaping
121a8a52-d151-4982-a95f-b064c50cf02e | section | 1 - Preliminary Works
52d82557-62da-4884-9f1d-c2a93d31eabd | checkpoint | 1.1 Check for correct documentation
04760756-b7a3-5cce-af2d-beb9a156d9d0 | note | FREQUENCY: Prior to commencing any activity
a03ba8b7-caf1-5df3-80ba-3f3a17191573 | note | – – – – – – – – –
af75c706-af9c-5d51-a6a5-1188b092bcc3 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
75195bf2-fa51-504c-a739-ef618743512e | note | – using the correct and complete set of drawings
e601ac01-74c9-58e7-9b78-9ef215f4f997 | note | – all drawings are the latest revision
9687aeeb-03a3-581f-830c-3eb62dddc7b9 | note | – – – – – – – – –
e4c4859e-6d72-56f3-83ba-19f178a20448 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
bb0fa257-2aff-527e-92ac-dc79dfbe696d | note | – – – – – – – – –
6132890b-4c2b-5981-b3fe-c0797eb735f9 | note | INSPECTION/TEST METHOD: Visual inspection
d80a484b-72e9-54b3-b923-3969c827329c | note | – – – – – – – – –
b3fe830c-c344-526a-ad06-4639ea4d9fea | note | RECORD OF CONFORMITY: This ITP signed off
445181fe-e887-5c7d-b4cb-daf17d402bba | note | – – – – – – – – –
b35525ae-b691-5df7-9b75-1b0dce0b729a | note | HP*
84c4ec32-5d06-54e3-b726-ff76f7482c64 | note | – – – – – – – – –
732a6823-a289-55a7-bce6-07ba1db51324 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f083e6c4-a6ef-51e1-9a4e-6226bc525ae6 | note | – – – – – – – – –
fe9d6f58-2c3b-5fa7-ab73-843f111351d9 | textbox | DATE:
febe8683-2515-49dc-8c7a-0a8542590ada | checkpoint | 1.2 Implementation of all measures and controls
89dbdc56-39df-5aef-bc0c-19d4baf60653 | note | FREQUENCY: Prior to commencing any activity
edea6ff2-033d-5ff5-be79-2597ca5a387e | note | – – – – – – – – –
0d84d5da-910e-5947-8285-e714a078cc12 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
29107d31-256c-5f0e-9782-ee1124089fb0 | note | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP
7f02ee95-3464-59fe-b644-b24d21db3f9e | note | – – – – – – – – –
3be196fc-f041-5c94-aba8-bc60c4a418c2 | note | REFERENCE DOCUMENTS:
29f67d97-6964-51b0-924f-3a6e2e9a71fc | note | • OHSCP
13eb7e8f-27e8-5ca2-9200-c7569664fd63 | note | • PHSCP
b211646c-5a22-501d-aa8b-be0e35d62331 | note | • PCMP
d345773b-b1b8-5e39-abbf-8e31fdaeb870 | note | • EMP
965534e4-025b-5abc-8022-570340daa25c | note | • ECP
0b6f73ca-a8d7-53f3-b0b1-c5079b8cb89e | note | • CEMP
b903008c-1b46-589c-814e-4ebee1df306f | note | • ERA
ba7f96de-ffc9-5089-a7b1-8e1e7d4c7267 | note | • QMP
9af4f1d6-266a-58ef-b3ca-d9bfdeed73be | note | • CHMP
a387dc24-1d57-52b0-acde-e69caaa2a04a | note | – – – – – – – – –
d4e46ec6-c9b2-5561-9249-866c6013fef4 | note | INSPECTION/TEST METHOD: Visual Inspection
7e89e024-56d5-50c6-b8ee-12f93e2023ed | note | – – – – – – – – –
184859a5-d1ba-5262-bc09-f18a9efaf27f | note | RECORD OF CONFORMITY: This ITP signed off
dc5c0dfd-871e-589d-80e7-93eb12064dc5 | note | – – – – – – – – –
69ee056a-3f2f-546b-a32d-405018887265 | note | HP*
781b88de-8428-5958-a7c4-3cc40c9037a8 | note | – – – – – – – – –
60268e5d-64a9-550c-9953-79ec92f9d7c1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
1fa06c30-45b5-5aee-8d03-5a17974bddec | note | – – – – – – – – –
08545217-b8aa-5474-b918-052768ef91cd | textbox | DATE:
9cf4fe1d-a54d-4273-8f6e-3c97d6943f3f | checkpoint | 1.3 Submissions and Records
ac8c0462-4422-5b43-ae6a-003857dbbacc | note | FREQUENCY: Prior to commencing any activity
2f1f8e59-cd00-596a-b8e5-b63f20fc8a39 | note | – – – – – – – – –
5c8e252d-6bbd-575e-9a6b-9a6d47c13232 | note | ACCEPTANCE CRITERIA:
17cf2c39-c9aa-5d59-9a98-1d8e3784511a | note | • The specified inspections, samples, records and certificates shall be made available or submitted to the Superintendent for acceptance prior to the commencement of associated work.
aa953884-7dc2-5ba1-b64f-1ac781df8d8c | note | – – – – – – – – –
b2269116-2c97-5ea6-af19-9df1be16d7df | note | REFERENCE DOCUMENTS: 720.03
081e6af4-f0eb-595b-98eb-79f4c5141278 | note | – – – – – – – – –
713bd0d9-cb77-59e1-9d5a-f2be768e8be7 | note | INSPECTION/TEST METHOD: Visual Inspection
5fb8d0dd-aa12-5167-afbd-d16c2511984d | note | – – – – – – – – –
729812c8-bb4f-510c-995f-57852423303b | note | RECORD OF CONFORMITY: This ITP signed off
73f2e5bd-0501-576c-b767-99e6bf96fedd | note | – – – – – – – – –
2d8a2147-2d55-53db-8738-e8911bf0c801 | note | HP*
bbfedb2f-2509-58d4-b04c-80e764dc47ea | note | – – – – – – – – –
94713297-bace-5bc6-9d61-16b7da59215d | note | RESPONSIBILITY: Site Engineer / Site Foreman
aa945339-a691-5206-895f-e052ea42ab4e | note | – – – – – – – – –
4a5d7b62-594c-5cd5-b6bd-30feeb8ca0ab | textbox | DATE:
86de12ab-d601-433b-91fe-3e84acec9be1 | checkpoint | 1.4 Permits
f8338be2-a0be-5501-82b9-bda7699daeb4 | note | FREQUENCY: Prior to commencing any activity
8c3dbabd-c27a-5541-a95a-cfe425bef7b0 | note | – – – – – – – – –
929e43db-118e-5c6a-96f4-ff1dc19707e2 | note | ACCEPTANCE CRITERIA: The Contractor shall obtain all necessary permits and obtain approval from the Superintendent prior to the pruning or removal of local native vegetation.
a42e11f5-702f-5479-87f1-4d77dd2855bb | note | – – – – – – – – –
11a31a71-0562-5930-89be-b179c83b4424 | note | REFERENCE DOCUMENTS:
19245c46-59eb-5835-8358-ef2a5702b33e | note | – – – – – – – – –
f1721574-1fe5-51ab-9690-842defc1a1b7 | note | INSPECTION/TEST METHOD: Visual Inspection
fb16af72-e24c-5818-b698-f1678be1fbbb | note | – – – – – – – – –
a64fdbfe-28ed-5878-9aa9-f1e6c3161e7f | note | RECORD OF CONFORMITY: This ITP signed off
b654e6a9-06db-5bb3-8e1b-32c8dd1819cd | note | – – – – – – – – –
7769fadb-3c43-5443-8551-df055407b1e9 | note | HP*
c04a61bb-6793-5986-877f-2c564823f023 | note | – – – – – – – – –
189f229f-dad1-5cfb-96e2-10e9534ee1dc | note | RESPONSIBILITY: Site Engineer / Site Foreman
38ede1bf-b2e7-559e-8ef4-7934b29ac1f0 | note | – – – – – – – – –
3bbd2a16-54b0-5220-adf7-d8abb0204f9d | textbox | DATE:
3e0659e5-7009-4073-a88d-3db176d121f7 | section | 2 - Construction Works
4f4f9afd-9e86-4ed3-b7f4-53573caffafd | checkpoint | 2.1 Excavation Permit
87a3b705-9994-5d8a-9b2c-8e5964bbb2cd | note | FREQUENCY: Each lot
c8583d38-e2f4-5bc1-b90b-aa7372e7b8eb | note | – – – – – – – – –
b988d0e7-c4e1-50cf-90f1-13a1912f1831 | note | ACCEPTANCE CRITERIA:
7d5b72f5-f177-5274-a0e7-fb25839d44fe | note | • An excavation permit must be issued prior to any excavation commencing.
536faa30-6a6a-55d3-86a8-bf05d3659593 | note | • Plant and equipment shall be appropriate for the task.
c18c45d3-37ea-5d93-86dc-f3b979d713f5 | note | • Excavation operations shall not disturb areas outside the limit of excavation
74d9a23d-c024-5ab6-8ea4-3feb9ca33a17 | note | – – – – – – – – –
7e8d814d-784c-5581-a608-576427bcf572 | note | REFERENCE DOCUMENTS: Excavation permit
cf6f5050-1618-5f9b-9785-278b735eeac8 | note | – – – – – – – – –
f4df538f-9ee8-5ab4-a433-49caa2e1f6dc | note | INSPECTION/TEST METHOD: Verify
6259c9d6-0d2f-5a6e-8281-072c4aae40d2 | note | – – – – – – – – –
9ce5176b-0cfa-55c3-9c96-f1164c29c6b7 | note | RECORD OF CONFORMITY: This ITP Signed Off
edeb56eb-bd82-50dd-98c0-cb53e7efec12 | note | – – – – – – – – –
a9f6c071-17e7-5977-9a09-376113ca60c8 | note | HP*
fc21de77-ca49-5053-a9ad-b3e0b8900968 | note | – – – – – – – – –
e9395bd2-8166-5ce9-8d35-4c31f6b96cfa | note | RESPONSIBILITY: Site Engineer
d4ee9c12-b3f7-51c9-b559-518df0f76379 | note | – – – – – – – – –
e6d1ee3a-9499-574b-943c-141f79f195c0 | textbox | DATE:
fe0f2fcc-91aa-4293-87b4-058ee820768a | checkpoint | 2.2 Setting out of landscape softworks
c8e55017-b78b-5485-ac7f-80eb423f07e4 | note | FREQUENCY: Each lot
bef52924-a414-5011-a03a-cde6b8bcf0da | note | – – – – – – – – –
7c9761b1-45ef-5b39-8184-a39111f277c7 | note | ACCEPTANCE CRITERIA: The Contractor shall set out the location and shape of planting areas in accordance with the Landscape Drawings.
a0bba96c-f911-59a7-9540-6617c1331eb8 | note | – – – – – – – – –
1c2cd276-13e1-5682-acd9-3e1c77de19bc | note | REFERENCE DOCUMENTS: 720.06
0a46213d-1b81-5c0c-b30c-23f265ca64f4 | note | – – – – – – – – –
dbb29168-be68-56bd-a766-89e6b5c7f665 | note | INSPECTION/TEST METHOD: Visual Inspection
bdd616e1-a061-540d-979f-f6ad7c627018 | note | – – – – – – – – –
1effd033-de98-54a9-a8a2-25f2b9960dc9 | note | RECORD OF CONFORMITY: This ITP signed off
76535e7d-25f7-5b5f-a0f8-fec7e7fbca15 | note | – – – – – – – – –
28a0b01d-5f5e-507f-a2c9-4141c6fa915f | note | HP*
86a35263-b223-515d-b76e-fdb94fcdf6be | note | – – – – – – – – –
34e9b56b-6aad-57ea-92a8-e0c5fb03d5ea | note | RESPONSIBILITY: Site Engineer / Site Foreman
240f3e0a-42a7-5bdd-bc24-f8f39b7a927e | note | – – – – – – – – –
63df7bbf-1ff7-58cb-8df3-e54fdf275e02 | textbox | DATE:
c07813db-8faa-4213-96ae-20efa8b9da3d | checkpoint | 2.3 Supply of Materials
3053e9d4-51b2-5468-b02c-da35ed8a6777 | note | FREQUENCY: Each Lot
920cc0ed-9c9c-542e-b01a-98895b89bbea | note | – – – – – – – – –
7c82e8bf-2ac7-53f2-8d15-09064700e940 | note | ACCEPTANCE CRITERIA:
30daca65-93d6-525f-aa61-05f4c54525a6 | note | • All materials shall be supplied by the Contractor unless otherwise noted.
0a3ecfa5-b1c0-5227-ae37-60f3c3cc593f | note | • If any materials are supplied by VicRoads, a joint inspection of the materials shall be made by the Contractor and the Superintendent following delivery of the materials to the site.
8020c70f-3235-51b3-8ad5-cc1d743afaa9 | note | • The materials, if satisfactory, shall thereafter become the responsibility of the Contractor.
c5ce3a94-7a48-570f-80d0-5413c0f207f2 | note | – – – – – – – – –
88490b63-0b38-5890-9b2c-62138abfe7af | note | REFERENCE DOCUMENTS: 720.04
552f2288-a50f-5a7e-9aed-df51cbe1673f | note | – – – – – – – – –
ca59f051-6112-5cee-b6e2-f39bd5d0dbb1 | note | INSPECTION/TEST METHOD: Visual Inspection
a1dac5c7-3d48-5448-b3da-3c663c210dc7 | note | – – – – – – – – –
8c54753c-730d-5762-8e6a-ceb54c2646a3 | note | RECORD OF CONFORMITY: This ITP signed off
fdc82160-d60f-5f7c-9424-83827dc7d2f8 | note | – – – – – – – – –
ca716ca1-60dc-508b-93ca-6ede7d87081a | note | WP
edc89b2e-4931-5a8d-bc71-7e688ef0eaf2 | note | – – – – – – – – –
3d56ddb5-010f-5f70-9221-e8a00e46dfc9 | note | RESPONSIBILITY: Site Engineer/ Superintendent
d53a0cee-b238-56eb-ae5d-e5aaf509a724 | note | – – – – – – – – –
8477f311-2fbd-51a1-b084-39c52b64e213 | textbox | DATE:
2436b8cc-8364-43b5-aed6-b84082b74845 | checkpoint | 2.4 Pest and Weed Control
d43f8afd-177c-57e0-9c9c-03d28b38a67d | note | FREQUENCY: Each Lot
ebb39971-6693-5740-b34b-a53423259392 | note | – – – – – – – – –
b6a00920-c46c-589e-8220-23bd29c35ba9 | note | ACCEPTANCE CRITERIA:
6fa61e76-f114-5e5c-b3fa-26f607d2bd89 | note | • Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
e078075b-a3ac-5bec-826b-02da6fed3199 | note | • Weed control shall be programmed and implemented to deplete the potential weed seed bank within the topsoil to be used in planting beds.
8a062f09-6d3d-55ba-9345-830ba6ff5bf3 | note | – – – – – – – – –
2af11b70-9e09-507c-83d7-4504919b048d | note | REFERENCE DOCUMENTS: 720.05
98e97563-8266-57ee-b57e-263af9809171 | note | – – – – – – – – –
894a0fd2-f15c-5c9b-8594-719d347a2588 | note | INSPECTION/TEST METHOD: Visual Inspection
d3d46e3e-8cbd-5d3e-bf69-a4bfc01da04a | note | – – – – – – – – –
636a182b-a75b-5d33-8b76-22a24128d80e | note | RECORD OF CONFORMITY: This ITP signed off
4879159d-1c23-591f-adbf-d4c5b918d5e6 | note | – – – – – – – – –
db7fb155-9b04-5be3-8777-fd7c8c069869 | note | HP*
fd26d272-b954-587d-b07a-67748d6e48a5 | note | – – – – – – – – –
83280f53-c5b4-53f1-9f44-eee25d336740 | note | RESPONSIBILITY: Site Engineer / Site Foreman
151c48b6-25fb-5fa5-b814-e2ac85f631ba | note | – – – – – – – – –
545d16ee-9166-5832-b0f4-ea0e1c7e0641 | textbox | DATE:
18d0a6c5-24e0-4611-91fe-bc91f1e1854f | checkpoint | 2.4 Fertilisers
020a041e-4095-576a-bbe1-a73e2a3c4fd6 | note | FREQUENCY: Each Lot
36741acb-41af-5240-8fab-fc85d93d9f6d | note | – – – – – – – – –
3bbff3f4-b7be-5c19-bd75-1ec141aaa89e | note | ACCEPTANCE CRITERIA:
1899466c-2e6b-5af6-a08f-ffe66431bedd | note | • Fertilisers for planting areas and advanced trees shall be slow release with a 9‑12 month release period and suitable for the establishment of plant types, sizes and species specified in the plant schedule(s).
82c40e88-fa00-5e10-88d7-60abe1036381 | note | – – – – – – – – –
4bca9cf5-156f-58f3-a7b3-e9c424efc129 | note | REFERENCE DOCUMENTS: 720.04(f)
1b952698-46b2-50f3-adb0-20fd050300e2 | note | – – – – – – – – –
7c42979e-e7fa-5bf7-92ba-a5016379dfc9 | note | INSPECTION/TEST METHOD: Visual Inspection
188b5168-9ab0-5a39-8d8c-6c93c5d5c5ae | note | – – – – – – – – –
320d7edf-cc80-5250-ad76-4f69bb2d7ab8 | note | RECORD OF CONFORMITY: This ITP signed off
dc29a9ac-333d-59f6-a6c1-8c8d10767c05 | note | – – – – – – – – –
cbf3a01c-4346-56a0-80c4-11dff0cfc506 | note | IP
52b24c88-daed-56f7-b740-66f7dd81c04d | note | – – – – – – – – –
803b86e7-03b5-5f8b-a2ff-e27faaec4fb8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
cb22504a-f860-5f5a-9391-29efa2496979 | note | – – – – – – – – –
3db700fd-6b85-5bea-a4f2-7fa6a3dbc05c | textbox | DATE:
8e3fd6d6-1ec8-4c9c-be8e-bec7a36f3f47 | checkpoint | 2.5 Mulch
82f3999d-85f7-54a9-b2fa-bda4fa203ea8 | note | FREQUENCY: Each Lot
a5138644-dc28-5575-8ef6-dac6ffd0d04e | note | – – – – – – – – –
9a026807-548d-58dd-812b-4b00f93b0f64 | note | ACCEPTANCE CRITERIA: All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454.
aab50839-6a33-54c9-bb55-882508b6135b | note | – – – – – – – – –
033cbb61-c223-5662-b2fc-f8f2fcf15ce6 | note | REFERENCE DOCUMENTS:
9e392038-9b0b-5d98-b6ee-bb0638b2733f | note | • 720.04(h)
d78680ec-96de-57ff-87cc-87ecda38f2d6 | note | • AS4454
ff4743a8-2623-5722-8220-da98648b1afd | note | – – – – – – – – –
4a6bb56c-0992-5d85-a490-4e6b5e46aa00 | note | INSPECTION/TEST METHOD: Visual Inspection
759bd31a-2f7d-5e59-b241-13c56a3d1823 | note | – – – – – – – – –
d9b2e73a-dc9d-5d72-af5f-4f92900b75bc | note | RECORD OF CONFORMITY: This ITP signed off
4c98dbde-9bcf-5a9a-b5ca-a98cf415989f | note | – – – – – – – – –
e4613fdc-a31b-5e43-8a46-6425029e0473 | note | WP
815efee1-7db0-5038-9878-075d25b132a7 | note | – – – – – – – – –
a70227ca-ed9e-5db6-9a27-b6275ea66f60 | note | RESPONSIBILITY: Site Engineer / Site Foreman
8678926d-6e51-5e2b-bfe0-d000bdfbe260 | note | – – – – – – – – –
4ea166ed-6db7-554a-8a8e-0d42fe18da20 | textbox | DATE:
f4bc68c6-d612-4d3f-8bdf-57f38eed7613 | checkpoint | 2.6 Weed Control Mat and Erosion Control Mat
73e13e2c-3057-5f78-ae55-ef871e555d2f | note | FREQUENCY: Each Lot
299a3e76-ebbc-587f-b336-ae1714fd23d1 | note | – – – – – – – – –
24271c61-3d43-5385-b8fa-98a1b85ac3df | note | ACCEPTANCE CRITERIA:
f22c5d0b-4e4b-5d77-be4e-16c97c2d710d | note | • The Contractor shall supply and install jute or approved equivalent, biodegradable, fire retardant weed and erosion control mat as indicated on the Drawings or as specified.
069132e8-f78e-58c4-8db7-b1e254e38d82 | note | • Weed Control Mat shall be minimum 700 grams per square metre and Erosion Control Mat shall be 300 grams per square metre.
a9658239-575c-5aca-b163-a19f6220f791 | note | • The surface of the mat shall permit water infiltration.
a97f8052-2f2f-5b98-96b4-590a33245597 | note | – – – – – – – – –
fa3092f3-7d2e-50c4-8731-55b5dec16b92 | note | REFERENCE DOCUMENTS: 720.04(i)
2866d0b1-d067-542a-99eb-b3ab644651f1 | note | – – – – – – – – –
1b97390a-5990-51c4-9756-bcb4ab213b5b | note | INSPECTION/TEST METHOD: Visual Inspection
f75c6b8e-dcb8-5ca6-9072-63628b1f298f | note | – – – – – – – – –
e4e18567-4d15-5cfd-98a5-6b04973d82c4 | note | RECORD OF CONFORMITY: This ITP signed off
e7ead351-1906-5263-a913-b8d730d83cb8 | note | – – – – – – – – –
b7012045-12c0-5202-87a4-f397d680686a | note | IP
86f49b19-73bd-56b1-8150-d3eee4ab3a9b | note | – – – – – – – – –
b734926b-02a2-57cf-9f01-141764fc55a2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0af652cf-2e47-5bb9-bdc2-016639062dac | note | – – – – – – – – –
0712cb84-fbbe-5dad-81c4-3c6cb3855077 | textbox | DATE:
8f353512-4a08-4566-9968-5a91c9ab1920 | checkpoint | 2.7 Ripping
fc902fe1-2be6-5b86-b8e0-2fc353921e42 | note | FREQUENCY: Each Lot
82697a2d-2178-5688-9efc-3b64abb6660c | note | – – – – – – – – –
4ed917bc-1303-5d06-b574-9a4fce9a831a | note | ACCEPTANCE CRITERIA:
586b3010-caf3-557b-bf3b-7c9232df347d | note | • The Contractor shall make available each ripped planting area, individual tree planting and grassing area prior to mulching, planting or grassing.
8304a83e-021d-51ec-8f6a-5629b1c0b2db | note | • The Contractor shall not proceed until the Superintendent acknowledges requirements for ripping have been met.
18548c9e-806e-59da-af25-3d4f556e865d | note | • In areas where ripping is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
b537165c-baf6-5d67-958e-d52d1fccc221 | note | – – – – – – – – –
a04459bb-87a2-5feb-8d48-2b9fd2b68713 | note | REFERENCE DOCUMENTS: 720.07 (b)
8e25d9d8-813f-584d-954e-912c1ef854af | note | – – – – – – – – –
e4aeeaed-e06e-5e4f-91fb-06c79a7348bb | note | INSPECTION/TEST METHOD: Visual inspection
0a894c85-d417-54c0-a307-915060565b96 | note | – – – – – – – – –
c347eaba-5a3d-5861-b4ba-989c77f0114b | note | RECORD OF CONFORMITY: This ITP signed off
958ac2d9-7d30-560d-919e-16fb8846924f | note | – – – – – – – – –
d7ae25c4-8a57-57e2-b701-d1886d21401f | note | HP
673570c1-b9e2-56f9-b38e-60847caa2e76 | note | – – – – – – – – –
a818aa6f-ee2c-57b0-bf85-b48af5b549dd | note | RESPONSIBILITY: Site Engineer/ Superintendent
df00a506-b6b7-5a0b-b1d0-a935c437fcd5 | note | – – – – – – – – –
3645a5f9-3b96-5b60-b985-217d0c380536 | textbox | DATE:
10519cef-83f5-4b0a-b971-a9884e1f21ea | signoff | HOLDPOINT AUTHORITY
af115908-7ece-4aac-92dc-b70585a32b95 | checkpoint | 2.8 Topsoil Finished Surface Levels
1c14cd90-8fde-5041-912c-5f4488b646a7 | note | FREQUENCY: Each Lot
57571859-6666-5e3f-b81f-cb2c192937e6 | note | – – – – – – – – –
1e16a2a3-a219-5c38-992e-b38ab8c79c91 | note | ACCEPTANCE CRITERIA:
a8458853-010c-53ec-a77a-259d90aff3fa | note | • The Contractor shall make available each ripped, topsoiled and cultivated planting area, individual tree planting and grassing area prior to mulching, planting or grassing.
9f552efa-6afe-56ad-91c5-70d8da0ebed9 | note | • The Contractor shall not proceed until the Superintendent acknowledges requirements for topsoiling and cultivation have been met.
201bf391-b7fd-506f-b881-b8d4018c5b94 | note | • In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
026e624b-9811-5945-972e-486b4308f46f | note | – – – – – – – – –
ae76bb4e-6c42-5c21-9bf4-44b010a9fc25 | note | REFERENCE DOCUMENTS: 720.07 (e)
cffd25bd-7199-5303-a4ec-3c058ecc99a2 | note | – – – – – – – – –
5f15c57f-8911-58d0-87ab-d45a96c42a56 | note | INSPECTION/TEST METHOD: Visual inspection
728674c4-b2e0-5098-8fdf-38c4383bf5a8 | note | – – – – – – – – –
ec1e7343-2136-5605-82ab-4663fa99d610 | note | RECORD OF CONFORMITY: This ITP signed off
57773588-1329-557e-9ccb-271bba815f63 | note | – – – – – – – – –
8477f62f-18ed-59ac-8b60-0994ba9c6fe3 | note | HP
7106b500-881e-587d-a29b-65b006eba5e1 | note | – – – – – – – – –
3f3dadd9-69b5-5afc-9f8d-189588b3df33 | note | RESPONSIBILITY: Site Engineer/ Superintendent
040f8f7d-25b7-5b74-84fe-4e626b64ac05 | note | – – – – – – – – –
ca4bdb77-3702-574f-b255-53663f5a5417 | textbox | DATE:
d1a3294b-f773-4865-bfab-9c775e833c47 | signoff | HOLDPOINT AUTHORITY
d3afa820-efd3-4320-b224-7a32b911126e | checkpoint | Final Inspection
1e39fdbc-a2d2-5be4-82fe-b47cd0ba3dab | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f9bea580-ec51-525b-be81-87d6d3be015f | textbox | Print Name:
46e28e91-046c-5378-956e-11f9baac81c8 | textbox | Position:
ded6507b-c6a8-51eb-8fb1-0011f223ecb2 | textbox | Date:
20595d58-ee32-4b5e-b854-2cf5d5d76e06 | checklist | ITP-01-019 - Line Marking REV2 |  | ITP-01-019 - Line Marking
ad4e19c0-251b-4755-93b7-68382d86a3d8 | section | 1 - Preliminary Works
6091ad69-ff96-4dc7-a208-27e7e915f48f | checkpoint | 1.1 Check for correct documentation
22a52063-4e31-5e8e-bc68-342d03321eb8 | note | FREQUENCY: Prior to commencing any activity
986b24c1-4261-51c4-a604-7d67ea70e60f | note | – – – – – – – – –
ae36b53a-6849-5589-9236-c1d40175daa2 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
2c3ef217-80fb-5657-8ace-d56b4bb98894 | note | – using the correct and complete set of drawings
401a4504-944a-5a4e-b91b-a2ba1b2da8ae | note | – all drawings are the latest revision
cabb697a-2959-5022-9ea7-cabac545cba4 | note | – – – – – – – – –
0eeb53df-2790-57d1-ba73-f35cc1442bb1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1382f7c9-e6af-5821-9ed8-22005b4441c7 | note | – – – – – – – – –
d9116052-5249-57ce-9265-6c9213211879 | note | INSPECTION/TEST METHOD: Visual inspection
fe473f10-67e1-57ff-82d7-7107c4c371a3 | note | – – – – – – – – –
92dedd51-eb63-5af5-a66f-5c609b1d3ca1 | note | RECORD OF CONFORMITY: This ITP signed off
43980265-88a1-5e68-81f1-4a5005e3bc3c | note | – – – – – – – – –
68a55c4e-2688-50ac-a63b-2dbd655bbfb4 | note | WP
563fefdf-7798-54a5-b744-b0bfb4a06334 | note | – – – – – – – – –
e57454c2-4494-5a97-8fc8-1ddc98af017e | note | RESPONSIBILITY: Fulton Hogan Engineer
1fc0ebf0-f6f1-59ec-98eb-4e11b0783a72 | note | – – – – – – – – –
6c3513a6-3aad-5aaf-a0dd-132dad8ab39a | textbox | DATE:
60dd4cf7-2b6d-40ce-b0e5-8c8a18edd65f | checkpoint | 1.2 Implementation of all measures and controls
ff29fdc4-29a7-5b4c-a75b-8d1071bd2efc | note | FREQUENCY: Prior to commencing any activity
62707af6-7ea3-52cd-8cc5-9e031bc02bf7 | note | – – – – – – – – –
bbbc238c-25eb-5600-abc3-b7ee013dc6f7 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
1bf1187f-50f9-5025-bbbd-237ade621624 | note | PSP, EMP, TMP, JSEA, SWMS & WP
0fec42be-7d1e-542d-9bda-914768b3a24f | note | – – – – – – – – –
b51917d3-bb2d-5f7f-b571-59d0b5e4a95d | note | REFERENCE DOCUMENTS:
5f5a8184-0893-5305-8527-ae5fbebf350c | note | • PSP
4bf4c3dd-4400-5caf-a8aa-870b9b252379 | note | • EMP
e8c6a3bf-391e-5b0b-8a50-e8f10b4ef356 | note | • TMP
f9bea558-7922-5ea8-a7e3-bbd162feaa82 | note | • JSEA
ecae18cd-2945-5785-b5e1-f499babd97e2 | note | • SWMS
06d5b8e8-a9f2-5870-90ac-09e2aace341a | note | • WP
68945cb4-c1d1-53c9-89ab-700a58fd8824 | note | – – – – – – – – –
9319c0a9-9856-5c11-b563-916d3911913a | note | INSPECTION/TEST METHOD: Visual Inspection
89c93e37-6ad7-59a5-b25f-1cbe23a7f40a | note | – – – – – – – – –
4fbaa30b-48ba-5564-bccc-15135c7d0c30 | note | RECORD OF CONFORMITY: This ITP signed off
9837fa95-2c98-5b92-b2b4-ce78474a4e15 | note | – – – – – – – – –
16db0a88-8889-5d99-8ea6-7e300e4f8b07 | note | WP
a58acaec-c7f3-5275-9b2d-3cee673f4c3c | note | – – – – – – – – –
372bbefc-722a-5159-ab7c-6f039163acd8 | note | RESPONSIBILITY: Fulton Hogan Engineer
4b24f2d7-8213-5628-8fce-95c53087c049 | note | – – – – – – – – –
417692dd-c902-5fed-9b5f-a9abac49bc87 | textbox | DATE:
fd184f70-cb54-4082-a17f-585fe2a4a1bc | section | 2 - Construction Works
638d60bf-f54e-444a-8ed9-75d0a65c3996 | checkpoint | 2.1 Setting Out
65cf102f-2fde-54d4-86a5-fa0d255c78a2 | note | FREQUENCY: Prior to start
00c8443c-8710-50e6-8c47-4a06dc9fc8ed | note | – – – – – – – – –
734ab6e4-f899-53a0-85d0-efe3f250bf75 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
7b45c0e2-84f3-593b-b644-28ed60f740c9 | note | – – – – – – – – –
a0455602-9c27-543e-be6f-500396efed1e | note | REFERENCE DOCUMENTS: Drawings
a77984d3-023b-5c06-8f02-2dddc7c4f371 | note | – – – – – – – – –
1c6ccb8d-1ab3-5531-92fe-ec218f2d8915 | note | INSPECTION/TEST METHOD: Visual Inspection
0220a0f5-f9fd-5d2e-a912-35e60f8c6e0c | note | – – – – – – – – –
338a4937-3698-570b-9cd6-7d7507ad40c2 | note | RECORD OF CONFORMITY: This ITP signed off
e4786853-eaab-5490-8cb6-f770f49ef86e | note | – – – – – – – – –
69a227d7-4c1a-52e2-b59c-4e75d172e1f9 | note | IP
eb07f7a4-2f86-5c17-84d3-8815403edbf7 | note | – – – – – – – – –
61e11154-9567-554e-af29-f82ea3716042 | note | RESPONSIBILITY: Fulton Hogan Engineer
63eabcc9-807e-5093-8b21-84aab4aed961 | note | – – – – – – – – –
b3e5b3fa-5a79-59b3-a7e0-826202d27d9c | textbox | DATE:
cecc0cd2-f80f-44d2-a563-3f964a51d786 | checkpoint | 2.2 Position of Markings
ef4af256-e8b5-5a84-bfea-d8401a845b6c | note | FREQUENCY: Prior to application
e89c3393-7ee8-5c94-ba79-38e29610d2c6 | note | – – – – – – – – –
d489d5ec-ec1d-5e5f-814a-8be462297a8e | note | ACCEPTANCE CRITERIA:
07ce0ab4-7e91-5d53-9ed8-c48c233acd2e | note | • Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
4fc85220-2dad-5044-9269-89ae89134ece | note | • Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2
33ff8f5d-819d-54da-9df6-4cc111fd0849 | note | – – – – – – – – –
26d13e62-f34a-5b8e-a4eb-6c7ad25cc8cd | note | REFERENCE DOCUMENTS:
924914f0-cd07-5ce6-a332-834c5a6644a8 | note | • VicRoads Traffic Engineering Manual Volume 2 Drawings
c0131d5d-ad1b-573b-926e-8d8702327aaf | note | – – – – – – – – –
aad1b9ee-d51d-528e-ab62-c4cfc1dfd02a | note | INSPECTION/TEST METHOD: Visual inspection
e60e2496-577d-5e92-a491-22bc86ac27fe | note | – – – – – – – – –
34de8de0-628b-5e2a-8e9f-860a9268e75d | note | RECORD OF CONFORMITY: This ITP signed off
7856ac12-d506-53e9-81f0-c5abf30025af | note | – – – – – – – – –
83b8a340-38bf-57d6-a405-b1439a611e0f | note | HP
f6f9e167-0761-575a-94ae-b8098ba8baae | note | – – – – – – – – –
c8b0ad5c-9ab9-5279-909d-ac426cc3ecfd | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
640ac053-08df-5121-8bca-bc169486cd0b | note | – – – – – – – – –
334ca219-54c0-5e77-bbd6-de0b6ae88555 | textbox | DATE:
d5628096-44f9-4850-ba53-9dfcf9f033a1 | signoff | HOLD POINT AUTHORITY
ebc75faf-3791-454d-b5ae-e05d2c6c7059 | checkpoint | 2.3 Materials
abe12929-85d3-5e02-82a5-fb2998488c97 | note | FREQUENCY: Prior to commencement
a5b12129-0d29-5aa0-85bb-2a7871b1eeee | note | – – – – – – – – –
27375bf6-2144-5cb5-b032-7e0ea698aa32 | note | ACCEPTANCE CRITERIA:
4c5a345f-7821-53ac-9d3d-24d8d8bbec5e | note | • All paints shall be approved under the Australian Paint Approval Scheme (APAS).
d472999d-6806-5cf5-8be6-2b29a6ca9acb | note | • Paint shall comply with the requirements of AS 4049.1 for solvent?borne paint or AS/NZS 4049.3 for water?borne paint as listed in Section 175.
0501322a-c5b0-5245-b7a5-4f5642baa097 | note | – – – – – – – – –
e4918dee-5b70-5b28-b010-5fb5d76f72f8 | note | REFERENCE DOCUMENTS: 712.A04(c)
3c200cf9-674b-552a-ad97-161e0334caa3 | note | – – – – – – – – –
b1681368-2956-5b41-8fb6-c9485b72c464 | note | INSPECTION/TEST METHOD: Visual inspection
1398a8fc-f919-5a95-8384-803f115077ed | note | – – – – – – – – –
3045bd8e-5f4d-5702-9eac-f6f910e70626 | note | RECORD OF CONFORMITY: This ITP signed off
5f100095-41b3-5ba0-b8ff-0f99ca46fe6a | note | – – – – – – – – –
baf4e20c-c24a-5e10-9e26-db37aabe7cba | note | HP*
27c719c2-b1e2-58bb-9325-2ed6011291c7 | note | – – – – – – – – –
7222861f-7702-5414-969b-78916b0119cf | note | RESPONSIBILITY: Fulton Hogan Engineer
ed67c018-36f6-59a8-9597-894626dedf9d | note | – – – – – – – – –
9d4d624a-c6a2-5582-85e0-c64e21bbc0b7 | textbox | DATE:
c6af508d-6ac7-436a-8cea-a8384643a28d | checkpoint | 2.4 General Markings
8b43c7c6-ab87-5afa-95bd-18e98779d24b | note | FREQUENCY: Prior to commencement
0dbc6a60-2806-5207-8e17-de1a1106cb08 | note | – – – – – – – – –
0e317a7a-9e96-50e9-b228-1512b5fc8851 | note | ACCEPTANCE CRITERIA:
049d763e-8b21-5a3a-8655-8bc33f3c4922 | note | • Linemarking shall be applied by a self propelled machine, and stencils shall be used with all roadmarking.
cbacc004-1c61-5828-8e74-a1caea0610fd | note | • All work must be undertaken by a contractor eligible for accreditation under the Painting Contractors Certification Programme (PCCP).
a7fdfdb1-ea11-5aef-ac8d-798ffcec95c0 | note | • This programme is administered by the CSIRO.
98b453f6-81f2-57f5-bebd-8836bb962410 | note | – – – – – – – – –
29389cbc-c7a5-51f9-9de6-0230052b9c83 | note | REFERENCE DOCUMENTS: 712.D01(c)
b28c84ea-84b6-5c24-953d-22c1e5f62790 | note | – – – – – – – – –
e2cca161-aaf9-50c3-8d93-ab209e421312 | note | INSPECTION/TEST METHOD: Visual inspection
0e2ac610-978f-51c9-933c-3c02b2f6d249 | note | – – – – – – – – –
63d434bf-d96d-5d29-878f-9e302bdaf691 | note | RECORD OF CONFORMITY: This ITP signed off
a3ec6b58-d15b-5329-acd4-2c8087b45de1 | note | – – – – – – – – –
bacf2eb6-3977-5385-ae6c-4f08ebdbc4c7 | note | HP*
4b3cdb1a-46f8-54a9-b6ae-6eef9c861798 | note | – – – – – – – – –
49519eac-a770-5b0a-8e50-33dc0ef63635 | note | RESPONSIBILITY: Fulton Hogan Engineer
19a821ad-ce38-502a-b6b4-9641d4316f39 | note | – – – – – – – – –
7d2574fb-50bb-5326-b1e8-e4dd5c0b83c3 | textbox | DATE:
a01c28a1-2d3a-44c5-a2aa-7cd674c23bb1 | section | 3 - Completion
e4dc5d7b-d71e-47a9-a7fc-c0c2bd57d7fc | checkpoint | 3.1 Tolerances
3426d1f3-bf6d-5e5a-bace-e207b0d327fa | note | FREQUENCY: Each marking
0a91f008-df23-5767-aa8a-580d76d990c0 | note | – – – – – – – – –
5b36d4f9-1e6d-589d-a56c-ec8194f7f5f6 | note | ACCEPTANCE CRITERIA:
ffd8bdee-1c15-51ba-813c-a6021181da3a | note | • The Contractor shall comply with the tolerances as shown in Table 721.A101 when installing pavement markings.
6d3d8cc9-e01a-55c7-a805-145b9cb6696c | note | (i) Distance between centreline of marking and set out marks <30mm
9f79f77e-59bb-57c4-ae21-79c29fc4663d | note | (ii) Width of completed paint markings <15mm
c09eca13-2892-5d7d-8446-d7386886182e | note | (iii) Length of completed stripes and blocks 0 to +10% of specified length
e5d036ea-71cb-5714-b0cc-ed377818618f | note | – – – – – – – – –
2e829a53-5a6e-5a8e-a33e-490a7439eff8 | note | REFERENCE DOCUMENTS: Table 712.A101
9ce2f314-2e71-551c-823f-375c49f62ad1 | note | – – – – – – – – –
8814fbbc-fbb5-5fb1-907a-2b88a50c4d0d | note | INSPECTION/TEST METHOD: Verify
2919e6c3-c404-5687-aacb-f4aa27a3d7a3 | note | – – – – – – – – –
b410345f-7b1a-5342-80be-26606e775586 | note | RECORD OF CONFORMITY: This ITP signed off
f97fadd2-bde0-5a36-9b7e-0707a1fdf4a8 | note | – – – – – – – – –
7862681c-2801-5ec9-9c1c-115ce98e8720 | note | HP*
e69bbe08-98d9-5ca5-9ef8-8b9c91cfee9c | note | – – – – – – – – –
d77eeda6-8452-50c0-b1cc-9fbc7cb7eeb4 | note | RESPONSIBILITY: Fulton Hogan Engineer
ee44bec8-02b9-58a1-8529-0fd693ae3434 | note | – – – – – – – – –
ec98b4e6-1b22-567a-9d97-e8a78e94055a | textbox | DATE:
1e232889-77aa-4dfa-9dfd-a82658f6b573 | checkpoint | 3.2 As-Built
a82cfd7f-081e-5432-b278-d5c65e16f9e9 | note | FREQUENCY: Post Completion
4d55263f-f0c8-5954-96e6-501688961256 | note | – – – – – – – – –
b72f3c77-6237-5b62-b59d-9f518320854f | note | ACCEPTANCE CRITERIA: As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
b9514e78-ea34-50ad-9c84-c71c78a6b5c2 | note | – – – – – – – – –
0995681b-82d3-5f9e-8f8d-98ae9ea0f33b | note | REFERENCE DOCUMENTS:
0e7c951c-5df5-5a38-9331-3b8fab009256 | note | • IFC Drawings
0c411c3b-7668-5eff-a727-06853945cb89 | note | • Survey Records
95f08c22-8403-50d6-b350-3f59b4990d8d | note | – – – – – – – – –
13fa10fc-510e-5f4b-abbc-1c6a6ec71705 | note | INSPECTION/TEST METHOD: Document Review
7a779898-ad3a-5995-ae9d-9f5cceba693d | note | – – – – – – – – –
bad5f7a1-60ad-572e-819f-b74db642684a | note | RECORD OF CONFORMITY: This ITP signed off
608e1db8-cd54-5f9c-9a36-e0055a89daf8 | note | – – – – – – – – –
a681bedb-14a4-5b7f-b93b-dbeab749a8dc | note | SCP
5b54136d-0e66-5822-b94a-b688ec0fa846 | note | – – – – – – – – –
1a0853db-d206-5d23-91b5-747f2932af9c | note | RESPONSIBILITY: Project Engineer/Surveyor
ed996f63-ae89-540c-8411-c31954e2d2d9 | note | – – – – – – – – –
175571e4-de3b-5508-9619-690dbe1e5f9b | textbox | DATE:
72cc9845-5fb3-48dc-a674-424624d3670c | checkpoint | Final Inspection
842adcdb-8f20-5056-bac3-aeccf82f5232 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
a7af28ae-c69e-522d-970d-ef0420b41d73 | textbox | Print Name:
6d5b261b-3808-536f-995c-43dcad603014 | textbox | Position:
1c239252-2315-5ad4-996f-29ff96dcdd7a | textbox | Date:
27184eb0-71d0-43b4-a2e4-da13a4e5a3db | checklist | ITP-01-020 - Fence Installation | itp | ITP-01-020 - Fence Installation
ef4aa7ed-bbe3-4a0b-a441-a1e0eea685f6 | section | 1 - Preliminary Works
988df552-14b0-4630-8638-92a99657c413 | checkpoint | 1.1 Check for correct documentation
f97c8d2b-4521-5b7f-9e33-192023f095ea | note | FREQUENCY: Prior to commencing any activity
b9db4a50-65b1-5174-913c-3febb43e2397 | note | – – – – – – – – –
33e3fc7d-9403-567a-82ca-fdae46bb4549 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
b6310b1d-e0d6-550f-9514-f588c3693b66 | note | – – – – – – – – –
51dd6527-a69b-534e-af6b-44e8fd151bfa | note | REFERENCE DOCUMENTS: Drawings and drawing registers
5e80ab4e-6735-50df-89c1-1a6431c7e8fc | note | – – – – – – – – –
7ea2f1e8-d3c3-5bed-92c1-0955766bfd22 | note | INSPECTION/TEST METHOD: Visual inspection
34863a4e-8598-5869-a5fb-7f30868a62ca | note | – – – – – – – – –
a725a851-a929-5b26-8208-a59622788a8a | note | RECORD OF CONFORMITY: This ITP signed off
325de4cc-28de-5c5a-89dd-54ad285e6be4 | note | – – – – – – – – –
c22fa680-0018-5d3a-9929-6cb7d800a01f | note | HP*
09a4a7aa-37d9-5e18-9e3f-edd07b9a5bf1 | note | – – – – – – – – –
906a87da-c3b1-503c-a9a2-cb87253573ab | note | RESPONSIBILITY: Fulton Hogan Engineer
fccd4a89-92a4-5e50-b856-653b2b800589 | note | – – – – – – – – –
bef971d8-3342-50b6-bc81-5d53738fd4f4 | textbox | DATE:
9bbe8c74-96e7-4486-9788-55f6d06496fc | checkpoint | 1.2 Implementation of all measures and controls
ab84e073-827a-5dc8-8545-9a13b4824fa0 | note | FREQUENCY: Prior to commencing any activity
458176e0-6eb1-59f6-8891-f72dd3804997 | note | – – – – – – – – –
2c240635-5273-5cb1-afa6-10eb6301c6b2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
e47be0b4-e5e2-561a-b61a-f17b58d31978 | note | • PSP, EMP, TMP, JSEA, SWMS & WP
af989748-5e37-57e1-b707-5b950e5eacb4 | note | – – – – – – – – –
55487363-9084-56d4-bce7-3126f8b53670 | note | REFERENCE DOCUMENTS:
32250332-7309-5223-a5b7-b5d54645b6f7 | note | • PSP
38814d70-10cd-524d-a0c3-0c4f4591144a | note | • EMP
59c5031f-c37d-50e0-89b7-49538cde6a54 | note | • TMP
14ba59a8-386f-5fe0-bcf5-af25185e6745 | note | • JSEA
6b939a4a-d147-5d64-b413-146ce0f6032e | note | • SWMS
75fb62a5-a2a9-5f02-b7d0-222a07fff3c4 | note | • WP
92c453df-5c57-5084-9747-3edd24bf5098 | note | – – – – – – – – –
b8071192-397b-5bd1-91c4-c01413825736 | note | INSPECTION/TEST METHOD: Visual Inspection
05567e9f-d88a-5c96-a2c9-9b3ea76150fc | note | – – – – – – – – –
433f1f9d-9ad2-5627-8e20-24d872a3c149 | note | RECORD OF CONFORMITY: This ITP signed off
e492e65b-948d-5772-a1e0-3ccd2c2c19f5 | note | – – – – – – – – –
a075ece0-dd30-506c-8c2b-b3475922b538 | note | HP*
8811fa74-30f2-5305-89c3-bd19a666d018 | note | – – – – – – – – –
51809be2-3126-5833-86e6-4831897e0072 | note | RESPONSIBILITY: Fulton Hogan Engineer
18cd5480-8426-5f8c-a83b-0cb80ebeba49 | note | – – – – – – – – –
03ebbb07-f367-5fe3-9e2d-b29a49db1336 | textbox | DATE:
d6f8214f-f208-4c9e-84f9-ace036e07039 | checkpoint | 1.3 Check Materials
546a8f30-8247-5ceb-b001-a4cbe1a83915 | note | FREQUENCY: Prior to commencing any activity
312ff2df-b057-59b7-9d29-1deac78bb70b | note | – – – – – – – – –
789ee001-03e0-582e-b2c9-402799965ea7 | note | ACCEPTANCE CRITERIA:
f636f56f-e665-5371-9d73-87cc234fd7ae | note | • Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of this specification 707 and drawings.
aaf0a16d-364d-5258-a62f-5d89b829976d | note | – – – – – – – – –
2467a81f-54ef-5d05-bc4c-490d2a52d82e | note | REFERENCE DOCUMENTS: Fencing Plan
a729257f-9326-5ec6-ae64-d83d31566a3b | note | – – – – – – – – –
abde675f-6500-58cd-a780-244ee0be4f83 | note | INSPECTION/TEST METHOD: Verify
512efbd7-385a-5573-9e54-a3900acbe32c | note | – – – – – – – – –
9b5582ad-d13c-51a0-b204-762778fd9efc | note | RECORD OF CONFORMITY: This ITP signed off
d11c04f5-6232-5e99-9b47-a2a736c238f8 | note | – – – – – – – – –
bbb7adac-fb60-5320-8e82-2a6e2b2cc408 | note | HP*
f0774258-b216-5a09-b415-5d5c7fcb9768 | note | – – – – – – – – –
4b7cfe8d-1f63-51d0-afb1-9011a095ec00 | note | RESPONSIBILITY: Fulton Hogan Engineer
ec2a0321-c322-5fe1-9f48-6378f9e740aa | note | – – – – – – – – –
fe46771d-f4ff-5dac-b9ba-75f6ec0e4e6d | textbox | DATE:
7e3d880f-9a50-4777-9611-cc2dbbf33e5f | checkpoint | 1.4 Confirm Footings position
03b28317-3e3f-5e0e-a9d6-aa5273a9078d | note | FREQUENCY: Prior to commencing any activity
c96e5b23-c045-5b13-9165-3fc8a79b845d | note | – – – – – – – – –
1ee88bd0-0059-5ce4-884c-5a0b9011c6e5 | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
adc3e083-1757-5c7f-b394-f30039c98a09 | note | – – – – – – – – –
e2384b44-47e1-5000-bcbb-301a648e5f4c | note | REFERENCE DOCUMENTS: Fencing Plan
391be83b-122c-5a8d-8a6c-af0dfeb44433 | note | – – – – – – – – –
fd96cc3e-cf2c-51bc-9598-5f19ce9a0504 | note | INSPECTION/TEST METHOD: Verify
04a1fe3c-c6b3-59f1-8706-c51892ad1381 | note | – – – – – – – – –
be016bb2-be81-579c-bcc8-3db016a587b6 | note | RECORD OF CONFORMITY: This ITP signed off
20a826b3-85a8-5b6d-8cb8-9fc2c569e097 | note | – – – – – – – – –
84c21d9d-7c97-5182-a1d2-84279878a763 | note | HP*
9c325b57-d389-56a3-9a58-1a501c2b3242 | note | – – – – – – – – –
05b01350-60d7-5504-a796-aa36a8f4dd64 | note | RESPONSIBILITY: Fulton Hogan Engineer
5f127409-e667-5bbc-96ad-d549c33b334f | note | – – – – – – – – –
9826b40b-9f58-5d65-ab31-6287b60b40b1 | textbox | DATE:
e89c8e5e-84df-443c-8b61-d3b236386414 | section | 2 - Construction Works
dd1319db-4027-4324-bbf3-e48d41268988 | checkpoint | 2.1 Footing Installation
55335b8e-9711-52f1-b087-1934f742ab5a | note | FREQUENCY: Prior to post installation
d36619d2-fdb5-5097-8fda-d6b829858e84 | note | – – – – – – – – –
44962c41-1970-5581-afb2-bced5c6a7caa | note | ACCEPTANCE CRITERIA:
d128b5ec-8f6a-590d-b861-f9625f929849 | note | • Concrete shall be of minimum strength N20
00cd0ab7-0272-553b-9c2d-fa840fcaab4d | note | • Concrete footing shall be 600mm x 250mm and have a 65mm steel sleeve set in the concrete
c7fc8fcb-9115-5faa-a55f-a4a97bd86b66 | note | – – – – – – – – –
7dc3e2d6-c8f2-5a28-b821-702393b1fe85 | note | REFERENCE DOCUMENTS: Fencing Plan SD3131
c8167c66-1ff7-5468-b68a-70a466fba848 | note | – – – – – – – – –
108d42a2-ac14-5b7a-b995-2b5e6c6ba6b7 | note | INSPECTION/TEST METHOD: Verify
6ca7a402-3482-53bd-986c-f3380d9ee2bb | note | – – – – – – – – –
353aef70-0327-58b5-8aec-585b57b3b471 | note | RECORD OF CONFORMITY: This ITP signed off
60ca65b1-8183-5699-9632-9fb8b88c9e8a | note | – – – – – – – – –
e2c959b0-948d-5e05-98d5-eb92d97916ce | note | HP*
9e0f1463-4cdc-5649-8ffd-59b14736be6b | note | – – – – – – – – –
8f2d88ee-4eb0-5e43-800d-57b3aae2451c | note | RESPONSIBILITY: Fulton Hogan Engineer
2621af38-1e59-5876-a102-04ed2f22465c | note | – – – – – – – – –
596855ed-3435-5da8-b025-74bdeeadca82 | textbox | DATE:
6424220b-5694-4a6d-a570-e2ac5646c8b4 | checkpoint | 2.2 Post Installation
41016d91-b1ed-5bba-9220-4bb4d9dfe914 | note | FREQUENCY: Each Lot
4cec6611-a07a-5991-8ea8-fe56f050bb90 | note | – – – – – – – – –
74a6d28a-fde0-5b8b-ba41-ff7347540edd | note | ACCEPTANCE CRITERIA:
59d963c5-75fe-52d9-afcd-69177aa77ee5 | note | • Posts shall be set in concrete footings of the dimensions shown on the drawings
ace4c961-e7cd-5cb0-a4e6-e41f1403c822 | note | • Posts shall be Installed to concrete surface in culvert area with baseplate and bolt assembly
3debdf6b-4041-5efe-a154-6f3565e923e2 | note | – – – – – – – – –
820c8f5c-6740-59e7-8ca3-ddd7febdb488 | note | REFERENCE DOCUMENTS:
3d32b5e3-dcfb-53eb-b5f9-7fdfa1a0329b | note | • 704.04 (d)
78bc62d6-a8b9-59b0-9938-8bbb9afd0eb5 | note | • AS1554
60cd0763-24e0-5510-836d-48d8c6e18c80 | note | • Fencing Plan
e573ba8a-ca6f-506f-b787-8cd9cae4b1e5 | note | – – – – – – – – –
2ddc15f5-6afa-5db6-8a13-0cea03d657b6 | note | INSPECTION/TEST METHOD: Verify
9e0f0bc8-e908-5d6b-9466-b43cc8b7eb6b | note | – – – – – – – – –
56263faa-9a21-5c61-8219-066bcd6eebeb | note | RECORD OF CONFORMITY: This ITP signed off
6a7511ba-6dfd-50c1-9ca7-e5c0cb0bb0ec | note | – – – – – – – – –
66b6c9eb-ced9-5b74-ad32-82165b93ca71 | note | HP*
b21c92a0-6545-562d-8f96-539a552525d6 | note | – – – – – – – – –
dfd15e19-1486-5da3-ab7c-4629ebb5477f | note | RESPONSIBILITY: Fulton Hogan Engineer
87eb8f93-3217-50b4-afcb-4e0cd4d20d40 | note | – – – – – – – – –
9c118902-9e6a-5273-a722-7c8c37fdd613 | textbox | DATE:
2b1ff393-bd6b-4dd4-ac11-ec3d8c8542ab | checkpoint | 2.3 Grout Installation
9039bf6e-6e6e-528d-86e4-82fafb52106e | note | FREQUENCY: Each Lot
97f0ec51-99ed-54e2-8e79-6631b8da5515 | note | – – – – – – – – –
9407c326-98b0-5f78-b8f0-f3c646246532 | note | ACCEPTANCE CRITERIA:
3dff12f3-2943-553f-b004-96c0a67212aa | note | • Footing surface shall be cleaned and roughened before application
49ff4e9d-56fd-5e4c-aa31-99cf180e543e | note | • Non shrink dry pack grout shall be placed under base plate where applicable in culvert area and footpath areas
57df062b-ff20-5947-847c-667281f6eb83 | note | – – – – – – – – –
6412a08d-c507-5292-a7c2-0d6ba915ac5d | note | REFERENCE DOCUMENTS: AS1554
364b72a7-c321-54c4-b452-2f350969e2e4 | note | – – – – – – – – –
95f1799b-3ab5-5c88-8e24-a41e6edde4e9 | note | INSPECTION/TEST METHOD: Visual inspection
cef406d5-fdff-5eb4-a5d0-fc7ee96050ed | note | – – – – – – – – –
a6f01e7f-7868-53b1-a581-694d3a9096a7 | note | RECORD OF CONFORMITY: This ITP signed off
45dced1c-1006-5cf7-b0a8-1461fa5cc80e | note | – – – – – – – – –
d15f7a2c-0544-533d-be99-ac1ada71d8a8 | note | HP*
2ffd7af4-9c0c-5cf3-a7ed-2dfe8f99e2b2 | note | – – – – – – – – –
dbc1b5cf-70b9-5fd3-94f3-e957d963fafb | note | RESPONSIBILITY: Fulton Hogan Engineer
2a27127d-9a94-58d3-b17b-850c2ba5c1d4 | note | – – – – – – – – –
0fffbedd-c558-5446-a8d1-c4cbd034c99b | textbox | DATE:
aeff53f5-d60a-467b-9296-cf5fa18b0a81 | checkpoint | 2.4 Chainwire mesh fence
9eb29383-e480-5027-9abf-d77d565bcc60 | note | FREQUENCY: Each Lot
18b04838-56de-5f0c-9434-15762124d72b | note | – – – – – – – – –
6909a979-475a-51a1-98e7-54b8c413891c | note | ACCEPTANCE CRITERIA:
7ed6e10b-e76b-5866-a0ee-93e5feec2d48 | note | • End, corner and gate posts shall be braced as shown on the drawings.
7507bfe1-7ba7-510a-8e6f-80b41295fd66 | note | • Line posts shall be braced as shown on the drawings at not more than 120 m intervals. Chain wire shall comply with the requirements of AS 1725.
b8fd674f-9ddf-52d5-a7bd-53861a8b053c | note | – – – – – – – – –
118324e9-585f-5cc7-84c1-279c8ea6dddd | note | REFERENCE DOCUMENTS:
b11a4c73-d944-5765-945a-c40785177091 | note | • 704.04 (d)
63bd5ac7-613a-59c2-9487-ba53ecb03fbf | note | • AS1725
2e889646-e0b3-5926-9bbc-6b04d31ddb7c | note | – – – – – – – – –
9a957bd5-cb2c-5bf5-ac9f-2390ce8ca399 | note | INSPECTION/TEST METHOD: Visual inspection
f2a16628-1835-514a-a58b-53bcea8eba7e | note | – – – – – – – – –
53052a14-99a3-56c5-868c-7ba78d252016 | note | RECORD OF CONFORMITY: This ITP signed off
5a8d93e1-2b18-5c98-82c3-3758c45a1df4 | note | – – – – – – – – –
be9b80b4-c51c-5e4f-8fdb-74d26af33b08 | note | HP*
5b244998-63a3-5eaf-8d06-da0ce05fc6b7 | note | – – – – – – – – –
96514638-229b-5cbc-8729-7d3671a903cc | note | RESPONSIBILITY: Fulton Hogan Engineer
ac1d9472-1a0e-5a8e-89a7-e2505e93bd69 | note | – – – – – – – – –
89d2a0f2-05bf-5edf-ae8d-c07ff9950e19 | textbox | DATE:
a261472f-9f6e-49dc-9e7b-8e4ed08b57f2 | checkpoint | 2.4 Handrails
45f60913-a26d-5f29-8d8d-4d4f807860b8 | note | FREQUENCY: Each Lot
e10a9726-0e2b-549b-98bc-8941ddfb7e76 | note | – – – – – – – – –
cdf4f458-2ef1-5b75-bdfa-5e528e76b9f5 | note | ACCEPTANCE CRITERIA: Handrail to be installed as per design drawings and manufacturers specifications
d64e4cd5-5857-533a-b5e2-4de0649cc88a | note | – – – – – – – – –
7e1c0a87-bd40-5d50-80a9-19678f852688 | note | REFERENCE DOCUMENTS: Manufacturer Specification
8c7a9abc-4f9d-5336-80f4-3043d83f1e1b | note | – – – – – – – – –
230cad62-19cf-5527-9d4a-4c48b4d7ecd9 | note | INSPECTION/TEST METHOD: Verify
6eb89cda-afaf-5f91-ba62-6d0bb5894c9f | note | – – – – – – – – –
2a9e0274-ad5e-5495-b549-11c7b2239878 | note | RECORD OF CONFORMITY: This ITP signed off
2cddd711-908a-5ab6-b194-233baa8665f1 | note | – – – – – – – – –
32b8bf8d-2051-5224-9e35-45cc495dcfdf | note | HP*
570eb404-7e49-528a-9a12-33498ae82619 | note | – – – – – – – – –
1d396c46-0a1f-5f21-9c75-bd69b032cd79 | note | RESPONSIBILITY: Fulton Hogan Engineer
cae53f97-b57a-5ffd-bf0b-f5300562dab3 | note | – – – – – – – – –
1c5ca685-442c-5193-a193-4674b0e11956 | textbox | DATE:
2bb598f8-7754-4882-bcfe-aa842212a060 | checkpoint | 2.5 Farm Fence Installation
c9c406ae-474a-536d-99d3-b43f74454de2 | note | FREQUENCY: Each Lot
10895cb6-6cec-50f8-a4e8-581675a8405c | note | – – – – – – – – –
218a3a92-f076-56a8-89c5-20d723295b57 | note | ACCEPTANCE CRITERIA: Farm Fence to be installed as per design drawings and vicroads standard drawing
0689998d-9dde-5a12-af6f-6ac9b857ca95 | note | – – – – – – – – –
45c129dc-2151-5243-b8c7-195f90288421 | note | REFERENCE DOCUMENTS: Fencing Plan SD3101
4ff00456-6e03-555e-86f4-5613ba99ca9f | note | – – – – – – – – –
c745223c-bfac-57bd-a611-d2c20b2ea029 | note | INSPECTION/TEST METHOD: Verify
c5956527-0bcd-5dfa-aefd-0dd73411e787 | note | – – – – – – – – –
5b256da5-1ec8-5b7e-af35-fbfe599425b4 | note | RECORD OF CONFORMITY: This ITP signed off
8684c340-f9cf-5ebc-bcfa-816befa0e35d | note | – – – – – – – – –
4708ef28-d9e2-510a-b741-9484e156cf4e | note | HP*
34ac6534-cbdb-5fc3-b51a-0c9fe852cc8d | note | – – – – – – – – –
3cd15caf-7602-5808-901c-28bd09d642f8 | note | RESPONSIBILITY: Fulton Hogan Engineer
0168a291-3241-5d2b-9e41-a67a60f4ecac | note | – – – – – – – – –
dd63b3fc-d48b-5213-a8d8-218c7e924a13 | textbox | DATE:
6ffbf8d6-9b08-41da-9ab0-780ac32d034d | section | 3 - Completion
a42ba4c8-08bc-4188-b49e-cae5b2d636af | checkpoint | 3.1 As Built
5e157b1f-ce0d-5441-aadf-51335a8478e9 | note | FREQUENCY: Post Completion
6957e279-0a6a-53ed-af0a-1ed935fd19bc | note | – – – – – – – – –
826880f1-91e3-5038-8d43-cb66b6ea5da8 | note | ACCEPTANCE CRITERIA: As Built survey recorded to confirm installation as per design drawings
fddd9bd4-e244-598d-a280-2bb694facb60 | note | – – – – – – – – –
c7877e63-bc3a-5dd0-ba00-d38ad2338ff6 | note | REFERENCE DOCUMENTS: Fencing Plan
81723240-cc7a-5148-aca6-808aec8eb7d9 | note | – – – – – – – – –
f87576b5-75fc-5427-9b9d-2e33c954f5e5 | note | INSPECTION/TEST METHOD: Verify
d6402f21-8f07-590a-b1e9-a0170aa95424 | note | – – – – – – – – –
e637a90d-4567-5d3f-9a2f-e2a17d584d01 | note | RECORD OF CONFORMITY: This ITP signed off
c6b7587c-4085-50a0-880f-c4536265311f | note | – – – – – – – – –
810055da-3268-5a2f-be57-5b4aec5a7b3c | note | SCP
6a9043aa-1612-52cf-bdf9-0e001f206385 | note | – – – – – – – – –
cff0fde4-abd4-5f61-96a4-854ce7da103e | note | RESPONSIBILITY: Project Engineer /Surveyor
a16b51d3-d3d7-5824-874b-db615ffb8283 | note | – – – – – – – – –
0fdee110-a96f-5940-8fb5-21e255fedac0 | textbox | DATE:
c1f2e95d-b539-4765-9f58-a64d030c90a6 | checkpoint | Final Inspection
15374d5e-6345-5f55-9869-09b195c583b8 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1e532c39-2371-5888-8a15-d664c608ba71 | textbox | Print Name:
8eed8ab6-b6d7-595b-836a-66726f94a1bd | textbox | Position:
a5b94c94-ecf8-548f-afad-8138ef5084d6 | textbox | Date:
64dde4b6-9fae-43ee-a60c-2d60e6628844 | checklist | ITP-01-021 - Type B Fill placement REV2 | itp | ITP-01-021 - Type B Fill placement
09c79ec4-c06f-4178-b1db-3b002226b9ad | section | 1 - Preliminary Works
138da631-91d0-416f-bfb9-b197d18c30bd | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
633cb1b4-b13b-56cf-8a8e-8d00c28a512d | note | FREQUENCY: Prior to commencing
aa383b60-b3d3-5989-a1d8-2ac14741edc9 | note | – – – – – – – – –
3fbce668-1099-5ac2-8303-cb623ea17198 | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
29503dc4-7301-59c5-89cc-dfd4cb80bdae | note | – – – – – – – – –
3bd59646-a46e-5380-bc37-285459531f56 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
a4d033e7-c83d-5c62-93bc-caa53f038762 | note | – – – – – – – – –
16860c18-37e0-56ef-9ee5-c1d6ff8fc18b | note | INSPECTION/TEST METHOD: Visual Inspection
8e7ecfd3-1a04-5652-9004-0007f91086d8 | note | – – – – – – – – –
b1ee78a7-2d31-5788-a402-d7f379384886 | note | RECORD OF CONFORMITY: This ITP Signed Off
eb876fcd-1cbb-5605-87f5-5b18375f9f67 | note | – – – – – – – – –
d8df9691-95d4-5000-9727-340e5e2288ad | note | HP*
7cec6005-c926-52ab-88c6-a9ccde07af22 | note | – – – – – – – – –
2a1f0b28-d67b-56a2-9608-7f4fb942dba1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
589a1d9b-fe8b-58d9-9b4e-d1d23797bdbf | note | – – – – – – – – –
87733f33-2d63-5184-90e5-9e848379af1f | textbox | DATE:
ac4a4707-2cad-4b11-91e5-dbfdd4d867e3 | checkpoint | 1.2 Implementation of all measures and controls
8c85536a-026f-567d-a9d9-963a7015bf8d | note | FREQUENCY: Prior to Placement/Each Lot
8264041e-683d-55ec-aeb4-92dff436b01a | note | – – – – – – – – –
b64ee222-f1b8-5d57-8314-707218a6d81d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
cd4c9d13-bf05-5bd8-bd9b-3b488f3b214d | note | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
2d1f5b86-8378-5cbe-ae7b-4f1e9e6d0602 | note | – – – – – – – – –
bc3c6a8b-af0d-58dd-8d81-ec860f6182ac | note | REFERENCE DOCUMENTS:
59e42b32-b608-5909-9c37-1cf3b4a87626 | note | • OHSCP
1ee2119c-570b-598e-95a8-b1b1f664872d | note | • PHSCP
a3ca613b-fa63-569d-9700-7929fd2bc02a | note | • PCMP
30ba0521-f234-5898-8f26-08814ed1bea6 | note | • EMP
aec1cbb3-f599-553b-94b6-58eb0da10624 | note | • ECP
5056f745-e9a5-53bb-b776-1ee1b1262490 | note | • CEMP
84004e29-409f-57ed-8938-54f2d30c768e | note | • ERA
c1c01e78-7cf9-502b-8005-07a4a5faf866 | note | • QMP
f24b5a05-66c9-5d0b-bac1-fe9e1c15e63c | note | • CHMP
a551f174-decb-5e43-9c35-e5303dbe6043 | note | • SWMS
15a91a7e-9ad3-5eb2-ad49-8e2a9ed1c2fb | note | • WP001.02
5e2d13eb-4ebc-5449-8224-187906e382a2 | note | – – – – – – – – –
dfaf9baa-23f9-564c-a3ae-8bcb7b565520 | note | INSPECTION/TEST METHOD: Visual Inspection
a74c9772-0695-5b6b-b82c-fd819e83da2f | note | – – – – – – – – –
cd35f6f3-0bae-5014-95ef-936a61026daa | note | RECORD OF CONFORMITY: This ITP Signed Off
51ce54b3-842d-5573-b9eb-91f4253d692d | note | – – – – – – – – –
6b2de51a-e084-5f45-bb34-a60353b595b0 | note | HP*
6a021108-56f8-5f0d-a8ec-788516f3f37d | note | – – – – – – – – –
329ec5eb-36c6-51fe-a6db-4986bb33b212 | note | RESPONSIBILITY: Site Engineer / Site Foreman
71ede1cb-cc69-5d2e-a957-a930c184062a | note | – – – – – – – – –
18155798-99e4-5be4-8818-6cfa7deb90b0 | textbox | DATE:
51ca2391-4e65-48db-918c-192ab7bc0348 | checkpoint | 1.3 Verify Material
fabc9674-ded0-5e7f-b36a-c81d3b6f6737 | note | FREQUENCY: Prior to Placement/Each Lot
e3e5fe74-5202-546f-b778-cdfa5b7bc3f0 | note | – – – – – – – – –
0b5ccf82-366e-575c-886f-3384caf44c5b | note | ACCEPTANCE CRITERIA:
4678665a-8ffc-5707-b21b-364f3ad1a9ec | note | • Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.
7807a76f-128c-5ea0-8022-98b401bd356b | note | • Materials that exhibit swells greater than or equal to 2.5% shall be classified as expansive and shall only be used as Type B material if approved by the Superintendent.
7041d8ee-7c10-5974-b9c0-ed381c89f99d | note | • Material within the top 400 mm of top of Type B material shall have a swell less than 2.5%.
41d0df93-8bff-5730-9508-254eaaba69a3 | note | • Materials that exhibit swells of 5% or greater are not permitted.
504473a2-a813-5df4-8530-c03a38bfe099 | note | – – – – – – – – –
902e0b43-cbb1-5ca1-8a6d-0c12614ba3b9 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
52ceb6d1-5a63-50e7-9110-14fadcd98f50 | note | – – – – – – – – –
f64fd486-24e1-5146-92fe-6b1b951e04d6 | note | INSPECTION/TEST METHOD: Site Inspection
f92718b0-8c04-5509-9e80-8adaf1b8f530 | note | – – – – – – – – –
db14c95b-b50a-524b-a5ef-3f4591f1a16e | note | RECORD OF CONFORMITY: Test Record (If silt is observed)
cdc15a08-2e16-5559-8f41-352c20d01e50 | note | – – – – – – – – –
a4d98fa5-40d3-567c-bd5a-43277f2fe71a | note | HP*
9a7f82d9-55d1-51de-a067-9a4179f237a7 | note | – – – – – – – – –
bfbe3969-6158-594a-8841-b3675b1d8755 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b511bdb8-de30-53f7-872f-f0af58c6a8d0 | note | – – – – – – – – –
3abed1b2-86b3-5377-b6ae-d1893cfed889 | textbox | DATE:
1572239a-ab9b-4a7a-a1af-1b2cbcf1b0c7 | checkpoint | 1.4 Excavation Permit
89f77c0e-2956-54fe-a10d-9c8c20f6443f | note | FREQUENCY: Each lot
a0fa97a7-38a6-5ade-b447-1381de63eb85 | note | – – – – – – – – –
e6643fb5-6451-5003-8b97-9f8c263d7282 | note | ACCEPTANCE CRITERIA:
f66d1b2d-91a1-5a59-8f09-019616ea05c6 | note | • An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
730499e2-d17c-5044-9046-c5a8b578cd20 | note | • Plant and equipment shall be appropriate for the task.
82e42a41-f0ae-5770-893a-f55d229d2049 | note | • Excavation operations shall not disturb areas outside the limit of excavation
0ecf9951-39fa-53f4-9d39-e15fe8d254da | note | – – – – – – – – –
87d64337-a7b2-5998-beb9-8de84af92074 | note | REFERENCE DOCUMENTS: Excavation permit
cb2f0ae4-8342-5c3b-8bc3-d3f6f01b45d9 | note | – – – – – – – – –
ab6de2d3-c55b-5ba1-9715-e006d607ee9b | note | INSPECTION/TEST METHOD: Verify
9f772f08-4824-5182-8645-427d315babdd | note | – – – – – – – – –
0431cdc0-3b4b-5c83-b248-c6cdeef3f1e6 | note | RECORD OF CONFORMITY: This ITP Signed Off
05504717-46a0-593f-b763-ef5c5137cc6c | note | – – – – – – – – –
266c7b24-fcca-5883-ad0e-b8849f80663d | note | HP*
2494276d-673c-5c5c-8e86-56516f25abf6 | note | – – – – – – – – –
70853835-f6b2-574c-a8d7-29dff8c9daa4 | note | RESPONSIBILITY: Site Engineer
ed6dccec-1043-5d60-83f8-adb0093c1c7f | note | – – – – – – – – –
89a604f8-3d6d-5909-b7d5-2daa96ef8cf8 | textbox | DATE:
1f38e43d-9baf-490c-a0c8-8f1ff0ee1825 | section | 2 - Construction Works
66a85455-a005-41d4-8512-340cf6e56a6b | checkpoint | 2.1 Survey set-out
0a837d7a-616e-58fc-8af8-eba398aa7140 | note | FREQUENCY: Prior to Commencing Excavation
2faf1e1b-2549-5f83-a3d2-8fd56ba60e22 | note | – – – – – – – – –
46ec5056-549f-52b4-8408-13566926543e | note | ACCEPTANCE CRITERIA:
0b6e7f51-7eea-5710-b4b0-cec9747747cb | note | • Survey activities undertaken to ensure and validate that all works meet level and location requirements.
fe5681df-e0d9-55a9-a0f7-a375cef0fefc | note | • The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
e71f0f60-0be0-525d-8fd8-841cf42487c9 | note | • IFC and latest available revision used
8503b1ea-0d9f-586e-bd78-6c7876872017 | note | – – – – – – – – –
3efd4a0c-8396-5eea-be87-ec47a89756f2 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
d15b30ed-13ad-5363-a1fd-bed9985c3e2a | note | – – – – – – – – –
3c35be4c-c355-52e6-b6b4-c95e649dc688 | note | INSPECTION/TEST METHOD: Site Inspection
d68cf9cd-ac68-5af2-8edc-4a325e414cae | note | – – – – – – – – –
f4473f8a-e2fe-5df9-bc7a-9389610aa363 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
781d63aa-2388-559a-8454-9c26ab727977 | note | – – – – – – – – –
c8012e9a-dbf8-5e47-9daa-2d4a87e0bfff | note | SCP
fd6c0f6d-02fe-58c9-b102-1e37e7209d9c | note | – – – – – – – – –
00a9ab12-2be7-5e82-afaf-961de3987d08 | note | RESPONSIBILITY: Site Engineer/ Surveyor
20df4330-7bdd-5475-ba79-9e3ef77a3f56 | note | – – – – – – – – –
6cc46f13-1cf0-5f77-9e59-c4406dde0420 | textbox | DATE:
59c391fe-b3e1-4b4d-bd37-80ce0cc6b937 | checkpoint | 2.2 Inspection of fill area
973cf994-449a-5e88-837c-fdfd16edbc76 | note | FREQUENCY: Each lot
b0247ba7-138e-5684-99b3-a610ba65db17 | note | – – – – – – – – –
ca85d0d4-7d9c-5f8e-83fd-bbe9d780cbb8 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
60908ee1-aad3-5acb-9f3c-2797ac4bff4f | note | – – – – – – – – –
80624085-4887-54b5-b17a-bd31d8816460 | note | REFERENCE DOCUMENTS: 204.10 (b)
19d1af71-a227-595d-8288-1d8c66a53b6d | note | – – – – – – – – –
7b05ca4e-aa13-50dd-9978-32a47b2e7cc9 | note | INSPECTION/TEST METHOD: Visual Inspection
f72b2d46-ab59-5aa9-a57e-e53c717622db | note | – – – – – – – – –
054713b9-885a-53a6-953b-3857c27b0bce | note | RECORD OF CONFORMITY: This ITP Signed Off
e9df4ed4-56e5-51e8-9334-d33181d5074c | note | – – – – – – – – –
c9188280-c723-5ae6-a484-dda87f306a18 | note | HP
eb4591a2-558e-5d4f-838e-909ae052a4b1 | note | – – – – – – – – –
9c12ee88-b71f-59ef-842b-fd62cf7194f6 | note | RESPONSIBILITY: Site Engineer / Superintendent
e2ae344c-e0a3-531f-9775-41d0f6c3d596 | note | – – – – – – – – –
d202da88-d374-5cbd-97bb-cd61940ffaa8 | textbox | DATE:
2875f3e2-9a05-4aa5-9df8-3a1c9902fcec | signoff | HOLDPOINT AUTHORITY
7f2c5574-f6bf-4621-80f5-d83132fad8d1 | checkpoint | 2.3 Keyed fill layer
b086c0df-b5b7-536a-a623-44d85378803d | note | FREQUENCY: During Excavation
f715245c-9ccf-5b45-b499-298fdf052200 | note | – – – – – – – – –
54afb3f8-7640-5142-89c3-ff7b8ff93dd7 | note | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
49d5b87e-61c9-5da3-9ee1-a62b9b376dd6 | note | – – – – – – – – –
4fe71550-a3d2-5127-9123-0c9098343eef | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
30d57088-100c-52db-a82d-a166ab7ad72d | note | – – – – – – – – –
5a081242-df2e-5ce1-88cf-70976fe33e05 | note | INSPECTION/TEST METHOD: Visual Inspection
58fc17db-0714-5b62-8b7e-371c7a51fa98 | note | – – – – – – – – –
25bf0156-6ece-51e9-9e8d-2326affc7206 | note | RECORD OF CONFORMITY: This ITP Signed Off
507a2cda-f5fd-53fd-9c43-47225632147c | note | – – – – – – – – –
404c6676-95eb-5d10-9fcc-58b7c9b608eb | note | IP
62877747-1442-52cf-9064-17ce995d39ba | note | – – – – – – – – –
b0ff1ab2-3ecd-542c-ae81-3ed9f0ade9b5 | note | RESPONSIBILITY: Site Engineer
311681f2-c532-5daf-919f-b2d6439f4812 | note | – – – – – – – – –
ea81a16d-b962-51ea-b73f-4c7dcf3878ff | textbox | DATE:
b3fded7d-be55-441c-9029-225f055d57f8 | checkpoint | 2.4 Layer Thickness
8dd7e02e-b957-57aa-9c39-5676b12e933a | note | FREQUENCY: During Excavation
00ddd761-3ec5-5ed2-a4ad-f8385e274161 | note | – – – – – – – – –
0fe29950-ed18-5282-8744-e6a901f4868c | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
6a858fb4-3d9c-5ce4-a825-90fa11656447 | note | – – – – – – – – –
fdd848a6-5c38-5146-8dac-7161fb68d72d | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(iii)
d0289c33-5271-5748-9cfe-bc57cd4dfd5c | note | – – – – – – – – –
7c599869-5a80-5dbf-96bf-79e3e4b4fe3a | note | INSPECTION/TEST METHOD: Visual Inspection
4c3f58f3-93b8-5d0a-9562-744a6639c311 | note | – – – – – – – – –
8eb389c8-301f-595c-97a2-8ccba3a2f224 | note | RECORD OF CONFORMITY: This ITP Signed Off
143d983a-a805-5f9a-abb3-64c4b6d73798 | note | – – – – – – – – –
e5399f9e-a59f-536c-9889-39ed44594f09 | note | IP
7f0c49b3-3d1e-5ef7-8bc1-733a8016b54a | note | – – – – – – – – –
0d17b534-9ec8-5119-b79e-7f6a2f5e83cc | note | RESPONSIBILITY: Site Engineer
2eb18e2c-fe07-574f-b37f-390e58cef5aa | note | – – – – – – – – –
3aacda80-7ec4-5c7c-9621-6da38e7a69aa | textbox | DATE:
f73d95ef-f670-4928-88b6-9ff1444fb417 | checkpoint | 2.5 Maximum Lot Size
b855e67b-96f4-568e-b755-5d88a8572c7c | note | FREQUENCY: During Excavation
de57009d-4c6b-5e90-a8a8-50269d7377af | note | – – – – – – – – –
89359cd6-7dec-5601-b0ed-90809b445cda | note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 10,000m2, whichever is lesser.
b2bce1f1-7030-535e-b3ea-10a72f195dc6 | note | – – – – – – – – –
21a74abf-8234-53c3-a850-c7524ddbac99 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
89e7fc65-eeb0-5212-88d8-5baa562ea428 | note | – – – – – – – – –
d7f58f58-e45a-5ab4-8ceb-f204755ddb18 | note | INSPECTION/TEST METHOD: Visual Inspection
f4f8a673-c260-5db2-9c10-f4048ca042a9 | note | – – – – – – – – –
b88a0f89-e33a-5e86-ab70-60ace5476d21 | note | RECORD OF CONFORMITY: This ITP Signed Off
aee225ab-a577-5200-886c-b166afef2197 | note | – – – – – – – – –
323d59a9-a908-5020-a90b-500dc5d05c7d | note | IP
66195267-e48c-579e-a2f3-92e15227d362 | note | – – – – – – – – –
eee32cc7-d3cc-54c7-b04c-6cf32cdb2186 | note | RESPONSIBILITY: Site Engineer
4cd447ac-b5ae-51ec-8db9-fc96605c4653 | note | – – – – – – – – –
90f32fe7-f059-5a61-a905-cce20810231f | textbox | DATE:
cc7aa855-c219-4373-9cb1-2a10d5f57f87 | checkpoint | 2.6 Type B Placement
935e79c2-9dbb-5e0d-ab88-696faa87cd87 | note | FREQUENCY: Prior to Placement/Each Lot
eb1b6f3d-b70e-54c1-bcba-c19d1c1a43da | note | – – – – – – – – –
58200893-2069-5a1b-9c7a-85c80a2fce2f | note | ACCEPTANCE CRITERIA:
429ae7ea-bd43-5285-8083-78de92774106 | note | • Type B material shall be placed in locations shown on the drawings, or if surplus Type B material is available, it may be used in locations specified for Type C material.
dabbeb97-aa14-5ab6-af3e-89ebea17c031 | note | • The highest quality Type B materials available shall be reserved for placement in the higher levels of Type B fills being constructed.
c3be97bc-7d87-505d-ace6-92bece990ba2 | note | • Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
1f1b1b4b-ffb3-5a11-92a1-0ac856cdcd8c | note | • Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm.
70470e90-c314-5094-b33d-516546861997 | note | • Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed.
6e49e679-fa35-5dd0-bb02-e1145593c810 | note | • The material shall be placed and compacted such that voids are completely filled with fine material.
b2347402-b98c-5c40-9758-b349f6fe268f | note | • Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones.
4078b9bc-cac0-5d68-a6df-06de140ab1f8 | note | – – – – – – – – –
33ac5fe5-5bf6-5732-a611-19e31070cabb | note | REFERENCE DOCUMENTS: 204.10 (d) (iii).
9a4fda84-2411-5b0d-a0a9-7bee21128784 | note | – – – – – – – – –
530eb65f-4e01-5020-b0d2-7e7e09265c31 | note | INSPECTION/TEST METHOD: Visual Inspection
34b86556-ec04-5ffb-a014-fddbc5f1cc0c | note | – – – – – – – – –
dc60ea16-a37c-5954-9b0c-150f3bc64b70 | note | RECORD OF CONFORMITY: This ITP Signed Off
11f1c75e-8f11-5af1-940d-f62ad70ec6fd | note | – – – – – – – – –
b71e12b9-0c32-5c2c-b71a-26a462d64eae | note | IP
03d18cad-0ff5-5bfe-a5c8-4bcec36eb76b | note | – – – – – – – – –
2ff0fbd8-627d-521e-8de2-a54f41d838ca | note | RESPONSIBILITY: Site Engineer / Site Foreman
1185deed-874b-5579-a4d6-0eb96a6d50e2 | note | – – – – – – – – –
7cb2be1c-a750-58fa-9aae-07edd8c4218e | textbox | DATE:
2f9930f6-a031-408f-958b-6373382f2922 | checkpoint | 2.7 Proof Roll
355914ce-1572-5160-8462-4911e6752e5b | note | FREQUENCY: Each lot
a2747667-8560-51aa-ad89-2ef2f1f3e612 | note | – – – – – – – – –
097da54f-dd19-5cbc-a7ea-677c4b0088fc | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
d0082a02-24dd-5b2b-970a-0073b0ad26b6 | note | – – – – – – – – –
77b6e459-743d-5f9a-92f5-92c13f8823e6 | note | REFERENCE DOCUMENTS:
9c4897ae-b7e6-5bef-b560-3b152df68750 | note | • 173.03
8ab3751a-f580-5f6a-be0a-90e808c4244a | note | • 204.12)
90abc82f-ac9c-56db-abd0-130a1fc9453e | note | • 204.10 (b)
3046db75-3656-5572-a333-c0880e11a954 | note | – – – – – – – – –
635f2083-0b68-5c04-abd7-0b3b8847015b | note | INSPECTION/TEST METHOD: Visual Inspection
776a3cce-8606-54d6-9e7e-6d51a186e906 | note | – – – – – – – – –
ff79d9eb-2fd1-5ebd-b2d0-c6c2699c6264 | note | RECORD OF CONFORMITY: This ITP Signed Off
b208e7f6-2c56-5189-9eeb-ef4e56e9e021 | note | – – – – – – – – –
a1ae1f36-83ce-554e-874a-ebfdc4a0958e | note | HP
178bfd5d-de7a-5593-b9ee-521569bcfa0b | note | – – – – – – – – –
4d23e025-9fba-59b6-ba7e-c31e56792c5b | note | RESPONSIBILITY: Site Foreman/ Superintendent
cf007fa7-460f-5eca-800a-e464723d8044 | note | – – – – – – – – –
19960443-f507-54b4-baef-e904662561ad | textbox | DATE:
943b5443-0b6c-4c04-a764-766a90e834aa | signoff | HOLDPOINT AUTHORITY
633eb8b0-7fa7-4771-b064-3b3279189ff9 | section | 3 - Testing
426cdf64-6b7d-4b06-944b-d03ea8e3aada | checkpoint | 3.1 Reduced Test Frequency
842600f8-61db-59b0-a70a-770e98ee814a | note | FREQUENCY: Each lot
8f92f963-7a41-5c5a-b356-5b53396b61dc | note | – – – – – – – – –
f42db932-9e6b-5df4-960f-2cd2c867e09b | note | ACCEPTANCE CRITERIA:
c2cb664a-3b16-5abe-95ec-1c37b19a185c | note | • Initial Testing requirements shall satisfy the full requirements as detailed in the specification.
2a3d12a7-24a9-527b-80fe-95004b62ab4f | note | • Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141.
42579f41-ec0d-5d53-932d-6fe3f747ca10 | note | • Reduced frequency resets if one lot fails.
518168aa-4f38-57e7-9635-b0bbe3c8434c | note | – – – – – – – – –
74e3f1b1-0bb6-5ba9-b8eb-7763de65fbd8 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
0d6f06b0-75ab-51a4-965c-3cca1f264f0e | note | – – – – – – – – –
dcf4d6fb-35ef-507e-9612-e11c1dd93c6d | note | INSPECTION/TEST METHOD: Test Record
9418e1a7-d059-556b-bc5e-3dd2830b7d07 | note | – – – – – – – – –
8f1bc12a-226f-55e9-9581-95fb0bbb5950 | note | RECORD OF CONFORMITY: Test Records
31822cc5-9a25-5787-a432-852434068ac3 | note | – – – – – – – – –
361f9102-6856-55b9-b4e2-85e19f83b9a3 | note | AP
5de3b476-e2b0-5f1d-887b-7b30c8d26ebb | note | – – – – – – – – –
12cc6438-a439-57a3-8965-2455306b4b39 | note | RESPONSIBILITY: Project Engineer/Superintendent
dec06a49-15a3-5d91-b429-c6df12d5b61e | note | – – – – – – – – –
91021f51-9a2a-53e9-9eb6-f4449b052a1a | textbox | DATE:
f06c15ff-ef76-4aea-b728-352813d6babb | checkpoint | 3.2 Compaction Testing
45988a28-ead9-52a5-aac3-5760ec108f1e | note | FREQUENCY: First lot then every Second thereafter
afd5626a-3b69-5d8c-8298-7bb11a15c5e0 | note | – – – – – – – – –
bd81d9ab-1a0f-55b7-9c15-fd26c2219b86 | note | ACCEPTANCE CRITERIA: Type B compaction required for Scale B is 98% Characteristic Value of Density Ratio
460c0a78-efed-50b3-bf86-0e7aa1ed35f4 | note | – – – – – – – – –
c07f067d-c9f7-562f-94de-0d6c3c8e461b | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
eaa65b6c-7c0a-581a-81c2-e4803ba8c2fa | note | – – – – – – – – –
3c461cb1-4180-5912-afb2-c6cceb36ea37 | note | INSPECTION/TEST METHOD: Verify
810a6dfb-05a5-5b91-9c18-addf1dc5d726 | note | – – – – – – – – –
01831bcc-113b-5a5f-874e-9e5687cabdd5 | note | RECORD OF CONFORMITY: Compaction Test Records
4d6e9bb5-459d-56e6-b3e2-12ed64b7735d | note | – – – – – – – – –
4f14f12b-96ff-55c6-b6ab-7678c0ce1859 | note | TP
84feb1c8-8dd8-5f3a-b2ee-04778bb51afc | note | – – – – – – – – –
0c086f2a-779a-5315-9bb5-fbe77c7b5888 | note | RESPONSIBILITY: Site Engineer
ff216c01-afdd-5a52-8f40-7fe331bcf443 | note | – – – – – – – – –
79f3abb5-80d8-5912-beb8-f3141d48586c | textbox | DATE:
e0333554-df09-4eb5-b418-80638139466b | checkpoint | 3.3 CBR/Swell
a25e58ac-5f82-5bff-b97c-45055eceffe5 | note | FREQUENCY: 1 lot test to determine assigned CBR and Swell
7088cb32-d713-5a0f-848a-97e438638c0c | note | – – – – – – – – –
2873451a-0491-5223-bb29-659d1dd151ba | note | ACCEPTANCE CRITERIA: CBR: ≥ 2%, Swell: ≤ 1.5%
f7c3356c-bc5e-52fb-9d07-30adeef9844c | note | – – – – – – – – –
a55c9222-e33d-5170-82dd-b55a30a794e8 | note | REFERENCE DOCUMENTS:
b4702895-9aac-5fb4-adaf-2df03fc1a87c | note | • VicRoads Spec.
f927ed7b-ffe9-5862-8ce8-52f7a3795bd0 | note | • Cl. 204.14(a)(i)
4de2955e-b324-550a-a4a0-1a639939f3c8 | note | • Table 204.141
2c89adc1-ea80-5e82-a166-86bc5d51200f | note | • Table 204.041
55c53068-78e9-5965-a4c8-0c9fe0d84a0a | note | – – – – – – – – –
abe5f871-32d5-54e8-80b2-b6b87fd6e257 | note | INSPECTION/TEST METHOD: Verify
61973671-b131-5dc4-9846-22db68da35b6 | note | – – – – – – – – –
10a3b047-ae96-5bc7-94bd-8c20c5057e36 | note | RECORD OF CONFORMITY: CBR/Swell Test Records
8173e657-d976-57cf-a642-2500aeb6a430 | note | – – – – – – – – –
f9796bab-84ba-52ea-b066-e1c871adbdb3 | note | TP
c0c18244-612a-5f6a-bcba-7333a0fa43e1 | note | – – – – – – – – –
4793e970-97bf-538f-a046-1a4db17a8b4f | note | RESPONSIBILITY: Site Engineer
6d3214b5-b0cb-5e00-9c21-3084922c0b58 | note | – – – – – – – – –
fcab4be2-f961-57b1-ba66-1739ec061038 | textbox | DATE:
542b7f21-7d71-4039-a3b0-6bec48127292 | checkpoint | 3.4 Survey Conformance (at Subgrade Level)
3d88d32a-177f-58d4-81b6-b9b4a69e97f5 | note | FREQUENCY: Each lot
b16e5cdf-7a49-5987-875b-8e46df98bddf | note | – – – – – – – – –
9d7f8f80-e5b8-500c-92bf-fa5a3193b231 | note | ACCEPTANCE CRITERIA:
ed33aacc-3a6e-57f1-add8-e79c3c7b447c | note | • The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
a8c10247-c327-5d16-9c92-d03721027eb3 | note | ○ Scale B: Range x = +5,-25
2515b25f-7853-538c-9b86-a648a1f0a19f | note | ○ Max S = 15mm
1343475e-6914-55d7-b4ec-f3524e07d8bc | note | ○ 40 measurements per lot
1d09369d-57f1-5e6d-b162-850c90afc2a7 | note | – – – – – – – – –
e0eff5ab-5d6b-51fd-a63d-6eebbc61c28f | note | REFERENCE DOCUMENTS: 204.03
c3e217ce-8999-5694-b4d2-519e24b158c9 | note | – – – – – – – – –
8d3fe57a-fb46-5a5c-a126-50183925c112 | note | INSPECTION/TEST METHOD: Survey conformance point
70f59a08-1f03-5691-8520-9bf8c0acde1e | note | – – – – – – – – –
7e1f7b6b-8d1a-521c-aeea-fbfdabd730b9 | note | RECORD OF CONFORMITY:
1666816b-f163-5a77-86f5-468fd12294cb | note | • Survey report
3e3200b7-00c6-5ca9-b91f-10a639545078 | note | • Lot Register
86055481-0242-51e4-a290-ddef3c5058df | note | – – – – – – – – –
3777fa50-6769-52a0-af24-0c853347348e | note | WP SCP
b36ea040-8a0e-57cf-b5f4-336c2717c029 | note | – – – – – – – – –
9ef55101-1376-545a-813d-2be2508cfca9 | note | RESPONSIBILITY: Site Engineer & Surveyor
24daeb72-bb37-5137-8dd6-ab52041420e2 | note | – – – – – – – – –
b3ac6a9f-d0d5-5186-ac92-9db30972b149 | textbox | DATE:
f2f0ab95-1e0e-4f92-a9db-4663f77f6727 | checkpoint | Final Inspection
7d8449b9-1b10-5e77-9892-914b444ae4cd | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
993306e5-ea39-5c16-87aa-0a92541b5b25 | textbox | Print Name:
e5c92733-4182-5e7f-8102-e0449138f556 | textbox | Position:
2539fa94-7fa3-5cb9-a71f-814016518e6d | textbox | Date:
987743d3-0d22-48c3-99f6-61461c25d320 | checklist | ITP-01-022 - Culvert Excavation & Backfill (V-Line) |  | ITP-01-022 - Culvert Excavation & Backfill (V-Line)
a60e7bc7-fa3b-4ee0-a928-22e4c1c32476 | section | 1 Preliminary Works
3a44dc25-77ad-4a76-89d4-81d1a60e61d9 | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
f3f5f921-5787-5610-9713-6bd937e5c4c3 | note | FREQUENCY: Prior to commencing
a5308269-6498-5894-babc-77909da4b42b | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
6edff5b5-3cd7-5a21-ad14-c68a0d285b12 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8e031745-4efd-53d8-8e59-56cff46b1e21 | note | INSPECTION/TEST METHOD: Visual Inspection
39028f93-07b7-5e30-9f51-0642aa48aaf8 | note | RECORD OF CONFORMITY: This ITP Signed Off
a41073b5-7d80-5ed2-8114-44729b5bad16 | note | HP*
e1fcb924-9ddc-5c65-91f2-c76a3a52b432 | textbox | SCALE A OR B:
c20c7b1e-e606-51f9-9ca8-38141a1e1ac5 | note | RESPONSIBILITY: Site Engineer / Site Foreman
615db958-2712-5559-8e48-c4ecb457393a | textbox | DATE:
5aaf90ed-a793-4bc1-b36e-efd0d721cb3c | checkpoint | 1.2 Implementation of all measures and controls
07c5a441-03d4-5729-977a-ed15345ba13f | note | FREQUENCY: Prior to Placement/ Each Lot
24394e6b-1aa0-5025-85f5-0098e138d501 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
49ae1e8d-5b4a-57d2-94e0-887acffe7e4a | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS, WP001.02
3fd2e8b0-0cfc-550c-ae69-6fee2ecc2de8 | note | INSPECTION/TEST METHOD: Visual Inspection
b38ae23a-52f5-51ec-b0c3-453569b2c6b8 | note | RECORD OF CONFORMITY: Visual Inspection
4a444b8a-83e6-579f-9c86-18fd7439877d | note | HP*
90680400-3033-599b-aeb6-83d59df52129 | textbox | SCALE A OR B:
76c45a7f-8d5f-5325-b834-15e775692606 | note | RESPONSIBILITY: Site Engineer / Site Foreman
af9402ec-ca70-5ab1-9827-b5c47b6605ad | textbox | DATE:
0a11eb71-4621-4df2-bc97-aa4eaff3019a | checkpoint | 1.3 Verify Material
b940d839-be80-5f36-9028-b93e780cea98 | note | FREQUENCY: Prior to Placement / Each Lot
989f508a-b7fb-506e-b447-51dc85233463 | note | ACCEPTANCE CRITERIA: •General Fill Material - CBR of more than or equal to 2% and must be free of particles greater than 150mm in diameter •Structural Fill Material - CBR of more than or equal to 8%. The product of the iquid limit and the percentage passing a 425mm microsieve must not exceed 1800. Grading of material shall comply with Table 4 of the V/Line Earthworks and Drainage Standard (NIST-2659)
aa897f5b-0183-5341-ac5f-a66fb4fa9e6f | note | REFERENCE DOCUMENTS: V/Line - NIST-2659 (2017)
4eabdb7f-2461-5df9-9549-4e70724fc619 | note | INSPECTION/TEST METHOD: Verify
48aac698-8fad-5162-bf1d-c9fcf27cfee6 | note | RECORD OF CONFORMITY: This ITP Signed Off
10d2d860-139c-5591-a38c-4b214f93b605 | note | HP*
b47210d2-a948-5e29-a40b-a23d7a6b5850 | textbox | SCALE A OR B:
f1a5ecf3-04ff-5f7c-87d1-bcabab8897e9 | note | RESPONSIBILITY: Site Engineer / Site Foreman
bf203d31-02de-5c5d-942f-fe5f2ed4bfa8 | textbox | DATE:
ffc90216-0543-433f-95a1-1b4de83d61bb | checkpoint | 1.4 Excavation Permit
5bc2d24f-3111-5577-a12c-ffdadb68354a | note | FREQUENCY: Each lot
8db5c211-f855-55fa-8b4b-a2a78c7a4a4c | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
829b1639-750e-58e3-8a5a-5ff707a4c40c | note | REFERENCE DOCUMENTS: Excavation permit
d4639be9-16fd-5f13-95c7-765a0068e302 | note | INSPECTION/TEST METHOD: Verify
d18df0d5-2cac-50e5-939e-6dd4b28f87fb | note | RECORD OF CONFORMITY: This ITP Signed Off
b6e65e0d-0c8c-5982-b9fd-51d4ece744c9 | note | HP*
e2ce7b98-29a0-51d8-a856-ac594271d8c4 | textbox | SCALE A OR B:
4c4bf56c-5401-5598-8caa-13f2bbb5be0f | note | RESPONSIBILITY: Site Engineer
eac418e5-675c-5d18-ad1c-d562ed30807d | textbox | DATE:
18963fbc-ce9b-4684-a4a3-2a98e72fd2bf | section | 2 Construction Works
e9397bb7-ae9d-4993-a19e-7b03b8d730a0 | checkpoint | 2.1 Survey set-out
0d303bb8-7953-5b65-92d8-57093ec9ede1 | note | FREQUENCY: Prior to Commencing Excavation
c8edbcb2-195c-5358-96bd-c4b69077f8a6 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
ae80fde4-c9a4-5b3a-8761-20813648d1e2 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
72dfc951-7815-556d-933a-18703edfde0d | note | INSPECTION/TEST METHOD: Site Inspection
533ca967-a254-5677-b8b1-12372da30118 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
2d02ca41-f747-5606-9f4c-cc2faa1bcdd5 | note | SCP
38a771f0-6c74-5f25-be09-759e81bff1b7 | textbox | SCALE A OR B:
997601d2-6c1d-5d1e-a179-7cf93bcbe048 | note | RESPONSIBILITY: Site Engineer / Surveyor
c1212365-b893-5e8e-b503-d3ba00ff2c62 | textbox | DATE:
2396d360-bff0-4a23-a3b4-63847d262bc1 | checkpoint | 2.2 Topsoil Stripping
34f9ed1e-ea8a-5cc9-b53a-d0e6c33560c9 | note | FREQUENCY: Prior to commencing Box-Out
2ea0e147-c789-5a2a-a398-ee8f1db28f03 | note | ACCEPTANCE CRITERIA: Top soil shall be stripped to a minimum of 150mm
bbc52e75-97ea-5dae-98a6-11e4f91c9be5 | note | REFERENCE DOCUMENTS: V/Line - NIST-2659 (2017))
6a4dd0c1-6404-5f4b-8a1b-ef7ebe1d1620 | note | INSPECTION/TEST METHOD: Site Inspection
c9feafec-052e-5a1d-a9ea-5f8eb3e7188f | note | RECORD OF CONFORMITY: This ITP Signed Off
cf4fa570-3d3c-5875-ab96-352fe5a0bf2b | note | IP
feb7c0d2-8855-581c-8120-f4886db57114 | textbox | SCALE A OR B:
61cd06c6-a650-5511-99ea-ef5a8c5bb1b1 | note | RESPONSIBILITY: Site Engineer
91b2ab5b-54c0-551b-8b31-f524d8a76b5c | textbox | DATE:
7df698f6-b8b9-408b-8e8d-ed1d12e71788 | checkpoint | 2.3 Excavation/ Box Out
62333991-a12b-5553-abb1-61fbc90c28e6 | note | FREQUENCY: Each Lot
1c1b5b13-69c2-522c-8c10-53307465f833 | note | ACCEPTANCE CRITERIA: Excavation shall comply with SAPR-73 "Excavation Management": - Trenches shall be excavated to allow a minimum 100m between side of trench and pipe/ culvert - All precautions shall be taken against accident or damage to the works ie. Benching
bc3f841e-2a60-5644-b932-ffc5ce9e491f | note | REFERENCE DOCUMENTS: V/Line - NIST-2659 (2017)
5cd5be30-f1a5-5c75-9bc8-82403bcb9867 | note | INSPECTION/TEST METHOD: Verify
ede76b31-b360-5095-b417-084c440c6574 | note | RECORD OF CONFORMITY: This ITP Signed Off
84532b07-04f7-5ffc-91a7-90130513c90b | note | IP
eca99c32-5a16-51bf-8626-276e5b3dd855 | textbox | SCALE A OR B:
cb845a64-07ef-5245-b17b-978f56b284be | note | RESPONSIBILITY: Site Engineer
2814a083-e747-528f-8e94-aa6818079f20 | textbox | DATE:
480ef2e6-2a81-4e49-bcfc-a9d799a4a297 | checkpoint | 2.4 Treatment of trench bottoms
a2184d48-fa04-546d-a9db-f6da2399a2c9 | note | FREQUENCY: Each Lot
be9a3b73-bb12-5c83-a7f7-de5fce57ac56 | note | ACCEPTANCE CRITERIA: The bottom of the trenches shall be compacted to a minimum of 98% standard compaction
4df6f2f7-2cd7-511c-a789-c36d115ca299 | note | REFERENCE DOCUMENTS: V/Line - NIST-2659 (2017)
4209ff69-01d6-5ed5-b26f-e9afe67f0517 | note | INSPECTION/TEST METHOD: Verify
f24de789-f28c-5e81-ab4d-a6577a5e00c6 | note | RECORD OF CONFORMITY: This ITP Signed Off
b83af4ee-7ccb-54a3-b8ca-68b02e598407 | note | TP
96c5336d-29d8-541b-a0b6-e38103b95daf | textbox | SCALE A OR B:
e1ab5508-ddf3-52e4-bc67-52a8b254c729 | note | RESPONSIBILITY: Site Engineer
3479d923-5b50-5dfd-9890-5549407bfe47 | textbox | DATE:
bc556902-964b-4aa5-bdb3-22127bf54ce0 | checkpoint | 2.5 Pipe / Culvert Basecourse
98cfb244-fe64-5e8c-92d1-ca8014d73f49 | note | FREQUENCY: Each Lot
e7959245-e439-59a8-baba-727218962e4f | note | ACCEPTANCE CRITERIA: Unless otherwise specified, a minimum of 200mm of compacted rock shall be installed below the pipe collar/ culvert base
9e6bc337-4a45-5b45-b4d4-2aafb09ed879 | note | REFERENCE DOCUMENTS: V/Line - NIST-2659 (2017)
6e99d3c1-8585-5d5a-b25c-e7e295da0aa7 | note | INSPECTION/TEST METHOD: Visual Inspection
77589b91-0d63-52f2-83b1-27cb6f03f88b | note | RECORD OF CONFORMITY: This ITP Signed Off
b571a625-efbb-55a4-a0de-771cfc63e5db | note | IP
1e39ffe6-5667-5d64-a628-6c200780eec7 | textbox | SCALE A OR B:
1648ada3-62ab-5c81-bbb0-61b6f092f0e0 | note | RESPONSIBILITY: Site Engineer
2d150f70-d486-5fcb-9999-239439d14599 | textbox | DATE:
ad0c35f3-25dd-413a-a246-68170e9ded99 | checkpoint | 2.6 Layer Thickness
458692f2-08bf-5b47-bdcd-16942bda947e | note | FREQUENCY: During Fill Placement
b19ca86d-7378-5b05-adae-39fbed7cab0a | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 150mm.
c5a0bb08-6e53-55d4-81fc-e343580e1136 | note | REFERENCE DOCUMENTS: V/Line - NIST-2659 (2017)
686515b2-a5e2-57fb-b5b1-7beb01e12b7a | note | INSPECTION/TEST METHOD: Visual Inspection
f386ef2a-e7d7-5a7b-954c-731ff86a02b6 | note | RECORD OF CONFORMITY: This ITP Signed Off
b853fd23-4973-5684-9e43-bd85cadc20fe | note | IP
9d228e0a-e92e-5b85-9d65-29040729f0a4 | textbox | SCALE A OR B:
abaab6fe-dc19-583c-ab09-f1afadecb694 | note | RESPONSIBILITY: Site Engineer
0a257d76-32cd-5962-9b70-cf454d005dac | textbox | DATE:
f7298ae6-1805-4c6f-95ac-0e5d257b78c7 | checkpoint | 2.7 Proof Roll - General Fill & Structural Fill
46aa9f1e-6d33-5aa8-9dcd-9660b3058945 | note | FREQUENCY: Each lot
23862ad3-89fc-5fa5-b076-cd3cb480c837 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
2ae20004-be43-54e3-a000-46894113c9b4 | note | REFERENCE DOCUMENTS: V/Line - NIST-2659 (2017) VicRoads Sec173
0526801c-de3f-5aaf-a2d3-7b06a36ee2eb | note | INSPECTION/TEST METHOD: Visual Inspection
7257ac15-f019-5707-91a2-2ec6aeaf6c4e | note | RECORD OF CONFORMITY: This ITP Signed Off
f49dc452-1625-5043-bd95-0a134d5583be | note | WP
74209a3a-5714-57a0-971f-42e163bf5d64 | textbox | SCALE A OR B:
f0c1aa3f-d05e-5859-962f-cc90fac68f49 | note | RESPONSIBILITY: Site Foreman / Superintendent
afdbe735-1dd2-5fef-acd3-e51557545e9d | textbox | DATE:
ba94add8-b78f-41eb-a8e4-89dcc9a3aa6b | section | 3 Testing
5dfea07b-cdd7-4cb0-b0c2-46cc5bf02eee | checkpoint | 3.1 Backfill Compaction Testing
e9db292d-b586-532d-af71-bc57a11ce769 | note | FREQUENCY: Each Lot
87fe0d17-0fe4-5268-b697-22706bf5ac93 | note | ACCEPTANCE CRITERIA: •General Fill Material - compacted to a minimum of 98% standard dry density ratio (RD) •Structural Fill Material - compacted to a minimum of 95% modified dry density ratio (RD)
ee246464-4675-5892-a687-967db1900b76 | note | REFERENCE DOCUMENTS: V/Line - NIST-2659 (2017)
b79ace68-ebf4-5192-b216-a4b80d9345f4 | note | INSPECTION/TEST METHOD: Verify
e334ff9e-a310-5997-ba27-4b71ea006022 | note | RECORD OF CONFORMITY: Compaction Test Records
fb878680-97ff-5160-9e50-403d1752fa5d | note | TP
fad909c7-0251-57ff-881d-afa2971ec7bd | textbox | SCALE A OR B:
bfdf92c6-56b7-5380-b196-8abf65786538 | note | RESPONSIBILITY: Site Engineer
0e610caf-444b-5cb0-82e6-c836e4871388 | textbox | DATE:
d08ae374-f70a-45c4-8cc4-a8d3f7f26129 | checkpoint | 3.2 CBR/Swell of Fill Material
eec31c22-d218-525f-adfe-d721ea3b8971 | note | FREQUENCY: 1 lot test to determine assigned CBR and Swell
11c81b54-a9a9-51f8-936a-67cd17e93e87 | note | ACCEPTANCE CRITERIA: •General Fill Material - CBR of more than or equal to 2%, no swell requirements •Structural Fill Material - CBR of more than or equal to 8%. The product of the iquid limit and the percentage passing a 425mm microsieve must not exceed 1800. Grading of material shall comply with Table 4 of the V/Line Earthworks and Drainage Standard (NIST-2659)
532875e3-6c0b-59e1-8645-148a545b28d7 | note | REFERENCE DOCUMENTS: V/Line - NIST-2659 (2017)
03613ed7-f8e5-5fd3-82ad-bf0dcdcb8ef6 | note | INSPECTION/TEST METHOD: Verify
0fc14be2-7fb5-5909-a48a-b0becc3f323e | note | RECORD OF CONFORMITY: CBRTest Records
822ea765-e552-5190-84e8-5980c75f5266 | note | TP
12d9d62c-bfc5-5cf0-b94e-1e26e14a3193 | textbox | SCALE A OR B:
79d9ff84-001d-5587-a7a8-dd1c84c8ef03 | note | RESPONSIBILITY: Site Engineer
73575003-721b-557c-859c-0e1566c7bbeb | textbox | DATE:
4b614a87-6e8f-4cf2-b0c8-695eda1aad6c | checkpoint | Final Inspection
5fe22859-ae56-54d6-986d-d8d88955e940 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
bcce02bf-f49a-585e-a3a7-011b48eef5cc | textbox | Print Name:
6ab55597-c5e5-5ac4-a4af-8f3c51ae9ac4 | textbox | Position:
d22de8cb-bb4c-5527-ab3a-23462379fbc5 | textbox | Date:
3ed5abba-a689-4d21-8b39-705c1cdcf163 | checklist | ITP-01-023 - Conduit, Pit & OCS Installation (V-Line) REV4 |  | ITP-01-023 - Conduit, Pit & OCS Installation (V-Line)
1f19bc3c-b9e5-4413-b43d-8ff3ac38cfa8 | section | 1 - Preliminary Works
f768bdce-ef21-45b7-9dd4-59f42aea1c4c | checkpoint | 1.1 Check for correct documentation
ff767dfb-2405-56d0-b4b7-6fe4b5744c8e | note | FREQUENCY: Prior to commencing any activity
d41322a3-56ed-5ee0-b32f-eba82e206c49 | note | – – – – – – – – –
9d518a98-4334-5675-8e40-fdd9f774f748 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
3f502f95-05a6-566c-ab00-b470a3e632a1 | note | – using the correct and complete set of drawings
6cd8bf61-4817-590f-ba4f-53df70e05499 | note | – all drawings are the latest revision
917a3c43-a0e4-5b8b-a7b9-f291fc2104b2 | note | – – – – – – – – –
ba65fe6a-e039-5153-b56a-af513fb752df | note | REFERENCE DOCUMENTS: Drawings and drawing registers
190fa44e-fa55-5356-b1b4-e1f215cac186 | note | – – – – – – – – –
56103395-6b7c-5e27-a9dd-768760e8ae2d | note | INSPECTION/TEST METHOD: Visual inspection
079ce5c2-6bba-50a0-ade9-b350604074bf | note | – – – – – – – – –
f6959da4-053a-53d7-ba04-03933be58b7a | note | RECORD OF CONFORMITY: This ITP signed off
c4756d72-d70b-5846-9a24-cf40e9a68719 | note | – – – – – – – – –
10d369f4-e8b3-5f44-af1f-963c34a70688 | note | HP*
e7a9d5b9-b863-51eb-a0ed-c67c7ca71206 | note | – – – – – – – – –
3e58e517-094a-5931-a2fc-a4ffaf68bdb5 | note | RESPONSIBILITY: Fulton Hogan Engineer
1e2b7f66-664a-550f-9e34-fd397e83b052 | note | – – – – – – – – –
a5aa6df7-2c46-539e-b91f-0e9ecfa982f5 | textbox | DATE:
cb75ef1b-9cef-49f5-a024-be17ca014200 | checkpoint | 1.2 Implementation of all measures and controls
10410af2-72b6-55de-b2e6-1f2655f6cc23 | note | FREQUENCY: Prior to commencing any activity
793c7745-117b-509c-a5c0-2561b5fc24a9 | note | – – – – – – – – –
86ec927f-a8e0-586d-a273-308a7fa928bd | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
57b37eab-4f59-5a81-a43d-002a8f54a915 | note | • OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
9ab23461-84d6-584d-8f84-d961cd90bb14 | note | – – – – – – – – –
77d445c4-32e1-54c3-ac5a-4977ddbf9701 | note | REFERENCE DOCUMENTS:
f3773101-7863-5410-ba1e-0c8cd2c63370 | note | • OHSCP
6d767b4d-ed7c-5bd9-99a7-974530984f6d | note | • PHSCP
572f67d8-a7c5-5f1b-a17b-93d4c2159c9b | note | • PCMP
a25e327a-0b0d-5171-9361-0ee1b164bcc6 | note | • EMP
38932fc7-c16d-5f9b-ac40-aa0feedc5bd7 | note | • ECP
ca6e5413-31c4-5e30-8306-44b3328f7c14 | note | • CEMP
7b141437-2c05-5c1f-a196-b9415b47b969 | note | • ERA
d980e9ad-421d-55f5-885f-3df42538850e | note | • QMP
fa9e40b5-fffd-5e2a-a301-c65a73750ef0 | note | • CHMP
cbaf162c-55eb-58fd-947f-44b1155c9641 | note | • SWMS
b7048f96-4b9d-5d98-b2bc-11f7449d3f59 | note | – – – – – – – – –
39b9b05a-90ee-5fd0-ac50-e110661667c2 | note | INSPECTION/TEST METHOD: Visual Inspection
2f09bd8c-bcc3-56ca-aea0-1281b630e1d9 | note | – – – – – – – – –
5a0fe636-beb5-554c-a2a7-3d7ad9966ff6 | note | RECORD OF CONFORMITY: This ITP signed off
5061b78a-6847-5c4e-a4ec-5aa409c3ba81 | note | – – – – – – – – –
0bfb5bf6-9cfa-5dbb-9900-78eadcc9ee45 | note | HP*
b74033ca-f286-578c-9510-d4825d8964dd | note | – – – – – – – – –
4fc29d2b-3d3b-56d9-8c05-e579660a2e7a | note | RESPONSIBILITY: Fulton Hogan Engineer
f6c4a7dc-693d-567e-8339-c10733b0e5e5 | note | – – – – – – – – –
58acfee9-0a4f-5f02-b258-4fd652d26eb7 | textbox | DATE:
4907658c-a135-4b9d-b289-871b0ba44833 | checkpoint | 1.3 Materials
4c75b506-6465-5754-9401-85d59d7b5212 | note | FREQUENCY: Per Batch
9b34f708-af40-573d-87e9-53b5661c77fe | note | – – – – – – – – –
539ea61e-362c-5826-9f77-e7fa515fbedc | note | ACCEPTANCE CRITERIA:
cf0ee92e-23e0-560a-abcc-9c82da807100 | note | • Carpark Lighting A pit is to be installed adjacent to each lighting pole with 1 x 100mm HD conduit and 1 x 63mm conduit installed between pit and the point of supply. 2 x 32mm HD conduits are to be installed between the pit and the pole mounting base.
dcafe4ac-7acd-5fa5-8c52-63794d7f2c97 | note | • Electrical supply conduit all conduits for underground mains shall be heavy duty 'Orange' underground category PVC pipe complying with the most recent issue of AS/NZS 3000 Australia/New Zealand Wiring Rules.
59ddf6d2-1f0b-5d92-a795-f6dd02095f86 | note | • Communications conduit to be white 1C50 HD PVC conduits and 1C100 HD PVC conduits
da1e0e12-a5ff-5ad9-b9b3-1d2922042c59 | note | • Camera mounting poles and structures shall meet AS47806.2 (2006) Section 5.4.1 (k)
2e391b04-2377-5dbd-bb61-dfc5d42d4ffb | note | • Cable pit lids shall be VicRoads type approved, impressed with 'VicRoads' and 'Electrical', 'Communication', 'Traffic signals" as appropriate as per VicRoads Standard Drawing TC-1220
06b9578d-76f9-5355-bbf7-77056e83f95b | note | • All equipment labelling to comply with requirements of NIST-013.4
522d919d-0816-561f-954f-64b465c0d49e | note | • Cable pits shall be 435mm dia x 550mm deep, Type 43 plastic HDPE – Aco Cablemate cable pit with concrete lid or equivalent
dd41577a-9a8c-56de-a6bc-9e6f31c1cbe7 | note | – – – – – – – – –
6e34e44e-3a27-589c-baa5-058610b20129 | note | REFERENCE DOCUMENTS: NIST-5031 3.2.2.5 (f) Drawings
ffa470c1-90ac-57b1-9160-a48727c42d63 | note | – – – – – – – – –
d81d1b53-5fe0-553b-b770-3b9855655f38 | note | INSPECTION/TEST METHOD: Verify
baa5969a-dcfc-5842-9779-b9d547b99b70 | note | – – – – – – – – –
c225d9ce-fddb-5106-a573-c7eaf8ae4389 | note | RECORD OF CONFORMITY: This ITP signed
3144fa52-4c5e-5b15-bdf1-1346c692ef69 | note | – – – – – – – – –
b34327b9-0119-54de-908b-b703b12451e5 | note | HP*
d2e60d51-e430-56e7-a2b8-177bfe76f60f | note | – – – – – – – – –
33d987ea-6cfb-5afd-bd76-ef220b5ec673 | note | RESPONSIBILITY: Fulton Hogan Engineer, Electrical Subcontractor, Vline representative
b7628620-76d4-51c5-accd-4c0d1e162ae0 | note | – – – – – – – – –
96f68bdd-b580-5bfb-9917-b285de0d338e | textbox | DATE:
afee1c15-6c77-4c09-a140-2ef702a3bcc3 | section | 2 - Construction Works
b1d62567-eea0-4e69-9e28-41814f3c7120 | checkpoint | 2.1 Survey set-out
0f69d187-92fc-5c6d-9ca3-1af354a1e6d8 | note | FREQUENCY: As required
7fc031d9-b64e-5101-8612-474e2a2fe33e | note | – – – – – – – – –
678a3869-772f-5067-abef-2b64bc0f5bef | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
79b23b10-dd4b-51fa-bc92-7b7cf526e555 | note | – – – – – – – – –
7a3b08aa-62b7-5599-9845-5503f2cf870c | note | REFERENCE DOCUMENTS: Work procedure, Drawings
435b98fe-5640-579f-a49d-e155a1c67e9c | note | – – – – – – – – –
52d415df-d693-5cb1-865b-ba0f166fba4e | note | INSPECTION/TEST METHOD: Verify
91d9a3f4-c253-590f-b5dc-b0bd971f338d | note | – – – – – – – – –
95d1d6cf-5ea3-5eb6-863d-a7bff119442b | note | RECORD OF CONFORMITY: This ITP signed
83aae153-dbb6-5fac-b2bb-533e2afda14a | note | – – – – – – – – –
9b5a2ad1-3aae-5e59-ba09-a36334914bb4 | note | HP*
cbd99ac7-2291-5711-9852-94612f90817a | note | – – – – – – – – –
f3911e22-234a-5ed3-a6b6-ce7bd66ce997 | note | RESPONSIBILITY: Fulton Hogan Engineer
e946f1a6-3ec4-5853-bdc0-c0c84ceb67a0 | note | – – – – – – – – –
ca621b85-da37-56fe-8080-755faaabbc66 | textbox | DATE:
95331683-e6a0-4187-876c-675c3ab495ce | checkpoint | 2.2 Excavation/Boring & Trenching
fbe03c17-aade-54fb-9b86-cfa20f20c8fa | note | FREQUENCY: Prior to Backfill
f7cf6d80-62ae-5b59-822b-721cc6c639f7 | note | – – – – – – – – –
653e3f5b-7655-5a31-a61a-9aab45c5769a | note | ACCEPTANCE CRITERIA:
b59bd3df-c988-5760-935f-25fa7d2244e4 | note | • Trenches shall be excavated to a depth required to achieve the specified depth of cover and drainage slope, plus an over-excavation of approximately 50 mm to allow for bedding sand. The width of trenches shall be as required to fit all the conduits and pipes for services sharing the trench with specified separations, plus a further 50 mm minimum clearance from the outermost pipes or conduits.
acd397fe-01e4-5f03-8e65-1907ed853682 | note | • Where trenches are excavated across roadways, car parks or paved areas, the Electrical Contractor shall backfill the trench with 20mm of Class 3 crushed rock. The crushed rock shall be placed in layers not exceeding 150mm finished depth and compacted to a minimum of 95% of standard density. The backfilling shall extend for a minimum of 1.0m outside all paved areas and shall be subject to the supervision of the V/Line delegated representative.
c29a432c-8681-50ef-a8d2-cc37e5fc6ea0 | note | – – – – – – – – –
84b81a87-dfd8-55c8-9c93-a95224c6e524 | note | REFERENCE DOCUMENTS: L1-CHE-STD-077 Sect 6.10.6
4f272379-2e8e-5ea0-a7c0-87386a8609a9 | note | – – – – – – – – –
c1716643-c8a9-507e-abd5-c09f9e9155b9 | note | INSPECTION/TEST METHOD: Verify
af2dda89-fb92-5beb-aad3-4a3cfb502ff2 | note | – – – – – – – – –
91fd4e8e-c6ed-5704-afcd-6b9ec0b9e107 | note | RECORD OF CONFORMITY: This ITP signed
02ab3a63-9288-58fc-becb-0c514218f93f | note | – – – – – – – – –
b86264b1-b4b4-515a-a78c-6833d9ab818b | note | HP
5b083afc-b6bb-5dc7-9fda-830b1b0344c0 | note | – – – – – – – – –
2381d6dd-cebf-5cf2-8ff6-058e80399c27 | note | RESPONSIBILITY: Fulton Hogan Engineer
8934ddc1-82af-5343-af66-ef4a251f0f7f | note | – – – – – – – – –
1bb4d9cf-a89d-5aca-ad77-1fc6f49a94bd | textbox | DATE:
fda9a2d9-49aa-4923-b1f6-e5823714cf76 | signoff | HOLDPOINT AUTHORITY
f0e55187-34fb-47c2-8d9d-c9da4d2bf572 | checkpoint | 2.3 Installation of Pit and Conduits
89c48b13-73e0-5765-a0df-3698907ad57b | note | FREQUENCY: Each Lot
10686b66-4c10-5b56-85e0-58f27d71bd49 | note | – – – – – – – – –
54973f3e-ced4-5638-9024-6883e56da152 | note | ACCEPTANCE CRITERIA:
f7fe521e-d795-5094-b602-542d669676a1 | note | • Underground conduits shall have a minimum 450mm cover if around the site but away from the track corridor, should only be in the non-trafficable areas. If exposed to traffic, the depth should be 650mm.
ad789a7b-678d-5d7a-836c-f642c4ee8bdd | note | • Upon installation conduits shall be cleaned and tested using a mandrel of at least 90% of the conduit inner diameter and length three times the inner diameter.
9dbfcef6-816d-5247-8f35-2e416f30130f | note | • Multiple conduit entry penetration holes on a pit wall shall be spaced at least 50 mm apart in horizontal and vertical planes
d7a051af-f4e9-5e7e-9408-5528224c2f4c | note | – – – – – – – – –
21ec60de-27fd-5794-8941-a92c7c856b70 | note | REFERENCE DOCUMENTS:
c60c4798-e29d-59e6-8ac3-87cceb3b03f0 | note | • NIST-013.3 Sect 4.2
daba8466-75d9-5fc7-8c3b-6c2f205b808e | note | • L1-CHE-STD-077 Sect 6.9
c34de87d-5a43-5f96-b173-c782d411940a | note | – – – – – – – – –
12cdb7ad-eef3-5968-bbf0-40f2b694b3f0 | note | INSPECTION/TEST METHOD: Verify
ff231c90-9c91-5a5d-a453-81874e9b4432 | note | – – – – – – – – –
f3402a97-2fc1-57df-bd2d-6d1500a1ae45 | note | RECORD OF CONFORMITY: This ITP signed WP
82867281-f89f-5ed9-acbc-92dea0a66c38 | note | – – – – – – – – –
b4e473c9-6f2a-51ba-880e-06fb1ae9eaf6 | note | IP
50c11dee-ebf8-53d7-80d8-30f0d48f4c83 | note | – – – – – – – – –
b046e2a8-910f-56a9-90d7-e7ede712b1d6 | note | RESPONSIBILITY: Fulton Hogan Engineer
31d4ba54-4a07-5518-8c6b-2c3837274e48 | note | – – – – – – – – –
7f1c3aa6-aed0-5d39-9758-f55afbccaf1c | textbox | DATE:
e878f5ca-3c66-4837-a8d3-262234868fbd | checkpoint | 2.4 Back Fill of Trenches (Trafficable)
3833cbd8-7c86-5ad6-82f0-a23863d7daaa | note | FREQUENCY: Each Lot
9a8539d4-0235-5dad-b7e3-d2bc2e765756 | note | – – – – – – – – –
54349ba6-b012-5593-a1ad-048f598b5490 | note | ACCEPTANCE CRITERIA:
7814050e-20c7-5faf-a6db-228ed44101fe | note | • Bedding: Graded recyclable glass in accordance with MTM standard L1-CHE-SPE-313
ebb00ead-922c-55ca-a83b-37f65f74aaae | note | • Backfill: VicRoads 20mm class two crushed concrete base compacted to 95% of standard density in 150mm thick layers
dda06376-6de0-5ccd-8a99-663ff014288e | note | – – – – – – – – –
764d04a7-bcf7-55f2-bd26-c727f12f2985 | note | REFERENCE DOCUMENTS:
427d8855-8f36-52ae-890f-70fe5d54d6bc | note | • NIST-5031 L1-CHE-SPE-313
afc9633a-4f03-574c-a106-ea70858c218c | note | • MRP-708-C-AUR-DRG-20-TNT-CLT-0810
d38b3c13-48fb-54fa-a7bf-81fec64811b4 | note | – – – – – – – – –
0d72cf12-326c-5778-9d3e-476ae1e66d6a | note | INSPECTION/TEST METHOD: Verify
271ef366-6509-5214-aa01-2328c29ce572 | note | – – – – – – – – –
db7f02d2-36a6-5a05-9a43-c8ca6fdccc60 | note | RECORD OF CONFORMITY: This ITP signed
634543eb-1bff-50e5-8edc-b788cfaf3d30 | note | – – – – – – – – –
6c109df5-118b-5bb4-a66a-b327cb8dd89e | note | WP/IP
9236f5c1-8717-5ab6-a72e-2dc1c40a282c | note | – – – – – – – – –
f8e1c513-7bbc-5dd3-a239-f27ff6dd3817 | note | RESPONSIBILITY: Fulton Hogan Engineer
1f24dda1-2405-51a2-b84a-6c93ca1304bd | note | – – – – – – – – –
96ef3e01-9963-59bc-9604-693b72ba781b | textbox | DATE:
a9b2bfef-34d8-4d0b-b652-c381e146efb8 | checkpoint | 2.4 Back Fill of Trenches (Non Trafficable)
58d537d9-33c3-554a-9b25-20305b7acebc | note | FREQUENCY: Each Lot
c7b4fe9b-51c3-522b-bdc1-e45a77a47a10 | note | – – – – – – – – –
ee341342-f007-5ce3-8bfc-991d2dab368b | note | ACCEPTANCE CRITERIA:
ef616e5a-f319-5b2f-a3c2-8e7a53d51d9a | note | • Bedding: Graded recyclable glass in accordance with MTM standard L1-CHE-SPE-313 or approved equivalent
5d6462dd-388b-532c-9272-11f27186f5a7 | note | • Back Filling: Site or imported material containing no more than 20% mass of rock fragments with size between 75-150mm with no rock or clay fragments greater than 150mm.
04918d0f-95cd-503b-9469-f01fb55821fb | note | – – – – – – – – –
0d2324e7-17f2-5399-bee3-ec5d3bcd881e | note | REFERENCE DOCUMENTS: MRP-708-C-AUR-DRG-20-TNT-CLT-0810
0cae516c-62be-54b6-a6d4-73e0844945fa | note | – – – – – – – – –
4aa4fbf1-c94c-5a25-a0a6-d5256c7a5b48 | note | INSPECTION/TEST METHOD: Verify
9003856d-90c7-5910-86ac-e91d48042c5e | note | – – – – – – – – –
0c20fb26-69ff-5eda-acd1-a24964f10554 | note | RECORD OF CONFORMITY: This ITP signed
62bd097e-206d-5c29-807a-4d023437012d | note | – – – – – – – – –
ba3014ca-e8ba-5887-9b6f-132b5e0201ae | note | WP/IP
4cb068ba-4ed6-5912-bf9a-f3539944f210 | note | – – – – – – – – –
74fd66bb-b290-5700-adca-a2005dd63507 | note | RESPONSIBILITY: Fulton Hogan Engineer
bc0e3bab-1523-5e01-961a-0933dd0a2372 | note | – – – – – – – – –
2faa26e1-45ac-58af-9855-ce64c34baa1c | textbox | DATE:
afc122ea-16f7-4d3a-afdb-b30e6e2c41fe | checkpoint | 2.5 Installation of Draw Cords
e474eac6-8a0c-55df-93f0-70b398480b3b | note | FREQUENCY: Each Lot
6381d93b-154f-5432-baaa-69917d219d11 | note | – – – – – – – – –
1a671454-e413-5b0d-b422-ce8f1d92d4fc | note | ACCEPTANCE CRITERIA:
b70fc346-35d8-5eee-8ac6-0880a06f94ed | note | • A draw wire of 6mm polypropylene blue/yellow rope shall be placed in each pipe and suitably anchored at each end. Pipe ends shall be sealed using pipe end caps or an approved equivalent to prevent the ingress of dirt or sludge into the pipes.
d3725b2a-dd2f-518f-ace1-dfe8ff8f684f | note | – – – – – – – – –
8e45d0e2-88df-5635-a42a-2189e726b866 | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.12(d)
b5aeb0a2-5c64-5298-820f-782171c87214 | note | – – – – – – – – –
6632aafb-3a4d-534e-8692-d22adcdb6a70 | note | INSPECTION/TEST METHOD: Verify
67170edd-de4e-52de-b45b-28d2a83e6dee | note | – – – – – – – – –
cc06ab34-8754-59e8-a1a6-feadf6e1d0a1 | note | RECORD OF CONFORMITY: This ITP signed
9ea8dddf-55bf-5a23-8e86-8e6f51a46f27 | note | – – – – – – – – –
4443470c-3a74-5db5-aff7-12d108157610 | note | IP
9be7adbb-09ff-5a05-b770-d56c6e7706fd | note | – – – – – – – – –
1e0150cd-2f69-5efe-9b59-ff115f40bec7 | note | RESPONSIBILITY: Fulton Hogan Engineer
ace2e721-584e-56a7-9a58-a73b8c4ea3f9 | note | – – – – – – – – –
fe8f20b8-e602-5c42-a0e5-3ded5b3f9414 | textbox | DATE:
69e43f67-9741-41e3-9f54-0fd9ede2760e | checkpoint | 2.6 Installation of Marker Tape
cbd9b49f-9e17-57f5-a18f-91f755db24f1 | note | FREQUENCY: Each Lot
5c96553d-bd2b-5b58-b0b6-49b3b2015616 | note | – – – – – – – – –
db5827a0-6938-5bb8-b4f2-5831e07d2ae5 | note | ACCEPTANCE CRITERIA: A 150 mm wide orange coloured PVC marker tape with the words "DANGER BURIED CABLES" shall be installed in all trenches at 300 mm below ground level except where cables are permitted in shallow trenches due to rock. In this case the depth of the marker tape shall be at the discretion of the Infrastructure Manager.
d7e5f799-e17b-539f-a7ec-eae387112de1 | note | – – – – – – – – –
2d1ae33a-4989-56b0-8c4d-791b077fd5d5 | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.11.1
573209bf-4e85-546f-90d1-0278f4b53283 | note | – – – – – – – – –
35b6b2e2-f7c4-502c-92af-2496a0a38f39 | note | INSPECTION/TEST METHOD: Verify
21fedc6b-8007-5ea4-9c62-0c1fd30d2420 | note | – – – – – – – – –
46ff7f3c-c9c7-56d2-985d-c35d600422d5 | note | RECORD OF CONFORMITY: This ITP signed
e5bed261-9c05-5c28-8acd-e31dc42b1c4a | note | – – – – – – – – –
3018f4f8-6faa-5697-b89f-33cc485ce82e | note | IP
7ac2ba54-5293-5b8b-ac7f-2742ba22856c | note | – – – – – – – – –
0f269917-eeea-5d67-bc15-f54b151772b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
e47b3e4d-f7db-5570-909a-cf3962098bee | note | – – – – – – – – –
60c68e7f-30d1-5af2-b0f2-66ad3dfed000 | textbox | DATE:
7a4629a7-e941-428d-aba4-6a2396f9455f | checkpoint | 2.7 Cable Pits & Pit Lids
2fd2ee81-333d-5144-ab85-80ebe5fb4ca4 | note | FREQUENCY: Each Lot
b6cd70a9-d3a1-5e5f-826f-478ab0331664 | note | – – – – – – – – –
2963e5dc-ea86-503c-ab6e-656cc8266973 | note | ACCEPTANCE CRITERIA:
a0841beb-0b4b-591e-9601-e3378291b568 | note | • Cable pits constructed and installed as per drawings
bad65950-0063-59db-aa54-730fed659906 | note | • Pits shall be placed at each horizontal change in direction or at spacing no greater than 100m
273130ef-cb89-57ab-92eb-d1fee93596d9 | note | • Seperate pits shall be used for power conduits (orange) and communications (white).
a9404c73-5b96-580c-9d47-57794d5508da | note | – – – – – – – – –
4ddbea38-2247-534b-8484-5cfa1cedfd2d | note | REFERENCE DOCUMENTS: OCS Drawing Package
d493cf0a-0b03-545e-84f7-b61b6e91167c | note | – – – – – – – – –
1509cf77-ff38-5612-b9f2-0047464c95ca | note | INSPECTION/TEST METHOD: Verify
d6b1265d-18ee-5c04-bc0c-5c2dfac1a0b6 | note | – – – – – – – – –
904e7bd0-2374-5b0a-b90b-e44f90ab2c9c | note | RECORD OF CONFORMITY: This ITP signed
c19d396f-ee17-5127-a5fd-e80fe58d2155 | note | – – – – – – – – –
96c0fcf9-aa4d-5dd5-b266-35cc7f326b7a | note | IP
818e6172-e754-53db-876f-34f9c7daa66e | note | – – – – – – – – –
e1a3ef62-6036-5945-92ed-3a7084e1ac3d | note | RESPONSIBILITY: Fulton Hogan Engineer
258d5acf-a12a-51e6-9634-7add2290a16c | note | – – – – – – – – –
f29f9f44-e6a0-5a60-8560-6dbe93bbbffe | textbox | DATE:
2abf7b26-578e-4a57-a453-29c5e5dca941 | section | 3 - Completion
511b1f83-7359-422b-82df-1ca0d08f8740 | checkpoint | 3.1 Cleaning of Site
b0477c2c-23c3-57af-a41b-4db7126389c1 | note | FREQUENCY: Each Lot
0bf73fca-766b-5816-a01a-7fa1ec2857d3 | note | – – – – – – – – –
8f2480fc-1e02-5bca-a8b4-c9cc9c41036b | note | ACCEPTANCE CRITERIA:
e2560a56-512d-510f-a408-4e0502483f1b | note | • All obselete cabling to be removed during installation and disposed of appropriately.
86c46ffa-92cc-5fb0-8384-cd8b9fb8c189 | note | • Upon removal of all redundant signalling equipment; the site shall be cleared of all project scrap and associated rubbish.
2c369140-b820-5c42-83e1-7743d7e98eab | note | – – – – – – – – –
ad44c015-8b0c-5657-a4a8-58d7ed62384a | note | REFERENCE DOCUMENTS: NIST-012.2 Sect 23
ebc04ed3-700f-56a4-951b-891b086f17cd | note | – – – – – – – – –
64411844-2ec2-5245-8443-86af30463a33 | note | INSPECTION/TEST METHOD: Visual inspection
fa2232ff-6913-56b1-9762-ca70d1421142 | note | – – – – – – – – –
7612b00f-8522-53d2-9c47-c2b367fb0683 | note | RECORD OF CONFORMITY: This ITP signed
eb0006b0-a346-5db8-a775-af407dc0c51d | note | – – – – – – – – –
08f2d517-1976-516e-8dd3-7c57e4ec60e7 | note | IP
bef1c0da-b848-552b-a704-ae86f31d77b1 | note | – – – – – – – – –
782a3094-2643-51c9-9110-75fdfe5a8ed5 | note | RESPONSIBILITY: Fulton Hogan Engineer
75ff570c-c329-5a0f-bd18-6134df5281bf | note | – – – – – – – – –
b5359763-419c-540b-90a2-a34b13dca44e | textbox | DATE:
d540ef34-ee8e-475c-862c-8cd8bed9925a | checkpoint | 3.2 Recording/As Built
111378f6-2b42-5f4a-a35c-144c6950ecb9 | note | FREQUENCY: Each Lot
07b8f3e5-e0d4-5c17-ae71-fede2dc1a9c4 | note | – – – – – – – – –
b091e0d6-6d27-554a-815d-34b087059770 | note | ACCEPTANCE CRITERIA: As-built drawings will be completed by the Contractor based upon the installed system by a process of editing the approved 'for construction' drawings.
3babf009-f5c6-5659-9257-4ddbf27673ba | note | – – – – – – – – –
111968bd-10a8-5f9c-8ed4-fa5b1bac00be | note | REFERENCE DOCUMENTS: NIST-013.3 Sect 5.1.3
19cdffb4-9123-5746-9e8b-4b4a08723976 | note | – – – – – – – – –
aa5012ff-7444-57a6-95b0-17d3c277fa4f | note | INSPECTION/TEST METHOD: Verify
910ad4c5-be04-53e1-a42d-286acb92bfe6 | note | – – – – – – – – –
1842e7d7-2681-5981-8be0-4e19fb438d36 | note | RECORD OF CONFORMITY:
d724ca43-3804-5703-82db-56a08b610385 | note | • This ITP signed
42052dce-2a4e-5785-9def-19a48e4e35ec | note | • As Built Drawing
d0ef3af1-a781-5901-a5ea-ddb866d3ef7e | note | – – – – – – – – –
780c9a6b-c726-59a5-8edb-0ed3f2b53540 | note | IP
7e5299d5-b652-543a-9bfc-59bcec09b358 | note | – – – – – – – – –
f312a37d-f0a5-5276-b3ba-75825c0894f4 | note | RESPONSIBILITY: Fulton Hogan Engineer
86d32aaa-db36-560e-ae55-f1e6fa16eef6 | note | – – – – – – – – –
9287768b-35b3-5a3f-a58b-c2eddd04251f | textbox | DATE:
89cd2fd9-6a17-452d-a947-35695fd9ef44 | checkpoint | 3.3 Commisioning
f646ba63-8829-5aa9-aed3-f3ad3e98259b | note | FREQUENCY: Each Lot
ba56df87-bb45-5d3c-9600-c6f546253921 | note | – – – – – – – – –
60ffc0ce-51c6-5d9e-868b-221e6fa5f3de | note | ACCEPTANCE CRITERIA: Commisioning to be checked against V/Line checklist. For OCS Only
72e1ab42-99d7-5bac-a419-98630f364154 | note | – – – – – – – – –
cf7bdd84-c970-59d4-84a9-4db0b1967d52 | note | REFERENCE DOCUMENTS: V/Line Commisioning Checklist
feb46271-4f96-5b0e-be2e-e798a4728889 | note | – – – – – – – – –
9a4e30c0-fc55-5286-8e08-fd24692773da | note | INSPECTION/TEST METHOD: Verify
43d5491a-1b18-5e38-9a48-e31d0f299ef3 | note | – – – – – – – – –
db8116a1-c92c-5b74-af03-cf22a07f9334 | note | RECORD OF CONFORMITY:
1806a330-9f36-5e24-ac4c-e7f9270e2128 | note | • This ITP signed
cd7e651e-3095-5dd6-b983-06f0ea4ca137 | note | • V/Line Checklist signed
84049003-345d-5877-9332-2409489cda46 | note | – – – – – – – – –
b9261aa0-2d69-5c14-9465-3e8d77a7ff9b | note | WP/TP
eafeb93b-d6dd-599c-8ac0-0eb560246cd7 | note | – – – – – – – – –
644811c1-e739-50a7-9dc7-93bed05433f6 | note | RESPONSIBILITY: Fulton Hogan Engineer
6eddc5a6-d1c2-540f-aeeb-b12c3f8199fb | note | – – – – – – – – –
d301e801-9597-5a36-82ed-24dfba95bcb3 | textbox | DATE:
ef21a31f-0ae6-4341-8c03-c5202c88aacb | checkpoint | Final Inspection
e0a62d8a-0f4a-5695-9e77-352851f5cc14 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
cba218ba-9a14-5677-a831-e4c31930dc68 | textbox | Print Name:
bce508e0-88cf-5686-9a58-57cc034b9830 | textbox | Position:
5cefe61b-924e-5fd7-9f90-6221e89cfbe6 | textbox | Date:
fe32ecf0-0e83-48a3-8748-ee130b9481f4 | checklist | ITP-01-024 - Installation of Public Lighting (V-Line) |  | ITP-01-024 - Installation of Public Lighting (Vline)
d290cefa-0333-4722-8693-4121b377363d | section | 1 Preliminary Works
4d001be1-87cd-449e-8d41-a4d093d90e53 | checkpoint | 1.1 Check for correct documentation
7383cd68-40f2-548b-984d-2f425bf21978 | note | FREQUENCY: Prior to commencing any activity
8ad67c3b-2b57-5a9f-97ab-ee3417d43b53 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
d5ee90e0-4a79-52c3-8d1d-2b58e52beb3b | note | – using the correct and complete set of drawings
0092648a-54f3-5f80-8147-4ae5b9a918c8 | note | – all drawings are the latest revision
c1d8f82d-5760-5998-aea5-61df1f244e23 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
469641aa-b24f-5950-af44-8d23261a693b | note | INSPECTION/TEST METHOD: Visual inspection
7be6ea49-eb67-5449-a0e6-e3b121f7eed9 | note | RECORD OF CONFORMITY: This ITP signed off
1dda4d5d-c6e7-5513-b725-fe6d996f4dea | note | WP
68f5f4f2-6e12-5620-9654-2ba0e73a5943 | note | RESPONSIBILITY: Fulton Hogan Engineer
2440810c-9ae3-5ba2-8891-98e551c0ed01 | textbox | DATE:
5f40bb17-b26e-467d-b7ef-72d2b9b260e1 | checkpoint | 1.2 Implementation of all measures and controls
693fe0ec-2709-5374-ad2d-e2a6438140a3 | note | FREQUENCY: Prior to commencing any activity
3ad67c86-a196-58fd-ba96-4ba358befcd2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
5df7816b-940b-5c05-9e2d-dadc8ebb1806 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
ec909b28-98e4-5810-92a3-5793a07b0948 | note | INSPECTION/TEST METHOD: Visual Inspection
cb471658-d05b-5f1c-9194-9498357e8c5c | note | RECORD OF CONFORMITY: This ITP signed off
e6982b5c-e361-5fb9-82c9-1408b8c92317 | note | WP
aa8fdee0-ce81-5d25-ad59-3c290053059b | note | RESPONSIBILITY: Fulton Hogan Engineer
64fafd60-a8f7-5f97-bec8-a2239c5252f4 | textbox | DATE:
61425c5c-575b-4dc5-9c6e-49479cda592c | checkpoint | 1.3 Excavation Permit issued
e1649946-9076-5b5b-93df-60cfc21babf8 | note | FREQUENCY: Prior to Commencing
044a57bd-90f9-5388-8c3b-d0552e8db24d | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
1bec8934-e7ee-5445-818f-e9c1ce3fd0d8 | note | REFERENCE DOCUMENTS: Excavation Permit
fea305e3-cd7e-5dd6-88f0-0ba9068614d9 | note | INSPECTION/TEST METHOD: Document review & Site inspection
02dd5b72-b2e1-52e9-8e16-4861f8cc9b86 | note | RECORD OF CONFORMITY: Excavation Permit #
4cff811a-e256-573b-ada6-6dc0f0d781c7 | note | HP*
ed3cd4ef-f1b2-5a77-8d80-8065bbdea778 | note | RESPONSIBILITY: Fulton Hogan Engineer
ca8700bd-6822-5142-b7ee-fac1c74aec3b | textbox | DATE:
59a74062-cac9-41ea-ab7b-332aa9223857 | checkpoint | 1.4 Services located and proven
b841928f-8220-5fb2-b36b-6a757cfdb143 | note | FREQUENCY: Prior to Commencing
ed11feab-9761-5683-9626-c09e8e3c6588 | note | ACCEPTANCE CRITERIA: All services have been located with a service locator and proven through NDD, signing the excavation permit as required.
d467fd7b-2cf5-5bab-b97b-135fc13d6006 | note | REFERENCE DOCUMENTS: Excavation Permit
042c08f7-d4b9-5719-87f5-697df31f6d3b | note | INSPECTION/TEST METHOD: Document review & Site inspection
8e982a0a-d435-5f5c-8c13-91a1e6cbb715 | note | RECORD OF CONFORMITY: Excavation Permit #, ITP Signed
db8f3ce8-9596-52c2-99e1-428b90a2868e | note | IP
ef7d6f9c-d141-5437-9ad8-ee6dd9e4168d | note | RESPONSIBILITY: Fulton Hogan Engineer
ff8456b3-09b6-5a56-9f85-80aca647f804 | textbox | DATE:
7a6a6d89-a97c-4b79-bfc1-eb9bb72515df | section | 2 Installation of Conduits
3fd01aa9-3297-444b-accd-87484e5b499a | checkpoint | 2.1 Conduit and Pit installation and backfilling
efbefe00-46e3-569b-9611-de2d8db660e7 | note | FREQUENCY: Each Lot
6e1519d8-c371-5dd8-b787-ee0995d3f626 | note | ACCEPTANCE CRITERIA: Conduit installation will be completed under:
16c53cd4-be53-5215-a5e0-4e083601304a | note | – ITP-01-023-Installation of conduit system
f7056f94-edc8-5233-953d-ef1c456a0022 | note | REFERENCE DOCUMENTS: ITP-01-023
abe16971-e540-5856-b3b3-277d8de8e94d | note | INSPECTION/TEST METHOD: Visual Inspection
1e98fa43-a5cd-5df5-ad3e-a2945f04a16e | note | RECORD OF CONFORMITY: This ITP Signed
40dff927-efea-5198-b5fe-106065d4021a | note | IP
a6f58ae7-2315-50d7-b50c-f326e126f9b3 | note | RESPONSIBILITY: Fulton Hogan Engineer
c06b7feb-d64c-50ce-8171-bc6bc482c92d | textbox | DATE:
c926a63c-3396-4b1c-a170-6e031a01264b | section | 3 Installation of Light Poles
d560281f-56ce-4e7d-9abf-55606545d7b2 | checkpoint | 3.1 Excavation Levels
eb372a3f-eccf-58ce-b21f-c6807e36f7ab | note | FREQUENCY: Each lot
4446b670-a82a-57c9-b627-09b616c1dfeb | note | ACCEPTANCE CRITERIA:
2190c970-50a6-5acf-8022-edf5b3c5b7e8 | note | – Care must be taken during excavations to prevent soil blocking drains or causing an obstruction on roads or paths. Roads and paths shall be made good to the satisfaction of the V/Line delegated representative.
0bd7a7bc-479a-56f4-ba15-8189a1d3455d | note | – Unless noted otherwise pole foundation to be bored pile provided in accordance with the pole manufacturers instructions.
17676fe4-a730-567f-91d8-afb5bd2b81f8 | note | REFERENCE DOCUMENTS: NIST-5031
3d9c71c1-f92e-50ed-8c4b-ce03399f2ec3 | note | INSPECTION/TEST METHOD: Visual Inspection
967d1643-f0a7-51e1-b618-a3f4ebe911b8 | note | RECORD OF CONFORMITY: This ITP Signed
e1a2d337-f2c9-52ad-9fe2-37199cc76d1c | note | IP
a6b5c0c3-1670-5f7a-b1cb-1f8e8f732380 | note | RESPONSIBILITY: Fulton Hogan Engineer
6ca43c27-bc56-5029-a475-ecc7e98ee72c | textbox | DATE:
f3a246f9-ed6b-4c39-9ecb-cf29fa1cd373 | checkpoint | 3.2 Installation of lighting pole bases
fd488d6c-bf3e-5087-a840-9080927a1141 | note | FREQUENCY: Each lot
6e9c6a35-784a-59bc-aa58-827a0139583e | note | ACCEPTANCE CRITERIA:
2a0423d5-9053-5caa-bb8c-50d91f55061b | note | – Underground installations require a pit to be installed adjacent to each lighting pole with 1 x 100mm HD conduit and 1 x 63mm conduit installed between pit and the point of supply. 2 x 32mm HD conduits are to be installed between the pit and the pole mounting base. The installation of pits is not required if junction boxes are used beneath an accessible platform surface.
84cdf32e-be6c-5dcc-ba8a-4534e07dc508 | note | – Should the supply cable not include an earth conductor or a separate earth cable is not run, then an earth copper stake is to be installed at the base of the pole and this earth stake shall be bonded to both pole steel reinforcement and supply neutral.
5b957642-faba-51b6-b064-d0ccf2e9956e | note | – All lighting poles to have a 6A Terasaki or approved equivalent (MCB) (C) installed at the base of the pole to enable seperate isolations.
bd99a767-5089-5daa-a7c0-80792df01c5e | note | REFERENCE DOCUMENTS: NIST-5031
677437e6-8872-5847-8138-f2578fa2a996 | note | 3.2.2.5 (f)
52f2e0b4-bacf-5671-bd5f-7793ffac2cee | note | 3.2.2.5 (i)
77be587f-508c-52b9-8222-1586e067fe91 | note | Drawing Plans
fae00db0-6cb7-5012-9426-202cfe661bd9 | note | INSPECTION/TEST METHOD: Visual Inspection
d7f83ca6-bd9a-5678-b88c-ddd350ef35a2 | note | RECORD OF CONFORMITY: Inspection
156bf314-f68a-5c36-9b96-e7366f744445 | note | IP
a2079347-48bc-5ce1-8b6c-ae784f143f2e | note | RESPONSIBILITY: Fulton Hogan Engineer
02c3a418-323c-569a-a0be-d4a698239bf1 | textbox | DATE:
a9d84bba-1fac-442c-bbe3-4724fa03219f | checkpoint | 3.3 Installation of frangible poles (Slip base and Impact Absorbing)
ad621cac-3593-5044-85f5-04b921016851 | note | FREQUENCY: Each Lot
b9b98349-5086-5b56-9fb1-515999079ea5 | note | ACCEPTANCE CRITERIA: The final design of the location and spacing of the light poles is to be confirmed with the V/Line Asset Management Department or delegated representative.
94a10b21-a259-5b88-b3a2-14461d856a53 | note | REFERENCE DOCUMENTS: NIST-5031
eb1be57b-4af5-5493-b22e-3ff8f86f06ac | note | 3.2.2.5 (V)
a52e4d34-8e46-56fa-9810-37e6bc248008 | note | INSPECTION/TEST METHOD: Visual Inspection
9ff0431c-5658-547f-a913-38987355a9c5 | note | RECORD OF CONFORMITY: Visual Inspection/Test Certificates, This ITP signed
dc7b5d20-3621-56cc-8536-34acf1f92be9 | note | IP
18d6c23b-b750-59f8-adae-f55915a62dd2 | note | RESPONSIBILITY: Fulton Hogan Engineer
47ce9250-6624-59ed-8b1a-6df5bd5fd24e | textbox | DATE:
bc1e934e-a3cd-4555-9807-2b7dc96d7b2f | checkpoint | 3.4 Installation of outreaches and luminaires
3af504f4-0690-5e7b-a8fe-364deabee220 | note | FREQUENCY: Each lot
dcee4995-233a-5487-91b9-538f8f2e8c8a | note | ACCEPTANCE CRITERIA:
9ddfc41a-b5af-5275-945a-c6441ec5b38b | note | – Only LED lighting shall be installed and the fitting constructed in such a way that insects and dust cannot enter the light fitting.
dd90b5eb-9b60-58bd-ad70-319cc2ba42e7 | note | – Every luminaire installed shall be equipped with the appropriate lamp of the rating specified or where not specified, in accordance with the highest nominal maximum rating of the luminaire.
fa59f0d6-2532-5566-a984-34a19df14512 | note | – All luminaires being maintained shall be cleaned and re-lamped, checked for operation and provide with new starters where applicable.
f784249c-4b21-5ac0-9958-2e5e69bbf401 | note | – Lamps, luminaires, and poles shall be of a type specified on drawings.
35194a7d-be3d-5261-9c83-afed5986b353 | note | REFERENCE DOCUMENTS: NIST-5031
1ff6869b-b389-5dcc-80b7-8c9e8a4015cb | note | 3.2.2.5 (VIII)
7211f3bc-e1cd-5b9f-ae69-fa2ee22ce5cc | note | 3.2.8
a7c778b7-43c0-5113-a670-b11d1e143f6c | note | INSPECTION/TEST METHOD: Visual Inspection
bab32e8e-41bc-5ca4-8f8b-e427b649dce3 | note | RECORD OF CONFORMITY: Visual Inspection
25212218-7248-52b9-9b89-62ca72eb8ddd | note | IP
5da6cce3-e1ec-55e9-819a-811fee7c1e98 | note | RESPONSIBILITY: Fulton Hogan Engineer
feb08302-c25a-50cf-b6e3-87b2fb3aed2a | textbox | DATE:
a0ef8655-0626-4ce9-a18e-4344a08d0f14 | checkpoint | 3.6 Installation of lighting distribution cabinet
6dea531d-6a0c-5d01-bede-340bc273965e | note | FREQUENCY: Each lot
2872de09-6f5c-5f1f-b390-5cb7c85ebcb2 | note | ACCEPTANCE CRITERIA:
14690042-a184-5e91-993c-c4a07384254b | note | – The number and size of distribution boards shall be based on the requirements to localise faults, reduce wiring runs, and minimise overall cost of installation and maintenance. The installation shall allow for spare capacity of not less than 30%, shall be accessible for future upgrading and maintenance and be constructed in a manner to minimise vandalism.
7b05d9cc-fbac-53d1-8b1a-70d00a90dc6f | note | – The design shall indicate the method of installation to be used. Under track crossings shall comply with the Railways of Australia (ROA) Code, or Victorian Rail Track Corporation (VRTC) regulations.
4e59ec4b-3dbf-5724-8978-bc6df5f0d654 | note | REFERENCE DOCUMENTS: NIST-5031
e2578d60-0e29-5fab-9918-36001ebabdf4 | note | 3.2.2.3
93d8633e-b7b7-561d-8a7c-921dca4719a1 | note | INSPECTION/TEST METHOD: Visual Inspection
7f949464-5eaf-5373-a97e-24ca9895f8a1 | note | RECORD OF CONFORMITY: Visual Inspection
472717a4-fb58-5460-a0fa-4c3866022302 | note | IP
7d10b171-8406-5e96-865b-6859f3291c11 | note | RESPONSIBILITY: Fulton Hogan Engineer
eeec35f5-1441-50c5-980e-794e262888cc | textbox | DATE:
4f52c291-be4b-4c45-815c-43fb69df7f92 | checkpoint | 3.7 Installation of cabling
afeb891b-0bee-5904-a40b-54bf33d32a01 | note | FREQUENCY: Each lot
3ce61e16-7ec0-54f5-a986-4db59c3337a1 | note | ACCEPTANCE CRITERIA:
6cef496d-7806-57e4-8157-6fa95738855e | note | – All electrical cabling to be in accordance with the requirements of AS/NZS 3000: (Australian/New Zealand Wiring Rules)
2d628876-03f6-510a-920d-72f8ad1ced67 | note | – Each pole to be cables from the pole circuit breaker
96547aa1-1d7b-52b3-8569-545e4a4961d9 | note | – All cables shall be terminated in an appropriate termination panel within the base of the pole.
9d83f06f-8092-5abb-a3d3-c53604021521 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
60299a74-a6e1-5283-a12b-7b180f813b84 | note | INSPECTION/TEST METHOD: Visual Inspection
f81b85ce-1480-55b8-be9c-d113b8459b15 | note | RECORD OF CONFORMITY: Test Certification, This ITP signed
106df34f-f01a-5437-8e74-2d333a2cf06d | note | IP
4d128f70-f088-5be1-a4fe-8b61c8c5e389 | note | RESPONSIBILITY: Fulton Hogan Engineer
75089b2e-03f5-5b2a-853f-3b9d9fb0cfdc | textbox | DATE:
59ba1ca1-47dc-4d9c-861b-b70fe7917086 | checkpoint | 3.8 Labelling of Assets
a763b33e-1705-54fa-a9ed-344a63e822f2 | note | FREQUENCY: Each lot
2b7e48bd-980f-5482-93e3-bfc7f06a9fbd | note | ACCEPTANCE CRITERIA: All distribution boards shall be identified by a systematic number. Each switchboard is to have a label attached to indicate its point of supply and the supply circuit.
854376d5-ee34-5732-876f-04cc4aaea53e | note | REFERENCE DOCUMENTS: NIST-5031
c73903a6-fc7a-5584-aa6a-2e46338aaa67 | note | 3.2.3.1
74634713-b8c7-59fb-9eb0-33bd3094585f | note | INSPECTION/TEST METHOD: Visual Inspection
9762c441-aadf-58a9-aa17-7b31fa6f02fc | note | RECORD OF CONFORMITY: This ITP Signed
13e8ac6f-2494-5f4b-a919-11019c94b487 | note | IP
a99c056b-d0a8-51cd-bfc1-36251c7059ff | note | RESPONSIBILITY: Fulton Hogan Engineer
75bfe211-dc24-5552-b8b9-cd8e9576500f | textbox | DATE:
3c393b42-885b-44be-bf79-dffe0dddaadf | checkpoint | Final Inspection
fd80822f-92be-5ea6-a1c1-32dd3e61b254 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
39a6a5d0-7082-552c-aa69-01f3b62c365c | textbox | Print Name:
94001ddd-12cb-59df-af47-1f145b122d14 | textbox | Position:
574f81e9-555b-542e-aa68-9a15fe686dc3 | textbox | Date:
2b0b11bc-0d8a-4fe5-b469-928e9c39848a | checklist | ITP-01-025 - Structural Concrete Construction REV2 | itp | ITP-01-025 - Structural Concrete Construction
4394b133-4ae3-49e9-a162-d92789a74ab7 | section | 1 - Design and Submissions
3177c347-43f6-47d5-9b36-0e6493746e1d | checkpoint | 1.1 Check for correct documentation
277b3a51-ed97-5487-8d67-eadcfa801a1b | note | FREQUENCY: Prior to commencing any activity
5cc76384-f1a9-54ad-8a89-4fcf9983f64f | note | – – – – – – – – –
181a4bdd-ce60-5df8-a836-41c86a4a3248 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
35fe9899-9462-5955-a7bc-078a69f94787 | note | – using the correct and complete set of drawings
d7256551-eb02-5098-af92-847cb399f857 | note | – all drawings are the latest revision
da215291-ddcd-5019-afc4-9b8ca0359342 | note | – – – – – – – – –
4a7a9af3-56e7-5fe6-8678-fd45d3ec17b2 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
72a7f026-8a92-5216-bccc-e71179fe3a79 | note | – – – – – – – – –
ce18584a-43aa-5ad0-abe3-eec88003a17c | note | INSPECTION/TEST METHOD: Visual inspection
fbb594d3-458a-540a-ba15-1288b56e9cbf | note | – – – – – – – – –
9d079232-8c09-517a-a205-e6037b3c5b04 | note | RECORD OF CONFORMITY: This ITP signed
d88d328e-3d65-50ea-bca7-822e22cae98b | note | – – – – – – – – –
2e9bc8e7-b228-5e39-9761-c23ad5bd4156 | note | HP*
57d5ee99-2d4a-514c-b4e3-3fdd3aed96c9 | note | – – – – – – – – –
d075b85e-50a6-5ef3-bd87-06f0da277bdb | note | RESPONSIBILITY: Fulton Hogan Engineer
ad162fb3-26cd-5f42-bb93-8101f2fea752 | note | – – – – – – – – –
f3aa82b3-ee07-5dd1-bfc7-3a2093351eaf | textbox | DATE:
58445a49-d1b0-4eed-9410-9e0718c9f8b7 | checkpoint | 1.2 Implementation of all measures and controls
08a0ce40-a59e-52bd-81f3-c3cbeb18ae20 | note | FREQUENCY: Prior to commencing any activity
271a8712-0590-5625-819e-15dfe5544de8 | note | – – – – – – – – –
a26c17e5-fef0-58ce-ac06-55bed1b8b4f4 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
3838466a-e737-5b56-9882-b48d3b8ba34e | note | • PSP, EMP, TMP, SWMS & WP
7a4ae881-84c6-5e9f-9a79-9e3fb128e3a7 | note | – – – – – – – – –
49e5808d-a796-564c-870a-8fc61389f199 | note | REFERENCE DOCUMENTS:
9c35f8e9-e360-53c9-83d3-c6a12d6d6059 | note | • PSP
042d2013-55a3-5dbb-bec0-1c430a2f3b34 | note | • EMP
a8fb0c58-74b1-5770-92c8-8f2202eec7af | note | • TMP
b55d626d-f3b0-5ec5-a67d-4f19afd9ad50 | note | • JSEA
cce9b297-cf6a-5352-90b2-1899c62b99ce | note | • SWMS
3e7f595e-998b-5d71-99a6-4f03e8c340be | note | • WP
da514f59-214d-5b4a-9dd9-9d7ade20ae44 | note | – – – – – – – – –
33cdf844-5554-5c5c-8bb9-17a8a5f32f71 | note | INSPECTION/TEST METHOD: Visual Inspection
facfbc3d-5e5b-5411-9c8e-7c8ff8b1ae71 | note | – – – – – – – – –
dc69a3b7-ba88-5ae1-b63b-1a07481ce7eb | note | RECORD OF CONFORMITY: This ITP signed
a3c205c0-bb3c-57f0-a2dc-cc71254f58da | note | – – – – – – – – –
8f6df0da-765e-5c7f-a18c-f5ad717054c4 | note | HP*
9b50fb59-aff7-5b7e-a8c5-1b1de4d90301 | note | – – – – – – – – –
19640b6b-1a05-51d3-920f-bb550c5a4785 | note | RESPONSIBILITY: Fulton Hogan Engineer
c4c5b67a-4f4e-5716-b7ee-f6d0cb8d6019 | note | – – – – – – – – –
86e8519b-4899-5f09-a592-2c805c79b249 | textbox | DATE:
97240fe5-1681-41e5-ac5d-20b5083fbf48 | checkpoint | 1.3 Approval of Mix Design
4611b908-d8e3-5117-9b7b-4d8f0470b58d | note | FREQUENCY: Prior to the first concrete pour
098d1e16-2173-5c10-8c19-8052a118eec2 | note | – – – – – – – – –
def7510c-3af8-5ccc-8535-b466dcedbab8 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
903c429c-d385-5cc0-9f5a-b59b17d0e994 | note | – – – – – – – – –
a8ef91a9-b935-5ae0-86b4-d2b48e161fa7 | note | REFERENCE DOCUMENTS: 610.07
0d4ab02f-42c5-5da1-ba25-f3509547e84b | note | – – – – – – – – –
97254fe6-f051-58be-ac6b-e545a1186b26 | note | INSPECTION/TEST METHOD: Verify
60ebe797-a3d7-52e0-8f78-68cd49204332 | note | – – – – – – – – –
13601501-3ef9-5653-bd31-e32a8487fac7 | note | RECORD OF CONFORMITY: This ITP signed
00f89031-4cda-5478-9fb4-6eafe7c97fec | note | – – – – – – – – –
92ab54a4-adaa-5756-b232-daae8d39a609 | note | IP
02d39f35-f47a-550c-94b2-2eaa97826a96 | note | – – – – – – – – –
b93c304f-fd2e-5be8-8050-f3dcbc9601e9 | note | RESPONSIBILITY: Fulton Hogan Engineer
491dc2b3-a79e-5391-89d6-45a5417a222d | note | – – – – – – – – –
10363769-3960-5eb9-864b-ca1f5f52948a | textbox | DATE:
ddda9ceb-74ff-49e5-9be6-72a3feffbd3e | checkpoint | 1.4 Reinforcement schedule
85d36af9-b3cc-5b09-80f7-122d882d5080 | note | FREQUENCY: Prior to concrete pour
66bdfad8-6578-5c6f-a1c8-090a3bbdc60f | note | – – – – – – – – –
e677d49c-41f0-5b1d-9fa8-de785cc395fb | note | ACCEPTANCE CRITERIA:
c27ab402-d1e0-55cc-97e8-8cb7fd2cc4e1 | note | • Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
ed239ee4-cb4d-5b7b-8c14-5bd336ccf25b | note | – – – – – – – – –
eb4c8c72-aaf8-50f5-842d-638d75e79527 | note | REFERENCE DOCUMENTS: 611.04
b20e251c-b420-500a-a82c-bc2d34a761a5 | note | – – – – – – – – –
a260b245-6cb2-5445-ac9e-df783037541f | note | INSPECTION/TEST METHOD: Verify
2bffadf9-1e82-5e91-a5cb-dc8ebf60963c | note | – – – – – – – – –
c65bddd2-622d-56cd-9f1e-dfb5617956b5 | note | RECORD OF CONFORMITY: This ITP signed
76a37afe-767b-5d70-9338-421d03d811e9 | note | – – – – – – – – –
8655a3ec-d587-5261-85da-5fd423a06ea2 | note | IP
0a59bbf6-e711-55cd-a9de-52024b479deb | note | – – – – – – – – –
23965a64-e07d-5047-bfd7-3af1c6c4e22a | note | RESPONSIBILITY: Fulton Hogan Engineer
7d929054-c71e-5cad-8b60-39102ebbec1b | note | – – – – – – – – –
9117e6f4-9f5a-506b-9388-ef8b9c10d75f | textbox | DATE:
ac700d91-4d55-489f-ba15-a86e396d677d | section | 2 - Construction/Erection of Formwork
851d11f8-e7e9-446a-8a9b-e85acc93b879 | checkpoint | 2.1 Excavation
af6854d7-4d53-549a-96b4-06e71e52503e | note | FREQUENCY: Prior to concrete pour
d8504415-a0d4-5b6c-b4a6-58867be7ffe4 | note | – – – – – – – – –
5fc03ab3-371d-5927-8370-fa1cd5ac0fba | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
a368b328-3902-5773-a19a-89fc49374bb9 | note | – – – – – – – – –
45c6a471-24e1-5a15-9fdb-d4386521fc2e | note | REFERENCE DOCUMENTS: Contract Drawings
95c9ca20-6a06-5629-8603-97b3a2e9536d | note | – – – – – – – – –
c6bed090-10ca-5f10-85fe-d5e81a5f5c03 | note | INSPECTION/TEST METHOD: Inspect
7d3ad8cf-bd77-552b-9b5a-4ce1e4c53bdc | note | – – – – – – – – –
0c69e862-c7e3-541d-8726-daad3beaa731 | note | RECORD OF CONFORMITY: This ITP signed
f3cb96e8-3548-563c-b84d-48c9f2d933a4 | note | – – – – – – – – –
a8769b1f-fe56-5c5e-990f-9e50ed761a08 | note | IP
b651459c-b585-58ff-b968-c031664f8fe9 | note | – – – – – – – – –
fa0f07f3-a40d-5949-a221-3942af5f7565 | note | RESPONSIBILITY: Fulton Hogan Engineer
b5f7d54f-b1fa-5b01-bcfd-84702848e049 | textbox | DATE:
0325cb73-8392-4683-ba65-7f1a28d1d42a | checkpoint | 2.2 Excavation (Pile)
3eca7927-9e4f-52f0-8f89-1e06c5f72a33 | note | FREQUENCY: Prior to concrete pour
aab19ecc-507b-518f-a701-5fb7878da6fd | note | – – – – – – – – –
5e65686f-37b2-58f8-ba78-69dc6209f212 | note | ACCEPTANCE CRITERIA:
6338761b-7587-520f-9d1c-618a5552f451 | note | • The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent.
b7d26c4f-2463-52e8-8bb7-e468d9e178d1 | note | • Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
89845f34-6d20-5ee5-8bcf-09962315375e | note | – – – – – – – – –
afc3c2b8-1fef-5560-8f6a-fb2599f359e3 | note | REFERENCE DOCUMENTS: 606.05
66ad7dc9-0b33-552f-b498-077527d04dd7 | note | – – – – – – – – –
5abc8051-87fd-5cfc-b8db-cc3a33ce9869 | note | INSPECTION/TEST METHOD: Inspect
952e28a6-00ff-5ff0-9403-79113424b826 | note | – – – – – – – – –
716a0ffc-98a4-504b-a281-cd2ce3b16517 | note | RECORD OF CONFORMITY: This ITP signed
4f46fb62-3f31-5b9f-b3d1-9ca73eb41ff2 | note | – – – – – – – – –
d5cac7cc-97e8-5c9a-884f-0c50df518cd6 | note | HP
fa74c519-16f8-5ffe-b8c5-23b5487f1f67 | note | – – – – – – – – –
aebd3d77-fe47-5c06-9916-e9de16349b1e | note | RESPONSIBILITY: Fulton Hogan Engineer/Suprintendant
529fa9ec-59be-5304-b46a-daa628333e2c | textbox | DATE:
e2ba30cf-85f9-4b52-a047-d5435534c361 | signoff | HOLD POINT AUTHORITY
c7231c34-e187-46ae-8218-9a9b6a734dc6 | checkpoint | 2.3 Construction Methodology
7cee0c92-27c3-502f-a3c5-426c94504ed6 | note | FREQUENCY: Prior to erection
fcc8bda0-89c1-5820-9767-79e723de0e63 | note | – – – – – – – – –
05a7399f-7020-5d48-930b-424f565cc9b8 | note | ACCEPTANCE CRITERIA:
f585dc92-6794-5b94-9133-92e837a21551 | note | • Designed and constructed in such a manner so it can be removed without damage to the concrete.
12321993-994d-5f2b-9823-6868f4bfc441 | note | • Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
268a1639-4fa9-5e4d-8420-e615c48e893f | note | – – – – – – – – –
e2cb4e6c-b6d4-540a-9e9f-bd296eb4ba53 | note | REFERENCE DOCUMENTS:
409c5409-3e0a-52cc-9c8a-3ffe74458b19 | note | • 614.04
3ac9e388-7e77-535d-bec4-408cd71705f8 | note | • 614.06
1401578a-f626-5064-8419-8564ba4ecdcf | note | – – – – – – – – –
73269fc0-b2bc-5600-b81e-daea78b72df2 | note | INSPECTION/TEST METHOD: Verify
efd59c9e-67df-5763-a137-4833b37406a8 | note | – – – – – – – – –
ad00e873-337e-51d0-802b-1c92178ed218 | note | RECORD OF CONFORMITY: This ITP signed
e81f5728-b2a3-542e-b752-fe9f4151ddbc | note | – – – – – – – – –
40edab6f-a253-5cf5-adcc-384f6765a4d0 | note | IP
0429d700-f6d2-5096-abcb-eb962c9dc4ad | note | – – – – – – – – –
1f57bc61-1f82-507a-8933-d55274eb2318 | note | RESPONSIBILITY: Fulton Hogan Engineer
470208a2-62dc-5e78-aa89-c7770ab517cb | textbox | DATE:
3c264438-4b8f-4009-b81f-abe652eba97e | checkpoint | 2.4 Construction Methodology (Pile)
0bb746b3-5d06-5deb-9c77-ad77444d74cb | note | FREQUENCY: Prior to construction
c84595f6-77da-5e37-a736-f6e3ed7f8fbc | note | – – – – – – – – –
bf0c6bce-1c41-59be-add6-fcac51c6fd08 | note | ACCEPTANCE CRITERIA:
921d8319-d88d-57b2-bc32-a5367b4a24d1 | note | • Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
2b36cd5e-595f-5655-b23c-fdfa29bf4eb3 | note | • Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
f1c6e811-fa90-510c-b681-f865b7a1c940 | note | – – – – – – – – –
2312f218-1672-5228-bb62-c2285ea76bf3 | note | REFERENCE DOCUMENTS:
b1fca3d0-58a6-508f-9736-6da9a522eafc | note | • 611.10
d9b41c34-bf36-58eb-aec2-fa18f96ca136 | note | • 606.06
9ba3b54c-852f-5efe-af95-b71784e26048 | note | – – – – – – – – –
d416297e-1e1e-5134-8453-791e956d36fd | note | INSPECTION/TEST METHOD: Verify
4291581f-dfd2-56c7-8456-da43ca86b29f | note | – – – – – – – – –
164382d7-48a8-5704-836d-645f7cc994b7 | note | RECORD OF CONFORMITY: This ITP signed
29995b70-a1db-530b-8f79-d3c6c2c9c580 | note | – – – – – – – – –
229c5f2b-a128-5af9-9abe-502c1ec1871c | note | IP
226d240d-8344-5545-974e-b127cfb27c07 | note | – – – – – – – – –
253fe4b5-1c26-5148-be21-40efd22067c5 | note | RESPONSIBILITY: Fulton Hogan Engineer
d3439226-6d85-57db-9df3-d78699737585 | textbox | DATE:
faf8cccb-8b88-47cc-a628-a5e23a2566f1 | section | 3 - Pre-pour Planning and Inspection
3506daf6-02bc-4602-acb6-c7cdbc057a23 | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
de20ce4b-aa09-5372-bacc-c6678d92d8c9 | note | FREQUENCY: Prior to concrete pour
fe0ae100-c291-52ba-ad25-b1bdb445e1ea | note | – – – – – – – – –
a92b0a9c-5e56-5b14-a9f4-211214b19c1a | note | ACCEPTANCE CRITERIA:
3e9841db-17f0-5bfc-847c-211153c08cdd | note | • Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent.
60861a3b-0c26-5694-8815-2d4a8a827857 | note | • Hold Point released by the Superintendent.
a6437495-f364-5eed-82a0-61519990b1ee | note | – – – – – – – – –
2bda06ea-b119-5401-afe7-2d3ce3dc17a3 | note | REFERENCE DOCUMENTS: 602.03
cc90d63c-5c63-5909-98a1-f58345c2f77c | note | – – – – – – – – –
3461b7b8-3405-5266-beb1-518024366ab3 | note | INSPECTION/TEST METHOD: Verify
583c58bd-1175-558f-9a2c-646669c8d1d3 | note | – – – – – – – – –
076896d7-26ce-5d47-bf77-d9803edc9213 | note | RECORD OF CONFORMITY: This ITP signed
0a18a026-5d4c-5adb-b6ba-a9428e424a9c | note | – – – – – – – – –
272665b5-b75f-540a-81b4-c959a1de1de1 | note | HP
af701708-a4d4-5b88-9135-ea92d5d0193c | note | – – – – – – – – –
29eb8121-eac6-5aae-a89c-a1d05217f350 | note | RESPONSIBILITY: Fulton Hogan/VicRoads
e9b4ed66-0db7-5e10-b0c8-280ed9ed2a65 | note | – – – – – – – – –
0d4de7d9-0f5f-5a96-a40b-df3ca97a1f44 | textbox | DATE:
ff4e92fa-e4be-4807-a2b1-8812694b1e36 | signoff | HOLD POINT AUTHORITY
383468df-f590-497d-88d1-f2c26e57350d | checkpoint | 3.2 Formwork levels and position
f72a52f8-09c3-5070-9ee6-6e8c431efa21 | note | FREQUENCY: Prior to concrete pour
478af03c-e53f-55cd-ac27-7fb4024ebe9c | note | – – – – – – – – –
0280edb3-460d-577e-a785-a5811679585d | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
8a085de6-b5a3-5e11-9cce-f983a87bbd0e | note | – – – – – – – – –
0b54bfe3-8966-53ad-b913-ccad1c81f1c3 | note | REFERENCE DOCUMENTS: 614.06
660fc6fe-3aa7-531e-9843-cabe5005c7f8 | note | – – – – – – – – –
5b2c5d04-c838-57e3-9469-997aade73884 | note | INSPECTION/TEST METHOD: Verify
3e102777-7d17-5376-8069-6e1f426f1eea | note | – – – – – – – – –
360fade9-2f4d-5358-af08-20931b032dfd | note | RECORD OF CONFORMITY: This ITP signed
ec382739-36c5-573d-859c-a887cb05a3c6 | note | – – – – – – – – –
f368ea75-7339-5746-a0a2-515c2f1bd9e0 | note | SCP
9a04da9c-99a7-5798-b9ca-2c283b32790d | note | HP*
592ad4d9-558e-5c66-8e9c-63bb304aebbc | note | – – – – – – – – –
1bab4346-a0d3-50f6-ad64-00eface58d3e | note | RESPONSIBILITY: Fulton Hogan Engineer
14d2a7c6-fee6-5265-981f-a48bd16c7ba1 | note | – – – – – – – – –
58c05ca7-5cab-524d-9621-b4db4a3a2b63 | textbox | DATE:
9d77e2fc-b5ea-4494-ab97-3daeb982fc65 | checkpoint | 3.3 Location of splices
c74fd92e-7bb3-5a35-b383-018b62089fad | note | FREQUENCY: Schedule Review
f7d6dfe7-9ad3-59fa-9486-f6a15038bf0f | note | – – – – – – – – –
b23ee7d5-6436-5b20-a2eb-ff6523d7743c | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
e1bee178-9dc4-5417-8b45-a655f6f2d9bb | note | – – – – – – – – –
ea20cb5c-2ec3-5103-a6a5-5fa1f3c9f168 | note | REFERENCE DOCUMENTS: 611.11
73bc04a7-74cc-56f9-ad52-ed2dded0d2be | note | – – – – – – – – –
e218930a-9186-50c8-a778-f192832a070a | note | INSPECTION/TEST METHOD: Inspect
3213163b-4228-5b54-89bd-4267c4af5edc | note | – – – – – – – – –
0726754c-3ac4-5c3c-80cf-10c6c808c22d | note | RECORD OF CONFORMITY: This ITP signed
9a645be3-1b6f-5a11-8ab0-5e7ebf35a339 | note | – – – – – – – – –
0535c3cb-0174-5802-83e9-f3780051ceb7 | note | IP
4f496896-e633-58e3-837a-3ece3d95efa9 | note | – – – – – – – – –
bb207e5c-34ab-5129-bc90-dac0256d9cad | note | RESPONSIBILITY: Fulton Hogan
62b505ee-876e-57be-962f-d3dc41590178 | note | – – – – – – – – –
ecdc00b1-b9ae-5d18-a990-745db7e1a2bf | textbox | DATE:
631159dd-5af7-4aa2-854f-38fbc1fd6e47 | checkpoint | 3.4 Cleaning formwork
eff58bfe-844c-5c65-9b5e-5260cec81de1 | note | FREQUENCY: Each concrete pour
74a04b42-c2d5-5a71-97a1-4bf517de04fe | note | – – – – – – – – –
0e4fa5ab-9903-5fd5-934e-dc226500306e | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
abc00d0f-7641-5e48-977f-0681b8f166d3 | note | – – – – – – – – –
0ecc6477-0180-55bc-9b4d-4a8fa00e418c | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
ff1b5290-104a-5ade-9ab5-07a5c29549cc | note | – – – – – – – – –
cdc7a2be-3dea-5369-86d1-556924da3e40 | note | INSPECTION/TEST METHOD: Verify
bb893f9a-2f02-5c0e-ba28-9d311f4d39b9 | note | – – – – – – – – –
048cc78f-296c-5588-8a0b-a7db17925f7e | note | RECORD OF CONFORMITY: This ITP signed
f249ef65-8427-5027-b333-f97580e8bc87 | note | – – – – – – – – –
0f17dcb8-fbff-52b2-b7ee-9481e54a0304 | note | IP
e43e7be5-e1ba-5846-bb3a-72c42898705d | note | – – – – – – – – –
45ce6960-38ce-56ca-8ba9-4af6fed434f5 | note | RESPONSIBILITY: Fulton Hogan
633b3798-1c3d-5d0b-884e-4071358ae520 | note | – – – – – – – – –
cd653f2d-4329-55af-b3e5-e609752cf740 | textbox | DATE:
2d0514a4-da04-496d-8793-77e8e45636fc | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
02818751-9982-5643-b6cb-76b15888ae98 | note | FREQUENCY: Prior to concrete pour
8d6280c2-c539-5752-a10b-b65936ae518c | note | – – – – – – – – –
5077c76e-87ad-5300-9f1f-5acdb5bbcdd6 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
fd75890a-454d-5f3e-9a12-57543e6397b0 | note | • Pre-pour Checklist completed and signed.
db64340b-7e9a-5d73-a0c4-092f65c368d5 | note | – – – – – – – – –
67093cb4-bb77-5647-ab33-091060b24141 | note | REFERENCE DOCUMENTS: 610.18 (a)
c482e9b2-41a0-5e96-9d6f-328e784decc7 | note | – – – – – – – – –
256e76b9-a35a-5db1-8348-b2b673ec090b | note | INSPECTION/TEST METHOD: Verify
d2b66d7a-9521-5790-8935-e8d3e75b1588 | note | – – – – – – – – –
f1ccb97a-a0aa-5c93-8aff-3921d25af3a3 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
d2fabd4f-3c86-5207-b9a4-4d9840a16369 | note | – – – – – – – – –
48bffefa-2220-52ab-937b-e4103621b621 | note | HP
ce7cd94a-2449-5e65-a7fd-ace2488155ea | note | – – – – – – – – –
269b94fc-dca1-5f9f-888e-e2e5e366922b | note | RESPONSIBILITY: Fulton Hogan/VicRoads
b6598d94-4c8a-5ecd-9de4-c6b7aec18987 | note | – – – – – – – – –
a8556e6e-94a4-5c05-b335-460e888a60b0 | textbox | DATE:
a2235878-fd15-453a-8526-824f4c34b95c | signoff | HOLD POINT AUTHORITY
de3ae6aa-60db-497c-9673-f36f76f04683 | checkpoint | 3.6 Reinforcement assembly of piles
346f4355-0e76-575a-8623-1cd0f777ef6c | note | FREQUENCY: Prior to concrete pour
c7c9f394-67a8-5cc3-b29a-37aa9a25105f | note | – – – – – – – – –
702b8ad3-b6c7-5b37-ba0d-f354bc0ffd75 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
aaae2e2b-0037-5aa3-bd3a-a36e2efb623d | note | – – – – – – – – –
761c24f9-6b8f-524b-b2d3-803c6328e662 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
97ac5129-b29c-519f-9837-7e681b05817c | note | – – – – – – – – –
0f7fe54b-54eb-5088-8bf7-2fa4cfa7601e | note | INSPECTION/TEST METHOD: Verify
078438bf-fbae-5570-b714-34f07a23cf91 | note | – – – – – – – – –
4888ee6b-39b9-59b7-aad6-eb8d714b2ccc | note | RECORD OF CONFORMITY: This ITP signed
029dcfdc-a675-504b-a374-bbcb098f235f | note | – – – – – – – – –
a90cc3f1-7ebd-50f3-825e-d13dbd21c4a3 | note | HP
6dfcc16f-401a-5ca4-8287-dac1a9fccbd7 | note | – – – – – – – – –
47c15d9d-ed19-572f-b96d-938792edfc28 | note | RESPONSIBILITY: Fulton Hogan
a9ce9c41-0c5b-51d3-9e4f-c6a97744d076 | note | – – – – – – – – –
8098743a-c43a-5b17-aca7-bf7e3811fafd | textbox | DATE:
9f83f956-3d80-476e-8ed7-6ba65ec99bed | signoff | HOLD POINT AUTHORITY
03c620c2-c604-41c0-a6fa-03c23a30c672 | checkpoint | 3.7 Monitoring weather
cb68b816-2244-586e-9ded-96d986b792d2 | note | FREQUENCY: Prior to concrete pour
f874b5af-3f80-54ec-b911-7ac7dc20456e | note | – – – – – – – – –
d08ad85b-03fc-57a4-ba93-1f19bdd514f8 | note | ACCEPTANCE CRITERIA:
e2d827c7-bfaf-5f76-983c-dd37c3813582 | note | • Concrete shall not be place when temperature is <5°C or > 35°C
d6ac215f-cfc7-504b-b187-8b3819be5144 | note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
914ecae5-46a3-5571-9cca-db7924f0ff5b | note | – – – – – – – – –
6fe41d1f-5a4d-5f29-82c1-7ac6c5cfcdf7 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
0f9c0470-0af7-552e-9037-afc524bfbcac | note | – – – – – – – – –
f84b0d23-eec8-50bb-ad8e-1ff135f09f95 | note | INSPECTION/TEST METHOD: Verify
8ad555a6-8284-587d-9349-32d086c75e0e | note | – – – – – – – – –
22bbe975-f41a-52a3-bf34-b2ebcd4ecb04 | note | RECORD OF CONFORMITY: This ITP signed
a6976225-fab1-5467-b353-e9e6a67fe00c | note | – – – – – – – – –
7e223618-3105-51bb-b173-9e08f9c0ac2a | note | IP
946c6ac8-0bf9-5cbb-b170-5d32e64dc61f | note | – – – – – – – – –
9f599052-2820-50bd-8ab5-57a55361b12f | note | RESPONSIBILITY: Fulton Hogan
f4179c15-305f-56fc-b826-ca7d7fb162d2 | note | – – – – – – – – –
065e0f73-d246-58e2-a3f7-3c70691584a0 | textbox | DATE:
aa6bdf1e-1ee8-4fc3-8257-6e760eca9a08 | section | 4 - Placing and Finishing Concrete
b7f023ce-63c7-4e63-932a-0e606343370f | checkpoint | 4.1 Carry out sampling of concrete
d5b0a140-b20f-526e-bf5e-f3abde8179ee | note | FREQUENCY: Each concrete pour
3d3cd601-f8ea-57be-a7e9-ebdba11705b9 | note | – – – – – – – – –
67cb1c0f-d175-5a28-9c4f-d86c07f4a3ad | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
9af339fb-096d-5044-93f7-50098e963f01 | note | – – – – – – – – –
6ceff4f0-70c0-51d1-a283-506b30fd436a | note | REFERENCE DOCUMENTS: 610.16
243504b1-e8b5-59e3-91f3-b809b9acda0a | note | – – – – – – – – –
bdb7bf21-7fff-5f78-8dc3-a7bd014f46f2 | note | INSPECTION/TEST METHOD: Checklist
af20775c-956f-5762-8831-620a8a4cce1e | note | – – – – – – – – –
14e429cf-f20a-5973-a574-e71ec0e88c6e | note | RECORD OF CONFORMITY: This ITP signed
0c39e5ea-30ae-51a2-a7fb-fe08bdc9f74d | note | – – – – – – – – –
1d437ada-7c69-5cd6-8b7c-ba324b1d47d9 | note | IP
7586db1c-d5fb-51e2-be85-bd4ec95afad2 | note | – – – – – – – – –
a63b57fa-024f-518b-ac2b-2c571a77d2e2 | note | RESPONSIBILITY: Fulton Hogan
f36a481c-af35-5fe2-91ec-fed05abd5e8b | note | – – – – – – – – –
546290c3-5e6d-5edd-bf60-695c675fe37f | textbox | DATE:
18d428df-ced2-497d-9d87-4e6f536cd1ce | checkpoint | 4.2 Discharge time
b9d973d9-777a-5cf0-8ae7-4ddeec9238e0 | note | FREQUENCY: Each concrete pour
2dd3ee28-ba1b-5c38-a9d4-e9abcbb67161 | note | – – – – – – – – –
26390b32-9205-5419-a5f6-d8dcdd727ca3 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
41f742f5-20b5-5b11-aa49-217237a91f4f | note | – – – – – – – – –
e6eb0ce1-a322-5677-8004-cd1886de558e | note | REFERENCE DOCUMENTS:
328f72d1-4acb-5e98-9ada-b0e43419023f | note | – – – – – – – – –
6b21ec25-7608-5368-bc6e-c5df199e4a44 | note | INSPECTION/TEST METHOD: Verify
c35aa057-cc2e-58b5-981b-549bf39fd9eb | note | – – – – – – – – –
b8c221fb-b0b3-56cd-b170-5de80bc1e9b6 | note | RECORD OF CONFORMITY:
9f74eef2-5cce-5654-9ee8-c86f3f67c6d5 | note | • This ITP signed.
0785bf6b-11ee-5bde-b130-81b86b8dae49 | note | • Accurate Site Notes & Load Mapping
4d963ec8-ff0e-55ca-8976-59359494ecb6 | note | – – – – – – – – –
3508a25c-f6b9-573a-a9d3-5c191aff5ff1 | note | IP
a485dece-e342-5817-8c87-0c6af549b1f4 | note | – – – – – – – – –
dc63778b-d0cc-594b-9b2d-8dbde7e348a8 | note | RESPONSIBILITY: Fulton Hogan
d10f63bd-b60f-5946-8fe3-e1f8398f1b52 | note | – – – – – – – – –
66ed6e45-46db-5049-a9b2-853da29d01db | textbox | DATE:
41ca6341-7f0d-448b-9bfa-4f3ea0085245 | checkpoint | 4.3 Methodology of placement (structural)
ec0f9ab5-15da-59ba-b0d8-a6f86091f963 | note | FREQUENCY: Each concrete pour
6b391af3-dd1b-5b1b-98fc-8a6f54a63dec | note | – – – – – – – – –
9ecdd13b-6b9c-5f61-8329-c593ba8ad7f9 | note | ACCEPTANCE CRITERIA:
ef56e934-0d00-5efd-98a1-148a04041a0e | note | • Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
71b03d95-0b00-5aea-a73c-b5d450122826 | note | • Concrete shall not be moved horizontally by vibrators
e9e6000c-6a41-5b66-96e1-a7b0eb3e5e2d | note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
2a3cfc85-6e29-5810-bb98-41bb34c7ed92 | note | – – – – – – – – –
defb66ed-5cdf-582f-bb4f-7129cf55329f | note | REFERENCE DOCUMENTS: 610.18
0d4902cb-1fbd-59da-b166-5d7324a42cfc | note | – – – – – – – – –
05190bbc-83b2-5edd-9393-c93a522ca202 | note | INSPECTION/TEST METHOD: Verify
fab11b31-98ef-544b-af0a-a1f9da9edb78 | note | – – – – – – – – –
1d9c8308-6280-58a6-b48a-5f93ac4d06c6 | note | RECORD OF CONFORMITY: This ITP signed
3b3e95ab-b278-5d87-92f2-22086df61ddd | note | – – – – – – – – –
4044c057-c126-51b4-9d1b-b67751358619 | note | IP
dc46c8a9-3fd3-5a56-b908-c96943033c30 | note | – – – – – – – – –
ed1e8c01-a424-59ea-9904-92e24b6ba2dd | note | RESPONSIBILITY: Fulton Hogan
43c94f65-796c-53b7-8239-1c72e15b16e8 | note | – – – – – – – – –
4425a813-2c8c-5ee9-b12d-9668045cda81 | textbox | DATE:
77e7c7c6-65f4-4a86-8c51-e42b7a718914 | checkpoint | 4.4 Methodology of placement (piles)
c8ec25c5-3b57-538b-80de-fedd3be72a2e | note | FREQUENCY: Each concrete pour
4c6dfd88-bedf-5184-a9c3-db63558fcf12 | note | – – – – – – – – –
f429b9ef-1233-55b7-8097-9e1c558be353 | note | ACCEPTANCE CRITERIA:
50b313e4-6b86-5377-86bd-31b71b72ccf5 | note | • Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation.
d49d37e9-0107-5e56-9c2f-b020287158c1 | note | • Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
6d897674-f9a5-5c48-a1e7-032eeaecada4 | note | – – – – – – – – –
71a2963d-bb74-5ed3-ac0e-b0e7db74efec | note | REFERENCE DOCUMENTS:
48e145f8-03d2-5dd7-b7c1-42164d4a6043 | note | • 606.03(b)
884013f7-7436-58ba-8a53-dcaa78bd6c99 | note | • 606.05
2802d8e0-2543-556c-b52c-672a19cbb9fc | note | – – – – – – – – –
9bb890ff-ce9d-5ba3-8265-5afb98c3eff4 | note | INSPECTION/TEST METHOD: Verify
4d07202f-54e5-52b0-90c7-83491f7eb752 | note | – – – – – – – – –
8ba47704-507d-539e-aedf-1c8702650ab5 | note | RECORD OF CONFORMITY: This ITP signed
422eb6c5-bba5-5491-9314-638d11ab3cc7 | note | – – – – – – – – –
47b92bd6-3634-5084-b74e-737f1d3e35a3 | note | IP
d9bdaae8-4cd8-558f-831e-1081f6def805 | note | – – – – – – – – –
82b77a9f-fa0f-54ef-916d-90e7e74d3fd4 | note | RESPONSIBILITY: Fulton Hogan
705e55d9-84b1-5748-a039-706080ac71c2 | note | – – – – – – – – –
ad1b01e3-bd34-56a4-9af3-16c0be36770f | textbox | DATE:
9d64b042-70f4-41a5-84fa-66c722b688a4 | section | 5 - Post-pour Details and Inspection
57c39f57-3161-4942-98b3-6ebf98ffac27 | checkpoint | 5.1 Curing
aeaea94c-cc2a-57bc-a3c9-74d91875ee33 | note | FREQUENCY: Each concrete pour
9897d7cd-a433-5850-ac33-ec8cec92297f | note | – – – – – – – – –
622d64c8-c9f3-5312-b09b-efa82b9ab8f8 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
c58481b1-e1e7-58f9-8d91-790b4f0df630 | note | – – – – – – – – –
6bfc0c1a-bd78-58e7-8f1a-79488a64e239 | note | REFERENCE DOCUMENTS: 610.23
70c55d36-45e9-56ea-9698-ba66b5462e4d | note | – – – – – – – – –
2912ea48-1a9c-579e-abf6-346977ace9ba | note | INSPECTION/TEST METHOD: Verify
250822e9-6cd2-5727-a6be-e4abacdafd3a | note | – – – – – – – – –
5edcac28-ff0b-538e-a0ba-e605bd9143e4 | note | RECORD OF CONFORMITY: This ITP signed
2c708924-db0e-5ba4-af0b-00808463b9fa | note | – – – – – – – – –
c6c01d87-fa6c-52a8-b4d2-f53dde0dc22f | note | IP
07b945d5-e2e0-51f0-9d2d-a99ad69155f9 | note | – – – – – – – – –
f31c1e3b-f943-564d-91f2-7ecd2df83e0a | note | RESPONSIBILITY: Fulton Hogan
90c1908e-ac47-5fbb-bf98-97d59a512da2 | note | – – – – – – – – –
fec4353f-789a-5ce4-95ae-95a43ebe2824 | textbox | DATE:
a4c460fa-ede1-47b7-a7fd-8db456cc7ae5 | checkpoint | 5.2 Formwork removal
523e1c41-8a32-57d6-8eb0-683c2a3f4717 | note | FREQUENCY: Each concrete pour
cb0af25b-7c10-5f8e-8178-2014f6adae80 | note | – – – – – – – – –
70196e31-2127-58ab-9951-686a0fd63cdd | note | ACCEPTANCE CRITERIA:
ed7b078d-e2aa-52c8-b362-7a6caacc8e8e | note | • Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal.
b2137ef7-ae59-586b-a3c0-56398fb72d1f | note | • Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
0b499d53-ed9d-5974-94a0-5c81a4f6928c | note | – – – – – – – – –
eb5e369e-82c8-581d-b70a-7b4634b5fa1c | note | REFERENCE DOCUMENTS: 610.25
2dc6095e-320b-51db-92e7-9f9bae19293f | note | – – – – – – – – –
4012a385-35ed-5a7d-8cc7-f875505e60a3 | note | INSPECTION/TEST METHOD: Verify
9c8a0cce-d59b-5ac3-85eb-28ceb6818c41 | note | – – – – – – – – –
43551248-2cce-51ef-8c6b-28e2bdbcd034 | note | RECORD OF CONFORMITY: This ITP signed
e6a13c82-035a-53d1-8172-820c4a11291d | note | – – – – – – – – –
c4f6d485-2c0a-523e-ae35-1dd4cae0c1be | note | IP
2a09fd02-5e9b-5157-afa3-9594afd5aefe | note | – – – – – – – – –
7202681b-19dd-5ac4-84d3-6283c558c464 | note | RESPONSIBILITY: Fulton Hogan
968837d0-ee2e-533c-bff0-2ebfbc04e88c | note | – – – – – – – – –
3d903ad2-a14d-55c0-838b-a0a8bf38ff0c | textbox | DATE:
7d563eef-84b6-4160-a1ec-359f4097bfd2 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
4261866a-60df-5627-9eab-a1c99365d32f | note | FREQUENCY: Each concrete pour
4086746e-f163-51a5-b986-64f50b171a25 | note | – – – – – – – – –
efdb2bf8-5c1b-5efb-809b-533a38d25772 | note | ACCEPTANCE CRITERIA:
7040d7b0-887f-52cb-9e78-3cb1f34a8430 | note | • Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
51bf9fb4-ae60-56af-aabd-51fa5fd18eb8 | note | • The centre of the pile head shall be in the specified plan position ±75 mm;
065da774-f9e7-58d1-8d12-ed92b738f14d | note | – – – – – – – – –
57649d21-cb28-52b1-bad9-ae6310b3db39 | note | REFERENCE DOCUMENTS:
1a07a0cd-bd07-5973-b0bf-dfdd1d3ba8e8 | note | • AS3600 Cl 17.5
b88b6133-edec-512e-8c95-2e76f0fc4fe8 | note | • 607.06
e3d7e692-9965-59fd-9426-b10574764810 | note | – – – – – – – – –
382cdb1e-d478-5637-aff5-1870ec4084ae | note | INSPECTION/TEST METHOD: Verify
648c1577-d572-5f20-aa08-f2d3d5d90b12 | note | – – – – – – – – –
5a5ef5c9-64fc-5de0-b4c7-c0f68151a9d3 | note | RECORD OF CONFORMITY:
84ea31ea-8f37-5ee7-b011-988359750ffd | note | • This ITP signed
3980efcd-a55a-5442-b13f-9e7c10d419bb | note | • Post Pour Checklist completed
e885d913-a6a6-5944-a26c-6f5d843b4070 | note | – – – – – – – – –
4fee76d4-c2fc-572b-932f-dbd8efdf5f4a | note | IP
29999c04-0876-5f81-921a-9941dd318573 | note | – – – – – – – – –
2ff5cdfb-d60b-5b17-8ade-14ccb1234167 | note | RESPONSIBILITY: Fulton Hogan
ae4079ce-90d9-5bc2-b18f-503d1f88ca94 | note | – – – – – – – – –
055d3aeb-673f-538f-8775-7472177e1771 | textbox | DATE:
898c4c80-2810-4a0b-b6d3-0da049663491 | checkpoint | 5.4 Concrete Sampling and Testing
fb00615f-987d-5508-8d9e-be92403928fc | note | FREQUENCY: Prior to lot closure
bfd0a9c1-36c9-5a1b-8891-445e26174e21 | note | – – – – – – – – –
64d08d5a-0a05-5d40-bea6-86df31443389 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
3bad3e2c-8115-5ec2-867a-8b5ba49348c1 | note | – – – – – – – – –
636cc072-a4a5-5a4e-92a6-38c32ccf7d9d | note | REFERENCE DOCUMENTS: 610.16
e0bae1c5-2420-5773-83cd-336bda340824 | note | – – – – – – – – –
df19a0a9-ff57-59e4-a504-b0c7e71170d5 | note | INSPECTION/TEST METHOD: Verify
22e1d16c-d2f1-5674-86de-b6d8dc6ebacc | note | – – – – – – – – –
496a297d-df78-53bb-b332-3546eceddc7b | note | RECORD OF CONFORMITY: This ITP signed
42731866-9e17-5a1d-8e0c-ab27599d0253 | note | – – – – – – – – –
c38406a1-089c-5c0e-bc50-b08151f49e69 | note | TP
8b01ca4d-bc9b-5272-924d-3d66bd3dd5ae | note | – – – – – – – – –
7b50e305-dd44-5ee8-9bf1-e634233443f6 | note | RESPONSIBILITY: Fulton Hogan
ab375e23-cbba-5456-8d24-077e1db7764c | note | – – – – – – – – –
f60f17ba-39b8-58dc-a773-083a1671eff8 | textbox | DATE:
863e9e59-e018-4f9b-8649-d5c45c5a2dbb | checkpoint | 5.5 Protection of Adjacent Piles
6edb672f-e505-5994-a5f2-4bf05dfb481e | note | FREQUENCY: Prior to commencing any piling
82117dbd-c8cd-5aad-8d64-b6f248c9b0c6 | note | – – – – – – – – –
1b46c531-e820-5491-969f-a06d7d91ea16 | note | ACCEPTANCE CRITERIA:
fdedfd95-7dc3-50b4-bfcc-48bddaa5d59f | note | • No pile construction shall be commenced within 2.5 m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
50b4941f-dd79-5885-89a4-e4b20983a184 | note | • Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
c7c4fb20-727e-5baf-b610-ebdaca168f96 | note | – – – – – – – – –
cf2cf1ef-9597-5879-bea5-e22fdc60d174 | note | REFERENCE DOCUMENTS:
092430cf-619f-5e2c-9aa3-c5654abd0cb0 | note | • 606.04(a)
fa293fe3-f74c-5cbd-ae10-96be4d2e047b | note | • 606.04(c)
5308329e-8e83-5065-adf1-90f9f5522013 | note | – – – – – – – – –
12da4753-1b32-5308-bac6-e0d929462744 | note | INSPECTION/TEST METHOD: Verify
4e1bbe8f-091d-5d31-b6c5-7ffb6916af8a | note | – – – – – – – – –
78483f52-f395-50ab-9756-014979550ea7 | note | RECORD OF CONFORMITY: This ITP signed
01478d4d-0d21-5de2-a4c7-91d9180a34a8 | note | – – – – – – – – –
741292af-52d4-5ef7-8f0a-0579c62aebcb | note | HP*
84902cdf-41a4-5b05-a375-51deaffd05d7 | note | – – – – – – – – –
71febc16-46ab-535a-8c47-d62d4410a501 | note | RESPONSIBILITY: Fulton Hogan
7ab2721d-82b9-5039-a23f-07e646b3c9e4 | note | – – – – – – – – –
eef60b50-53c0-52c2-bcd3-e20c321b6249 | textbox | DATE:
16276795-8018-4dc9-8432-5f1327b9a1d5 | checkpoint | 5.6 Integrity Testing of Piles
4a8044ff-700d-5ab2-8fb1-1d2e061c033c | note | FREQUENCY: Each concrete pour
1b2c07e1-2c49-581c-8d94-98f2ede76014 | note | – – – – – – – – –
a4d268ab-cc6c-5f97-a7e9-322721956f84 | note | ACCEPTANCE CRITERIA:
2b429345-ac1b-5312-931d-65446ce17d0e | note | • The contractor shall provide details of the pile testing consultant to the Superintendent for review.
0eab57c5-e233-54a0-b1f7-92bc74b8b808 | note | • Integrity testing shall be conducted in accordance with the integrity test methods specified in AS 2159.
bdeac742-7122-5412-9340-dae9758d4b66 | note | – – – – – – – – –
39547fee-fa59-59c6-82be-ff87fcee0e11 | note | REFERENCE DOCUMENTS: 607.07(a)
3d862fd2-c9d4-5652-b1f4-9ac0d1b6661e | note | – – – – – – – – –
a550d126-38d0-5ff3-af77-5b3c2357f3b4 | note | INSPECTION/TEST METHOD: Verify
43ec1edd-b1e6-5c8c-ab20-57aaa9438b3b | note | – – – – – – – – –
7b82ab7f-43f9-52bb-af4b-3a69bdc62706 | note | RECORD OF CONFORMITY: This ITP signed
75197836-a8da-5e41-953a-8f6325cbdb19 | note | – – – – – – – – –
391b3e34-6ef9-583f-8abc-2e2d3befec46 | note | TP
a292920c-243d-5072-ab43-2aea81d3b2d9 | note | – – – – – – – – –
241d4adc-0905-56b7-a2ee-bb14e9ff4353 | note | RESPONSIBILITY: Fulton Hogan/Subcontractor
64e83fd1-2025-5824-9424-6342a545c991 | note | – – – – – – – – –
d9f406df-3ab4-5cce-8b42-bdf4c07c02a2 | textbox | DATE:
d8c1d20a-cb63-4118-b134-ae992de8fed7 | checkpoint | 5.7 As Built Drawings
e3438f8f-ed23-5f19-b434-b3639c8174c4 | note | FREQUENCY: Prior to lot closure
b744fbfa-b9cb-5520-bab8-4fc05a9de513 | note | – – – – – – – – –
330f7708-1c53-56ca-b993-9dc883941bf9 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
431ef768-f599-5d9e-8c4f-77233f15b299 | note | – – – – – – – – –
db518d87-3c04-5ca2-82ce-a784bf923adf | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
9858d0ba-4e20-5816-8773-cb2254deaf29 | note | – – – – – – – – –
51fc341d-94a3-5984-b886-8fa8d676e499 | note | INSPECTION/TEST METHOD: Verify
33f0d4ae-4628-58e9-8a4b-342bb4675e1f | note | – – – – – – – – –
e097b435-a54e-5b62-9273-95284c8c15da | note | RECORD OF CONFORMITY: This ITP signed
242bb520-7f51-58d4-b811-66126d0cbfad | note | – – – – – – – – –
da7d11fe-f0d0-5b53-ad73-6d556b43561d | note | IP
62dff8b3-9138-5f6a-bca6-bcc30ce11701 | note | – – – – – – – – –
ec371fbf-d286-5924-a708-908fd516335d | note | RESPONSIBILITY: Fulton Hogan
5b290ed7-0cc2-54eb-a828-9bef8264cb8d | note | – – – – – – – – –
8bab3eaf-ad02-5b6c-ab8b-c5afcdddf152 | textbox | DATE:
3dba17fb-eccd-46aa-905d-79edb1179f9a | checkpoint | Final Inspection
0971a2e6-0bfe-593e-acf0-a7bb41f139df | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
66b4a1a0-ee4b-5b8c-9e96-4d3497ea9eb9 | textbox | Print Name:
1392fc91-687e-5309-b0e7-5026e6625e91 | textbox | Position:
c5c0c207-f81d-569c-a272-f00b358cb76e | textbox | Date:
0b5b1871-2fc4-472b-ad64-1aff0d3347d7 | checklist | ITP-01-026 - Safety Barrier Installation | itp | ITP-01-026 - Safety Barrier Installation
bfddf5d4-c6d6-48c7-9e41-6c316f025073 | section | 1 - Preliminary Works
9b86486d-0ee2-4dc8-a9f7-6e70ef4fffcb | checkpoint | 1.1 Check for correct documentation
6eaba19a-448a-5fb7-9079-b0f14fa02a19 | note | FREQUENCY: Prior to commencing any activity
0041a60b-dbe3-550d-b541-f5b2bdd8ecba | note | – – – – – – – – –
357351c2-5431-52a6-8f82-1e4ee94a3972 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
fd1656a5-2014-5f08-9c17-d75403bf818d | note | – – – – – – – – –
262542d1-316f-5016-b02c-f15996b7f33a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
596f6074-0d93-5f52-aa82-54068195a2b3 | note | – – – – – – – – –
8cc4b292-f30a-5f3b-a1b0-4dc33fc1f487 | note | INSPECTION/TEST METHOD: Visual inspection
2fd22c4f-6c82-5f12-b585-0d6a6cad4bd0 | note | – – – – – – – – –
a0556489-3e8c-58fb-b383-abbcd50a63d4 | note | RECORD OF CONFORMITY: This ITP signed off
54e86f62-9a4b-5cec-85c8-e2fd437094ac | note | – – – – – – – – –
ca599452-d06c-5874-9af8-0aeaac75aac1 | note | HP*
c785080c-75b0-5f3c-81f2-eda0d38f7c6e | note | – – – – – – – – –
975a2111-ae47-50f1-b24d-dde62cefceb7 | note | RESPONSIBILITY: Fulton Hogan Engineer
dec737d5-0fe7-57c4-b875-d163592b4f86 | note | – – – – – – – – –
2afc1a3b-943f-5cc7-b428-c8115e91f153 | textbox | DATE:
4a6e089d-e201-403f-b09c-cbff8f8b77a2 | checkpoint | 1.2 Implementation of all measures and controls
7de3efc9-9fc1-537a-9b04-abd5ec7494e2 | note | FREQUENCY: Prior to commencing any activity
fc73b1f8-fed3-5be8-a1a3-8680484909c6 | note | – – – – – – – – –
d8eb207a-2dde-5d70-8d02-82b0a4cf1e47 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
e84292aa-63ae-52cd-b976-eaeaa5ed467b | note | • PSP, EMP, TMP, JSEA, SWMS & WP
1b54341c-5219-56a7-a802-3da79c0fa58b | note | – – – – – – – – –
f1d78716-9bcf-5805-8a01-c44477edf5aa | note | REFERENCE DOCUMENTS:
bfc46c50-21dd-5323-811b-759f0fa97626 | note | • PSP
1f40437c-a3c4-5cae-b9ab-1806a0537630 | note | • EMP
ba7553cd-cc8b-56b2-b917-0997a7dd42fe | note | • TMP
53f560fc-4e29-526f-bffe-90f986587ba4 | note | • JSEA
32ffef5d-701d-50d6-aad6-63811736b1fb | note | • SWMS
13b19799-5cd9-5d30-8097-64ef497fe7ab | note | • WP
1125b561-b08c-5d9c-948d-2c40fae483b0 | note | – – – – – – – – –
e3f7417b-a07f-5d42-933b-4bf124c372f9 | note | INSPECTION/TEST METHOD: Visual Inspection
9428a36b-adbc-5764-ac21-d83e307b9529 | note | – – – – – – – – –
2cc4bfb2-b129-542d-b40a-e798cea63423 | note | RECORD OF CONFORMITY: This ITP signed off
75fc26c1-6bc5-5535-83c2-78e1bb78684b | note | – – – – – – – – –
9b4042a3-d339-51c5-bcf6-45db4e9815be | note | HP*
0bd46091-2422-5872-bf46-72115bec2fab | note | – – – – – – – – –
c96a732d-c073-5361-81d5-cf8f809ac47c | note | RESPONSIBILITY: Fulton Hogan Engineer
1a4f323b-1ea9-5e58-8171-13a11b76c80a | note | – – – – – – – – –
0183f500-82f0-5898-b257-5c4ff96817ab | textbox | DATE:
8a4a9b60-6469-4454-bed6-151190a5fb16 | checkpoint | 1.3 Material Approval
bb662d6b-ca3e-5e03-a2c4-b2b06919bf57 | note | FREQUENCY: Prior to commencing any activity
d7c412d0-9aaa-5b95-9fed-c86dd198fc8d | note | – – – – – – – – –
fa01e656-1b59-528e-96e3-c40f32579bf8 | note | ACCEPTANCE CRITERIA:
196545b1-7c21-58f8-a02c-ee586d1ef698 | note | • Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used, FHC shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
542706ea-ba3e-5b38-91a5-c82455ea8705 | note | – – – – – – – – –
249c23d7-08fd-585b-b309-6fd9c4311bc9 | note | REFERENCE DOCUMENTS:
faf41288-b6c5-5978-8736-184ba7bd7c54 | note | • Fencing Plan
58cf3842-a38c-5de1-be88-41e55e4f233a | note | • RD06-04
d006f2e6-7ae7-5ef1-ac28-f73ca910a300 | note | • 708.04
83bea9a7-5f3d-5b23-87bf-5d7a32d29e09 | note | • 708.05 (b)
4ed8672b-dde6-56d3-bd39-2cb692800037 | note | – – – – – – – – –
7788dd77-1c15-5661-a6a9-f9a4e61f8fd4 | note | INSPECTION/TEST METHOD: Verify
5ac3aca3-5858-5fb7-accf-620a4afb245f | note | – – – – – – – – –
477aca57-8cc2-5ec8-bdfc-3d20bc0dc78a | note | RECORD OF CONFORMITY: This ITP signed off
e0f7b792-4dab-51c5-9cac-9433c8719d27 | note | – – – – – – – – –
0ab0f505-4132-5018-8a5f-38fb4434c816 | note | HP
3118ae47-1b43-57db-a445-11b0338178c4 | note | – – – – – – – – –
298c5e43-6d30-5aa8-a9d0-6fc60a382beb | note | RESPONSIBILITY: Fulton Hogan Engineer/Superintendent
79533625-103e-5b0b-aacb-d6ccb73a5e6a | note | – – – – – – – – –
97d66326-c191-5c93-bc61-a46ad4b619f6 | textbox | DATE:
57b89f14-ddc9-4621-a55d-9a9e062863ea | signoff | HOLDPOINT AUTHORITY
100b8bc7-a253-4d22-b5c7-f21e7be6260b | checkpoint | 1.4 Location of Works
7f1b20d3-10b9-5fff-acd5-8b571283261a | note | FREQUENCY: Prior to commencing any activity
da92f39f-c993-51ec-9057-36a266e79461 | note | – – – – – – – – –
fd5c8f9a-7c2e-5c71-8858-46dfa5a7580e | note | ACCEPTANCE CRITERIA: Prior to installation the Contractor shall confirm with the Superintendent the required location and length of all guard fence.
8acff0e4-0505-5537-b4ee-9c89f8dd9989 | note | – – – – – – – – –
7b167c20-f3a0-5c3c-8079-64d1ddf275cb | note | REFERENCE DOCUMENTS: Fencing Plan 708.08
7abc3a53-7a10-5a34-9f72-96f681a57a19 | note | – – – – – – – – –
e5f97398-7e1d-54ea-b6d7-492a0f4f14fd | note | INSPECTION/TEST METHOD: Verify
98de8414-5ac9-5588-8c9d-a69aea8a3ee0 | note | – – – – – – – – –
12e46c63-72c4-504b-ada6-2ee9c1ca84cd | note | RECORD OF CONFORMITY: This ITP signed off
de22eaaf-80eb-539e-8bba-a50eb73368e3 | note | – – – – – – – – –
cc4f2f0d-d5d3-53d3-8f3b-a0de51a1b930 | note | HP
94462d7d-062a-5e90-9420-c488bb3c1882 | note | – – – – – – – – –
f7539347-9387-5c38-86d4-15fc63d62d31 | note | RESPONSIBILITY: Fulton Hogan Engineer/Superintendent
fb82a428-2b4b-57c9-90fb-ca89b5c8ac79 | note | – – – – – – – – –
0b875631-9e96-53f6-808c-ae2533de1ef2 | textbox | DATE:
bcde508a-c31a-433a-9f62-aae1034a22a8 | signoff | HOLDPOINT AUTHORITY
6f0cf904-6709-4e23-876f-9159b4bc4ed5 | section | 2 - Construction Works
4d22c184-1110-4e06-b6e1-1f7bd28c76b1 | checkpoint | 2.1 Inspection of Materials upon Delivery
5d8e027d-3a3f-5992-8d40-f5a56ad16f63 | note | FREQUENCY: Each Delivery
b0c8e8e5-ece5-50e0-af8e-5113232848e5 | note | – – – – – – – – –
5833a261-bb32-571c-a2d8-4f4a2148930b | note | ACCEPTANCE CRITERIA:
2fadd718-24a9-5762-863a-8a4728213789 | note | • Posts shall be inspected upon delivery for compliance and damange. If scratched or missing coating, this may be rectified with a minimum of two coats of a zinc-rich inorganic paint
a9a7730a-9de1-5050-9e91-e27d9b0dddf0 | note | – – – – – – – – –
62dd2776-47fc-5e9f-9868-9f6084b7d4c6 | note | REFERENCE DOCUMENTS: 708.07 (b)
6f200003-eb5b-5a1f-afb1-e0ae0fecedef | note | – – – – – – – – –
ddff9c58-20d7-535b-9798-fd2b2dbaf88e | note | INSPECTION/TEST METHOD: Verify
7e10a390-5432-58b0-9aca-4b9739b82a22 | note | – – – – – – – – –
c97634e9-f4c7-50b2-8ec1-24f7a6fd59e5 | note | RECORD OF CONFORMITY: This ITP signed off
6eec2fb0-1037-5731-a0d5-81a59450fcbd | note | – – – – – – – – –
3a9b6e6c-e26d-5544-bec7-362cc65c2342 | note | IP
62e6a80e-e07f-535b-980e-63a31457dbbd | note | – – – – – – – – –
391747c3-2934-5c8d-acae-d963a49110e3 | note | RESPONSIBILITY: Fulton Hogan Engineer
0c7f193f-f894-518d-beea-16c54f621973 | note | – – – – – – – – –
58067456-6130-5f75-a78e-7023d3362430 | textbox | DATE:
09ca8958-457d-4a61-b637-868e906f1c48 | checkpoint | 2.2 Post Installation
d28070e3-c85c-52a9-9d22-5003d53e139b | note | FREQUENCY: Each Lot
7a5a5b22-70f1-5977-a245-60d423749b90 | note | – – – – – – – – –
f6afbbfb-8975-5302-9e07-c045f356fd4a | note | ACCEPTANCE CRITERIA:
58b19beb-9cfc-5a74-b964-e2a182db7663 | note | • Posts shall be installed to the depth, line and spacing shown on the drawings, and to the tolerances in clause 708.07(d).
6e496e0c-52f1-578f-9544-6059537a0ee6 | note | • Posts shall be installed by driving, provided there is no distortion or damage which may reduce their effectiveness.
1f8e5726-b7dd-5493-9f06-de2afb82265c | note | – – – – – – – – –
47e837a0-edd1-5c7b-b4df-462ae55c6646 | note | REFERENCE DOCUMENTS:
3b29fc45-b48d-566e-bde9-ce2e6bc770af | note | • Fencing Plan
f0df57ab-8dda-53a1-8420-f329a9e33ef7 | note | • 708.08 (a)
2fc768e4-bc1c-505f-906b-ae958f840723 | note | • 708.07(d)
ed3121d1-a32d-5460-b716-18d68d582101 | note | – – – – – – – – –
da4a7088-8741-5219-aa46-8bb232c15f00 | note | INSPECTION/TEST METHOD: Verify
efe63ee2-093b-5348-aa41-1799f2f05d47 | note | – – – – – – – – –
8a0129b4-8058-5d93-a580-7cbacdceb79d | note | RECORD OF CONFORMITY: This ITP signed off
b5525105-8c5e-5857-8078-5b8face7b014 | note | – – – – – – – – –
c17ec6c8-0dbd-5e20-ac93-7b1134165781 | note | HP*
5fdb90e3-fe08-5111-aacd-668c1df390bd | note | – – – – – – – – –
6619c78a-9592-5020-a18d-186c2e8ce5dc | note | RESPONSIBILITY: Fulton Hogan Engineer
81a0b072-d6a9-591d-9a19-279cc88bb269 | note | – – – – – – – – –
5e3c9824-903d-5c16-b49a-f99cfd0c429e | textbox | DATE:
85e757b9-4dce-4af3-ac18-6c7aaf72fa2f | checkpoint | 2.3 W-Beams
675c2945-96b1-5afd-b249-b7eec8495117 | note | FREQUENCY: Each Lot
2bb19061-12d1-5adc-8034-c02ce6b08f66 | note | – – – – – – – – –
3cb515b4-bdf5-5571-aab8-213df5f66f95 | note | ACCEPTANCE CRITERIA:
4356d5d4-31a4-5fd6-b1aa-91c63ecd6559 | note | • The w-beam sections shall be lapped so that the exposed ends face away from near side approaching traffic.
e0a9a585-6812-53e0-aa22-014ae8829e1e | note | • The edges of the w-beam section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened.
a6c7ea6d-8a64-59a8-b604-e9e98dddd5da | note | • All bolts on the traffic side of w-beam installations shall be flush with the w-beam
1396edad-7e94-5983-86fb-8cf599496256 | note | – – – – – – – – –
ce4fedbe-ac21-58e3-a577-f10556095de5 | note | REFERENCE DOCUMENTS: 708.08(b)
32ea06ac-7162-5203-9b3c-688aa0904343 | note | – – – – – – – – –
38e11ab0-4af5-5d72-9f5f-469deffc3fdf | note | INSPECTION/TEST METHOD: Verify
2f73e401-3446-5514-87e4-81f6cd6521bd | note | – – – – – – – – –
1b81a833-6246-5634-bf0c-c865a1b22005 | note | RECORD OF CONFORMITY: This ITP signed off
3dd24d8a-3a22-5f52-9652-0c8e9377afb3 | note | – – – – – – – – –
6896d574-7adb-5d0d-88b8-d55942f3251d | note | HP*
95953273-b467-5d10-a476-7d7b4f3395f7 | note | – – – – – – – – –
1377cef5-9fa7-5d8e-883a-4a99cc465d90 | note | RESPONSIBILITY: Fulton Hogan Engineer
85514a68-59a8-5fd2-830a-9220a6b4c333 | note | – – – – – – – – –
e4da98ac-c404-5929-bfea-dee7ecabf109 | textbox | DATE:
182affa2-6bff-428b-bc28-519c7de29cb4 | checkpoint | 2.4 End Treatments
f7a16f58-ce37-5cd0-b918-de7f73205b63 | note | FREQUENCY: Each Lot
368bf44b-731e-5eb0-83ce-0ed62336195d | note | – – – – – – – – –
bbc1a04a-95dc-56e0-8042-420f87161c0e | note | ACCEPTANCE CRITERIA:
3c1d738f-2328-550e-9a22-2986580d41c6 | note | • During installation of wire ropes in the end treatments of w-beam, the Contractor shall ensure that no twisting of the rope occurs.
f876cf8b-98b3-52ef-ad33-7b226fb8ac58 | note | • When rope assemblies are used, the nuts at each end of the rope shall be tightened to a minimum torque of 50 Nm on the assemblies or as per the manufacturer’s requirements.
13c9297f-6e22-56c2-9332-e0eebef330a8 | note | • The Contractor shall maintain tension in the wire ropes in end treatments until the Date of Completion, by keeping the nuts at both ends tightened to 50 Nm or to manufacturer’s requirements.
2d71997c-1039-5a3c-8715-4afc2ac0eb39 | note | – – – – – – – – –
5b6a82ad-11fb-5669-ab06-f55810187c82 | note | REFERENCE DOCUMENTS: 708.08 (c)
1668dbce-6aec-514b-9aa9-1acafe377455 | note | – – – – – – – – –
46ac3173-887a-5692-81ea-6d6abc5bc9e4 | note | INSPECTION/TEST METHOD: Verify
1c39175e-9355-536b-86ce-f88b567da7ec | note | – – – – – – – – –
2627882e-0407-5311-b352-57d8e83827f5 | note | RECORD OF CONFORMITY: This ITP signed off
4d6be494-a8d9-504b-930a-da5f6e16821e | note | – – – – – – – – –
c5b19961-847b-5042-bb2d-ba75acab40d5 | note | HP*
ab2a8ec8-f1db-59cd-b845-fa1ecda4b804 | note | – – – – – – – – –
311cd0d4-cce2-515e-a76e-010f52f9e263 | note | RESPONSIBILITY: Fulton Hogan Engineer
244ad75b-802e-5b8a-8137-b92e909ea566 | note | – – – – – – – – –
337c9225-3021-5891-b72f-34543e1f25a6 | textbox | DATE:
56405677-ccd8-4975-94c1-1010291762c4 | checkpoint | 2.5 Delineators
219ffac0-daeb-536e-ac3a-b9b9f5cd63f9 | note | FREQUENCY: Each Lot
3c2f2d1d-a614-5bcc-a2aa-5306b9850693 | note | – – – – – – – – –
638ae94b-3551-5194-9049-ad079a80bfe4 | note | ACCEPTANCE CRITERIA:
e8abc281-3f36-54e5-9ab8-c38bbe4b115d | note | • Delineators shall be fastened to the top of w-beams, comprising of a flexible plastic mounting brackets fitted with 100cm2 of Class 1A retro-reflective material
1aa1316d-87ae-55d0-942c-63e52c95e485 | note | – – – – – – – – –
ba3bc491-fa37-52e2-bc78-a26f84c89fcd | note | REFERENCE DOCUMENTS: 708.11
f2cf5471-6612-5bdb-8018-38fb2deefd61 | note | – – – – – – – – –
8a8fddc1-ba1c-5193-8777-8b16ae46368c | note | INSPECTION/TEST METHOD: Verify
f18a09ce-8706-5fa8-a329-b6058f9d5861 | note | – – – – – – – – –
da277fad-99e8-5fb2-9b28-3a606dbfe7b1 | note | RECORD OF CONFORMITY: This ITP signed off
862b98fd-b39e-54db-bf31-2a83a9d6a2c9 | note | – – – – – – – – –
cee21315-dfaa-516e-9419-ef7fd7ea15b2 | note | IP
3702d588-3434-5d3d-a36a-7a2d687f46b3 | note | – – – – – – – – –
fa2bdb4b-812d-5664-bbe4-f5c6565b494a | note | RESPONSIBILITY: Fulton Hogan Engineer
a2927474-366a-5285-9826-1c38f8fb7222 | note | – – – – – – – – –
7787fed3-91e7-5ca9-a0ec-63a403d65760 | textbox | DATE:
4f629c0d-8c48-4100-90d3-c2cebfa12b0d | checkpoint | 2.6 Concrete Maintenance Strip
676cf872-f147-59d2-b032-d23bdaf9fce2 | note | FREQUENCY: Each Lot
031885ed-28a3-56f1-9277-d2e405fa0456 | note | – – – – – – – – –
ae6bec64-0dff-59a6-b33e-d80b3037e0c0 | note | ACCEPTANCE CRITERIA:
5490eaeb-8091-546e-aec5-50558236d7c7 | note | • The Contractor shall provide maintenance strips beneath the guard fence and terminals as indicated on the drawings and/or as nominated in Table 708.121.
95946290-b112-5c54-b85d-f2ebac989403 | note | • The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock.
e7335d09-96f2-50d7-8038-5b69b792a9af | note | • Where the concrete maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced.
91f6c94a-ea63-5216-a7d7-e2dd10951649 | note | • Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post.
89efb88a-c9f8-581d-800d-d846648fe4ec | note | – – – – – – – – –
00d67e83-373d-5285-9048-612682a7c4a1 | note | REFERENCE DOCUMENTS:
644ada3e-cc3e-525e-ab81-8beef6efef8e | note | • 708.12
8fc1ad9e-3fc7-53c8-a108-d7adce5ddfef | note | • 708.12 (a)
bdb2860f-5abd-507c-8cfc-c7bd4ac3b547 | note | • Table 708.121
cede186d-8301-5f74-8095-72c0a17eda71 | note | – – – – – – – – –
82edcf0d-3a16-5d06-82f4-71fe02ffa55f | note | INSPECTION/TEST METHOD: Verify
7bf6b6a8-05df-5e51-9023-740cecdfa625 | note | – – – – – – – – –
22039fbf-04f9-52bb-9f46-2f14ed741745 | note | RECORD OF CONFORMITY: This ITP signed off
6bbaa95c-6b26-5c67-9a43-aafc7ce2c48e | note | – – – – – – – – –
4f3c3416-2c4a-5eba-b28b-cf1f68e50b52 | note | HP*
05bdc459-6c5d-5598-83ab-2931f2390ae3 | note | – – – – – – – – –
ccc226b7-0a7d-578f-a338-4bf5ae906938 | note | RESPONSIBILITY: Fulton Hogan Engineer
c15683e3-2721-5fd3-8c02-95b96d90b7f9 | note | – – – – – – – – –
07d5268f-b934-5f61-9dbc-b0047aaf527c | textbox | DATE:
26d18c7f-8263-4e15-a2ae-6673df66eb14 | section | 3 - Completion
31389cac-2eae-46d8-9d34-c93946352f68 | checkpoint | 3.1 Tolerance Conformance
caad0093-264c-5d42-8c40-1aaaa2bcc061 | note | FREQUENCY: Each lot
17f5abd7-eecc-5b99-bf17-9701f537ecff | note | – – – – – – – – –
9aeedd0d-4957-54cf-8645-3ebd0558d253 | note | ACCEPTANCE CRITERIA:
6fe54900-14ae-5d9a-a3fc-b96d997c4d0f | note | • W-beam guard fence shall be erected to the following tolerances:
eab2ae85-991c-58ff-b7ac-22f14abe3901 | note | (i) Variation from true plan position of posts ±20 mm
f7915d8e-2a4c-5446-8313-378e66a27727 | note | (ii) Variation of line of w-beams from specified vertical profile ±10 mm
ab86ddb5-4b8d-54e4-860d-c6cef2ce0c09 | note | (iii) Variation of w-beams from specified horizontal alignment ±20 mm
b913d152-f085-5cba-9d50-3420bd48b627 | note | (iv) Variation of posts from vertical +0mm, -15mm
9ed455f5-1f3e-5c7d-8d21-fb257c5f1a54 | note | (v) Orientation of block &/or postto w-beam +0mm, -15mm
fae803c8-527b-533a-b0ee-d5db8034bb93 | note | (vi) Dimension of holes -0mm, +50mm
c1c4a1e6-8fda-5c55-acaf-611ee5372384 | note | (vii) Top of bolt head relative to W-Beam -0mm, +5mm
3998d82e-df45-5087-ba2f-2971807fb482 | note | – – – – – – – – –
a88a2c21-3bc2-56d2-950f-d8210f3f2be6 | note | REFERENCE DOCUMENTS: 708.08 (d)
4a2c7062-38de-5285-8ae8-af338ce151f0 | note | – – – – – – – – –
88f0054d-daf4-5ae1-b0f1-a66e84f05432 | note | INSPECTION/TEST METHOD: Verify
535ed864-00ec-5b5e-8d9e-303af3829d2c | note | – – – – – – – – –
82a5123a-c774-5a3a-a17f-84297a160670 | note | RECORD OF CONFORMITY: This ITP signed off
fce0a7b2-4974-5e7f-b7c9-dff6f30f767a | note | – – – – – – – – –
7c600412-0f0c-561e-957a-66336f8b5ee4 | note | IP
3698aee2-30cc-5ab3-a0ad-150157c11cae | note | – – – – – – – – –
7bd30321-e52e-57ef-bd8f-1870bd6eec2b | note | RESPONSIBILITY: Fulton Hogan Engineer
759ef81b-d559-5972-bd1c-55c796d38809 | note | – – – – – – – – –
765953f1-dcbe-5d59-a77b-ae1b1a0d368e | textbox | DATE:
c673bc5f-b953-473e-9af7-e8e83aa2abb0 | checkpoint | 3.2 Certificate of Compliance
d500d1be-a7da-5a75-8047-8a7adbe742c7 | note | FREQUENCY: Prior to practical Completion
ff40456d-03f9-5da1-a7a1-49f11958a43f | note | – – – – – – – – –
4d0aa301-b588-5f9a-9127-28bf4e1afdd1 | note | ACCEPTANCE CRITERIA:
8befce6e-2370-509b-9461-b8f41027532e | note | • Further to clause 708.07 Installation, and prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract.
e09e3be1-4ae5-5601-ac90-a0c6c4c3af5b | note | – – – – – – – – –
693b4b1e-35c2-551e-bb9e-9c544a56cb9a | note | REFERENCE DOCUMENTS: 708.1
a71e161d-005a-54c9-8da2-8b40bc2da280 | note | – – – – – – – – –
f40eeea1-1123-551e-bb56-2a98e8818ca1 | note | INSPECTION/TEST METHOD: Verify
eb969b36-39f6-5c17-99ba-f7dc12c485af | note | – – – – – – – – –
4c20527c-3eb6-5919-8520-7cb2968b8a39 | note | RECORD OF CONFORMITY: This ITP signed off
fc5dbf4c-17bd-52e3-b119-384c4c90f017 | note | – – – – – – – – –
de38dbc9-25cd-5c61-a954-d1f09007df41 | note | HP
f385426b-52d4-59d3-81a4-ce5b4bcf673c | note | – – – – – – – – –
2dbc8689-f23a-521c-ac0a-ec77a0b1a50d | note | RESPONSIBILITY: Fulton Hogan Engineer/Superintendent
9fc78e50-3421-539a-8b41-239f5bcb37e4 | note | – – – – – – – – –
e01c8ccd-6553-5d53-be9c-71f759928225 | textbox | DATE:
3a5e1f33-ccb6-4b35-b6cd-78d91742d4da | signoff | HOLDPOINT AUTHORITY
a8cb4aff-babe-4304-ba40-79d3620b3ec5 | checkpoint | Final Inspection
d7269cf6-984b-55a1-829a-81f93ce309d2 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5ccb504a-eb2f-502d-aa76-25e0e3741ff8 | textbox | Print Name:
983513ca-7650-50f3-a330-9757308aa587 | textbox | Position:
cbdd7b76-436c-5988-b568-fb4c595bed37 | textbox | Date:
56aaf294-de29-488a-9ff5-b1bc19f400c9 | checklist | ITP-01-027 - Pile Footing Construction REV1 | itp | ITP-01-027 - Pile Footing Construction
496f4926-9868-484f-b78c-7bf39daae004 | section | 1 - Design and Submissions
bc4ccf79-a625-499d-ba81-6aab8f431ce2 | checkpoint | 1.1 - Check for correct documentation
2132225b-bd6f-5509-9f34-a5939cfbcb49 | note | FREQUENCY: Prior to commencing any activity
168056bd-b4a5-55f5-aacc-d8ead93ea3c7 | note | – – – – – – – – –
664a656d-ca51-5757-9be0-b61d015b610c | note | ACCEPTANCE CRITERIA:
ac90b278-762d-5480-bd61-b164a5b93cb4 | note | • Ensure that all employees and subcontractors are:
c35ea0d2-a67f-5764-9924-7cf9bfb14c13 | note | – using the correct and complete set of drawings
e9f96298-4d40-5121-a5bd-1d57813179ac | note | – all drawings are the latest revision
4d426c96-09d9-5824-80f1-0b1c2d71a591 | note | – – – – – – – – –
8246e1d1-3561-5c85-9ff7-ecf48e89c341 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
451532fc-4f32-59c5-bb2e-fa635f15b3ff | note | – – – – – – – – –
12790ac1-52e1-5408-aea9-49631efc248b | note | INSPECTION/TEST METHOD: Visual inspection
c4c83d72-ae8e-5f79-b066-912632e45407 | note | – – – – – – – – –
210acb43-0568-5651-9442-438d3f75662c | note | RECORD OF CONFORMITY: This ITP signed
8bceb987-bf9c-53e8-af25-020506935ceb | note | – – – – – – – – –
01eb4638-c023-53a1-8ed6-a608e0ca1f5a | note | HP*
4632b99f-9273-562b-b43f-e87da56778f9 | note | – – – – – – – – –
b33c8df1-61f4-5554-9256-de2dce1fc76d | note | RESPONSIBILITY: Fulton Hogan Engineer
c96d7209-9716-571f-9dd2-8268535f5835 | note | – – – – – – – – –
aca3bcf8-962c-5cf6-8ee6-aef5107fda10 | note | DATE:
48a934c8-5c95-407e-8b6f-41f0c4b135e9 | checkpoint | 1.2 - Implementation of all measures and controls
5bba038f-a2f5-52b8-9fd3-bdf57080ba5a | note | FREQUENCY: Prior to commencing any activity
f3bb63c0-488f-5d27-9151-32cd0bf27975 | note | – – – – – – – – –
9abbad87-fffb-53a7-890d-be0f10f6d7a2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
5d925c2e-b543-5fa1-b552-6a5581313d41 | note | • PSP, EMP, TMP, SWMS & WP
aef624e2-4b6f-576a-b257-66ae6860cd2d | note | – – – – – – – – –
fb85cc7b-39e8-5919-b7b2-61d396aa3c3d | note | REFERENCE DOCUMENTS:
7885ea99-5fe9-58e4-811e-a79ffbcf1dca | note | • PSP
57c271b5-9a58-51b2-8d88-5673d875c94b | note | • EMP
8cef1eb7-4aca-58b0-a30b-23e49232139b | note | • TMP
dc1d51e3-3f2c-5aad-800f-4d6e2439f006 | note | • JSEA
76af52ca-5b66-51d2-b41a-770a6de5a5de | note | • SWMS
19f8bdb5-6d3d-5046-a7f5-984783f55727 | note | • WP
fdf1e94e-25ca-5a3f-8792-35779f5e4413 | note | – – – – – – – – –
8c1a7e30-104d-5db6-826c-15a1037502ab | note | INSPECTION/TEST METHOD: Visual Inspection
7a68aa8d-00d8-59a2-9ec3-0411f63050fb | note | – – – – – – – – –
02b6d3da-26f0-5c71-9c5e-47e4a2247e44 | note | RECORD OF CONFORMITY: This ITP signed
d1c6c3e0-1df7-56e6-b2f8-1005fcd13fc2 | note | – – – – – – – – –
285328a2-7c5a-53f7-a02b-ea70c47a89f4 | note | HP*
037d51e6-cba7-5553-9419-f1ef8ab3fc8e | note | – – – – – – – – –
a8ee8a2a-8b66-50b6-af7c-5df86acfc524 | note | RESPONSIBILITY: Fulton Hogan Engineer
6f4194de-315d-5c97-a605-d439f97f6bde | note | – – – – – – – – –
ab89e35a-769b-50c2-befa-19b27f297f2b | note | DATE:
120a41c6-a8b2-42f5-95f7-fed90bd0a1ca | checkpoint | 1.3 - Approval of mix design
1f0e6577-b637-591a-a3e6-105b644da0d9 | note | FREQUENCY: Prior to the first concrete pour
1a4d46c6-ff2a-5cc8-8cb2-db0471da3ade | note | – – – – – – – – –
f067770e-d923-5522-8fc7-e9926558db35 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
d2fb8c0b-921d-5813-8c06-30b0820f3ef6 | note | – – – – – – – – –
3702f18c-fd34-5206-9eec-9698e93aa4c0 | note | REFERENCE DOCUMENTS: 610.07
fd0491a5-a408-53de-9d0b-a7957095e90f | note | – – – – – – – – –
92e3f2d8-a631-5260-9c7b-9f58b2787e4d | note | INSPECTION/TEST METHOD: Verify
60ec38af-64b0-50f5-8473-c00f77fe8133 | note | – – – – – – – – –
c11d056a-993c-563f-b2a3-92467ccbbb0f | note | RECORD OF CONFORMITY: This ITP signed
4f9c3893-2ea3-501a-b0f2-5e6473be7504 | note | – – – – – – – – –
8ada4e23-8ab7-59cb-aa7e-b5fe6c402eb1 | note | IP
ec1f090e-231c-57cb-bba7-d45b1d3de3da | note | – – – – – – – – –
07c0b84f-ac29-5a81-a402-b43bc5eaf076 | note | RESPONSIBILITY: Fulton Hogan Engineer
0e3e6851-324a-5661-8fa4-6c3b6ff8a8f3 | note | – – – – – – – – –
4280a3e3-e0d5-57d9-9e92-fcdeea651c3d | note | DATE:
2bbf3486-9a70-4e85-938c-0e6b07ab223a | checkpoint | 1.4 - Reinforcement schedule
e9acdac7-5765-5d65-b6be-0dac212f420d | note | FREQUENCY: Prior to concrete pour
b570093b-1ad8-56ab-935f-569e1aee9f88 | note | – – – – – – – – –
e23471f9-de04-507a-9069-eccff0603b29 | note | ACCEPTANCE CRITERIA:
65320c48-b4ba-5088-9fd7-3ddb770ba61d | note | • Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
f1202e7f-78f9-5370-910c-78c85b913462 | note | – – – – – – – – –
b3385dcc-0e06-5cdb-b218-44052aa739ad | note | REFERENCE DOCUMENTS: 611.04
8f907182-1d46-5711-b309-a037be57d22b | note | – – – – – – – – –
f8082d5d-ad0b-55e6-807a-4864411e03f5 | note | INSPECTION/TEST METHOD: Verify
dc320b5b-e778-5cea-b69a-3dac90ed7353 | note | – – – – – – – – –
3c0343d8-eae6-5af0-8bf2-f42a366ac411 | note | RECORD OF CONFORMITY: This ITP signed
b24fff00-a1d6-5e84-88d8-25dff33293e0 | note | – – – – – – – – –
329aff08-194a-5c22-8dd5-8ceea28a3200 | note | IP
fce23935-25ef-5741-98a0-2a8841490f45 | note | – – – – – – – – –
8ece724d-0f33-562c-b192-baf3c580578f | note | RESPONSIBILITY: Fulton Hogan Engineer
3730e816-b074-5a79-8da2-9631f25ec6b8 | note | – – – – – – – – –
0e94be36-f254-548d-8a61-9bf1ae1bdaf2 | note | DATE:
e7929427-ef83-4217-bd4e-1ed96deee1dd | section | 2 - Construction/Erection of Formwork
895881fa-534c-489e-a733-84943785bd14 | checkpoint | 2.1 - Excavation (Pile)
2c596b60-0389-5c5c-a140-d64b53dcd12d | note | FREQUENCY: Prior to concrete pour
78b1afac-50d7-5875-b236-bad5321d0e5d | note | – – – – – – – – –
312bd937-b5fe-5587-adf4-3794a19837d6 | note | ACCEPTANCE CRITERIA:
1d43b57f-631d-556e-a5fe-bc049b8957dc | note | • The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent.
53c627ae-a16d-5b38-85f5-a7d933dfdb33 | note | • Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
5ffc8a87-3b01-513a-8ab7-8298f17acba5 | note | – – – – – – – – –
0e39613b-a6fc-5a86-9c0e-d44a557e5814 | note | REFERENCE DOCUMENTS: 606.05
8605b057-eec5-5ccb-9a0e-cfd104d10c32 | note | – – – – – – – – –
fff6b56b-ad40-5646-a354-b4104a9b4623 | note | INSPECTION/TEST METHOD: Inspect
c6c5eb7d-34b9-5a6b-b491-95285c7b0ad2 | note | – – – – – – – – –
96126332-d912-5fa8-85a7-2ed2ea6abb76 | note | RECORD OF CONFORMITY: This ITP signed
357aa6ff-c605-5163-b462-a4dbb06cce14 | note | – – – – – – – – –
9223b8fb-1aa1-5750-a343-4d458accf9f4 | note | HP
60d11a9b-df29-54a3-abd4-396cbb11ff74 | note | – – – – – – – – –
d50ceab8-3bee-5d52-86fe-e9d6b3a2026b | note | RESPONSIBILITY: Fulton Hogan Engineer/Suprintendant
1ead9cad-4fad-54f3-be04-f7cf9dfa482b | note | – – – – – – – – –
04af5c80-f0a1-5043-958a-0eb7c4cc0271 | note | DATE:
cf2c8dc0-7106-4015-8ae6-b92a2244c766 | signoff | HOLD POINT AUTHORITY
721cbd05-fb5d-42de-b515-349e87b6e0e0 | checkpoint | 2.2 - Construction Methodology
6661f44f-7088-5fd9-8aae-824ab2960d0e | note | FREQUENCY: Prior to erection
b8cfe19f-44a3-5101-b092-e484bc604a6e | note | – – – – – – – – –
1f81c61c-f45d-51a2-b356-b9b467d1e8fb | note | ACCEPTANCE CRITERIA:
9ae209a3-d777-5d4e-b6e7-289df436d2f3 | note | • Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
c2de6dfc-8b04-5805-b8f0-eae5202b785a | note | – – – – – – – – –
e86d1cc2-e9e2-5b22-a6e8-559d525b6d90 | note | REFERENCE DOCUMENTS:
1b04136e-f473-5248-a5e4-56ccef433bf2 | note | • 614.04
47ef81bc-21e5-5057-ad57-b16dee660d30 | note | • 614.06
771dbbba-086a-5a59-b9f8-bcf47bf3f5ea | note | – – – – – – – – –
64690d40-9b82-5744-813e-16e09c4bf90a | note | INSPECTION/TEST METHOD: Verify
87b56631-a7e8-51ad-b89f-0c09b4728ad9 | note | – – – – – – – – –
0ebe121f-3aec-5da6-b760-84093bc586cf | note | RECORD OF CONFORMITY: This ITP signed
9f927a28-662c-596b-b232-791a26f8477e | note | – – – – – – – – –
e8174277-e297-5fe6-a395-1ff78b292b11 | note | IP
c0f6750c-f164-5695-ae2d-bb554f251c2f | note | – – – – – – – – –
7c0c9da2-9661-5b22-92fd-9a6b61742cf5 | note | RESPONSIBILITY: Fulton Hogan Engineer
265703c0-68cb-53e5-a88d-e905ea87f499 | note | – – – – – – – – –
ba0f31d7-28ca-543f-b40f-42d4c03e406d | note | DATE:
a8609a75-06ff-46ca-8477-85eddc6daec8 | checkpoint | 2.3 - Construction Methodology (Pile)
6f35f47e-3dc7-5285-9f3a-474e610c6598 | note | FREQUENCY: Prior to construction
c6a18e9a-82c4-50b9-a466-614a2918835a | note | – – – – – – – – –
aa9967a5-8051-54e9-a37e-7dc84c0433b4 | note | ACCEPTANCE CRITERIA:
d6d3dea6-028f-5c33-809c-5d099261fd32 | note | • Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
3c962006-1e37-58f3-b624-31e2e4583a59 | note | • Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
fa7d3f46-4f7b-5130-b0b1-725a08398d14 | note | – – – – – – – – –
9ba83961-640c-5537-a3ea-19a9ff91f7d8 | note | REFERENCE DOCUMENTS:
5ae8bf0f-11ac-50d0-8c32-baf4c2a7f0c3 | note | • 611.10
38d3d0bb-78d6-59f1-9f3c-00230222616d | note | • 606.06
f23f174c-63c0-516b-805c-d5ff8c4e96ae | note | – – – – – – – – –
fe4082f4-2b7c-5cc6-a2f5-e3a128e2d217 | note | INSPECTION/TEST METHOD: Verify
6d39cb95-a1a3-5b18-9c4b-733ecd93d1e7 | note | – – – – – – – – –
370542f7-ccfb-587c-bb3a-314348ebf20d | note | RECORD OF CONFORMITY: This ITP signed
20e6fe6b-225d-5957-919c-d21009e389b2 | note | – – – – – – – – –
0c101b73-61b9-510c-8455-e16648f1400c | note | IP
85814809-860c-5570-a997-85273d7c04c8 | note | – – – – – – – – –
45bc6323-0014-5c06-9136-4f47d2b3c540 | note | RESPONSIBILITY: Fulton Hogan Engineer
492f91c7-75cc-5273-9ba5-0b27cd3a5130 | note | – – – – – – – – –
ef3c644e-d572-5544-ae4c-45a9d752e454 | note | DATE:
71dd4e0f-728c-4dc1-bf75-059033a8f005 | section | 3 - Pre-Pour Planning and Inspection
43c33352-ea15-4d2e-8092-3bd3ec059b9c | checkpoint | 3.1 - Cleaning formwork
14e0a339-98d2-50ec-aeda-c465d3f9b40b | note | FREQUENCY: Each concrete pour
6b5143f4-06f1-5832-847b-567c89d87493 | note | – – – – – – – – –
2ac8d1af-56f1-5d2c-b693-7a9ca7609b2a | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
9125dbe8-3ba0-5546-bbf9-25d6b8eed356 | note | – – – – – – – – –
690d9616-34ae-5534-b611-c07046a1e236 | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
c647074b-87b3-5a25-ab65-b3088a6a8157 | note | – – – – – – – – –
5265e6bc-0ab9-55bc-9e19-8c3c994e00cf | note | INSPECTION/TEST METHOD: Verify
a7204383-648e-5bf2-b563-fe684983d25f | note | – – – – – – – – –
58bfdd52-7982-5205-a114-cd29e95ba9cb | note | RECORD OF CONFORMITY: This ITP signed
ad212f42-50ce-5d48-9774-93c25a59c616 | note | – – – – – – – – –
44631bd1-76cb-548e-ac68-b302bc0fd0fd | note | IP
8792fd5f-ff46-57be-a6a8-650f8ed960f2 | note | – – – – – – – – –
783be832-2661-5d4e-a827-ba5231b431f3 | note | RESPONSIBILITY: Fulton Hogan
76043aa3-af3b-5d12-a8ff-5d2cb08651db | note | – – – – – – – – –
7ad09c2f-d986-5960-9af2-8bf7d15855cc | note | DATE:
05782f45-a44c-4203-ab22-e637d551b82b | checkpoint | 3.2 - Correct forms, reinforcements, rag bolt assembly and embedments
ebd0c754-ec8c-5c60-ad11-1dd5adbde5df | note | FREQUENCY: Prior to concrete pour
d855b3d1-9b2c-5d74-8557-510d7f2bfa69 | note | – – – – – – – – –
50e9443f-8fc0-51cd-b40c-fa9e6cf465fc | note | ACCEPTANCE CRITERIA:
b17aeea9-c71e-574c-aa64-46f24989d164 | note | • Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
0b4297bd-9f63-52fe-a285-e47f639f4525 | note | • Pre-pour checklist completed and signed.
57a50476-c0bb-5bce-bd02-d5dab6f24a9f | note | – – – – – – – – –
9cb844bf-6ee9-5c95-b65c-bd32ca909b11 | note | REFERENCE DOCUMENTS: 610.18 (a)
b48c9410-afaa-5601-8940-0b80b80c5b10 | note | – – – – – – – – –
5fb8d783-0bc9-53c8-bf48-b85a3371acf1 | note | INSPECTION/TEST METHOD: Verify
b12b73dd-f984-5bf0-beef-3c455e3acb94 | note | – – – – – – – – –
1a2e829e-fd2b-5ea2-8d25-ba79f87d5c52 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
4dc8b820-46af-5858-b6cc-e1f4fd222ec0 | note | – – – – – – – – –
fda488f0-243b-5f40-baf2-41309dc685f9 | note | HP
bb9175a6-8d75-534c-92ff-ebf4a58f6739 | note | – – – – – – – – –
d8d4a466-fab3-5bce-a326-6d8329a89f3f | note | RESPONSIBILITY: Fulton Hogan/Superintendent
a5347a78-139e-5057-bd41-09389a78a683 | note | – – – – – – – – –
68acf6db-fec0-5a48-82e1-b2b95ba98672 | note | DATE:
8e0c2cfa-5ef8-4887-a940-78fc47cb93a3 | signoff | HOLD POINT AUTHORITY
3a8f1e82-e2e3-4768-a9cb-a1d3bfff1e4e | checkpoint | 3.3 - Reinforcement assembly of piles
d8007cf3-bbbe-5102-a7e8-141be235153b | note | FREQUENCY: Prior to concrete pour
f6d63d5b-fb50-5ca9-a7b4-d9f8a9191a03 | note | – – – – – – – – –
15398e41-b85e-5b4d-8e77-f9ad660d71c8 | note | ACCEPTANCE CRITERIA:
0a0a44fa-91ab-5efb-b62c-eda50f64c0ba | note | • Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
c60459f4-bd60-5380-9aea-1716026806d6 | note | – – – – – – – – –
56ae378e-720a-5b9d-9230-3b4905c0e37f | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
a7ab8c02-8c56-5416-bda4-113eca992935 | note | – – – – – – – – –
a4fe49df-38a9-5e67-973c-04d3547a2b21 | note | INSPECTION/TEST METHOD: Verify
99c821c9-6be7-533b-8fb9-3a7f6b9521ad | note | – – – – – – – – –
2e56cc69-d930-542a-a33a-cb7b4673d3c2 | note | RECORD OF CONFORMITY: This ITP signed
531e269a-007d-572d-98f8-df8e970f5f7b | note | – – – – – – – – –
6b29fe0c-debe-5c03-9922-d1cd9d6624cd | note | HP
1044893d-f13d-5491-af4f-845952fad89a | note | – – – – – – – – –
df019766-3c1e-5518-8ce4-bc34b860940e | note | RESPONSIBILITY: Fulton Hogan
d3f5c4b5-c090-5904-a663-806bac6308af | note | – – – – – – – – –
0583044c-d297-540f-b6c5-0a1474b4c59e | note | DATE:
2b8519d4-63c7-4bca-8bec-58541d6b86c3 | signoff | HOLD POINT AUTHORITY
d476974f-3754-4adc-a91b-8ebaac55db94 | checkpoint | 3.4 - Monitoring weather
1c4d490c-2d5e-5694-8e57-e356fec7ad15 | note | FREQUENCY: Prior to concrete pour
a6c63c5a-1e2f-56b1-9f46-f1e63565d7d2 | note | – – – – – – – – –
e1472990-ef28-5959-a92f-5dd0d362db45 | note | ACCEPTANCE CRITERIA:
87327113-28c2-505d-aa1f-7ef58afb2ec7 | note | • Concrete shall not be place when temperature is <5°C or > 35°C
2880d9d3-53dc-5cf2-94b3-d6c1ef1bf8dc | note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
5a799202-3fd5-5798-8486-3ebd5c4823c7 | note | – – – – – – – – –
fb042ef5-c57f-5a1b-90d7-7dbe784027b7 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
30d56940-e131-5625-b290-6a2d159c43bd | note | – – – – – – – – –
b0b3077e-3ff9-556e-ae09-961def042fa7 | note | INSPECTION/TEST METHOD: Verify
d625c156-ff7b-59f7-9a20-6c34dee3e583 | note | – – – – – – – – –
c58f3040-6a33-5abe-990e-2c82a949f18e | note | RECORD OF CONFORMITY: This ITP signed
4d865cf9-d75d-5516-9b85-21ab0d71c24a | note | – – – – – – – – –
1d0a96dd-5738-56bb-a236-b41c24b6e2cd | note | IP
572efc1d-6a10-5d1e-a30a-59fd96442b32 | note | – – – – – – – – –
d20c5ec6-4db8-58d4-a4e4-91530ce6fb11 | note | RESPONSIBILITY: Fulton Hogan
db30ddc2-3bae-5fa7-86f1-a2675527e691 | note | – – – – – – – – –
50a1d22f-3f0e-5f68-8f8a-077fd8e6a27b | note | DATE:
748c4087-f5d7-4dcd-abc9-c40f2bfd471e | section | 4 - Placing and Finishing Concrete
392cba48-04aa-4e81-85f4-c377696bc8b3 | checkpoint | 4.1 - Carry out sampling of concrete
78133213-8e4b-560a-af12-50e1f0a18d4f | note | FREQUENCY: Each concrete pour
2ccae786-6a25-5bbd-ae85-56c64665e5ac | note | – – – – – – – – –
5d2ce9ff-bacb-5da1-a2bc-b82b6377112f | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
b1191402-3813-5c05-929a-cce110e622bd | note | – – – – – – – – –
4eb3f3cf-7422-5ad9-a965-17650a10b2d9 | note | REFERENCE DOCUMENTS: 610.16
10edccb9-e712-548c-9adf-7b44a66a4b18 | note | – – – – – – – – –
d9f436fc-651a-5a9f-8486-6311dec1ba48 | note | INSPECTION/TEST METHOD: Checklist
28c5b501-e675-5f53-9f05-c83c349e6c73 | note | – – – – – – – – –
21d4b3f2-14dc-566e-adb3-97a1db50ec08 | note | RECORD OF CONFORMITY: This ITP signed
44ab1987-381f-5534-8977-09cb9a73f549 | note | – – – – – – – – –
228db29b-fd17-5646-b8f5-73ba88fe84bf | note | IP
9c3ade73-c7fb-5a4c-b2b8-fbc0b4e3172c | note | – – – – – – – – –
ea175fa1-ae7f-58f1-b621-21bce2552011 | note | RESPONSIBILITY: Fulton Hogan
ac88992d-8f93-5fb5-9a80-1aab3650d4be | note | – – – – – – – – –
d4ecea9d-54e5-5131-bdef-7c9cc02fe235 | note | DATE:
17f9bd01-0bea-482c-8f76-282cb3c36854 | checkpoint | 4.2 - Discharge time
45c782f2-96f1-5b29-bcfb-584fa7a62de8 | note | FREQUENCY: Each concrete pour
17e23743-995f-5929-8d3a-da75ef85f84a | note | – – – – – – – – –
1da929e6-d8c2-50c4-9d5a-55aa12c6243e | note | ACCEPTANCE CRITERIA:
15bc9515-377a-5a87-8c85-7240d363d37e | note | • Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
a2254e0b-bdbf-5336-b37b-33b09687b94b | note | • Batch to be used has a discharge time of 180 minutes. Boral VR400/40 (SCC) (180min')
82627573-3934-5943-a75d-56eccf0b8d33 | note | – – – – – – – – –
c4fb80c0-83d3-5ae2-832e-0138ba4ed31e | note | REFERENCE DOCUMENTS: 610.13
28a64797-ab73-5995-a8a1-e89102dd5a48 | note | – – – – – – – – –
eb6df635-b408-59c7-a993-3a77f5aa4511 | note | INSPECTION/TEST METHOD: Verify
334185a1-ae5f-537d-b90d-9d9fabcb9124 | note | – – – – – – – – –
fac33103-d2a1-5b67-9f6f-2ddebdd50f34 | note | RECORD OF CONFORMITY:
81c2c2ff-fcd9-51cf-a229-d1625a496c2a | note | • This ITP signed
2c203894-2583-56e0-bcc7-6310166048c7 | note | • Accurate Site Notes & Load Mapping
37d74e48-da17-58a6-b9c1-9b86063c42ae | note | – – – – – – – – –
9fabf6e2-7a4d-558d-931b-00d9213887da | note | IP
d3b11fce-e9cb-59a0-b2ee-cd1f0a842bff | note | – – – – – – – – –
2ab5db75-7da7-54d6-978d-472a82bba187 | note | RESPONSIBILITY: Fulton Hogan
824d3268-212e-5113-94c6-d2f7ffb91c06 | note | – – – – – – – – –
534d39e2-3fa2-5f7c-8584-ac4b64c6f263 | note | DATE:
c518d6de-a355-419a-8e11-314efddf78eb | checkpoint | 4.3 - Methodology of placement (structural)
ffd9e5e0-b732-5ed2-81c9-7d74a1f3e622 | note | FREQUENCY: Each concrete pour
905a72b2-a2de-5d68-b978-0fb1c7264d86 | note | – – – – – – – – –
f85a4c78-a5b3-5ff6-8e2d-f454cd34fa86 | note | ACCEPTANCE CRITERIA:
22f46889-5032-585b-a54e-f60d104f4317 | note | • Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
9f12d6dc-9e78-5e87-9147-eb0cdd64574a | note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
e8ce6578-7c9d-530d-bda1-37a668aa0ee5 | note | – – – – – – – – –
97f60cc9-5a82-559e-b23a-9866dd8b0442 | note | REFERENCE DOCUMENTS: 610.18
9aec3ee6-4a75-507f-b84c-1e53f546f660 | note | – – – – – – – – –
85e123bf-ead0-5943-98cc-36c12e9dfc2d | note | INSPECTION/TEST METHOD: Verify
618a4eaf-4abe-5eb2-995e-67973370ffa6 | note | – – – – – – – – –
16774891-0bc0-5d85-af1f-33e9acf1d45d | note | RECORD OF CONFORMITY: This ITP signed
884cbc72-68b6-56e7-8b34-f105e41b2e52 | note | – – – – – – – – –
0cd5d063-57ad-572c-beba-297cbc175ac3 | note | IP
7dbb86a5-9121-527e-a959-1afc0f1af701 | note | – – – – – – – – –
e901dc97-adfe-56a0-a99b-05b6ad7188df | note | RESPONSIBILITY: Fulton Hogan
6e80b531-547b-55a7-87aa-1bd3168d5dce | note | – – – – – – – – –
c42e69a1-4d76-5566-b172-d18513d6d935 | note | DATE:
ec970fee-060b-4178-ade3-1a5e52a52071 | checkpoint | 4.4 - Methodology of placement (piles)
d9bd4f0b-5100-5ccd-a5b3-cef364cee142 | note | FREQUENCY: Each concrete pour
9ca83832-6858-51d8-bcc6-2ba15f9a05ac | note | – – – – – – – – –
20a58aa6-a5e7-5866-8225-626d55c93418 | note | ACCEPTANCE CRITERIA:
f696e27a-fc8d-588a-a9f4-1030a6893a45 | note | • Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation.
f4a272a6-7e25-5ae8-851a-0bc42e9d882c | note | • Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
a19afeb3-0124-5a29-b9e8-e0074f09f290 | note | – – – – – – – – –
f62548a3-d126-5d8f-af5e-f5ec0280f672 | note | REFERENCE DOCUMENTS:
4d9dd549-a3ee-5962-9102-dbb9372666b0 | note | • 606.03(b)
c52821bb-8bed-560e-b840-9d82695bda24 | note | • 606.05
41f608c0-1aea-5713-8874-ea1efd0ccbbe | note | – – – – – – – – –
a4451c90-f844-58e6-a157-3c77a1b49698 | note | INSPECTION/TEST METHOD: Verify
5ab6d5f7-fc04-5296-9666-7bf5577fbb15 | note | – – – – – – – – –
4b6eae72-495a-522f-8fea-e54093167d23 | note | RECORD OF CONFORMITY: This ITP signed
3654e2bf-f134-5f40-8e16-5a77bee0a052 | note | – – – – – – – – –
b9ea9f7c-d1eb-5c08-90c9-2e20d4bd43ec | note | IP
7fe9d799-17f7-5156-b2b0-2bd4fa2f69cd | note | – – – – – – – – –
09b98e5b-7792-54b2-bfcd-2e1ca1b03948 | note | RESPONSIBILITY: Fulton Hogan
60a5d795-46e5-5afe-b0e1-82c26436eed4 | note | – – – – – – – – –
f1f6595e-a0ab-5e73-bdd5-469aca603bc5 | note | DATE:
d402d471-8daa-4b1b-93e2-db0ffe9da237 | section | 5 - Post-Pour Details and Inspection
8463e0d9-61b9-44c5-b4ae-96985ed51f1f | checkpoint | 5.1 - Curing
2f69e403-d20a-55c7-881e-043911a7b9c3 | note | FREQUENCY: Each concrete pour
c256fa42-6b2e-51b6-8210-99b2ccf862ab | note | – – – – – – – – –
618ae243-5ab5-5a7a-abe3-537770c814d8 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
440d0a6f-96c3-55fc-94c7-cb62ebd93264 | note | – – – – – – – – –
be1bd106-a8e2-5392-97eb-92c8b734f9f5 | note | REFERENCE DOCUMENTS: 610.23
8b408104-ad14-59b0-a8bf-e981d71589dc | note | – – – – – – – – –
a036cdc8-850c-567d-872f-9c9b3b221f3d | note | INSPECTION/TEST METHOD: Verify
cbdab737-199c-500d-8651-70b25e519485 | note | – – – – – – – – –
46237f20-a35d-559c-9edf-de65ab617084 | note | RECORD OF CONFORMITY: This ITP signed
a096d794-0182-5ef5-9947-c2a38e91d0a8 | note | – – – – – – – – –
a43a1b9b-7f75-56ea-b0ac-d8d2e3c6a6a9 | note | IP
f0b5379b-b392-5cb5-b51b-fe0ab7bcf730 | note | – – – – – – – – –
991569f3-500b-5497-b2dc-d9c38ab6ea85 | note | RESPONSIBILITY: Fulton Hogan
8b980515-02fa-5e38-be09-b1d40c7a4178 | note | – – – – – – – – –
2fed61f5-2326-5014-914b-d613f0fe6140 | note | DATE:
ce20d4e8-d16a-4814-8620-b73c7c9ec5f6 | checkpoint | 5.2 - Formwork removal
dd700f0e-46c9-5f73-8610-9d06741e5a6d | note | FREQUENCY: Each concrete pour
8d0b9084-0efe-5efd-8d74-bb9e5c99ba47 | note | – – – – – – – – –
462866d2-b1c2-52f2-ab8b-927be548cd7f | note | ACCEPTANCE CRITERIA:
8f54a479-509c-5cf5-95f9-ffde84e569b4 | note | • Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal.
909f6f72-7b5b-5c42-a92e-12251b86ea90 | note | • Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
ab4a9699-fdcf-51be-b14b-59672b5dd251 | note | – – – – – – – – –
68133dc9-2cc4-55e9-afc0-1de7ec294d2a | note | REFERENCE DOCUMENTS: 610.25
b51a48ed-0263-557f-8947-3d6659fb253f | note | – – – – – – – – –
7ca68d45-448a-5ca3-bf3d-0f102edc7315 | note | INSPECTION/TEST METHOD: Verify
a10135e4-3e0a-5805-a866-3bea1abff6d7 | note | – – – – – – – – –
12a278f5-670b-5266-99f4-f601f4d33c16 | note | RECORD OF CONFORMITY: This ITP signed
df339d4e-051f-5076-a18c-17ab3d695d10 | note | – – – – – – – – –
63fb8f9d-d828-5012-a3bb-1422f15ba3cd | note | IP
9ce39278-4448-5883-b17f-7a45fbd8a846 | note | – – – – – – – – –
2df91335-7d7f-59b9-a8a4-c9a3281989b7 | note | RESPONSIBILITY: Fulton Hogan
8f3cf01c-f040-567c-ba03-f8eaf38bc13e | note | – – – – – – – – –
c14a048c-844e-58ce-9084-aa14d12070a5 | note | DATE:
a8c3a6e1-4b31-4113-b3d1-6131677fae42 | checkpoint | 5.3 - Positional tolerance and dimensions of concrete members and piles
584816da-4476-554f-babc-616ffc7dd266 | note | FREQUENCY: Each concrete pour
12e0520a-f8d5-56a8-8e60-b65c787ac07e | note | – – – – – – – – –
c9a68dbc-52bd-56d2-8b78-d80e3af1c715 | note | ACCEPTANCE CRITERIA: The centre of the pile head shall be in the specified plan position ±75 mm;
5378cd32-3ae1-545a-9e48-8c81609590a2 | note | – – – – – – – – –
775cfc0c-1184-5852-b8ab-f3acb60c9e41 | note | REFERENCE DOCUMENTS: 607.06
c0d68efa-3563-59bd-b502-6e8390f881a9 | note | – – – – – – – – –
db238336-40dc-53e2-8fe8-b807bc840fbd | note | INSPECTION/TEST METHOD: Verify
de40556c-75ab-578d-b24c-fd9d5f482c2d | note | – – – – – – – – –
810db306-a952-56e3-b478-6593238ea92c | note | RECORD OF CONFORMITY:
33f73929-247c-5222-8e69-90909744aed8 | note | • This ITP signed
5d441462-076f-5dc1-b6fc-603e078337c7 | note | • Post Pour Checklist completed
388a547b-db71-5cd6-b250-cd10755c27dd | note | – – – – – – – – –
f0b3e617-7d97-561b-90d2-58ffec501e61 | note | IP
10aead22-b485-5b64-a811-f24ad4ede767 | note | – – – – – – – – –
50fa4077-dd6e-56cc-9bad-26bdabd64dc2 | note | RESPONSIBILITY: Fulton Hogan
dde1d988-8faa-524a-8c18-1076e063bd8b | note | – – – – – – – – –
c2dcfe70-8cb2-50c4-b56a-b35d9381b1ac | note | DATE:
bc4260af-41a1-4e08-acbf-1beb9425d58f | checkpoint | 5.4 - Concrete Sampling and Testing Self-Compacting Concrete VR400/40
6c6df0a6-0da7-5e48-b593-85439008074e | note | FREQUENCY: Prior to lot closure
b5fd9100-5561-5cc7-9edf-184d85de7367 | note | – – – – – – – – –
993b9eee-bf71-5670-824a-a838cdb8ba5e | note | ACCEPTANCE CRITERIA:
ea8eb2fe-5fe3-5d83-953f-c732b1c2b545 | note | • Concrete sampled and tested for Compressive Strength:
aadc4b6e-b8e6-5288-96d8-365d17278cc1 | note | – 2 cylinders @ 28 days for VPV=13% & Compressive Strength=40MPa
73931931-53f2-5e6b-b613-f7bf7929d6db | note | – 1 cylinders @ 7 days for Compressive Strength=26MPa
e57154b2-f38c-5321-8f0d-5da897018341 | note | • Slump flow of 550 - 800mm spread
ced30004-0a2e-5e75-987c-9913de67c8e1 | note | • T500 of 1 to 5 seconds
2d3f8db0-b6c4-5278-9b4d-b0230537887c | note | • Passing Ability of less than or equal to 10mm
7e7d9138-f3fe-5da3-981b-a6a1d1f1eb00 | note | – – – – – – – – –
11f4e48a-3606-5084-836a-8132edc91f0b | note | REFERENCE DOCUMENTS:
90a7401e-09ca-5c36-ab78-2f9eb821e43e | note | • 610.05
2040aca6-bf74-5f2a-ac7c-dfe13b28d575 | note | • 610.06
3a47798e-eac6-5816-a9df-d411c303f778 | note | • 610.13
57bbde93-7999-55e3-b238-91bc136c4e06 | note | • 610.16
dad019b4-3506-5177-baf1-489d9731f2ad | note | – – – – – – – – –
149d3b3c-8de7-5071-9b0c-287c7732ab2a | note | INSPECTION/TEST METHOD: Verify
cb77fd66-0209-500f-ae2c-e5858a650ce4 | note | – – – – – – – – –
12dd1a3d-d9e2-56d7-9dc0-d903230cfc50 | note | RECORD OF CONFORMITY: This ITP signed
f9febc70-e4cd-5a60-a682-530810e95541 | note | – – – – – – – – –
7a2a4d70-c16f-50b9-9fff-5e845642b525 | note | TP
6263392e-50e0-5c77-8a9a-6b1df17dbe7d | note | – – – – – – – – –
f96e828a-d474-5290-ad24-9a8d806eba72 | note | RESPONSIBILITY: Fulton Hogan
ded5ef0b-be53-5d1f-a3f8-d9e75e2e86dc | note | – – – – – – – – –
36271aeb-47c7-59cb-b5c5-48ddf47aef14 | note | DATE:
cc8e7a5b-4d31-440e-9451-f12a12769636 | checkpoint | 5.5 - Protection of Adjacent Piles
23b6a99d-5724-5ec1-aa7b-8b1cba285a28 | note | FREQUENCY: Prior to commencing any piling
769ea7cd-8a47-59d5-94e6-0381a20b4570 | note | – – – – – – – – –
d89e87c7-4981-58bc-a21e-0d15c5c55763 | note | ACCEPTANCE CRITERIA:
883b2c46-c954-57d4-b306-67b75f0601a5 | note | • No pile construction shall be commenced within 2.5 m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
f407a516-dd88-5e8a-b5d4-a76717816eb9 | note | • Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
277efb00-bbe4-5adb-a6da-be1a2e319d1a | note | – – – – – – – – –
93b981ed-4b48-5538-b893-341518cbdfae | note | REFERENCE DOCUMENTS:
6fea299d-8683-5703-ae6d-e274d91f978d | note | • 606.04(a)
7cd28fed-7d54-5c69-82e9-a49f9cfa7711 | note | • 606.04(c)
f2384992-03d8-5d28-8e43-d485e4c0a9d9 | note | – – – – – – – – –
a23cc8a5-a2b1-5c6a-aecd-e901896f590a | note | INSPECTION/TEST METHOD: Verify
a874733d-35c7-58a1-ba76-2225dd11780c | note | – – – – – – – – –
ecb6146b-92f1-5fb2-bce4-a2a5320fdb55 | note | RECORD OF CONFORMITY: This ITP signed
2e24e1bf-7e2e-5403-a3e4-b7dd595f5ae6 | note | – – – – – – – – –
0d70a4a1-d45c-5f21-9394-d87f5a5f768f | note | HP*
dba72044-e6c3-5448-ab47-09f9de49f820 | note | – – – – – – – – –
98ed2886-9782-59f0-87a6-2fde55b36d85 | note | RESPONSIBILITY: Fulton Hogan
b963bddb-ba9b-5074-9e53-cc2c0684dc9c | note | – – – – – – – – –
6c5fd3f5-0e6a-5242-a47f-4039a0fec9b7 | note | DATE:
69330ba5-961b-4712-9175-4a9ee7974a5d | checkpoint | 5.6 - Testing Post-Pour
e97f0743-05ce-5d09-8f48-f6929c3c65b8 | note | FREQUENCY: Prior to lot closure
5905b9c0-d720-5929-99f3-1d8a60b9ab34 | note | – – – – – – – – –
d245f3b1-1d7b-56e4-aaf2-56245de99ef2 | note | ACCEPTANCE CRITERIA: Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
4aa4eef3-4edf-5b73-96f2-6de9d1ba5036 | note | – – – – – – – – –
5d4b545f-a493-5c5e-abe4-6ba77bae71b4 | note | REFERENCE DOCUMENTS: 606.07
a161fd92-ece7-5ecd-8ba9-f416f40464b1 | note | – – – – – – – – –
05cc34ab-3eab-5d1c-9f81-de281e53a5fd | note | INSPECTION/TEST METHOD: Verify
ab1e7e81-8d00-52c1-873f-21784ab87c51 | note | – – – – – – – – –
30eeeaa1-bf2e-5fd8-83a4-029968b60784 | note | RECORD OF CONFORMITY: This ITP signed
36c9e160-8775-5eec-951f-153a54d91b16 | note | – – – – – – – – –
29aa6bed-787d-5336-a380-08448e976c37 | note | TP
b3d618a4-b82c-512f-b44d-fc5fe856771d | note | – – – – – – – – –
516b07f7-456c-50f3-bbaa-612c7f684cc7 | note | RESPONSIBILITY: Fulton Hogan
2650fe0d-5248-54eb-b187-df102d9ff389 | note | – – – – – – – – –
d19ea952-ce69-5328-b1f7-d007e7072f0a | note | DATE:
d374ae58-1fc2-481a-9b89-a55e73a9a900 | checkpoint | 5.7 - As Built Drawings
33f39151-3493-5c6b-b28f-cbcb09ca1874 | note | FREQUENCY: Prior to lot closure
c5eab3fe-a099-59ce-ab77-f688734c564f | note | – – – – – – – – –
458caacd-8561-5407-99c9-3a45870570a4 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
94881e45-b19d-530c-b51a-2983567d5f29 | note | – – – – – – – – –
ad905274-07a7-520c-935a-207987086186 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
efa7afeb-7698-5905-9eca-63d7e52b0175 | note | – – – – – – – – –
ce729d7f-befb-5ae8-bb19-64217c673c8c | note | INSPECTION/TEST METHOD: Verify
9a3347f0-f572-577c-be57-859cbe9597b0 | note | – – – – – – – – –
bff9ba69-b88b-5ed2-9817-7f5b57858f71 | note | RECORD OF CONFORMITY: This ITP signed
0143627c-bf51-53c4-aacd-b431de974318 | note | – – – – – – – – –
d1e27c94-3f39-5a87-992a-863f002bb8bf | note | IP
06ec2ce5-6f1c-5eb7-bbac-ae220e3b17f1 | note | – – – – – – – – –
c8a4aa63-9096-5b4a-9694-d271b814bae7 | note | RESPONSIBILITY: Fulton Hogan
9707bca0-fc20-5088-80d9-073c89dea318 | note | – – – – – – – – –
139347b4-a5dc-5106-9471-845a0a99fe34 | note | DATE:
01ad7a10-e166-4e7f-86d9-364d1448c758 | checkpoint | Final Inspection
cbc15fe9-329d-5d6e-8ba2-73db3a403a26 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
29f718bd-d464-50e2-9552-9b85ef1b752b | textbox | Print Name:
a1c13c20-192c-5e39-bea7-94d79a830e9d | textbox | Position:
8f016fa2-5e06-5877-9db6-61607a1c8654 | textbox | Date:
c3f8e724-7e84-450e-8576-4a24b8c6cac3 | checklist | ITP-01-028 - Chainwire Fence Installation |  | ITP-01-028 - Chainwire Fence Installation
9a201d93-e4ca-4bc4-86a3-0effb044a1c8 | section | 1 - Preliminary Works
8bd1e49c-7ffa-4159-99cf-7ad8970b9d8b | checkpoint | 1.1 Check for correct documentation
41c03141-3745-5474-b23b-e1477482143f | note | FREQUENCY: Prior to commencing any activity
192dd019-a6ba-5dcb-a79f-e2354fc519ce | note | – – – – – – – – –
051c49a0-a70a-5275-9fae-125d3dd3f0a4 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
a619ce15-5780-5c0c-b6cb-d4e8cbd1d13a | note | – – – – – – – – –
93dc7668-c28a-5617-9c0e-0ea987adee7d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
0b633774-6bf6-50b3-9416-9f61698b5e36 | note | – – – – – – – – –
8f7be824-f83a-550f-845f-c319ccb3efc7 | note | INSPECTION/TEST METHOD: Visual inspection
11deb594-bf79-5c0d-b56c-3520c4d89f81 | note | – – – – – – – – –
38143093-a904-5ebd-b870-0a20d548be3d | note | RECORD OF CONFORMITY: This ITP signed off
d0d18a85-60a5-5487-b5ab-d0e82d28f9c0 | note | – – – – – – – – –
9f6700a5-0c76-5089-b6a7-b4b6f7dcac9c | note | HP*
06631e42-025c-5826-bf72-83869d25ec83 | note | – – – – – – – – –
d860ee4a-fa27-54ba-8a1c-336476afcd1c | note | RESPONSIBILITY: Fulton Hogan Engineer
168b5608-d85e-52a5-98e1-623ada00ff1f | note | – – – – – – – – –
ac7c4751-5aa4-5b23-a5bf-7da602c8b5a1 | textbox | DATE:
bc9a8c0a-9177-4c5b-99ed-c4dac296abdb | checkpoint | 1.2 Implementation of all measures and controls
bf62a10c-9a96-5033-add5-6d43b2990121 | note | FREQUENCY: Prior to commencing any activity
8b76a499-f1e3-5305-b7fc-d7c6eda653d8 | note | – – – – – – – – –
040aa1ff-a934-575b-98f4-ec31621365f3 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
70c18fb2-0af5-54af-9e37-41d1aaf6e211 | note | • PSP, EMP, TMP, JSEA, SWMS & WP
c3933215-d61e-5894-a355-9eb7405a0212 | note | – – – – – – – – –
d094d984-a7d1-5f67-8788-780046c0b741 | note | REFERENCE DOCUMENTS:
db0bc441-63d7-5350-a05f-c6ff1735bae1 | note | • PSP
9401a45a-be1c-5696-848d-a0e849a1a549 | note | • EMP
66a580ef-7f47-5d76-8b33-60b984164b6d | note | • TMP
b356081a-752a-5a21-8105-af42ae26f35c | note | • JSEA
53ea49fb-d67e-519a-a0ae-c1ee165f8b1f | note | • SWMS
37419aea-62e8-56a0-b861-9f8d5d5ac25a | note | • WP
97fc7639-1fb2-5ec1-9b73-11c77d8d3a3e | note | – – – – – – – – –
95f5c6f5-5033-5862-8226-d52dace76816 | note | INSPECTION/TEST METHOD: Visual Inspection
ebb4adc9-61d2-5100-908b-347dd4ad9238 | note | – – – – – – – – –
8b62b706-e10e-5c9d-a71f-3821084a7c7f | note | RECORD OF CONFORMITY: This ITP signed off
21e66e3c-8c27-54b8-9d26-c3c2063a4b54 | note | – – – – – – – – –
cd358a60-101c-5cbe-902e-5b7edb6f5427 | note | HP*
614e21e1-a8a6-5a78-a397-4bb1868d3497 | note | – – – – – – – – –
fab3bc20-870b-545c-821a-1e80b3f82bcd | note | RESPONSIBILITY: Fulton Hogan Engineer
9700e320-34af-5dc7-9eeb-04b45d90dc74 | note | – – – – – – – – –
b3a0f1b3-b9ac-5fe2-9b3b-efdbab9b8430 | textbox | DATE:
0caa282d-20ba-40a9-a494-ef16810f14d5 | checkpoint | 1.3 Check Materials
7d93cf86-673a-5f24-af5e-03bb53b68d06 | note | FREQUENCY: Prior to commencing any activity
df6021da-7323-56b1-a85e-128a1f5540bb | note | – – – – – – – – –
809a08ae-9c64-57a1-bf29-bc798f34ffbd | note | ACCEPTANCE CRITERIA: Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of this specification 707 and drawings.
53b1b43d-ab14-5faa-ae9f-f67f94d78865 | note | – – – – – – – – –
7e210cc8-335c-5305-9a39-d71c3c06bb83 | note | REFERENCE DOCUMENTS: Fencing Plan
36255933-3b9a-589c-ab19-05cb1e101f2c | note | – – – – – – – – –
9489fd96-af23-55e2-a6e7-afbf12bc2a2b | note | INSPECTION/TEST METHOD: Verify
a2205ed6-0851-520c-b486-4ec66c8a6ffc | note | – – – – – – – – –
9b1ce017-a2a0-5a48-93b7-a35fe0421666 | note | RECORD OF CONFORMITY: This ITP signed off
0aa2d71c-9583-5ae9-95b0-f461ee74ea1a | note | – – – – – – – – –
5ba1a93a-9ba7-599d-879f-e1a23a7f0ba6 | note | HP*
816f3b29-49a9-500b-b051-a6ae9eeabb8a | note | – – – – – – – – –
55261079-dc1e-5e9b-8935-b3d4c643c1ce | note | RESPONSIBILITY: Fulton Hogan Engineer
55cf2f94-1826-5c73-ae41-64ce09b73c88 | note | – – – – – – – – –
35315c85-9f93-50b7-bbe3-30276fe23ae4 | textbox | DATE:
dac77a48-8885-44dd-88f5-5da7a4427ae5 | checkpoint | 1.4 Confirm Footings position
431284d2-1ed4-5957-bd39-1152acafd400 | note | FREQUENCY: Prior to commencing any activity
d39988c7-fde8-5146-9cb7-2341aa637b7b | note | – – – – – – – – –
de54d93f-582b-52f8-a19c-5dd6590531a0 | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
443c99ae-994f-5cf6-80be-e51100c5bdf5 | note | – – – – – – – – –
007c5052-5fad-53ba-b79a-67ca536f56a2 | note | REFERENCE DOCUMENTS: Fencing Plan
69b919f2-eae9-59be-bcd3-89cd8ac0ea42 | note | – – – – – – – – –
20866681-1051-5d0a-bb15-8fcb8d13e6c2 | note | INSPECTION/TEST METHOD: Verify
8d8ef1ca-5309-5724-8f0e-0aa3058a235b | note | – – – – – – – – –
ad4933fd-b471-5dac-b6ac-0ae8f5eca91b | note | RECORD OF CONFORMITY: This ITP signed off
0a20c595-cfb7-5b54-8c32-89cb4a328eef | note | – – – – – – – – –
0877fd74-2302-5311-ba2f-40eff02a0fa5 | note | HP*
fd31cf0f-bb2a-5023-8aaf-415bd5c10765 | note | – – – – – – – – –
3b037243-0054-560b-9115-babb65a3d3ed | note | RESPONSIBILITY: Fulton Hogan Engineer
7a483a00-5379-5aae-8d35-6e41b3b47451 | note | – – – – – – – – –
84e2571c-4deb-5771-bbca-61e4102fde68 | textbox | DATE:
5fe69f3b-c094-4924-a9a9-108790c1543d | section | 2 - Construction Works
51916c6a-9f83-4b38-af40-4ce4d0484340 | checkpoint | 2.1 Footing Installation
4e956d71-47c5-5374-90f8-37b1e6862cbf | note | FREQUENCY: Prior to post installation
50045595-fca6-5dcf-a232-5d624a9defa3 | note | – – – – – – – – –
201a2593-ce6a-59b1-b65d-a6b44e6510d2 | note | ACCEPTANCE CRITERIA:
36f741b0-6a46-504f-9485-a296426380f6 | note | • Concrete shall be of minimum strength N20
0b63bcd6-f654-5421-aed3-9621e8e41921 | note | • Concrete footing shall be 600mm x 300mm for intermediate posts
5a34ad3f-1657-585c-9672-e66cc80d90d3 | note | • Concrete footing shall be 900mm x 300mm for end panel posts
b658ec4d-39cb-5f2c-bef8-28722fa51163 | note | – – – – – – – – –
97731311-f925-5ae0-b593-e8da7fa9014d | note | REFERENCE DOCUMENTS: Fencing Plan SD3131
4d77f6c9-7f67-5e7a-ab5e-e7d641fb8487 | note | – – – – – – – – –
c49ebc20-7734-54c1-97ca-69bc4821392e | note | INSPECTION/TEST METHOD: Verify
ac73249d-f03d-505c-88a9-26e34644df6a | note | – – – – – – – – –
918dcb2a-79ce-528c-8271-af037a08ee1f | note | RECORD OF CONFORMITY: This ITP signed off
3807fc04-3f43-564a-9f7b-e46e6cb6831e | note | – – – – – – – – –
2032834e-b09f-5f01-887e-965c99708338 | note | HP*
a0653015-daa4-5d4f-84ba-57008f011909 | note | – – – – – – – – –
115d89b8-1507-57c2-8035-9bc3e3ca7b50 | note | RESPONSIBILITY: Fulton Hogan Engineer
787cdeaf-4f56-533d-bc02-b4dd0af7caa6 | note | – – – – – – – – –
2549d2c7-2435-5ccb-9f9e-76a3be4cb645 | textbox | DATE:
95761726-104d-4e87-a9c5-81949e5b3aac | checkpoint | 2.2 Post Installation
7d56d9d4-3eb9-5265-b6eb-76389df833cd | note | FREQUENCY: Each Lot
c762094a-1724-5925-a517-fb7c367ff5b4 | note | – – – – – – – – –
6efa1f7f-b390-51a1-8697-7e68a52b216a | note | ACCEPTANCE CRITERIA:
420ebdeb-2503-51d1-ba41-91ad58bc7434 | note | • Posts shall be set in concrete footings of the dimensions shown on the drawings
b9e7ab97-331b-5cf6-8259-c889ec1c99a5 | note | • Posts shall be Installed to concrete surface in culvert area with baseplate and bolt assembly
2967dfb1-1332-5757-aa4c-0e070e012dd9 | note | – – – – – – – – –
7b30e258-e657-5cad-9c1e-e3d1f97ffa25 | note | REFERENCE DOCUMENTS: 704.04 (d) AS1554 Fencing Plan
bd8a36d3-50e8-5ffb-b372-9d539adafb4c | note | – – – – – – – – –
9d3b3e12-c3f5-5a2d-b8b7-808a4c375f64 | note | INSPECTION/TEST METHOD: Verify
dfb95acf-13d1-52e4-8153-5cadf24df723 | note | – – – – – – – – –
dc6e7a4b-70bc-5391-a5b8-e3673488604b | note | RECORD OF CONFORMITY: This ITP signed off
2b7a68f5-c3e2-54c7-a641-2034ddba2a5f | note | – – – – – – – – –
2319b625-21f3-5ec9-ab38-d6c9077deee4 | note | HP*
ac0549d4-ce9b-566d-9772-55a3eea19225 | note | – – – – – – – – –
2820f00c-104f-566f-9123-ddeff7a88a7c | note | RESPONSIBILITY: Fulton Hogan Engineer
ef89427a-bb43-5089-937f-7e7a189434bf | note | – – – – – – – – –
66da27ff-0089-57c8-9f58-a6965993a737 | textbox | DATE:
4f89b89a-00f0-4195-a3cc-bba2f78d9c0e | checkpoint | 2.3 Grout Installation
f1ed2d1a-7751-526d-b470-5ee918d217a8 | note | FREQUENCY: Each Lot
2b09bffa-a8db-54b4-bcf5-b1589c8bee87 | note | – – – – – – – – –
cd86ca79-826a-51cd-b62c-2c2c1fa17ad7 | note | ACCEPTANCE CRITERIA:
cdd3f2c0-b4f6-5bbb-ad72-a7a070f6add1 | note | • Footing surface shall be cleaned and roughened before application
1cb0f493-6677-589e-a1db-324943c53ee2 | note | • Non shrink dry pack grout shall be placed under base plate where applicable in culvert area and footpath areas
e144a408-3951-50be-a2c7-d8cfbeda4cc1 | note | – – – – – – – – –
ff9e2383-7eed-50ff-b5b6-da3d4bc18439 | note | REFERENCE DOCUMENTS: AS1554
26d3c6fb-6235-5513-83eb-e0d8b5edf1e7 | note | – – – – – – – – –
51c69164-3b96-52c9-b74b-b7a166a4ef15 | note | INSPECTION/TEST METHOD: Visual inspection
a87375ee-1eba-5902-bbe3-6043f2da4e99 | note | – – – – – – – – –
249b4da6-d27a-56e1-8f1a-583f1a40e7f1 | note | RECORD OF CONFORMITY: This ITP signed off
6825e157-6a80-5897-91a5-ccfefa83e10c | note | – – – – – – – – –
4d572e19-c800-54cf-95fc-17b5a821db2a | note | HP*
01244a19-0777-5a42-8b29-59d851cb924d | note | – – – – – – – – –
a12a7f3f-43fa-515a-9109-72c32ad34967 | note | RESPONSIBILITY: Fulton Hogan Engineer
d1c90c77-962c-561c-ab03-5ef6d71fed90 | note | – – – – – – – – –
6f8c47f1-53ac-55c6-a9a3-d5d2da1f265d | textbox | DATE:
a5dd109c-1f7e-459e-9bd7-e4375e036729 | checkpoint | 2.4 Chainwire mesh fence
1002f855-b02c-5804-8d2b-6792c4aac917 | note | FREQUENCY: Each Lot
91a72135-af15-509f-b6bc-1c3119705826 | note | – – – – – – – – –
b46ad6de-00ea-5563-b13b-8a21813ecbae | note | ACCEPTANCE CRITERIA:
fda2538f-903c-55db-a028-93e6c956a4a9 | note | • End, corner and gate posts shall be braced as shown on the drawings.
dbbc5039-fc23-5074-a8bd-53e83b34e422 | note | • Line posts shall be braced as shown on the drawings at not more than 120 m intervals.
b29783c7-499a-5891-8553-d1f2a5099267 | note | • Chain wire shall comply with the requirements of AS 1725.
82441f78-3a30-5334-a635-af3bb6b42f0a | note | – – – – – – – – –
c0984fe3-947e-5846-8ca6-43ea9b47cba5 | note | REFERENCE DOCUMENTS: 704.04 (d) AS1725
0b6849cd-6dde-5169-b9b6-4a6342fd316f | note | – – – – – – – – –
2685a278-cb2a-5756-8a47-badf28b94528 | note | INSPECTION/TEST METHOD: Visual inspection
389cea7f-75be-5275-a083-190b4f94c25b | note | – – – – – – – – –
11c5107b-05d2-537c-a6c0-37719641e02e | note | RECORD OF CONFORMITY: This ITP signed off
a84491ea-1c54-57d4-a845-afb03ed4ec75 | note | – – – – – – – – –
35eda9fa-0b31-53a0-bd51-518271cdadfc | note | HP*
decbea9d-f97f-59c8-b875-2023401d2097 | note | – – – – – – – – –
409fb0f8-1563-56f8-8682-3e8c8510fa1d | note | RESPONSIBILITY: Fulton Hogan Engineer
71f8f842-2ca1-59c4-b8a4-ad6e6fca3d12 | note | – – – – – – – – –
aebbc686-a685-56d8-a1ff-4779a31eca52 | textbox | DATE:
3644088e-e87f-4566-b4f1-24f0a117ec57 | section | 3 - Completion
6b9cb749-1374-454f-af0e-e6fd4a089e80 | checkpoint | 3.1 Clean up
4c4d4c55-e1e8-559a-8a8d-8f77ffe2ce02 | note | FREQUENCY: Post Completion
8d73b56d-ef57-547d-b5fe-46836830a4c8 | note | – – – – – – – – –
ba2e606c-72c6-5abe-a0e8-b235d7b34595 | note | ACCEPTANCE CRITERIA: Personnel to ensure all chainwire is tied off and that work areas are clean and free of excess materials
951f4ee8-42fd-5991-b792-f766734e104c | note | – – – – – – – – –
298d6dd6-a7a2-5a8d-8f20-5ce543190bb0 | note | REFERENCE DOCUMENTS: Fencing Plan
b24faa81-5675-5d65-8e14-bb707429fdd5 | note | – – – – – – – – –
dbf89490-b6e5-521d-b9f9-70e569d64647 | note | INSPECTION/TEST METHOD: Verify
1be44143-7faf-59f1-9f17-ee041147d755 | note | – – – – – – – – –
2bd96166-a2af-5ce9-aabd-1c8207ff0504 | note | RECORD OF CONFORMITY: This ITP signed off
7bcf9b97-8b8f-5e75-86dc-bfb8e9b181ea | note | – – – – – – – – –
4ebad3b4-ea5f-59db-b33c-98636af54ddc | note | SCP
9c5619d2-40e8-56af-a5cb-853f7b727940 | note | – – – – – – – – –
3590557b-f02b-51d6-a2de-9a564ddd2584 | note | RESPONSIBILITY: Project Engineer/Surveyor
0820889b-f919-58a6-a86c-963493017ca4 | note | – – – – – – – – –
3e9cb58e-99bc-5bfb-a41b-8cf0485dd356 | textbox | DATE:
ca63353d-ffdd-428f-9c79-cbb08c07f9f0 | checkpoint | Final Inspection
bdec26c8-79df-51be-8c42-072e7f4a00ee | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
17b52110-958a-539f-a811-490d648495e0 | textbox | Print Name:
584a0eba-f46b-5fe7-93e6-c2bb3bbe3376 | textbox | Position:
4e94b0d3-3d2d-5d63-968e-beeec546b683 | textbox | Date:
cacce97d-28a9-4417-9680-fc25f7eed288 | checklist | ITP-01-029 - Farm Fence Installation |  | ITP-01-029 - Farm Fence Installation
f0523b33-af34-41a0-9eef-8969751e77d8 | section | 1 - Preliminary Works
19952b4a-4e31-4754-9b22-b7a08ac53b97 | checkpoint | 1.1 Check for correct documentation
838e2108-8475-5a3b-b2a0-7cd0718ae7c3 | note | FREQUENCY: Prior to commencing any activity
dce5a3a8-ac51-58d5-937f-dc461b3c8168 | note | – – – – – – – – –
cf63395b-134d-5ed0-9820-ac946c575ebc | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
36882f4b-e6e2-56a0-ae65-fc253f233498 | note | – – – – – – – – –
1423657f-b780-5697-b397-ab5200aeb8ca | note | REFERENCE DOCUMENTS: Drawings and drawing registers
5cac44f2-2828-56f9-b254-f0e39d101650 | note | – – – – – – – – –
3e9fad2f-84da-5a97-824c-8aeeb7c061aa | note | INSPECTION/TEST METHOD: Visual inspection
de3ff502-0cda-598d-813c-ded7e7c5ed34 | note | – – – – – – – – –
8562c580-e99b-5a66-8787-69ac7028e2ee | note | RECORD OF CONFORMITY: This ITP signed off
4b2fdd59-513d-50e7-a822-4f306519df23 | note | – – – – – – – – –
f430b49b-077a-52ce-b86d-01e1417638fc | note | HP*
b2facecf-1720-53db-bb91-023229307707 | note | – – – – – – – – –
036f77f0-9619-54cf-852f-6d22699caf95 | note | RESPONSIBILITY: Fulton Hogan Engineer
978baef9-37aa-53ca-8fd9-96b3669e3e44 | note | – – – – – – – – –
12ccdbea-bb74-5359-9050-1a01fe4f665b | textbox | DATE:
143f3965-fbe6-4d5e-909a-cf27ea3dc30d | checkpoint | 1.2 Implementation of all measures and controls
428cd251-5c38-5c6e-8542-f28df359d94b | note | FREQUENCY: Prior to commencing any activity
1333d11f-61ae-51a8-8b08-5e3ae9067c68 | note | – – – – – – – – –
fd01bb1b-0999-5b40-96c8-f1a1b99f4bfa | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
bcde99b8-d7d4-5f25-a5ac-ca4a546faf03 | note | • PSP, EMP, TMP, JSEA, SWMS & WP
3dafd185-746c-5c92-8147-0eef8a25f48b | note | – – – – – – – – –
375c4678-b4e9-5567-9bf6-f686bb8de982 | note | REFERENCE DOCUMENTS:
fdd3b653-01dc-5eb9-93da-bf1d9cc77bca | note | • PSP
3fef48d3-7abd-53ed-953a-6f98803ad35c | note | • EMP
18bc670c-050e-5b90-ac60-f6dd450d2ec9 | note | • TMP
2b974ebb-c0af-5e41-8e05-01afd32ed37c | note | • JSEA
eb067cd0-487a-5138-aaed-8047d4e18bb1 | note | • SWMS
c5d102b2-5241-5e2f-85b3-45ca8db0effd | note | • WP
3d4d9574-e40f-5852-8c6c-3ff66bb97e55 | note | – – – – – – – – –
eecfe52e-f899-5a1f-825b-32e97bb1d71d | note | INSPECTION/TEST METHOD: Visual Inspection
f44f7ff7-ed05-537d-9d04-b29ac1f729c0 | note | – – – – – – – – –
db01d79f-4684-5416-8b50-3608b8fd35e1 | note | RECORD OF CONFORMITY: This ITP signed off
d410d75e-e709-52aa-b4e9-9ef53eccc68e | note | – – – – – – – – –
31455357-bf93-5a65-ba51-6bedb9f69b12 | note | HP*
384e7dc4-aa33-5f5b-b8e8-45649c667298 | note | – – – – – – – – –
635939e9-2f93-5f27-993e-b69aa80ce423 | note | RESPONSIBILITY: Fulton Hogan Engineer
ebf5daa9-3937-563a-9f9e-78fd8f888d14 | note | – – – – – – – – –
fe3fa9ec-8835-51d4-8164-e0909bdef7ff | textbox | DATE:
36e88c22-5ce4-4e47-98b4-09279b472631 | checkpoint | 1.3 Check Materials
4de8c8af-94c3-5cc0-8510-fe96ade3952d | note | FREQUENCY: Prior to commencing any activity
cc248f2b-eae1-5074-ac73-c4e9359a5ff0 | note | – – – – – – – – –
19381cbc-be5e-5988-b4ce-231298515727 | note | ACCEPTANCE CRITERIA: Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of this specification 707 and drawings.
af6cc3bb-0c66-5832-8675-ec0f2ea076d8 | note | – – – – – – – – –
297b2f0a-7280-5b5d-ac5f-bf30f310dc8d | note | REFERENCE DOCUMENTS: Fencing Plan
dd8705b6-820d-5e30-9a6d-fc5f4c72f434 | note | – – – – – – – – –
fd2080fe-cd2f-5502-8386-d3e6dc40f6ce | note | INSPECTION/TEST METHOD: Verify
d21151d1-3732-5a74-b15b-f2ad2fd4dd0a | note | – – – – – – – – –
3dbc1843-4ef6-5f8c-8fd0-ee8426518d91 | note | RECORD OF CONFORMITY: This ITP signed off
3a41abb8-363a-5317-9670-7a11bfa9ad04 | note | – – – – – – – – –
983ea606-9a43-5197-ba0f-63249765f1c9 | note | HP*
202799af-c1fd-59ce-83fc-7ff87b2d5598 | note | – – – – – – – – –
7ae31593-538a-5d01-9dbb-8fc10f8b0eb3 | note | RESPONSIBILITY: Fulton Hogan Engineer
93771200-b11f-5402-b0c1-30488eee1776 | note | – – – – – – – – –
cdc0777e-0ccb-5e6f-83b8-d0a302162ac4 | textbox | DATE:
c4313184-f499-4def-8bf7-1498c0ae59e8 | checkpoint | 1.4 Confirm Footings position
8eba2c7d-7200-573f-9cfa-dbee8df323df | note | FREQUENCY: Prior to commencing any activity
f2497fe1-d2c7-5087-934e-f5b9008da984 | note | – – – – – – – – –
3bc62e68-55f5-58e5-8edd-8c5bf6deefdb | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
1eaf7d26-0d85-5091-a5ac-2452ed08dff5 | note | – – – – – – – – –
240f6cf4-e27e-5825-9c2c-d289b4078e95 | note | REFERENCE DOCUMENTS: Fencing Plan
07b9bfa1-40e1-59fa-b603-ef9a44393ae6 | note | – – – – – – – – –
5aba3af7-35d0-5361-82db-2db6c82cec92 | note | INSPECTION/TEST METHOD: Verify
f7fabbf4-7ff2-562d-b699-565fa7bb8fb6 | note | – – – – – – – – –
47951527-a4ab-590b-baf9-4a256aa36410 | note | RECORD OF CONFORMITY: This ITP signed off
799cf674-1b68-5a99-9522-24153a05c075 | note | – – – – – – – – –
026ee41a-db13-5911-8c56-f91681d6eab0 | note | HP*
43901cd9-40c3-54bf-b2bb-8a0c76779e48 | note | – – – – – – – – –
530dabbc-663b-502b-8922-70865ad54c82 | note | RESPONSIBILITY: Fulton Hogan Engineer
6e47c469-b16e-5062-94bd-d5fbd81ffeb9 | note | – – – – – – – – –
07eea486-028a-50ab-8bb9-bffea5399c50 | textbox | DATE:
9525918b-0914-4298-82b2-a5d6c13d0935 | section | 2 - Construction Works
459e9e5d-634a-40b4-8b4d-7029ab80e5da | checkpoint | 2.2 Post Installation
f4f162cc-8b0c-5771-b0bb-f97f8109a23a | note | FREQUENCY: Each Lot
b11eb978-4c26-5a58-8b54-cfb1e5103f7a | note | – – – – – – – – –
25ba3409-678d-52c1-8eb6-e3c1cef4e263 | note | ACCEPTANCE CRITERIA:
e47f8c0e-1fca-55df-a78d-a60877d39772 | note | • Timber and concrete posts shall be set in dug or drilled holes
7a6bb60f-a444-5478-9d58-b053dbe76ef6 | note | • Posts shall be set solidly and any space left around the posts shall be backfilled and the backfilling compacted.
5ba0dd9c-2d50-57eb-8aa6-024a9565db8c | note | • Concrete Shall be 20MPA strength grade complying with the requirements of AS 1379/1991
8ef18eb2-d521-5c5a-9112-c2cdfe5cc191 | note | – – – – – – – – –
db86de71-7b10-5b35-a061-c549053ae614 | note | REFERENCE DOCUMENTS: 704.04 (a) AS1379 SD3161 Fencing Plan
0f5ca0ea-141c-5cea-82df-ee9a6ebb4413 | note | – – – – – – – – –
4541b3b7-ad08-51d7-905a-3079b60bf375 | note | INSPECTION/TEST METHOD: Verify
10a8037a-e722-59ec-91b9-4efafbe18b63 | note | – – – – – – – – –
0359b540-957b-56db-8151-bd5c386aede2 | note | RECORD OF CONFORMITY: This ITP signed off
3112abd3-b057-5413-a9f4-b0e057866a18 | note | – – – – – – – – –
391bc89d-88a0-5eb0-b859-0c4af6940b74 | note | HP*
12567950-f56f-543a-954a-258922dd1ae6 | note | – – – – – – – – –
fd5989b0-49b5-56c4-823c-177b1467c3ca | note | RESPONSIBILITY: Fulton Hogan Engineer
117b51c9-03d9-55f4-8d0d-b8e01231223c | note | – – – – – – – – –
009eeeb2-50b7-5215-a79a-7ecb32a319c4 | textbox | DATE:
33034e86-28f0-4870-9561-c7a667a36fbf | checkpoint | 2.4 Strainer Assembelies
1534cfef-5d46-562c-9050-17e735244c73 | note | FREQUENCY: Each Lot
80b601d2-5cbf-5f93-afde-ab4f94944848 | note | – – – – – – – – –
c3753f25-6624-5e6c-baab-1facfc33d55d | note | ACCEPTANCE CRITERIA:
0114b466-e9c5-5e92-ab75-7d6713ce8910 | note | • Strainer assemblies shall be provided at all ends, angles, abrupt changes of grade, and intersections of cross fences as shown on the drawings.
0fcb8108-c739-50b1-add3-5144d70ec3ad | note | • Intermediate strainer assemblies shall be provided on straights at intervals not exceeding 200 m, and spaced to the best advantage in the circumstances.
9641f67f-ac72-52b7-8522-0ae2805306d0 | note | – – – – – – – – –
c371b4a3-f09a-5ea2-9819-1cad0c44a075 | note | REFERENCE DOCUMENTS: 704.04 (a)
829518f1-1f58-518e-b65d-3ff14f9cbe84 | note | – – – – – – – – –
3d42569f-85bf-50b4-ab81-3b361c4fdbee | note | INSPECTION/TEST METHOD: Visual inspection
8f3cbba7-5f3b-5ff7-99ab-46ce64a8ca4b | note | – – – – – – – – –
f75fbd6d-7d67-569d-b216-f0de6c282921 | note | RECORD OF CONFORMITY: This ITP signed off
95f75e34-01d4-5247-b7d1-a7d34cf21074 | note | – – – – – – – – –
4f1d1e6f-e4ea-54ff-b49e-98196332d943 | note | HP*
a11b0055-19dc-55a6-b974-bf6d149a6516 | note | – – – – – – – – –
b2f0af7f-c8d7-54dc-a280-236cc8660fd7 | note | RESPONSIBILITY: Fulton Hogan Engineer
08a4c7f2-0301-5170-b253-c358e56e9e41 | note | – – – – – – – – –
bf380179-843a-5616-9d6f-173b763e369d | textbox | DATE:
6942df83-29d8-48d0-905f-f01197af56f2 | checkpoint | 2.5 Strainer Assembelies
0621b36a-cdf8-5100-86e6-be6ee6a7744e | note | FREQUENCY: Each Lot
1130626a-8666-5694-94e4-246ff5993c47 | note | – – – – – – – – –
fe92779c-3f77-50b5-b52e-637a97a5c9b5 | note | ACCEPTANCE CRITERIA:
22021534-eb69-56d0-b2bb-f1fe2690e18c | note | • Plain wires shall be reeved through holes drilled in the posts except that where treated round posts are used wires may be attached with staples after straining.
c4ed371f-e082-5f55-972c-f7f86d093c27 | note | • The length of staples shall be 50 mm for pine posts and 40 mm for hardwood posts.
df054998-7203-5d50-ada1-0b66d220d6da | note | • Barbed wire shall be secured with galvanized tie wire of not less than 2.5 mm diameter passed through holes bored in the posts, and twisted to the barbed wire on each side of the post, or shall be stapled to treated posts with staples.
2b1e91b2-66a4-53a1-9c1e-c7e74f102dee | note | – – – – – – – – –
2fa1da09-0a2b-5813-bd22-aa19a14537d6 | note | REFERENCE DOCUMENTS: 704.04 (a)
ca747437-b688-5b87-8f8b-d1900856c853 | note | – – – – – – – – –
d31e0f27-18dd-572c-9ed2-7d5e50493074 | note | INSPECTION/TEST METHOD: Visual inspection
c760c49c-ff7a-5fdb-8c6d-3584ce7b4ea8 | note | – – – – – – – – –
93b34d31-2650-5a8c-b451-c70cde01c361 | note | RECORD OF CONFORMITY: This ITP signed off
a7f3275f-8229-5860-b13c-2223572a6ccd | note | – – – – – – – – –
1dee8c35-75f6-5290-8e40-d1027a2dd063 | note | HP*
be0638a7-ceab-5fa7-a43a-b0a2df8db77b | note | – – – – – – – – –
dd3c49cf-6ced-55b2-86bc-e212b40adc51 | note | RESPONSIBILITY: Fulton Hogan Engineer
23353119-8197-5c16-8c1f-9e3bec888993 | note | – – – – – – – – –
5c6228be-5fee-55d0-8c88-b3537874a8af | textbox | DATE:
d04364ad-a6aa-4b98-9555-72f9105159fa | section | 3 - Completion
51d00d28-9eff-44a9-85e0-413c95026078 | checkpoint | 3.1 Clean up
8a0385b9-5cb3-5eca-8591-a64776d38c42 | note | FREQUENCY: Post Completion
d5808d4b-f3e3-53f2-918a-88f00de787e7 | note | – – – – – – – – –
fddc933e-7c69-5bda-b675-8a1a97d8a76f | note | ACCEPTANCE CRITERIA: Personnel to ensure all chainwire is tied off and that work areas are clean and free of excess materials
553a68a6-6654-5035-b52c-45f4ecef5ced | note | – – – – – – – – –
2c79ca07-7d4a-59bc-a80b-ccb8f11d1781 | note | REFERENCE DOCUMENTS: Fencing Plan
c8fcd112-31e2-59b1-b53b-de47e52093ce | note | – – – – – – – – –
970a4dba-15f8-53b8-95bf-cf39d34da70c | note | INSPECTION/TEST METHOD: Verify
bde8f816-2785-56e6-adf0-6c143d121829 | note | – – – – – – – – –
7b5e73b3-a81d-52f8-9b25-0c730161a077 | note | RECORD OF CONFORMITY: This ITP signed off
af07e21f-fabc-5a9d-8385-3cde8235dd2a | note | – – – – – – – – –
fa2209db-2f0e-5a7f-857d-7127be061f9c | note | SCP
76d8df96-2ea3-50d8-a718-c1453e92522e | note | – – – – – – – – –
e5d2752b-5c44-5494-8a59-bd8b3ace9d03 | note | RESPONSIBILITY: Project Engineer/Surveyor
fb3c676f-2807-5f45-9176-68857db64318 | note | – – – – – – – – –
b0aae3c3-a993-5249-b111-6b1c70c9f2ba | textbox | DATE:
8f0df819-2590-475f-a02f-0a7f351e938a | checkpoint | Final Inspection
bd61b43f-7a58-51fe-9502-51125dc2b2d4 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
983849fd-596b-530f-8cf5-d87900600a15 | textbox | Print Name:
4e9177e5-1ac1-5f36-a2b0-a0699739e85d | textbox | Position:
10cf9922-ad3a-5259-8ebf-8a7955bcbd8a | textbox | Date:
7ca25c5a-a1d6-4c3a-addd-37e25a7f901d | checklist | ITP-027 - Pile Footing Construction | itp | ITP-027 - Pile Footing Construction
87e7a4f7-642f-4d00-baca-bdee169a10b7 | section | 1 - Design and Submissions
31b861c9-2413-46cb-a386-b44b9aac953f | checkpoint | 1.1 - Check for correct documentation
a47e0284-119b-5b0c-9e68-b7054f5f9fff | note | FREQUENCY: Prior to commencing any activity
17bca5d9-d821-59ed-9e7c-ea60037527aa | note | – – – – – – – – –
fed40b45-3660-5816-9728-651c912b02af | note | ACCEPTANCE CRITERIA:
bce033b1-984b-5fe7-b37e-984930f6b907 | note | • Ensure that all employees and subcontractors are:
d68f53a0-eb3d-5b7d-9216-8c5ed2a92242 | note | – using the correct and complete set of drawings
c91fa48c-7f1f-5d5e-b882-54255f62979a | note | – all drawings are the latest revision
a6c58ace-9735-5135-9381-ea1804da0a85 | note | – – – – – – – – –
83005f64-cb61-5ad0-b1b3-c79da3e37841 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
bfdf2dee-b7e4-5f78-9bf1-b6505d108753 | note | – – – – – – – – –
12e75903-9a04-5b59-b189-3faa6f8fb790 | note | INSPECTION/TEST METHOD: Visual inspection
b25cec4d-6f1d-5ce8-928c-2ee64816ecba | note | – – – – – – – – –
8d5d078d-c543-57c8-b3af-26c3b5a96d84 | note | RECORD OF CONFORMITY: This ITP signed
cea6d28d-d8a8-5a11-ba5a-8a57b5b6b84d | note | – – – – – – – – –
297ca5aa-8326-59f4-a68c-8360feef79ae | note | HP*
05d7cd71-72c1-5dda-b995-8d68f520ad2d | note | – – – – – – – – –
a1d70827-f3df-5ff9-a83a-7beab878a414 | note | RESPONSIBILITY: Fulton Hogan Engineer
45395891-3f4c-5579-8f98-d57fff6ccb55 | note | – – – – – – – – –
55916cb6-726f-5f44-b031-690ae8dc4689 | note | DATE:
b302cc1f-9734-43b3-9337-e75c4a341276 | checkpoint | 1.2 - Implementation of all measures and controls
be7b4b49-c9d4-5c79-943f-cc8095fa6635 | note | FREQUENCY: Prior to commencing any activity
79ec7d21-b5db-51f5-bff9-e9e4de756413 | note | – – – – – – – – –
fc49fe0f-5c0e-525a-8f4d-74b701fb5a31 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
757ef258-1bd7-5906-b06d-b9e1891d8fea | note | • PSP, EMP, TMP, SWMS & WP
27e46e84-55c7-573f-974c-3371759e3548 | note | – – – – – – – – –
acd886cb-83e9-574d-be14-f046fac52211 | note | REFERENCE DOCUMENTS:
54e3903b-7174-5297-9a9c-a1eb908abea6 | note | • PSP
5b969021-6fcb-5d56-9269-1e2dedc022cb | note | • EMP
8805ba51-c498-523f-8b2e-4be02f24beb1 | note | • TMP
ed53a502-0fe0-5004-9677-74deec7cdd98 | note | • JSEA
1722a2cb-b022-5d7a-a119-ad54b75f632d | note | • SWMS
cc31c91c-3eb0-56c3-9e8b-252d9113ac62 | note | • WP
9e8352c7-1bc6-5547-911d-aa300bb1ebf3 | note | – – – – – – – – –
0fcb2f17-8aed-5959-a664-815477ace637 | note | INSPECTION/TEST METHOD: Visual Inspection
9413a2e4-e549-5eee-939f-bd87cc825a5e | note | – – – – – – – – –
0589061e-0d14-50ab-8f40-8d0e7c554ecb | note | RECORD OF CONFORMITY: This ITP signed
be50dcd8-9891-5cae-b29c-4b01bb1d8b32 | note | – – – – – – – – –
d6c7c008-e9a1-5312-af93-7e60dda61bdb | note | HP*
93f46a4c-92e4-5cd9-a1c8-1a65253a436e | note | – – – – – – – – –
eb637fda-35a4-5b04-94bb-0bf5d0423e5b | note | RESPONSIBILITY: Fulton Hogan Engineer
c01c8757-1b69-55ee-bdb3-c95dd57f2555 | note | – – – – – – – – –
d451ea2e-0454-5ffd-bf74-0119a1492f9b | note | DATE:
f5ffbb29-54e5-4bff-93ef-f8c368baf550 | checkpoint | 1.3 - Approval of mix design
6e65f786-9f38-51ff-8422-97244c986b63 | note | FREQUENCY: Prior to the first concrete pour
a64b9f94-3421-57a8-8a35-3f99e4119086 | note | – – – – – – – – –
955950ae-a56f-5914-8f7b-d901fb78c209 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
9f872ff7-efe2-5f06-a2b4-8a327aaefe56 | note | – – – – – – – – –
0051bb90-95d2-542b-bec6-168de255f426 | note | REFERENCE DOCUMENTS: 610.07
8c8bc8c5-30ab-5b55-a40e-c7f9925499a1 | note | – – – – – – – – –
2f292ca3-9fab-503e-bea0-39fd057a31e1 | note | INSPECTION/TEST METHOD: Verify
e0e0102a-e002-5650-8b9e-5752ef2edaf2 | note | – – – – – – – – –
0783a4d4-a475-51ce-84a0-b4e9590c0e98 | note | RECORD OF CONFORMITY: This ITP signed
ffabcdaf-60a4-58a1-9d4c-8770c46b62dd | note | – – – – – – – – –
36a99c4e-159b-5f97-a09b-a60d52819fd6 | note | IP
13cbc6eb-3430-5380-9348-daecd9fe0649 | note | – – – – – – – – –
3bcfa5a7-9a7a-555f-bad2-32f7d21a446d | note | RESPONSIBILITY: Fulton Hogan Engineer
bdd4b106-598b-5f84-989e-372be55fa2b5 | note | – – – – – – – – –
c14e5c4c-2f71-54b4-bc43-3f6512f30556 | note | DATE:
be02e6d4-9931-41c3-9567-4bc304f57399 | checkpoint | 1.4 - Reinforcement schedule
cf001b9c-456c-5e27-99bd-f04dedba946e | note | FREQUENCY: Prior to concrete pour
eda2aab0-7617-556f-9288-d5407a8911be | note | – – – – – – – – –
e89c3429-cef1-546b-9f1b-af246e55affd | note | ACCEPTANCE CRITERIA:
a3377096-cb32-51cf-8494-c9b807d900f0 | note | • Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
aee51973-3bf9-5c24-8643-9e922f42b944 | note | – – – – – – – – –
e0273bd1-7c12-511a-9f1a-e56d9f014159 | note | REFERENCE DOCUMENTS: 611.04
3b5b588c-3c46-5150-9f8e-3521c031e55f | note | – – – – – – – – –
2be6bb61-608c-51d6-b277-fc4ecbd334e5 | note | INSPECTION/TEST METHOD: Verify
d88c7f69-0490-52c5-ae3d-206dcfadc96f | note | – – – – – – – – –
49688ba5-d5ee-5fa4-a564-96687c645af5 | note | RECORD OF CONFORMITY: This ITP signed
4f2919b0-15c9-5f48-a2ef-ddf7140a59ba | note | – – – – – – – – –
535b4bda-0fac-5a05-9c50-24a2eebd4d61 | note | IP
4e461fad-75b8-5890-a045-e0390b3d1173 | note | – – – – – – – – –
56229621-9ba8-5ea0-8bef-9396367f6fda | note | RESPONSIBILITY: Fulton Hogan Engineer
b3d4a986-e871-5e2c-8889-3697605ced58 | note | – – – – – – – – –
6d607916-a535-5306-b872-4d4c478dbc54 | note | DATE:
5bf40764-0522-4e6d-82a9-ec3a8cc69b37 | section | 2 - Construction/Erection of Formwork
326c22a6-4e4d-4530-8db2-94badd9ca4f6 | checkpoint | 2.1 - Excavation (Pile)
985817e0-df9f-55d5-9d1a-2a53e6aadb9e | note | FREQUENCY: Prior to concrete pour
1d7f0ee8-0345-5bfd-aed9-5901a88c2b93 | note | – – – – – – – – –
777ff433-ed23-5855-b242-9bf4f6327f36 | note | ACCEPTANCE CRITERIA:
24512d1d-1f42-5db5-b98e-c8054078a20a | note | • The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent.
f44078f2-e5f2-55fe-9c03-f7db101eeae1 | note | • Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
8ecb3909-a377-5ef5-b5b4-64653406abac | note | – – – – – – – – –
4c5e5477-8837-5b32-bfed-9205b645fd69 | note | REFERENCE DOCUMENTS: 606.05
2a2fae3e-ef38-50fa-ae00-a72277ae3fb9 | note | – – – – – – – – –
6550cb96-2a92-5cf0-b87d-c2c462b0af3a | note | INSPECTION/TEST METHOD: Inspect
f70f2e65-6f3f-5d1f-b74f-0a60903a6689 | note | – – – – – – – – –
2df1946d-8ac1-5931-8f86-cd8c879955c9 | note | RECORD OF CONFORMITY: This ITP signed
934aad7d-6f95-5c4b-b29a-25499a7b2230 | note | – – – – – – – – –
55b25724-afc0-5f79-aa84-e647c7e1d513 | note | HP
62114f8c-ea11-5970-adbd-c966c787e911 | note | – – – – – – – – –
bc62dd4d-8ef9-5ea1-8d33-36410f1676bf | note | RESPONSIBILITY: Fulton Hogan Engineer/Suprintendant
eebc8077-66b7-56e6-8691-9fe654b791ba | note | – – – – – – – – –
16be4dab-67e2-5b56-81ed-ce434495fb7a | note | DATE:
f8a2b0a7-26ea-48a1-bc35-df077ab0ef3e | signoff | HOLD POINT AUTHORITY
6ccf1a50-b12c-49f8-955b-3f7919e8a57a | checkpoint | 2.2 - Construction Methodology
37837c08-0e4c-56fd-802e-15e608b57b12 | note | FREQUENCY: Prior to erection
74150521-ecdb-54d1-bce6-0e77d846792e | note | – – – – – – – – –
dd1237a5-4e43-572a-baf9-a5b3630f7ceb | note | ACCEPTANCE CRITERIA:
f3d6b1dd-83f1-5fb1-aa6a-95190a9e2f4e | note | • Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
2895a4e0-d414-5c1e-aca0-573789a0e225 | note | – – – – – – – – –
48488d02-7a37-5780-93e2-7550985bfd5c | note | REFERENCE DOCUMENTS:
659caab8-1735-5095-9933-8fa6f1e603ee | note | • 614.04
c8f848da-2f78-533c-a335-c1f2e2432bfb | note | • 614.06
d4a9cd50-498f-5dd7-bf34-9fb0407dd357 | note | – – – – – – – – –
fff695ea-90d3-562b-8922-9b9f3ddf606a | note | INSPECTION/TEST METHOD: Verify
9004854d-7107-57d7-99ae-1c42415750ff | note | – – – – – – – – –
39593ec5-7bd3-5b07-9d68-744352b56573 | note | RECORD OF CONFORMITY: This ITP signed
ed75e33b-32c9-53f1-b6b6-2bf6bd56a934 | note | – – – – – – – – –
b38e2209-22ee-5883-860b-385f501a64e9 | note | IP
f0665457-18fc-50e9-80f9-cac1bfca32f9 | note | – – – – – – – – –
eebf8e6c-0169-51f4-a6e0-f390ceed9abd | note | RESPONSIBILITY: Fulton Hogan Engineer
a9c56a51-5df3-56cd-8c7f-4ad20f43ffbe | note | – – – – – – – – –
e6479d4e-5eb2-5598-93c9-dcdb11b9fa0e | note | DATE:
8228bfb6-d420-4071-a107-bf67e698deef | checkpoint | 2.3 - Construction Methodology (Pile)
7ec73a1d-44f5-52e8-aa0c-38c4a1b912e2 | note | FREQUENCY: Prior to construction
c3bb18c1-6009-55e1-b809-e416dceb773f | note | – – – – – – – – –
2bd3c6d8-fc1b-5083-9948-ebb498ac7ae0 | note | ACCEPTANCE CRITERIA:
4a5e4fd1-93ba-50e4-833e-3252cc2c062a | note | • Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
ae3d7c30-673c-5965-9abf-0060bf54a8bb | note | • Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
d21d6bb9-50c2-5138-9f51-73f7704ccb61 | note | – – – – – – – – –
cd3aad60-8adb-514d-96d2-7739ffa3dac8 | note | REFERENCE DOCUMENTS:
7807a2c2-da54-5db2-b738-e1eb7d98f0db | note | • 611.10
9f821922-a9e8-5359-befd-1e4e292a03e0 | note | • 606.06
cd70367e-e420-511f-9b3a-82189dccbb18 | note | – – – – – – – – –
35a2f640-9446-52a8-91ca-d9edfb10b6fe | note | INSPECTION/TEST METHOD: Verify
656d084b-c991-5ff5-86b1-3c74db70eec8 | note | – – – – – – – – –
db0a1329-f9c3-5d2b-aa53-e474811d5a29 | note | RECORD OF CONFORMITY: This ITP signed
0e31110c-5d2d-5eec-90df-04bbe2d90e43 | note | – – – – – – – – –
db757d5d-9a0b-56c0-9a39-2efba6327cd1 | note | IP
3ab8a309-c077-5b23-93ed-ab9d94521cd2 | note | – – – – – – – – –
5bbd7e13-2d0d-579e-b84d-e1e9e9f2dcd5 | note | RESPONSIBILITY: Fulton Hogan Engineer
8bffe551-d2ca-5c3f-aa70-2f6859e9917a | note | – – – – – – – – –
debba083-071f-59bf-983a-5dde48d7f622 | note | DATE:
6acff48f-e494-46f7-9088-54cf9ded345d | section | 3 - Pre-Pour Planning and Inspection
75b2a590-7648-42ec-b5d5-e8741600d8d2 | checkpoint | 3.1 - Cleaning formwork
34d7e357-bff5-5e57-995e-79cbe2d00760 | note | FREQUENCY: Each concrete pour
eaded495-cac0-5de4-85a1-ad144d48142b | note | – – – – – – – – –
e6af578d-5bb5-5d3f-8270-ca5ca7aa87d5 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
8c3b9939-87a2-559c-84b5-7451727ac7b3 | note | – – – – – – – – –
d3de7977-1e52-5ac3-a9b4-374259908a6f | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
c676a4f3-11c2-5fca-8272-fefe2c72d20d | note | – – – – – – – – –
a7255f79-cf0b-5d6e-8096-90de1cb7e0eb | note | INSPECTION/TEST METHOD: Verify
9f2fdb8f-a4ee-5827-acf1-3c626ea18faa | note | – – – – – – – – –
444ca461-331b-5718-9a3c-1cc444af496e | note | RECORD OF CONFORMITY: This ITP signed
62afca2b-64f8-5b5e-a546-84487013a814 | note | – – – – – – – – –
8f28280b-694a-576a-aa04-dd8d3b78ef94 | note | IP
9934856c-9148-5f82-910e-d2e004119593 | note | – – – – – – – – –
07d64dc2-08cf-5c3d-9b9d-8f3bae6f21dc | note | RESPONSIBILITY: Fulton Hogan
3db65267-4ea3-5d4e-8040-5a77752b64a9 | note | – – – – – – – – –
51c59218-7434-5e1c-8794-ed3098e05d84 | note | DATE:
95a214fa-d136-4d7a-983e-23eb01c9a318 | checkpoint | 3.2 - Correct forms, reinforcements, rag bolt assembly and embedments
607840f1-4fe0-586c-a219-279a1ff1eb30 | note | FREQUENCY: Prior to concrete pour
de2d2a26-46dc-5570-b848-41152f19ff9c | note | – – – – – – – – –
69109387-d8ae-5043-8302-ec905374926c | note | ACCEPTANCE CRITERIA:
62e79e1f-ae26-5b13-9b44-86fb85f7b744 | note | • Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
bd616c94-1a49-53c6-b208-eff30b25804c | note | • Pre-pour checklist completed and signed.
18586d37-083b-548f-beac-ffcec3565a9e | note | – – – – – – – – –
6e89ef30-571c-5bac-bc43-15508e253ed3 | note | REFERENCE DOCUMENTS: 610.18 (a)
4491f319-1d5d-506d-94a1-79b2b362e946 | note | – – – – – – – – –
d2525927-44e8-595e-8372-250970517780 | note | INSPECTION/TEST METHOD: Verify
47d4c115-5302-57c1-9718-163d2b110afb | note | – – – – – – – – –
af7c5ad2-70a8-52aa-8ee7-b80da33f2c26 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
84b4efb8-b4e1-59a3-980c-dd92bb7f7598 | note | – – – – – – – – –
840d9193-8b4c-5a3f-955b-99fe043254ce | note | HP
e4a10c28-1f79-5832-abc3-fd94f5d29f4a | note | – – – – – – – – –
c5b2b857-a06e-512e-87b1-32209bad87c1 | note | RESPONSIBILITY: Fulton Hogan/Superintendent
e5f3f75e-cb75-5a8b-9b82-ca02b23887e5 | note | – – – – – – – – –
ff93054d-f2c6-5e70-ae55-3ced6d2edd01 | note | DATE:
97401815-4aa1-4c1e-a79a-45c145b6f5e9 | signoff | HOLD POINT AUTHORITY
d4dfddd7-1f59-4b77-a07a-ea294c615919 | checkpoint | 3.3 - Reinforcement assembly of piles
079e4cb7-0d79-54ec-8a47-5dff7f11286b | note | FREQUENCY: Prior to concrete pour
1dd8314f-bb8a-54e4-93ac-0ab93ef952d3 | note | – – – – – – – – –
6e7a1a41-04f2-590b-9dbb-32a47e9d635f | note | ACCEPTANCE CRITERIA:
f1d0b5be-4ad2-5b8a-b978-745fc5b83d12 | note | • Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
616d26d4-68e8-53fd-b624-76444f7b6ea9 | note | – – – – – – – – –
48fdcd80-d9cd-53e8-8e8d-8a3aab2b4709 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
18063cca-9f39-5d53-9fa7-d2b0e87faecc | note | – – – – – – – – –
ba356144-61c1-56c1-b078-bd43c222bfce | note | INSPECTION/TEST METHOD: Verify
2dd9e777-1bc8-5b6c-a829-79dda5e77574 | note | – – – – – – – – –
01a4534b-a632-5193-8c89-92b83359c2b5 | note | RECORD OF CONFORMITY: This ITP signed
51fb1bb3-3602-5b2d-b6cc-eebe401a6556 | note | – – – – – – – – –
ada27cb9-35b2-546f-af75-f9dcca3e61d1 | note | HP
944e6954-f938-529c-9cfc-7835ecdffcc9 | note | – – – – – – – – –
25d7ad1d-2435-590a-88d0-b59e4427fac3 | note | RESPONSIBILITY: Fulton Hogan
d60a6334-81a1-5507-96f3-09fd92da5bf3 | note | – – – – – – – – –
f98f502f-7187-59d8-8ec8-1babb6842fed | note | DATE:
b73b3a65-504d-49f0-a4d1-53aaa1928957 | signoff | HOLD POINT AUTHORITY
101529b7-c936-4991-a5df-b88235203403 | checkpoint | 3.4 - Monitoring weather
86ed4e2f-17bc-58d0-af30-3538d58888d8 | note | FREQUENCY: Prior to concrete pour
21e72d9e-9f12-5685-beda-851941efc5a0 | note | – – – – – – – – –
393215f3-fef4-5282-92cf-b1b5446e2b41 | note | ACCEPTANCE CRITERIA:
44746507-af43-5c94-8c54-460427fdc8c1 | note | • Concrete shall not be place when temperature is <5°C or > 35°C
887a09f8-3459-542c-855b-67db40db7db0 | note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
e5c53281-aef6-58fb-8622-3a7908905e9f | note | – – – – – – – – –
1d882d01-e8d2-5a9c-95db-e679915e7733 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
0711fd93-dcd7-5aa9-a43f-0ec59a1b99c7 | note | – – – – – – – – –
262c14f7-60d9-518d-921c-60861aeec506 | note | INSPECTION/TEST METHOD: Verify
73250da9-f54c-5ac8-8035-2f46e658b0a9 | note | – – – – – – – – –
4ef315e1-b0bd-521e-bdb0-fdef3c25e118 | note | RECORD OF CONFORMITY: This ITP signed
ca971a7f-d397-5545-bc40-571f96aa936c | note | – – – – – – – – –
bfa76078-7fa1-577b-b098-a2836651c949 | note | IP
949284fb-a129-51bc-88ad-67ff6a23d7aa | note | – – – – – – – – –
66e812eb-6082-5408-98a0-2937d7ff7504 | note | RESPONSIBILITY: Fulton Hogan
e93ecbcd-e75a-5aa7-ac81-7220c085e6de | note | – – – – – – – – –
337735a8-c27a-5d68-b8a6-0a682c78fc15 | note | DATE:
74a99e86-5336-49b6-8e56-f1cc0c08db80 | section | 4 - Placing and Finishing Concrete
da66ce20-c840-4479-a0b8-54cc2a6b0e69 | checkpoint | 4.1 - Carry out sampling of concrete
388eadb5-67d4-595d-b98c-e480d7e33976 | note | FREQUENCY: Each concrete pour
a8c945d0-86df-5f2c-bd54-595e3863bf8b | note | – – – – – – – – –
f8c9d452-8772-5c6d-ac84-000ea69d4da9 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
29e119c7-3a6a-5c1e-bfc9-973e358dbce2 | note | – – – – – – – – –
5c7a210c-ea7d-539d-9cda-4d0be36cdd66 | note | REFERENCE DOCUMENTS: 610.16
73958088-0bfc-56f5-9469-027044741dd3 | note | – – – – – – – – –
d41da003-e756-50db-98a2-60fa76cb9d7c | note | INSPECTION/TEST METHOD: Checklist
1f10261e-b974-5d9e-b89b-fc5216d9afbb | note | – – – – – – – – –
aed95429-7b0e-5721-b1bf-7ae66bd61344 | note | RECORD OF CONFORMITY: This ITP signed
9e5858d3-e010-5d99-bdb7-7198b0dd8ffb | note | – – – – – – – – –
298f8542-811b-5926-8658-1aa3d5934475 | note | IP
3d7690a1-e29f-5bd9-8528-992a8b6f7e6d | note | – – – – – – – – –
2312b038-38f4-5185-860a-261da1408750 | note | RESPONSIBILITY: Fulton Hogan
d0aa6ef7-6655-5f1b-9933-44e537e42185 | note | – – – – – – – – –
6af7148d-98f9-5e06-bdc7-7cca28dd6780 | note | DATE:
85008102-9e93-49a0-9c90-0ed7f86ab557 | checkpoint | 4.2 - Discharge time
71a5131e-8bdb-558b-9409-64e9d455597e | note | FREQUENCY: Each concrete pour
30e260ca-6575-518e-8a54-24350d781c9c | note | – – – – – – – – –
9d25a97c-85f5-5adc-82a4-7dfd35200439 | note | ACCEPTANCE CRITERIA:
80cbd33d-c3b0-54b5-a296-37d06288f2ed | note | • Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
a21449b9-7ba8-5aa0-98c3-5d1daeaa7564 | note | • Batch to be used has a discharge time of 180 minutes. Boral VR400/40 (SCC) (180min')
b1a88e21-7beb-552c-b563-58a37b30f1e3 | note | – – – – – – – – –
86630164-c270-5d74-8438-d68357b4d06f | note | REFERENCE DOCUMENTS: 610.13
1e6b7b03-e6ab-5c4a-b5a3-f64f9c49b755 | note | – – – – – – – – –
6bdef436-670a-5924-9799-f4b7acd61aa2 | note | INSPECTION/TEST METHOD: Verify
603a062b-3ffc-5019-b903-acec5cf97e2e | note | – – – – – – – – –
ca5009ef-7412-5c5b-90a1-2d1d1c2c5d3c | note | RECORD OF CONFORMITY:
dbd3998d-5096-5334-a8ef-f248a5237bbb | note | • This ITP signed
dc9509fd-b7dc-5c8b-b611-972ed20e70ba | note | • Accurate Site Notes & Load Mapping
d36b1567-f46b-52b6-b82c-37a3b21dc927 | note | – – – – – – – – –
ea3d319c-fac0-594f-ab09-e28fa8dfd980 | note | IP
2e2d8bcd-16c9-5a85-9bf3-165e65d8ac03 | note | – – – – – – – – –
17317bfe-7a05-57e0-ba0a-79a88d2dcca3 | note | RESPONSIBILITY: Fulton Hogan
4b2255fc-93dc-50f4-96f2-81fdb0fddd1f | note | – – – – – – – – –
c8dbfb91-33fe-50de-93bd-2452e5998c73 | note | DATE:
03e049c4-d74a-4511-8eb9-1d4d04ce9fd3 | checkpoint | 4.3 - Methodology of placement (structural)
d17cc8a3-6807-579f-bd72-28a045e0407e | note | FREQUENCY: Each concrete pour
d35c0bd3-d2ac-511c-a2b4-90f918b20397 | note | – – – – – – – – –
803288dd-cc59-5c5d-8618-02ee6070c5bb | note | ACCEPTANCE CRITERIA:
fe27834d-d7fb-56da-895b-d325c17a6057 | note | • Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
f8c37cdc-8259-5740-8e5e-614a5bc1774d | note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
1837e7fc-947f-57c0-8188-947ab273e521 | note | – – – – – – – – –
8f21bb05-61b7-51e4-acdc-0193b12176f8 | note | REFERENCE DOCUMENTS: 610.18
2d919e24-65dc-5cea-ba0d-549fba5979a5 | note | – – – – – – – – –
274dcb1c-6489-579a-bffd-9e55e325c2eb | note | INSPECTION/TEST METHOD: Verify
5c6a4dc1-b296-5261-96f5-0bd79e9cfba3 | note | – – – – – – – – –
5ff76ccc-498c-522b-94f2-fbd5a9797622 | note | RECORD OF CONFORMITY: This ITP signed
e9ca528f-5ae9-5323-ac2d-ce82131ca3fd | note | – – – – – – – – –
4ea1b228-cc35-522a-8de5-eae7efb8e0b4 | note | IP
237ffcfa-a8b0-5e97-a494-9bc8be4a7f20 | note | – – – – – – – – –
cca42ebd-f162-572d-b988-29c0026fac36 | note | RESPONSIBILITY: Fulton Hogan
401fcf53-bbf1-5fb5-9ed6-01757a9ba75f | note | – – – – – – – – –
da8d91f4-be6c-5934-8117-286dfc6a2bd6 | note | DATE:
5a3e41f1-1d05-416b-9a27-72df65a2398a | checkpoint | 4.4 - Methodology of placement (piles)
f48b6d3c-acce-5ef4-9cc2-42e4fcbfe929 | note | FREQUENCY: Each concrete pour
7a882ae5-ddb0-527f-ac2d-f8c93a81f8f6 | note | – – – – – – – – –
ccd1ae8d-c7be-588e-a4be-baed44c83550 | note | ACCEPTANCE CRITERIA:
d4a0e171-9605-5818-9cf3-e83b73e86402 | note | • Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation.
7f058d29-4901-512e-873f-a04cd4597753 | note | • Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
fe570654-1252-5167-9375-4de50a03de4f | note | – – – – – – – – –
32caa1b6-5c02-5e0c-8720-1f9e263363f9 | note | REFERENCE DOCUMENTS:
38905088-7a83-5c58-b429-9f2c8b2be3f5 | note | • 606.03(b)
a58bb417-732e-571f-a4f1-4a50864f5aba | note | • 606.05
15c1b392-aa9a-508d-a53f-4db2595a9880 | note | – – – – – – – – –
48a60e34-c4c3-5e73-9366-7a1e8206c02a | note | INSPECTION/TEST METHOD: Verify
3125ab9c-edbb-5bc2-aa49-7370fb0e32db | note | – – – – – – – – –
366b5e3c-d3f0-59f0-bfa9-4e25987561b2 | note | RECORD OF CONFORMITY: This ITP signed
f4b2074d-d87e-5f22-927b-d2ab298e3179 | note | – – – – – – – – –
ce8837c1-c66d-5f63-8d7f-a3b8cbe8d8ae | note | IP
8e38db6a-e915-53df-8d1b-d2a7c4beb62e | note | – – – – – – – – –
96e8f040-7531-5566-95c5-bd2456e1c1e2 | note | RESPONSIBILITY: Fulton Hogan
9ea6294f-571d-5581-9afa-4d69f760ef4d | note | – – – – – – – – –
6d672649-8162-562c-a5b9-fbfc2da06771 | note | DATE:
b584fdf8-3b70-45f9-8fde-ef1081b7cba5 | section | 5 - Post-Pour Details and Inspection
c3eda981-9c0b-44a1-b146-ca71a1b8144d | checkpoint | 5.1 - Curing
fe35fa98-1631-5438-aef0-5dd5fe143275 | note | FREQUENCY: Each concrete pour
38aa2ab6-5010-5f32-8de7-f7e662b5bd7e | note | – – – – – – – – –
dc1c4ebe-0dee-55cf-b1b5-056fb0839c4b | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
b12c139c-84d6-5029-829a-9faa73681ea7 | note | – – – – – – – – –
1414d444-8c0d-56d1-9f52-724605f20366 | note | REFERENCE DOCUMENTS: 610.23
e45c3617-9f94-542f-80ed-c974d0b36ef8 | note | – – – – – – – – –
1aa4fbcf-8d38-5cdd-84c8-603e3cbbf337 | note | INSPECTION/TEST METHOD: Verify
b55d1c7c-2726-5dce-acb9-a8593eb27a00 | note | – – – – – – – – –
b4ab14ca-409d-58da-8c6a-c1f8c2292af4 | note | RECORD OF CONFORMITY: This ITP signed
2d7f2477-c5ca-5057-bac9-b99a304a0274 | note | – – – – – – – – –
e2a38f26-5eff-56e1-860f-49e59dcf7684 | note | IP
26bd723c-e65d-59e6-b43a-b995d41d48c4 | note | – – – – – – – – –
1a1b9d70-420f-53af-991c-7323b875f7a6 | note | RESPONSIBILITY: Fulton Hogan
da47a66b-dcb0-5b03-8d07-d2a138b3ec6a | note | – – – – – – – – –
41da9391-9335-55a9-a61b-dc2e32e0d228 | note | DATE:
86320e49-e4e4-42d2-b811-c623969b9303 | checkpoint | 5.2 - Formwork removal
9243956e-1a95-55ea-9dda-6d2dfaa1c349 | note | FREQUENCY: Each concrete pour
0ac3562e-2b8a-5949-87ab-365b7ceec1d1 | note | – – – – – – – – –
40971302-3c1a-5fb9-b296-ca16f8194d9f | note | ACCEPTANCE CRITERIA:
d57a117a-d925-5c98-a581-3f970e3dca81 | note | • Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal.
c29edf60-e347-5c3d-a625-d8d34ed9ed07 | note | • Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
ea0f5f33-2a73-570f-8d72-0ed739684b0b | note | – – – – – – – – –
7322e1fd-efad-5da8-9f37-7785043d5873 | note | REFERENCE DOCUMENTS: 610.25
ea74e3a0-795a-526f-a787-4beeed240cf0 | note | – – – – – – – – –
3c848ebf-0f31-5ea5-bd58-a23adb3f8ad5 | note | INSPECTION/TEST METHOD: Verify
278c97af-0285-545c-8b87-8f1df2e9a95a | note | – – – – – – – – –
2edf8e50-3d87-5af3-82e0-b349e2a4e114 | note | RECORD OF CONFORMITY: This ITP signed
cdc0413b-4d9b-5dd3-914f-7386afd8b54d | note | – – – – – – – – –
8fdbf562-1139-56a8-90ce-3fb61d815ddb | note | IP
ea88f27d-ad95-5aa8-8d5c-d5d98e187a1d | note | – – – – – – – – –
ea3dff30-b7ad-55cf-a954-220c3c7b8110 | note | RESPONSIBILITY: Fulton Hogan
e57394e6-4346-57fd-9455-451463441dc0 | note | – – – – – – – – –
03b37408-0cf6-508c-b1c3-2d8c49a8f842 | note | DATE:
f763113c-f8ca-4755-9381-4e3aa3663dda | checkpoint | 5.3 - Positional tolerance and dimensions of concrete members and piles
6eb095bc-1c43-53ef-a6e5-685fd9547502 | note | FREQUENCY: Each concrete pour
d85a4e1f-3142-5b87-8e16-4f0dd0f91528 | note | – – – – – – – – –
47f6db2b-d9fb-5ff4-9495-1f4fb151710a | note | ACCEPTANCE CRITERIA: The centre of the pile head shall be in the specified plan position ±75 mm;
ebd35ea6-6929-5f16-a164-0e329da5d99d | note | – – – – – – – – –
637fa129-5aba-5d2b-824f-351491d7d14a | note | REFERENCE DOCUMENTS: 607.06
9035b6a5-1779-57e6-90bb-adc27b67e540 | note | – – – – – – – – –
0670ee0c-a666-5bd9-bb20-6104795503d9 | note | INSPECTION/TEST METHOD: Verify
8fe45ea4-31a3-54d7-a121-f8b5cfa0fb8c | note | – – – – – – – – –
878713d6-5a8b-5498-a826-06453bf80913 | note | RECORD OF CONFORMITY:
1211a9a2-7242-59eb-89f0-5a03c36b6958 | note | • This ITP signed
d85203e5-87fe-5e61-8fd7-161d42754484 | note | • Post Pour Checklist completed
83d67fcb-878a-529c-9e51-57bfb03b41fa | note | – – – – – – – – –
f79f6a73-1df4-5c10-8a66-5413371ff5ff | note | IP
4f3b0244-7fe0-553d-98bc-18f0ad456906 | note | – – – – – – – – –
5f37a90d-5c07-5070-bc3e-7475df461bf2 | note | RESPONSIBILITY: Fulton Hogan
c239a079-e037-58dc-99c4-4733e8dfa737 | note | – – – – – – – – –
0ea0c551-5c5c-55e2-a5b9-cc9ab86962fe | note | DATE:
d8bec73d-3bdc-45d5-abfd-ce9cad9993a4 | checkpoint | 5.4 - Concrete Sampling and Testing Self-Compacting Concrete VR400/40
014414c7-3faf-5841-9340-2cc0a4df1343 | note | FREQUENCY: Prior to lot closure
def03efb-41d0-53ef-ab92-4b79b1a9f269 | note | – – – – – – – – –
515f012b-663f-570f-87a0-795a25fef98a | note | ACCEPTANCE CRITERIA:
55f70502-5efe-5453-9f91-4dbe7b148ddc | note | • Concrete sampled and tested for Compressive Strength:
9cd02f20-f722-5cee-a7ae-55ca03823dd8 | note | – 2 cylinders @ 28 days for VPV=13% & Compressive Strength=40MPa
bbb9d086-af65-53ca-b119-6c37122edadb | note | – 1 cylinders @ 7 days for Compressive Strength=26MPa
39c744e6-637c-5190-a16f-449fdc403e52 | note | • Slump flow of 550 - 800mm spread
0921e6cc-0276-535f-8e1c-7439955675c4 | note | • T500 of 1 to 5 seconds
2f034db4-1763-5620-8f12-9154f1310177 | note | • Passing Ability of less than or equal to 10mm
981a3e2c-85b3-55e6-9c85-35cfd57bd6a9 | note | – – – – – – – – –
c5fe7be2-38ef-5d2c-9b1e-2d0782ca47fc | note | REFERENCE DOCUMENTS:
bcd38439-aef3-5f5b-9347-a899a5a0a826 | note | • 610.05
e53723a3-888b-536a-b00a-f24d8f5db898 | note | • 610.06
5bdd3c78-aaa2-5ad0-aa54-6824ec3752e6 | note | • 610.13
3eb95948-16d9-5267-a208-14c326c700f8 | note | • 610.16
93f4d2c2-ea6d-5186-84c5-f22319ed4b4d | note | – – – – – – – – –
df564225-cde5-5605-9ee2-9a570b84d338 | note | INSPECTION/TEST METHOD: Verify
436d2746-019f-5cf6-a0cc-52d27ff43685 | note | – – – – – – – – –
2ca8874f-7849-52c6-bcf2-13cfaffd951e | note | RECORD OF CONFORMITY: This ITP signed
fbfd95ce-7238-5a8b-a099-b587dcedf0c9 | note | – – – – – – – – –
c6622227-eb70-528e-b53f-2b9d084c9c37 | note | TP
61d47c22-c77c-5ba5-80c8-518e0c0c5582 | note | – – – – – – – – –
5561a68d-7455-538f-a563-6a2867d0d882 | note | RESPONSIBILITY: Fulton Hogan
43246334-ad20-58a4-908f-16eae5801977 | note | – – – – – – – – –
f4492850-3dbd-58b4-b44d-3bf63f29f5b4 | note | DATE:
eafb3d61-5f72-41c0-b305-143f2de23a05 | checkpoint | 5.5 - Protection of Adjacent Piles
e690d5e4-7a2d-5973-afb2-e1df9000c5b1 | note | FREQUENCY: Prior to commencing any piling
3d15219b-f1aa-5c28-9e13-ecd78c59b75e | note | – – – – – – – – –
16ca98e8-55c9-5f64-b15c-dd3da1b00851 | note | ACCEPTANCE CRITERIA:
dffa60e3-646b-583b-b449-0aa8aa720252 | note | • No pile construction shall be commenced within 2.5 m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
c7f38ee5-e1e9-5018-969b-2372cd5b5ce0 | note | • Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
192067d0-41b8-538c-9169-7066eff5df03 | note | – – – – – – – – –
a230fd43-b6b2-59f3-a01b-12d00b2747eb | note | REFERENCE DOCUMENTS:
52e4334b-2ebc-554e-af92-736ef9a4302b | note | • 606.04(a)
c69e4150-572b-5a7d-8e49-0f06b16d02d0 | note | • 606.04(c)
de683e4a-7f37-55c0-b08c-f4314c5cd977 | note | – – – – – – – – –
4ac1689d-0d71-5e2b-9de8-4d1e3b3ef1b5 | note | INSPECTION/TEST METHOD: Verify
55cd5fcd-940b-5d8f-a4e8-334f51c67140 | note | – – – – – – – – –
739fd928-eaf8-5c69-9644-f88e58d5c58d | note | RECORD OF CONFORMITY: This ITP signed
0564a05d-be35-58eb-89bf-2f116378af5f | note | – – – – – – – – –
128508f0-086f-590a-9b8e-ca91d3c71150 | note | HP*
bb08fd3b-1dfd-5861-9d55-36e3c07a2dbf | note | – – – – – – – – –
35edac5d-21c0-5be2-9fd1-540ea0e44344 | note | RESPONSIBILITY: Fulton Hogan
06cc0315-3b3c-5eae-b66a-b4efefce46d8 | note | – – – – – – – – –
b1d068f9-332d-524a-ba61-3bac214286fc | note | DATE:
0d7c9512-5398-4548-80b6-d500c9092d28 | checkpoint | 5.6 - Testing Post-Pour
e997694c-aee5-549f-a322-717488514bd5 | note | FREQUENCY: Prior to lot closure
0616420b-3cfa-50ad-823a-3eba4fee2087 | note | – – – – – – – – –
37aa0084-21d6-5d6e-81e2-ecef89187693 | note | ACCEPTANCE CRITERIA: Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
77237332-60f3-566e-9e97-ba21fd58deec | note | – – – – – – – – –
7d49fd5e-9a5d-53c1-83e4-4b3ddab03fec | note | REFERENCE DOCUMENTS: 606.07
2eea2593-15ef-5074-a2e5-22f45f11d519 | note | – – – – – – – – –
3cf0198b-5532-5a78-95b0-c9c312110bc7 | note | INSPECTION/TEST METHOD: Verify
6eaf894c-c20b-5713-8d3f-a327327a455a | note | – – – – – – – – –
2b2db54a-8394-5394-b34b-bed9a14ef4df | note | RECORD OF CONFORMITY: This ITP signed
c13650fc-cc74-5207-81f0-e2038ba5b1fa | note | – – – – – – – – –
da96f2ee-7052-5f71-9e9c-c17ecf64f899 | note | TP
7ed71d08-6ae0-55cb-90c8-e22b4ebe3bf2 | note | – – – – – – – – –
006fd137-b260-55db-91c9-0b4688080acb | note | RESPONSIBILITY: Fulton Hogan
cb12c99c-135c-5cde-ac27-ce9ff194b599 | note | – – – – – – – – –
9abe2798-c61c-5179-8811-6108669c3400 | note | DATE:
314b79e3-f9b0-4257-8438-86c79dd85015 | checkpoint | 5.7 - As Built Drawings
54c4adc3-bae2-51ca-a85a-b07cf87666de | note | FREQUENCY: Prior to lot closure
b2b90705-9379-5bff-9d2f-75b3a61cd9d8 | note | – – – – – – – – –
050dc48b-b59e-53a2-8c75-006897685292 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
79e057d6-1e3d-5b13-af44-000444a6adf0 | note | – – – – – – – – –
f960dd5c-f5d2-5a05-a947-f75a1d47c132 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
6e65750e-244d-542c-9155-696ba1274f5e | note | – – – – – – – – –
b2f6c98b-0c9e-5d51-8270-f469c3189346 | note | INSPECTION/TEST METHOD: Verify
ea58bdbf-533c-5bd0-9206-f18c732ee031 | note | – – – – – – – – –
903eb360-6549-55e7-bb17-0c404a2f6b89 | note | RECORD OF CONFORMITY: This ITP signed
c151f680-3ec5-5043-8c80-18e7a15f15a5 | note | – – – – – – – – –
21492517-7071-5b48-a03a-ded9eab42dc9 | note | IP
7d473a15-9fdb-5d55-8d23-9fd2e22ac3f9 | note | – – – – – – – – –
0b786cb3-4d06-5b26-a8d3-b300ccfeba3e | note | RESPONSIBILITY: Fulton Hogan
376a571b-035f-5346-a80c-5f17d60c68e3 | note | – – – – – – – – –
be52e0b9-4158-5454-beca-a0146ff8cedf | note | DATE:
3e23ea28-3685-4cf8-a449-2ab76a988aed | checkpoint | Final Inspection
942a247e-5559-5daa-bbbd-70a65235b249 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1e4f879d-a251-54eb-a5c3-4451cf85f80c | textbox | Print Name:
fa24fa60-5e7a-5949-9748-99a185d4c483 | textbox | Position:
2853177b-a0af-50fc-b8eb-132a2f2cd4d2 | textbox | Date:
49e9677a-0d0b-449d-85b7-276470896535 | checklist | Order Acceptance Certificate |  | Order Acceptance Certificate
12943a19-296b-4e89-8610-186004108dcb | section | Details
299008b7-c19c-49ab-b096-e107e16ac5bd | checkpoint | Order Acceptance Certificate - Details:
26df869c-364b-5337-8dba-fc4570a0258a | textbox | Subcontractor (full name of Subcontractor, ABN, Subcontractor's ACN and ABN)
2eb4f8b3-24b4-509a-a680-b0f3d57f095a | textbox | Order No.:
fda27679-0268-5ec1-8d89-a67e5a5a0a0d | textbox | Delivery Site:
c1ecb7ca-7c00-5a43-ab8e-f666b52d185d | textbox | Date on which materials delivered:
17f8af05-1b5e-53b7-8f4d-cf7e71790961 | textbox | Delivery vehicle (registration number):
2ca1ff99-0543-5738-af8b-82cdf2afb10d | textbox | Subcontractor's delivery personnel (full name)
9da443e5-70ed-4df2-9584-8026f3c806ef | checkpoint | The Subcontractor has checked all Materials included in this delivery and is satisfied that all of the Materials comply with the Subcontract.
f49bcdd7-7752-4834-9362-9fe7007efd98 | section | Packaging Inspection
f7efd4df-ac80-4516-8d22-c884e09d0a28 | checkpoint | Fault ID:
d7141a89-cf9a-53d6-8c68-4cf61641f55d | note | OK = Meets all criteria
264aa1e1-3c3d-5b72-8fce-1af348ca932a | note | QI = Quantity incorrect
ca21b412-03b5-5d09-97b4-2d9ee671248f | note | IN = Item incomplete
3457fb17-0547-54a1-8ebb-240b183207aa | note | MI = Make or type incorrect
fb82b640-67e9-510b-b76f-aae5e6fe8a0b | note | TD = Damaged in transit
b464411a-d4f2-50da-9fe6-ea7949eff2a2 | note | NI = Not properly Identified
dafaff95-94f0-43b2-9827-31d1a7c12ee1 | checkpoint | 1)
d8838fd4-42e4-545f-bbc3-164b119035be | textbox | Item ID:
f1747108-3797-59e9-ab63-187dda6b5535 | textbox | Item description:
94d4fa2b-d653-51ff-bb41-5a4e91a5a354 | textbox | Units ordered:
312647ca-e310-5d64-b75d-c3a5de485175 | textbox | Units delivered:
3c257c9c-666f-5eff-a881-68a745592d82 | textbox | Special Storage/ Handling Requirements?
95a4bd6d-cb13-5c7f-aa0a-5d87ebc9d304 | note | The following is for completion by Fulton Hogan
1fa0eaa4-4b2e-57fd-a948-96f881afc53c | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
64e578b4-bf59-5698-94c7-aa0bce1af94d | textbox | QA Docs Delivered?
c0047024-782a-5a95-aa6e-2c33f166bbfc | textbox | Defective?
3ba9965e-8683-5216-a997-f55043183dc8 | textbox | Number Accepted / Number Rejected?
a0ef6a72-6302-5518-b832-a9b16088a3a9 | button | Fault ID: | IN, MI, NI, QI, TD,OK
5ae03347-d150-4588-af55-93390cbcc564 | checkpoint | 2)
b9bbe515-cdb9-52da-a601-af1f6add88d0 | textbox | Item ID:
c06237d4-e09f-5b2c-bde7-99af5765362e | textbox | Item description:
5c2d3bc4-3dba-547a-9ab9-dcfb68cf5753 | textbox | Units ordered:
8872be9e-4831-52ee-86e6-00f242756f7f | textbox | Units delivered:
8c4d01c7-8a60-59e9-84cd-3c02383da2c7 | textbox | Special Storage/ Handling Requirements?
e2d5c6d8-ef61-59c9-b841-977d32ab4a6a | note | The following is for completion by Fulton Hogan
144f28fc-a402-5cfd-a3bb-828b778d61ba | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
d5102441-c1ce-5ceb-9175-9533c1a0d4ed | textbox | QA Docs Delivered?
10dd7c9f-76f0-5fe6-9a17-279bbb36972b | textbox | Defective?
205e0f38-faa3-5da2-a5f5-ea2a09cb063d | textbox | Number Accepted / Number Rejected?
a085b80c-e20f-5494-a4bb-dc33a9c01ba3 | button | Fault ID: | IN, MI, NI, QI, TD,OK
9dabf12c-f420-4c9c-aa1e-a2f408eb797b | checkpoint | 3)
336a18e0-ed7f-5ba9-9ee6-aff4f88183a9 | textbox | Item ID:
c7e3b33c-1979-54da-bd76-0ce5cf95294f | textbox | Item description:
25ec5fd9-095e-528d-88e2-0fc282908933 | textbox | Units ordered:
fe66fb66-d37c-5fff-89ab-2e2f86992d31 | textbox | Units delivered:
c467898f-5ead-54cc-bb93-bb94b7fe30f6 | textbox | Special Storage/ Handling Requirements?
ce62082a-001d-51ae-bdc6-d192c6d4e76a | note | The following is for completion by Fulton Hogan
311b3276-80bd-5f0a-abf7-186fd49479a0 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
1828f81f-2998-516f-bc95-82ef35755ab1 | textbox | QA Docs Delivered?
397d76d0-bba5-556e-bc39-126e6df3b68b | textbox | Defective?
6955f281-89b2-5639-a303-2f6f80fa8e7c | textbox | Number Accepted / Number Rejected?
857dfe1c-c9b4-5b03-b399-212a63c4d011 | button | Fault ID: | IN, MI, NI, QI, TD,OK
ac05f80a-5bd2-4b6d-8f57-5cb320e74383 | checkpoint | 4)
3eb6c981-9bd5-5f81-85f7-d9eb36110453 | textbox | Item ID:
5a166474-3679-5d09-8097-1b7c2960b3b3 | textbox | Item description:
d7556f2f-be58-588b-8634-9e624755de36 | textbox | Units ordered:
5afb4336-7220-5f27-b9d3-6e860f43b0e0 | textbox | Units delivered:
3d166f82-af17-5ca5-8788-7082d02829fa | textbox | Special Storage/ Handling Requirements?
9cd10690-9350-5896-9992-b86699a05dc2 | note | The following is for completion by Fulton Hogan
1197b1d0-b454-5448-9b41-d9ed29790501 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
27bfd839-e575-5796-a2e1-58552dc6a9b2 | textbox | QA Docs Delivered?
7bdc30b0-5333-5b27-9747-c41162453f3e | textbox | Defective?
c372ff09-55f8-5879-9d5e-ca3531aaa342 | textbox | Number Accepted / Number Rejected?
8b86a63b-f58b-5cb2-ab2e-491761bb4335 | button | Fault ID: | IN, MI, NI, QI, TD,OK
12a1b6e8-2ee7-4ca6-8d7b-645ea3d5192c | checkpoint | 5)
1df24836-e00a-5616-b484-880f7896c7c8 | textbox | Item ID:
fa21c17b-0574-52bf-bf08-563d28356418 | textbox | Item description:
b39788d2-d3ad-5535-bffe-c39f527d0529 | textbox | Units ordered:
3a6bcbb9-7c61-5101-8828-05c0a1acfab6 | textbox | Units delivered:
63eb36b4-95bd-5005-ae97-5c039aefa74f | textbox | Special Storage/ Handling Requirements?
07bfbeec-42a7-5d31-93fb-a3f639d119ba | note | The following is for completion by Fulton Hogan
6b74498e-07ba-5582-994d-1426de0522e5 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
c9561080-9956-5c65-934d-96dbfc843366 | textbox | QA Docs Delivered?
9474dbe8-47d2-59cd-9219-0f4bff4ab1e5 | textbox | Defective?
f7fe828d-0a1e-5826-8eea-59070d59d7b0 | textbox | Number Accepted / Number Rejected?
c5a07d43-de97-5f5f-87e9-c1bef7c53b17 | button | Fault ID: | IN, MI, NI, QI, TD,OK
f01b980f-c0b1-47e9-a5c3-744f7dbc6281 | checkpoint | 6)
e3a53d9f-324d-5b13-8f86-900fb833a61f | textbox | Item ID:
b0ac751f-be3a-522b-8432-857453722168 | textbox | Item description:
98c099c4-4fe2-5514-b4b9-18089a685f36 | textbox | Units ordered:
2e1e864d-cfc2-510f-a976-4bd9e5776ee5 | textbox | Units delivered:
0dffaa5c-255e-5eab-9194-6df0f9318234 | textbox | Special Storage/ Handling Requirements?
f74e30c6-a390-59f9-8a6a-ba3c2c5fa65f | note | The following is for completion by Fulton Hogan
b1698db1-9bf3-50d1-91ee-d34e8017b97a | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
04c2730e-cb4e-52f5-b69b-b516349a4c71 | textbox | QA Docs Delivered?
a9244c0c-b231-5814-87bb-bcbebce51d54 | textbox | Defective?
ca0bb783-49a5-52f2-afc9-eced8142f531 | textbox | Number Accepted / Number Rejected?
a3e989e8-2ece-54fc-9daf-002a925eaedc | button | Fault ID: | IN, MI, NI, QI, TD,OK
ef9cb382-f4fe-4c06-9f22-38e94d03074a | checkpoint | 7)
89ca7288-9c23-583d-8354-4857f08a6b8c | textbox | Item ID:
83eb4ff7-ef1b-5f14-aa77-10cfde20c578 | textbox | Item description:
178201eb-f955-5d00-8d12-2f508789c1c3 | textbox | Units ordered:
8c1dc002-3d82-5906-a5e1-8d66532471cc | textbox | Units delivered:
9e5a9ef3-e2fe-5c99-bf40-314301afde56 | textbox | Special Storage/ Handling Requirements?
037608d4-9b6a-5ddf-bb65-7c37f8f975be | note | The following is for completion by Fulton Hogan
a73b233a-08ce-5183-bd46-389fc28e9f98 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
a1c260df-c7fc-5434-a64f-f35c3e86bb6e | textbox | QA Docs Delivered?
40f2d8ad-aefc-5535-a8e6-9d52403c42dd | textbox | Defective?
420ca35c-4556-5039-9085-ac0145c9e90f | textbox | Number Accepted / Number Rejected?
af70d27b-56c3-5df3-8bf5-9a3453dd8e2d | button | Fault ID: | IN, MI, NI, QI, TD,OK
d2e08458-dcfe-421e-97d3-95919f770c59 | checkpoint | 8)
9ef8613a-0052-5e64-923f-e776ddd8b356 | textbox | Item ID:
cefd7583-ae2e-5ea9-9777-d78571179bd9 | textbox | Item description:
e2daa413-059d-5f7f-b05f-a47e92ede044 | textbox | Units ordered:
7e27b152-4e84-5d54-b1e5-e5c606ee35e2 | textbox | Units delivered:
908442ce-5202-5a80-a884-2e74306598f4 | textbox | Special Storage/ Handling Requirements?
a6723a8e-1112-5a2d-872b-10397b9c695d | note | The following is for completion by Fulton Hogan
001864d2-c672-5988-bd4c-969307b437e6 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
8342c84e-6eda-5d79-9d00-ebbdc40fb783 | textbox | QA Docs Delivered?
5491e8d7-f014-55a5-9386-5dcb3ff21be2 | textbox | Defective?
dae8b8bb-36e3-5030-9768-c9db5ba4f2d4 | textbox | Number Accepted / Number Rejected?
46ee071c-5860-5fc9-956b-ac2ab4ff1551 | button | Fault ID: | IN, MI, NI, QI, TD,OK
0387cfa6-fe7b-44d8-bccd-a233999cacef | checkpoint | 9)
eb8a912b-2310-59b6-8845-8d22c176a052 | textbox | Item ID:
f898eb76-d42f-5436-bdba-4ffb849bcd0e | textbox | Item description:
af16646f-66fb-5f1e-82c0-dfa6e923da67 | textbox | Units ordered:
9ca3e250-4f28-5787-8e0b-dc5bc1827f25 | textbox | Units delivered:
14e72ed4-9db3-52d8-9596-c9ce4662e2f3 | textbox | Special Storage/ Handling Requirements?
5c2dad4a-585a-567e-beef-c7eaa7d126ad | note | The following is for completion by Fulton Hogan
d9f0057e-3720-5b4d-9804-d12fd34c3ab6 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
992f2d3b-be8a-583b-8a59-b64688da13b4 | textbox | QA Docs Delivered?
8cd1c247-bdb3-579c-ab05-cd851b7afadc | textbox | Defective?
ecbb7aea-855e-57ce-aeac-047cbdd4c484 | textbox | Number Accepted / Number Rejected?
81acb421-01ef-5d8c-a6fb-45569e2d39a0 | button | Fault ID: | IN, MI, NI, QI, TD,OK
faacf936-0071-4450-8338-c520ab500d68 | checkpoint | 10)
893f7f07-8d25-55e7-86a3-aaa60700a98c | textbox | Item ID:
f7ed5f4b-c79e-588c-abd6-492a124b5a73 | textbox | Item description:
8994620a-19c2-515a-a0ad-e9843933e400 | textbox | Units ordered:
6da1516f-337f-5711-8583-8e451212a748 | textbox | Units delivered:
33acf274-678f-5649-9b96-5cfd63ac6473 | textbox | Special Storage/ Handling Requirements?
e2392083-526f-5d15-bb6a-f8a850ab191a | note | The following is for completion by Fulton Hogan
29334cc9-fb34-53be-8fe6-4c94734a69a4 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
8a0f8651-8b81-52ce-ac06-bf22f44a6060 | textbox | QA Docs Delivered?
d815e39b-a922-5137-a592-562758f83fb6 | textbox | Defective?
f23a82fb-185f-535c-a817-a90e1fd209d5 | textbox | Number Accepted / Number Rejected?
a6a8722d-abea-5b05-8c1d-c53973a075a2 | button | Fault ID: | IN, MI, NI, QI, TD,OK
bbd4b638-e033-4a0f-b2da-4740144418f5 | section | Sign Off
fd234d6e-3723-4b46-9c59-97648a505183 | checkpoint | Accepted by Fulton Hogan
71ea96d9-967c-45f8-b494-97ef82ee39da | signoff | Sign Off
47e3bf20-5bc9-49a4-87dd-a26790aa97f1 | checklist | SYS - ITP-01-009 - Culvert REV2 |  | ITP-01-009 - Culvert
c804da90-8ed4-43c4-8d25-96f963121e72 | section | 1 Preliminary Works
e04672e1-d721-4280-a804-1fa79b49c5c4 | checkpoint | 1.1 Check for correct documentation
1664d757-9073-5241-afd9-93b5ffa42285 | note | FREQUENCY: Prior to commencing any activity
5b4aeec5-2747-5f75-a185-535aa319b831 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings - all drawings are the latest revision
613dbde4-73be-523d-bdd3-04e935cc57f9 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
b178f3b4-2de7-520b-817f-7da023421dd2 | note | INSPECTION/TEST METHOD: Visual inspection
12a9b793-ac6c-5380-8d15-8bcf9e57b8c0 | note | RECORD OF CONFORMITY: This ITP signed off
e550fad4-3c2d-532a-9d54-dbb9ab0a5a35 | note | HP*
76f1b51a-e653-5388-a233-f6bba929cea1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f23fa348-53c3-5517-8bf0-d0bba0625c16 | textbox | DATE:
dbb04cd5-af4f-4d64-baf6-38cced852bad | checkpoint | 1.2 Implementation of all measures and controls
e647344d-8672-5090-b620-fad7bb4634a1 | note | FREQUENCY: Prior to commencing any activity
34070656-7ac5-5c4a-a7b1-95f0cd63ada2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
cb43d345-e496-5ffc-850b-a073cffb4665 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
4d92e04d-b4f9-5be5-857f-f433f9b705d5 | note | INSPECTION/TEST METHOD: Visual Inspection
69805b6e-74ab-525b-afd2-47457d96d26d | note | RECORD OF CONFORMITY: This ITP signed off
4817e784-6cf0-5acf-8f5f-cf2923090940 | note | HP*
e99c97ab-a8cf-5af5-b39c-18725e03ef7d | note | RESPONSIBILITY: Site Engineer / Site Foreman
4cf5d6e9-326c-5324-8dae-71fbd05a590b | textbox | DATE:
48fa9320-5363-4561-88f8-315633dafd3f | checkpoint | 1.3 Precast Materials Inspection
69a9a361-ab67-50e1-a63f-95738d7b347e | note | FREQUENCY: Each Delivery
4d607ad2-e807-52d7-8fbe-570a9bc33d29 | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
6d4ebe6c-2cbb-5b02-8631-9b73e2dd24b4 | note | REFERENCE DOCUMENTS: 619.08
6a13fba9-a9a5-57bc-8509-a507a30985ba | note | INSPECTION/TEST METHOD: Visual Inspection
43740b39-4746-5053-91ee-f108dd302259 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
79bd25d3-9da5-571d-902c-be853d4d315c | note | IP
231ddb09-5690-5d17-b02f-4aceb142008e | note | RESPONSIBILITY: Site Engineer
3e2fd5d3-7b0c-500c-815f-63b537f43832 | textbox | DATE:
c37b16b4-6a8c-41f1-a951-8e1e12de03c0 | checkpoint | 1.4 Precast Pipe & Culvert Compliance
cc074aae-6eb0-5f4b-9b51-c401460ed51d | note | FREQUENCY: Prior to Commencing
0168668d-2045-51a5-a21a-53f0198b8e83 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
8a80edf5-0149-5bfc-a88a-26b48f2c727a | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619 701.04 701.05
268ca207-4be2-5e09-b435-c8fb70314ae1 | note | INSPECTION/TEST METHOD: Document review & Site inspection
1a5e04a3-1cc2-552e-9fb4-6b181dbbe7ed | note | RECORD OF CONFORMITY: Receival & Inspection Checklist Manufacturer cetificate or accreditation
e8204202-4bdd-556f-82f1-e6d7c8c27cee | note | IP
3f8f7e18-ed87-500c-8076-070abc91f649 | note | RESPONSIBILITY: Site Engineer
ec982e63-6a3c-5759-b205-cfefe11d5eac | textbox | DATE:
c04b5212-d4c5-402f-8e94-98576feb84e7 | checkpoint | 1.5 Bedding material classification
1c1e1c14-341c-53be-b454-370c1ddeff6a | note | FREQUENCY: Prior to start
e8b9065a-7ed5-57cb-9d0d-32c2945b4afc | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below: 100% passing 19mm sieve. 5%-40% passing 0.075mm. PI = 20 max.
00b30ad5-3112-5c60-bcc5-d21d2a4ceb1f | note | REFERENCE DOCUMENTS: 701.16 Table 701.091 Table 701.092
88492de4-2ac0-527e-ae94-3eb9cfd96431 | note | INSPECTION/TEST METHOD: Verify
0f6a6cf1-0032-516b-b429-8ea0fa96cdab | note | RECORD OF CONFORMITY: Test Reports from supplier
29c7df22-f765-590b-be0d-a6ee0b10a6b5 | note | TP
16e4bcd6-f494-56bc-b992-db26313c5a94 | note | RESPONSIBILITY: Site Engineer
1c3b3f3c-e922-53e9-9f5b-5ed1541e785a | textbox | DATE:
a14ee0d5-6fb7-4b70-9a00-82df38c34136 | checkpoint | 1.6 Backfill material Classification
71b4daa6-2e28-5761-9ba3-8b04ad0e6e83 | note | FREQUENCY: Prior to start
1d75c04f-ecc0-5c9d-9361-9eb6ae876c1f | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below: 100% passing 37.5mm sieve. 5%-40% passing 0.075mm sieve. PI = 20 max.
5fb15f20-2cf7-51db-8723-1caa1852b4cb | note | REFERENCE DOCUMENTS: 701.19 Table 701.091 Table 701.092
9f6c67da-574a-52cc-a3cb-d9f954942deb | note | INSPECTION/TEST METHOD: Verify
e707a6b6-f8c5-5221-ad00-2c8d6f622a53 | note | RECORD OF CONFORMITY: Test Reports from supplier
ec3ad95c-c209-5710-8e61-edc6528d58f4 | note | TP
c0bb992f-56a3-5aae-93b5-9c38bcdc4f24 | note | RESPONSIBILITY: Site Engineer
a35a2c8a-e578-5361-865a-d2568584974b | textbox | DATE:
1ddc821b-c1e3-4382-ac4b-47423b072a9b | checkpoint | 1.7 Mortar material classification
e8610bdb-8753-59f9-af41-aa51ceb8e77c | note | FREQUENCY: Prior to start
49c6b135-f531-54f7-80f9-4c9b186cba28 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of not less than 40 Mpa. Only whole bags of material shall be used. Test certificates, material data sheets and health and safety data sheets shall be available for all materials. The mortar and grout applications shall be cured in accordance with the requirements of clause 610.23. Mortars and grouts shall be sampled and tested in accordance with the requirements of clause 610.28.
1cd8df16-32d6-5dc4-b0a1-3598f6b0f9a2 | note | REFERENCE DOCUMENTS: 610.33
08d72412-7211-5db7-b6f5-e70c5b6120e0 | note | INSPECTION/TEST METHOD: Verify
408528c1-cd68-5313-a76e-97ee1542ee40 | note | RECORD OF CONFORMITY: Test Reports from supplier
5746b16d-9f81-5551-893d-2efd82d0a0fa | note | TP
3d073e0c-56bd-58ea-a2ce-3395367848ac | note | RESPONSIBILITY: Site Engineer
a3faa562-e8f4-5919-8e2e-54c9a1a493b6 | textbox | DATE:
f5a47ba5-1b02-4ee3-9fc1-3f7da9df3a45 | section | 2 Construction Works
0d1a7c8a-d4a9-4081-8bef-ebb44fffbd88 | checkpoint | 2.1 Excavation Permit
1b95ec3a-1581-56c6-9669-e86b34d1e871 | note | FREQUENCY: Each lot
044b1a78-a0eb-542d-bc93-f09ca4b4f1a5 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation.
80e4636a-75f5-55b2-bc07-5b9de6b0e794 | note | REFERENCE DOCUMENTS: Excavation permit
4655c5d8-60f5-5119-bf02-700069cd79ee | note | INSPECTION/TEST METHOD: Verify
a669f170-b971-55a2-ad65-8b12fc2e93b5 | note | RECORD OF CONFORMITY: ITP Signed
7f5d6717-8dcc-51f0-9f60-c50cefedf4ab | note | HP*
e3d6ab5d-5cb9-53ed-91dd-446d93b721c7 | note | RESPONSIBILITY: Site Engineer
4fa03fdc-ffe4-59e0-b261-ab490d2faa3f | textbox | DATE:
cebc9a06-fd01-4a61-b3bd-e2abb71c575c | checkpoint | 2.2 Review
c5ee226a-ec8d-5906-9b62-8c0222a66859 | note | FREQUENCY: Prior to construction
72821d64-2ef3-5c74-95c2-b49f3ad3c0cb | note | ACCEPTANCE CRITERIA: Culvert construction shall not commence until the Contractor’s construction quality procedure and inspection and test plan(s) addressing all requirements of this section have been reviewed by the Superintendent.
26164e4e-4a61-59dd-9f59-2e5ed1f36db7 | note | REFERENCE DOCUMENTS: 626.02
c0a9c26f-483a-57de-9c39-26536767f766 | note | INSPECTION/TEST METHOD: Visual Inspection
74f75399-2968-5040-9542-44dfe4017574 | note | RECORD OF CONFORMITY: ITP Signed
bd0476ee-0834-5c94-9148-9dec16299826 | note | HP
253dbe1f-2fe8-561f-ad8b-61d41f1636a9 | note | RESPONSIBILITY: Site Engineer / Superintendent
02ae07ca-1140-56d2-ad71-929af2aa2808 | textbox | DATE:
7ae27e7f-9b4c-48db-89d2-787ab2bd2dbc | signoff | REQUEST HOLD POINT SIGN OFF
f110417c-b1e5-4234-b9f7-417115baae20 | checkpoint | 2.3 Diversion of Water
2538c0e2-e806-59e9-99e4-acdd3b883b65 | note | FREQUENCY: Prior to construction
9ace5dbf-068f-54fe-8e21-a4ac4a50e5d7 | note | ACCEPTANCE CRITERIA: Culvert construction shall not commence until water flow has been diverted to the satisfaction of the Superintendent. Pumping options shall not be used.
826665c4-8df7-51b7-bb38-cbe7f8bb7e1a | note | REFERENCE DOCUMENTS: 626.04
ce2d7d74-b2da-5be4-bca6-c0a3ce2fef90 | note | INSPECTION/TEST METHOD: Visual Inspection
5e2adcdf-6610-5b91-bbe5-b99a6f896c1d | note | RECORD OF CONFORMITY: ITP Signed
f8a0e927-f56f-5c47-9732-b29f427ee098 | note | IP
5e78bab9-19a7-5f2b-a6ad-0a97ac5c0398 | note | RESPONSIBILITY: Site Engineer
5cf70746-095b-57c8-ae37-2ed9fcdd98e0 | textbox | DATE:
2c502537-1bec-4fdd-b03e-f5a1c7a57d0c | checkpoint | 2.4 Conformity with Drawings
aa8ddab6-9e55-5c72-b9a8-fb5db59b7aac | note | FREQUENCY: Prior to excavation
34c76419-c6f0-5269-8892-d5a35d8e0dbb | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
e838d054-6e90-563f-9261-a9d03771d6a3 | note | REFERENCE DOCUMENTS: 701.1
19b4e43a-576d-5234-bac1-cc2584e98ccb | note | INSPECTION/TEST METHOD: Visual Inspection
8e9e476d-8acc-5218-8db8-d60cc0360924 | note | RECORD OF CONFORMITY: ITP Signed
0d9dacdc-30f6-5681-95f0-055d965c81cd | note | HP
df5a24c9-d42e-50e0-997d-d19501e462ba | note | RESPONSIBILITY: Site Engineer / Superintendent
945ae3cb-6494-51c4-b2c6-a4c70da4c776 | textbox | DATE:
6dee3e07-c69f-4ebe-8618-8ae256346fe8 | signoff | REQUEST HOLD POINT SIGN OFF
eb755e8d-4d88-45c3-83b9-9b45b57b4242 | checkpoint | 2.5 Tolerances For Placement
857559ea-53db-5b0d-971f-43402dbe7656 | note | FREQUENCY: Prior to Backfilling
b47062fa-559c-5c0b-a3d2-1aca46a02c14 | note | ACCEPTANCE CRITERIA: The culvert shall be constructed in the location, to the alignment, cross sectional shape, dimensions and levels shown on the drawings with the following tolerances: Grade: 5 mm in 5 m (1 in 1000) Overall plan position: 50 mm Gap between adjacent units: 12 mm maximum Step at joint between adjacent units: 12 mm maximum horizontal or vertical.
08163f52-acc2-5881-bb2f-f1dac1c6b4bb | note | REFERENCE DOCUMENTS: Drawings 626.03
7ac42e79-ab5e-5195-9c43-45adb2ad68ac | note | INSPECTION/TEST METHOD: Visual Inspection
4e145ded-31b8-53bf-9370-b60cf6c072c7 | note | RECORD OF CONFORMITY: ITP Signed
b3661e1b-b417-566f-b009-20a53c23cd40 | note | IP
8deebd13-2c68-59ed-8b69-d781acf5599e | note | RESPONSIBILITY: Site Foreman
5dea3bba-98b5-5f90-b95e-b554f41dd233 | textbox | DATE:
ac4a9c54-310c-4ff4-a6a7-038feaf45694 | checkpoint | 2.6 Foundation Inspection
00bf1ea9-2b35-5aaa-9ca5-c3cd5d58e84c | note | FREQUENCY: Prior to Bedding
9ffd6228-fb4d-5e44-a801-8559bbcdda2e | note | ACCEPTANCE CRITERIA: Bedding for the cast-in-place concrete base slab shall consist of a compacted layer of 20 mm Class 3 crushed rock, of not less than 150 mm compacted thickness. Where shown on the drawings, this material shall be placed on 40 mm Class 3 crushed rock spread in layers not exceeding 150 mm compacted thickness and compacted to achieve the required bearing pressure specified on the drawings. No bedding material shall be placed until the foundation or foundation materials have been inspected and approved by the Superintendent.
e5d99e7e-6544-579e-b6fb-17606b279912 | note | REFERENCE DOCUMENTS: Drawings 812 626.06
77c3925c-fc56-5558-8186-81cf27cabdb0 | note | INSPECTION/TEST METHOD: Visual Inspection
80b03085-f814-565f-99ec-f2e84adbb9bc | note | RECORD OF CONFORMITY: ITP Signed
ffe286a2-4d15-57e0-aba5-363bc9c154f3 | note | HP
79a26658-dd0b-5230-8b06-47ee366afa6c | note | RESPONSIBILITY: Site Engineer / Superintendent
d8bd96b2-e394-5f65-bf8b-c708388f9fbc | textbox | DATE:
243bb11b-09dd-4a55-81f1-84d702fcac3c | signoff | REQUEST HOLD POINT SIGN OFF
ba612c4b-9e27-4110-b54f-ce8b203c144b | checkpoint | 2.7 Cast in Place Concrete
95cbfb2c-e6b8-5e84-bd18-1af35407d36d | note | FREQUENCY: Prior to construction of concrete base slab
866b2211-a877-5e2e-8cf8-a57255271835 | note | ACCEPTANCE CRITERIA: All cast?in?place concrete for culvert construction shall comply with the drawings and Section 610. Steel reinforcement shall comply with the drawings and Section 611. Construction of the concrete base slab shall not commence until the bedding has been approved by the Superintendent.
72afb519-d025-5d63-9cf2-889116252250 | note | REFERENCE DOCUMENTS: Drawings 610 611 626.07
41fec53d-f9e5-5f9c-a1b4-db205b91d052 | note | INSPECTION/TEST METHOD: Visual Inspection
df012ac2-d086-52dc-bb81-8095cd5e6e82 | note | RECORD OF CONFORMITY: ITP Signed
4d200713-208f-5c15-adec-ef5d827cfa7c | note | HP
ae0a37cd-8025-52c8-a23b-d593e5cbdf87 | note | RESPONSIBILITY: Site Engineer / Superintendent
8ad7cc04-9823-50da-8ce3-9b2d110c5ec5 | textbox | DATE:
f4bb6bae-8d41-4df8-9bf4-140269043db2 | signoff | REQUEST HOLD POINT SIGN OFF
9a83c5de-4afa-4ead-8ed9-0c3cc9676a53 | checkpoint | 2.8 Placement of Crown Units
bb91c806-da2b-5239-b160-03696ac6af24 | note | FREQUENCY: During Construction
8e180cb9-cf07-566e-bfd8-941ae1f57034 | note | ACCEPTANCE CRITERIA: Immediately prior to placing crown units, including link slab units, the surfaces of the bearing areas which support the crown units or link slab units shall be cleaned, wetted and then covered with a sufficiently stiff cementitious mortar to give a continuous finished thickness not less than 5 mm and not more than 10 mm after the crown units or link slab units have been placed. The cementitious mortar shall comply with Clause 610.32 and shall be mixed with only sufficient water to a moist dry-pack consistency that can be displaced to provide an even bearing. Cast-in lift anchors shall be cut off flush with the concrete substrate, and recesses filled to the surface with shrinkage compensating proprietary polymer modified cementitious mortar in accordance with Section 689. All mortar joints shall be protected and cured in accordance with Section 610.
997f5d8b-e2c2-553a-881d-f7a724467dce | note | REFERENCE DOCUMENTS: Drawings 610 610.23 610.16 610.32 689 626.08
858d1cf4-c636-58d3-876f-0bca39769c51 | note | INSPECTION/TEST METHOD: Visual Inspection
0eff21c2-9550-5d94-bfe4-d15f2191fdf9 | note | RECORD OF CONFORMITY: ITP Signed
1c02b2c8-735b-53f4-a14a-81a9b8697d6a | note | IP
1438b198-b974-5739-bf2f-f72fb243dbdd | note | RESPONSIBILITY: Site Engineer / Site Foreman
ba125265-44be-5531-81d9-70554795c2c2 | textbox | DATE:
6b698f06-fef7-4dd7-a341-a015b530f9cb | checkpoint | 2.9 Covering External Surface of Joints
a2389713-7ecb-5f00-8af7-999fcc60fe70 | note | FREQUENCY: During Construction
fdcb2bee-8e13-55b1-a65b-baab7dbdaa50 | note | ACCEPTANCE CRITERIA: External surfaces of joints (top and sides) between adjacent units shall be covered full length with one layer strips of 150 mm wide synthetic nonwoven fabric, factory impregnated with a rubberised bitumen or a neutral petrolatum based compound. The fabric covers shall not be wrinkled and shall be applied on surfaces free of foreign matter in accordance with the manufacturer’s recommendations to ensure effective adhesion onto the outer surfaces of the adjacent units. In the case of multi-cell culverts, fabric covers are not required where the gap between adjacent cells is filled with cementitious mortar or grout which complies with Clause 610.32. The Contractor shall submit to the Superintendent for review all test certificates related to the supply of fabric cover material at least 14 days prior to commencement of installation.
168fba11-7edd-5c25-a431-937c790230a9 | note | REFERENCE DOCUMENTS: Drawings 610.32 626.09
7d8ad71c-1c72-5ea5-a2a4-f7b3345c59b9 | note | INSPECTION/TEST METHOD: Visual Inspection
eaf1159f-07ae-5be6-bc59-1ad9e5e752b4 | note | RECORD OF CONFORMITY: ITP Signed
6cfb5b6e-6cc9-55e8-a11c-2f8b76819d39 | note | HP
16745240-8c6b-597c-99e3-92f4c09e7b19 | note | RESPONSIBILITY: Site Engineer / Superintendent
504406a8-0805-55f4-9ff9-496f9716b618 | textbox | DATE:
ad5a3b18-cbd1-48a5-b973-26d23d9e3aa3 | signoff | REQUEST HOLD POINT SIGN OFF
e859ec76-834a-449b-9d0c-935d501c85ce | section | 3 Testing & Completion
3a61d0c8-74ee-477c-8dd1-0fcf98a5dde5 | checkpoint | 3.1 Compaction and moisture content of backfill & bedding material
95837fb7-6bf7-5400-b32f-a78cf155947c | note | FREQUENCY: Each culvert
9d4aeefc-c8e9-5719-b669-2c9f5138840e | note | ACCEPTANCE CRITERIA: Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested. The calculation of density and moisture ratios shall be based on standard compactive effort. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. Backfill material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
93d016f5-3b2b-575e-aa1c-8a16fce204fa | note | REFERENCE DOCUMENTS: 701.2
86c37bcf-55e4-5cc8-9aaa-294c13eecdbb | note | INSPECTION/TEST METHOD: Verify
f0b418b2-3ae1-5a9e-b2ff-7dadf25eb8e1 | note | RECORD OF CONFORMITY: Test Reports
9b07766d-3ebd-5542-99b9-ddaddb768a65 | note | TP
c75fd105-50b7-5d31-93ce-a83e4c97ba6c | note | RESPONSIBILITY: Site Engineer
8b071f08-c582-5386-b6c8-8384b1f34156 | textbox | DATE:
87eb6318-e5d9-46ed-8cb9-a1577f6cc013 | checkpoint | 3.2 Foundation material at the level of the underside of the bedding
55bda049-1e94-5ee4-8f18-cadcfd91304f | note | FREQUENCY: Each culvert
6252f12a-9b74-5b36-bd58-546157c74d2c | note | ACCEPTANCE CRITERIA: Where the nominal size of bedding or backfill material after compaction is greater than 40 mm, the moisture ratio shall be determined on material that passes the 19.0 mm sieve.
fc8a5916-11bd-51e7-8a6f-025261bcd077 | note | REFERENCE DOCUMENTS: 173 626.05
fce80ad0-3b2a-5dba-818e-5f7699e61916 | note | INSPECTION/TEST METHOD: Verify
6ee8c0ea-7d07-59c7-927e-ec4da6d24c7b | note | RECORD OF CONFORMITY: Test Reports
5fc191cc-2c04-5a4d-b845-6c29fe5403b0 | note | TP
48543e10-87e3-548e-8d7a-9dd49556adef | note | RESPONSIBILITY: Site Engineer
8c507a89-173e-5447-8d0a-743feedf27e3 | textbox | DATE:
fb880e0f-be15-410a-bb57-1fd0b48c6ce6 | checkpoint | Final Inspection
6fc945ad-8075-5e77-9041-d229e17f7cc9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
8da4540c-bf60-5aa5-94e1-e7ed4a7873a3 | textbox | Print Name:
cb9ea4a3-5b36-55da-bd44-970d0fe95685 | textbox | Position:
c323e124-963b-5fc7-95e3-903d87a9be59 | textbox | Date:
fe8cb7d4-867b-490d-9974-fd30d828608e | checklist | SYS - ITP-01-015 - Kerb and Channel REV2 (old version) |  | ITP-01-015 - Kerb and Channel
9d4fb2cc-5016-40b0-ab4e-e6425ead6434 | section | 1 Preliminary Works
5d1ede62-f04f-46a8-84af-d6ce93a46812 | checkpoint | 1.1 Check for correct documentation
7cda6311-78db-5e94-8757-ba185a2bedaf | note | FREQUENCY: Prior to commencing any activity
9dbeb4a6-19bb-5627-b5c7-b8c1d4d97bdd | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
9d3540a0-6375-504c-8319-136415f0fb84 | note | – using the correct and complete set of drawings
924be6e9-146f-511c-a507-4f4444bfe233 | note | – all drawings are the latest revision
497dd8b9-af80-5400-8c6c-d78d4281da70 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
ca659d31-68d4-5a14-a590-55ea6f62ffef | note | INSPECTION/TEST METHOD: Visual inspection
6d538274-3292-50fe-971b-58df4a681133 | note | RECORD OF CONFORMITY: ITP Signed
490e55e6-1049-5bb4-88bc-a93abe55d61f | note | HP*
bd4b82b8-5a9b-5b82-acb0-29d93796b748 | note | RESPONSIBILITY: Site Engineer / Site Foreman
888e054e-bcaa-56d5-b79c-d6e5b3a40e6a | textbox | DATE:
9d9135ef-d574-4872-9939-fcf9a80173a9 | checkpoint | 1.2 Implementation of all measures and controls
a46b596e-7124-5efd-a6a3-b6c1d42db32b | note | FREQUENCY: Prior to commencing any activity
542ac9d4-8c9b-5058-bc67-0d846f78d732 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
78ddc39c-9e68-521f-9808-cdf38ff3c007 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
2ed73d93-f510-5574-a7d3-81e1f3de89d6 | note | INSPECTION/TEST METHOD: Visual inspection
8ad78b0c-ef02-5470-a67e-bf933987399f | note | RECORD OF CONFORMITY: ITP Signed
c5b4dbc0-b0a8-5242-a81d-4eb00f12edbd | note | HP*
a9d29cf5-f903-5bcc-af25-179f31898a31 | note | RESPONSIBILITY: Site Engineer / Site Foreman
93d84b93-3f9f-5e64-9797-37c6badd4fa9 | textbox | DATE:
035d69a5-a419-497e-8ebe-794dd825dafc | section | 2 Construction Works
dd45dc01-f3b3-4696-81c5-3bde54fc3f8a | checkpoint | 2.1 Setting Out
630b980e-b975-50c9-89c4-7ae04266cd5a | note | FREQUENCY: Prior to start
db94237c-c786-5934-8834-d5cb3350a40b | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
2e2a35f4-a7f3-577d-99e6-81cbffff7b87 | note | REFERENCE DOCUMENTS: 703.17
c51542f4-b0c6-5bdc-8886-876b28d35a64 | note | INSPECTION/TEST METHOD: Verify
0ddefb9c-03da-555b-bbca-25eaf2234705 | note | RECORD OF CONFORMITY: ITP Signed
3293031a-03af-55d3-be13-15ea993beda9 | note | HP
ed1d4745-9e9f-58f2-83a0-35c6ecbf9cd1 | note | RESPONSIBILITY: Site Engineer / Superintendent
c9d51def-95b1-5b06-8d57-6e135d792e5b | textbox | CLIENT:
6071b02b-6ec7-5ebd-bb59-268767547a81 | textbox | DATE:
27bc0cd5-ec14-4883-8a22-b178a5df689d | signoff | HOLD POINT AUTHORITY
6f65f46d-ee52-4fe5-aa8a-3d7d4a60476c | checkpoint | 2.2 Temporary Drainage Provisions
bda90111-3d04-54cd-97c3-4591dae4a05e | note | FREQUENCY: If Required
b6ebda31-c4b0-5f86-a614-92e01795f0b5 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
18f87c38-8279-5c31-9ddf-48db1780c244 | note | REFERENCE DOCUMENTS: 703.18
a9e2de4c-0a3d-563a-b923-0f56f3689b27 | note | INSPECTION/TEST METHOD: Visual inspection
fa4e8d71-53cc-5ca7-95e8-5f4cc5ab72e5 | note | RECORD OF CONFORMITY: ITP Signed
9ac634eb-148e-5e96-b7ce-90c9e7d55a5e | note | WP
584dae36-5758-5197-a299-bc1e55b8d1ab | note | RESPONSIBILITY: Site Engineer / Site Foreman
4ee6d987-7a97-5fe6-9666-29d9c726c718 | textbox | CLIENT:
de217819-6d72-5f31-8c51-d65209eaf355 | textbox | DATE:
bf8b6345-2699-4f78-8839-e7f789adf6ba | checkpoint | 2.3 Bedding
9b07a21f-2d91-50b0-80c8-a42e4bc4b8d7 | note | FREQUENCY: Each lot
37532b5f-31a4-5f1f-8196-38323700678a | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
56e0ceeb-1d8b-5bca-b7f8-d5add54538b7 | note | • Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
d824c65f-a9e6-5516-b445-a9be01094ca3 | note | • Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
1e7c124b-38f0-5abd-9673-9cca20e4d791 | note | REFERENCE DOCUMENTS: 703.21
1f50799f-1553-5437-8f3c-6d3863239815 | note | INSPECTION/TEST METHOD: Visual inspection
bf6184c5-7e01-5836-870c-a6c788f333e1 | note | RECORD OF CONFORMITY: ITP Signed
b8af1fc4-7d5e-5af5-bbd6-603d05fcb938 | note | WP
2ece14e7-f6c9-56c1-87d5-0e9b791c988f | note | RESPONSIBILITY: Site Engineer / Superintendent
a4b03b92-b2d6-52dc-a485-30db00d1202e | textbox | DATE:
ef867306-f759-45b1-bee2-a3f877fd326d | checkpoint | 2.4 Pre-concrete check
5a32922a-124d-5259-a3a5-03d5b74b6646 | note | FREQUENCY: Each lot
fadda721-aa0f-533e-b0e4-3f81d883d08e | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
e64c1fd8-8db9-5082-b2ec-7629c8a86b2b | note | • Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
4ab8d35d-1b40-56dc-b750-5172fbff3e92 | note | • Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
9fab20ae-077b-5808-96b8-5a5e65364e1e | note | REFERENCE DOCUMENTS: 703.08
47d39a80-60d4-5833-9b78-c11d1085930b | note | 610.17(a)(b)(c)
1db3e479-ff14-5e87-ab97-24144a89f19d | note | INSPECTION/TEST METHOD: Verify
7c369d73-6375-59ff-8974-e347a0d5198c | note | RECORD OF CONFORMITY: ITP Signed
1316f1e2-cf76-5756-bb9d-185c1a4f9d61 | textbox | Ambient Temperature..... °C
df5aa8bf-dd5c-5112-8f74-fc34270a5e0f | textbox | Concrete Temperature...... °C
a341f27e-2e80-5607-a3bc-0ed60dbb8ca4 | note | HP* / WP
7a5dae89-deb1-58ff-a54e-646b5ed4cc23 | note | RESPONSIBILITY: Site Engineer / Superintendent
5fb50175-8b32-53ba-8099-165c9135862a | textbox | DATE:
9fb97719-487a-4373-9c6d-5cc2f6864584 | checkpoint | 2.5 Concrete Placement
1852c7ca-1562-5a65-847d-b43aefb45756 | note | FREQUENCY: Each lot
5607f149-2a34-5023-95ae-1e94f8202d52 | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate.
cb27847b-ad5d-521e-946d-f1d719fb6afa | note | • Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
6ecafdf2-02ed-5e9c-8703-3b240dd453e2 | note | REFERENCE DOCUMENTS: VicRoads Spec 703.23
4f263d94-4cd9-54a2-bce7-660efe98581a | note | INSPECTION/TEST METHOD: Site Inspection
ffb70a40-7b5a-575d-a6a5-98555f29f302 | note | RECORD OF CONFORMITY: ITP Signed
8b1e21cb-d9e9-5078-aed8-98bf060244c4 | note | IP
d8621e8a-b525-586a-9f2e-45ced8475f23 | note | RESPONSIBILITY: Site Engineer
eaadb358-d60b-582c-bd67-ac2c8b75a21c | textbox | DATE:
3ada318f-00b7-4cdd-af6f-e7d4502718a2 | checkpoint | 2.6 Finish Surfaces
0b757f7e-f999-529e-9ddf-ae35b7f5d362 | note | FREQUENCY: Each Lot
19eca422-b837-5c55-86da-13fa1f319a8e | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
b2296c4e-6bf1-5a58-9531-5f67e0f923d8 | note | • Concrete to have a neat appearance and uniform colour.
4e647b0c-38a7-5ffd-a9f2-80fd4ecfc811 | note | REFERENCE DOCUMENTS: 703.25
e53a0ce9-01cf-53b6-be5d-8afcfe9e3371 | note | INSPECTION/TEST METHOD: Visual inspection
a6065a47-2dcb-5a2c-a0fb-54be1dc2b34c | note | RECORD OF CONFORMITY: ITP Signed
33ef3a4a-6a3c-5288-8edc-4e068061b952 | note | IP
7d54341a-b26e-5642-8e1d-cf7781e80ab2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
20479ca3-4136-5f70-9558-3aca70dac1d6 | textbox | DATE:
cae7b05b-411b-4174-9dc5-ff1a49580bc2 | checkpoint | 2.7 Tolerances
3ac92645-1c6a-524d-9fce-7ab449f67a57 | note | FREQUENCY: Each Lot
9996cbd3-a0c3-530e-ac2b-7667db3ad1a4 | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5mm from dimensions shown on drawings. Section dimensions to be within 5mm and 15mm for width, for dimensions less than 25mm tolerance to be ± 3.
590c7a10-db03-542e-bcd4-1ebf23645622 | note | • Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
c8faf38f-128d-54dc-8b40-c3f2920b69f4 | note | REFERENCE DOCUMENTS: 703.15
fca4defa-8034-5fe5-b8d1-8175068af6dc | note | INSPECTION/TEST METHOD: Verify
b99bebce-47ea-528c-9dfb-e4a7adfdd397 | note | RECORD OF CONFORMITY: ITP Signed
a991b11a-50e2-52d6-8253-492a69686ace | note | SCP
7b4f19de-8cd9-52bc-b101-5e08e6050d8d | note | RESPONSIBILITY: Site Engineer / Surveyor
36131f82-7009-56df-8e20-ab5f632108fb | textbox | DATE:
09992507-48fe-4948-83e0-cd5fcc9f6440 | checkpoint | 2.8 Joints
fe1f1493-a396-5619-8923-a8a8cb0c7f53 | note | FREQUENCY: Each joint
5b2938cf-8d65-5bf3-884c-1105225987d4 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
47ae5f85-46a1-5fac-9a03-e63b1eafee4d | note | • Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
8ac8fbd7-580c-563b-ba44-50554fdd7eda | note | • Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
dacba51c-990d-5b54-bea3-0c5ab04c075d | note | REFERENCE DOCUMENTS: 703.26
b11f67fb-6756-5e1e-a92a-33dcc676897e | note | INSPECTION/TEST METHOD: Verify
f0551db8-1b7e-59cb-b3dc-62f2780e76d0 | note | RECORD OF CONFORMITY: ITP Signed
cb18fa7a-7953-5024-bf9f-fbca1a03362b | note | IP
ac1d56af-a6c6-5894-b779-6bb103aad8a8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
477f7fd4-65c0-5393-9c5a-6115760a00ca | textbox | DATE:
da97a125-6f7a-40f4-9cc3-b3c920580999 | checkpoint | 2.9 Backfilling
69efbc75-b516-5415-8d2f-11f5b7005743 | note | FREQUENCY: Each Lot
3422f146-637b-5525-bf1f-32d952b85078 | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
e0811644-f252-59e8-9fdd-1f194052880b | note | • Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
8585e087-534f-5d0c-84b0-ba4fa83e182e | note | • Layers shall not exceed 150mm compacted depth.
ac766d5e-02f7-5273-b594-5ff64d4f3ebf | note | REFERENCE DOCUMENTS: 703.29
89a3ad6e-bb47-56c2-934d-d30c54722b18 | note | INSPECTION/TEST METHOD: Verify
4b674843-1e14-5c5e-a871-0802a9caade7 | note | RECORD OF CONFORMITY: ITP Signed
9ed7b165-3187-586e-bc6b-a2a70924b3fa | note | IP
cbe5599b-a580-5411-a4c7-c20845bfe42d | note | RESPONSIBILITY: Site Engineer
517933ed-00a3-526b-9e66-0be13bb0f115 | textbox | DATE:
fe8e5560-93b5-45d9-8f03-42c77a7db815 | section | 3 Completion
cdd3a873-f058-4769-9a9a-c264fdb6e870 | checkpoint | 3.1 Survey data captured for as-built purposes
eedb2395-4568-5bf6-8cf9-87ba203b5999 | note | FREQUENCY: Completion of each lot
da4b3c02-ff92-59df-a2a7-987c012d20b1 | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
4b30c2af-6e0a-5d75-b809-2aa50c3a4638 | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
80b19a0a-feb2-541d-88c9-674bad85c448 | note | INSPECTION/TEST METHOD: Document review
97b78683-4d40-5734-852f-3ce7b8d09d25 | note | RECORD OF CONFORMITY: As-built survey records
66e412dc-fd5c-5e0f-9fc3-31ec7300f223 | note | SCP
0e3eb206-1352-5e19-b815-af6ac17fd7e0 | note | RESPONSIBILITY: Project Engineer / Surveyor
cd5b8bba-022e-5c64-8ad2-468a7a69064f | textbox | DATE:
a3738825-7629-4d99-a816-b0a5529e6ac4 | checkpoint | Final Inspection
36a0bccb-45b2-5c5c-b288-f056f57a1863 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
64e871be-44dd-59e4-9fae-7aa7fd6e317b | textbox | Print Name:
46913ee6-df0c-5623-80fb-5dd73b9d4703 | textbox | Position:
ccc33581-8c96-5a87-a6dc-08684e3ecef3 | textbox | Date:
1245be45-ea5e-46ef-ad72-2ac884ddc23d | checklist | SYS - ITP-01-021 - Type B Fill Placement (old version) |  | ITP-01-021 - Type B Fill Placement
774c0881-5821-4c27-b84d-ba97c41bc96d | section | 1 Preliminary Works
7cc6fd27-659d-4a57-882d-c7c32bc741d4 | checkpoint | 1.1 - The current revision drawings/documents are being used including subcontractors copy.
71232857-f2b4-502d-a489-31debe9feb2c | note | Frequency: Prior to commencing
a1c95487-ea1a-5358-9e4c-3fc3e27fcd7d | note | Acceptance Criteria: Current revision drawing/documents are being used including the subcontractors copy.
6adb2ea5-df25-5b87-9012-62dcbefa0813 | note | Reference Documents: Drawings and drawing registers
4c505c57-05b7-5c20-83ea-68c3c0ef820a | note | Inspection / Test Method: Visual Inspection
c69e9ca8-773c-5c40-9277-abc8915b4d0d | note | Record of conformity: This ITP Signed Off
b12f3e19-a258-5e67-a5bf-48f368f968af | note | HP*
0a22d271-acb7-52a8-b44f-eba5f0e135f5 | note | Responsibility: Site Engineer / Site Foreman
a0e164d0-8fde-49c7-92c3-93246c717074 | checkpoint | 1.2 - Implementation of all measures and controls
5b72f622-3179-515b-8190-16b373105bbc | note | Frequency: Prior to Placement/ Each Lot
77045e21-3688-505e-b483-8c7c6bebbd5e | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
bc47b128-cab7-53c6-8bd8-8ac1fe076dcd | note | Reference Documents: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS, WP001.02
959b42fb-35a1-507f-b28a-20252b837200 | note | Inspection / Test Method: Visual Inspection
4137dd50-6740-5a09-96d9-bbbccc3d5960 | note | Record of conformity: This ITP Signed Off
73dd7be8-9431-5697-8435-f18b9d5e850e | note | HP*
fbe9cad7-0754-5bb9-843e-0857ec0a409a | note | Responsibility: Site Engineer / Site Foreman
36a08af3-2b72-47cd-901a-e0b119c6b3db | checkpoint | 1.3 - Verify Material
625273e9-8f18-5830-8976-80a4f18724c5 | note | Frequency: Prior to Placement/ Each Lot
f61bb769-0569-5b3f-80ce-5c65b3c101a7 | note | Acceptance Criteria: Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20. Materials that exhibit swells greater than or equal to 2.5% shall be classified as expansive and shall only be used as Type B material if approved by the Superintendent. Material within the top 400 mm of top of Type B material shall have a swell less than 2.5%. Materials that exhibit swells of 5% or greater are not permitted.
aefb8335-6e5a-56be-b010-53de4b02995a | note | Reference Documents: VicRoads Spec. Cl. 204.04(c)
74d3da13-3481-5d67-b91d-5dd9dccb73a2 | note | Inspection / Test Method: Site Inspection
0131bfe5-2238-5fc6-9bca-b29168178a47 | note | Record of conformity: Test Record (If silt is observed)
27c44a52-14b5-51fb-a6b4-acf517efa679 | note | HP*
3f1dc25d-a691-52fe-823d-8f3ee10c2b1b | note | Responsibility: Site Engineer / Site Foreman
baec3cbb-ce1d-41a8-9ee3-993b067eb78a | checkpoint | 1.4 - Excavation Permit
faca6bb1-a849-516d-80c3-6ea4c5412066 | note | Frequency: Each lot
8fb7f106-8c53-5e35-8b8f-ad126294cb5b | note | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
5bd7531a-c16d-56f4-8e6c-85316d7e19b2 | note | Reference Documents: Excavation permit
f3e89d86-637c-5712-9327-b6a74e878393 | note | Inspection / Test Method: Verify
4d9f9571-7b0c-54f5-a0d2-408b8a5835ae | note | Record of conformity: This ITP Signed Off
6074e4c2-ecbe-56c6-8bbd-5bcc16e0e4f6 | note | HP*
004c1275-7be7-55f8-986f-cbde04fece80 | note | Responsibility: Site Engineer
c4e77708-ee06-4d97-833b-82ee07446805 | section | 2 Construction Works
a642f953-830a-44c0-99b3-fb5961f3dc23 | checkpoint | 2.1 - Survey set-out
d7f4e5a9-ab61-5ecc-ba50-a223017480b6 | note | Frequency: Prior to Commencing Excavation
c6d89c44-5d41-552c-8826-11ca76a263a1 | note | Acceptance Criteria: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
9546e263-be4f-5d0f-81ec-0f7ba2e80c28 | note | Reference Documents: Latest IFC Drawings
84a03f44-1c35-5cdd-a9e1-d65107573ff3 | note | Inspection / Test Method: Site Inspection
6929a6e7-4a1e-5548-a8f3-8f0387e578f1 | note | Record of conformity: Survey records & pegs on the ground
805353ff-ed76-551b-b20d-2ca6747d9a39 | note | SCP
7435204f-f476-54a3-9ea6-602755197805 | note | Responsibility: Site Engineer/ Surveyor
39495f62-80e3-4363-83d4-9c4c4b2ad810 | checkpoint | 2.2 - Inspection of fill area
f18dbd7c-a38f-5458-b4b1-b51ae96a4460 | note | Frequency: Each lot
aa94aaa8-01f5-5241-8b1b-c049c331cb52 | note | Acceptance Criteria: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
7429e237-3d17-5b70-921e-ab5b1391b0fa | note | Reference Documents: 204.10 (b)
50470bd6-951a-58eb-9809-65ac455eed43 | note | Inspection / Test Method: Visual Inspection
bec62fee-dbab-5cbd-9c6b-62db2f230244 | note | Record of conformity: This ITP Signed Off
4aca0ab3-817f-5b1f-b0d5-afa3076404a7 | note | HP
f7711999-e19f-56ae-9e4b-5d6d85897617 | note | Responsibility: Site Engineer / Superintendent
d647836e-4e7c-4fce-9938-852a37010962 | signoff | HOLD POINT AUTHORITY
6783807d-c03d-4ca2-9c16-834d54f03f0f | checkpoint | 2.3 - Keyed fill layer
edd24767-c8b3-5c9e-8a46-23587addb611 | note | Frequency: During Excavation
8cf36c32-9f99-585b-bffc-1eddea296aef | note | Acceptance Criteria: Placement surface textured to ensure layers keyed into each other.
17aab429-aa84-5658-958c-f5d02697e0b1 | note | Reference Documents: VicRoads Spec. Cl. 204.10(d)(i)
f87f521d-63de-57ea-abbc-26624c123691 | note | Inspection / Test Method: Visual Inspection
599b3f8c-7dd8-5ca6-a47d-566fb3ac292c | note | Record of conformity: This ITP Signed Off
9987e559-474e-56d0-b718-c806d88d7246 | note | IP
d5f9185c-c390-5847-bf64-92ff5101a816 | note | Responsibility: Site Engineer
8b047c25-79fe-47fc-94a9-8b6303051eff | checkpoint | 2.4 - Layer Thickness
7593963a-3715-51d3-8784-afb9dc0e7e0f | note | Frequency: During Excavation
6655d103-8843-5167-8064-ad058a13e1f5 | note | Acceptance Criteria: Layers placed and spread in uniform compacted layers not thicker than 200mm.
8771d853-6825-50d0-b462-4506e21b256c | note | Reference Documents: VicRoads Spec. Cl. 204.10(d)(iii)
72d7ef36-81dc-5325-b9a4-364dfc6f5e21 | note | Inspection / Test Method: Visual Inspection
4dac1a1f-cbde-5474-8537-0cbdd934d8bf | note | Record of conformity: This ITP Signed Off
9a2b38a9-cbd3-5be6-b65d-0813f143f6b2 | note | IP
de5948d6-dd28-55d8-8542-6bfa4a336934 | note | Responsibility: Site Engineer
3bae4524-6e2b-4dee-8eb4-7c5682011c27 | checkpoint | 2.5 - Maximum Lot Size
9026d9d5-4708-5e7d-b3be-9b980de6328d | note | Frequency: During Excavation
c7942713-265f-5846-ba80-706cc2b2bbba | note | Acceptance Criteria: Lot size for testing is to be one day's production or 10,000m2, whichever is lesser.
593f10cc-2b9d-53cb-a18e-cfd592e8060b | note | Reference Documents: VicRoads Spec. Table 204.142
f2859522-e093-55f1-9544-9cd119af5b4c | note | Inspection / Test Method: Visual Inspection
9d4fc6e9-fe5b-56ec-a666-0d66ef3859fe | note | Record of conformity: This ITP Signed Off
6468ced2-3cba-58d0-b6f7-9b969f76ff25 | note | IP
2ae2c081-56c4-58b4-9521-d0913f150362 | note | Responsibility: Site Engineer
35ebc729-2d6f-4086-8a44-d457d8d093ed | checkpoint | 2.6 - Type B Placement
d335b1dc-0078-51dc-bea6-6f35b5e59291 | note | Frequency: Prior to Placement/ Each Lot
74b547bd-d07b-5e54-a30e-fa668bde5be5 | note | Acceptance Criteria: Type B material shall be placed in locations shown on the drawings, or if surplus Type B material is available, it may be used in locations specified for Type C material. The highest quality Type B materials available shall be reserved for placement in the higher levels of Type B fills being constructed. Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm. Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm. Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed. The material shall be placed and compacted such that voids are completely filled with fine material. Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones.
e130448e-fffe-55f3-8252-6e2ae25fcee3 | note | Reference Documents: 204.10 (d) (iii).
581f41c7-8851-5b55-af26-82dfad035d41 | note | Inspection / Test Method: Visual Inspection
0cb4bb75-0d3a-5b7d-afd2-de4d952ab4fe | note | Record of conformity: This ITP Signed Off
d98daa8b-98c7-5ae1-a8d8-82c047f66dc9 | note | IP
426ebda2-20e4-553a-b175-6c4b194cc06d | note | Responsibility: Site Engineer / Site Foreman
c9c412a8-262a-46c9-ab13-afe6869dc393 | checkpoint | 2.7 - Proof Roll
50ded1be-446b-52ab-8e62-0cf74fa3fca8 | note | Frequency: Each lot
2835875e-721f-5818-9e0a-36e961f170bf | note | Acceptance Criteria: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
3dadf1e8-db43-5db9-bb18-c3c1da8b21a3 | note | Reference Documents: 173.03, 204.12), 204.10 (b)
76c5f74d-a314-5aee-adfc-675db481c52f | note | Inspection / Test Method: Visual Inspection
4d3130b2-012e-5424-94b0-20622d175553 | note | Record of conformity: This ITP Signed Off
bc7ec8b0-8815-5af4-bb50-78f7ca2cdcd8 | note | WP
e95a0f79-fd07-5585-a370-8658de89a55b | note | Responsibility: Site Foreman/ Superintendent
18ee7b57-5f34-4ce3-8d63-a2b3fa5e167e | section | 3 Testing
3cecec3b-d7ed-46a2-8107-c0f2b6607d05 | checkpoint | 3.1 - Reduced Test Frequency
63c776e5-2f81-5ef9-9480-fd429f744612 | note | Frequency: Each lot
cf0e2dca-97bb-5b48-932c-55148afa3bb3 | note | Acceptance Criteria: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
f7a40f5e-266b-591a-8517-170e189cc5d4 | note | Reference Documents: VicRoads Spec. Table 204.131
a2ba9668-4f79-5372-a80a-ec8bb547bdbb | note | Inspection / Test Method: Test Record
47ff4f80-d4a6-5ae8-8680-c4b3f38ee7f2 | note | Record of conformity: Test Records
6985146c-a955-5da7-a765-daea64f81a44 | note | AP
074850d8-7868-50e0-a806-940fc2774810 | note | Responsibility: Project Engineer/Superintendent
bacbb1c4-ea93-426c-b7e3-1d934c7997b1 | checkpoint | 3.2 - Compaction Testing
992bd5b1-0fd3-5d8f-9b30-1516fdc429ac | note | Frequency: First lot then every Second thereafter
38785d07-75fa-583c-a3d8-e0d7413c42c1 | note | Acceptance Criteria: Type B compaction required for Scale B is 98% Characteristic Value of Density Ratio
f7d3d012-4a81-5f11-8c74-cb2d22abba1d | note | Reference Documents: VicRoads Spec. Table 204.131
690b87a3-b823-580b-9842-7283b79b1a53 | note | Inspection / Test Method: Verify
a2eec8ec-0adc-5cc5-b184-851e35dba104 | note | Record of conformity: Compaction Test Records
c38741a9-0020-506a-ba89-deb94db94141 | note | TP
ffbb2923-bbfb-5dfc-b2a8-cb1672c15cf5 | note | Responsibility: Site Engineer
03bb1d4e-a90c-4c12-83da-688b795797ed | checkpoint | 3.3 - CBR/Swell
6ce7cec4-7a6f-5486-ac59-5865fb3a22e8 | note | Frequency: 1 lot test to determine assigned CBR and Swell
19116bc5-5768-583a-a634-cae47926625d | note | Acceptance Criteria: CBR: ≥ 2%, Swell: ≤ 1.5%
4903253d-4176-5031-813d-b48b9258168e | note | Reference Documents: VicRoads Spec. Cl. 204.14(a)(i), Table 204.141, Table 204.041
b81ec86d-3be0-5729-8580-25481780e872 | note | Inspection / Test Method: Verify
1465d712-d796-5046-b47d-923e23286710 | note | Record of conformity: CBR/Swell Test Records
2537b0d1-6c63-5b74-88a7-845cdc967725 | note | TP
a3f7b4b6-16bf-5d7a-abf4-64d68f13603b | note | Responsibility: Site Engineer
f3dc91e0-a493-4d3d-8f73-e3c9c1643f68 | checkpoint | 3.4 - Survey Conformance (at Subgrade Level)
075fc5dd-1553-534e-87ed-975246c08cfc | note | Frequency: Each lot
37f9434b-0a45-5bf3-bc67-633022218684 | note | Acceptance Criteria: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031. Scale B: Range x = +5,-25 Max S = 15mm 40 measurements per lot
988d5f52-46bd-591a-88aa-4389e2c78f60 | note | Reference Documents: 204.03
a35c17cf-7543-519a-a724-43f16d0d2ca0 | note | Inspection / Test Method: Survey conformance point
8043d3f3-ac33-555a-9bde-631e76da4268 | note | Record of conformity: Survey report, Lot Register
c79965fe-186a-571c-a11c-9b4f4569906b | note | WP SCP
d137ba24-59b5-5d94-9f9f-377584e07baf | note | Responsibility: Site Engineer & Surveyor
f26e52a1-4d32-4aa6-bacc-1c392a0f29b7 | checkpoint | Final Inspection
3b325800-ae6b-50fd-bb84-dac8c79561db | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c4a5aafd-4f99-5886-bc5f-4b7a8aa8f6a4 | textbox | Name:
89fae9a7-ff5c-5aa4-bbb7-b4e79a2c4e02 | textbox | Position:
992c6925-f533-4f66-821b-c5c17d2aa641 | signoff | Add Signature
f3bf132d-7bff-46ac-a0e1-3c67e8480e19 | checklist | SYS - ITP-01-023 - Conduit, Pit & OCS Installation (V-Line) REV2 (old version) |  | ITP-01-023 - Conduit, Pit & OCS Installation (V-Line)
796ef1d2-8768-4326-8eca-825bf56ec5b4 | section | 1 Preliminary Works
476c9cb4-0953-4e69-803d-a40c3daddcd2 | checkpoint | 1.1 Check for correct documentation
1d131289-ccab-5e4d-beb8-3e82d228c713 | note | FREQUENCY: Prior to commencing any activity
ed11a414-53dd-5f91-90ac-291045aff067 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
2bcf3679-279c-57cd-8950-0299c40d9c06 | note | – using the correct and complete set of drawings
84f631da-83c5-5c4f-9d40-45011b8d61e1 | note | – all drawings are the latest revision
b2883bc4-8ca6-5fd5-8cca-a67759c71538 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
d966a4e9-b0ab-56c1-92fe-d14946c22362 | note | INSPECTION/TEST METHOD: Visual inspection
0a59a377-e868-5512-a819-75834ac895e1 | note | RECORD OF CONFORMITY: This ITP signed off
e36a0840-1e1f-5a2e-a946-297cfb600c16 | note | HP*
23358e97-4de2-5dbc-9d88-dc28f49e977e | note | RESPONSIBILITY: Fulton Hogan Engineer
9f4b5065-04e5-5747-a3e1-4aa8602428d0 | textbox | DATE:
f436ad84-0828-49fb-8244-004b32c8628e | checkpoint | 1.2 Implementation of all measures and controls
6e076509-edce-5f97-805a-9833665a46bf | note | FREQUENCY: Prior to commencing any activity
f5eb6ad7-72f9-5a7f-a815-60846bd33247 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
5bfa2278-4bc7-5b96-948e-53fb6af65a2a | note | OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
81fc0afe-7cc0-5ec7-89db-cc28dc054e6c | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
9a05718a-46ed-5c89-98d6-8b93378f6f99 | note | INSPECTION/TEST METHOD: Visual Inspection
b91b017e-f03e-5fc9-8c39-d038b6cab2e9 | note | RECORD OF CONFORMITY: This ITP signed off
d954a16b-b6f0-5071-8781-cd036b67b1dc | note | HP*
f18b9fe4-6cb6-5c4a-b5c4-b9aa0d04f9c5 | note | RESPONSIBILITY: Fulton Hogan Engineer
ffa16068-715c-5183-81a9-4330841511e7 | textbox | DATE:
1ec352c2-d568-4996-a79d-069b6df84a37 | checkpoint | 1.3 Materials
20cc6424-fdd7-5adf-a211-b7ee8706376c | note | FREQUENCY:
2e940b61-f226-5a00-9309-fe44ce8cbc64 | note | ACCEPTANCE CRITERIA:
63787b1b-2670-5c94-b121-f15ba11f4003 | note | REFERENCE DOCUMENTS:
89846e64-6f5c-5239-97bb-6cea451a8d32 | note | INSPECTION/TEST METHOD:
c5899624-8a28-5ea7-9e53-1049c89f7f8d | note | RECORD OF CONFORMITY:
68aa2c4e-0a60-5537-977b-2b704d78e03e | note
1cceafcd-d536-5a50-9fdb-1f343921e358 | note | RESPONSIBILITY:
27607b3d-1bdd-56ba-ba82-bd0373d170cd | textbox | DATE:
c267c5aa-c750-404d-abcd-609d7709e887 | section | 2 Construction Works
f83766a1-6859-487f-ada9-1efac0c06d27 | checkpoint | 2.1 Survey set-out
57a7d3bf-af32-5dce-8ff6-e29277d80a1e | note | FREQUENCY: As required
a3c2bdb6-de6e-5f79-902c-16864403faa9 | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
efcb2bd4-70ab-5489-96f2-eda05c8dee93 | note | REFERENCE DOCUMENTS: Work procedure, Drawings
dc63d9b6-63ce-507e-b8ac-4c8529460f86 | note | INSPECTION/TEST METHOD: Verify
76d03c44-a189-5108-8521-2a7dd85fb7e9 | note | RECORD OF CONFORMITY: This ITP signed
257566c4-7a4a-5b70-8b63-a33d4c3773d6 | note | HP*
f5a04495-92e9-5e45-a720-8f10974b9186 | note | RESPONSIBILITY: Fulton Hogan Engineer
e2632e6d-7fc6-5a3d-9351-738a64b36ea0 | textbox | DATE:
316b36d8-6684-4599-8d72-7edc82ad4e6b | checkpoint | 2.2 Excavation/Boring & Trenching
3190c5c9-7081-541d-bf10-247bbcee4ea6 | note | FREQUENCY: Prior to Backfill
f3cec537-1367-537c-8ad0-c2a9941b6a60 | note | ACCEPTANCE CRITERIA:
3af0959e-4212-56ac-b7ea-fbef2801dae6 | note | • Trenches shall be excavated to a depth required to achieve the specified depth of cover and drainage slope, plus an over-excavation of approximately 50 mm to allow for bedding sand.
05866dbb-108f-5462-b574-368bb0199792 | note | • The width of trenches shall be as required to fit all the conduits and pipes for services sharing the trench with specified separations, plus a further 50 mm minimum clearance from the outermost pipes or conduits.
5d138203-0b65-54c9-981a-496b8e72ef04 | note | • Where trenches are excavated across roadways, car parks or paved areas, the Electrical Contractor shall backfill the trench with 20mm of Class 3 crushed rock.
7d892096-65ab-5e5a-a51e-90ea3326a5e5 | note | • The crushed rock shall be placed in layers not exceeding 150mm finished depth and compacted to a minimum of 95% of standard density.
2e331450-c1ac-5f25-be91-75b378bb064f | note | • The backfilling shall extend for a minimum of 1.0m outside all paved areas and shall be subject to the supervision of the V/Line delegated representative.
892d2ddb-9774-51c9-b405-e3d63ed65de2 | note | REFERENCE DOCUMENTS: L1-CHE-STD-077 Sect 6.10.6
a173517d-ab66-56fc-90df-026fbdf1941c | note | INSPECTION/TEST METHOD: Verify
09fab28d-1720-5a49-ad99-249ddea485dc | note | RECORD OF CONFORMITY: This ITP signed
e68329f7-6487-5525-937d-3f33b30a4834 | note | HP
fd0aa9c2-ab9f-5856-b852-4b2ec81d2703 | note | RESPONSIBILITY: Fulton Hogan Engineer
c864577d-333e-5648-bb8b-6cfb096d7c52 | textbox | DATE:
744a9cd1-97dc-4153-8d63-c5d27b304d92 | signoff | HOLD POINT AUTHORITY
5ec495d3-9dbe-46ab-95d2-dad3d86c4f5f | checkpoint | 2.3 Installation of Pit and Conduits
f4b7246b-7ed1-5bbb-af34-d899e3781288 | note | FREQUENCY: Each Lot
708df6f1-6a5b-5961-b2f8-13f8ba87e570 | note | ACCEPTANCE CRITERIA:
72135643-2c07-5433-bad0-145736b98b83 | note | • Underground conduits shall have a minimum 450mm cover if around the site but away from the track corridor, should only be in the non-trafficable areas. If exposed to traffic, the depth should be 650mm.
55b0f4ce-894a-5a38-b2ae-4344c9d76647 | note | • Upon installation conduits shall be cleaned and tested using a mandrel of at least 90% of the conduit inner diameter and length three times the inner diameter.
e334bf41-bd48-5c41-b1a6-734eb8b3e3bd | note | • Multiple conduit entry penetration holes on a pit wall shall be spaced at least 50 mm apart in horizontal and vertical planes
9d6fb579-ebb4-5a10-bd7e-c5fa98e10c94 | note | REFERENCE DOCUMENTS: NIST-013.3 Sect 4.2
fdd6768f-66b1-53a9-bee8-fcf73c3d225e | note | L1-CHE-STD-077 Sect 6.9
889631c1-3f13-5d9a-b9a0-34c5b6ca2c3d | note | INSPECTION/TEST METHOD: Verify
c6ab82a5-19d4-5897-8737-11275e466e34 | note | RECORD OF CONFORMITY: This ITP signed WP
d5616502-801f-5295-b88b-c520a90b96fd | note | IP
4255db6b-409d-5ef8-826c-c25f2380efd5 | note | RESPONSIBILITY: Fulton Hogan Engineer
dd8a25b1-4ce5-5c5b-9ad8-e482dac9129f | textbox | DATE:
88832410-a987-4706-b695-080ce5203443 | checkpoint | 2.4 Back Fill of Trenches (Trafficable)
88e6cd74-70e8-58e9-ae2a-21d58c8b4f8b | note | FREQUENCY: Each Lot
186b3461-12f0-567e-881d-5c48916bcd9b | note | ACCEPTANCE CRITERIA:
fd11ba07-dce9-5a4a-82ab-ccf0b1e2ac04 | note | • Bedding: Graded recyclable glass in accordance with MTM standard L1-CHE-SPE-313
646486e0-6f23-5ab2-94bf-94f8e1990c52 | note | • Backfill: VicRoads 20mm class two crushed concrete base compacted to 98% modified relative compaction in 150mm thick layers
0a684467-3fa3-5309-9a1e-85f43e88291c | note | REFERENCE DOCUMENTS: L1-CHE-SPE-313
691ad6f8-fcad-5f24-90ec-e856c03e1da9 | note | Design Drawing
0d502e93-5106-53b4-8b25-1520deeb7b59 | note | MRP-708-C-AUR-DRG-20-TNT-CLT-0810
d6bcfa1e-7ad4-53b1-85eb-3f55d6b2b886 | note | INSPECTION/TEST METHOD: Verify
9e65bf73-af25-568b-a1f0-90e7fc36c6d6 | note | RECORD OF CONFORMITY: This ITP signed
dd3f8476-4910-54e1-be36-9145e7761472 | note | WP / IP
3df58188-a87d-5a84-ae80-941117dd5dca | note | RESPONSIBILITY: Fulton Hogan Engineer
edca805a-1b56-5eba-aab7-6943173b429d | textbox | DATE:
50080297-fc99-4fe1-a908-a8bd59ffc2ca | checkpoint | 2.4 Back Fill of Trenches (Non Trafficable)
8d9c58c4-4ce0-5f63-9213-cd461bad2cb9 | note | FREQUENCY: Each Lot
0807c81f-e769-5166-9bd4-eb3796f53b93 | note | ACCEPTANCE CRITERIA:
04ca100e-36d1-5781-9f22-124401c27376 | note | • Bedding: Graded recyclable glass in accordance with MTM standard L1-CHE-SPE-313
13cdc2d2-ad55-5cb7-bccc-994e01b4cdcd | note | • Back Filling: Site or imported material containing no more than 20% mass of rock fragments with size between 75-150mm with no rock or clay fragments greater than 150mm. Compacted to 90% modified relative compaction in 150mm thick layers.
62df8150-b5e3-5a53-aeb4-2039c058d914 | note | REFERENCE DOCUMENTS: MRP-708-C-AUR-DRG-20-TNT-CLT-0810
69e79998-e86e-5fe9-a55b-0853249d2fae | note | INSPECTION/TEST METHOD: Verify
0b7c03f5-2cb7-52c3-87bd-482b9b1eef34 | note | RECORD OF CONFORMITY: This ITP signed
b556b077-633e-5b33-b8bb-de5a5157f64f | note | WP / IP
fbe7893d-b51c-5024-a5b7-b547de945d05 | note | RESPONSIBILITY: Fulton Hogan Engineer
c0194f9e-6351-5dc6-bd63-2169e56d89f8 | textbox | DATE:
34ce7f22-52f1-4e98-b43b-2b415380a31d | checkpoint | 2.5 Installation of Draw Cords
888cff7c-f398-5658-add4-16542369ca1e | note | FREQUENCY: Each Lot
eade5609-9174-52c4-bdc9-9dce87dcdd53 | note | ACCEPTANCE CRITERIA: A draw wire of 6mm polypropylene blue/yellow rope shall be placed in each pipe and suitably anchored at each end. Pipe ends shall be sealed using pipe end caps or an approved equivalent to prevent the ingress of dirt or sludge into the pipes.
67b674c1-2996-5e98-8848-e48acc80b41b | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.12(d)
0d74b4a0-3c33-54dc-b5c3-60790dd3cbc0 | note | INSPECTION/TEST METHOD: Verify
5dfaa7be-07e3-5115-91d1-fcc0dba1e1b5 | note | RECORD OF CONFORMITY: This ITP signed
b8237713-f28c-5bc1-b51c-23c089e89451 | note | IP
3ed5e221-a347-564d-8ddf-ec1dbed354f8 | note | RESPONSIBILITY: Fulton Hogan Engineer
de2eca8e-c32d-5901-8185-feaf157c93b3 | textbox | DATE:
b631fc01-c815-4aa2-83ae-aea0cebafbc6 | checkpoint | 2.6 Installation of Marker Tape
109fdb36-9ff7-584a-93e9-3c2ec6de23c8 | note | FREQUENCY: Each Lot
c075e024-92f1-59dc-8915-0d0315d76499 | note | ACCEPTANCE CRITERIA: A 150 mm wide orange coloured PVC marker tape with the words “DANGER BURIED CABLES” shall be installed in all trenches at 300 mm below ground level except where cables are permitted in shallow trenches due to rock. In this case the depth of the marker tape shall be at the discretion of the Infrastructure Manager.
74ddd69c-9189-503f-b4ae-2aff2fa758e2 | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.11.1
b6d4883f-53ab-52db-b886-0e3c658156ea | note | INSPECTION/TEST METHOD: Verify
360d2333-8cb0-5126-af0c-d3e786b0015a | note | RECORD OF CONFORMITY: This ITP signed
fcbe7be1-b630-5752-bbfb-73aca8faef9f | note | IP
67d26d3f-c698-512e-afe6-694c9095601d | note | RESPONSIBILITY: Fulton Hogan Engineer
1f9de508-fca3-5f9c-a602-5ea99c244c10 | textbox | DATE:
b09bf544-2fae-4e93-a633-99794545ca8a | checkpoint | 2.7 Cable Pits & Pit Lids
6e9de7a7-fe68-52a3-aa25-9a0c88ffd6b8 | note | FREQUENCY: Each Lot
03f3c3bd-c013-50b2-b8a9-35227394bd76 | note | ACCEPTANCE CRITERIA:
1081bd37-ac5a-5435-bf79-ec45bab59372 | note | • Cable pits constructed and installed as per drawings
4f661c45-20ac-5cf0-bdf0-a1d38e6589c5 | note | • Pits shall be placed at each horizontal change in direction or at spacing no greater than 100m
81fbdc9a-c58c-5b86-8a18-a6e00892e26e | note | • Seperate pits shall be used for power conduits (orange) and communications (white).
9e56bed4-ad39-54d3-b625-0669ae194cf6 | note | REFERENCE DOCUMENTS: OCS Drawing Package
300ead12-1833-5401-8970-9d349b57c296 | note | INSPECTION/TEST METHOD: Verify
62fb2123-7ae5-5886-a1f1-a5c92f289c1b | note | RECORD OF CONFORMITY: This ITP signed
86c7758c-cfcc-5ea2-8c4b-c5431be73f9e | note | IP
0d6d93ba-d1be-5368-95c0-521d4d49b973 | note | RESPONSIBILITY: Fulton Hogan Engineer
bb062edc-4cb2-5f0f-a9bf-0ec4c02d9adf | textbox | DATE:
0c1702d5-efd4-425f-8587-f65866942c78 | section | 3 Completion
9f6a96f8-7447-4428-8ef3-a2acad2cd127 | checkpoint | 3.1 Cleaning of Site
0402b0c0-84de-5754-ab0d-1b33bcd58b63 | note | FREQUENCY: Each Lot
44050220-7fbd-560a-a6f1-d69129358865 | note | ACCEPTANCE CRITERIA: All obselete cabling to be removed during installation and disposed of appropriately.
99de3fa3-d398-5e5b-9825-09de8ae28a07 | note | Upon removal of all redundant signalling equipment; the site shall be cleared of all project scrap and associated rubbish.
9b585240-c8a1-5b86-8eda-054d55476522 | note | REFERENCE DOCUMENTS: NIST-012.2 Sect 23
c2c16b77-ba02-5308-be71-ffbf307dd0d6 | note | INSPECTION/TEST METHOD: Visual inspection
2d815059-5b6b-503c-809d-2429b563f5fd | note | RECORD OF CONFORMITY: This ITP signed
cbb2ff2a-3049-590e-94c1-a8723d8c79fd | note | IP
d367fe53-4645-5f6f-844b-5a1983b831db | note | RESPONSIBILITY: Fulton Hogan Engineer
6d4a2b9f-f240-5c5d-aee4-0c769aac3f3c | textbox | DATE:
861cf1e4-3370-48cf-a187-e2c971441ce6 | checkpoint | 3.2 Recording/As Built
2ef0a809-729e-5413-9ecc-f70c2bf70997 | note | FREQUENCY: Each Lot
1dd66f7c-0744-5743-ab98-253616d7fe79 | note | ACCEPTANCE CRITERIA: As-built drawings will be completed by the Contractor based upon the installed system by a process of editing the approved ‘for construction’ drawings.
0dfefef7-04ab-5711-9c1c-01f05ca4ce09 | note | REFERENCE DOCUMENTS: NIST-013.3 Sect 5.1.3
04ce1d0c-e937-570b-9345-b33eba66089a | note | INSPECTION/TEST METHOD: Verify
be693ccd-fae6-5ae2-b53b-48825fab4ecf | note | RECORD OF CONFORMITY: This ITP signed
48aaa107-6d71-565f-8c6f-487b4e13f13b | note | As Built Drawing
3d0f812a-cf98-58ad-9db9-9816a8708a31 | note | IP
69de795e-2a95-5b98-b38b-b6b1cf6dbd3f | note | RESPONSIBILITY: Fulton Hogan Engineer
f671a5d0-f3d7-58ce-a31c-a9b1473b5899 | textbox | DATE:
6900d92c-9097-49ee-a72e-307a8ebb8ee8 | checkpoint | 3.3 Commisioning
9473b617-ae7e-571e-9dd3-7b4ab4c4194a | note | FREQUENCY: Each Lot
78430b89-3a7b-5695-a77d-9ba99cd9fe47 | note | ACCEPTANCE CRITERIA: Commisioning to be checked against V/Line checklist.
52b6af1a-35b4-5bc3-a4d3-eb9c43a48c25 | note | REFERENCE DOCUMENTS: V/Line Commisioning Checklist
e43a2457-d9ef-5192-8b77-0cb3251fa768 | note | INSPECTION/TEST METHOD: Verify
a7e879a8-49d4-5975-872f-a050acf5bb11 | note | RECORD OF CONFORMITY: This ITP signed
7aa36f58-fcb8-55d1-9c77-4de2dacf4895 | note | V/Line Checklist signed
19317d4f-d1b2-5b6d-b52d-55204ef948d2 | note | WP / TP
69631b54-43e8-5b1d-80c0-9631a6380867 | note | RESPONSIBILITY: Fulton Hogan Engineer
bb944942-6411-5c75-a8bf-e1949e9ea470 | textbox | DATE:
94ac15c6-c4c6-46ec-83a7-656af8a63064 | checkpoint | Final Inspection
af49903c-0097-5c4e-a304-02d93165c1d6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1ce89ec9-81ce-56c0-a86b-706271c0d66a | textbox | Print Name:
81d89125-c344-51fd-94fd-bb06b194d586 | textbox | Position:
c9fdcbb4-d005-5143-8681-aede15fd73b5 | textbox | Date:
7e4e8877-b907-4ad2-89cf-fac08e798517 | checklist | SYS - ITP-01-025 - Structural Concrete Construction REV1 (old version) |  | ITP-01-025 - Structural Concrete Construction
7f96e167-5dc8-43a8-b63b-c3a295193c34 | section | 1 - Design and Submissions
7ec85a2c-15d1-465a-b6e8-0e20cde35a64 | checkpoint | 1.1 Check for correct documentation
72dee599-13d9-54c5-83c2-4e399225d03f | note | FREQUENCY: Prior to commencing any activity
09ab7b3e-849c-5b46-8435-7812737f18f7 | note | – – – – – – – – –
9f28bc6b-8990-5c60-87d0-ac50cb21a5ea | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
9a942126-7284-589d-839e-8b5984e8c63b | note | – using the correct and complete set of drawings
4abfc300-a79c-5377-826d-d5cf8792b905 | note | – all drawings are the latest revision
f539a284-f253-5a04-847c-da8ef5c9a7d6 | note | – – – – – – – – –
15858d36-933b-57ce-8ce6-09ed0be01808 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6063d63e-de7e-5778-b226-275068938f77 | note | – – – – – – – – –
60266d7b-401c-5faa-ba3f-db8678891331 | note | INSPECTION/TEST METHOD: Visual inspection
8148d1ed-9176-50f9-bd4f-3c0b93f2338c | note | – – – – – – – – –
f8497f2a-3cb2-5053-bb3b-0a910df5b573 | note | RECORD OF CONFORMITY: This ITP signed
1da395ec-20a7-596f-a295-a7e23807b898 | note | – – – – – – – – –
8303a715-0bce-52ce-9e49-00cd89397450 | note | HP*
ccf8873d-774d-520a-8b3d-349db6abadb8 | note | – – – – – – – – –
f9a87977-74f9-58b7-b96a-8c106ed36091 | note | RESPONSIBILITY: Fulton Hogan Engineer
ea0b81d7-ae97-5cc7-ad02-9078aaf5acfe | note | – – – – – – – – –
49ca5cd5-ec80-5223-92b8-eaaf8306c42d | textbox | DATE:
cece1d10-cfdf-4c84-b0bd-47c05b2dfe46 | checkpoint | 1.2 Implementation of all measures and controls
6a39de2a-c1a6-5f7b-a906-96e3b50dd530 | note | FREQUENCY: Prior to commencing any activity
7e3e09bf-52d5-549c-9451-972d8e9a840b | note | – – – – – – – – –
2ca6721a-9a3f-597b-924a-85e21a0b996d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
d0aaa2a0-1210-5112-a59a-8c7473afed81 | note | PSP, EMP, TMP, SWMS & WP
567ea0bc-6d1f-5915-8ad1-60ca7d117945 | note | – – – – – – – – –
41172c63-6c74-5213-9511-25ebc3e140fa | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
bb218baa-b67f-518f-8d32-a9078a8427d2 | note | – – – – – – – – –
eb0752ce-54c2-50ac-a51d-fa0744e01eca | note | INSPECTION/TEST METHOD: Visual Inspection
cc183b74-de29-5e41-bc43-710729b30dfc | note | – – – – – – – – –
9d6834bd-24ac-5466-bb90-3b239727fc34 | note | RECORD OF CONFORMITY: This ITP signed
fbbbc47e-1902-5b11-b453-4f0246758cc7 | note | – – – – – – – – –
5f79da9c-78f3-53a5-88c8-1ea7f7188d9e | note | HP*
952c0e03-de9b-5a59-a5b2-d564839e11ef | note | – – – – – – – – –
9795ee16-4e3b-50e5-a2f2-a5ed200ec588 | note | RESPONSIBILITY: Fulton Hogan Engineer
602ab288-cf8b-591a-a160-e2cbda4d39a5 | note | – – – – – – – – –
e79d2d19-c031-57e2-bb23-b6c220fcfb0e | textbox | DATE:
9814fda6-640d-432e-8206-baa6c61f48c8 | checkpoint | 1.3 Approval of Mix Design
bc0068f1-b756-500a-844d-aa7a371199b3 | note | FREQUENCY: Prior to the first concrete pour
711a8ce5-ab10-58c0-97df-15f1aba1cc65 | note | – – – – – – – – –
7afd4744-3e32-5f0c-8bb0-5e5c1ce52fc9 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
aab81743-c4c4-5363-8131-ba35ee5c687c | note | – – – – – – – – –
0bf44b4e-7c0f-5ac7-906b-b09328df8edc | note | REFERENCE DOCUMENTS: 610.07
a0c90efa-b33a-5dd7-b813-aae5f39e9880 | note | – – – – – – – – –
99c08fd6-9ee4-5966-a509-d3ec6d9a7296 | note | INSPECTION/TEST METHOD: Verify
2db26b84-a30a-54bc-a416-046fd9be7e1f | note | – – – – – – – – –
5d6e35d1-47d0-567d-8798-681fbca40eb5 | note | RECORD OF CONFORMITY: This ITP signed
1a3d1222-623f-53e6-975d-c7128fe1510b | note | – – – – – – – – –
9a364cfb-11c0-5f6c-bfc6-6d84683682d2 | note | IP
d1d1bb13-fefd-50eb-989f-0c229166f137 | note | – – – – – – – – –
0b58b651-aa0e-5eec-8e1e-cb56326931a8 | note | RESPONSIBILITY: Fulton Hogan Engineer
7beebb32-9214-5803-b5ef-4072964063c2 | note | – – – – – – – – –
6c54aadc-67d8-5028-8e82-36af629ced95 | textbox | DATE:
c93d1481-f40e-458c-83b5-ee5daa6c7310 | checkpoint | 1.4 Reinforcement schedule
ec50e606-3d3c-58a0-b8b9-507c9f507ecb | note | FREQUENCY: Prior to concrete pour
d07c796c-14da-571a-ab41-1f2e5f641d7e | note | – – – – – – – – –
3e9330d7-14cb-52ac-a188-37ec3d611c5f | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
edc43385-94ea-542f-ac54-65056549b757 | note | – – – – – – – – –
7744630d-57ff-5415-8abc-091880cc00a7 | note | REFERENCE DOCUMENTS: 611.04
479eec80-2dd8-5ea1-89d3-0b032dc4a0c3 | note | – – – – – – – – –
45758aff-881d-5283-9d6a-6ef4c5ccd405 | note | INSPECTION/TEST METHOD: Verify
175e392e-f5e6-51e6-ae1f-95502cac17c7 | note | – – – – – – – – –
75e2d1cd-30f1-531a-87c6-38c865d5a0af | note | RECORD OF CONFORMITY: This ITP signed
f2d7c256-b3a4-57de-b812-63f7dbf9debc | note | – – – – – – – – –
24c6e5cb-7d70-5c24-85b6-9a56b1122ed1 | note | IP
2f29c34d-acb1-5d84-9c09-e292963f5cde | note | – – – – – – – – –
a734b4a8-4004-5aba-8de5-3dc3e8df1513 | note | RESPONSIBILITY: Fulton Hogan Engineer
5fa3da63-7a04-5a06-b88c-a43007322ec8 | note | – – – – – – – – –
c41945ae-f407-5dd1-8784-5f18aa8a891a | textbox | DATE:
296e7a6c-eb63-418c-937b-e34ab200885b | section | 2 - Construction/Erection of Formwork
19a0018f-bd0b-4d59-82f3-3aeefe06fea7 | checkpoint | 2.1 Excavation
e59d411d-fa97-5919-ab0b-4cdadae4fd24 | note | FREQUENCY: Prior to concrete pour
92aa11cf-a8ee-55ca-ba79-a727fb1b0002 | note | – – – – – – – – –
7fcf2881-a0c3-5a9f-8a30-23dddcb5353c | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
f1dc0d3b-6aa0-5548-93f2-0f340d165139 | note | – – – – – – – – –
6b772744-4329-5d68-826a-a903a5847cad | note | REFERENCE DOCUMENTS: Contract Drawings
316e5ced-29d1-5c26-9868-81f41b68fc92 | note | – – – – – – – – –
80130165-fb20-5092-8d91-50f2b5931c2a | note | INSPECTION/TEST METHOD: Inspect
0469c45f-b405-5129-9bff-195708fb9590 | note | – – – – – – – – –
559a8df1-3a99-5479-964d-20fcd2187af1 | note | RECORD OF CONFORMITY: This ITP signed
f2e2d32a-e731-54c9-8473-a4b9a7b9a7f7 | note | – – – – – – – – –
aab0363a-ee67-568e-99d6-534147456df6 | note | IP
b723fb8d-fdd9-572b-801f-30f19352f403 | note | – – – – – – – – –
0a007a26-3ac4-59c2-bc3e-015feb1d05a5 | note | RESPONSIBILITY: Fulton Hogan Engineer
125b6c13-463d-5237-90d8-14d4e0a878b8 | textbox | DATE:
d7a1742d-b959-4313-a83a-3efb150e0bac | checkpoint | 2.2 Construction Methodology
cfd1ead4-ec1f-5686-ae7c-aef19e663a45 | note | FREQUENCY: Prior to erection
417cef7e-dcb5-5543-a9c8-d8cf7fa458c5 | note | – – – – – – – – –
58e210e3-f2a7-5264-86ae-91956a1755f6 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
ac053183-d48d-57b0-a02f-857963bdb7bb | note | – – – – – – – – –
206090a6-0c6d-5ba9-8df9-a82213b8eab8 | note | REFERENCE DOCUMENTS: 614.04
0756ea27-5151-582f-8788-da51a6846777 | note | 614.06
62af8f02-1336-5ec5-86c2-5efbe7d3f007 | note | – – – – – – – – –
cf75fd92-628f-534e-a17a-efe3c5a51eb7 | note | INSPECTION/TEST METHOD: Verify
e956722c-11dc-5ff7-9545-cd8f566a1222 | note | RECORD OF CONFORMITY: This ITP signed
be41434e-59a1-55f3-b3bd-f0315cec3605 | note | IP
6661b9fb-87f7-542f-8d64-2281b364114a | note | RESPONSIBILITY: Fulton Hogan Engineer
180df3cc-8289-5711-8a37-e790dd33e362 | textbox | DATE:
e22ca495-5bb1-43de-bc8a-7313f3fe095a | section | 3 - Pre-pour Planning and Inspection
c16617ec-59d8-47b1-9a99-2eddf57f7cc3 | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
34e33778-804a-5c41-b113-7a2e0ad7ca6c | note | FREQUENCY: Prior to concrete pour
97805ac1-f228-58af-8948-44c292e7c171 | note | – – – – – – – – –
940673b6-885b-57b3-a8ea-b20ba8d5d50f | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent.
75f0a31d-df6c-58b1-9528-31e984bbc5cf | note | – – – – – – – – –
a27e7144-70ee-5add-8457-ebdf59277e07 | note | REFERENCE DOCUMENTS: 602.03
6ac286a7-1ae5-50f2-aefa-b6f4fcadd3d6 | note | – – – – – – – – –
197bfd90-f3d5-5577-a44e-3a2bed17281a | note | INSPECTION/TEST METHOD: Verify
024519ba-c146-5c2c-91ad-4b8e42fcc578 | note | – – – – – – – – –
e7e63879-5de4-5d99-8351-15c7250905ee | note | RECORD OF CONFORMITY: This ITP signed
e5cc82d1-80c7-5535-8004-da481e576adc | note | – – – – – – – – –
5e40960b-e100-5e2b-9100-61681c481899 | note | HP
8c5db70f-42e2-57cc-9cf2-c77ed79975dd | note | – – – – – – – – –
45c2cf35-6c3a-5bff-a6c2-0db3125196a3 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
9a313602-8148-53f3-842c-01ec1d90d428 | note | – – – – – – – – –
84b54ea0-774e-5ed0-878b-23bf9770904e | textbox | DATE:
dc784f90-b091-4440-8579-c3ab51ddad08 | signoff | HOLD POINT AUTHORITY
c9c56db9-f8b1-4239-baad-ce2ec4134590 | checkpoint | 3.2 Formwork levels and position
a98e7323-2cc9-5447-a56b-6e48a8bbb8df | note | FREQUENCY: Prior to concrete pour
835f1670-791b-537a-9bb7-bbbd78c1ec28 | note | – – – – – – – – –
8341f184-9665-5392-8b1d-cc16f61bfe1b | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
2dac292f-fa85-593a-b2f5-e91559ef65c7 | note | – – – – – – – – –
a5f4fa5e-c1ee-5317-8ae7-5023c18ca125 | note | REFERENCE DOCUMENTS: 614.06
10ffa8f5-99fc-5ef7-9f08-492c94212455 | note | – – – – – – – – –
95ef3503-a788-5dae-b4d6-aea3cdbd753b | note | INSPECTION/TEST METHOD: Verify
b747ba63-bed3-5ff6-abed-5c34cc24f5e6 | note | – – – – – – – – –
a687f56d-13c0-5561-847e-dd25c84d5571 | note | RECORD OF CONFORMITY: This ITP signed
7c3c6dbd-220a-53c9-8b02-60b3f2152793 | note | – – – – – – – – –
be442461-7341-59da-b97d-e4a9799cdc94 | note | SCP
a3d38e8c-236b-55d7-a919-377baa4e6841 | note | HP*
e2d234dc-7143-54e2-afee-186b40edea69 | note | – – – – – – – – –
dd850839-ba0e-5ec9-b636-aeafcad163dd | note | RESPONSIBILITY: Fulton Hogan Engineer
8a31a81a-3a43-5fcb-a7aa-60cf6bdb1277 | note | – – – – – – – – –
a95e10dc-706f-509f-b244-ab3d3bcc7ebb | textbox | DATE:
f6426335-db42-400c-ac7c-61c2dbafb5c4 | checkpoint | 3.3 Location of splices
f2432ff2-fe0e-55a9-a365-d42201a80b44 | note | FREQUENCY: Schedule Review
09ffffd5-2ddb-5633-9f65-6a6247b7a2fb | note | – – – – – – – – –
31ccc91d-9730-592f-963c-e5ffdbea4216 | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
1082a544-2bab-5006-8b14-6630bbf94f7b | note | – – – – – – – – –
3872bb29-4a10-569d-a6a1-671016d9f692 | note | REFERENCE DOCUMENTS: 611.11
ce26272f-d7a2-558a-aab0-f5dbfb9cc3df | note | – – – – – – – – –
e346c46a-8139-5de7-9d8b-6261e77533dc | note | INSPECTION/TEST METHOD: Inspect
4dfe0e72-cfbb-50a5-ae91-bea09c108f80 | note | – – – – – – – – –
a0796bcf-3f78-52d3-bdb8-e0dd56ce0e03 | note | RECORD OF CONFORMITY: This ITP signed
ef9205c0-d823-5476-b719-34d058563603 | note | – – – – – – – – –
6ced437f-25cd-5569-ac62-b80566b4b8e8 | note | IP
772fc7fa-3e4a-5a83-9d02-67194c78711f | note | – – – – – – – – –
96e43575-abde-5e54-a617-4ef496ead60c | note | RESPONSIBILITY: Fulton Hogan
004a4fb6-8306-5204-8465-7e3be307d5f1 | note | – – – – – – – – –
d9f3b947-3dcc-53aa-bcc6-5a3b83ef9177 | textbox | DATE:
4937cfa4-8406-4863-9acd-c3f8026fdc8d | checkpoint | 3.4 Cleaning formwork
5c1b94ac-da76-57a7-b500-9e49d46eeecb | note | FREQUENCY: Each concrete pour
f8af1082-3a37-5b94-aa86-2b58661a725f | note | – – – – – – – – –
858cb2d6-ac14-5191-a212-0548e607c66e | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
e208d91c-0e75-5be2-a946-4d8d331e7777 | note | – – – – – – – – –
ea72be3a-a21d-50cd-9d7a-e0c5e490456b | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
813f2c9b-e663-5dd0-a247-1ce06309b40a | note | – – – – – – – – –
7732d582-230e-519f-bb06-acefd3d1ab4c | note | INSPECTION/TEST METHOD: Verify
794479da-c82e-51a0-9c73-7345306e5139 | note | – – – – – – – – –
a07fe559-9bce-5080-8495-8b9bfc517911 | note | RECORD OF CONFORMITY: This ITP signed
8c7fe3f8-eaec-5594-8619-12d8dac4d022 | note | – – – – – – – – –
dd376d54-4ea1-544a-a15c-2b19b2262c21 | note | IP
7aecffc5-0ad2-563a-967f-db15e88e44a8 | note | – – – – – – – – –
c2e46dbf-69a7-5d02-ae6c-6c704bb70b62 | note | RESPONSIBILITY: Fulton Hogan
12c45c34-87a1-5479-ad47-3dd52b1d5585 | note | – – – – – – – – –
83df8a1d-dc03-541a-a639-a6253f8254db | textbox | DATE:
f852b749-a2e3-4577-b694-b32f9a35b1c3 | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
672fe9bb-b890-53c9-aef8-14f4dd637534 | note | FREQUENCY: Prior to concrete pour
6c5ea910-2d58-5970-962f-ae73e86a49cc | note | – – – – – – – – –
c522800a-5767-5802-bd01-65d2ee6eef4f | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
994cf3d6-712d-5b81-be3d-25c9a3f6258a | note | • Pre-pour Checklist completed and signed.
6c2bd9e3-effd-5457-9222-7e6ebdb4d62f | note | – – – – – – – – –
cf51dff2-d1ad-5cfb-94ac-301db11a5047 | note | REFERENCE DOCUMENTS: 610.18 (a)
c328b283-6fee-5faf-a6ba-0940fe4dfed8 | note | – – – – – – – – –
7c136405-1670-5670-b64b-ce9bd98227bb | note | INSPECTION/TEST METHOD: Verify
4ec1bd67-72bf-562d-ac48-8970d25e2f45 | note | – – – – – – – – –
92432221-d251-5ccf-9a37-324d102f41f3 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
e9edeb97-f5b3-55eb-863c-8ece3ec666dc | note | – – – – – – – – –
a314c184-75e9-5c4c-8634-f2a16bf8464f | note | HP
30757c12-9e16-57d7-b381-9d0bc70a5858 | note | – – – – – – – – –
bfebb767-4738-5fa0-8dd1-d5075a9505c5 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
b8983389-146f-5c50-ba88-51488228d650 | note | – – – – – – – – –
d808a995-3ee8-576a-b386-ccf557f90b20 | textbox | DATE:
f3121472-3296-4940-8a94-f01994ec7610 | signoff | HOLD POINT AUTHORITY
ab9d6f3c-b913-44c6-a71d-cc2eb2bf96a5 | checkpoint | 3.6 Monitoring weather
bd2feacb-5090-5c97-867d-efc6c803af70 | note | FREQUENCY: Prior to concrete pour
bad9bf77-37ac-5f50-8c31-72609d30eb73 | note | – – – – – – – – –
de17b638-fa83-5d17-9688-0241108923ca | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
36ab773a-1859-551e-87c1-a81d7ab1c42a | note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
4ac12dfa-e0ae-5ecb-a82c-fea10fd04780 | note | – – – – – – – – –
42ab8fa4-3adb-5003-a3db-a31bde50bffe | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
70a4cbfe-e2ef-5ccb-ac3d-4621402494c7 | note | – – – – – – – – –
59d8ef2c-e0cd-51bf-bb36-fec669778134 | note | INSPECTION/TEST METHOD: Verify
a696b7f8-0696-5160-ab86-8dab9390af15 | note | – – – – – – – – –
ce5f551a-dc30-5450-b7a9-18a38c91941c | note | RECORD OF CONFORMITY: This ITP signed
2e4c74a1-45c9-5359-88d0-37df7aca8f3c | note | – – – – – – – – –
6ab0925f-52fd-5f2f-af9d-17c6383146c2 | note | IP
71d95b9a-e262-5fd8-827f-3eb0635ed874 | note | – – – – – – – – –
b3250589-5d42-5350-8992-54197f12db38 | note | RESPONSIBILITY: Fulton Hogan
8c5d1eaa-1111-5ab2-a209-2549ab2d6a92 | note | – – – – – – – – –
ae953b0a-e7a8-5b1d-bd9e-95fb0d0be7d7 | textbox | DATE:
9ae55a6e-1f59-4d26-8f63-f36a63f195d0 | section | 4 - Placing and Finishing Concrete
c82ce15f-d354-44d7-9d78-1f6c0311f7d3 | checkpoint | 4.1 Carry out sampling of concrete
b2b951e2-18c8-5749-963f-77f87352fd39 | note | FREQUENCY: Each concrete pour
b5e6bd96-cb2d-5047-80bb-236af66e4ab2 | note | – – – – – – – – –
a9a5d029-0936-5cf6-beee-007de90c39b4 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
99385e79-f100-5f21-9a69-9051acb964eb | note | – – – – – – – – –
8f766064-31ea-501a-a7ac-def8243f7032 | note | REFERENCE DOCUMENTS: 610.16
e29ad8f0-d2a9-53f0-8b2c-d43d43264d30 | note | – – – – – – – – –
c9f2259b-df05-5d89-aeb7-de0b16c93f8c | note | INSPECTION/TEST METHOD: Checklist
9b6f2cd2-0961-5a2e-aae8-eee5bbc2340f | note | – – – – – – – – –
32e4a6f6-6f13-505e-8828-434720180fe5 | note | RECORD OF CONFORMITY: This ITP signed
36509617-b78e-5e57-921a-8c0fb035b909 | note | – – – – – – – – –
7808234b-679c-5e16-9f26-ce8491edfd56 | note | IP
349c25fd-3e67-5f7a-886e-e0a3d2ed5598 | note | – – – – – – – – –
56ef4470-b8ee-57ec-9249-f904bbc2d108 | note | RESPONSIBILITY: Fulton Hogan
ac8a12bf-b5c9-5df8-81e1-352a32426dc8 | note | – – – – – – – – –
74aa27ac-f6f0-5977-a7f3-27255710b784 | textbox | DATE:
a8a45cc5-ea71-458c-9a0d-1a82c46e253f | checkpoint | 4.2 Discharge time
1508aa20-e4ba-58ed-9875-f07639e61395 | note | FREQUENCY: Each concrete pour
6aefd64f-5da6-5ffe-97b4-a4143bd8be65 | note | – – – – – – – – –
4c429dda-c830-5e17-aec6-06a290138b30 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
aa3a79c1-426c-5220-bff2-9e1ecf6625f4 | note | – – – – – – – – –
6eb330b7-b62a-514a-933a-717894ef6e36 | note | REFERENCE DOCUMENTS:
a4276a85-07da-50ed-97d9-d30e652fd632 | note | – – – – – – – – –
92139397-8f1f-501d-95c9-ed41bd139188 | note | INSPECTION/TEST METHOD: Verify
45409636-be84-5f75-9b8a-0fbb5a7caac0 | note | – – – – – – – – –
dd73ef8c-cb26-5387-952e-73aefb585add | note | RECORD OF CONFORMITY: This ITP signed.
4f18ebff-1ce2-5375-9968-5508febd1eb0 | note | Accurate Site Notes & Load Mapping
e966afed-6259-586c-a520-92f14c120304 | note | – – – – – – – – –
59e91f24-27d7-5b53-ab90-fb01775343aa | note | IP
87beb616-1232-5e4a-9875-53ba09827a18 | note | – – – – – – – – –
87136c84-7347-5a62-aed8-e1e8aab2cb91 | note | RESPONSIBILITY: Fulton Hogan
a272274c-71a3-53ed-9d8f-9a4178039224 | note | – – – – – – – – –
533433dc-814c-5d33-982e-17e102179198 | textbox | DATE:
c6a1ddfb-5c60-4107-8fa4-9a9cd0248d1b | checkpoint | 4.3 Methodology of placement
b7a24421-8f06-5969-bf9c-50b809af155b | note | FREQUENCY: Each concrete pour
b2555ddc-0b64-56ed-83a7-f418e46ae30c | note | – – – – – – – – –
bbbe35f5-ebd3-5aa7-9351-d49c2cf72015 | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
3c594887-404a-5c92-ae0d-442cd6c6f574 | note | • Concrete shall not be moved horizontally by vibrators
32ee91a9-fa2f-5e90-a5ac-844f753e5d85 | note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
e4ee1dc6-ed82-50c0-8c88-17424da590b2 | note | – – – – – – – – –
62c4e547-cb89-5a87-9407-e31e023264c2 | note | REFERENCE DOCUMENTS: 610.18
6c617369-b1d2-50fd-ba81-72d13fc74b4c | note | – – – – – – – – –
927009ee-dbb4-54fd-bdd4-07b6d634142d | note | INSPECTION/TEST METHOD: Verify
af6f2110-5d92-504d-96a6-4ac47716e4be | note | – – – – – – – – –
8c3645c5-2222-520b-bbef-c8e074a8b675 | note | RECORD OF CONFORMITY: This ITP signed
a24c969f-7473-5d5a-936f-79795287a875 | note | – – – – – – – – –
54f8fbad-20d3-5348-8139-925251607399 | note | IP
656e08d8-41da-5d9e-802a-d4fa143f8b6c | note | – – – – – – – – –
de4be0c8-b9f7-51d8-ae81-0ca207a205fe | note | RESPONSIBILITY: Fulton Hogan
c08e3e97-adb8-53f5-a04b-58fa59decc8a | note | – – – – – – – – –
4e797398-41b4-581d-a7cb-20f5f1064d45 | textbox | DATE:
d5a7f4a2-961d-4a2d-a04a-8cd9978fa917 | section | 5 - Post-pour Details and Inspection
61cd2411-b86f-430c-8577-0964e7d138d7 | checkpoint | 5.1 Curing
598e322d-6709-5b95-8914-9cbb3946b594 | note | FREQUENCY: Each concrete pour
91900fd6-177b-5d61-b87a-01126eb6e049 | note | – – – – – – – – –
702f38d8-0719-5549-b38c-ebdca09eb4e3 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
6a1bcbef-4ce6-5446-b402-a9fcd8f52fb4 | note | – – – – – – – – –
d9f433ba-db0d-559f-b4f5-9ef8e1387a70 | note | REFERENCE DOCUMENTS: 610.23
26bb5fa8-ef91-5b65-a795-79f38c9ea696 | note | – – – – – – – – –
e8f76224-7f02-5402-ada5-6872920a2a06 | note | INSPECTION/TEST METHOD: Verify
a410a46f-7315-5368-b6bf-01fd8acfdcf8 | note | – – – – – – – – –
8e721b07-471f-5b42-bbc3-b1418bb80edc | note | RECORD OF CONFORMITY: This ITP signed
f365958e-fc55-55b2-868b-61d75f921560 | note | – – – – – – – – –
ee62b8bf-e175-5ac0-854e-10b06566a37c | note | IP
9051ee5f-253a-5a69-b39e-513cf22473ce | note | – – – – – – – – –
e3b33b5a-bbe6-5bcb-adb7-995fc2a09be0 | note | RESPONSIBILITY: Fulton Hogan
1ed31e52-8980-5ef7-b1ef-48600a4c0fb6 | note | – – – – – – – – –
91c048e5-c1fc-5598-967c-b73bbff17c7a | textbox | DATE:
60d315d2-54a8-4f7e-a206-52c4e9c1dba1 | checkpoint | 5.2 Formwork removal
5fe31032-e64e-5087-838b-915466d153a7 | note | FREQUENCY: Each concrete pour
e35cc6ce-767f-5ce4-820a-380164dc3470 | note | – – – – – – – – –
abaa0955-71d0-51f1-9c7f-8c58b131ae78 | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
c9bb71fd-4ec7-5209-865a-0003e4be1b0c | note | – – – – – – – – –
b90bbffc-2071-52f1-8373-9189695fbb1a | note | REFERENCE DOCUMENTS: 610.25
a803e3ce-015b-5f1c-b33d-8f3f8d552b1b | note | – – – – – – – – –
13f789a9-0bfe-5183-b79d-ea2c4b82e036 | note | INSPECTION/TEST METHOD: Verify
4ff10b18-2627-5b7b-8772-c80f43d6e058 | note | – – – – – – – – –
6d5b424d-6e11-5a8c-9b43-1cdf8112add8 | note | RECORD OF CONFORMITY: This ITP signed
b78b7d9e-e55e-57a2-8696-918f97058058 | note | – – – – – – – – –
c95026f6-5ca6-55cb-8809-fe0e8087ac4a | note | IP
bfd7a8b5-8e25-5962-9efa-ac98e01284f7 | note | – – – – – – – – –
e005cc2e-64ef-5e32-9e21-54696867e1dd | note | RESPONSIBILITY: Fulton Hogan
4cb20ab5-b9e8-5a4e-b343-288a530f4c81 | note | – – – – – – – – –
f1581f5f-ecbe-5ada-b17a-c33af06c8278 | textbox | DATE:
f56bca9c-b41e-47ef-9e70-a21aed1a2c86 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members
169fc08a-919b-5f03-9657-767a6c345145 | note | FREQUENCY: Each concrete pour
6cd2b063-86fa-5d3d-89ba-5d493feccb4e | note | – – – – – – – – –
f9718eaa-64df-50b8-b2a9-56c9db43e5ea | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
36b7bfbc-3b64-51b6-8570-760dd6364512 | note | – – – – – – – – –
d06dc5f7-307f-553e-b7cf-a6aa872f360f | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5
9916ded6-622b-5f0a-94ad-afb552ed4cff | note | – – – – – – – – –
170d0b29-4edd-55f3-bb6b-841aebc71331 | note | INSPECTION/TEST METHOD: Verify
dbeebb40-a6a1-5582-8be2-e584ee44edb2 | note | – – – – – – – – –
cd07858c-43f8-52ad-ad86-72b390599c8c | note | RECORD OF CONFORMITY: This ITP signed
8812469f-5605-572f-b333-9d4c4104ce3a | note | Post Pour Checklist completed
467da28b-e99f-5159-98a6-8fcc9cbe815c | note | – – – – – – – – –
3296e0d6-30ba-5a9d-a522-62ef580525d6 | note | IP
77e938c1-8cae-56d9-8519-ff819c194acf | note | – – – – – – – – –
61a7a100-79cc-557b-89c2-49d5bc82f42c | note | RESPONSIBILITY: Fulton Hogan
47b7ef0d-59b6-5768-8c49-d645c212fe5c | note | – – – – – – – – –
3b28ced3-e209-5ac4-b6c5-8dbe062d27ab | textbox | DATE:
31a145da-44e9-4242-bcb4-5338f37b9509 | checkpoint | 5.4 As Built Drawings
05969b29-66a3-58d2-b0dd-a70d93419fc5 | note | FREQUENCY: Prior to lot closure
544fab11-4bd1-5fac-b2ab-b29cd24bdb4a | note | – – – – – – – – –
01799171-b155-5c34-8dd8-de375715463d | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
e58966ab-3900-5afc-a1bf-7544fd751b4d | note | – – – – – – – – –
bbadc25f-c75b-5aed-90f2-131a68f00b43 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
bd5f0775-0442-504d-bc17-936e40843e03 | note | – – – – – – – – –
37e59b66-0f4f-51d7-85dc-280568e2e317 | note | INSPECTION/TEST METHOD: Verify
1a92f986-fc70-5f9d-b745-553503cd00f6 | note | – – – – – – – – –
ef8af0c8-1f67-5bdc-96f2-06d024bab3dc | note | RECORD OF CONFORMITY: This ITP signed
5e225183-7542-55f0-be22-ed622993eead | note | – – – – – – – – –
bd246823-5755-5a85-a7df-01c734bbc18d | note | IP
512a4795-5109-5f4b-9c8d-219db0a7d82c | note | – – – – – – – – –
1647363c-4ad4-598b-8d81-2fa3e77bd9ff | note | RESPONSIBILITY: Fulton Hogan
de0b90f4-6c9e-5e37-a732-96bbf493ba2e | note | – – – – – – – – –
31a00aa1-8b31-55b3-98be-6244de841d98 | textbox | DATE:
e761e962-1dc7-4679-ab6a-822e8e8643d5 | checkpoint | 5.5 Concrete Sampling and Testing
5d183671-8c73-5bf2-ae5a-1263afb44aae | note | FREQUENCY: Prior to lot closure
9f66f6df-31d4-5089-a569-6bdb834e10a5 | note | – – – – – – – – –
d9ab54ab-74f7-50f5-a142-df29c4abfe75 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and slump
4b7a03f3-f1f0-524f-89ca-93a7b83e3452 | note | – – – – – – – – –
2f02e9b7-8e41-5e67-b514-b19d7348f9d5 | note | REFERENCE DOCUMENTS: 610.16
4a41c5f8-debc-5b0d-9871-22e35d59985f | note | – – – – – – – – –
4e5a37db-2b35-5a27-b3fb-8120c4387f9b | note | INSPECTION/TEST METHOD: Verify
77596ae1-c5c0-5d40-8812-9c46459869fd | note | – – – – – – – – –
04b5cc54-3aec-5057-b431-f13d07e94088 | note | RECORD OF CONFORMITY: This ITP signed
c1596ef6-82d7-54b6-bb76-46d5782fe3dd | note | – – – – – – – – –
998020b9-ff6f-53bd-b260-029a7d9055e5 | note | TP
2d11be95-5c17-57c5-924b-85bed309581f | note | – – – – – – – – –
1257e05c-6efe-5358-9052-f6e1286c2378 | note | RESPONSIBILITY: Fulton Hogan
a6f23faf-987f-56a5-8a74-80f42203e327 | note | – – – – – – – – –
b6a5b3c3-eaa6-5907-ac13-4fd8440e94e3 | textbox | DATE:
76572c27-3ee7-4551-b4b2-92941b4ba7c6 | checkpoint | Final Inspection
3c0fdd34-a8ff-5001-a622-8eab5bb9be01 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
530afb0f-bedd-5d75-a85e-ccebfcbdc7c7 | textbox | Print Name:
9256b74f-f9cb-5079-842d-aeb279e06f5e | textbox | Position:
c84288ff-f39a-5c7c-bdc6-6e2c552690cb | textbox | Date:
78606a9e-4815-44e9-be4a-d375b4dd906b | checklist | SYS - ITP-01-027 - Pile Footing Construction REV1 (old version) |  | ITP-01-027 - Pile Footing Construction REV1
f3c21fc0-081a-413d-8838-f6813ef39750 | section | 1 - Design and Submissions
e65bb23b-2d47-4b3f-a1b3-73726c4b4ba5 | checkpoint | 1.1 Check for correct documentation
6c26a545-2a93-51a7-af71-c1e09d57d112 | note | FREQUENCY: Prior to commencing any activity
174ac236-059d-5319-ba5d-bcaeb2704436 | note | – – – – – – – – –
68638fe7-bad5-5f33-9dc8-db66b2f4f5b5 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
123a524d-2fda-506b-bf62-7168ac6f3323 | note | – using the correct and complete set of drawings
715175da-bb68-5c27-96e5-5e7eba4f2e2e | note | – all drawings are the latest revision
286f9b8c-4bd2-5bd8-9825-7700f3afeb60 | note | – – – – – – – – –
8a8e274b-2ee8-5dcd-8327-82bbfd11fa15 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
494a0329-024a-5e19-8fb6-05dcf75f1ec1 | note | – – – – – – – – –
25329d6b-3970-5fc8-8c95-6cbd76ab84a6 | note | INSPECTION/TEST METHOD: Visual inspection
075e8378-e205-55b7-91b8-4c3b858a219d | note | – – – – – – – – –
fbf6ff1e-1ebd-5cfb-8390-6939493ef05b | note | RECORD OF CONFORMITY: This ITP signed
cd275126-849f-5e8d-988e-409ae96a684d | note | – – – – – – – – –
ba8dd977-53ee-59ff-a9ce-dfcb382d2edb | note | HP*
2bbf8758-ac80-5bc2-a5fe-8e039f9ca28f | note | – – – – – – – – –
fac5f478-5e16-56a9-b350-c5af08453ca1 | note | RESPONSIBILITY: Fulton Hogan Engineer
2e90016b-300d-5a78-851f-3316ee159004 | note | – – – – – – – – –
490511ee-fcf4-5991-84aa-7b4e43de0341 | textbox | DATE:
ca1a4bb5-fa66-47ac-af0b-97249b4b69fa | checkpoint | 1.2 Implementation of all measures and controls
2e374a8a-e78a-5cfe-a5c8-79a93af8db62 | note | FREQUENCY: Prior to commencing any activity
fc7adc19-3e78-5eb2-a606-08e974e4898c | note | – – – – – – – – –
c56ed091-6316-5fb0-860e-143ef82a06cd | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
6fb6b09a-1270-5a2f-bc04-d9dabaaf2500 | note | • PSP, EMP, TMP, SWMS & WP
b64320b3-1b59-5259-848c-7807bdd47366 | note | – – – – – – – – –
52402efb-7c17-5871-9426-247cd59246fb | note | REFERENCE DOCUMENTS:
193267b5-f2e9-599e-800a-c9d4770297f3 | note | • PSP
ba9c9e6e-2d60-5089-b132-5c737de2ee7e | note | • EMP
1d31e4fa-7824-5154-a0e4-d22a33063aac | note | • TMP
cce7ce0c-b7ae-53af-b737-1a34aba2aa29 | note | • JSEA
08382c31-83ad-5103-a90d-b01eadfdb874 | note | • SWMS
db4abfce-0c44-5cd2-8d44-51690d8124af | note | • WP
da68be02-a792-5021-9b5a-88b3eaf2cfcd | note | – – – – – – – – –
dbab5f4c-f14a-5007-a492-9eeda3fb3b0b | note | INSPECTION/TEST METHOD: Visual Inspection
e1ecab8d-cd86-5065-8f7d-5efc18426d6b | note | – – – – – – – – –
cd73eccf-e155-58d4-9a4c-47af62af631f | note | RECORD OF CONFORMITY: This ITP signed
74fa84d4-f570-5a10-8b94-5fb9c4ebf959 | note | – – – – – – – – –
625711d7-fb1f-56fa-8021-9094152825a1 | note | HP*
2666e365-291b-5ca1-a314-291844cb27ff | note | – – – – – – – – –
767caa77-da1f-500f-a761-b6ba036fe873 | note | RESPONSIBILITY: Fulton Hogan Engineer
d5c61375-188a-5bec-8258-a9c96243c595 | note | – – – – – – – – –
635fba61-2025-5c75-8412-a95b155de1cd | textbox | DATE:
93e65821-581c-457e-9404-e23461d7b36f | checkpoint | 1.3 Approval of mix design
63becc52-9732-54f9-8f10-b071bba91c4c | note | FREQUENCY: Prior to the first concrete pour
9f88be24-13e2-5ecf-a8da-e75dacbf9576 | note | – – – – – – – – –
6ee2112c-bc9b-50fc-8748-e8c24dc718df | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
5964c44b-6046-5fb5-9720-b80e6ff88ec2 | note | – – – – – – – – –
e0c08dcf-7954-5b31-abd1-f4074efcb263 | note | REFERENCE DOCUMENTS: 610.07
edecaf3d-e63a-5d6a-8a3f-c3e74da7c582 | note | – – – – – – – – –
a3bd625d-f4c2-54ac-8f69-568ad87beb52 | note | INSPECTION/TEST METHOD: Verify
0b00491c-c858-5aca-8647-7245ff480e4e | note | – – – – – – – – –
ef4d6278-7b95-58b2-89b6-e76cbc8365f8 | note | RECORD OF CONFORMITY: This ITP signed
770f3b17-1c42-530e-afd0-ff32d04e1dd9 | note | – – – – – – – – –
4fb4f9ae-1479-5c40-9de9-9159df652b08 | note | IP
1232b0cd-a3e9-5feb-ba78-3ef726650c57 | note | – – – – – – – – –
fd82052c-71b9-56fe-88d3-f55f49d253a2 | note | RESPONSIBILITY: Fulton Hogan Engineer
59e3ee6c-ef65-5f3a-bf06-5b96d3acc2de | note | – – – – – – – – –
5a33528a-0f8f-5638-9cd2-a5c828ba8c6f | textbox | DATE:
41e09bf8-6b31-4f02-a6f7-1cb9f498c9ca | checkpoint | 1.4 Reinforcement schedule
6dc5ecf1-2241-52d6-b562-38e545183419 | note | FREQUENCY: Prior to concrete pour
0bdcfcd3-14bb-5fc7-abc4-371275549f72 | note | – – – – – – – – –
2fe8f82a-de85-5e82-aa80-fb4e6667dfd5 | note | ACCEPTANCE CRITERIA:
32ea668e-af41-586d-96ae-386ed002fda6 | note | • Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
c0e09b41-e127-562e-864d-8889b6dec6fa | note | – – – – – – – – –
5c908c54-0a38-5564-ae52-059ff465bfed | note | REFERENCE DOCUMENTS: 611.04
ea83597c-0736-5e3d-a55e-1bbceebcde8e | note | – – – – – – – – –
0291ee25-4ac2-542f-97b3-1869d1e34191 | note | INSPECTION/TEST METHOD: Verify
ac6e66fc-7af2-5167-98ec-f567d6fc7739 | note | – – – – – – – – –
8d414532-a17a-55fb-a170-82f9fa7ffd03 | note | RECORD OF CONFORMITY: This ITP signed
bef4f785-20fe-5e16-a049-9b1dfac53612 | note | – – – – – – – – –
51a1df94-5242-5fee-a2f9-0345ce2f939a | note | IP
8831e755-8b96-5a2c-8fd4-6b55962f0c04 | note | – – – – – – – – –
9154ab92-c43f-5d53-bb85-c0ccc0f00c41 | note | RESPONSIBILITY: Fulton Hogan Engineer
2520439a-4561-5e33-ab94-f214cd31ee69 | note | – – – – – – – – –
ed0561de-f4f1-5a6e-a8f3-4c0b419518c1 | textbox | DATE:
d3b5f294-025b-4057-b2bd-c4ef795fc508 | section | 2 - Construction/Erection of Formwork
2ab6cf89-c267-4885-b044-780835e7c330 | checkpoint | 2.1 Excavation (Pile)
cfd773ea-a9bf-58bf-a372-b615d126f22e | note | FREQUENCY: Prior to concrete pour
4c4637bf-b9c8-5067-91cc-8a48d51a9943 | note | – – – – – – – – –
3e349192-750a-5d25-a20b-2e0336a3d745 | note | ACCEPTANCE CRITERIA:
b09aeca6-fee4-5297-9425-53d679e4786e | note | • The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent.
bda07df3-6a24-5fa3-bbb7-60a7c95736f9 | note | • Prior to inspection, the pile excavation shall be de?watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
5139e405-ab05-5269-88ed-31303e5199f4 | note | – – – – – – – – –
0bfec674-daf9-5799-a7d3-3cd5d36bef8f | note | REFERENCE DOCUMENTS: 606.05
8416704b-e99f-53dd-8259-a6e5df0b6955 | note | – – – – – – – – –
f04ed219-3ec5-5024-9288-81f683f15345 | note | INSPECTION/TEST METHOD: Inspect
30324d7a-9f14-5b94-82e4-0fc36da6d85e | note | – – – – – – – – –
7770ae2d-8db6-5aa5-8695-750a74706309 | note | RECORD OF CONFORMITY: This ITP signed
ca5ab303-1da7-5b35-8ae5-99ecab72cb17 | note | – – – – – – – – –
52aaaca0-8cdd-502b-bb86-1efafd8c0b57 | note | HP
6daf5172-eb56-5dba-bba1-87b232fa32aa | note | – – – – – – – – –
637381c2-e1fb-51e9-9d26-62d719ee12c9 | note | RESPONSIBILITY: Fulton Hogan Engineer / Suprintendant
b613b453-e5fe-5365-a16b-afe62bd511a1 | note | – – – – – – – – –
48295769-29d0-5ec0-94d2-f5fddc69441c | textbox | DATE:
3027f9a2-7e44-4f3d-b2da-bc80d3d12b28 | signoff | HOLDPOINT AUTHORITY
19e86121-64e3-4cf7-bb6f-c7e3b360bcd2 | checkpoint | 2.2 Construction Methodology
62e3b37d-1695-5d15-981b-6ef74471fc89 | note | FREQUENCY: Prior to erection
7ec47c0b-577c-5194-a676-b3b5891ab5b4 | note | – – – – – – – – –
25aa74c7-553d-5f1a-a2cc-981ca6dad497 | note | ACCEPTANCE CRITERIA:
789720db-495a-5462-9491-337da4dff17b | note | • Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
d1fb9c87-9727-5bd1-b8c1-9957322342b1 | note | – – – – – – – – –
0c34ce5f-a782-561c-b091-5b0239e030b1 | note | REFERENCE DOCUMENTS:
3aae1f34-0cfa-56c0-9b05-d84fd3f3945a | note | • 614.04
3bd8e90b-3841-5e8a-bd99-dc8f3aa498b8 | note | • 614.06
9f64a5ff-cdfd-57a6-8902-52c13a46bb32 | note | – – – – – – – – –
f8c92418-17f5-582d-9579-1895f8dddd1a | note | INSPECTION/TEST METHOD: Verify
70cd2a55-9501-5bd5-a810-e68a43741cc0 | note | – – – – – – – – –
6da01a63-dedc-5a76-a085-73847f96c7db | note | RECORD OF CONFORMITY: This ITP signed
bb3e8392-7e82-5f77-a280-5e4d90b5804c | note | – – – – – – – – –
822fb537-a45f-53c4-8611-7a21f2a5e4c0 | note | IP
f1f4fd09-f064-52b8-b4b1-46dd4461eacc | note | – – – – – – – – –
ed6f3809-0e54-5c5d-852d-197a07b9e291 | note | RESPONSIBILITY: Fulton Hogan Engineer
1f4324a7-acc2-5530-a4b2-982768a5f9d2 | note | – – – – – – – – –
f9fc91d0-c06d-5631-a419-97f7d9607de4 | textbox | DATE:
13e98ca2-82fd-4a3a-a24d-84c368db67d4 | checkpoint | 2.3 Construction Methodology (Pile)
d6ff5ab5-e692-5e85-801d-98c14dc414d4 | note | FREQUENCY: Prior to construction
bd2f03b6-6637-5a8f-b3be-289b80551bb7 | note | – – – – – – – – –
aae05f4f-1a78-533e-a834-43a6c5219f66 | note | ACCEPTANCE CRITERIA:
ff9c8945-9eb9-5cb8-a595-8a00219cc527 | note | • Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
3fb76822-d289-5ebd-8196-cbfc343ff091 | note | • Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
47b70d04-8395-5a51-8aa0-0ada787146de | note | – – – – – – – – –
1f17a262-4f5b-53af-b46e-29e9e9786ac1 | note | REFERENCE DOCUMENTS:
9ef58153-22e6-5201-b583-aa0e847dad47 | note | • 611.10
b21ccf5a-ecb3-5836-8898-ed91dc0352c8 | note | • 606.06
8bde91ec-8701-5cff-b35f-f528eaa903fd | note | – – – – – – – – –
b045b4a0-666c-5de5-96b1-2e893bbf88e0 | note | INSPECTION/TEST METHOD: Verify
69665557-76e9-5b41-9384-9295e7480de6 | note | – – – – – – – – –
76b684df-94a9-5a61-99f0-4d204705312d | note | RECORD OF CONFORMITY: This ITP signed
c7f683a4-2ee1-55b4-950e-183db9d8f975 | note | – – – – – – – – –
2b70d787-f39b-5144-8676-5c33df354aaf | note | IP
6a86316b-c975-57af-a190-446105f758d1 | note | – – – – – – – – –
f784f42a-8caa-5b1d-810a-472c1e3ea4a7 | note | RESPONSIBILITY: Fulton Hogan Engineer
bb6e859a-6d24-5551-b80f-32aa159eab9a | note | – – – – – – – – –
c5bd7755-0d3d-521c-a8bd-7f16a1521a98 | textbox | DATE:
9bf03027-688a-4be7-9967-424d5c3983bb | section | 3 - Pre-Pour Planning and Inspection
d562090d-5411-43ef-b156-cebd17aea3f1 | checkpoint | 3.1 Cleaning formwork
8992886b-5a3e-5ed4-a0c6-fad7af79f5d6 | note | FREQUENCY: Each concrete pour
6e1fc547-0fda-5442-8e92-24802019c90f | note | – – – – – – – – –
787d378c-3fc1-5e5e-8f1c-69aad7fb45b5 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
f20e3c28-e6a7-513a-9ef5-57bed73e6c89 | note | – – – – – – – – –
09216eae-fda2-5c97-925f-cbfbbc7146f5 | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
5c9b3905-b003-5bf9-ba41-e83c85750235 | note | – – – – – – – – –
c435c0b7-910b-5203-95ec-079c048dfff8 | note | INSPECTION/TEST METHOD: Verify
7112fdf7-2c67-5f0a-8685-93991c143ffa | note | – – – – – – – – –
fd05f713-8486-5e69-ac8c-0b8cfeb5f93a | note | RECORD OF CONFORMITY: This ITP signed
320d5a53-92f2-54d3-8327-eb253edbe403 | note | – – – – – – – – –
ccf9cc16-7a06-5213-a0eb-aecc83f7110a | note | IP
68c6e5d9-b981-5ae4-a414-9732b6d5f1a0 | note | – – – – – – – – –
f1725b7b-c093-58d3-b2a8-18a5aa681486 | note | RESPONSIBILITY: Fulton Hogan
d443e351-daec-5270-b6e7-4a317122bbc4 | note | – – – – – – – – –
d5ad5f16-b2dc-5fac-a14d-f4660cebbf86 | textbox | DATE:
3d50552b-7192-4e66-8ca1-b0cedb164f93 | checkpoint | 3.2 Correct forms, reinforcements, rag bolt assembly and embedments
2f101310-37a3-5626-accf-453df9309137 | note | FREQUENCY: Prior to concrete pour
129f11bb-d1c4-570f-a5bf-2324edc85aaa | note | – – – – – – – – –
7487f4b7-bcbf-5fab-bed7-a1b117da2dd5 | note | ACCEPTANCE CRITERIA:
4d8d06a5-8d4f-5640-8a9a-f4eda10187a1 | note | • Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
3fc66a95-c8e2-50d7-b860-19092becb23e | note | • Pre-pour checklist completed and signed.
6fdc9555-ba63-58f5-9366-fd59561d131c | note | – – – – – – – – –
63002291-904c-52db-9cdf-31ee23a6ac9e | note | REFERENCE DOCUMENTS: 610.18 (a)
86464873-80e8-5d3c-b4d2-3e2584a67f07 | note | – – – – – – – – –
1d38f80c-0694-52b7-8de0-97267a7b4ad5 | note | INSPECTION/TEST METHOD: Verify
170aa76b-7912-55cf-9aa9-d5ea11b11943 | note | – – – – – – – – –
e777e47f-2116-5dce-8ca2-2d13eae09c06 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
4f0885ee-f0f9-5e36-a4b9-753a45286364 | note | – – – – – – – – –
5d919e72-372a-50f1-99c0-407cc0f81d2c | note | HP
1be25cbc-8037-503a-afd8-7da5a5dbfcb0 | note | – – – – – – – – –
780fd274-3d4f-506d-ac8c-de0c228b8a76 | note | RESPONSIBILITY: Fulton Hogan / Superintendent
ff2988a7-23c7-5219-a990-479e88642105 | note | – – – – – – – – –
a11de91e-caaa-54e4-889a-4ac2e99435d2 | textbox | DATE:
0b761541-1736-432e-8845-f242f2cd7886 | signoff | HOLDPOINT AUTHORITY
fb888b03-6426-4d21-80b9-b61167e31a72 | checkpoint | 3.3 Reinforcement assembly of piles
aa961cd9-9601-5e5a-9545-6b872628350c | note | FREQUENCY: Prior to concrete pour
feaa7bd8-dcc1-5b2d-8ef8-7c5c4f2fb128 | note | – – – – – – – – –
955b4ef2-f79d-5e81-8a82-7ddf71deefef | note | ACCEPTANCE CRITERIA:
59bc3ad3-8d76-5dd9-aa24-ae2d9514436f | note | • Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
5f113a6f-9e1a-5732-b9b4-3530bb5799a3 | note | – – – – – – – – –
e3171a1c-c6a0-54a8-ad67-341becb4bfe5 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
6fe7c7e8-7214-5c8f-88c2-1300dbfdb4bd | note | – – – – – – – – –
7d65de1d-0a56-5d24-85cf-1b789d3a41cc | note | INSPECTION/TEST METHOD: Verify
f5a83918-4bc9-51de-9922-7daf0f27c632 | note | – – – – – – – – –
61da4780-e609-5f46-95d5-89d1e8e4fc89 | note | RECORD OF CONFORMITY: This ITP signed
ff2ff180-f926-5998-9527-d6e816a7dc50 | note | – – – – – – – – –
079945aa-d55f-5cfc-8eb9-d82bf9705ce0 | note | HP
2a1e0712-7d02-5077-bc8e-394c2eb93486 | note | – – – – – – – – –
7a6b3a58-4eff-52b7-949e-8d93e6462a62 | note | RESPONSIBILITY: Fulton Hogan
06c0d351-0865-5309-821a-116470853926 | note | – – – – – – – – –
c608c858-711a-5053-b04e-c801d4c6c468 | textbox | DATE:
db7e2fb0-77a7-4594-a3d2-94b8cfab1cbb | signoff | HOLDPOINT AUTHORITY
fccbd224-ebb5-49b9-9a3f-dd3c8aa7e824 | checkpoint | 3.4 Monitoring weather
a261419a-540b-5797-b9e3-5f987ade25bf | note | FREQUENCY: Prior to concrete pour
b20b79ee-0f83-531f-81d5-4bfa5a29958c | note | – – – – – – – – –
84c7af40-8f96-5c73-b1fc-08e90c61669f | note | ACCEPTANCE CRITERIA:
47460eec-85ed-5ced-bfea-1ff17a5f5916 | note | • Concrete shall not be place when temperature is <5°C or > 35°C
a7bf5aae-1b61-581d-aab2-ddf0810ecee9 | note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
93cee524-e1e5-5658-9f53-704393553477 | note | – – – – – – – – –
939c86b4-3949-53ca-a39f-d9c167508ca7 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
af951f54-68f3-5f34-8521-709279bfe6ec | note | – – – – – – – – –
40c8cf38-59af-5255-9633-c95f43ae4d0a | note | INSPECTION/TEST METHOD: Verify
7fe6114b-78e4-5ea8-ae66-b88134896a45 | note | – – – – – – – – –
393f3c64-10c5-51bf-a53d-61ff4044a696 | note | RECORD OF CONFORMITY: This ITP signed
a83acb8d-3230-577c-9c71-ac084324b522 | note | – – – – – – – – –
8cfa8de0-28ae-51a9-bd90-c0060456aa30 | note | IP
1d73129a-3390-536a-8a5f-87e2c3cc4911 | note | – – – – – – – – –
30c4a6cd-818c-5412-a7a3-23e3a6e68e5d | note | RESPONSIBILITY: Fulton Hogan
b4811c0d-1013-5a0b-84cc-6169ee27afc5 | note | – – – – – – – – –
a5b8b446-d853-5efe-9934-0ed76870ba80 | textbox | DATE:
e2a0eebd-fc61-478f-94f2-1dd1bdb532f6 | section | 4 - Placing and Finishing Concrete
230f3ea7-3307-4a9f-a230-48573a66c816 | checkpoint | 4.1 Carry out sampling of concrete
ba964d3f-6593-50b3-8076-eaf6c64e6653 | note | FREQUENCY: Each concrete pour
75f8f23a-5056-5ef6-9551-086850d0ac3c | note | – – – – – – – – –
43e3b480-b2f7-52c3-8a85-b25ff9318147 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
495e321d-a2f2-537e-a15d-af001b1465aa | note | – – – – – – – – –
16a86d27-6a15-5f41-be18-2db93bb0029d | note | REFERENCE DOCUMENTS: 610.16
6602e8e2-7752-55d6-92d1-fbe27a65b926 | note | – – – – – – – – –
57eedb68-a3ba-539d-b23b-bedf9b968604 | note | INSPECTION/TEST METHOD: Checklist
60bccf6f-9ce6-5c77-9a55-da404ca5c7b0 | note | – – – – – – – – –
e614ee4c-998b-5c26-92d4-4eb71af1c4fb | note | RECORD OF CONFORMITY: This ITP signed
21c3bae3-ce22-5de7-91ed-139d4a86ae37 | note | – – – – – – – – –
cbb764f2-70cb-5302-afa7-d59475031118 | note | IP
f33f21b7-9e65-5008-9aae-b35b7a15517a | note | – – – – – – – – –
e07734e4-3653-560a-89e8-3f3f1f915015 | note | RESPONSIBILITY: Fulton Hogan
f56ae02c-a841-5953-835b-61a0989300d2 | note | – – – – – – – – –
14207241-704a-537b-b1e2-a107cb31936a | textbox | DATE:
65538f3c-560e-4e57-9fbe-ad2aad24b132 | checkpoint | 4.2 Discharge time
727ee265-f17f-5f49-b55a-816209931c9c | note | FREQUENCY: Each concrete pour
56caa091-b346-5487-9cea-63212b1a1400 | note | – – – – – – – – –
7d6f10b7-ebba-5aef-b750-694599d7ef49 | note | ACCEPTANCE CRITERIA:
66f032d7-9648-5b3b-a68c-2d13f1634ef1 | note | • Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
ce37ab5c-c0b4-5ddb-86e8-6fc4b5930acb | note | • Batch to be used has a discharge time of 180 minutes. Boral VR400/40 (SCC) (180min')
19519a67-9a6f-598f-861d-09e9dd6d96f6 | note | – – – – – – – – –
dcd867c1-1c78-5c86-afec-16dca33a728e | note | REFERENCE DOCUMENTS: 610.13
c5466ffc-a0e6-5881-8c7b-59d4ea4b60fe | note | – – – – – – – – –
6023187f-aa4d-526c-a393-2a41b43e2022 | note | INSPECTION/TEST METHOD: Verify
6568c81b-4de5-5286-bb64-043ecb52e4c4 | note | – – – – – – – – –
9914ca4f-4693-5887-b349-e7c23ca219e7 | note | RECORD OF CONFORMITY:
b6d73dc9-59b3-5773-ac90-4bd5d5369523 | note | • This ITP signed.
6d156519-2533-5399-9db4-71cd00f55111 | note | • Accurate Site Notes & Load Mapping
12aba0cb-7a64-58ca-bc3a-3f875e1613ad | note | – – – – – – – – –
f1066f46-2659-5a7a-8c9c-b64c209e64be | note | IP
145f8bf2-d891-5385-a582-4eab5348465c | note | – – – – – – – – –
0bbaa756-4abf-5f81-abb9-257b2788c371 | note | RESPONSIBILITY: Fulton Hogan
854a00fa-4754-5db7-b543-62f4f7af073b | note | – – – – – – – – –
68b40373-3ffc-519d-9944-b92907b01c50 | textbox | DATE:
ac0c2c72-d743-42cc-bcaf-3fddd19c6d6e | checkpoint | 4.3 Methodology of placement (structural)
ce9b8d0b-4c05-502d-8818-3f9e5e16ee0b | note | FREQUENCY: Each concrete pour
1c89a620-dc12-5b7a-9c1c-08ea57d5949c | note | – – – – – – – – –
8f8b1dc6-9d8e-5722-ae0a-c1fee429d9d1 | note | ACCEPTANCE CRITERIA:
73280fac-08bd-5897-9a23-6e788daf145d | note | • Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
f6372031-739c-5844-ad68-def57411a376 | note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
6e8d2ca5-f4fa-55e0-8808-41744c9f2f00 | note | – – – – – – – – –
7f1297cf-2f72-5781-939b-66c17da42ea8 | note | REFERENCE DOCUMENTS: 610.18
fb33df66-6d03-5a2d-9970-74a39fdb9311 | note | – – – – – – – – –
aea56db8-9e42-53fa-9a24-2238c890ee14 | note | INSPECTION/TEST METHOD: Verify
88ab9b00-287a-550b-a40a-6df4d2647cd9 | note | – – – – – – – – –
c291debe-c68a-5825-a177-37bde9c5e499 | note | RECORD OF CONFORMITY: This ITP signed
fdf1e904-4221-592a-b34d-78a71f93afd9 | note | – – – – – – – – –
f624a263-57f1-5e62-a176-737e35df8761 | note | IP
ddc4b767-1f9b-59fb-89dd-697ea8e87221 | note | – – – – – – – – –
bfce82f3-50ce-587b-ad15-7a64fce27fbe | note | RESPONSIBILITY: Fulton Hogan
3d4ed034-3062-508d-bf32-f888bdb53dc3 | note | – – – – – – – – –
306cb02c-f567-52c6-85be-2530820802dc | textbox | DATE:
fc855f97-d9d9-41be-9bfa-8093ae712c61 | checkpoint | 4.4 Methodology of placement (piles)
762a1eb5-1ec3-5620-9f5d-7c07ac81a516 | note | FREQUENCY: Each concrete pour
67257797-9ae8-557e-8b0e-21d545da3cd0 | note | – – – – – – – – –
d7ac394d-d314-5270-8c23-1f351de315dc | note | ACCEPTANCE CRITERIA:
2dfb17e1-375a-5e3d-93f2-274ed4b98c29 | note | • Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation.
5b3aef04-89e9-5147-ab69-5d9fb7bde365 | note | • Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
e7566b8a-cd0e-5b1b-9075-6b713154216c | note | – – – – – – – – –
2175204d-93c7-51c0-b612-66cb229b3d14 | note | REFERENCE DOCUMENTS:
41918edb-84e3-5778-8b0e-ba80988b8ae3 | note | • 606.03(b)
1a70d40a-91de-5782-b4be-dffd971688a5 | note | • 606.05
97373c57-86c1-56c9-a910-52a0fe3e6712 | note | – – – – – – – – –
4c9ae7a4-0345-5a0a-8445-c854a19d674a | note | INSPECTION/TEST METHOD: Verify
77a89c67-e0ec-5200-8a6b-48d88839df8f | note | – – – – – – – – –
b0498b11-0c72-5b08-983f-64084452d41b | note | RECORD OF CONFORMITY: This ITP signed
50393fe1-5059-5d46-8752-37f427260d5e | note | – – – – – – – – –
60251c6b-99e0-5a24-8959-ce899ec64f43 | note | IP
e24765b6-6f16-5741-ac58-b952986a1c32 | note | – – – – – – – – –
2c731f65-1fc9-56cf-82d3-acb71ce2959f | note | RESPONSIBILITY: Fulton Hogan
e4368d64-4b46-5de3-84ba-641dc9815cec | note | – – – – – – – – –
07d61d9d-8f83-583c-a57a-cd32873213e6 | textbox | DATE:
0c0b9785-22c2-431e-a508-b29685907fcb | section | 5 - Post-Pour Details and Inspection
bf7e5134-b01e-4c6e-8023-92b97f6fd016 | checkpoint | 5.1 Curing
634caa58-5533-542d-9b96-c7538387e8c2 | note | FREQUENCY: Each concrete pour
4097c5f0-788a-5c80-959e-02cc58846dd7 | note | – – – – – – – – –
a8c90bd0-7bfb-5c40-a6a3-033d7d4c15a8 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
b88b695d-b464-5d74-9035-b76958926031 | note | – – – – – – – – –
373b0c0a-e9df-5eae-9522-f425ad22c10b | note | REFERENCE DOCUMENTS: 610.23
0c6c8cad-93a6-5766-8a07-fe5fd31446e5 | note | – – – – – – – – –
c6277435-a54f-50c5-b470-c50281ce8675 | note | INSPECTION/TEST METHOD: Verify
bf52c795-7f48-5766-8122-8bafc504b63a | note | – – – – – – – – –
8ae025ec-46de-5ea4-802d-0aa173082044 | note | RECORD OF CONFORMITY: This ITP signed
29b0db93-f50b-52d6-9910-271c9446054c | note | – – – – – – – – –
f3be9f08-128e-555f-9627-a2daa0a2b22e | note | IP
e49e8ce8-a138-50fe-901b-85627328627a | note | – – – – – – – – –
9c5255d6-9309-50e6-9522-a2a240faddd7 | note | RESPONSIBILITY: Fulton Hogan
0c7d61b5-0bfb-521b-b6f7-4ba205cf4821 | note | – – – – – – – – –
2db055fc-3995-51f2-af7d-3fdad6d849e4 | textbox | DATE:
d904c578-66c4-417e-b40e-70009f82c00b | checkpoint | 5.2 Formwork removal
48c346c3-a8a7-577c-9d57-091704a78763 | note | FREQUENCY: Each concrete pour
f8df16f5-5b3b-52e2-82db-5540523b88bb | note | – – – – – – – – –
2b5e51ef-053b-5fae-b9cf-f5a7fcc9c749 | note | ACCEPTANCE CRITERIA:
ed9e9d13-c754-5c5b-ac85-09cbd199bba3 | note | • Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal.
846271a3-606c-5b00-b472-020d5a4a7e93 | note | • Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
54dcc8ce-d98d-507d-884b-92ad3b20d55b | note | – – – – – – – – –
68ad25fd-317b-5671-a5c4-053f44c6cb50 | note | REFERENCE DOCUMENTS: 610.25
46c78923-af1f-5a86-ac4e-ed2e334b56f4 | note | – – – – – – – – –
4a7276c3-3519-503f-a22f-bae336b7f7a0 | note | INSPECTION/TEST METHOD: Verify
2185fc64-9fea-5219-9836-87f3c9122211 | note | – – – – – – – – –
d6c77da6-6b86-595e-bb22-c817be4277df | note | RECORD OF CONFORMITY: This ITP signed
e6183732-51d4-58e2-b026-152aa72bb156 | note | – – – – – – – – –
cb6f160c-f9c1-5206-a278-2a7f2ca7bc7a | note | IP
01c0f410-7e6d-5d63-8963-372ef823b970 | note | – – – – – – – – –
8d2e1244-df25-5e78-a73f-5ffc89c5da0f | note | RESPONSIBILITY: Fulton Hogan
7fdd3bc9-494a-5855-be67-97d7dc4df42d | note | – – – – – – – – –
9de5f7ab-3c8d-583b-aebc-c431d8b5cbbb | textbox | DATE:
2772378f-99b6-43b8-8db9-65e5b3cdf55c | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
8e78751e-c8c1-5e93-af06-f2639b4c6be0 | note | FREQUENCY: Each concrete pour
29643fed-9659-560c-a53b-1e6f3ff16c20 | note | – – – – – – – – –
b5326690-7805-50c2-ad34-bf3d5c212923 | note | ACCEPTANCE CRITERIA: The centre of the pile head shall be in the specified plan position ±75 mm;
2a776000-f937-5b9e-b3d8-d8e81665d464 | note | – – – – – – – – –
e8b745f5-102f-5e6e-be30-e24b9a897a04 | note | REFERENCE DOCUMENTS: 607.06
c22ab2d9-890b-5865-be69-1beb7a14c1a5 | note | – – – – – – – – –
44a3f580-d160-54a2-8729-af54d3c8abd1 | note | INSPECTION/TEST METHOD: Verify
98fc473f-dc33-5ca1-8ad4-84425bfd5617 | note | – – – – – – – – –
a7f3f530-9c64-50a3-a800-224c70a0910b | note | RECORD OF CONFORMITY:
d18864e3-d1fd-5115-aba4-958749e0a054 | note | • This ITP signed
096eaa65-b347-59a9-88de-598a159fa91c | note | • Post Pour Checklist completed
2a3d15e9-ba3d-5836-be7c-5efd70c07fc0 | note | – – – – – – – – –
a8189218-ac7f-5ab0-8f57-6dc38814c092 | note | IP
47e52b47-b24b-58f1-8ea3-3c71fd18718c | note | – – – – – – – – –
72a1ff61-b001-51b0-b18c-ac8eb34b3275 | note | RESPONSIBILITY: Fulton Hogan
807ca24c-7bc8-553c-a29d-9b8504a67841 | note | – – – – – – – – –
02615b5b-2d4f-578d-b3b1-49bdce92924f | textbox | DATE:
cc59c9cb-191f-489e-8338-0e3cf0bde377 | checkpoint | 5.4 Concrete Sampling and Testing Self-Compacting Concrete VR400/40
a289045d-4bc8-5dd4-888d-84eb43f928e2 | note | FREQUENCY: Prior to lot closure
b3fc3afa-4bd6-5dd2-838a-bbb34709a726 | note | – – – – – – – – –
c572298a-1f85-59aa-8bbc-dbd576c7e9e0 | note | ACCEPTANCE CRITERIA:
efcc78c4-3fd8-597f-84ca-8d02626e7f4f | note | • Concrete sampled and tested for Compressive Strength:
5446f0a4-078a-5dab-9152-a0424d2066b1 | note | – 2 cylinders @ 28 days for VPV=13% & Compressive Strength=40MPa
d036cc5e-ab09-5c67-a4d0-fa2d2cfc80f5 | note | – 1 cylinders @ 7 days for Compressive Strength=26MPa
3c890e87-ec95-58c2-bd96-a3509421a43e | note | • Slump flow of 550 - 800mm spread
6976bba3-c628-53a1-97fc-dbfc524a76c1 | note | • T500 of 1 to 5 seconds
7ee0b310-e337-5710-946c-343311d5f577 | note | • Passing Ability of less than or equal to 10mm
17fae931-4249-5e03-94c9-273b6188feea | note | – – – – – – – – –
ef1fbd85-0909-5c0a-800b-9484b831cb0b | note | REFERENCE DOCUMENTS:
4a58795b-133f-5cd7-bc19-d29d6c755da6 | note | • 610.05
049878a8-a9ae-5e84-bcd1-566f4de6e0b6 | note | • 610.06
a376894a-00d0-56db-b645-f5af204c9b81 | note | • 610.13
52271765-f625-55cd-8cf4-8b9ef0e4acf0 | note | • 610.16
59c0079a-181c-5e3b-bf5b-31ae956362ce | note | – – – – – – – – –
341c7a15-fb67-5fb8-9202-cc7922832b9a | note | INSPECTION/TEST METHOD: Verify
824b2aad-97de-5393-9a68-5a85346a84c4 | note | – – – – – – – – –
9d8d8c91-99e6-5cef-a3d8-51ee596ecddd | note | RECORD OF CONFORMITY: This ITP signed
95571ac6-a75e-5699-82ee-265a58a5df84 | note | – – – – – – – – –
9ccf5c0f-1230-50dc-bb1e-4cc31ba9ec85 | note | TP
b6b455b9-a50b-517e-98a3-54b1ac47d3bc | note | – – – – – – – – –
8cfc22cf-3d74-5e38-ba0d-5d9c3c2fd442 | note | RESPONSIBILITY: Fulton Hogan
2b7a6359-d5f9-5cf9-9a95-a8ad8100720a | note | – – – – – – – – –
8da62c14-73a0-52aa-9c2f-2dc138d55577 | textbox | DATE:
adf29750-a6ef-4b96-8f84-f630641cc219 | checkpoint | 5.5 Protection of Adjacent Piles
0d57d50a-fa42-54a0-a502-889965b765bf | note | FREQUENCY: Prior to commencing any piling
33dd40a4-495d-52e6-9654-607c3f6db694 | note | – – – – – – – – –
7a26fea9-3b1f-5ffe-bc33-261dc183cda0 | note | ACCEPTANCE CRITERIA:
d0d72797-3047-5e04-87dd-acf945f7bf81 | note | • No pile construction shall be commenced within 2.5 m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
e6961e8c-34d0-5061-bcf0-83c3d830fc1e | note | • Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
4dd846c9-5b6e-51a0-b9c6-e1c9fe4d0400 | note | – – – – – – – – –
affa796a-aa62-5d6f-a2af-de986345a3ca | note | REFERENCE DOCUMENTS:
9a5cfdc7-2b68-5211-9976-5df1d182eae7 | note | • 606.04(a)
e3bed027-692c-5e06-b4f3-11857e86a388 | note | • 606.04 (c)
ef35662d-3355-5bb7-bcd9-55fc3861c72a | note | – – – – – – – – –
75139fb5-a942-503c-a625-32f9183cc540 | note | INSPECTION/TEST METHOD: Verify
2ddee186-f2fd-598f-b958-ee8e81d791a7 | note | – – – – – – – – –
85c304d8-e1c1-5d79-9f38-28d0beb19492 | note | RECORD OF CONFORMITY: This ITP signed
2693f07a-1320-5352-8ae1-388dbc43d66b | note | – – – – – – – – –
21eccc9c-a394-53c2-a8c3-b0ddacb6be52 | note | HP*
f2e6cbd9-2269-51c2-9fcb-b984a7176cfd | note | – – – – – – – – –
a73667f7-562e-55cc-a9a6-a63a443d03f2 | note | RESPONSIBILITY: Fulton Hogan
5922dca3-3f12-563a-9dc3-f9a4fb025d14 | note | – – – – – – – – –
08e465ec-ad85-5c67-bd6a-70b2b8d6ef1c | textbox | DATE:
ab3565a8-fb5c-4abf-8b88-28ed7c32368d | checkpoint | 5.6 Testing Post-Pour
f26e85a8-afb7-528f-9c82-114e35510f18 | note | FREQUENCY: Prior to lot closure
072731f6-0fc2-5829-bf08-fc2c32942ab9 | note | – – – – – – – – –
cfd8b76d-4e6a-56db-ba32-9411bfabca52 | note | ACCEPTANCE CRITERIA: Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
37c469b5-78cc-5527-9ec4-64ebabfabfa9 | note | – – – – – – – – –
9c336f3c-e09e-51d0-b8cb-c1791a69ab1c | note | REFERENCE DOCUMENTS: 606.07
28bf3583-add8-5e60-9c66-1e8007217da7 | note | – – – – – – – – –
b2b2bd4c-d779-5059-960b-0c3860e73807 | note | INSPECTION/TEST METHOD: Verify
bf21798d-4441-5272-adb4-e928aebf59df | note | – – – – – – – – –
055f9ff4-6ec5-5128-95c6-a777ff7a8ae8 | note | RECORD OF CONFORMITY: This ITP signed
2617ad21-4ee6-5009-8b60-c2f78e7e5894 | note | – – – – – – – – –
e3e79091-f355-5c64-bde8-ea8441464539 | note | TP
aebf9d57-8416-563c-a3db-040426d0551e | note | – – – – – – – – –
eeeecadc-5d50-5271-b342-63ec2c89d62b | note | RESPONSIBILITY: Fulton Hogan
dd35fcb2-c72b-5dce-a0f5-1317ccb02d53 | note | – – – – – – – – –
f7b4b3e2-dcc3-575e-bf92-0265c6b373e0 | textbox | DATE:
27bca403-889f-430a-bf1a-a55b473e706a | checkpoint | 5.7 As Built Drawings
08821fc7-8d1f-53d0-b723-e8a2ad01f4fc | note | FREQUENCY: Prior to lot closure
bc1114f7-effc-585b-b97c-42940219b919 | note | – – – – – – – – –
a7d533f7-4825-589b-9fff-6628a804a9c9 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
f9fe89a7-c01f-595f-8956-a06472717198 | note | – – – – – – – – –
ff2f157c-e7e3-5e6f-b93d-94c0077b8b26 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
f24131f7-beb1-50fc-81d7-5898380b985b | note | – – – – – – – – –
db228d88-7136-5b0c-8d1c-6a9c3fe42332 | note | INSPECTION/TEST METHOD: Verify
cc808d0f-3ae0-5d5c-8683-7536c8d6280e | note | – – – – – – – – –
c9f41010-3857-5742-97fc-531d304eaf83 | note | RECORD OF CONFORMITY: This ITP signed
7e28b661-6642-51f5-aff9-8d0b70de7c30 | note | – – – – – – – – –
9cf223ea-be89-5f09-acef-4214117da71a | note | IP
12eebd45-b994-56ee-8569-11818827d096 | note | – – – – – – – – –
ed36776c-0c0d-50a5-b6ca-a7a13df66114 | note | RESPONSIBILITY: Fulton Hogan
0ca336b7-c827-56cc-af36-bc6cbb3db95f | note | – – – – – – – – –
71597925-bddd-5c94-a8e1-a08e7ad953ce | textbox | DATE:
8e289af2-d87e-43b1-bd04-a0d62fef83a8 | checkpoint | Final Inspection
9a5f6bb8-15e2-5cb7-aa09-925de7ee5cdd | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
814a2a28-f2a2-5339-9989-87a881983875 | textbox | Print Name:
bf3dcbf3-4262-5f9b-88c8-115376a8f456 | textbox | Position:
cc69d602-2447-595f-ae7b-977ed6b480db | textbox | Date:
7c26fee2-8dc3-463d-901f-d60d0c873df9 | checklist | SYS - ITP-027 - Pile Footing Construction REV1 (old version) |  | ITP-027 - Pile Footing Construction
80a63b70-456d-4cec-8796-6649503cf970 | section | 1 - Design and Submissions
f2bb3915-0723-4465-a205-510071bd4b05 | checkpoint | 1.1 Check for correct documentation
11aac51c-683e-5310-9980-25989eb75d0c | note | FREQUENCY: Prior to commencing any activity
2f6c5743-c4e9-5e56-a83d-9cc43f88c7b8 | note | – – – – – – – – –
41e7026d-2a0f-54ed-b16b-5711112a76b0 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
4d186629-3c71-5f6b-8c56-d2bc211fa413 | note | – using the correct and complete set of drawings
5e3ee5b4-89e9-5878-a36a-53d5d5e31c13 | note | – all drawings are the latest revision
b4310f01-06de-553d-8120-d1855f12ed4c | note | – – – – – – – – –
1d5dbf8e-776b-5c9b-bd14-35e0f61b89a3 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
71be6f6d-477b-5ab7-b3e1-4a7369c1b2ee | note | – – – – – – – – –
f16a0f1d-1c88-56df-b9dd-b4febe4dc277 | note | INSPECTION/TEST METHOD: Visual inspection
c0494d7d-d64e-51e5-8ae9-a0609e44f1a3 | note | – – – – – – – – –
4b95a023-28ac-580a-bac0-eb4b6bd5ab1c | note | RECORD OF CONFORMITY: This ITP signed
77b1176e-130d-5e6f-9d1b-00cdfa4b704e | note | – – – – – – – – –
8b6a9001-5aa9-5f8d-9851-a5f2afaf4bb3 | note | HP*
5f50db87-e0b6-5a7a-a6ac-9cb9adce739f | note | – – – – – – – – –
37bd3f10-6755-5991-a4b3-a17e5704f1a1 | note | RESPONSIBILITY: Fulton Hogan Engineer
8c37c5d2-e4ec-5e7e-8cd1-173d7622ef5f | note | – – – – – – – – –
0733f48b-ecbe-5cba-9368-118abf77684a | textbox | DATE:
f9be41f2-7db2-4461-acd9-030371fe0c7e | checkpoint | 1.2 Implementation of all measures and controls
cf88dc06-b394-5b19-bdd3-e155a1ddd94d | note | FREQUENCY: Prior to commencing any activity
b79f9bc0-e5fc-53ac-94a9-340628a32632 | note | – – – – – – – – –
7a92c587-8cb9-5ad9-9dcb-496232a34f0a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
68847c5a-0121-5306-bd7f-ab9cea87993a | note | • PSP, EMP, TMP, SWMS & WP
9615c362-2f9a-58f7-b113-c4f772a11757 | note | – – – – – – – – –
2b16191f-087e-524b-8c68-22fb6c54a5df | note | REFERENCE DOCUMENTS:
67d1a7ab-0d49-5da6-9758-560416f02869 | note | • PSP
d5762309-e2b4-50c9-8cbb-f1a707c0a1f9 | note | • EMP
5f0dfa40-6a85-57d9-b18d-ae8d6a4baf80 | note | • TMP
d4dcbd02-3429-5fdf-ad3e-4ca8bb58e927 | note | • JSEA
b5f05b23-68ed-5538-aca6-765eab0c8dae | note | • SWMS
eaa31620-c50b-5bbe-ab99-2fcf2cc08abd | note | • WP
5e1dbf1e-ae37-5bf5-a101-26a5cf2c6d8a | note | – – – – – – – – –
e9f7a6c6-9ba1-5ec1-abcd-cc6796254adc | note | INSPECTION/TEST METHOD: Visual Inspection
bf33a8c5-d637-5e89-a401-3c57708b7470 | note | – – – – – – – – –
3eb0a7f5-7d85-59ad-b9e4-bbc03e0bc97a | note | RECORD OF CONFORMITY: This ITP signed
c5867756-7034-5579-8c83-b3f29b7d71bc | note | – – – – – – – – –
c036d516-91c8-58fc-b55b-1a46f955bbb9 | note | HP*
603fcc04-8dc8-5ae1-968f-184e62148e1a | note | – – – – – – – – –
f3b3192e-168f-534c-9215-3ffb1f0e9878 | note | RESPONSIBILITY: Fulton Hogan Engineer
abe6d061-7e4e-5694-8170-a97c236714a5 | note | – – – – – – – – –
507a6ce6-a406-5d10-93c3-b2b0ed28764d | textbox | DATE:
e18b10b7-e911-40e2-88d1-e603dfdc8e49 | checkpoint | 1.3 Approval of mix design
cccc2e0e-270f-5682-baa1-05e650e2a005 | note | FREQUENCY: Prior to the first concrete pour
67446fba-7343-5035-9b04-384aca7d0341 | note | – – – – – – – – –
d3321768-607e-55e7-b3c7-7c21e42fd1db | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
f718d43f-ab44-5535-b2e0-5e22f76228dc | note | – – – – – – – – –
7c4adc21-354d-57a4-b735-434494634d78 | note | REFERENCE DOCUMENTS: 610.07
4dd8dfda-24ee-54d2-bd1a-0c2f535ede29 | note | – – – – – – – – –
12f5a698-54f2-577b-8672-44df30bb06cf | note | INSPECTION/TEST METHOD: Verify
1d89cef9-bf32-5872-a195-3e6b309016fb | note | – – – – – – – – –
02fa1e8e-d760-530e-bc3d-80228947dc0f | note | RECORD OF CONFORMITY: This ITP signed
66f1a057-47de-5c21-b111-d922e0bfa8f7 | note | – – – – – – – – –
0319fcfd-b750-50c6-8830-bdb781952604 | note | IP
d1532f0c-d42e-51d7-ba64-00b3f9593375 | note | – – – – – – – – –
954b6afa-bbeb-5673-b859-8498202b2c71 | note | RESPONSIBILITY: Fulton Hogan Engineer
05986f39-2afd-55e1-8e3b-948ef17943b5 | note | – – – – – – – – –
d7c912c9-d660-558c-8ae3-7a59118b1ed5 | textbox | DATE:
f6904b91-e0b8-454c-b919-26b87c5b4404 | checkpoint | 1.4 Reinforcement schedule
02c9dd87-2d5f-5fd4-8231-fe28843aa46d | note | FREQUENCY: Prior to concrete pour
d8e0d20a-3f5b-5c00-a344-da62f28437be | note | – – – – – – – – –
e50bd7ab-6db0-5ea7-946b-feed35e3f240 | note | ACCEPTANCE CRITERIA:
61da1a60-64b2-599e-bd65-197970b69a48 | note | • Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
707e59c4-6a54-540e-9ec2-9210922bbc2b | note | – – – – – – – – –
5c56afb7-b064-54a7-bc9d-889287e244e6 | note | REFERENCE DOCUMENTS: 611.04
7130ba10-4fc7-5abb-8b55-659ab0e4ebfd | note | – – – – – – – – –
853588ac-b394-569b-91c5-cd2e4d331721 | note | INSPECTION/TEST METHOD: Verify
b9f7bc7b-4e87-55b9-864a-2dd2fbf8fd7c | note | – – – – – – – – –
3f6c05f2-e8d5-5504-beb5-4884f652cc0d | note | RECORD OF CONFORMITY: This ITP signed
7755b019-0c8b-52dc-8d39-0c8dde8a5b63 | note | – – – – – – – – –
f1ab41f5-b260-51a4-a1e7-25bd04fa94c1 | note | IP
1e67140e-93b9-58fe-b8b9-873fe97ce2d2 | note | – – – – – – – – –
3cf22645-c190-5c66-9d7a-94d6321107d1 | note | RESPONSIBILITY: Fulton Hogan Engineer
cbdb48f9-ed6f-5ae6-86f9-13ed277c6352 | note | – – – – – – – – –
75ba0b66-5d6e-56c4-aafe-091f335d0a0a | textbox | DATE:
f87acf8d-6d88-4002-ada6-55ee7d62c0e1 | section | 2 - Construction/Erection of Formwork
2cf55536-f879-4980-a349-1e47b861c780 | checkpoint | 2.1 Excavation (Pile)
cf6e0206-1019-5141-b699-2b499d71ecfd | note | FREQUENCY: Prior to concrete pour
c7970496-164a-5424-820b-204e5432d020 | note | – – – – – – – – –
571fd589-2b1c-5eba-8d7c-9547ab180b53 | note | ACCEPTANCE CRITERIA:
e40287ac-2bab-5275-acf4-3f4e8419eb96 | note | • The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent.
9dffbcf2-d27f-5586-8bcf-4e2f22870743 | note | • Prior to inspection, the pile excavation shall be de?watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
48e24395-4dbc-5134-b693-075d47077dfc | note | – – – – – – – – –
b88002dd-06c9-5964-b705-30f5f6b82886 | note | REFERENCE DOCUMENTS: 606.05
adcc849a-5942-52bf-b0c8-818562332f18 | note | – – – – – – – – –
81634c0e-9b1b-572d-844d-4ad300168cd5 | note | INSPECTION/TEST METHOD: Inspect
e0dd41dc-31c0-5b81-a700-38601357fac8 | note | – – – – – – – – –
5ae9a364-a663-566f-a1f8-1bebb30bc736 | note | RECORD OF CONFORMITY: This ITP signed
49719aa5-6030-5788-8e87-658cce91cee2 | note | – – – – – – – – –
420022e9-a42a-5fdf-911f-bb4a8f9cfba6 | note | HP
b46e5d86-e16c-582c-9ee0-6b7d82830aaa | note | – – – – – – – – –
865bf1cb-ef87-5bf4-8997-f9a5041f034f | note | RESPONSIBILITY: Fulton Hogan Engineer / Suprintendant
8997dd72-c6b2-5c69-b9e6-9a3914dd98ef | note | – – – – – – – – –
dddcf11f-ca58-5323-9269-b41a1e8bb59a | textbox | DATE:
202b9f45-d2a5-4379-bedd-4d0528230961 | signoff | HOLD POINT AUTHORITY
f764c97e-b392-4474-ae01-e5e4fe1fcd2d | checkpoint | 2.2 Construction Methodology
da89fecc-9de8-5dc5-823f-afa2c578548c | note | FREQUENCY: Prior to erection
af3cf813-96ca-5b68-bffd-ef24c25ec02a | note | – – – – – – – – –
c4330962-b3c9-5ee4-b8cd-9ddd97934dd2 | note | ACCEPTANCE CRITERIA:
89a13083-8f2e-5fba-abd1-da9d75324632 | note | • Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
4037b56c-a578-56f5-9a37-3fdc2fe9b2a1 | note | – – – – – – – – –
80e16cfc-7499-50db-b465-5ea5fa4a966e | note | REFERENCE DOCUMENTS:
9c4f402b-d549-5f60-bd1a-9ca33145cab5 | note | • 614.04
da70072a-653f-529b-93d5-900e41f720d0 | note | • 614.06
b2b21e8d-cb6d-5c0c-b40f-a0e7b245e17f | note | – – – – – – – – –
0d1d5955-6584-572b-9510-64a6f948e2fb | note | INSPECTION/TEST METHOD: Verify
65bbfb1e-adfc-58d0-912d-914805357cac | note | – – – – – – – – –
1de05207-85a2-58ca-afcf-dc92d3a10fb3 | note | RECORD OF CONFORMITY: This ITP signed
bd1143fa-326e-500a-8a9a-b591c118d53c | note | – – – – – – – – –
184710d8-910c-5092-8cb8-e02843ce545f | note | IP
844d6ad4-4f21-577f-84b1-a76a68281bff | note | – – – – – – – – –
17300dff-0fa5-53b3-890a-431d1184864b | note | RESPONSIBILITY: Fulton Hogan Engineer
76ee248c-1ba4-5a95-8a4a-de7d4ac887f0 | note | – – – – – – – – –
5d0c33c7-0c00-5233-9dc8-c95083140641 | textbox | DATE:
e7c83ba9-a110-4fef-8b59-16746f27a057 | checkpoint | 2.3 Construction Methodology (Pile)
939f91e0-509b-5a7a-8969-739914fc49fa | note | FREQUENCY: Prior to construction
1af91887-9131-5e68-b848-e1d0e7c5c4ce | note | – – – – – – – – –
304969ba-04e1-5f20-a020-3a1df1148201 | note | ACCEPTANCE CRITERIA:
e74a169f-2063-5e8a-bf72-0beaaeeccf21 | note | • Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
d3bec749-e8ec-5fc1-a1be-faf29a2cb3fc | note | • Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
727ceabf-a3b3-5a3b-b849-3bd5761491a7 | note | – – – – – – – – –
ac21fa4f-7347-5b06-bfbb-4308bf7472c0 | note | REFERENCE DOCUMENTS:
04021b83-4240-5bd6-bb22-578d8e1cb158 | note | • 611.10
f7ea6624-39b8-5f3c-8472-1decfe384c3e | note | • 606.06
c99b5f4f-dccb-51a5-9675-8f54c3da92c1 | note | – – – – – – – – –
5f26de16-83e5-51d4-9768-dcb106d8c961 | note | INSPECTION/TEST METHOD: Verify
93877b21-2780-5234-a662-b9053e2b3007 | note | – – – – – – – – –
23f8c6ab-68af-5fe6-bdc2-103ceaf0d5c2 | note | RECORD OF CONFORMITY: This ITP signed
e5074770-79ec-5469-a3f8-8d4aa902ff86 | note | – – – – – – – – –
4c94476a-3b4b-5e59-ba7d-787dd28521da | note | IP
a262542a-ec6f-5e65-abe1-68957b3381d0 | note | – – – – – – – – –
7609606b-30b6-5fc1-b685-7e6dce60868d | note | RESPONSIBILITY: Fulton Hogan Engineer
71d02d15-6dc0-52da-9f56-e5d71a86a1a3 | note | – – – – – – – – –
4137afea-5b67-59f7-bc4e-c5a10990af8f | textbox | DATE:
af6608a4-173d-43ae-89c5-cb2e78e6405b | section | 3 - Pre-Pour Planning and Inspection
e92f5b6f-af1e-4ab1-9925-442727436920 | checkpoint | 3.1 Cleaning formwork
e1212e92-dcbc-56e0-a577-fe3780ccae13 | note | FREQUENCY: Each concrete pour
b448c654-0e4c-5de1-a6b6-2f8b77d2a67b | note | – – – – – – – – –
62fe9469-b4c5-5779-970d-66b084971fc8 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
ff63b367-8dd9-51fb-8ac8-395bf70adadb | note | – – – – – – – – –
0cd33560-e6f4-52d4-a0f2-bb2e108a317a | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
f71b22c3-b587-5f47-806b-8f336075392b | note | – – – – – – – – –
3019008f-5f2a-5867-90d7-84b69fd938df | note | INSPECTION/TEST METHOD: Verify
0d738292-f61a-53a6-b059-8f1d189a0a8b | note | – – – – – – – – –
21271718-77ea-5067-8b24-ef093a8c76a5 | note | RECORD OF CONFORMITY: This ITP signed
ea6aba26-55a3-5ff2-b947-ba0e1fbb360c | note | – – – – – – – – –
77e379b4-6939-51fe-89ae-fa0cd68fa09b | note | IP
9c88be05-eb54-5d96-8ffe-cfa362894e3e | note | – – – – – – – – –
5808969d-3eae-59d8-980f-cfddac3e4043 | note | RESPONSIBILITY: Fulton Hogan
b7eb2068-3d70-5529-ab74-eb3f3ca66c94 | note | – – – – – – – – –
fd834e2b-6f98-5070-b66d-ec69718046e4 | textbox | DATE:
fdac2159-7e87-491e-b479-4965616933cc | checkpoint | 3.2 Correct forms, reinforcements, rag bolt assembly and embedments
4bb2f8bd-19a4-5d12-bf79-18b7e74a67f4 | note | FREQUENCY: Prior to concrete pour
f8403daf-e720-5dee-8291-c658fc125bb7 | note | – – – – – – – – –
13ca8cc7-8867-560d-98dd-28e3a2f8a468 | note | ACCEPTANCE CRITERIA:
d8d21a5b-ae5d-5e71-8356-9ba8a3da26df | note | • Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
3b023e16-bdf1-55db-b395-787faffedf71 | note | • Pre-pour checklist completed and signed.
5a3d0f2a-0856-5483-af84-cf1c34f6db16 | note | – – – – – – – – –
49657e2f-ac31-573a-9d00-2703f3acf581 | note | REFERENCE DOCUMENTS: 610.18 (a)
93a6bea7-6f2e-5113-b587-3caabf0263df | note | – – – – – – – – –
b73bd8e3-0ee1-54dc-bfe2-2e2a94c7816b | note | INSPECTION/TEST METHOD: Verify
d861a186-59ad-51bf-9e96-b6b24d783d39 | note | – – – – – – – – –
32a17b9a-6ace-5d95-a1a9-887e5d5cbe34 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
31d2aba6-ea68-562c-870d-23e52cb38c9d | note | – – – – – – – – –
aa139fbc-885f-5ca7-a66e-da9043a49ddf | note | HP
2358e13b-1f9c-5a53-83c2-37aaa2a30cde | note | – – – – – – – – –
bd23e0e3-188c-53a3-81ea-b55af9e06824 | note | RESPONSIBILITY: Fulton Hogan / Superintendent
97b96dee-72c2-5947-ad1d-4741652c058c | note | – – – – – – – – –
a720ff2b-c1c3-55bc-8010-9a849beedc7b | textbox | DATE:
fb1b1bd9-e7b0-49a0-996b-84edff1e4bbf | signoff | HOLD POINT AUTHORITY
ade81092-d3da-4bb2-95a0-0f829c128185 | checkpoint | 3.3 Reinforcement assembly of piles
a202bb35-61a5-51b2-b868-ce24ae0558df | note | FREQUENCY: Prior to concrete pour
56327a6f-be67-522b-a3df-dd72b32988ef | note | – – – – – – – – –
5ee3c80a-e14c-55bb-81f0-7a25154bbe83 | note | ACCEPTANCE CRITERIA:
f88f211e-9552-5041-80c2-1b14d397a374 | note | • Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
361fbbd8-ca04-522d-aca7-8ac5f93b6172 | note | – – – – – – – – –
b15a4cba-06ae-5b7a-b456-281f2b27209d | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
21b36a71-ba38-5d81-82b8-c948bf5b3b10 | note | – – – – – – – – –
11781a96-ee99-5a66-ad4b-6fb6224436a0 | note | INSPECTION/TEST METHOD: Verify
a8b538e0-000e-55a5-bfe5-2d6b4a276d1a | note | – – – – – – – – –
8170b1f5-4df9-55ea-91b7-0d38eaff215c | note | RECORD OF CONFORMITY: This ITP signed
bd3a5627-5a7f-542e-aae9-d7df913b150f | note | – – – – – – – – –
d3d1a5c2-5681-50d1-83e6-a8d1c582382b | note | HP
015ffaa3-62fc-5a6a-ba93-a99195cee9da | note | – – – – – – – – –
e2b9fbce-3c3c-5872-aa87-ff21adeee026 | note | RESPONSIBILITY: Fulton Hogan
c068220f-229f-517c-9c96-f93cd4182518 | note | – – – – – – – – –
8d0f8bae-9969-5e49-acb2-6753e9af62d5 | textbox | DATE:
7855c493-13ad-402c-91ef-9e7e28049a86 | signoff | HOLD POINT AUTHORITY
ae582278-7451-4b39-8767-5780e4ebc398 | checkpoint | 3.4 Monitoring weather
1833dd38-b299-5a8e-b52e-6f2897d4dddd | note | FREQUENCY: Prior to concrete pour
fdf0ff91-75a7-5461-a8b0-55cde2f67326 | note | – – – – – – – – –
b614c1a7-3ec5-5cf2-bfab-bbdcc0c47a4f | note | ACCEPTANCE CRITERIA:
6398acea-12ab-59cd-86e3-2ed31ca0bf52 | note | • Concrete shall not be place when temperature is <5°C or > 35°C
63da369f-d7c2-5669-88ec-8934f87245e1 | note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
7bde6357-d306-5d68-a4c9-bec653ed915f | note | – – – – – – – – –
4f755d19-1c23-59fc-b09c-ede45324e4ed | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
14baa4d6-12e8-5d26-9d0e-0a1d8fa1c7b1 | note | – – – – – – – – –
c64bc36f-a92f-5965-b456-4422eedd5309 | note | INSPECTION/TEST METHOD: Verify
ccf48882-9e26-51c1-860f-4c5da0ff2b4b | note | – – – – – – – – –
0a2ab45c-05e4-553d-8e56-01b637844e3d | note | RECORD OF CONFORMITY: This ITP signed
5bd3c2cb-ff3b-5ba9-b115-ef4abf6235a4 | note | – – – – – – – – –
75a1bbb4-1b55-5eee-b405-d5022e760579 | note | IP
06439a20-f95c-5d75-a4ef-07c042fab09a | note | – – – – – – – – –
df9bc413-1f84-5d51-9e06-7a0d86b25d9b | note | RESPONSIBILITY: Fulton Hogan
700aa465-3763-5e4f-b83b-b60a0bcbb0b6 | note | – – – – – – – – –
ef203170-6f21-57b9-b27c-522a2d744bee | textbox | DATE:
6d3c7b4e-6dd3-4253-abf9-c83e68cb0a00 | section | 4 - Placing and Finishing Concrete
e6ef024e-3204-42e2-a6c4-0cc574bd07da | checkpoint | 4.1 Carry out sampling of concrete
25fd322e-341f-5428-ae9b-7e2c1030c749 | note | FREQUENCY: Each concrete pour
d42edeae-c05d-5fd2-b2b5-277604b4c669 | note | – – – – – – – – –
fe7bba8e-b8d8-5415-9cd9-93aeb824d206 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
e349f8a2-6cb0-5a1f-9fe1-d40eba16b943 | note | – – – – – – – – –
19d94eac-f004-549b-8a31-7a32e1371ae5 | note | REFERENCE DOCUMENTS: 610.16
e5ee2012-e840-5262-9c64-fb2952e3dafe | note | – – – – – – – – –
2189ce8c-600e-5220-8626-e792777fb358 | note | INSPECTION/TEST METHOD: Checklist
0907b36b-e9c2-531a-a0a0-ab0f4743e197 | note | – – – – – – – – –
81bda227-f069-50f5-93dd-32f0abcf0ed2 | note | RECORD OF CONFORMITY: This ITP signed
79231db3-fbb9-5d69-99dd-d0a546a879d5 | note | – – – – – – – – –
c2d74f48-9159-516c-9887-7707a1775698 | note | IP
d12b1a3b-b2c1-50cc-bc51-201ffb2f2a0e | note | – – – – – – – – –
cb36422e-de77-59c9-aa13-0f0950677cf0 | note | RESPONSIBILITY: Fulton Hogan
2e557240-1412-549b-b0f7-0bd780b443fc | note | – – – – – – – – –
1f5f50c6-ef09-5119-8385-e2ad9e91af38 | textbox | DATE:
515c4017-4cea-4cfa-a7d8-2bcc39858d39 | checkpoint | 4.2 Discharge time
a59305c8-4994-58bd-8781-be6e40c521b1 | note | FREQUENCY: Each concrete pour
edf91985-2df3-582b-8bec-b865a26e43f0 | note | – – – – – – – – –
d3072cc9-c9b3-5c8c-be0c-4bbbf0b177c8 | note | ACCEPTANCE CRITERIA:
a0d4864a-cd40-5f7b-a01f-b94504aba29d | note | • Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. Batch to be used has a discharge time of 180 minutes. Boral VR400/40 (SCC) (180min')
dfb75dfe-5b94-561c-9755-f5ef592b1afa | note | – – – – – – – – –
d305dc40-271e-59f7-b208-cbb0b5fa7ff8 | note | REFERENCE DOCUMENTS: 610.13
7d74889e-1815-54c4-99fd-eeb6f13b85ba | note | – – – – – – – – –
b728ea60-8a0f-504f-897d-3e11865fb6aa | note | INSPECTION/TEST METHOD: Verify
d9d5f222-1897-5ca7-a9da-7abaf78164c0 | note | – – – – – – – – –
03eedb19-89ef-54db-8ebf-d774c8d45046 | note | RECORD OF CONFORMITY:
ea89b4b0-e893-5326-9974-b2134693932a | note | • This ITP signed.
8515d52b-d4d6-5110-a7a8-de2e994b2308 | note | • Accurate Site Notes & Load Mapping
29ee7fc6-1d87-5cb6-8e6b-b49586cb98c7 | note | – – – – – – – – –
b971b905-3541-56cc-b41f-578382b44ede | note | IP
0fd53173-f01e-51dd-8df3-be04885e1366 | note | – – – – – – – – –
98b1c982-998f-5f5f-b81a-52e23704a527 | note | RESPONSIBILITY: Fulton Hogan
d3772539-3f6c-5c5b-a932-85b64ea469c5 | note | – – – – – – – – –
81aa5fa1-9438-570a-9c85-c982dc94115c | textbox | DATE:
f7c4bd0c-dd05-47a6-ba45-a5a7e6eb0d49 | checkpoint | 4.3 Methodology of placement (structural)
bfa5e9f1-9dcf-5494-9b71-8c138dbba0e6 | note | FREQUENCY: Each concrete pour
1714bdce-7741-5d57-8930-cffc27c0a429 | note | – – – – – – – – –
a9ceb317-9abd-504b-bb3e-e7dee33a1a57 | note | ACCEPTANCE CRITERIA:
39957297-1d30-5480-b730-2cd373ef06a3 | note | • Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
25dd5fe7-c0d9-5ed6-8f69-860d06a41f56 | note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
b5c34239-3c90-5612-b442-927e57d0660a | note | – – – – – – – – –
c12dde6e-dd0b-58a0-a650-1d43d6ba41e5 | note | REFERENCE DOCUMENTS: 610.18
9faa162e-ff08-5963-9ef7-dc66e45757c3 | note | – – – – – – – – –
8fa343f4-1541-5f51-acca-c5783e70a4c4 | note | INSPECTION/TEST METHOD: Verify
08f197ed-b59b-5733-9b31-1a15b49b3ee2 | note | – – – – – – – – –
978a5353-7bb4-55a6-9776-3ab7152b3efe | note | RECORD OF CONFORMITY: This ITP signed
c136daec-b2f4-5932-8dab-8cb86151be28 | note | – – – – – – – – –
0abf072c-5a8b-5bbd-b7cd-89c1bbb6c253 | note | IP
69f2603f-d67b-556b-a47b-486620b92ff7 | note | – – – – – – – – –
9db120c4-96d3-5760-9dad-280f43fa0e87 | note | RESPONSIBILITY: Fulton Hogan
4fed0b61-f1c7-52c9-8dff-e33778ef640d | note | – – – – – – – – –
3da32210-0538-5bc5-b89b-c625f7a39995 | textbox | DATE:
62114d0a-e991-430a-8a21-ee6039b0c7ba | checkpoint | 4.4 Methodology of placement (piles)
59b1e27d-739c-5125-afdc-e0b1a87e89cd | note | FREQUENCY: Each concrete pour
730dd6e9-c8e5-540d-9317-cdc57b85fd77 | note | – – – – – – – – –
efb33062-3eb1-5071-a8ad-defc6d68786d | note | ACCEPTANCE CRITERIA:
4288d805-c69b-5d78-833c-d689ab4c10fd | note | • Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation.
90ed9555-dda5-5ccf-8588-b206889f594e | note | • Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
8d37e897-64a1-5701-ae91-ec34720b2f16 | note | – – – – – – – – –
7fa75dd6-0ac2-5ad7-9a6d-43599fa7ee6d | note | REFERENCE DOCUMENTS:
0e70ca88-fba6-5a75-8c35-d378484da7ab | note | • 606.03(b)
b2b884fe-07a3-5e1e-b141-34dfebd2fdd8 | note | • 606.05
17e4413f-daac-581b-a5ef-ae098e91a67e | note | – – – – – – – – –
5aee8061-2914-5943-bee1-a9bf21f6f324 | note | INSPECTION/TEST METHOD: Verify
2380a100-1ce8-53ea-b08f-6a6d40985389 | note | – – – – – – – – –
90008de8-c09f-59c7-9f2e-090b5aa31b02 | note | RECORD OF CONFORMITY: This ITP signed
9599f578-633e-53fd-9ca2-708d4d0293a3 | note | – – – – – – – – –
12594043-0a15-56ee-8669-6eaf3657d356 | note | IP
045bd8f2-3144-533d-81bb-a2cf0f364b11 | note | – – – – – – – – –
1d9918fc-852d-5abd-9efb-6b58180c96af | note | RESPONSIBILITY: Fulton Hogan
660152d7-c57d-5fa5-a17c-09a7a23b7550 | note | – – – – – – – – –
b7ce316b-3e0e-5e3d-9634-f431415be95a | textbox | DATE:
4e540bfd-7319-44ea-ba98-52d537063c69 | section | 5 - Post-Pour Details and Inspection
a61cad48-10fd-479f-a8eb-b0e534ba72c0 | checkpoint | 5.1 Curing
40d2494c-f3c0-5c6b-9a92-968c0f5ae2af | note | FREQUENCY: Each concrete pour
7cc3f0a1-b12c-5110-a02c-3854d2bfb484 | note | – – – – – – – – –
b764c1b5-ddee-5403-8458-d5c40be412d0 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
457c7a4d-332e-5350-90df-861fc9d78b2f | note | – – – – – – – – –
8dcd4e83-8948-5e8e-8db6-c5193b3c98ee | note | REFERENCE DOCUMENTS: 610.23
c9f79191-0f5f-542f-8495-02f15ff29482 | note | – – – – – – – – –
cde3ba8b-ad1f-5c44-b026-2a7577edc230 | note | INSPECTION/TEST METHOD: Verify
047c2e38-8654-5a48-bc35-fc9b20c4cc8f | note | – – – – – – – – –
fb7ddc9c-aab9-540b-b0c0-908e077a5875 | note | RECORD OF CONFORMITY: This ITP signed
56687b3b-5e56-5417-be45-d6ff5c17b807 | note | – – – – – – – – –
b97698f6-cbda-59ff-8e91-d77817b3bc2f | note | IP
a00d7d8f-3d9f-5c94-9576-108f988fbaa6 | note | – – – – – – – – –
98ac0ff6-c98e-5603-ac4e-1fb90df0bb41 | note | RESPONSIBILITY: Fulton Hogan
2f0eac06-6d95-54ab-ad0f-73fd5153a76e | note | – – – – – – – – –
4207bcd6-990c-53bf-af3a-d82477f19d65 | textbox | DATE:
85cdab04-846c-4307-9f79-38a6c10d940a | checkpoint | 5.2 Formwork removal
1da1ad25-688a-5eee-ad04-2e2833b5b310 | note | FREQUENCY: Each concrete pour
542189c0-2d6a-5d02-abe7-a18d74c8d33c | note | – – – – – – – – –
8dcd2b0b-a75e-5dd7-87cb-a494a20a5d57 | note | ACCEPTANCE CRITERIA:
1ace0f40-2b59-5ba5-9eb5-9301db118b90 | note | • Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
00665212-456d-53c8-bbe6-ba89b5605225 | note | – – – – – – – – –
30fe614e-0772-5299-956c-a53befa7e876 | note | REFERENCE DOCUMENTS: 610.25
6ca29a5d-e3cf-56f0-8a46-a66a6662ed4f | note | – – – – – – – – –
091ad702-790c-50d7-8e68-05c6c3133069 | note | INSPECTION/TEST METHOD: Verify
7b67fba3-f18a-5583-98dc-279207940e19 | note | – – – – – – – – –
5cb1ee89-19dc-554e-8006-861574e22a8d | note | RECORD OF CONFORMITY: This ITP signed
1dbc665e-9deb-5dc6-b1b4-d3ba0c03c0a2 | note | – – – – – – – – –
1ef9908c-191e-5d8d-8d91-4d9b498a2139 | note | IP
e03dddeb-c2f0-5608-a76d-cd3650c6385f | note | – – – – – – – – –
3424b039-7166-59d0-ac57-790854547aa2 | note | RESPONSIBILITY: Fulton Hogan
8cdcffb9-f7ad-5d6b-aaa5-c24051bc58ee | note | – – – – – – – – –
4518b063-7c1b-5199-bb97-36af1b94104f | textbox | DATE:
a9fd583e-f102-4c09-a1be-9c6e7a240938 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
b7b73338-bf74-52c7-810f-a2ce99576999 | note | FREQUENCY: Each concrete pour
0b4184d3-a064-5acf-97e3-06c7542862bc | note | – – – – – – – – –
92482ef5-c787-5768-b112-11ddb45c82ed | note | ACCEPTANCE CRITERIA: The centre of the pile head shall be in the specified plan position ±75 mm;
945ad269-45ce-57a3-ac96-2e50a67c7b72 | note | – – – – – – – – –
0cda6919-4313-5ad8-8b23-fd8e94e45890 | note | REFERENCE DOCUMENTS: 607.06
bfa23842-468a-51c5-8ec3-7040f7ebb747 | note | – – – – – – – – –
3d1bc86d-097b-53b7-9b7e-e389b025381d | note | INSPECTION/TEST METHOD: Verify
2804f9df-95cb-52bd-aed0-474a44221f8f | note | – – – – – – – – –
6eddcb30-55ef-5210-b05d-0c11e6cd052e | note | RECORD OF CONFORMITY:
7dc3fcef-6909-5255-b0f0-8fedef7f7c0d | note | • This ITP signed
5fa2c15b-754c-5ddd-9dd3-ab301de3cb02 | note | • Post Pour Checklist completed
126ce1d8-64a6-573b-99a1-4a5a555dd71d | note | – – – – – – – – –
8e948ee5-5788-5d85-8eca-6b52f314ef05 | note | IP
1d76b95b-f2e7-5a00-8638-74e21be63251 | note | – – – – – – – – –
19a6f825-0853-5faf-beb8-cf7a09b64da8 | note | RESPONSIBILITY: Fulton Hogan
9708665e-eaa8-5485-ac9c-3458506488c6 | note | – – – – – – – – –
cddd9473-c21b-5db8-ab82-ac0ca11a2e1b | textbox | DATE:
ac3995be-2a98-40f5-905d-aa89bc4c63ac | checkpoint | 5.4 Concrete Sampling and Testing Self-Compacting Concrete VR400/40
797e8a36-d10d-5f49-9ab1-f77d40bffbd7 | note | FREQUENCY: Prior to lot closure
2b6857bb-9c1c-5730-9f90-06ba6bc0842e | note | – – – – – – – – –
ae230029-d379-5c68-9c44-c059ed2ea510 | note | ACCEPTANCE CRITERIA:
5953f847-11bd-5885-b35c-e703ffa5af02 | note | • Concrete sampled and tested for Compressive Strength:
bb9eddcc-df4e-5941-9cd5-ead0ebaa6ddf | note | – 2 cylinders @ 28 days for VPV=13% & Compressive Strength=40MPa – 1 cylinders @ 7 days for Compressive Strength=26MPa
e86dfb6d-97e4-5255-8e3b-cbda0ca371fb | note | • Slump flow of 550 - 800mm spread
114255f6-47b7-52c9-ace2-b28ae01f872f | note | • T500 of 1 to 5 seconds
2373b728-c6e1-535c-8152-f5fb009c8713 | note | • Passing Ability of less than or equal to 10mm
96109a60-d704-557d-b39b-7e79450ef3e0 | note | – – – – – – – – –
e53338a5-fa32-5f5c-9291-a550b3418a1c | note | REFERENCE DOCUMENTS:
dc427b72-c41b-5dc8-9fc0-0b2378f5687b | note | • 610.05
c921a430-1198-5276-b9c4-fefc2e1b240f | note | • 610.06
e66c5ef3-27e0-5063-b9c1-2c658388f34f | note | • 610.13
2a54944a-cf69-5fb3-8f6d-bbde68ccb78b | note | • 610.16
56ca3391-6728-5f55-921d-a6ac1bf3a258 | note | – – – – – – – – –
95912183-e827-5261-9261-639e439439ea | note | INSPECTION/TEST METHOD: Verify
76c906e9-3f6e-5db8-9cf6-3e98182dcae4 | note | – – – – – – – – –
62e17d3e-a2ef-57a9-aff6-570db48fd463 | note | RECORD OF CONFORMITY: This ITP signed
c527f180-a527-547d-82b2-48e29d7e51d0 | note | – – – – – – – – –
76244a79-1351-5a95-910c-922bb4b868d9 | note | TP
fad60afa-fee4-513b-b7e0-3360bfc71d04 | note | – – – – – – – – –
986385ba-33ac-55c2-9d34-aa2b849f3c5e | note | RESPONSIBILITY: Fulton Hogan
a76c601e-d0f1-5c64-b6ff-c9d31502e7e7 | note | – – – – – – – – –
66fa8826-c467-5a68-9404-a2e62b5a8276 | textbox | DATE:
4779dd98-b565-45bc-9a02-4469f1b21c10 | checkpoint | 5.5 Protection of Adjacent Piles
99b75373-c369-5fa7-a7d1-5638a76b0a89 | note | FREQUENCY: Prior to commencing any piling
a9869643-25c0-589b-8f16-e835036f636c | note | – – – – – – – – –
2905467f-3136-52cf-8308-e1e5d5c674ea | note | ACCEPTANCE CRITERIA:
31878769-16ae-5553-a6b7-4f3c2f79e32f | note | • No pile construction shall be commenced within 2.5 m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
e6d424c5-a551-5d50-ab92-e939786442ec | note | • Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
c6915d17-2fad-5eff-b5b7-6fcfa36dde16 | note | – – – – – – – – –
6f7902bc-978f-564e-89bf-1983e4a574cb | note | REFERENCE DOCUMENTS:
e707be72-9ee1-5dcb-a658-a53aff9c66e2 | note | • 606.04(a)
7d18e0fc-337b-5993-bf59-861b49163898 | note | • 606.04©
b75c80c0-f4bb-59fe-bf99-7c6261d1752e | note | – – – – – – – – –
e590ea5a-24be-5e56-bde5-2cf140403193 | note | INSPECTION/TEST METHOD: Verify
7a4934d8-6368-51c2-9324-8ff6959db1b7 | note | – – – – – – – – –
a0b35847-4709-5196-9de4-7ffea81fa9d0 | note | RECORD OF CONFORMITY: This ITP signed
031c146e-b938-5a79-a4c1-0e1162d52e87 | note | – – – – – – – – –
9c56c5b0-bfa8-5fbe-9947-a1cc8d9a138a | note | HP*
cc3af182-72a0-55ab-b22c-9d5cf4ba5246 | note | – – – – – – – – –
2db95b3f-59ac-58ff-95e8-663990433ba3 | note | RESPONSIBILITY: Fulton Hogan
e7027717-9a90-5a2d-9cd6-05ea341c1adf | note | – – – – – – – – –
10593d43-b44e-598f-a67c-fb3ddba04900 | textbox | DATE:
92ef1d08-357e-41dd-8e2f-b18aacc7dd4e | checkpoint | 5.6 Testing Post-Pour
13d51783-9bf5-5bec-850b-184f418429ab | note | FREQUENCY: Prior to lot closure
06f82e36-3319-53a4-81ff-f29f41b92a55 | note | – – – – – – – – –
4a94b28d-69c7-524b-ab2e-b22e42cf6285 | note | ACCEPTANCE CRITERIA: Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
bf63f3b6-17e6-58a1-bc3d-b3b64461fdb0 | note | – – – – – – – – –
ca2948e4-68b2-5c08-a0e5-39ac4fdded13 | note | REFERENCE DOCUMENTS: 606.07
feb716f1-0edd-5424-aaee-d0fcc09fbd50 | note | – – – – – – – – –
d10e5502-b7a0-554e-b885-9cde7c1b1924 | note | INSPECTION/TEST METHOD: Verify
ad141282-bca9-5aab-ac53-dd1a6b2a0099 | note | – – – – – – – – –
9a40a486-c6ad-544c-818f-1a34b9a673d1 | note | RECORD OF CONFORMITY: This ITP signed
fc428127-e259-50a5-857e-4ef94cd1372e | note | – – – – – – – – –
9f32e41f-d49f-5a61-a54d-957bdf9e8326 | note | TP
c98dc07c-ead5-5524-b4c6-ab210c44d390 | note | – – – – – – – – –
4d6793fb-63f4-50c6-9116-70462fd0e451 | note | RESPONSIBILITY: Fulton Hogan
aae89291-61cd-5c15-9f7c-131f4a3e9d60 | note | – – – – – – – – –
4dcbecca-e243-55c1-8c6f-b2d71aaf4278 | textbox | DATE:
e6f19da8-d9c7-4770-85bd-57cebce9cdc2 | checkpoint | 5.7 As Built Drawings
cc23ad55-e52d-5294-a946-4e1d2dd37651 | note | FREQUENCY: Prior to lot closure
182a5382-e5c6-5adb-81cd-0e736b6bcf6f | note | – – – – – – – – –
7a256d0e-8469-5fb9-b60e-1315f5fde457 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
b5d659f4-966a-53c1-8340-921fd2e40ca5 | note | – – – – – – – – –
8b0e4998-842b-51f2-86ac-d37f11f6ad92 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
8d2c1c0f-91e6-5ce3-b75c-cd1e0cd48503 | note | – – – – – – – – –
0e12867a-8e21-5b2d-8f7e-72cfdf9cce6d | note | INSPECTION/TEST METHOD: Verify
874d9420-e095-5b0e-95b7-704fd42d7bd5 | note | – – – – – – – – –
e68e93e3-6116-58c0-8e91-2d11cd996b75 | note | RECORD OF CONFORMITY: This ITP signed
c96c0908-c3cf-523f-9d15-7564a50bb259 | note | – – – – – – – – –
95bf73ab-14c5-5510-af03-753a2e04f2e6 | note | IP
44165282-b4ac-5331-a6cb-44aa340d768d | note | – – – – – – – – –
042d7a99-cf20-5506-b656-2d32afe0c6dd | note | RESPONSIBILITY: Fulton Hogan
289b7052-ce16-5ce7-b75a-759aadabc210 | note | – – – – – – – – –
a7c98635-3455-5c01-a6f7-30e72c99cac5 | textbox | DATE:
e63c5a3b-7bc1-40af-9b64-691959991053 | checkpoint | Final Inspection
6e9e354c-828a-542d-a60c-f132ce824cd2 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
351dd0b5-c4a8-511b-a4a8-9f9f03cc0c99 | textbox | Print Name:
1ecb9195-e3c4-51ee-b1ac-23dba1acceb5 | textbox | Position:
f400b313-30db-55b6-9b79-3219a0255b6a | textbox | Date: