## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
5e8561d6-9f47-4844-b608-663b0c000238 | checklist | ITP-001 - Clearing & Grubbing | itp | ITP-001 - Clearing & Grubbing
018eeb26-7017-47c3-82ee-7c9cf91d7117 | section | Preliminary Works
e0b5c2c5-22b0-45b8-9cfd-e15df7417b19 | checkpoint | 1.1 Check for correct documentation
87c6ede2-acc1-52e1-99d7-bbe02bbf2bbf | note | FREQUENCY: Prior to commencing any activity
57aaf374-1e01-5844-b21e-f94bee7ebecc | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
b09c081c-b826-567d-9fb3-4dd633e9576d | note | – using the correct and complete set of drawings
52437762-88cb-5094-a29a-09837c206261 | note | – all drawings are the latest revision
38b5832f-61e1-5f87-a9ee-831eee3f8381 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
07bf528b-7b57-5726-9f89-9d94b1aeae3d | note | INSPECTION/TEST METHOD: Visual inspection
2c41ce30-4c50-5010-a0e7-ed411cc2bd14 | note | RECORD OF CONFORMITY: This ITP signed
263420ca-3fb7-52d1-87fd-a0c1d3751dab | note | HP*
bd32b309-557a-58da-9f13-1c2b7f4dae54 | note | RESPONSIBILITY: Site Engineer / Site Foreman
022b1350-6b87-5077-abc3-bf8e038e1f4f | textbox | Date Completed:
a8edecd6-f993-4cbf-9156-22c64137703d | checkpoint | 1.2 Implementation of all measures and controls
89535cff-c367-54ad-8f20-be4a45c8740e | note | FREQUENCY: Prior to commencing any activity
dfb577c3-33c8-5ce0-85fb-993cd5c22d63 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
7e612abd-ac67-5bf5-96e3-daf5ce30daf7 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
dc052b98-0106-5ea9-b34e-937fd8f1d341 | note | INSPECTION/TEST METHOD: Visual Inspection
1676f665-9d3c-5eca-b244-e1b92dc71c5d | note | RECORD OF CONFORMITY: This ITP signed
88fc10cd-a67f-53ce-9791-2003a01d02a5 | note | HP*
17b66d3a-eddc-5790-8187-4f31d776374f | note | RESPONSIBILITY: Site Engineer / Site Foreman
eeeb3d7c-d78e-5f24-a005-8ea9de6bf203 | textbox | Date Completed:
4a5d6e72-3e8b-47ad-81e6-7daf5639f2e7 | checkpoint | 1.3 Flora & Fauna
cf78026b-0280-560f-9b6f-024760d9205f | note | FREQUENCY: Prior to commencing clearing
d8e6ab1b-94be-506d-bfdd-3474f9d638e6 | note | ACCEPTANCE CRITERIA: A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
d7b74db4-02a6-5f35-bb24-015baa700504 | note | REFERENCE DOCUMENTS: EMP, ECP
5b1e8cfe-9ea9-510e-9b34-2d97c7b9136d | note | INSPECTION/TEST METHOD: Visual Inspection
688cfb64-8706-5977-95d7-2667d9141d95 | note | RECORD OF CONFORMITY: This ITP Signed off
8f029120-14c9-56ce-a832-cd0b90640f37 | note | IP
be759124-8baa-5a0e-96d9-57fa328ebdc8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
84591c23-a3e4-52fd-a1b2-a7978a2f235b | textbox | Date Completed:
42c3d241-7bff-42fe-8bd3-57b4d0f6e506 | checkpoint | 1.4 Permit to distrurb flora & fauna
58bf8b32-2a48-50f7-8867-dc13bae90685 | note | FREQUENCY: Prior to commencing clearing
941b5513-c76c-50ee-b691-f574ea78efcd | note | ACCEPTANCE CRITERIA: MRPA has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
12a82dde-e74b-5a40-94fb-f41bdc7789c9 | note | REFERENCE DOCUMENTS: EMP, ECP
5a6b1e5f-3a8b-5bec-acd2-ef4eece7f2f6 | note | INSPECTION/TEST METHOD: Visual Inspection
66bcf677-4370-50c2-b82d-152ef3255cc8 | note | RECORD OF CONFORMITY: This ITP Signed off
962a7e44-0729-5ee7-8c17-f6b4c89bab74 | note | IP
a223fa89-bf80-5ee6-bb0e-591705d5fb3c | note | RESPONSIBILITY: Project Engineer
2de8558c-ac56-59c4-9f00-7ffac68c7618 | textbox | Date Completed:
def6dcf0-f577-492e-929f-2fbf9d2b8dfc | section | Clear & Grub
365350e7-a704-4b3e-8ee0-94f3334fe51b | checkpoint | 2.1 Define work area
8ba73e86-5c1b-5eae-98e3-cbfec35a51cc | note | FREQUENCY: Prior to commencing clearing
dd1baa09-0dba-539a-85fe-c9e055ffca74 | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
26e7be4f-20bf-5037-af2f-3403f228fefe | note | REFERENCE DOCUMENTS: 201.03
78a2a894-380a-5d9d-9198-a7379f0a1c04 | note | INSPECTION/TEST METHOD: Inspect
79aab02c-dbc4-5823-89ef-01148b439ec9 | note | RECORD OF CONFORMITY: This ITP Signed off
825707cf-7bdc-5f3a-a1bb-c7b13fcbb0d3 | note | WP
652aa638-9faa-5f92-90ca-ed877be14213 | note | RESPONSIBILITY: Project Engineer/ Superintendent
874828a9-fac3-5893-be16-db43b39bbd4b | textbox | Date Completed:
584edb24-f8ae-4f52-8643-a50a9f676d51 | checkpoint | 2.2 Joint Inspection to Mark vegetation or habitat to be removed
12dacde0-3f4c-5e0d-b638-0c0b31d87abb | note | FREQUENCY: Prior to commencing clearing
31098ad4-021e-530b-b9e7-b4e048941a54 | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent to confirm and clearly identify and mark trees to be removed, consistent with Appendix O Tree Assessment Report.
d799c555-c6f1-5115-9f5f-9501482bfa84 | note | REFERENCE DOCUMENTS: Drawings 201.10
f2e54739-88ea-5405-b46f-0a6e6c19d582 | note | INSPECTION/TEST METHOD: Visual Inspection
0f4d4e33-d773-5c05-be38-a057f33362e0 | note | RECORD OF CONFORMITY: This ITP Signed off
9fca5fb5-d51e-552a-b367-4a4711d0104b | note | HP
d739ffc4-e289-5457-9470-798f6cc3e215 | note | RESPONSIBILITY: Project Engineer/ Superintendent
8da5a609-6bc9-56b1-b40e-d48bdcda5fba | textbox | Date Completed:
8329e32f-ac78-4386-b1b4-1127e6359038 | signoff | AUTHORITY HOLDPOINT
4f6532fd-6914-43d3-ad8f-c2c23c8b1cbc | checkpoint | 2.3 Identify No-go Zones
a2208c61-5da4-5849-9b3e-48f9645826a6 | note | FREQUENCY: Prior to commencing clearing
85aa76b6-7cbb-5fe4-93bd-76f1f6d74a9d | note | ACCEPTANCE CRITERIA: Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing.
60e1dc68-e647-56f3-b473-93dd547286b2 | note | ○ Signage shall be erected outside the limit of the of the vegetation or the habitat site, at intervals no less than 20 metres apart or as per the SSEMP
a1511766-6f6d-5a9d-ba11-ba4756aa11c9 | note | ○ Prior to any work onsite the contractor shall fence and sign all no go zone sites as per the EMP. Any works required inside TPZ shall be completed under the supervision of an Arborist
3126bf1f-04d2-5f39-be23-d5cc7785220e | note | REFERENCE DOCUMENTS: Drawings 201.10
dcdb0a71-e2ab-53cf-bf5d-5308e995e8d3 | note | INSPECTION/TEST METHOD: Visual Inspection
e43eba8f-dcb9-59c5-8d70-5c87fe804dfc | note | RECORD OF CONFORMITY: This ITP Signed off
5da80423-a5dc-5352-bf01-d39e42103ad8 | note | HP
da3737aa-91e6-5914-9b2a-2b2997a705a9 | note | RESPONSIBILITY: Project Engineer/ Superintendent
cbc49134-a5e1-5350-b3ec-93274170f2b9 | textbox | Date Completed:
6005effc-cc65-49d2-9690-67dc442a4995 | signoff | AUTHORITY HOLDPOINT
1006291d-fcb7-4e28-a5d6-3e3518e6e3ab | checkpoint | 2.4 Clear felling distances of trees are adequate.
678c5ac8-42df-570a-95f4-2b4fda78ae23 | note | FREQUENCY: Prior to commencing clearing
07f48a30-9372-53c0-84ad-40d2fe010c58 | note | ACCEPTANCE CRITERIA: Ensure the clear distances are adequate and signage is inplace as planned. Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
4c7fb260-b841-5505-9391-047ebc9d8b64 | note | REFERENCE DOCUMENTS: 201.04
a989bab2-0a6c-54b6-82db-30f019be2e5f | note | INSPECTION/TEST METHOD: Visual Inspection
d0e99c46-5c61-5415-8c7c-fd29591a089e | note | RECORD OF CONFORMITY: This ITP Signed off
9bc5dff7-33a0-5981-afda-3a464c92f169 | note | IP
9f56a110-9056-5c7d-add5-0e4214612b64 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0bec02ab-91d8-5e5e-8cc5-9465d97c9f24 | textbox | Date Completed:
0334e5a4-a38a-4f71-88e4-27ae23fb9489 | checkpoint | 2.5 Clear and grub trees and vegetation
f652c66f-5347-5967-b56e-33f5f7b2ad58 | note | FREQUENCY: After clearing
b098695f-c8d9-53e9-afe4-08dd3ec1bbae | note | ACCEPTANCE CRITERIA: Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level. Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
af6000ac-c471-5bf8-be7a-9dc59b8c9463 | note | REFERENCE DOCUMENTS: 201.04, 201.05, 201.06
f47002a7-f8cd-5d75-9282-34c3e85a13c5 | note | INSPECTION/TEST METHOD: Visual Inspection
7fc292ba-bab7-5d8f-93b6-16ec07294564 | note | RECORD OF CONFORMITY: This ITP Signed off
64b70a98-3e26-5f87-8b32-d06a4d442c3d | note | IP
66276e01-c4e8-58cd-b663-98713c03977e | note | RESPONSIBILITY: Site Engineer / Site Foreman
d9391d92-1401-5fef-9bcd-3f1a64801c20 | textbox | Date Completed:
b0856821-e521-4487-9ef2-878917f7e385 | checkpoint | 2.6 Backfill holes
1df111bb-b92a-59c4-a192-e2d4abf592db | note | FREQUENCY: After clearing
a64fd92b-4d99-5d8b-b56e-c9e88da87cee | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material to the surrounding material and compacted to the same degree to the sorrounding material.
30b3aaf1-9e70-50eb-9cb7-21f0499c3999 | note | REFERENCE DOCUMENTS: 201.05
4c1f5d7e-356d-590f-a671-af01d5f19521 | note | INSPECTION/TEST METHOD: Visual Inspection
2ef167c2-f827-51d1-928c-ca1aa5ff9135 | note | RECORD OF CONFORMITY: This ITP Signed off
47e47403-edbe-54e2-8c71-601ab319fb96 | note | IP
dfab901f-89c5-5e66-9c99-c3613977a036 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c1740f29-dec8-5664-8920-d9f8ef98a19a | textbox | Date Completed:
5052ca53-1a5d-48e5-a729-6051ff15bb70 | checkpoint | 2.7 Dispose of Trees and vegetation
3c4c427d-d2e1-57cf-9a4e-02cf52d9b520 | note | FREQUENCY: After clearing
cb113aa8-41d9-5a64-8e30-a2afaf4ae8b6 | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works. Noxious weeds shall not be mulched.
3c1ea9c2-b5a7-50e5-831d-3db690d76186 | note | REFERENCE DOCUMENTS: 201.07
ec2591f9-5132-50df-8ed2-5ddb83aa3119 | note | INSPECTION/TEST METHOD: Visual Inspection
9defec2a-4993-5afe-8dc4-c767bcbace67 | note | RECORD OF CONFORMITY: This ITP Signed off
b7125640-5335-5479-80b0-fbbf8c81fc5a | note | IP
01417a23-0245-5f4e-890a-d468649f1f1c | note | RESPONSIBILITY: Site Engineer / Site Foreman
ad2622ab-1fe4-5363-8e31-09b28a5e6455 | textbox | Date Completed:
97075fe3-fe52-4b78-a511-d036232cbbac | checkpoint | 2.8 Dispose of concrete, bituminous and other recyclable materials.
842dc5dd-48e4-5025-b33f-fb84bd3f9249 | note | FREQUENCY: After clearing
d42a91d4-00cf-5c16-aa5a-17e0b59637a6 | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
b5c41f4e-c160-5f8f-8418-ecca1abf9e82 | note | REFERENCE DOCUMENTS: 201.07
9a663194-718d-5aed-b6ce-8a4cc161b1bb | note | INSPECTION/TEST METHOD: Visual Inspection
e8de4653-40cd-56e2-b8b9-d221609301f9 | note | RECORD OF CONFORMITY: This ITP Signed off
253efb05-287c-5488-8b90-65fe0cf73bc2 | note | IP
07e899b7-0f79-5dcd-8940-7deac1f6f882 | note | RESPONSIBILITY: Site Engineer / Site Foreman
e19b577f-995a-58ff-bb5e-c7c85721867b | textbox | Date Completed:
90e81aad-a712-44d7-9f14-8f907809ce8d | checkpoint | Final Inspection
c6a10675-8e6d-5e06-82fc-ef1ae90e5ce0 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7a72178d-01b7-5078-93bd-33468e6499f3 | textbox | Print Name:
bdde0adc-49ae-5946-9eca-be793fe93703 | textbox | Position:
a54346e5-d2dd-573c-a86c-c03cd53deec9 | textbox | Date:
ff535517-6ac6-4387-b1c6-47a7639fb826 | checklist | ITP-002 - Stripping Topsoil & Topsoil Placement | itp | ITP-002 - Stripping Topsoil & Topsoil Placement
1c90da3f-0b75-4b3b-a738-6b8215acd860 | section | Preliminary Works
ba178327-ebfb-4f2b-8d95-350ed42ac797 | checkpoint | 1.1 Check for correct documentation
be7774ed-9841-59c4-bc26-01993fbe404f | note | FREQUENCY: Prior to commencing any activity
cfdaf46f-d4f2-5513-8bbc-291ca49ed0c9 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
898fdd7b-98ac-56f2-b6a8-bd07f8ffd05c | note | – using the correct and complete set of drawings
d9b34e39-8c14-5d1a-bf5a-622e6e939e1a | note | – all drawings are the latest revision
964ebb63-b3e5-5cef-82e6-6d5a7f81a5d1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
76592f43-ed7c-5bf7-843e-3b7bf84ab256 | note | INSPECTION/TEST METHOD: Visual inspection
a3dbc4e1-4b06-56a4-ab40-3d7411468f89 | note | RECORD OF CONFORMITY: ITP Signed
4585e278-003d-520d-a650-8ddb679e8e55 | note | HP*
ab5bb5c8-06dc-5323-bd7d-cffd5ade6df2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
8f5dabb2-59cb-5a5a-ac44-808133ca6e68 | textbox | Date Completed:
4aec96a8-1b89-41ec-ac07-672caa82d09b | checkpoint | 1.2 Implementation of all measures and controls
a34c2b1c-d423-5924-8a96-7ddb70be87c2 | note | FREQUENCY: Prior to commencing any activity
d440dcfe-f916-5e17-8402-c7af75a4344a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
5953c136-004a-5b98-83b1-a18dd7113d29 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
f96bfe80-ad5c-515c-a7d0-650a28fcb5f0 | note | INSPECTION/TEST METHOD: Visual Inspection
08c06cb7-dba8-51fd-8d4e-25181126912d | note | RECORD OF CONFORMITY: ITP Signed
6c1c0881-bdc7-55d1-8149-a0a2797d5015 | note | HP*
54a4493e-67cd-55e6-8da2-af4fbb374a1d | note | RESPONSIBILITY: Site Engineer / Site Foreman
a42fd917-ef87-5ebc-867e-694990335b40 | textbox | Date Completed:
b76aa27b-bd81-4890-9be9-3f1c7f06ef65 | checkpoint | 1.3 Ensure correct materials are being used
291b6718-9e04-5420-853a-1bf3c7f3d8f2 | note | FREQUENCY: Prior to commencing any activity
d391e22a-b49a-5461-a618-61288013ef72 | note | ACCEPTANCE CRITERIA: Topsoil placed on formations and disturbed areas shall be capable of supporting healthy, full cover of grass growth, and contain organic material
2244d6a3-d2e5-503c-8e10-622fa0ab87d9 | note | ○ Topsoil material shall be free from subsoil, tree roots, clay balls, stones, rocks, rubbish, contaminants, weeds, pathogens and toxic levels of any element with a pH in the range of 5 to 8.
92f6d2c8-3afd-51ac-bcf9-cd2d18d250e5 | note | ○ Imported topsoil shall conform to the material properties outlined in Table 720.042
0dd59599-86e6-54fa-ac7b-5c1b7dedb0d9 | note | REFERENCE DOCUMENTS: 204.04a
29957b68-ef0e-5a61-b34f-36de983d6c56 | note | INSPECTION/TEST METHOD: Verify
78447d57-5355-5a43-8e7c-378ed5f98507 | note | RECORD OF CONFORMITY: ITP Signed, Material Test Report (Import Only)
ba017127-2d98-5da0-aa41-dbe26625f9ce | note | TP
bf51325d-dc2b-5675-996d-1cca58487851 | note | RESPONSIBILITY: Site Engineer
f5400d4b-afd4-5c04-914a-d61e79e4b64f | textbox | Date Completed:
a264a72a-a5cf-4948-bcfc-634208ed3ec3 | section | Stripping Topsoil
42e778e0-a00a-4a7d-9865-860836fb6242 | checkpoint | 2.1 Survey Set Out
ae5776e3-a334-5c8e-a686-1e3a84a48405 | note | FREQUENCY: Prior to commencing stripping
ee656beb-8398-5804-8780-e11f238ac022 | note | ACCEPTANCE CRITERIA: Area has been pegged out in accordance with the drawings
a1c90fdf-b425-50b0-9bb8-0c77ac689cc4 | note | REFERENCE DOCUMENTS: Work Procedure
c0ee3956-7a85-5215-afb3-a6cce64b52c2 | note | INSPECTION/TEST METHOD: Verify
134f2a98-27df-5939-a55a-d58684ad1864 | note | RECORD OF CONFORMITY: ITP Signed
aebbf897-f71d-5f4a-b158-44c00ac465b9 | note | IP
d61bd699-4e25-50e1-8705-937199aa38ce | note | RESPONSIBILITY: Site Engineer / Surveyor
6f82d74a-909f-557c-b925-be593c34223c | textbox | Date Completed:
bef7063b-e6e0-4d64-981b-a14fc9c08fe5 | checkpoint | 2.2 Archaeological monitoring
d1b7e9c8-b702-51d8-af61-b2228911b2d0 | note | FREQUENCY: Prior to commencing stripping
fe150d20-d482-56ba-83a1-f68dccdca418 | note | ACCEPTANCE CRITERIA: The Contractor shall immediately notify the Superintendent if an archaeological site is encountered, or if any suspected artefacts are found. A ‘No-Go Zone’ shall be established for identified Cultural Heritage sites that are to be protected during the work under the Contract and in accordance with the CHMP
38f3dbaf-bfdd-5293-a8fc-7e0e7a5c732b | note | REFERENCE DOCUMENTS: CHMP
131986e8-1586-52d9-b2a9-2fe2d79a73fe | note | INSPECTION/TEST METHOD: Visual inspection
174c7450-c3ba-54e5-ae0e-c6b515382e03 | note | RECORD OF CONFORMITY: ITP Signed
ae0073ef-a2ce-59d3-9486-ec168ab7404b | note | IP
ead05e44-4939-5555-9d30-947474fb8112 | note | RESPONSIBILITY: Site Engineer / Site Foreman
a7330461-c0c4-5fbc-9b43-ddd4be27fa99 | textbox | Date Completed:
a259d7ba-0e85-45f5-aea4-2f45bbc2c3c7 | checkpoint | 2.3 Excavation Permit
ec212cc8-853e-5e2d-a08b-0baf706cb9aa | note | FREQUENCY: Each lot
ebb5db9f-5d90-531d-8038-48d5176066b5 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation.
6280e469-ed0b-5457-940a-59a1e357e881 | note | REFERENCE DOCUMENTS: Excavation permit
2d78bfe8-c8d7-52e8-8cd4-0a9d715f91b7 | note | INSPECTION/TEST METHOD: Verify
9589bdf1-1ef0-57f1-a76f-dd4f7451c75d | note | RECORD OF CONFORMITY: ITP Signed
021a6b9a-1daf-540d-9712-36564265af75 | note | HP*
7c3db772-068a-5446-82cd-c4fb30b7384f | note | RESPONSIBILITY: Site Engineer
d8ba77d6-d0e6-516a-b824-441e62d3a527 | textbox | Date Completed:
1d556407-cac7-4d41-82ff-6567a30b4de9 | checkpoint | 2.4 Designation of stock pile area or disposal site
10265a39-748a-5acf-8e12-e7c757a32f5d | note | FREQUENCY: Prior to commencing stripping
08fb8bde-ae54-5ad0-90d1-5b8d69fa1d84 | note | ACCEPTANCE CRITERIA: An area for stockpiling has been designated or a disposal site identified
5e2c54ec-448d-5d68-9bb6-a605328488aa | note | REFERENCE DOCUMENTS: 204.05c
ab956223-e511-5b6e-b634-bb6ae287941b | note | INSPECTION/TEST METHOD: Visual Inspection
1a8a67d5-cefc-5e70-8da3-5e9f256ea9d2 | note | RECORD OF CONFORMITY: ITP Signed
ce92104c-5414-53fc-80c7-ddc2e7009c8f | note | IP
8a42e5e8-28ae-58ff-9258-949b4a88e11c | note | RESPONSIBILITY: Site Engineer / Site Foreman
9f3a3d29-e8ed-5df4-bbe2-4dd8309a0618 | textbox | Date Completed:
31933ec2-b16a-467f-bf98-112b5b9d6995 | checkpoint | 2.5 Weed treatment
03d7486c-c60c-5bea-b710-970b25c0fcbe | note | FREQUENCY: Prior to commencing stripping
67cfcdff-8ce8-5fe6-9782-dbb687b815f4 | note | ACCEPTANCE CRITERIA: Site has been inspected for noxious weeds and weed treated if present
88d2d8c5-43e9-5e7f-8809-17f3adda1c84 | note | REFERENCE DOCUMENTS: 204.05c
fe682ffe-ca25-5c70-be51-04331a5b4e33 | note | INSPECTION/TEST METHOD: Visual Inspection
b19dc46d-6e97-592b-91f2-9309e1631c6b | note | RECORD OF CONFORMITY: ITP Signed
aab5c8bd-e58d-5b08-8f45-bf55cc6f7ec0 | note | IP
649562c6-8547-5867-aeeb-7a52cef3bc74 | note | RESPONSIBILITY: Site Engineer / Site Foreman
7a95000c-b4c2-526f-ab89-fb863c74bf33 | textbox | Date Completed:
9d1433fa-b555-4239-9699-f5a5613072c0 | checkpoint | 2.6 Maintenance of stockpiles
a7edd66a-9797-57d9-a251-96292241f56b | note | FREQUENCY: Each lot
9a6d1e21-e3ba-5e34-bff5-b9710d10e809 | note | ACCEPTANCE CRITERIA: Stockpiles maintained neatly and away from stormwater drains
1563c70b-edda-5f78-862f-105a20ee9cf1 | note | ○ Erosion controls in place
80431c2d-3a9e-5531-871a-9f1b0e44002f | note | ○ Stockpile treated to minimise spread of weeds and pathogens
ef8ce5b0-6f51-56a5-9760-173a4b446c62 | note | REFERENCE DOCUMENTS: 204.05c
32391cd1-ee46-5bff-b682-94d5ae16f130 | note | INSPECTION/TEST METHOD: Visual Inspection
53192470-24c7-5c07-afbd-50d1f1c82b42 | note | RECORD OF CONFORMITY: ITP Signed
20dac884-f1d0-5deb-818c-ee7a3690d324 | note | IP
20d3c6fa-9cb8-5e99-85ab-1eb55d3a0de1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
379056a4-dc2f-5a17-8043-99f8a029e3eb | textbox | Date Completed:
3666f8bc-4315-400c-957a-4e4b8d6d050e | section | Placing Topsoil
be00811f-2ce4-4dd8-a608-f4e8018ca1c6 | checkpoint | 3.1 Surface finish of cut and fill batters
4e886cb3-329e-5e30-a1f0-b6aeb731bfe6 | note | FREQUENCY: Each lot
708b3d4b-1626-56a3-ae4d-a2e49d7c6e48 | note | ACCEPTANCE CRITERIA: The surface of cut and fill batters to be topsoiled shall be textured by scarifying or horizontal grooving
9f9e693b-78ed-5ccd-8804-b00c0790712f | note | REFERENCE DOCUMENTS: Cl 204.06 (i)
8d0e8732-6ee4-587e-bbc6-98f9b6be0107 | note | INSPECTION/TEST METHOD: Verify
4875060e-befd-5457-ac5d-6007283f34ff | note | RECORD OF CONFORMITY: ITP Signed
ad15f634-d9a0-5ce4-ba9d-327fa711af6a | note | IP
15a9b47f-f591-5554-b8ba-7dbc8cc5e327 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f996c425-b05f-5301-a0d8-6a5cac3e4041 | textbox | Date Completed:
ab09c0ee-da8e-48fe-88b1-99ef2af3ec29 | checkpoint | 3.2 Topsoil Placement
64a4d754-d8e1-591e-9c6c-712e1f907989 | note | FREQUENCY: Each lot
66365fd8-99de-5cf5-b2c1-7d52c5cc953a | note | ACCEPTANCE CRITERIA: Confirm underlying cut/fill areas comply with Cl204.03 before placing topsoil.
1bd045c2-dfc7-5204-8d41-3054dadce860 | note | – All disturbed areas not paved or landscaped topsoiled to the following depths:
e55af9ce-539c-573c-8050-afbe6d1d741e | note | ○ batter slopes > 2:1 = 50mm min
14195bc0-3a52-51ae-8f2f-269188de35ab | note | ○ planting beds = 100mm min
f4c4eda1-dee8-5d08-a292-f096e3a70fe0 | note | ○ verge - 50mm outer edge to 20mm within 100mm of seal
c661107a-e26c-57c9-a554-37c0285774ba | note | ○ all other areas – 75mm min
cbfc958a-0172-53cd-86a7-7d8cc8774e55 | note | REFERENCE DOCUMENTS: Cl 204.17
8233bb6e-13ef-5e4c-9fdf-557f3c3caf1a | note | INSPECTION/TEST METHOD: Visual Inspection
101184f7-679c-536b-80cb-29d2e5102829 | note | RECORD OF CONFORMITY: ITP Signed
8425f58d-afb6-532c-beb1-49a0203490aa | note | IP
1a38b436-4923-5eef-aa14-aa8e782c8b1d | note | RESPONSIBILITY: Site Engineer / Site Foreman
fec0d94b-564c-597c-9103-e3e9a679caf7 | textbox | Date Completed:
bd4223a1-7e20-4b8c-9d40-7a6e81fed873 | checkpoint | 3.3 Surface level
9d48e3cd-e4bc-5929-af8e-9d0e2f3c2e8b | note | FREQUENCY: Each lot
2e754a9c-0289-5534-bcc1-cb2bc00d0b3c | note | ACCEPTANCE CRITERIA: Area topsoiled spread, levelled, but not compacted (except verge area).
640b7484-cde7-5379-af3d-bc461560fb6f | note | REFERENCE DOCUMENTS: Cl 204.17
81465944-bfc3-53e2-bd64-f5dbda17a49d | note | INSPECTION/TEST METHOD: Visual Inspection
4e1ee878-f7fb-5127-acc7-23fd93c53dad | note | RECORD OF CONFORMITY: ITP Signed
eab4b7e3-4f90-52a9-bc89-1fc487b9db4d | note | IP
e42d0b5d-68a7-5baa-a52e-aec3370eec8d | note | RESPONSIBILITY: Site Engineer / Site Foreman
dfa4289a-1b9f-59b6-890c-adf1eea7db01 | textbox | Date Completed:
62a95e49-5e5c-458c-8a08-51849414e57c | checkpoint | Final Inspection
10367acb-4ab3-520e-ba26-48c63bb95c2b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f9bd33f9-ef15-5340-9a77-f653cdba161d | textbox | Print Name:
d7187cfe-de18-5845-9a97-461bac790e93 | textbox | Position:
b1ed5ce4-8a73-5dd5-a134-10c4740e8c47 | textbox | Date:
dc1fe5ef-3b38-45f3-a906-b8d9df0edeb0 | checklist | ITP-003 - Subgrade Preparation | itp | ITP-003 - Subgrade Preparation
14b16671-094f-40e7-b78f-5c2ace7f04f9 | section | Preliminary Works
864a979f-3cfe-436f-86c3-cae39366a0db | checkpoint | 1.1 Check for correct documentation
be6f0aa1-ce2a-599b-8559-e20a6253f87f | note | FREQUENCY: Prior to commencing any activity
36660261-7841-5c77-b649-258caafd9f17 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
16f15610-0b8a-51ed-a17e-b421797935bf | note | – using the correct and complete set of drawings
66570b15-8707-59fc-9a19-362c27a5ebb9 | note | – all drawings are the latest revision
4c113ea8-4d91-5626-9b8f-2005312f58b7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6cfa9ca7-507a-5c3f-ace6-a8218559b0c2 | note | INSPECTION/TEST METHOD: Visual inspection
4d918af2-6466-573d-8786-f246526ecfca | note | RECORD OF CONFORMITY: This ITP signed off
1cab753b-8152-5048-93f2-ded007627a4e | note | HP*
f7b1f701-4952-570b-a4ad-dce07800943a | note | RESPONSIBILITY: Site Engineer / Site Foreman
22a879c2-4058-5bbf-ac46-48dd0d55eddf | textbox | Date Completed:
4a7e583a-9e2e-4b9b-ae80-ec0e3e767087 | checkpoint | 1.2 Implementation of all measures and controls
08320b51-d605-5c16-b57f-68bb2146d494 | note | FREQUENCY: Prior to commencing any activity
320d261c-a9d5-5f1f-bb4b-2122320c7acf | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
6e3572b3-80d8-527b-bd47-9cddd56d2984 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
15377386-051e-5e0a-bde3-a60ec9c5b068 | note | INSPECTION/TEST METHOD: Visual Inspection
bfc4ead8-7de4-5be4-9f8a-0d43260a23a0 | note | RECORD OF CONFORMITY: This ITP signed off
395af62a-71ed-5e16-936a-2ef0fc4c05a8 | note | HP*
d2a7ec4a-9fb3-5d7a-a9d7-0d0d1751bae2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
741fb1dd-ffdb-5366-b05e-b72f8df7f765 | textbox | Date Completed:
1a5283e1-7e5a-470c-b333-fef3e53ca339 | section | Construction Works
6a0c1f6e-d224-43b7-9bb6-32f4a7013da1 | checkpoint | 2.1 Survey Set-Out
53e71246-7ef5-511f-9116-2f1024a966b7 | note | FREQUENCY: Prior to commencement of excavation
84a59bc2-fddb-5787-ac0f-ee91ada1db6f | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
63106326-e1b6-571b-b1ae-b9eeb7604919 | note | REFERENCE DOCUMENTS: Drawings, Work Procedure
9bfd3f3f-40c2-5f0c-8154-66cb3e6470bb | note | INSPECTION/TEST METHOD: Verify
0dd58053-73e4-5eeb-a2e6-f9e169d7ef3d | note | RECORD OF CONFORMITY: This ITP signed
646c128a-19f8-5d9e-a332-1b582641840c | note | IP
c98d5d46-aed2-5878-b85a-d3a5ce1bce51 | note | RESPONSIBILITY: Site Engineer/ Surveyor
cd33853c-d8e8-530e-b9c8-699f205f2b19 | textbox | Date Completed:
7ee72907-db8c-44c1-b1f1-14123ef3fff2 | checkpoint | 2.2 Excavation Permit
5970abea-1d0e-5041-888c-17b92f32ce1a | note | FREQUENCY: Each lot
00f1a456-d627-55ad-a510-d2878b9eb07a | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation.
d7ee502b-bf25-50f0-a49e-b3d8e9647516 | note | REFERENCE DOCUMENTS: Excavation permit
9ce4d93e-403f-5d34-8e1b-32d5724d040a | note | INSPECTION/TEST METHOD: Verify
7b117ce4-e75c-5f51-a27f-b05d8bdee83c | note | RECORD OF CONFORMITY: This ITP Signed Off
4a56abf0-03f0-5f14-89c0-369025eae819 | note | HP*
e842c77f-e9fa-5169-a30e-a529bfa72cbc | note | RESPONSIBILITY: Site Engineer
53f48481-33ba-5347-8af6-5841f3cedb37 | textbox | Date Completed:
c7b7d8ff-0158-4e24-a598-f17400398c87 | checkpoint | 2.3 Subgrade Material Properties
c7034a50-32d6-5eef-ad3d-d7522a05ea8f | note | FREQUENCY: Each Lot
71ba813b-b950-5076-9467-3bf30836a657 | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
2e01c65d-a70f-595d-9378-400c46da3df7 | note | ○ If parameter met rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
8ed2c08b-49e0-5798-a38f-92b96838b248 | note | REFERENCE DOCUMENTS: 204.06 (e)
b3de0311-fc7f-5adb-8434-70bf751dc8d8 | note | INSPECTION/TEST METHOD: Test Point
d4a6ea41-5df6-5e82-802a-324770d42d3b | note | RECORD OF CONFORMITY: Test Reports
b05e10a8-2b2a-5093-9950-034bca978d6f | note | TP
fbe7f037-6006-5e4a-9e08-cb4b2d526ac4 | note | RESPONSIBILITY: Site Engineer
8eca3dda-654d-5a57-b1b8-f308f66df176 | textbox | Date Completed:
7558515a-fb7e-4357-9074-e76809c633bb | checkpoint | 2.4 Inspection of Subgrade Material
463f705e-b87e-5a9b-b8bf-13841ecdd8db | note | FREQUENCY: Each lot
772dd975-2ee4-5e62-bb7a-be0d4937eefe | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
22dc9492-3bb5-56a4-8aef-d73ec85c277e | note | REFERENCE DOCUMENTS: 204.06 (c)
6305e69d-9633-52f5-ae16-6a09d096f412 | note | INSPECTION/TEST METHOD: Verify
ad8af686-bad3-506a-86f7-90b9913c4736 | note | RECORD OF CONFORMITY: This ITP Signed Off
0773957f-6306-5f27-a52e-7bc7fe83d39a | note | HP
b3abece5-2a2d-55f1-9783-89a4bb750510 | note | RESPONSIBILITY: Site Engineer/ Superintendent
f1e61a7d-7031-5e5c-852c-e88a547c8165 | textbox | Date Completed:
f6445178-e811-448a-bfb2-3764425ecf6f | signoff | AUTHORITY HOLDPOINT
2e7f0938-1df2-4961-8f43-9c0f80783d6a | checkpoint | 2.6 Acceptance of Rock Subgrade (when applicable)
f4fdb916-97f8-51f3-9bde-08e9c619f091 | note | FREQUENCY: Prior construction of the regulating layer
c8af3bd9-20eb-5a9b-8d66-0d04430d0285 | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
3e35cde0-95bb-5804-9e51-6dc8234717e8 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
4aafc664-35ba-5406-acf3-f2f6d61cddd0 | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
4dd66ff0-cd5d-55b0-b20b-9df91d899bba | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
aaade842-44fb-5a3d-b0c2-8e33161adedf | note | HP
d3f14ee9-2d7c-5aef-973a-cad68824dcb4 | note | RESPONSIBILITY: Site Engineer/ Superintendent
bab5b9f5-e852-5c9a-9da6-262d1b2c7f79 | textbox | Date Completed:
8e2d67d7-3b4a-4de6-8669-b18bf58f143c | signoff | AUTHORITY HOLDPOINT
34f73afb-4129-4439-a84f-37ee970a0d58 | checkpoint | 2.7 Unsuitable Material
af278c57-2b0e-5362-b535-45f15eb280cd | note | FREQUENCY: Each Lot
7670b594-538e-5745-a6c9-160f62c09581 | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
c00caa42-71c3-55ee-a67d-f8437ce3545e | note | REFERENCE DOCUMENTS: 204.07 (d)
577e5a7b-d6d8-5330-8396-225f5dbb81c2 | note | INSPECTION/TEST METHOD: Visual Inspection
bcb72e42-b1b9-516f-a03c-a29a0f6a11ba | note | RECORD OF CONFORMITY: This ITP Signed Off
e8eb47f7-8f51-5c96-a544-d126d109c051 | note | HP
d904b1f3-2d8e-59b9-afee-bc0f520c0b17 | note | RESPONSIBILITY: Site Engineer/ Superintendent
a7095040-1d9c-5955-8e3c-6bc883488203 | textbox | Date Completed:
8ea7aa03-2e97-4016-8c1f-2457e2641350 | signoff | AUTHORITY HOLDPOINT
64fb5b9b-8dc0-4d55-ba78-060e30ac09e3 | checkpoint | 2.8 Groundwater
976d3094-b76b-5584-b831-b109d8e6b0da | note | FREQUENCY: Each Lot
a07d0684-99d7-5861-ab6b-adc62bc6fa9d | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
e574eb4b-4240-55fa-aebc-7d44015e2eff | note | REFERENCE DOCUMENTS: 204.06 (h)
f44a8492-3579-5828-a99e-cbe7e74195d5 | note | INSPECTION/TEST METHOD: Visual inspection
64b9b8f8-7556-5235-8d04-8fca22591951 | note | RECORD OF CONFORMITY: This ITP signed off
5e472938-f363-546e-a6bb-3d1923070279 | note | HP
d658841f-8084-521a-8126-3d8525d5657b | note | RESPONSIBILITY: Site Engineer/ Superintendent
2a46ae83-50ff-5ca5-aec6-5151eca1c8ca | textbox | Date Completed:
924025eb-d07b-4e1b-bac3-af5c11e0923e | signoff | AUTHORITY HOLDPOINT
cde7b97d-c49b-40d9-aeba-d9d71032d092 | checkpoint | 2.9 Trimming and Level conformity
94960a3c-972f-57a9-a20b-69ea10448d17 | note | FREQUENCY: Each Lot
e7d5499f-db1b-5dd7-91c9-82ef6ae1496f | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2.
5bf5a17b-877e-5171-8b22-4979c219646d | note | – Level tolerances:
30e4b6e3-3b1e-571b-a57d-56c507061a53 | note | ○ Range x = +15, -30mm Max S = 12 mm
59d9d49e-8821-5b18-bb12-f363b9e52515 | note | ○ 40 measurements per lot (Scale B)
5ba691ce-1eb4-5e2f-ad46-2f3aed97c12d | note | REFERENCE DOCUMENTS: 204.03(f)(g)(h)
d67020a3-b9c4-5765-a17a-fe548dc19606 | note | INSPECTION/TEST METHOD: Survey Report
44f7a24d-252c-5174-9e9c-0bef71d2f3ce | note | RECORD OF CONFORMITY: Survey Record
ddcc60a6-240d-5569-b473-6364a7ce5877 | note | SCP
ed90f6c7-93b7-55ef-a6de-20805a1263f0 | note | RESPONSIBILITY: Site Engineer/ Surveyor
a5cc56c4-f82c-5a47-a098-3d344964fa73 | textbox | Date Completed:
64235536-8ece-45f1-9991-7d343a50fdfb | section | Testing
d7071153-8e16-4c89-a448-a77bbcc0142b | checkpoint | 3.1 Proof Rolling
46a52024-0b2a-5d0e-bb56-872c278f01a9 | note | FREQUENCY: Each Lot
ce4096a8-b611-574d-b95a-a1243869f527 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
0807631c-e467-52fc-a4fc-99049ec2b6f1 | note | REFERENCE DOCUMENTS: Section 173
395e858c-585a-504d-b190-844f444d91dd | note | INSPECTION/TEST METHOD: Visual Inspection
586362d7-e068-581b-98ce-a32c1d1fe90c | note | RECORD OF CONFORMITY: This ITP signed off
d8d7fe2e-d642-53f2-840d-4dd83ab292ef | note | HP*, WP
c26f09e5-0246-56f3-b8dd-1ffa867de910 | note | RESPONSIBILITY: Site Engineer/ Superintendent
33febd79-1b3c-56f4-b55d-1b841811271d | textbox | Date Completed:
273b8858-427f-42bd-8756-a7e77dd85c41 | checkpoint | 3.2 Minimum Testing
f2d8faa3-e3d4-5955-8596-22f5e856e23c | note | FREQUENCY: Each Lot
6616c59f-38f4-5af8-9bc4-00b3c5b27683 | note | ACCEPTANCE CRITERIA: Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test.
7cd6efec-5ffd-5cd1-b6c8-6fec6d95d744 | note | ○ After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
30437554-b4ce-5fe7-b6a3-6b277f3f1289 | note | REFERENCE DOCUMENTS: 204.14 c
cfe55a24-7d6d-5457-a5cb-a90e4d169fd5 | note | INSPECTION/TEST METHOD: Test Point
6d0d9d71-a318-520e-86af-8c9462ba4967 | note | RECORD OF CONFORMITY: This ITP signed off
a52f0817-dd18-537b-ba4d-d5ef27b6a33e | note | HP*, WP
8af305dd-192f-5b91-8206-873b2f853368 | note | RESPONSIBILITY: Site Engineer/ Superintendent
1343fbea-f7dd-5947-ac98-4d1878204981 | textbox | Date Completed:
a6468237-37b5-4523-8378-f72cb508a058 | checkpoint | 3.2 Compaction Testing
5be0b178-9b74-5bfa-95b0-289c165d0b18 | note | FREQUENCY: Each Lot
1e47174b-01fb-5d1e-921d-d2a84d0f5990 | note | ACCEPTANCE CRITERIA: Ripped and re-compacted material below Cut Floor Level = minimum compaction 98% SDD.
be849ca1-34a5-5d23-8d03-d569c65fadfd | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 95% SDD.
25ddcecc-e2a3-5d96-b5b5-a0c9dd17c48d | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 95% SDD.
a5b7fd14-a4b6-506a-aff4-fb7b9ca92ac3 | note | REFERENCE DOCUMENTS: Table 204.131
2beebec6-4a03-5f61-b157-388255efdebe | note | INSPECTION/TEST METHOD: Test Point
f42690da-c267-56da-8b17-afb0d6f15222 | note | RECORD OF CONFORMITY: Test Records Lot Register
1fadf292-170a-50aa-b8e6-d420c5bcf897 | note | TP
f500569d-b483-590a-af9e-2b394dd39a0d | note | RESPONSIBILITY: Site Engineer
2235858f-3244-5ec5-ac4f-bd63a12f8e4a | textbox | Date Completed:
809e9e8b-2d0a-4430-a082-499f9309ae7d | checkpoint | Final Inspection
f4b3f6c2-dcc6-5ddf-9746-217cee176441 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1f565adb-2add-53ba-858d-7b68809c4f10 | textbox | Print Name:
10208194-ba2f-5254-a6bf-ae86e688eaf3 | textbox | Position:
322ed660-9983-53a1-b5a2-59fde1ce02bc | textbox | Date:
e56e390f-8ff4-4335-b98f-f9f5692eb3c9 | checklist | ITP-004 - Type A Fill Placement | itp | ITP-004 - Type A Fill Placement
75f4c904-4589-47b3-880d-63dd3545b7ff | section | Preliminary Works
d8ccb91a-4e91-48b4-8ee1-87db2b81dfe5 | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
6ecdb993-f97e-5efc-ba07-273962de8c87 | note | FREQUENCY: Prior to commencing
de5086be-882c-5e87-a2a6-98cbcc6708b9 | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
82db62a9-e6ae-599a-8f12-1fb446a75529 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
498b911a-5186-5ab8-b5cb-36b68e58d39a | note | INSPECTION/TEST METHOD: Visual Inspection
072eae40-c76f-5deb-b9af-2578cbe6f17c | note | RECORD OF CONFORMITY: This ITP Signed Off
63c418b6-9af7-5e3b-a5cd-45c2149b04b7 | note | HP*
3139ec36-d1e7-58ef-9507-c950a527ce5d | note | RESPONSIBILITY: Site Engineer / Site Foreman
5b394891-30ee-5c60-9764-fbc8a74478ed | textbox | Date Completed:
e250a1c5-5a37-4aef-b4e3-3f6aae8f71b4 | checkpoint | 1.2 Implementation of all measures and controls
f45c8f62-c314-553e-be24-958648175386 | note | FREQUENCY: Prior to Placement/ Each Lot
fd31f03b-f9d5-5ee2-8e77-88f32e74f7d0 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
f83d0bb6-59bf-51ac-991c-34c4df1a9113 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
66db0f5b-c39d-5e4d-acb2-2c60e95f1d12 | note | INSPECTION/TEST METHOD: Visual Inspection
bbac8a3b-11ac-523e-b206-b1634b457808 | note | RECORD OF CONFORMITY: This ITP Signed Off
8ce55903-b154-512f-a19e-d2db49692823 | note | HP*
39fdbce0-c1e9-5c54-8990-a3a724455e60 | note | RESPONSIBILITY: Site Engineer / Site Foreman
56394e81-debe-5715-be3a-e96c09a6246f | textbox | Date Completed:
76b1209d-2a77-43d9-bd53-c2bbcac7fc32 | checkpoint | 1.3 Verify Material
d56162d6-1cf2-5e72-a7e5-f7596c65bbab | note | FREQUENCY: Prior to Placement
3014429c-d9d5-5006-978c-1389343d3719 | note | ACCEPTANCE CRITERIA: Assigned CBR to be greater than 6% (<10%), swell is to be less than 1.5%, unless approved as expansive. Soil is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075. PI between 6 and 25. Permeability of less than 5X10^-9 for capping and verge material
0dbb8195-7d1f-52db-befc-facb4c872ed9 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(b) Cl. 204.06(c) Table 204.041 Table 3020.052
a0b94917-7e6e-5562-adb5-f3d701c50332 | note | INSPECTION/TEST METHOD: Site Inspection
39263d33-68ad-56a8-92e0-0bde7d797142 | note | RECORD OF CONFORMITY: Test Record (If silt is observed)
1d368a30-e9e5-59db-9f2a-9b116b9a60e3 | note | HP
f6b98e43-6d2f-58c4-a5af-951b59a75458 | note | RESPONSIBILITY: Site Engineer & Superintendent
e504e1e0-fcd9-522a-a1e4-d595f23f3e45 | textbox | Date Completed:
b630f16f-c9f1-432e-8c40-dc1931dfde05 | signoff | AUTHORITY HOLDPOINT
947e9e10-866d-45f7-925d-8858f7b4da0e | checkpoint | 1.4 Excavation Permit
2a5213f9-84bd-5c80-8c18-8f7d1c3c2d02 | note | FREQUENCY: Each lot
0c5e7ae5-76f3-5872-a555-c677f7ddf2bf | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation.
621bc110-360b-51f3-aa2c-4df52ab25bad | note | REFERENCE DOCUMENTS: Excavation permit
8246fdd3-8a9a-55df-a2ae-f1f0138c7fd0 | note | INSPECTION/TEST METHOD: Verify
277c549f-ca44-580f-8da7-7d9e982b2e33 | note | RECORD OF CONFORMITY: This ITP Signed Off
a86c0519-5d7f-5f7b-9745-022db828f152 | note | HP*
b3a02fe6-ad27-598a-9b17-7c877fdfe3da | note | RESPONSIBILITY: Site Engineer
14366dd1-430f-51f3-8ddb-5d5ea336274e | textbox | Date Completed:
4c7bd8dd-db33-487f-bc70-f05734d9d27a | section | Construction Works
a2e1edc1-b38e-4d15-9794-b6388f061a8b | checkpoint | 2.1 Survey set-out
cc70ba72-148b-5c89-8c3d-cd1ce6757cf9 | note | FREQUENCY: Prior to Commencing Excavation
baa08f07-e753-515f-ae08-e1df95790b9e | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
39f9433f-a5d0-5477-b33a-95c1ca980237 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
2d8dbb58-f09d-529b-be3e-2ac7d798542c | note | INSPECTION/TEST METHOD: Site Inspection
852536ba-7832-5900-b8a8-2f9caebc4b0c | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
bcbbcec8-b3da-5a9b-8dfd-1b867fc29688 | note | SCP
60b3f373-0b2f-5bfd-aefe-f34a52bef6a1 | note | RESPONSIBILITY: Site Engineer/ Surveyor
f0755d78-0ba6-5b62-87f4-f18b68266f03 | textbox | Date Completed:
a5d2044a-9d13-40ac-a2f5-40e6c1d80cb1 | checkpoint | 2.2 Inspection of fill area
899aa5e1-edda-5ef4-854e-4b34efe17360 | note | FREQUENCY: Each lot
8a56c566-5458-5260-9c0b-9897e96e50d5 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
12c5609d-b781-5237-b507-a7b6420370d3 | note | REFERENCE DOCUMENTS: 204.10 (b)
3cd552b7-6604-585a-8aae-54e6a15f4022 | note | INSPECTION/TEST METHOD: Visual Inspection
7207fe76-0f08-5c68-84b9-dbec1aab159c | note | RECORD OF CONFORMITY: This ITP Signed Off
5928d8f8-7e26-52a0-bf86-18d83da150d6 | note | HP
e6230922-5f0b-519a-ab91-b7c720bc67c7 | note | RESPONSIBILITY: Site Engineer / Superintendent
b09ee0be-1103-55c2-8e9a-feb8ca159928 | textbox | Date Completed:
fcb26462-b44d-4067-9d4a-dfae870fd068 | signoff | AUTHORITY HOLDPOINT
b4605080-fa77-4ff0-9535-6aafc44d394e | checkpoint | 2.3 Layer Thickness
ba55163c-9dee-5cf4-8b49-1c2dd26bfe68 | note | FREQUENCY: During Excavation
3241d3e8-30af-5965-89b2-971d2c88c58b | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
f4cb9672-c2d8-5d12-bfbe-07a56ce2fa72 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
84c6a93f-3895-5b91-baea-287752b50e7e | note | INSPECTION/TEST METHOD: Visual Inspection
aa2ddc0f-9500-56e8-8889-342281a0bd7d | note | RECORD OF CONFORMITY: This ITP Signed Off
ffe8c66e-6d89-56f1-983b-77ac1f5c8e15 | note | IP
96581859-70fe-552a-b600-bc422112613f | note | RESPONSIBILITY: Site Engineer
5e81f093-e7c1-5dbc-835b-a9623b45b044 | textbox | Date Completed:
57a5a5ec-0992-409b-a7e6-03bae9b6d41d | checkpoint | 2.4 Maximum Lot Size
d5132140-c39f-5d4a-b8a4-dc580c70c4b3 | note | FREQUENCY: During Excavation
bb986640-973d-5476-af57-a8b704db5a8b | note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 5,000m2, whichever is lesser.
1d0aba88-da7c-5e0f-b323-999d5953c5dd | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
8d65550e-c705-5d9b-9766-b3dcdb81fcbc | note | INSPECTION/TEST METHOD: Visual Inspection
f58a6a30-fd06-501a-ba34-094d76b76f5d | note | RECORD OF CONFORMITY: This ITP Signed Off
84ac03b1-f1b5-5063-b5e2-c05e9d37418d | note | IP
d5e0336e-e28d-5563-8055-7769c90dae7a | note | RESPONSIBILITY: Site Engineer
d8543b5c-64cb-536d-bb5f-8e281fca8fdb | textbox | Date Completed:
f38651a4-1c18-4ccd-a2ce-f6bd33a4adec | checkpoint | 2.5 Type A Placement
1e93078f-c5da-5de1-b753-d0d46923d8ca | note | FREQUENCY: Prior to Placement/ Each Lot
13df71c7-8c7c-5d48-bf1d-b74ab0d14560 | note | ACCEPTANCE CRITERIA: Top of fill must be shaped and compacted to minimise damage due to wet weather note 12 on Pavement Details 009-0001 "Capping Material can be substituted for (3%) Cement treated Stab Sand in confined areas
4f4d660e-4933-5bfe-9ff6-ac21f5ce4acc | note | ○ Any rocky material present must be uniform throughout the layer
31b1a867-c356-5c1d-b52b-88a0f4b8f977 | note | ○ Each layer shall be kept generally parallel to the surface of subgrade
1fb160d5-d9c8-56a9-b088-4ebcb4dea781 | note | REFERENCE DOCUMENTS: 204.10 (d) (i). 204.10 (d) (ii). Table 3020.052
036a7420-3fab-5e61-aba9-1e650d1b6b0d | note | INSPECTION/TEST METHOD: Visual Inspection
a5ec85dd-ac2d-58ae-ae0a-93b5e3536d95 | note | RECORD OF CONFORMITY: This ITP Signed Off
bfad1d15-ee3b-5960-8454-9a9d92cbd478 | note | IP
c45d78ae-ad25-56fc-8cc4-f88fa0fe03f7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
e5e0dae0-56b9-549b-8f3b-9d87fdcb99ab | textbox | Date Completed:
fb5d835f-b9a9-4185-a804-552b12c55303 | checkpoint | 2.6 Proof Roll
47423b69-2569-5670-87ad-1b93e7cc936d | note | FREQUENCY: Each lot
b1e28933-ab14-5be0-8892-df892243afcd | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
a039ac9a-fdc8-56fa-9ec0-54ba6e68508a | note | REFERENCE DOCUMENTS: 173.03, 204.12) 204.10 (b)
8bab939e-9b87-5f32-9245-01684ba65fca | note | INSPECTION/TEST METHOD: Visual Inspection
2011aaba-3236-5840-aa6d-609e89f1cfe7 | note | RECORD OF CONFORMITY: This ITP Signed Off
f22be64a-34e3-5d93-a6a4-c23bf79a36e6 | note | WP
db75687f-15df-5a1c-93b6-5e5ba870bdd8 | note | RESPONSIBILITY: Site Foreman/ Superintendent
eb058e04-7dee-5e2e-98a6-f4b6e8bcecb8 | textbox | Date Completed:
04ec0bcb-1cb0-4cd1-abee-135dd1fe4650 | section | Testing
e06a5a5e-a744-42f2-a164-623a8a550d78 | checkpoint | 3.1 Reduced Test Frequency
b1d62aa3-096f-5284-928d-4e0cfe4ddf00 | note | FREQUENCY: Each lot
ddb434c2-6e0d-5a0c-8a04-250bd739d92e | note | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
fc47a587-07a4-51ee-ab95-c756842639cc | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
7d0af920-45ed-53a9-9c77-efa711a02798 | note | INSPECTION/TEST METHOD: Test Record
e4d628c6-e98e-5162-81d1-752e7a05a174 | note | RECORD OF CONFORMITY: Test Records
2e6868aa-dabd-599c-ab0a-c9586f0c1e55 | note | AP
f1f11744-21a4-53a5-be93-332695cd94b2 | note | RESPONSIBILITY: Project Engineer
269e6646-6490-58c4-a6e6-981151270c34 | textbox | Date Completed:
b5840fed-b4e7-484b-9fdd-52c48f1b25d4 | checkpoint | 3.2 Compaction Testing
50783cca-f45f-5c60-b0f9-8b7442b7056b | note | FREQUENCY: Each Lot
b5a43dc9-9ffd-5578-a849-960ee1522ee1 | note | ACCEPTANCE CRITERIA: Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B).
9245da81-2911-5940-b526-2e859bfec548 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
af3e7481-0d50-5864-8fb1-21fcda4a2d06 | note | INSPECTION/TEST METHOD: Verify
71aec34d-f7b7-5293-8574-2f7d0f9319eb | note | RECORD OF CONFORMITY: Compaction Test Records
a72553b8-546e-58ff-9e26-4fa31a4e2729 | note | TP
df7dd4ff-f1e1-5f0e-9f7a-678ca5a56701 | note | RESPONSIBILITY: Site Engineer
9549eb82-de55-5948-b9df-26186a005317 | textbox | Date Completed:
b7c7d919-8e89-465d-9fb3-09dc877ae950 | checkpoint | 3.3 Compaction Testing (Small Lots)
8b7caf4a-2375-57a3-b1c8-5cc3ef96396e | note | FREQUENCY: Each Lot
75315883-cf90-5c8e-9f2a-45457e298be4 | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% SDD.
1fd3e8c4-d0b4-5b13-b448-b17670dd9a66 | note | REFERENCE DOCUMENTS: 173.04 d
43bd6a98-1afe-5bc1-9965-f884a5ac2fc4 | note | INSPECTION/TEST METHOD: Test Point
2999b982-9572-57d6-a078-29b35e0d1907 | note | RECORD OF CONFORMITY: Test Records Lot Register
ca75e609-53b6-55bb-ae5b-f88e7e0c1947 | note | TP
6af6cac4-e05e-5b99-9107-fcce2bf70cab | note | RESPONSIBILITY: Site Engineer
fe8a4221-bf48-5aae-af1c-776daf509d06 | textbox | Date Completed:
a81c942b-3787-4d1d-b1c6-b830f842c7d9 | checkpoint | 3.4 Maximum Particle Size
81ba8cb7-3a6b-57d8-8c43-28e8e9dd4d60 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
0385cdae-ad90-53e1-b6c7-82ae28219a29 | note | ACCEPTANCE CRITERIA: Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075
61311910-43ee-5a72-9035-452644f4e4d4 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
b2309b05-a20e-5757-b337-34b7ce68ee5e | note | INSPECTION/TEST METHOD: Verify
832c768f-6fd7-5e6e-8f47-eace6e0a4303 | note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
a6cd5e1c-3f1b-5b05-a3a4-4817bded7a04 | note | TP
6bfca3bf-822b-5bfc-8a75-67ac3c483603 | note | RESPONSIBILITY: Site Engineer
4f5877ff-0e06-5bbd-b539-b9486568da67 | textbox | Date Completed:
588a5fc6-65d1-4e08-9c8d-ee3e6a9a6694 | checkpoint | 3.5 CBR/Swell
bbaf5e6c-e00b-583b-be4f-42b4fdd77710 | note | FREQUENCY: First lot only
05c817b0-2ba5-5dc4-9b1d-2b556fff0c6e | note | ACCEPTANCE CRITERIA: CBR: ≥ 6%, Swell: ≤ 1.5% (Verge material less than 1.0%).
1f9f8b8c-4f3a-5556-a188-49283eb0db17 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(i) Table 204.141, Table 204.041
39711b90-e79d-5c1a-b424-6c3acfe78b78 | note | INSPECTION/TEST METHOD: Verify
a2e01294-6dd1-5000-9fee-63b7647b28e3 | note | RECORD OF CONFORMITY: CBR/Swell Test Records
955c3267-ab02-54b7-a023-c8f9cb6fb004 | note | TP
7d34faba-ac7e-5d24-ba73-7dff845fc7db | note | RESPONSIBILITY: Site Engineer
641719b8-3012-5c97-9537-04b6748676d1 | textbox | Date Completed:
5f46798d-8a24-458c-bc32-4cdc1abaf385 | checkpoint | 3.6 Atterberg Limit Tests
3a642653-dd4b-5e27-868b-b763a05850db | note | FREQUENCY: Each lot, unless reduced frequency has been approved
0f7c1d6e-91c5-5097-a4b1-bf5cd855421f | note | ACCEPTANCE CRITERIA: PI between 6 and 25, PI x % passing through 0.425 to be less than 1000
18facde4-f64b-5304-bd46-1e5f0b5882b8 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
e49d0a5d-ff07-59e5-978a-f96d8fd20522 | note | INSPECTION/TEST METHOD: Verify
bd43a2eb-abf0-5a44-96ba-c2a3c45460a2 | note | RECORD OF CONFORMITY: PI Test Records
cfe8aed0-32ff-5bea-9a13-1158193935fe | note | TP
4120ce66-0551-549f-ab05-5962d381e6c2 | note | RESPONSIBILITY: Site Engineer
ac96a5cb-16dd-548b-a04d-007af1ccfe4b | textbox | Date Completed:
50ddd3c4-30de-494a-b39a-d88bd80d8cac | checkpoint | 3.7 Permeability
702a1a4b-fe5a-5021-ab8d-158ffd01a0f2 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
71310ae8-17a9-5f03-83cd-7906a5652824 | note | ACCEPTANCE CRITERIA: Permeability of less than 5X10^-9 for capping and verge material
474ceed4-62e1-50db-a6df-dbb700a17cab | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
83f05760-b2c6-5e92-ab9c-0cd1f05c1ff6 | note | INSPECTION/TEST METHOD: Verify
f8727199-dd50-56af-8de9-5e2ebf986e6a | note | RECORD OF CONFORMITY: Permeability Test Records
4c6fa822-cea0-559a-9948-593516c34f6c | note | TP
6463541b-057c-5d4b-b5ae-f8b6d7050b24 | note | RESPONSIBILITY: Site Engineer
51014c57-af54-549e-b1a2-d9a996e38bf3 | textbox | Date Completed:
a3db7c22-5286-4af5-825a-de4e90008277 | checkpoint | 3.8 Material Property Testing (Scale B)
239b30bd-b9c5-5d31-9ef7-f0b71f1d2d8b | note | FREQUENCY: Each lot, unless reduced frequency has been approved
dcf61991-d055-5113-88a2-ec94da37384b | note | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
46befcd1-7b88-5df9-8dd7-104f15f09498 | note | REFERENCE DOCUMENTS: Cl 204.04 Cl204.14
73ae911b-0927-57f4-a83d-0e72edcc81e3 | note | INSPECTION/TEST METHOD: Verify
f3072fec-9cc3-505e-9353-330f8f543a10 | note | RECORD OF CONFORMITY: NATA test report
fc6dc640-c833-56fb-b5d5-08807cf50fcb | note | TP
f293d086-7be1-5b8c-b0c6-e6b0f31b38cd | note | RESPONSIBILITY: Site Engineer
da14909c-86ef-5202-8387-429b38a58601 | textbox | Date Completed:
f8b04c18-de05-46f1-9262-b8a7bd9001d8 | checkpoint | 3.9 Survey Conformance
8d0bf24b-e71d-5d8b-b9d8-cc6a5f49a77c | note | FREQUENCY: Each lot
4e831e24-de3e-56c6-aa76-17d44b3577bc | note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
10c0546f-1297-5395-9c78-a094f5f4b7b9 | note | ○ Scale B: Range x = +5,-25
620fca79-a5ef-51d5-8e8c-b5faf4144d84 | note | ○ Max S = 15mm 40 measurements per lot
63752f05-d5e9-548f-a68a-3fde980e113f | note | REFERENCE DOCUMENTS: 204.03
682d3788-b9a9-5a20-8904-fd2f11e276af | note | INSPECTION/TEST METHOD: Survey conformance point
c2f785b1-8902-5420-b337-90cb0cbb6d98 | note | RECORD OF CONFORMITY: Survey report, Lot Register
f9261f5e-b164-5459-8e8b-1a7cb5b2a769 | note | WP, SCP
b5669b9a-a3ad-53da-a3ca-8a8572b72099 | note | RESPONSIBILITY: Site Engineer & Surveyor
6a659451-b6f3-5af5-89db-5c68a32b593d | textbox | Date Completed:
5d328dd6-82bc-4bc7-a023-193e701b0f77 | checkpoint | Final Inspection
a3490456-c427-5c6c-a5c0-5dacf5de2499 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
026104c7-16a0-5ee5-a0c7-cb8d2e252702 | textbox | Print Name:
9a777a3f-e4ba-5fee-81bd-6a2fe1993207 | textbox | Position:
a4a3b18a-ba90-512a-95cd-0804f842da8e | textbox | Date:
6d63de4a-aea4-40f1-9edc-7d4b4909c73a | checklist | ITP-005 - Sub-Base Construction Class 2 | itp | ITP-005 - Sub-Base Construction Class 2
9c98349c-4d46-4db1-b2ae-fb7d27d6dc4b | section | Preliminary Works
ff3632cc-72a6-4442-a6a9-38546a4978ae | checkpoint | 1.1 Check for correct documentation
69b661b1-092a-5877-85ad-4497300adf91 | note | FREQUENCY: Prior to commencing any activity
ee8ac5d8-6e4a-5d45-9d90-7f698f3be2d4 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
cbf23f02-b702-5d1a-a7a0-a9a53d9b5a24 | note | – Using the correct and complete set of drawings
f05238a5-2865-5a7d-8aea-571cb8da1989 | note | – All drawings are the latest revision
15a72f0e-fee8-5a52-94db-2b4079d2df56 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
68a4337b-151b-5866-beee-ca33a3a04bec | note | INSPECTION/TEST METHOD: Visual inspection
fd390ae5-e9df-55b7-a384-50997068c5e9 | note | RECORD OF CONFORMITY: This ITP signed
294f88ae-ddad-59ab-b810-e9da15a19815 | note | HP*
dcd1bb31-2b1c-535f-af9a-50fec9d11eb9 | note | RESPONSIBILITY: Site Engineer / Site Foreman
6419ebbc-48ad-5be0-a240-5a1e2b1113ff | textbox | Date Completed:
262900ea-f125-4281-a2cf-7994050b274a | checkpoint | 1.2 Material Mix Design
54a43d6e-709b-5ba6-b812-3c64ff3497d9 | note | FREQUENCY: Prior to commencing any activity
524f75ef-e164-54dd-bb84-285f34855ecf | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
fec41483-9a5e-5362-b8ab-94b11041c9be | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
05e3ae9a-5d82-551d-82ad-b739b6239346 | note | INSPECTION/TEST METHOD: Document Review
373747f7-870d-5326-b08c-1136044f08c7 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
87d09f7f-9f3a-53bf-a612-2cfa6e16bbdd | note | HP*
0a21659a-3313-58ca-abfd-8f7403a31422 | note | RESPONSIBILITY: Site Engineer
c52970eb-b8c3-5f04-b483-43f40ed75d66 | textbox | Date Completed:
6caf42af-be44-4af3-8489-337c38b124a3 | checkpoint | 1.3 Implementation of all measures and controls
393f6928-b0d8-5024-86b2-d47501e33dc4 | note | FREQUENCY: Prior to commencing any activity
b594f2f7-e646-5809-96c9-76f41c193324 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
fe2492d9-9401-5e38-bece-9832a4b744ee | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
f1799a63-1316-5176-8ec8-e7d6c6a3d042 | note | INSPECTION/TEST METHOD: Visual Inspection
d449d604-6a5b-51cd-a53f-6638da166521 | note | RECORD OF CONFORMITY: This ITP signed
bf86ab78-119f-54f5-89f8-b5a2db97c287 | note | HP*
20571b8b-1dec-5276-b47d-287f87fab5c2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
972fb9b7-dbd8-5d8d-a4e7-1caae699c132 | textbox | Date Completed:
66c9d022-74fe-4308-a5a3-c59a3d800f23 | section | Construction Works
2b30cb9f-33ba-485e-a04c-1580f0404214 | checkpoint | 2.1 Transverse Joints
1333faee-9eb0-5f88-9418-c390a390d44f | note | FREQUENCY: Check prior to placing material
c5db76a1-95c1-5399-aa98-bce94ff01d44 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
740e5f3f-582b-553f-8a45-bf6b24e48d75 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
b9689f33-d379-5209-8726-71badd1397fc | note | INSPECTION/TEST METHOD: Visual Inspection
e7871550-fbba-5483-bf84-292ad442c14b | note | RECORD OF CONFORMITY: This ITP signed off
8870ca8a-0860-5a55-b9a7-29fb4f8881e9 | note | IP
9b58d026-06ca-5de7-b876-74c35f75e97a | note | RESPONSIBILITY: Site Engineer
0424ce41-ee83-522f-b165-2dd2700b2d0f | textbox | Date Completed:
70339aef-efe9-4373-9bbb-27ce10cf8b68 | checkpoint | 2.2 Longitudinal Joints
1814a9fe-1ad1-5c01-8aff-76a8e9ec5511 | note | FREQUENCY: Check prior to placing material
a1b715b2-4fc6-507c-a1d0-2ee0c539a86e | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
1fe1b273-35f2-5268-ada9-a6e475a8f675 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
2b1426cd-bb08-512a-9c26-e343f03f403e | note | INSPECTION/TEST METHOD: Visual Inspection
5e2ae2df-f1b5-530a-a265-cf33791f1968 | note | RECORD OF CONFORMITY: This ITP signed off
fcc8e340-f707-5e38-b6db-e34ee69d91d2 | note | IP
ee531b7a-e732-5081-9b6f-f447ef88f35f | note | RESPONSIBILITY: Site Engineer
ddaf7450-8d31-5149-b388-6dfdd0ed0e64 | textbox | Date Completed:
8e3178be-cf82-4987-ba90-3ee8c3f889dc | checkpoint | 2.3 Lot Size
e894910c-9a9f-5d98-b7b4-d1a981fe062a | note | FREQUENCY: Check prior to placing material
db5b98a9-b2d7-505b-8cbd-c4e4016a1924 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
ffe7a86a-12cc-5805-a59e-afd7d75817d8 | note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
79649275-d52d-5ecc-96c6-4e4caf0051bd | note | INSPECTION/TEST METHOD: Site Inspection
0d18b93d-6aed-5051-a8af-64f1902839dc | note | RECORD OF CONFORMITY: Signed ITP
8f83b963-fbc2-5cf0-8c2b-5623cf4b237e | note | IP
09481d88-933d-551e-aa06-83cdc2e9d436 | note | RESPONSIBILITY: Site Engineer
55995cf9-41e9-54e1-af1c-bef3b5ab5135 | textbox | Date Completed:
e2df3335-4f3f-49c2-a496-daea2b04b523 | checkpoint | 2.4 Layer Thickness
3804cfa3-ed70-52f2-aaf5-91f4f0c59423 | note | FREQUENCY: Each Lot
94eb10bb-3bfe-5f6c-bcca-ffb2450b7633 | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
dc14884c-a4fc-55db-82cd-a9730b6fb20e | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
12c1cc1e-629b-5ce6-a897-d7b0b398e984 | note | INSPECTION/TEST METHOD: Site Inspection
75bda658-e39d-5724-8f69-29d4d5560cb5 | note | RECORD OF CONFORMITY: Signed ITP
89d51948-e60c-5137-a135-e65c1deaec28 | note | IP
fce54093-6b82-5919-a458-0cfdd8532bd7 | note | RESPONSIBILITY: Site Engineer
548c6f1c-03fe-564b-952c-bd63808875cb | textbox | Date Completed:
e52520b5-ccd7-472f-98cb-ac95780e2dc6 | checkpoint | 2.5 Proof Rolling
7e25bfbc-42e6-5b1b-8039-9e486a3c0951 | note | FREQUENCY: Proof Roll each layer
59e3d740-0d37-522a-acc9-dd201db44993 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
0601fbc6-ef5c-5483-9296-6a2b389eec5e | note | REFERENCE DOCUMENTS: 173.03
2bd5bc47-43e6-5806-8a98-d03a959210a9 | note | INSPECTION/TEST METHOD: Visual inspection
ad0bb068-4e72-5d43-af0e-84664d8068eb | note | RECORD OF CONFORMITY: This ITP signed off
e0679afc-5d3b-548c-96c0-b933af0f3d33 | note | HP/WP
84510636-a6e9-5e4a-87d2-5cd0d2b36b7f | note | RESPONSIBILITY: Site Engineer & Superintendent
8565f502-1337-53cb-81e1-3a7a630ce9ae | textbox | Date Completed:
59f65aab-f638-42ac-895e-f8d2538a9d9c | signoff | AUTHORITY HOLDPOINT
97f874c4-9309-4e44-b424-72916e3ec497 | section | Testing Requirements
254a00c0-6bd5-44e6-9d6f-d10865404d80 | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
d1fa6620-a846-5186-a9ce-740d4f3d6c29 | note | FREQUENCY: Prior to Testing
0e02d862-8024-5cc7-9766-0f59d178ed5d | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
3e260ad9-8f71-59ff-ac9c-d57fad138698 | note | ○ Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post- compaction testing will be required for that pavement course.
23e8722c-b529-52ac-b0be-a6e9d1b289cb | note | REFERENCE DOCUMENTS: Table 204.161 Cl.304.08 (a) Cl.304.11 (b) Cl.304.11 (c)(i) Table 304.111
3569ddaf-e1e5-5295-a6d0-3c7897031bbf | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
6409499d-2573-5541-91bb-7c86cb196ecd | note | RECORD OF CONFORMITY: Signed ITP
b4fac641-1396-5d8b-aaac-5af5a584dffa | note | AP
143116b0-4c07-56c8-9e12-d4c1a2fec3b1 | note | RESPONSIBILITY: Project Engineer
d16844ce-da5d-5429-ac87-f46e0bd17ad0 | textbox | Date Completed:
29414b65-d285-4b86-98f1-11266a9b8843 | checkpoint | 3.2 Compaction Testing
6ba52f22-6e53-5303-9d01-4e616acadd31 | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
0ab6ce4f-55c5-564e-b8dd-c6a6fcf2536f | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
8e4d3da2-2264-5177-aa32-950aec317aa4 | note | REFERENCE DOCUMENTS: Cl304.08 Table 3040.061 Cl 304.11 (b) Table 304.111
088ab25b-c794-5036-8916-705235d5faca | note | INSPECTION/TEST METHOD: Test point
c4f387ef-f536-5da0-926c-1283afb9bfb6 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
f3cd7007-f025-54e2-b73c-c051bbd3ef26 | note | TP
e693accf-6fe8-51f2-84f2-037e01bef561 | note | RESPONSIBILITY: Site Engineer
0984f30b-5daf-52c9-88d1-ab77c01fe79c | textbox | Date Completed:
bfff6a3b-f810-4442-94bb-c433f6cfcacb | checkpoint | 3.3 Compaction Testing (Small Lots)
f1845787-57d0-51c7-a579-c5e2b3fbcc0c | note | FREQUENCY: Each Lot
24a3bf87-de40-5f05-a2c8-f3eee53754b8 | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
af2a19b4-9949-53ae-9db7-4d7a4014d5bc | note | REFERENCE DOCUMENTS: 173.04 d
0d96a2ef-c10a-57e1-8813-d57902b260f9 | note | INSPECTION/TEST METHOD: Test Point
58118741-5247-5f47-8457-5e57853e0afd | note | RECORD OF CONFORMITY: Test Records Lot Register
4fa477bb-bbe8-5779-9e4f-b8dc5b4c3ddc | note | TP
6a4b601c-84ce-5654-ab7f-23c56bf6f8af | note | RESPONSIBILITY: Site Engineer
258686c4-b0eb-564e-a73c-cd3d50967ca0 | textbox | Date Completed:
19a1fb9c-e446-4161-9a08-66e22cc23723 | checkpoint | 3.4 Material Grading - Post Compaction (Class 2 & 3 Only)
831027aa-9d9a-5f13-bb94-f333d83089f7 | note | FREQUENCY: First Lot Only
f9b93532-fa82-5bcc-8c6f-020b7427a0ea | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
0e2ca58d-944e-5777-a248-db47da934dc4 | note | ○ Class 4 - N/A
bda32df4-4cbd-597d-8a7c-b10001539177 | note | ○ Class 3 - As per Table 304.101 - VR Spec. 304.10
44308044-09cd-57ee-9b85-cb74ff9502bc | note | ○ Class 2 - As per Table 304.101 - VR Spec. 304.10
6d65fcf1-e659-5330-9961-988042ef7a64 | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
7b3abbed-7672-5297-866d-65c84014a6e8 | note | INSPECTION/TEST METHOD: Test point
407c4e80-2450-585e-8f79-076cde1e07d6 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
d1aa979d-f555-5de8-af21-d488f617b133 | note | TP
de9f0390-88df-5ee6-abca-173ed1b4524d | note | RESPONSIBILITY: Site Engineer
79a50940-5d25-5171-8850-ad5dcb7dc3a8 | textbox | Date Completed:
49f9dfa6-0ee7-400f-9409-edf66a10a437 | checkpoint | 3.5 Plasticity Index - Post Compaction (Class 2 & 3 Only)
1daf242f-ea2e-5988-8b15-19298483207f | note | FREQUENCY: First Lot Only
35d3f4db-5a70-5ef3-86a8-7f378e9e03e8 | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
cad260b4-af14-5a78-8fcf-8895f1cccb08 | note | ○ Class 4 - N/A
9f4f5438-a59d-5d5e-b715-792742cba74b | note | ○ Class 3 - 0 to 10
cd662d1b-a35e-5778-b751-c50fd7b1aaea | note | ○ Class 2 - 0 to 6
420215df-197e-53a5-8abb-1213943cfd40 | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11 Table 304.103
5c028c3a-4525-582b-a9ac-b8871bd79fe3 | note | INSPECTION/TEST METHOD: Test point
60ac73d7-9955-51ff-8649-249b7e02c499 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
fc511829-8847-5a16-ad37-61b0d3db1052 | note | TP
b08dcb52-415e-5d31-a805-51959998ce5a | note | RESPONSIBILITY: Site Engineer
720198cd-563f-5b10-ad72-72e2dbd310d0 | textbox | Date Completed:
d0da5b64-64d5-40a3-87f4-78d453eb14aa | checkpoint | 3.6 Survey Conformance
60855a5f-f64c-5854-9ac4-8871e871ac0d | note | FREQUENCY: Each lot
5a48ad5f-77f2-5db6-a227-4b79111080be | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
c8f37248-1955-52b9-9009-1b2b9042ee00 | note | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction Surface level tolerances:
6728404a-ab15-52e3-aac2-6f90c1b286ac | note | ○ Range x = +6, -16mm Max S = 15 mm
5df1a0f9-1eaf-57d4-82b7-93c9579ac8c8 | note | ○ 40 measurements per lot (Minimum)
d21579be-8541-555f-98fb-3bfe4f04e213 | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings Table 304.062
226a9428-154c-554a-987a-8c2064b3c4b4 | note | INSPECTION/TEST METHOD: Survey
8fd1fa1e-6624-5508-99e7-73d9b135d7ed | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
b70d2b30-840b-5260-a02e-25518f17de39 | note | SCP
8909edd2-989a-55f9-b5d8-004b9b31bb30 | note | RESPONSIBILITY: Site Engineer/ Surveyor
99dc9268-5468-5422-9e38-ac85491d0fde | textbox | Date Completed:
7852dcf3-64a5-44fd-b352-947c5023fddc | checkpoint | Final Inspection
59590e46-ec34-5856-a480-bee31566c56b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
59fde864-de3d-5e71-a049-0b7ca89f58aa | textbox | Print Name:
8ef92668-dfd2-56c1-bf05-f4dd1dcc9ac8 | textbox | Position:
c836f9ee-d92e-5a92-aee9-aa9bbb615a37 | textbox | Date:
07a6e8ec-9324-47ef-ae52-1f395a7507c3 | checklist | ITP-006 - Sub-Base Construction Class 3 | itp | ITP-006 - Sub-Base Construction Class 3
20904419-55ed-4f83-89bd-8fcddfabfce5 | section | Preliminary Works
7827371d-45b9-4e2d-a826-9d16f0a84c6d | checkpoint | 1.1 Check for correct documentation
5c9e8833-e351-599d-b0b1-2f5caba916c9 | note | FREQUENCY: Prior to commencing any activity
38b2d12b-0f52-5691-ac23-404b250b2068 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
513dff67-7095-5ebf-8a52-5c656b63b077 | note | – Using the correct and complete set of drawings
ceae1910-f3d7-5a97-843b-ace85856fcce | note | – All drawings are the latest revision
1fbe6a26-2b47-5560-8918-2ccb162b68fc | note | REFERENCE DOCUMENTS: Drawings and drawing registers
0f88657b-1da0-5b2d-a9fa-09f314f1ba35 | note | INSPECTION/TEST METHOD: Visual inspection
5eea8e80-367e-5a50-814b-7300f8747505 | note | RECORD OF CONFORMITY: This ITP signed
03c83c40-224e-5068-935d-3470bedbdd6f | note | HP*
490c577a-e70b-56d0-a42f-0fcce20cb632 | note | RESPONSIBILITY: Site Engineer / Site Foreman
daf06c97-3596-5005-85d5-a03f0e7f3f9d | textbox | Date Completed:
e383d060-3cb7-492a-97a4-f76989ec639c | checkpoint | 1.2 Material Mix Design
04817e06-194d-56c0-91ce-69ac68c33266 | note | FREQUENCY: Prior to commencing any activity
2b7e3bed-8703-5589-99d3-3bf865c2369e | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
daf0d1ee-635c-5549-bd25-4c5e00e3aabe | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
d788e42c-5a40-51a0-86b9-387cfe01a426 | note | INSPECTION/TEST METHOD: Document Review
612d5988-ed9c-537b-ad31-06aaadf8d1b1 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
6742eb99-679e-5191-80ad-5a7e1bf8a44d | note | HP*
4eba4dc0-8976-5a3d-adf9-3a570bc44f5e | note | RESPONSIBILITY: Site Engineer
577de924-bca7-566d-9bd2-8993b12b6ebd | textbox | Date Completed:
15b4bcf3-da24-493c-b80c-c5d31dc21420 | checkpoint | 1.3 Implementation of all measures and controls
3c2e687f-c826-5035-8c46-5c93d57e6bcb | note | FREQUENCY: Prior to commencing any activity
7875e870-62bf-5752-bef5-04ca4991402b | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
df37db33-725f-5947-8a47-83e5a0152b10 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
6098fe1c-02b7-5914-83cb-c45ed96b9a23 | note | INSPECTION/TEST METHOD: Visual Inspection
0dbb0664-9b50-54e1-8b15-169e1793d44f | note | RECORD OF CONFORMITY: This ITP signed
72e5694f-17d5-564a-83f2-02eacafdea2e | note | HP*
8bdee64e-4a97-5588-b96e-bcfae58ce8bd | note | RESPONSIBILITY: Site Engineer / Site Foreman
58af2790-d8e3-5114-b6d4-cb1818792f68 | textbox | Date Completed:
778863aa-935e-4afb-84e1-ee41233c9df7 | section | Construction Works
20380d12-45d6-4a42-8076-4296c3e28047 | checkpoint | 2.1 Transverse Joints
debc4f4a-d450-5511-a53a-c18ce1417bcd | note | FREQUENCY: Check prior to placing material
1f1dd7bd-f268-5a4f-8902-e06294f81241 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
859fb748-d437-5725-8df8-143f0c1dbb01 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
c340e364-50da-5c2d-b0d1-d1a781f3d8a4 | note | INSPECTION/TEST METHOD: Visual Inspection
7df5ac02-c749-50f8-9005-bbae561d3aeb | note | RECORD OF CONFORMITY: This ITP signed off
ea6646c0-e9b5-5419-8bc4-857cff269d47 | note | IP
a30dd1c1-b69c-547f-b8a3-5dfe33fbc209 | note | RESPONSIBILITY: Site Engineer
ba1c4584-bc3d-5f7d-b5bb-b6bc323b07fb | textbox | Date Completed:
9e287db7-0255-4279-b064-20a1e5b3eb70 | checkpoint | 2.2 Longitudinal Joints
70373f40-4c3d-5aac-8484-8781dc50002f | note | FREQUENCY: Check prior to placing material
6416be97-b88a-54b9-a67e-326ee4f9ce65 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
9c8553a2-71f8-52ba-b52e-7920566c1338 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
532a000d-4f1e-5e26-8918-cfb483dd4318 | note | INSPECTION/TEST METHOD: Visual Inspection
ae3fbac4-13b0-52f7-93af-e0c8ec5d9d7a | note | RECORD OF CONFORMITY: This ITP signed off
baf43a4c-7afe-5cd3-8a3a-e049fba9502c | note | IP
ef9a9514-f84d-54d7-825a-c3833931aa88 | note | RESPONSIBILITY: Site Engineer
83fea349-e377-5572-a7fe-f33a113265a6 | textbox | Date Completed:
688398d2-7ca9-4b79-bae4-28dd1aff7511 | checkpoint | 2.3 Lot Size
6e7e52b7-ecef-5403-819e-1eeac05d2bc4 | note | FREQUENCY: Check prior to placing material
93372d3c-e153-5289-a001-d6bb1ea00241 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
86634db9-f855-5bc7-b00d-39b6f5d9d9fe | note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
0aa5cfc0-d469-5430-8696-fa0be9bdc697 | note | INSPECTION/TEST METHOD: Site Inspection
fabf0cd9-df41-5667-afe8-151853dd478b | note | RECORD OF CONFORMITY: Signed ITP
990978a8-92b3-56e3-a2d7-7a8ab351d564 | note | IP
16d891e1-145a-503b-8bb0-5474ab9a9955 | note | RESPONSIBILITY: Site Engineer
b863f2b6-f536-5755-827d-3868ffd3f9c4 | textbox | Date Completed:
78476636-cb46-4f95-88fd-f57762234796 | checkpoint | 2.4 Layer Thickness
0d99afa4-f627-5b83-8b97-ffac28980ba4 | note | FREQUENCY: Each Lot
53c771e8-5949-5efd-8cf2-f7286ee7bdea | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
0ac3ee50-8b60-51c1-b00c-65ddfc61e2ba | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
8e3e8a2a-2a9a-5b2e-bfbd-8fc6bf915a41 | note | INSPECTION/TEST METHOD: Site Inspection
e5ac77e8-bfed-56da-911c-f53f27ddc420 | note | RECORD OF CONFORMITY: Signed ITP
767bb588-dfcf-50db-b38d-f8df6281472a | note | IP
de936d1e-5113-5285-b13d-7304d3e8cc1e | note | RESPONSIBILITY: Site Engineer
7638185c-f0ea-5bf3-875f-7a9a15746eb5 | textbox | Date Completed:
e0d700a2-241b-4df2-afcd-3ed4d5283c3b | checkpoint | 2.5 Proof Rolling
7a88a4d8-911e-52bb-9745-e3bf00b01e67 | note | FREQUENCY: Proof Roll each layer
73c0361c-a158-55a5-890b-7e849939b6de | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
ab36732b-8499-5376-a64f-64857841b5db | note | REFERENCE DOCUMENTS: 173.03
5ea350b0-c518-5050-ac97-b747131d69af | note | INSPECTION/TEST METHOD: Visual inspection
a4c46e97-f4f9-5d9b-823a-bc702d4435c6 | note | RECORD OF CONFORMITY: This ITP signed off
5d74be0e-0fae-55b1-84c4-b898170d7b2d | note | HP/WP
959843da-80ba-591d-8645-9363b79471ba | note | RESPONSIBILITY: Site Engineer & Superintendent
9b4cabc4-7fc2-527d-82d6-087c6d6da789 | textbox | Date Completed:
b1b01d18-39b9-45e0-99d2-2601df7a6816 | signoff | AUTHORITY HOLDPOINT
e70b7cb1-9514-4d42-bda0-822f6a998f5f | section | Testing Requirements
5fedd009-8ca0-4002-ad5d-16ab7c57a848 | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
0c6afecd-0f06-51dc-a1eb-c30761235aef | note | FREQUENCY: Prior to Testing
fa19bd9e-2ac0-56f9-8547-94e72f6698ca | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
e271ca84-5ea1-51fc-bb2b-f041092b0594 | note | ○ Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post- compaction testing will be required for that pavement course.
067e5342-f115-5bd0-83bb-294bec9da928 | note | REFERENCE DOCUMENTS: Table 204.161 Cl.304.08 (a) Cl.304.11 (b) Cl.304.11 (c)(i) Table 304.111
d467770a-018e-5f33-84fc-7f63031903cc | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
9a33b4ad-6f5a-5420-8c09-2d0c045e3cfc | note | RECORD OF CONFORMITY: Signed ITP
c3aa9c6d-c750-50ef-abdc-b75ff56233a0 | note | AP
d4aa5244-65f2-5c96-a5dd-ed0fe8ddd753 | note | RESPONSIBILITY: Project Engineer
ef046787-023f-566e-98c5-a566c8323248 | textbox | Date Completed:
394c9dd8-2817-4fcb-8c8a-24d1be1ad48b | checkpoint | 3.2 Compaction Testing
654a95ac-d819-587c-8cee-1d9413a450cc | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
4aac9da1-e733-5df3-989e-19e25c81955b | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
d2444a02-0a8e-51bd-8534-39893e288b5c | note | REFERENCE DOCUMENTS: Cl304.08 Table 3040.061 Cl 304.11 (b) Table 304.111
43c230b9-6c71-5959-bf01-65b2ad53fc18 | note | INSPECTION/TEST METHOD: Test point
9e78d980-3125-5417-92fc-ca88abfebbc4 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
25dbd529-9113-5a9d-8163-c057f7060eac | note | TP
0d70b2b3-068a-5c97-bd78-2422d8a1a630 | note | RESPONSIBILITY: Site Engineer
50753747-c041-57e3-aae7-c15987671bc4 | textbox | Date Completed:
362ce2f8-fdd5-40ab-8abd-692209855d89 | checkpoint | 3.3 Compaction Testing (Small Lots)
f5e1dc94-7867-5a1c-82ea-986f1097c664 | note | FREQUENCY: Each Lot
a504a9a7-7325-5955-9770-8ff9b620272e | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
445479fc-7ad3-5958-9639-3118827b81a1 | note | REFERENCE DOCUMENTS: 173.04 d
41e9f930-3644-595c-9f52-f9be8b72c106 | note | INSPECTION/TEST METHOD: Test Point
b31177a6-c305-553f-a195-cf625acfdaaf | note | RECORD OF CONFORMITY: Test Records Lot Register
f436bf6e-5167-55da-9bd0-7266ee4335a1 | note | TP
88b856e7-5d63-5df4-b156-afb031770a13 | note | RESPONSIBILITY: Site Engineer
a5f40680-cf34-56be-8f4d-8b761cee0545 | textbox | Date Completed:
f49b96f4-ed4b-4f55-aa31-9a71c3a2fb5b | checkpoint | 3.4 Material Grading - Post Compaction
3b9ab381-c686-5aeb-b05f-8e5844f795d8 | note | FREQUENCY: First Lot Only
c0574f2b-4fad-50cc-b1c9-5b34f99c7605 | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
114ec23a-1c2c-553d-8497-278bfc25d62e | note | ○ Class 4 - As per Table 304.101 - VR Spec. 304.10
cac0f09c-850e-5f21-9a6a-3c0aecc9431a | note | ○ Class 3 - As per Table 304.101 - VR Spec. 304.10
891a2ce4-38f8-540b-97e1-43d4c1b25e8d | note | ○ Class 2 - As per Table 304.101 - VR Spec. 304.10
30a19964-9ac6-52e7-9ea3-6d82dcb8c145 | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
bd641320-1b7d-5726-ad53-283a162938d3 | note | INSPECTION/TEST METHOD: Test point
016e57f5-a92c-5e9b-825a-5582a1dca134 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
a4fb7bd3-725d-5f5e-9db5-550f0c1efa90 | note | TP
cc079126-706b-5fd4-b9df-c091e6492687 | note | RESPONSIBILITY: Site Engineer
0cb98c94-5672-5cd9-a35f-b5b3689f9d5f | textbox | Date Completed:
e51a704c-364f-4c9b-baec-3cdf5a356a84 | checkpoint | 3.5 Plasticity Index - Post Compaction
49c51031-9143-5c10-981d-142f180907b6 | note | FREQUENCY: First Lot Only
dc1b9c6c-e2cb-529d-bfd8-6aac737bc2e2 | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
d6d67f66-b933-57bd-9fbe-584480f87135 | note | ○ Class 4 - 0 to 10
9af3616b-1756-576b-b611-ed38a8a765a4 | note | ○ Class 3 - 0 to 10
5386480a-2cf6-5c89-a3e5-38f443a90c68 | note | ○ Class 2 - 0 to 6
7270df2e-4fe3-54ca-aad1-515b54c90f2c | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11 Table 304.103
8fddebb7-5cfd-5ec3-9584-a5265702c8f6 | note | INSPECTION/TEST METHOD: Test point
b1b7f922-32c1-5607-87e4-0d2e727cf1ef | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
f2af5a7b-61e7-580c-9161-a7585e9a86f0 | note | TP
2d7e4bc0-b253-5bf9-bb90-2e7fc8ff2c6b | note | RESPONSIBILITY: Site Engineer
f223f268-f778-5e69-b0ac-fcfd05ff2fe1 | textbox | Date Completed:
ddfdb41a-0469-47dd-8a43-2329e272955e | checkpoint | 3.6 Survey Conformance
5f2b1569-85dd-57af-829a-c1ddcbeb1512 | note | FREQUENCY: Each lot
e306b685-5738-51b1-9cd9-9ffefb9c633c | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
ad1083e5-68bd-50ab-849b-ca7e1fecafaa | note | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction Surface level tolerances:
6faed0e7-25dd-5100-a479-b3ba456f889a | note | ○ Range x = +6, -16mm Max S = 15 mm
969e969c-c5fb-54db-9223-21582da1f585 | note | ○ 40 measurements per lot (Minimum)
f7ac1bac-0f30-5b3b-b9be-5ab17fa54d3b | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings Table 304.062
15ed01e6-09eb-5293-a7ed-512ebab97fae | note | INSPECTION/TEST METHOD: Survey
135d7c41-f099-5999-b8c2-b4377ab448af | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
10768d87-3b0f-5f79-9375-a7de3afdcb53 | note | SCP
f053256c-883f-5522-9064-86313b8cfd66 | note | RESPONSIBILITY: Site Engineer/ Surveyor
104fc0da-7811-5e3e-a9bc-4a6e933b561a | textbox | Date Completed:
9dd0bc73-68cb-47b1-8a79-8054ddc6e1bc | checkpoint | Final Inspection
359dc339-f62f-5069-9e37-9b9b2dd04771 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c5df1ba4-831f-5cc2-b0de-e7e8529c4d7e | textbox | Print Name:
1924ed31-520d-54be-8ff9-4dca356b6290 | textbox | Position:
d668ea33-1278-5bed-adbd-5cfae2cecaf9 | textbox | Date:
eb6a5331-a913-4f57-b3fe-4a5c60b2d53f | checklist | ITP-008 - Stormwater Drainage | itp | ITP-008 - Stormwater Drainage
2bc93d22-c7a0-4971-b343-8ef9610bc24d | section | Preliminary Works
3f355746-6c43-4eef-b7c7-8e2db64c121a | checkpoint | 1.1 Check for correct documentation
a85839e3-806b-580f-ab52-f8f810f59409 | note | FREQUENCY: Prior to commencing any activity
fd481ec6-9d70-5b72-9b40-6eae80769caf | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
47a8ae66-b6bf-5505-baa1-6d83bd855160 | note | – using the correct and complete set of drawings
7789192d-ae84-5e57-ab8d-d8e6df39de59 | note | – all drawings are the latest revision
da7a4899-271b-574b-9791-3756d864ea89 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
48cbbecf-afc1-53c5-b5bf-f6bb78510356 | note | INSPECTION/TEST METHOD: Visual inspection
f0af67a2-bd17-54fa-bb5d-40155ecfea45 | note | RECORD OF CONFORMITY: This ITP signed off
b346bc7c-3558-5d4d-a44c-c65a4ed861a6 | note | HP*
c1e9434f-bdb8-5103-a68a-d1c923cc20ee | note | RESPONSIBILITY: Site Engineer / Site Foreman
2750ffcf-432b-576c-b19c-27190ba55644 | textbox | Date Completed:
ebbf6c1a-7327-484c-8901-89a6d9d9cf19 | checkpoint | 1.2 Implementation of all measures and controls
7dd6a457-f270-5ffa-9d66-a43df27f1b6b | note | FREQUENCY: Prior to commencing any activity
82b2ea90-fbae-56ce-8a1b-17af7661269d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
da3346af-b0aa-58fb-9cd2-bfec549682a0 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
1ff96de7-28ca-5b3c-834e-639dfcbcb3ba | note | INSPECTION/TEST METHOD: Visual Inspection
1da85082-57fa-572b-bd1a-0ee2c839da4c | note | RECORD OF CONFORMITY: This ITP signed off
48eb09f9-136c-51b9-8ceb-c396848be6de | note | HP*
07c12b6b-3c22-5582-9ef7-2a34cd9215c1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
881df267-dc86-517f-a07c-0050c676d50b | textbox | Date Completed:
7ec5b081-61df-407d-86ab-f40525fcd404 | checkpoint | 1.3 Precast Concrete Pipes acceptance
bce6156d-cf07-5173-bd8e-b7ad4b59f3fa | note | FREQUENCY: Each Delivery
8cf56d5a-9c6c-5116-9096-5a952944eeab | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
8ca4c189-5cd6-55ec-89b3-9fe50c7c8ae1 | note | REFERENCE DOCUMENTS: Cl. 701.05e
2f801760-7657-50f3-8da7-c6444a6b2337 | note | INSPECTION/TEST METHOD: Visual Inspection
6fff502d-dd85-573c-8197-f29e5f22e2c8 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
b3f90477-1ce6-5158-8b7c-6b106c6f1046 | note | IP
0cd17653-dfe6-5e86-b31c-d1db40592e46 | note | RESPONSIBILITY: Site Engineer
5b0dcd53-4b07-5c29-a3dc-fc2eb25b3832 | textbox | Date Completed:
6c9be291-d9c9-4421-b3a9-c683a5b4582f | checkpoint | 1.4 Precast Drainage Pit Compliance
3c6a96d2-cda8-5944-b408-95c2f085bc54 | note | FREQUENCY: Prior to Commencing
26577bf6-cfd5-5a0b-bfd8-a1057dc42d8c | note | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
58eed90e-fa35-51d4-b021-5103ee850372 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.610 Cl. 705.04 AS5100
6db8c061-b624-546c-8324-a788a53786ac | note | INSPECTION/TEST METHOD: Document Review
57791fad-2861-53c6-8f4a-ae49e53cda0c | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
d9951aca-32cc-55d4-b255-add6a1b4bede | note | IP
6d70497c-bcf0-5728-99db-10b9b91bf3f6 | note | RESPONSIBILITY: Site Engineer
b0bf2c4d-f50f-509a-b070-f8d142db3bf9 | textbox | Date Completed:
3c7d2d57-5426-4f88-b476-f6d124f600b8 | checkpoint | 1.5 Bedding material classification
b3b31734-fb12-5d42-a2db-b36b3c0357b9 | note | FREQUENCY: Prior to start
73663cb3-c82f-5539-ad1b-97f4623b92bf | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
d539108d-bc43-5cdf-95cd-224ef5eab468 | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
19fca0bf-030d-549b-8850-5e697c104a18 | note | INSPECTION/TEST METHOD: Verify
4ab5b870-f385-5e1f-87e6-92d22a8d02ab | note | RECORD OF CONFORMITY: Test Reports from supplier
02bd763c-71d2-5701-9fe0-b364bf59a1d8 | note | TP
2ecf28b4-b532-5929-a1e2-88f2878a01e0 | note | RESPONSIBILITY: Site Engineer
a91743e8-4f0e-5aa7-a7d6-07a0628f43ce | textbox | Date Completed:
e4208166-657b-4046-a2ba-cc9fcffe47d0 | checkpoint | 1.7 Backfill material Classification
b541cdc3-7a09-5917-81f3-80687db4685d | note | FREQUENCY: Prior to start
05559a67-1779-58e0-abe0-f7f97fdaa7e1 | note | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
db894743-89a0-5101-a4c0-14bcfdd4f23b | note | REFERENCE DOCUMENTS: 701.09(d), 701.091
42da1491-b213-5fba-97df-6150dbdd51c7 | note | INSPECTION/TEST METHOD: Verify
17d89bd3-07de-57a4-bc46-234f6a4a2acc | note | RECORD OF CONFORMITY: Test Reports from supplier
57e2dc96-a10e-5088-a3d0-b0eeaa0ae4e2 | note | TP
eb20d667-b543-5bb4-864f-6f91d37b3c38 | note | RESPONSIBILITY: Site Engineer
e91fbe3d-9c2a-5aff-af26-b780d1ca1c4b | textbox | Date Completed:
42ebd61a-b1c0-42d8-af68-4adc4d87d452 | checkpoint | 1.8 Mortar material classification
8ada7f46-58d7-500c-aa70-1626702adb9d | note | FREQUENCY: Prior to start
e1309e71-b713-5432-9787-1333cdc0e441 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
0dc78e5e-9e4a-5c8c-9009-d44b9047b9db | note | REFERENCE DOCUMENTS: 610.33
f29566b7-6868-5037-8c19-2bfe02f615c0 | note | INSPECTION/TEST METHOD: Verify
73348d86-c7bd-5d03-8dc7-226787aa3df4 | note | RECORD OF CONFORMITY: Test Reports from supplier
4df94e70-81e9-559a-bb52-536dc20236a1 | note | TP
c951dca8-b377-5fe1-aa79-e007b5a8b059 | note | RESPONSIBILITY: Site Engineer
a821399d-2b80-594f-9d9a-5cba8a33d99c | textbox | Date Completed:
794f24c5-ebbc-4d98-a229-c3c133eab142 | section | Construction Works
4660ce69-07c3-42b0-8724-3ae3669253e6 | checkpoint | 2.1 Excavation Permit
1374abae-6bb2-5591-af8e-c219a4c40e7b | note | FREQUENCY: Each lot
2e1ff66c-0313-5935-a8f2-267a6fb4d16b | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation.
4ef9bd8b-728f-58f6-85c2-064703475fab | note | REFERENCE DOCUMENTS: Excavation permit
b9c30171-4da2-5b5e-927f-9d879ce5e51f | note | INSPECTION/TEST METHOD: Verify
94d466ae-d9d5-50bc-8d25-8c24c66a8c7e | note | RECORD OF CONFORMITY: ITP Signed
073d77d7-d820-5aed-9e77-22a7ccb5c9eb | note | HP*
91ba7b56-b2b1-52c5-a2c3-e07b9fb1fe2a | note | RESPONSIBILITY: Site Engineer
5e2ed6bf-a3e4-5615-bd89-c802f0da55fc | textbox | Date Completed:
2ea6d87d-d74b-414d-bc36-120222250488 | checkpoint | 2.2 Set out drainage
b2fdb8dd-fbb0-5799-9ee1-f2a77dec2743 | note | FREQUENCY: Prior to backfilling
eed79bd5-dd4f-5d43-87ee-4e5c34c2ff21 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
cfdb1ca5-e682-5f2e-a219-8904d70f4895 | note | REFERENCE DOCUMENTS: Drawings 701.10
a774040d-052c-57b0-ac64-f7212a4b6c49 | note | INSPECTION/TEST METHOD: Visual Inspection
843a08df-8eb9-5f08-b835-4bbe8956bf77 | note | RECORD OF CONFORMITY: ITP Signed
17743f44-3406-5cf7-ba8a-09b25967bb94 | note | HP
f19de469-7552-515d-b1b4-9c2935e9836e | note | RESPONSIBILITY: Site Engineer/ Superintendent
125bd657-61cf-52d9-9169-d919f0f65788 | textbox | Date Completed:
c3ce15fb-cfb5-4338-9b49-cdc8f6d59b21 | signoff | AUTHORITY HOLDPOINT
c634a3fc-5b93-4f4d-9792-5d11f0a85d7b | checkpoint | 2.3 Excavation (pipes)
c3dfb7f0-917e-5ef9-b839-365219a717ec | note | FREQUENCY: Each Trench
524b2970-37bc-5c0f-935b-d4d187a5de89 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
04e2bac3-da43-5209-9858-8da4da6e28f5 | note | – Depth of trench:
a72e88f3-50bb-54dd-9b0a-3835409e41eb | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
5651eb46-3d87-5286-9edc-6459e56728df | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
1676bda7-03d6-5761-926d-a1fb1180fe6d | note | REFERENCE DOCUMENTS: 701.151, 701.15
169fa3fe-aa4d-588f-a83c-d1b76e2abe36 | note | INSPECTION/TEST METHOD: Visual Inspection
267a60ca-21aa-51fe-9e4b-bb4437027f79 | note | RECORD OF CONFORMITY: ITP Signed
8e5e3185-42a8-59e8-a0b5-25dd0c13d482 | note | IP
784c8143-aa1d-582a-bc1f-8623188f9e27 | note | RESPONSIBILITY: Site Foreman
c2403b46-c26b-5a13-96ba-62f89f029b4d | textbox | Date Completed:
05d24209-7425-4596-8870-eb38031a5350 | checkpoint | 2.4 Excavation (pits)
a4120773-dde2-54dd-ae80-4688e3cb7df2 | note | FREQUENCY: Each Pit
59b66034-15a2-555f-ba9c-9c555e73382b | note | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
6416d8a6-de00-56ed-9bc1-aedb8773a2e6 | note | REFERENCE DOCUMENTS: 705.05b
99d588ad-7ceb-57b1-a9af-30e4c9c7ec68 | note | INSPECTION/TEST METHOD: Visual Inspection
ec2fa0df-ec9b-5690-b5f8-5ab058e54154 | note | RECORD OF CONFORMITY: ITP Signed
e71633db-0ef2-5aa9-a91d-58bbabdbacdd | note | IP
8e09f8a4-dab7-55e0-8f80-81075f42a6d8 | note | RESPONSIBILITY: Site Foreman
0eede8a8-f384-5d7d-a22a-d834cfb71dc2 | textbox | Date Completed:
9ca75774-7da6-4265-aac6-4132dd723c35 | checkpoint | 2.5 Compact base of trench
6783b844-4538-5603-87a4-034b913c42a5 | note | FREQUENCY: Each Trench
2809aec3-74c3-5ba1-b387-e6aa0298fa13 | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
b8ace326-c07f-5d03-976c-4c39058773c2 | note | REFERENCE DOCUMENTS: 701.15
7075480b-af10-5391-ab39-2d28c4a6df6f | note | INSPECTION/TEST METHOD: Visual Inspection
07cc469b-7465-5e94-a19b-f98b09236d47 | note | RECORD OF CONFORMITY: ITP Signed
cdd1eaec-6a05-5ea1-945f-7fb85f1d15c8 | note | IP
7a753f3d-2c2b-51b3-9964-0488515183a3 | note | RESPONSIBILITY: Site Engineer
20116440-fadd-54fc-a91f-141559cb9883 | textbox | Date Completed:
2659b0c1-6974-4f5c-b295-56d9c443abc6 | checkpoint | 2.6 Place bedding material & compact
770f9395-8907-5812-8039-570e3cd30af6 | note | FREQUENCY: Each Trench
3f037007-7ef3-51dc-a0e8-72ea206c9d8a | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
fb4f9553-6834-5d7b-aa58-ac172fefad39 | note | REFERENCE DOCUMENTS: 701.20, 701.20a
c35b900a-cad0-52c4-b567-56c9b20327b8 | note | INSPECTION/TEST METHOD: Visual Inspection
a1d9a436-21d5-52e6-8aaa-39bc401a4acf | note | RECORD OF CONFORMITY: ITP Signed
d91e2831-3fa8-520d-94a9-e40b8cc7d80f | note | IP
3733603b-2916-58c9-a9c8-dd9e9b99e59c | note | RESPONSIBILITY: Site Engineer
1d4d2f31-1f59-5668-8868-42fb1602decb | textbox | Date Completed:
f627bf6d-77f7-4676-b53e-2926f7d67fc6 | checkpoint | 2.7 Place pipes & precast pits
acaf26e5-5fba-57b8-95ca-690aaeb98e23 | note | FREQUENCY: Each Line/Pit
9bc4f741-1d23-54c4-be74-e59c3ccfadc8 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
1561f2a7-e301-51cd-835b-792106016c75 | note | REFERENCE DOCUMENTS: Drawings
1610bf37-9425-54d9-8034-7e41423fd299 | note | INSPECTION/TEST METHOD: Visual Inspection
f7166c76-ebc9-559e-a1a2-a73f2e14bb11 | note | RECORD OF CONFORMITY: ITP Signed
f902bacb-ef5b-5d20-b188-6fcb35d8dbf7 | note | IP
a474033d-83b8-5c7c-a9ce-f9f568f86f5b | note | RESPONSIBILITY: Site Engineer / Site Foreman
355728af-ae3b-5358-b5be-a802c09aa242 | textbox | Date Completed:
ed98f9e0-197c-42a5-bea4-8232576c440e | checkpoint | 2.8 Jointing pipe sections
4bf686a7-50c9-5383-b29c-d2a1fb35ca90 | note | FREQUENCY: Each Line
d72194e4-c6c3-56da-8eac-cfdac255e893 | note | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
47e31ee3-335b-5001-8f83-cd4e169b1de3 | note | REFERENCE DOCUMENTS: 701.18
9cc9c2ca-149f-565d-ab0d-d6c94dfe43cc | note | INSPECTION/TEST METHOD: Visual Inspection
f8780d87-104c-5fb0-9021-8ec63b23c18d | note | RECORD OF CONFORMITY: ITP Signed
60a1403d-38dc-5658-a7cc-c7ec802001d3 | note | IP
9ff057ea-d5be-5d5e-8b45-a179c75dd0cc | note | RESPONSIBILITY: Site Engineer / Site Foreman
192aec45-7fb7-5681-ab28-0903dd42587c | textbox | Date Completed:
b1dd915c-05d5-4a55-b0da-b9e622cfa55f | checkpoint | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
4f5c83d7-41ce-58d3-9562-b627f80bd563 | note | FREQUENCY: Each Pit
bb200dd9-744f-5dc1-9bd3-358ec185990a | note | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared. The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
cb0ea08b-1243-5ef0-afda-c656911cb3d4 | note | REFERENCE DOCUMENTS: 610.32, 701.17c
0c6cbe72-ed62-571c-a063-9d0bf795a32f | note | INSPECTION/TEST METHOD: Visual Inspection
61b0598d-93de-5e66-a84b-960279640472 | note | RECORD OF CONFORMITY: ITP Signed
62220c0b-fd75-556f-94e7-60d3fd1ef51c | note | WP
f8afd591-833f-5469-9ef9-322a1295ef0d | note | RESPONSIBILITY: Site Engineer / Site Foreman
8ef92fe7-d8e1-5eaa-b5e3-54bd24ae0345 | textbox | Date Completed:
548f48f3-92ab-4292-9e2f-9eba1deb0378 | checkpoint | 2.10 Survey of laid pipe or pit
5702e628-b8be-55c2-8da1-bd006548266e | note | FREQUENCY: Prior to backfilling
de71711b-ed20-5cc8-b40e-89af781ad3ca | note | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances:
6933017f-eb0b-55cf-ae47-cfdc1e347c98 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
fa45ee10-a947-51e3-abeb-b1fc63f2a214 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
3513b7f7-dcf1-54bc-843c-dcc555cb88cc | note | (c) invert level of pipes at pits ±50 mm
96649880-bcf8-5697-8d32-fe903e5fb72d | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
402f6b52-56cf-5cd1-b15f-a8836d54510d | note | REFERENCE DOCUMENTS: 701.10
4150e260-6584-548a-ab33-ffaccc0496c9 | note | INSPECTION/TEST METHOD: Survey Conformance Point
350ddd43-977b-589d-9c91-cf8e3d61a68a | note | RECORD OF CONFORMITY: ITP Signed
8e2df265-918d-593b-9a78-307bb150117e | note | SCP
4d2c711c-f18e-5816-aac2-5ded3299adbb | note | RESPONSIBILITY: Site Engineer/ Surveyor
d3943ead-6462-56a3-a11f-fb6798c3e82f | textbox | Date Completed:
baf1a1cd-1571-45af-9cf1-45b5d68440c0 | checkpoint | 2.11 Haunching & compaction of bedding material
e77e8f1d-d8a2-560d-817b-a9a0118ec2d0 | note | FREQUENCY: each lot
b3303c53-38e4-57e2-9a97-0f521846d542 | note | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
dedfb0af-1497-5cbe-8799-5a11f50acdd5 | note | ○ Loose layer thickness <=150mm
38474ba6-4236-5153-8ee0-7b910f4a9e4a | note | ○ Compacted to refusal using hand held mechanical equipment. 1 lot = 150mm layer
466ee2c9-06e1-506d-ba00-dbeb229eb0fe | note | REFERENCE DOCUMENTS: 701.16, 701.20
a436d347-d1f5-561c-a578-632d44489bb3 | note | INSPECTION/TEST METHOD: Visual Inspection
d250e7e6-8bc6-535b-b40e-1f4be4532c39 | note | RECORD OF CONFORMITY: ITP Signed
306968f1-fc27-5ffd-aa26-8d4a063daeeb | note | WP
31f4ed7e-bc8e-5945-be0b-3f7c28e3ccd1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
2403390c-ab4b-54cc-b2a2-5043c9063e5b | textbox | Date Completed:
f4cec4c3-d1cf-47af-93de-5bb400c8e574 | checkpoint | 2.12 Place & compact backfill material over pipes
f20b19be-ff4f-5ad2-86a0-94e0883511b9 | note | FREQUENCY: each lot
3004be90-14db-53a4-8fa4-628e21edb368 | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill
ee793184-bdca-5c3a-9a09-5d908dc33e16 | note | ○ trench with selected back fill material to subgrade level
1f3ee5da-e90c-5db6-9e52-93736818583b | note | Backfill under area not paved: Back
8389a4ba-d288-5231-893c-27d657b7a248 | note | ○ fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
baf48f4b-5631-5a88-8bdd-087ed717b24f | note | REFERENCE DOCUMENTS: 701.19, 701.20
188ada25-d8b4-5132-a719-d3dc845a4606 | note | INSPECTION/TEST METHOD: Visual Inspection
0195e7d4-1921-5afb-b1dd-9c85c6bbf1ba | note | RECORD OF CONFORMITY: ITP Signed
4ba899d5-a9ef-57d3-8bb4-663ad082eeb7 | note | IP
f2892bf6-a7e1-5c8c-a1c3-9c7e370f2a6f | note | RESPONSIBILITY: Site Engineer / Site Foreman
bd90dae2-5bae-5766-bbb2-3b437dbcc97a | textbox | Date Completed:
d8ff1f83-a3f7-428c-a913-c1dc5be9b9cd | checkpoint | 2.13 Place & compact backfill material around pits
2f265737-7485-521f-889c-a126a84ea589 | note | FREQUENCY: Each Pit
c049a679-c2ea-5b36-96b6-aa8e94f0487d | note | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm. Compacted to refusal using hand held mechanical equipment.
2034f40c-2239-5cf7-b16b-327f26cf6591 | note | REFERENCE DOCUMENTS: 705.18
fea65635-773b-5ae1-b871-7b64397c8cc5 | note | INSPECTION/TEST METHOD: Visual Inspection
b93aebd1-60fb-506e-ad56-ededa4f41557 | note | RECORD OF CONFORMITY: ITP Signed
d6f7dfbc-30fe-5834-97c4-6c149dba3dc6 | note | IP
19516347-0c30-54e7-aaf1-4715a096b548 | note | RESPONSIBILITY: Site Engineer
1df57040-53a9-5e87-a632-d9db772e3cb3 | textbox | Date Completed:
0ce3fe47-9e50-487a-b473-4626f2b09fc1 | checkpoint | 2.14 Backfilling with cement stabilised sand
02592d6b-cb72-5a34-beb8-23034d22f3a9 | note | FREQUENCY: Each culvert
575f8cee-ea6d-5af9-8b39-c06ece3f8b11 | note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
6bb4bb66-2191-5293-806e-559bfb54f137 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(a)
ded89c0a-f622-59b2-89be-acea8fb86d5f | note | INSPECTION/TEST METHOD: Site Inspection
9c12b3e9-3bda-5e6c-a10b-2551ec400e1d | note | RECORD OF CONFORMITY: Superintendent approval, ITP signed
e4db7862-f77b-5a9a-a8d5-0778a8d6f0ab | note | AP
16e962fa-ae06-5e83-8503-ddfd0ba8fa78 | note | RESPONSIBILITY: Project Engineer / Superintendent
a62fbd37-b080-5a5b-8c38-f4a6f979c235 | textbox | Date Completed:
f196e705-bda8-405f-ac26-39371ea51ec8 | checkpoint | 2.15 Install step irons
9b6479e0-4848-584e-b9ad-5dfb2819a5bd | note | FREQUENCY: Each Pit
12817339-f7fc-5928-8065-812abae1e41e | note | ACCEPTANCE CRITERIA: For pits > 1m deep.
a1acc96f-b2be-5a1f-941a-e13e947975f2 | note | REFERENCE DOCUMENTS: 705.12
2aac1770-b59a-5011-9a25-9bc619227b80 | note | INSPECTION/TEST METHOD: Visual Inspection
6d765ce9-f9cd-5b80-941a-f7c80b8ad50a | note | RECORD OF CONFORMITY: ITP Signed
20cd8764-b5c4-598c-8452-024062a65da0 | note | IP
95e6f0cb-65ed-5efb-a910-573f83cd96f4 | note | RESPONSIBILITY: Site Engineer
1d395f2a-5fe8-5c95-827b-960837506697 | textbox | Date Completed:
3cafec37-4293-4b53-b20f-762774ec68b8 | checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
fc37bcb3-f7cb-50f2-b983-8a09f9e2a579 | note | FREQUENCY: Each Pit
4fa3574f-e84a-50aa-bda0-1cf41d6984fb | note | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
cfd4404d-10b5-5286-afe4-4e6129e87cd9 | note | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
49771af9-aab5-5d3c-8497-26289b6464b7 | note | INSPECTION/TEST METHOD: Visual Inspection
6b5c874f-e508-5a81-9167-0313871fea89 | note | RECORD OF CONFORMITY: ITP Signed
8104af83-9a1c-5ae4-96c3-42b3d127c871 | note | IP
5a2d21d7-a79c-54a5-a1e6-f49007a1680e | note | RESPONSIBILITY: Site Engineer
8b6df7d3-eb37-516f-96eb-a6be374c162c | textbox | Date Completed:
ec49f85b-111e-4241-8b9c-9ba737b21316 | checkpoint | 2.17 Place pit covers
482708a7-8e50-55a9-8d93-e640505bad3e | note | FREQUENCY: Each Pit
e66bddf0-8efd-528c-a62a-af1dd3285f96 | note | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
f7b14762-ddf7-532c-b791-244927b4e0c9 | note | REFERENCE DOCUMENTS: 705.17
864b61ca-33ba-5dd6-83d5-9a607dac506c | note | INSPECTION/TEST METHOD: Visual Inspection
2a721f1c-7ac9-5b40-a7d2-7a3ec525862c | note | RECORD OF CONFORMITY: ITP Signed
ebdfbb49-45fd-5bb7-8ed4-4ce5f921ed44 | note | IP
ef112137-fb57-5bcb-b8db-b2b8c4ddde34 | note | RESPONSIBILITY: Site Engineer / Site Foreman
07afe513-6650-57a4-92d3-9568e5f264a4 | textbox | Date Completed:
f3d59524-db9b-4a86-a578-1a4c3422b7e9 | checkpoint | 2.18 Repairs to damaged pipes and box culverts
8578c28c-7882-53af-8fd1-ccd5e8db8003 | note | FREQUENCY: Each damaged pipe or culvert
a5df230e-e6e0-5717-b527-ffd7342b1a2c | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures . All repair procedures undertaken in accordance with Cl 701.25.
28bf02c0-789b-5f73-8a52-b083edffbcee | note | REFERENCE DOCUMENTS: 701.31a
0dc7799f-f81b-5838-a18f-fed77f48a0a2 | note | INSPECTION/TEST METHOD: Verify
89e8f6c3-b290-5d6e-be0d-f29108f52b84 | note | RECORD OF CONFORMITY: ITP Signed
ad60feb6-b9e7-5e90-900e-7473744d05fb | note | HP
7fbf9ac7-c778-5bcd-9ca7-ba68dc157f6b | note | RESPONSIBILITY: Site Engineer/ Superintendent
275b03ba-a6ef-5df9-98db-39a522946bc8 | textbox | Date Completed:
96719f68-c55d-454e-986c-f87da7347e8a | signoff | AUTHORITY HOLDPOINT
ecc4eb7f-113b-4dcd-9717-2a6af8fc4205 | section | Testing & Completion
e484eb1d-406a-4f39-888d-40fcc397d4ae | checkpoint | 3.1 Compaction and moisture content of backfill & bedding material
44eb8b8f-3401-56ad-b1a9-8a3450d773f8 | note | FREQUENCY: at least 20% of all lots
c34ca4d7-84b1-5608-b56c-b0d89df91819 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 97% using standard compactive effort.
874515f3-2076-580e-8c0b-048756261dd2 | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
3ad6b2d3-1420-5918-8232-aa7022dfd8f2 | note | REFERENCE DOCUMENTS: 701.20a, 701.20b
7c80a9a7-7ae4-59ed-b8cf-85cfbb326e95 | note | INSPECTION/TEST METHOD: Verify
7c91f6eb-e6b2-5761-9d97-c8805499c26f | note | RECORD OF CONFORMITY: Test Reports
5912704a-dc6c-50e1-8aee-eb5b6d9f4c52 | note | TP
c7ce0af6-f5e3-5f3c-a9bb-5e123e956084 | note | RESPONSIBILITY: Site Engineer
f50d4d2f-cd9b-50d4-abf2-67dae8f3777d | textbox | Date Completed:
9b9f4664-3e44-405f-a71d-40e465bb80f2 | checkpoint | 3.2 CCTV inspection
5285b12e-23eb-5db6-868c-edcc6fd63a83 | note | FREQUENCY: each lot
559fa85b-e82e-55e4-98da-cf187fecee27 | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
373c91fb-f59e-5969-88cb-62d95c268edf | note | REFERENCE DOCUMENTS: 701.30
46a6ad30-5576-5814-88c5-647d3012b3bf | note | INSPECTION/TEST METHOD: Visual inspection
2df577a2-0c8b-5508-b7e5-829c4394f3e6 | note | RECORD OF CONFORMITY: CCTV Report
f0d34633-33a6-5b3d-a53d-990d39a036c7 | note | HP
49a135a4-2865-50c8-ae05-e41b45482b73 | note | RESPONSIBILITY: Site Engineer/ Superintendent
fc824c31-11e8-5824-96e5-523a586692fc | textbox | Date Completed:
10d2669c-64fb-4677-93c1-178e932fc1f7 | signoff | AUTHORITY HOLDPOINT
19edf9d3-5ec8-4951-a8bb-8fcb01e3c17d | checkpoint | 3.3 Flushing of pipes
f4f572ef-dd6b-57d4-a4ed-0022119f4f72 | note | FREQUENCY: Each line
bd3adca3-35c7-5609-b281-fb9d35e00464 | note | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
122a067b-8011-5a91-b869-bb842899ac40 | note | REFERENCE DOCUMENTS: 701.28
2c959cea-0908-57dc-b543-bb148cd0bd6f | note | INSPECTION/TEST METHOD: Verify
a7ad96be-b1ce-5c5d-b570-9b4b1cc539aa | note | RECORD OF CONFORMITY: ITP Signed
5fb3d9a0-5188-5204-9128-10ca24ab5a6f | note | IP
41af477d-113f-52b0-a4f3-3bb7c6f084cc | note | RESPONSIBILITY: Site Engineer
58b83555-7ffe-589b-b268-f992eb82ffc1 | textbox | Date Completed:
a528cf40-f4b3-4227-aa60-3bd2bba62ddc | checkpoint | Final Inspection
e8121776-428a-52a1-bdb6-a5b5d5008ae8 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c546f7d7-8d38-5fd0-907e-d57c98aa69c0 | textbox | Print Name:
5cf73912-3587-5a27-8197-0bdb1168af3d | textbox | Position:
dc57c681-ec89-5900-9a25-fca527852191 | textbox | Date:
9d5730f8-7010-443d-94d5-43330bd49857 | checklist | ITP-012 - Hot Mix Asphalt | itp | ITP-012 - Hot Mix Asphalt
6af7f8b1-8970-4118-9902-26941aabc7f2 | section | Construction Works
68e55505-674f-4c59-9ff4-0573bf1a6edf | checkpoint | 1.1 Submission of Mix Design
8aeca7bf-dcec-50b9-acdf-79b5adb1be39 | note | FREQUENCY: Prior to commencing paving
884a0a49-fe55-593c-a889-8bc727cb7b84 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
68d51817-45fb-5d92-8eff-fc893999bc10 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
edeb7a40-c036-5798-ba1f-bd6b28522f2d | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
a0e5409f-923a-558c-acb9-87f11f19f490 | note | RECORD OF CONFORMITY: MRPA approval Completed ITP
00f96b8c-568d-5388-b260-0e2d33f4653c | note | HP
0e919175-2dde-5dd5-a6f1-dc015f40916b | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
838e535a-545d-55c1-afa9-fca2365cde7a | textbox | Date Completed:
39a3c7c1-4138-4fc0-9225-7279b7cd32c7 | signoff | AUTHORITY HOLDPOINT
321209d4-2e88-494a-8a96-f86e3aba6f78 | checkpoint | 1.2 Implementation of all measures and controls
14d9c20a-6ba3-58d2-ba7d-558014a42708 | note | FREQUENCY: Prior to commencing any activity
f1fbbd3c-3b13-5e47-ab2e-201c74925f8b | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
a1150ffa-2104-574a-a40c-2f74be2ceb87 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
8d200f41-7826-5052-9f9e-ba8463c8f226 | note | INSPECTION/TEST METHOD: Visual Inspection
e82ff737-081b-50b6-a402-126b2e27e69c | note | RECORD OF CONFORMITY: This ITP signed off
4855db33-7ca3-5a25-975b-db137fb39aca | note | HP*
cb836c26-d150-5a27-9fd4-b51e37b33dc8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ac8cc6f8-2e29-506f-8c01-e4c31dbfa02e | textbox | Date Completed:
0b45f1a2-6daf-4c1d-9084-31965261bb79 | checkpoint | 1.3 Site Inspection and Base Condition
a887b304-2434-528d-85c4-cb261d18894e | note | FREQUENCY: Prior to commencing paving
e3e16b71-b2ee-526b-9bb1-45d7e110eb49 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
c0c3ebbc-1b89-5632-9711-5583a7a7db1d | note | REFERENCE DOCUMENTS: 407.17, AS2150 10.1, AS2150 10.3
dd319179-123e-5973-9c2b-ae397133b6ae | note | INSPECTION/TEST METHOD: Visual Inspection
eb33e0a8-82ea-58f7-864f-e3b5780bed51 | note | RECORD OF CONFORMITY: ITP Signed
6829ea63-a2a3-5ecb-814f-719d64472cf1 | note | WP
ee8d6701-a447-549e-9ee9-4cd9bf6d4004 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
0fec433b-a848-5b2b-bfce-58d8a984b8c1 | textbox | Date Completed:
efa459c5-d4ee-4407-9a73-73f74b8140dc | checkpoint | 1.4 Ambient Conditions for Placing
1b0a10a3-58be-5ded-8dfe-d55fbd103a6b | note | FREQUENCY: Prior to commencing paving
8557b9c1-83c5-5740-8b13-4fdafb43cc70 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
74459188-1d99-579d-b110-e3deb787ef90 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
cb549274-ff25-587a-be2e-eee1ee882c20 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
a1a647fe-06f8-5a55-9758-908afd11de34 | note | REFERENCE DOCUMENTS: 407.17
5ffee86d-72d7-50b6-80a3-116270dcb6b3 | note | INSPECTION/TEST METHOD: Verify
149ab24f-e38f-59bf-a8d4-ef90b0d1a896 | note | RECORD OF CONFORMITY: Thermometer
3e6d2b9e-e27f-526e-a229-20eaf1280c76 | note | IP
99da9056-20de-5664-9aaa-b3c685c566a5 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
3c2453db-de82-5b09-bf93-6773e6a81345 | textbox | Date Completed:
907b69c1-79a3-426d-9584-fa799e6f962d | checkpoint | 1.5 Planning of Joints
4447e19c-7ed4-5c6c-8a73-314f2a2945c5 | note | FREQUENCY: Prior to commencing paving
3c9afc21-017a-55ec-a444-e4387d9ceb90 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
3f941947-b741-56d2-8f7a-fbb38aaffe87 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
9e90ae99-2d42-5829-9a4d-6e85f6603522 | note | ○ Longitudinal Joints Offset from layer to layer by at least
bc759348-fb3e-5f7a-83f8-9104ca9cca68 | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
ee22da3f-1db4-5e19-a602-8e3eea6f4668 | note | REFERENCE DOCUMENTS: 407.21 (b) & (c) Pavement Drawings
2ca7870a-240d-5128-9b47-10ed0728bceb | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
a772fa6a-8db9-5ced-96f1-247a2896958d | note | RECORD OF CONFORMITY: Paving Plan
6a6060aa-8ef4-595f-b616-86326320d8dc | note | WP
be80bacc-5a41-5f16-b1a1-f3b2727c6344 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
1cb2e088-8f4f-5fcf-848e-a45c2ed335bf | textbox | Date Completed:
5b69a2e6-8749-4063-bf5e-78ac5b1681de | checkpoint | 1.6 Longitudinal Joints with existing Pavement
3d97475d-bd0b-534d-99ee-0fc1018d0c29 | note | FREQUENCY: Prior to commencing paving
5d55925a-1484-5c8f-975b-ab8386a88649 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each indiviual layer.
727928a5-bf19-5d3d-8c75-2c03634d297e | note | REFERENCE DOCUMENTS: 407.21 (c) (ii)
9fe10512-271d-5a58-b31b-73a149b31557 | note | INSPECTION/TEST METHOD: Visual Inspection
fef06c69-0526-5220-bcbb-2c46d106bf10 | note | RECORD OF CONFORMITY: ITP Signed
74844497-f475-5c08-a701-044013f7d054 | note | WP
6dc4f0df-db3a-566f-acba-ec1f22f82ac6 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
6d712427-79e8-51a4-963b-ad5533604313 | textbox | Date Completed:
97bd0214-87c9-4e8e-b13a-ae4bbcfa4eee | checkpoint | 1.7 Lot Size
4f9b3288-f52e-5507-8d60-22a25ed42b8d | note | FREQUENCY: Prior to testing
6006403b-fc4f-54c9-8496-09a22ccd6789 | note | ACCEPTANCE CRITERIA: Lot size for determination of testing shall be in accordance with 407.27 (b) (ii), where less than 500 m2, reduced testing may apply
8ac72e67-609f-5e9c-8029-65b1b9e052fd | note | REFERENCE DOCUMENTS: 407.27 (b) (ii)
bea12b7f-1a50-5cc0-8ae9-bf03821cbcdf | note | INSPECTION/TEST METHOD: Visual Inspection
c0d977a0-bf62-5bbc-86e4-ff67efd77704 | note | RECORD OF CONFORMITY: ITP Signed
1581ccb3-9422-570e-a7b0-1bb0f001b8f2 | note | IP
22ab63d4-c51c-5851-a480-489f4aae944d | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
17575162-4107-5c04-9026-3a84ec2c2750 | textbox | Date Completed:
812c862b-790d-4353-b001-fc5d7e2c3ffd | section | Asphalt Placement works
21d7cffe-9926-4c36-818e-e8f96439a042 | checkpoint | 2.1 Tack Coat
c1260cfd-2d7a-5bfe-84b6-0e5aa873ce48 | note | FREQUENCY: Prior to commencing paving
59dd7b02-0781-54ef-8fe9-efe850fa6287 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving.
7f9a2340-485c-5d0d-8b37-2943dc5fa435 | note | ○ NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
647be36f-18d8-5306-9df6-40ff21b91160 | note | REFERENCE DOCUMENTS: 407.19 AS2150 11
4a2acc93-e277-544f-9f8c-ec4e021b325d | note | INSPECTION/TEST METHOD: Visual Inspection
00c88977-33bd-5d75-8981-a26fc552a437 | note | RECORD OF CONFORMITY: Spray area
969e741e-6cf7-5644-bdc8-f3c3bcd77194 | note | WP
0156cf38-2bb3-5281-af53-26281639d3c3 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
1ee51b3b-602b-5462-8d27-52e628055f7d | textbox | Date Completed:
10888c52-6845-4bfd-a0df-905d11de2a16 | checkpoint | 2.2 Commencement of Placing
c337b561-38e6-5165-88b6-abed444a0d21 | note | FREQUENCY: Prior to commencing Paving
cca37223-0301-5171-b633-1a02e7718f21 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
a269d547-771a-5655-9eda-83d433b521b7 | note | REFERENCE DOCUMENTS: 407.23
50d33bc5-93db-51b8-8fee-600d1b835882 | note | INSPECTION/TEST METHOD: Visual Inspection
599eb34e-6a08-57da-b578-16c61a59f97b | note | RECORD OF CONFORMITY: ITP Signed
59ed3147-842c-52bd-b163-02be3ba6f6c2 | note | HP
2bddba68-20b3-55e3-b158-6855917ecda8 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
0e2cf6dc-291b-5d53-b7b0-1bc5e9d5f139 | textbox | Date Completed:
80f2152e-d0bb-483e-8fd4-4c85a6bddc86 | signoff | AUTHORITY HOLDPOINT
c071b208-1165-47f9-a5bf-3cb578d8c502 | checkpoint | 2.3 Mix Design Confirmation
6bb58591-a396-5ebb-9218-ceca2e49b51c | note | FREQUENCY: Each lot
ff6a9af0-e95b-52d4-9308-eb740009c825 | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
099203dc-31be-56ad-8492-0693df504189 | note | REFERENCE DOCUMENTS: 407.2
0ce9f2a5-7bd7-5d2f-9c6e-66b834a32d5c | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
17e658d3-8b37-5af4-86af-fd52f3711229 | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
1829dc37-4d4b-566c-af7e-5b8412caf340 | note | HP*
b03d34cb-bea8-5535-80a1-438170711d67 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
dc76bbfa-3c8e-55b0-9612-395784237bf1 | textbox | Date Completed:
d32d036c-3e4d-41e6-8bec-ba057954ff4f | checkpoint | 2.4 Delivery of Mix
607aa2c4-3920-552e-b9a9-9c104786c7ed | note | FREQUENCY: Each load
b59202dd-aad3-514c-ad84-c887c9f78d3e | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
5e9f3781-d337-549a-882d-d1ea89fc7afb | note | REFERENCE DOCUMENTS: 407.20
44d3e3bf-b15f-54be-b0a3-b64fb5890ea6 | note | INSPECTION/TEST METHOD: Visual Inspection
d672b85e-f784-5eac-b7d5-0f484c79d718 | note | RECORD OF CONFORMITY: Delivery Docket
255ac471-8aad-53e4-8da8-80cc8d8323eb | note | WP
326bae4b-c35d-529b-86c7-002419e1ae85 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
22f8b334-e6b5-541e-9573-a0953c54f2f7 | textbox | Date Completed:
cc11e2bf-accf-4262-8867-965011576663 | checkpoint | 2.5 Traceability
c5724acd-ad7b-54c0-bf2b-c2665543271e | note | FREQUENCY: Each lot
8bc5b43a-62ed-500c-aa82-14670de4aa15 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
8461055e-6335-59b5-b590-da09caf0b266 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
ca4f8cf1-0145-5344-ad85-d2a840baee93 | note | INSPECTION/TEST METHOD: Verify
15544b34-e1b1-5d05-97f4-601485da8966 | note | RECORD OF CONFORMITY: Daily Lot Record
171eddae-61e0-56ed-b287-cf858fd18a9f | note | IP
cbda8036-0d33-500d-b79e-40eecb9d1ff3 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
aab9b30a-a3c6-589b-a691-f2abc8217d2f | textbox | Date Completed:
90ac5ea2-e364-4160-8d01-db8c26a3af1e | checkpoint | 2.6 Layer Thickness and Level Control
c49b27e3-c7c1-511c-bf66-ff02c20b8f3d | note | FREQUENCY: Regularly during paving
c1ca8218-cb69-5563-94ee-1c83d3ce12f1 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
ac6c2de3-46e9-5cc0-b7e2-bca808a017a4 | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
3f08a1d4-9a15-5ecf-8920-33342e8043df | note | INSPECTION/TEST METHOD: Verify
ec25781e-8f04-523f-8ff8-b7dca7a93216 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
840f0bdf-edb6-5f61-94ae-d6264cd26fc1 | note | WP
a1d11b7a-7701-59ed-b4a2-4da5a9c91f42 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
9ca5bee2-d314-570d-b9af-8a87e69cfc9b | textbox | Date Completed:
78672645-7bba-4943-974f-7dc2cc882fab | checkpoint | 2.7 Paver Stoppages
33d16804-68dc-5b1e-a1b5-c9c9059c06b9 | note | FREQUENCY: If paver stops
6dc6bfb4-8737-54b2-84a2-a23cea7b256b | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
da37f577-3caa-5d91-b56d-831de8c30cb4 | note | REFERENCE DOCUMENTS: 407.25 (c)
b88b7c88-4252-59bf-b9e6-5bcf0b37017d | note | INSPECTION/TEST METHOD: Verify
82acda0c-2c15-5179-89f7-a19444b9f5ec | note | RECORD OF CONFORMITY: Thermometer
4744b9b0-7728-5555-affb-059ec862cc9c | note | WP
4b2c0908-1374-53ba-a088-e6123948370e | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
4eec1e31-5397-57ab-8f82-8b4de60b2e97 | textbox | Date Completed:
17f5dd26-0174-41a9-869f-a1bad18f3f7d | checkpoint | 2.8 Surface Finish of Wearing Course
bd2f2877-5775-54c7-8d82-1be43749abdd | note | FREQUENCY: During paving and after final roll
fd74d599-13d4-5159-b535-18e9b5a127dc | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
0cc20f25-001f-598c-9487-ade16f3ddc1b | note | REFERENCE DOCUMENTS: 407.29 (a)(i)
6030e36d-5a23-5bbe-96bd-eaa6db5ca05b | note | INSPECTION/TEST METHOD: Visual Inspection
10ab8a93-6207-56b2-80bf-db6c25a3adb7 | note | RECORD OF CONFORMITY: ITP Signed
1205ac8e-4859-52d4-93dd-9453a09134c9 | note | WP
18a0d35e-10e6-5728-9468-94b429015129 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
364c2f3e-0f37-5e05-9fc6-c06596a173db | textbox | Date Completed:
1c93b68d-597a-422e-9c4b-9affe5cae88d | checkpoint | 2.9 Kerb and Channel
4ea82c81-7990-5bd3-8973-88f382eed23b | note | FREQUENCY: During paving and after final roll
1d869848-5dca-5bf8-8a89-687d676eb92c | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
e7eee414-e453-52c8-b062-87f50bbc058c | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
20ab5ffe-89fd-5607-93c7-5a9ee02d72ba | note | INSPECTION/TEST METHOD: Visual Inspection
d50f602e-37a0-57ca-9b91-f1e820df7d48 | note | RECORD OF CONFORMITY: ITP Signed
8763c0dd-ae53-57ab-979e-9bb0b7f84758 | note | WP
749f31a6-7990-5beb-985e-86f2af9bc211 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
a21e8451-7da9-5c86-b0a7-fc3a59c29c75 | textbox | Date Completed:
f7bf408b-94a5-4148-bd31-dd3b75e0a678 | checkpoint | 2.10 Alignment of layers not placed against concrete edge
cecdd5bf-c015-563f-be31-47f17e3b70ad | note | FREQUENCY: During paving and at completion of work
af1d03e6-dbc5-5396-b1f7-ffc710c3747d | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m.
ea1b1004-9237-55f2-92f1-08b0db8a3571 | note | REFERENCE DOCUMENTS: 407.29 (a)(iv) Drawings
a61734cd-62a9-5dab-99d8-d04bad36fd99 | note | INSPECTION/TEST METHOD: Visual Inspection
a25661f5-fd14-5061-9b84-b6cd19f5237f | note | RECORD OF CONFORMITY: ITP Signed
77f9aa64-8ff1-5568-b1e6-deabb56803a5 | note | IP
8d46c894-a84c-5502-8a84-accf36713170 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
fb8fa8a7-39e2-54b2-8933-566c30ebb121 | textbox | Date Completed:
9d83bbad-0f37-466c-9470-20d1ae310de1 | checkpoint | 2.11 Width of layers not placed against concrete edge
550ea724-eea8-5067-b97a-bae724b38614 | note | FREQUENCY: During paving and at completion of work
46cb82a6-02e6-55d3-a314-21eaa05430c6 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm. The average width over any 300m shall not be less than the design or specified width.
fa36c062-9ff9-5882-8632-8c0126aae3dd | note | REFERENCE DOCUMENTS: 407.29 (a)(v)
2c2a5c9c-9afa-5909-b7a0-7ba46dcddef5 | note | INSPECTION/TEST METHOD: Visual Inspection
7bc6629a-a6bc-5ee7-a026-9b9089474987 | note | RECORD OF CONFORMITY: ITP Signed
1eb38fb4-69ee-52ec-bfb8-f1fad4334831 | note | IP
8c1d59ad-9338-5362-a869-9970bffe6c83 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
3f48d935-dede-5231-b010-6c24dcc23e01 | textbox | Date Completed:
df9f25c9-4293-4e91-bf7e-fad004b3d16b | section | Testing
e0e7cf69-679a-4dba-a38d-47fe80e146f3 | checkpoint | 3.1 Compaction
17a47375-2e00-55c8-a091-f375d757d8b1 | note | FREQUENCY: Per Lot
f77b39ed-9d2d-5b9a-9b3e-0ad7399da565 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
afad3fe4-4248-588d-80f8-6bf072495bfc | note | ○ 95.0% or greater Accept lot
1b45f12a-f8b2-5f6f-b6b4-d95f43852b3e | note | ○ 93.0% to 94.9% Lot may be accepted at reduced rate
7b46d1bd-8435-5bc9-8788-0fd06b5a5ef5 | note | – For layers ≥50mm, if characteristic thickness is: 96.0% or greater Accept lot
f3701cdb-8ff7-5029-893a-414ea429b7d6 | note | ○ 94.0% to 95.9% Lot may be accepted at reduced rate
34be3b41-5cd8-5013-8b32-95378a35e1e5 | note | REFERENCE DOCUMENTS: 407.27
b042b7b0-6cbc-525c-ae0c-019671931295 | note | INSPECTION/TEST METHOD: Verify
d59617ac-e3e1-565e-8535-209838d3c542 | note | RECORD OF CONFORMITY: Test Report
fb106f29-c7a4-528e-8fb6-c49677033af3 | note | TP
8ba4ccbf-599a-50d6-b825-85c28f85e417 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
74da8b57-56c6-5550-8efa-e6dc2513fa90 | textbox | Date Completed:
856e2622-541d-4d08-992a-c2169fd179ee | checkpoint | 3.2 Level Conformance
3f89f8ae-c481-59d3-9f09-e1aeccc5f106 | note | FREQUENCY: Per 4,000m2 at completion of work
a8ec2697-5d93-5e1d-95fd-370072421bc2 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm (Scale B)
7bdafddf-0bff-554b-a288-becbd80bbf47 | note | REFERENCE DOCUMENTS: Table 407.293
29056073-b788-5f69-8c17-f7af6ae0d0ef | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
ce78c1ac-f11c-578c-819b-ba295e9dd999 | note | RECORD OF CONFORMITY: Survey Conformance
10dfab6d-bfb9-5de3-9e25-80151dfd5391 | note | SCP
1a9ad535-3c21-592b-8ec0-d1459a7fdb3c | note | RESPONSIBILITY: Site Engineer/ Surveyor
19e2ff0f-e414-51db-a166-bbe9266ff72b | textbox | Date Completed:
bb479058-c9f9-480f-af95-5dba3b51b457 | checkpoint | Final Inspection
946af718-51c8-5635-b0c6-0116d156db85 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
48c38d2e-1e30-5e77-8498-9d72c78b29ca | textbox | Print Name:
f8b35d08-9237-5108-8078-0b814684545d | textbox | Position:
990c3c1d-4920-5b9a-8813-d83c34d841ec | textbox | Date:
6aed98b0-ca75-4f81-95a7-017e8490c5a5 | checklist | ITP-014 - Subsurface Drainage | itp | ITP-014 - Subsurface Drainage
423021ab-bc69-4b49-a7d2-ccbc70d89f1c | section | Preliminary Works
a24e3fd3-4b68-4934-820d-cf9a39a1f916 | checkpoint | 1.1 Check for correct documentation
c1693279-4ae5-55c9-89b2-fc88b83205e3 | note | FREQUENCY: Prior to commencing any activity
9404b279-d446-5ac7-b772-6d0800446096 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
e8119c13-1ef6-5c3a-a88b-612f0936d8f7 | note | – using the correct and complete set of drawings
be829e7a-4679-5018-b40f-277e3ca0f2f3 | note | – all drawings are the latest revision
88493e6c-fd29-578e-867e-2347a4d05b4a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2ab2f49c-8e1f-561a-8db0-ce93c133cad7 | note | INSPECTION/TEST METHOD: Visual inspection
22e195a0-61cf-5e58-a362-686ec5ef8ebc | note | RECORD OF CONFORMITY: This ITP signed off
3b47c89b-f58a-5ea2-bdff-1e40d3a17128 | note | HP*
583dcfd3-9d04-59dc-bfe5-1591fa5440af | note | RESPONSIBILITY: Site Engineer / Site Foreman
65b8dfc9-9893-5c12-b27b-d75e7db781dc | textbox | Date Completed:
91506e32-12c7-41f1-a169-5f34cca79b0c | checkpoint | 1.2 Implementation of all measures and controls
4e1ca2db-7a0a-5021-b821-f9170d788f99 | note | FREQUENCY: Prior to commencing any activity
ec486918-2fb3-5208-ae11-9814eba6a7e9 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
cf90adac-cdda-5b17-8798-8cc40179d79e | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
3285edf8-a702-5e4e-810f-24a9c68e0616 | note | INSPECTION/TEST METHOD: Visual Inspection
83a04add-bece-5564-8729-3f71a7e5ee2e | note | RECORD OF CONFORMITY: This ITP signed off
fbe2fe5f-1f72-51a1-892f-d8056f697617 | note | HP*
0804d272-512c-58c5-bad2-309efa53a8e5 | note | RESPONSIBILITY: Site Engineer / Site Foreman
a6f27500-b877-5710-9c12-95de8eba8289 | textbox | Date Completed:
2b7f435c-0c6d-46c1-8d13-8f49d99685e6 | checkpoint | 1.3 Placement of no fines concrete methodology
10d3c9c1-8c93-5c2e-9a98-2872594fb67f | note | FREQUENCY: Prior to works commencing
fbc0707b-e769-50ac-9fd0-6284ba77e774 | note | ACCEPTANCE CRITERIA: Where no fines concrete is to be used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures
5f55e0e8-3837-557c-a0f4-8ff75c179e44 | note | REFERENCE DOCUMENTS: 702.09(g)
206c4a5a-cb16-5dfd-adee-98af408b8d20 | note | INSPECTION/TEST METHOD: Verify
1bfec44e-2684-52d8-b942-92e57d73661d | note | RECORD OF CONFORMITY: This ITP signed off
04334e89-491f-50d2-8d53-62ed9fc4f1d7 | note | HP
b5088b29-fc4e-5a74-a7c5-0c1080a88ad1 | note | RESPONSIBILITY: Site Engineer/ Superintendent
0807d059-5c84-55da-abbd-7bccfb48ebaf | textbox | Date Completed:
7d2ff4dc-38ee-49fe-90ff-b10223cbb3c5 | signoff | AUTHORITY HOLDPOINT
676d2887-8ea9-4532-aa19-7a49f5dad28a | checkpoint | 1.4 Material Classification
495d92b0-2377-5815-bf8c-b9b278ea24c9 | note | FREQUENCY: Each Lot
94a4b9c2-31ee-5346-9cbd-325ded85a0c0 | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000kN/m/m corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
86637f4e-1e96-5948-9692-020ea733aeba | note | ○ Granular filter material for bedding and backfill: Trench backfilled and bedded with specified material on drawings (Type 2 as per SD 1061)
aa1d5d1d-755d-561f-b142-b1611e36151f | note | ○ Geotextiles: Shall comply with Cl 702.06.
893a289a-b0c8-58f2-9b7b-59f057a95cac | note | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
39af32f0-5f18-5909-b8ae-d928819bc532 | note | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
5d48920b-97cd-5059-9bc5-a3649333d7b2 | note | ○ Flushout risers: Constructed to the detail of SD 1631
726f3bbb-1a5e-5c39-a7f6-3432db3f7cbe | note | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
068b1771-c4f6-5faa-9f8d-aaecf9d3c70a | note | INSPECTION/TEST METHOD: Verify
dde46682-bacb-5c2c-a091-9be5a0d13905 | note | RECORD OF CONFORMITY: This ITP signed off
6c44544f-741b-5119-8a59-cb4caf12b2e6 | note | WP
01b9aa18-5f69-56af-a76b-6c79ab0143e4 | note | RESPONSIBILITY: Site Engineer
aecafa7c-88ea-5dfc-97bf-b3d6a98bfbf8 | textbox | Date Completed:
5aa86719-463c-40ea-a155-f3a0434901cf | section | Construction Works
7e124ea4-599a-4a9a-b5d5-45c885b16c5d | checkpoint | 1.5 Excavation Permit
eb57b970-a013-55b9-8eec-4067af53d9b6 | note | FREQUENCY: Each lot
59089929-f56f-529e-858f-4ba09b6a12ec | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation.
b1bc1e7b-b630-5f9c-8685-808383b7aac4 | note | REFERENCE DOCUMENTS: Excavation permit
b5dd1ec0-05b4-53c0-a77b-875800bacdec | note | INSPECTION/TEST METHOD: Verify
cfbbea1d-6024-58aa-bad2-a6284316b302 | note | RECORD OF CONFORMITY: This ITP Signed Off
a48f996b-8eaa-5d5a-b1c3-483afb30fb76 | note | HP*
cfba18e0-0b3e-51bd-b551-f667ce0615c2 | note | RESPONSIBILITY: Site Engineer
892c60df-4660-51e2-9a42-5ee50639fd85 | textbox | Date Completed:
cbffaba4-b40f-44d8-b746-409838290205 | checkpoint | 1.6 Excavation of Trench
7d347741-30c2-5c70-b41e-2a479c431846 | note | FREQUENCY: Each Lot
d42e8461-2573-5ad5-a35b-2b9dc4c8dc46 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
6ddaa513-a88d-54c9-bae9-500e62f8ec81 | note | REFERENCE DOCUMENTS: 702.08
221a6184-0d1a-56aa-b0c3-02f3ea8438ca | note | INSPECTION/TEST METHOD: Visual Inspection
1c3d166b-9aff-5f4e-a006-b9e9125781b7 | note | RECORD OF CONFORMITY: This ITP signed off
a7136963-7261-5e03-89a7-49bb18598bf7 | note | HP
92a5781a-c4f2-5264-8ba6-4d9871ae6cd9 | note | RESPONSIBILITY: Site Engineer/ Superintendent
bafcd561-2425-51c6-9151-fe8f15bfcd55 | textbox | Date Completed:
940a904b-ea82-4d4f-9876-0f076925f3a4 | signoff | AUTHORITY HOLDPOINT
f3c224d0-6d27-4e9e-84b8-fadbb95662ea | checkpoint | 1.7 Placement of bedding
d9df2326-0e39-5caf-8617-b83253ac58c3 | note | FREQUENCY: Each Lot
b33253f2-e6b3-5447-89fe-f5ab795da02e | note | ACCEPTANCE CRITERIA: Bedding of granular filter material, 25mm sand placed across bottom of trench and screeded or graded to level
05f5f64b-5376-5eec-82c3-952d0c9fbbb2 | note | REFERENCE DOCUMENTS: 702.09 (c)
2ba491d6-32c3-5c7f-85c4-c56797ded097 | note | INSPECTION/TEST METHOD: Visual Inspection
ee98d8dc-882a-561e-a845-22641234aa7a | note | RECORD OF CONFORMITY: This ITP signed off
e42a1ea9-6855-50f4-be11-df0c5de3812a | note | IP
6e710dc9-3032-5d45-8caf-657e71affdce | note | RESPONSIBILITY: Site Engineer / Site Foreman
5a8d8f1d-a1da-52b3-b32c-84c0e9c94320 | textbox | Date Completed:
3f082cfd-ed1a-42a0-b908-0e65d36185eb | checkpoint | 1.8 Placing pipes and geofabric (if required)
10599611-ae63-5aa0-8786-f8e37b17c539 | note | FREQUENCY: Each Lot
484d9631-f00a-5308-ab0f-a7959d4d4769 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe. If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping.
6ea30801-2d4d-5e69-ac58-0828f30643d8 | note | REFERENCE DOCUMENTS: 702.09
a0f478dd-5880-54b6-8194-537eb41ebf42 | note | INSPECTION/TEST METHOD: Visual Inspection
e08fb438-8e6f-58b9-8cac-f8d6c7708450 | note | RECORD OF CONFORMITY: This ITP signed off
59ae1b57-9b71-5e4e-97a6-314642d297c6 | note | WP
cf716a2d-6933-5539-820d-8203485841a7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
de9123e9-b4c4-5374-96d8-7d7677196e5f | textbox | Date Completed:
c5d013bb-bbed-467a-a21e-759a7cc33401 | checkpoint | 2.0 Install Pits and Flushouts
0bc1e7df-ea40-5cef-a3d5-985d3c97b258 | note | FREQUENCY: Each Lot
3851e5b1-520b-568f-891b-2f834e487e8e | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
134af3ea-b899-50c7-8855-72022802be2b | note | REFERENCE DOCUMENTS: 702.1
8bc70990-fb9c-5ee1-baed-fd5ec37c82fa | note | INSPECTION/TEST METHOD: Verify
bed06493-9d0c-5e47-a65c-7dc9fedc8583 | note | RECORD OF CONFORMITY: This ITP signed off
55632c43-5444-59d6-87e1-752b85a35f56 | note | WP
28a8d74a-6ab4-52ed-9eb0-282615f76a8a | note | RESPONSIBILITY: Site Engineer / Site Foreman
dfeb94c0-dca7-528d-95de-434b837a0f38 | textbox | Date Completed:
3744a354-58d1-4d65-89d6-24bd9178b778 | checkpoint | 2.1 Flushing Test
119c2972-ae6c-5344-b2d9-6a7f13bcdc83 | note | FREQUENCY: At completion of stage
05df12fb-3a29-56ff-adc8-77bae5a554f1 | note | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
cbcab504-0596-5c99-97d2-47538cc99df8 | note | REFERENCE DOCUMENTS: 702.09(i), 702.09(h)
8e6029f0-e55b-58e6-b5fa-9e30bf9db00d | note | INSPECTION/TEST METHOD: Site inspection
d3fc7049-99c5-500b-8437-c9bb362cfba4 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
a3debdc9-882f-5520-9406-ed83a6102027 | note | WP
e0a4eed1-c79a-5228-b053-07308d7a634d | note | RESPONSIBILITY: Superintendent / Site Engineer
d2a5b97c-d70d-56fa-8b61-37588c72144d | textbox | Date Completed:
f7224972-c3a5-4734-bc65-f8d514a7d402 | checkpoint | 2.2 CCTV
93809b56-62a5-519c-bca9-843b256c481c | note | FREQUENCY: At completion of stage
f6b91ceb-30bb-5d14-9cb1-16ec69725db3 | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
68c84ef8-cf78-5c38-81cd-b8d0315a0c24 | note | REFERENCE DOCUMENTS: 702.09(i)
8c7fc99d-4876-58cb-9091-10dc3a87473a | note | INSPECTION/TEST METHOD: Site inspection
aadef08d-4199-554f-92c2-2afadee99fdb | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
52b16ca2-b2ec-554b-a3c5-44c1e8305720 | note | HP
c6df1dc2-58b4-5602-927f-a4b0ae446a79 | note | RESPONSIBILITY: Superintendent / Site Engineer
a510ee7f-d5b6-5a96-b559-086238a822db | textbox | Date Completed:
d86ec2fb-224d-478b-bedd-e094cca816d3 | signoff | AUTHORITY HOLDPOINT
5c4b72f3-0d64-4afb-9f84-91b93d255ff6 | checkpoint | Final Inspection
a4df744d-c931-58d9-81cb-7f99eace686b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
6aee0d14-8b19-5c9f-a08b-068c3c5e5fea | textbox | Print Name:
d44a7998-f21d-5b87-a5fc-6b2cc5ffe514 | textbox | Position:
bc0f4ef9-db7a-52fc-99db-0fde99354054 | textbox | Date:
a1d81a7b-9873-4f66-a10a-dc6932865152 | checklist | ITP-015 - Kerb and Channel | itp | ITP-015 - Kerb and Channel
ac08f09e-d66b-43e9-a44b-41c283faeaab | section | Preliminary Works
efca595b-eb65-4b8c-aa5e-57bbb3e41749 | checkpoint | 1.1 Check for correct documentation
3599fa7e-d16d-5e1a-8918-c9b21cfb8c44 | note | FREQUENCY: Prior to commencing any activity
787c8e88-a45b-5b0c-a3a8-c9cdf4c06e99 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
debc59b2-8d16-54fb-9222-2eecbcd6a5f9 | note | – using the correct and complete set of drawings
a8863b2e-1273-5a4f-8742-f78c13493081 | note | – all drawings are the latest revision
0dd713dc-bcef-53e3-a69c-7ae7c796f5de | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1517535b-378d-5b08-8168-52f88cea3487 | note | INSPECTION/TEST METHOD: Visual inspection
327b9e30-a718-5a6a-bce9-c0102ad56307 | note | RECORD OF CONFORMITY: ITP Signed
dc452347-2076-5e51-a41a-7bf647f4e63e | note | HP*
b4170090-4ba6-59c4-97c4-6316353154db | note | RESPONSIBILITY: Site Engineer/ Site Foreman
b898b979-aa63-55e2-a232-3efc79801cff | textbox | Date Completed:
dfff3ee3-3697-41e8-80eb-0a66fe5f942d | checkpoint | 1.2 Implementation of all measures and controls
094e0396-18ac-5db0-b8a6-1743563051a9 | note | FREQUENCY: Prior to commencing any activity
ca7b8142-c169-598c-943b-2b56316ff1cf | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
c6ac52f2-9a64-5918-9050-878c7ce13238 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
028056d5-64dc-5196-8895-2f1f1b7dd66d | note | INSPECTION/TEST METHOD: Visual inspection
2a55bb7d-5dd2-54c7-b18d-e1919f31ba19 | note | RECORD OF CONFORMITY: ITP Signed
b90a998d-b485-5fd1-99ef-4a0e10cdd7f7 | note | HP*
e2b15a13-08ae-5847-83c7-db45f3d315eb | note | RESPONSIBILITY: Site Engineer/ Site Foreman
2f49fb73-4e3d-5bec-8e90-b2a504e51194 | textbox | Date Completed:
da18d7bc-12e2-4ba2-af62-663e092baa75 | section | Construction Works
c7594c7a-5b7d-4dcd-bdea-e6399c142143 | checkpoint | 2.1 Setting Out
f077c44a-7b58-5599-8949-19d6cac3da69 | note | FREQUENCY: Prior to start
ca94714b-0101-542f-9306-b9d60cfd0f2f | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
1e605ec1-c48f-582b-9d35-8eff688fb987 | note | REFERENCE DOCUMENTS: 703.17
72991a0a-bbb0-5b85-b905-f70f247ac7a0 | note | INSPECTION/TEST METHOD: Verify
c6a56f15-2e8c-502c-afcf-185ed47de674 | note | RECORD OF CONFORMITY: ITP Signed
08b1a027-d922-50d5-89ca-3eae957bcf5e | note | HP
a908d8ab-5af3-514e-b792-2e114da46ed1 | note | RESPONSIBILITY: Site Engineer/ Superintendent
8ff53a12-9ffb-5abf-bb49-983102df8188 | textbox | Date Completed:
4df1e771-3159-4b60-8d24-f3ba3b74f19e | signoff | AUTHORITY HOLDPOINT
26d9698f-fab6-4847-a755-8bc69e2f0267 | checkpoint | 2.2 Temporary Drainage Provisions
ba765328-3345-5348-b468-cecac62aaa58 | note | FREQUENCY: If Required
44ddc6dd-be0a-5bc7-8cac-3938737354e0 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
f98061c1-84aa-534d-8151-5da04914fd90 | note | REFERENCE DOCUMENTS: 703.18
9088c5e0-5f55-5347-9338-09bd9871ce56 | note | INSPECTION/TEST METHOD: Visual inspection
04babe31-2840-5b25-b7c7-32b273345276 | note | RECORD OF CONFORMITY: ITP Signed
c9094278-773c-5090-b2df-b3817f849cfb | note | WP
5ca45e6d-2492-5184-9d21-2c7e374f4137 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
c7e6f8b3-d376-5ba9-a87f-7df811ca52c6 | textbox | Date Completed:
87dea51d-95b2-4f5a-8665-459fbd07df54 | checkpoint | 2.3 Bedding
e5c963be-6f34-5158-84f0-d9ab53ff3c35 | note | FREQUENCY: Each lot
9e4ec947-3e70-5535-859d-6a6d7d0358a8 | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively. Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used and compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
7d3fb5e0-ff75-5921-b27b-0e90e6d7c219 | note | REFERENCE DOCUMENTS: 703.21
6ee44ef9-dfda-57d6-9413-f247d2ee86ac | note | INSPECTION/TEST METHOD: Visual inspection
46c7375c-4590-5b54-b9ae-4cab4629ef03 | note | RECORD OF CONFORMITY: ITP Signed
21398f6f-d270-5488-a3da-fb58daecfefc | note | WP
0020ac23-6cdd-5a4f-b781-6b912312a6d7 | note | RESPONSIBILITY: Site Engineer/ Superintendent
639dd03d-4025-530d-9f8d-eab9b92d5adf | textbox | Date Completed:
61704177-273e-4cd8-a4cf-17c3940f907a | checkpoint | 2.4 Pre-concrete check
1d5b4a15-8734-58da-ac3e-60dcf45240d3 | note | FREQUENCY: Each lot
e0be20cd-dbfd-5235-af33-0ed7e0c050ac | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
8e7c129d-7439-52b5-82ad-e16c91656a35 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
76308b48-b8ad-5e2e-bfa8-1c97cc1c85ed | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
e9f2f7f8-96cb-5664-9ab5-50b3dab21af0 | note | ○ Concrete to have a minimum of 320kg cementitous mateiral or geopolymer binder per cubic metre of concrete
0885e279-03e8-557b-a8eb-d149a4898d66 | note | REFERENCE DOCUMENTS: 703.08, 610.17(a)(b)(c)
5a9945dd-aa03-5258-9efc-dfa34ccfef19 | note | INSPECTION/TEST METHOD: Verify
2d76f2e3-8dff-511b-9701-bc366f26dabf | note | RECORD OF CONFORMITY:
595405a2-84cc-5b44-af4d-2018c1e6ffdd | textbox | ITP Signed Ambient Temperature |  |  | °C
3e119270-85a1-5e0d-8fd1-050a6e0d0b97 | textbox | Concrete Temperature |  |  | °C
5b995387-51fe-5abd-939c-fa868eb87f4c | note | HP*/WP
77059459-c529-517b-9f57-a4e7c48006ac | note | RESPONSIBILITY: Site Engineer/ Superintendent
02996a0e-cd38-5096-9fa1-35f69b7b4fdc | textbox | Date Completed:
4612e0c6-a106-4556-8189-7ff47f15bb16 | checkpoint | 2.5 Concrete Placement
faeed2a9-bf71-52b7-a4c8-27ddedce38f2 | note | FREQUENCY: Each lot
636dd720-20ee-509b-8363-643d92ee7390 | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
bcdc7519-b014-5b17-8080-4d8521c67cc6 | note | REFERENCE DOCUMENTS: VicRoads Spec 703.23
fb069faa-4766-5906-9354-8f8140973a3f | note | INSPECTION/TEST METHOD: Site Inspection
e719c46b-6ec9-57c5-a37c-0fea794e62af | note | RECORD OF CONFORMITY: ITP Signed
89cd488f-aa86-53e8-a81e-43723e13bdd8 | note | IP
077d777b-598c-50d6-8b01-467736eb515d | note | RESPONSIBILITY: Site Engineer
dd1b091d-d0f8-5098-95bb-520c914f1aaf | textbox | Date Completed:
59456646-c0a0-4430-abff-c0e472fbdf76 | checkpoint | 2.6 Finish Surfaces
c137bc56-d93d-5df2-84fd-1939472ad895 | note | FREQUENCY: Each Lot
62b68b64-ebee-5b31-9dc0-aae15bb5db8b | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished. Concrete to have a neat appearance and uniform colour.
7fcffc46-1e33-5abb-a05a-87718d0c72d5 | note | REFERENCE DOCUMENTS: 703.25
9c8d5d9f-9a6d-54d8-ae99-b8f22d9bfde3 | note | INSPECTION/TEST METHOD: Visual inspection
550b09eb-c259-5b6d-ae8e-10da032a5b1a | note | RECORD OF CONFORMITY: ITP Signed
3c7377c4-be8f-5cb8-97a3-859ad2933278 | note | IP
bec22a57-cfbb-5ac4-af9f-303492fd0f30 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
45133058-802e-552e-8435-1690e094bdc1 | textbox | Date Completed:
eb1142eb-845e-46b5-a9ea-84e5b0298696 | checkpoint | 2.7 Tolerances
8de4ea2b-bed5-5e5f-bd7b-f5ccc323a31a | note | FREQUENCY: Each Lot
7b60952f-22e6-5b38-b7f6-cce5e13613fd | note | ACCEPTANCE CRITERIA: Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of ‑0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
ae071fea-1759-53ba-9a79-d093e5838b04 | note | REFERENCE DOCUMENTS: 703.15(b)
89157bd4-1b53-52b5-b358-bb148720b4e3 | note | INSPECTION/TEST METHOD: Verify
b187a6db-27f6-58da-a785-a3a186df439e | note | RECORD OF CONFORMITY: ITP Signed
1a38b19d-1ebc-5218-9a46-6c22c02b82df | note | SCP
ebf72465-815c-52fc-8934-ec0b9677d9ed | note | RESPONSIBILITY: Site Engineer/ Surveyor
1939af79-07c4-5c4f-86a7-ccb9418c775a | textbox | Date Completed:
ac542621-f16f-4c93-942f-a23c96ebe307 | checkpoint | 2.8 Joints
f617751e-992c-5eb9-9e0e-f5dc178ee445 | note | FREQUENCY: Each joint
4e6bc3f9-f575-52a8-95d4-9eba983f3d72 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
05a21a97-87a4-5261-9574-ee5d5d2b350d | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
56e3bb0c-3ccb-5cb1-bb65-d8aebc312c64 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
c9655a7d-28ba-5e3d-8ec7-0171588d70cb | note | REFERENCE DOCUMENTS: 703.26
2eeae56c-b384-5a25-948c-512b918ac751 | note | INSPECTION/TEST METHOD: Verify
47a70c60-4c0e-5ca6-8371-387be0861bb9 | note | RECORD OF CONFORMITY: ITP Signed
a2d74fe4-319f-588e-a0da-f88b235a801f | note | IP
9bb77b61-dc28-5244-8d2d-a74c4238ff8b | note | RESPONSIBILITY: Site Engineer/ Site Foreman
60a98fc9-88d2-54bb-ad4d-5f3ee4ba8a4e | textbox | Date Completed:
f0e27e7d-b62c-444b-9af4-ec5eec397beb | checkpoint | 2.9 Backfilling
34e35883-520a-51ef-814b-ff20657480f1 | note | FREQUENCY: Each Lot
09374740-3240-5a94-9960-6decde332c2f | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified. Layers shall not exceed 150mm compacted depth.
7b81b30f-44e3-5f8d-81d0-dcfc4d8d065e | note | REFERENCE DOCUMENTS: 703.29
6baa1123-d2ac-58f1-aa70-65bbba6a365b | note | INSPECTION/TEST METHOD: Verify
1c6e5a81-566a-5f34-8140-7967540bd15e | note | RECORD OF CONFORMITY: ITP Signed
867b4219-eae3-5e2a-8ad8-915c9bae4477 | note | IP
fe0c64a3-478d-5914-a04a-d1ab974491f6 | note | RESPONSIBILITY: Site Engineer
bab41f66-d353-56ee-baf3-41a50f2df0b2 | textbox | Date Completed:
cd5b9f7a-562e-4de4-bdfe-836859943dca | section | Completion
9e9ff5dc-8b35-400d-8cd4-8889a99659f0 | checkpoint | 3.1 Survey data captured for as-built purposes
ed371d1c-900a-5168-95e6-9a89aa4371b7 | note | FREQUENCY: Completion of each lot
46c1d470-cb7a-5705-bb33-a7ac0a3d870f | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
335ffa09-d5be-5f3b-985c-4076da1f36b9 | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
33684f1b-048b-5968-a5f1-07118386568c | note | INSPECTION/TEST METHOD: Document review
f031ada3-9410-54d6-bf43-b0da98a2fb30 | note | RECORD OF CONFORMITY: As-built survey records
22d20368-459c-563e-abff-16cfdd15e1c3 | note | SCP
68ba27d9-2777-598c-97e9-1ed3caca6a7f | note | RESPONSIBILITY: Project Engineer/ Surveyor
5d6bdb1f-dd2c-54dd-8d7c-e5e431166c5d | textbox | Date Completed:
bd4b2870-2937-4200-873f-b12c8961e106 | checkpoint | Final Inspection
97ea7d03-b228-5451-84d8-9d727330d157 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
41144efd-e53b-5a2a-be94-78d2f19815d1 | textbox | Print Name:
794e7cb9-fb0e-546f-a61a-5d2ca1e842ae | textbox | Position:
44442dd8-4cad-5230-b7a0-90f6f41c9bff | textbox | Date:
b5b8193c-f6b3-4179-a277-03ce9a5b60ed | checklist | ITP-019 - Line Marking | itp | ITP-019 - Line Marking
7c150c02-2124-429d-aa56-4b0171f9f8b1 | section | Preliminary Works
655296a5-aa00-4189-9a8d-a00209c1e088 | checkpoint | 1.1 Check for correct documentation
fac2855d-533c-572d-8e2e-ef0609e2431c | note | FREQUENCY: Prior to commencing any activity
488ed517-2a31-52ba-a307-2d32bff0f197 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
3835bcb9-82d2-5944-876a-af18c9e180ee | note | – using the correct and complete set of drawings
a99a7807-9082-5566-bc5a-a03f0b9848b2 | note | – all drawings are the latest revision
5dcc757d-3942-59bd-950a-ad134a643f5a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
ab155186-d588-50cc-a43e-21047237b9f7 | note | INSPECTION/TEST METHOD: Visual inspection
2b505d29-8b8f-5170-902d-f8f0e11f89df | note | RECORD OF CONFORMITY: This ITP signed off
f6b90015-f7d9-5287-b20f-b6522208f9dd | note | WP
be67f40f-6c18-5229-8f69-451bc6fc3631 | note | RESPONSIBILITY: Fulton Hogan Engineer
bdd8abbd-90a2-51e3-9812-5b8197208702 | textbox | Date Completed:
8637647e-aa04-4808-99ff-5f2339a94825 | checkpoint | 1.2 Implementation of all measures and controls
6c6493b3-5d92-5183-b3a0-e8b89e9ed302 | note | FREQUENCY: Prior to commencing any activity
3d66960e-7107-566c-81e8-486793c7f9fb | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
5343880b-fe01-56d4-824b-5c1632cd7b06 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
13585037-d91d-532c-8777-a0cac3476b9f | note | INSPECTION/TEST METHOD: Visual Inspection
d4626ae5-734e-52e3-ae2c-f3837973d03c | note | RECORD OF CONFORMITY: This ITP signed off
9f065d5c-51d5-5229-8667-ccb4de861a23 | note | WP
ce463da9-b069-5301-9d9f-653fa9f3b3ed | note | RESPONSIBILITY: Fulton Hogan Engineer
86c5249e-ad1d-58c5-a280-db303679335e | textbox | Date Completed:
35163879-7265-4ddf-8b35-c677d218e1e9 | section | Construction Works
5a0d2bfe-68b0-4647-94b3-b6479ecfc528 | checkpoint | 2.1 Setting Out
34564662-8bde-56b5-941d-e1e8925b8aa5 | note | FREQUENCY: Prior to start
09079431-7e35-5cc7-a406-23c6ab7010fa | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
445e47bb-5749-5141-b8a8-4326d0bc2160 | note | REFERENCE DOCUMENTS: Drawings
b83c8970-9268-51a3-8682-3bc82b1b0184 | note | INSPECTION/TEST METHOD: Visual Inspection
5de451f3-ad6f-5f65-a967-52733f217f8d | note | RECORD OF CONFORMITY: This ITP signed off
b26d2d0c-eec1-5043-97fe-2756ed60345f | note | IP
247473ae-3a58-51b7-b8eb-24dd34f2afd1 | note | RESPONSIBILITY: Fulton Hogan Engineer
4d90405c-ba34-5b3b-a47a-51cfa6042611 | textbox | Date Completed:
84f6cf81-fdb8-4dae-81fb-f5e68260f9f5 | checkpoint | 2.2 Position of Markings
a9fd487d-546e-58c1-8541-e20fa5f522c2 | note | FREQUENCY: Prior to application
39c22318-7e9b-5846-807d-4a6c7653e4e2 | note | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted. Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2
713d4739-afab-5498-b34e-bed25e10e147 | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2 Drawings
d35a105d-9204-53ae-b57e-1ec9ccf05b5f | note | INSPECTION/TEST METHOD: Visual inspection
fdada2aa-185d-5f5d-9560-e7a91bdfa1e3 | note | RECORD OF CONFORMITY: This ITP signed off
a31f0d9b-5481-5e4e-a38e-ad4f34912996 | note | HP
64939f6a-1689-5614-8dec-5db81ec228c9 | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
febc767c-18a0-5feb-b1c0-08fcbc05d00c | textbox | Date Completed:
ba4ad423-fbb0-472f-9a20-3b601cfff43c | signoff | AUTHORITY HOLDPOINT
aa1c34f3-5f31-4bf1-8531-4f96e4260108 | checkpoint | 2.3 Materials
3133bd19-3932-5f97-88a4-d2322865cc7d | note | FREQUENCY: Prior to commencement
ed861a99-15c9-5193-b234-22cdd48c5584 | note | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent‑borne paint or AS/NZS 4049.3 for water‑borne paint as listed in Section 175.
91e47657-88e5-5995-b3e1-1f2be2f0ee8d | note | REFERENCE DOCUMENTS: 712.A04(c)
37e507c1-9d04-547a-a87a-fe454fea775f | note | INSPECTION/TEST METHOD: Visual inspection
6c7d1d76-daed-5be0-a3fa-b5a4e757061b | note | RECORD OF CONFORMITY: This ITP signed off
32a80a6d-2f72-534f-a60f-043cd1adc61b | note | HP*
f3c0ddad-affe-558d-b715-a9c72ca72e15 | note | RESPONSIBILITY: Fulton Hogan Engineer
9bb0f4af-c262-58c7-8211-67413736c71a | textbox | Date Completed:
98555310-258d-47e9-9cdc-374b120dddb0 | checkpoint | 2.4 General Markings
23adffb1-1e77-56f5-9f96-168ea7af2d77 | note | FREQUENCY: Prior to commencement
47f58d12-e1ac-5d6e-8334-b50dfcca499a | note | ACCEPTANCE CRITERIA: Linemarking shall be applied by a self propelled machine, and stencils shall be used with all roadmarking. All work must be undertaken by a contractor eligible for accreditation under the Painting Contractors Certification Programme (PCCP). This programme is administered by the CSIRO.
a41fec25-2cf5-5c6a-8ed6-cdd3bfd672fa | note | REFERENCE DOCUMENTS: 712.D01(c)
08089368-71aa-534d-a302-ae49480a61d5 | note | INSPECTION/TEST METHOD: Visual inspection
d72de609-77b0-557e-ad63-1fa42ba5c0ad | note | RECORD OF CONFORMITY: This ITP signed off
844b6925-c17f-5f4c-87f9-adb50548ffdb | note | HP*
dcfa5cd9-865c-5e7d-8032-b9d0bb82ea61 | note | RESPONSIBILITY: Fulton Hogan Engineer
7c988cd9-f05c-557c-b61c-722619a29a65 | textbox | Date Completed:
0c540734-19ad-47a6-922b-96cb29db7a8d | section | Completion
37b7214f-96ae-4a4c-84bd-b3a2d1fedc58 | checkpoint | 3.1 Tolerances
555e1c73-1327-568c-b67f-486896066240 | note | FREQUENCY: Each marking
0d58fb94-2cc7-5200-819f-076fb58e9165 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances as shown in Table 721.A101 when installing pavement markings.
83d28d9d-9feb-5387-b5b6-accd67ff4aba | note | (i) Distance between centreline of marking and set out marks <30mm
f41398b9-7d82-59c9-a070-28e3f82ae85c | note | (ii) Width of completed paint markings <15mm
2cfd060a-d4a9-5165-96d7-9bd827fcaf9a | note | (iii) Length of completed stripes and blocks 0 to +10% of specified length
e1b35787-5a60-55f2-9983-0f4a4e0008db | note | REFERENCE DOCUMENTS: Table 712.A101
70e4284a-c30b-559d-94f0-6af24204fef5 | note | INSPECTION/TEST METHOD: Verify
20e15a39-cdc1-53f0-a1d0-8dcdd40baa14 | note | RECORD OF CONFORMITY: This ITP signed off
2d71b646-8770-5d91-a90e-6649d8754af8 | note | HP*
379ca049-6d91-5efe-8aa7-3f3f4983ac0f | note | RESPONSIBILITY: Fulton Hogan Engineer
bfa132e5-bfb1-5322-b548-65420406b954 | textbox | Date Completed:
3b4b3077-9fc8-49e6-aff1-79cba1338161 | checkpoint | 3.2 As-Built
ae3f2ce0-541d-51d5-b3f3-3ab760a3a7e4 | note | FREQUENCY: Post Completion
ea70fa87-3734-5ba8-8012-f19b2afceb81 | note | ACCEPTANCE CRITERIA: As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
dc79d1b4-20c9-58ed-bb5f-8fed8ea10075 | note | REFERENCE DOCUMENTS: IFC Drawings Survey Records
bd959149-f5d2-560b-9c62-9cb426f867d5 | note | INSPECTION/TEST METHOD: Document Review
533e6296-5818-549c-9037-dbe6a8da1ccd | note | RECORD OF CONFORMITY: This ITP signed off
3a5e55ae-4ad7-531e-b4e2-421831eac4ef | note | SCP
806f9b0b-8695-572e-a9a6-8b256efe71b1 | note | RESPONSIBILITY: Project Engineer/Surveyor
1b94357f-22ef-5cc9-89a8-ec37e649bccb | textbox | Date Completed:
5b40840e-b512-4b5a-bc26-5c79507f2f0c | checkpoint | Final Inspection
abfab156-44e0-5c56-a3be-2d307ed4d9db | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4fbbff58-3ba2-5581-9e64-e6e66e8c45b2 | textbox | Print Name:
7e9f873c-b73c-5423-b5b9-7ec5c2a555e1 | textbox | Position:
3c3e0f88-b9a2-5570-9fb2-0ba97173e589 | textbox | Date:
1c5f0e1a-2423-4e75-a713-11f29e9e4bed | checklist | ITP-027 - Pile Footing Construction | itp | ITP-027 - Pile Footing Construction
904a65d5-d7d1-4cb5-997a-9606851c1b26 | section | Design and Submissions
ad7e1be6-6018-4156-84e1-db33fd9d8cf3 | checkpoint | 1.1 Check for correct documentation
46da5412-0165-5316-ab35-87cf5616984b | note | FREQUENCY: Prior to commencing any activity
70faa10e-2f35-51fa-982b-5207b80a8d13 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
bfbc55ec-7b31-5ab2-8b06-e93d0ac8745d | note | – using the correct and complete set of drawings
9eb93418-d680-59a7-b643-4633b0d72310 | note | – all drawings are the latest revision
88b558b5-1a5e-53ad-b5a4-c11c3e667087 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
ad9c54a5-d975-5077-a9f2-fce3257dcd5d | note | INSPECTION/TEST METHOD: Visual inspection
0443cd1d-bf31-51c1-bb24-8ba6701bd517 | note | RECORD OF CONFORMITY: This ITP signed
67aece82-2572-5425-af34-85b96230fe8e | note | HP*
f7c211ed-728f-5ee5-a4cc-81b5c59edfb7 | note | RESPONSIBILITY: Fulton Hogan Engineer
8fdea59d-19a1-5004-935f-5cbfe8aaac88 | textbox | Date Completed:
dd51c28c-ba10-474a-9ddd-c728a6a64f5a | checkpoint | 1.2 Implementation of all measures and controls
90b60d03-fc97-5309-96cf-6c3f9a9c7eed | note | FREQUENCY: Prior to commencing any activity
194d6b23-5122-5c17-ab38-a3bf83db91a9 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
dcec46b4-f6c9-5504-b181-f070c8b35da1 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
4b7b4fcd-12c7-55fa-b0ad-0cb3321530ce | note | INSPECTION/TEST METHOD: Visual Inspection
4b24dac5-76a8-5710-ad21-42c55cd4bcc0 | note | RECORD OF CONFORMITY: This ITP signed
c8a269ba-c651-51b2-a396-79720760d959 | note | HP*
417f2ed7-e064-5769-9430-e11e3dce4086 | note | RESPONSIBILITY: Fulton Hogan Engineer
39f35e6a-9f30-5ce3-93e9-7b955a1942ef | textbox | Date Completed:
35f42831-ca82-4040-ba6e-a7f7b972fcae | checkpoint | 1.3 Approval of mix design
23851e04-4e60-5c18-a258-35db42834143 | note | FREQUENCY: Prior to the first concrete pour
860e5e03-2f9f-5e69-adc4-71d88d25a906 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
9d20dd4f-ffea-5cfd-a607-d229f0497621 | note | REFERENCE DOCUMENTS: 610.07
4ed42fa3-6661-5349-b0e5-c9c3c84fac98 | note | INSPECTION/TEST METHOD: Verify
422a5a02-9342-5b6c-be5b-190e9012c0ab | note | RECORD OF CONFORMITY: This ITP signed
d07b2b21-e2be-56bc-83a5-af16b7f3624f | note | IP
9d65a06d-4eb5-5097-8ab0-7ab3266c99cf | note | RESPONSIBILITY: Fulton Hogan Engineer
acfc1531-f749-53f8-b08a-158fd31558e0 | textbox | Date Completed:
52494699-310c-4115-924f-72db5c29b20d | checkpoint | 1.4 Reinforcement schedule
6f844378-0932-53d2-b41a-2f3308e4c8f8 | note | FREQUENCY: Prior to concrete pour
6357e51a-7532-54ab-a417-f57dd6e8e677 | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
eb6e8d95-1021-5be5-8405-52eb6fd7cebc | note | REFERENCE DOCUMENTS: 611.04
0c6d8304-c3db-5db8-b41e-381c3e2b897b | note | INSPECTION/TEST METHOD: Verify
99de8e6e-078c-511a-9583-50abb8b12f80 | note | RECORD OF CONFORMITY: This ITP signed
7e8e3cd8-2bcc-5e11-8a06-c861230604f4 | note | IP
4b74f238-feec-54a2-9a92-5bd82c491b17 | note | RESPONSIBILITY: Fulton Hogan Engineer
78a1aa05-dbb8-55fe-bc4f-8492248999ce | textbox | Date Completed:
5883f6c7-11b9-4334-b6d0-5ed861a2b221 | section | Construction/Erection of Formwork
9f6812f5-4cdf-4665-a374-3e9570597154 | checkpoint | 2.1 Excavation (Pile)
8b4d39dd-a43c-545c-baa5-519ade66200f | note | FREQUENCY: Prior to concrete pour
856391cd-3d19-53ad-81df-3ee36f415c93 | note | ACCEPTANCE CRITERIA: The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent. Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
cc1d8722-0cde-5cea-99b3-122dabf67be7 | note | REFERENCE DOCUMENTS: 606.05
64ca6402-0a61-5b5e-bfe0-b85e4176d4de | note | INSPECTION/TEST METHOD: Inspect
8ce6cac8-3f9d-5ee9-88f0-ebab4bbe6905 | note | RECORD OF CONFORMITY: This ITP signed
9f6289e4-4b15-547f-b901-6db75e6a6ce7 | note | HP
59ff41a7-5eb5-5e1f-88e3-1511303aa2f2 | note | RESPONSIBILITY: Fulton Hogan Engineer / Suprintendant
2c5422af-fe78-5192-a8b1-77f9e1a39cb6 | textbox | Date Completed:
0ed24225-804f-43b6-97d1-5f820b82c676 | signoff | AUTHORITY HOLDPOINT
0dbf765e-2eae-4c74-8ee2-0aec5f958ead | checkpoint | 2.2 Construction Methodology
f28214cb-6209-5cec-a621-bf6b53189384 | note | FREQUENCY: Prior to erection
dc53d3e7-0c5d-5c72-b706-9bf92e4d56f4 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
9dea4250-c29a-5460-a4f6-c4813b8e560f | note | REFERENCE DOCUMENTS: 614.04, 614.06
dfe60341-84f3-578e-b7b0-2c6019f82587 | note | INSPECTION/TEST METHOD: Verify
3886f4eb-9578-5619-9dd4-51bd9f16dabc | note | RECORD OF CONFORMITY: This ITP signed
1e257eda-370b-53a1-91cc-875ee3f3e782 | note | IP
d1be8421-faaf-5f9d-934b-2f5b3c9abc18 | note | RESPONSIBILITY: Fulton Hogan Engineer
5909244a-9b1c-597d-b992-f03bdc3b31ff | textbox | Date Completed:
be6ea42d-e04d-4e1b-9b9d-01bcb692b08c | checkpoint | 2.3 Construction Methodology (Pile)
ee0cb84b-f758-5291-ba03-874a6af3fd7e | note | FREQUENCY: Prior to construction
26d55826-9352-5bee-b31e-d0957430f1f6 | note | ACCEPTANCE CRITERIA: Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
28542715-4ceb-5b46-bd75-5c8e9cecf955 | note | ○ Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
73bfd47d-062a-5a6f-ba25-a06298b011c6 | note | REFERENCE DOCUMENTS: 611.10, 606.06
ae88e64a-c671-5f01-a1dd-ee176cb68a15 | note | INSPECTION/TEST METHOD: Verify
fa2ccda2-1b5b-537e-9bb4-0056412be1fb | note | RECORD OF CONFORMITY: This ITP signed
9177bd92-cd31-5bf4-b40a-6f1601038d04 | note | IP
b20abbb7-ff1f-5be2-ae91-91d363b49ed2 | note | RESPONSIBILITY: Fulton Hogan Engineer
618ceace-38ac-5284-84d4-bbd15f3ebcab | textbox | Date Completed:
313fd502-becf-4853-942d-f770264b0a89 | section | Pre-Pour Planning and Inspection
427f1ca3-3bd2-4732-93c7-7404b0bfc1df | checkpoint | 3.1 Cleaning formwork
2871d925-dd33-548f-9128-2d971ed9c53d | note | FREQUENCY: Each concrete pour
35727862-d37d-54d0-8315-e2ffc89c45ec | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
8a91945e-f069-5769-88c8-d90d797456ee | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
59303f27-5589-5c06-8bd3-315292ff2371 | note | INSPECTION/TEST METHOD: Verify
c6bca09e-bb53-5652-a98b-12e78eefa1c1 | note | RECORD OF CONFORMITY: This ITP signed
1129d941-a026-56fa-b723-f5bb2d8d8152 | note | IP
b487273f-ef8d-5e71-9c0d-90834ae0f467 | note | RESPONSIBILITY: Fulton Hogan
7db5f25d-374a-5a77-b6de-00532214df54 | textbox | Date Completed:
57f8fc9f-e7ad-4077-b65b-009a03f58c54 | checkpoint | 3.2 Correct forms, reinforcements, rag bolt assembly and embedments
64e3421c-5a0e-574a-82ab-f7a9c88ca96d | note | FREQUENCY: Prior to concrete pour
733a4fd7-dd85-5bfb-892b-b76f7cfe09ea | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. Pre-pour checklist completed and signed.
35e593f1-6816-571a-8506-8660dda630de | note | REFERENCE DOCUMENTS: 610.18 (a)
af8f9033-b83c-553c-86aa-fc5e23b7afc6 | note | INSPECTION/TEST METHOD: Verify
5b54e23d-4c8c-595d-9bb2-b45b70732fb2 | note | RECORD OF CONFORMITY: This ITP signed & Pre- Pour checklist completed
f4603ec4-0726-5999-a728-05cd6cc75a67 | note | HP
0e3f5f47-1796-5cc8-952b-01be4e87c16c | note | RESPONSIBILITY: Fulton Hogan / Superintendent
c3572acb-d610-52ba-8f7c-1f86e53a33dd | textbox | Date Completed:
036d8d58-cfa4-4d3d-bac7-c5f4b314581d | signoff | AUTHORITY HOLDPOINT
2a366e14-762d-4aa7-a3ee-df059bed8b43 | checkpoint | 3.3 Reinforcement assembly of piles
2302a521-5019-5cba-8820-43c2578d95b0 | note | FREQUENCY: Prior to concrete pour
e3c641d4-a6cf-5037-9987-1f1897bfdf02 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
4cec31db-eca3-5d29-bc64-bec92512b4a8 | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
d67ce520-dc86-522c-a84d-c774e3949f13 | note | INSPECTION/TEST METHOD: Verify
bde707a6-99ef-5f1b-aa80-3717defeaff3 | note | RECORD OF CONFORMITY: This ITP signed
89bd741c-ff93-55a5-9056-aa369213b4d5 | note | HP
dcaeb3ee-adb6-5325-befa-56f56f1ef37b | note | RESPONSIBILITY: Fulton Hogan
d69e249a-57c7-5f49-87c9-b8d935e2ab5c | textbox | Date Completed:
bc1838ea-f69a-467f-bf64-5300a222154e | signoff | AUTHORITY HOLDPOINT
801e8d07-4e55-4036-8f36-45084c4d1416 | checkpoint | 3.4 Monitoring weather
42c00daf-f33f-564e-80c9-8025c97c9b90 | note | FREQUENCY: Prior to concrete pour
6a6982e8-f763-5a70-a482-b0ac61584bc7 | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
2c2202cc-16d1-573c-aa7d-696e796eb830 | note | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
9f458a9b-34f7-51ad-9735-a7931369a10c | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
6ef38094-09cb-5ca4-a24d-b4caa66cc042 | note | INSPECTION/TEST METHOD: Verify
175efbf8-663a-590a-b6ea-f0b0c7a33346 | note | RECORD OF CONFORMITY: This ITP signed
29b78711-be22-509e-93fe-3bb9543c10f0 | note | IP
ccbf8dd8-b778-5f86-91fc-e8388d8503ad | note | RESPONSIBILITY: Fulton Hogan
18470c0c-6770-5a18-aaab-47cd4b3fa068 | textbox | Date Completed:
70738d07-3f37-4854-8601-fec6dae99da9 | section | Placing and Finishing Concrete
d1a3c7e2-6ff3-4cf5-8060-5f466aa614eb | checkpoint | 4.1 Carry out sampling of concrete
4bf5993b-ede7-55e3-bf79-39b82ef3b27c | note | FREQUENCY: Each concrete pour
58492712-5d1f-5936-a44b-f09ebc481d1b | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
578544a4-9cc5-5f7e-8b22-f9d437f070ca | note | REFERENCE DOCUMENTS: 610.16
4d66bf9c-1716-5eee-9794-b99238fcb0aa | note | INSPECTION/TEST METHOD: Checklist
18ff6223-72c4-5f55-8fb9-84d47e09efcc | note | RECORD OF CONFORMITY: This ITP signed
70897684-4599-53c0-b4dc-d45675aaa040 | note | IP
6871a8a5-4b2f-59ca-ac00-99d731cc78e7 | note | RESPONSIBILITY: Fulton Hogan
9f1d99fc-eee6-5045-ab9f-6385b0ca714e | textbox | Date Completed:
09c9e1cd-564f-4ca3-9a93-7deaf73e1dfc | checkpoint | 4.2 Discharge time
b1eb5ba1-2913-53ba-a0c0-e40326861dbd | note | FREQUENCY: Each concrete pour
d0537738-1250-56dd-b5b0-127aeb95f5c7 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. Batch to be used has a discharge time of 180 minutes.
20cbed04-f612-5c89-ab9e-85430f4f05f5 | note | REFERENCE DOCUMENTS: 610.13
bd67bc1e-5604-542b-bd3c-b4f675651d08 | note | INSPECTION/TEST METHOD: Verify
ebb61ec3-a618-53c1-95d6-ac8140650f99 | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
b1c35ab1-f50b-5497-bb68-795b66701e52 | note | IP
a375c2ba-e197-51cf-b155-d4ec59dabc8b | note | RESPONSIBILITY: Fulton Hogan
4b3c0f0c-b266-5906-a142-d52534e60bf5 | textbox | Date Completed:
eb338bee-483f-474e-a88f-3629a51acc43 | checkpoint | 4.3 Methodology of placement (structural)
0d80b58f-c7e0-5a38-8be6-ab2f7b7e6d3f | note | FREQUENCY: Each concrete pour
4880c40b-fb69-5d48-af16-767dac53b101 | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials In continuous pours the max. time lag between truckloads on site is 25 minutes
0aef508e-7831-5079-b7bc-7ce708a022b5 | note | REFERENCE DOCUMENTS: 610.18
ed4abdc2-4786-554b-9877-65967ee6a5b2 | note | INSPECTION/TEST METHOD: Verify
392522c9-8763-5594-9c03-d5f1cf896722 | note | RECORD OF CONFORMITY: This ITP signed
54d9201a-1f76-51ed-af90-e9a1c86f1a9e | note | IP
b288299f-fea1-5c6e-9401-a0c4ba8b39ae | note | RESPONSIBILITY: Fulton Hogan
702e2179-b258-52a1-ba02-318d79d5239d | textbox | Date Completed:
196ddf55-434f-4564-9ecc-cda027a6cfc4 | checkpoint | 4.4 Methodology of placement (piles)
5c7a9db1-97ea-570f-8be6-b1c565d8f173 | note | FREQUENCY: Each concrete pour
1c616621-7ce9-5413-a584-fae0a1c08648 | note | ACCEPTANCE CRITERIA: Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation. Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
b77c7d81-fbcc-55ea-befa-6a1ab4520f2f | note | REFERENCE DOCUMENTS: 606.03(b), 606.05
d5c2352f-b7c7-5e26-9273-cc59af71e764 | note | INSPECTION/TEST METHOD: Verify
ccf13d7a-fbee-5028-802b-38761a4943d4 | note | RECORD OF CONFORMITY: This ITP signed
d30cfdfe-0979-52e5-a8d5-8a9a5c82b928 | note | IP
a650743d-da23-5774-a254-ab7b1377ab7d | note | RESPONSIBILITY: Fulton Hogan
1508445f-3ab2-5460-bea4-117da678bb32 | textbox | Date Completed:
e046c4e1-38d2-4c38-8ae4-18a8c354fe2e | section | Post-Pour Details and Inspection
2c17ecf8-0c70-4527-a04b-2cb75d5117d2 | checkpoint | 5.1 Curing
a14974fe-5bc7-549e-b8d7-731bae2c2360 | note | FREQUENCY: Each concrete pour
95196da2-1eb4-5219-8c4e-1affb107be92 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
cbbd176a-ced0-5a87-bf39-5994b66b720f | note | REFERENCE DOCUMENTS: 610.23
bc643553-5274-502e-8ae4-4a919d1e8457 | note | INSPECTION/TEST METHOD: Verify
040bcd40-6a86-563f-be53-f131cbe2adf8 | note | RECORD OF CONFORMITY: This ITP signed
f88647ab-bf96-59da-b1b0-e4df3a5f2f6c | note | IP
b2274bf3-c60d-5b90-8109-1f6b83ec26e8 | note | RESPONSIBILITY: Fulton Hogan
6228a067-94e1-5811-be0b-0a870440a07c | textbox | Date Completed:
6c83844b-ef1a-4f66-8d2b-84526ba08f70 | checkpoint | 5.2 Formwork removal
8eda6d4a-5fa9-5185-80be-281fde9d02e7 | note | FREQUENCY: Each concrete pour
d51f89bb-e9ec-5671-bed6-c3f5fadaa4e2 | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
15908552-8159-5512-b0e2-dfa4c64bdc29 | note | REFERENCE DOCUMENTS: 610.25
e1ff3e2d-d1b7-5268-a138-8c24f0b000e8 | note | INSPECTION/TEST METHOD: Verify
aa591358-f3fe-51b2-8295-651811e50fae | note | RECORD OF CONFORMITY: This ITP signed
4d5d7d25-520c-5607-84db-45756639b31f | note | IP
f40d2fd6-7df2-5fe8-a5c4-73e4a8a69c65 | note | RESPONSIBILITY: Fulton Hogan
ebc37e66-11ef-581d-90b7-f7f6fe1af2c2 | textbox | Date Completed:
6208544d-7685-4b03-917f-5cd2a790dba7 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
93055546-14d5-5248-abb3-be0d1837ce9a | note | FREQUENCY: Each concrete pour
352ab905-cbe4-5150-ab12-38ff2703aee6 | note | ACCEPTANCE CRITERIA: The centre of the pile head shall be in the specified plan position ±75 mm;
d5e6dd9e-279f-52a5-b0e8-d9e3d2667c2e | note | REFERENCE DOCUMENTS: 607.06
eb9dde91-6952-59d1-8c37-f3107485b0cf | note | INSPECTION/TEST METHOD: Verify
e3540ced-a78b-5795-9e7e-6980a715c804 | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
3b0d5ffb-5319-52b6-8005-036ad702180d | note | IP
bfc7982d-9ace-59cd-90a9-989f5758ec39 | note | RESPONSIBILITY: Fulton Hogan
e7a5d0f3-d20e-5687-af1b-57b2959edd79 | textbox | Date Completed:
7df18757-b9b9-4af1-828f-71035f5af262 | checkpoint | 5.4 Concrete Sampling and Testing
afb7d76d-35a4-5f1d-85e0-54caa583d499 | note | FREQUENCY: Prior to lot closure
d00cf94d-19e8-5a81-b4f2-78a9def8ec0b | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength:
a840d739-97e3-5c01-b227-3cb3d81820c3 | note | ○ 2 cylinders @ 28 days Compressive Strength=32MPa
842207b9-d1ff-5fd5-a376-c78d295fea9a | note | ○ 1 cylinders @ 7 days for Compressive Strength=20MPa
08dcdb69-16f7-56ea-8737-ae960efd810b | note | REFERENCE DOCUMENTS: 610.05, 610.06, 610.13, 610.16
204a26a6-0993-5b68-bbbd-9fcff9bf6e75 | note | INSPECTION/TEST METHOD: Verify
44c43222-9540-5853-a1a5-94beef7694d3 | note | RECORD OF CONFORMITY: This ITP signed
a6a6467a-5c33-54f0-b8de-82322ed00b2d | note | TP
c0039d95-87c5-515e-b515-4e8259c5b9b5 | note | RESPONSIBILITY: Fulton Hogan
1d836a48-55aa-5f5a-9843-e78983a15371 | textbox | Date Completed:
ef2da256-e19b-4718-a91b-7f0bb4918102 | checkpoint | 5.5 Protection of Adjacent Piles
da9b33b3-a965-51fb-9b17-5cadbed5525a | note | FREQUENCY: Prior to commencing any piling
cdca2218-3d57-5f88-9b34-b8f882a13712 | note | ACCEPTANCE CRITERIA: No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
22a0fe00-980e-58d9-af29-fce7c9a72118 | note | ○ Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
d1d47aa9-b7d6-53d9-a5a3-3bfd9374b2ad | note | REFERENCE DOCUMENTS: 606.04(a), 606.04(c)
b880fb66-de6b-53cc-b1ce-4b67bc9350a4 | note | INSPECTION/TEST METHOD: Verify
ff5cf9d7-c802-51e5-b3bd-2c95290db0bf | note | RECORD OF CONFORMITY: This ITP signed
caccf905-3d62-55fb-aef2-cda5b48caf00 | note | HP*
237c9649-1edc-54e3-bd0a-e2ea58c85cbd | note | RESPONSIBILITY: Fulton Hogan
1414d055-5d7a-57ac-886c-95c9193dc068 | textbox | Date Completed:
a958b664-4c78-4161-bdfc-472a6b6dbb3e | checkpoint | 5.6 Testing Post-Pour
0b6f5948-1db0-5265-b420-b48ff0f00f52 | note | FREQUENCY: Prior to lot closure
fbf138d7-5b4c-5ced-9f2e-b210ab824e72 | note | ACCEPTANCE CRITERIA: Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
225f6061-ac80-5f97-9e57-e38fc8856d8b | note | REFERENCE DOCUMENTS: 606.07
9ae21e52-242e-50b7-bfbf-364e8040c1a5 | note | INSPECTION/TEST METHOD: Verify
18bd72fb-87ee-5c23-b571-3e534a2affa5 | note | RECORD OF CONFORMITY: This ITP signed
2836b98a-a128-5c2c-99b9-a1046582c92e | note | TP
8a661cd2-30bf-54ec-a0eb-c4830bd74ef1 | note | RESPONSIBILITY: Fulton Hogan
a8eba66b-df32-552d-b978-3a2f86912c27 | textbox | Date Completed:
6d0ff4df-0c89-4799-b2f7-1043c6b31702 | checkpoint | 5.7 As Built Drawings
795d68e7-6cb3-580a-9ad5-7f701613eb32 | note | FREQUENCY: Prior to lot closure
18d9f2f0-b678-505c-933d-5a7fce4d3ea7 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
7bc98fd3-1709-5746-bb5b-d14944b8e897 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
e7f997fe-d814-5a69-85d8-10b73e57c724 | note | INSPECTION/TEST METHOD: Verify
cae52ee4-9f63-5fe9-a562-e3b3327d9b37 | note | RECORD OF CONFORMITY: This ITP signed
752d695c-53cd-5203-bc8c-dbc23e77698f | note | IP
ca84ecab-68b2-51a8-bced-c1698a2fbad0 | note | RESPONSIBILITY: Fulton Hogan
90b3e776-05ea-5dfd-85e5-ed78673d8fb8 | textbox | Date Completed:
ff9c024c-535f-425a-aa0c-24269fb8573e | checkpoint | Final Inspection
acbd3646-12db-5ad7-b916-86e1dbf8447e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
6f5f3586-ad8a-5e1a-98b5-b8a320504bc6 | textbox | Print Name:
925ddb8e-3909-5fe6-9b45-d85ee18cf015 | textbox | Position:
c5ab1de6-3f00-539c-bcac-4e2a9b6e7f91 | textbox | Date: