## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
80493ca5-a540-4f9c-8e13-ee20e6f4ddd6 | checklist | FHC-ITP-006 - Class 3 Crushed Rock Rev4 | itp | FHC-ITP-006 - Class 3 Crushed Rock
4ded8d5d-2a1a-48fa-be35-1bdc50b4a3bb | section | Preliminary Works
58e40e42-79ec-4c8f-beb0-0d3646e9747a | checkpoint | 1.1 Check for correct documentation
a627e396-a12f-51ac-b6c0-ea645c35b309 | note | FREQUENCY: Prior to commencing any activity
3fab8659-0ca6-5dba-a091-8d4444157c95 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
c110f68a-6cb0-5dfc-8e58-919b6c1f3991 | note | — Using the correct and complete set of drawings
502fd151-0c3c-51cb-822b-13797a18c53b | note | — All drawings are the latest revision
07e03f78-38f5-5553-838a-a587293b1aea | note | REFERENCE DOCUMENTS: Drawings and drawing registers
a253bf19-1cf9-5df9-b573-8f63815efc95 | note | INSPECTION/TEST METHOD: Visual inspection
d32dd999-eb9c-5609-90fa-0a48c9917946 | note | RECORD OF CONFORMITY: This ITP signed
f328ea84-ee0f-5608-ae52-394c1a1138b7 | note | HP*
f41410c4-db13-5520-8214-7fae355e6b19 | note | RESPONSIBILITY: Site Engineer / Site Foreman
91b3b1db-2b1a-5214-bb73-236c06d50c10 | textbox | Date Completed:
247bf56e-33f7-459e-ab45-eaf5f9469a45 | checkpoint | 1.2 Material Mix Design
bb42efd5-4542-5c72-87b3-cc6e8826a849 | note | FREQUENCY: Prior to commencing any activity
1d7c6db2-edc3-5651-8bda-97cf4745084c | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
5d09ca7c-c26a-5a60-a8bf-d312fc313eac | note | REFERENCE DOCUMENTS: Cl 812.04, RC 500.02
ddc68fa8-a4cd-5c3a-b33d-dbba1ada47ed | note | INSPECTION/TEST METHOD: Document Review
bcf9d1a8-0394-5c1b-aab0-1d55d10728aa | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
c5e8b987-2fa5-5fa7-87a0-8f49d2cbe057 | note | HP*
62aa07ea-6ef8-55ff-bc6a-f984abb5853f | note | RESPONSIBILITY: Site Engineer
cc493d36-03a3-5e93-92a5-50c1a358eb17 | textbox | Date Completed:
00d3334e-4d8d-404c-bad7-f0b35d524814 | checkpoint | 1.3 Material Approval
d7c9832c-ad99-52ab-997d-6ab2245dc5d5 | note | FREQUENCY: Prior to Placement
850f4f7c-6c15-54ef-a8f2-05003177e5a2 | note | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
ceef2993-fa12-57e6-96f6-12868e74252d | note | REFERENCE DOCUMENTS: Material specification sheets
78475307-ed64-52a6-8259-95908f0e26f1 | note | INSPECTION/TEST METHOD: Verfiy
2c34b52e-3e2d-51cd-8fcb-5ee224d7ccec | note | RECORD OF CONFORMITY: Teambinder Acceptance
812a7948-701f-508c-b1ee-07a180e76226 | note | HP*
435aadcb-5e6c-5b3f-8ab2-2b4bd077a9a7 | note | RESPONSIBILITY: Site Engineer
18bc3bf0-9f80-515b-a345-d0717df16b8e | textbox | Date Completed:
210c66dc-f8d3-4bfe-94d9-26a3815ed7cc | checkpoint | 1.4 Implementation of all measures and controls
9401e0bd-5892-51c1-8bae-a6d4e7241095 | note | FREQUENCY: Prior to commencing any activity
dddc2c5d-fc1b-503c-993f-4869536febe5 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
e438fe90-9e66-5a67-9465-a789ee52bd57 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
6a02abd0-9493-5e70-a12a-0a4b18a4e698 | note | INSPECTION/TEST METHOD: Visual Inspection
8d70d50a-e5ff-56fb-a311-c7f60da1c0ed | note | RECORD OF CONFORMITY: This ITP signed
9fedfd96-ab78-55b3-b255-c9f89845c91b | note | HP*
725b84c1-5b62-51bb-a969-3b699081a431 | note | RESPONSIBILITY: Site Engineer / Site Foreman
2f0c0316-1c76-5389-b1da-d430265c7965 | textbox | Date Completed:
79f39a50-64d5-4c9e-9f62-e45fb04bf7f6 | section | Construction Works
3702d8b0-b40f-4840-adff-1e6f4141174b | checkpoint | 2.1 Transverse Joints
2db31d71-0b2c-5d40-a775-f9c597290fbb | note | FREQUENCY: Check prior to placing material
e89b6d85-5f8c-531a-9793-6f0574fda650 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
4e0d9c85-59d8-5a5d-a790-c71cf1a13cf1 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
757252d2-e89b-5a8e-bf0f-2495b0bee242 | note | INSPECTION/TEST METHOD: Visual Inspection
dd5d8d1d-9584-509e-baf2-567505349a0d | note | RECORD OF CONFORMITY: This ITP signed off
74dced9f-d1a0-503b-8388-57b372a0804d | note | IP
6b7ff5ad-d708-5952-9bd7-90e423e09484 | note | RESPONSIBILITY: Site Engineer
ca85e490-cd24-526e-a149-930fd94f5294 | textbox | Date Completed:
0001eaea-b932-4cdf-a6ca-214731bd4b35 | checkpoint | 2.2 Longitudinal Joints
b5a5aa0a-ac58-52be-a8d0-e70a1312ca25 | note | FREQUENCY: Check prior to placing material
e0622d6f-ada5-509a-998e-56dbb7842cf1 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
c68f45e4-d6c0-51fc-a6c8-6dd85cd8913e | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
cbfac9af-1e87-56d5-b3b3-84dcb76a9166 | note | INSPECTION/TEST METHOD: Visual Inspection
0407d089-10f2-5356-acba-b125b3519e89 | note | RECORD OF CONFORMITY: This ITP signed off
18c350cc-4fcb-5455-a18c-b1c67e7fcc1d | note | IP
a408b0ee-2f6c-52b0-b1a4-311d6ff4985d | note | RESPONSIBILITY: Site Engineer
1852ce79-7c56-582c-a624-e252e7cdf485 | textbox | Date Completed:
f5ba7939-0b9e-4175-8957-7b9a9a935e0a | checkpoint | 2.3 Lot Size
1bec3bc0-f7fd-5255-9689-c6bc6617907d | note | FREQUENCY: Check prior to placing material
ce69e85b-d23a-56d2-8b6c-2902a95ae46e | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
5d28db5d-e605-50ec-824f-844eef9f4232 | note | REFERENCE DOCUMENTS: . Cl.304.08 (b)(ii), Table 304.111
1165e373-5fb1-5b3d-ad46-522b72914010 | note | INSPECTION/TEST METHOD: Site Inspection
f14feedf-62bd-5165-8fbe-ad8a52126621 | note | RECORD OF CONFORMITY: Signed ITP, Delivery Dockets
47854a6f-db09-5a48-bb81-619be1be9ed3 | note | IP
8c123130-ed29-5435-bb78-2114832272af | note | RESPONSIBILITY: Site Engineer
b9baeb7e-19ab-5253-a145-6647827adf35 | textbox | Date Completed:
b65bd46c-9a4d-4236-899b-0e21b766d7bd | checkpoint | 2.4 Layer Thickness
ea865932-31e6-57e5-a074-ae45e9699481 | note | FREQUENCY: Each Lot
98c46de5-2b2d-5dc8-956f-172c73f6f66c | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
fe16d2ec-bb7a-5dc8-a3aa-d0bb102a4f2b | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
ec27bbdd-b44e-5c4d-8415-9acf1ae9986a | note | INSPECTION/TEST METHOD: Site Inspection
cb311311-7d6a-5647-8011-6b9fd51dcf0a | note | RECORD OF CONFORMITY: Signed ITP
f1205dbe-4be5-51a3-8943-895b0e9dfcc0 | note | IP
9c3fc6af-0fd3-5d09-bff8-475e3468448c | note | RESPONSIBILITY: Site Engineer
18db45b4-ac14-538e-bc1c-9b622d5f24c2 | textbox | Date Completed:
b0ec2358-ad42-4cf7-b024-21e671409466 | checkpoint | 2.5 Proof Rolling
5bbba266-a720-5ab8-a9fd-42f1d21d01f9 | note | FREQUENCY: Proof Roll each layer
7e71d408-e1e4-55c2-8ea2-702d41b8298a | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
1ad27ccd-e4b0-5f54-a581-03640dfedaea | note | REFERENCE DOCUMENTS: 173.03
221c78f3-503c-5618-a2fb-755f7852c4b1 | note | INSPECTION/TEST METHOD: Visual inspection
cb6845aa-d9a0-58f0-ab8b-27031ff70cf2 | note | RECORD OF CONFORMITY: This ITP signed off
37f10080-1e3b-50f1-a1ee-21b36c2bbd7c | note | HP/ WP
bf2a988e-a725-5ee4-b662-f2085a01f015 | note | RESPONSIBILITY: Site Engineer & Superintendent
6c9ba691-9749-5845-a891-7ff24e464a02 | textbox | Date Completed:
769b3710-2219-4c3e-8225-c96117f11f77 | signoff | AUTHORITY HOLDPOINT
e75c0424-6622-437a-8b2b-c12b545d8f32 | section | Testing Requirements
b5771a79-93be-44c9-931e-3d4489833fde | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
7edc6227-3ee8-5097-8018-89585740a13e | note | FREQUENCY: Prior to Testing
45ca897e-ecb9-5c6f-aeb3-913a02d637e3 | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
caf6f7ed-7ea9-5812-9fcd-764276834e77 | note | ○ Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
bd906679-8ced-5a6b-a442-a34032b38b24 | note | REFERENCE DOCUMENTS: Table 204.161, Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i), Table 304.111
00f564b0-b2a0-5049-b393-038931f3cfa9 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
13b62f2c-30af-56a4-acb6-1bc093cdc20f | note | RECORD OF CONFORMITY: Signed ITP
a2781d02-2486-5b4d-90ed-b3ad728f84fa | note | AP
85687540-9023-538c-8950-5bb1171fe697 | note | RESPONSIBILITY: Project Engineer
43b4b9c0-8f79-5f41-815f-a3f3a2fed8aa | textbox | Date Completed:
6f512ab4-1190-4da6-9284-4df0e7522821 | checkpoint | 3.2 Compaction Testing
0a5ebdb7-e23f-5362-9170-88d2114773c3 | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
3d34baf2-2c28-5c1a-b828-6598547392b3 | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
250c50ec-d362-5c37-8aff-a2fe9660a717 | note | REFERENCE DOCUMENTS: Cl304.08, Table 3040.061, Cl 304.11 (b), Table 304.111
a5554bf6-f0a7-57ea-b074-969eb33f55df | note | INSPECTION/TEST METHOD: Test point
8f62a131-138c-56cb-8c19-39ed2df3d8cf | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
706fe664-fcb0-563d-aff9-ed9401f442b0 | note | TP
53a6c030-34f7-52a3-819a-768d4b09b055 | note | RESPONSIBILITY: Site Engineer
c351b414-0d57-57a9-9c0f-c9fa22535a61 | textbox | Date Completed:
b80896d1-c6b7-4397-bf43-e4043ce27503 | checkpoint | 3.3 Compaction Testing (Small Lots)
90fb1f6f-38fc-5e82-9674-1c216fb07c89 | note | FREQUENCY: Each Lot
cb70a11b-3188-5466-b928-7978638c3249 | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
379b4f58-e297-530d-aefe-86c9464baf64 | note | REFERENCE DOCUMENTS: 173.04 d
4ae3648c-4867-535a-bb01-9f412a20f3df | note | INSPECTION/TEST METHOD: Test Point
74ceed11-39af-52a2-b21b-eb3e4e5e898b | note | RECORD OF CONFORMITY: Test Records, Lot Register
2d179439-8e88-5e54-9c2f-66efba39f114 | note | TP
041e6940-00f4-5f2d-bdf9-1fe83aa55765 | note | RESPONSIBILITY: Site Engineer
cf8dfa37-3ec9-5a05-bd11-7adc4436cd8c | textbox | Date Completed:
a1046da1-a0cb-45ef-92a5-7cd58b466952 | checkpoint | 3.4 Material Grading - Post Compaction
4d57ca7d-7e21-5d65-afe3-cac636e2a2e6 | note | FREQUENCY: First Lot Only
b47a635a-b7a8-5beb-81aa-b04e4011b0a8 | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
62d7217d-3a41-56c4-97ba-005f95f8ec67 | note | ○ Class 4 - As per Table 304.101 - VR Spec. 304.10
54f47550-05c6-54db-87ae-ab956f3941e9 | note | ○ Class 3 - As per Table 304.101 - VR Spec. 304.10
6a137c47-f096-59b1-8769-55e2f6580298 | note | ○ Class 2 - As per Table 304.101 - VR Spec. 304.10
f5e6ab05-e4dc-5613-8bc8-dbcb4b33fe53 | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
78c95ddb-6c48-593d-a7fc-fd815ccef448 | note | INSPECTION/TEST METHOD: Test point
a0f593fe-7906-5979-ad8b-db4371255467 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
bdc479be-fc71-5eb7-b8e4-43ac579c0d1c | note | TP
f5c7acde-d786-5ef7-99c9-7c9a49912191 | note | RESPONSIBILITY: Site Engineer
b2f23d88-c4c7-5af3-b509-be3f4fb9109c | textbox | Date Completed:
321043f3-d8ec-46b9-8a70-cde249534463 | checkpoint | 3.5 Plasticity Index - Post Compaction
17eba612-2713-5b44-81a8-cf45645b3db7 | note | FREQUENCY: First Lot Only
413529ab-99b0-5ae9-a87d-f28b862c7672 | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
7e1ae50c-3441-5e87-b945-847017d166de | note | ○ Class 4 - 0 to 10
8b5b2204-a0fa-565b-9915-7236edd01d63 | note | ○ Class 3 - 0 to 10
82425040-04aa-5b10-89c0-b08a44cc8bd7 | note | ○ Class 2 - 0 to 6
a1fe34b0-5605-54bf-9a0d-ba736cb725ba | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11, Table 304.103
12cdf358-d534-5623-be47-d2076ee29b50 | note | INSPECTION/TEST METHOD: Test point
ffb7c189-f986-573b-bd5c-bfa5b079c2d7 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
636030a8-d273-5d25-9707-66f2b78aa033 | note | TP
bc685cf1-8f46-52dc-b191-a98d81e42e9b | note | RESPONSIBILITY: Site Engineer
458cc527-0eb7-568e-9b23-c78c73c93507 | textbox | Date Completed:
0a240e12-0b1c-470d-a75e-b74a1cce7167 | checkpoint | 3.6 Survey Conformance
78696f48-6301-5f6e-bbd8-2ae3d1637f3b | note | FREQUENCY: Each lot
9f0705e5-23f3-57d7-a6f2-8d4e5d9ab385 | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
4abb109b-3fd9-57ff-87b5-ce03a3d0846a | note | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
ae156dbc-cbc5-583a-a1ba-e11346696b2d | note | Surface level tolerances:
ae441932-44a8-534f-b57a-c8d1e4fedd03 | note | ○ Range x = +6, -16mm
78ee3c95-5bda-5003-a1b9-1b4b2be550db | note | ○ Max S = 15 mm
18528068-490b-54e0-847a-fa74ad60d779 | note | ○ 40 measurements per lot (Minimum)
f84a0117-38e9-535b-9cb1-df0443dca04e | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings, Table 304.062
6766e604-29e0-55d9-9518-329f37cad822 | note | INSPECTION/TEST METHOD: Survey
934d2a46-4378-58d1-ae6d-9d8be0d37097 | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report, Lot Markup
89226bae-15cb-5544-89ed-459dbf670901 | note | SCP
426004f8-e1e1-5853-a0f3-48237975d28b | note | RESPONSIBILITY: Site Engineer/ Surveyor
11f135df-7e79-58c2-b483-af9701b6754d | textbox | Date Completed:
435ad56b-add3-4784-b3e5-a5809ef7eea8 | checkpoint | Final Inspection
55a90447-07c7-5824-89a5-5c51a38ba3a6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0abdf444-e873-58cd-8f4b-d05fc019eb9c | textbox | Print Name:
f6e5500b-1d02-5937-979a-343af13f11e7 | textbox | Position:
f0ad3ad0-3271-586c-8a4b-0f3bfd0a8fdc | textbox | Date:
3b76b997-e4f2-4545-a4e5-b337bd366771 | checklist | FHC-ITP-008 - Stormwater Drainage - Greensborough Rev3 | itp | FHC-ITP-008 - Stormwater Drainage - Greensborough
ae15a908-a041-4393-9379-54e3173c5730 | section | Preliminary Works
e5c90182-7d9f-49d5-bdee-c91983784314 | checkpoint | 1.1 Check for correct documentation
583f4c5f-597f-54bc-8f59-54aead0d6896 | note | FREQUENCY: Prior to commencing any activity
6ea87036-a060-5c52-9bb7-b7de459efd91 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
e481fa9c-4646-526e-89a7-872eb59de39c | note | – using the correct and complete set of drawings
c16f347b-0ddd-5454-9056-a77d7fa0d544 | note | – all drawings are the latest revision
c44d8eba-a452-5f17-998f-c42b3601743d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2562d875-5991-5f26-b8ad-e2b08c69c2cb | note | INSPECTION/TEST METHOD: Visual inspection
636150d1-ccce-5545-9997-502c7a082286 | note | RECORD OF CONFORMITY: This ITP signed off
4ae4eeff-471e-529f-bfd1-1a50c1447a8e | note | HP*
14a81699-d36b-5f9b-b36e-0ffbc7cf3fd9 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0ceedaff-d4b3-5baa-913b-9b3ca8ebe362 | textbox | Date Completed:
eb2814dd-a7ee-44b3-9541-4a0621d2aa76 | checkpoint | 1.2 Implementation of all measures and controls
d3551ed5-ff91-5587-bbda-94736ca85295 | note | FREQUENCY: Prior to commencing any activity
8e61dab1-3519-594f-af94-8fcfa083825f | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
d50e33b9-b125-5153-98c4-95732ed87d32 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
c25367a9-40ef-5d6b-84de-255f9c158049 | note | INSPECTION/TEST METHOD: Visual Inspection
467b3335-d7c7-5b10-986f-9f4f770404c2 | note | RECORD OF CONFORMITY: This ITP signed off
89d886bf-a443-5c74-b922-6e15555c16d9 | note | HP*
3bec9625-4b70-5be5-a544-51cada804f90 | note | RESPONSIBILITY: Site Engineer / Site Foreman
47738e7d-dd8d-587e-87f1-3c3801bb1378 | textbox | Date Completed:
232ab2a3-6c92-44df-a3ba-f6a8b8241df9 | checkpoint | 1.3 Precast Materials acceptance
2bcd9aa6-c40c-5dc5-87d2-911bed0a72f1 | note | FREQUENCY: Each Delivery
fcf8d77c-4293-522f-81da-ebe78b55350b | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
4ca1013c-6409-5831-8342-993547aa5e6e | note | REFERENCE DOCUMENTS: Cl. 701.05e
b222399c-aedb-50ad-b914-2eced0012e49 | note | INSPECTION/TEST METHOD: Visual Inspection
f91091ef-f1b2-5cc0-b1d0-e65b57ad45c2 | note | RECORD OF CONFORMITY: This ITP signed off
68ee377d-aa39-5272-944c-cbfa84318131 | note | IP
4de4d794-fa3c-5cee-b721-d5b3ae1a55f5 | note | RESPONSIBILITY: Site Engineer
6067f3d4-8bf5-5e7b-9d80-0d3414551252 | textbox | Date Completed:
3a222527-4da3-4aa0-8c49-0e6c004a14bb | checkpoint | 1.4 Precast Pipe & Culvert Compliance
0cf62f31-c508-5e4f-b853-13693cc5b4ea | note | FREQUENCY: Prior to Commencing
23f61a19-78b4-53a9-955f-aaf206128020 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
19077111-1c36-57c1-a2da-8d587dc304fe | note | ○ Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058
d8418726-ae82-5488-9910-2da3ff797d4c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04, Cl. 701.05(a), AS4058, AS4680
29d334f0-de36-596c-8405-f3253eb13da5 | note | INSPECTION/TEST METHOD: Document review & Site inspection
ff0e98e3-9efd-53fa-b095-97a84c0b3e46 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
dc9a5f5b-e2f6-53af-90e7-5e2328bf967f | note | IP
cc4fd50c-62ac-5162-a864-d6e50a989b2f | note | RESPONSIBILITY: Site Engineer
d7241c06-e4ff-54e8-b28a-0dc1ef83b39d | textbox | Date Completed:
8a0dc7a8-cbc0-4ef4-91d7-9988c396390d | checkpoint | 1.5 Precast Drainage Pit Compliance
94c2bc94-a55b-5de1-9329-e3a6aa2fa4ac | note | FREQUENCY: Prior to Commencing
02ac5494-1f28-5ce0-a03f-7b872478a291 | note | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
63939f1d-77dc-5b8e-bce3-2657ececd9e0 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.610, Cl. 705.04, AS5100
c853c2ac-a1e2-5b1b-bfff-bf543539054a | note | INSPECTION/TEST METHOD: Document Review
c681e0bf-9a92-517c-acad-0d8599c2ff88 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, This ITP signed off
2ddfc1f6-cd85-5653-82ad-9c35c5be18e1 | note | IP
5aa466cf-5f2f-5e63-8256-b03a1d6d482e | note | RESPONSIBILITY: Site Engineer
67cc3efb-e60d-5edb-a724-ba85cd35a5a2 | textbox | Date Completed:
f660eb01-547a-4bee-880f-98cc7bd443cd | checkpoint | 1.6 Bedding material classification
87beeafe-f2ef-548f-aa3c-6ef7883df054 | note | FREQUENCY: Prior to start
cdf5a273-45c3-53b9-bd46-bebee7a04763 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
9af71189-200d-59e2-9758-98e74cd90bb8 | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
d67def80-a0f4-50e7-b6cd-1857635a3b86 | note | INSPECTION/TEST METHOD: Verify
55a54fe8-384c-5800-8a0f-200c92cb6ca6 | note | RECORD OF CONFORMITY: This ITP signed off
71ea6574-006e-5d8d-9284-6ecfb3271d46 | note | TP
31f5c290-4a7b-5504-a00b-57daed0b2c2e | note | RESPONSIBILITY: Site Engineer
39de717a-5eaf-53b0-a58c-a16c5e28853d | textbox | Date Completed:
24f37b62-bf8b-4949-93e0-a3d04a69cd0e | checkpoint | 1.7 Backfill material Classification
2a1d6768-9e55-5f1e-8492-8d6124a4aff9 | note | FREQUENCY: Prior to start
05c0fd5b-6a55-5188-9f0b-6e49ed504454 | note | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
6c38209c-5ed4-5420-854d-3d861fa7e62a | note | REFERENCE DOCUMENTS: 701.09(d), 701.091
ab589eed-e1c1-5d4e-a9f5-c3120591bf35 | note | INSPECTION/TEST METHOD: Verify
b76891b0-84ae-57db-9268-b18e372256bb | note | RECORD OF CONFORMITY: This ITP signed off
558bcdbf-7548-583a-b047-d7f20b99167a | note | TP
e09fe767-583e-5938-a1ec-81b2f4458166 | note | RESPONSIBILITY: Site Engineer
de5730d3-b598-5397-8141-efef20f2093e | textbox | Date Completed:
7498565e-b44c-4d2d-9110-b86c13e98616 | checkpoint | 1.8 Mortar material classification
e9dffddf-7b43-5539-9c08-7ba712152995 | note | FREQUENCY: Prior to start
0c28af81-98fc-5139-90d6-be7102f84bdd | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
41d79e2f-2741-5fa3-99b6-ae165e478f38 | note | REFERENCE DOCUMENTS: 610.33
ff4d52ef-0953-5272-b097-d3c6a56fc722 | note | INSPECTION/TEST METHOD: Verify
c36c4db7-5728-53a8-a4d5-2a089c75b3a6 | note | RECORD OF CONFORMITY: This ITP signed off
c08311a6-bd62-5b39-9e13-dd48bb757683 | note | IP
ccb340e7-f6ac-594e-81a7-04ccf5022785 | note | RESPONSIBILITY: Site Engineer
3e2b7c38-4ccd-593b-a50e-5a831dd1e882 | textbox | Date Completed:
fe7cf329-851c-4971-9ffe-697f1c3f9264 | section | Construction Works
23d896d1-48f7-4f20-938c-0b10049f1d64 | checkpoint | 2.1 Excavation Permit
0d2bab41-d3f3-519c-b467-c42c6fbf201e | note | FREQUENCY: Each lot
ebc6ea1b-c6c4-5752-a69f-930645f1b629 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
08de8946-0098-5ba4-b2f4-be28c740b323 | note | ○ Plant and equipment shall be appropriate for the task.
d89d2b25-4401-5793-88ac-b8a8dd017719 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
66f9c88c-8b79-57da-b715-0aca40c261c1 | note | REFERENCE DOCUMENTS: Excavation permit
5ebefb5b-e2c5-5ad1-a35b-3c49a2d6a7ed | note | INSPECTION/TEST METHOD: Verify
5d54778b-3c87-5954-b0cc-209d396a55d8 | note | RECORD OF CONFORMITY: ITP Signed
a946cb3c-c963-5a5f-898b-c44ff5a98a71 | note | HP*
353243f0-13a8-5971-8cfb-ce224870ac2e | note | RESPONSIBILITY: Site Engineer
c621b401-65bc-516b-8d36-8f018b25406e | textbox | Date Completed:
c87c4e08-4218-4223-9044-f52ab88efed0 | checkpoint | 2.2 Set out drainage
e18948bf-99df-5ae7-b5f7-dbfe94ab6ff2 | note | FREQUENCY: Prior to backfilling
a9b07645-5c26-596c-b550-9ba354acb17a | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
3e09c5fb-0ea0-5709-90c2-994b16ae0c97 | note | REFERENCE DOCUMENTS: Drawings 701.10
efd06daf-abc2-510e-9190-c0a413e099d4 | note | INSPECTION/TEST METHOD: Visual Inspection
94141217-0aca-548d-a403-b804a93fb36a | note | RECORD OF CONFORMITY: ITP Signed
bcd079d3-1468-5248-960e-fa739b776024 | note | HP
e7354725-23f9-5553-bd7a-2fb30e93db64 | note | RESPONSIBILITY: Site Engineer/ Superintendent
a559eaf2-2ffc-577b-b363-78d1f3d594c1 | textbox | Date Completed:
f8e8a1bb-0671-4628-8f5d-6b948222bcb7 | signoff | AUTHORITY HOLDPOINT
d65b2968-8764-428a-a798-86e0d1accbcd | checkpoint | 2.3 Excacation (pipes)
daa348c8-0bdb-5938-8e1c-f3f794362e36 | note | FREQUENCY: Each Trench
c34878a0-f10c-58fd-9edb-e5fa1529f5d2 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
fa6ddd06-68a0-515d-b55a-0924e35ec666 | note | Depth of trench:
776badc2-d0de-5947-80f5-db6159a0f523 | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
cd8871e7-d048-5414-b0a7-3d7e79c8e54d | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
e70091d6-bc28-5c7d-b3a9-813574a2354b | note | REFERENCE DOCUMENTS: 701.151, 701.15
6f953dfa-8c39-50a2-b939-f982872a3990 | note | INSPECTION/TEST METHOD: Visual Inspection
e9bc093e-072f-5506-8549-0a0f2cfbb52c | note | RECORD OF CONFORMITY: ITP Signed
63ac8498-3433-516e-8d1c-cfbb9bb58a81 | note | IP
b563e133-16f6-593e-98f1-978d5046f2d2 | note | RESPONSIBILITY: Site Foreman
469e7707-4377-58b8-bc31-37f33c6095ae | textbox | Date Completed:
a389809b-efdd-4ea8-b417-297bf0cf3847 | checkpoint | 2.4 Excacation (pits)
8b79fb97-96a4-51e3-b904-14b1b920217d | note | FREQUENCY: Each Pit
7c563f84-44a0-5104-8e20-81c62fb9a284 | note | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
ddcea500-784f-58f2-885f-ba5eb5cab994 | note | REFERENCE DOCUMENTS: 705.05b
f06a83e3-8e56-5e4e-9657-ea940cf46193 | note | INSPECTION/TEST METHOD: Visual Inspection
196fd375-fc4c-5f5c-b774-8d8e782d974b | note | RECORD OF CONFORMITY: ITP Signed
02dbdad9-ec9e-5eab-9269-12801c343522 | note | IP
9778a57c-b6a7-5793-ac3a-6811a1aaccdd | note | RESPONSIBILITY: Site Foreman
f4b29176-2e72-5b00-94d0-5ccf7ad72ea3 | textbox | Date Completed:
1c2a107c-5d4b-4f07-9757-4d1a1c75c6c4 | checkpoint | 2.5 Compact base of trench
99097dea-c235-5dd4-a9c3-4e661f059981 | note | FREQUENCY: Each Trench
540179a7-1dd7-58c9-ba53-e77f6a5821ef | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
a2e971d8-0abc-5925-922f-657d05a19520 | note | REFERENCE DOCUMENTS: 701.15
13710a6f-4e86-56cd-876c-43ee17df713d | note | INSPECTION/TEST METHOD: Visual Inspection
4df30730-407b-5511-b72f-eaaa08520cb4 | note | RECORD OF CONFORMITY: ITP Signed
8efbfc1f-b1fa-57de-9f8e-ccf81ffc9e24 | note | IP
8e395795-046d-5f16-b991-fed2ea8d7341 | note | RESPONSIBILITY: Site Engineer
e6da3e67-9801-5fde-8e78-ca68dca97229 | textbox | Date Completed:
028b0c07-916b-41c9-8932-d20dfc2966bb | checkpoint | 2.6 Place bedding material & compact
e95e1cb6-5d22-5193-92bb-d63ac27435fa | note | FREQUENCY: Each Trench
5f30eddf-65ee-5c4c-af36-990642336e66 | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
d7bacb49-dd19-5df4-8519-09a05cecc851 | note | REFERENCE DOCUMENTS: 701.20, 701.20a
a553f6a5-475c-5b08-80e9-cf940d2c03a1 | note | INSPECTION/TEST METHOD: Visual Inspection
d1f88e1c-f23f-5872-8e77-f29e19c65052 | note | RECORD OF CONFORMITY: ITP Signed
3e68c03d-7e90-57cd-b9e0-39a471e890f5 | note | IP
e3e9a028-07fe-501e-add7-918d288e1111 | note | RESPONSIBILITY: Site Engineer
30447b6e-fb94-58bc-9525-50a1f53b2ddf | textbox | Date Completed:
2f3ff497-428c-4441-8965-d82fdd26492c | checkpoint | 2.7 Place pipes & precast pits
2dd61eab-a650-5a75-9876-7a04aaa32c60 | note | FREQUENCY: Each Line/Pit
bf98a54b-6dfb-5228-a260-dd822405160f | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
f36b916f-d283-5007-a647-ee1dd783cd07 | note | REFERENCE DOCUMENTS: Drawings
72303b00-8e04-5d82-9f27-f348b4103f3f | note | INSPECTION/TEST METHOD: Visual Inspection
4f576592-981a-53ab-832d-17f9ed26ccb0 | note | RECORD OF CONFORMITY: ITP Signed
8ab2a22d-1baa-558a-8900-3cc88b9083bd | note | IP
5aa9246d-cbdc-5654-8053-d6ea36e8bb33 | note | RESPONSIBILITY: Site Engineer / Site Foreman
80c7b215-7507-52fe-a3b6-fd83f9d6710d | textbox | Date Completed:
87e91458-5fed-43b7-8048-6f0fc20122fb | checkpoint | 2.8 Jointing pipe sections
0d3769a0-2216-5492-b9d8-8d2581b0375e | note | FREQUENCY: Each Line
dfa3d026-7caa-56f6-b38b-0def4f55fbd4 | note | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
3540a664-5315-56ed-8577-7fb1561d6dfd | note | REFERENCE DOCUMENTS: 701.18
724090a7-080d-5336-a9b6-beda32cea60b | note | INSPECTION/TEST METHOD: Visual Inspection
172c5dee-e24f-5ae2-933a-da1d4c4d5b46 | note | RECORD OF CONFORMITY: ITP Signed
7c05a3b0-c6a0-5a25-bfad-a58ae591d8dd | note | IP
9f68f81b-76f8-5e6b-bb64-37d4e39a518b | note | RESPONSIBILITY: Site Engineer / Site Foreman
9df66b0f-eec3-56bb-9b17-f868eb91625a | textbox | Date Completed:
53e27188-d3ca-46b9-aab8-f8cac7eb0acf | checkpoint | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
d8a60f3e-cbe0-5913-8d9d-9a4b343fc7ca | note | FREQUENCY: Each Pit
f7a15190-1230-5efb-bc93-798850b2710c | note | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared. The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
273e1d1d-bcf8-54a9-b756-894ee88c0a96 | note | REFERENCE DOCUMENTS: 610.32, 701.17c
1bdb15d8-d49d-5580-a168-3e26d4a16cfe | note | INSPECTION/TEST METHOD: Visual Inspection
3de43adc-b641-528f-9b4b-676de4922188 | note | RECORD OF CONFORMITY: ITP Signed
9e107d6b-50e2-586a-9ac0-73f87f580f1a | note | WP
3f885dda-0ba7-5e60-9c97-010dc5ffba3b | note | RESPONSIBILITY: Site Engineer / Site Foreman
fe3442ba-683a-598b-9609-d7f5d74867b0 | textbox | Date Completed:
3fd2617a-b760-405a-b830-55e60c44c8d1 | checkpoint | 2.10 Survey of laid pipe or pit
462cac56-466e-55e6-a600-e18f64956d28 | note | FREQUENCY: Prior to backfilling
fdd94135-e8ca-5b68-9fc0-501fc5f4abe1 | note | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances:
f54371c9-6add-554d-8e80-a59dc965ec6e | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
2d4defb3-0725-5df4-a329-0855c5b7d3b8 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
66784000-cbd4-57a5-8637-56ff7c1a898d | note | (c) invert level of pipes at pits ±50 mm
83027cea-37c8-524e-a32f-4a159109ec96 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
dea9d7fd-ff6e-5716-a973-23c21c5a6e88 | note | REFERENCE DOCUMENTS: 701.1
300fd0ed-7141-5271-9c44-fce901987763 | note | INSPECTION/TEST METHOD: Survey Conformance Point
852a8240-a1bc-5ae1-8f35-c5b061e0ca39 | note | RECORD OF CONFORMITY: ITP Signed
a595e2a4-fa16-562d-bf62-29ef450a709b | note | SCP
77340dd9-3ac4-59a1-a665-e79dc8f77ac4 | note | RESPONSIBILITY: Site Engineer/ Surveyor
b5321977-8374-5c39-882f-74d120c57136 | textbox | Date Completed:
23a3d53b-f293-4aeb-a455-fc444e93940f | checkpoint | 2.11 Haunching & compaction of bedding material
427d56fc-741b-529b-b88f-7621c53e2a8b | note | FREQUENCY: each lot
0e42c96c-0218-5ee3-ae41-9b202fa60258 | note | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
86f9aa4d-17c0-5af7-8b50-316a7f05c221 | note | ○ Loose layer thickness <=150mm
ea60fd6c-7b9c-5b0e-bf6f-b6389040de02 | note | ○ Compacted to refusal using hand held mechanical equipment.
9396e7da-cd9f-58af-9e87-4561ab748e51 | note | ○ 1 lot = 150mm layer
eeec9e35-b788-5e0c-8bed-d68ed1625818 | note | REFERENCE DOCUMENTS: 701.16, 701.20
efb44e12-c056-51c2-9612-fa05c82c3e54 | note | INSPECTION/TEST METHOD: Visual Inspection
16f31ac4-d4ab-55dc-bd10-89464140cc4e | note | RECORD OF CONFORMITY: ITP Signed
85b22bc8-191c-5510-aa61-91f4c99018ad | note | WP
adcb3fc8-909e-5680-a3f1-49b115bb028b | note | RESPONSIBILITY: Site Engineer / Site Foreman
b23df6e5-a156-5bbc-a7d2-66fbd2b914f9 | textbox | Date Completed:
17a5c3a6-db75-452b-a9a6-c9e2236a5ad0 | checkpoint | 2.12 Place & compact backfill material over pipes
b695d7ce-4db7-57d9-95bf-cf516a963a77 | note | FREQUENCY: each lot
31aea318-014c-5482-bb27-21e36783dbf6 | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
14748d04-6436-5d60-a82a-120ccc74c65f | note | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
e40ddddb-5ba8-58fc-bf6d-29a31e2f230c | note | REFERENCE DOCUMENTS: 701.19, 701.20
ed33c1e8-8cd3-5cb8-a992-2f97f173ec9c | note | INSPECTION/TEST METHOD: Visual Inspection
d3a3dbd9-f77c-5301-8783-36e42f3d573b | note | RECORD OF CONFORMITY: ITP Signed
74a592d7-1eaf-55d4-963f-1df6c1daec02 | note | IP
e9b0a45f-15a8-5ec0-a686-79f83f3e2b43 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0d2914cd-6213-5e46-9da9-b2b912978f9b | textbox | Date Completed:
cd685f53-17a6-463a-8d84-b1aacfc2903a | checkpoint | 2.13 Place & compact backfill material around pits
696d061a-a834-52f4-939f-ae62fc256c14 | note | FREQUENCY: Each Pit
bfe1dd8d-900f-5509-bca4-a7e73fa5abc6 | note | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm.
c06a0cb3-e875-589a-a6b2-e7f00e3d43e4 | note | ○ Compacted to refusal using hand held mechanical equipment.
5eb21983-7d25-5173-9488-071f04bd0e8d | note | REFERENCE DOCUMENTS: 705.18
48d41ad0-a3f6-50d2-a5ff-c9aa9eccd022 | note | INSPECTION/TEST METHOD: Visual Inspection
7a7f9c5e-be7e-5e1d-984f-d5b871ab81b8 | note | RECORD OF CONFORMITY: ITP Signed
c1a68b98-5d08-5e19-a3c0-ce6548def20d | note | IP
186ade0a-6fc2-541e-9ad7-612f98310e5a | note | RESPONSIBILITY: Site Enginer
62fd0e5b-3f1b-5216-9a52-0c69e9629284 | textbox | Date Completed:
edd90fe9-3dfa-4fec-82f6-58490c90d9df | checkpoint | 2.14 Backfilling with cement stabilised sand
0eca6fbb-da23-533b-8ce5-1a2521e4d3da | note | FREQUENCY: Each culvert
29cb031a-daca-5fbb-8b35-96a0b9b1f14b | note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
e4997bb2-c92e-58d7-a1f2-17929513f687 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(a)
d080d930-bd21-53c3-8af0-a6a50bfa9a21 | note | INSPECTION/TEST METHOD: Site Inspection
b3e1d596-8278-5a44-aca0-7602aed05039 | note | RECORD OF CONFORMITY: Superintendent approval, ITP signed
02b8ad55-5c0c-54ec-9e9e-c97ac220833e | note | AP
8a7220e8-0d0c-5454-bab9-7fb41adb786a | note | RESPONSIBILITY: Project Engineer / Superintendent
10e3b50f-b0df-5940-9a88-a3f904badf55 | textbox | Date Completed:
41cbb03d-cf68-4916-b056-07b48717bb73 | checkpoint | 2.15 Install step irons
b3b9a4d1-2d9e-5d73-a181-6ddc4c6d1364 | note | FREQUENCY: Each Pit
9d650d97-4fad-54ae-922e-32361efa24b8 | note | ACCEPTANCE CRITERIA: For pits > 1m deep.
a7ca16ec-ed7d-5b53-8069-6e9cbb4c0134 | note | REFERENCE DOCUMENTS: 705.12
127a4fbd-9a4c-5231-8f2b-31863dfac4b0 | note | INSPECTION/TEST METHOD: Visual Inspection
ee8d9c71-7b00-5c4f-9203-3f4a7bd234b3 | note | RECORD OF CONFORMITY: ITP Signed
72e7961c-6c5e-54ca-959c-9a7a2b332b43 | note | IP
1337f838-2ac5-5e1f-823b-1e36cecd5671 | note | RESPONSIBILITY: Site Enginer
6abdce1a-65a4-5c60-9b99-ba450394e221 | textbox | Date Completed:
c6ceeca5-2633-4c4b-869d-870180eae59a | checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
04c3c1c1-c9fd-57ef-bc94-5902af6f3063 | note | FREQUENCY: Each Pit
a2daf14d-0fc8-5ada-a149-43e63fbedb1c | note | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
57e401fc-55e5-5ad3-8205-6965abcf2b70 | note | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
5e097d92-cc04-5aad-a293-cbe11a0d8713 | note | INSPECTION/TEST METHOD: Visual Inspection
0042ffe6-d90a-5ad9-84cb-50906156f6ad | note | RECORD OF CONFORMITY: ITP Signed
b32ec9fc-6349-5bed-9da4-14b0713b39ac | note | IP
735b1b99-805c-54d0-bf0e-74eed5abc268 | note | RESPONSIBILITY: Site Enginer
0b750f5f-4748-5c8e-8b2a-8456f32d2451 | textbox | Date Completed:
51688ca9-ebe4-49df-8ae1-39e1cd06db4d | checkpoint | 2.17 Place pit covers
1bab6e4c-9b7f-5b09-9156-e7c19d9d8796 | note | FREQUENCY: Each Pit
124576de-c5c6-5d06-935a-53a1f898a1fc | note | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
2702b875-d5e6-53f7-aefa-4fa9d6e66644 | note | REFERENCE DOCUMENTS: 705.17
5595eb62-b1a8-5a2a-a57d-3ee362a9ac6a | note | INSPECTION/TEST METHOD: Visual Inspection
533ed036-86e6-5425-919e-3ed4aa6c9944 | note | RECORD OF CONFORMITY: ITP Signed
7a3f2fe5-e562-5ce2-8f71-c0186820a240 | note | IP
898b8bb8-3273-51e4-afb6-d3aed7888d18 | note | RESPONSIBILITY: Site Engineer / Site Foreman
8d7fa641-4b65-5aed-b949-dbca104fc542 | textbox | Date Completed:
777f686a-8770-4d28-aad1-71612448d6bf | checkpoint | 2.18 Repairs to damaged pipes and box culverts
471cc943-1106-5dd1-87e2-2ef5a7b32186 | note | FREQUENCY: Each damaged pipe or culvert
cd5ae055-42d7-54ae-b837-b8e824cfe95b | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
a6a68041-06f6-57da-9503-257f2a0fc9b3 | note | ○ All repair procedures undertaken in accordance with Cl 701.25
d5e896f2-9fd9-553c-9ca5-18955e0dfe60 | note | REFERENCE DOCUMENTS: 701.31a
1232bba8-a844-5afe-aa53-39a0a10d8095 | note | INSPECTION/TEST METHOD: Verify
8cd9276e-0d75-5f9a-b28a-e2a165e64be1 | note | RECORD OF CONFORMITY: ITP Signed
265dd03f-bf43-5901-9792-be8e349bb32d | note | HP
a2a5331b-7d43-52ec-bd39-36b61e2721c6 | note | RESPONSIBILITY: Site Engineer/ Superintendent
1bec36cf-49c6-5ded-844a-1ef2c48ad517 | textbox | Date Completed:
44357bfe-d8c2-4609-8b4d-e7242410680d | signoff | AUTHORITY HOLDPOINT
3ed9b39f-e5aa-4976-965e-1f8e366aa826 | section | Testing & Completion
2adb1f39-1e9e-4cf3-bda0-f2259ad09b82 | checkpoint | 3.1 Compaction and moisture content of backfill & bedding material
cc8eb990-8b69-5596-871d-766f392fe5e2 | note | FREQUENCY: at least 20% of all lots
02421f30-842b-5ece-8109-24a2311287b0 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 97% using standard compactive effort.
f68fdb83-b354-5e96-b65e-3b4213cc992d | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92 between the completion of rolling and the placement of the overlying layer.
97fde96b-ada6-57ae-b078-6ffae97ce36c | note | REFERENCE DOCUMENTS: 701.20a, 701.20b
385857c8-eeff-54fb-8c79-b45e564d0a82 | note | INSPECTION/TEST METHOD: Verify test reports
864268e2-c4f0-59b9-9a41-3678a24d7c81 | note | RECORD OF CONFORMITY: Test Reports
ebd56052-ca53-5486-8021-ea4339f3a24f | note | TP
998a1b20-1149-5caf-82f4-fbd88f3e6089 | note | RESPONSIBILITY: Site Engineer
33eac2b4-b246-5cc3-8d39-e8feba74df36 | textbox | Date Completed:
d96b8a65-bfa9-49d1-9a71-5122318a681f | checkpoint | 3.2 CCTV inspection
bbcb25cd-4bf8-58f8-b824-46e1b00f3bf9 | note | FREQUENCY: each lot
ad28d517-c5b1-583e-b7ff-cf94319a0446 | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
b4744232-4e11-5bfa-bb7a-a52349f5f241 | note | REFERENCE DOCUMENTS: 701.3
13f019ed-135f-5008-b6ab-1b84216a8238 | note | INSPECTION/TEST METHOD: Visual inspection
ee3fd7b2-a430-58c5-9544-57fca0564ad4 | note | RECORD OF CONFORMITY: CCTV Report
1609a738-f5fb-5026-bc95-6489ed068ee0 | note | HP
7315140f-70bd-59e3-a9b3-2ecd06c7752f | note | RESPONSIBILITY: Site Engineer/ Superintendent
4dbb0efe-df69-54df-8882-c04e48be0c7a | textbox | Date Completed:
a2d7d524-e97d-47dd-8246-d0da34bc06cf | signoff | AUTHORITY HOLDPOINT
3010bdfe-1563-42b4-8758-fa56cc2393b9 | checkpoint | 3.3 Cleaning of pipes
87c8271d-b9ad-5fdb-bfa0-4235fa78062d | note | FREQUENCY: Each line
c3c9c6c0-30f0-56f2-90b5-67c37d59be8f | note | ACCEPTANCE CRITERIA: All pipes to be clean upon completion
b63cbb01-f971-54e3-94c3-4e28559055ab | note | REFERENCE DOCUMENTS: 701.28
c3816a00-43f8-5e8f-b278-ac937b20ead8 | note | INSPECTION/TEST METHOD: Verify
162cf238-1225-5777-8ce3-7f56f3678442 | note | RECORD OF CONFORMITY: ITP Signed
231e8674-5c3a-5ef5-bdf5-167a0d64799c | note | IP
7d5be437-ae5a-5337-bffa-26c387e2dda5 | note | RESPONSIBILITY: Site Engineer
11076550-c65d-5033-a098-bfee378ebda6 | textbox | Date Completed:
63924048-586f-427b-9776-e1f42847a967 | checkpoint | Final Inspection
0b5bcc0c-a15e-5007-a0c9-286f6b281f4e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e8ad562b-f74b-5813-8417-06e36ea24200 | textbox | Print Name:
30c04eeb-77e0-5e43-8286-9a725754385b | textbox | Position:
e0eddc85-2cb1-5b6c-8772-2291cf95f459 | textbox | Date:
dc6b6253-385d-4d21-baa0-34379400bd02 | checklist | FHC-ITP-012 - Hot Mix Asphalt - Greensborough Rev2 | itp | FHC-ITP-012 - Hot Mix Asphalt - Greensborough
961094b2-265b-4e44-a412-6682b7dd058f | section | Construction Works
3bef2d0c-f0e0-4563-8f40-d84d95b1803f | checkpoint | 1.1 Submission of Mix Design
4e54cacc-35e9-554c-bb24-07f5404774ff | note | FREQUENCY: Prior to commencing paving
9009338f-a346-5576-ad98-c283938aab37 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
bf5f744d-0845-5ac9-ad0e-775aec5114d2 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
34279025-43cd-5e7c-9dd2-08a4b7d3d105 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
756fc6fb-49a3-5270-b67f-35c6c3095e5e | note | RECORD OF CONFORMITY: MRPA approval, Completed ITP
f55fc5d7-e8af-5ebe-87c7-9ded65e2a848 | note | HP
c88b3725-02ce-5ad3-8db5-6f47a08827d6 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
5a4bea14-e8cb-50d3-9acb-cdc19b67f748 | textbox | Date Completed:
7815a3ca-eeac-41b6-a5c1-cec2747a117e | signoff | AUTHORITY HOLDPOINT
364a2cbd-e0d5-4914-9e00-5540e8d15f78 | checkpoint | 1.2 Implementation of all measures and controls
49cb51ca-a02b-5d96-b9df-57da1f91beea | note | FREQUENCY: Prior to commencing any activity
e1f370bc-f845-58b4-89d2-df09b4f385e5 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
8ab1d0b8-17b7-546a-b251-c546f4bbbf6c | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
f761cf6c-ca96-5808-9992-881b1b1d6bf5 | note | INSPECTION/TEST METHOD: Visual Inspection
81de9189-ede9-5df2-8be0-a96afb9cd164 | note | RECORD OF CONFORMITY: This ITP signed off
9917bfc9-c2e0-5a30-8018-52af26a99b17 | note | HP*
e906239a-f638-57d6-b830-91d06a061ce6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c872ed30-4197-5d23-bf38-74c1731141e8 | textbox | Date Completed:
61f4bbbe-9571-4e39-89b8-0d9968ebfbf6 | checkpoint | 1.3 Site Inspection and Base Condition
c66d4696-4098-50cd-972c-9bb20cad4efe | note | FREQUENCY: Prior to commencing paving
175bd45b-acc0-5286-b989-3efc3c13032b | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
d0f69894-2da1-562e-b8a8-b37f97e26727 | note | REFERENCE DOCUMENTS: 407.17, AS2150 10.1, AS2150 10.3
06038610-1fa7-54b8-a092-52c7c5fce7cd | note | INSPECTION/TEST METHOD: Visual Inspection
147f5642-1ed9-54b3-ad47-3c2a12a6ba4a | note | RECORD OF CONFORMITY: ITP Signed
26e26227-afd4-5d00-919d-35cdc6b254aa | note | WP
b4f7966f-b0de-5876-acc4-fd6474657ded | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
9d5741e1-4623-5a0e-a969-7e30fba68f36 | textbox | Date Completed:
7e8c1c76-ceef-4d16-9ed0-b8f69c3ae34f | checkpoint | 1.4 Ambient Conditions for Placing
e9b75671-5ffc-53af-9f8b-108c1e70b691 | note | FREQUENCY: Prior to commencing paving
f4cd622c-3f23-5472-a52e-54bac70790c6 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
5272a033-4314-5690-b99d-7b4f1deddcd0 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
c5f95837-d962-5b50-b38f-c29e8ed6dc4a | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
3c17563a-7202-59f8-9ef5-b2f4cbde0d69 | note | REFERENCE DOCUMENTS: 407.17
5b0d93df-9c23-5bee-bf02-a2bccbc6baa6 | note | INSPECTION/TEST METHOD: Verify
3844f580-54dd-5a0b-939a-79b35ce8c5ed | note | RECORD OF CONFORMITY: Thermometer
223545c7-e131-5944-b7b6-c8f41bfbbaef | note | IP
47fb0c2f-7451-5bc7-966f-7f10823be3e0 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
bcaca7e6-e607-51b8-aadf-8952d9ebe70b | textbox | Date Completed:
f9054412-75b6-4993-b046-7b4ac52d8eaa | checkpoint | 1.5 Planning of Joints
cb8ced35-7d77-5d62-9bda-fd70e0d75dfa | note | FREQUENCY: Prior to commencing paving
223968a9-9d15-5016-a469-ada460456d93 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
16c219b5-0462-5bea-9b0b-8fb3a40ec0d6 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
691280c6-a344-5216-9327-16fbf9d6829c | note | ○ Longitudinal Joints Offset from layer to layer by at least
960aab07-2a02-5003-904a-eabf02b10aa3 | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
8a2ca932-9fdc-502f-ac7a-797e65dc9f0b | note | REFERENCE DOCUMENTS: 407.21 (b) & (c) Pavement Drawings
7938f44f-a44a-5a6c-8a51-f2829c32b61d | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
b68f7402-b0e6-5bbe-8f16-0b22e00f6e9c | note | RECORD OF CONFORMITY: Paving Plan
9d053431-3683-56b6-9cf7-b081b97e19ea | note | WP
504b2168-f80c-5bee-aea5-162466779aed | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
171d31d8-5f3d-5104-a976-d753df0958bd | textbox | Date Completed:
140ecf2a-2db9-472c-b7dd-578e3db48248 | checkpoint | 1.6 Longitudinal Joints with existing Pavement
c030bba7-90cf-5864-b724-4bf8606fb633 | note | FREQUENCY: Prior to commencing paving
7db2718e-2698-5066-ae3c-2e81c867c2d5 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
0e683756-c1da-5255-a04b-bd0a8eb99d65 | note | ○ Depth of step to be cut to the full depth of each indiviual layer.
61d3b3df-9242-5380-9969-ff8221177733 | note | REFERENCE DOCUMENTS: 407.21 (c) (ii)
6ce7e6a6-ff57-5cc2-bf94-903309a5c00e | note | INSPECTION/TEST METHOD: Visual Inspection
db58858a-0343-57b5-8dfa-27bf6b6c016a | note | RECORD OF CONFORMITY: ITP Signed
7d1c319f-5a44-5c79-8118-f4a9b082401d | note | WP
f80e35a5-4cfb-5bca-be9d-4681ec446dbe | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
5cec2121-0905-50cc-b3e5-1cb86182d106 | textbox | Date Completed:
94c78425-5405-4151-bdc5-7ac520f7d273 | checkpoint | 1.7 Lot Size
d87e07be-aa08-53a0-a82c-db82568253d4 | note | FREQUENCY: Prior to testing
c08f15f4-d93e-5948-b988-40dc834033d5 | note | ACCEPTANCE CRITERIA: Lot size for determination of testing shall be in accordance with 407.27 (b) (ii), where less than 500 m2, reduced testing may apply
ce54f53e-0a09-5014-bf2e-731500233ec2 | note | REFERENCE DOCUMENTS: 407.27 (b) (ii)
8e1583e9-e23c-5900-bbbe-d9edf4bdfa3a | note | INSPECTION/TEST METHOD: Visual Inspection
e0799440-9107-5455-b4fc-7a02531433c9 | note | RECORD OF CONFORMITY: ITP Signed
2f9bfdf4-4dd6-55fb-8a69-0bef856d0af2 | note | IP
0c6ffc7c-0910-5ddc-954c-d75e1a57d8c5 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
858cca07-fe76-50a1-b8c0-de52dd70cd52 | textbox | Date Completed:
5bbd24a3-f381-402b-9888-0e4d125770c5 | section | Asphalt Placement works
a9cdcd83-16e4-4933-a615-219a83522ea1 | checkpoint | 2.1 Tack Coat
006b405e-1e84-5d95-9153-345e290e5c88 | note | FREQUENCY: Prior to commencing paving
7b5b5049-17d9-512a-9876-f8a08fc49b90 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
4c908e6f-9354-5f42-8883-8ecd44b6bdc0 | note | REFERENCE DOCUMENTS: 407.19, AS2150 11
9cac5eeb-8762-5f81-891b-a58b61751725 | note | INSPECTION/TEST METHOD: Visual Inspection
10fa75b5-6b22-5c70-858e-25945b751e34 | note | RECORD OF CONFORMITY: Spray area
d45efc8f-38f6-5876-8969-53c42db39b8f | note | WP
f4db321b-d795-5c24-938b-9f5202e171e4 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
6af0468d-d1e3-54df-9bf2-6d390d44343e | textbox | Date Completed:
a8492324-9f67-4b6d-98a4-88324da8785e | checkpoint | 2.2 Commencement of Placing
319e069b-df1f-5553-881f-bafb7b71f16b | note | FREQUENCY: Prior to commencing Paving
90c115c2-a6d1-51b0-bb41-7cb8c22cdd2e | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
ea5ee8b9-2bcd-59bb-b460-fc3eb17a5975 | note | REFERENCE DOCUMENTS: 407.23
17168e12-5ff0-5838-8c34-cf3e610fa3f8 | note | INSPECTION/TEST METHOD: Visual Inspection
e7db2bbf-55d2-5182-8645-b1fa81c4635c | note | RECORD OF CONFORMITY: ITP Signed
c8d775be-d004-5158-bc56-7e94cd7f6dc3 | note | HP
dc2c454a-75b4-5ed7-a99d-20bd4e14a983 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
7fce9533-7c9f-51c6-a0d1-0b927342e73f | textbox | Date Completed:
1f47a957-efdb-4861-9aae-b537f52121e3 | signoff | AUTHORITY HOLDPOINT
721fce0b-726e-4925-8f49-efbc55165656 | checkpoint | 2.3 Mix Design Confirmation
bef8da5e-fb3b-5d22-b9af-416447ffe2b3 | note | FREQUENCY: Each lot
1104ba44-9761-509c-a8ba-d39f8f548ec1 | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
94e5b07b-b06d-578d-8836-50bf3641a8fe | note | REFERENCE DOCUMENTS: 407.2
e2f3974d-14e7-50e2-b418-8d2d36a07b39 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
7293fdb1-8d5d-54db-89c9-4b9493e6369b | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
cf14f42d-d1bc-5762-8baf-1fdf615223a5 | note | HP*
7486ac86-dfcd-5191-888d-fc7117410cb5 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
3cbc7f87-368f-52e7-bfab-6f905f0a0743 | textbox | Date Completed:
47b6247a-b214-46b3-8c04-96352da1b4e3 | checkpoint | 2.4 Delivery of Mix
abb10f8a-53a1-5cc1-92a5-bb2cf381d163 | note | FREQUENCY: Each load
39d79741-98af-5084-a54e-e12ebbc47c08 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
520f0d9f-cf61-5aea-983b-712616338e82 | note | REFERENCE DOCUMENTS: 407.2
0f316e76-dfc6-5e2a-9896-e0edc7165065 | note | INSPECTION/TEST METHOD: Visual Inspection
c2d9edaa-a516-56a4-a645-950576a83635 | note | RECORD OF CONFORMITY: Delivery Docket
9d5f61cf-39f6-510a-996e-04297cb098ad | note | WP
ed458a2a-2097-5913-8088-221701b17cd6 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
a63b710c-0125-53ac-ba96-c867deeac544 | textbox | Date Completed:
02d94296-8d8f-4fd3-b96d-1608ff204ff2 | checkpoint | 2.5 Traceability
f3022c05-c94f-51fb-b562-9c83f291afee | note | FREQUENCY: Each lot
e2a34fd9-fa4e-5fec-8e57-babbd20f3de0 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
17b2a27a-1223-5bbd-a699-d2e931645ce5 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
3545cac2-3db6-5c6b-b059-7ea51f08c6f9 | note | INSPECTION/TEST METHOD: Verify
42707adb-ae62-5127-b4fa-97fbf83b67e7 | note | RECORD OF CONFORMITY: Daily Lot Record
d2901f22-2daa-56f4-b07f-c5e9fbef347b | note | IP
2d0dfef5-9deb-57b0-922a-62b8f8c77a03 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
c13527f5-05c4-5532-8f2d-58b86ccd5c2d | textbox | Date Completed:
efb8be30-ff56-45f4-9e89-92c407422713 | checkpoint | 2.6 Layer Thickness and Level Control
b9e9e3d0-dda6-5eb1-80ea-a285ccd00b52 | note | FREQUENCY: Regularly during paving
79173513-2af4-568b-943f-f475e7127fe7 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
35fd4608-4822-5d75-9c63-527b37d77b51 | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
2b737923-3b4e-50a2-850a-2d56eac99e84 | note | INSPECTION/TEST METHOD: Verify
4bfbb5f2-698d-58d3-8ab5-979d1be584fd | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
e66fd1d8-7a04-539a-8dea-b1dda62df26b | note | WP
716070c6-a9cd-565d-b6f1-688f0a3bd2c7 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
7d0dfac3-df53-5027-a0c7-9f7e22abbf8a | textbox | Date Completed:
589e127c-3f4e-425c-ab15-e686d66a046e | checkpoint | 2.7 Paver Stoppages
adf59b9d-9605-5252-bac6-5bbb50778d15 | note | FREQUENCY: If paver stops
32644af3-a800-59cd-9544-150076ddd017 | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
31282c0f-53f9-5104-979c-b51340c8c9b4 | note | REFERENCE DOCUMENTS: 407.25 (c)
b9d41109-1121-5d4b-98af-e0d0f712ff1f | note | INSPECTION/TEST METHOD: Verify
c27ebc32-91d6-578b-a0b4-5104a7cd0b8e | note | RECORD OF CONFORMITY: Thermometer
62481e7f-e365-575c-b647-92e2df4e2a47 | note | WP
71195773-b6ae-5d74-b258-54e91eb7e81d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
58841ff4-356e-5afc-a736-df61fe583325 | textbox | Date Completed:
05d679a1-ac0a-4a14-a0e6-2820be0ce3c3 | checkpoint | 2.8 Surface Finish of Wearing Course
941d45f8-5502-5a90-ac73-2aae18bb22e9 | note | FREQUENCY: During paving and after final roll
4517896a-fccc-586f-a349-cc31e97f78ca | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
ab88da25-b1b8-5c6c-a2f1-389190618b62 | note | REFERENCE DOCUMENTS: 407.29 (a)(i)
9b4b4f76-7603-52e1-b3f2-bbb13b6ba0dd | note | INSPECTION/TEST METHOD: Visual Inspection
0422d8f9-6dd5-5cb4-9193-f677280823b2 | note | RECORD OF CONFORMITY: ITP Signed
da4c0092-d2c3-5539-a311-85406b87131e | note | WP
d9c890dd-cee8-58c6-9c02-cee53861f70e | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
79b81d3b-3bee-51cf-887d-9cc637dd8bdd | textbox | Date Completed:
63a6e179-372a-4fc3-bb96-1107dacca73e | checkpoint | 2.9 Height Relative Kerb and Channel
001bd3e4-872a-57f8-9c09-288b3b36698a | note | FREQUENCY: During paving and after final roll
85992273-16f3-58c7-9fb0-619144de0924 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
05e853f0-846e-504a-88f9-76acda6f70ae | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
1c690047-4a22-58b7-ab5f-68d0734fa7d2 | note | INSPECTION/TEST METHOD: Visual Inspection
2ef2649e-8351-5a9c-a97f-69db4c0aab09 | note | RECORD OF CONFORMITY: ITP Signed
c5abb27a-c82a-53d8-a256-5021f1cda25d | note | WP
58878977-26d5-5b47-9cab-952e53adf678 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
78111957-c382-54dd-bc02-5151d2845a30 | textbox | Date Completed:
71ac2aba-e990-4ed3-bf45-c94c7d4408d0 | checkpoint | 2.10 Alignment of layers not placed against concrete edge
e8770488-6c26-5148-b401-a8cb3b68ce72 | note | FREQUENCY: During paving and at completion of work
9f9117d3-e3c7-5679-b4d2-17627fcffff5 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
b0c94081-a5a5-5874-ac2d-483657c2aa42 | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
c6a17d89-7bc4-5ef0-b305-c60e56f89a55 | note | REFERENCE DOCUMENTS: 407.29 (a)(iv) Drawings
aaaeaaa6-89ee-540c-9bed-17e71750ac75 | note | INSPECTION/TEST METHOD: Visual Inspection
42b409f4-c845-53cd-bd7c-3d22adbe198c | note | RECORD OF CONFORMITY: ITP Signed
facfe78b-651b-5902-87cb-bfd6e1201597 | note | IP
89b954b8-04a0-5200-84a0-112051a09bcf | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
3ec753d5-f28e-55fe-860f-bac7a0d3b642 | textbox | Date Completed:
5482a819-01e0-4f72-b28f-f5f1634bcab2 | checkpoint | 2.11 Width of layers not placed against concrete edge
bbdf9f02-c652-5d36-9926-7479a6b7bfc6 | note | FREQUENCY: During paving and at completion of work
d9632c69-d651-5b2d-8519-510f6fea8468 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
8b74d749-5838-5c25-be5a-fd2f6a792531 | note | ○ The average width over any 300m shall not be less than the design or specified width
e55cbc0f-98e3-51d3-a862-fe1133fd302f | note | REFERENCE DOCUMENTS: 407.29 (a)(v)
d6edfcc7-64f7-5d65-aa47-74e536401cc9 | note | INSPECTION/TEST METHOD: Visual Inspection
89d17d97-ab6d-5b51-a2cd-6973a711d63c | note | RECORD OF CONFORMITY: ITP Signed
7236bb15-0d13-5fea-a4e0-0ede473722cc | note | IP
04c4572c-519f-523b-8607-d9213483723d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
908915ae-7848-5eef-9b07-2cf599114d68 | textbox | Date Completed:
a0f9b61c-2f22-45e7-8b9b-b45d3e9c3035 | section | Testing
ad72117e-e106-4b1a-b8ee-5ac8f6dcf247 | checkpoint | 3.1 Compaction
c6b8295e-e6c7-54b7-a850-0083c3901e33 | note | FREQUENCY: Per Lot
809c9e4c-5478-513f-941f-c44dc1353242 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
94e4b8b2-225f-5b94-8f5f-b69e774ead6d | note | ○ 95.0% or greater Accept lot
44b76dc0-4710-5844-9c71-7bd9aed209d0 | note | ○ 93.0% to 94.9% Lot may be accepted at reduced rate
af911e10-4d18-5a99-a27b-344fa1244287 | note | For layers ≥50mm, if characteristic thickness is:
47c23b25-fb96-5ca2-b849-7fc26735794a | note | ○ 96.0% or greater Accept lot
4d006e11-1e16-51cf-bf06-5ee572a2bde6 | note | ○ 94.0% to 95.9% Lot may be accepted at reduced rate
a20ac54d-9511-5a6f-9a31-830d4bfc59bb | note | REFERENCE DOCUMENTS: 407.27
aecd5ace-c3fc-521f-8000-635d2569f315 | note | INSPECTION/TEST METHOD: Verify
ed06685d-09fe-50ca-947d-ebfed77ccb9f | note | RECORD OF CONFORMITY: Test Report
b608c0d4-1f1d-5d06-99f5-4aa3fd114e72 | note | TP
2f9dd65c-790e-5586-8fdb-820f01356408 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
4a6209ee-c3dc-5833-bd00-334f7b0b77ae | textbox | Date Completed:
b78a0262-982e-4c96-905a-c1398fb10ed1 | checkpoint | 3.2 Level Conformance
53c2ee0f-c3e7-52dd-800e-ab07425174c8 | note | FREQUENCY: Per 4,000m2 at completion of work
b645354c-248e-57fb-9f7f-760a30d4b733 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm (Scale B)
f943e847-c7b4-5ff4-95f7-6883f44869e9 | note | REFERENCE DOCUMENTS: Table 407.293
ccc38938-66a4-5e81-8532-c2157897de78 | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
c60896b6-3265-5cb1-8c30-4a928a2d016b | note | RECORD OF CONFORMITY: Survey Conformance
e24ad7e5-ab19-5fbe-98ba-8ccf8131c011 | note | SCP
465307bc-dccb-5df5-9ceb-d1d536984eec | note | RESPONSIBILITY: Site Engineer/ Surveyor
c88b0432-64ee-5b24-8ccb-956885d0f410 | textbox | Date Completed:
dc971568-6145-4e93-ba73-82ca736ff906 | checkpoint | Final Inspection
9b94aece-98d2-5dc8-8279-ab428e543ce9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
04d0edc1-a3fe-5773-8870-0430f68a3d1a | textbox | Print Name:
ed53b7bc-c342-531d-a624-d10c7fe2eb11 | textbox | Position:
ecc9bb0f-28cb-5339-8f55-89f87fd937ef | textbox | Date:
7c1eceb6-6eb7-45d9-8f5f-8ba8d6d01047 | checklist | FHC-ITP-013 - General Concrete Paving Rev2 | itp | FHC-ITP-013 - General Concrete Paving
2061ee44-b67a-4a51-82e2-41addc7e4e15 | section | Preliminary Works
805a9531-c515-497f-aac9-ac02159c60aa | checkpoint | 1.1 Check for correct documentation
906fe084-ea06-535b-9428-bb0f6830c466 | note | FREQUENCY: Prior to commencing any activity
da0e82b9-b905-5e54-942e-b89d6d8ac694 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
26a3d9f8-b262-5132-958f-fa217fa7f4d3 | note | — using the correct and complete set of drawings
84469908-4745-5540-9c71-8555ab02bff5 | note | — All drawings are the latest revision
c8aaac92-2b90-5395-a9db-b0b0c441caf2 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1b3f9151-60ba-51b2-8eb7-b42ad07f57f2 | note | INSPECTION/TEST METHOD: Visual inspection
967d23d5-b615-5de6-86f7-88af295efe16 | note | RECORD OF CONFORMITY: ITP Signed
5589e5c9-5ee7-5e62-80ed-3bfb37e64887 | note | HP*
909131b4-2c1c-5fd8-af39-373f0685a36a | note | RESPONSIBILITY: Site Engineer/ Site Foreman
c062c2f5-0729-5a2e-9543-91c9e7e72958 | textbox | Date Completed:
b843056b-cde3-49d6-85e8-6033b9116921 | checkpoint | 1.2 Implementation of all measures and controls
9aea6c5b-a650-55b7-aead-fe5fe6466fce | note | FREQUENCY: Prior to commencing any activity
e7560506-ab7a-588d-aa30-3d38eca3e488 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
95c1c17d-17f8-5e74-be22-4b363c525506 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
21a5af06-1a49-50b7-ad7f-eadb6bc9de27 | note | INSPECTION/TEST METHOD: Visual Inspection
a828d9ce-5be5-59af-a72b-619f135a55e3 | note | RECORD OF CONFORMITY: ITP Signed
e343bdac-1087-597b-8e97-46f7ce261c4c | note | HP*
d45884f8-b5fd-5b05-af05-4476d94e2518 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
be06815f-89d3-50a8-8c8a-0bc89719746e | textbox | Date Completed:
6ee42447-594f-4d95-8bbf-6a5bfbf84155 | checkpoint | 1.3 Submission & Approval of Concrete Mix Design
b00eb4d7-a3cd-5b5c-b7cd-b522ca037fe6 | note | FREQUENCY: Prior to first concrete pour
e421602f-d9b0-5880-9140-c504642833ad | note | ACCEPTANCE CRITERIA: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
53929441-c2c0-57e8-af4a-9c8ae1e8b02e | note | REFERENCE DOCUMENTS: 610.07(b)
d4449abc-e250-5c70-a520-69c7ee6abdbf | note | INSPECTION/TEST METHOD: Verify
5fff6e94-da31-5a6c-b77e-17b8551b93aa | note | RECORD OF CONFORMITY: ITP Signed, Mix design approval in teambinder
b2bff18a-dc89-5fe2-84c0-196b53711184 | note | HP
a53aba3d-534a-539e-b527-748e57e96734 | note | RESPONSIBILITY: Site Engineer/ Superintendent
33875a83-d0dd-5752-959e-27bdd137d2d4 | textbox | Date Completed:
db19955f-1ef5-422b-ad11-f091a463aa17 | signoff | AUTHORITY HOLDPOINT
140a1bb0-9c09-4314-824f-a140f3a149a6 | section | Construction Works
f4b8ad84-bf17-4d52-b15a-be2baf9d46e5 | checkpoint | 2.1 Setting Out
a84b4f09-2919-5e52-8fde-b22cb06f714a | note | FREQUENCY: Prior to start
2f568af6-3f54-52c5-acdd-0db8b3e854a8 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
6eb8011c-e98f-5a68-8a70-22c9ce967905 | note | REFERENCE DOCUMENTS: 703.17
80dd1cf9-3694-5015-a6f1-8be785d6ffc9 | note | INSPECTION/TEST METHOD: Verify
5172df7b-df4e-5a71-8d76-ed21dd814605 | note | RECORD OF CONFORMITY: This ITP Signed
c4894919-3ea9-528d-bff2-d0cd76a7dd0c | note | HP
180a9a2b-c51a-5e48-a58f-95d87b4601ca | note | RESPONSIBILITY: Site Engineer/ Superintendent
2b987b40-d2db-5e16-9583-1b32ff0e323e | textbox | Date Completed:
9c910f4d-0601-46d0-a525-4201fd2a822c | signoff | AUTHORITY HOLDPOINT
0310e133-76bf-43e5-b812-8b01d24df31f | checkpoint | 2.2 Excavation Permit
50666b3f-941c-5577-93e4-00375f738bb6 | note | FREQUENCY: Each lot
53d7be81-a386-507a-bbf2-16311e96ff2f | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
0e1bcf73-769c-5f27-ae96-a4aafe3779f6 | note | ○ Plant and equipment shall be appropriate for the task.
02f427bb-2f0a-5639-a750-38d8a726e844 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
5200a93f-d865-5db4-9396-6d97c44d53af | note | REFERENCE DOCUMENTS: Excavation permit
04b18f01-f046-524d-9381-c0546253e1da | note | INSPECTION/TEST METHOD: Verify
1d438b48-8621-575b-9b77-c7c237b67bcd | note | RECORD OF CONFORMITY: ITP Signed
94c7f490-4428-5a5e-8aa4-e43cf0f120fe | note | HP*
956ecae8-0738-5a32-a083-eecb88fec555 | note | RESPONSIBILITY: Site Engineer
6e628131-e13e-5ef3-be7a-11057fd141ab | textbox | Date Completed:
bc09f80e-1783-49b5-b9f5-7cd765139ea7 | checkpoint | 2.3 Excavation
c3114b09-465e-597f-9acc-c3a55ee59e9d | note | FREQUENCY: Each Lot
196c90dd-5379-57d0-b6d8-4707d268d179 | note | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
9b8e51dd-ea32-5416-bd4f-2eb5cdd0e005 | note | REFERENCE DOCUMENTS: 703.2
6907a74b-906a-5443-8a9d-8b6088b0ebd2 | note | INSPECTION/TEST METHOD: Verify
f331dc45-c920-5bd6-873c-8d0b4072fbf2 | note | RECORD OF CONFORMITY: ITP Signed
cac68ea4-bddb-52a3-b2d3-a38aa552b15f | note | IP
082b5427-e589-5390-bd31-b88fb899be72 | note | RESPONSIBILITY: Site Engineer
9f1b0ca3-4f69-5821-90fd-e1baddd4ba87 | textbox | Date Completed:
7f0ea607-b624-46be-a3d0-3240d3373cf3 | checkpoint | 2.4 Bedding
1ead50d0-8d4a-5ebb-982b-03e55924be42 | note | FREQUENCY: Each Lot
53e2a390-e1c2-5296-9db0-999d2931c929 | note | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
5468ea04-e593-556e-b3f5-d0e92a74657f | note | ○ 100mm thick layer of 20mm Class 3 crushed rock bedding for median infill
8ff40fcb-137b-5416-8983-9e318e1dc5d0 | note | ○ 150mm thick layer of 20mm Class 4 crushed rock bedding for footpath/pram crossing
e1db7fd0-3e74-54ff-997e-0d0a6d216b38 | note | ○ Bedding trimmed, moistened, and compacted as per Section 304
9443fd0d-fcd3-5e12-aff0-f6af630af632 | note | REFERENCE DOCUMENTS: 703.21 Drawings
375d17cc-7c4f-583c-bd2a-2b29a18bfbaf | note | INSPECTION/TEST METHOD: Visual Inspection
4e83ddf3-a8fd-5f89-bee3-047c978ee619 | note | RECORD OF CONFORMITY: ITP Signed
4fdb0e9b-2c39-54ed-aebd-3a46846ad51d | note | IP
11b3c15e-d6e3-59db-bd4c-86957cb40bb3 | note | RESPONSIBILITY: Site Foreman
33899aa9-6872-53d8-8c75-af4cc7259e31 | textbox | Date Completed:
22473b86-eda6-4e82-ac4b-61d0c8fd24b4 | checkpoint | 2.5 Formwork
367c533a-4ca9-5121-ae37-b2f6f6c97fe1 | note | FREQUENCY: Each Lot
15c24956-79d1-552b-86f5-dcb0be01c63d | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
56af1f04-d032-56bf-b149-1bb4435459b9 | note | REFERENCE DOCUMENTS: 703.12, AS 3610
aae18478-c27a-57f7-a9d0-b446d0911fa0 | note | INSPECTION/TEST METHOD: Verify
21fcfe09-0a50-5d9c-9c20-d63a003cb09b | note | RECORD OF CONFORMITY: ITP Signed
90f4a427-e0bd-5aba-a665-04d9a20e135d | note | IP
93fc9d71-130d-51a0-8b2f-087f315069b6 | note | RESPONSIBILITY: Site Engineer
479f1148-ace9-55ae-a54e-4ce890f74774 | textbox | Date Completed:
d36ab2d2-bd99-4f13-9060-2cda411e422d | checkpoint | 2.6 Reinforcement
54682d55-b7e6-57cd-948a-769542a21c09 | note | FREQUENCY: Each Lot
d35f391b-fbb7-57ae-8b14-5acbc5f09c43 | note | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL82 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
1c7ebc05-5758-5679-971b-35da8ad48852 | note | ○ Reinforcement must comply with the requirements of AS/NZS 4671.
83c31b36-d6cd-5595-a9bb-bb38e60701bf | note | REFERENCE DOCUMENTS: 703.13
ca8b892a-64e4-540f-89c7-6700fad2a6e8 | note | INSPECTION/TEST METHOD: Verify
0d62876e-e04d-58b6-9490-7b4ab20d9576 | note | RECORD OF CONFORMITY: ITP Signed
570f0d2c-34d8-5be4-a2bb-fa1a930e9a53 | note | IP
d1671287-1b6f-590b-a9b0-5e7eb758fdcc | note | RESPONSIBILITY: Site Engineer
712ae850-53bd-5506-883f-633622ad347a | textbox | Date Completed:
aa620dac-a4ab-46e5-84d2-ce8948a5b759 | checkpoint | 2.7 Concrete Placement
11cbb35d-16cc-5e44-81cf-a7f8ec57ba13 | note | FREQUENCY: Each Lot
00b81ff7-3e93-5463-98ae-3468a48d8f97 | note | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
ab6e3581-4b77-5926-8e4f-37984ed45adf | note | ○ Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
e99476f6-e3dc-5448-b25e-e6ed4cd27128 | note | REFERENCE DOCUMENTS: 703.05(a), 703.08
8421acef-62c4-5e8f-aa6f-33a2c2cf9310 | note | INSPECTION/TEST METHOD: Visual Inspection
2b40a34a-1b31-5ae3-9314-d6f372edf495 | note | RECORD OF CONFORMITY: ITP Signed
04a9fbd0-7d3f-576b-a388-9d5daf9658f9 | note | IP
e22b4c7a-faae-5cfd-b8c3-12df76aa5d14 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
ad1c4a37-6c22-578e-8243-3cc89fc78291 | textbox | Date Completed:
ba80de4f-bd85-4a1b-9a49-e0650ef4ccd2 | checkpoint | 2.8 Surface Finish
cf507f08-843b-5083-a47d-18c21acf9693 | note | FREQUENCY: Each Lot
0757b110-31cc-562c-98a3-2c51ee277e90 | note | ACCEPTANCE CRITERIA: Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
13cf9ee0-2691-549d-887d-b917921fdb4a | note | ○ Footpaths and other Surfacing shall be compelted with a wooden float.
3a11a2a7-9879-5103-9f70-8a59bb1677e8 | note | REFERENCE DOCUMENTS: 703.25
85f78c20-b4b5-5d52-a1c5-b00e124ebbd2 | note | INSPECTION/TEST METHOD: Visual Inspection
1c17ccde-4040-5a46-b85c-b935dd6a7c78 | note | RECORD OF CONFORMITY: This ITP Signed
a79ce5a8-6f94-5740-8e53-b38cb48ccc7b | note | IP
7ff121db-3be2-58f3-88da-f3ab4d96a329 | note | RESPONSIBILITY: Fulton Hogan Engineer
09501ce2-e32b-5001-bc9e-4288a900fe70 | textbox | Date Completed:
f181c0c9-862c-4613-9f76-eb1736001d49 | checkpoint | 2.9 Pram Crossings
9a6f51c7-652a-57da-89ba-711f94bd27e4 | note | FREQUENCY: Each Lot
44a99e4f-9f21-5b3a-b239-3dd3a470cadf | note | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
ad0dc036-022e-5eb5-ab7c-d7478eb5d631 | note | — For pram crossings within concrete kerb refer to Figure 24A of AS 1428.1
0efa6cc7-7e7d-5813-bcad-34413943cf05 | note | REFERENCE DOCUMENTS: Figure 24A AS1428.1 Design Drawings
57689692-7b41-5adc-9591-e36213c61ddd | note | INSPECTION/TEST METHOD: Verify
6c8f7ce6-2934-52cb-8c82-1ab8449c33f8 | note | RECORD OF CONFORMITY: This ITP Signed
f08a681e-e8ae-58a4-9438-dce526ebfe84 | note | IP
be2c979f-0d28-5c78-ad7d-2717fa1b2a8d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
5e5253dd-97e0-5726-b572-c8264b29c273 | textbox | Date Completed:
c619f9b9-b59a-4c9a-bd9a-3f756e910134 | checkpoint | 2.10 Joints
3dacaa17-4f62-51f2-8b3b-8cf33a8523e6 | note | FREQUENCY: Each Joint
735bac00-7ada-5b50-8287-984dab586c15 | note | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
91852bd5-de40-5bdd-9e1b-8ac38deb00fc | note | ○ Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
606afe81-c0f0-5729-a327-b8319879a188 | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
b49c1285-bd69-510c-927c-9cc61ed3cd04 | note | REFERENCE DOCUMENTS: 703.26
8b1a3b19-55cf-56ba-8311-5ce811a144b3 | note | INSPECTION/TEST METHOD: Visual Inspection
473629bf-f843-5e63-a472-3275d086a997 | note | RECORD OF CONFORMITY: This ITP Signed
0661d5ac-8f87-5fbe-bfd4-f5459c17b7f5 | note | IP
021fc19b-cec3-59f2-bb26-35b00e511c05 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
989b1245-e479-506e-a82e-652ceb943bf4 | textbox | Date Completed:
d12fe8c3-4776-4431-ba58-0e4960d3e3e3 | checkpoint | 2.11 Protection of concrete
bc4e689c-5e70-58ac-94ff-58b89de6c88b | note | FREQUENCY: Each Lot
27272960-7064-5636-a37c-4d18ffce0dba | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
c1794198-9a04-5f8d-ae76-17059d13d8c7 | note | ○ Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
b7b4cf3d-7332-5c22-9604-16ac98490160 | note | REFERENCE DOCUMENTS: 703.27
71ed1205-481d-5fa6-ad7d-d5e2e320345e | note | INSPECTION/TEST METHOD: Verify
51c59bfd-2119-5c62-8f55-36e3f6df224b | note | RECORD OF CONFORMITY: This ITP Signed
aac71462-d14e-5ca8-aeef-c6e1f8923776 | note | IP
2bdf5b09-08fc-534f-9921-8a1795eb4c1d | note | RESPONSIBILITY: Site Foreman
1674780c-4de6-5035-b64a-c71b1db383bf | textbox | Date Completed:
daccf56d-a2d4-4512-800b-cb930b75fdf1 | checkpoint | 2.12 Curing
56df8600-ee5f-52e3-8f6a-f5dedfa8d30a | note | FREQUENCY: Each Lot
b5ce6978-5694-5f5a-8905-e2cf436cb07a | note | ACCEPTANCE CRITERIA: Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
64aa5630-989f-551c-b0ba-7151f77c7f75 | note | ○ Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
4e36f0ec-0503-5571-8910-89952c423dd2 | note | REFERENCE DOCUMENTS: 703.1
7ecc1710-2a29-51cf-95b1-3c04912e7c2b | note | INSPECTION/TEST METHOD: Verify
480550a5-ad03-5733-b670-627b4e700554 | note | RECORD OF CONFORMITY: This ITP Signed
44b9e0ef-c5e0-53ba-b7a8-595e837f6d81 | note | IP
94d02674-f716-58a7-ab8e-753083175e6d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
14faa120-1da6-52cd-99d0-7af6a85ca98a | textbox | Date Completed:
a42be337-431f-4335-9b84-bcaba7ef0616 | checkpoint | 2.13 Ambient Weather
904b610a-8d91-58b4-89d8-0b395057f0da | note | FREQUENCY: Prior to commencing any activity
50102589-6c3e-5a7c-b5ff-e3fbb5ca03c6 | note | ACCEPTANCE CRITERIA: Concreting operations shall comply with the requirements of clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for limits, restrictions and treatments to be applied for concreting in hot, cold and wet weather, except that curing shall be in accordance with clause 703.10.
989afb6b-a9e2-5a6d-8c10-cf058fd3e3a8 | note | REFERENCE DOCUMENTS: 610.17(a), 610.17(b), 610.17(c), 610.17(d), 703.09
30851984-a370-5010-b396-a77657022c9e | note | INSPECTION/TEST METHOD: Verify
1fcf638d-3a17-546a-bdcc-51a1d4ff854c | note | RECORD OF CONFORMITY: This ITP Signed
c7daa1f8-942a-542d-989a-104e44f7c752 | note | HP*
d41641b0-87f8-5ad9-b363-f5f763f7ef8b | note | RESPONSIBILITY: Site Engineer/ Site Foreman
013e826d-7440-53a3-9e58-7ce17f4a8166 | textbox | Date Completed:
b709a055-2b65-4802-a0e3-01182e2a766a | section | Completion
86260a6a-36ad-499b-8844-ce6d5375610f | checkpoint | 3.1 Carry out sampling of concrete - strength and consistency
68068a3c-5040-5854-9081-7bdce15f1879 | note | FREQUENCY: Each 50m3
276ff185-138d-556f-8379-fdd0113b2d66 | note | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
95ae288f-ecb9-533f-9005-8db32fec0ee4 | note | ○ The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
08c7ef0b-c269-5949-82cb-d7326da44472 | note | REFERENCE DOCUMENTS: 703.11
de65f2db-31c8-5eb5-8fe5-a734181f9604 | note | INSPECTION/TEST METHOD: Checklist
0c14576d-487c-537e-9cbc-df63510ab32e | note | RECORD OF CONFORMITY: ITP Signed/Test Records
45c0e87f-3f6b-5c5f-a877-4e52d8ee9a26 | note | TP
a9621781-764f-561c-a0ea-57e0273a35bb | note | RESPONSIBILITY: Site Engineer
5765d71d-23fb-5940-b204-0fcdacfe6873 | textbox | Date Completed:
bd203f0b-3212-4342-a023-61e8528cc0eb | checkpoint | 3.2 Tolerances
1285e1e0-5fba-57da-9782-a51f46482a4b | note | FREQUENCY: Each Lot
73ba288a-fbeb-5dd1-87e4-1ffd968ce4ca | note | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
f8be4deb-4e79-5558-a225-8d36fdaa3ab0 | note | Section dimensions shall be constructed within the following tolerances:
21f79297-2c76-549d-95f5-1fcee9e7f974 | note | ○ 5mm and 15mm for width; or
02e1deab-90de-556c-a60a-48795871012d | note | ○ ±3mm for dimensions less than 25mm.
c94f8a78-e928-530b-a6b3-18d9d608dac9 | note | REFERENCE DOCUMENTS: 703.15 Drawings
11c0831d-fe88-5912-a133-2936a67402fe | note | INSPECTION/TEST METHOD: Visual Inspection
1f961850-3863-58b9-8fbb-ed4f1f265423 | note | RECORD OF CONFORMITY: This ITP Signed
30edd8f1-0d44-56fc-bac5-d8108f2ac7f2 | note | IP
5fcc8487-256e-5b4c-aad8-5f8e7b80efa2 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
2d146c59-e39c-5ded-901c-3f31cfe0b56a | textbox | Date Completed:
ad3195a4-e04d-41af-adbd-50311e784ac4 | checkpoint | 3.3 Backfilling
f62ea99d-1f1a-5c1d-b144-8749ce655a6d | note | FREQUENCY: Each Lot
a28bcf67-9d9b-54cc-82e6-ea15f57550c2 | note | ACCEPTANCE CRITERIA: After curing, no earlier than 3 days, backfilling shall be completed as per the below:
a4a80ff5-f4bf-5c8c-a677-e8c9afbc85e4 | note | ○ Topsoil compacted in layers < 150mm
aef11108-3114-53e9-8a03-b3b2f442e0bb | note | ○ Width ≥ 300mm behind edging to top of edging
4d23fcd0-8124-5efb-8460-5556b5ea1bb2 | note | REFERENCE DOCUMENTS: 703.29
0bf141f3-b4b6-5b6a-a56b-520fabed26ee | note | INSPECTION/TEST METHOD: Verify
93a8fe7e-99ad-5150-87af-19d7be2ea966 | note | RECORD OF CONFORMITY: This ITP Signed
95d339cc-00ca-51ed-bf9c-923e4f50bc17 | note | IP
2556c8bc-ade4-54a2-8e3e-5fb2ccd3440e | note | RESPONSIBILITY: Site Foreman
60b499d4-4f91-5761-beab-7c51c1f87b29 | textbox | Date Completed:
6d7f48c4-6c20-48c2-b952-f5f47fa0822a | checkpoint | Final Inspection
12aa164f-0377-5078-a8d0-a6defabddda0 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
cbec61f8-619e-514e-80a4-a5a77e5bf88f | textbox | Print Name:
91c8db15-f42d-5478-ba34-314305243a3e | textbox | Position:
7acf4710-4e89-5bdb-81c7-e7dbf665db7c | textbox | Date:
df8f4c7f-2e22-4be4-83e6-d7e26c440235 | checklist | FHC-ITP-015 - Kerb and Channel - Greensborough Rev2 | itp | FHC-ITP-015 - Kerb and Channel - Greensborough
6ee0f4e5-152f-4c38-992a-c9cea39264a9 | section | Preliminary Works
0852180a-8f45-488c-a37e-f7625df7c0c3 | checkpoint | 1.1 Check for correct documentation
522d368a-9980-5c7d-a91b-f05c2f3e451e | note | FREQUENCY: Prior to commencing any activity
dab8f530-eeeb-5949-931e-0a6a8082c8c6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
154453d1-f62b-56ad-9e0b-244f4e8ddf8e | note | – using the correct and complete set of drawings
f23f5be0-7f19-5c11-89fe-2ab812c61b13 | note | – all drawings are the latest revision
228626da-c1d9-5d4e-9ade-9d870adf2fa7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
d1664554-9a96-57db-b80d-1851b484706b | note | INSPECTION/TEST METHOD: Visual inspection
4a7f4b39-156d-53aa-9ad9-464171ab9e48 | note | RECORD OF CONFORMITY: ITP Signed
bdb179a1-186e-5177-aed2-e2f41de9c2b7 | note | HP*
e5bcc09e-ae56-5c00-bef5-7aaa43fd5ea8 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
912f1d0a-f382-5033-8a6a-02451b8039d4 | textbox | Date Completed:
f034b392-32eb-4097-9711-4c441517406a | checkpoint | 1.2 Implementation of all measures and controls
0d5a9e21-80c2-5e83-b077-088b2787a985 | note | FREQUENCY: Prior to commencing any activity
a11b6472-bccc-5ca2-b11e-1585fdbac794 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
962772ad-af22-5417-b96d-b01734c9ed0e | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
6915ffc7-c5df-5495-a7da-a2b26a8feaba | note | INSPECTION/TEST METHOD: Visual inspection
e4ed3e58-c69d-5c2e-9be8-b9d8383413c0 | note | RECORD OF CONFORMITY: ITP Signed
8c73f1a1-7dbe-5e6a-83eb-ae3d6e56482c | note | HP*
1a9f4f20-731d-518e-8529-e5ee1ba23799 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
9cc51477-cbb1-5352-bc7c-e72821f1d95b | textbox | Date Completed:
95f7a719-b607-431c-98cd-db676d533a6b | section | Construction Works
82101443-1dc4-4f37-83a2-b3aa4eb43ecd | checkpoint | 2.1 Setting Out
a276319f-1908-5482-851b-963a77aa4ee2 | note | FREQUENCY: Prior to start
d35538a2-9e62-51b2-9818-f1baae0f52c6 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
84d20cb2-4cb9-5f66-96a0-a91a5ac3c58c | note | REFERENCE DOCUMENTS: 703.17
1970036b-7dd4-5445-a57d-164e31f806d9 | note | INSPECTION/TEST METHOD: Verify
4d6c551e-5037-5719-b531-6a5c49dd0106 | note | RECORD OF CONFORMITY: ITP Signed
6ffcaaec-094f-5809-a811-fec3d3470629 | note | HP
9d52d668-87b8-51c9-8c94-3c1f801ad1af | note | RESPONSIBILITY: Site Engineer/ Superintendent
d23e198a-acfa-5523-b421-d474aa57375c | textbox | Date Completed:
859e9d4b-19fa-404c-b2eb-ae492c0c093e | signoff | AUTHORITY HOLDPOINT
adc544d1-8b11-47cc-ae99-c9fb60742412 | checkpoint | 2.2 Temporary Drainage Provisions
4a503b68-420b-5c35-a327-111c85778c6d | note | FREQUENCY: If Required
ed6e28bd-27d7-55a8-b5f6-0ac9d80d57bf | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
5f04f043-96e8-5e9a-a8ec-127076fbd109 | note | REFERENCE DOCUMENTS: 703.18
cfdb5c03-1e55-56c9-937e-df71e4b3f344 | note | INSPECTION/TEST METHOD: Visual inspection
63636f2b-c5aa-59ec-b209-af2015756e5e | note | RECORD OF CONFORMITY: ITP Signed
c10517c1-a2fc-5285-8c76-e55c32fed5e6 | note | WP
0c4c7a14-800c-5251-89f8-f4e8932abfb8 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
c8050135-63f4-566e-8d5b-44b269065c7e | textbox | Date Completed:
c6397f94-76bf-4fe4-8d80-be28592bacd0 | checkpoint | 2.3 Bedding
ea742bf4-9572-5883-b09b-f7d7554c1932 | note | FREQUENCY: Each lot
54220551-31dd-525a-a628-02dd67bb6df6 | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
d221075f-282f-5cd0-962c-5ce5ba3808ec | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
f888ebfc-fe00-5803-a91e-0bcfd56f1458 | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
90319a35-2f1d-5efa-ab98-fc2b8fe409b1 | note | REFERENCE DOCUMENTS: 703.21
4629615d-5372-52ee-839e-4adf9a889549 | note | INSPECTION/TEST METHOD: Visual inspection
8238facc-5334-51f0-bfd2-ded9439d45e5 | note | RECORD OF CONFORMITY: ITP Signed
d8858a0d-5ec3-5d4a-9653-d4b1318b223b | note | WP
9cf5ea60-225b-5cd3-b564-218ead122307 | note | RESPONSIBILITY: Site Engineer/ Superintendent
63a3dfad-8946-53ed-aa31-0eea87685b31 | textbox | Date Completed:
5d704f91-451d-4e1d-be71-33f3917e32f2 | checkpoint | 2.4 Pre-concrete check
c0533ea0-2cb8-5d3d-8618-4c85b1b8688c | note | FREQUENCY: Each lot
ffc133c2-3b71-5627-b462-cfe554971955 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
9130b0e1-f355-5160-81ba-82a2c6058949 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
64237b14-5f19-5e52-a20a-a9bb5a766109 | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
1c7f7a33-c860-53ed-af27-d468823af8d1 | note | REFERENCE DOCUMENTS: 703.08, 610.17(a)(b)(c)
40f54764-f176-5488-8c79-6c04c1cd6e75 | note | INSPECTION/TEST METHOD: Verify
97953148-eaaa-56a2-909e-c360f4552b17 | note | RECORD OF CONFORMITY: ITP Signed
f22e3531-9745-553b-9c02-7fc4be5a5437 | textbox | Ambient Temperature |  |  | °C
6be4117f-d696-5430-9214-b376fc6d2370 | textbox | Concrete Temperature |  |  | °C
1437652a-3d11-54bb-9a48-bc6d178a7195 | note | HP*/ WP
05948f62-0b94-5fa3-94af-f085ac669cb9 | note | RESPONSIBILITY: Site Engineer/ Superintendent
5cd56541-b961-5bf1-b8a2-f3899e724ced | textbox | Date Completed:
f10123f9-95ca-4534-a747-c3e31751f910 | checkpoint | 2.5 Concrete Placement
3443b815-4104-5ff9-be3b-6bcf1c8b0bb0 | note | FREQUENCY: Each lot
c4afe241-02fc-5f45-9762-f1f3224ce24e | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
d0ef7d31-066b-597a-81bc-f484a9e5516e | note | REFERENCE DOCUMENTS: VicRoads Spec 703.23
c88668d4-a517-5088-bffa-72a65b1d082b | note | INSPECTION/TEST METHOD: Site Inspection
01125295-63c5-5f59-b308-dfc2c78e9a46 | note | RECORD OF CONFORMITY: ITP Signed
141f7074-9165-56e2-a804-f57532438d5d | note | IP
9334a75d-223b-561b-98d6-18ab18a4aac8 | note | RESPONSIBILITY: Site Engineer
e0883229-db22-5924-b6be-37072c358aca | textbox | Date Completed:
555fd04d-13cb-40aa-b212-b3cd168f555e | checkpoint | 2.6 Finish Surfaces
f338a601-da11-5f62-9945-91f6ca3a4fcd | note | FREQUENCY: Each Lot
0963560d-2864-5961-9b5a-f3145fdfb43c | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
84379711-3137-5184-bc2e-c5f4412e1d62 | note | ○ Concrete to have a neat appearance and uniform colour.
52e5bd2b-70a4-538b-a786-4ec4c136fc9f | note | REFERENCE DOCUMENTS: 703.25
45ed7b64-9436-586a-95ea-205a5cb6ca85 | note | INSPECTION/TEST METHOD: Visual inspection
950b8b8b-7dcc-538a-aefc-637a65a991dd | note | RECORD OF CONFORMITY: ITP Signed
82578ebe-a2ff-5119-814e-07dab7a41dea | note | IP
ff817205-7d2b-5674-aef5-4b6adf1c563a | note | RESPONSIBILITY: Site Engineer/ Site Foreman
29f94a48-52ef-5a1a-8f2b-41dc06f4db7e | textbox | Date Completed:
4fd96471-a26f-4de3-9aa9-cb07cce41725 | checkpoint | 2.7 Tolerances
996fbe7a-e74f-5c3b-adf2-4e1f75ee8be0 | note | FREQUENCY: Each Lot
69b77dac-3870-5fe5-80e9-b97dab70fd30 | note | ACCEPTANCE CRITERIA: Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of ‑0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
303955a0-af38-58ba-81fb-f5aaee2a3b69 | note | REFERENCE DOCUMENTS: 703.15(b)
8d32c7af-eb97-5d9b-96b4-2d11a21993c2 | note | INSPECTION/TEST METHOD: Verify
d2986e34-6ca6-5596-b7ba-3a82b51c4d88 | note | RECORD OF CONFORMITY: ITP Signed
8c3c3888-aedf-5061-944b-7dc6a7fcc05c | note | SCP
725402c6-0d11-50dc-bfd8-5af6f543c81f | note | RESPONSIBILITY: Site Engineer/ Surveyor
86d58dcc-1934-5f7d-888a-feefdd6f11a3 | textbox | Date Completed:
c204f629-0887-404a-9c69-adbdc6416ae2 | checkpoint | 2.8 Joints
39b946e7-1806-58b1-aa79-80c7b08a81dd | note | FREQUENCY: Each joint
1c416f97-252d-5829-b901-f20f92a833b4 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
78f16a35-2c0d-556b-b073-c95d4df61470 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
e75b2552-f4de-50dc-9764-5a121ad26647 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
5cf13086-aaeb-5095-92e8-82e41b6687b2 | note | REFERENCE DOCUMENTS: 703.26
d04c455b-8355-54c1-a35a-f940015179d1 | note | INSPECTION/TEST METHOD: Verify
b612eef9-ca44-5d2c-ba87-2ac4c76ffbb5 | note | RECORD OF CONFORMITY: ITP Signed
3567233a-17aa-5f04-b953-220c21fbd238 | note | IP
5a0fde22-7422-59e1-8d79-912cd17bf28d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
159c4e98-6f10-50fc-9db6-4a396a6139ee | textbox | Date Completed:
7835e641-83ef-42f9-86da-cddbfd0e3063 | checkpoint | 2.9 Backfilling
e0977b3d-3463-53cc-bf7e-e54e00d56b9b | note | FREQUENCY: Each Lot
4a895cb4-f265-513e-889c-f6303aacc4d8 | note | ACCEPTANCE CRITERIA: Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
b55e4f4a-fafb-50c1-af60-ac712020f50c | note | REFERENCE DOCUMENTS: 703.29
9670d428-7c71-5041-b497-1ca7f9f7bd4d | note | INSPECTION/TEST METHOD: Verify
b79adafc-0f89-5e16-952a-2b25b71bfd00 | note | RECORD OF CONFORMITY: ITP Signed
0288ec77-6b7f-5581-82e0-51b05ee97035 | note | IP
14a3d3be-d057-5da3-a291-0686c6a95fa3 | note | RESPONSIBILITY: Site Engineer
1bdafed6-58c8-52ed-878e-fd1ebed3c7f8 | textbox | Date Completed:
1d12a846-cbac-479a-8adc-a48ce9e363ae | section | Completion
33847143-0259-4f17-862b-c279a78d5963 | checkpoint | 3.1 Survey data captured for as-built purposes
6a161615-ed3e-5b00-b02a-f8366a0a1f5b | note | FREQUENCY: Completion of each lot
6337e1f8-1386-51e4-ac0e-cf918bbbf164 | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
7ff60da2-17ec-53d9-abc8-1b2ea1c70b5d | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
b01e5c9c-a04f-5061-b9a5-8660f03c077b | note | INSPECTION/TEST METHOD: Document review
d3201dc4-131b-558a-86bc-0eb83f36f717 | note | RECORD OF CONFORMITY: As-built survey records
6ab5f608-6777-5894-8043-7567d1d94bba | note | SCP
ee222296-f366-51c0-b906-f3109a87736a | note | RESPONSIBILITY: Project Engineer/ Surveyor
f2728a6e-15b1-51dc-91b7-7e908261fa8e | textbox | Date Completed:
d4c5d050-62be-43cf-a8eb-a30776b9fba7 | checkpoint | Final Inspection
cf9dddbc-469b-55eb-bde1-876e76cd1bda | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
434019d1-4e8f-52c9-afde-a992e4bf7bab | textbox | Print Name:
dce8ed18-ae1f-58fb-9391-cbf645293601 | textbox | Position:
7a621750-47b2-549f-9afb-99bc9979861b | textbox | Date:
a6bd2d1c-ef58-41af-826d-c80710b8f406 | checklist | FHC-ITP-025 - Structural Concrete Construction - Greensborough Rev1 | itp | FHC-ITP-025 - Structural Concrete Construction - Greensborough
68ae43c3-eb1e-44d0-9758-52462432d38c | section | Design and Submissions
585e6480-6a1a-48a8-87f3-f93e754543b7 | checkpoint | 1.1 Check for correct documentation
3f663146-6d2b-5a72-ad75-aa9872859c4c | note | FREQUENCY: Prior to commencing any activity
992fe1b6-b7da-52c3-aaa4-59b32a9753e0 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a70126b7-4f09-5f39-813a-a635d1b01c20 | note | – using the correct and complete set of drawings
d5bcf764-46f3-56c2-b7d6-7186a0a33bf3 | note | – all drawings are the latest revision
5d9e245e-a69f-5acb-be9e-02dddb21b320 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
31026e56-1463-5a38-be35-6f68329170b6 | note | INSPECTION/TEST METHOD: Visual inspection
0fa7a2af-30f3-5d76-9d3d-5ef5bd1ea984 | note | RECORD OF CONFORMITY: This ITP signed
c5b0953e-8109-5396-875e-2751ed5fe972 | note | HP*
17e3bce2-46a3-5894-a6a4-54422f6e4904 | note | RESPONSIBILITY: Fulton Hogan Engineer
d7cc4dfe-d331-53bf-b8d9-5ddc3b3e3f8d | textbox | Date Completed:
8dd91c31-0074-401a-89c0-9f3f5894282b | checkpoint | 1.2 Implementation of all measures and controls
7000d084-7460-5465-bdd4-9204e57d133c | note | FREQUENCY: Prior to commencing any activity
ee4c1b94-ca79-5d7b-afba-49a32274b02e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
f99b1c3d-c311-577a-a9ab-29bb444019f0 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
ab2aab4b-b4f5-5ab8-bee6-3f197f474fd3 | note | INSPECTION/TEST METHOD: Visual Inspection
c6960b54-13e2-5422-bd48-2996d5737262 | note | RECORD OF CONFORMITY: This ITP signed
f9c9ea2b-e0e5-5809-b7e2-fb50f0a0317b | note | HP*
665d0482-3b56-5839-9531-73acaaf84638 | note | RESPONSIBILITY: Fulton Hogan Engineer
9d67c994-f800-5cc0-bfe4-659fcb25fa78 | textbox | Date Completed:
b2ff2d2c-81c9-4489-9e24-ce1ff19054c5 | checkpoint | 1.3 Approval of mix design
855db6bc-da80-5280-bc35-c5baa3dcaa20 | note | FREQUENCY: Prior to the first concrete pour
1f44a21b-9002-5506-b474-60ebfdb19cd9 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
d5f0b4b0-90f9-540f-860a-96cca76adef2 | note | REFERENCE DOCUMENTS: 610.07
85fc749d-a990-57c0-8348-6e3b6954d99d | note | INSPECTION/TEST METHOD: Verify
ec88e650-2acf-556b-a2b0-230e33f7ed85 | note | RECORD OF CONFORMITY: This ITP signed
49aaf07c-6e62-5108-9766-4cc1a1d489b0 | note | IP
db3b0e56-c693-5003-8c07-d5024855bfcb | note | RESPONSIBILITY: Fulton Hogan Engineer
211deb35-6838-513b-bcdf-0137f7e0fd98 | textbox | Date Completed:
b93cdd04-a601-4d84-8c48-7f36027e6f00 | checkpoint | 1.4 Reinforcement schedule
6f8cf3f6-2290-5942-857b-8edf5a2cb840 | note | FREQUENCY: Prior to concrete pour
6bc67ebe-eb3c-548b-84f8-5c4e9a1c62a8 | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
90a69ee2-02ca-580a-b64a-828fc030990d | note | REFERENCE DOCUMENTS: 611.04
27836d0c-35b5-5e53-b4da-f2faff7beedf | note | INSPECTION/TEST METHOD: Verify
972f6f92-bd6a-5f99-8f0f-afe3e48a0622 | note | RECORD OF CONFORMITY: This ITP signed
328b91fd-181c-5580-8ee1-50d1763d2ab3 | note | IP
3377c4f1-dcef-5c7b-8a7f-7424078fa5be | note | RESPONSIBILITY: Fulton Hogan Engineer
94f32c40-400b-5001-8621-0d6b957feb2b | textbox | Date Completed:
f716f95d-72f3-4733-bfa5-5bee5ad600f0 | section | Construction/Erection of Formwork
ec6704f2-d4ea-4a15-b587-11d2acebb87a | checkpoint | 2.1 Excavation
639830a0-1808-5987-844b-60ebf4a3c500 | note | FREQUENCY: Prior to concrete pour
82d6a514-0d2d-5837-a884-b0d66fb8c4f5 | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
fe7fe062-1af3-5e6f-b3f9-07a9f5e5c8dc | note | REFERENCE DOCUMENTS: Contract Drawings
6b67c638-8bae-5215-9bc4-40040fc43899 | note | INSPECTION/TEST METHOD: Inspect
a0959c25-5a8e-545c-bc07-3eec096f5fe1 | note | RECORD OF CONFORMITY: This ITP signed
760593cd-9ab6-51c5-ac44-2a924ea18de1 | note | IP
70e3acb7-cd12-55b0-8779-bf8ed78ed792 | note | RESPONSIBILITY: Fulton Hogan Engineer
9b9dc8ac-7236-519c-bc1e-7dc5570d866d | textbox | Date Completed:
e5273d1d-b6cf-4c9a-9422-2e44f8c5dfbe | checkpoint | 2.2 Construction Methodology
bf8e8adb-3f28-5fd7-a8d5-14f96e8a3dfa | note | FREQUENCY: Prior to erection
fb7175fd-ed1e-53a1-af63-1ff53b5c323e | note | ACCEPTANCE CRITERIA: Constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
1be4f444-5a66-5c9a-89f7-0278e88a746b | note | REFERENCE DOCUMENTS: 614.04, 614.06
50664a5a-4226-5590-85f1-68b2b3d49443 | note | INSPECTION/TEST METHOD: Verify
a5237faf-1a1c-58ab-934f-8ed0ead3567d | note | RECORD OF CONFORMITY: This ITP signed
60150228-d270-5654-be0c-36a93915c238 | note | IP
eb905c40-71a5-5ba6-a193-b6664b04dd7f | note | RESPONSIBILITY: Fulton Hogan Engineer
9e5a83a5-fe0f-5aec-9b02-eae066adfcbc | textbox | Date Completed:
59590317-4dca-4067-aed9-ddaad6376b02 | section | Pre-Pour Planning and Inspection
69d2c8cd-33f3-4a46-a67b-7d997221510f | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
ac510a57-70b4-5e13-91da-6f12717ec6e2 | note | FREQUENCY: Prior to concrete pour
3bd0a810-6bb0-568e-92a6-fbe7d242a545 | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent.
9a18d2b8-ede9-5c0a-b665-d467114248bd | note | ○ Hold Point released by the Superintendent.
b7b81f03-1874-5b02-88c2-df92cabe0404 | note | REFERENCE DOCUMENTS: 602.03
2ed9979b-aadb-5a44-8139-5aab1f8118a3 | note | INSPECTION/TEST METHOD: Verify
ca14c65f-c634-5479-b595-a01f34d9a7f5 | note | RECORD OF CONFORMITY: This ITP signed
36b9759b-a7cf-555e-8c58-083265f9495f | note | HP
b58e40b5-69eb-5c54-a469-846d566c5ca5 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
e4376f79-1af0-5cc9-8ebe-a17b7a603196 | textbox | Date Completed:
fb8f78e7-1b41-425b-8b64-acd6139991d9 | signoff | AUTHORITY HOLDPOINT
e35d1883-b65d-429c-ad0a-0063f10edc72 | checkpoint | 3.2 Formwork levels and position
977bb9e9-59be-540a-b3a9-916d4698844b | note | FREQUENCY: Prior to concrete pour
98089fe1-e675-56ef-9b49-f7f9145982ce | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
c12768b9-9008-5b7d-9a59-c09d22f5275b | note | REFERENCE DOCUMENTS: 614.06
7dd1c3c5-90bc-5ed7-98ba-ee8a933ee4b9 | note | INSPECTION/TEST METHOD: Verify
658b4a70-1eec-5db8-a325-896cddc9ab34 | note | RECORD OF CONFORMITY: This ITP signed
fb22c6ba-9ab3-58e8-ade5-86f15b6e5ba4 | note | HP*
b2e355b2-a4f3-59a5-a2c3-b7fe498376ff | note | RESPONSIBILITY: Fulton Hogan Engineer
db774204-14cc-5a90-ab38-bc69fca60f2d | textbox | Date Completed:
67a52681-3777-486d-9929-09934bd99e84 | checkpoint | 3.3 Location of splices
48f13e3e-1890-5a80-82ad-144c39a56d3d | note | FREQUENCY: Schedule Review
8014f695-0a1d-5613-b54e-2d4a02b536b1 | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
39972487-a69f-5696-80df-817816ba12a1 | note | REFERENCE DOCUMENTS: 611.11
33c9523d-371a-5484-b67b-5cf87d4c2a96 | note | INSPECTION/TEST METHOD: Inspect
bae53403-b915-539d-9172-2fe8170dcaaf | note | RECORD OF CONFORMITY: This ITP signed
7cc585fc-11ec-5804-a5c3-2dc7f59b8307 | note | IP
392c1eab-750d-5c9d-8937-055cf9a97cff | note | RESPONSIBILITY: Fulton Hogan
af8cef7c-9406-5449-a6db-c4d89e65fa21 | textbox | Date Completed:
0ea0ea98-9d7f-4196-a26d-681529bf9e00 | checkpoint | 3.4 Cleaning formwork
cf5eebe5-b01c-5541-ae98-143b1b93b224 | note | FREQUENCY: Each concrete pour
55c631a3-27b1-56cb-bb41-b919fbe4ce43 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
afd0356c-65fa-59a5-8598-7284eb30dce0 | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
57785410-78bb-5e4b-af79-1c61c9537436 | note | INSPECTION/TEST METHOD: Verify
931d2f42-a53f-555f-8f19-cd3e2b601eb5 | note | RECORD OF CONFORMITY: This ITP signed
be3ea124-d0be-5732-9fb5-5f97352c7737 | note | IP
94bb4a51-8aa5-5f1f-a974-74fcf547e071 | note | RESPONSIBILITY: Fulton Hogan
1ba7ba27-0019-57f4-bc16-df4e20c265cc | textbox | Date Completed:
fc810ca1-58ee-4bd3-b7f8-bc97d504d266 | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
dda5f687-6172-514c-a5f6-1160a0927db5 | note | FREQUENCY: Prior to concrete pour
7aeb2f52-9e4d-5544-a83d-42b85f28c8ee | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
a0e30715-7592-51db-a528-c0a5b2fd9671 | note | ○ Pre-pour checklist completed and signed.
b8d4bda2-bd9c-5a5f-8d11-cc6cac80f220 | note | REFERENCE DOCUMENTS: 610.18 (a)
d9715071-26d3-5f7a-8609-66af307d6faa | note | INSPECTION/TEST METHOD: Verify
eb837913-10ae-5162-b07c-403564de9d37 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
6f0bf699-ea2c-5654-8cf9-e8c1279f6eb1 | note | HP
459b89e0-adf8-592c-afcd-e757c0db8973 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
406b8728-1e7a-57be-9547-829f10cd5610 | textbox | Date Completed:
2cc36162-5126-423b-98b5-727e2610f507 | signoff | AUTHORITY HOLDPOINT
b651f6c3-d8af-4d97-93ab-f0e3cf86afce | checkpoint | 3.6 Reinforcement assembly of piles
f722b531-7fcd-5b1b-8b84-860450559329 | note | FREQUENCY: Prior to concrete pour
9aaa96e5-368c-59e0-9d62-e2679ab5a14a | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
96810f45-e0de-51c8-9e0e-ef17b09038d2 | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
de54fe9e-643b-5aef-a2b1-8718a1ef5644 | note | INSPECTION/TEST METHOD: Verify
74baeb17-1aab-5255-a06b-d1e7906f8992 | note | RECORD OF CONFORMITY: This ITP signed
8fb9d340-6cbe-52e6-9e5c-9c50ab10dcc9 | note | HP
ec8ff778-c74b-5326-b513-75077432364d | note | RESPONSIBILITY: Fulton Hogan
4bcf057a-4170-5c69-a9a5-38e27d2eb6cd | textbox | Date Completed:
da86a9cb-831f-4c4f-b69f-935394fc0ce1 | signoff | AUTHORITY HOLDPOINT
ac066f9e-c103-4ca6-ac2e-4e5c88f6494b | checkpoint | 3.7 Monitoring weather
30ee3184-390f-5c9a-9c91-80990020a3d5 | note | FREQUENCY: Prior to concrete pour
bb1013ad-bacb-5dcf-9117-124f79a9de5d | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
dc4298f3-8e27-5b43-9bb0-e16e40f7de7a | note | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
5344b5ce-e794-5b8d-accc-4f69001b6a8c | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
d738464f-c61e-5c96-929f-bb4368f20a2f | note | INSPECTION/TEST METHOD: Verify
b02b0e77-5a12-586b-9785-da4cc918df3f | note | RECORD OF CONFORMITY: This ITP signed
2c733d54-514e-50cb-8d65-7dca563d2104 | note | IP
a81b438c-df85-5813-ab2c-298b050931b6 | note | RESPONSIBILITY: Fulton Hogan
104ad99d-984f-5aab-ae25-39bef98bb602 | textbox | Date Completed:
03670cce-c1dc-4eef-9a46-1ff2a6362521 | section | Placing and Finishing Concrete
cde5b8b6-4c64-45d6-b47c-4b807e262276 | checkpoint | 4.1 Carry out sampling of concrete
b6f5b3d0-013d-5a53-ba9b-16cc5c2b1f02 | note | FREQUENCY: Each concrete pour
960ec2a3-1f66-53ac-81a1-407c86018dbe | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
5d42f2d2-c6a6-5cb7-a052-1e23c29f44e0 | note | REFERENCE DOCUMENTS: 610.16
3fca577c-1a41-523d-9bb3-bf895404e5b7 | note | INSPECTION/TEST METHOD: Checklist
8c1b9ec4-a2b1-56b3-b533-5c2a91fcc429 | note | RECORD OF CONFORMITY: This ITP signed
3af7dfaf-43e2-5f91-851f-d11e5f8f2afc | note | IP
ecbc43d1-33a5-578c-8e19-2510e02f4fb8 | note | RESPONSIBILITY: Fulton Hogan
34b0179d-5717-536f-bcff-1dd0d0bc67c6 | textbox | Date Completed:
a05f8245-f304-49e9-8fc7-952328ebe0d6 | checkpoint | 4.2 Discharge time
fe523d15-7b5e-5b68-be25-35eff89832af | note | FREQUENCY: Each concrete pour
6ee83c47-78b4-54f0-bc5d-8a7ca80daec3 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
6b717ba6-9b0b-5f41-882d-06bdd00d93b3 | note | REFERENCE DOCUMENTS:
4c668bc9-8ce3-5a65-8d05-2b4cefe38993 | note | INSPECTION/TEST METHOD: Verify
66575107-f33c-5980-a220-ef832c05c2db | note | RECORD OF CONFORMITY: This ITP signed
22f58355-0c29-50f6-938f-76ec2cf35c01 | note | IP
aa724761-6978-52e5-91ab-49bb1a53301d | note | RESPONSIBILITY: Fulton Hogan
706266c8-5a28-5ab7-84ff-0691fb76cd5b | textbox | Date Completed:
76cee866-5e91-4b40-bc7f-8baed21ab750 | checkpoint | 4.3 Methodology of placement (structural)
dcba064d-8324-5ec4-a596-5ae7304101af | note | FREQUENCY: Each concrete pour
621aa2c2-8037-5bba-88f2-7d33b62f621d | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
5dc01563-2ee5-5400-b7aa-7314956affce | note | ○ Concrete shall not be moved horizontally by vibrators
212c690d-5132-5a42-89a5-23a484dbd2f9 | note | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
ecfdc457-f51b-526e-acc0-a461545a1789 | note | REFERENCE DOCUMENTS: 610.18
4596915e-9f47-5608-b20a-51b9c5cca22c | note | INSPECTION/TEST METHOD: Verify
3bdafd38-cea1-5f95-947a-fcc2360d6414 | note | RECORD OF CONFORMITY: This ITP signed
87881430-d56e-564b-928d-80bcf0eb9945 | note | IP
d40e23cc-a53f-5673-835f-87cab1e71f2a | note | RESPONSIBILITY: Fulton Hogan
6aef2309-4a4c-5817-8daa-ebb4e93c1faf | textbox | Date Completed:
209cb986-b461-4b8e-932a-ec59e6a70b9d | section | Post-Pour Details and Inspection
29e38b5a-c7e6-42fb-b5ef-75bbc1d6bf8d | checkpoint | 5.1 Curing
d8ad7d5c-2f39-5d18-812b-edfb10c86cf4 | note | FREQUENCY: Each concrete pour
04f749da-1556-5a40-888f-6827f265ad69 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
8482c95a-835f-56df-b637-cfa58ab1acae | note | REFERENCE DOCUMENTS: 610.23
4f0776fa-0146-59fe-b3c5-32d9e45b551f | note | INSPECTION/TEST METHOD: Verify
f6b56587-c2fa-5002-bf2d-dd19ba4ff0b8 | note | RECORD OF CONFORMITY: This ITP signed
24ad75f2-fc83-5cb7-b8e6-e5ad45248c7d | note | IP
7e869956-9150-5dee-b659-990cd3555431 | note | RESPONSIBILITY: Fulton Hogan
97655479-4f33-5b6d-82d4-25bb92b4822a | textbox | Date Completed:
64d0665c-0734-4f13-ae9c-96f9faedb630 | checkpoint | 5.2 Formwork removal
58436730-ce5f-5cc7-a9d6-121d44f38363 | note | FREQUENCY: Each concrete pour
65d86891-b168-50e8-afee-ff0bf09d2201 | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
9815a337-0249-5224-bdb0-f28d775f4478 | note | REFERENCE DOCUMENTS: 610.25
dc0791e8-2717-5fc9-a4c8-04979a4447f7 | note | INSPECTION/TEST METHOD: Verify
c5ed666d-65c8-5531-95dc-3e4b50dae7fe | note | RECORD OF CONFORMITY: This ITP signed
31e42989-4386-50eb-a180-37c6011d01fc | note | IP
c7ba69da-861a-54f7-be88-8325de27312c | note | RESPONSIBILITY: Fulton Hogan
3e92329f-4f8f-5207-b8e2-7dd3d3f5dd89 | textbox | Date Completed:
e6b0af9e-252c-4961-8a65-eadbd66a892d | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
b0e7cd66-aa2e-5601-8708-c919dba6f7b7 | note | FREQUENCY: Each concrete pour
26f66ae4-ec55-59e1-a435-b100dc0a7419 | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
93a5e878-c324-568d-b305-065a64c45771 | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5, 607.06
42118a77-3b87-5c0e-9d52-a47eba47d7a3 | note | INSPECTION/TEST METHOD: Verify
32a4bf04-1ee1-53d1-8497-b0ca755513fe | note | RECORD OF CONFORMITY: This ITP signed
b9c534dc-fb62-5990-b57c-3f645992666e | note | IP
a97b810e-82c4-5f37-9cc1-f7ad02ab1cdd | note | RESPONSIBILITY: Fulton Hogan
2d5a1a02-3651-55f0-9cd2-00d0a6fd3adc | textbox | Date Completed:
8769fec9-d527-43bf-ae0a-caeb09dc6fa0 | checkpoint | 5.4 Concrete Sampling and Testing
2e32c0a4-1320-5c97-b236-bb7dc5e6d23f | note | FREQUENCY: Prior to lot closure
655de979-b042-5744-af43-bc4880830ddf | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
453dcc74-fb53-5d3a-999b-0e8695b8c3ba | note | REFERENCE DOCUMENTS: 610.16
2e3f63d6-a10e-5294-bd60-ba1dc1162d24 | note | INSPECTION/TEST METHOD: Verify
bb2f3455-fa6c-5325-b47b-4ffee67f11f1 | note | RECORD OF CONFORMITY: Test Reports
ff7d6c0e-d95c-5d07-9b86-f270480d32d5 | note | TP
15d7e497-ce82-539f-9415-b21d83f19192 | note | RESPONSIBILITY: Fulton Hogan
6a77d02e-1865-552d-8319-69f586cc335c | textbox | Date Completed:
5f2db4d6-0977-4d60-a154-d221e08b6541 | checkpoint | 5.5 As Built Drawings
df502035-8cd8-5f1c-9a6b-82b8cfab93a9 | note | FREQUENCY: Prior to lot closure
497ab45b-852e-53c9-a9a5-4358ac5343f5 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
7392010b-5640-5101-8753-73591ead6fcd | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
d53aff0a-1d55-5ffd-b2a2-282004169854 | note | INSPECTION/TEST METHOD: Verify
fbc0bee2-3bc5-59d4-a36e-b5f40b63929a | note | RECORD OF CONFORMITY: This ITP signed
33d44d2e-5204-59a1-aba4-8f44705ebc70 | note | IP
7712dd12-aff6-5cb3-9e6c-49b5aad10284 | note | RESPONSIBILITY: Fulton Hogan
158183e8-29aa-5284-a38f-fda1175736b4 | textbox | Date Completed:
cbc99f50-0172-4590-a3ac-a644f226f532 | checkpoint | Final Inspection
643f2475-bbd7-5fde-9be9-f3cf8585ae67 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d371c703-385a-577c-981f-0a761da8cbc1 | textbox | Print Name:
41fdb1d2-ae88-533d-a10e-16ef7f909d06 | textbox | Position:
c5f590fe-7f16-53e9-b03b-a9ce65edaea9 | textbox | Date:
133eb515-2571-4c1a-88fc-f6a335692e57 | checklist | FHC-ITP-029 - PVC TGSI Installation Rev0 | itp | FHC-ITP-029 - PVC TGSI Installation
538b6409-e082-4789-879a-2dde9f512a1a | section | Preliminary Works
06827cec-4f0d-4a12-9f0e-58df67004bd8 | checkpoint | 1.1 Check for Correct Documentation
e1f8e3ad-929a-5aea-b6c4-d247e456c42f | note | FREQUENCY: Prior to Commencing Activity
a6257017-9ba8-5697-abc8-ba170c8d93b1 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
05602ff7-dfc9-506c-a47a-f8777102e064 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
b6b869fd-c23e-5a40-99d9-1c31164843f3 | note | INSPECTION/TEST METHOD: Visual Inspection
472117b5-7a78-5fa2-ac7a-4b58882bf55d | note | RECORD OF CONFORMITY: This ITP Signed off
961cbc59-2ae7-5087-a05b-ee84f6f25127 | note | HP*
5a923780-8ba2-5293-8dce-702fc26efe72 | note | RESPONSIBILITY: Fulton Hogan Engineer
ee27b32d-7672-5b89-b97b-0425f8d87967 | textbox | Date Completed:
2acd9f31-6e08-4261-9d6e-eb6c12f4f09c | checkpoint | 1.2 Implementation of all measures and controls
849d1086-2a8c-5040-aa70-91813de1f626 | note | FREQUENCY: Prior to Commencing Activity
542c729d-7fcc-53c8-85b6-f420991f8eeb | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
b7d8074b-6f98-5310-8dc8-8159a17a7083 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
4997f7fa-d6ab-56ac-9b32-073e23dcd92b | note | INSPECTION/TEST METHOD: Inspection
b122ade7-d2eb-5acb-821f-148dbb0b186f | note | RECORD OF CONFORMITY: This ITP Signed off
5cfac833-dc93-53f7-a1f8-b5325bd8d92d | note | IP
299817d0-2d0b-5e49-9c77-f5639b65dc8e | note | RESPONSIBILITY: Fulton Hogan Engineer
b313d178-ca87-5b42-bdac-649941f9dc5e | textbox | Date Completed:
0cdeee79-35ae-47af-9b63-e2084621dc2a | checkpoint | 1.3 Check Materials
1fd0b304-2e0e-5f66-9f6d-921c83a60a16 | note | FREQUENCY: Prior to Commencing Activity
74835a4d-3719-536c-997f-65c0da4465e9 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
a95b7955-8996-538a-93e3-39aebd9a493a | note | REFERENCE DOCUMENTS: Receivable Inspection List
63458cc1-e560-5df1-9720-3dbb1552ea6b | note | INSPECTION/TEST METHOD: Visual Inspection
62ade022-cc50-5a54-901e-f5dbaa4e3a2e | note | RECORD OF CONFORMITY: This ITP Signed off
165a135f-8e89-560b-83df-db03619702dc | note | HP*
72a6c16d-856a-55c1-83c9-0caef931e58f | note | RESPONSIBILITY: Fulton Hogan Engineer
18666180-2161-5858-b2c8-f754fd13c303 | textbox | Date Completed:
b089ad69-7abc-47e8-969a-46527a06f55c | checkpoint | 1.4 Setting out
0741a71f-e511-5a65-9c52-7061eef177b6 | note | FREQUENCY: Each Lot
dc35aa50-dafc-5133-8409-6de5a5f8848c | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
4e6b3882-e60e-580e-a532-8e5036c6f78c | note | ○ Line and level of tactiles shall be set out according to design levels to suit new kerb height (if applicable).
1f42822e-6009-52c5-9894-10bd54b79831 | note | REFERENCE DOCUMENTS: Work Procedure
e9d293f3-d74d-521a-8951-5c7b9641c2f3 | note | INSPECTION/TEST METHOD: Inspection
b6ee2b52-fdc6-544e-92f8-e6ef14ae497c | note | RECORD OF CONFORMITY: This ITP Signed off
497e67fb-8a63-5774-9fcb-25aa8aa853f0 | note | WP
6c749ee7-25d2-540b-a2fd-16eb9b523019 | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
3fa053f6-b698-5a91-aed0-ceec11892b69 | textbox | Date Completed:
6fdfb365-e4e7-4f3f-b472-2b1f4f3ebd2b | section | Construction of Access Ramp Bluestone Footpath
2a7a9fa7-b700-4d90-a8af-03e115cc8f22 | checkpoint | 2.1 Base preparation
16fdcd14-090d-5d7b-9e46-32bb0bc75fc2 | note | FREQUENCY: Each lot
4177a1ae-0cb6-5e9e-8171-38c385aabc58 | note | ACCEPTANCE CRITERIA: TGSI should be laid in accordance with the site specific application and applicable standards before fixing
ad1f278a-3dfe-5f29-b4fd-924a4c779d0d | note | REFERENCE DOCUMENTS: IFC Drawings
cb44b2ea-eba2-5407-afa1-464ae1285193 | note | INSPECTION/TEST METHOD: Visual Inspection
3ec10814-e7f5-51b7-a0f1-a14f6167478f | note | RECORD OF CONFORMITY: This ITP signed off
01e89552-caa9-520c-bcf2-0e183ceab747 | note | IP
63b95723-2d6b-563f-ad91-e4b797589233 | note | RESPONSIBILITY: Fulton Hogan Engineer
98e86123-7e06-54c9-ba93-eb6e9dff47bd | textbox | Date Completed:
a55c6868-c506-478c-84f6-0460b6a08294 | checkpoint | 2.2 Placement of TGSI
745e64e8-7f1b-5566-991a-f5fd6069e315 | note | FREQUENCY: Each lot
d91806d4-52ad-53f1-ab32-34e540b96c23 | note | ACCEPTANCE CRITERIA: Ensure the placement of the TGSI are in accordance with IFC drawings and are compliant to AS1428.
7b8c7cdb-3567-5685-8548-16e22f19bfa5 | note | REFERENCE DOCUMENTS: IFC Drawings
c78407ad-3693-5f20-ba01-71b5d8d58066 | note | INSPECTION/TEST METHOD: Visual Inspection
2eba399f-3a61-52fd-9ca5-b975c166fef8 | note | RECORD OF CONFORMITY: This ITP Signed off
2904e7e6-0136-5e52-996a-97a3da8cc88d | note | HP
5ee6aa6b-9c25-5feb-b316-52f9bd221bf2 | note | RESPONSIBILITY: Fulton Hogan Engineer
acd1eed7-5db5-5176-b2b9-76b788a7cb97 | textbox | Date Completed:
00f5bfbf-8e90-4006-ac40-c59aef955d21 | signoff | AUTHORITY HOLDPOINT
c31999b4-7400-4317-87d5-c61555d09630 | section | Completion
e188859b-df6a-42ca-9ba5-12b486eb8c06 | checkpoint | 3.1 Completion
fd9baa9d-d698-5bfa-ba21-afdd6048ac70 | note | FREQUENCY: Each lot
46cc16b9-dda3-5ef2-852c-1ee3b45bf5fd | note | ACCEPTANCE CRITERIA: Ensure pavement area is free of debris and waste.
fdccd9f6-0055-5c60-a1f9-fe14577b4471 | note | REFERENCE DOCUMENTS: Visual Inspection
f184b212-a5e3-51e0-8360-29cdc56720d0 | note | INSPECTION/TEST METHOD: Visual Inspection
7d5760e2-bff4-55c2-a88c-46383f63be8b | note | RECORD OF CONFORMITY: This ITP Signed off
f735e8e5-e8da-5260-9892-2a69cd2f18bc | note | IP
cef6a3b8-f591-5b79-aaca-894f9bcb0af5 | note | RESPONSIBILITY: Fulton Hogan Engineer
3a9183c2-571c-55be-bb5d-609368ed3a37 | textbox | Date Completed:
f3797ba5-c7e1-48f4-ab64-93388db00946 | checkpoint | Final Inspection
23d8e7aa-c8a6-5655-9a36-3576a1e8faa1 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
929c8727-cbd1-51f2-9628-c52423a73ddd | textbox | Print Name:
df56f27c-15bf-5d33-90b6-f788f791806c | textbox | Position:
53546167-f6b8-59dc-9898-b98c1506a9a8 | textbox | Date: