## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
70af5071-6f28-4de9-9c62-fc96797739ab | checklist | ITP-000 - Client Pre-Construction Checklist | itp | ITP-000 - Client Pre-Construction Checklist
db43974e-a43a-40e1-a120-184302bf4ddc | section | Design and Submissions
64e7dcdd-353a-42b5-bdcf-8032763206b4 | checkpoint | 1.1 Submission & approval of concrete mix design prior to commencement of project
e3c8f27d-9791-5b2b-b92a-d2e5662a773b | note | FREQUENCY: Prior to first concrete pour
50a52aa4-034e-5982-b6cc-a37cc2536943 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
311a1d79-5c57-5797-b727-8af91522837d | note | ○ Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
c14c80d2-19e1-5804-8ef5-23f3f7ab1bce | note | ○ Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
0e3100b2-6ab3-56f7-ac50-846ddcd33580 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
4bb09fe6-b7d9-5e32-aff8-d7308ada06e8 | note | INSPECTION/TEST METHOD: Verify
be4adfc0-38b3-5b3e-83e3-d954bdd095a2 | note | RECORD OF CONFORMITY: Mix Design ITP
b44af1a7-d0bb-5d36-914f-c98604f21cb0 | note | HP
674caec7-b802-520d-b264-7c8096bbc848 | note | RESPONSIBILITY: FH Engineer / Superintendent
bee16262-4e54-57ac-8075-ccbb6e51d8e3 | textbox | Date Completed:
af54aad8-1bce-4101-a945-c28ee44ee74e | signoff | AUTHORITY HOLDPOINT
41196478-36e6-44fd-a4ba-ad838ab85526 | checkpoint | 1.2 Submission & approval of asphalt mix design prior to commencement of project
60a2d3c0-0004-5573-825f-a46cd34d5ac8 | note | FREQUENCY: Prior to commencing paving
9715fddf-2711-5fa7-98a0-02466bf29c54 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
ad585206-e46b-5612-88da-22c142b69c2a | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
faf49191-38ab-5abb-9e62-e13157e04a83 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
914faf6f-ca43-5698-ad85-7cae93471902 | note | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
8fb19a31-5a46-5bec-a320-334aa26ac7ee | note | HP
fb30b7fa-19be-58fc-8fda-48cc9abff3d3 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
a99cda88-67dd-5be2-a30e-25ebd4583abe | textbox | Date Completed:
1ee62b48-fc2d-41eb-a5b0-5084e03bbafe | signoff | AUTHORITY HOLDPOINT
8fa164cd-2f9b-4471-b15f-8f7d63b08fae | checkpoint | Final Inspection
ad5ebd0b-877d-5de4-af20-ba5ce88a4731 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
6bd77af4-e67f-5dc9-a37b-83ca9c44b771 | textbox | Print Name:
d7bae941-ceb9-5e21-87d8-f2ae6f8f9ef2 | textbox | Position:
43d5e593-3dab-59fd-bb28-a8ad008d2843 | textbox | Date:
e5ac0532-9f3e-41b0-9bd3-fd1216b67454 | checklist | ITP-001 - Subgrade Preparation | itp | ITP-001 - Subgrade Preparation
ac4c4ed8-54ed-40bd-bfc3-1793677913ca | section | Preliminary Works
7bcb6931-3eb4-4525-a8c4-546351182697 | checkpoint | 1.1 Check for correct documentation
8b9f313a-eecb-5aeb-8735-a850ae6458ff | note | FREQUENCY: Prior to commencing any activity
9d6dbe20-df5f-5558-b6cb-697bd5d27c6e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6dc908c7-8c5e-51d0-9316-36aae3aaac82 | note | – using the correct and complete set of drawings
44b8d66b-3e56-598e-ad4b-2c3725357344 | note | – all drawings are the latest revision
aa6d6cad-4e4b-587c-b5c8-c45f2d77ae87 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
623b0f8e-0588-5fe9-9e9a-93c67d6546fa | note | INSPECTION/TEST METHOD: Visual inspection
21174ee0-404a-5a65-ba6d-7f6c93ab0729 | note | RECORD OF CONFORMITY: This ITP signed off
71bb0285-c6d7-5435-a2de-ddbe86c04ee0 | note | WP
93daedf5-2e48-5e17-bf47-a62b81796624 | note | RESPONSIBILITY: Fulton Hogan
742a6a32-b909-58e9-b781-7f17935ab9d0 | textbox | Date Completed:
bb532473-74e4-4a47-b421-156dec5444f2 | checkpoint | 1.2 Implementation of all measures and controls
b73a05d1-99e9-5e09-af2b-e77d7f704e8a | note | FREQUENCY: Prior to commencing any activity
a28bd2a6-6886-58ef-959e-5bebe600f4ba | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
77858797-9c43-53d9-9f48-5b2fbe1cb324 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
470360c8-2553-5c85-aba7-a0fddf08ba44 | note | INSPECTION/TEST METHOD: Visual Inspection
d95152b3-a90d-5e9a-a8d3-6f5a885a3abd | note | RECORD OF CONFORMITY: This ITP signed off
b7205093-ca65-5d79-a966-3d2fee9adb74 | note | WP
79762ed0-ea9b-5aa3-bf51-c09b655593b8 | note | RESPONSIBILITY: Fulton Hogan
573d6af5-e249-5dd8-957b-03861e489e76 | textbox | Date Completed:
dc48bc07-d2c3-4997-97b3-5b3db357bbf5 | checkpoint | 1.3 Selection and approval of disposal site
d5be085e-ea83-5f6a-957f-ae3693f8787c | note | FREQUENCY: Prior to commencing any activity
10357d20-f7cc-51cd-a664-889b41996b61 | note | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accorance with Yarra Trams site classification report.
2c03ddd5-9299-547f-8f58-7a51a89aba26 | note | ○ It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the authorities controlling disposal of material at that location.
162f6a02-88fe-5a96-998c-7190a7904ec7 | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019-ST-0033 CL. 4.2.1.5.
a72a9b6c-34d0-5b58-ac1b-7ae8c2ef1904 | note | INSPECTION/TEST METHOD: Verify
fb5e9d80-e649-518f-8155-2aad6c6909a2 | note | RECORD OF CONFORMITY: This ITP signed off
7bd5793b-fe2b-5fc9-ae8b-19f1d1ae71d9 | note | WP
56661291-fec8-560b-b39e-e093c2261f63 | note | RESPONSIBILITY: Fulton Hogan
a74880e1-984e-5fd6-8c63-5d737b3eba20 | textbox | Date Completed:
8908d158-e27f-480f-98e6-6dc2b67c901b | section | Construction Works
23d19d8b-b3ef-4a34-8a45-496de2bf56cf | checkpoint | 2.1 Excavation
b70beadc-fa2d-5702-afc9-868f8189f62b | note | FREQUENCY: Each lot
e40650ee-9233-5845-b9dc-5d32aba884a6 | note | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of works.
4b13cb03-6e6b-5f0f-8f68-4f089e4a6bda | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4. Subgrade Preparation Work Procedure
eb162099-d9ce-5772-a3b1-89e925be0c49 | note | INSPECTION/TEST METHOD: Verify
8c613f65-ddf0-59be-b30f-c8294027c7ce | note | RECORD OF CONFORMITY: This ITP Signed Off
fc898385-86c3-549b-8878-0408d87d4103 | note | IP
5b324436-89f3-582f-9873-af1f2dd705d2 | note | RESPONSIBILITY: Fulton Hogan
e85b8104-9fb3-59ab-83dd-c1d1f9346c92 | textbox | Date Completed:
f946d3c2-9db4-4078-80c1-34b801999132 | checkpoint | 2.2 Excavation Permit
eb7b7eaa-0ffc-57d4-bb0f-69e9803aa15b | note | FREQUENCY: Each lot
29e5ba4c-b915-5341-a439-db2783fbcc1f | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
0bc68c65-1603-5d35-a7bd-3560a96ab05c | note | ○ Plant and equipment shall be appropriate for the task.
4b101260-c852-568c-9984-6fc13b438af3 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
29ad9d6f-108c-5d26-b19f-aa4c61c7fd8b | note | REFERENCE DOCUMENTS: Excavation permit
aec90c9b-fecc-5d20-99db-aad7e418cdf7 | note | INSPECTION/TEST METHOD: Verify
460a2879-cecc-5a3c-b927-3dd136507e33 | note | RECORD OF CONFORMITY: This ITP Signed Off
d046ee5f-adad-5c16-9fda-f59ebe9fecf3 | note | HP*
fae7beca-1f54-56c8-b757-f39d6acadae3 | note | RESPONSIBILITY: Site Engineer
a4981a70-8e9c-5aa4-92ed-0907bfff8928 | textbox | Date Completed:
a4376deb-4230-49f6-b35b-9bd8396f77ec | checkpoint | 2.3 Reinstatement of bonds
f7523025-998c-5d6b-8783-7b1fca93e513 | note | FREQUENCY:
d6d904d6-2f6e-5350-a8b2-5f9f268c32e9 | note | ACCEPTANCE CRITERIA: Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
553794eb-4770-5252-bf33-3b748e03e7bd | note | ○ All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
8cfc386a-2bd6-51e4-9d09-b3b4036b3b78 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
496daa37-0d72-5c98-8db6-33ae511c3187 | note | INSPECTION/TEST METHOD: Verify
11b2c347-b6ff-537e-a52b-81e15bbf11d7 | note | RECORD OF CONFORMITY: This ITP Signed Off
36b2e95f-1da9-57c9-8898-2dc9f0600cdf | note | IP
f11b7154-22d2-5d1d-a37a-458cfa30d17e | note | RESPONSIBILITY: Fulton Hogan
5fd873b5-9534-591a-a5ec-14e2fcca0f9c | textbox | Date Completed:
5b305148-cdab-4244-a889-383716289203 | checkpoint | 2.4 Inspection of subgrade material
c5f1882d-603d-5ac1-94b3-2e3e9734de62 | note | FREQUENCY: Each lot
ea294812-ed01-5533-b09a-4968eba4e7b2 | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the standard.
53913b55-3442-5425-9f34-d3feb123f41d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
929ace76-829d-5d41-9cb6-33c1a7bbd9ed | note | INSPECTION/TEST METHOD: Verify
5b76c4d3-272b-5faa-aa00-346f613f66eb | note | RECORD OF CONFORMITY: This ITP Signed Off
f16dcb1d-a4bc-5cce-a32c-467818330785 | note | HP
2a907c8e-abc3-5589-87aa-2e5dd580d75d | note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams Superintendent
aace7a21-9973-5506-beab-ce90bc1eebab | textbox | Date Completed:
75f4fdfb-bad0-4211-8798-8107d56742a1 | signoff | AUTHORITY HOLDPOINT
25b3c04e-01e9-4cad-ad41-b6b3c6b6ab24 | checkpoint | 2.5 Width and level conformity
72a37d38-caf1-5235-8445-6c4e380e9106 | note | FREQUENCY: Each lot
8d02fbb7-2737-5e9e-a690-95c2e4c32a9f | note | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings. No point in the general surface shall vary more than 12mm from a 3m straight edge.
d32746e2-d73d-5f3e-9e83-0ce3d397dadf | note | ○ Finished formation widths shall not vary more than -0 mm, +50mm from dimensions shown on the drawings
73d8cdc1-918a-567d-8633-61095838be57 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
f0d7f03a-66e8-5320-afe1-e2dae318dc06 | note | INSPECTION/TEST METHOD: Survey Report
a7b38264-9061-5828-b445-bcbd9c93bfdd | note | RECORD OF CONFORMITY: Survey Record
73dc5d26-c201-5359-9912-a1bf6aec88f7 | note | IP
b44ca641-6037-52d9-a1c8-a0b2dfc735f8 | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
abcf7329-57df-55dc-85a8-b88e6349b4e1 | textbox | Date Completed:
3e209346-a38f-418e-baf8-41cb4ebcffe7 | checkpoint | Final Inspection
eaadfe38-9025-5473-8f47-48da429a0f80 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
effd3b26-6f7c-50f8-98ff-dcb8ea3fad82 | textbox | Print Name:
e1427fdf-4c2c-5bae-9f07-cf180b358280 | textbox | Position:
e13b57ba-799d-5dff-bc0e-9d56798b0d46 | textbox | Date:
f4a05df2-9931-469f-b661-2f295551c297 | checklist | ITP-002 - Feeder Conduits and Pits | itp | ITP-002 - Feeder Conduits and Pits
424b8768-c99f-47ce-b5df-f7dbfbddd69b | section | Preliminary Works
d758274e-7f86-4fc1-86a6-b16757bacd7c | checkpoint | 1.1 Check for correct documentation
8fd80269-7645-5f1f-b0db-90e328c906c0 | note | FREQUENCY: Prior to commencing any activity
913fee1c-1c18-50ed-a80a-a2d522eb74bf | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6c87b1bb-e840-5c05-afbc-49c184cbd9dc | note | – using the correct and complete set of drawings
140bc4ff-72cb-5362-a0bd-c7b1cf3aff7b | note | – all drawings are the latest revision
301858eb-bcae-5273-82be-82fe8074252f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
f35a5063-8202-5b64-8548-4175e0f4fe77 | note | INSPECTION/TEST METHOD: Visual inspection
a0c8f9c1-786f-557f-9c01-9a5fd6d2b61c | note | RECORD OF CONFORMITY: This ITP signed off
5933c7cf-5601-5e46-a0ea-e9d1fd8ba581 | note | HP*
3cbc24ad-c5b0-51da-8719-4ef1b5a70c52 | note | RESPONSIBILITY: Fulton Hogan Engineer
3f53ab92-d08d-5342-9ccb-2972e4916642 | textbox | Date Completed:
c6fdf24a-dcd5-4f0e-974a-ef4a496a7484 | checkpoint | 1.2 Implementation of all measures and controls
464ac9cb-e091-5563-b6ba-f1fce8acf1ac | note | FREQUENCY: Prior to commencing any activity
7fb13542-d82c-5888-84ee-af132a56e532 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
7f6855e1-b514-5ed8-b94e-21d6b6c702f9 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
24740925-340d-5794-8f4a-9dad1b388024 | note | INSPECTION/TEST METHOD: Visual Inspection
f3ac9c82-47ab-531f-85ac-9a2562739308 | note | RECORD OF CONFORMITY: This ITP signed off
d01ddbc6-f079-529d-8532-d9293e9bfd8e | note | HP*
e88f044e-3c9b-53bc-88be-f1eb737ab688 | note | RESPONSIBILITY: Fulton Hogan Engineer
fc839156-9aed-51f2-89bf-6db24786f24d | textbox | Date Completed:
1beccf14-ed6b-4dbf-bd35-fec77bcac68f | checkpoint | 1.3 Materials
39227905-1f1f-5b0b-a83c-b670edefe598 | note | FREQUENCY: Per batch
c0c239b9-4ce4-518d-87c4-bc96eae53bb3 | note | ACCEPTANCE CRITERIA: Electrical supply conduit to be orange. (Heavy duty 100mm diameter UPVC)
1fc9868b-6586-5bdd-ab51-f60ebbac47cf | note | ○ Modula Stakka pits to be used for feeder pit, entries for conduits to be cut with hole saw.
ea9bfc8a-b09a-583d-a158-ab59a329bcba | note | ○ All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
71848d7c-b32d-57c9-acb8-c45e458c95bd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4 AS 2053
67a122ed-b08c-5aca-be26-6a55017aa9e2 | note | INSPECTION/TEST METHOD: Verify
71d7d302-62c0-53c5-86e3-9beb5916c998 | note | RECORD OF CONFORMITY: This ITP signed
33aeb974-eb78-5fb2-9b90-a5d3e02f97c2 | note | HP*
bd04ac35-90ca-564e-97a2-b1b730e24dee | note | RESPONSIBILITY: Fulton Hogan Engineer
070a679b-d61d-58e6-82ab-96acaf0a130c | textbox | Date Completed:
3299c875-0ca4-43da-b9d5-6b3811be283a | section | Construction Works
e9b082b2-c155-4f1f-850d-7674ddf63d5d | checkpoint | 2.1 Survey set-out
11565d2c-2cb0-5b38-a084-e242b2aa6bb0 | note | FREQUENCY: As required
f72275f5-d492-582f-b4da-16f07bd2ddc1 | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
4939a78b-1b6a-5128-8265-a32e04e5dc8c | note | ○ Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
e7466251-e371-5189-987b-2d0d70fa45a2 | note | REFERENCE DOCUMENTS: Work procedure
c675f187-2dd4-5261-b7f2-1df704bd2c55 | note | INSPECTION/TEST METHOD: Verify
bed747d9-a3db-5062-a69f-821ec95a6ff2 | note | RECORD OF CONFORMITY: This ITP signed
3a06d92a-fde9-5315-984b-4c0b9793efb0 | note | HP*
bbd6a624-71cf-5275-866c-2c95b9d59c3a | note | RESPONSIBILITY: Fulton Hogan Engineer
181d78d7-2d5f-5aa7-b8cc-4e4bfe1d7f3e | textbox | Date Completed:
a625c71a-5a3a-41ee-a170-505d4c90f166 | checkpoint | 2.2 Excavation and trenching
0ede7172-e41e-5fbf-ada6-461d3d14b9bb | note | FREQUENCY: Prior to installation
79d8d3d9-22e4-51c8-89ff-b3adf4782f1e | note | ACCEPTANCE CRITERIA: Minimum cover for underground conduits shall be 600mm
078cb4f0-724a-5a65-af86-b69c660b6baa | note | ○ Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
d7fa8bb2-0bf2-53ce-a6ba-e5a30ef77ee0 | note | ○ Trench shall maintain a minimum clearance of 300mm from all existing services where possible
691781c9-b08f-5250-9910-f44d1c83061d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
db86ab13-602d-5c75-958b-4161a0203599 | note | INSPECTION/TEST METHOD: Verify
985f4f6c-f09b-52db-be00-dad2310be8ed | note | RECORD OF CONFORMITY: This ITP signed
e973d763-fb72-57d5-85ad-d39ac2ea2a16 | note | WP
281b14fa-d546-53b0-a06b-b183c0285682 | note | RESPONSIBILITY: Fulton Hogan Engineer
78e5f59a-18f1-5142-a5b6-1c0b7d34b31b | textbox | Date Completed:
ca77925d-32d7-4e39-b5f6-92bb8faf3d22 | checkpoint | 2.3 Installation of conduits and pits
ac303d39-0f71-5cc9-9551-92a6383a5c61 | note | FREQUENCY: Each lot
fb9a66bb-42cb-5a39-9a99-724a4b63fc2d | note | ACCEPTANCE CRITERIA: Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
f3724319-c20f-5983-82e6-06ea656fabab | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm sand
7cb3c881-9a7e-57dc-9b09-f302a7cff9c0 | note | ○ Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
12681fdc-349c-5de8-8b78-0bd0c6a9a47a | note | ○ Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
dcf8ba7c-06e6-5caf-aabf-a7382406b2fc | note | ○ Conduits shall not be subject to construction loadings
b09d3760-7a13-5cf9-9dc3-1a47b20b9fe3 | note | ○ Pits shall be constructed as to allow for class D rated covers
e1df04b6-7e60-5526-929b-14fa3e9a7fd9 | note | ○ Conduits shall be placed a minimum of 100mm above pit floor.
584defd2-6ce0-51d1-aa2f-410e3deb9b88 | note | ○ A 50mm gap between conduits shall be maintained as they enter pit face.
e7986a17-f283-5e0c-878f-97e86814baa5 | note | ○ Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mm beyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
ae21479c-e36e-5ed2-a803-1e4ccdae5895 | note | ○ Conduits installed for future connections shall be installed to the track margin
fa5ec0e5-a998-5c18-bcfe-1dd127aa86a8 | note | ○ 100mm of concrete around and under pit lid to be installed for structural integrity
313501dd-3ee7-5c34-9e9a-d2701150e877 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
390e664b-eff3-51a5-8e9e-d5a996c079fb | note | INSPECTION/TEST METHOD: Visual inspection
137a8662-8764-5360-ad6c-c1c0deab76c8 | note | RECORD OF CONFORMITY: This ITP signed
41ef6892-ec39-59d3-a14e-1f01a8b26f5b | note | WP
d4a2c34c-1bfc-5d1d-b350-41c13d8aae1c | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
1c7053e5-a234-5194-91eb-de1fccfc56ab | textbox | Date Completed:
327a9c13-ffbb-416f-ac76-c5f08369cd09 | checkpoint | 2.4 Inspection of conduit installation
d6ec20dd-de17-5d5b-b440-e8d9d9a809b5 | note | FREQUENCY: Each lot
ed2ba30f-f40a-58cc-baef-fc5f4d4338d0 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspected by superintendent and conform to design drawings before any backfilling is to commence.
99e4315b-5425-5423-be53-76019ca88ffb | note | REFERENCE DOCUMENTS: Work procedure
45c99685-f6ef-55b4-a756-8acc294e8e69 | note | INSPECTION/TEST METHOD: Visual Inspection
879a0359-2e8a-5416-9832-187f56d38127 | note | RECORD OF CONFORMITY: This ITP Signed
39a4238d-c667-5796-b869-55955f58925e | note | HP
d3018ac6-3719-5bb6-9419-55d272ff8a4f | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
ad7472a1-bddb-5385-9ef0-0be77056e3f1 | textbox | Date Completed:
6526c790-f376-45f5-809c-79bdce08bbc0 | signoff | AUTHORITY HOLDPOINT
285cc5eb-046f-4f84-b0dd-aa16f2a8d9b5 | checkpoint | 2.5 Back fill of trenches
d50d923b-d9f5-5e31-890b-4e965545dfe5 | note | FREQUENCY: Each lot
751abe8f-7890-56b0-8ad5-985633c42594 | note | ACCEPTANCE CRITERIA: Backfilling (only to be used for road crossing trenches)
2a3ca926-e30b-5b3f-8848-a30d53519965 | note | – Conduit trench shall be backfilled above marker tape with crushed rock or suitable material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
3516f2ae-b433-5355-83d2-cc70ccf1adae | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
c8acf1db-ffe6-5181-b68a-1f5568cf47ee | note | INSPECTION/TEST METHOD: Verify
694a3c6c-e4e0-5547-8661-c5d3d535363b | note | RECORD OF CONFORMITY: This ITP signed
8dd63da1-5e72-529e-9e50-18f684999a3c | note | WP
22ed00ce-8131-591f-83d9-e291fe9405c6 | note | RESPONSIBILITY: Fulton Hogan Engineer
800a9231-02ce-5c64-8dd9-87aa7365dcbf | textbox | Date Completed:
bc4e8b18-822d-4f99-b727-3205e9e150f2 | checkpoint | 2.6 Installation of draw cords
ec0a35e8-862a-526b-9f57-2f5c32ddfa40 | note | FREQUENCY: Each lot
276cf4a3-6432-53f4-b933-411027dd3766 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'.
7144c361-42f5-59da-b745-497ea3d8b4f1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
e29bf431-2889-5b50-8c06-7917a86123ee | note | INSPECTION/TEST METHOD: Verify
546d0cdf-9489-5dbf-bb8a-68cd4832d633 | note | RECORD OF CONFORMITY: This ITP signed
c63ad4d4-3209-5a4a-81f3-2917b500b861 | note | WP
bcef73f8-d421-58c8-a96e-48468c50e0c2 | note | RESPONSIBILITY: Fulton Hogan Engineer
26382d85-e672-57f1-965d-2b9c6eb6593b | textbox | Date Completed:
f9bfc352-d3bc-43d8-a60d-2a315b3dac99 | checkpoint | 2.7 Compaction
46db9d37-fde4-5fb7-87eb-c6b539a8233a | note | FREQUENCY: Each lot
9c2cbce9-17ef-53f9-82a2-24a32e727773 | note | ACCEPTANCE CRITERIA: Bedding and backfill material to be compacted using mechanical plant
73ca2dab-a742-5a26-82b8-7d3dac37a722 | note | ○ During compaction optimum moisture content of bedding and select fill is within 85% to 115%
c3aac49a-f40c-5a9f-8386-d1e0151e68e3 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
9a5bca46-6b38-5f2c-99fc-a6902f62473c | note | INSPECTION/TEST METHOD: Verify
de2860b1-ee25-5934-bf38-06c84a060b79 | note | RECORD OF CONFORMITY: This ITP signed
f2c48a66-8096-56fe-b422-321150df9933 | note | IP
dbf730f4-2250-5936-a3ab-37552b5d82d0 | note | RESPONSIBILITY: Fulton Hogan Engineer
07577085-4042-5e67-8eef-1dcf47fe1b8e | textbox | Date Completed:
a10ee35d-b3fb-465f-85b1-01f2c2854e0d | checkpoint | 2.8 Feeder pits & pit lids
48a6904e-1797-5b20-8044-8185a2b11119 | note | FREQUENCY: Each lot
18554eed-a20d-5604-9a92-0eb242d40d37 | note | ACCEPTANCE CRITERIA: Feeder pits to be constructed and installed as per drawings
545344b4-4229-5560-bd6e-59c090ba51c7 | note | ○ All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar.
b215e085-e973-577d-bc46-10dd4110de73 | note | ○ Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
9748eea5-f3b0-5050-bd6b-4b14c6c2b1f9 | note | ○ Gatic pit lids shall be filled with structural grade concrete.
3d0b8eb9-ad34-5daa-a699-67334f106521 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
dc64505a-e118-52de-ac4b-ed6ee61b3984 | note | INSPECTION/TEST METHOD: Verify
b3c7290d-6534-52f4-9881-9b6f30d4f8c9 | note | RECORD OF CONFORMITY: This ITP signed
56742f18-9e4f-5bf8-a043-5bca1698db6f | note | WP
f1c347fa-0205-58be-843a-efd5aa630ec1 | note | RESPONSIBILITY: Fulton Hogan Engineer
649f2c17-6dbe-59f7-8b1c-0aaa51e5ffe8 | textbox | Date Completed:
d29b3afc-3df7-4eb3-9102-7014333c6dd8 | checkpoint | Final Inspection
652b6b6e-d165-5d16-8cf6-aca97efb45bf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3c0b65f0-319f-50ea-a3ed-31c601ff4b2d | textbox | Print Name:
f825bce8-6baf-534f-a4ed-32164c2ab854 | textbox | Position:
104218d7-27f5-5f3f-94f6-1843e7b698aa | textbox | Date:
f71f75f7-5a0f-4e10-bd88-d870030365a3 | checklist | ITP-003 - Electrical and Communication Conduit | itp | ITP-003 - Electrical and Communication Conduit
b0fc17dd-0f8c-4aee-9f72-45a7ba1f3e69 | section | Preliminary Works
3ea9bd06-c35b-489a-915a-0b70c80d40f0 | checkpoint | 1.1 Check for correct documentation
feaa42a0-8e69-5ae8-9230-71cf3588cfa0 | note | FREQUENCY: Prior to commencing any activity
ceb19796-2d94-50f4-b4d6-f2e8c1440bc9 | note | ACCEPTANCE CRITERIA: Employees and sub contractors shall be issued with the most current and complete construction drawings
730bbad7-49aa-5696-acd7-978112b6451f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
d4d01ab0-186f-547a-85fe-dfc060c8ce0e | note | INSPECTION/TEST METHOD: Visual inspection
183ea139-30d8-5573-afff-6d000ef2c2d7 | note | RECORD OF CONFORMITY: This ITP signed off
8dff84c6-b214-5fc6-accc-5b124c07c8c9 | note | HP*
ab067d2d-71db-51ec-992f-92438bb6325a | note | RESPONSIBILITY: Fulton Hogan Engineer
ac3867c8-9071-5054-80f2-aec58eefef36 | textbox | Date Completed:
25612433-9405-4db4-9bf7-63293e962fee | checkpoint | 1.2 Implementation of all measures and controls
399830ce-1d7a-50d2-9ff5-41f833bdd63d | note | FREQUENCY: Prior to commencing any activity
90b70083-bc4c-584b-bf51-fbbbdc19b76a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
1daf181b-d1a5-5422-b36f-297189c0e494 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
3a4f746a-d30b-5e00-bfca-afa68fc45f45 | note | INSPECTION/TEST METHOD: Visual Inspection
c423df40-aed4-58cc-bb98-878cb7caf708 | note | RECORD OF CONFORMITY: This ITP signed off
1a1c3630-f9df-53a6-bf21-70989744b66f | note | HP*
6875c7ce-8946-5025-876d-8c7d678d5a55 | note | RESPONSIBILITY: Fulton Hogan Engineer
f42e448e-1fe0-53a6-b577-7ae8bd268c02 | textbox | Date Completed:
beb22483-12aa-4c41-8991-bdd9ea3b625a | checkpoint | 1.3 Materials
80997069-ea4e-50df-a556-4360dab924bc | note | FREQUENCY: Per Batch
7c3a1e8d-dc65-5bff-8686-11c839a5ce08 | note | ACCEPTANCE CRITERIA: Electrical supply conduit to be Orange and rigid HD UPVC of sizes as required.
bcccdd25-12f1-54ef-91e6-39e6123fa043 | note | ○ Communications conduit to be White and rigid UPVC of either 32 or 50mm size or larger as required as outlined in the drawings.
c72d47b9-9ef1-5027-854a-09f11ecaec14 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.1 AS 2053
36087dd8-d545-5aa6-982d-0e3ad4e30246 | note | INSPECTION/TEST METHOD: Verify
bd976491-8df1-5807-ba8a-f8fa88ec453a | note | RECORD OF CONFORMITY: This ITP signed
2e1df166-a856-5c27-ad0b-c254215168df | note | HP*
5cfe3526-31c9-50cb-ba44-2d7e36f6cd53 | note | RESPONSIBILITY: Fulton Hogan Engineer
3b03288d-020b-5745-9577-be889175ac57 | textbox | Date Completed:
d56a0c71-08f9-455f-9811-73740527fb67 | section | Construction Works
88fa7106-a260-461d-9785-86391b327779 | checkpoint | 2.1 Survey set-out
820bb83a-8f75-5a09-b499-2ae40713d6d6 | note | FREQUENCY: As required
78516f26-9457-5277-befb-13a49c977946 | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
013b474a-b04c-5180-b504-d4346774ee20 | note | REFERENCE DOCUMENTS: Work procedure
68f5438b-4ba5-5e74-ac44-feddfdc4f450 | note | INSPECTION/TEST METHOD: Verify
fd5056eb-f73a-5d44-adde-e4b1bf3454ad | note | RECORD OF CONFORMITY: This ITP signed
45a3a6ad-05af-56d0-a82a-01cb51a87d87 | note | HP*
28b3f508-7bf1-5bc3-8ea7-3d70ec187048 | note | RESPONSIBILITY: Fulton Hogan Engineer
83344a47-2e21-5e30-8779-fbe90f3c80a4 | textbox | Date Completed:
c237d065-e1fb-4b7d-9e80-07763ce62df5 | checkpoint | 2.2 Excavation and Trenching
bcd91ca2-c06f-5f4a-bb4d-fb0d3b6ca701 | note | FREQUENCY: Prior to Installation
cc03f5a1-652d-5cf6-a5d4-8ca445a9b801 | note | ACCEPTANCE CRITERIA: Minimum cover for underground conduits shall be 600mm
83b0477f-355c-51fd-a787-e28612943529 | note | ○ Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
07db6bda-0d8a-54ee-ac22-01686cf74c52 | note | ○ Trench shall maintain a minimum clearance of 300mm from all existing services where possible
f3837f45-f5ba-5d62-93d2-8baea2241d7f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
bcce986d-faa1-54ce-9d6d-f8a07b4f55dd | note | INSPECTION/TEST METHOD: Verify
4e32c364-212f-504e-949b-e58cb06fe992 | note | RECORD OF CONFORMITY: This ITP signed
0feb4a65-298a-59b7-be10-d36fdc53eacf | note | WP
862e4f28-245e-552a-bb92-26ebb4363271 | note | RESPONSIBILITY: Fulton Hogan Engineer
d76a6410-2b7b-5c0b-8fb2-277f14f34788 | textbox | Date Completed:
95d0dbe2-4a67-4854-a1ac-33c4be143322 | checkpoint | 2.3 Installation of Conduits and pits
f12f5c3f-1c78-5df5-a34b-34e83d304096 | note | FREQUENCY: Each Lot
53099cbd-d2d0-50f3-9577-5a395ea2f439 | note | ACCEPTANCE CRITERIA: Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
c3782706-da28-5904-adb5-753d5d111ee5 | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand
bed7e3e2-2a11-5541-9d85-7758179b1f85 | note | ○ Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
a0d738f4-e414-541a-8c42-728fab4e5744 | note | ○ Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
dbe5456d-b50d-56e5-99b5-2b116cf18be8 | note | ○ Conduits shall not be subject to construction loadings
dd0ae666-da97-5930-ab1d-9d9b64bc4477 | note | ○ Bottom of lowest conduit shall maintain a minimum 100mm above pit floor
a26c9250-762b-5042-8538-1b5dca6f5d19 | note | ○ Conduits shall be capped with UPVC electrical caps
a253625f-9943-5c97-9577-cd1bae38631f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
87cd52bd-78df-5d1b-9094-d3d39fee5e2e | note | INSPECTION/TEST METHOD: Visual inspection
079564ad-2ff6-5482-b412-4f482603c722 | note | RECORD OF CONFORMITY: This ITP signed
5b9a205c-7234-5f58-9b26-7b16945a1176 | note | WP
c7ba9daa-0c04-59c2-ba24-1603b29ed0ba | note | RESPONSIBILITY: Fulton Hogan Engineer/ YT
234bd7a2-7740-5c02-91ea-3756fcacbb79 | textbox | Date Completed:
6744eab4-d17c-4798-98dc-fb7532a1a9c8 | checkpoint | 2.4 Inspection of conduit installation
b7cded97-3cd6-56ef-b9ad-1db4acafd18c | note | FREQUENCY: Each Lot
242fef25-6a5c-5b81-a62b-251c078152d9 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
282bb474-49ed-5569-990d-1f36dadf0b69 | note | REFERENCE DOCUMENTS: Work procedure
50f6bf10-9da6-5128-a9cd-4518658919b3 | note | INSPECTION/TEST METHOD: Visual Inspection
1f928ce5-3671-50bd-a381-b5b4a4b4f4a9 | note | RECORD OF CONFORMITY: This ITP Signed
7bc6978d-89b7-5010-a530-b280c23952bb | note | HP
e4300954-b608-5558-8c91-75047f2047aa | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
6e2f8148-90b2-5845-bd56-0d71ecaa32c1 | textbox | Date Completed:
3891e76c-fbef-493e-aa2d-3b3df007a559 | signoff | AUTHORITY HOLDPOINT
443ec7a6-b8d3-44e8-a654-0efcf763a561 | checkpoint | 2.5 Back Fill of Trenches
0e9ccbac-43ed-551d-9516-d31e424e6be4 | note | FREQUENCY: Each Lot
4a1ed21f-0120-5888-8c68-c5aa2f3f43b2 | note | ACCEPTANCE CRITERIA: Backfilling (for trenching or road crossings)
6b530ee2-2129-592b-868b-ba27e7b90bf6 | note | – Conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction using handheld mechanical plant
a07eaf0f-fc84-5e1b-a5da-a5d80f212f87 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
a3bf080a-a286-5ef8-9c37-ad6d47fae14d | note | INSPECTION/TEST METHOD: Verify
a804ecd5-2bb2-5fbe-8970-40590f2931f4 | note | RECORD OF CONFORMITY: This ITP signed
4548668a-83cc-5609-83c1-d9404e6529f8 | note | IP
3ac41929-322f-5789-88cb-56812c169f23 | note | RESPONSIBILITY: Fulton Hogan Engineer
05a35e1e-516e-5360-846d-6d6e0fb258da | textbox | Date Completed:
6c701f67-5eb9-426c-ae9b-89f10f1e7162 | checkpoint | 2.6 Installation of Draw Cords
a08a9734-7424-5d10-986d-2850e12eddf4 | note | FREQUENCY: Each Lot
ae5d6ec2-d390-583c-87f6-a3fb84bbc7b8 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit, material to be used shall be 6mm 'telstra rope'
84afe8cf-c070-5a2e-8a85-5d611fe1ea83 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
226aa993-6ee7-53c9-9aa4-889263f499cd | note | INSPECTION/TEST METHOD: Verify
ee7a448e-2e36-5a85-aeed-5bd481c522fe | note | RECORD OF CONFORMITY: This ITP signed
5de27f98-9d60-51cc-b4d7-9969ea4aadc0 | note | IP
2fb6c97b-86f6-5371-a74f-c37001c29814 | note | RESPONSIBILITY: Fulton Hogan Engineer
9967d35a-7097-52c3-b735-18e238f7c0a2 | textbox | Date Completed:
780f383e-cfbb-446c-888b-baa401fad2f6 | checkpoint | 2.7 Compaction
52e3deb2-73d0-5e1e-acab-6f5f164ec187 | note | FREQUENCY: Each Lot
6d29bf84-27a7-51ef-acc8-db4d627d1873 | note | ACCEPTANCE CRITERIA: During compaction optimum moisture content of bedding and select fill is within 85% to 115% as provided by suppliers
66d1a918-a884-52ac-a41b-7f484c69c02a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
9543e8bf-8036-504e-afc8-f296b774fd92 | note | INSPECTION/TEST METHOD: Verify
5f4cf11b-6625-580c-aedb-d56041abcc9a | note | RECORD OF CONFORMITY: This ITP signed
3de0a9b5-eca2-5fe9-927d-a3bbdfe3c090 | note | HP*
c5bc5264-237a-58b3-b2f5-d2c8799ce044 | note | RESPONSIBILITY: Fulton Hogan Engineer
2df4709d-c61c-5701-8e10-6a6a81d37504 | textbox | Date Completed:
256f68d5-f5af-44cf-8a02-16b7f3f8e4a6 | checkpoint | Final Inspection
7eaedd9e-9a57-5219-918f-2267389bf380 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3b9d0882-65c1-5051-92bb-2a1a2a2dc476 | textbox | Print Name:
3212c419-f165-53af-94fe-ad4ec5bad6fe | textbox | Position:
e7a9465e-cd8d-50d1-a208-7f3b1522c839 | textbox | Date:
756fd22d-9bb0-429e-85e1-02d29e4c7c12 | checklist | ITP-004a - Class 2 Base Course Placement | itp | ITP-004a - Class 2 Base Course Placement
25f5aaea-e8ad-4740-b01b-71cd48c90573 | section | Preliminary Works
8d12871e-7bea-4ab5-b854-c1be662e2c89 | checkpoint | 1.1 Check for correct documentation
c6364d94-aa99-5f85-a259-2c5e252b6de7 | note | FREQUENCY: Prior to commencing any activity
45bd7c79-f887-5605-a849-90a24f55adc9 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub contractors are using the most current and complete set of construction drawings.
7b271ca5-e1f9-5aad-ae72-726a88e0b4c5 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
5eaa5c3e-a51b-5c07-b00c-9306589feb5a | note | INSPECTION/TEST METHOD: Visual inspection
e5908491-6cca-5231-8c7b-f62619e2070c | note | RECORD OF CONFORMITY: This ITP signed
b76b5fd9-6b82-57ef-8198-e9f8d14fbbf4 | note | HP*
fa30d8b3-fb8b-53a4-9d2a-a3b4972ea567 | note | RESPONSIBILITY: FH Engineer
c988a48b-ee37-54ff-88c7-9269acef60c8 | textbox | Date Completed:
9b938346-ec33-4d16-ba6c-5044759552f7 | checkpoint | 1.2 Implementation of all measures and controls
3a137eea-b10b-5aa0-b352-66e32acac6df | note | FREQUENCY: Prior to commencing any activity
a9b109a8-5bac-5763-9187-df2c55bf9ac0 | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
86dfa7b2-1d7d-5935-8fed-9320ac049650 | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
8e3861c9-70e6-56a6-a6cf-0e7df8a45be4 | note | INSPECTION/TEST METHOD: Verify
b21f0fff-8384-5b79-8bf6-74aff51c4b41 | note | RECORD OF CONFORMITY: This ITP signed
88aab369-883c-591a-8003-cb693495e860 | note | HP*
f3d226c0-1b56-5f3a-b542-8199ef265b4c | note | RESPONSIBILITY: FH Engineer
5ecddc5d-11d7-5a02-ac18-a2f4655940f7 | textbox | Date Completed:
fad76927-a65f-40c9-952f-35e60babe595 | checkpoint | 1.3 Material Compliance
2f1f1be6-9ebf-5045-a236-ef4edb94f5c0 | note | FREQUENCY: Prior to commencing any activity
88a4b2cc-4f80-52b0-998b-8827dff810ae | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
fd578ef9-3caf-52ac-aa9a-f4998f18160a | note | REFERENCE DOCUMENTS: CE-019-ST-0033
b2ac2dbd-caba-5bca-a948-245cdd34fb10 | note | INSPECTION/TEST METHOD: Document Review
7e195b50-38d2-580b-aeae-1965c283c850 | note | RECORD OF CONFORMITY: Test Reports from supplier
77b87a9d-a3b7-565c-ac10-2076fbe81a7c | note | HP*
203a772e-5946-581d-b832-b43793a9afee | note | RESPONSIBILITY: FH Engineer
b4f8b96c-6039-5bad-8303-141f0dd6c1cb | textbox | Date Completed:
5d75f0cf-1421-49ad-a431-11905e9d4802 | section | Construction Works
0c1093f0-77eb-47e0-be20-89660601f4e8 | checkpoint | 2.1 Sub Base
19318f09-76b8-53c9-9939-fbef5670d408 | note | FREQUENCY: Each Lot
306c6892-ddad-5663-80a2-7b20c25dc593 | note | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
fcec5d56-e280-5f9b-a545-d175e49fa8f6 | note | ○ ITP-001 HP for subgrade inspection signed off
385f4276-4dfb-532f-8b7d-1339d5ac4fa3 | note | REFERENCE DOCUMENTS: VicRoads 173.03
7fa1881b-fcb1-54db-a414-723446ea853b | note | INSPECTION/TEST METHOD: Inspection / Test Method
1860b99b-7df9-5ea8-885c-0e5dc9ab4db0 | note | RECORD OF CONFORMITY: This ITP signed
c9cc4b06-bc68-58a5-aa71-9194ffb217cd | note | HP*
8f0f1337-49b6-558e-a1f8-9eec619401a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
0456ff72-98a9-5412-9ded-7baca8298737 | textbox | Date Completed:
22b151c3-c6a5-4480-9860-8d3cd6cd3386 | checkpoint | 2.2 Spreading material
e1a00720-c6a6-5058-9627-acfa39bd9e20 | note | FREQUENCY: Each lot
be43be3d-3344-562f-ac64-3bb5f5ab6490 | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 150 mm in compacted thickness
f737aeee-ba42-5739-b9ba-123076f0b611 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
ffd4f03a-a0d2-55d1-91b0-819f0a0d8830 | note | INSPECTION/TEST METHOD: Visual Inspection
a64fbd96-7ad5-5c03-84d9-e51a704abc5d | note | RECORD OF CONFORMITY: This ITP signed off
41741d87-637c-5c62-8009-14290182cdb6 | note | IP
3d777bbb-f922-51fe-ac30-fb7cdaba77ec | note | RESPONSIBILITY: FH Engineer
305f811d-5244-50f2-8fc4-ebbae4e3a606 | textbox | Date Completed:
5447498d-9409-4b44-a865-db687475dfa1 | checkpoint | 2.3 Compaction
97a9fd40-9c5e-57a6-b3f2-1764de2ad766 | note | FREQUENCY: Each lot
af2e43db-6961-5e3a-b020-aa1ed190a09b | note | ACCEPTANCE CRITERIA: Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content.
c2753511-6652-590b-b210-d60a6342e15c | note | ○ Each layer of material shall be separately compacted to a density of not less than 95% Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test.
37211dff-fbe5-507d-bec6-5bc95de2471a | note | ○ Compaction testing shall be carried out once per days production and shall comprise of three samples
e15da6d3-2a55-516a-a000-292cf89838aa | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
36f23535-5485-5414-a199-0dda1272d363 | note | INSPECTION/TEST METHOD: Visual Inspection
49164aa4-6451-5430-97b4-efdad6e9b8ad | note | RECORD OF CONFORMITY: Test Results
73783109-2cab-5f1d-8361-0faaf36bf503 | note | TP
672ab339-3e62-5992-8f53-9ca341469852 | note | RESPONSIBILITY: FH Engineer
e7b8b829-c357-5e3c-8c0a-82fbc77e7b8d | textbox | Date Completed:
10a7d3a6-b2b8-4d7b-978b-7f59bfc0a076 | checkpoint | 2.4 Level Checking and Conformance
5e4c3dbf-f669-54f5-b13b-5b5929a06c4f | note | FREQUENCY:
2ce3c3db-a144-5ba4-8281-07f8673e672d | note | ACCEPTANCE CRITERIA: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
d6de735e-6618-5eb1-8a2c-99d90cbba20d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
6b1b4d90-b615-5485-9287-04abf56fc6b9 | note | INSPECTION/TEST METHOD: Verify
99811203-7c99-5f48-bbdc-6965aa0169e6 | note | RECORD OF CONFORMITY: This ITP signed off
0c2751c0-8162-5bf2-bb4b-5ba1df76c6c1 | note | IP
71832ff3-13fa-5582-ba29-b0ea89395b8a | note | RESPONSIBILITY: FH Engineer
f63e9918-2275-5f67-a034-bdbfafd3db63 | textbox | Date Completed:
a6274ddb-6db7-44b0-82bc-4a353fd96b0d | checkpoint | 2.5 Finished surface
aef42cb6-5812-53a6-a1c2-d642fab230bf | note | FREQUENCY: Each lot
652ea34a-2bda-55c2-8f2a-832693052565 | note | ACCEPTANCE CRITERIA: Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
91f87649-d18f-58d8-8b22-cf34b35f0626 | note | ○ Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
67abcc4f-83a3-5093-a966-97e0023206a0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.2.8, Contract drawings
09c37ee7-3dc2-5201-b93f-60242bf1cef3 | note | INSPECTION/TEST METHOD: Visual inspection
caf41923-0ed4-5c21-a1ab-1ab89d0cdb0c | note | RECORD OF CONFORMITY: This ITP signed off
565e1d97-183c-5b9f-9a3a-614f1cf0be55 | note | SCP
4b7e7fc3-e5e6-5dda-ac1d-7c6a032892e9 | note | RESPONSIBILITY: Surveyor/FH Engineer
a3c0910b-75d7-5904-ad8b-6c6568215d57 | textbox | Date Completed:
f25a388e-0146-4e97-b1f0-5e40dfd462b4 | checkpoint | Final Inspection
b31af310-eecd-576e-9f0f-0a41e60e8f67 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
dfff958b-df70-510c-b6a8-f9ce045d5c6b | textbox | Print Name:
dc1cbed3-b485-512a-ab21-4b401a660042 | textbox | Position:
29f236a6-e39f-5455-92c1-e4cf7c044b7a | textbox | Date:
9526e561-5f3e-4fce-bd82-44ee15f69e94 | checklist | ITP-004b - Cement Treated Crush Rock Sub Base | itp | ITP-004b - Cement Treated Crush Rock Sub Base
da1623bd-1a52-4181-9d0d-bf58b9ff20be | section | Preliminary Works
72440417-a4c7-4000-80ca-d79e066e11d5 | checkpoint | 1.1 Check for correct documentation
66fb2f32-b2a3-58b2-9bb9-ee1ba4d618ea | note | FREQUENCY: Prior to commencing any activity
06cada76-488c-5079-97aa-5b47fcb4e16c | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and complete design drawing.
54608efb-f5e2-5d0b-bf10-4d70efc359be | note | REFERENCE DOCUMENTS: Drawings and drawing registers
14adcd22-1abc-502d-ac1b-291e48439fd6 | note | INSPECTION/TEST METHOD: Visual inspection
26284103-7c4f-5fe5-b4c0-f6b5e820912f | note | RECORD OF CONFORMITY: This ITP signed
63661fa4-7139-55c2-963c-bd7e1dff41fd | note | HP*
dbcf4fa2-f6a1-5a61-8a1d-3d3c205b473a | note | RESPONSIBILITY: Fulton Hogan Engineer
0e40fa8a-9f58-5178-b7f2-cdf6d4f2f05c | textbox | Date Completed:
3ad7d3e5-aff7-4f7a-9dda-9be6007a26e5 | checkpoint | 1.2 Implementation of all measures and controls
11225d64-0d64-5e84-890f-19219ae5ce9b | note | FREQUENCY: Prior to commencing any activity
9162832a-5dfd-5cf8-9355-b88326dfba88 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
0cb92c55-4ebc-5f48-8233-d6e3811714ca | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
c8147214-4688-5b6c-bcf9-f49c8ac5596b | note | INSPECTION/TEST METHOD: Visual Inspection
f88380bc-a55a-5bdc-8089-662b4c6510b6 | note | RECORD OF CONFORMITY: This ITP signed
59110d3d-4487-5743-ba13-5b33cff891cc | note | HP*
785230f9-d6e2-50a1-9100-d86f2f7e7063 | note | RESPONSIBILITY: Fulton Hogan Engineer
30bbb48a-bdc5-5dd7-aa07-4828bfcb437a | textbox | Date Completed:
acdb0b1e-9413-430a-9654-21af9af804cf | checkpoint | 1.3 Confirm CTCR is appropriate mix
87654721-7984-5ec8-a52e-be672431e614 | note | FREQUENCY: Prior to commencing any activity
e9beebab-78b1-52dd-baf4-db4f14a9a2a4 | note | ACCEPTANCE CRITERIA: Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
9677c09a-be53-5e62-af53-78b9e45057d4 | note | ○ CTCR shall be tested in accordance with 815.141 by supplier
74559e86-835e-54b0-86dc-c663f29b5233 | note | REFERENCE DOCUMENTS: Design mix specifications / delivery docket
1c0ec08d-5fb1-5fea-addf-687427e56f3e | note | INSPECTION/TEST METHOD: Inspection
aeb34767-0bd2-5d63-8030-f03e7f5b9535 | note | RECORD OF CONFORMITY: This ITP signed
eb241e89-e0fb-5a20-b4d8-a691b80f1e99 | note | HP*
f5c0f61c-1972-5886-aac4-efe367e7ce46 | note | RESPONSIBILITY: Fulton Hogan Engineer
b909917d-1e31-5050-8743-aab081c6339b | textbox | Date Completed:
4cf44f47-36a0-4b7b-b6f1-18d1024aa9a3 | section | Construction Works
3e68d62e-9782-4020-9a24-ccd5779aaffe | checkpoint | 2.1 Sub base
5b85d683-46d6-55ab-8935-ba7fb0f2cec1 | note | FREQUENCY: Each lot
b834c515-1d4c-5a0d-a325-0854ce37830f | note | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
1ec2c28e-8ea9-5370-9bcc-5a4f30d83954 | note | ○ ITP-001 HP for subgrade inspection signed off.
22117adc-5ab6-5009-a290-c2aafdca6cd6 | note | REFERENCE DOCUMENTS: VicRoads 173.03
097cc047-8471-5b45-a00a-c0785bd3629a | note | INSPECTION/TEST METHOD: Inspection / Test Method
6a5c952a-9555-55c6-a90a-f8cf542ed54f | note | RECORD OF CONFORMITY: This ITP signed
014e0c7a-04ea-57e0-9a02-ef1eedd7f573 | note | HP*
f2e94c23-4ffd-546f-a241-23755c6d9c69 | note | RESPONSIBILITY: Fulton Hogan Engineer
5f074198-e490-58a3-9be0-b4413fdfabe2 | textbox | Date Completed:
2c943a4d-90f7-45bd-b45d-324a93f3de71 | checkpoint | 2.2 Moisture content
9a47e2a7-e4bc-5808-9c96-6b42637297b9 | note | FREQUENCY: Each lot
d9cbdecc-dcad-5a97-a1d3-dd792e9866b6 | note | ACCEPTANCE CRITERIA: Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
c768765c-45ff-5694-bee7-7f54f8f086eb | note | REFERENCE DOCUMENTS: VicRoads 306.05
6bfe499f-6d12-5133-aa21-063bd85c0826 | note | INSPECTION/TEST METHOD: Inspection / Test Method
46438edb-b288-50d2-9d0e-60b97c9eedb9 | note | RECORD OF CONFORMITY: Record of conformity
02d76023-926a-53f7-82cb-71d8edd62ee4 | note | IP
08d2c2c6-63be-5ee4-83c1-51099698ff00 | note | RESPONSIBILITY: Fulton Hogan Engineer
b4f7d33d-80e2-5837-9ada-58a14bd2fb4c | textbox | Date Completed:
c19623b2-c376-4328-bfb6-3ab149d8f033 | checkpoint | 2.3 Jointing
02e46139-a569-5517-947c-78aa086d2339 | note | FREQUENCY: Each lot
353df457-1a75-5bfc-87d9-0e2a20b72673 | note | ACCEPTANCE CRITERIA: Material shall be spread to minimise number of joins.
f1244870-f71f-509a-bae2-6ead81b6f83b | note | ○ Transverse joints in adjoining paver runs shall be offsset by >2m
70161af8-1250-5576-b9bb-5cbe7fcfd875 | note | ○ Longitudinal joints shall be offset from each layer >150mm
2f6d2ab6-bfad-503e-89a7-497ecfbe0044 | note | ○ Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
cc20264e-2df9-5b34-931a-ee965755903e | note | REFERENCE DOCUMENTS: VicRoads 306.08
8a3f0ee1-2da6-5b90-a248-3efeffe526c8 | note | INSPECTION/TEST METHOD: Visual inspection
d16631e3-5934-58c3-a236-809339b8fb18 | note | RECORD OF CONFORMITY: This ITP signed
2647a8f5-9c89-503b-8b05-7951467ecfcc | note | HP*
8fb382ab-5fb0-5da8-bd5e-4a5f64b927e2 | note | RESPONSIBILITY: Fulton Hogan Engineer
1faf809f-c81c-53f2-a1b0-e16580c640f8 | textbox | Date Completed:
f6a661d7-a8a6-4351-8cf9-507ece853e01 | checkpoint | 2.4 Conformity with drawings
fc60e74e-7a93-5904-af8f-a1e78864652c | note | FREQUENCY: Each lot
6a15bfec-bdaf-5c45-a363-4ce55957419d | note | ACCEPTANCE CRITERIA: Pavement sub base shall be finished to smooth and uniform surface
374107f6-6dd3-5f67-b9a5-ad3dd0fa1feb | note | ○ Surface of sub grade shall not lie more than 12mm below a 3m straightedge
8bc9aa76-d24d-567b-81d9-036f0a654971 | note | ○ Subgrade height shall lie within +15 to -25mm
b31c0bcc-4f7a-5f1a-8461-0132fe81a281 | note | ○ Sub base height shall lie within +10 to -25mm
321f4f76-9d48-57dc-b065-98b08e5945b8 | note | REFERENCE DOCUMENTS: VicRoads 306.03, 306.11
8b7b04a3-e4a5-5767-a4e5-0a03bbfbd94c | note | INSPECTION/TEST METHOD: Visual inspection
47c07950-47be-5b43-850a-aee76375ec43 | note | RECORD OF CONFORMITY: This ITP signed
66dc515a-b30c-5562-9da0-55b96333e1fd | note | WP
657bc2e7-6d96-56b6-961e-59e89d37ed12 | note | RESPONSIBILITY: Fulton Hogan Engineer
b42ec1f6-2511-507d-abef-c3bfe16b6185 | textbox | Date Completed:
701f2559-0641-4206-b8d8-a3e5c8a9b67e | checkpoint | 2.5 Curing
c61a8fae-9311-5d9f-b7ac-b068e584da6b | note | FREQUENCY: Each lot
5935b358-1462-5441-9ced-c20671be2134 | note | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
1700fb65-b09a-5b87-bcd2-245c1ed7b8b1 | note | ○ As per VicRoads, 4000m2 shall be maximum lot size
f40f8e2d-0810-55a3-ae7e-c34be2df5fdc | note | ○ No trafficking before 24hrs unless approved by superintendent
2109b576-18b1-5d23-80d9-c6aa444647e1 | note | REFERENCE DOCUMENTS: VicRoads 306.11
16c8c833-19f8-5bbe-a911-317f92f60e51 | note | INSPECTION/TEST METHOD: Visual inspection
aeae18a2-d51d-5fca-ae86-ca4828d600a8 | note | RECORD OF CONFORMITY: This ITP signed
8f0e2449-5471-5e6a-a312-198f075613b1 | note | IP
4ee3311a-dac2-52d8-9e39-1bf56a5d08f1 | note | RESPONSIBILITY: Fulton Hogan Engineer
885cb0aa-261c-582b-9cd1-e5d9b95c96d5 | textbox | Date Completed:
694ef6b4-ce42-414b-a239-5a8846627e22 | checkpoint | 2.6 Compaction testing
cac4cfaf-5485-5ecc-bba0-4b09a20ea249 | note | FREQUENCY: Each lot
89b91489-8d9f-569e-8d39-9a967c8b17c4 | note | ACCEPTANCE CRITERIA: CT material shall be placed, trimmed to level and compacted within allowable working time (306.091)
6d2c79fb-6820-5155-b02d-105f92a2fc00 | note | ○ At completion of compaction, any segregation shall be rectified
b1f90fcd-954c-508d-b1f8-0b53a7ce01e1 | note | ○ >500m2 96% modified compaction 6 tests
3190d9ab-1ee8-568e-9ad0-38b2e99886e9 | note | ○ <500m2 98% modified compaction 3 tests
421fec50-cd1c-5d69-ab4c-492a942d259b | note | REFERENCE DOCUMENTS: VicRoads 306.09, 306.11
4cb81930-5f4b-56ad-81e5-0bea92af3a3e | note | INSPECTION/TEST METHOD: Visual inspection
d4a57246-4fe7-52b9-9855-8fcce51a3085 | note | RECORD OF CONFORMITY: This ITP signed
97c83726-1576-5a33-b2a2-7bd1b03e54a7 | note | TP
67055eca-42d8-5cbf-abe6-e79554e068f3 | note | RESPONSIBILITY: Fulton Hogan Engineer
b0e99970-3103-5e09-819c-2cba0b6f90a5 | textbox | Date Completed:
77a5b367-506f-4504-942d-4040e7e44557 | checkpoint | Final Inspection
d2cee1da-d58b-55be-884a-75f56d87a3d9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
77487a74-6a83-5de7-a900-3adcccb68338 | textbox | Print Name:
caf3e82e-45bd-574b-a63d-246e198cb274 | textbox | Position:
7c52cf21-330c-5905-9e72-9abda5839190 | textbox | Date:
d2299c1d-b8b9-4eb5-8ba8-fe670e95043c | checklist | ITP-005 - Track Drains | itp | ITP-005 - Track Drains
fd4cd3dd-1cbf-419c-b48d-2d99604105f1 | section | Preliminary Works
cead31ec-0abb-4d04-823e-43c1b183d381 | checkpoint | 1.1 Check for correct documentation
cabd1714-0fc4-5e1f-82df-e9a11fea8051 | note | FREQUENCY: Prior to commencing any activity
f279bbf0-511b-5cc6-bd2a-e2c121e861f7 | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwaded to the superintendent
0291b97e-7978-5444-a88e-0353c339eb3e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
674b16ab-d0e8-5adb-9c72-5d3554d4b21f | note | INSPECTION/TEST METHOD: Visual inspection
9b4043ed-a00b-5f04-b0af-19bd8a155052 | note | RECORD OF CONFORMITY: This ITP signed off
8f64a462-e770-5bb0-a161-9befa4203717 | note | HP*
47441800-d8c5-52ac-ba82-9ac5a3092e3a | note | RESPONSIBILITY: Fulton Hogan Engineer
273c6e06-a629-5ea0-bd58-196da2d24366 | textbox | Date Completed:
c5a70aac-70c8-40d1-9331-1601a2e90169 | checkpoint | 1.3 Materials Check
d8cb029c-070f-5872-84c6-6da55d035bde | note | FREQUENCY: Prior to commencing any activity
89f45532-a136-5ab6-bee6-d4bca8d29e51 | note | ACCEPTANCE CRITERIA: Ensure drainage pipes are of correct classification and are without damage
8a9eb1fe-0ed0-5513-a681-172ba42583ee | note | ○ Check triangle drains are of adequate quality, and are design according Ri57A rail profile
95450ac2-61f7-5431-875d-df3f102b9d4b | note | ○ Ensure lid and j-bolts being used are in accordance with STD T9022
828d90fd-2b13-519a-9811-1eab04e4c50e | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1, STD T9021A STD T9020 STD T9022
93e3ffbb-6fed-5263-9104-92ca33a38d9a | note | INSPECTION/TEST METHOD: Visual inspection, Inspection Checklist
c8dc7056-2941-51eb-bc31-59429515201b | note | RECORD OF CONFORMITY: This ITP signed off, Recievable Inspection Checklist
7e607259-69a5-53a8-b12a-e2fb9e736d27 | note | HP*
413c8780-c6d0-5692-b082-54b473d27430 | note | RESPONSIBILITY: Fulton Hogan Engineer
443d72c0-51c2-504b-a1fd-568b4c26f2ad | textbox | Date Completed:
b51e3524-1e1b-4b3a-bf48-07318196c380 | checkpoint | 1.4 Bedding Sand
db82c8c7-2cf0-5ea9-8314-8474cdc557a7 | note | FREQUENCY: Prior to commencing any activity
45c68241-9820-54fe-b310-aba3391ed684 | note | ACCEPTANCE CRITERIA: The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following: Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities,Consisting of hard durable particles, and well graded.
3ff4ee17-71bd-549c-8b65-55c000471c34 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
570f5482-df48-5814-9f13-1728beb57b36 | note | INSPECTION/TEST METHOD: Visual inspection
5e8ead91-338f-5290-8d0d-f3b8dc369335 | note | RECORD OF CONFORMITY: This ITP signed off
224977a6-5510-50d0-ac5e-281eab5bf2d8 | note | HP*
2cd5e0f4-4da1-59eb-a0a2-d62e1f4a1717 | note | RESPONSIBILITY: Fulton Hogan Engineer
0d91adfa-d126-57c5-a038-11b495c52355 | textbox | Date Completed:
62d1609b-549f-4418-890e-8ea641b47447 | section | Construction Works
84a9f5a8-f61e-46d5-931a-bbe2e8009585 | checkpoint | 2.1 Set out drainage
291fc2f4-44f2-5c4b-98a1-be4cb51470d0 | note | FREQUENCY: Prior to commencing any activity
7542dc14-e837-5628-9924-239934d81147 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent. Track drain locations are to be identified and based off IFC drawings and sections.
95c2cdd5-1068-5e2f-9f50-6c2b176ef44b | note | REFERENCE DOCUMENTS: Design Drawings and Register
6b0f3f0f-5910-5b31-87cb-a5375f049cbe | note | INSPECTION/TEST METHOD: Visual inspection
e8eab20a-6a5d-5b19-8742-a19b928829d0 | note | RECORD OF CONFORMITY: This ITP signed off
a9ca5ae7-8e26-5b7a-b8ce-8eb61e1c72c0 | note | HP*
4466662f-94c1-59d0-8a86-5878ece583e1 | note | RESPONSIBILITY: Fulton Hogan Engineer
849a63f0-1f86-500f-905b-4a17c5e02172 | textbox | Date Completed:
90a31ff3-1063-433f-959d-779a903cbd76 | checkpoint | 2.2 Excavation (pipes)
887985ef-54e8-560a-8cab-75330a8d3473 | note | FREQUENCY: Each Trench
7f16bb18-0301-5296-a904-aa17680cf9df | note | ACCEPTANCE CRITERIA: Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe. Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
519fb435-77a0-51e6-9b24-213978aa5cc3 | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
7e10c3a2-a62f-513c-8d2d-061a9d3fb137 | note | INSPECTION/TEST METHOD: Visual Inspection
b09acf81-e8ee-5b29-8fee-88e96c7c293d | note | RECORD OF CONFORMITY: This ITP signed off
e451e23b-a7be-54de-8b88-fbe373c18b1e | note | IP
a91abcdd-41fb-5c79-a894-8d8b597362b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
35c95e8f-f0aa-57ec-8498-f24cb0674e8a | textbox | Date Completed:
c41a1256-225a-444f-b746-24d741e850cf | checkpoint | 2.3 Bedding
bf2c7ee9-3f93-5f18-8cdb-a3c7417ee909 | note | FREQUENCY: Each lot
f8dd088d-826b-56a3-8f0e-0be61c0a2984 | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
80448da7-9ead-5e3f-a47c-85fc8f09c9e7 | note | REFERENCE DOCUMENTS: STD T9021A
c35bf895-01c2-58fd-87a6-12a4dbfa73f3 | note | INSPECTION/TEST METHOD: Visual inspection
eae16234-115a-5e1a-aaba-8d9f08040fe9 | note | RECORD OF CONFORMITY: This ITP signed off
176590cb-c5a4-5a28-a549-0b2bf7aa24ca | note | IP
48355281-d0fa-53eb-9bc7-675d63609b1f | note | RESPONSIBILITY: Fulton Hogan Engineer
32ac86d1-2223-5b2e-8669-d475eef4a589 | textbox | Date Completed:
5f5b3d5c-ef7a-4e72-bb3c-1c5eb6cadc0f | checkpoint | 2.4 Joining
6cf42e45-cb02-5bed-a61d-651b093ff097 | note | FREQUENCY: Eaach lot
58aea52b-4b82-5a2e-9515-02f6d8cbee93 | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends.UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
02c71049-6f0a-5075-83c9-65ee84ebc4ce | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
6b2cdd24-e48a-5de2-afa0-e14930656fe9 | note | INSPECTION/TEST METHOD: Verify
499098ed-1e03-5639-b8c5-255274c5e609 | note | RECORD OF CONFORMITY: This ITP signed off
13d91133-0df6-5664-97fc-e62af8db4676 | note | IP
b4c75f8c-b5d7-5e72-bc6d-f0cd1feebc31 | note | RESPONSIBILITY: Fulton Hogan Engineer
8a174b50-5730-592a-884b-fbafc89b9011 | textbox | Date Completed:
edf4e7fe-1452-452c-a984-fd6b30c3f630 | checkpoint | 2.5 Track Drain Installation
3ca88a55-4902-513f-a54a-9c0a263109f7 | note | FREQUENCY: Each Lot
84ae36e0-ee6d-5195-9dd5-6d1487897fd3 | note | ACCEPTANCE CRITERIA: Track drains shall be welded to designated positions, and cleaned of all weld splatter. Weld shall be sealed after installation. Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
9a5f7d84-6517-5d3c-89ce-bda5b279a7f3 | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
39a7c7c3-91a8-5ac7-bd8b-a72b477a53fb | note | INSPECTION/TEST METHOD: Visual inspection
1808d12c-b28e-5df4-b9e9-f60142158520 | note | RECORD OF CONFORMITY: This ITP signed off
3d18509e-4f32-589c-a425-bf042dfc0dee | note | IP
7e17228d-316c-5aa4-b2d5-89e46c0512eb | note | RESPONSIBILITY: Fulton Hogan Engineer
580f0670-ecfd-5be4-bd96-8e13d6ac87e1 | textbox | Date Completed:
cb7da4a7-8752-4c7e-b9da-54c820f6d472 | checkpoint | 2.6 Points Drainage
e666c321-c7ff-53d6-8bd3-359022598079 | note | FREQUENCY: Where required
854a2304-bb15-57d0-93f4-c85b584f5bcc | note | ACCEPTANCE CRITERIA: The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit. Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
81a340fe-cec9-57a7-9ada-7ba2868f5f65 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304, STD T0305
e9cf51f2-3b15-505d-9a36-91fe625e0ba4 | note | INSPECTION/TEST METHOD: Visual inspection
d726c590-fc67-5f46-9e01-9e18971b1548 | note | RECORD OF CONFORMITY: This ITP signed off
ddf2f629-997c-5935-874e-51f3216f741b | note | IP
e130766c-f48b-556b-af2b-bc9cfb61b87c | note | RESPONSIBILITY: Fulton Hogan Engineer
68179521-5237-5883-8d1f-e27330b08991 | textbox | Date Completed:
afc3b7de-8f46-46b4-ba03-9ccb0f31443b | checkpoint | 2.7 Concrete Pour
1b658f83-bd2b-515c-b739-e4da6f00bea9 | note | FREQUENCY: Each Lot
8117b57d-b37d-5235-95f9-998b2cae92d6 | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
b2270e67-9ef9-5cb3-ba6f-0e5a1423d944 | note | REFERENCE DOCUMENTS: STD T9021A
ab686c1f-a40d-5c73-92d1-441013e5e8e1 | note | INSPECTION/TEST METHOD: Visual inspection
f75af0e4-9852-5fe2-aa85-0cf3b45003a0 | note | RECORD OF CONFORMITY: This ITP Signed off
55f6c6ef-6b8b-54a3-9de2-8cb61d55e223 | note | IP
30021017-68e3-572c-81c7-45670def6dcd | note | RESPONSIBILITY: Fulton Hogan Engineer
3121e960-39db-5416-80a3-602716ad03ce | textbox | Date Completed:
da57b4eb-b737-4afc-8d10-1403bba3c9e8 | checkpoint | 2.8 Connection to local drainage
4db238b0-eb58-5b3f-98d4-23903190a593 | note | FREQUENCY: Each Lot
3bdf1dd6-3a0b-548e-921d-0a884360c7ed | note | ACCEPTANCE CRITERIA: Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority. The minimum pipe size shall be 150 mm.
94411abd-dc9c-5719-b2d6-a44a7649817d | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
83a28c1e-e1e5-56b8-bda5-975eface31bc | note | INSPECTION/TEST METHOD: Visual inspection
64e0da9a-2792-5768-b074-87b43c2bd912 | note | RECORD OF CONFORMITY: This ITP Signed off
0cf75853-e34e-5342-adaf-20255e22b254 | note | IP
f117dd04-82dc-5e89-a40e-3a03d0851f9d | note | RESPONSIBILITY: Fulton Hogan Engineer
82c95efc-1083-5564-836c-32ebd17a3c93 | textbox | Date Completed:
e479ffc5-d6f1-4031-97b3-d1be9326805a | checkpoint | Final Inspection
282f0202-ae9b-5bda-b8de-08363062a4a6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9809b768-4d29-552d-8502-71eddf3c93fe | textbox | Print Name:
bed2d2f0-b193-57cd-a9e9-b04bbe663a0e | textbox | Position:
cce58fef-039f-5a42-92a8-6439c2f7243f | textbox | Date:
8b5da89f-5dc3-4ffc-a37f-c9d202c5f5cb | checklist | ITP-006 - Track Placement | itp | ITP-006 - Track Placement
5951c1e2-675c-44ad-a897-28bdbdd90e54 | section | Preliminary Works
42cccafe-531b-4f30-b020-7f2b38bea4ba | checkpoint | 1.1 Check for correct documentation
930be278-72f2-5e54-aaf5-f90ef945f4ad | note | FREQUENCY: Prior to commencing works
97371fdb-94b0-578a-bf02-f533ee8ac703 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
2ae4cc80-53c9-5ad9-95d0-aad77c4e2d4b | note | REFERENCE DOCUMENTS: Design Drawings and Register
90ad267a-0712-5813-9afb-611e7d643fca | note | INSPECTION/TEST METHOD: Visual Inspection
1da036ff-def7-55b8-8186-5d1aadb718ae | note | RECORD OF CONFORMITY: This ITP Signed Off
0e694a8e-7d31-5372-a883-208e511ccc8a | note | HP*
18cdaf4c-b615-5a7b-9fce-7eb68ab466a7 | note | RESPONSIBILITY: Fulton Hogan Engineer
a45b23bb-0a05-5ece-a7ef-07a4eab4ab6e | textbox | Date Completed:
9b7e5be3-2598-43bd-b5c2-ac98183cfda7 | checkpoint | 1.2 Check materials
db3a41ba-d2f2-57a9-8521-d8a8222cfecf | note | FREQUENCY: Prior to commencing works
b3fce41e-5552-5573-b518-ac2d1adc4e73 | note | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
8214525b-cffb-5766-b8bf-424a79c79688 | note | ○ Check condition of rail sleepers
e3ecf706-b860-56ad-8373-7d768d1c77b4 | note | ○ Ensure rail jewellery is of sound condition
e021c9a2-03a4-5b24-b683-7b180319cb32 | note | REFERENCE DOCUMENTS: AS 1085
c28c92bf-161e-58d0-a6d3-852bd9b6a23e | note | INSPECTION/TEST METHOD: Visual Inspection
5a037e7e-b626-55f5-b12a-24d93b6c946d | note | RECORD OF CONFORMITY: This ITP Signed Off
a5705e54-8d54-5984-97ad-b52bf5f1c184 | note | HP*
f712ad39-c59d-5822-a3a9-f24c438cf549 | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
c15b83ab-e633-5ed6-aa14-67a8dc5db853 | textbox | Date Completed:
131c5da6-d7c4-463b-9e42-752e647e615e | checkpoint | 1.3 Check special works components
eea205fe-d692-5269-a87c-06e41bff5034 | note | FREQUENCY: Prior to commencing works
7954c310-93de-5722-8193-14c3ea882285 | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
5391d278-d5a7-53c2-a0ec-fcd88790e797 | note | ○ Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails. Superintendent to visit yard from intial inspection of the rail and fabrication plans.
1b16eb96-572d-5e29-a8f4-4229136db977 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
429ebb33-94fa-5395-b2c2-69832ca532ad | note | INSPECTION/TEST METHOD: Verify
2fec4c05-a135-5fb4-92a6-4a9188ead81d | note | RECORD OF CONFORMITY: This ITP Signed Off
d5ce62c6-9c68-5122-b1d3-1b1bfa80062c | note | IP
b84da4b1-fa4c-5f0f-975c-f53be1336770 | note | RESPONSIBILITY: Fulton Hogan Engineer
4cec69ff-b3eb-5459-bc44-16d00004f378 | textbox | Date Completed:
4e7c7b9b-ebc9-4087-ac08-d635247dba51 | checkpoint | 1.4 Check curved rail
ba959754-fddf-5acb-8a24-c5ed0430bde0 | note | FREQUENCY: Prior to commencing works
f90214fe-72fc-5af9-a722-ddcbd5b205b7 | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
e8324a3f-679c-5350-9386-2af8e77f64f5 | note | ○ Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails.
18a83fee-8f81-5b20-9153-29a995686653 | note | ○ This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
1ccea710-8abd-5681-bb9f-6f9a671bddef | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
2fdfe69a-22f1-53f0-99c2-ee0ea15d9923 | note | INSPECTION/TEST METHOD: Verify
fd0d654a-5761-5090-831f-ca59c34575c1 | note | RECORD OF CONFORMITY: This ITP Signed Off
6c3a189a-7a91-5138-9343-3356000dbe28 | note | HP*
6cd37005-bb3d-5b8d-9383-554fed5479e4 | note | RESPONSIBILITY: Fulton Hogan Engineer
d5e4ad99-c035-5cec-8c56-1bfd7d348037 | textbox | Date Completed:
fd5cbbdd-610a-457b-8605-622a266446cb | checkpoint | 1.5 Welders qualifications
58a3c3fc-ed69-5651-b731-98fc84220f95 | note | FREQUENCY: Prior to commencing works
fbcd8507-c4fb-5931-b8ab-a4989e61c3e1 | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements;
aad287c4-3eeb-58f4-bc4a-5d96fd79868e | note | ○ TLIW2012 Grind Rails
092847fb-caf1-54eb-a96a-4f3ac1b57a4e | note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
82101856-3347-5943-8a97-bcdda9cad4de | note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
2e46fff2-48b0-5f8f-8d30-cdeaaca60882 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
4da82791-412a-558b-96b5-6dea01a0becb | note | INSPECTION/TEST METHOD: Verify
caca7049-5036-5fcd-ad1f-28fe56266aa9 | note | RECORD OF CONFORMITY: This ITP Signed Off
0fb1f26b-45a8-50d9-b202-4652d702bc74 | note | HP*
74e2141d-b722-5a64-ba65-e9c59cf972ba | note | RESPONSIBILITY: Fulton Hogan Engineer
f482f8a3-cb32-536d-879a-1355a0fbab98 | textbox | Date Completed:
7eb756fd-6576-4ebb-9541-bcb5feca0bfa | checkpoint | 1.6 Ultrasonic testers qualifications
ce960b16-cd2f-5511-8621-3e95d799efe5 | note | FREQUENCY: Prior to commencing works
444e5ef2-fa80-50a3-a85a-4df3b518ba5a | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
1981e40b-00b9-5e4e-97d7-6a57ac1285be | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
70a326a9-340e-57b5-88a6-e999cef92c54 | note | INSPECTION/TEST METHOD: Verify
deaf164b-c6ac-5611-8ce9-947805e9f88e | note | RECORD OF CONFORMITY: This ITP Signed Off
22293779-3614-5a4a-824f-cca38beee2e1 | note | HP*
3156fd71-7e16-553b-8420-e4a9ff6b2110 | note | RESPONSIBILITY: Fulton Hogan Engineer
5c3fc3a2-0dc3-5585-901c-453ee15e5dbd | textbox | Date Completed:
74dc7fed-7ba5-47c0-b226-1b6d01cc75e1 | section | Construction Works
69219444-c0b9-4349-9741-9cb85a2df75f | checkpoint | 2.1 Installation of sleeper
272f3341-858d-5f69-8fb9-0a52cf0cadf5 | note | FREQUENCY: Each lot
caf3df30-87ba-5770-b5eb-67093a73aefb | note | ACCEPTANCE CRITERIA: Dual block sleepers shall be installed at 700mm intervals, toelrance of +/- 50mm in placement
22dda136-b1ed-5641-b06a-935f762b03eb | note | ○ Dual block sleepers shall also comply with the design offsets at each chainage
6546927f-6e4f-5a5c-b460-c7970640014c | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
9e817f46-ef34-5d30-b5be-c8c478c3c11d | note | INSPECTION/TEST METHOD: Visual Inspection
ebced512-f130-5624-b287-a5faef6d5aa2 | note | RECORD OF CONFORMITY: This ITP Signed Off
4e4eaccc-e305-5b79-9f84-9293bb9fb8a4 | note | IP
9ef4163b-aa21-5c81-b1aa-57242b05a29c | note | RESPONSIBILITY: Fulton Hogan Engineer
e8571b55-a789-59fa-bcd4-21be845cd6aa | textbox | Date Completed:
acf71d3d-9eab-4ba2-8502-efc1c1a8c136 | checkpoint | 2.2 Placement of rail
a9df80bf-afad-507e-983f-5e8fe9397786 | note | FREQUENCY: Each lot
2ac91f71-608e-5e99-874e-e1b7d67fe05e | note | ACCEPTANCE CRITERIA: Ensure rail strings conform to rail plan
5435b437-9e1c-5672-8497-7a07311e9fbf | note | ○ All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
81302acc-2410-5797-ae05-6ec92428c517 | note | ○ Bottom of rail and bearing surface shall be clean of foreign materials before laying
729b5007-6db6-5686-b7fa-753baeea7cd4 | note | ○ Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
2aaa2741-eea5-52f6-a37f-a94a63146e3c | note | ○ Geometry tolerances as follows:
5c89e41f-62fc-5a29-adf5-292d8ba944d8 | note | – Centreline location: +/- 3mm
d4c6e685-7408-512f-82ad-a57e96a4426f | note | – Level: +/- 3mm
95106c6f-4cff-5004-9d15-5649e6237abe | note | – Line measured (>10m chord): +/- 3mm
70faf331-9f77-5ac6-998c-8b1ea625e662 | note | – Twist (3.5m chord): +/- 2mm
64f6c5fe-ecf5-58a0-a652-32d3d58b2c9d | note | – Cant: +/- 3mm
ee524045-a9a7-507d-8ab6-64b8279911a1 | note | – Gauge (open track): +3mm, -0mm
70a6d77b-6b15-59e0-b1a6-92cc4e906463 | note | – Gauge,Turnouts (opposite crossings):+2, -0mm
4d422fb5-3b32-5baf-aeed-37bd75148602 | note | – Gauge, Diamonds and ‘H’ Crossings:+2, -0mm
8d8dbec0-1194-5d00-9a24-de4a91194645 | note | Note: Cant shall be applied uniformly over transitions
da00a75a-16a5-56ca-805e-d41798eaa4b3 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
5a2e11a3-e832-5c4a-a0b8-7726b8166823 | note | INSPECTION/TEST METHOD: Visual Inspection
78369876-b3a4-5f90-83be-db193bc848b3 | note | RECORD OF CONFORMITY: Completion of track charts
404e1e65-e5dc-5389-b268-a6eb95d621af | note | HP*
dab944dd-f29a-57a3-a252-915da39632dc | note | RESPONSIBILITY: Fulton Hogan Engineer
35403483-4cad-5a03-adc3-e8b8be31dc06 | textbox | Date Completed:
77086e2e-761b-474e-85b7-5bf4f1f5ad6f | checkpoint | 2.3 Placement of jewellery
d024babc-ebc5-5699-8569-56671db0a48a | note | FREQUENCY: Each lot
2fd19cc3-e64e-5c8d-86f2-972aff8d0f2e | note | ACCEPTANCE CRITERIA: Each sleeper shall be fastened to track with approved jewellery and rail clips
d38ff6da-e21d-55ef-a2cd-6d1371bbb98a | note | ○ Clips shall be installed with panpuller or equivalent
2bfa65ae-6015-546f-9a4a-ff529cca330b | note | ○ All fasteners shall be sealed as per agreed method with Yarra Trams
f6beccd1-e821-5438-98be-b77f415ee268 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
652589d9-1fdc-599a-8085-1ec502b52327 | note | INSPECTION/TEST METHOD: Visual Inspection
9714e745-55de-56e2-9b23-dc7b3d5b3227 | note | RECORD OF CONFORMITY: This ITP Signed Off
1aa56904-5ab1-5597-8de3-ec74e9830ad6 | note | WP
5c21199a-e15a-5a9b-891f-e9e4e848aec2 | note | RESPONSIBILITY: Fulton Hogan Engineer
88b07e1e-96d1-5bf2-bfcd-6de4ca5c5772 | textbox | Date Completed:
0ed39088-7631-4774-a941-c0b9914a59c2 | checkpoint | 2.4 Rail end preparation
fb45a275-b917-5f7e-ac08-1ea9844d8a5b | note | FREQUENCY: Each lot
17b9bb27-0e37-52f5-b7f9-b28222454071 | note | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
f52bc9a6-7550-5d57-afa5-a246ab7a88cd | note | ○ Minimum closure length from proximity of welds shall be 2m
645d205c-fd93-53c5-aa46-0d8f8d030653 | note | ○ Rail end conditions shall match (i.e flame cut - flame cut)
d62ebc71-4467-592f-8d59-15ea4d46d125 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
92c106a9-4cb2-5570-993b-943036ec0fa5 | note | INSPECTION/TEST METHOD: Visual Inspection
fdfd21e2-1950-53d5-807b-91afdf2d6a71 | note | RECORD OF CONFORMITY: This ITP Signed Off
8b9916d3-8d88-502f-8dbc-5cf895c3a111 | note | WP
e3e204ea-8c91-52e7-90fb-2e7b10c7d7bc | note | RESPONSIBILITY: Fulton Hogan Engineer
91d9012e-173f-5cfd-8be8-0a85319051f7 | textbox | Date Completed:
0636e12c-1c9c-46db-b37f-254b1cd0e683 | checkpoint | 2.5 Welding of rail
bfa09ddf-9437-5feb-b638-4d34ef4519bb | note | FREQUENCY: Each lot
e67ff9d4-ce34-577e-aea8-35aa3b7a54a6 | note | ACCEPTANCE CRITERIA: Joints shall be square across the track
1c43403e-67b6-5803-b841-d767bf16b813 | note | ○ Maximum skew at square joints shall be 65mm
5be17194-7180-5591-9c9b-96671307ab38 | note | ○ Portions shall match rail type (i.e HHR, Ordinary)
023195e8-9e14-56e4-8e14-851fadeaadc7 | note | ○ Welds shall not be within:
80e7e806-090b-556d-be54-f0819518d1aa | note | – 3m of another weld
3e12d2c0-6456-5e7f-bef3-a6d48e117ce4 | note | – 3m of a rail end
754655bd-1df1-5813-905d-6d5286609910 | note | – 1.5m of a glued insulation joint assembly
1aea3d3b-aeac-5fba-9605-98e33c0048c9 | note | ○ Field welds shall be +/- 50mm from centre of bay between sleepers
7d0b8a28-441e-5cda-b8c0-ff7ececbca42 | note | ○ Weld Return forms shall be completed by qualified welder
b9cab2c6-8baa-51b3-bb3e-032b87ab58a0 | note | ○ Welds shall be grinded after 1 hour
277499d1-1fa6-5434-8221-8a83374cabf8 | note | ○ Welds shall be free of water
e4ff07b0-16f3-5a67-beca-3d7d7498e35e | note | ○ Post grinding, welds shall be cleaned for visual inspection
ba67493f-2078-52d0-917a-6638360626a2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
aabf6f38-9224-5c99-8270-cd2ea33ab392 | note | INSPECTION/TEST METHOD: Visual Inspection
f5afc860-010e-5ed5-858c-089796308be8 | note | RECORD OF CONFORMITY: This ITP Signed Off
f30cfe5f-f292-522d-af54-f408eaa99be8 | note | TP
ad76b4bf-68e0-560c-8c85-0d8200c032a6 | note | RESPONSIBILITY: Fulton Hogan Engineer
a0d37b62-37b5-5d3a-b9fd-425a589b1827 | textbox | Date Completed:
fdc14760-57cc-4f27-88db-34a48b0360e9 | checkpoint | 2.6 Grinding & cleaning welds
c8d819f4-69ed-5454-8608-4caf5b058ea4 | note | FREQUENCY: Each lot
b4d17a7b-3877-591f-ac6a-4a6bd28ed595 | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
39ed88b4-1684-552e-9d8f-c55e18e099cb | note | ○ Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
41a3953a-7b8a-57c5-bcca-09c13766686a | note | ○ The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
4b1d3654-6aba-5be6-8413-fbf72149eada | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
ebe55b72-0b41-5912-bd0d-f251ba4efad8 | note | INSPECTION/TEST METHOD: Visual Inspection
1dd936a6-65da-58cd-9863-cae49b1fd957 | note | RECORD OF CONFORMITY: This ITP Signed Off
1167c9fb-771b-52f5-9103-a2042e20779f | note | IP
ad08481d-91ec-5e6a-9220-70a95122ec1d | note | RESPONSIBILITY: Fulton Hogan Engineer
d0b8d9c2-9f0c-52c6-af9d-67c58067b33d | textbox | Date Completed:
f0792a81-5fbd-4da9-9b83-8799c1da099a | checkpoint | 2.7 Track adjustment
8784980d-e7b3-5b1d-a77b-9992479bb1d0 | note | FREQUENCY: Each lot
ab801fb7-db19-5709-bea8-39d1ce6a589f | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with an approved type of thermometer.
087e7c93-b7ed-5df3-a318-bbe9561df412 | note | ○ In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
b916b060-56c5-508b-b1ef-0b9de8a2a31e | note | ○ Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
f893a12e-d35d-5aae-835b-eaf226d8c838 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
ce3c2c71-996e-5034-8550-39de0ea88d4b | note | INSPECTION/TEST METHOD: Visual Inspection
7253fa07-dd48-5dfa-b7eb-09b684529bec | note | RECORD OF CONFORMITY: This ITP Signed Off
af02e9da-25ff-5e4d-a194-0a1f8487c4f7 | note | IP
41fb14f8-ec92-59a5-8856-b51dafd5c12b | note | RESPONSIBILITY: Fulton Hogan Engineer
e6d8c241-f67c-5a4d-841e-b5e8d3e6eb5d | textbox | Date Completed:
6e915780-6e2f-47d3-9eff-2abf88c01e87 | checkpoint | 2.8 Track bonds
f4021da6-1c7a-5044-9d49-466742950a52 | note | FREQUENCY: Each lot
6206b872-6802-56cd-975e-f26b9f641f3e | note | ACCEPTANCE CRITERIA: Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
75ae23e9-4f65-58e5-809a-fff48b2be904 | note | ○ Ensure bonds are sealed as per agreed method with Yarra Trams
57ca56f4-8e2d-529d-8e7f-a32b0b13979c | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
9727ab48-5ce4-542e-b1ee-aa1e7d970af1 | note | INSPECTION/TEST METHOD: Inspection / Test Method
1f19ce04-f328-5f6d-bc29-d9dab7b42be3 | note | RECORD OF CONFORMITY: This ITP Signed Off
9fbee832-bef7-5e1c-9292-de023fb34750 | note | IP
12948d83-3fbc-5c7c-b441-0d9b6d004aee | note | RESPONSIBILITY: Fulton Hogan Engineer
6542008d-7409-5f8d-8a27-1eb688f88a38 | textbox | Date Completed:
b7f11076-b6b6-47bb-811e-12ac35212e55 | section | Testing
1f5a1bc9-b602-4fd0-9d9a-29967eb7f3a9 | checkpoint | 3.1 Track testing
ab5d1750-dc91-5f58-883a-66f180d7eb33 | note | FREQUENCY: Each weld
15cf356b-0a0b-543e-9a97-5d1b8ab450fd | note | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator.
96a9cd23-97cc-524b-a05f-8dacf1f673a4 | note | ○ Failed welds shall be cut out and replaced
1a7eaa80-b00f-58bd-a3c3-1d5978469a7f | note | ○ Testing documentation shall be recorded and supplied to the superintendent
6a1f1e14-fb3f-5f28-a229-0a30f7478e9d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
e35f363e-3e32-518b-9d1d-10bd51869775 | note | INSPECTION/TEST METHOD: Inspection / Test Method
a5e3ce2d-3151-5205-873e-7442aad31279 | note | RECORD OF CONFORMITY: This ITP Signed Off
b34e433d-6a68-5379-9e31-c0f8fc8d8db2 | note | TP
cc4cd490-65b9-5cf4-8879-f3534b3ae3f4 | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
e4a73887-ea0e-5e5d-a04b-b9f986b24463 | textbox | Date Completed:
af58b324-c90c-4c96-a62c-4fd17f7f9e5d | checkpoint | Final Inspection
8ae6db51-95bf-587d-a30a-0e7a50343ad6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e18d0dbb-453d-5296-b32a-bd86ad253b2a | textbox | Print Name:
cd8ebf72-1c41-57d9-acb0-007457492bb9 | textbox | Position:
ac58350f-0f89-598b-a512-1c3ee69bf7af | textbox | Date:
540be182-6f79-4a78-9075-a1f3b8fc8876 | checklist | ITP-007 - Concrete Track Slab Pour | itp | ITP-007 - Concrete Track Slab Pour
e53c6717-06ec-4f13-b4e2-ecf6056d1593 | section | Preliminary Works
c4d2be12-3651-4b82-b730-916276e9246f | checkpoint | 1.1 Check for correct documentation
80d978ae-b15d-5aea-b6cb-975d038cf2ca | note | FREQUENCY: Prior to commencing any activity
6cf5d822-6305-532b-9234-6e5263196452 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a52f03c8-e512-5a85-a096-7c13cc48bcb6 | note | – using the correct and complete set of drawings
c0b7c5f1-89ec-5946-bd80-e69f9a02baa0 | note | – all drawings are the latest revision
3d9d2b35-aaf7-5280-b49b-e16072269a6f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
e1e12bd9-ae6e-57d5-9e96-4e51b8c507bb | note | INSPECTION/TEST METHOD: Visual inspection
298b8476-102e-5c83-80dc-e0cdc55abfbb | note | RECORD OF CONFORMITY: This ITP signed off
c274798e-9d30-5521-8cea-ceebd2fecf1b | note | HP*
87aeaa89-3b57-582e-8d23-ea8001e1d229 | note | RESPONSIBILITY: Fulton Hogan Engineer
b4d050ee-b241-51d2-8af4-e9d98a3f4954 | textbox | Date Completed:
adab516d-51fe-4104-8044-d28c248168bc | checkpoint | 1.2 Submission & approval of concrete mix design prior to commencement of project
e7ac9404-86bc-52bc-a2e4-f28e447363b6 | note | FREQUENCY: Prior to first concrete pour
e414c99d-5dad-5eaa-990b-bf1d44d89180 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
fe644056-1156-5467-ba69-165e92100cfe | note | ○ Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
78019969-fe5c-5754-b7d0-996ea1b2a0d1 | note | ○ Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
5830e079-894a-5a52-9fb0-5e92c2b3f556 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
773383e7-8cfd-5571-8c81-99cc2591684d | note | INSPECTION/TEST METHOD: Verify
85a43ac6-55d4-5fdb-a676-290f7ded0e13 | note | RECORD OF CONFORMITY: Mix Design ITP
bea54228-9e57-5b2d-9c4d-a079cda9a4d1 | note | HP*
24f92d2e-e966-5c16-a25d-e5c4986e6fcd | note | RESPONSIBILITY: FH Engineer / Superintendent
90a5fe92-790a-5eb3-a38d-c7ec15d80437 | textbox | Date Completed:
a09b97ae-f203-40d7-95ba-f35460e6f32e | section | Construction Works
6ec1bf24-7ca1-4fd7-989c-0f193fee4571 | checkpoint | 2.1 Weather monitoring
112610f2-604c-507b-966f-0eb42a38ecb4 | note | FREQUENCY: Prior to start
384b495b-96ef-5c2a-8d0a-e2dd04ecf600 | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
9b54dd3d-520e-5ffd-af40-876256e918bf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
c1d40a3c-5713-559e-a916-f732f33e0984 | note | INSPECTION/TEST METHOD: Verify
916449b6-c368-5430-872c-9c33189f1d03 | note | RECORD OF CONFORMITY: This ITP signed off
790f274d-1bd2-571b-8342-f5db31b0751a | note | HP
120efac1-cb7d-5866-bb81-935b4df90215 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
1467a1a4-a733-54b2-9c40-4ddc662901fa | textbox | Date Completed:
b053b22b-b813-4e03-93c6-fe30139865a1 | signoff | AUTHORITY HOLDPOINT
b33b5c19-dc64-41a7-b177-782da0ed7b66 | checkpoint | 2.2 Surface preperation
6310d2c3-c7cc-59bb-8487-7122909a645d | note | FREQUENCY: Prior to start
037c847c-b219-5be7-aa22-071878aefbfa | note | ACCEPTANCE CRITERIA: Crushed rock surfaces shall be moist and thouroughly cleaned of all foreign and loose matter prior to pour
82957c7b-191f-574d-bc3f-9281ac2ade85 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
25528747-a29a-5618-9f22-d1a52ab1b1fa | note | INSPECTION/TEST METHOD: Verify
2dd25e2c-a5d0-5c25-874f-73fbef41ebaf | note | RECORD OF CONFORMITY: This ITP signed off
2a52ffbb-0ecd-5e90-85f0-2294a627eb4c | note | HP*
0eba2325-02ae-5a8e-a0a2-098ef21d97e4 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
6c8c7e27-1221-562b-9834-f910e5f07955 | textbox | Date Completed:
8d88a645-1e8b-4591-91a8-3d3694684a1e | checkpoint | 2.3 Setting out
65949595-4701-517b-92bb-59583e7474a3 | note | FREQUENCY: Prior to start
13c05f67-2bb3-5c84-be08-270d477a3b9f | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications. No survey/level pegs to be removed by any persons until completion of works.
ec931199-52e9-526f-a212-a9f89212ef72 | note | ○ Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
20886113-6be9-5009-aa06-400a6c86e062 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
94973799-42f5-56d4-875c-b1467bb741d3 | note | INSPECTION/TEST METHOD: Verify
155e9363-ee9b-53c3-8d89-9c98a7c22f83 | note | RECORD OF CONFORMITY: This ITP signed off
d4d13315-4bee-591b-8c48-c53b2f57fa0a | note | IP
dbe409e7-ab0d-5d4a-a27c-e933e3bcd98a | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
4893f186-dad0-5a2f-8de7-315d9385c9dc | textbox | Date Completed:
130df47a-124d-490a-bb62-363197408864 | checkpoint | 2.4 Formwork
49bbeb41-48f5-5f70-acc7-77b3b34faeb7 | note | FREQUENCY: Prior to start
e7cda98b-22b4-53ff-aae4-331cc75a3a42 | note | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
a24272cc-2a89-53e8-913a-1a8f1452aca9 | note | ○ The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
b528fa66-bdb4-5d01-922d-933a268f5535 | note | ○ Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
ba39a81b-fac7-5161-9687-81d6e01b80dc | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
10edcb1a-df79-50f4-8ddf-0a7d37edb05e | note | INSPECTION/TEST METHOD: Verify
a06c3c51-bc26-55d9-a81c-edee0bdd512f | note | RECORD OF CONFORMITY: This ITP signed off
6fc0789d-51a9-5876-b475-37f322bac44d | note | WP
131ff8db-7de6-5d10-80e2-f2b0a3cea4ad | note | RESPONSIBILITY: Fulton Hogan Engineer
9fd8b9f3-d6f1-5376-b9a8-2150f8be884a | textbox | Date Completed:
681e0ebc-efe7-42bb-ae59-7512f3baf170 | checkpoint | 2.5 Reinforcement
c290d3e0-f712-55d5-80a2-fc1feee5262f | note | FREQUENCY: Where Required
3a3f29b3-f083-5835-9ff8-a3ab8178de1c | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
c678ef45-90f8-5dda-a27f-3227915ddf0a | note | ○ All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
e5aafea1-ea51-51bb-bae9-3497f80ace1b | note | ○ Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
0efcce01-f22e-53f2-907f-95f909eddbe3 | note | ○ Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints. Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
c1d80bf3-e347-5968-a2f9-a9905c7ca3f8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
22827e6d-9dae-58ad-9c74-6be21f658d4f | note | INSPECTION/TEST METHOD: Verify
6249c2a6-059c-5e37-8a75-860c5717140a | note | RECORD OF CONFORMITY: This ITP signed off
a184cb3c-5088-57c8-ab07-7cbc5169cf7b | note | IP
530b6854-720f-5c6d-a6d8-f33a8215891b | note | RESPONSIBILITY: Fulton Hogan Engineer
f8e76cf8-e4b2-5c44-9dd1-a1a5480f3404 | textbox | Date Completed:
1ce7679d-02c1-4eb0-ba8d-915ea06a3d4e | checkpoint | 2.6 Dowels
346b3dc2-e3a4-55a0-af1e-841e53a0f978 | note | FREQUENCY: Where Required
ebd30e67-f6ec-5a5c-82a6-0260cc63e61b | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
8b32cbcc-a996-515d-8f6c-b77692c9b3c4 | note | ○ All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
31a489bc-bced-59d1-98d1-a7e0914340a6 | note | ○ Dowels shall be clean and free from mill scale, loose rust or oil.
db1216de-2198-5a1a-8549-386434cdb312 | note | ○ Ensure that all dowels are securely held in their correct position until the concrete has set.
1f0257c8-df3b-52b2-8121-8aaa831b0431 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
5a9b57d3-e9b0-5454-ad2b-806c5be71d03 | note | INSPECTION/TEST METHOD: Verify
f1877ed6-8739-599f-93a1-f3188d8798c3 | note | RECORD OF CONFORMITY: This ITP signed off
abd6bbcb-6005-5965-91ee-0d45786478d2 | note | IP
d136beed-61f7-5447-8a46-905c9ac8117d | note | RESPONSIBILITY: Fulton Hogan Engineer
9de003ba-d9b2-54f0-927b-040ba202616a | textbox | Date Completed:
935a492c-7c07-474c-a661-1cd645fb2086 | checkpoint | 2.7 Pre pour inspection
972e3531-3c1f-5037-bd88-7534d860f15f | note | FREQUENCY: Prior to start
8b4ad568-5f5e-57d6-bed9-b025451df341 | note | ACCEPTANCE CRITERIA: Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
b7146aed-778b-5f7e-be1b-d95d13c08e21 | note | ○ Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
2d69cb43-b8aa-566f-836d-f7e356cf9053 | note | ○ Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
dec0493a-c62b-500a-bafb-426fb2dfd9ea | note | REFERENCE DOCUMENTS: CE-019-ST-0033
b2ef802e-cc73-5f53-b7fc-9abc6fa9d317 | note | INSPECTION/TEST METHOD: Inspection / Test Method
a1cdf744-81ea-5b17-8b4d-5dba832430a6 | note | RECORD OF CONFORMITY: FH Track Inspection
b13c1405-4198-586c-9358-4dbd1af923c2 | note | HP
638293b9-181d-5000-832e-3ca04121154d | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
f2ad76f7-7c03-500c-bbc9-f528c363ec2a | textbox | Date Completed:
acb2270b-7d07-4da3-8314-13235a19091d | signoff | AUTHORITY HOLDPOINT
8253dd6c-4cab-4e8e-b767-080af498362d | checkpoint | 2.8 Carry out sampling of concrete
cb03d5e5-f4bd-5bfe-a848-d3bb78cede5a | note | FREQUENCY: Each concrete pour
e2379dda-b820-5fcd-82f0-63d9c54794e3 | note | ACCEPTANCE CRITERIA: Slump:
354a3b51-f204-5eb8-8382-48e4af069a19 | note | – Concrete Slump shall be 100mm +/-20
5be957df-6cac-53c5-b37c-bd76aa28b081 | note | Compressive Strength:
7915182b-6275-5a35-903d-54d009122e08 | note | – Shall be measured in accordance with CE-019-ST-0033
966f095c-2b89-58db-a715-a8e0d06408bc | note | – Testing frquency =
95533c10-48d4-5db8-a71f-110acf98e409 | note | ○ 0-50m3, 1 sample
09cb0d35-5e02-554c-930a-8d3c6e577810 | note | ○ 50-100m3, 2 samples
68916fe9-44f4-52a0-80fd-7b3d04365d9a | note | ○ 100m3+, 3 samples
b301c21d-1017-58cf-979d-b2ec50ea46dc | note | – Each sample shall consist of 4 cylinders
1ca1819a-3c6e-5cd3-9a61-58175e821a9f | note | – Test Results will be provided to the Superintendent
d91a13b7-95e8-5b64-92d5-b39f2fe77fe8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
365649ef-d363-5c70-b956-ad2adf01ef95 | note | INSPECTION/TEST METHOD: Verify
33bdc06f-414c-539e-a168-94d3db3e51ef | note | RECORD OF CONFORMITY: Concrete supplier test sheet
7151850e-34dc-5c81-b741-88942432948b | note | TP
7e0a56df-0888-53e4-9997-de40667136cc | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendent
80be2a4d-6979-51a7-8d6b-62ce9167fd89 | textbox | Date Completed:
2926fe58-1487-4b8a-b36d-5d78639b8519 | checkpoint | 2.9 Concrete placement
b173666a-5e6e-5f5a-84e3-b665f8fadaf5 | note | FREQUENCY: Each Lot
f604655b-4967-5cc4-b0ec-4e272e74d583 | note | ACCEPTANCE CRITERIA: Ensure formwork is clean
42165cd4-ed06-5e2f-a14d-34f2cd3303aa | note | ○ Concrete shall be entirely discharged 60 minutes after batching,
f9e2f738-1322-5297-9993-7a2498ce1a66 | note | ○ Ensure that pouring does not occur from a height greater than 1200mm
d2c6b8f9-735e-53db-980b-4143f156d201 | note | ○ Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
1bd32b14-0d29-5390-81c9-722602e0af65 | note | ○ The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
c9ccd215-3534-59c7-bce1-0fe2a93a4396 | note | ○ There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
254a588c-8f8a-5a58-938e-08770fa88dcd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
fe991469-5c7d-5daa-afd8-c8cac520ea9b | note | INSPECTION/TEST METHOD: Visual Inspection
9e1af8f8-caf6-58c3-871e-f4fd04db753d | note | RECORD OF CONFORMITY: This ITP signed off
28fc8e16-f69c-557f-b031-b5d6d359329c | note | WP
8a879a1c-bfa4-5c16-98c5-85bb74df0d90 | note | RESPONSIBILITY: Fulton Hogan Engineer
1debdbd3-39bd-5818-a835-cb119079a3ad | textbox | Date Completed:
5172e466-1a37-43d6-8376-a908f10c44d1 | checkpoint | 2.10 Compaction
4ad983f7-74e9-5800-9352-27c815b516c7 | note | FREQUENCY: Each Lot
f80f6897-2bf7-51cc-b5be-3603b7c9a41e | note | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator
f1099ee1-7650-50c6-a4f1-096486bdb026 | note | ○ Vibration shall take place until exposed concrete surface is free from air voids
57c0da42-86b9-5d57-8e43-12fe3aa9b5b7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
941052a1-856f-5e64-9173-f8f028fa5218 | note | INSPECTION/TEST METHOD: Visual inspection
da01c3e9-7dc7-5380-83d0-49e44772cf75 | note | RECORD OF CONFORMITY: This ITP signed off
09d3e253-2cf1-5a57-a5b0-e1722aa56376 | note | IP
70995f55-e5fd-5d42-a937-5d72b11e8d50 | note | RESPONSIBILITY: Fulton Hogan Engineer
14128742-c7bb-59f8-8679-e8704f83606a | textbox | Date Completed:
7d4701ae-5b88-4dc9-ac86-9bd39bae1523 | checkpoint | 2.11 Record location of each batch
5e54c557-b979-5724-bb27-b2c4d192c121 | note | FREQUENCY: Each concrete pour
37966958-e4ba-5344-8c20-2a489ce153e2 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
56be51d4-c41d-57f4-b5e5-054d2af50d14 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
83b4dfeb-d3f4-5cff-9dc7-89918c7ee9be | note | INSPECTION/TEST METHOD: Checklist
a52e9365-9924-5f8d-8db7-df1513bab310 | note | RECORD OF CONFORMITY: This ITP signed off
0d725ff3-4113-5ddd-a142-6cb6a43a4e0e | note | IP
2808b9fc-7ee3-5357-a75f-f696cc787568 | note | RESPONSIBILITY: Fulton Hogan Engineer
ab281294-8985-5db0-a919-f88a506d38fc | textbox | Date Completed:
d49c8956-f3fa-4b95-a6c6-1ed34b4ba4bb | checkpoint | 2.12 Curing
eec60959-7666-5389-9d5d-332e9b3290e3 | note | FREQUENCY: Each concrete pour
8f7b61e9-0628-579c-90cf-933390a71a3e | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
26074dfc-9ed6-51b5-b2b5-7ee7d563c7f9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
6af2cf9e-ee6b-5187-bb02-a71c5c93fbf8 | note | INSPECTION/TEST METHOD: Checklist
ce54e91b-b88d-5af7-8ecc-eb9add5dceda | note | RECORD OF CONFORMITY: This ITP signed off
767cd305-ac32-5a50-b443-c5eb18069d10 | note | IP
b89aa2a3-2b06-5a88-b85d-71bf3e05c089 | note | RESPONSIBILITY: Fulton Hogan Engineer
6b4afa42-114e-5179-ac57-84eb97f1c81a | textbox | Date Completed:
00d2af11-533c-4a4f-af92-bda94725fb2a | checkpoint | 2.13 Tolerances
22d22933-c4b6-5cc5-be57-d37d27cc2680 | note | FREQUENCY: Each concrete pour
949a7f26-eab0-52e9-b876-9964765a5e7f | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
91915350-d1d0-5c84-952f-50ad0febc823 | note | ○ Plan dimension of slab +10,-10mm
d59dc0d2-4cc7-5c05-af24-7eb2acc8edef | note | ○ Thickness of slab +10,-10mm
9f3079c6-8a93-504d-ae65-db99d58496df | note | ○ Cover to reinforcement +5,-3mm
f8480e33-49f1-56b0-922f-389d4822ecb5 | note | ○ Finished level of slab +3,-3mm
83cdfa21-3913-5f47-b822-444976ed17f2 | note | ○ Foundation level of slab +0,-20mm
0ad01b1c-f57d-5a6c-9ca2-827eef7aba33 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
fdf39335-2b43-5f4c-9a1a-4a615cd782aa | note | INSPECTION/TEST METHOD: Checklist
bf99464f-bb5c-5d81-8467-24b1557f34f5 | note | RECORD OF CONFORMITY: This ITP signed off
b9e68c2c-c470-5d19-9b67-50b3610e53fd | note | IP
8c3ec234-cb97-5caf-81e9-e2e4437615a1 | note | RESPONSIBILITY: Fulton Hogan Engineer
37e86dcb-4385-5c46-ae06-bc8f447bbddf | textbox | Date Completed:
d4e50aa0-4a28-44b2-94fa-ed03435d55dd | checkpoint | 2.14 Slab finish
8e4e5607-1641-5628-b03d-39a8297a7066 | note | FREQUENCY: Where appilcable - if track is Type 1 structure
d303ec75-9e25-521e-8789-8aaf9e643d53 | note | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities. All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections. A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C. The slab surfaces shall be broomed to provide a non-slip finish.
0308e79d-3544-5d39-a07e-3775cb7a48d9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
f12b1520-863e-5a38-b281-b4011f5c68e6 | note | INSPECTION/TEST METHOD: Checklist
686b455c-8028-5fcc-ab87-40758d0e8c6e | note | RECORD OF CONFORMITY: This ITP signed off
d5676bbe-6670-5ec4-90f6-b1ef45183166 | note | IP
1507e1ae-2855-5332-ae88-09ffbcb97115 | note | RESPONSIBILITY: Fulton Hogan Engineer
b8d513cf-cff8-560f-85ba-0b7c157c247e | textbox | Date Completed:
4dc37648-9a12-422f-b262-cd428d2377e4 | checkpoint | 2.15 Post pour inspection
820b485a-2495-5be1-9253-dd2013f33412 | note | FREQUENCY: Each Lot
cc9f180b-b076-5b80-b38b-f20df37ca9a0 | note | ACCEPTANCE CRITERIA: Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
fba73a7a-2169-5232-8fa3-13c91632804a | note | ○ Ensure no defects are present in slab
944662b4-c06d-55ee-ad72-7a0911b4fb34 | note | ○ Complete Fulton Hogan Post Pour Checklist
2b9ec831-1fdf-5129-a587-70aa8237938f | note | REFERENCE DOCUMENTS: CE-019-ST-0033
af516227-7cde-5a03-af02-677e08ce9ba4 | note | INSPECTION/TEST METHOD: Visual Inspection
88a2f87e-cd85-56ea-8171-e7e075a9f559 | note | RECORD OF CONFORMITY: Post pour checklist
0ef3465a-d72e-511a-9d07-fb0c834aafe5 | note | IP
80595987-cd1c-5e9f-b9f5-12bcb9ad1165 | note | RESPONSIBILITY: Fulton Hogan Engineer
afb5b4cb-bfdb-52f0-ba03-41a3d8c798ed | textbox | Date Completed:
817acc39-f755-4bcc-a5a0-a374caa81df6 | checkpoint | Final Inspection
a446bc5f-52e8-59cc-b957-a5946d28107f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
10fc9898-f796-52eb-87bc-718baeb62ad8 | textbox | Print Name:
5d6880ec-20f0-552c-b7e3-998bb45e6488 | textbox | Position:
e528fab0-7c5e-5003-bc29-e627f88315e6 | textbox | Date:
31192c2e-d023-4ac2-8547-527f8e691760 | checklist | ITP-008 - Hot Mix Asphalt | itp | ITP-008 - Hot Mix Asphalt
f19df006-adc4-41e7-aae9-d0b3acfc458c | section | Construction Works
40212e57-357a-4e4b-b166-3c0e8b0f70af | checkpoint | 1.1 Submission of Mix Design
114058c3-bf9c-5e4d-a699-cc1729ee3b61 | note | FREQUENCY: Prior to commencing paving
ebe5c33c-f6d6-56cd-8897-43aea694f849 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
923a5ef2-b187-5162-abc5-0cfebe21435a | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
5a0a19f3-90df-58ed-a918-b36a343f3136 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
8a7a81d4-b0c2-579d-9a00-67dfdc1f7f3c | note | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
a30f3328-dcd6-5612-99f5-2b73a318834d | note | HP*
0ba9880b-2a16-5d86-aec5-c9214cec50fc | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
37b1ec39-f850-5d30-9bc0-3d1e3e1b59d1 | textbox | Date Completed:
adb8fc53-af51-489e-81d7-8af11d852b19 | checkpoint | 1.2 Site Inspection and Base Condition
dad8ae5d-e57e-5265-91bc-d38252953c83 | note | FREQUENCY: Prior to commencing paving
e630332f-0111-5f88-a1e0-1341116242f6 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
fbb5fb8b-6b6f-59be-af76-22d87363222e | note | REFERENCE DOCUMENTS: 407.14 AS2150 10.1, AS2150 10.3
4521bfa4-8b3d-5b4f-9892-7baada019da9 | note | INSPECTION/TEST METHOD: Visual Inspection
52b3d9b3-2838-55f4-867b-4963886f9267 | note | RECORD OF CONFORMITY: ITP Signed
542a07ec-d3c2-58c0-927b-5885b781496b | note | WP
0f67ba0f-2e9e-55b1-85c5-69ae7fddcb0d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
f470adb5-bc43-520d-8420-8c5674ed0f0d | textbox | Date Completed:
5c3190b2-c5cc-4344-be72-c970a7bb320b | checkpoint | 1.3 Ambient Conditions for Placing
d83d3c02-df22-5373-9173-c1c7e85ea571 | note | FREQUENCY: Prior to commencing paving
e7edb447-eea3-5f57-b9b6-8a1352cedfb1 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
97eaa3a2-ee3b-5f6e-8ab5-0d37e9c436cf | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
8d2b9b02-851a-5c1d-9d89-5c173329fe79 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
9d427ccd-82e8-5c61-8db4-7793a4c1250f | note | REFERENCE DOCUMENTS: 407.13
259deb1e-45a4-5efc-a21b-632852a2abeb | note | INSPECTION/TEST METHOD: Verify
bd709d34-4f1f-5138-af8d-d6f3426f717e | note | RECORD OF CONFORMITY: Thermometer
f3d953e6-283b-5934-a33b-c06ab35d3ac2 | note | IP
595ff9dc-3141-5875-9a2f-258e99e6a9ba | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
06bc1566-6a32-5a87-9d03-9f18c4b736a9 | textbox | Date Completed:
17ffea56-7c03-4697-b2cf-a86323253b7c | checkpoint | 1.4 Planning of Joints
6becf620-d23c-53fc-95d0-dbab5fbbe4eb | note | FREQUENCY: Prior to commencing paving
45fcfb27-ceed-5c85-a4bf-b6445ff40340 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
b2407632-2bed-5e7b-beb9-62a2e79c2355 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
54b16eec-3c97-515b-bbdb-d43a65dd910b | note | ○ Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
5be4f05e-2861-5027-9b79-9f36cc3d787c | note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
31c52f33-84a7-5442-94b8-880fedab121e | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
c73c18a5-d055-5fa5-9cf0-8b3ecc29965e | note | RECORD OF CONFORMITY: Paving Plan
179995af-ab5d-5781-8639-e45d23c80ced | note | WP
2d61ef99-2665-57ee-94ab-f498e50964bd | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
0813cda2-5ca4-5797-85f6-2f52e7b33ffb | textbox | Date Completed:
0194c481-91e5-4be4-aa57-a558d37d54a9 | checkpoint | 1.5 Longitudinal Joints with existing Pavement
ac861718-1889-5502-89c7-e7c10d8b4361 | note | FREQUENCY: Prior to commencing paving
84ad80d8-a6d0-58d4-b356-0c2ce4b49041 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
973d4086-9cb7-50a5-8e8c-055191713e6c | note | ○ Depth of step to be cut to the full depth of each indiviual layer.
20c9db23-6704-59e5-9d29-1e2092841bbd | note | REFERENCE DOCUMENTS: 407.16 (c) Project Specs. Section 3040.06 (d)(vii)
9f3bf738-8888-59f2-bbc3-f4ac15e64b86 | note | INSPECTION/TEST METHOD: Visual Inspection
a29fb200-8285-5624-8add-2fa48ce2d780 | note | RECORD OF CONFORMITY: ITP Signed
ae4e8e31-99c6-5543-8991-cbb5ccacd54b | note | WP
b46148f1-3e13-5b44-81f0-89b4e94a1a8d | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
baf61bda-15c8-5fbc-b7bc-bb226200c5bd | textbox | Date Completed:
e4d4943f-ad1c-4883-b211-95cbcc9ba05b | section | Asphalt Placement works
f610e2de-7644-4fb0-af4a-2c466dc88d83 | checkpoint | 2.1 Tack Coat
21b36e93-359d-5bc9-b2cc-e3be23601023 | note | FREQUENCY: Prior to commencing paving
7bc4d6da-b90f-595f-a536-d99e40d5af13 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen) or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
2d2189c6-ca3e-5331-91bd-55f1f265e105 | note | REFERENCE DOCUMENTS: Vicroads Spec 407.19 AS2150 11
56355f65-e144-5a97-8cdf-418a5f52838d | note | INSPECTION/TEST METHOD: Visual Inspection
46ef0fb4-f6cb-5cdd-86d3-8a3aed2685fc | note | RECORD OF CONFORMITY: ITP Signed
3a82c4a7-8245-5027-82ca-3427b1150ab3 | note | WP
41b36943-0ca6-58ff-ac58-750d36d52283 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
82272bb0-afd8-5712-9b69-b85a3f3dddb6 | textbox | Date Completed:
edc985ec-2eb6-4e50-8944-d72d68efe7f0 | checkpoint | 2.2 Commencement of Placing
8cd29838-8179-55ea-ad42-c80c6da45fab | note | FREQUENCY: Prior to commencing paving
3e4804a1-dce6-52e5-87cc-32bff9a88172 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
18b4f381-17db-5ba6-aaa3-48c82ccb07a1 | note | REFERENCE DOCUMENTS: 407.18
9df3c8c9-46db-5b0b-9b27-e57b6811985d | note | INSPECTION/TEST METHOD: Visual Inspection
e718f024-4186-5502-8e22-fad13f003bea | note | RECORD OF CONFORMITY: ITP Signed
f8b68615-3d33-5d16-8b45-f16c106780bb | note | HP
307c1bc3-1f7f-5236-bf79-87bad3c45027 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
79189363-c47f-590f-bc2d-fe76c1737281 | textbox | Date Completed:
47dff0be-ea50-47ed-8efe-c7c0b4b2b1a2 | signoff | AUTHORITY HOLDPOINT
2853a2bd-155d-4ebd-8be8-bc3c7a794da3 | checkpoint | 2.3 Mix design confirmation
7aaef0cd-ca28-57e4-901c-ab4d79821d2a | note | FREQUENCY: Each lot
d02c7d05-1af9-5833-b87d-d1ca5dff1fee | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt mixes shall be in accordance with Yarra Trams Track Structure standard drawing.
429b86ff-99dd-5503-85d5-4e26cefd2957 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06 STD_T9010 - Typical Track Structures
4b111e71-5287-5679-82f7-c83b703b8bc7 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
f939e45f-292a-5812-9134-e420021996cd | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
feaf9e3f-f476-524b-8fc9-e497b45d745a | note | HP*
cbcf665e-7fef-57a8-95c6-9c9bc085f618 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
00bd6a82-d31a-5351-aedd-2f0ecd2dcca2 | textbox | Date Completed:
5ed8ca57-7189-420e-b3b7-685489934261 | checkpoint | 2.4 Delivery of mix
640dd140-e801-5a52-86fa-05511c8827ac | note | FREQUENCY: Each load
dc7ea31a-3c07-57f4-9a29-ee7e161eae6b | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
68c97e8b-90fb-567b-abf9-645b07793b1e | note | REFERENCE DOCUMENTS: 407.16 Table 407.081
7d4d0c24-87a6-5ee9-925a-6d96fb252a0c | note | INSPECTION/TEST METHOD: Visual Inspection
c5d9b3aa-b193-55a0-b10c-ed4006388337 | note | RECORD OF CONFORMITY: Delivery Docket
ebe0dc3c-2186-593b-9ad3-f4c8976c569a | note | WP
e8bdd29a-ee4e-55f2-bbdb-03a2591be7e7 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
1112e926-7a46-51cf-aae7-41fb1a35dd52 | textbox | Date Completed:
0e4ad0fc-00ac-426e-bbad-b9692e3e461a | checkpoint | 2.5 Traceability
d8a9ebb1-ff65-54d9-8b55-afcceb36e77d | note | FREQUENCY: Each lot
9bf0ff7a-cc88-59fe-8382-c6f62e6982cc | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
f756339f-4041-58a4-b3de-6bdf56024730 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
79225c59-ac33-5668-a8c9-14174dc0a92d | note | INSPECTION/TEST METHOD: Verify
b327389c-37a9-5ebd-b0d7-5f2a8508fe27 | note | RECORD OF CONFORMITY: Daily Lot Record
4960edbb-b014-52c3-a149-30d57f8394a4 | note | IP
9dd3708b-9ce4-52c4-b250-6f2b8e7fedf3 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
2d01d55c-c43a-5db4-bc46-a12d85fd624d | textbox | Date Completed:
e3428926-f11e-41c0-88eb-7f545b644616 | checkpoint | 2.6 Layer thickness and level control
2f0d0950-7017-52df-a895-9a7f3c61eb4f | note | FREQUENCY: Regularly during paving
8d633698-f14f-5a19-81fd-8e9d020c27f8 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
d60ee1fb-4708-5ec8-a1d4-a1bab056e8ba | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
4922f45a-1b87-53eb-b6eb-fbeaabc4eeec | note | INSPECTION/TEST METHOD: Verify
da385e23-391c-5ae1-9333-aa35fb31692c | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
82259403-c9ff-5185-a410-083ed237c0c5 | note | WP
8f134b03-e507-5814-a416-1510e1601c77 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
dfa36636-e869-5f2e-a9f9-cb61d1bb4934 | textbox | Date Completed:
3c905b2c-2881-4202-bc55-63c2a7679139 | checkpoint | 2.7 Surface finish of wearing course
c0d4db1f-b04a-56a9-a186-511bd841b6f7 | note | FREQUENCY: During paving and after final roll
9634e972-0438-51e2-bc07-f788a21a72a9 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
e7efd9ab-78f8-55aa-887b-b30b6b0eff2f | note | REFERENCE DOCUMENTS: 407.23 (a)(i)
0285991c-cc13-5389-92a2-0adeb0d20dcc | note | INSPECTION/TEST METHOD: Visual Inspection
4823638b-2fe1-53d1-9545-73471a829282 | note | RECORD OF CONFORMITY: ITP Signed
7232d5b4-de24-575e-913b-146b6a99e6f5 | note | WP
33d8fc41-feae-57d1-8696-1c8fc07d9142 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
b720da59-c95d-5321-9df4-b5b69dc877e7 | textbox | Date Completed:
a5c9d6ff-7a25-4c97-9c20-e2959cee0ab1 | checkpoint | 2.8 Alignment of layers not placed against concrete edge
3e267a58-ad2b-57c7-839b-f979befc2732 | note | FREQUENCY: During paving and at completion of work
b7d66e29-0ab7-541a-a030-efba6d26f205 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
59200ec4-ee74-5b8b-b495-e5f1981a7549 | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
f37f6f95-dda9-5fe8-81d7-83bf793e6589 | note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
dcb8c3ba-8f28-5a06-a76c-803437821aad | note | INSPECTION/TEST METHOD: Visual Inspection
6f5a9f75-5d09-5089-9c92-f0d5af147a02 | note | RECORD OF CONFORMITY: ITP Signed
8fae8f2e-68fd-571e-99f6-cc8b885167c8 | note | IP
66a4bee4-e220-5fff-8714-1f8407fe18c0 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
73b1d5d4-ae2f-5ff6-b7f0-6abec6a2873f | textbox | Date Completed:
8f572ab6-8d68-441a-b036-ad8e832303fc | section | Testing
5812a089-66db-4bc1-a279-bf5d48b128ce | checkpoint | 3.1 Compaction
30a35c0f-ce59-53d2-9156-26ac252110b4 | note | FREQUENCY: Per Lot
f057c7de-1ebe-536b-bdef-3f8bd3cf3cf7 | note | ACCEPTANCE CRITERIA: For wearing course layers <50mm, if characteristic density ratio is:
5e294785-4cd3-56ec-b362-b65beb03051b | note | ○ 94.0% or greater Accept lot
1678b526-eab2-5666-806f-142c4292c77b | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate.
861dcc5b-a5fe-5943-b71e-ade934db1634 | note | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
c3a418bf-df78-5cf9-83e7-4a10afc91336 | note | REFERENCE DOCUMENTS: Table 407.221
6e9cb77f-f8d7-5959-8762-41f50225db21 | note | INSPECTION/TEST METHOD: Verify
0c24f71d-0555-576f-b439-339ed874fd07 | note | RECORD OF CONFORMITY: Test Report
fbaf5f1f-18ad-53a2-8beb-658a63ef8ed4 | note | TP
1ec0fd31-6c27-587a-b879-f1bdfe769bc1 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
72a57047-4ebf-51f2-95f8-a184d2fd4c7a | textbox | Date Completed:
10da7d55-c729-47c5-8cd7-704879fae2d4 | checkpoint | Final Inspection
1f095ff4-a33b-53b4-b0c7-0a261829815b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9f6ccbd9-ebce-546a-9105-4fc820ce80ad | textbox | Print Name:
86406c4c-b6ad-51ad-bc62-0c89d4062ea2 | textbox | Position:
7d19ad29-8372-5c81-9c66-834ebc39f9fe | textbox | Date:
38c3dbc4-b5b1-4c88-a995-9a8a114a1bc6 | checklist | ITP-014 - Bluestone Kerb Installation (MCC) | itp | ITP-014 - Bluestone Kerb Installation (MCC)
e88414f9-e2e5-4d7a-8fa7-e1938838c301 | section | Preliminary Works
30d0047d-bc60-47fa-b535-631ea43686e5 | checkpoint | 1.1 Check for Correct Documentation
f3181abc-5756-57e4-b81d-9d9a4b0f281b | note | FREQUENCY: Prior to Commencing Activity
06033938-7937-5d97-828e-651bfc0243f9 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
9c3bdafa-4d4d-5751-9b9e-d4a82adef9c4 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
3a88f538-a76d-5669-8325-2f479004168f | note | INSPECTION/TEST METHOD: Visual Inspection
8504c005-d7e3-5244-97a7-5e221ec42e06 | note | RECORD OF CONFORMITY: This ITP Signed off
b9a5a2c7-0c44-59fc-a964-3ddcb9384b19 | note | HP*
e369dd91-0632-52b6-b619-f47de6ab94b2 | note | RESPONSIBILITY: Fulton Hogan Engineer
93b23464-f3d6-5772-996c-1d608f412b8d | textbox | Date Completed:
436ee04b-ec8f-40b5-8141-52f7a2e07f84 | checkpoint | 1.2 Implementation of all measures and controls
2c2fc8af-44b0-5e2b-ad4d-d341c4571952 | note | FREQUENCY: Prior to Commencing Activity
1023087a-4daa-52fd-89e6-3cd780215619 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
56c155fb-754e-5ba0-9547-ee5ec942d3e3 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
1c13aaf8-b4f0-535c-84fd-395be041ecbd | note | INSPECTION/TEST METHOD: Inspection
5e67e541-c1c0-582d-be19-5343212d3432 | note | RECORD OF CONFORMITY: This ITP Signed off
8a502d21-a97e-5615-8bc7-fc3d9b8a8204 | note | HP*
768eee18-ca33-5b49-a553-7dd6c126e06c | note | RESPONSIBILITY: Fulton Hogan Engineer
a3394957-8443-5f09-abb7-d692bf124c18 | textbox | Date Completed:
b13ac22b-029a-48b5-92de-c77a38a9f454 | checkpoint | 1.3 Existing Bluestone Kerb Demolition
6c29f111-dde8-576b-bdb4-57fc30616ab4 | note | FREQUENCY: Each Lot
4e3ff463-c742-53ad-a567-ce406baaff89 | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
df7f5d89-0cc3-597e-bef7-0e0f6606f481 | note | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
6a990d7a-56b0-5b7b-98cb-0ee99448b91d | note | ○ Bluestone shall be salvaged and re-used in new kerb alignment
92c089f7-2a00-502f-956e-afba3476a00f | note | REFERENCE DOCUMENTS: Work Procedure
f8a8e6e6-b60b-56a6-ade2-a3a00299ae3c | note | INSPECTION/TEST METHOD: Inspection
4ab3a444-a9de-5e0f-9218-1a85ab798a7b | note | RECORD OF CONFORMITY: This ITP Signed off
d8921a99-ffc2-5acf-acd6-0c5dc5feced6 | note | IP
16ccd69c-9aa3-5b26-92f6-a76daadcca07 | note | RESPONSIBILITY: Fulton Hogan Engineer
a1febe65-d842-5c29-92ff-44ec8c1f7ec5 | textbox | Date Completed:
31668000-a559-4e65-9e70-23d3b8d5f736 | checkpoint | 1.4 Setting out
211a0322-53f7-54c1-8e55-a318bab7697f | note | FREQUENCY: Each Lot
377c7315-28a3-596a-b607-93531a2777dd | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans
2f55be8f-a23e-58af-8ce0-d57261530043 | note | ○ Alignment of new kerb shall be marked out using string line
e463bc12-38ba-5a41-98bf-f85f3f018625 | note | REFERENCE DOCUMENTS: Work Procedure
3e0925da-b495-53a9-95d3-be54e596e778 | note | INSPECTION/TEST METHOD: Inspection
b7fea9b5-7c04-5fc9-857b-468fa5a2ad6e | note | RECORD OF CONFORMITY: This ITP Signed off
c3697a64-76ac-5d48-ad1a-13c8791d8627 | note | HP*
c700975f-8f23-5995-8b58-c599a5723ec9 | note | RESPONSIBILITY: Fulton Hogan Engineer
693aec83-00d4-5e5a-8094-00545837a339 | textbox | Date Completed:
f2db7c89-467e-4e49-bce8-e9201b581a4d | section | Construction Works
cb8f5fb5-cac7-405e-b6ee-1f6e636c4b52 | checkpoint | 2.1 Saw cut (if required)
1e29b3a8-4677-500b-bc29-566ec1fdc9e4 | note | FREQUENCY: Each Lot
87113702-9551-5ae9-a5ec-76c2cc6ec9c0 | note | ACCEPTANCE CRITERIA: Saw cuts shall be made to the following depth for existing asphalt pavements:
ac94c958-fdf5-5d38-b2e5-06c2d5fc3bdb | note | – Footpath: Minimum 75mm
f8a7b767-1cd7-51a1-9da2-5a1495a1ff31 | note | – Roadway: Minimum 125mm
d55a63b8-8d0a-528a-b18a-b693bfb78193 | note | ○ Excavate to allow for design heights
087f9702-92e3-5851-8c33-50ad226712f6 | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 2.0
023a549f-7c8d-5974-90ad-470820d41c05 | note | INSPECTION/TEST METHOD: Visual Inspection
831a121e-a74c-5dd9-8484-7aee8740cc7f | note | RECORD OF CONFORMITY: This ITP Signed off
973a6ca8-1a17-52cf-ad49-fa0eb69ebabe | note | IP
ffb7a3b5-6781-5650-9d91-aa00077db56c | note | RESPONSIBILITY: Fulton Hogan Engineer
782d8833-7f4d-5b8d-910d-bd5e5a6a4a94 | textbox | Date Completed:
3d3a81f5-b1ad-4ec1-8ead-b0f656d03405 | checkpoint | 2.2 Concrete Placement and Setting
bd963ca4-2f14-5804-93ba-b21aedc83562 | note | FREQUENCY: Each Lot
5bcfd4fc-0082-5778-9683-526514b7aca7 | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness
b73cc350-e3c6-5f84-a9b3-ce8911b7ce4a | note | ○ Gaps of >10-30mm< shall be provided and filled with mortar
7bbf44b6-2d6c-5487-b207-14fd45d4e430 | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
65ba6c8d-b190-5941-903d-65adb24f7741 | note | INSPECTION/TEST METHOD: Visual Inspection
57cd6635-24ac-55fb-82b6-4cfa511eaa49 | note | RECORD OF CONFORMITY: This ITP Signed off
b67d58f9-6f2a-5111-884b-9ec4bef24247 | note | IP
4be25011-d8ba-59a0-95e8-5894529a52bb | note | RESPONSIBILITY: Fulton Hogan Engineer
662ad976-a6ef-5c99-9681-482d43ddd010 | textbox | Date Completed:
6dff0b56-658b-4f4a-83e2-9e72799ca61b | checkpoint | 2.3 Mortar Mix
fdf763c0-e800-56ff-bbfe-cce829e7ceb2 | note | FREQUENCY: Each Lot
8f2f7646-990d-58c4-a967-86a2cf61f00d | note | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following:
bec6c755-ecf4-5c9c-9df9-3f42ba1cd547 | note | ○ 16% cement
3291b211-5413-5cd1-84d4-6956e3218167 | note | ○ 16% stonedust
957c707f-14e0-54dc-9961-f5fc9d5fbf12 | note | ○ 67% blended wash sand
d85f63d3-62cd-5008-aea9-54e365c973fb | note | ○ 1% lime ready mix grout
b2f9ade4-254a-5205-8e5a-38d559443cf8 | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 4 AS 3972 CoM SD 1P 50406
142c675c-b8bb-5c48-88fe-7205b7603a02 | note | INSPECTION/TEST METHOD: Verify
3b320b15-aa8d-5298-8151-95321b325148 | note | RECORD OF CONFORMITY: This ITP Signed off
628b502f-edbb-596f-b4a9-a5bd348f1793 | note | IP
38e475cd-5d04-50f9-a488-032f68115d25 | note | RESPONSIBILITY: Fulton Hogan Engineer
82283328-6071-5e51-a9df-317afb53290e | textbox | Date Completed:
dd0266a1-1500-42b1-ab99-07786b221406 | checkpoint | Final Inspection
c7253003-22c2-5264-a6b3-6fd552def326 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
71c7af5b-34c2-5c66-9880-d32ae3a514c7 | textbox | Print Name:
7ea0db66-3db7-558b-9951-2a50bd7ee66a | textbox | Position:
3f75c72c-a9b9-588a-8b82-b618d5161fcd | textbox | Date:
e41effd9-76c3-454a-8a1b-7b8504d3ead6 | checklist | ITP-015 - Sign Installation | itp | ITP-015 - Sign Installation
0a54e461-5afa-495b-8ab8-2604bcdfcc83 | section | Preliminary Works
9f42792b-6570-463d-8a45-688b24435044 | checkpoint | 1.1 Check for correct documentation
9411ce85-5df7-5bc5-ba74-e4e71498410e | note | FREQUENCY: Prior to commencing any activity
96228a04-2bf7-5d5a-8a46-a6457419672b | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
c2250e88-6d6c-547d-b6e5-3aee2663498b | note | – using the correct and complete set of drawings
42652ddf-e758-5f80-b279-438560d16892 | note | – all drawings are the latest revision
85ea196d-d7c2-52f2-a53d-9b827fa965e7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
fee2fea4-cda9-5ba6-becf-e97d9eed787e | note | INSPECTION/TEST METHOD: Visual inspection
07a644ec-842a-5068-8567-f7ab28dac2ae | note | RECORD OF CONFORMITY: This ITP signed off
f9b770c3-1f58-5fc9-a6cc-4ce6ab611249 | note | WP
1c406b57-2f37-5e94-8735-184117b4c375 | note | RESPONSIBILITY: Fulton Hogan Engineer
2d118336-9e5d-5c47-ab75-e1ecf347249d | textbox | Date Completed:
b7ea17f9-7aad-4984-ade5-008bad646ae6 | checkpoint | 1.2 Implementation of all measures and controls
47a37243-5192-520f-8069-65b13dcfc5e2 | note | FREQUENCY: Prior to commencing any activity
88d3ce82-d62d-5cb8-b246-2f33298b3507 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
6d3c96b7-df1d-58e3-96b7-5ff981cd35c3 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
cff9098a-bb8b-5bbc-8135-3accd510fa02 | note | INSPECTION/TEST METHOD: Visual Inspection
414e03bb-fb1b-5edb-b2b5-ed81f52946c9 | note | RECORD OF CONFORMITY: This ITP signed off
8a36ee82-636c-56ce-a9c7-f51319218a1e | note | WP
a00c5802-a0e1-5596-9bc2-b03b49e89a81 | note | RESPONSIBILITY: Fulton Hogan Engineer
388c2221-ad13-5016-9c2a-0b952895377f | textbox | Date Completed:
5dca69a3-cdc5-4270-9327-a3accda73ba6 | checkpoint | 1.3 Signage Conformance
b0c3a23f-a71d-5e93-beb3-5df56756c47e | note | FREQUENCY: Before commencement of activity
7624ab27-2cd8-5755-83c9-72a4ba632eaf | note | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
077adcee-c3b0-5ff8-913a-3bdd33d085f1 | note | REFERENCE DOCUMENTS: Drawings, AS 1742
3dc3fdea-0d93-5f8c-924d-4cb53258d6f8 | note | INSPECTION/TEST METHOD: Verify
818c77a5-e6b4-5212-8576-7faf44a918b5 | note | RECORD OF CONFORMITY: This ITP signed off
aea1ff9f-647d-547a-b51c-21121803d669 | note | WP
f215413b-5f6a-5a7d-bdfc-44eb7148787b | note | RESPONSIBILITY: Fulton Hogan Engineer
9dc3ab54-01da-5ed9-a6ea-2a6848e8cd26 | textbox | Date Completed:
097e1777-89aa-4ea3-84f8-0403172f92e9 | checkpoint | 1.4 Service Identification
6205e47c-4445-54f7-b2da-4a01e05a48de | note | FREQUENCY: Prior to start
837b170d-42cd-5ea7-843d-ade2740a5557 | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
8872439e-4f3b-501f-950b-57fc7af4a5bd | note | REFERENCE DOCUMENTS: DBYD, Service chart
e2591912-e99d-5e09-ab72-ecc53a1d5d60 | note | INSPECTION/TEST METHOD: Verify
342a8f91-e8d2-54d9-806e-f7fde9c157f2 | note | RECORD OF CONFORMITY: This ITP signed off
9db28279-0a00-515e-872a-ad2305fd8a73 | note | WP
d1c6a6ab-f6b8-5061-8be7-eec906467043 | note | RESPONSIBILITY: Fulton Hogan Engineer
b89bc66c-f11e-5ed3-a494-c8265685548b | textbox | Date Completed:
439a1b11-87ac-428d-9061-10905eb22efc | section | Construction Works
4b8ed4df-b912-43dd-b799-c485f9f5384c | checkpoint | 2.1 Setting Out
bb9c1e4c-586c-5de3-a697-0a970eaf2d00 | note | FREQUENCY: Prior to start
ebb43ff7-69d9-597b-8adc-66a9336cff29 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
2c74c072-c886-529b-a9db-d9a3de93a90f | note | REFERENCE DOCUMENTS: Drawings
2bf38303-c58c-5374-b4a7-2b88b4be41a3 | note | INSPECTION/TEST METHOD: Visual Inspection
d15149a5-52aa-5da1-b781-5de08a0d8c3c | note | RECORD OF CONFORMITY: This ITP signed off
91a16a90-57fb-5dd9-9193-97ae985d40e1 | note | IP
b2ad7a55-0d30-57ab-a968-3157586c89b7 | note | RESPONSIBILITY: Fulton Hogan Engineer
90de75c6-cb9e-51d2-a30f-014d651ab706 | textbox | Date Completed:
90155beb-d977-4a1a-88c8-432f7fa9552c | checkpoint | 2.2 Post & Foundations
56ed9b34-d1f4-5207-8b4f-9efb5a3fc853 | note | FREQUENCY: Prior to Start
9dd43760-0d9e-551a-b71b-bbebadf4f624 | note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
b5077537-bc5d-5acb-a2fb-9f45870daf9f | note | REFERENCE DOCUMENTS: 714.06
0c469bcd-90d0-55e1-9b43-04c1b7a633db | note | INSPECTION/TEST METHOD: Visual inspection
48ac6f91-0fc9-57cc-a02c-b43809bc07d7 | note | RECORD OF CONFORMITY: This ITP signed off
175751fb-095a-539d-a13c-158a967c048b | note | HP
fc6cee8d-b5e8-5c7d-911b-b29f89ada9cf | note | RESPONSIBILITY: Superintendent
7bac6bba-67b5-51dc-a05d-213c2f2727ce | textbox | Date Completed:
b58e83c6-2cc2-4913-89af-f5ecb8b8bb20 | signoff | AUTHORITY HOLDPOINT
4fa2bf69-7892-4495-ba14-cdbbfa99c4d9 | checkpoint | 2.3 Signage Install
8f01d7c2-393e-5218-91a5-8319ab3fa774 | note | FREQUENCY: Each Sign
3a9b89fd-c852-5cbc-bab6-b13247094d2a | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
9cb4e914-f8cf-52c2-89a2-7c909f360fc9 | note | ○ Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
26025769-38ed-5341-9ecb-ed26c430e58c | note | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
c858a82f-2d2f-5c37-be2c-b933f7d8a717 | note | REFERENCE DOCUMENTS: AS 1742, TS 1313 Drawings
03e7484a-28ed-51c5-a9d5-9a5e0f84fa88 | note | INSPECTION/TEST METHOD: Verify
bb52a964-748c-5091-9873-6e8d68138129 | note | RECORD OF CONFORMITY: This ITP signed off
4b420965-1ac8-5dfb-86d5-93ea201bfd5a | note | WP
e17074b3-92d3-5426-a3d6-d3ef70c8d0c2 | note | RESPONSIBILITY: Fulton Hogan Engineer
93a7dddf-78d7-5970-a68b-3bbe888b28e9 | textbox | Date Completed:
b7ea296b-7038-48f6-a20d-5fb4376049e5 | checkpoint | Final Inspection
be83e8d5-5262-5bd1-9231-98b5149e5f86 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1e78ff96-6b93-5e55-928d-9fdaabd90397 | textbox | Print Name:
0fd21b84-69d2-59ee-8cd4-a754dac9f4d8 | textbox | Position:
6ebbd5e9-f66e-5d5b-80bc-a43ca868d725 | textbox | Date:
622bb483-3625-47d1-b31d-bab5ee1f794d | checklist | ITP-016 - Platform Bluestone Pavement Installation | itp | ITP-016 - Platform Bluestone Pavement Installation
29e7f8ca-a792-4466-8b13-52cefb6fbeb7 | section | Preliminary Works
fb9ef2ef-8e24-4c09-9b4f-2454a746fd8a | checkpoint | 1.1 Check for Correct Documentation
27cfc167-2007-5524-ac09-086a2a4a2cec | note | FREQUENCY: Prior to Commencing Activity
667b9e60-34ce-5265-bc75-695ed7130076 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
b50e00fb-204d-56cb-91ce-c0a54fd7d552 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
f07f33aa-ddf2-5a36-9157-913d76d2d143 | note | INSPECTION/TEST METHOD: Visual Inspection
5bd868db-11b0-5ebd-9ae3-6bb67f6092e2 | note | RECORD OF CONFORMITY: This ITP Signed off
2a8a283e-c4aa-506f-8dec-6d9deaa4b349 | note | HP*
6196cf01-4184-5319-a093-9c0a5f54d562 | note | RESPONSIBILITY: Fulton Hogan Engineer
aedb189f-9866-568c-995a-690e01158818 | textbox | Date Completed:
f0d95b63-3908-4781-9b10-9ba7cbf49ef9 | checkpoint | 1.2 Implementation of all measures and controls
6064c59d-1949-5e10-98dc-12c92ee3b682 | note | FREQUENCY: Prior to Commencing Activity
539294b1-ad69-5be3-bdbf-175d7e9f1a3e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
2ea25cd4-afcf-564e-bab8-d72d96a5243d | note | REFERENCE DOCUMENTS: Work Procedure
2ac36188-7a46-55e2-b146-8030ca097d0a | note | INSPECTION/TEST METHOD: Inspection
ef931860-9ea9-58e6-99a0-fc1cef4d87f1 | note | RECORD OF CONFORMITY: This ITP Signed off
f4f9edd7-ec73-5546-9f97-f6555608c57e | note | HP*
64cd0287-1488-5f04-8c6b-4cce074f0d55 | note | RESPONSIBILITY: Fulton Hogan Engineer
75395040-2822-53c0-a72e-5f2af1b4029e | textbox | Date Completed:
90d1dcba-42b1-4535-b8ce-465a06281b34 | checkpoint | 1.3 Check Condition of Material
0a3d4fbb-55d6-5876-a957-cfd963171e58 | note | FREQUENCY: Prior to Commencing Activity
0416e79f-3e13-5769-b5df-d34bcf0fc3c6 | note | ACCEPTANCE CRITERIA: All bluestones shall be inspected at delivery for visible damage
992880ce-a591-59ea-993a-18db35aec4a0 | note | REFERENCE DOCUMENTS: Work Procedure
fecd0d49-2fd5-5e6d-9bad-c4501307d57c | note | INSPECTION/TEST METHOD: Inspection
82ae0975-b2e4-5948-9d97-830017980c07 | note | RECORD OF CONFORMITY: This ITP Signed off
40c7ead1-ff2e-57d5-83e8-6baef7d0174b | note | HP*
b0af2482-657d-54fa-bb05-b77b47cdc556 | note | RESPONSIBILITY: Fulton Hogan Engineer
821db2cf-46bd-51c5-83e4-a859534b73e0 | textbox | Date Completed:
10745f23-3304-4696-ab65-e53529735b37 | checkpoint | 1.4 Lifting method
89cceed9-d19e-5e61-8384-f3937f348d34 | note | FREQUENCY: Prior to Commencing Activity
b9f6f769-c306-59ac-b93f-caf5c4f23ef2 | note | ACCEPTANCE CRITERIA: Bluestones can be moved with excavator and grabs/slings or with a vacuum lifter.
dc79218b-5e84-571d-8710-1f5496e68234 | note | REFERENCE DOCUMENTS: Work Procedure
149961e3-59db-503d-9b4b-40a40ce8b0b5 | note | INSPECTION/TEST METHOD: Inspection
22f12178-774d-5c3f-9448-f817ec528d64 | note | RECORD OF CONFORMITY: This ITP Signed off
e409e4fb-41c9-513d-a456-8018426889e2 | note | HP*
7a240c8e-23b4-54a6-a53f-9048134bffe9 | note | RESPONSIBILITY: Fulton Hogan Engineer
a4a8dfcf-4e74-5084-aa76-e4856b66d17f | textbox | Date Completed:
9cea789f-2627-4aad-9666-e86b12f90f04 | section | Construction Works
b19997a7-685b-4de0-80ea-c9c35dfe361d | checkpoint | 2.1 Base Course
1019ed53-e197-5c9d-b155-c31c32226e09 | note | FREQUENCY: Each Lot
f2a4bde3-3371-52b0-8772-56c7581ebb38 | note | ACCEPTANCE CRITERIA: Class 2 compacted rock (98% modified density) shall be compacted to min 100mm thickness.
ce3f20f8-e845-5abb-9719-b65f5edc2d7f | note | ○ Soft or areas deemed unsatisfactory shall be removed and rectified
73da078a-da03-5781-a7a2-05a6989dfda3 | note | REFERENCE DOCUMENTS: STD_T6111
7679a76f-8506-59ec-acf6-e05cde3268f8 | note | INSPECTION/TEST METHOD: Visual Inspection
d2dcec9c-079d-5cd8-be99-3d45012a2f08 | note | RECORD OF CONFORMITY: This ITP Signed off
3bd137c3-0224-588a-8c37-8d40f8fe374e | note | IP
96315d5c-66e5-5053-80d8-53a16061602c | note | RESPONSIBILITY: Fulton Hogan Engineer
8d6ba928-7a47-5e7b-8ea3-00d98cc4d7fc | textbox | Date Completed:
b1272539-f9cb-44dd-8bb7-a784d8c46fce | checkpoint | 2.2 Concrete Placement
5aeabeab-cef5-5910-9d92-7eb5d93bcc19 | note | FREQUENCY: Each Lot
d2783009-700c-50a3-b2bd-bb4ad263a196 | note | ACCEPTANCE CRITERIA: Bedding shall be >100mm 32MPa concrete with 6mm aggregate. To match the blinding layer of the edge beam
b4374dc5-eff6-5e93-9744-f850b1aaafda | note | REFERENCE DOCUMENTS: STD_T6111
819a1755-6db1-5e6e-9a4b-41999f2f7c66 | note | INSPECTION/TEST METHOD: Visual Inspection
509c9e05-2d0c-5fb6-8872-ee639fb52075 | note | RECORD OF CONFORMITY: This ITP Signed off
1665650c-d783-585f-a2d2-d830d3a459d3 | note | WP
2d748304-9f70-5da5-85c2-e0a9a0ca6c32 | note | RESPONSIBILITY: Fulton Hogan Engineer
b8fc299d-5e9f-5746-ba11-53ad03b9cb7c | textbox | Date Completed:
d4efda43-13d2-4e11-8dc2-a89b65e5a45f | checkpoint | 2.3 Setting
48d5d899-a52d-5d0b-b64b-cb3fbd41180b | note | FREQUENCY: Each Lot
89d15858-38da-535f-bc6d-9e2126411fa0 | note | ACCEPTANCE CRITERIA: Tie rods shall be N12 (300mm long) and chemset 100mm into kerb, 2 per stone
8021f5fc-e7cc-5ae9-919c-253f06842cc5 | note | ○ Tie rods shall be installed with bond breaking compound specified by superintendent
543ceb2e-a69d-5371-8b84-6366a42d0257 | note | ○ Bluestone shall be laid 150mm below finished surface level
645a14ed-0a5e-5e5c-a6d6-a84d9c1c97e9 | note | REFERENCE DOCUMENTS: STD_T6111
6c45cfb0-28fb-53a4-9931-5e0da9ce20b2 | note | INSPECTION/TEST METHOD: Visual Inspection
b1c01c30-c2bf-53e9-8897-46e97429cef4 | note | RECORD OF CONFORMITY: This ITP Signed off
49a69811-6a0a-5835-a2c8-af2c41ad2ba6 | note | WP
790b608c-9f1d-5fdb-af55-ea7e2a3f46e4 | note | RESPONSIBILITY: Fulton Hogan Engineer
3eb16f50-dc93-5916-9f21-cd45ae7644ca | textbox | Date Completed:
a791b43d-b50c-44f7-b751-7be02e0ef553 | checkpoint | 2.4 Sealant
4859b52f-42a9-5a66-a724-e79f5199c12c | note | FREQUENCY: Each Lot
e99d1561-7e0c-564d-950f-4fd2263240b5 | note | ACCEPTANCE CRITERIA: Sealant at construction and expansion joints at back of kerb shall be 'Gun Grade THC 900' by Tremco, of black colour
327c2eb1-ed31-5d11-8b35-490097abc7e7 | note | ○ Loose materials shall be removed as not to impair adhesions
15dfc3c4-5204-58c9-bcf5-61cc4bfce91b | note | REFERENCE DOCUMENTS: Work Procedure
dfbeadc1-dc24-5ecb-a0db-172b020ad22e | note | INSPECTION/TEST METHOD: Visual Inspection
26369ac6-06ca-589c-bbd9-682a83367a81 | note | RECORD OF CONFORMITY: This ITP Signed off
0942498c-5b4f-54d8-950f-5e565f75098f | note | WP
24137daa-d44f-5484-808f-0155be29449f | note | RESPONSIBILITY: Fulton Hogan Engineer
44e66cee-cbc1-59a0-a7ae-77702472ae72 | textbox | Date Completed:
0eb90275-d171-4d14-81db-19f093100fa3 | checkpoint | 2.5 Platform line marking
d76cb539-f63a-5504-97aa-b4778b218ec5 | note | FREQUENCY: Each Lot
1e165861-1328-5c39-bad7-3becaccdc1c0 | note | ACCEPTANCE CRITERIA: 50mm yellow lines shall be placed along the edge of platform, one on the top face and one on the front face of the kerb.
96125f34-d13e-55e1-93a4-f006cf3b989c | note | REFERENCE DOCUMENTS: YT Construction Standard
915c1400-6515-56fb-949e-a7cc83f7a7b1 | note | INSPECTION/TEST METHOD: Visual Inspection
ac67f574-4639-59bf-b304-1ed0138a5c5d | note | RECORD OF CONFORMITY: This ITP Signed off
00630eb4-cbfc-5ff1-897a-1ec0eb220776 | note | WP
e7a203a9-bc5a-5b28-9575-3f85d56ecac1 | note | RESPONSIBILITY: Fulton Hogan Engineer
585b2688-cc6c-5929-a8ed-7926c47b29dc | textbox | Date Completed:
d22bfe2c-2228-4bbc-bc26-88334b39c4fb | checkpoint | Final Inspection
d9f83c6e-c3ec-58e8-82dd-b4b558c7f9a1 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e7dec7e6-cbeb-5a6b-8fc5-aa4279c0e54a | textbox | Print Name:
38d79703-0d70-5768-9d2c-fb771c8a23f9 | textbox | Position:
6d864b20-225c-5e44-bad4-f244e0f8b987 | textbox | Date:
4b5ee26c-63c9-461f-807d-65c3efe7e9ec | checklist | ITP-019 - Fencing Installation | itp | ITP-019 - Fencing Installation
74cdfd32-e160-4b67-a538-b86c139b3df5 | section | Preliminary Works
bbad0132-0f1e-47ab-a97d-e834720ea9ff | checkpoint | 1.1 Check for correct documentation
52cdfb20-00e8-5928-b5c0-66c7183e67f7 | note | FREQUENCY: Prior to commencing any activity
247e6b2c-024f-5240-b2ed-dea8782de0b5 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
3f1aea56-cca0-5850-83c3-b6de8eeda3b0 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c9cf506a-203e-5ea8-92bc-3922f15d46e2 | note | INSPECTION/TEST METHOD: Visual inspection
4e5ea4da-f76d-5f76-a9b3-945ad4008572 | note | RECORD OF CONFORMITY: This ITP signed off
9a4911ba-2e46-5151-9e5c-2595f7d1fcf8 | note | HP*
36ea455f-c8f2-5c58-a852-023222074b57 | note | RESPONSIBILITY: Fulton Hogan Engineer
8d9d9503-2e43-5742-a59b-e7c0e7114c70 | textbox | Date Completed:
2f3ef464-7011-481e-a015-74c41bc8213d | checkpoint | 1.2 Implementation of all measures and controls
75f7a972-b136-5d00-8f02-d0a5c9d07a49 | note | FREQUENCY: Prior to commencing any activity
50d75063-b3f7-5fa5-90af-504af50ec5c5 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
dc9cda4b-fc5d-5385-8d28-4de4600d3490 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
d93b8774-0d1d-5e3f-a3ac-cef192d12bea | note | INSPECTION/TEST METHOD: Visual Inspection
2e538c7f-6d0a-5e79-b0fc-bda899cf72da | note | RECORD OF CONFORMITY: This ITP signed off
c8019546-f1d7-5a3a-81d6-9236a771d458 | note | HP*
aee21d5d-488d-5053-9329-547a1e78847c | note | RESPONSIBILITY: Fulton Hogan Engineer
ee5ca4d9-9c46-5b14-9595-473eeada75db | textbox | Date Completed:
009c789c-8ea7-457a-a096-c5ffb8b2a182 | checkpoint | 1.3 Check Materials
d62e2420-7083-5b58-9ea9-994758011416 | note | FREQUENCY: Prior to commencing any activity
fc621738-a9e4-5a20-8354-b7fe3a40387f | note | ACCEPTANCE CRITERIA: Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish, linished, pickled and electropolished
a0ee9cad-cc34-57cf-bef6-9894950a6b4d | note | ○ Welding shall be in accordance with AS1554
9ba16b1b-a60f-54e6-97e1-c92cb5d40875 | note | ○ Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000
5e9cf967-d46e-5e5d-90b5-8cadd41f2406 | note | REFERENCE DOCUMENTS: STD_T6000 CE-021-ST-0012 cl 4.3.1.4
8429c468-9a39-5206-b3ad-21f18283381e | note | INSPECTION/TEST METHOD: Verify
0f6552dc-78ba-559f-8568-2b366c571fb4 | note | RECORD OF CONFORMITY: This ITP signed off
725500eb-d8f0-5ed4-a13e-f2eb1b7ccb89 | note | HP*
68f91ff2-edc0-59e3-bebf-b2776dff26d4 | note | RESPONSIBILITY: Fulton Hogan Engineer
96b8240c-d49f-5559-965b-c1c039c51566 | textbox | Date Completed:
19278925-7946-4f3d-acae-bf4b75f93c6e | checkpoint | 1.4 Confirm Footings position
ff1dd8b2-78b5-5a39-b396-2037baf80cb1 | note | FREQUENCY: Prior to commencing any activity
1b01c652-78d6-5c8e-ab85-c6cc1bbf4410 | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
85d87938-2441-59d3-b1c2-730b8f436ff8 | note | REFERENCE DOCUMENTS: Construction Drawings
649e9fdc-6a9c-5873-973a-80d3199da446 | note | INSPECTION/TEST METHOD: Verify
dab740a8-50fb-5bf5-8891-3f6a006420ae | note | RECORD OF CONFORMITY: This ITP signed off
92adecb9-4e48-5086-bb25-7c7f4f72a9bb | note | HP*
d5156496-1bb7-53f5-b7f2-fac04ebcfe43 | note | RESPONSIBILITY: Fulton Hogan Engineer
0104c7f8-a56a-5c84-bd7f-ae39a651e105 | textbox | Date Completed:
6967c07c-3055-4ebb-a993-6646aae90316 | checkpoint | 1.5 Bonds
011a28d8-ca14-55b6-bab9-59d35396e3a8 | note | FREQUENCY: Prior to commencing any activity
6c3fc66e-d609-5c2a-ad5b-3ea1169dd35d | note | ACCEPTANCE CRITERIA: •Ensure fencing is isolated and earthed to achieve electrical isolation. Lug shall be fitted to baseplate at specified fencing location
c8fb6293-dde4-5a82-8416-ae8a05aa0314 | note | REFERENCE DOCUMENTS: STD_T6000
ca0d2294-24e1-577d-bfd2-ae8d0a05e75e | note | INSPECTION/TEST METHOD: Verify
e407cad8-5f7a-5074-8162-2e5ba1e2f7c7 | note | RECORD OF CONFORMITY: This ITP signed off
08323ecc-34f8-5625-833c-3092b9a84407 | note | HP*
00db8aa5-2875-5036-9f7f-abc2b80ecd58 | note | RESPONSIBILITY: Fulton Hogan Engineer
13051538-e33e-57f6-8e18-9266de027224 | textbox | Date Completed:
b2e29f1b-f0ea-492d-a0fb-6bf38b6784f7 | section | Construction Works
45b8d35b-414d-4f7b-a93d-1fd7906551be | checkpoint | 2.1 Footing Installation
4d2d8a03-96f0-51f9-8afd-288125ccbf8b | note | FREQUENCY: Prior to Asphalt
8a43b44f-ccc5-5a9c-854a-d13fb044f9d2 | note | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20
e5c742d3-d506-5e1e-82e5-c6a075212794 | note | ○ 4 M16 hot dipped galvanised bolts shall be chemset 175mm into embedment, per footing
5b93ee14-6bc1-5a05-a47b-19f078fbb851 | note | REFERENCE DOCUMENTS: STD_T6002
c0c65957-a2c0-5233-b5d1-768dc0567bec | note | INSPECTION/TEST METHOD: Verify
68e3d2b8-d3eb-58bb-929d-d5cf31d5dc77 | note | RECORD OF CONFORMITY: This ITP signed off
b7b43ab1-3c8d-5ed0-8e74-5f3ff849609d | note | IP
524503d1-2d29-5eee-a1b2-e1eb248d1dc2 | note | RESPONSIBILITY: Fulton Hogan Engineer
7e9230db-f89a-5adc-9d79-e345fec91105 | textbox | Date Completed:
74098ad5-d014-45b6-b89c-a86fe3d78363 | checkpoint | 2.2 Post Installation
84866559-72f0-5fd8-a8a6-303da5b5adfc | note | FREQUENCY: Each Lot
89c21473-cb17-5928-9ce1-ca529fdb1ac1 | note | ACCEPTANCE CRITERIA: Post shall be installed to designated height and level
6875b611-9920-5a77-86f9-1386237db48c | note | ○ Installed to footings with bolt assembly
36480988-1263-5a59-8ec4-f8361aaa2783 | note | ○ All bolts shall be insulated from base plates, using non metallic sleeves and washers
98bd5408-94d7-5de4-892d-967ecba28603 | note | ○ The top of fence base plate shall be level with surrounding pavement
cc097bba-0f11-5aec-bad0-6f6f3dcd6c9f | note | REFERENCE DOCUMENTS: STD_T6002
4a191f84-0d1f-5c81-a32e-46bc94f82102 | note | INSPECTION/TEST METHOD: Verify
7da59b25-3f45-533b-aa65-a7b21fbfb682 | note | RECORD OF CONFORMITY: This ITP signed off
ced1e34d-13bd-5c24-ad88-e11190631900 | note | IP
3840ae8f-aae6-5c96-b0b3-d0ab02a14d9b | note | RESPONSIBILITY: Fulton Hogan Engineer
521631c6-4f38-5d33-827a-a1e5b7108948 | textbox | Date Completed:
689c4bc1-1413-4340-8029-d45272ef9702 | checkpoint | 2.3 Grout Installation
c2d07366-8c78-5262-b9d3-8f8b2e47e658 | note | FREQUENCY: Each Lot
b5d90c60-8f54-585f-8c3c-c811487faecc | note | ACCEPTANCE CRITERIA: Footing surface shall be cleaned and roughened before application
c165f6cc-3c70-500b-95b9-fe9710225692 | note | ○ 50mm of Non shrink dry pack grout shall be placed under base plate
32b65832-5ca3-54ad-983d-d2c08770b6e1 | note | REFERENCE DOCUMENTS: STD_T6002
6261b487-d856-50b9-a8c7-18cf365d93e3 | note | INSPECTION/TEST METHOD: Visual inspection
b074ff58-9ff1-5c1b-8db7-a47e918a387b | note | RECORD OF CONFORMITY: This ITP signed off
365c639e-11ff-513e-a41b-b9ac50bcfa9b | note | WP
182e1e78-d2cd-53fe-ad3a-2cd37f6eef9e | note | RESPONSIBILITY: Fulton Hogan Engineer
8c1694ea-6643-5004-bd07-8ac44d3cf4ab | textbox | Date Completed:
e12694f1-3096-4535-b37a-a8db4e89fd72 | checkpoint | 2.4 Continuous Handrails
3d72cdb8-8521-5ff5-a20e-1005b467fcfe | note | FREQUENCY: Each Lot
c17b714e-2d05-5082-b08e-d2182b28c398 | note | ACCEPTANCE CRITERIA: 5mm cap plate on handrail returns
aaffd5f4-e1fd-5b98-bc33-faef9271f391 | note | ○ All sections to be welded as per AS 1554
254ab823-f94c-56f8-8e79-d09cc6a63bd5 | note | ○ All sharp edges and welds to be ground back to smooth finish
64bb2db1-9569-5452-a563-96a4ff08e223 | note | ○ Domed buttons to be welded on top of handrail 150mm from the post centreline
20e02920-b5c2-5e4e-8a80-fccc49629720 | note | REFERENCE DOCUMENTS: STD_T6001 & T6002
a3bdab72-d729-53ec-a9c1-cfca76bed42e | note | INSPECTION/TEST METHOD: Verify
f646657e-b9b3-5400-96a9-ddaac26b190b | note | RECORD OF CONFORMITY: This ITP signed off
80bde574-8bc6-5180-837c-82ed3d6d586d | note | IP
712a6778-0ec6-5ce2-afd0-d8dd2e6395ea | note | RESPONSIBILITY: Fulton Hogan Engineer
53d93aea-0332-540c-a954-75c58890cb80 | textbox | Date Completed:
45b151b6-9845-4626-840d-530dd07cf078 | checkpoint | 2.5 Wire Rope Tensioners
867000f2-d93b-5861-941a-dd26303b4a69 | note | FREQUENCY: Each Lot
6336ecc7-ec1a-5d33-b545-7220a7de19ee | note | ACCEPTANCE CRITERIA: Architectural wire rope cables to be inserted into ferrel on fence post and to be tensioned with tamper proof fastenings (Loctite 243 Threadlock)
2ae21762-a54b-568b-a065-b8eac89964da | note | REFERENCE DOCUMENTS: STD_T6000, T6001 & T6002
3e102256-c19c-565a-ae48-6b4ef95a79a9 | note | INSPECTION/TEST METHOD: Verify
c39b0ba7-2b96-5132-bc19-2521df9284a6 | note | RECORD OF CONFORMITY: This ITP signed off
5b261bdf-a59b-5252-aa0a-3f9cae36ee3b | note | IP
3c6e2ad7-240d-5098-a65d-007884a371cf | note | RESPONSIBILITY: Fulton Hogan Engineer
5dcf63da-cfcd-5bf5-a971-5dcfd32fc8f1 | textbox | Date Completed:
c1b2ad36-ac8f-4704-b74b-69188e1df90d | checkpoint | Final Inspection
96df1837-9ac1-5c0c-8ec0-5997ead9bf06 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
14c7f96e-5d1f-5e16-bf59-4f76caf30ab5 | textbox | Print Name:
ec2fdfc2-126d-5554-af75-b8947610bda5 | textbox | Position:
3521f7a1-1cac-56d0-a7f9-d3bce7ea273b | textbox | Date:
a1acb052-fa9c-4f13-80f0-60b4604692f2 | checklist | ITP-020 - Exothermic Welding | itp | ITP-020 - Exothermic Welding
915547a1-9293-469b-93df-88abb75b7d3b | section | Preliminary Works
5b748def-7057-418f-be72-97e3e10a235c | checkpoint | 1.1 Check for correct documentation
79616545-8ffc-5328-be2d-4f056b74d4b0 | note | FREQUENCY: Prior to commencing any activity
a09d41c9-cdbe-5620-9d1e-004951adcafd | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
5aaafb90-a1e0-5112-ae36-00f5d95d3d52 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9249ecda-3961-5dee-ac74-b3f9b39d301d | note | INSPECTION/TEST METHOD: Visual inspection
aaa5aedb-d336-5b35-8cb0-cba3c70723ea | note | RECORD OF CONFORMITY: This ITP signed off
5d0b426b-a13e-5944-a2d3-312cea378b7e | note | HP*
cf0d38c8-ce92-5baa-8b92-8f5aa6d974cc | note | RESPONSIBILITY: Fulton Hogan Engineer
1e1d64c3-48aa-55cd-84bf-fb48fe64a6d8 | textbox | Date Completed:
6f396ce4-c0dc-4baf-a205-64c985ea1dc7 | checkpoint | 1.2 Implementation of all measures and controls
04dd4f5b-33d8-54f0-8c2b-5db6ee81cd32 | note | FREQUENCY: Prior to commencing any activity
f2fa6ef5-4ae2-50ec-a130-73fe99fea7e2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
e55e79db-e0cf-59b1-adf4-6098db234507 | note | ○ Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit
1f68f630-b1ef-5b71-9593-431bc071e5a6 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
34c0b804-f0c8-5062-8765-9d4b809d70be | note | INSPECTION/TEST METHOD: Visual Inspection
7603c5f3-9f92-5290-b6bf-c964311bd971 | note | RECORD OF CONFORMITY: This ITP signed off
a3b3926f-16ab-51ce-a203-7a83ce01292f | note | IP
03d5dcfd-26c9-57dc-bd71-6fe0fdc9f54d | note | RESPONSIBILITY: Fulton Hogan Engineer
8236a108-93ea-511f-a732-46edc1935b6f | textbox | Date Completed:
47a8bf6f-b8cb-4900-8706-566168ef0129 | checkpoint | 1.5 Materials Check
bc44a1bc-12c2-53b5-adde-eb73e9e3fb9e | note | FREQUENCY: Prior to commencing any activity
3eddd8d3-e6c2-578e-96f1-78be6f79d32b | note | ACCEPTANCE CRITERIA: Ensure the materials and equipment gathered are for the correct type of connection being made. Inspect the mould ID tag to ensure that it corresponds to the application, indicated by the following parameters:
41dc1807-91c8-58e5-9c20-13c7f2e15778 | note | 1. Mould part number:
6f9d301b-cb48-5980-82ce-e93c4fcf2d1b | note | 2. Conductor size:
d7922b79-cdf1-5e86-bf7f-b69f58c3c738 | note | 3. Welding material required
a5ace0dd-f1f8-5896-b343-a043f4cd56cc | note | – Check to ensure the graphite mould is not worn or broken, which could cause leakage of molten weld metal during the reaction.
37b873c4-ec7a-5151-bc87-07d007ca6fb2 | note | – Ensure a working fire extinguisher is available within 10 metres of the working area.
70e706f8-0b31-59ce-9b8d-88c3571ef168 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
9052eae7-fde5-59d6-a173-3c674902b917 | note | INSPECTION/TEST METHOD: Visual inspection
c675b60b-251c-579e-ba32-ecf87053f936 | note | RECORD OF CONFORMITY: This ITP signed off
1742eb26-7a4f-582a-93fe-3240f8a4e8ca | note | HP*
00ae5fbe-27b2-5ee4-8afd-56018de05abb | note | RESPONSIBILITY: Fulton Hogan Engineer
7ab67f01-ccb6-5b6f-8139-90b338fd90a3 | textbox | Date Completed:
a3adc1a4-2624-428a-ba36-c93511480337 | section | Construction Works
a0d1d214-047f-47e9-9862-55c9ef5e6137 | checkpoint | 2.1 Preparation
2c68d2ca-a2bb-56e7-9ba0-b92dd2b57b4c | note | FREQUENCY: Each Weld
18f397d8-1bad-5ca6-b052-126d8e01ac99 | note | ACCEPTANCE CRITERIA: Ensure the position of the conductors being welded is correct.
d7939d66-0256-5ba9-9b2a-bb09185ef116 | note | ○ Heat mould to ensure it is dry.
75a67312-ece0-5a1c-b2cd-49723b30939f | note | ○ Strip & clean conductors, ensure they are dry & clean.
961fc8d3-11a5-58c4-9b91-4bfc314f0490 | note | REFERENCE DOCUMENTS: Design Drawings and Register
3568a93b-687b-51cb-b976-d2a5e8bbb3da | note | INSPECTION/TEST METHOD: Visual inspection
632cec11-e3ea-510e-9c62-940f23caab35 | note | RECORD OF CONFORMITY: This ITP signed off
a40c6616-7eaf-5947-9cc4-cb18dc483245 | note | IP
79dd0a80-012a-5fec-b4dd-58e4bf833847 | note | RESPONSIBILITY: Fulton Hogan Engineer
e1e65c2c-0bff-52cb-878c-a1c3125a5b06 | textbox | Date Completed:
604a2d25-7ca4-4a29-b071-be0e4eea0565 | checkpoint | 2.2 Welding
3b1c9788-a4f4-5cdc-9589-6e570e9a6f20 | note | FREQUENCY: Each Weld
28591011-bba3-5321-8fff-29638ed6029b | note | ACCEPTANCE CRITERIA: Ensure conductors are correctly positioned in the mould, allowing the mould to close tightly.
674b9f93-1758-53bf-91d7-fbf255e2f244 | note | ○ Ensure welding material has been insected and is intact.
034fe26e-c549-5266-b772-913ea4bd2090 | note | ○ Ensure reaction is completed and molten material has solidified (allow 30 seconds post ignition)
bed5434a-f024-56f3-bb01-8dcd7a78bcf6 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
877a59fc-de5c-554b-80e1-753686003b84 | note | INSPECTION/TEST METHOD: Verify
62316f8c-9797-5cc0-9700-a3a0f226358e | note | RECORD OF CONFORMITY: This ITP signed off
ceb563f2-9343-5250-8196-95567d994fff | note | IP
b28bb5ae-e102-59da-b4a2-ba44de1ef122 | note | RESPONSIBILITY: Fulton Hogan Engineer
29c93b53-376f-5480-8747-d4fc16a8cf68 | textbox | Date Completed:
1714641d-0b68-4641-81cd-b5252a222669 | section | Testing
81262f44-d1df-45fa-9813-0cd9b71b4c31 | checkpoint | 3.1 Weld Review
cbdca046-8e4b-5b57-93d4-1fa965b44338 | note | FREQUENCY: Each lot
053dcee0-99e1-5299-b077-c2fd6f206909 | note | ACCEPTANCE CRITERIA: Ensure weld is inspected and that a quality connection has been made.All welds shall be inspected a Fulton Hogan engineer.
89ca3225-47ea-5f03-87fb-6c841c183ae6 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
2f09d397-718b-5a93-8577-4d28b938297f | note | INSPECTION/TEST METHOD: Verify
6ecfede9-3258-511a-a771-49d44dfe9268 | note | RECORD OF CONFORMITY: This ITP signed off
07ecd349-956f-54de-968b-e9d122da5da1 | note | TP
6b8ed74b-1f9f-5506-abc9-d339b0f60a64 | note | RESPONSIBILITY: Fulton Hogan Engineer
9e0dcb7d-a32c-54d4-8bd9-fad20f5da3b5 | textbox | Date Completed:
640aad48-829d-48e7-930b-27072ed5cb29 | checkpoint | Final Inspection
511fe209-a73e-52dc-819a-414917689bd0 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
6a8a232b-39c2-522d-9dcb-5bc11d645a5d | textbox | Print Name:
c7c5702c-8280-5ae1-8002-a49b0127c0a3 | textbox | Position:
ace221ea-6a57-588a-bbc1-a229a0bf162c | textbox | Date:
f43fdfea-04b8-4b89-8035-bdf26d044168 | checklist | ITP-021 - Line Marking | itp | ITP-021 - Line Marking
473e5f2a-ebd5-4ac6-80d0-f4a8a0fe8ab6 | section | Preliminary Works
795f11a1-36c0-4aae-88ba-734add4d92d9 | checkpoint | 1.1 Check for correct documentation
b49f90e3-30e5-5733-8f96-45a5964925e8 | note | FREQUENCY: Prior to commencing any activity
0656df70-1ac3-5366-bf7d-34d3eca50a9f | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
28a9e4fa-e9e4-5332-8bf6-6fc060d7ea3a | note | – using the correct and complete set of drawings
7fb40d62-0a58-5351-a8e8-e03bc5104746 | note | – all drawings are the latest revision
a4ead065-5ade-55a1-8858-1fe71aee4c24 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
e0bf0d44-cfdf-5345-87c0-b0279613a82c | note | INSPECTION/TEST METHOD: Visual inspection
dea0e375-23ba-5371-ab28-623f50cab8cd | note | RECORD OF CONFORMITY: This ITP signed off
628924d8-3aa5-5604-a21b-b6d8dd92547e | note | WP
5f208d40-de0a-5b97-a902-497c73b96749 | note | RESPONSIBILITY: Fulton Hogan Engineer
e237f412-97e8-5bc6-8f5b-ffd4b34fa90d | textbox | Date Completed:
c9075c96-1b60-4671-b518-11620ae998b4 | checkpoint | 1.2 Implementation of all measures and controls
733ec517-8b9a-5db8-b8c2-9865e117da7f | note | FREQUENCY: Prior to commencing any activity
efc691b3-72f6-56c5-bc41-8ca3b1bd6fa9 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
2e157766-c640-5684-bd30-d44ae5388766 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
d697f537-b42e-5928-98c0-8da09a8d6e7f | note | INSPECTION/TEST METHOD: Visual Inspection
b1e5fbd6-399a-5903-8650-0f22d7305ab7 | note | RECORD OF CONFORMITY: This ITP signed off
1ffbb8d4-d0d6-541e-8719-0bc03195e07a | note | WP
c4e6c291-3d68-569e-b797-924ee5a2827b | note | RESPONSIBILITY: Fulton Hogan Engineer
ca53b0e6-dbaa-539e-b39d-499ba12401d5 | textbox | Date Completed:
5daf1580-d9ab-4342-a4eb-9e37e86cc9d5 | section | Construction Works
4595da6d-38fc-4fe3-831d-6f6167db5f6c | checkpoint | 2.1 Setting Out
e075b5e8-f840-5bc1-a7ad-5b0c2630c09e | note | FREQUENCY: Prior to start
732a08e8-9b29-57ee-bae9-bcd67376c73d | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
326d23b6-dc96-54f2-8124-4718b6276c77 | note | REFERENCE DOCUMENTS: IFC Drawings
99d53f5c-4809-541f-b830-e21b65516953 | note | INSPECTION/TEST METHOD: Visual Inspection
90679868-06bc-55e8-8039-18fdfc1d0600 | note | RECORD OF CONFORMITY: This ITP signed off
a0748bf1-b22b-5594-866e-e38468cb20b8 | note | IP
6779ec62-406a-5171-91e3-0dc63262056c | note | RESPONSIBILITY: Fulton Hogan Engineer
a170e1bc-e688-58ab-b344-326ca419eb25 | textbox | Date Completed:
aa417dec-a181-4032-bb75-e2966cb8a94b | checkpoint | 2.2 Position of Markings
9e05bedb-27d8-5f91-bb20-36e50c6c57f8 | note | FREQUENCY: Prior to application
703c1acf-f00d-59a4-aa0e-e05c182ba85c | note | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
74130170-9b27-50c9-b151-dc446da65c44 | note | ○ Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2.
a7a746e9-2899-5c66-9d1b-4889d383f460 | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010,
997eb18c-2d41-5af7-855c-23a3c0cc4f41 | note | INSPECTION/TEST METHOD: Visual inspection
f2e4889c-db6b-5725-9c6f-06385d5caf4b | note | RECORD OF CONFORMITY: This ITP signed off
205b9ba8-a0df-5a2f-89a9-f8a671b014a4 | note | HP
1c5e2ddf-2384-5b21-afdf-9da46b73ec87 | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
a55f91ee-053f-50a7-ab11-d00c702b5dbd | textbox | Date Completed:
2d1ca791-d53b-4938-99b4-2d5f3675e374 | signoff | AUTHORITY HOLDPOINT
40af6f02-6547-4c88-b110-8751bd09ce69 | checkpoint | 2.3 Tolerance of Pavement Markings
99a9d321-c652-575c-9a44-06f96f9da27e | note | FREQUENCY: Each lot
025db27f-3caf-598c-ab64-9b4d3d11ec97 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings. The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
a77f8e42-3b91-52d9-92ec-42ff56cb09b9 | note | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
a8b081b6-d8fe-5350-96de-51f3af7d98b1 | note | INSPECTION/TEST METHOD: Visual inspection
81bf0ef2-d93d-5fc4-83db-d7a4a475fefb | note | RECORD OF CONFORMITY: This ITP signed off
c5d25214-78d9-5140-8ebc-c1a493aa1e74 | note | IP
1dc213b4-e68f-5c8c-aba2-009c0d9fd579 | note | RESPONSIBILITY: Fulton Hogan Engineer
5ad4c554-b1cc-5e05-b5f4-d3b2e235d053 | textbox | Date Completed:
1c74e1b7-2eff-43ce-ad5c-baab5dfd0b77 | checkpoint | 2.4 Raised Pavement Markings
4f25df54-7531-5561-af9c-c14599665ff6 | note | FREQUENCY: Each lot
2cbed821-12f1-5c69-89f0-77abb5fba4b6 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
f63cfe12-b1ec-5b45-8a11-afde4d2e1517 | note | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
bbd526e6-3c68-5782-88b5-7a7648f14acf | note | INSPECTION/TEST METHOD: Visual inspection
3b34541d-2ad8-50d5-a347-336e0e0b16c1 | note | RECORD OF CONFORMITY: This ITP signed off
1264c159-14dd-537a-a521-8c59e6b4eee3 | note | IP
999a7552-eed8-5d40-af79-52b29ddc398c | note | RESPONSIBILITY: Fulton Hogan Engineer
190af744-bfad-503a-b214-34c232032894 | textbox | Date Completed:
a018e0f8-67c0-4d85-b63a-8673ecb482f3 | checkpoint | Final Inspection
56656a31-38de-5def-baf4-300bdd90d969 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
308cbdaf-cbd6-5b42-aef5-9947b708a91e | textbox | Print Name:
5e840561-8055-580f-b2e1-74019cb5fc64 | textbox | Position:
dfd47237-b621-5e31-b2b5-70e837755086 | textbox | Date:
ec055aaf-7590-4a37-9188-c957897344bb | checklist | ITP-024 - Overhead Pole Installation | itp | ITP-024 - Overhead Pole Installation
0f785ef8-ea47-4a4f-90f8-cf1691181463 | section | Preliminary Works
08749afa-b96f-4dfa-b90d-bbba5c2cb8c9 | checkpoint | 1.1 Approval of OHP Layout and Rake
410b36d4-4467-57d4-b441-7b27fd8babbc | note | FREQUENCY: Prior to commencing any activity
f11ce9ee-c941-54cd-8b28-ff9bfe729b1c | note | ACCEPTANCE CRITERIA: Check that layout designs satisfy the requirements of the Principal, and drawings are approved for construction.
ede81b0a-72a6-5dca-abfc-e1ae0aa4728c | note | ○ Confirm pole rake bearing and grade.
70df509b-de04-51c0-95e3-1f9a5f8d30fb | note | REFERENCE DOCUMENTS: Plan Approved for Construction
6757f467-e33a-576a-81a9-32cf08e404de | note | INSPECTION/TEST METHOD: Verify
9d3426bf-50db-5c8d-8c7f-197fd3ba203c | note | RECORD OF CONFORMITY: This ITP signed off
04bc758f-f8a7-58eb-a31b-ccb709b13168 | note | IP
7e200cc8-5053-5aa5-989b-2d33d2fa8159 | note | RESPONSIBILITY: Fulton Hogan Engineer / Yarra Trams
41871503-c5f0-5a93-9c30-b6f746b0e9ac | textbox | Date Completed:
9de5c433-144c-428f-aa01-99a19ae178a8 | checkpoint | 1.2 Check for correct documentation
c7001286-1def-52db-a13a-23ae29ffa7dd | note | FREQUENCY: Prior to commencing any activity
8084267f-2bf1-5a15-bcae-3c8f4a628474 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a3d147bd-2849-5ace-9d4b-c6b2127039aa | note | – using the correct and complete set of drawings
9a22b1e8-5ff0-5b72-a7b9-16f3c991ad4e | note | – all drawings are the latest revision
cbac2db6-3758-5bf1-9886-218d90a7858c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
98f58336-778a-5349-b94c-4016f4bb61b3 | note | INSPECTION/TEST METHOD: Verify
9c74cbd4-da19-5257-9878-7082afe83460 | note | RECORD OF CONFORMITY: This ITP signed off
b74b90a7-b149-5ec7-af63-d810dddf8a9d | note | HP*
18b11e98-5a28-5f13-9539-fb28dd749c7c | note | RESPONSIBILITY: Fulton Hogan Engineer
946de13a-0dd2-59c0-b2c5-14018ea38b71 | textbox | Date Completed:
f8fa6892-192c-4bf6-82ac-bb5dd3cba299 | checkpoint | 1.3 Ensure Safety and Environmental Measures
cb49a272-6cf6-50bc-86a1-93bc9f3a33c3 | note | FREQUENCY: Prior to commencing any activity
a72e1847-63b9-5e9f-9b2c-98f2f9b6c50e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP.
3934c6bc-8634-5a7d-8bd4-96a507129def | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
6b3d3c2c-db69-5619-8d36-a33ea238b91e | note | INSPECTION/TEST METHOD: Verify
c17ec4eb-8b5b-58ff-b199-5434d6a5b8d3 | note | RECORD OF CONFORMITY: This ITP signed off
d72733f9-ee41-5752-a18b-21c1d923ca01 | note | HP*
e5a344ce-ae3c-5075-8fd9-2d6f6cc85e13 | note | RESPONSIBILITY: Fulton Hogan Engineer
4e4a6722-38b0-5cce-83e7-887b522e2068 | textbox | Date Completed:
5a90ff0f-b9a7-47aa-838e-b55f350923b9 | checkpoint | 1.4 Services
1f33b700-39a1-57fa-8056-f17cf8d6219a | note | FREQUENCY: Prior to commencing any activity
07f5fc7d-034e-5b5c-ba83-9958cce0a0e6 | note | ACCEPTANCE CRITERIA: Check DBYD records for any known existing services in the area.
14b61958-b315-538d-ba11-65f4cd1bc2d7 | note | ○ Service proving is required to ensure all service locations are known.
1bdfe0ff-dafe-5949-9a31-e29a0dd52874 | note | REFERENCE DOCUMENTS: DBYD Records and Inspection
356eb0b7-91cb-5be4-ac4a-c9db58b56625 | note | INSPECTION/TEST METHOD: Visual Inspection
18d44c71-349e-59a6-88d3-31e6a429d352 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
3596dcd3-b9e1-5706-afec-5ae12769de4e | note | WP
85e5402a-f4cd-5ed9-a29d-6c9697543fa7 | note | RESPONSIBILITY: Fulton Hogan Engineer
cee1d74c-b56e-5a8d-a42e-d8438886b2cb | textbox | Date Completed:
a6dc5a11-4c2d-452e-bfc6-fd1a68186294 | checkpoint | 1.5 Lift Plan
40111fe9-665b-55f8-a885-a88ed56da398 | note | FREQUENCY: Prior to pole erection
ff417a24-349b-520d-9554-5b121a97cbe8 | note | ACCEPTANCE CRITERIA: Ensure a lift plan has been prepared for the lift to mitigate against the risk of lifting the overhead poles near a live overhead power line.
54636a57-564c-50ef-9ab7-bf96a6b3628e | note | REFERENCE DOCUMENTS: WP 02 Cl 3.7
20102b68-ffb9-59a7-8a08-49ea7215c94f | note | INSPECTION/TEST METHOD: Veify
7ac1ecfa-4776-5bda-a124-003bab3a70ec | note | RECORD OF CONFORMITY: This ITP signed off
4cd48d71-8907-5711-940a-051429fc3143 | note | IP
d9e69135-38ec-5716-ae33-8f42f4560519 | note | RESPONSIBILITY: Fulton Hogan Engineer
76c6bf6d-2831-5835-9ce0-cabe217d5df9 | textbox | Date Completed:
26d07962-9011-42bf-b0ee-dca423adae1f | checkpoint | 1.6 Pole Type and Quality Conformance
4751db7c-ebbd-5ff8-94c7-dd48ed3e634f | note | FREQUENCY: Each Pole
3fd99943-63eb-5fac-85c2-a2d8f146e017 | note | ACCEPTANCE CRITERIA: Principal Supplied Poles and Rag Bolts shall be examined for any damage, corrosion and rust. The materials shall be check for conformance to requirements.
1d7be7e8-cc8e-5c87-b7f1-7da696636ff7 | note | ○ Ensure that draw rope is installed prior to pole erection if required and galvanising tags are removed.
6ae18b45-fae9-57e5-88c1-da4fb65bf223 | note | REFERENCE DOCUMENTS: Contract Drawings, YT Tram Overhead Construction Specification 2013
756ba865-e396-57e5-904c-21839c46552b | note | INSPECTION/TEST METHOD: Verify
454d8cf5-97c2-5678-99e0-cc2108ce5cc8 | note | RECORD OF CONFORMITY: This ITP signed off, Recivable Inspection Checklist
194047b6-f843-5a3e-b799-20545ed11fb6 | note | IP
9fe13b92-2571-59ae-bccb-f909b79675e4 | note | RESPONSIBILITY: Fulton Hogan Engineer
385d3c52-cefa-554c-90e9-4043c33e9393 | textbox | Date Completed:
15bd7d75-545b-48a0-bee7-2e6c2d9a457c | section | Construction Works
ac616105-41b8-423c-b495-f565d105a229 | checkpoint | 2.1 Hole Excavation
ff69a20e-3b70-52c4-9923-a335312bd12d | note | FREQUENCY: Each Pole
5dbb3a38-dab6-52f5-bb89-832e4b02b6ca | note | ACCEPTANCE CRITERIA: Each hole shall first include a bored hole of uniform diameter throughout the entire depth, 200mm lower than the embedment depth specified on contract drawing.
da5b90d8-c6ce-5f18-b56a-296b8fe0686f | note | ○ Boring direction shall be in line with specified new pole rake
d8e00fd0-1e47-5b7c-acdb-7ad823e11088 | note | ○ Diameter of the hole shall always be at minimum 100mm greater than the diameter of the pole.
4b990831-3ba3-58ff-9aa3-8e62454801a2 | note | REFERENCE DOCUMENTS: Contract Drawings, YT Tram Overhead Construction Specification 2013
7b59bc83-b383-5684-9017-49aedd44edb3 | note | INSPECTION/TEST METHOD: Inspection/Verify
04ccda50-8bdd-580f-9b96-80d04e474547 | note | RECORD OF CONFORMITY: This ITP signed off
28ef0e62-53e9-5160-85a8-2119804f4792 | note | WP*
720036a6-18f9-5773-ab09-28a80f193b46 | note | RESPONSIBILITY: Fulton Hogan Engineer
f2c1d19e-ddca-54f8-a086-5926e0b19b9d | textbox | Date Completed:
2290c926-710b-4e44-93fd-34897f78e2d0 | checkpoint | 2.2 Pole Setting
bb0ee49f-bddd-5e48-a099-1c8c950e898d | note | FREQUENCY: Each Pole
0c873943-6400-5a12-93fe-5d640c60fae4 | note | ACCEPTANCE CRITERIA: Ensure that poles are set as per IFC drawings.
460be313-2e5e-52c2-a759-7a09a11adbb6 | note | REFERENCE DOCUMENTS: Contract Drawings, YT Tram Overhead Construction Specification 2013
2b327647-a87a-5c03-a4de-284a85cf1ca8 | note | INSPECTION/TEST METHOD: Visual Inspection
1c90f9f7-4846-575f-a2af-f08e322d33ee | note | RECORD OF CONFORMITY: This ITP signed off
112bf116-95a5-5f3b-a039-5ef092692769 | note | WP
ef4f5423-aa39-5162-8c3f-5668dbc7698f | note | RESPONSIBILITY: Fulton Hogan Foreman
3fb0b233-0325-57ab-b9f5-432104855235 | textbox | Date Completed:
4efe60be-762e-4d84-b4c0-b1a9c7e26b90 | checkpoint | 2.3 Pole Rake
743cf538-578b-5d79-beba-7a12098502af | note | FREQUENCY: Each Pole
798f2b99-b56b-5c30-9637-6a9df5759baf | note | ACCEPTANCE CRITERIA: Ensure that poles are set to rake as per IFC drawings.
5712a5df-6460-5ecc-940a-e6eee487c093 | note | REFERENCE DOCUMENTS: Contract Drawings, YT Tram Overhead Construction Specification 2013
b36f80c8-cce9-5888-8864-8c73d72c0d66 | note | INSPECTION/TEST METHOD: Visual Inspection
4605b314-25bd-53dc-b89b-f625a34cab46 | note | RECORD OF CONFORMITY: This ITP signed off
c4838845-0066-5f66-9fb3-d4c7571937e0 | note | IP
d3168f47-c0c3-5453-b826-593f9cd587d1 | note | RESPONSIBILITY: Fulton Hogan Foreman
4d54f7f4-7d48-5383-b288-2fe98ecac64d | textbox | Date Completed:
7970ad5f-999e-44c9-9559-f2586dc52031 | section | Testing
a1515384-4454-4f5e-91d5-8d95293813d2 | checkpoint | 3.1 Visual Inspection
f34ed5a0-4262-56db-9dfc-cd76f2064cc7 | note | FREQUENCY: Each pole
d84f7301-dd4e-59ef-9c6d-94cbacba721a | note | ACCEPTANCE CRITERIA: Surface of each pole shall be visually inspected for any damage, corrosion or rust before and after erection
06c4e030-86e9-5dd6-a1c2-b1dc742b3115 | note | REFERENCE DOCUMENTS: Contract Drawings, YT Tram Overhead Construction Specification 2013
0b2059b2-eaba-5816-8c11-a3015cc5395c | note | INSPECTION/TEST METHOD: verify
9f765a6d-41f2-5a83-a18e-9dbe0a0b7599 | note | RECORD OF CONFORMITY: Visual inspection
9c967cfc-508c-50e0-bef2-b7b424c1bad1 | note | IP
576f5b88-892f-53ef-aadb-198cb5f86a8c | note | RESPONSIBILITY: Fulton Hogan Engineer
9317f414-c64d-560e-9061-980a9299df57 | textbox | Date Completed:
e0559918-8f17-4b4b-8489-01276a7816c6 | checkpoint | Final Inspection
be01b15e-0b76-5b2e-823b-e3f0f6bd564e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
2d68c53e-07a8-53ef-af14-91bf3e1ec83e | textbox | Print Name:
d2bbc9f6-dd69-5489-8b9d-534f51fc26fb | textbox | Position:
9192cef1-3a0d-5b49-883e-8a20a10dcf35 | textbox | Date:
c1f958c6-77ea-4748-9b83-c1125c65bb2b | checklist | ITP-025 - Structural Concrete Construction | itp | ITP-025 - Structural Concrete Construction
37ca8ee6-d0eb-4dd1-97ee-353428f8b710 | section | Design and Submissions
26c5b6e0-7256-4118-a0b5-80320c13764b | checkpoint | 1.1 Check for correct documentation
017c8cee-2074-5aa6-bde0-9584740e5824 | note | FREQUENCY: Prior to commencing any activity
4df1a024-0a2f-569f-8e11-e05669d94317 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
f10f29cb-be15-507b-b021-8aca7c56d229 | note | – using the correct and complete set of drawings
3bad38a0-9aea-58a7-95b5-70a7dca72a0e | note | – all drawings are the latest revision
b7997cbf-946a-5f59-85b2-acf9fd23d547 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
3ff6bf0a-2f95-5318-969c-42e3bec7a2ab | note | INSPECTION/TEST METHOD: Visual inspection
8ddd574b-135c-504f-a0ce-68b45305e0ae | note | RECORD OF CONFORMITY: This ITP signed
3c773280-359c-564f-9e6d-9c89842f9632 | note | HP*
db6de107-f036-55c6-bbec-0d68153f0a2b | note | RESPONSIBILITY: Fulton Hogan Engineer
0b8fec98-2bed-553d-849b-072f3eabb9fb | textbox | Date Completed:
24971b14-5082-49ac-8bab-5b9e9ec20c39 | checkpoint | 1.2 Implementation of all measures and controls
364c0521-4de1-59bd-aa3a-f1cf1a29be9b | note | FREQUENCY: Prior to commencing any activity
b2a3019b-55d7-5592-af01-fbc724baa08c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
64eb9eeb-16d7-5913-bcf1-d58383aaf76d | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
a6a32548-2718-505a-8f4d-cb0ba6ae918f | note | INSPECTION/TEST METHOD: Visual Inspection
e7850d8d-afa0-53ca-93b5-eeb318e6398b | note | RECORD OF CONFORMITY: This ITP signed
662201da-0b83-58e2-a4f9-05f4d1d6ee10 | note | HP*
1f8756e0-9dbc-5ef0-9cec-1a698cf04cb0 | note | RESPONSIBILITY: Fulton Hogan Engineer
1a01f6d7-3fe9-5f5f-9ec8-3acc92525d65 | textbox | Date Completed:
deb6d1bd-4c10-4afc-b8d1-04f3dba5eecb | checkpoint | 1.3 Approval of mix design
bfe6864b-1e37-5f82-acbd-b7b5f4f6ec4c | note | FREQUENCY: Prior to the first concrete pour
00d99f71-8e48-5bf5-80c0-b520b96c4637 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
795b6837-19a1-5fd4-85e3-9aae1e5ceb68 | note | REFERENCE DOCUMENTS: 610.07
7a651822-cf05-59a7-9d30-360ac780bc6e | note | INSPECTION/TEST METHOD: Verify
dc9f9455-22e3-5cb3-9151-673ad3912052 | note | RECORD OF CONFORMITY: This ITP signed
e4d1a461-154e-5979-a14a-1dcf7d297964 | note | IP
3f2efa2d-b797-50e5-82bd-52d0f2b957bb | note | RESPONSIBILITY: Fulton Hogan Engineer
ec394cb9-581f-5de9-9b80-16460876b270 | textbox | Date Completed:
4cf5bda1-42ee-461e-950b-e623d1bfcbcd | checkpoint | 1.4 Reinforcement schedule
8e9aadfe-0dd1-5e97-82b3-828742f73054 | note | FREQUENCY: Prior to concrete pour
8347229e-4d60-58f7-ad9e-9bcc00119861 | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
950d5ee3-da51-56ac-9d44-aadddb53001f | note | REFERENCE DOCUMENTS: 611.04
4be356ae-cf85-5e34-b479-182c3d237cb0 | note | INSPECTION/TEST METHOD: Verify
abf760e5-1f0a-5dbe-875f-47bcca16efc0 | note | RECORD OF CONFORMITY: This ITP signed
20a8cf18-2d90-553c-82c4-28cab99e5e87 | note | IP
01f1a7cc-fbc2-53cf-bd3e-abef03df7960 | note | RESPONSIBILITY: Fulton Hogan Engineer
34d723ee-e8c7-544a-aac6-ae7243cfedd8 | textbox | Date Completed:
dcc9909e-5025-46b1-93ad-f6b36b555f59 | section | Construction/Erection of Formwork
3a6fdd5a-1250-46e0-8982-7c63dc564559 | checkpoint | 2.1 Excavation
e30d9af6-9c16-5bf1-bd7c-8d2db95beac9 | note | FREQUENCY: Prior to concrete pour
49728c8d-89d5-5d5c-a30f-98e0cad9b4d4 | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
4d96e897-8216-5774-9c24-227a0fcacf3d | note | REFERENCE DOCUMENTS: Contract Drawings
f13e2bd2-01b7-51fb-bd43-23c2c4eca6f4 | note | INSPECTION/TEST METHOD: Inspect
0f65ad57-d85d-5487-a5c4-9a709168349e | note | RECORD OF CONFORMITY: This ITP signed
2d830267-cf83-54c6-8961-f2473c5567cd | note | IP
1f2b1597-1996-5aed-bc23-ec8aaa41ce0e | note | RESPONSIBILITY: Fulton Hogan Engineer
c1d2c076-14dc-57d1-bcf7-78a8d0a960d9 | textbox | Date Completed:
a382adff-5e1d-4d81-ba72-696037017594 | checkpoint | 2.2 Construction Methodology
6c77eb7f-9421-5acd-b6a1-61253ca18f17 | note | FREQUENCY: Prior to erection
d7c34a4d-f653-52bf-a503-5bc62ac71356 | note | ACCEPTANCE CRITERIA: Constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
15d7230e-897b-5cf3-a5e5-7b79844c2261 | note | REFERENCE DOCUMENTS: 614.04, 614.06
783798dd-d860-52b0-bfb3-1a4d64887697 | note | INSPECTION/TEST METHOD: Verify
53042e3c-3467-58a6-bb4e-b88390a56682 | note | RECORD OF CONFORMITY: This ITP signed
1106820d-ec9a-52af-a3e4-b77844f0b3d4 | note | IP
4aaba8ad-9b66-57a1-9b6c-5867e28de1c7 | note | RESPONSIBILITY: Fulton Hogan Engineer
23af2cf7-2337-50b9-b914-eb1151867df5 | textbox | Date Completed:
745d1d39-eaa7-42ad-87a2-b818f85d7939 | section | Pre-Pour Planning and Inspection
a9b8e872-6116-47a7-83d6-b7316c13b075 | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
eb55c487-72c9-5542-ab1a-152da5c706f9 | note | FREQUENCY: Prior to concrete pour
09ab3d89-3b7a-53db-ac76-fe4645d94ebf | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent.
6042af7f-b104-5331-bf9e-65d20fd0d5a1 | note | ○ Hold Point released by the Superintendent.
668b6e58-8b71-5a1a-bdab-0e8b50bfc4f3 | note | REFERENCE DOCUMENTS: 602.03
3a693686-2af8-5518-b1b9-bfa2453a837d | note | INSPECTION/TEST METHOD: Verify
64c9e20f-71f7-50aa-b6a3-0f55b6677d38 | note | RECORD OF CONFORMITY: This ITP signed
9d0d8eb8-ad09-58ca-8ae8-24b58bbefa14 | note | HP
d0167a7e-a01a-5933-9450-ba53fae67cd1 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
4be75047-2cf6-5725-b59f-090d2f07ea01 | textbox | Date Completed:
8220287e-710a-4208-80df-01efc431267d | signoff | AUTHORITY HOLDPOINT
756d0a7b-005e-426c-bfbc-e742eeb1854b | checkpoint | 3.2 Formwork levels and position
b9cf6928-ed4d-572f-a52b-fe963d111784 | note | FREQUENCY: Prior to concrete pour
5b7eab89-66e0-5867-9b3d-a39b60aa5597 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
2cfa3788-1e36-5566-8627-d25bd598c635 | note | REFERENCE DOCUMENTS: 614.06
2e7894f9-de7d-5c53-8aef-04b3cf91450e | note | INSPECTION/TEST METHOD: Verify
e58aa771-574e-5d03-8ff8-002d435263c6 | note | RECORD OF CONFORMITY: This ITP signed
c1734875-3eda-547f-8a9e-63360624ce7c | note | SCP, HP*
9d751c88-9be0-5875-905a-0394757582f6 | note | RESPONSIBILITY: Fulton Hogan Engineer
83f875d1-316f-5d04-bf7e-753fcbd8ee50 | textbox | Date Completed:
81f915ce-bba2-4dc4-91de-b6dad7478a72 | checkpoint | 3.3 Location of splices
986a7e65-90bb-59e0-819a-89dfad4bbdde | note | FREQUENCY: Schedule Review
084abf75-2453-5272-ac80-20f5a9a8eed4 | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
1f609427-cbe2-5eec-a947-fb27b057af09 | note | REFERENCE DOCUMENTS: 611.11
0c39e5c2-bf6e-50bb-a21d-b52c232321b9 | note | INSPECTION/TEST METHOD: Inspect
80a893e0-d01b-5b86-a4a2-512dfcb1da80 | note | RECORD OF CONFORMITY: This ITP signed
00f5d571-2146-537f-a995-c8b713314d36 | note | IP
9220c506-6ebb-5782-8329-353ecd518a0d | note | RESPONSIBILITY: Fulton Hogan
b4f10879-ee4b-5643-93cf-e538729caa40 | textbox | Date Completed:
58207249-6cc9-4dd8-9253-534b0e7e1236 | checkpoint | 3.4 Cleaning formwork
9dba84fd-6297-5bf0-9bee-64ba19422d3b | note | FREQUENCY: Each concrete pour
be16a0fe-f568-5c45-b550-5de403f70b6f | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
22a8a424-26f9-58c0-aeac-e2f27be6933a | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
5c76c52e-4d10-5267-964c-528eed486ad0 | note | INSPECTION/TEST METHOD: Verify
ed26229d-5e71-51b1-9b53-b5a87aacb64d | note | RECORD OF CONFORMITY: This ITP signed
7833c1eb-de07-5410-b13b-fe89db4c986a | note | IP
e92364f9-1854-5345-8ad6-14ce2b15b983 | note | RESPONSIBILITY: Fulton Hogan
e34a8b05-86e2-58d0-9bd1-407a97281152 | textbox | Date Completed:
2a292e24-fcdf-483f-b8e9-b1c2a8c5f471 | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
e4c50143-7ebb-5aea-b973-8ad8dc07b5c5 | note | FREQUENCY: Prior to concrete pour
f6b7c702-bf06-555e-9c78-eac4fcb213c5 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
8ecd48de-66a0-5e8e-a579-aa917251a565 | note | ○ Pre-pour checklist completed and signed.
9dbc7f73-e58e-5f64-9d95-de056a9993b0 | note | REFERENCE DOCUMENTS: 610.18 (a)
4a74ec8b-3da7-5635-8ff1-d2b657fcbbe0 | note | INSPECTION/TEST METHOD: Verify
1f9691d5-788a-5c9a-86fd-08d6d1a623f3 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
c24d9951-c495-5ca9-bdda-b2f8fdf06d67 | note | HP
459b8e95-ec18-59bf-8914-56a7c8856dff | note | RESPONSIBILITY: Fulton Hogan / VicRoads
e86a6189-0355-5356-914b-97deb4bf0525 | textbox | Date Completed:
7bcc8eea-90f8-4aae-80d4-97a57de43d61 | signoff | AUTHORITY HOLDPOINT
2c19a71a-5aa4-4d48-9947-49795352ce99 | checkpoint | 3.6 Reinforcement assembly of piles
19202575-4cba-5859-bc5a-0e98fd5ac4b4 | note | FREQUENCY: Prior to concrete pour
28d31ef1-78ff-5a4d-957e-17a9cac97594 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
6faf4659-06b7-58b4-b040-e31c4acd304a | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
f9889ec2-e369-52b6-afb8-d5b334915e72 | note | INSPECTION/TEST METHOD: Verify
c62c8aa4-f2f3-58e4-ac6f-ea49f8267181 | note | RECORD OF CONFORMITY: This ITP signed
e6eb78dc-c882-53ba-b46a-58c265235a88 | note | HP
076b0e42-b20e-52b8-88a2-759f0a309091 | note | RESPONSIBILITY: Fulton Hogan
99759f87-3f7e-5015-b19a-4adff67e657e | textbox | Date Completed:
9fd09c22-66b1-48c0-a0c3-28c35c936e23 | signoff | AUTHORITY HOLDPOINT
5b7e0099-f278-45bc-b820-1532f7fc2927 | checkpoint | 3.7 Monitoring weather
3c14c30a-fbcf-5d30-84c4-ca4672e89faf | note | FREQUENCY: Prior to concrete pour
f9a8c6e6-6627-57b3-9150-224b49cf6715 | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
5a3ce001-ad92-5a97-b893-69b26398ff63 | note | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
1b8333f1-daa5-5633-989c-e59751078b97 | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
b53c03c8-9bc5-52e4-a16c-93ce732b12c6 | note | INSPECTION/TEST METHOD: Verify
32097a83-6732-5fd9-9345-4da6e348df0a | note | RECORD OF CONFORMITY: This ITP signed
2a96edf3-2b67-5c22-8b77-3492b2b31a3b | note | IP
c7e74528-86cd-55e6-b906-0d1437f00096 | note | RESPONSIBILITY: Fulton Hogan
4d00a2f4-c4e8-5d67-a322-8e3156f29490 | textbox | Date Completed:
70bef2f7-5c2d-4991-b876-a2b2ab09fb84 | section | Placing and Finishing Concrete
f2bddc3f-2441-41b9-abdf-aaff9ede6c2d | checkpoint | 4.1 Carry out sampling of concrete
12f94739-c1aa-5078-baf8-c19b1a99e3db | note | FREQUENCY: Each concrete pour
3585149e-b6ff-5675-b3f5-3be307af71c2 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
61a5d191-ae49-599f-b03c-a9830597650a | note | REFERENCE DOCUMENTS: 610.16
256c1b30-95b1-56a4-8968-66123cce4537 | note | INSPECTION/TEST METHOD: Checklist
3dcbda1c-04d0-5ffb-8799-6eabc7ba5702 | note | RECORD OF CONFORMITY: This ITP signed
789ee16b-5c7a-5297-85ad-cd1213680378 | note | IP
99b67fdc-6091-5e21-98ee-d3ea16e327bd | note | RESPONSIBILITY: Fulton Hogan
d4d33f94-d85d-5123-9f4a-981e8c85b6bf | textbox | Date Completed:
ac215c05-8c82-4995-bc03-7fd7572a6210 | checkpoint | 4.2 Discharge time
c6365937-36a7-50fc-90cc-d31f862884a4 | note | FREQUENCY: Each concrete pour
aa056871-d4f6-50b6-9487-2c85cf8218e7 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
f20647b8-0835-52a7-b9d0-5f89c27a012c | note | REFERENCE DOCUMENTS:
bcc5ffd3-9b38-5228-b5a9-45f482c7c17f | note | INSPECTION/TEST METHOD: Verify
01dc5e2e-52a6-5997-836b-0cd916d61722 | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
977b57dd-b999-5406-b208-174367c0a3cd | note | IP
923a51a9-edd8-5f68-9761-51f73fccc352 | note | RESPONSIBILITY: Fulton Hogan
58767ca4-06c3-5781-bfa6-fb0502d4325d | textbox | Date Completed:
b351fdcb-5aaa-4bbe-9f0e-77b88cf9f805 | checkpoint | 4.3 Methodology of placement (structural)
c7c41d05-357d-580f-bdb4-dde83d181729 | note | FREQUENCY: Each concrete pour
d11845a3-6429-5f9c-a7ea-3ee99f23d264 | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
5a68bb7a-73b4-56c6-a132-797051653818 | note | ○ Concrete shall not be moved horizontally by vibrators
812083c8-0559-5dc7-b17f-58acc6a44bf3 | note | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
307a8288-5d6a-595b-a584-f5428b96930c | note | REFERENCE DOCUMENTS: 610.18
68d53419-2ddb-5951-bc92-c367639ebc45 | note | INSPECTION/TEST METHOD: Verify
b6c4439e-498a-519a-b941-b73ad293b20a | note | RECORD OF CONFORMITY: This ITP signed
90e5ae37-9dae-5df1-9400-ff0a7f655aee | note | IP
9a7c854d-8a2d-5981-ba57-988bb87e4db0 | note | RESPONSIBILITY: Fulton Hogan
30e1255c-8604-5db3-bcc0-e841d93ccc64 | textbox | Date Completed:
73b519ae-836f-4564-9937-6cf04e266a64 | section | Post-Pour Details and Inspection
1cb4d158-836a-43a4-a64e-2980e8a654be | checkpoint | 5.1 Curing
a5cec41b-405c-5fcd-97e6-89a1e670cc1a | note | FREQUENCY: Each concrete pour
9cd97d20-2a3d-5816-938e-41631e83c0e5 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
7bfdfe6b-a484-5d42-92af-53a9065df8f6 | note | REFERENCE DOCUMENTS: 610.23
d87244c2-30aa-5b94-86c8-194a8455f31a | note | INSPECTION/TEST METHOD: Verify
2405cefd-539c-5e41-9bba-446192bba514 | note | RECORD OF CONFORMITY: This ITP signed
4dac924b-1984-55a2-ace4-8a080c26ca40 | note | IP
8dcc9912-310b-5d4c-9f2f-50dd89ecbb9a | note | RESPONSIBILITY: Fulton Hogan
2acb1d38-36c3-5aa1-998a-56dddacc45b6 | textbox | Date Completed:
b585e988-40a7-42e2-b611-f35c410eccea | checkpoint | 5.2 Formwork removal
ffe0c6c3-9def-52eb-92ab-822eca7a97b2 | note | FREQUENCY: Each concrete pour
95b49095-484d-5e3f-b49a-b01080031853 | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
e90b6aae-9615-5b3b-8524-4f11739b4d68 | note | REFERENCE DOCUMENTS: 610.25
bb8ea87d-3db4-57c0-8066-248347af2261 | note | INSPECTION/TEST METHOD: Verify
7d267c01-61dc-5b09-841f-a60d9db2f2a9 | note | RECORD OF CONFORMITY: This ITP signed
11f25c83-7d26-5199-bb9b-75fff640d128 | note | IP
45c0b9a1-e43a-597e-a191-cbc81bcec633 | note | RESPONSIBILITY: Fulton Hogan
594cef86-0195-5416-a223-4396621ba32e | textbox | Date Completed:
971ab553-e2b2-429f-9344-3d951a070c79 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
2e14e681-96d4-5424-a276-ac0136a3592d | note | FREQUENCY: Each concrete pour
a7f97676-8ad4-559f-9956-51e58ff47ecd | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
49c663dd-1576-5343-8cfc-367edd84ce3e | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5, 607.06
1a15e64c-2c90-564e-80dd-bf606ab2a972 | note | INSPECTION/TEST METHOD: Verify
29ced344-7992-51d0-8ec8-cf204effe018 | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
238d50b5-aa69-5a52-b029-2bf7c6df69e6 | note | IP
c6c81762-08c2-54bd-8aea-63f6d88f347a | note | RESPONSIBILITY: Fulton Hogan
89b53829-8325-5ca4-96de-c9a03b03c9c5 | textbox | Date Completed:
c3fda81a-ada2-467c-a14c-76d5e74454f8 | checkpoint | 5.4 Concrete Sampling and Testing
b7bd604d-b307-5c3c-8d16-8669c93053c6 | note | FREQUENCY: Prior to lot closure
be456d2a-f9ae-50be-881e-8981d12dff2c | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
f408d5cf-0c18-5d04-8a37-2cabe32b6fa0 | note | REFERENCE DOCUMENTS: 610.16
53ea28bf-9bdb-5a2e-93e8-a57b414b24f1 | note | INSPECTION/TEST METHOD: Verify
e1c6e155-71cc-55f4-947d-0ad7a5a38f33 | note | RECORD OF CONFORMITY: This ITP signed
66a5509a-4203-59cf-bf7f-a63e322b2ed7 | note | TP
6ffe2921-3a0d-5090-adf3-36d66af75193 | note | RESPONSIBILITY: Fulton Hogan
534a1cfc-beb9-582e-9558-f69e3934c0f6 | textbox | Date Completed:
361e9a18-c755-4a70-aa79-affc730a3764 | checkpoint | 5.5 As Built Drawings
69553c7a-6e22-5bd4-ac10-da9278021e34 | note | FREQUENCY: Prior to lot closure
dcf30b90-4de5-5ac9-a44c-48dad22ac332 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
64543abb-796f-544b-a128-af04cc487808 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
64f18bed-41bb-5354-97c7-adcf0fcd1b36 | note | INSPECTION/TEST METHOD: Verify
23657334-3d5b-517d-aeea-deb91628d8d7 | note | RECORD OF CONFORMITY: This ITP signed
f8200f56-cc46-5c99-b15e-e1b63915062b | note | IP
e3214fc0-0eb2-5ce5-8224-b034d80c0b8e | note | RESPONSIBILITY: Fulton Hogan
94f3ccfc-fdc7-5732-948b-0abf78ec12bd | textbox | Date Completed:
c199c657-40fc-4fe6-86ca-d2883679ec01 | checkpoint | Final Inspection
a85450e1-34a5-5106-a113-5a36e3fb43e9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
41bb3bb4-b973-53e3-9bdb-d627efa1079c | textbox | Print Name:
35c3ba7b-cf37-54c3-937d-8e44db848113 | textbox | Position:
f3bb4234-18f2-5c4d-ad0c-96979183c530 | textbox | Date:
ba6a6ba6-b2e9-4c6a-ba75-9b7fa3d22d39 | checklist | ITP-027 - Pile Footing Construction | itp | ITP-027 - Pile Footing Construction
f286c8ee-2987-4fc4-be95-9116e3989d06 | section | Construction Works
b5ddf6ed-4958-49d9-881a-d191bce2b41c | checkpoint | 1.1 Check for correct documentation
547a39c4-22dc-54b7-83a6-40f2f388160b | note | FREQUENCY: Prior to commencing any activity
69cfd722-ae80-541f-900e-f5f2ae48e925 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ba74f05e-24f3-5fef-a74b-f1839bcbb0e6 | note | – using the correct and complete set of drawings
a28ede52-1ee5-576e-ae09-cf1b48ec5add | note | – all drawings are the latest revision
08392535-a83d-5536-a476-a4ba9a8524aa | note | REFERENCE DOCUMENTS: Drawings and drawing registers
e9cb8491-a582-5b92-9fd8-f01ebc20b2c1 | note | INSPECTION/TEST METHOD: Visual inspection
af31b2fe-30c9-5d44-b406-d13810d77e98 | note | RECORD OF CONFORMITY: This ITP signed
27d08573-428f-5dc0-a7e4-8ba2ee21e7cb | note | HP*
1abdcd7b-0b2d-5fb9-9769-be0083f7ed99 | note | RESPONSIBILITY: Fulton Hogan Engineer
0b5fda32-3e95-59eb-a1d5-0c7be2c893b2 | textbox | Date Completed:
96bbfa93-de90-414b-81e7-59328c50ae81 | checkpoint | 1.2 Implementation of all measures and controls
dd054232-9115-57fc-bae3-abaff374feb7 | note | FREQUENCY: Prior to commencing any activity
7bd68408-6c19-50d2-b851-d1662b92e9dd | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
d621828c-f35d-5074-8d0c-b161ba241bee | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
7333a86b-266d-5356-b140-8c8d0f49bc47 | note | INSPECTION/TEST METHOD: Visual Inspection
d1d86872-2431-5e77-a811-eb50f4c9b266 | note | RECORD OF CONFORMITY: This ITP signed
5bf1563d-7bcb-53c7-a7ca-c738c8776cc2 | note | HP*
7b215a8f-c646-585d-b826-b8d725cb8289 | note | RESPONSIBILITY: Fulton Hogan Engineer
eb54c5d2-d28b-5846-8275-333224d64e3b | textbox | Date Completed:
4ca80318-7b14-411c-b261-11c4cf16d7aa | checkpoint | 1.3 Approval of mix design
b7fb2036-9e07-5a3a-8ced-5924ede9138f | note | FREQUENCY: Prior to the first concrete pour
f96edfc4-b65a-58cc-935b-45eb7c13f96f | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
9571677f-a2a0-54b0-86b2-8b48d1f90689 | note | REFERENCE DOCUMENTS: 610.07
adc7754c-4a28-50d5-bc7f-e9255b2f44aa | note | INSPECTION/TEST METHOD: Verify
1d91534e-1b97-5062-8618-9e8cb225bb10 | note | RECORD OF CONFORMITY: This ITP signed
d33473b7-a5a8-5948-87f4-7a8bce652fe2 | note | IP
c3abec39-caf9-563f-ace0-c56ba639eaaf | note | RESPONSIBILITY: Fulton Hogan Engineer
929ee954-b5b2-5420-948f-bcde4ed57685 | textbox | Date Completed:
a790309c-12e0-4bc4-92a8-1b5cf90e2a1f | checkpoint | 1.4 Reinforcement schedule
b3fd58b3-e7a6-59c3-8e44-a17d58910529 | note | FREQUENCY: Prior to concrete pour
6c718766-34aa-59a0-874d-8a4314740340 | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
28ffc6ba-a04a-5b27-83d5-ae1dc479286e | note | REFERENCE DOCUMENTS: 611.04
308296f7-2a2b-5f72-8af7-66bc54d585d6 | note | INSPECTION/TEST METHOD: Verify
fb134d89-2362-59d9-92d8-0548d92a4f14 | note | RECORD OF CONFORMITY: This ITP signed
7672e3fb-834f-5fc7-a425-aab154348328 | note | IP
70672aa6-a97e-5450-a1d5-291ed74ab517 | note | RESPONSIBILITY: Fulton Hogan Engineer
9e02f80f-ab1e-55d8-b0c7-31751d981112 | textbox | Date Completed:
7fc444a7-0a8b-49af-8989-db289ad4fdbb | section | Construction/Erection of Formwork
5ddb6c22-fb8b-42e3-9e0e-5b992cec2f73 | checkpoint | 2.1 Excavation (Pile)
96a8a967-bffc-578b-9a86-97a33652459b | note | FREQUENCY: Prior to concrete pour
5e136b9b-764f-5a91-b745-8b89f6a66660 | note | ACCEPTANCE CRITERIA: The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent. Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
e4bab491-bfc1-5246-bc5d-ecd5acf30bcb | note | REFERENCE DOCUMENTS: 606.05
ac152385-2a24-580f-a791-763fb5145139 | note | INSPECTION/TEST METHOD: Inspect
5820acdd-0f22-5704-a437-d62ddfeb9531 | note | RECORD OF CONFORMITY: This ITP signed
8b8090ee-1b03-5c76-810e-73263b1ce179 | note | HP
961a93d3-8dd0-556b-a682-af760154f4e6 | note | RESPONSIBILITY: Fulton Hogan Engineer / Suprintendant
5f2d5fbf-59a4-5a51-9347-fddc137a32d8 | textbox | Date Completed:
eefee247-7b07-416f-b458-88962343f7c2 | signoff | AUTHORITY HOLDPOINT
bf7c2b49-a160-4235-a97c-2064137f5411 | checkpoint | 2.2 Construction Methodology
478f70af-6b60-58f0-98d4-890d4b7badc6 | note | FREQUENCY: Prior to erection
a8945cb6-d911-5d56-a837-2e54bfa69807 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
99eb29e8-4d97-5d5b-90a3-888c95ec49c3 | note | REFERENCE DOCUMENTS: 614.04, 614.06
ded2afe6-2cb7-5c6e-b3db-f9aa2cd04add | note | INSPECTION/TEST METHOD: Verify
254072db-72c6-533b-a060-4531fe970ef3 | note | RECORD OF CONFORMITY: This ITP signed
c0270ad6-ce26-50cf-bf38-8a4ea2ad945d | note | IP
6b749cde-5c01-500f-9478-12dd06a1d216 | note | RESPONSIBILITY: Fulton Hogan Engineer
aab2ad47-c414-5c0a-99ba-8a3faf3dfd70 | textbox | Date Completed:
4e63e03f-ca1f-4a55-9fbb-2ebe24d2c92d | checkpoint | 2.3 Construction Methodology (Pile)
242bf495-ae49-56fd-a3a2-7f161c31e3e5 | note | FREQUENCY: Prior to construction
62657f8d-d69e-5a15-9694-f3456d3b373c | note | ACCEPTANCE CRITERIA: Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
1ca5eb69-6f7a-57f0-add7-cfb7f1a412dc | note | ○ Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
8c4ab3b7-3290-5512-8df3-e36ff2c2cde3 | note | REFERENCE DOCUMENTS: 611.10, 606.06
d76f329c-5d93-50b1-b9e0-1e5c38112a18 | note | INSPECTION/TEST METHOD: Verify
0e391a56-0d88-5840-b611-415659a29782 | note | RECORD OF CONFORMITY: This ITP signed
ef9b8740-e730-5b12-8db5-a33924b54240 | note | IP
1b70cf43-af55-5e2d-a01f-da107595a438 | note | RESPONSIBILITY: Fulton Hogan Engineer
de1eef3c-9382-532a-af24-84bb190e6d6c | textbox | Date Completed:
f883418c-769b-4624-a714-bdba491d93fa | section | Pre-Pour Planning and Inspection
ae9be4c6-a57b-42e2-8adf-ad2a98b7c700 | checkpoint | 3.1 Cleaning formwork
b6ea87bf-c5af-5918-aefb-93738cc1c9e5 | note | FREQUENCY: Each concrete pour
b581007c-f9de-536d-89e8-c92e81d693cc | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
6860bba7-ab73-5e5b-a3b9-583ebcfdd7fc | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
cb74be78-f7fe-547b-bd74-4bdac0c12cf7 | note | INSPECTION/TEST METHOD: Verify
2c406926-3958-5ff0-a0c5-204ddc8437c6 | note | RECORD OF CONFORMITY: This ITP signed
d29fe76c-c1a6-55da-9928-04ac613c3a22 | note | IP
9df996ed-8772-50c0-9dac-30c72c5beefd | note | RESPONSIBILITY: Fulton Hogan
1dc92603-5488-529b-99f7-a47a18c57168 | textbox | Date Completed:
9e4379cb-9c8a-4327-bc4d-e7491aefaf04 | checkpoint | 3.2 Correct forms, reinforcements, rag bolt assembly and embedments
a240de67-b677-58d5-85e4-0d1249da1ace | note | FREQUENCY: Prior to concrete pour
7bcabd99-e540-5b11-9bca-ad405a47f0e2 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
1d3377d4-efab-572a-8985-998c2d989df3 | note | ○ Pre-pour checklist completed and signed.
25da8f6e-8cb1-53ba-a914-993c73771424 | note | REFERENCE DOCUMENTS: 610.18 (a)
949607a9-78e8-55ce-846e-1fd90b3e39b7 | note | INSPECTION/TEST METHOD: Verify
683e4e2f-64d5-5a76-962a-6bfc151e6bdd | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
be6b7c15-5edd-5452-ae3d-baa980ce22f6 | note | HP
71249f26-046b-5405-bc28-7eeb626ba847 | note | RESPONSIBILITY: Fulton Hogan / Superintendent
4aa98c17-ccd4-5a0a-99d1-f4dca7de7b05 | textbox | Date Completed:
a8717a27-f939-44a6-9e15-49326f7babdc | signoff | AUTHORITY HOLDPOINT
4c9567ab-bb21-4e4f-8739-303873d938a4 | checkpoint | 3.3 Reinforcement assembly of piles
8e2f99a0-6443-5eaf-8262-d52d7ec8e8d9 | note | FREQUENCY: Prior to concrete pour
640a9bd5-f8ab-57c4-935a-7fc95fcc6503 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
4fa4a9c6-778b-51df-ac59-4824edd02343 | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
b3197dd2-036e-5b13-9d89-190c163265a4 | note | INSPECTION/TEST METHOD: Verify
7f2a11d5-f9df-5531-bac9-515db03335db | note | RECORD OF CONFORMITY: This ITP signed
3551df4e-e1cb-5658-8e9b-a3d51843aa7d | note | HP
378513c2-91ec-5e45-b058-ea44821288ea | note | RESPONSIBILITY: Fulton Hogan
6647cf7b-fbab-57b6-9904-26c215f944f1 | textbox | Date Completed:
00796bb9-80a6-4b5b-b8cd-0deb307db41b | signoff | AUTHORITY HOLDPOINT
1a5cd2ee-1913-4df6-a77f-5e667147ae85 | checkpoint | 3.4 Monitoring weather
3156b847-441e-5669-9631-9ccd358329af | note | FREQUENCY: Prior to concrete pour
3aec5dd8-b6d7-5d9c-9df1-cb9ff47e7f9f | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
82a2b215-503c-5cc3-a860-a59ce19f0668 | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
e895b4bb-a30a-5fb8-bcb7-54e12b548879 | note | INSPECTION/TEST METHOD: Verify
67769a6f-99bd-5181-9425-2952701cfc52 | note | RECORD OF CONFORMITY: This ITP signed
9d73647f-9472-5185-9d24-e6be49a76d87 | note | IP
d5f085ee-831d-5f3a-9f5d-5cb22d35b2d2 | note | RESPONSIBILITY: Fulton Hogan
691966c4-5954-5208-81dd-3d2039a4a820 | textbox | Date Completed:
25bb3d64-b28d-4138-a8c8-5feda4311053 | section | Placing and Finishing Concrete
80665115-a80e-4536-aa14-9a2b29f47f68 | checkpoint | 4.1 Carry out sampling of concrete
6ddc45fd-7a17-5c17-bb7e-920a5d09d71b | note | FREQUENCY: Each concrete pour
c29d5d5b-b737-561b-a81b-39543e2bcc8c | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
a6256a8e-5ac3-5438-9eb0-d47736ff22da | note | REFERENCE DOCUMENTS: 610.16
bc0e77dc-58d3-5177-903a-f44aace3e86d | note | INSPECTION/TEST METHOD: Checklist
f4482f59-3b42-5bc2-baf4-d12226c764c1 | note | RECORD OF CONFORMITY: This ITP signed
6e570a20-7d9b-5905-ac1e-27a6e040745a | note | IP
f5f76034-b987-5c41-bfdc-521e66756dd4 | note | RESPONSIBILITY: Fulton Hogan
c0d17f5a-3bbd-53ec-a768-4fa8c5a0fbc4 | textbox | Date Completed:
1fe7718b-4085-44ed-981d-739550d56f8b | checkpoint | 4.2 Discharge time
371098b0-e79f-55de-a0ad-6f6cd138a5a2 | note | FREQUENCY: Each concrete pour
97a41ca6-f8c3-5a86-aa52-d38c7701ca9d | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. Batch to be used has a discharge time of 180 minutes.
970cf501-297a-580c-b496-e78ef9ef24ae | note | REFERENCE DOCUMENTS: 610.13
f3e96fa5-b39b-5a04-93a8-d57b0f5d04b4 | note | INSPECTION/TEST METHOD: Verify
1b69e184-fd0f-5b4e-b545-d62cf4cec681 | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
a7b4cce0-6ad7-5d8f-936d-3abbf2e6413d | note | IP
9421e33f-3e41-535f-8d71-a9ce94e12a81 | note | RESPONSIBILITY: Fulton Hogan
1246fc0e-baa7-50cf-b6f0-b89474cc7ed0 | textbox | Date Completed:
e24f067f-d74b-473d-922a-b42296eae879 | checkpoint | 4.3 Methodology of placement (structural)
0d53d661-e709-51bb-98fc-7b1d874e02ea | note | FREQUENCY: Each concrete pour
bd01f028-3e57-5904-ad0f-245790879df0 | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials In continuous pours the max. time lag between truckloads on site is 25 minutes
9dd25a2e-49f6-51b7-baeb-b01d809eb318 | note | REFERENCE DOCUMENTS: 610.18
fcd8dd96-650e-5747-afdd-8eb4d0ad7023 | note | INSPECTION/TEST METHOD: Verify
abced5e3-43eb-5491-ac36-c085e3b72c35 | note | RECORD OF CONFORMITY: This ITP signed
16314d7e-d934-50f2-9391-69c8f35eddec | note | IP
43bc12ee-4c94-5847-827d-db4ca5bbaf3f | note | RESPONSIBILITY: Fulton Hogan
a847e6f3-e959-5c01-a6d1-44965572886f | textbox | Date Completed:
cdfd89b8-393e-4879-a3a3-28c209f9e9e3 | checkpoint | 4.4 Methodology of placement (piles)
68689735-2c60-5bd8-8401-8ee8ecb1e6c9 | note | FREQUENCY: Each concrete pour
852d08dd-edf0-5daa-ab64-c61c518e64fb | note | ACCEPTANCE CRITERIA: Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation.
ea742c5c-07f3-55b3-b663-901c1acd2447 | note | ○ Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
c1bf9601-1b50-5c51-94bd-09e94b3fdb48 | note | REFERENCE DOCUMENTS: 606.03(b), 606.05
77391b06-e144-5e62-be95-eb78ce793bbe | note | INSPECTION/TEST METHOD: Verify
de134a5b-7f76-5a02-b0fb-839983c65f06 | note | RECORD OF CONFORMITY: This ITP signed
0f5d47f1-328e-5a97-8d2f-acf6eaa16403 | note | IP
c9ea25a5-ca06-59cd-b1d5-72b3261cc215 | note | RESPONSIBILITY: Fulton Hogan
624411a8-5d9c-503a-8a78-81e1c2d87daa | textbox | Date Completed:
598183b3-4204-444d-9498-9ebdc13ec345 | section | Post-Pour Details and Inspection
01756798-2aaa-4d7b-a684-f667003d7973 | checkpoint | 5.1 Curing
abec380b-0366-5114-b8fd-ef284a5f534b | note | FREQUENCY: Each concrete pour
d54925b7-0d94-556c-9790-053a09fd4b40 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
c64c2343-9483-5114-bd2d-5ea4ffa7ce57 | note | REFERENCE DOCUMENTS: 610.23
24f078e8-3eb5-5721-878f-2f5fc9be2f22 | note | INSPECTION/TEST METHOD: Verify
96e16827-75fc-5b24-a07d-5963f045a359 | note | RECORD OF CONFORMITY: This ITP signed
f8663350-574a-5747-956c-7fd587625640 | note | IP
6dc41e2b-f869-5991-b49d-0a7836643c48 | note | RESPONSIBILITY: Fulton Hogan
e61e7a5e-1d17-5930-8c5c-817c15d62b00 | textbox | Date Completed:
929c67b9-0c8d-4267-829f-bd1ad5a45393 | checkpoint | 5.2 Formwork removal
8032b2b1-4f41-513e-b052-9846c8196c24 | note | FREQUENCY: Each concrete pour
60354908-e6a2-5213-9033-f5c8188e6ed1 | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
d779b3f7-e31a-5a66-a9c4-18571c0b4e08 | note | REFERENCE DOCUMENTS: 610.25
ccb7baa9-0e7f-526d-b805-a590cfa69b82 | note | INSPECTION/TEST METHOD: Verify
96dbf162-c954-5b24-a482-9638ede2e418 | note | RECORD OF CONFORMITY: This ITP signed
b97bf296-b458-5dba-8b78-3e01c4872417 | note | IP
f74d898d-7f50-5374-a8fe-02a50878089f | note | RESPONSIBILITY: Fulton Hogan
50ca30a8-dc01-51cb-b037-3e596ee5a072 | textbox | Date Completed:
1ed4ec0e-554a-4a88-afd0-2e3feebca051 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
86d962ef-5148-50f7-9eb1-520cf88dd1e5 | note | FREQUENCY: Each concrete pour
e1ec3de2-7969-581c-b50d-1bfd617ebaec | note | ACCEPTANCE CRITERIA: The centre of the pile head shall be in the specified plan position ±75 mm;
22a8e0c0-5607-51d7-a764-bcb4529a6992 | note | REFERENCE DOCUMENTS: 607.06
d14113dc-1ae6-5a76-82f1-72c441bc587d | note | INSPECTION/TEST METHOD: Verify
b2be3fe3-cd4c-5991-a17f-05e2bfbfcb6a | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
d62bacb2-910a-550c-a42b-e68d8981f803 | note | IP
9708a7e9-2bf8-5a29-9fac-7f5d0d832b4e | note | RESPONSIBILITY: Fulton Hogan
0d4f3794-3a73-54d9-b05e-fbfe93d6ca8a | textbox | Date Completed:
03b3da68-72f7-4c87-97a8-92b18baf7f59 | checkpoint | 5.4 Concrete Sampling and Testing
1d0d2a89-2697-5e22-825f-494c68b7f631 | note | FREQUENCY: Prior to lot closure
4a114978-844e-5ae9-9bee-246a11b81186 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength:
5e790f3a-f5cb-5cae-85ed-125c4c2078a5 | note | ○ 2 cylinders @ 28 days Compressive Strength=32MPa
2e4f0ad6-2739-5b22-9659-0a3664089999 | note | ○ 1 cylinders @ 7 days for Compressive Strength=20MPa
55a6cd98-48a9-58cc-93ff-88a1525ddcb0 | note | REFERENCE DOCUMENTS: 610.05, 610.06, 610.13, 610.16
facc4843-a11e-5626-bc48-2686bc63d59b | note | INSPECTION/TEST METHOD: Verify
cd7b86ac-b3c1-55ac-aa50-045380bca5f2 | note | RECORD OF CONFORMITY: This ITP signed
2c6c8be7-8b7b-5e91-86b3-834bd9c098d9 | note | TP
831a541e-0f90-5560-a655-0421a953711d | note | RESPONSIBILITY: Fulton Hogan
e2488ef2-9677-584e-97a7-5573f47686c9 | textbox | Date Completed:
5a46030d-6b42-4bb9-b743-8d911ccd6b1a | checkpoint | 5.5 Protection of Adjacent Piles
62ea9cc4-8594-5ea9-97e6-f02423141bf7 | note | FREQUENCY: Prior to commencing any piling
f4e750f5-54ff-5b12-a64f-cdd5bb9d5e95 | note | ACCEPTANCE CRITERIA: No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
374ca4f7-daa1-57aa-9b08-0d7cb4cf436c | note | ○ Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
4c44adf4-5f91-5cb9-a8a3-558dfbb253e3 | note | REFERENCE DOCUMENTS: 606.04(a), 606.04(c)
a97a0eae-43f7-508e-9522-c103233d6017 | note | INSPECTION/TEST METHOD: Verify
3b7d1cc9-f450-5ba2-89c6-9cab31096127 | note | RECORD OF CONFORMITY: This ITP signed
f7b5ec0f-416c-5f36-8efc-7305b01c8786 | note | HP*
6090a46a-6f8c-5ee6-8252-7a37961a242a | note | RESPONSIBILITY: Fulton Hogan
c3258990-a268-5c12-9ec4-633136d6f6d0 | textbox | Date Completed:
21edf6d8-f3c5-4d6d-8c07-0f678e7852bb | checkpoint | 5.6 Testing Post-Pour
0fe91ae3-3ba4-5cdb-96f3-c13d27fc4e1c | note | FREQUENCY: Prior to lot closure
c9587433-ee73-5b0f-bdad-963c16d3b9be | note | ACCEPTANCE CRITERIA: Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
09a454a4-e8d7-5383-986d-209ad3402f6b | note | REFERENCE DOCUMENTS: 606.07
6576a915-dd1b-5561-8ab4-b786d99d5fb3 | note | INSPECTION/TEST METHOD: Verify
29c7eee4-974f-5ba6-9f8e-eac9b80af8fc | note | RECORD OF CONFORMITY: This ITP signed
4882073b-526b-5dfe-ad37-8cb2636758fc | note | TP
0fa871b6-b8c5-5ea5-976d-9c97931ecf8f | note | RESPONSIBILITY: Fulton Hogan
696c4cc3-2aac-50ad-ab91-8bd6965bd4a3 | textbox | Date Completed:
cda0c40d-132c-402b-bdb3-cb3956b31d99 | checkpoint | 5.7 As Built Drawings
3a8766c7-a887-5d24-a342-a5d4edcaac43 | note | FREQUENCY: Prior to lot closure
7706254c-3c09-5522-b54d-f5391dc0426e | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
cfbefd2d-59ca-5c16-83b5-b1e1d910611e | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
46093cf6-55dc-5bfe-b069-4849e45fcb90 | note | INSPECTION/TEST METHOD: Verify
0677a31e-1ae3-532c-9c76-bdf40325f9e9 | note | RECORD OF CONFORMITY: This ITP signed
b90a2f06-0a95-56ec-ab29-09d51660bebc | note | IP
291329c8-3b11-5422-8da6-1ecd5ccbb014 | note | RESPONSIBILITY: Fulton Hogan
39971187-162b-56f2-958f-3111414e137b | textbox | Date Completed:
ae1bc0dc-ff41-4bb6-84c2-7ed136439333 | checkpoint | Final Inspection
b32ec701-8669-5258-a3bf-0bc540191855 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3b8880bf-741f-5d0d-aa56-32685a64d53a | textbox | Print Name:
7ad92111-d891-5ccc-ab5a-e9a25163bb4b | textbox | Position:
a68496d0-e03e-5617-b5ea-06d7ff0fb361 | textbox | Date:
06b18612-a2ca-41f0-9c3f-efdb55a33b46 | checklist | ITP-029 - PVC TGSI Installation | itp | ITP-029 - PVC TGSI Installation
bdb7366b-45fa-4efd-8296-20ed41f6765f | section | Preliminary Works
71d47979-f31b-4d94-8ddc-f18c73c60e86 | checkpoint | 1.1 Check for Correct Documentation
1635e16b-f4b1-57f1-a47a-bea1b80b81a9 | note | FREQUENCY: Prior to Commencing Activity
86c14fa8-e4d3-5064-a556-9c04daf0749b | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
925c0b85-b52e-577f-aa9f-b269e0da0bb4 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
0368d2a8-d812-5b43-970b-73e3c0d3f64c | note | INSPECTION/TEST METHOD: Visual Inspection
823bad52-1596-53c4-b672-f1e300aaaef5 | note | RECORD OF CONFORMITY: This ITP Signed off
c40bd569-7079-51ba-bb73-2433d10b1ed7 | note | HP*
be8c110c-cca8-553e-bf8d-eea561f8d71e | note | RESPONSIBILITY: Fulton Hogan Engineer
18c83f1a-c46c-5355-9579-8ad325c6e065 | textbox | Date Completed:
cf0381f2-a0e2-499c-b163-d3abb8d420e2 | checkpoint | 1.2 Implementation of all measures and controls
9fbfde98-d6e0-56ae-9d63-75ad5618eb7c | note | FREQUENCY: Prior to Commencing Activity
f962f4c7-69ec-536a-a087-8560b4d49881 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
63498ff5-3012-5e4d-b4ba-7e1637ce0f7f | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
52b08849-5f98-5a23-90d8-aa776fdb9866 | note | INSPECTION/TEST METHOD: Inspection
ace63f0b-2d91-5b8d-8d11-14b435ee4cf4 | note | RECORD OF CONFORMITY: This ITP Signed off
3de5d2a6-9b6f-525c-8684-32b986a990df | note | IP
ab216ffc-893f-5041-a6a4-333ec43d3fb0 | note | RESPONSIBILITY: Fulton Hogan Engineer
f4eb7197-7512-563a-bcc1-fd6bbb83059c | textbox | Date Completed:
11eaabde-ddc5-4560-81a8-38442180b6d8 | checkpoint | 1.3 Check Materials
14157a20-9184-506a-8dbb-b1beb3fc5668 | note | FREQUENCY: Prior to Commencing Activity
f7ddfc32-5415-5d00-8152-a94afeb16c93 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
89d189ac-5ae7-56ed-89c4-b9c36899c5b6 | note | REFERENCE DOCUMENTS: Receivable Inspection List
388bc29e-5250-5962-924c-89cb65af8cf0 | note | INSPECTION/TEST METHOD: Visual Inspection
18804799-696c-59ac-88ec-4c3c084517d4 | note | RECORD OF CONFORMITY: This ITP Signed off
6269e19a-bf74-5be1-be02-204f4361c59e | note | HP*
3a011bc3-c405-5781-bb5e-9cb5b1c3f66e | note | RESPONSIBILITY: Fulton Hogan Engineer
04e8b42f-4434-5e60-893e-b5bd2ef1ed32 | textbox | Date Completed:
ee263f8f-a07e-4d25-8f55-3c20481785d2 | checkpoint | 1.4 Setting out
f5b8bfb7-4283-5eba-87df-60e3389e2c8e | note | FREQUENCY: Each Lot
26fd2567-7038-5ee8-a741-5d7c630a884e | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
cbe5b274-a33d-5c1b-a53e-3bf7f3f029b9 | note | ○ Line and level of tactiles shall be set out according to design levels to suit new kerb height (if applicable).
3d5b48af-71ed-5cf8-9c06-df5c35a274d5 | note | REFERENCE DOCUMENTS: Work Procedure
7e271b04-7172-560c-8245-dfc6bbfd1520 | note | INSPECTION/TEST METHOD: Inspection
c08708c4-8fb7-5275-a8d9-1fdd103af61a | note | RECORD OF CONFORMITY: This ITP Signed off
942154ca-61dd-5d85-a8e4-e0286dde9060 | note | WP
b91bd1d7-c566-5da7-909a-00b3e9e266d9 | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
db9a1ae2-5399-5cb6-a0ae-2b8e9373a2ae | textbox | Date Completed:
7b86007b-8eaa-4722-bbfb-24863d137f9b | section | Construction of Access Ramp Bluestone Footpath
ead4abf8-05a8-4946-9c9e-d36cc36275f7 | checkpoint | 2.1 Base preparation
ed23f898-170a-5b31-a5be-2c48fe7f2125 | note | FREQUENCY: Each lot
c3b83c1e-12a0-552a-90f4-817ab27fca02 | note | ACCEPTANCE CRITERIA: TGSI should be laid in accordance with the site specific application and applicable standards before fixing
cb2b2534-91fe-5e4f-a51f-739ac2fefbfe | note | REFERENCE DOCUMENTS: IFC Drawings
fe8b153b-86be-5aa6-8d1f-cef0624451ea | note | INSPECTION/TEST METHOD: Visual Inspection
b3aa997f-6b2e-5d61-8a41-788f6d644e9d | note | RECORD OF CONFORMITY: This ITP signed off
ee5f43be-fd89-5376-970b-032612faa410 | note | IP
1d6b07d3-be02-560f-a0b0-8a416e0de028 | note | RESPONSIBILITY: Fulton Hogan Engineer
380de746-2d52-5fd6-99e2-2868beb61126 | textbox | Date Completed:
1b1c3b77-828d-4ab8-ae6e-e5355302268f | checkpoint | 2.2 Placement of TGSI
5921d402-244a-5d0b-ac2e-c60b34efcbcd | note | FREQUENCY: Each lot
120bf33a-bffc-5dfb-a92f-70f4674d1177 | note | ACCEPTANCE CRITERIA: Ensure the placement of the TGSI are in accordance with IFC drawings and are compliant to AS1428.
7459de7c-ca96-549c-923e-ecef49888747 | note | REFERENCE DOCUMENTS: IFC Drawings
74425852-c1fe-5abd-8dc7-b5c2eb17fb5d | note | INSPECTION/TEST METHOD: Visual Inspection
cd18e96d-dadc-515a-9545-b01d1ca3ea3e | note | RECORD OF CONFORMITY: This ITP Signed off
002b3d10-8327-5f9a-bd41-77a638bf4c06 | note | HP
ca266360-6c8a-5b5b-bb5b-fd6e432e0f46 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccb99896-5a9f-5ccb-ad0e-f65387e9de6d | textbox | Date Completed:
2fa2c6e9-158e-4f2e-b4b4-4f43fe294576 | signoff | AUTHORITY HOLDPOINT
18fd4935-b943-4227-9e7d-3366e2e8291c | section | Completion
5185ddc1-6c6e-408d-81e4-8b450ace3db7 | checkpoint | 3.1 Completion
f08c04fc-2395-58d4-8c3a-d9c0b6ec8dee | note | FREQUENCY: Each lot
c11b9c1f-794e-5bef-8d5c-14c6172a39ee | note | ACCEPTANCE CRITERIA: Ensure pavement area is free of debris and waste.
5c46a3e4-f6eb-5aa6-8364-c4c766c7280d | note | REFERENCE DOCUMENTS: Visual Inspection
047172a9-454c-5c15-905e-dcc67f502bc4 | note | INSPECTION/TEST METHOD: Visual Inspection
e8d1e333-a242-5ac1-9254-31151baa72ed | note | RECORD OF CONFORMITY: This ITP Signed off
2d6c3248-3bc6-57cb-bacd-3086828fb451 | note | IP
981964e4-5887-5b7a-bae8-16d17f37cc8f | note | RESPONSIBILITY: Fulton Hogan Engineer
5d9ee954-90a2-5c17-a869-0513a4720021 | textbox | Date Completed:
9103d28c-721a-4684-99f3-3f4d7bc898e4 | checkpoint | Final Inspection
f077d2ea-fcc5-53a4-91e6-c253a1b20017 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
68005702-25c0-56ac-a874-043378314ad8 | textbox | Print Name:
e6118283-cd62-5984-8f1c-75c1af6dd246 | textbox | Position:
0e249a42-e432-599d-8b36-a149a3094ba3 | textbox | Date:
5e44d31e-3958-4232-85c0-f7c81fc53dfe | checklist | ITP-031 - MCC Stormwater Drainage | itp | ITP-031 - MCC Stormwater Drainage
c4b25132-4991-4b47-ae8d-902292d588fb | section | Preliminary Works
d780efba-b0e0-4c55-9328-761ac22ef9e0 | checkpoint | 1.1 Check for correct documentation
68261048-87e2-54d7-ac0f-51340000107b | note | FREQUENCY: Prior to commencing any activity
12dbb632-74f2-596e-94c6-5ba91c1f9299 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
fbe8a16a-d2d4-5329-82d7-2be57d5d1b4b | note | – using the correct and complete set of drawings
d9533d4d-d6c7-5bde-8e95-9df6e1d0c56e | note | – all drawings are the latest revision
763217b3-e533-53bd-8a38-8f017f5f3683 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
ac680486-b39e-5301-84d0-d6ac9bdff3ad | note | INSPECTION/TEST METHOD: Visual inspection
f343af6b-1c80-566a-85d3-658e7010d98f | note | RECORD OF CONFORMITY: This ITP signed off
4b2bef65-58c8-5052-9b1e-11339a0d738d | note | HP*
c19668b2-4889-5693-9037-a8e1c8bc2ce0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
2566d0f5-6ce2-577b-adad-ccb24169b296 | textbox | Date Completed:
8450b842-7cd9-46dd-b47f-4e44f2fe7218 | checkpoint | 1.2 Implementation of all measures and controls
1a5b027c-e139-5dc7-bad6-45c1c56f4ad5 | note | FREQUENCY: Prior to commencing any activity
8c571746-33b2-5e71-8a10-a5ad6b3e68bd | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
0537081d-d728-56f7-a0a1-87b12127fba9 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
9390dc98-61d5-5a06-9a07-d6776ceb0755 | note | INSPECTION/TEST METHOD: Visual Inspection
e7bfd93e-5f6f-5e4a-8296-06d7eb6fe2e5 | note | RECORD OF CONFORMITY: This ITP signed off
02679dfe-26e5-5b17-a5e3-3aa6003b432a | note | HP*
efd07847-727a-5454-aacd-05aeede20550 | note | RESPONSIBILITY: Site Engineer / Site Foreman
4dcee3d4-2506-5607-9625-f26a488765cc | textbox | Date Completed:
f5d2a4b7-b868-4900-ad23-a0ddc87b2b50 | checkpoint | 1.3 Precast Materials acceptance
e7f884c1-b8fb-5817-acdd-43a3e63964ab | note | FREQUENCY: Each Delivery
d99886d1-3ac3-5496-b76f-9ddea25a6833 | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
c510d11a-fc30-5dd8-aebf-47f0cae26d74 | note | REFERENCE DOCUMENTS: Cl. 701.05e
93b858fb-37c4-5fea-afa5-aab6b0ea4ad0 | note | INSPECTION/TEST METHOD: Visual Inspection
3821230e-5f40-592d-a65e-6c2fb2fbfeaa | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
e2e80c6d-d9af-51fb-8940-a9a2b4d60412 | note | IP
1cdccd05-db7d-5c93-abd6-162e8e51fd9b | note | RESPONSIBILITY: Site Engineer
7f57dc6b-06f2-5b65-b72c-fa9879da8b46 | textbox | Date Completed:
e4b4403a-aeb2-47a4-abf6-1e7f74cc35e5 | checkpoint | 1.4 Precast Pipe & Culvert Compliance
2c48aa35-b257-5f35-b6b5-17a01d86bb98 | note | FREQUENCY: Prior to Commencing
43495af2-e0a8-5a04-9b1a-86da7e97d73c | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
215c9a10-06bf-561e-bb26-2e9321dc6795 | note | ○ Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058.
11e313e5-1d41-5be4-8336-ae3602a74661 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04, Cl. 701.05(a), AS4058, AS4680
9a529991-a54e-51cf-8678-1b96ca424c7e | note | INSPECTION/TEST METHOD: Document review & Site inspection
bb10d3c9-57be-5d83-8ee6-24216c5c0ce5 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
2a966ae9-6623-555c-90c5-38c3773a9fe9 | note | IP
2c845632-3da8-56d2-afda-5089cfd6bdde | note | RESPONSIBILITY: Site Engineer
736feed0-fe3b-53d4-9d66-b284475871e3 | textbox | Date Completed:
11f7dd6d-8829-448f-af3d-796e9d245bfc | checkpoint | 1.5 Precast Drainage Pit Compliance
e8ddc2a8-7a52-5ba2-9ebc-32a4a642ca95 | note | FREQUENCY: Prior to Commencing
615f9074-ee4f-5c36-b72f-bb8909db5507 | note | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
88bc396d-2b65-548b-a0c6-196770c56675 | note | ○ Pits to manufactured as per the City of Melbourne Standard drawings 1P 50301, 1P 50318
30acbb6b-8731-5720-a445-2c811f090b00 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.610, Cl. 705.04, AS5100, City of Melbourne Standard Drawings 1P50301, 1P50318
28b0807e-1fde-540f-9dcc-2df0211a5c0b | note | INSPECTION/TEST METHOD: Document Review
30351d35-8976-5676-ba0a-93c2199f4fc9 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
ab5644c3-494e-5cbd-bc55-d205fe2432b4 | note | IP
92692214-32d2-511a-b080-974ccd4aa0c9 | note | RESPONSIBILITY: Site Engineer
e1e98521-dcad-5fda-93f2-6418da7ea2f4 | textbox | Date Completed:
b88d9d3e-04b1-4a4f-86ad-5ba9b97eb890 | checkpoint | 1.6 Bedding material classification
3fd2644a-662a-52d4-8bed-4fde186a4842 | note | FREQUENCY: Prior to start
8669ab9f-48ba-587f-9c23-d59b46c9e97a | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
dd85d741-fa4f-5311-b7ff-882359fd0847 | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
c0a2c515-6d1d-5aaf-8603-c11fef5afc58 | note | INSPECTION/TEST METHOD: Verify
985ddf6b-21dc-51ab-ae7c-db5ee865e4b3 | note | RECORD OF CONFORMITY: This ITP signed off
7992ce57-ba37-5a73-a7a7-44658ebb7b75 | note | TP
1668d895-27c9-5f33-88a1-5bdf24d257bf | note | RESPONSIBILITY: Site Engineer
d31ed9b7-c230-5603-be52-c8401bd3c682 | textbox | Date Completed:
a3a20c50-9791-4731-a87b-e8ac503989fd | checkpoint | 1.7 Backfill material Classification
695fd4cc-cbfa-5847-ac05-df10b40e2cce | note | FREQUENCY: Prior to start
9aad53db-a7b8-5621-939a-cadd3bcb261b | note | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
e2b80d02-0966-56a1-81a7-cbd5a0aa6731 | note | REFERENCE DOCUMENTS: 701.09(d), 701.091
8deb9ea2-75bc-5f5b-a730-d4371620c33d | note | INSPECTION/TEST METHOD: Verify
d8c86596-1732-586d-b249-ba56e2f95298 | note | RECORD OF CONFORMITY: This ITP signed off
6e963cf8-9e32-57f3-8624-1aada8abc93d | note | TP
8745c5dc-9bff-55ef-8f7a-49c96f5df56a | note | RESPONSIBILITY: Site Engineer
00db9610-a712-5c14-9856-4ab94e52ed7d | textbox | Date Completed:
2c9ed76c-63ad-4c8f-bbd1-093afd46ab12 | checkpoint | 1.8 Mortar material classification
88b3c96f-4fbc-5c6d-afa8-a5898f1ca297 | note | FREQUENCY: Prior to start
2b54334b-a290-55d0-bc5d-7a71bc1aa441 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
4e9fb2ec-eff7-5a66-9aaf-815667cd2ce9 | note | REFERENCE DOCUMENTS: 610.33
b2b8a3c4-67a3-5808-b099-88e4c1b1caeb | note | INSPECTION/TEST METHOD: Verify
3cbb583b-b134-5258-b65a-45f53b73cca8 | note | RECORD OF CONFORMITY: Test Reports from supplier
8bda2683-e090-5013-932a-ed0f9a8d1302 | note | TP
33395bde-52ba-5bc5-bdc6-d8ca10560d92 | note | RESPONSIBILITY: Site Engineer
0e38f378-a2c5-5e4c-9df1-b06b1db6f24a | textbox | Date Completed:
62f04c6b-90ec-4a09-ad40-1a608441481d | section | Construction Works
1096254c-35ad-407f-a86a-2581a8a38734 | checkpoint | 2.1 Excavation Permit
d28f9b3f-17ce-5e32-b551-d8b58f46384a | note | FREQUENCY: Each lot
3252a9b2-7992-56a5-959b-dc697fb4247e | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
acdb07c1-6c1f-5a4a-80ef-4057dd83feab | note | ○ Plant and equipment shall be appropriate for the task.
a1873663-e47f-5f8a-abce-299db28c3a99 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
7a0dbe79-cde1-5975-8227-18fcc03ac890 | note | REFERENCE DOCUMENTS: Excavation permit
a79d5f47-ef28-55b0-9231-50c19ca2ab68 | note | INSPECTION/TEST METHOD: Verify
513f4f87-2f00-55e8-9eb7-e72e1b0fe4ec | note | RECORD OF CONFORMITY: ITP Signed
365610ef-a6bf-517e-b28b-0ef8f2d44cf0 | note | HP*
c66f11e2-da23-57c6-adc6-1b48061a75ce | note | RESPONSIBILITY: Site Engineer
d6c33251-cb04-5bc0-b5a6-2a3620f11b43 | textbox | Date Completed:
3708d96b-de02-4994-be64-5b3d83573014 | checkpoint | 2.2 Set out drainage
41b996c0-ed5b-5847-9fe3-9e3622fdc967 | note | FREQUENCY: Prior to backfilling
0e875489-a186-5b79-a425-a61147620bdf | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
90680e59-7afd-5e92-b157-314499ce9553 | note | REFERENCE DOCUMENTS: Drawings 701.10
11495a5b-8903-5b6a-9ca1-83bd9f24b8de | note | INSPECTION/TEST METHOD: Visual Inspection
bc01678e-5c1f-5796-b4d3-59067e27d4a7 | note | RECORD OF CONFORMITY: ITP Signed
a94cd93e-1d08-53ff-96cc-0a1dea61c727 | note | HP
9c27c7db-dabb-542e-bb8d-dfc116b98441 | note | RESPONSIBILITY: Site Engineer/ Superintendent
956dbba3-5f5b-56d5-90f1-bd93f57318b8 | textbox | Date Completed:
87d9fca1-7bec-464f-bd2e-b14bf4bbba57 | signoff | AUTHORITY HOLDPOINT
0f73b3ae-8d04-4245-8642-d3a63199f1f7 | checkpoint | 2.3 Excavation (pipes)
0df387e5-b1fa-5b20-be21-b80f70b2b5b1 | note | FREQUENCY: Each Trench
9fa6d2c8-7511-52b7-8b03-b7e4bb34cac7 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
1ff96808-f58d-5d35-86fd-c72a386454a4 | note | Depth of trench:
14fc7e4d-5de7-5e31-9292-406293bf5aea | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
e22907a1-1f0f-55c0-8f3e-3c103d3c814b | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
cfe6d059-7fe8-5425-9216-5606784d7996 | note | REFERENCE DOCUMENTS: 701.151, 701.15
db7d481a-aa58-5388-a0d8-3d4a3e91455d | note | INSPECTION/TEST METHOD: Visual Inspection
ad5eccad-3336-54a6-a306-83686f670ed8 | note | RECORD OF CONFORMITY: ITP Signed
554d353e-f99e-5001-b49b-5f14032efb62 | note | IP
f1d3e7fb-4acc-5544-9e19-8aa4d96ff3da | note | RESPONSIBILITY: Site Foreman
1e249a01-59e4-59fc-bf8e-70fa546176f6 | textbox | Date Completed:
85b7fe14-182f-497c-a510-a9d6da4ebf53 | checkpoint | 2.4 Excavation (pits)
d6e2f98b-ae7e-51a5-9523-202ef19dabda | note | FREQUENCY: Each Pit
fb0b2e0a-5ea7-5e81-b840-0804476202ef | note | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
d90db286-22ae-5893-856a-eea4a5ecc912 | note | REFERENCE DOCUMENTS: 705.05b
a1734ee8-c9f0-5c02-b984-620094fe6bb0 | note | INSPECTION/TEST METHOD: Visual Inspection
bd718d36-1b09-5c18-a807-196838325241 | note | RECORD OF CONFORMITY: ITP Signed
e8adcdbc-4482-55a1-a2d7-b74be9c083a2 | note | IP
fba76189-b0a2-5546-ad3a-5c7e6eb1a578 | note | RESPONSIBILITY: Site Foreman
f71590ab-b81d-576f-b255-50b57cb3928d | textbox | Date Completed:
f3ee935c-6e65-4419-ae06-ee37a8249a1a | checkpoint | 2.5 Compact base of trench
7d40498e-a1ff-58b4-8569-4083d0cd9c3c | note | FREQUENCY: Each Trench
22fd46ec-0aeb-5b72-85af-bdfa222ae7ea | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
a59e31b5-eec1-5f0f-b3be-b335aeb1c026 | note | REFERENCE DOCUMENTS: 701.15
357222d1-9b46-5695-9411-76eb0fb7e369 | note | INSPECTION/TEST METHOD: Visual Inspection
1e8903f5-5f6f-512e-8762-d1bad0e7708a | note | RECORD OF CONFORMITY: ITP Signed
7346c101-8177-5458-b2fa-a70f4241c310 | note | IP
4f8c447b-bc6b-58d3-8681-202d3e95f076 | note | RESPONSIBILITY: Site Engineer
1cd690a5-7d74-5ef7-a83d-412b0ab8ef15 | textbox | Date Completed:
58280007-c27d-4ae7-92b9-8391cb3d4793 | checkpoint | 2.6 Place bedding material & compact
a2a691c2-549b-555f-899a-3e02b74d19d6 | note | FREQUENCY: Each Trench
1c5e6e37-3479-5d9e-9114-5e110a5d1a5e | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
8100446d-0736-57b7-af67-f9e94ea6e9f6 | note | REFERENCE DOCUMENTS: 701.20, 701.20a
daac6bfe-47e9-578e-bf0a-3b3a6c8b6c29 | note | INSPECTION/TEST METHOD: Visual Inspection
6948669a-7c1b-5c75-b8a3-2a4144820a31 | note | RECORD OF CONFORMITY: ITP Signed
c59669d1-4b07-5c97-bef5-d4c2491dcddb | note | IP
9a92a259-ba11-599d-8ac2-bc116fa6f45f | note | RESPONSIBILITY: Site Engineer
3da65226-c7e3-5e50-8bb5-efd567b6a907 | textbox | Date Completed:
1a96ec29-7056-4049-8519-79c44720ae8a | checkpoint | 2.7 Place pipes & precast pits
2045938b-9baf-5396-83e9-275dcc33a6c7 | note | FREQUENCY: Each Line/Pit
e5b39a28-372f-5370-9c03-0fd5621ea922 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
f8583187-ed07-56f0-8e25-8e03c48c3f7a | note | REFERENCE DOCUMENTS: Drawings
aceb958d-0155-5050-bfa3-9e74f2d07e56 | note | INSPECTION/TEST METHOD: Visual Inspection
590e699e-3cde-5eb0-ab92-c59270e45eaa | note | RECORD OF CONFORMITY: ITP Signed
8a96d205-ee8a-55e0-b7a5-7a7a970761b9 | note | IP
ff51ace7-fb73-502d-a9ca-1287338ff3ef | note | RESPONSIBILITY: Site Engineer / Site Foreman
fbfdaa30-339f-5396-b370-ae515473ec8b | textbox | Date Completed:
5da8e448-a002-4470-b305-c0028dc2c705 | checkpoint | 2.8 Installation of In-Situ Cast Pits
481e09f5-5d75-58f0-a82d-8284b9f19cf0 | note | FREQUENCY: Each Pit
6d4ded27-2e97-55b3-8674-bbcc74c578cb | note | ACCEPTANCE CRITERIA: In-situ cast pits to be installed as per the City of Melbourne Standard Drawings 1P50301, 1P50318
b5ae5ca5-3fac-5add-bb75-77838e681366 | note | ○ Pre-Pour inspection to be completed
47d6c07b-bc83-5623-ab0f-671f09417cbe | note | REFERENCE DOCUMENTS: City of Melbourne Standard Drawings 1P50301, 1P50318
75f839d4-3425-5717-b800-03865da409d1 | note | INSPECTION/TEST METHOD: Visual Inspection
af0dab4f-0cc2-54db-b34c-d017c812f2f6 | note | RECORD OF CONFORMITY: ITP Signed
03b88280-689e-5e81-aabc-a1724d524a41 | note | IP
50c85084-d44e-56e8-a058-1939a767986b | note | RESPONSIBILITY: Site Engineer / Site Foreman
6797049d-4b02-5f22-87b6-8cacc65b7a52 | textbox | Date Completed:
38232e6f-41b8-4812-91ea-599a4d5a773d | checkpoint | 2.9 Jointing pipe sections
177ceaff-c07e-5aa4-b985-10a24bba6f7c | note | FREQUENCY: Each Line
41580123-481d-5444-ad1f-97824690ac6f | note | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
7b6c61b0-6647-5a80-ac6e-851b2e7e5995 | note | REFERENCE DOCUMENTS: 701.18
5b08fcac-29cd-5c35-98ed-eb05ce89748f | note | INSPECTION/TEST METHOD: Visual Inspection
55eb6554-b192-5e23-9318-ac0fa2e63c01 | note | RECORD OF CONFORMITY: ITP Signed
d4040a7b-74ad-5388-9bf4-c2a3589ebc50 | note | IP
317422d0-c7f7-54c2-bd3e-9c8f0e9fd3df | note | RESPONSIBILITY: Site Engineer / Site Foreman
7d45212a-7e81-52d5-98a2-dab966d6389e | textbox | Date Completed:
ed34e02a-c8d7-48ad-ad3d-b1d0535f54f8 | checkpoint | 2.10 Sealing - for joining culvert sections and pipe penetrations in pits
591aadbc-b92f-5387-8234-0e7b09c0a917 | note | FREQUENCY: Each Pit
5fc56239-fe73-5e6c-941a-21476d6347d7 | note | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared. The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
f887589f-1f9b-5f69-8df5-25f981ba5671 | note | REFERENCE DOCUMENTS: 610.32, 701.17c
9dccdd3f-0491-5eb8-b551-5dd44404da1b | note | INSPECTION/TEST METHOD: Visual Inspection
2b2e0531-6017-53e7-85c3-bd7a35c312ac | note | RECORD OF CONFORMITY: ITP Signed
7107cb47-c57a-55df-b31e-e413e7f2710f | note | WP
0382f27d-a626-5476-97ab-ccff28c846be | note | RESPONSIBILITY: Site Engineer / Site Foreman
4f6d34fc-3e93-546d-abd8-9c9a1abf6c33 | textbox | Date Completed:
5f79e4c7-10b2-4e8e-8b6b-aa81a0b303b7 | checkpoint | 2.11 Survey of laid pipe or pit
eab88786-1829-563d-a23b-07e8ae738284 | note | FREQUENCY: Prior to backfilling
054a718f-bd8f-5973-9628-e62671025193 | note | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances:
49a42b78-d539-5374-886a-c8c8ed31f0f4 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
c0a20787-1e61-5c87-bc9f-d215a8403e36 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
0235e0e4-b07a-5b84-8fa0-ad803a4e45ce | note | (c) invert level of pipes at pits ±50 mm
affc5b12-ada2-5c9f-8da7-9252a9bc85dd | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
e84f51ea-c55d-58e9-912d-a875cdf0bdc2 | note | REFERENCE DOCUMENTS: 701.1
bfcd7d3c-e735-53c0-8096-61bf9b281343 | note | INSPECTION/TEST METHOD: Survey Conformance Point
6c902c77-af70-59f0-8704-15acdc647a85 | note | RECORD OF CONFORMITY: ITP Signed
bf2a72e8-7124-5107-a458-60dd5987de57 | note | SCP
3241e3d1-6524-5d16-9738-6468d6f5d6b8 | note | RESPONSIBILITY: Site Engineer/ Surveyor
b817f0da-71e3-53f3-af42-b71019ef0db2 | textbox | Date Completed:
56403b6d-f5d4-4f62-b9e8-9b358dcd2136 | checkpoint | 2.12 Haunching & compaction of bedding material
0a1234c7-bf16-5d13-ab12-0f4834a205d7 | note | FREQUENCY: Each lot
dec4547e-c8ee-5e7c-9dac-8389916e8a73 | note | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
af8d72ac-ee7e-596a-a592-92d87564ad81 | note | ○ Loose layer thickness <=150mm
86433864-1135-53e5-ab5c-111c50a09617 | note | ○ Compacted to refusal using hand held mechanical equipment.
baaae124-b883-5ebc-9e1e-b73049e1388a | note | ○ 1 lot = 150mm layer
0a5088d3-1132-535d-9008-f8d43efe41d9 | note | REFERENCE DOCUMENTS: 701.16, 701.20
d1dba5e7-c3b5-52a3-85bf-c10a76f9d24b | note | INSPECTION/TEST METHOD: Visual Inspection
11a9dd41-7f2e-551d-aad8-4b6e3fb20395 | note | RECORD OF CONFORMITY: ITP Signed
5cea91cc-8dfa-5b1c-b879-c308faee1e9f | note | WP
8268543a-d713-5b38-bb70-e587cf27db88 | note | RESPONSIBILITY: Site Engineer / Site Foreman
4fdc6692-b610-54f5-a082-602d5eeaa120 | textbox | Date Completed:
3aef2371-faf5-484f-8b56-22e149a63f3d | checkpoint | 2.13 Place & compact backfill material over pipes
004c034f-7d48-53ea-bccf-7c325e365cb7 | note | FREQUENCY: Each lot
20805993-9124-52e3-96e8-b5ec96c62ba4 | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
372c156b-95ce-566e-9de5-64365d662554 | note | Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
cc31bee2-935e-55bf-8b5f-bb38f7dc9a89 | note | ○ Loose layer thickness <= 150mm.
232aa595-9785-51a9-be66-a54cec73ceed | note | ○ 1 lot = 150mm layer
3a8544b5-a701-55a0-94f4-0b360d0e6b1a | note | REFERENCE DOCUMENTS: 701.19, 701.20
40dd10ae-ecef-5ed8-8d8a-330c41871d62 | note | INSPECTION/TEST METHOD: Visual Inspection
16f8205d-3135-579c-beff-07213520b401 | note | RECORD OF CONFORMITY: ITP Signed
e59e0259-c685-52e0-aef2-8cb4755ba985 | note | IP
d3c8de26-fe3f-5f6e-8d6e-bd116c7347c4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
53a527a7-348e-5b83-bce1-a14e3d6e02ad | textbox | Date Completed:
927935e2-a79d-4626-9665-5ca4591f737c | checkpoint | 2.14 Place & compact backfill material around pits
e9c60315-76b3-5bf1-8eb1-30ee3efb5899 | note | FREQUENCY: Each Pit
5a63e91a-e629-5fda-a8dd-906225654369 | note | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm.
19133ed3-4c2a-5999-93f7-46ff57896e3e | note | ○ Compacted to refusal using hand held mechanical equipment.
820000bb-1cbd-526c-9779-e0ecf9073f8a | note | REFERENCE DOCUMENTS: 705.18
196042f2-5fca-5e9d-8eff-9290bdb489c9 | note | INSPECTION/TEST METHOD: Visual Inspection
ea5785b0-b258-5eb5-bba3-9483f3a1bb9b | note | RECORD OF CONFORMITY: ITP Signed
42e8f2fe-7d6d-5945-9398-e812266c9f6f | note | IP
103f99e3-ec07-5d6b-855d-f97c3160df4a | note | RESPONSIBILITY: Site Enginer
72a67c87-95da-5e89-9ae9-bd4855224d80 | textbox | Date Completed:
777049cd-cbfd-4966-acf5-3a3e589f3177 | checkpoint | 2.15 Install step irons
e9cbb9a1-cb9e-52c5-b988-a8af955cfa40 | note | FREQUENCY: Each Pit
1b66f08a-ef9a-5695-bd0f-071aaa4b0f16 | note | ACCEPTANCE CRITERIA: For pits > 1m deep.
48b5ef32-96a2-5ecb-a04f-ed14e3cee6fe | note | REFERENCE DOCUMENTS: 705.12
91edbafd-3d3a-5330-b625-69b99e47e353 | note | INSPECTION/TEST METHOD: Visual Inspection
763c8c0e-ad48-54b6-a4a8-847d00234f53 | note | RECORD OF CONFORMITY: ITP Signed
4c0e2b27-56b6-5428-a210-fbd01e13f551 | note | IP
53a8f420-7cd2-5a15-a272-e88ec95a38f0 | note | RESPONSIBILITY: Site Enginer
6a8ab350-7c49-5b59-bcde-fbd6f71d3b77 | textbox | Date Completed:
2bc10911-acba-46cd-aa85-c9111f16e938 | checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
e8a225b3-54ab-56b1-b6e0-90897cdf71e7 | note | FREQUENCY: Each Pit
5b007cdb-2c4f-514f-ad6b-7439453ee0d2 | note | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
1562ba21-c5be-5a1b-a18d-7db8d39eb95a | note | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
cf64d8cc-9d3b-5c83-8958-84b200761a43 | note | INSPECTION/TEST METHOD: Visual Inspection
3d3aca9c-7533-5341-b452-596c48b99515 | note | RECORD OF CONFORMITY: ITP Signed
d70166c0-6b1b-500c-90d9-0d1533990b87 | note | IP
ca1be696-a212-5c70-ab61-881f51be952e | note | RESPONSIBILITY: Site Enginer
a37caaf7-0813-5426-8dcd-06c48b435b66 | textbox | Date Completed:
4ba1239f-8b50-4d6f-886c-2e539a9794f9 | checkpoint | 2.17 Place pit covers
b586c935-9dc5-53d0-95b8-a97251b147b3 | note | FREQUENCY: Each Pit
60d8dd64-ca4b-5d8d-bd43-f755014a14b7 | note | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
df53eef0-366d-5422-866d-d0ea09fc2c80 | note | REFERENCE DOCUMENTS: 705.17 CoM Standard Pit Lid Drawing
4d6e0276-e85a-532c-a7f8-5abd021f9817 | note | INSPECTION/TEST METHOD: Visual Inspection
3cb59741-a937-5a57-af51-884000d87edf | note | RECORD OF CONFORMITY: ITP Signed
078b17b5-67e3-5cfb-ae34-975ca3e6b99f | note | IP
1a519f48-0876-52bd-9a7a-7f54e79bc21c | note | RESPONSIBILITY: Site Engineer / Site Foreman
6d2ea2cd-a5ba-540a-9c35-5aaf08c2c3cc | textbox | Date Completed:
9429e9eb-2a86-4ed6-8091-95a61c949277 | section | Testing & Completion
fe662d78-eefa-49e1-8176-73d06a129dcf | checkpoint | 3.1 CCTV inspection
f72cd569-6dc5-5f54-b0c6-5a8f5ec4a554 | note | FREQUENCY: each lot
27011924-d770-5bf9-908c-3d3d8224f8e1 | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
add7eb3d-c150-5348-9650-0ab14f6c54ec | note | REFERENCE DOCUMENTS: 701.3
31ca62dd-4efd-529e-98e5-ae4e7f28c4df | note | INSPECTION/TEST METHOD: Visual inspection
bcc98648-2e6e-5418-beeb-76851effbe7f | note | RECORD OF CONFORMITY: CCTV Report
8c8be53b-15e7-5262-ab92-518d351cf192 | note | HP
3974634d-0096-55d1-b8e4-f6a8e393a0b3 | note | RESPONSIBILITY: Site Engineer/ Superintendent
16458dd4-9de4-5ad6-b678-d1ded09262af | textbox | Date Completed:
bc1bb271-78ba-4cbf-9f8e-85a63a5cf735 | signoff | AUTHORITY HOLDPOINT
d445c9ed-f193-41bd-bc8e-698de3f54541 | checkpoint | 3.2 Flushing of pipes
98685103-23e1-536d-924f-9dbcf1558a61 | note | FREQUENCY: Each line
ccb402fd-71cb-5ed9-94cc-c95df559f477 | note | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
7e5fea62-d51a-53bb-9953-57d12005d3c5 | note | REFERENCE DOCUMENTS: 701.28
da2c8c6e-c5d5-5629-927c-752520c55d04 | note | INSPECTION/TEST METHOD: Verify
a5637eb2-60e0-569c-93fe-53f38153dfeb | note | RECORD OF CONFORMITY: ITP Signed
f19da8e4-4c90-5f9c-a477-c15a339259cd | note | IP
c826be5f-3624-56b9-9d4f-dedc055d50f7 | note | RESPONSIBILITY: Site Engineer
84b0ebd5-5c2a-5d04-99c4-bd806f46ef87 | textbox | Date Completed:
f94f3bbe-f149-4fad-8de1-59f9938cca0c | checklist | ITP-036 - Kerb Access Ramp Bluestone Footpath | itp | ITP-036 - Kerb Access Ramp Bluestone Footpath
bf7dd50f-fe9a-4082-bf74-a84baf4c6672 | section | Preliminary Works
0e7958a6-15a4-4ded-a945-a2e79ea011ae | checkpoint | 1.1 Check for Correct Documentation
8a8cfb45-5c02-5533-a151-891b51c2051b | note | FREQUENCY: Prior to Commencing Activity
0d881a93-29d0-50d7-bd13-211fc45796c6 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
da4405a8-a1a8-5848-9490-6d925ecf86af | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
0b9c8c9e-8bfd-56c2-a173-0112dff4ee39 | note | INSPECTION/TEST METHOD: Visual Inspection
eab662d5-11b8-57fd-98f1-61a7918d71cc | note | RECORD OF CONFORMITY: This ITP Signed off
1c857771-4bd4-5130-bfe8-fed9d0dd196a | note | HP*
dd967a7b-2953-5808-8442-d23f689c0191 | note | RESPONSIBILITY: Fulton Hogan Engineer
68cbf4a6-f936-5f5d-bda1-16d7a26a9b8b | textbox | Date Completed:
c95a22d1-5bfa-4da3-a42c-c919f28d0df0 | checkpoint | 1.2 Implementation of all measures and controls
17da48fd-5ba1-54b3-bd72-329f3a8ff3ae | note | FREQUENCY: Prior to Commencing Activity
d89ca9e8-67e8-53be-b56e-365799ab114d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
cbc99d3a-22ac-557f-9491-74866ceaca23 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
72bb8ee6-7d81-5379-b150-545d39c4a8f9 | note | INSPECTION/TEST METHOD: Inspection
ec1f32e1-b70a-5f21-83a4-0307f1e5813a | note | RECORD OF CONFORMITY: This ITP Signed off
5c17b802-1964-527a-a1dc-7dd949760799 | note | HP*
b6438844-17ff-5209-845d-b645e8e67b33 | note | RESPONSIBILITY: Fulton Hogan Engineer
3a7a6975-1635-5de8-863d-d1a1d1869c1f | textbox | Date Completed:
0607a73a-77ea-4b40-9baa-6c0fc892310e | checkpoint | 1.3 Existing Bluestone Kerb Demolition
23832d0d-ce60-50fd-9021-728a43047fc4 | note | FREQUENCY: Each Lot
8eb344ef-b6b5-53fe-9e20-e2aac5298ff8 | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
0a7c90a9-98ac-5695-a3e3-3c5ffba12118 | note | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
1ad31bf7-2585-547a-8ab1-4ba85254e2e0 | note | ○ Bluestone shall be salvaged and re-used in new kerb alignment where possible
007afe97-4daf-54b3-bbd0-5bb5d9b6e66a | note | REFERENCE DOCUMENTS: Work Procedure
234a9a51-b23c-5078-bda3-0814387466c9 | note | INSPECTION/TEST METHOD: Inspection
0541ca08-c3ec-5fb3-bcc4-5b301432d1cd | note | RECORD OF CONFORMITY: This ITP Signed off
a4d0fcf3-e7ef-506d-b7f5-603a86858f8f | note | IP
4d92391e-632d-5aee-ad72-3dd1bb594bf9 | note | RESPONSIBILITY: Fulton Hogan Engineer
b19f3142-3be8-5046-8e38-ee3dccf4fee4 | textbox | Date Completed:
99e98cf2-dfc3-4d6d-a7ad-8040ce1ce857 | checkpoint | 1.4 Check Materials
9865df0d-8863-5633-a09e-998df9dc65f1 | note | FREQUENCY: Prior to Commencing Activity
78b600b8-2a91-584a-95d9-8cdeedb82b21 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
9d18a7e2-0995-5135-b683-e26d924579b0 | note | REFERENCE DOCUMENTS: Receivable Inspection List
dd9998d4-c917-53a9-9c52-ba529703db8c | note | INSPECTION/TEST METHOD: Visual Inspection
3c17bb1a-ed7d-5b6e-a1c8-0c7f6a45fa2c | note | RECORD OF CONFORMITY: This ITP Signed off
53ffe7eb-5035-559c-80fb-90050defb7e3 | note | IP
079829fd-9f0c-50bb-966e-3fcc1d3f1802 | note | RESPONSIBILITY: Fulton Hogan Engineer
699d3c21-eb2b-5d35-bd82-6239ccf9b87e | textbox | Date Completed:
49b00e14-ef7a-49d3-aa18-089e8174036d | checkpoint | 1.5 Setting out
e3086f16-bfda-5051-a146-22222da24ba6 | note | FREQUENCY: Each Lot
eaad1767-d21a-5c8d-a7a6-98125f4c6b23 | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
ecb7f916-295e-5f7c-9dc4-e467fcb4d76b | note | ○ Line and level of bluestone pavers, tactiles and inlay shall be set out according to design levels to suit new kerb heights.
970ed600-20cf-5bbc-94e1-d75b619c4bbb | note | REFERENCE DOCUMENTS: Work Procedure
9103723f-1edf-52d1-bb16-c09eb8b6ce00 | note | INSPECTION/TEST METHOD: Inspection
f2a84a33-8887-5586-a81b-e0274f401ddd | note | RECORD OF CONFORMITY: This ITP Signed off
55274919-bf5b-5869-9d82-0fb9d713449a | note | HP*
b7336792-3312-5b16-807d-264c8a9b87f6 | note | RESPONSIBILITY: Fulton Hogan Engineer
081ec050-fdc3-5294-bb31-ce5d609be61a | textbox | Date Completed:
a3ac38a7-42b6-4d22-bd74-f1a84b857665 | section | Construction of Access Ramp Bluestone Footpath
951b1b9b-1e9d-441a-9d8d-3c4c197f9d3c | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
e903a0b3-385e-5288-8480-4bd9d88a776c | note | FREQUENCY: Each Lot
407d8674-5135-53b5-a0d1-445a3dd49c28 | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels.
5c9e8eb6-193c-540c-acdf-bd9acb86314f | note | ○ Bluestone kerb shall be placed on a bed of low slump, 20 Mpa concrete of 75mm minimum thickness.
e0678ff0-5719-5716-98ae-f5d6fab9eef7 | note | REFERENCE DOCUMENTS: IFC Drawings, CoM Bluestone Paving Specification
b02be26f-63ab-5c76-a9a9-4d52e815ff3e | note | INSPECTION/TEST METHOD: Visual Inspection
d5edae5a-8052-5f03-9e28-6b014e454648 | note | RECORD OF CONFORMITY: This ITP Signed off
5c93e2b9-a31d-5caf-bd18-4b7bdc0b49c3 | note | IP
f5b8fdf9-12dd-5fcf-8ce6-0d79c98ee194 | note | RESPONSIBILITY: Fulton Hogan Engineer
3378d1d4-f918-5d49-85b9-5e615aebca20 | textbox | Date Completed:
76e88c38-cc08-4b29-aad9-223b3ae512a8 | checkpoint | 2.1 Base preparation
f0ab0b09-68d8-5d54-b783-3e12cb11a380 | note | FREQUENCY: Each lot
9883aee6-e539-5b31-a07d-c6d860308fda | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign materials and water pooling
303d8b0a-5732-5931-af64-c4dabb3b53a8 | note | ○ After placing and vibration, the concrete shall be screeded and trowelled to the correct level.
2fde9bef-a2db-5948-85d4-ff0bf83efd2f | note | REFERENCE DOCUMENTS: CoM Bluestone Paving Specification
2d4ecfd6-f588-543d-9cfe-73b751059d27 | note | INSPECTION/TEST METHOD: Visual Inspection
eeb89573-248c-5055-a090-1a20b7b3a178 | note | RECORD OF CONFORMITY: This ITP signed off
b46dc71d-11b8-51dc-a226-dfe4c793b13d | note | IP
27ea7758-01a6-58f7-b668-68cba7882654 | note | RESPONSIBILITY: Fulton Hogan Engineer
dcadf245-42af-5ea4-85b8-45f6f31ea6d4 | textbox | Date Completed:
971cfbb9-954d-46eb-ac7c-96f3cc9a8e8a | checkpoint | 2.3 Mortar Bed
9d6e71dc-6133-50c0-85bd-ccc02b57d02b | note | FREQUENCY: Each lot
a33f1055-46c4-5a5d-aa27-50e1acdfcd42 | note | ACCEPTANCE CRITERIA: Mortar shall be applied at average thickness of 30mm to concrete base
3d8fa325-39a6-567d-b1d5-7dec6eabda1b | note | ○ All pavers shall be coated in mortar slurry on rear face before laying
f4e55af7-1678-5870-b389-3eb437a6302f | note | REFERENCE DOCUMENTS: Dwg 1P50201
df095495-f76e-5b67-9e6a-f005f542e3f9 | note | INSPECTION/TEST METHOD: Visual Inspection
800a9e82-1c6c-5ff4-8a90-1e8fba850f96 | note | RECORD OF CONFORMITY: This ITP Signed off
568b8163-8b7b-58e8-8ffa-08db9276e828 | note | IP
2681ff67-2f34-5851-9002-fe048b8a8543 | note | RESPONSIBILITY: Fulton Hogan Engineer
dc7716c4-4965-5389-af05-44714221b587 | textbox | Date Completed:
067a2d9d-0e7d-4675-9b7d-47552fac9101 | checkpoint | 2.5 Cutting of Pavers
f7262d68-7615-5a02-a6f6-0fb1ad5ab0d6 | note | FREQUENCY: Each lot
74a4c607-3296-56d7-91ff-4e4223db03d0 | note | ACCEPTANCE CRITERIA: Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
01690855-49f5-5d66-ac4a-fd9fff9062bd | note | REFERENCE DOCUMENTS: Manufacturers Specifications
5fba9a38-0528-51f2-bab0-5a979edb7c95 | note | INSPECTION/TEST METHOD: Visual Inspection
66d815d2-ebe4-5e0c-9186-65280452318d | note | RECORD OF CONFORMITY: This ITP Signed off
26efe85a-cdb0-51f3-96d3-3d20e8e89048 | note | IP
3d2f49a9-4c1f-5dc8-9bcb-6cca0be19592 | note | RESPONSIBILITY: Fulton Hogan Engineer
b046e005-9062-5e33-9bec-1f48e68a3081 | textbox | Date Completed:
361b5bdf-90e0-46d2-82ed-11f1856107ff | checkpoint | 2.6 Placement of bluestone pavers
720f7b34-c76a-54c7-bed8-d6c72b10c582 | note | FREQUENCY: Each lot
39018aeb-4bb1-5548-a20d-94c00ca47721 | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402.
9b6751b6-77dc-5015-b99e-6c5cb5b4e9ba | note | ○ Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8.
fcf76c38-0b2c-5f56-b6c6-52422c5bc28b | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
70030947-a0b5-54a4-b7f3-a593708c1acf | note | INSPECTION/TEST METHOD: Visual Inspection
479a9448-b08e-551c-933b-4676885114b3 | note | RECORD OF CONFORMITY: This ITP Signed off
660a2c81-cdb1-54b7-8296-6d615b6b53f9 | note | HP*
f92c47ad-25a3-5302-a732-f0b3aea7dee2 | note | RESPONSIBILITY: Fulton Hogan Engineer
df118c27-957a-5c67-bfbf-ad1c6f2eb289 | textbox | Date Completed:
91f52a58-4d25-46be-896a-c5ab75c5210c | checkpoint | 2.7 Curing
3ba80ac1-7918-5251-ac35-12742d9b3370 | note | FREQUENCY: Each lot
c2a588ca-6f44-50f7-98c9-29516f02cbc9 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic
d753d0b3-14c1-568e-a02d-1dc9014c52ba | note | ○ Where required, ply shall be laid over area of works
156aaff8-4897-5a79-9de1-02da582093f0 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
e4405564-900b-5e8f-a831-126e99f639ea | note | INSPECTION/TEST METHOD: Visual Inspection
00a32dae-8b58-5f15-80cc-e07e0fb7d387 | note | RECORD OF CONFORMITY: This ITP Signed off
1b2b855d-9aeb-5b81-9c07-de3e0038ebd5 | note | IP
cb303d4c-c43c-54e3-a584-db2b733b4cee | note | RESPONSIBILITY: Fulton Hogan Engineer
a35da1ce-a658-5af3-8b0e-c2f2c506de9e | textbox | Date Completed:
12798008-35d1-479a-a549-dcc01aee8048 | checkpoint | 2.8 Grouting
3443ed88-7e11-5920-b0b7-a1d00dc1db42 | note | FREQUENCY: Each lot
5202cc16-e16d-5d7e-840e-b3e79f804d6d | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using agreed colour and mixture
24fdb5f0-fc9c-55b9-a4bc-e6ac06d97a86 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
1de98c85-ae01-5faa-a9f9-1b0a41413890 | note | INSPECTION/TEST METHOD: Visual Inspection
41e155e1-d2a4-5b52-8bb2-339250df6658 | note | RECORD OF CONFORMITY: This ITP Signed off
a09417a4-aae4-5925-a375-553c89f34b35 | note | IP
08d9547d-38b4-533e-9906-c2b95209f74d | note | RESPONSIBILITY: Fulton Hogan Engineer
5a1f52f6-d898-517a-9edd-f12f533f3255 | textbox | Date Completed:
a6f8df0f-4f7d-4ce6-bb6d-8bd8ca2bdf83 | checkpoint | 2.9 Installation of Versatac Granite Tactiles and Granite Inlay
e744d73c-e46d-5a9e-a93b-2d459a9b7692 | note | FREQUENCY: Each Lot
4e9fb267-75b9-5738-b8e7-fe648dcd4eb2 | note | ACCEPTANCE CRITERIA: Tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201.
ae1464da-8b76-5703-9547-6575a33016ef | note | REFERENCE DOCUMENTS: Dwg 1P50201
044161d1-a51d-5fec-8745-dca565e8504e | note | INSPECTION/TEST METHOD: Verify
b6a551b1-ccf6-5a3d-9f9d-83dd8e50ad2b | note | RECORD OF CONFORMITY: This ITP Signed off
f09868f6-590e-5097-bbcd-cc4edf6127dc | note | IP
5be7d890-c443-5e80-bcfe-510565899db7 | note | RESPONSIBILITY: Fulton Hogan Engineer
6082025b-4067-5755-b60e-08124a60fcd8 | textbox | Date Completed:
978dad7a-8ee2-4a1b-9f98-0ad5212390d1 | section | Completion
8ac6d0db-3803-4021-831e-c9e1aada5f7a | checkpoint | 4.1 Completion
8000eb25-971e-594a-b5d4-c20139e206f3 | note | FREQUENCY: Each lot
7a2dbd16-dd85-5281-9047-fb82a92104f4 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste
42676efe-8fa9-5f6c-b9c7-41d2c6b3fca2 | note | ○ Bluestone pavement is free of mortar stains and cleaned to satisfaction
d2aa1af3-ccda-5291-9ea8-e8a27dc0fe34 | note | REFERENCE DOCUMENTS: Visual Inspection
d77b51ed-cea3-5022-9aa9-2e65c48892dc | note | INSPECTION/TEST METHOD: Visual Inspection
78eebfb0-354c-575f-a778-e44e33fb880a | note | RECORD OF CONFORMITY: This ITP Signed off
17f63461-40fb-5e54-ad8a-0fc07c4c3b75 | note | IP
5dc90668-beef-5861-9d7e-ab856613fe46 | note | RESPONSIBILITY: Fulton Hogan Engineer
a538ee3c-59b4-5c67-b291-0fbac8fdd91f | textbox | Date Completed:
0e48c8ff-616c-4cfd-ab41-51b4f37314d6 | checkpoint | Final Inspection
be738e92-2b6c-533c-a3f4-df0a872b84f2 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
60b39f2b-bdfc-5c60-9dfd-3bfaae337231 | textbox | Print Name:
17e79732-7369-53e3-b20f-979ac8028725 | textbox | Position:
8f5b6027-6557-5b9c-86be-e9ae1266ffe7 | textbox | Date: