## Master List Templates
Id | Type | Name | Values | Prompting Name
ecaed04e-332b-4e70-8e7d-0d34d827131e | checklist | ITP-005 -Track Drains |  | ITP-005 -Track Drains
eac7f392-1c24-451e-bef2-a2ace5255a3b | section | Preliminary Works
f2051218-07ec-40f1-b3ca-1d75662d25ce | checkpoint | 1.1 Check for correct documentation
9e719214-6f4c-522a-a6cd-8392c44ccdb9 | note | FREQUENCY: Prior to commencing any activity
139d3e82-c1be-5d58-8955-208cf82d45a6 | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwarded to the superintendent
8f2a61a5-b312-5f92-8888-1b93eb7e5495 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
86c0aaa8-b18d-50b5-8605-5514dd478421 | note | INSPECTION/TEST METHOD: Visual inspection
86e70454-672b-53a3-8ed7-3869e180b07a | note | RECORD OF CONFORMITY: This ITP signed off
47ad83f4-0d5e-550a-b12d-bdf6ac4668c5 | note | HP*
44c17bdc-3d8a-5b41-8d12-6f82fb650741 | note | RESPONSIBILITY: Fulton Hogan Engineer
7c64b342-81bb-5d5d-b737-3664f9ccfe76 | textbox | Date Completed:
0f8b0809-12b8-4d9d-aa84-9c6f757c5bfd | checkpoint | 1.3 Materials Check
201b920b-fff7-53fb-a870-f2e6543c6a66 | note | FREQUENCY: Prior to commencing any activity
1b3ccf73-4750-56ad-84be-0170f69ad3b9 | note | ACCEPTANCE CRITERIA: Ensure drainage pipes are of correct classification and are without damage Check triangle drains are of adequate quality, and are design according Ri57A rail profile Ensure lid and j-bolts being used are in accordance with STD T9022
503fc156-3cab-59f1-aa1b-be63ee508c71 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A STD T9020 STD T9022
62c931ab-d295-583c-983f-44dd2009f59d | note | INSPECTION/TEST METHOD: Visual inspection Inspection Checklist
2cb56583-da6b-5213-9c22-b0c108412b4e | note | RECORD OF CONFORMITY: This ITP signed off Receivable Inspection Checklist
58d8df27-e9ff-5bfa-aa47-909e3008f527 | note | HP*
9d48d4d1-305c-57c6-ae7f-418261af225e | note | RESPONSIBILITY: Fulton Hogan Engineer
c613a3e8-8884-51fe-87c4-51d2ef2ada77 | textbox | Date Completed:
6b955491-33fa-4d74-bd51-491f6c27398a | checkpoint | 1.4 Bedding Sand
be7f4aa8-56d6-5470-b0ee-e2088df95052 | note | FREQUENCY: Prior to commencing any activity
0a61d9ee-c190-52d9-bfdb-20b31ec4de3b | note | ACCEPTANCE CRITERIA: The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following: Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities, Consisting of hard durable particles, and well graded.
12b85dcc-a727-5564-b1ca-04242d428bff | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
49d72c40-2574-5953-88aa-67494223445a | note | INSPECTION/TEST METHOD: Visual inspection
17698916-737c-595e-8736-0cf94fd3fc2a | note | RECORD OF CONFORMITY: This ITP signed off
f26b99bc-fcd7-5ad0-9536-25fae0c2836b | note | HP*
dcf78e96-d86b-5266-bdc7-61bb5d8b69dc | note | RESPONSIBILITY: Fulton Hogan Engineer
5b343919-49cc-5fbd-ba3b-98d52a0c3281 | textbox | Date Completed:
d1d4e554-e4fe-4411-91de-96068a99e672 | section | Construction Works
2c85e9c6-3137-4630-ba3c-e1dde5464374 | checkpoint | 2.1 Set out drainage
caaae469-153e-5cc3-acef-277af5c4474d | note | FREQUENCY: Prior to commencing any activity
ad9c3afa-56dd-5492-8e71-aaf93898aaa0 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent Track drain locations are to be identified and based off IFC drawings and sections.
9a68a058-3867-5080-9914-5aa1bbdf7b21 | note | REFERENCE DOCUMENTS: Design Drawings and Register
064b1ee0-969a-5c23-8298-a379df9fc504 | note | INSPECTION/TEST METHOD: Visual inspection
245db1aa-66ed-5cac-983d-38884a4e574c | note | RECORD OF CONFORMITY: This ITP signed off
425074ba-d042-5055-8167-1925612e9994 | note | HP*
bb1dbb91-5f3d-507d-aaad-1e4bfc4cf12d | note | RESPONSIBILITY: Fulton Hogan Engineer
01db7acf-86c9-5424-848b-934d6dbea948 | textbox | Date Completed:
86ddaf8d-b21d-4bce-89b3-0207d2e63957 | checkpoint | 2.2 Excavation (pipes)
bf991b72-e9f5-5704-ab45-3b2270b14b48 | note | FREQUENCY: Each Trench
7141dcb5-2981-53f6-bcdc-c847bc298ee6 | note | ACCEPTANCE CRITERIA: Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
0005575c-c604-5029-8a8e-a710b26761a6 | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
298cb14e-25f3-5992-b46e-cff5236cfceb | note | INSPECTION/TEST METHOD: Visual Inspection
34067c0e-3af7-5e54-8198-2bfb5e571e8b | note | RECORD OF CONFORMITY: This ITP signed off
049e91f2-9006-573a-b4d9-3522339d240d | note | IP
400cdc14-1eb5-5cdb-b30b-abdc5b532723 | note | RESPONSIBILITY: Fulton Hogan Engineer
e53e65d6-3f8c-5b04-9f51-3fb137c6a005 | textbox | Date Completed:
ceae9883-25a2-462b-ac45-ab3d538284f5 | checkpoint | 2.3 Bedding
73c9f0d8-b0bb-5508-81fc-60e8ae3c0a0f | note | FREQUENCY: Each lot
b2ce27e0-5219-5f2d-b51f-57e4b990dd9d | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
7f2bc204-3460-5ca9-bcda-a544d15b1647 | note | REFERENCE DOCUMENTS: STD T9021A
0687c0d7-ff21-519f-8601-7c9730189f4e | note | INSPECTION/TEST METHOD: Visual inspection
a2edf9f4-6b0c-5c5b-9eba-b35fd6d744bc | note | RECORD OF CONFORMITY: This ITP signed off
ad361632-a777-5d09-bc13-2b473ab9bef6 | note | IP
c32c9e71-a5da-5238-8370-7f0395f44ee7 | note | RESPONSIBILITY: Fulton Hogan Engineer
fd377ac5-3462-58d7-9325-b7c7059a283e | textbox | Date Completed:
038769a5-34f1-4317-9f47-f4cbcb11d8f1 | checkpoint | 2.4 Joining
a94f0cdc-9b05-5d9b-a208-2de8953bacac | note | FREQUENCY: Each lot
79f92300-c431-5b2d-880b-2d0916abf8dc | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends. UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
4b4afdd1-c36b-54d7-8dc5-1fcad749e3f4 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
a5b02335-b8ab-5e24-ae7a-edabbf4aa38c | note | INSPECTION/TEST METHOD: Verify
e3c9e811-2635-515f-b699-d5f5f7fc6df6 | note | RECORD OF CONFORMITY: This ITP signed off
0a1eb945-08ac-5d4d-8419-b374df341353 | note | IP
b7ee8190-0104-5e7d-9f61-fe91f31e1f6a | note | RESPONSIBILITY: Fulton Hogan Engineer
bcdf340a-0c97-5499-bcf1-73c35e1d851c | textbox | Date Completed:
7404b6b8-f380-44b6-8893-86e9ae3d5771 | checkpoint | 2.5 Track Drain Installation
bcb9e419-0c30-58e2-a589-911be6f63c8a | note | FREQUENCY: Each Lot
60775f54-b8b5-5e44-9f11-378cdc08e3fb | note | ACCEPTANCE CRITERIA: Track drains shall be welded to designated positions, and cleaned of all weld splatter . Weld shall be sealed after installation Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
af44239c-bc5a-5595-8463-f5e0465063f1 | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
17397136-4493-5a90-863b-4cc6073c7c5a | note | INSPECTION/TEST METHOD: Visual inspection
40d3ddd1-703b-5466-8cc0-e9748af75f69 | note | RECORD OF CONFORMITY: This ITP signed off
7712113a-ee3e-5cc8-ae7d-fc28660963f4 | note | IP
cff7c239-1375-5488-889d-acbc26e26f4a | note | RESPONSIBILITY: Fulton Hogan Engineer
04e22a8e-dbe6-5ea4-af6c-61d4fa3f8460 | textbox | Date Completed:
85285304-8566-4134-a131-ff0b566340b7 | checkpoint | 2.6 Points Drainage
fbd7ddc6-4b76-5d56-939b-a9497f761e8b | note | FREQUENCY: Where required
4fccfa6e-7221-5447-a2aa-4b4ffe8e22a7 | note | ACCEPTANCE CRITERIA: The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit. Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
8e137636-5107-5c62-8a9b-b5840eaa00b6 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304 STD T0305
fc87165e-8a07-53a6-a3a0-a3c04a4b3b6a | note | INSPECTION/TEST METHOD: Visual inspection
6d521cb0-cc98-5d40-b5de-d8192ef268ad | note | RECORD OF CONFORMITY: This ITP signed off
8e64e7f8-a85b-5db2-9a34-6f6d5a717f80 | note | IP
aef69ae8-9e63-59b0-a6f4-2a0837003fd7 | note | RESPONSIBILITY: Fulton Hogan Engineer
62b33a48-1ead-5979-b570-1158f4a4ff71 | textbox | Date Completed:
3a851b00-e731-45bc-84ec-31257adfb249 | checkpoint | 2.7 Concrete Pour
b0f20b78-72e1-5c15-b42c-20412d0cdc86 | note | FREQUENCY: Each Lot
5b83efcd-c52c-5e90-a3ce-8e2e42be8687 | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
a91e4d76-8c95-5912-a0e3-137ceaad966d | note | REFERENCE DOCUMENTS: STD T9021A
ba9b49a0-0288-577a-a42d-1ba812e56b5f | note | INSPECTION/TEST METHOD: Visual inspection
7de4930a-a1f4-5d1c-9d6e-829361583ee6 | note | RECORD OF CONFORMITY: This ITP Signed off
5d59bb42-4d3c-573a-97bf-b143f9e147d1 | note | IP
20ca46b3-6049-5f3c-8e6b-06ff285f9fd4 | note | RESPONSIBILITY: Fulton Hogan Engineer
635780ce-b909-5130-b541-a1e26f8c15fd | textbox | Date Completed:
8d012a0c-1f5e-4070-be78-d5e006f4ff97 | checkpoint | 2.8 Connection to local drainage
305ef7df-44af-5943-a00a-71b7279fa183 | note | FREQUENCY: Each Lot
cd115ee8-3add-5d8f-abd0-e570dc7d2a7e | note | ACCEPTANCE CRITERIA: Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority. The minimum pipe size shall be 150 mm.
cae01919-f869-5ebc-8777-eca12e7fe323 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
d79f1177-d76d-50df-8fd4-49977bd413b3 | note | INSPECTION/TEST METHOD: Visual inspection
2ac641e7-770a-5b33-9f41-0431d6fd0644 | note | RECORD OF CONFORMITY: This ITP Signed off
6bda4e3c-2d2e-584e-bb67-b8d1c8e77017 | note | IP
8c4fc595-790b-578a-aefc-5aaedb4a854c | note | RESPONSIBILITY: Fulton Hogan Engineer
087dcad1-d2f7-503d-971e-45f7e1db9f50 | textbox | Date Completed:
81b2f811-b347-4215-b94a-a67a53782d71 | checkpoint | Final Inspection
1bbceff5-f8d0-58c7-b622-91d67342ba2a | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
9cb10ab5-7b2a-5756-b173-077872aa5869 | textbox | Print Name:
23931154-332b-5613-8fa5-5dee83d1ee32 | textbox | Position:
965abdee-ad61-53de-b310-88c0839c6fad | textbox | Date:
ef9adb73-4025-4c46-b76c-9fd74476ae5e | checklist | ITP-009 - Site Survey |  | ITP-009 - Site Survey
27d38ee6-7096-4ac2-a0d6-39853269658e | section | Preliminary Works
958b804e-2684-4468-bef7-5939180f8782 | checkpoint | 1.1 Check for Correct Documentation
ff6ace04-9922-546d-8976-3e06dc5ee2bc | note | FREQUENCY: Prior to Commencing Any Activities
60129060-88e2-5013-8ff1-448c1ec17ca0 | note | ACCEPTANCE CRITERIA: •Ensure that all employees and subcontractors are using the most current and updated complete set of drawings
7e1bbb17-09b5-58ee-9024-bdacb5168d9f | note | REFERENCE DOCUMENTS: Design Drawings and Registers
27c69a3f-4567-5811-9a9a-1ba7e2999558 | note | INSPECTION/TEST METHOD: Visual Inspection
2ac2d28a-8b83-52ef-b5be-fa191013505c | note | RECORD OF CONFORMITY: This ITP Signed off
db8480bc-a597-58b1-ae1a-7d8acc0c0eaf | note | WP
86a70e5d-98c3-5dbd-899d-ce9e77937000 | note | RESPONSIBILITY: Fulton Hogan Engineer
a70d21b5-cceb-550f-99e4-646b8b8f1d95 | textbox | Date Completed:
56b8f698-22bf-46ac-b13d-32951dafca24 | checkpoint | 1.2 Implementation of All Measures and Controls
c1cd39ed-c47a-52fe-a314-dd4a369c79ec | note | FREQUENCY: Prior to Commencing Any Activities
6d5ea1cf-06f6-5c57-b5b8-f3207b68b1a3 | note | ACCEPTANCE CRITERIA: •All necessary measures and controls are implemented, including: SWMS, WP, TMP, EMP, PSP, PMP and QMP
4ea6ee31-211b-5fae-8c7e-810064e214c8 | note | REFERENCE DOCUMENTS: SWMS, WP, TMP, EMP, PSP, PMP, QMP
eeeb9014-3641-5e03-8e56-9c325ea6864b | note | INSPECTION/TEST METHOD: Visual Inspection
93a08f4a-41db-5d26-9b1c-074ef7b7133b | note | RECORD OF CONFORMITY: This ITP Signed off
457921e1-5219-50d8-b6ac-2c6a5ba3527b | note | WP
2715a98e-dabf-5342-869e-0f7b86f95ea3 | note | RESPONSIBILITY: Fulton Hogan Engineer
3796228a-6e73-5600-a5f7-4c947e7d597b | textbox | Date Completed:
71c9df2a-1cf5-4f55-8898-1ace8a255d20 | checkpoint | 1.3 Confirmation of Design Drawings
c7766e33-6cdd-5013-8390-2fc8e141e342 | note | FREQUENCY: Prior to construction activities
a013b26a-5341-5d88-ba78-08a90af967bd | note | ACCEPTANCE CRITERIA: •Surveyor shall validate RL points, kerb, pavement, platform and track dimensions, measurements and levels specified in design drawings based on bench marks and control points specified by superintendent •Superintendent shall be made aware of any discrepancy between design and actual values
eaac8b96-084a-5bfc-8db4-a9e45c241dbc | note | REFERENCE DOCUMENTS: Design Drawings and Registers TS 1313 cl4.2.5
45ceb344-1bf8-51c6-bbd2-cc90944c93dc | note | INSPECTION/TEST METHOD: Verify
02128d6e-618d-5b72-8cd3-1312eb548425 | note | RECORD OF CONFORMITY: This ITP Signed off
8258a5dc-8b3f-59a2-babe-f33d1c7b54e3 | note | HP*
1a5ed7b3-c3c0-57e0-909b-b79c474ee4ac | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
77e89f07-c37c-526e-bf0c-1b3d9533fe77 | textbox | Date Completed:
2febd351-12b5-4af4-94d9-e341bfecfdee | section | Construction Works
89ec485e-d888-469f-917f-68e738907db4 | checkpoint | 2.1 Set Out
778ed5bc-3017-55e6-8370-02eab34ce32a | note | FREQUENCY: Prior to start
33a63fee-2847-533c-8538-c54a0e862ef7 | note | ACCEPTANCE CRITERIA: •Tramway track shall be set out to an accuracy of +/- 3mm, based on bench marks and control points specified by superintendent design drawings
8cb9ba7e-ae21-5a6e-ab91-a8a6a83a3a84 | note | REFERENCE DOCUMENTS: VRIOGS 005.2 Pt1 cl4.0
d521a8f7-4b42-5d8f-ae67-8b95f357bdac | note | INSPECTION/TEST METHOD: Visual Inspection
a87a3f09-3a2b-517c-a64f-ec2e70d8e8cb | note | RECORD OF CONFORMITY: This ITP Signed off
4fa5fdf7-337d-5206-9e00-016933d7a618 | note | IP
bbe692c8-b801-5f56-b645-89e7afdcb770 | note | RESPONSIBILITY: Fulton Hogan Engineer
ce0de9f7-cfba-505f-8584-8eda970eb2b5 | textbox | Date Completed:
2d9a987b-76a2-4856-a98a-cb2bc7586075 | checkpoint | Final Inspection
05f25f34-af5e-594a-a75b-bf1401819c15 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f66262ef-f319-5007-b503-3ead941c7393 | textbox | Print Name:
6591a265-f154-5da5-81e1-8318aa7efc4a | textbox | Position:
6cc3d668-f717-5684-9642-64a5624e2de5 | textbox | Date:
d03f0845-e8cd-47ce-8852-ec86c20aece8 | checklist | ITP-010 - Kirby Welding |  | ITP-010 - Kirby Welding
6ce9e30f-12bc-45cd-9aa0-c09a091c93be | section | Preliminary Works
051f4121-146b-4d86-a108-0be9f86526f4 | checkpoint | 1.1 Check for Correct Documentation
c4135c7d-f290-5049-9631-86d7201e6f4e | note | FREQUENCY: Prior to Commencing Works
ad3b879e-b855-5f56-99a8-13b7e096f41e | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
cdeef963-9471-5f44-8d02-c41b531e3b95 | note | REFERENCE DOCUMENTS: Design Drawings and Register
6de449b4-fb10-5b05-ba4e-a4bc02977b0d | note | INSPECTION/TEST METHOD: Visual Inspection
e50a247c-39a1-553f-848b-0bc66b04ddb4 | note | RECORD OF CONFORMITY: This ITP Signed Off
7e8acf33-25ec-5d0d-8ab1-4c24fce13230 | note | HP*
1d0ca30a-a16f-5f72-b401-a7e636a607eb | note | RESPONSIBILITY: Fulton Hogan Engineer
149c0676-5a9d-5ea8-8273-bf05c5cd6d91 | textbox | Date Completed:
5771f382-d89a-4d14-8e9a-82b6b134021a | checkpoint | 1.2 Welders Qualifications
cfb90772-86e5-541b-8d67-8450eec546ad | note | FREQUENCY: Prior to Commencing Works
f0cce697-1374-5bd6-a950-64e893efa9f7 | note | ACCEPTANCE CRITERIA: Welders shall be trained and qualified for the brand and each type of weld used, e.g. standard gap, long preheat, short preheat, junction etc. Certification shall be provided to and approved by the Superintendent prior to commencement of welding.
00207a98-7ecd-567e-a888-429e8b150190 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C
e77cd084-179f-5674-80ad-e016b96493e2 | note | INSPECTION/TEST METHOD: Verify
fb3c56d2-4f35-5a76-92c1-abccbc18a108 | note | RECORD OF CONFORMITY: This ITP Signed Off
b3f2a0ec-bccc-5d29-8524-816665c1a93d | note | HP*
bb4df4b9-0bd1-5566-ad93-64848a82cf41 | note | RESPONSIBILITY: Fulton Hogan Engineer
afedd8f0-9aa0-59c2-bdc0-e76b2a2bce6d | textbox | Date Completed:
41f3b9be-f7da-43c2-a73f-9d4d28c8b696 | section | Construction Works
b5c2963f-0605-4e1d-84e4-1495201687ff | checkpoint | 2.1 Cutting Rail Ends
f0722c4e-e6e1-5b5c-8e14-f8e50ecf0147 | note | FREQUENCY: Each Weld
4be6dc8d-0666-59b9-a64c-b141b5d6d5b2 | note | ACCEPTANCE CRITERIA: Rail ends shall be saw or friction cut. The cut ends of each rail shall permit butting of the rail heads to within 1 mm across the full head of the rail. The prepared surfaces shall be visually inspected for cracks and reground if any are detected.
11c1640d-f60c-521a-874f-0753f7e36699 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.4.6 & Appendix C
b90a7230-d04d-5b1a-af0c-cda3a6b0cbac | note | INSPECTION/TEST METHOD: Inspect
7a36dbbc-db97-5c81-92f1-bb67330c58b5 | note | RECORD OF CONFORMITY: This ITP Signed Off
0276a335-eec4-5fa7-b0fb-8aff26bedec4 | note | IP
49f547d0-fe16-5599-9c9b-f8ddd084b264 | note | RESPONSIBILITY: Fulton Hogan Engineer
b0b63861-3f55-5156-9a67-7b630c849482 | textbox | Date Completed:
57b8639d-0bc6-431b-b2b3-14a40a05da14 | checkpoint | 2.2 Butting and Aligning Rail Ends
2efc677b-d2d8-5702-8dd5-e3fba854c8af | note | FREQUENCY: Each Weld
8baaaf2a-f69c-5243-9ecb-c8bc6eeed8a9 | note | ACCEPTANCE CRITERIA: Rail ends to be welded shall be butted together as closely as possible, preferably with no gap between rail heads. Care shall be taken to ensure that the rails are not pulled together excessively, forcing the feet of the two rails together and producing a peaked or high joint. Rail ends shall be butted and aligned, and assembled with base plate and spacer blocks, if applicable, prior to commencement of pre-heating.
5f96e2fb-6888-5aec-835e-ca46b76ed0c2 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
8ee5942f-e4c7-5a25-8e84-b5b57ff757e8 | note | INSPECTION/TEST METHOD: Inspect
0e1d7fcb-ce36-5f6d-b1b1-3bbdb179c93f | note | RECORD OF CONFORMITY: This ITP Signed Off
e2fa2f17-147b-52e6-b391-4064b5de6f17 | note | IP
36bd4369-06f9-5086-b685-6d1d3d11623e | note | RESPONSIBILITY: Fulton Hogan Engineer
002c4ff9-619b-5084-81ee-fbf05e1795ab | textbox | Date Completed:
cb88010c-b72e-4a28-85f6-9e8491681ac0 | checkpoint | 2.3 Preheating
6c62c2fe-d42a-5a9e-97d9-5572beb6a080 | note | FREQUENCY: Each Weld
b3eb1232-aea8-57cd-acd3-35420a2a38cf | note | ACCEPTANCE CRITERIA: A correctly adjusted, suitable oxy-LPG pre-heating torch shall be used. The preheating torch shall not be applied closer than 30 mm to the rails being pre-heated. Both sides of each rail end shall be evenly pre-heated from the rail ends to150 mm beyond the rail ends. Pre-heating shall be confined to the top surface of the foot of each rail and to half the height of the web. Preheating shall be such that during welding, the foot and web of the rail shall be at a temperature of between 270°C and 350°C
1a4a7a41-ba0f-5204-8017-19d83a96b559 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C
4da2f7ab-9e37-50d4-a862-0f5800769bb9 | note | INSPECTION/TEST METHOD: Inspect
94b02f7c-a747-567d-bc47-3b7fae7de6ce | note | RECORD OF CONFORMITY: This ITP Signed Off
6d9288b0-3412-55c3-9cf7-0344e447054b | note | IP
67418c94-9042-54f6-a518-feb429ea44be | note | RESPONSIBILITY: Fulton Hogan Engineer
81132e57-781b-5205-bf2a-cbcff8314f5d | textbox | Date Completed:
adf58520-86c4-47d1-a243-43a5f4a40ec7 | checkpoint | 2.4 Welding
8f4cc3d2-a15a-518b-9b41-956740ad4ca5 | note | FREQUENCY: Each Weld
1829aff1-1535-5897-8776-d50c66b5017a | note | ACCEPTANCE CRITERIA: Rails and components shall be clamped in position prior to welding. Welding of the joint shall be carried out as a continuous operation. A disruption to the procedure may require additional preheating. All weld ends shall be welded using an overlapping back welding technique over the weld for a minimum length of 20 mm to ensure that all craters are fully filled to the full cross section of the weld.
90fcbbc0-3804-5730-879c-5e8247854d51 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.9 & Appendix C
d9d08cf6-bbca-52d4-b0ea-fab0a1821a3c | note | INSPECTION/TEST METHOD: Verify
332d1979-a0c6-5e73-b709-32ed40318008 | note | RECORD OF CONFORMITY: This ITP Signed Off
b8e0de61-3036-5ade-ac71-a095d76dcdb8 | note | IP
962774ca-7607-56dd-b744-5c514ceaa794 | note | RESPONSIBILITY: Fulton Hogan Engineer
95e02d87-edb1-5bae-8a44-6801b27caa5e | textbox | Date Completed:
caf878d5-2a10-48be-96e6-cc7c32c804a6 | checkpoint | 2.5 Cooling Weld
be7c2430-8121-519c-9176-0d2b514e2c14 | note | FREQUENCY: Each Weld
744989a2-860a-5d48-96a8-2048873e0cf9 | note | ACCEPTANCE CRITERIA: The welded rails shall not be permitted to cool rapidly. Heat blankets shall be used to cover the welded portions of rails (i.e. web and foot on each side of the rail ends. The blankets shall extend a minimum distance of 300 mm beyond the extremities of the welds, i.e. minimum length 900 mm. The heat blanket shall remain in place for a minimum period of 15 minutes after completion of welding.
6a7e27bb-4680-55ad-9d4e-18db254b5370 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.9 & Appendix C
d4390b9d-dc49-54e2-8556-48dc7ff14243 | note | INSPECTION/TEST METHOD: Verify
7f204b56-e8eb-5c93-8177-83f965714724 | note | RECORD OF CONFORMITY: This ITP Signed Off
877bc161-443b-5464-92f0-4387635bf43f | note | IP
8b5d4aa0-58c0-53d1-8b4a-0356b18cb3e0 | note | RESPONSIBILITY: Fulton Hogan Engineer
f72a56f2-77ec-5891-a3a6-f12777ca2c82 | textbox | Date Completed:
c027ee32-7767-46d8-8976-f32f7b3be326 | checkpoint | 2.6 Grinding Weld
b6cbf54e-f1f9-51d9-9946-db15e1d8b585 | note | FREQUENCY: Each Weld
8464a60e-9d86-552f-bba3-7641318a691a | note | ACCEPTANCE CRITERIA: Grinding of the rail head, as applicable, shall be performed only after the rail head has cooled to below 50°C. A rail profile grinder shall be used to grind the rail head weld. A spindle (straight) or disc grinder shall be used to grind the rail check and groove. A 1 m straight edge shall be used while grinding the rail head (wheel running surfaces) to ensure a good straight surface and profile.
7175a633-6788-56ea-ae7e-681b0b57f0f2 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
8a597317-5d3c-5c47-8278-e7d90f64d1c6 | note | INSPECTION/TEST METHOD: Verify
3a4815cb-1c4b-51e4-8933-360072aacf19 | note | RECORD OF CONFORMITY: This ITP Signed Off
d975281f-616d-58b9-8e9d-7fbd653604c3 | note | IP
4e0d9898-d90d-578f-8a71-994e8fc98f2c | note | RESPONSIBILITY: Fulton Hogan Engineer
24c64d01-6b5b-5492-bd39-0e568e1209bc | textbox | Date Completed:
34d1791a-5010-4168-aa9d-ce9e84763fab | checkpoint | 2.7 Flushness of joints
3f8312d4-d8cf-5673-a90b-129972d94155 | note | FREQUENCY: Each Weld
84cb6a30-8bc8-50e2-94a7-9da79d06186b | note | ACCEPTANCE CRITERIA: Misalignment of rail heads on the running and gauge surfaces, due to different amounts of rail wear, shall be rectified by grinding. The slope of transition shall not be greater than 1:25. Misalignments of the groove and check not exceeding 3mm shall be rectified by grinding. The slope in transition shall not be greater than 1:10. Any grinding required to make joints flush shall extend to 500 mm each side of the joint
1ac262bc-c6fd-5c9f-aa4c-6c6cea28f828 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
a38b15e8-6693-5608-b52d-ed696ee3a8f2 | note | INSPECTION/TEST METHOD: Verify
59fedffe-b35e-5351-b462-3c69579240fa | note | RECORD OF CONFORMITY: This ITP Signed Off
b9bd3c31-63d9-57fb-82f0-a9190eccca59 | note | IP
c8e29fbd-a43a-536d-8cf1-15c4eb9f61d8 | note | RESPONSIBILITY: Fulton Hogan Engineer
be68efcf-f874-5b48-9ae0-5c03472fd780 | textbox | Date Completed:
6f153477-065b-4671-ac37-2cb8a80467f3 | section | Testing
d9408c89-b47c-4bf2-886c-b4e43a7be02b | checkpoint | 3.1 Weld Review
99a7f5de-dbd8-56ed-9ff7-d183c46bf2d6 | note | FREQUENCY: Each Weld
6676ea1b-79f1-5b7b-8d15-49bc1a1b226e | note | ACCEPTANCE CRITERIA: All welds shall be inspected by the Superintendent & Fulton Hogan Engineer; Unsatisfactory welds shall be cut out and replaced
4fe24971-21f1-584c-b853-e2bbc77dc753 | note | REFERENCE DOCUMENTS: Works Procedure
6540be9c-be9a-52ba-99c2-fd6a965fe788 | note | INSPECTION/TEST METHOD: Inspection
b2a6ae53-e3d5-5de0-94b8-a79ff9ff6ff5 | note | RECORD OF CONFORMITY: This ITP Signed Off
59dd73a0-f399-5e16-9eee-167b3970abd4 | note | TP
2004bc84-3009-5664-9660-1e39b03304ec | note | RESPONSIBILITY: Fulton Hogan Engineer
8ba95dd6-8f3b-5aa9-a18b-7502d08d0c08 | textbox | Date Completed:
1222cb7a-e022-4002-a00a-6b6987c55519 | checklist | ITP-012 - Signage Installation |  | ITP-012 - Signage Installation
a3504402-fb6e-4be1-9968-c9e4dc246c89 | section | Preliminary Works
59218fd9-56ec-447b-b971-319d8263f4f4 | checkpoint | 1.1 Check for correct documentation
5b55b167-d026-501c-8827-496e53cc2c99 | note | FREQUENCY: Prior to commencing any activity
a2bbe5c2-e40a-516b-8d6a-5bd338064f3d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
1dc872bc-603e-5c1f-8c2c-51ab396f3a31 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
d047aa87-a871-54e9-bba3-fbcef3254131 | note | INSPECTION/TEST METHOD: Visual inspection
997f144a-5452-5f6a-8496-46a3f5935a99 | note | RECORD OF CONFORMITY: This ITP signed off
c3ff9d1e-afe6-57f5-9f09-5fb7c9914da2 | note | WP
073c5a2e-9218-5b2e-a926-e7f0815dc495 | note | RESPONSIBILITY: Fulton Hogan Engineer
c246c574-34b4-5aa5-a1a4-0af831e4032f | textbox | Date Completed:
5a9a42c2-574c-49dc-8407-3a1c7c2b823b | checkpoint | 1.2 Implementation of all measures and controls
54d00be6-a510-5435-b05f-ef3b2bf18253 | note | FREQUENCY: Prior to commencing any activity
4451c61c-67b3-5309-bf9d-998b0a8153ee | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
0b24013b-7218-5674-a8b9-d5ddb4ec8cf1 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
35e74f4f-00d5-55c2-9ea8-9fae5c02b358 | note | INSPECTION/TEST METHOD: Visual Inspection
514978bb-6d92-5132-952c-f741fcb0a156 | note | RECORD OF CONFORMITY: This ITP signed off
7a686923-c73a-549b-9038-134e6f733e96 | note | WP
b580089b-ab1a-5576-97b1-86c2a82b4eb3 | note | RESPONSIBILITY: Fulton Hogan Engineer
f1adc6a5-3426-5078-a2f6-954f75314887 | textbox | Date Completed:
ff943067-b05f-430d-86e6-77d43279198e | checkpoint | 1.3 Signage Conformance
d6dfd112-7563-53ee-8ee0-b15d67538f0e | note | FREQUENCY: Before commencement of activity
757d46d8-9e93-5d69-9982-0547b32395a6 | note | ACCEPTANCE CRITERIA: Ensure sign size and image correspond with contract drawings and meets specification
838ef221-7600-57a7-b5e1-afc9721a8221 | note | REFERENCE DOCUMENTS: Drawings AS 1742
da6f0f2a-80a0-563f-8197-093ca535beff | note | INSPECTION/TEST METHOD: Verify
c710acb3-4ef5-50a4-bc63-aa4dd73fad7b | note | RECORD OF CONFORMITY: This ITP signed off
67ffedcb-e52d-5de5-a61d-17ed98f0fc0b | note | WP
2ea98616-5bd9-5484-ade0-860f258b5af3 | note | RESPONSIBILITY: Fulton Hogan Engineer
1aa05846-88a1-5db5-90f4-a3d91d1d4b5f | textbox | Date Completed:
f315cbe4-cfac-4c52-88c4-b0f5a40eb144 | checkpoint | 1.4 Service Identification
d3a40923-9164-54e3-a8be-1127e62894e4 | note | FREQUENCY: Prior to start
2859eaec-d183-5b60-abbb-1971ffaa4507 | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
4921dd9e-fc81-5235-ae02-d9a75879af53 | note | REFERENCE DOCUMENTS: DBYD
a2ca2c7c-6e74-529d-bb4c-98bc0c8513e1 | note | INSPECTION/TEST METHOD: Verify
96810005-6e0c-525b-a740-d4dd959435c5 | note | RECORD OF CONFORMITY: This ITP signed off
0165270b-667e-509e-95e9-15923e4bcebd | note | WP
9c78692b-6fd9-5653-b8ff-89ef15177f05 | note | RESPONSIBILITY: Fulton Hogan Engineer
8548e621-9ed6-5bc4-b52b-76359d87bf4c | textbox | Date Completed:
0442a90f-cd5e-4d48-8c8f-757f335c94a5 | section | Construction Works
f12adca8-db8f-4b1d-a87c-2799d8dc3816 | checkpoint | 2.1 Setting Out
490ef352-e2bb-5f23-82af-bc35fd975863 | note | FREQUENCY: Prior to start
d5c39923-eaa4-5bf7-8cf3-2cf39be4afb2 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
2d32d08c-77e3-5317-84f7-3323793b1ca4 | note | REFERENCE DOCUMENTS: Drawings
23e504d8-7158-531e-b6ed-55efe689fe60 | note | INSPECTION/TEST METHOD: Visual Inspection
2c7080b6-372e-554e-9702-97060ba4aa2e | note | RECORD OF CONFORMITY: This ITP signed off
91388a12-4cce-5e5f-9587-6e06242aaa5a | note | IP
8be419db-8384-5fc3-8b32-6e7c7b0259d6 | note | RESPONSIBILITY: Fulton Hogan Engineer
edd7d644-0a85-5a17-b369-a046513845d9 | textbox | Date Completed:
1c3cbc98-4927-40b4-ae31-81834e3636be | checkpoint | 2.2 Signage Install
001a8804-fc11-5e93-8de4-fad871ab7dba | note | FREQUENCY: Each Sign
8ce4d4de-dfc4-54f5-844b-cbae46592b04 | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position. Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
89cc30a2-29cb-55e3-a273-89117f2ed837 | note | REFERENCE DOCUMENTS: AS 1472 TS 1313 Drawings
399a2021-dcae-51db-8557-991ba0b867d8 | note | INSPECTION/TEST METHOD: Verify
c0eb98ee-56f6-53ea-a83a-8398da7e20fd | note | RECORD OF CONFORMITY: This ITP signed off
8ad17730-f3f4-5e2e-9204-44480e88a5f3 | note | WP
54413ac4-6ccd-5ddb-8472-611ddfaed9dd | note | RESPONSIBILITY: Fulton Hogan Engineer
7e44db39-f4a0-54c0-a2d2-e71983c52afd | textbox | Date Completed:
44b3c2fa-3d72-4db4-b802-56e8a2427706 | checkpoint | Final Inspection
a044ca53-f4b0-5c8d-acdc-77469c77b6a4 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
9fe4154e-b069-5888-9cfe-afd49da76428 | textbox | Print Name:
c90e1941-725a-5840-a525-5d9b21ac2cde | textbox | Position:
89a9edd3-9241-5394-bab0-064c79dd5fee | textbox | Date:
aaa6dbf5-cf25-4126-9ef5-dd082805c45c | checklist | ITP-014 - Bluestone Kerb Installation (MCC) |  | ITP-014 - Bluestone Kerb Installation (MCC)
2823aaee-1362-4792-93f9-179a7c3f7d3b | section | Preliminary Works
7c0e8567-8c47-48d5-99d9-faceb15a0103 | checkpoint | 1.1 Check for Correct Documentation
88036de9-7ada-5464-85b7-b679c7e3891e | note | FREQUENCY: Prior to Commencing Activity
b2e6c174-701c-571c-b0a8-4c8e5c56b2d5 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
38302d59-ddc4-595f-ba4a-9b2aa8397ce4 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
751797ce-b577-5ce9-b69a-db4d45c15c41 | note | INSPECTION/TEST METHOD: Visual Inspection
cce78733-5588-50de-be57-50ac3789ce18 | note | RECORD OF CONFORMITY: This ITP Signed off
49c3a646-1df9-5add-8228-e5d47f6900e5 | note | HP*
de51f12c-4f08-5e02-9e77-a6f4f6da252b | note | RESPONSIBILITY: Fulton Hogan Engineer
34bbfe26-e321-57c4-90a9-ee8b55c5af20 | textbox | Date Completed:
7320f1d3-a27f-43e8-b34f-de1de9ba4123 | checkpoint | 1.2 Implementation of all measures and controls
361113f3-84fb-5b87-82eb-4c9b21544828 | note | FREQUENCY: Prior to Commencing Activity
708cbc8d-fb46-5a50-8943-1ba09fae27d4 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
cb7fb956-6921-5cba-8bb0-d65aa8d29927 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
413db448-f729-5032-9a80-1b844c1929e6 | note | INSPECTION/TEST METHOD: Inspection
f8d6e1f3-caa6-5ddb-9083-dddb67d69860 | note | RECORD OF CONFORMITY: This ITP Signed off
a8bde62d-497b-5cb1-8435-e3534d0c440c | note | HP*
640d0896-6e76-57fb-8c09-feb4c2d5739b | note | RESPONSIBILITY: Fulton Hogan Engineer
3be7282b-72d7-5eea-a59c-f62a599a390c | textbox | Date Completed:
1a1d61a1-7b17-420d-a14d-96fbb268e9b9 | checkpoint | 1.3 Existing Bluestone Kerb Demolition
30f6f458-e137-5c4d-ade4-8e5225257661 | note | FREQUENCY: Each Lot
da606d4e-055f-5ae7-b652-9ffe5331fb9c | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone Bluestone shall be salvaged and re-used in new kerb alignment
1fefcf1c-4ea7-5dd8-9efe-86247802a13a | note | REFERENCE DOCUMENTS: Work Procedure
9bc7bbd8-778b-5f1a-9ab6-6c20bea90c83 | note | INSPECTION/TEST METHOD: Inspection
0e67b9b0-15e3-588d-ae43-daf61b8c28b1 | note | RECORD OF CONFORMITY: This ITP Signed off
3d0bc8eb-1a34-5568-b4f3-d7d925a16179 | note | IP
c848906e-758c-5263-9434-5e814428b2fd | note | RESPONSIBILITY: Fulton Hogan Engineer
a95c0d53-c25d-5a5f-9e7f-5f054228c9aa | textbox | Date Completed:
312baa09-c14c-46dd-b295-5e2f3e9df60c | checkpoint | 1.4 Setting out
e94980ea-8d29-5e02-a6a0-30f13f375372 | note | FREQUENCY: Each Lot
61ee84b1-729f-59e5-b4da-db59ee653aa8 | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans Alignment of new kerb shall be marked out using string line
bd4ed746-87f7-5573-8073-bacccf93399c | note | REFERENCE DOCUMENTS: Work Procedure
e092313f-9c6b-5af0-ae07-0f46fdfecaea | note | INSPECTION/TEST METHOD: Inspection
fb78a4dd-1947-5d6e-a3cd-4bea09650435 | note | RECORD OF CONFORMITY: This ITP Signed off
13a0e05e-4387-5bad-a8d9-05172c62f96c | note | HP*
b05f8309-8deb-513a-bdee-00a2142f20cf | note | RESPONSIBILITY: Fulton Hogan Engineer
5fad23b2-527d-5612-8adf-b6bc51511eb9 | textbox | Date Completed:
25305b7f-a4e6-4531-90d0-9e9052aef347 | section | Construction Works
d0ad7f30-7d55-4deb-884f-6b6bd19c96f3 | checkpoint | 2.1 Saw cut (if required)
39fe1332-6f05-5e21-9b2e-90531da2a94f | note | FREQUENCY: Each Lot
4ec90fa0-ffcf-5cd2-b47b-6f4803974f8d | note | ACCEPTANCE CRITERIA: Saw cuts shall be made to the following depth for existing asphalt pavements: - Footpath: Minimum 75mm - Roadway: Minimum 125mm Excavate to allow for design heights
e80053f8-492f-5662-9dac-00c4639e56c2 | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 2.0
72df02b5-bb95-5570-b8c3-139f6d3fe936 | note | INSPECTION/TEST METHOD: Visual Inspection
76eb9fca-68a7-5293-8af1-1a93d2a83d5b | note | RECORD OF CONFORMITY: This ITP Signed off
a0fe31b6-91e3-5672-a873-89c2c6cd34be | note | IP
45e26502-b55a-5cdc-9a97-831f2d38e4f4 | note | RESPONSIBILITY: Fulton Hogan Engineer
64f30b8f-88f7-5211-b601-10d285f7b784 | textbox | Date Completed:
212cca58-f25d-47b4-9b81-14f7530aa2e2 | checkpoint | 2.2 Concrete Placement and Setting
6e95ae52-be72-5a0b-8eef-b049d61dd8e3 | note | FREQUENCY: Each Lot
a87ba097-ef71-583f-abdc-d0a38e48478d | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar
c3e08ea0-0658-5c7c-b288-4102345d0539 | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
2b762a49-fcca-50c4-b0cf-331c84caa425 | note | INSPECTION/TEST METHOD: Visual Inspection
c667295e-304e-5fd2-9e6c-288ca9711e32 | note | RECORD OF CONFORMITY: This ITP Signed off
f03124bc-f0d7-523a-9869-5c5379157a30 | note | IP
3b4bc136-1efc-5027-8758-29ac8be0e860 | note | RESPONSIBILITY: Fulton Hogan Engineer
f068f975-84e8-579d-9fd2-e5f0875c84f2 | textbox | Date Completed:
fbfe8fae-f22f-494c-9467-f696f9ae5a78 | checkpoint | 2.3 Mortar Mix
c2488668-22fd-54ca-bd7d-193b1fe5e30b | note | FREQUENCY: Each Lot
ce510f21-dff7-5b9f-99f2-66203e047cbe | note | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following: - 16% cement - 16% stonedust - 67% blended wash sand - 1% lime ready mix grout
d8ac4772-aa1a-5987-81e8-a436bc6ccc95 | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 4 AS 3972 CoM SD 1P 50406
c38262b9-795b-5af8-a5ab-d60fd99d0737 | note | INSPECTION/TEST METHOD: Verify
c3bcea6d-e6bd-55ba-b97d-bec4ed7f55d9 | note | RECORD OF CONFORMITY: This ITP Signed off
599fbdb7-2358-5e0f-a086-cc445fe77c3c | note | IP
0ebbcf15-296b-5d56-bd33-73951a8bb5e6 | note | RESPONSIBILITY: Fulton Hogan Engineer
2db6f630-19e1-558d-a142-dd1bc8fabfad | textbox | Date Completed:
7f422229-6fbe-415d-9265-be7d128b6f38 | checkpoint | Final Inspection
b5c507e6-a4d8-502c-9ba2-49e49291973d | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
21b0693a-3131-59aa-9377-735d5461a9ea | textbox | Print Name:
438dd459-8e7d-5a2e-80cc-7e6f23da0581 | textbox | Position:
956ef8a0-e733-59a2-bd30-02ac69ebb754 | textbox | Date:
c363c2e6-1b72-4efc-aacc-74b399d8031c | checklist | ITP-015 - Energy Absorbing Bollards |  | ITP-015 - Energy Absorbing Bollards
e172fd22-06cb-44ba-8172-b884fd33bfe2 | section | Preliminary Works
36af9d91-ee2e-4bad-b057-7e9ed21d4953 | checkpoint | 1.1 Check for Correct Documentation
9f4f69df-d072-5720-bce3-18d43ae69cc8 | note | FREQUENCY: Prior to Commencing any Activity
1d44aacb-ef88-5260-aef7-c196b15acf73 | note | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
f351a2fb-d004-56f1-bca4-0da3b9ad82ea | note | REFERENCE DOCUMENTS: Design Drawings and Register
0aa4c29f-3be2-50b3-b4c8-f8a4b36afd58 | note | INSPECTION/TEST METHOD: Visual Inspection
efdfe11a-9fb4-51eb-87bc-3df25a98e36d | note | RECORD OF CONFORMITY: This ITP signed off
9b72c6e9-1439-5aee-af89-7847f77b83da | note | HP*
233b1c24-0237-5b79-a574-55e4e7d0900e | note | RESPONSIBILITY: Fulton Hogan Engineer
d5237858-faa4-5dc4-948d-d487d64d946a | textbox | Date Completed:
75824eca-e856-4de3-83ff-0d1a349ccaf2 | checkpoint | 1.2 Implementation of all measures and controls
38b41293-ac5b-58af-aae7-5eaf7571a213 | note | FREQUENCY: Prior to Commencing any Activity
5b764db0-ba0b-5269-8f66-edb9836a1604 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
dd875f2a-fe79-552e-90ba-d3109a820ad8 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
503b4015-7efc-5282-a49b-1e12122f2dfb | note | INSPECTION/TEST METHOD: Visual Inspection
aae83b35-00ab-5779-9504-be57d00e846a | note | RECORD OF CONFORMITY: This ITP signed off
a82a5ae0-a06a-5b9d-9d99-cba2ab3a83ad | note | IP
57439984-5d45-5a2a-8935-af9daebfdf9b | note | RESPONSIBILITY: Fulton Hogan Engineer
d82630c6-39b4-5301-ad86-05c5be65a069 | textbox | Date Completed:
f9a5c7d5-fee2-42cd-b7df-1f9b646d67ce | checkpoint | 1.3 Service Proving
310b8360-2283-58d5-bc5b-4ad38a579b8b | note | FREQUENCY: Prior to Commencing any Activity
659eb53a-0546-5c1d-a74c-fc192fb9a18c | note | ACCEPTANCE CRITERIA: Service locating shall be conducted in form of DBYD and service location
51d6886c-9b3e-5dc9-b52f-703e66043ddc | note | REFERENCE DOCUMENTS: DBYD Service Locator
3da7bbb6-5e16-5375-b114-91ca50519bc8 | note | INSPECTION/TEST METHOD: Verify
0ab53de5-6821-599f-9446-0092238049b2 | note | RECORD OF CONFORMITY: This ITP signed off
a6c79647-ce42-5a78-af67-068648b758d2 | note | HP*
8a3681c6-be37-5594-bc57-0cb2b085355f | note | RESPONSIBILITY: Fulton Hogan Engineer
18477a0a-3d4c-5baf-8b89-40b59560cc37 | textbox | Date Completed:
13be9a81-02f4-4ccd-a262-57793fbe58d6 | checkpoint | 1.4 Excavation Permit
540277f4-580d-595d-a8d1-18229d3536f9 | note | FREQUENCY: Prior to Commencing any Activity
c5cc9e19-28cd-5dce-93d0-60a790e6d11c | note | ACCEPTANCE CRITERIA: Ensure excavation permit has been obtained for the specified tasks
af6bca3d-8ce3-56d7-bc5b-9ed38a087347 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
dc4883ba-38a4-5b69-b6bb-a9ba7784ba17 | note | INSPECTION/TEST METHOD: Visual Inspection
bdd2fca9-92f7-5a0b-89b0-50d8be919953 | note | RECORD OF CONFORMITY: This ITP signed off
d8d8b0d9-f291-5832-be15-0b2dac49a5a9 | note | HP*
9ed95b37-6804-5a34-afa0-194134e0f1cc | note | RESPONSIBILITY: Fulton Hogan Engineer
ffa8b8dc-8600-538a-bcaf-e62c629b380c | textbox | Date Completed:
26848522-0c60-4e59-8c27-9e19938b02e7 | checkpoint | 1.5 Materials
b13102e7-4d36-5218-923a-5c11c326ba75 | note | FREQUENCY: Prior to Commencing any Activity
593d62ec-a13c-5915-bd08-06521e2e41d4 | note | ACCEPTANCE CRITERIA: All materials shall comply as per technical specification Ensure materials are not damaged
72fa504b-f5e3-549a-8332-0e4ddad1618a | note | REFERENCE DOCUMENTS: ASE TS
089f9c08-bd4a-581f-832e-3a1fea469878 | note | INSPECTION/TEST METHOD: Verify
1f4793b8-f897-55b9-aca5-118aa61d26a6 | note | RECORD OF CONFORMITY: This ITP signed off
e35374a2-214a-576d-84f6-dfea4624de7d | note | IP
11018413-7491-51e1-8546-4527280ab0f4 | note | RESPONSIBILITY: Fulton Hogan Engineer
2acae374-2ff7-5781-beef-698295de090b | textbox | Date Completed:
774823cb-bdec-4943-b97c-4c9a47726737 | checkpoint | 1.6 Setting Out
fea5aac5-e7c2-59e0-a0dd-0736823bae40 | note | FREQUENCY: Prior to Commencing any Activity
af697200-8074-53cd-883c-981d10865b5b | note | ACCEPTANCE CRITERIA: Ensure location of bollards conforms to design drawings Mark hole centre position at location
6d3088ce-4520-5ee4-9dec-0684d335221e | note | REFERENCE DOCUMENTS: ASE TS cl1.1
f506c76e-6b9e-5b39-83cd-873be1a6deb4 | note | INSPECTION/TEST METHOD: Visual Inspection
1e42c83e-a96d-566d-a186-a2e9783dd786 | note | RECORD OF CONFORMITY: This ITP signed off
49f6d2a7-1d57-583d-8af7-9ba7ae117d82 | note | WP
33510672-4bef-5f96-8279-4e56adf14fb9 | note | RESPONSIBILITY: Fulton Hogan Engineer
52b275a4-e79f-55f2-be3f-8491ea1bce0e | textbox | Date Completed:
9b0e8397-283d-493b-ac3c-ac3352b91ac5 | section | Construction Works
8655134f-3589-4149-997e-21c6fd8926ea | checkpoint | 2.1 Excavation
00174762-ad83-5413-812c-8b9ead00993d | note | FREQUENCY: Each lot
370141b6-755e-579f-b616-edadc853d745 | note | ACCEPTANCE CRITERIA: Care shall be taken in excavation Hole shall be minimum 600mm dia and 1000mm in depth
17baf021-ffe4-5760-a160-683bc0b82d8a | note | REFERENCE DOCUMENTS: ASE TS 2.2
569adde8-a081-5db3-81ce-2f577e456ac6 | note | INSPECTION/TEST METHOD: Visual Inspection
cef3e82b-1b36-53bf-b7b7-1b4185ce74ef | note | RECORD OF CONFORMITY: This ITP signed off
7ba44245-6fb6-554f-9899-aa7afefdc168 | note | IP
89ff7549-db8c-5d9c-a4fb-8e5c2c2fbc42 | note | RESPONSIBILITY: Fulton Hogan Engineer
41b8231c-27e4-5398-b35b-5af7e88dab46 | textbox | Date Completed:
2045e5aa-ff2e-429d-b9ec-3b257e810bd2 | checkpoint | 2.2 Placement of block
81780c18-7125-548f-af38-61247c8f6c3b | note | FREQUENCY: Each lot
42567b17-2afb-5ff4-86c1-deb15e6007c8 | note | ACCEPTANCE CRITERIA: Block (brick, wood, foam) shall be placed at hole base Ensure base is supported by solid ground, and block is level
63a81bd0-3717-51c2-abe0-51dfbc5d7c7d | note | REFERENCE DOCUMENTS: ASE TS 3.1
b8366b6e-f659-5039-a335-9c635b7d7903 | note | INSPECTION/TEST METHOD: Visual Inspection
9dafcee9-94fa-5f35-b15d-c5010dba393e | note | RECORD OF CONFORMITY: This ITP signed off
20f050ab-a20f-5965-824f-fca56436b3c0 | note | WP
f2667b32-edfd-5396-9a4a-0bbcb81c2028 | note | RESPONSIBILITY: Fulton Hogan Engineer
e1880d0b-4cc8-5fed-bc5d-319e71fe9e8f | textbox | Date Completed:
a0be6617-409e-4f22-ab8b-134c8baf4246 | checkpoint | 2.3 Installation of Cartridge
3b51db39-f597-57fc-9011-6abf4a4c3233 | note | FREQUENCY: Each lot
66f31a3e-9259-5529-ba32-d592314cda8f | note | ACCEPTANCE CRITERIA: EAB cartridge shall be placed on level block
ad5bf4e1-eaef-5dd2-bde3-53088542a664 | note | REFERENCE DOCUMENTS: ASE TS 4.1
83e9fac4-276c-5f21-8901-1208684807c2 | note | INSPECTION/TEST METHOD: Visual Inspection
51741062-097f-56a1-a03e-5d4c91db5954 | note | RECORD OF CONFORMITY: This ITP signed off
5cdb81ea-bc49-50c2-a48f-c5d7e61c7d9d | note | WP
2c3c11b4-273d-5d5d-9ad4-10795cff31d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
ef580cfb-01d3-5468-a57b-682a50142882 | textbox | Date Completed:
07ba979b-1ff8-47f4-aad9-7e9bc6a5dbdc | checkpoint | 2.4 Pre Pour Checklist
0d45af90-3c30-5030-9619-575a3c2dfc90 | note | FREQUENCY: Each lot
a5ea5f5b-b0e4-517c-b44f-fe4eedc336f6 | note | ACCEPTANCE CRITERIA: Ensure minimum clearances are provided, no foreign materials are present, and EAB cartridge is level
837ab97c-4e35-500d-b482-0a6d55035269 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
7f2a32ec-6f0e-5e71-a1a3-0a168ee13b20 | note | INSPECTION/TEST METHOD: Verify
fb7afaa3-2e52-5ac7-8e0f-1645b6c1c51c | note | RECORD OF CONFORMITY: This ITP signed off
72fc6f3f-adeb-545f-ba34-5d90d58fe230 | note | IP
0a02357a-35c5-5605-9720-298398a04cf6 | note | RESPONSIBILITY: Fulton Hogan Engineer
029f52f6-60c5-556e-83aa-9aead1095319 | textbox | Date Completed:
4dafe5d7-c730-44fb-b28b-75f784334d3e | checkpoint | 2.5 Installation of Concrete
0fa2d619-5293-5fdd-9e0d-d17b46a4c8a3 | note | FREQUENCY: Each lot
c54d81ac-2a54-5aa4-8d0b-60b2e871cc06 | note | ACCEPTANCE CRITERIA: 32MPa concrete shall be placed to cover reinforcement cartridge and fill hole Concrete shall be compacted by use of vibrator If surface pavers are to be used, allow 25mm gap from finished surface Ensure cartridge is level post compaction
ab12431b-8fc6-58e4-88a3-30042e5977f5 | note | REFERENCE DOCUMENTS: ASE TS 4.2
cde6445a-577f-5463-8d3a-f4a05b8b0012 | note | INSPECTION/TEST METHOD: Visual Inspection
7e920cdd-8ee2-5061-9a6f-f52227d0c293 | note | RECORD OF CONFORMITY: This ITP signed off
b8a1e715-2e58-58c0-b79a-ebd6d95c7c27 | note | IP
7920b3b1-9149-5fa5-9dd7-73d8fe2ed545 | note | RESPONSIBILITY: Fulton Hogan Engineer
a54fc4b9-8ed7-5948-ac35-24d297e063d7 | textbox | Date Completed:
b39c109d-3d50-4ab4-9af8-36dcc6944d78 | checkpoint | 2.6 Installation of Bollard
a310f99c-5879-5dec-b737-b189b1d3adf0 | note | FREQUENCY: Each lot
62a59d39-edb9-5d22-8801-e762cdef7b11 | note | ACCEPTANCE CRITERIA: Ensure bollard is installed, and bolts are tightened adequately Concrete, pavers or bitumen shall be finished to specified requirements
313f1b56-8b5c-5ddb-a49f-399a63a99d4b | note | REFERENCE DOCUMENTS: ASE TS 5.2
be9a29a2-b3f0-5911-a802-15d84f418bb0 | note | INSPECTION/TEST METHOD: Verify
b05a7ffb-3323-5830-b1ad-f8d1bb6e864a | note | RECORD OF CONFORMITY: This ITP signed off
44bdfa7f-602e-5d44-b4fa-6cdd8b5c121b | note | IP
c07446a4-7162-5267-a3ea-163668b807cd | note | RESPONSIBILITY: Fulton Hogan Engineer
106a18d8-2d93-5d12-83ed-c6efa7cf83ee | textbox | Date Completed:
f8408594-98b4-4b76-8a4b-7d901849428e | checkpoint | Final Inspection
7ddcd1ca-83e4-5c71-b725-aaaaffb44c48 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f8b1c20a-0f3a-5521-952f-4a1243a20c09 | textbox | Print Name:
2631b7fc-a95b-5d75-98a0-468fcabd2099 | textbox | Position:
dce930d2-37dd-5911-9be8-198c0c293b8e | textbox | Date:
4021f14a-48fd-40a8-acd1-152d16690d08 | checklist | ITP-016 - Platform Bluestone Kerb |  | ITP-016 - Platform Bluestone Kerb
80341959-40c4-4fad-b47a-fe6dbfbb360b | section | Preliminary Works
d0acd62d-23cb-49de-ac05-f87f51002f72 | checkpoint | 1.1 Check for Correct Documentation
a2548de4-5c7a-5e89-9e80-2d7280378a5b | note | FREQUENCY: Prior to Commencing Activity
442d5e1e-9fd7-5e37-950e-55fcffb2e3e1 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
35505b02-60af-5afd-b61f-c19eeca0be5c | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
9143e769-18d4-5f6c-9742-36481ea6b2e9 | note | INSPECTION/TEST METHOD: Visual Inspection
d039153c-c0d3-5735-ae27-aa3fa69c3def | note | RECORD OF CONFORMITY: This ITP Signed off
cb8db0b0-e55a-5f2e-82c4-49ae13dfb24f | note | HP*
d92a7554-2a30-5006-b8cd-62f895881157 | note | RESPONSIBILITY: Fulton Hogan Engineer
5f3928e1-26ac-5600-a0d3-73b3cb60dc66 | textbox | Date Completed:
e62ff21e-031d-4733-8578-51404186517e | checkpoint | 1.2 Implementation of all measures and controls
c5e2b3f9-2965-53b4-afe9-e493d8ee83b8 | note | FREQUENCY: Prior to Commencing Activity
339c9aec-e1bb-5253-9003-1fcc9f709fad | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
ae2f27a8-478f-5fdb-831e-026d28e7e734 | note | REFERENCE DOCUMENTS: Work Procedure
95158c27-b862-561b-8441-97dd15674345 | note | INSPECTION/TEST METHOD: Inspection
65f88381-ca6a-5755-be78-882effa1423e | note | RECORD OF CONFORMITY: This ITP Signed off
b10bd37c-75bf-50f1-80fa-a43a749d7193 | note | HP*
9524b755-9d3a-51fe-8db6-d0b9597ec82d | note | RESPONSIBILITY: Fulton Hogan Engineer
2bdeaf86-1d47-5722-92cf-07d202e7072f | textbox | Date Completed:
b477b789-8f1b-4afe-b7ee-c5b104163247 | checkpoint | 1.3 Check Condition of Material
7eda0ea8-ad97-5b89-a48a-ac656fd4232a | note | FREQUENCY: Prior to Commencing Activity
01105d52-b3ea-5761-bac6-dd3bf03d8c14 | note | ACCEPTANCE CRITERIA: All bluestones shall be inspected at delivery for visible damage
e13af6eb-7611-505a-ba14-ebbdd888c1ad | note | REFERENCE DOCUMENTS: Work Procedure
97b83582-6907-57c5-ba13-67611673cafb | note | INSPECTION/TEST METHOD: Inspection
ddd1b6b9-64a4-57a9-b441-768e51e3d9c9 | note | RECORD OF CONFORMITY: This ITP Signed off
16d40d2b-789b-501e-91e2-f8340e486580 | note | HP*
57bafc94-b97c-5e41-ac88-14aa6fbb2d20 | note | RESPONSIBILITY: Fulton Hogan Engineer
f9519560-6553-52d3-9b60-492c7daaa7ec | textbox | Date Completed:
548eb07d-8904-4aba-aeea-81025079e62e | checkpoint | 1.4 Lifting method
8f3009a4-2edd-52ac-9cfc-1e02160ce34a | note | FREQUENCY: Prior to Commencing Activity
90ae9b66-46f1-561d-8c60-cc54bbc42a1c | note | ACCEPTANCE CRITERIA: Bluestones can be moved with excavator and grabs/slings or with a vacuum lifter.
19893db3-0002-5118-97f8-849c6c5b0194 | note | REFERENCE DOCUMENTS: Work Procedure
78079a0a-a702-5928-8ea7-d349d3bbf6e5 | note | INSPECTION/TEST METHOD: Inspection
3671fafe-1116-51ca-aec6-5cd0297883a3 | note | RECORD OF CONFORMITY: This ITP Signed off
8e112798-fcb7-526b-aaf7-e3c541219a1a | note | HP*
31a022a9-699b-539e-953f-5b9ff456198f | note | RESPONSIBILITY: Fulton Hogan Engineer
934d19c9-41c9-5e6b-89cf-0af21b1ec1b3 | textbox | Date Completed:
81ce272e-1839-481c-a3c0-00f773f4d8b0 | section | Construction Works
6945bfc5-6823-4c3d-ac94-3a548b525cb2 | checkpoint | 2.1 Base Course
df2cdd04-a4f2-5928-90aa-5f8ba780d258 | note | FREQUENCY: Each Lot
43ad9c04-717c-5640-9e39-b678375ddeb9 | note | ACCEPTANCE CRITERIA: Class 2 compacted rock (98% modified density) shall be compacted to 100mm thickness. Soft or areas deemed unsatisfactory shall be removed and rectified
b93b58fa-66ad-5113-b713-91618255027b | note | REFERENCE DOCUMENTS: STD_T6111
d17ce53b-de0e-5ef6-8156-e2ad71292c7c | note | INSPECTION/TEST METHOD: Visual Inspection
c87e6fd0-dbd2-582a-b25e-52cef81b4c75 | note | RECORD OF CONFORMITY: This ITP Signed off
8fc9f920-8b21-5218-8918-f6ae4bc06758 | note | IP
9b7cb503-e4f7-50ea-980b-68dd7e806ccd | note | RESPONSIBILITY: Fulton Hogan Engineer
c701b563-1866-5592-8080-e20fe11ae464 | textbox | Date Completed:
002f722b-4cba-45c0-be4a-9592446b3b85 | checkpoint | 2.2 Concrete Placement
5467dda5-9d09-58f3-994c-9e90fb20cf45 | note | FREQUENCY: Each Lot
633c3079-ee33-503d-bda5-e211bd4afe2a | note | ACCEPTANCE CRITERIA: Bedding shall be >100mm 32MPa concrete with 6mm aggregate
8cf704b0-5737-5005-82da-87683f7dba8e | note | REFERENCE DOCUMENTS: STD_T6111
22ae1d88-2d57-5ffb-a0dc-12b0bef821cc | note | INSPECTION/TEST METHOD: Visual Inspection
8ee73d6e-0397-5c55-a6b2-94596a8eed37 | note | RECORD OF CONFORMITY: This ITP Signed off
1c7213a3-4ccb-56e4-bdbf-2c8d1cb69e83 | note | WP
93fe0ac8-55aa-57b7-93cc-c1bd48321385 | note | RESPONSIBILITY: Fulton Hogan Engineer
8238da5a-c039-5712-a107-b0af0b934838 | textbox | Date Completed:
d483adcc-c504-4c88-b1fd-21132ac600d0 | checkpoint | 2.3 Setting
9fda5c45-e6ec-5194-b171-903831e7b28c | note | FREQUENCY: Each Lot
b2335ecb-db47-5cf5-b465-58de02e444de | note | ACCEPTANCE CRITERIA: Tie rods shall be N12 (300mm long) and chemset 100mm into kerb, 2 per stone. Tie rods shall be installed with bond breaking compound specified by superintendent. Bluestone shall be laid 150mm below finished surface level
09a3f1a2-7d46-55a3-b243-35ca92c6ec67 | note | REFERENCE DOCUMENTS: STD_T6111
7ced3642-be25-5a53-a4ac-ead42286e5b7 | note | INSPECTION/TEST METHOD: Visual Inspection
4a0fafb2-a83e-5d70-b079-9c328f3e7dab | note | RECORD OF CONFORMITY: This ITP Signed off
a440a053-ede6-51ca-bcb2-bb82e3536669 | note | WP
8991cd87-206f-510b-b422-9ead3712fc67 | note | RESPONSIBILITY: Fulton Hogan Engineer
2c20f57c-be04-530d-a1d7-6e2055600b6b | textbox | Date Completed:
0088aed7-4fbe-41c7-a1b6-607df81ce210 | checkpoint | 2.4 Sealant
36b74be9-38aa-507a-8ca2-cf4c8ce5f647 | note | FREQUENCY: Each Lot
1602cc34-fb4d-5d7c-a864-d901185c7167 | note | ACCEPTANCE CRITERIA: Sealant at construction and expansion joints at back of kerb shall be 'Gun Grade THC 900' by Tremco, of black colour. Loose materials shall be removed as not to impair adhesions
7fed2930-1f76-511e-bcf7-a11431289edf | note | REFERENCE DOCUMENTS: Work Procedure
ad95e78f-3348-5e7b-94bd-d4095d4ce5c0 | note | INSPECTION/TEST METHOD: Visual Inspection
3f20adc4-5ada-5913-836b-4ef18b97912d | note | RECORD OF CONFORMITY: This ITP Signed off
2d09d70a-4586-5fbb-b669-26d88b4a706f | note | WP
54dff88f-bc42-5fe7-bec0-0ae5f83772a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
9bc4e390-4e92-59d6-8c5c-0a463a75bdd0 | textbox | Date Completed:
9965b26d-e31e-4414-99fc-c5881786f830 | checkpoint | 2.5 Platform line marking
130986b2-14da-50cb-bff4-ade747cbf2ac | note | FREQUENCY: Each Lot
3eec5748-9193-5020-b042-549c6ad13cbc | note | ACCEPTANCE CRITERIA: 50mm yellow lines shall be placed along the edge of platform, one on the top face and one on the front face of the kerb.
84f0efd7-39e7-5a49-b82e-bf5aaa6524d9 | note | REFERENCE DOCUMENTS: VRIOGS 005.3 Cl 7.9
4fc7bb84-e0b7-5e98-a0d5-d434727ff397 | note | INSPECTION/TEST METHOD: Visual Inspection
bab7fdfa-098f-5f80-aa59-2e6f0aba4996 | note | RECORD OF CONFORMITY: This ITP Signed off
3e2d50fb-91d0-559e-a125-5c4ae5572182 | note | WP
708737ac-7cd0-53d1-9bc7-f40a6c688a79 | note | RESPONSIBILITY: Fulton Hogan Engineer
887c1057-f440-5fe6-adde-27e80ae44a62 | textbox | Date Completed:
05db137c-415f-46a6-a565-031f66e844bc | checkpoint | Final Inspection
9edd7723-aab9-5b7b-9ab2-fb9dcd3b997d | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a4416711-96fb-5d71-972f-2db1cdd0a460 | textbox | Print Name:
61f72a9c-1db5-58d8-9a6c-3d0503e4ee78 | textbox | Position:
4f054cac-e682-539d-b1c0-60ee385087bb | textbox | Date:
e25de9b9-6ed1-4c2a-a425-b5f501e3686f | checklist | ITP-017 - Bluestone Paving Works |  | ITP-017 - Bluestone Paving Works
9c653a61-6004-4a61-9bbb-4d8a22309fb8 | section | Preliminary Works
9630952a-79fe-4e1f-9cc6-6e89fb6e0e94 | checkpoint | 1.1 Check for Correct Documentation
da852508-2839-5929-8d3a-115c3403a5b7 | note | FREQUENCY: Prior to Commencing any Activity
175ddb91-e267-5ba2-be28-7cfbe7335219 | note | ACCEPTANCE CRITERIA: Ensure all employees and subcontractors use all current and complete set of design drawings
ca961dac-661d-5b53-8257-89a892ca0357 | note | REFERENCE DOCUMENTS: Design Drawing and Registers
52a11ca3-ec01-5bcf-916d-cdcf44ae671d | note | INSPECTION/TEST METHOD: Visual Inspection
958f424a-381c-562a-a847-39027df1d2bb | note | RECORD OF CONFORMITY: This ITP Signed off
05940d70-10cc-5a27-ad9c-117ecd33011b | note | HP*
e126a03c-8c52-57cc-85d7-82cf610194d5 | note | RESPONSIBILITY: Fulton Hogan Engineer
ed547ee2-192b-5935-a332-fd88dd9d28fb | textbox | Date Completed:
f9513f63-413d-400d-a3d2-d53624c9ecd4 | checkpoint | 1.2 Implementation of all measures and controls
2b9c722f-1c2f-56fc-9d15-e5b2b9b6d497 | note | FREQUENCY: Prior to Commencing any Activity
c8ac200a-0987-5b1d-b120-8feb1378c5d1 | note | ACCEPTANCE CRITERIA: All necessary measures and controls shall be implemented, including: EMP, PSP, SWMS, TMP and WP
c8e087c6-751b-5797-8b1a-f8e6b9f5d3e7 | note | REFERENCE DOCUMENTS: EMP, TMP, PSP, SWMS, WP
76451bcc-5c01-5fa5-917a-1a5b3fe6e4b7 | note | INSPECTION/TEST METHOD: Visual Inspection
afec54ee-b630-5d42-b8e1-c603131b464c | note | RECORD OF CONFORMITY: This ITP Signed off
4937d070-9cd6-533b-805c-efefed4f7350 | note | HP*
70a5345f-9a59-5716-83c0-5030b411907d | note | RESPONSIBILITY: Fulton Hogan Engineer
5462603a-52ce-5cb9-ade1-2a604faac659 | textbox | Date Completed:
4baad907-dad8-4ec2-bcc8-c04d1f43da28 | checkpoint | 1.3 Check Materials
dbfad4f1-2dfd-58ca-b50b-f0f252b899f2 | note | FREQUENCY: Prior to Commencing any Activity
46d06369-6f5c-5770-82fa-3c8e1848b9fb | note | ACCEPTANCE CRITERIA: Inspect materials for any chips, cracks or other visible damage.
3aa662f4-028e-5782-98ef-724c023ba7ba | note | REFERENCE DOCUMENTS: Receivable Inspection Checklist
4b5b4347-d3cf-50fc-9be4-84f206ea61c1 | note | INSPECTION/TEST METHOD: Visual Inspection
37a4f2b5-14ab-58e5-b21f-4ca972b44f8f | note | RECORD OF CONFORMITY: This ITP Signed off
f8f24a4f-640e-5aa6-9afe-e4601fbb744e | note | HP*
cac8a09a-fecc-5802-9d83-102eb5d5eb12 | note | RESPONSIBILITY: Fulton Hogan Engineer
1eae1869-d569-5563-a1a0-2a57f4797868 | textbox | Date Completed:
f1472b87-ce40-425f-a00a-93773b90d8dd | section | Construction Works
63383330-6a63-4ec5-bec9-5440a10c9b8c | checkpoint | 2.1 Base preparation
8898c624-325f-5e92-b1c9-b9f66f71ca09 | note | FREQUENCY: Each lot
d7ab0d21-2052-5ef3-909c-c34df4663568 | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign materials and water pooling. Formed groove of 10x25mm in concrete face shall be filled with caulk
4c5d05b9-31a1-5b3e-ae76-4930fe1689bd | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
05b291b7-6421-5ef6-860e-99d78f4d0fbb | note | INSPECTION/TEST METHOD: Visual Inspection
d3d3e42f-237d-52c2-a33e-3bd96d253c94 | note | RECORD OF CONFORMITY: This ITP signed off
e3696ee3-363b-5ff4-b6d3-a19f28957d30 | note | WP
966f178a-8783-5942-9ae9-9363d49f46a6 | note | RESPONSIBILITY: Fulton Hogan Engineer
05f855de-b302-507a-9bdd-2573812be780 | textbox | Date Completed:
7c64a3ed-e2a9-49b3-a772-1bbd5c727820 | checkpoint | 2.3 Mortar Bed
40763fe9-0be8-5291-ad39-a68c2c0e71a6 | note | FREQUENCY: Each lot
1c267cc9-af08-5ea7-a52f-7c17403d3f1d | note | ACCEPTANCE CRITERIA: Mortar shall be applied at average thickness of 30mm to concrete base. All pavers shall be coated in mortar slurry on rear face before laying
d9b1b95e-da34-588b-ae56-0c1277258cc6 | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
0bd139bb-837e-5278-a65b-99ae5a854372 | note | INSPECTION/TEST METHOD: Visual Inspection
4ad10e17-0ea0-5752-a148-79591572f173 | note | RECORD OF CONFORMITY: This ITP Signed off
53051dd4-cebe-5d85-86ea-2f05dd295d80 | note | IP
e13db657-5d85-5879-8b70-5683d3e33b95 | note | RESPONSIBILITY: Fulton Hogan Engineer
8b14e489-3743-549c-ade7-443d15e58c7c | textbox | Date Completed:
a1380dcc-d3d6-4699-b47f-cca7e7ed7cba | checkpoint | 2.5 Cutting of Pavers
a3d3bb09-4527-52d2-84be-cbe84e67384e | note | FREQUENCY: Each lot
28ebcb66-d6f9-55c7-953b-825f7dbaa5f4 | note | ACCEPTANCE CRITERIA: Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
98955e67-a02c-5a59-b573-48e7aea516e5 | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
a5b4052f-77b5-50ae-bec9-df5698b39d2a | note | INSPECTION/TEST METHOD: Visual Inspection
72ce4eb5-a640-535e-9b5a-2a37d506d48a | note | RECORD OF CONFORMITY: This ITP Signed off
e4ad5e8e-9513-50f3-bf8e-7fab4c80ad55 | note | IP
86106bf2-0fcc-5965-bf44-0ab5c4633f86 | note | RESPONSIBILITY: Fulton Hogan Engineer
ed5560bb-68d1-5c79-8b9f-dcb64ae77b12 | textbox | Date Completed:
cfe890a3-1b78-4f1d-8ebd-319dfa7c5039 | checkpoint | 2.6 Curing
7eef6d4c-da3c-5469-9ce7-93776e6d82dc | note | FREQUENCY: Each lot
8141e62d-7ea1-5b60-8a4e-fefda6a46dc8 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic. Where required, ply shall be laid over area of works
c58f3e15-c489-5e13-804a-c2971fc08f0e | note | REFERENCE DOCUMENTS: Manufacturers Specifications
c0646f52-78df-5ae3-a893-e58d0d4967d0 | note | INSPECTION/TEST METHOD: Visual Inspection
e4266fb5-61b1-5a2b-8223-9998d11faca1 | note | RECORD OF CONFORMITY: This ITP Signed off
f2c2b2c7-37bf-5282-a020-a5097cb0ccca | note | IP
164e64a9-1e09-5a51-85b2-40f916e462bf | note | RESPONSIBILITY: Fulton Hogan Engineer
b0088dce-e5d6-5bb6-970a-7145ab28a5c5 | textbox | Date Completed:
d561adf7-334e-432f-b4f9-6da169e9b719 | checkpoint | 2.7 Grouting
2bd0ff4b-4353-566a-ac83-a3ff51e03452 | note | FREQUENCY: Each lot
6e8648d0-a067-5891-ab3d-3739adaf5fb8 | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using agreed colour and mixture
a4633d92-7e59-57f4-b214-161f0e47d6c0 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
1cbfa87d-7038-573d-9dcd-60aa305acb5b | note | INSPECTION/TEST METHOD: Visual Inspection
57053a4f-c69e-5334-ac1e-07a494a5b14d | note | RECORD OF CONFORMITY: This ITP Signed off
e163b2d5-6406-5b19-ae05-66ec66490bc9 | note | HP*
367cfa0a-e6ac-585e-9fa8-ac0e93215746 | note | RESPONSIBILITY: Fulton Hogan Engineer
b6adbf9a-c500-5cdc-992c-b64feddbd1fc | textbox | Date Completed:
d482e4d5-980c-43f6-bcc3-c269da74813e | section | Completion
5c258841-3f54-4b01-86c7-68e4d2be0262 | checkpoint | 3.1 Completion
9a9e700d-e0f7-571d-ade2-febc6408be5a | note | FREQUENCY: Each lot
f5a04fd5-a9ed-5687-9035-ddcc9cd607f2 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste. Bluestone pavement is free of mortar stains and cleaned to satisfaction
6b898521-1124-5796-9219-9a1de667a0a8 | note | REFERENCE DOCUMENTS: Visual Inspection
e3d700a1-20dd-595b-8f7d-3227be8cc470 | note | INSPECTION/TEST METHOD: Visual Inspection
1f5c5f8f-8b91-5710-abfd-f8664b91f3f5 | note | RECORD OF CONFORMITY: This ITP Signed off
397520c1-e255-5c50-baa1-538a9096df03 | note | IP
a6a50501-4ca5-592b-82ff-815316a4d1b2 | note | RESPONSIBILITY: Fulton Hogan Engineer
ba027320-2903-530e-a4ab-b8f253da3146 | textbox | Date Completed:
c44a7ce0-99e3-483b-9f37-908d07e37bba | checkpoint | Final Inspection
e89590e4-4186-5bf4-b60b-ab4eb7184e65 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a2c7b2e5-85c4-5e91-bcf6-968e75228cee | textbox | Print Name:
90f91f29-ca67-5965-a9c9-3aef5df87012 | textbox | Position:
efa56ab8-ad83-53ba-878b-c45b1d8905f9 | textbox | Date:
feaccad0-1cc6-4852-b305-10633d349c6e | checklist | ITP-019 - Fencing Installation |  | ITP-019 - Fencing Installation
4a42966f-d30b-4e74-80d8-628c0857a678 | section | Preliminary Works
aba07417-a9fa-4b0d-9419-7a41a5e10222 | checkpoint | 1.1 Check for correct documentation
86fde12f-5661-568a-a3df-36093d4a7645 | note | FREQUENCY: Prior to commencing any activity
790bbcc5-870b-500e-95f0-51685ba38c79 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
e30f1a54-fc0f-52c1-9bcc-3b9d0bc7af30 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
39f9a67f-3453-5f8e-a8a3-0e25ac221937 | note | INSPECTION/TEST METHOD: Visual inspection
fb67d309-1a47-5ed6-a6b4-936dc3c1951a | note | RECORD OF CONFORMITY: This ITP signed off
a92c3aac-bf91-5a0b-a83e-43fc7c3efaf4 | note | HP*
58ef852f-1386-5cb2-a0c7-ebd63118066e | note | RESPONSIBILITY: Fulton Hogan Engineer
bc6760f0-d553-591b-909e-35db646f8f1c | textbox | Date Completed:
39d5b15b-3a73-4bc2-b531-2c232f638ad8 | checkpoint | 1.2 Implementation of all measures and controls
e61787cd-986a-5b1e-83ad-acb6027d00be | note | FREQUENCY: Prior to commencing any activity
cdb43d3c-e5e5-5f75-8ec6-a6f5c8598c02 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
3037b6ce-4972-5164-9635-d013b4e09f6f | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
0323f1e8-eae6-5808-9cd4-68a11c805e68 | note | INSPECTION/TEST METHOD: Visual Inspection
2a7aae24-1d7a-5cf1-ba4b-190ba749da4c | note | RECORD OF CONFORMITY: This ITP signed off
ac0e4a7b-cecf-5973-9df8-4be7888d0df8 | note | HP*
4abdf5c3-9d8e-5f7a-95f1-a575878377ff | note | RESPONSIBILITY: Fulton Hogan Engineer
8a1ffe2e-5909-5aab-9ebc-4ed864513bbf | textbox | Date Completed:
3c0aec95-6a38-49c5-9b6a-5cfaa6bd3518 | checkpoint | 1.3 Check Materials
d4f7c5de-adf6-52e2-b396-1df50a565327 | note | FREQUENCY: Prior to commencing any activity
9d1b317a-8f11-5209-8556-3dfdc605ebf4 | note | ACCEPTANCE CRITERIA: Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish, linished, pickled and electropolished. Welding shall be in accordance with AS1554. Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000
e62792f1-0920-5a3c-b412-137e40f5e936 | note | REFERENCE DOCUMENTS: STD_T6000, CE-021-ST-0012, cl 4.3.1.4
8349d94e-5b0b-58b1-8201-a973a4eff7f1 | note | INSPECTION/TEST METHOD: Verify
a8069f06-f02b-5205-a94a-620353aaeba5 | note | RECORD OF CONFORMITY: This ITP signed off
024921b1-926b-5578-adb3-ab6c8988afd4 | note | HP*
4021779d-0ec2-5564-bbc1-4779540072fc | note | RESPONSIBILITY: Fulton Hogan Engineer
21941661-f36f-5959-83ae-9dcb0889f2a4 | textbox | Date Completed:
6ecc4b94-46aa-4405-9539-5ea73adfdafd | checkpoint | 1.4 Confirm Footings position
119b20df-c82b-5572-a8a6-8f74fa74330b | note | FREQUENCY: Prior to commencing any activity
4b0c3afe-1076-5efb-bf26-4834be217a75 | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
1f2a5d57-7c0d-54ad-9c8a-777f1427277b | note | REFERENCE DOCUMENTS: Construction Drawings
db3b173d-e600-5af0-8b8f-57ce054d1b64 | note | INSPECTION/TEST METHOD: Verify
7d00e8e7-cfd1-5916-bebf-43e9df0ec90c | note | RECORD OF CONFORMITY: This ITP signed off
efc3b4c3-42a4-5bac-8ffd-91e6f8f79b24 | note | HP*
a287fe8b-ca5a-5123-8eb7-099b5b298218 | note | RESPONSIBILITY: Fulton Hogan Engineer
c567e8bf-6014-5b36-986c-2a6c8bdae3b3 | textbox | Date Completed:
0d662e65-602e-4cb4-8fcd-f966f812bd1a | checkpoint | 1.5 Bonds
0824e45e-faf1-54bf-a5e9-05332fc4812a | note | FREQUENCY: Prior to commencing any activity
abaeef60-6b3b-541e-86a8-1c999bfa6af5 | note | ACCEPTANCE CRITERIA: Ensure fencing is isolated and earthed to achieve electrical isolation. Lug shall be fitted to baseplate at specified fencing location
67cab031-5460-511b-b332-1b781443aaf9 | note | REFERENCE DOCUMENTS: STD_T6000
a0d1634e-2e93-5b83-ad16-f526a88a8f2d | note | INSPECTION/TEST METHOD: Verify
6a0992a3-606e-534e-a697-9fa908b19acd | note | RECORD OF CONFORMITY: This ITP signed off
d5861211-1759-5f22-963c-e5a239fa3b73 | note | HP*
11c6fdfd-9856-503d-97d0-d581a1d34157 | note | RESPONSIBILITY: Fulton Hogan Engineer
924a1afb-4bb2-58d5-971c-190b794bb827 | textbox | Date Completed:
7d1e8369-e34e-4757-955a-bdd3f66716c9 | section | Construction Works
5cf3a7e8-5d12-4fd9-893a-7b79a38ed373 | checkpoint | 2.1 Footing Installation
530bfb72-3729-511b-8052-f3d982c87b0f | note | FREQUENCY: Prior to Asphalt
704d4e59-b220-5ee6-b75a-6ad49118df71 | note | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20. 4 M16 hot dipped galvanised bolts shall be chemset 175mm into embedment, per footing
ad8c0df6-4c16-5ae5-8d6e-f3afdaaeff09 | note | REFERENCE DOCUMENTS: STD_T6002
a7f280b7-7fc3-5f5c-a7b4-2e7a1224292a | note | INSPECTION/TEST METHOD: Verify
b49f42e4-f631-50e8-afc7-a131a343d2a3 | note | RECORD OF CONFORMITY: This ITP signed off
0a682e0b-3ec2-558d-9c14-c9b0a9ba5de9 | note | IP
eb1ceb8c-bd89-5f7c-b8cf-d6a1080ff909 | note | RESPONSIBILITY: Fulton Hogan Engineer
2d42928e-883a-56c7-9a51-f4bbc566137e | textbox | Date Completed:
7fcc8f7d-1b57-4ab2-ac1f-fcca80c31ead | checkpoint | 2.2 Post Installation
e91b5e1e-4cf0-5776-877f-86dc8eaa582d | note | FREQUENCY: Each Lot
12e277d0-2c90-5545-ba21-bd35fed3cd3b | note | ACCEPTANCE CRITERIA: Post shall be installed to designated height and level. Installed to footings with bolt assembly. All bolts shall be insulated from base plates, using non metallic sleeves and washers. The top of fence base plate shall be level with surrounding pavement.
3a4effde-9177-5ca0-94fc-a3040553d95a | note | REFERENCE DOCUMENTS: STD_T6002
153cc8b7-f8d1-5ecb-9ed0-2b69d63a01d5 | note | INSPECTION/TEST METHOD: Verify
cfb389bd-85db-536d-867e-b80081af4143 | note | RECORD OF CONFORMITY: This ITP signed off
a363507f-a075-5110-a4a4-e63c5deb26bf | note | IP
e4ea7d3a-812b-5317-8b03-5991acae9399 | note | RESPONSIBILITY: Fulton Hogan Engineer
fe4c4abf-f176-54af-885f-81902b63b048 | textbox | Date Completed:
2884354c-6021-46dc-bfea-6226b6d2392a | checkpoint | 2.3 Grout Installation
815ec29e-c34c-5b13-8cf6-076ab75cf170 | note | FREQUENCY: Each Lot
f0ef7231-df0c-5776-9e7e-fc5cc838ff9d | note | ACCEPTANCE CRITERIA: Footing surface shall be cleaned and roughened before application. 50mm of Non shrink dry pack grout shall be placed under base plate
576e5f0a-7aff-5280-aba7-e9fd972b3080 | note | REFERENCE DOCUMENTS: STD_T6002
b621e1ce-8a3d-5ca9-bdad-9a8694d3f8c4 | note | INSPECTION/TEST METHOD: Visual inspection
f66e8eae-6b03-568e-b3c1-e7926eb5b475 | note | RECORD OF CONFORMITY: This ITP signed off
63be8778-224d-5bda-92af-996de4b2989b | note | WP
63d168ea-ee15-576e-98bd-67b4f6a5ad19 | note | RESPONSIBILITY: Fulton Hogan Engineer
c2d01ad0-1d7f-5a32-868d-e994d13a5c22 | textbox | Date Completed:
c7610ba6-d217-4480-ab75-46866c30c725 | checkpoint | 2.4 Continuous Handrails
f83684e5-5b78-5aff-b474-e47fd2d260eb | note | FREQUENCY: Each Lot
1bd5f1df-9e65-5459-a34b-9a8b91e35988 | note | ACCEPTANCE CRITERIA: 5mm cap plate on handrail returns. All sections to be welded as per AS 1554. All sharp edges and welds to be ground back to smooth finish. Domed buttons to be welded on top of handrail 150mm from the post centreline.
ac8a3f30-b8a5-5b4e-8723-3451c4e5efe2 | note | REFERENCE DOCUMENTS: STD_T6001 & T6002
e0f42eb1-9502-589c-9e0e-7ceb0ad4b6d8 | note | INSPECTION/TEST METHOD: Verify
7d4259b4-64e9-5d61-9708-2130d18b6322 | note | RECORD OF CONFORMITY: This ITP signed off
24719845-0f5d-5dbc-a6c1-456eb527d3a6 | note | IP
c0aa6569-652c-59b1-8226-6a8a4e311f32 | note | RESPONSIBILITY: Fulton Hogan Engineer
e0c9178f-5e96-5a11-a91c-20dee2942434 | textbox | Date Completed:
a0ddcf8d-d95c-490f-a76b-cef4546e7154 | checkpoint | 2.5 Wire Rope Tensioners
4f0a7ef7-c213-5298-94f8-f2a9abeb90e9 | note | FREQUENCY: Each Lot
562a3c3f-1700-5c61-aa94-b4df2f78dba3 | note | ACCEPTANCE CRITERIA: Architectural wire rope cables to be inserted into ferrel on fence post and to be tensioned with tamper proof fastenings (Loctite 243 Threadlock)
9c8eea9b-d819-5d49-9fb3-3224faf7ade2 | note | REFERENCE DOCUMENTS: STD_T6000, T6001 & T6002
168a2387-8ca4-559e-bc90-151c5ceb1219 | note | INSPECTION/TEST METHOD: Verify
d2d139c7-d47c-5289-a6ab-fcb1c34e7515 | note | RECORD OF CONFORMITY: This ITP signed off
afb2e819-fee4-5464-b62f-1cb3f1d537c5 | note | IP
42bd34b4-c022-548e-b0be-64aad8546e64 | note | RESPONSIBILITY: Fulton Hogan Engineer
885fdd8e-5f5e-55e8-a44f-e962c1d9ec7f | textbox | Date Completed:
2fdf12ee-2167-4bdd-9472-05524417183a | checkpoint | Final Inspection
ad178de0-99db-537a-a948-ddedb327fef3 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
bf42e633-c6ad-5391-899e-322476b1386c | textbox | Print Name:
703c9e86-6dc3-5af9-9577-2ec2f819ea6c | textbox | Position:
9846a06d-672a-5758-93aa-65a24ca508a1 | textbox | Date:
144a62ff-d937-42c8-aed8-e070e93130b3 | checklist | ITP-020 - Exothermic Welding |  | ITP-020 - Exothermic Welding
1de85215-d329-45f4-91af-4cbfdb59cd35 | section | Preliminary Works
5b89e1c0-f82f-446b-abd8-3a322c5483a6 | checkpoint | 1.1 Check for correct documentation
5737a2e5-ab17-5742-af36-4c0929d81c87 | note | FREQUENCY: Prior to commencing any activity
555905d4-f59f-59f6-bb4b-bc9015110c63 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
d7e1a8d4-1fda-583b-aff3-450afc6ef321 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
15841062-e649-5bed-8773-1d08a8f7e184 | note | INSPECTION/TEST METHOD: Visual inspection
1e6025d9-1a6d-5444-af4d-c3930647b11e | note | RECORD OF CONFORMITY: This ITP signed off
8b34f132-1111-5e48-8dca-5cbfb7812037 | note | HP*
6cd44bb3-0168-5dcd-9081-09ddc2b8d537 | note | RESPONSIBILITY: Fulton Hogan Engineer
93a4d347-85d1-5229-be6d-c1c60ab675d3 | textbox | Date Completed:
8478ab02-ab79-4742-8802-10c6119e72f7 | checkpoint | 1.2 Implementation of all measures and controls
141cc903-1e99-5079-919b-8beaf2659c58 | note | FREQUENCY: Prior to commencing any activity
3d270118-7b9f-53f5-87f6-21bde4e48224 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP. Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit
24a13351-3266-54c0-bb1d-b58e7612f558 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e067120b-951e-5014-b441-cce06ebcfbc8 | note | INSPECTION/TEST METHOD: Visual Inspection
9aa47274-60f4-5a98-b690-66f7d48c9776 | note | RECORD OF CONFORMITY: This ITP signed off
82dee1d2-4ae3-5f2e-87f6-bd59ff3fee40 | note | IP
abc8ba22-f6fd-5eda-ac40-2184e81cb02c | note | RESPONSIBILITY: Fulton Hogan Engineer
69e0bd2a-602b-5efb-9aee-84dd05d3d085 | textbox | Date Completed:
9190b21a-5cc8-48ba-bcf9-058160918646 | checkpoint | 1.5 Materials Check
2e8d2da0-10c0-5337-8f47-32fe9b261f5d | note | FREQUENCY: Prior to commencing any activity
32eec5ba-ce2e-5b5c-a972-97a79726096f | note | ACCEPTANCE CRITERIA: Ensure the materials and equipment gathered are for the correct type of connection being made. Inspect the mould ID tag to ensure that it corresponds to the application, indicated by the following parameters:
6cd3cb08-6977-5108-8f13-939415c26a55 | note | 1. Mould part number:
e3085b7a-c123-5864-bcbe-cea63d3bfc62 | note | 2. Conductor size:
ff5a1219-8caf-58ea-b2ff-9f07ee5e84bf | note | 3. Welding material required
85203a54-acc5-5d52-bca5-7c3357c255bd | note | Check to ensure the graphite mould is not worn or broken, which could cause leakage of molten weld metal during the reaction.
d5c1916c-6153-52c4-80ca-f2ccbecaf5d3 | note | Ensure a working fire extinguisher is available within 10 metres of the working area.
480fce13-7862-5158-9f13-b3d7e89d6951 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
44704c48-abea-517c-a779-1e8fa4d0ed74 | note | INSPECTION/TEST METHOD: Visual inspection
1b5896b1-847b-55bc-a701-10fd71936bac | note | RECORD OF CONFORMITY: This ITP signed off
58a209ca-249a-5177-937e-376618bb6510 | note | HP*
ee240a90-4a30-5981-9d65-505e86dafa24 | note | RESPONSIBILITY: Fulton Hogan Engineer
5d4aa062-9b8f-5069-8a18-7f13014a7f58 | textbox | Date Completed:
37560977-beb2-4c13-9241-d0362dc8a225 | section | Construction Works
d585d52c-faeb-4325-9ce0-cdf114bcca4d | checkpoint | 2.1 Preparation
e05b7f0f-7739-5e5a-b823-799072a1c8f7 | note | FREQUENCY: Each Weld
51c919b1-c094-5481-b275-e1f5bcd0842a | note | ACCEPTANCE CRITERIA: Ensure the position of the conductors being welded is correct. Heat mould to ensure it is dry. Strip & clean conductors, ensure they are dry & clean.
41cdae8b-0e39-521f-902d-790581224b43 | note | REFERENCE DOCUMENTS: Design Drawings and Register
885bda41-4138-5f44-88e2-8fa4ac8ccb2c | note | INSPECTION/TEST METHOD: Visual inspection
663fdf37-3ac6-5cff-a954-b8b1397bf3b0 | note | RECORD OF CONFORMITY: This ITP signed off
0b0e2e67-87e7-589a-934c-2ca86e399977 | note | IP
5d8ff630-fd50-5355-8d00-c068f7f4763b | note | RESPONSIBILITY: Fulton Hogan Engineer
f6ccf044-bb96-54f0-b658-dcbb60541fce | textbox | Date Completed:
3959a5ef-0740-42fd-bf8d-ba3b9f85fc6e | checkpoint | 2.2 Welding
3f69303a-5f5a-5d8e-8340-6d2124b1dc4a | note | FREQUENCY: Each Weld
cdf94c59-85f5-5b28-a32f-358f1abb95d7 | note | ACCEPTANCE CRITERIA: Ensure conductors are correctly positioned in the mould, allowing the mould to close tightly. Ensure welding material has been inspected and is intact. Ensure reaction is completed and molten material has solidified (allow 30 seconds post ignition)
a8db93ee-8900-5f45-bd07-6394d484814c | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
bb2eb571-5e08-5997-a9d3-0bc8303aeb90 | note | INSPECTION/TEST METHOD: Verify
a7fcd6b7-4f18-5fe2-9865-2714d763e3da | note | RECORD OF CONFORMITY: This ITP signed off
6a81fced-e910-5354-b5c0-c03a6ef0cb9f | note | IP
0b60f5e4-906b-54ae-b9e7-6910cc6e0c52 | note | RESPONSIBILITY: Fulton Hogan Engineer
7f02524f-5c97-554b-ad4d-f9c6203bbc7b | textbox | Date Completed:
7b1c6888-4c2c-482c-9591-a0b245f7c0d2 | section | Testing
7cb79786-abe3-4e66-b6ba-49db04981b28 | checkpoint | 3.1 Weld Review
40886372-ffb2-5bc0-818d-02b1ba7496aa | note | FREQUENCY: Each lot
d0d9c1cf-e7c1-5b27-b32a-9db32aa6374d | note | ACCEPTANCE CRITERIA: Ensure weld is inspected and that a quality connection has been made. All welds shall be inspected a Fulton Hogan engineer.
2f0f6626-0e58-5812-b2d8-1bd286bbe3f9 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
a670037f-24d6-54d1-860f-a15486475ab8 | note | INSPECTION/TEST METHOD: Verify
883ffe5e-c3b9-5190-93b9-6fe79d9603cb | note | RECORD OF CONFORMITY: This ITP signed off
75ff4990-aac6-59e4-a5cd-a4a518682e0d | note | TP
e94d4a8e-7df4-5a0c-b636-646e348f6b2c | note | RESPONSIBILITY: Fulton Hogan Engineer
82c6b158-5f97-5091-acf3-45e22b985b6f | textbox | Date Completed:
48cf313d-e667-4c0d-a644-a09ff72e7668 | checkpoint | Final Inspection
5cb96962-5184-5919-afe6-94ac0528e8ea | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
e2a9991b-31f7-533b-bf6e-db9008abe381 | textbox | Print Name:
499aa2b6-8c69-56dd-8834-4c08ca22afcb | textbox | Position:
56e67e63-fc15-594a-829b-b897e3213996 | textbox | Date:
42c8acff-71af-4fb9-aea4-30fa0b4e2efe | checklist | ITP-025 - Platform Concrete Footing |  | ITP-025 - Platform Concrete Footing
41ca733f-34da-4447-bd2b-a38816e32f29 | section | Preliminary Works
0cf5f343-70e5-4d90-ab04-3b0a1b146991 | checkpoint | 1.1 Check for Correct Documentation
6a36c141-8362-57de-baf0-a15b4a1f93ce | note | FREQUENCY: Prior to Commencing any Activity
80313078-903e-5930-8aec-327d1c284dcc | note | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
ddc2d1fa-cb8b-5513-bfed-2453a32bbb92 | note | REFERENCE DOCUMENTS: Design Drawings and Register
cd78cdc5-e5b5-5bd7-bf97-8ad132a7d8ca | note | INSPECTION/TEST METHOD: Visual Inspection
a47b013f-027c-5e57-9494-d0fe92cb2368 | note | RECORD OF CONFORMITY: This ITP signed off
fa9514f3-778b-5d93-9e8e-dca761d41800 | note | HP*
6ada61db-0340-5e44-b377-86f5f78b542f | note | RESPONSIBILITY: Fulton Hogan Engineer
70fc659f-12c2-5ee4-be4c-a5d6495713f0 | textbox | Date Completed:
9f97b57a-11ef-4dfa-84e5-a84b321a6eec | checkpoint | 1.2 Implementation of all measures and controls
ad20030e-946a-5a72-b52d-4d3ced538247 | note | FREQUENCY: Prior to Commencing any Activity
65eb5c25-3647-5f8f-a6a6-c692ce081e0a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
e564021e-1ee5-5c85-9518-4a921f532fac | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e0cd75ef-ed59-5e26-a8dc-89fb62136bc3 | note | INSPECTION/TEST METHOD: Visual Inspection
884cd2bf-9f1e-5def-bca3-4adf8c634bcb | note | RECORD OF CONFORMITY: This ITP signed off
82a1edca-041a-5855-8b2f-9ad0dddedef3 | note | HP*
80d37b3d-695e-5728-b2da-189091ac09f1 | note | RESPONSIBILITY: Fulton Hogan Engineer
9b4237d2-c1c3-5b33-9ba5-723773d6bd0a | textbox | Date Completed:
f0a30300-e7e0-470e-841f-82b57e9c38b3 | checkpoint | 1.3 Setting Out
cb46810c-7805-5f65-be53-d5a2cfab48ca | note | FREQUENCY: Prior to Commencing any Activity
26d21657-ec54-526a-a40b-ecdfe75de39e | note | ACCEPTANCE CRITERIA: Ensure that position of footings has been correctly identified according to design drawings
67ab7e21-dbbe-5636-9f61-163e05571f15 | note | REFERENCE DOCUMENTS: Design Drawings and Register
cb790f6c-5704-53a5-b5f1-3f4abe1b0fe0 | note | INSPECTION/TEST METHOD: Visual Inspection
b804c4e1-55cb-51b5-882a-5fa89808c433 | note | RECORD OF CONFORMITY: This ITP signed off
d9f29269-e0df-507d-850a-ec1af5f53b63 | note | IP
4741c425-5531-5d83-8dec-d75e231ea5c9 | note | RESPONSIBILITY: Fulton Hogan Engineer
42612588-b5a6-5bfa-87d6-2a3ecab7d243 | textbox | Date Completed:
5e0b5595-ce2a-4b88-a878-ae48ccf0f3d0 | checkpoint | 1.4 Material Check
f8c4c644-f58e-56ab-8c16-8b7766ab9a48 | note | FREQUENCY: Prior to Commencing any Activity
21c25a39-6622-5cf8-bbdc-f406f7078129 | note | ACCEPTANCE CRITERIA: Ensure that materials have been correctly ordered based on the intended use. All bolts shall be hexagon head class 4.6, unless otherwise stated. Ensure bolts are of specified length and grade
8df893d0-2363-59d5-935f-2b76a8da71cb | note | REFERENCE DOCUMENTS: STD T6100
98f5744d-9217-5ac5-88c7-965326325ce4 | note | INSPECTION/TEST METHOD: Visual Inspection
a9d0ce9b-4e3c-5ee6-b07c-c5a02ca7722c | note | RECORD OF CONFORMITY: This ITP signed off
9fbeaa8e-a2a2-5b1e-b3b2-c213d077ceb1 | note | IP
ca7ada39-27d7-54cd-b736-0171d1a2ebfa | note | RESPONSIBILITY: Fulton Hogan Engineer
fbcd0aa7-2b13-545e-a5f5-658d0446137e | textbox | Date Completed:
9e2d8971-fc81-4aa5-b96c-4c6f6b87012c | checkpoint | 1.5 Concrete Slab Check
71d5d95b-f1cb-5c10-8152-56522d8ac720 | note | FREQUENCY: Prior to Commencing any Activity
c53b3eb5-d0e4-562a-a204-69e44d092de7 | note | ACCEPTANCE CRITERIA: Ensure recess has been provided in concrete at location of footings, ensure recess is to correct depth. Refer to Adshel specifications
36554759-e1d1-518e-9b72-79c2a107f4d3 | note | REFERENCE DOCUMENTS: STD T6102
c4908493-ec9f-5216-8b0d-68c73a19e4de | note | INSPECTION/TEST METHOD: Visual Inspection
66540f13-57bd-515d-aa76-397f98a84bd1 | note | RECORD OF CONFORMITY: This ITP signed off
352b4413-7a34-5f6a-8330-fddee7cd60d6 | note | IP
b0c23e8c-d3c3-5c88-8976-2b22250514d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
60688346-c119-5a5e-8482-2996e1675adc | textbox | Date Completed:
ca8baaf7-6371-4eef-aaa7-3bb3bf0c063b | section | Construction Works
422be50b-fec9-4e50-90d4-32506f06ba14 | checkpoint | 2.1 Bolt Installation
f69eb442-c6f0-5b65-a166-e30bcf58ab44 | note | FREQUENCY: Each lot
98f85a62-2937-57de-95a7-43fd31e9b20c | note | ACCEPTANCE CRITERIA: Install bolts as per specified minimum anchorage depth. Ensure anchorage procedure conforms to standard"
8afe35c3-22fc-5302-b743-72f91ff2bf33 | note | REFERENCE DOCUMENTS: STD T6102
93232f4c-0842-5a56-998c-762fae90c427 | note | INSPECTION/TEST METHOD: Visual Inspection
46eade24-def5-53ef-b7e8-62c81383e06d | note | RECORD OF CONFORMITY: This ITP signed off
58857e25-c735-582b-aaf8-92035f3df3bb | note | IP
86349776-bd7c-5e26-97bc-d7b7c5af79ed | note | RESPONSIBILITY: Fulton Hogan Engineer
ed8afd91-2676-5a20-9676-adcf55007aa3 | textbox | Date Completed:
29c34348-5f14-48f6-8b3f-6f68463d4392 | checkpoint | 2.2 Placement of non shrink grout
1d4dee20-e96f-5d9b-9552-a9d195b8a2c9 | note | FREQUENCY: Each lot
de240681-251e-529a-a69b-e4fb94f3a18b | note | ACCEPTANCE CRITERIA: Non shrink grout shall be placed between concrete pavement and base plate, at thickness >35-75<mm
83d01077-2aef-52fc-b77e-4eda79a6e9db | note | REFERENCE DOCUMENTS: STD T6100
b8da7315-8f16-54f7-bb52-6dac8b6e2aaa | note | INSPECTION/TEST METHOD: Visual Inspection
dc09ed1e-9319-54e1-8ed8-d64ead867202 | note | RECORD OF CONFORMITY: This ITP signed off
33aaed3a-9e87-56d0-b48a-d057a1e9af65 | note | IP
0680d148-37c4-5b87-9968-7cc2dc3794e1 | note | RESPONSIBILITY: Fulton Hogan Engineer
4627ba81-1703-586b-ab8d-33ddc4998cd0 | textbox | Date Completed:
687084c7-c21f-4bdf-ab21-6baf6640c9f9 | checkpoint | 2.3 Placement of Grout
20f14e68-7de9-5764-9a03-5caa40251058 | note | FREQUENCY: Each lot
14e09f59-1586-57c0-91eb-8613c916f250 | note | ACCEPTANCE CRITERIA: Grout shall be placed as to fill the gap between baseplate and level height of concrete
5aca15db-53a1-540b-b729-95028f89a9f1 | note | REFERENCE DOCUMENTS: STD T6100
e43cf61f-0cc5-5989-9dca-aa1ca12af140 | note | INSPECTION/TEST METHOD: Visual Inspection
91009604-3842-5c1c-8b93-6a47b72a5c07 | note | RECORD OF CONFORMITY: This ITP signed off
4cc2a084-bef2-5486-af6d-906cbee14e27 | note | IP
7645155d-9b39-56de-839e-ce1f1292033a | note | RESPONSIBILITY: Fulton Hogan Engineer
7417d717-42b4-5697-a78e-9edd4a52daf2 | textbox | Date Completed:
dc8e77d7-4cda-497b-b574-61c1ad9dad47 | checkpoint | 2.4 Pavement (if required)
d3254f0b-225a-5bfa-9b08-3b343fb9ebf6 | note | FREQUENCY: Each lot
63f41f09-7f56-5036-8afb-b53bdc17daf5 | note | ACCEPTANCE CRITERIA: Minimum depth of specified pavement shall be 50mm, ensure the bolt assembly is not covered by pavement
c1fd2181-cbfa-5069-a546-1b5d11a3eada | note | REFERENCE DOCUMENTS: STD T6100
053188d2-1cfe-5848-909b-ea3986ae52cd | note | INSPECTION/TEST METHOD: Visual Inspection
77169c7f-cbe5-5d44-9eca-fac25dc32b24 | note | RECORD OF CONFORMITY: This ITP signed off
9d34ae26-5120-5c0b-bd17-600f98d80b56 | note | IP
47cbe41a-7762-5efe-b26e-2b2b7a69b6bf | note | RESPONSIBILITY: Fulton Hogan Engineer
f30b7946-61df-51d9-8b19-e0b875b59575 | textbox | Date Completed:
0077eb53-bb02-4057-b92e-2be723e92f10 | checkpoint | Final Inspection
cb786e83-fd78-501b-9d58-5708e7634fe0 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
d5deb707-ab10-52c4-95ef-ca97eec9d8cd | textbox | Print Name:
e8daf0df-a571-575e-90ca-acd52e0df1c3 | textbox | Position:
76b7f067-1ecd-559f-bd03-a554293f44a1 | textbox | Date:
76779e58-1098-478f-a652-5807cc405494 | checklist | ITP-029 - TGSI Installation |  | ITP-029 - TGSI Installation
9d5f2181-a699-437b-9014-e9af1562ebe8 | section | Preliminary Works
72dec241-57cb-4be8-8df1-8997ab41ea73 | checkpoint | 1.1 Check for Correct Documentation
58512ea7-b77d-5e20-8a7b-475aeeafb400 | note | FREQUENCY: Prior to Commencing Activity
26a879f6-047e-591d-b091-6bea99caefdc | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
d8a5b310-bb4d-5a9b-a73a-ff0a13699629 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
eebee218-17ad-58a8-9eae-3dfd95b70389 | note | INSPECTION/TEST METHOD: Visual Inspection
3c0a9ed6-5091-57b2-81a7-639ad953fe84 | note | RECORD OF CONFORMITY: This ITP Signed off
0fb1f4d3-102e-5c60-a055-e8253610859e | note | HP*
50546b5b-7f3f-5967-bdad-49d9aec1b90f | note | RESPONSIBILITY: Fulton Hogan Engineer
73d98214-a900-568a-b724-26a5e8ab3999 | textbox | Date Completed:
054b5a87-a7c5-4727-8954-c54572c54629 | checkpoint | 1.2 Implementation of all measures and controls
040389a3-a39b-5d7e-87dd-cf3a8c928630 | note | FREQUENCY: Prior to Commencing Activity
74fbdbfe-2296-5d74-830c-17feae25274c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
850dea4a-3ce9-58a2-b077-07e0c1d65952 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
f040fcf1-e4f3-5314-bf50-eec8ac9ece07 | note | INSPECTION/TEST METHOD: Inspection
17074e00-8c2b-5829-a082-2c9b0aa1ad65 | note | RECORD OF CONFORMITY: This ITP Signed off
9cd76f2f-69f6-56c2-94e4-acdd4a66b2fb | note | IP
22b0733f-a1c9-5bbc-8610-d3c973b5f7fa | note | RESPONSIBILITY: Fulton Hogan Engineer
93786f4c-b348-52a9-9717-6ab2aae0ddc2 | textbox | Date Completed:
f5f47abd-4aae-4fdf-9719-e35a2a415e49 | checkpoint | 1.3 Check Materials
fc43b9d8-4a85-5760-a5c8-afaadb1d36b6 | note | FREQUENCY: Prior to Commencing Activity
58d25e05-90bd-5d00-935d-9f5818a6fa3f | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Bluestone / Granite Tactiles. Tactiles in asphalt areas shall be Pandatac Granite Tactiles.
708a5c66-ebfb-5386-bb52-e446a7b1eb7d | note | REFERENCE DOCUMENTS: Receivable Inspection List
dc14ded3-3911-5dce-bfa3-6abe545a9f77 | note | INSPECTION/TEST METHOD: Visual Inspection
7a2f3996-490e-51d8-8a7a-afd3380a1b1b | note | RECORD OF CONFORMITY: This ITP Signed off
050b8703-726a-55da-8263-610f63e7bd56 | note | HP*
7cb5ad01-8613-595c-b057-98adcbc89700 | note | RESPONSIBILITY: Fulton Hogan Engineer
80156d47-4943-54c0-bf0c-f36d15ea9cf4 | textbox | Date Completed:
92b9f671-f9e9-40b6-8b55-fd56429eceea | checkpoint | 1.4 Setting out
5c0690fc-fb8d-5252-83c2-7908c174a6f5 | note | FREQUENCY: Each Lot
f29f5923-6b5e-5350-8d3a-5c71d05f596a | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
185241d9-34a4-57e4-903b-cc38d329f1db | note | REFERENCE DOCUMENTS: Work Procedure
8873ab8a-58d4-581f-8fbc-231a17c26ca5 | note | INSPECTION/TEST METHOD: Inspection
98a06d18-bca3-583c-9cde-e79b235320a9 | note | RECORD OF CONFORMITY: This ITP Signed off
d003c7a7-c5f5-5cc2-80ed-487e2c5d3a01 | note | WP
4176e7be-6c24-523e-80c2-6230ce466a55 | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
844d0cd3-0a9d-59a8-a2f1-6b7732e9732e | textbox | Date Completed:
b5f632f7-d226-44c9-b023-d04adca08381 | section | Construction of Access Ramp Bluestone Footpath
63ed54f7-5f8a-4844-b14a-b3d4e897f19e | checkpoint | 2.1 Base preparation
bc295a75-ca07-5c7c-bb3b-d950a1849cd7 | note | FREQUENCY: Each lot
026356d3-860e-5bf7-88c3-f807c21faf54 | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
9a6d7c68-2897-5bd5-8b7b-5e610dc5d830 | note | REFERENCE DOCUMENTS: Dwg 1P50201
5ab8edea-1529-5cef-aebc-7ee1cb0a4b12 | note | INSPECTION/TEST METHOD: Visual Inspection
9aeeed16-682a-53c5-81fd-fc422cb53b41 | note | RECORD OF CONFORMITY: This ITP signed off
f9b7b0d8-129c-5f22-a7d8-e71a0f11965e | note | IP
745c0ee7-5d55-5fc1-9f5e-2a1999ea132d | note | RESPONSIBILITY: Fulton Hogan Engineer
970d87b0-c72e-5592-be1b-ab9e699dd0d4 | textbox | Date Completed:
0001697c-1d7a-4335-8f76-0bec0e304d44 | checkpoint | 2.2 Placement of bluestone pavers on mortar bed
142277e1-b7c3-562d-ba06-a975d6757590 | note | FREQUENCY: Each lot
fb029f77-0549-5f7c-b4c6-232eb3a47b31 | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402 on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying. Kerb access ramp wings shall be at an angle of 45° or as per design and the ramp gradient shall not exceed 1:8. Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
3cff16c3-a237-5170-8713-68c87968756f | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
f0b2a502-3a56-5470-ae1e-488939f79a3d | note | INSPECTION/TEST METHOD: Visual Inspection
6218e6eb-ff61-5258-9d83-99501f514ad2 | note | RECORD OF CONFORMITY: This ITP Signed off
bf02fa11-c03e-58f7-8f86-8df634856b9d | note | HP
f1f0efad-cb76-54eb-973c-c429564e3a27 | note | RESPONSIBILITY: Fulton Hogan Engineer
812fbfd2-bd44-54ec-8a31-2f52c034580c | textbox | Date Completed:
fe0e76c9-6bc6-4b8f-8aef-b5d256eed844 | signoff | REQUEST HOLD POINT SIGN OFF
d3ba9b27-d408-4820-bcbf-d59897a9a2b6 | checkpoint | 2.3 Curing
eafb2a3e-8d65-5689-97db-1d3856a63489 | note | FREQUENCY: Each lot
697d9fb7-53cb-50d0-9836-9fff5997f247 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic. Where required, ply shall be laid over area of works
018244ae-13e0-56c7-a0cb-00fb585d21b5 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
ae6191c5-b455-5596-9c1c-da2f30b1d483 | note | INSPECTION/TEST METHOD: Visual Inspection
66a69c17-6945-58e0-9b14-836394f552fc | note | RECORD OF CONFORMITY: This ITP Signed off
fb919fdd-51a1-50a6-8b39-ba4a30885ac3 | note | IP
3f475cb3-ec35-5e5a-bedc-85916a133eb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
5329c1e4-4b54-565d-9b5a-a88de1f51bc5 | textbox | Date Completed:
71b4ee5f-e481-4883-8714-4be2c8f9e29b | checkpoint | 2.4 Grouting
624d0230-f2ee-5d4d-b2ca-97774ce6a563 | note | FREQUENCY: Each lot
0410b7ca-d319-575a-a538-9d789043b9f4 | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using Lanko Durabed to specified mixture content. Grout shall be spread & clean appropriately as required.
2ac2d53e-425a-57ef-aa9c-8a50eb21cf13 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
0013bf4b-96ad-520d-9459-d33d207f0dae | note | INSPECTION/TEST METHOD: Visual Inspection
af2e5ce4-6b9d-5f8c-9752-00f05614ff0c | note | RECORD OF CONFORMITY: This ITP Signed off
317ba425-7186-54c1-a058-38eea202305c | note | HP*
e013bb63-1cb3-5764-9992-e926b6d0de98 | note | RESPONSIBILITY: Fulton Hogan Engineer
38609131-229b-5e95-b11c-3a08fd974abe | textbox | Date Completed:
2dddb408-4816-4aa0-a6cf-2c93686f9c1b | checkpoint | 2.5 Installation of Versatac Granite Tactiles and Granite Inlay
d2e20344-0a4f-5c08-b52f-761db9b6d38e | note | FREQUENCY: Each Lot
5b46034a-c1f4-5b7b-986a-a2ad9155b12e | note | ACCEPTANCE CRITERIA: Granite tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201 with surface deviation of under 5mm. Tactile Pavers shall be placed on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying. Tactiles shall be cut with a diamond blade and allow a 5mm grout.
5996e517-121a-5436-92f6-bda4c207319b | note | REFERENCE DOCUMENTS: Dwg 1P50201
d4e16df7-8a3d-5fbf-8c65-4b2fee305e75 | note | INSPECTION/TEST METHOD: Verify
5d57676b-5612-5bf0-8317-ad2d4a804c5c | note | RECORD OF CONFORMITY: This ITP Signed off
6f395c1f-bbad-57ae-ad12-3eff1bf7704d | note | HP
e5bd8232-8f33-573f-acf1-a05a38306b7e | note | RESPONSIBILITY: Fulton Hogan Engineer
cb41ed74-357c-5781-a1ed-baf819222a11 | textbox | Date Completed:
76c39ebc-62d0-4c3d-be2b-25f0c5964a49 | signoff | REQUEST HOLD POINT SIGN OFF
2c2f50b5-bb9a-4e45-9ba2-91ce89116d77 | section | Completion
ee7535d6-fbb5-4a6f-8fd4-5783b14a88ff | checkpoint | 3.1 Completion
382d5dd1-9e0b-53b0-93f5-1b3e3766919c | note | FREQUENCY: Each lot
5642da93-e1b9-5f43-ba90-7de163daf3d7 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste. Bluestone pavement is free of mortar stains and cleaned to satisfaction
77b89f3a-6712-5853-8e3d-e75aa01021cb | note | REFERENCE DOCUMENTS: Visual Inspection
b33e71e0-fbc5-51f4-9e9b-f853da82e949 | note | INSPECTION/TEST METHOD: Visual Inspection
4c407344-98db-5b2d-b9af-994897943ec1 | note | RECORD OF CONFORMITY: This ITP Signed off
eac5c9f3-89e9-509b-9737-7d2845ff7085 | note | IP
70e307a4-fced-5f79-b6f9-be82596888d7 | note | RESPONSIBILITY: Fulton Hogan Engineer
494d6bc7-7028-5fd9-807b-8116c1ac1716 | textbox | Date Completed:
fc4c4352-1444-4831-947b-04ed65da7e5a | checkpoint | Final Inspection
920badbf-d7cf-5263-a798-b907ed9a2c10 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
da5e0cbb-0608-5ba6-9d86-0fecb14305cc | textbox | Print Name:
9b7aa94a-118f-508d-be5f-eaed31536ef4 | textbox | Position:
3aedafbd-670b-5dee-89aa-3d6f4d1f5fe2 | textbox | Date:
80871329-bdcd-4bec-bc5b-7dbcc7b3791d | checklist | ITP-031 - Precast Stormwater Pipe Installation |  | ITP-031 - Precast Stormwater Pipe Installation
cb43fa44-2e2f-4f09-a104-2dc9bfefd580 | section | Preliminary Works
a2a3d341-e729-4e40-ad3a-6323202934eb | checkpoint | 1.1 Check for correct documentation
cdb385f3-3512-50b9-b475-c64ebf73e732 | note | FREQUENCY: Prior to commencing any activity
3223ec45-8b20-503c-be2e-f8e99623ea65 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
344bc3b2-8cf7-59ad-ad94-75c86b12ef54 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
485dd589-3c0b-543a-952e-a853f08dfe6d | note | INSPECTION/TEST METHOD: Visual inspection
a0eb09eb-9b24-5853-85dc-efcb2842ef6a | note | RECORD OF CONFORMITY: This ITP signed off
bc3de693-93aa-589b-bfa6-acf051b58987 | note | HP*
1b6d53a8-7c69-5bc2-a9ed-af1c5a97a653 | note | RESPONSIBILITY: Fulton Hogan Engineer
941b4ab1-2373-515d-a94c-eaaf196f9890 | textbox | Date Completed:
8b90be19-3f22-4b8e-ab5a-1a5838fa4d0e | checkpoint | 1.2 Implementation of all measures and controls
e546188b-8d64-593b-97d4-f1330b917fbf | note | FREQUENCY: Prior to commencing any activity
fe58b9cd-e1e4-5bb9-96ff-68562039ffaa | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
e0e5ea83-5b98-5c82-b570-3f1963bf0fb9 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
9c55124e-7aed-533e-bc2c-5c601641be2a | note | INSPECTION/TEST METHOD: Visual Inspection
07202c91-1ef7-50c2-870d-214470a7cb75 | note | RECORD OF CONFORMITY: This ITP signed off
3381c12c-3b65-5811-9468-e12bedf3932c | note | IP
d51edbab-c0dc-5806-9d8d-aba7630aafda | note | RESPONSIBILITY: Fulton Hogan Engineer
84074ef2-79a1-5e06-9502-20202539d8ec | textbox | Date Completed:
7451c7b7-9a9e-400f-8582-b9b4ee6c91f5 | checkpoint | 1.3 Pipe classification and delivery
6636086a-ff0a-5815-886c-3934b91f8126 | note | FREQUENCY: Each delivery
d8457e97-33d1-5fdc-81cb-81edd352653c | note | ACCEPTANCE CRITERIA: Pipes shall be of the size specified on the drawings and either: Socketed reinforced concrete to comply with AS 4058 - 2007, with rubber ring joints complying with AS1646 - 2007, or Fibre reinforced concrete including fittings, to comply with AS4139 - 2003. Condition and compliance of the pipe is to be inspected upon delivery.
4ad543a7-5c1c-5a36-9153-08a8179fd4de | note | REFERENCE DOCUMENTS: Cl 4.1; Appx 2: Cl 7.0; Dwg 1P50318
d731092f-ba4e-572d-9a53-99dadb855cc4 | note | INSPECTION/TEST METHOD: Visual Inspection
f8f56355-9f3e-5db8-9c85-0f268b41da80 | note | RECORD OF CONFORMITY: This ITP signed off
28613be2-7be2-50af-9b7f-130945927c20 | note | IP
810da3be-fd16-5996-9fc6-8777f77746ce | note | RESPONSIBILITY: Fulton Hogan Engineer
e2f36268-4752-5449-b990-874e5978eb43 | textbox | Date Completed:
8c14e83e-996b-4c28-89c5-1f0b86aff113 | checkpoint | 1.5 Backfill and bedding material classification
e28d78de-a8b0-5334-97a7-1d3e7b80ea31 | note | FREQUENCY: Prior to start
0ddb8a98-ced0-5ee7-b65f-dafcc28fd861 | note | ACCEPTANCE CRITERIA: All crushed rock used in the works shall be Class 2, 20mm nominal size. Sand shall conform with the requirements of AS2758 - 1998 and AS1141 - 1997 and shall have grading within the limits as defined in the code.
09477858-8880-57d1-b01e-1baea9e7059a | note | REFERENCE DOCUMENTS: Cl 18.0
6adb6493-bb3d-5675-8f7a-d08296b5bad5 | note | INSPECTION/TEST METHOD: Verify
1e3fb593-8b99-56e4-bb31-eb319f2b8fcf | note | RECORD OF CONFORMITY: Test reports from supplier
a5fd55e8-1d1c-5c45-a3dd-c19bd608ee9e | note | IP
54cc624b-4aac-5c79-97da-2e1579f73a0e | note | RESPONSIBILITY: Fulton Hogan Engineer
6e5f7b57-9f3b-58fc-9d21-ccc1d78a944e | textbox | Date Completed:
1652d220-3d6d-413f-9016-05fdfd080820 | section | Construction Works
c9dfcfed-faa1-478a-8a40-b4aa15fe3807 | checkpoint | 2.1 Set out drainage
3ade98a2-a1f1-5962-96c6-24143585ab97 | note | FREQUENCY: Prior to backfilling
8ebe8b22-50a9-5660-8108-0e355db0a2a4 | note | ACCEPTANCE CRITERIA: The line and level of all drainage lines and pits must be in accordance with the provided design drawings. The position of all drainage lines and pits are to be confirmed with the superintendent if ambiguity arises.
7f59848e-fcd8-5819-a790-806ae318cb3d | note | REFERENCE DOCUMENTS: Design Drawings Appx 2: Cl 8.0
1dbc62af-ede6-5d19-999f-db4c5072208a | note | INSPECTION/TEST METHOD: Survey Conformance Report
bef5083d-01e0-51bd-bbf0-44391cd55b75 | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off
d5efc9ec-1fd1-5641-bb73-25ab44d9ec21 | note | SCP
09f4a1c6-f2e4-5e6e-9684-bc84b2741af7 | note | RESPONSIBILITY: Fulton Hogan Engineer / Survey
283fa5a1-3d5e-5f25-ba55-15d07724b473 | textbox | Date Completed:
a97767c5-9bf1-4b3a-99fb-7d2767b2a5a6 | checkpoint | 2.2 Excavation
29979228-4ba5-59d5-aa15-c5431eb5b241 | note | FREQUENCY: Each trench
d15de657-eefb-5b55-b411-79be71ad78d3 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth greater than 75mm below the specified level of the invert of the pipe to allow for appropriate bedding. Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed. Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m. No stockpiles within 2m of end of the trench to reduce bearing pressure.
dfdff10a-bf31-5740-b6ff-568f0525f657 | note | REFERENCE DOCUMENTS: Appendix 2: Cl 8.0, Cl 9.0, Cl 11.0
376f4c1c-184d-5aa7-badd-196a474956ae | note | INSPECTION/TEST METHOD: Visual Inspection
e14fb186-30d6-555a-89a4-cf9f4ee492df | note | RECORD OF CONFORMITY: This ITP signed off
c16ecb21-eb9e-5b00-b2b1-a28f72944a0c | note | IP
30cf57c3-f7fb-508e-a143-4cdbc726b2ab | note | RESPONSIBILITY: Fulton Hogan Foreman
66ea3e69-e808-5bf1-911d-f613dbae3f18 | textbox | Date Completed:
0b96481b-6cff-4f9f-8320-aaf6b4111b90 | checkpoint | 2.3 Inspection of trench base
a5f6937d-9830-5a89-b76d-2ba4dbb060f2 | note | FREQUENCY: Each Lot
69b780c8-bb58-52ca-8015-55e547b04015 | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
fffe9e58-2185-5f52-8cc6-748167e45cbe | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0
d2995ae2-9497-5c33-9a30-fd59c5104be5 | note | INSPECTION/TEST METHOD: Visual Inspection
cc89e7d0-d6b2-5986-bf70-79dd231a6ccb | note | RECORD OF CONFORMITY: This ITP signed off
c43cff28-f122-5889-b092-abfd6fee1dd7 | note | IP
8404bc4a-4f50-5b16-ae22-f372a2214498 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccef1801-bf59-5aca-9f3d-bd75e78aeebe | textbox | Date Completed:
aa14746f-b4ac-44c6-ae43-e93fc970384f | checkpoint | 2.4 Placement of bedding material
bbe7347d-de94-50b0-81a8-b855607480c1 | note | FREQUENCY: Each Lot
9e147125-8df4-5016-8200-00f6db8b5206 | note | ACCEPTANCE CRITERIA: A 75mm minimum layer of consolidated sand shall be used to bed the pipes of the diameter specified on the drawings.
ad6afd50-f18d-55a7-b673-a0f6802cf2e8 | note | REFERENCE DOCUMENTS: Appx 2: Cl 9.0
9561e6f9-a877-5153-8e47-da823440fa48 | note | INSPECTION/TEST METHOD: Visual Inspection
056fb510-f9e5-5c6c-b736-6184d2dc948f | note | RECORD OF CONFORMITY: This ITP signed off
9fe5f03f-dd59-502e-94b1-1905b78a1405 | note | IP
4b9686e5-24c9-5ee8-aaaa-5e8fd24a2506 | note | RESPONSIBILITY: Fulton Hogan Foreman
4ffd3a91-b584-51d3-8c47-03af5d0567d0 | textbox | Date Completed:
dfdb1146-6342-4482-be2e-57b1e39aeb5e | checkpoint | 2.5 Placement of pipes
1847c87e-05eb-5a46-9b5e-61591b6f1cf1 | note | FREQUENCY: Each Lot
78db297f-9736-5dbc-b6de-df49dd95d25c | note | ACCEPTANCE CRITERIA: The pipes of the diameter specified on the drawings shall be laid on the bedding firmly for their entire length. All pipes shall be laid true to lines, level and grades, and shall be butted tightly together with lips. Rings must be in place between pipes and not dropped to be visible.
d3889d01-1343-56ec-913d-61852363bf69 | note | REFERENCE DOCUMENTS: Appx 2: Cl 9.0
6b959ded-69f6-539d-9996-03b9c12eceb7 | note | INSPECTION/TEST METHOD: Visual Inspection
3449efcf-80c3-5a6e-8aaa-0e392dc21a30 | note | RECORD OF CONFORMITY: This ITP signed off
62329db1-ded9-5bf4-8aba-367c89ce692d | note | IP
1268ef48-a80c-59bd-9d6c-990503fc0d24 | note | RESPONSIBILITY: Fulton Hogan Engineer
fe2e1a0d-8e05-5690-905c-54fd924f7d54 | textbox | Date Completed:
c5c21459-0294-4516-9404-c9714f85b0ce | checkpoint | 2.6 Sealing
a3bc3b0e-3c25-58a0-a4d2-1544ad711a27 | note | FREQUENCY: Each Lot
f58738ea-fcf8-50f4-bce4-03a839bcc261 | note | ACCEPTANCE CRITERIA: All pipes connections to pits shall be neatly made, and the ends of all pipes properly trimmed off and stopped with cement mortar.
d8e5e53b-17d0-5a6e-93de-968cc2f1bb8a | note | REFERENCE DOCUMENTS: Appx 2: Cl 12.0
ff9113be-1dc7-5dba-92bc-c02698608d15 | note | INSPECTION/TEST METHOD: Visual inspection
5f0a78a4-48dc-534b-81bd-23938637dd2c | note | RECORD OF CONFORMITY: This ITP signed off
2535a53d-ab42-52e6-b267-30991bebe6c3 | note | IP
3ee4f68c-9bd7-5aa0-84b8-015514975287 | note | RESPONSIBILITY: Fulton Hogan Foreman
f10727f6-d36c-5e8b-a901-32b692034e99 | textbox | Date Completed:
ccdb1fc8-038a-47b6-bd26-af6a42bf7357 | checkpoint | 2.7 Bandage Joint
c623ab40-df90-5c8d-8279-ae53ad4c9bd1 | note | FREQUENCY: Each Lot
f5e6bced-f5d5-586e-aa46-846778ab981e | note | ACCEPTANCE CRITERIA: Construction bandage must be constructed where 750mm pipe connects to existing in accordance with Melbourne Water standard 7251/08/420 with SL82 mesh and 40MPa concrete.
a1ad2f94-249c-5e36-ba40-80d67d7ce3d9 | note | REFERENCE DOCUMENTS: Melbourne Water Standard Drawing 7251/08/420
bc1edb9d-a705-53e9-be68-a8fd08baeb54 | note | INSPECTION/TEST METHOD: Visual inspection
0b5aa4e3-585d-5281-9327-fcdba8313a28 | note | RECORD OF CONFORMITY: This ITP signed off
caa311c7-185e-5ad7-85fd-eae1cf9bb93a | note | IP
b0617a17-ab1d-55c3-adcb-a2ff980b69af | note | RESPONSIBILITY: Fulton Hogan Engineer
0ee28f16-a922-578d-ab73-63c46a772df6 | textbox | Date Completed:
9c3e2911-c2c4-4d8d-8ca1-bf1524d8daf9 | checkpoint | 2.8 Inspection of Pipe Installation
350a1c87-2100-5cba-bd6f-1ff110ec486c | note | FREQUENCY: Each Lot
9ea370c5-ca53-5c78-b967-bef1e625ca7b | note | ACCEPTANCE CRITERIA: No further backfilling shall be done until the Council's Supervisor has inspected the work.
8b325c9f-b4e1-5448-a5cd-80a7a67cb9c4 | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
a63ca885-f223-5ffc-b872-a7a8da4a4506 | note | INSPECTION/TEST METHOD: Visual inspection
d4d7d5ba-9824-5438-8ff6-63081657a092 | note | RECORD OF CONFORMITY: This ITP signed off
5e014a38-e8d0-5272-a8a4-27d642c48893 | note | HP
6de879cd-f08a-59f6-9174-8ba2649ed7e1 | note | RESPONSIBILITY: Fulton Hogan Engineer / City of Melbourne Supervisor
bf3e9c8e-4144-5759-b858-65d2af2c03a2 | textbox | Date Completed:
a86a5ca1-724c-44cf-afd7-a2cea166302f | signoff | REQUEST HOLD POINT SIGN OFF
acca8e23-d483-4d37-86d4-952e4aa8a6bc | section | Testing
52af1f48-fac3-4548-b40e-b605207c3272 | checkpoint | 3.1 Crushed Rock Placement & Compaction
d550144e-abb4-5ebc-b5fb-5ad940bf7087 | note | FREQUENCY: Each Lot
1acbdd59-fec3-5d30-9ae7-0dad2f55866a | note | ACCEPTANCE CRITERIA: The trench shall be backfilled with Class 2 crushed rock to the springing line of the pipes immediately after completion of laying. Further backfilling shall be with layers of crushed rock, Class 2, no thicker than 150mm compacted to 95% Modified Relative Compaction.
acfa716b-e823-5685-916d-400da1bc343c | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
ae0cc798-69a0-5a82-be68-2317dfbb4cb6 | note | INSPECTION/TEST METHOD: Verify
d9356e2d-5908-5af6-87b3-f683a990f847 | note | RECORD OF CONFORMITY: This ITP signed off
14ae4068-d88a-5818-82dc-c06e9ef412bd | note | TP
33d10156-f16e-5610-be03-e42c64707863 | note | RESPONSIBILITY: Fulton Hogan Engineer
ac201eb2-56cb-55b2-8637-e60dc118db93 | textbox | Date Completed:
0dc87804-d4fe-4ff7-b887-513f06582e0b | checkpoint | 3.2 CCTV Inspection
11116eba-1ffe-5657-a4ea-dfdc706aadd3 | note | FREQUENCY: Each Lot
a3af7d5d-1d63-5f14-80b3-f278b2ccde80 | note | ACCEPTANCE CRITERIA: All drainage lines constructed beneath pavements are to be inspected by CCTV.
ae940c40-b7df-5357-8fa6-a468f0e93763 | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
751d2cde-3587-549a-91e0-aab80be65f3d | note | INSPECTION/TEST METHOD: Verify
709f5b6a-a5fb-5d2e-8ef1-090a285630f1 | note | RECORD OF CONFORMITY: This ITP signed off
8638d594-d8b6-5831-804f-5e4f6a18982b | note | TP
4d2da017-a61c-57a9-8fd6-d0b792a150cb | note | RESPONSIBILITY: Fulton Hogan Engineer
d6207561-9220-5a5e-a4f2-a885ede980fa | textbox | Date Completed:
98bce6ce-fec3-47bb-9fa4-13a9f670efb4 | checkpoint | Final Inspection
b70a0e05-4f4b-564f-9faa-aca495cc2f70 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
0355a40b-3d40-579a-a7d4-b951aacc73a4 | textbox | Print Name:
ff00e4c4-80f0-5e54-8c32-af0b733f9f11 | textbox | Position:
9f74a7a5-a468-55ec-972f-d221dca76024 | textbox | Date:
c5c88ae7-98b9-4060-a672-3dd414d8ef27 | checklist | ITP-032 - Orca Island Installation |  | ITP-032 - Orca Island Installation
85cf0213-5784-4b70-8a66-549d5f606344 | section | Preliminary Works
a7a6e5fc-0ece-47b6-9fa2-4a489c493b68 | checkpoint | 1.1 Check for Correct Documentation
59cfbaa8-a8b8-52cc-984e-418aa3abab55 | note | FREQUENCY: Prior to Commencing Activity
de752495-8dbe-5ce0-87e1-a214fcb25283 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
50739957-d3b7-5213-b2ac-6a55c57a6042 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
f051c969-1b2e-51a9-8e32-bbc81da0c353 | note | INSPECTION/TEST METHOD: Visual Inspection
e2561d01-0e6e-5723-8dd7-16cd6801f121 | note | RECORD OF CONFORMITY: This ITP Signed off
2b91a9dc-5f6e-527f-94ed-3df5bb0b7b36 | note | HP*
9d7a9c82-b320-54cd-8721-7022bd92d0c5 | note | RESPONSIBILITY: Fulton Hogan Engineer
daa30b17-1d35-5595-be4d-b98c19223f63 | textbox | Date Completed:
2c4f5d3e-e19a-4d76-aa8f-e4e72a16bdb6 | checkpoint | 1.2 Implementation of all measures and controls
18892569-6400-5e8e-bb15-8543283ff710 | note | FREQUENCY: Prior to Commencing Activity
7f5fcadd-e5e0-50e1-8af5-94146e8d3758 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
7b93c346-79ba-5028-a300-5d0a83c46dd4 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
a099a9a4-c5c5-58fd-b572-1bd66339343d | note | INSPECTION/TEST METHOD: Inspection
cc182ecc-16ab-5a93-b63b-fe364238659f | note | RECORD OF CONFORMITY: This ITP Signed off
9f57672d-303c-5434-b77a-1476ca4f6e20 | note | IP
d0072b76-bb7d-5738-98bc-36749a1027f2 | note | RESPONSIBILITY: Fulton Hogan Engineer
84731356-2d73-58f0-b197-bbb78e5cfb27 | textbox | Date Completed:
6c9c5be7-7b5b-4092-87f7-ebc12396b499 | checkpoint | 1.3 Check Materials
ab3bb1d0-5e1f-5ddc-be71-53f460185139 | note | FREQUENCY: Each Delivery
af0b7a77-2f2b-5ff7-b246-daf2154649a7 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
105381bf-c010-5bc1-afa7-841aab593d59 | note | REFERENCE DOCUMENTS: Receivable Inspection Checklist
c74c084a-5fbc-54bd-b858-f3c3725644ce | note | INSPECTION/TEST METHOD: Inspection
3bc0eaae-005d-54e2-8810-b2733cfe41a9 | note | RECORD OF CONFORMITY: This ITP Signed off
0c368bf9-522d-5cff-8be5-480fdcb7b9a4 | note | IP
a09df259-f857-5138-88b6-d246bb2f7afe | note | RESPONSIBILITY: Fulton Hogan Engineer
9f6b177f-7e9a-5ac6-9ac4-911b2682be50 | textbox | Date Completed:
ad863e19-1786-446c-85a6-f5500dec3653 | checkpoint | 1.4 Setting out
8363cd56-0c35-5fd4-9628-2e9389e84b0b | note | FREQUENCY: Each Lot
e35f60c7-5ba7-5436-818a-8f8a58359ef6 | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans Alignment of new separation kerb and islands shall be marked out using string line
609681cb-f391-53ee-b5e7-b0fe6ea37bf8 | note | REFERENCE DOCUMENTS: Work Procedure
e55fb4aa-546f-5a72-9747-077e2a8d7531 | note | INSPECTION/TEST METHOD: Inspection
3f21009f-a27a-53ed-8b6a-1b5f6d86c61d | note | RECORD OF CONFORMITY: This ITP Signed off
b7b83f67-5d8e-54e4-95fc-2fad2bd30483 | note | WP
4804fdc3-9edc-513e-b639-a7b775cd4426 | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
75fb96ee-80a6-5dbf-bb87-17dac0f4538e | textbox | Date Completed:
bddce686-383c-4e55-98ee-f10f01ee2c68 | section | Construction Works
91905c5a-b9b7-4914-a5c2-2595b0671442 | checkpoint | 2.1 Base Preparation
8c9a7879-2992-5855-a24a-85c5f715dcf4 | note | FREQUENCY: Each Lot
6c4e87ab-04a9-5db9-8793-719843610c6a | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign loose materials and water pooling. IF required glue foam tape to the road where channel will be placed to ensure containment of adhesive.
a897b5f9-184b-5e23-809e-12896cc2ca7e | note | REFERENCE DOCUMENTS: Orca Installation Guide
2f1ed3a6-dd2b-57b7-bd91-311d8b401644 | note | INSPECTION/TEST METHOD: Visual Inspection
ee121277-4464-51fb-a579-9d93956ec3b4 | note | RECORD OF CONFORMITY: This ITP Signed off
cc3d8ec2-59ea-59c0-a2c5-a24f46bb5dc3 | note | IP
4552939d-5805-5fd5-9343-366dd5f1f8f2 | note | RESPONSIBILITY: Fulton Hogan Engineer
638befcd-3f0b-5cd2-87d8-d7ccee31caac | textbox | Date Completed:
b3d49de4-d310-4462-9188-ef57e778a2e4 | checkpoint | 2.2 Preparation of Orca Polurethane (Adhesive Agent)
2426beb4-a069-589f-97d0-07ac63a56746 | note | FREQUENCY: Each Lot
9e61fb96-8f08-5768-b1c1-1059b835114d | note | ACCEPTANCE CRITERIA: Mix Orca Polyurethane as follows: - 2 parts of Part B Polyol Black - 1 part of Part A MDI Using a paint stirrer in a drill, stir for a minimum of 4 minutes. Once Part A & B have been mixed, add 1:1 Part C Rubber Compound in the mixed A+B compound and stir again for 2 minutes. Ensure even mix throughout the adhesive.
308d4521-d8d7-53e5-92ec-493f57ef816d | note | REFERENCE DOCUMENTS: Orca Installation Guide
d1956aef-160d-5e21-81b0-d9c6286274eb | note | INSPECTION/TEST METHOD: Visual Inspection
4ed7fec6-570b-51df-8146-841ab259ead4 | note | RECORD OF CONFORMITY: This ITP Signed off
3d6c3a94-8c20-5a9d-882d-1dffcf3891c0 | note | IP
a69cf8bc-1d2e-556d-b01f-52779f5da28c | note | RESPONSIBILITY: Fulton Hogan Engineer
b1adbf5b-413a-5118-9492-deae056494f3 | textbox | Date Completed:
a22e4f17-81a1-41ee-8a4f-5df05d5b498c | checkpoint | 2.3 Placement of Orca Polyurethane
3f93e246-1555-5ba5-b798-53dc8c80b7a5 | note | FREQUENCY: Each Lot
318cdded-0d31-5371-9830-88432aede8cf | note | ACCEPTANCE CRITERIA: Pour the Orca Polyurethane compound onto the road, spreading to a thickness of approximately 2mm.
ebb14c76-76a5-5f3c-9158-33b230ca9edc | note | REFERENCE DOCUMENTS: Orca Installation Guide
dfdcb997-e5bc-5f82-a102-ee5769427b95 | note | INSPECTION/TEST METHOD: Visual Inspection
c5784f2e-74fc-5be7-bcd2-63dbda4fd356 | note | RECORD OF CONFORMITY: This ITP Signed off
af043eca-3f1f-56dd-8a2a-6f4d08d15fdc | note | IP
30aa9523-c787-5d64-bf2b-53721d91f8a3 | note | RESPONSIBILITY: Fulton Hogan Engineer
8650bab4-bfe4-5567-bb11-0609e03c1bae | textbox | Date Completed:
e824f497-e4d6-4bd4-983f-d79a772833b9 | checkpoint | 2.4 Placement and Securement of Orca Island
2cd0053c-bd8d-5426-ad86-af06edf33814 | note | FREQUENCY: Each Lot
712e9f31-5a40-5aff-b5c5-d072b442d033 | note | ACCEPTANCE CRITERIA: Lay the island on the polyurethane material. Drill holes through island fixing hole into road surface, then screw island down securely with 12mm x 150mm coach screws and mudguard washer. Ensure screws are all the way down to secure island. Plastic plugs to be put in bolt holes.
2794af55-5736-5c9f-a490-38c5a376b4fd | note | REFERENCE DOCUMENTS: Orca Installation Guide
549d46d8-a420-5860-a7f5-84a95554dee5 | note | INSPECTION/TEST METHOD: Visual Inspection
6aed28a8-b3c6-5827-afe7-0fa44c7ffb48 | note | RECORD OF CONFORMITY: This ITP Signed off
d43ccbd0-db13-5199-aeab-a7eda4fcb2ac | note | IP
9f8345b7-a2ff-5f64-b712-470b59091b81 | note | RESPONSIBILITY: Fulton Hogan Engineer
bbe7fe02-d3cf-59ff-aba1-9c9dfadd0363 | textbox | Date Completed:
9d07b370-f253-4724-b615-ee430c262e98 | checkpoint | Final Inspection
31d3b027-31ec-5a5c-9892-35cd1a8c0dca | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
8bac44dd-5e18-5316-8fc2-ded1d7d59227 | textbox | Print Name:
93da29e9-afd7-5b14-88c3-f97695f4ebb1 | textbox | Position:
bfef5598-cac3-5682-bc07-3481aacfd539 | textbox | Date:
b9a3bbcf-ee0a-4fd2-aa2f-d22e69a2c7eb | checklist | ITP-033 - Insitu Concrete Pit |  | ITP-033 - Insitu Concrete Pit
646bbf3b-f00c-4265-9df6-fc3ffe83fa29 | section | Preliminary Works
816c912c-71f7-4b5c-a899-47cdacbc53c2 | checkpoint | 1.1 Check for correct documentation
d2990ba7-ada6-5dff-afab-1ae3beb16e7e | note | FREQUENCY: Prior to commencing any activity
63293069-7df6-5ec3-b1dd-751e8b83b91d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
6d13e60b-beab-5241-9770-0155b4bd607a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6f560b21-261e-5e7c-9849-f9b33ccec8bc | note | INSPECTION/TEST METHOD: Visual inspection
dab88ffd-4497-50e7-a52f-22399e3a2bf6 | note | RECORD OF CONFORMITY: This ITP signed off
038293bc-89e4-5919-94a5-4827d580315a | note | HP*
04f121a8-22a9-5a39-80a3-1e297b31d3b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
f6480e2b-b21a-5a60-806c-daf90c9e56d3 | textbox | Date Completed:
d689c02a-55ef-4e47-a8bf-27db1cc06bdb | checkpoint | 1.2 Implementation of all measures and controls
638c1463-12a8-5456-8c4c-26eaf673f9df | note | FREQUENCY: Prior to commencing any activity
aa74b322-eb0e-58c0-92c8-f63b86386a99 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
e8b3c9a0-7217-5b16-994a-3d677aca2c20 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
a38d568b-a126-5a43-b889-068eb26e5c00 | note | INSPECTION/TEST METHOD: Visual Inspection
6bdc116e-84e2-5358-9a2e-5f633e0b4a6d | note | RECORD OF CONFORMITY: This ITP signed off
73c4c175-3c36-5b31-9e93-c8779c8a3c29 | note | IP
799747d3-09c2-53b1-91d1-e0957c9ae2dd | note | RESPONSIBILITY: Fulton Hogan Engineer
664aa47f-c4b1-5f6d-af37-f745e228ac0c | textbox | Date Completed:
a2b67dfa-0e67-447e-b0bb-029d77de0c3e | checkpoint | 1.3 Pit material classification
52187fa1-7f56-55a4-94d4-b48ae8228cc4 | note | FREQUENCY: Each delivery
22f19105-e74c-5056-8576-d521d8d7f2c7 | note | ACCEPTANCE CRITERIA: Concrete used shall have a minimum strength of 32MPa and be. Steel fabric shall be SL82 reinforcement and conform with the requirements of AS4671-2001.
7710b1e0-cec9-55dd-8ff4-acf553536261 | note | REFERENCE DOCUMENTS: Dwg 1P50318
53d5aa47-b908-5db3-9dbe-4d199c5adc01 | note | INSPECTION/TEST METHOD: Visual Inspection
14d9745e-32a7-5edc-9973-1436e7babc4b | note | RECORD OF CONFORMITY: This ITP signed off
5c333421-a415-544b-a03b-344d095a2b64 | note | HP*
bc70b1dd-d03d-5a1f-a916-586d069a29a4 | note | RESPONSIBILITY: Fulton Hogan Engineer
067eb19b-2524-5ce2-8f93-5c85c823c8de | textbox | Date Completed:
9b2863ee-4f72-4a12-8c5a-df0fea285b1c | checkpoint | 1.4 Backfill and bedding material classification
efa19785-4b3d-58a2-af49-1eb78a3b3046 | note | FREQUENCY: Prior to start
78e0ca57-8f95-5955-a33d-d040d823cd70 | note | ACCEPTANCE CRITERIA: All crushed rock used in the works shall be Class 2, 20mm nominal size. Sand shall conform with the requirements of AS2758 - 1998 and AS1141 - 1997 and shall have grading within the limits as defined in the code.
60adfc2f-6599-5bf8-94e6-90bcb3f4b00d | note | REFERENCE DOCUMENTS: Cl 18.0
6e47baed-507d-5f60-adad-af102cdb2e28 | note | INSPECTION/TEST METHOD: Verify
a6782468-f064-5a2b-a3a1-7d92135769a3 | note | RECORD OF CONFORMITY: Test reports from supplier
17dc9f1f-7ef8-5aac-8b3e-26ee4fb88e02 | note | HP*
e4f4ebae-a019-533f-904d-8283d04ff9c5 | note | RESPONSIBILITY: Fulton Hogan Engineer
aae5d3a4-a4e8-57c4-8a21-ed7de60a8747 | textbox | Date Completed:
5b76516d-cced-4238-8319-96e7f28760b7 | section | Construction Works
12a3c39c-578c-4049-958d-665038e9bdbd | checkpoint | 2.1 Set out pit location
d01e5ea9-aa28-5be9-9f2d-a789d24b2810 | note | FREQUENCY: Prior to backfilling
ec261a44-49cb-5c84-9fc5-0c43e11f2dd8 | note | ACCEPTANCE CRITERIA: The line, level and location of all pits & structures must be in accordance with the provided design drawings. The position of all pits are to be confirmed with the superintendent if ambiguity arises from the drawings.
f6d52be1-d21b-5be8-9efb-308c8eadd428 | note | REFERENCE DOCUMENTS: Dwgs Appx 2: Cl 8.0
018895b1-d81b-5534-956a-0e98de49f6f5 | note | INSPECTION/TEST METHOD: Survey Conformance Report
8a6617fb-72cc-52c0-8978-22454a04befa | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off
e8d394bf-a8ad-5102-8af5-09588d3bf89f | note | WP
3a8f319a-ae62-5d04-8d41-c6dd1f36b38b | note | RESPONSIBILITY: Fulton Hogan Engineer
88edc0e5-f855-58f6-a2a1-049d89444b86 | textbox | Date Completed:
d16a4fcb-63bc-405a-adf6-0e99543fbd4f | checkpoint | 2.2 Excavation
edb206f1-efba-51d0-908e-cfb682d5b2c2 | note | FREQUENCY: Each trench
04606e24-96a4-5bdd-80ac-e8d90feb1c6c | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth greater than 75mm below the specified level of the invert of the pipe to allow for appropriate bedding. Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed. Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m. No stockpiles within 2m of end of the trench to reduce bearing pressure.
a24221a7-4bbf-597d-ba7a-f52c128627f2 | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0, Cl 9.0, Cl 11.0
bf157885-cdc9-505b-8789-90543c1ab74f | note | INSPECTION/TEST METHOD: Visual Inspection
4d1ff526-2648-5065-8b6e-f3abf7f10f84 | note | RECORD OF CONFORMITY: This ITP signed off
14389dbd-f4cd-56cc-b21d-bd56f0ac1e63 | note | IP
c4ed7ca7-e8d5-5423-8503-281d27c9d29c | note | RESPONSIBILITY: Fulton Hogan Foreman
425f52c2-dc6e-5bbd-b448-a1d0a6edbf4a | textbox | Date Completed:
2e664806-7cc3-4d6e-8ae3-0540f81e97d5 | checkpoint | 2.3 Inspection of trench base
ae5fb236-84ad-50db-bda2-052999efbded | note | FREQUENCY: Each Lot
55c13594-c890-509c-9e8b-60c301270cd4 | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
a738f250-d073-5130-8374-fd321a8334f2 | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0
b95d1139-9bb2-583b-8452-54c30ba3c6d5 | note | INSPECTION/TEST METHOD: Visual Inspection
21ff7196-04a1-5bd6-8ff5-109925bdc0b8 | note | RECORD OF CONFORMITY: This ITP signed off
6cb370ec-6a79-5d19-9924-dd36095f07d4 | note | IP
c501ec82-5ac1-5434-9174-b0c466f2bafb | note | RESPONSIBILITY: Fulton Hogan Engineer
24693771-460f-5093-be28-85a9ee305a42 | textbox | Date Completed:
30e06b91-471b-41ec-bd46-8c5f0aa9784d | checkpoint | 2.4 Placement of bedding material
26a66305-6d77-5fb2-a77e-6207e18a4384 | note | FREQUENCY: Each Lot
a605daeb-63fe-5055-a7a4-628c19507a3d | note | ACCEPTANCE CRITERIA: A 75mm minimum layer of compacted class 3 crushed rock shall be used under base of pit
fd47632d-c7fd-5171-b1ee-8cfc56bec5e6 | note | REFERENCE DOCUMENTS: Dwg ELPOD-2021-17
62698e4b-41a3-5ac8-a751-0ac570659e26 | note | INSPECTION/TEST METHOD: Visual Inspection
b3326d67-fb3e-5455-8f15-3d8b73e932ed | note | RECORD OF CONFORMITY: This ITP signed off
aa46cb81-973b-56ed-814e-eaba03bf59de | note | IP
8d4cf218-5f80-5e00-a634-c82cbca04dc9 | note | RESPONSIBILITY: Fulton Hogan Foreman
997ef97c-2e67-55bd-868a-dcbd41ad91c3 | textbox | Date Completed:
80dc04e1-6994-4848-8319-eaf5ff3bc1af | checkpoint | 2.5 Concrete pre-pour inspection
ea8c0afe-3f1d-505e-a26d-4e05faeb4137 | note | FREQUENCY: Each Lot
449a5ea6-468b-5dc4-b7db-806a8ffc1a47 | note | ACCEPTANCE CRITERIA: The site of the concrete pour for the cast in-situ pit shall be inspected by a client supervisor before proceeding. Reinforcement shall be check for correct cover & lap as per drawings
371828bd-af62-571d-8be8-558a2dfcd8a5 | note | REFERENCE DOCUMENTS: Dwg ELPOD-2021-17
ef24a2ff-6cb0-5e20-baf4-c95246d5d265 | note | INSPECTION/TEST METHOD: Visual Inspection
76118506-9aae-5621-9948-ab7c6ddbc99d | note | RECORD OF CONFORMITY: This ITP signed off
ff1f006c-76f3-5550-8186-b206a4c9e111 | note | WP
12a8556f-1599-5d28-9d68-f50b3b9d0ead | note | RESPONSIBILITY: Fulton Hogan Engineer / City of Melbourne Supervisor
f5f0cc6e-276e-5ada-9530-79b096e0d367 | textbox | Date Completed:
47efbf3e-a587-489c-8cef-40fd5995c832 | checkpoint | 2.6 Concrete pour and pit construction
0ff62b93-8da6-5522-be77-2d3704c5d182 | note | FREQUENCY: Each Lot
def4888d-7ed5-5d92-933a-807141feec8e | note | ACCEPTANCE CRITERIA: All pits are to be constructed in accordance with City of Melbourne's Drainage Specification 2012 and Standard Drawing 1P 50318. All pits are to be constructed in accordance with City of Melbourne's Drainage Specification 2012 and Standard Drawing 1P 50318. Pit should also be constructed in accordance with site specific drawings. The walls and slab of the pit shall be 150mm concrete reinforced with SL82 mesh placed centrally. Minimum concrete strength of 32MPa.
4ff4150f-d9fa-52c7-ab18-0284e00abc9b | note | REFERENCE DOCUMENTS: Cl 4.1, Dwg 1P50318
a6ee1354-8f7c-5207-9c10-4b8166b71b6d | note | INSPECTION/TEST METHOD: Visual inspection
1b39a138-b509-5b62-adce-17b399e188e6 | note | RECORD OF CONFORMITY: This ITP signed off
b6da5a3c-c1d4-5159-8374-354cdeb44198 | note | IP
8f4012ec-c34e-52a7-aa3e-2a3cf0d830a5 | note | RESPONSIBILITY: Fulton Hogan Engineer
d75493db-4e8f-5fa9-8948-972befe8d8d1 | textbox | Date Completed:
e8f172e9-04cd-44cf-8d8b-d5840b9edc41 | checkpoint | 2.7 Pit base shaped with concrete to match pipe invert
f7b0ff29-9899-5709-b2e9-3dbd0cb81ca2 | note | FREQUENCY: Each Lot
37e66c5d-6931-5e15-981d-ebcb2a91e20e | note | ACCEPTANCE CRITERIA: Construct as shown on Standard Drawing 1P50318
2ecf2ac4-b917-5d2a-863e-b6e1b09d1e95 | note | REFERENCE DOCUMENTS: Dwg 1P50318
59638440-a14c-5845-80de-5950a6ddfa17 | note | INSPECTION/TEST METHOD: Verify
c3a9914b-5bca-5ded-8756-2595a076eba3 | note | RECORD OF CONFORMITY: This ITP signed off
fccf87b7-b1c6-50e0-9796-88fe7f476534 | note | IP
98e4c6d8-3485-5eee-9743-5466adacc5e9 | note | RESPONSIBILITY: Fulton Hogan Engineer
6ac3f5ba-f4b1-59d8-bbfe-152f301b14aa | textbox | Date Completed:
6010dca2-a345-4382-815c-6ffd8d2528c1 | checkpoint | 2.8 Placement of pit covers
352f595b-ac23-56ca-8e4a-58a02442e51e | note | FREQUENCY: Each Lot
7bbd7b1e-aed8-5e00-abdb-e52c3b8eaafb | note | ACCEPTANCE CRITERIA: All pits shall be fitted with standard City of Melbourne covers specified on the drawings of appropriate class.
b6412b0a-3e1f-5192-a46a-f9ee4856761d | note | REFERENCE DOCUMENTS: Appx 2: Cl 12.4
e125a20d-a409-56e5-8b07-0d0d56f98c40 | note | INSPECTION/TEST METHOD: Verify
7659c38a-be9d-587f-88b4-9fa9978e5160 | note | RECORD OF CONFORMITY: This ITP signed off
44e5bb05-8228-53de-b643-c7fda1be682d | note | IP
fc4d5db1-1238-581c-9415-ba5177d1c0c9 | note | RESPONSIBILITY: Fulton Hogan Engineer
b307e88c-14d2-5d7f-888d-96f6554592ca | textbox | Date Completed:
b9ed2fa3-829c-4132-a728-8f41a71a85c4 | checkpoint | Final Inspection
7d0e95c0-1c3e-58ba-b54c-befa51eab828 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f39cbd64-9a05-5b33-b558-cf761ca1fdd9 | textbox | Print Name:
5a181708-1c96-5923-9c11-4e97db3564d6 | textbox | Position:
0c00c6ee-5226-566c-ac47-8d90c75f7190 | textbox | Date:
de86af6c-b39a-49c1-a9dd-950af0bdeb03 | checklist | ITP-034 - Safety Zone Construction |  | ITP-034 - Safety Zone Construction
592c053d-4de9-4506-8dda-832c102b4c8f | section | Preliminary Works
c32c0172-a1c0-46a4-b021-57207240eab9 | checkpoint | 1.1 Check for correct documentation
0fc069c3-8a9d-52b5-a723-d58e8e039d47 | note | FREQUENCY: Prior to Commencing Activity
ec4adba3-fe97-5e02-847f-1b169713e6c7 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
a8fce97a-0e78-58fe-8dbf-d52940da31fc | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
bfa90eb7-bf54-5484-b943-0dfa2e20d87d | note | INSPECTION/TEST METHOD: Visual Inspection
59457f23-7141-5d47-bd79-933af3af11c6 | note | RECORD OF CONFORMITY: This ITP Signed off
ef4bcf8a-9cee-5098-bb97-154007e55d23 | note | HP*
c8f62898-1f30-579e-81d7-d340f9a8de7c | note | RESPONSIBILITY: Fulton Hogan Engineer
ccf61aaa-8350-52da-8a46-f8682e51996e | textbox | Date Completed:
5214b235-c8ad-4fef-9db4-e8dd7f1a021b | checkpoint | 1.2 Implementation of all measures and controls
fca4106f-7482-5365-b02d-fe624cb043e6 | note | FREQUENCY: Prior to Commencing Activity
23733788-acf7-50e7-8d05-d43c78afbc29 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
61050be2-503c-5e9c-89e2-c8f20eaa2c08 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
f3759995-54c0-5dc9-a98d-a274902fbc98 | note | INSPECTION/TEST METHOD: Inspection
d9808507-6595-50d2-a1cb-a707ca4be3f2 | note | RECORD OF CONFORMITY: This ITP Signed off
fa980c01-1c2e-5296-ba07-4f869d577686 | note | IP
8b71d6e4-e095-5595-8f23-a25198fe0a66 | note | RESPONSIBILITY: Fulton Hogan Engineer
5d3b30d9-c8f3-5124-803a-4c452768c15c | textbox | Date Completed:
cb65326e-08f3-4d13-9700-34748f090501 | checkpoint | 1.3 Material classification
bcc1c52b-0370-572c-ae6d-0fe4d4b99fa4 | note | FREQUENCY: Each Delivery
9abfabb2-c969-51c3-8e43-717fc78dca2b | note | ACCEPTANCE CRITERIA: All kerb shall be inspected at delivery for visible damage. Ensure correct single panel Type A fencing & sleeves are being used and are free of damage.
4b8235b1-f359-5717-af71-d899cab72604 | note | REFERENCE DOCUMENTS: STF T6107
9904d9cd-7d4b-5027-8454-9e0741a6cd91 | note | INSPECTION/TEST METHOD: Inspection
de7c5b00-50c3-5061-bf01-64e986344444 | note | RECORD OF CONFORMITY: This ITP Signed off
baeb4500-b721-5948-9b0a-0b03db131bf2 | note | IP
a05e7f13-b47d-556d-96b9-ce8784cd6337 | note | RESPONSIBILITY: Fulton Hogan Engineer
5ab49eb0-efc2-55da-aca0-50bf3f8bf455 | textbox | Date Completed:
5361fbc1-13d3-47a4-ac64-4394e55e3185 | checkpoint | 1.3 Setting Out
1a2ab982-973d-5d83-a6e8-606e1887f37d | note | FREQUENCY: Each Lot
708050d5-a8c4-5004-8900-0cb624671cf5 | note | ACCEPTANCE CRITERIA: Line and level of kerb, fencing & linemarking shall be set and marked out according to the design and standard drawings.
37af523d-bf54-5d53-ac0c-94b13060f6de | note | REFERENCE DOCUMENTS: Design Drawings Dwg P15671
94aaa178-18fc-5ea2-a934-93a373ef2640 | note | INSPECTION/TEST METHOD: Inspection
900df7a1-6ee8-5d5c-8d00-6b8b00310a38 | note | RECORD OF CONFORMITY: This ITP Signed off
e1352696-9da5-515c-b9fe-8dda823e7e17 | note | WP
8f87863d-7e44-519d-a55d-c1110be9016f | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
50fe781f-0784-52af-bbd4-5576bbbaa7f6 | textbox | Date Completed:
76dc6b2a-c524-4f0f-9e4c-3f64cd7a521d | section | Installation of Concrete Kerb
c2c597d3-805c-44e7-ba42-3c76f61a44ac | checkpoint | 2.1 Base Preparation
81dac243-3175-5ddb-8bb1-8ca1b0eda300 | note | FREQUENCY: Each Lot
573f5f6a-b550-501b-99bf-699b87db47da | note | ACCEPTANCE CRITERIA: Pavement base shall be inspected to be solid free of loose materials.
74648c53-7a77-58be-adfd-692c85fba7b6 | note | REFERENCE DOCUMENTS: Dwg P15671
d9f7cbac-2559-5694-b4fb-489fe862907a | note | INSPECTION/TEST METHOD: Visual Inspection
dd179456-965a-5262-a092-8c46f58300c8 | note | RECORD OF CONFORMITY: This ITP Signed off
d0ebf45c-11a7-57c8-b0d1-06a25268c0de | note | IP
55ea7807-de49-5831-b4a8-0eacdcd881b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
cbae07f7-e235-559e-a0d5-6a3d3a00eefe | textbox | Date Completed:
b2c8db37-84b1-4d1c-8a64-461608f0bf6d | checkpoint | 2.2 Drilling of Holes
95ebc4af-41c4-5a55-8504-9ac24fffda38 | note | FREQUENCY: Each Lot
dfb44868-9816-58dc-af5d-d3084c61a2e8 | note | ACCEPTANCE CRITERIA: Location of holes drilled must align with the provided design drawings. Two holes per stone shall be drilled to an approximate depth of 130mm. The width of the hole drilled shall be minimum 4mm larger than the width of the pin to allow for Chemset material.
b211d74f-4380-55cd-a54b-dcfe42fbedae | note | REFERENCE DOCUMENTS: Dwg P15671
b4d8ee3c-3c18-5b99-8111-c47a4472f84f | note | INSPECTION/TEST METHOD: Visual Inspection
c0f1d7eb-479e-5f85-9b32-e3ef5d2c31f6 | note | RECORD OF CONFORMITY: This ITP Signed off
8487bee7-c608-5f7a-8252-151a62252e97 | note | IP
e9646013-db5d-5a5c-bbdf-c6e59ba6c86d | note | RESPONSIBILITY: Fulton Hogan Engineer
2daba6f7-b059-588b-bce9-dc6a0aa0a236 | textbox | Date Completed:
25b49dbe-e8a4-4003-b64f-6769eda84bb2 | checkpoint | 2.3 Placement of Kerb
cbbc7fe1-9c83-50d5-afb7-b2190b597323 | note | FREQUENCY: Each Lot
c001d2d9-fd9a-594a-ba8b-d4d38cf75c20 | note | ACCEPTANCE CRITERIA: Apply Chemset material and position kerb stones such that the pins sit in the holes allowing the stone to lie flat on the pavement.
e7399f23-f6bd-5a7d-a03e-ef8b33935d0b | note | REFERENCE DOCUMENTS: Dwg P15671
d67ff664-d461-5293-a2ab-9c3bfb7d13a5 | note | INSPECTION/TEST METHOD: Visual Inspection
6021cebf-35bb-5157-8071-b0e3a82ded04 | note | RECORD OF CONFORMITY: This ITP Signed off
abdc4403-8049-5977-a8a9-26bcc64e4b53 | note | IP
83b6cf50-c75c-50ac-893f-28ce235d7a5b | note | RESPONSIBILITY: Fulton Hogan Engineer
a4826c22-1842-50dc-92f1-d436fb9c75f7 | textbox | Date Completed:
5e9af24b-6a18-4eb4-832d-bfabcc2d3324 | section | Installation of Single Panel Guard Rail
bac37641-fd11-4bfa-a767-9560f5229b03 | checkpoint | 3.1 Installation of Rail Post Sleeves
913f1405-6715-5511-ab95-af09b6d9aef6 | note | FREQUENCY: Each Lot
d115328d-68f8-5337-b164-0e9210f8a0c9 | note | ACCEPTANCE CRITERIA: Location of post sleeve's must align with the provided design drawings & 2.4m spacing. Core two 100mm diameter, 300mm deep holes per panel at 2400mm centres. Insert post sleeve and secure using non-shrink structural grout.
cae17f7e-6158-5750-bcfe-e3b10fada6a9 | note | REFERENCE DOCUMENTS: Dwg P15671
135e1168-14e7-5a91-82df-a93ec5fdff14 | note | INSPECTION/TEST METHOD: Visual Inspection
aa24cbc8-d4db-5d56-8ad9-95f62d66d608 | note | RECORD OF CONFORMITY: This ITP Signed off
5fd1bab7-7b8b-5e14-9a41-207e3bc371bb | note | IP
869bfc51-ebc0-53a4-9774-1cc48477e078 | note | RESPONSIBILITY: Fulton Hogan Engineer
087a78dd-4cf1-5043-ae46-ffe9cf53baaa | textbox | Date Completed:
9750ec5f-1fb0-4e4d-acb5-41329d3cce55 | checkpoint | 3.2 Placement of Fencing Panel
ab80a9ff-c698-5d78-b3c6-0b0151d92d42 | note | FREQUENCY: Each Lot
244697dd-6d76-54d7-863e-b581a07c2d5d | note | ACCEPTANCE CRITERIA: Align fencing panel such that the posts sit securely in the installed post sleeves. Ensure fence panel is free of damage and is positioned in accordance with the design line and level.
9768a069-6d83-54cf-8384-4c416452c71e | note | REFERENCE DOCUMENTS: Design Drawing Dwg P15671
c1b00404-fc1a-5a27-a9d8-739f8f47f149 | note | INSPECTION/TEST METHOD: Visual Inspection
dd535384-0703-51ff-8836-9a226a10d492 | note | RECORD OF CONFORMITY: This ITP Signed off
bd13d590-95c5-5a26-be0f-e27a358c47ca | note | IP
41bb2732-1785-52d5-82b8-8942d76e0cad | note | RESPONSIBILITY: Fulton Hogan Engineer
ccc1de5d-4ffe-52f5-8a20-4347cd72f15c | textbox | Date Completed:
d4fa836e-4ee1-4f5b-b985-1fed84806a0a | section | Linemarking
268686da-d1ba-4589-99b6-a97b373a68c3 | checkpoint | 4.1 Linemarking
376d91c2-4301-575c-8fe7-53faf9174d33 | note | FREQUENCY: Each Lot
1af6d83f-1030-5fe2-b79b-e244bba53283 | note | ACCEPTANCE CRITERIA: Linemarking to be completed in accordance with design and standard drawings.
40f6c336-475f-50d0-8c1b-12e0a0cc8393 | note | REFERENCE DOCUMENTS: Design Drawings Dwg P15671
71482c99-e856-5500-ba96-68694b9df0e5 | note | INSPECTION/TEST METHOD: Visual Inspection
3ba0a6b3-9148-535a-8264-6220eb9daa9d | note | RECORD OF CONFORMITY: This ITP Signed off
717c228d-0020-53c1-afcb-2720934319c8 | note | IP
5734164f-925f-5655-b62b-3b23904445ec | note | RESPONSIBILITY: Fulton Hogan Engineer
03aada48-0183-5207-917f-8d4cd8c44572 | textbox | Date Completed:
f90328e9-877d-4a8e-9f8a-e86bfbb6f883 | checkpoint | Final Inspection
e1de1ee9-e9e2-5a8e-9b23-3bd8b7df9da5 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
1cc3aef9-c3bc-557c-befd-353b428987ed | textbox | Print Name:
754b0f78-c289-505c-99f5-10f7ba9a5274 | textbox | Position:
a2921bcd-2e25-5174-b756-098eae9ed6a3 | textbox | Date:
26cb2541-6f44-4ead-8bce-fc05ea3994db | checklist | ITP-035 - Kerb Access Ramp Asphalt Footpath |  | ITP-035 - Kerb Access Ramp Asphalt Footpath
ee591d63-d5a1-4949-b367-249005efe442 | section | Preliminary Works
dcf7ea66-bf3d-4c2e-8c00-b5f6e55cc594 | checkpoint | 1.1 Check for Correct Documentation
269c50c5-4335-55f2-ac6f-ce08f4fc37a2 | note | FREQUENCY: Prior to Commencing Activity
77af6e24-9151-5d13-ba57-c42ac783f492 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
30618744-9a56-51fa-8182-80a91779a366 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
f4df79ce-43a3-5c8e-81b8-cfee3e0fcae5 | note | INSPECTION/TEST METHOD: Visual Inspection
0619d166-deb3-5e8a-9fc3-5e55dbe86675 | note | RECORD OF CONFORMITY: This ITP Signed off
c123da8e-0eff-5219-b590-f52f8f9e8bf5 | note | HP*
f4def454-72c7-5039-9f1a-0f57a352cfaf | note | RESPONSIBILITY: Fulton Hogan Engineer
da10a0da-6aa5-5e2d-a744-634ade79f635 | textbox | Date Completed:
ade28501-ab03-49e7-9912-5bb448d38aad | checkpoint | 1.2 Implementation of all measures and controls
aeba95b4-3a17-5c88-b544-fbb6234856b2 | note | FREQUENCY: Prior to Commencing Activity
343a329a-9a31-56ce-96a2-f657c5dd77b5 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
e65b2830-cef6-51d8-8f5f-98ff17f8f2ad | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
7ff5a8e8-2a99-5c4e-92b4-31e3fe65dfeb | note | INSPECTION/TEST METHOD: Inspection
0f546919-5ade-53d4-85cd-2fbad021a06e | note | RECORD OF CONFORMITY: This ITP Signed off
ba3b6931-2be4-5426-9415-d3739884af79 | note | IP
327739f9-5412-5552-a528-197f83a088dd | note | RESPONSIBILITY: Fulton Hogan Engineer
c101e5b4-b4c4-5c0d-aaed-b62c6fd09001 | textbox | Date Completed:
c43b00d1-6ee1-434d-aee5-a4197382f1fd | checkpoint | 1.3 Existing Bluestone Kerb Demolition / Removal
63aa5d71-12ae-5a19-8194-f94d650ff5d1 | note | FREQUENCY: Each Lot
199e214c-c1f2-574f-af9c-cbbd6c150192 | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone (if applicable) Bluestone shall be salvaged and re-used in new kerb alignment where possible
c8d82dc9-03c2-540d-9bc4-d2a7c8330b67 | note | REFERENCE DOCUMENTS: Work Procedure
6f01147f-870f-5f04-a732-dfd276ee9907 | note | INSPECTION/TEST METHOD: Inspection
b30ccc84-9218-5fc3-a506-d4cad5c29c2c | note | RECORD OF CONFORMITY: This ITP Signed off
ebd94304-45e5-50c4-a673-25dc975d69dc | note | IP
a271eb68-6ef4-5bc0-990c-9ebc1b654b7d | note | RESPONSIBILITY: Fulton Hogan Engineer
30e9c808-b302-5c4f-840e-ab577a607ea4 | textbox | Date Completed:
3a4b20fa-2c0f-4abb-9e47-b27afb48e5d3 | checkpoint | 1.4 Check Materials
17bc89cb-f743-5d0a-8870-73a92af336d2 | note | FREQUENCY: Prior to Commencing Activity
10e3a094-a533-5662-807c-1833997a6f61 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Granite Tactiles. Granite inlay shall be 50mm wide x 40mm thick Spring White Granite Inlay.
8d676394-9d79-5f49-a4c8-472e57c25ea4 | note | REFERENCE DOCUMENTS: Receivable Inspection List
7442db3b-e6bf-5e0b-9606-258528ab1f27 | note | INSPECTION/TEST METHOD: Visual Inspection
a135e28d-9746-5571-9ae5-91d641514379 | note | RECORD OF CONFORMITY: This ITP Signed off
3d5801e0-0b5c-55f0-96ae-e54787c86615 | note | HP*
53a2386f-cac4-5db7-9c76-a7c5524c69d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
0fb8885a-5876-5074-bd8a-7740ad45997b | textbox | Date Completed:
e0ffc64d-1f7b-482c-92e8-514375da89c5 | checkpoint | 1.5 Setting out
3db4c3c4-8cab-5611-9d7a-2c6b11eb71ec | note | FREQUENCY: Each Lot
ae527ad0-9330-57bd-a3ca-5429f47629ee | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
73ef6965-526b-5b66-b8ea-c746597e9646 | note | REFERENCE DOCUMENTS: Work Procedure
fcef10d2-ebe5-569e-b6ba-5328c590dfec | note | INSPECTION/TEST METHOD: Inspection
de6f5fb2-8d39-59d9-8abd-f7d55d42f20d | note | RECORD OF CONFORMITY: This ITP Signed off
df210f57-6257-5faa-83f1-cd086162390b | note | WP
4c183b5d-2855-5068-989a-846d983c870b | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
a2e69996-dca1-5a08-a190-5b69839b60bb | textbox | Date Completed:
b1444a37-4b0f-4003-b880-5fc71fd49574 | section | Construction of Access Ramp Asphalt Footpath
68e7085c-a8f2-40b0-9482-bb0eedb7e5b7 | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
2cc31c67-71d9-5ffe-8afd-5d88d3a41105 | note | FREQUENCY: Each Lot
efec4ea2-75c5-549b-b2be-cf455fbaed8a | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels. Bluestone kerb shall be placed on a bed of low slump 20MPa concrete, minimum 75mm thickness. Formed groove of 10x25mm in concrete face shall be filled with caulk
ec0ca6b0-02e7-5205-b77e-cfe202aa76ae | note | REFERENCE DOCUMENTS: Dwg 1P50201
8981377f-f8f7-544a-b319-27ac1327632a | note | INSPECTION/TEST METHOD: Visual Inspection
d8f9045b-0ca2-5126-a21b-13a406077acc | note | RECORD OF CONFORMITY: This ITP Signed off
ffdb29a2-bb86-5657-8c6e-bc431105b9bf | note | IP
d79a940e-8808-572c-b08e-f1645fe02782 | note | RESPONSIBILITY: Fulton Hogan Engineer
e64188b9-5608-5e5d-b587-358f4c3bdcc4 | textbox | Date Completed:
f1ab9b20-1f03-41dd-aaf7-dc82de986846 | checkpoint | 2.2 Base preparation
a78f242e-276c-5cbf-b6f8-f067beead71b | note | FREQUENCY: Each lot
79801543-d9a5-5a97-8e02-a3bce7cab18d | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
78aa16c9-ef2c-5b7f-9108-869532fce6e7 | note | REFERENCE DOCUMENTS: Dwg 1P50201
7b09f44a-565c-575b-b899-f38531ba83a7 | note | INSPECTION/TEST METHOD: Visual Inspection
331a8893-dd6e-5474-9806-68b9476597ca | note | RECORD OF CONFORMITY: This ITP signed off
20a9d807-5e8b-5bfd-8671-fb64209c1b07 | note | IP
fba4ff62-cca0-5e3a-ab73-b309a6eb52bb | note | RESPONSIBILITY: Fulton Hogan Engineer
5bbcbd19-4182-5772-97a8-681d6023473f | textbox | Date Completed:
b47cedcf-ada7-45e3-9674-7d41a61bda12 | checkpoint | 2.3 Installation of Kerb & Gutter Blustones
47da9a64-ee82-58a9-b014-aab198dc4806 | note | FREQUENCY: Each lot
bf5e0ba8-97b9-5f18-ac49-397e5bef506e | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar.
bacfed7c-16c6-5d83-95e5-abb0ae0480df | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
7521dc29-fbd2-5066-92ba-0bee7084d7de | note | INSPECTION/TEST METHOD: Visual Inspection
ef3d88fd-327f-5924-96ef-e0a4d0b42aaa | note | RECORD OF CONFORMITY: This ITP Signed off
70e7f742-7b14-5493-9f07-340adefdf355 | note | IP
bbd3f038-93f9-54c3-b32a-3790b11babd2 | note | RESPONSIBILITY: Fulton Hogan Engineer
a82d928f-9e2b-55e8-a259-d2af5adf4dd4 | textbox | Date Completed:
845e7533-ab04-485f-8a4c-4ec0e91f84ca | checkpoint | 2.4 Asphalt placement
3ae8f9ac-ca4c-50fe-9ea3-305d8b264a0b | note | FREQUENCY: Each Lot
2482b55c-510f-5ea2-9133-e1d03bc5c413 | note | ACCEPTANCE CRITERIA: Asphalt ramp to match adjoint asphalt footpath and sit flush with channel at grade of ramp using 7mm type N hot mix asphalt. Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8.
f4648241-1193-5d13-a6ed-3ed43f209c8f | note | REFERENCE DOCUMENTS: Dwg 1P50200
39db275a-08f4-5014-92a7-f5428c9cdc32 | note | INSPECTION/TEST METHOD: Visual Inspection
6697926c-8549-5892-a76c-4a289c043502 | note | RECORD OF CONFORMITY: This ITP Signed off
a9a9a300-6586-5bb3-afec-d038e6d28f72 | note | IP
40ca199a-74c9-5f0b-a5b5-b5565dd13ec1 | note | RESPONSIBILITY: Fulton Hogan Engineer
aaab07b5-21f2-5661-99ae-2754b67ef078 | textbox | Date Completed:
dab9ad62-4b20-42c8-a898-301463f72471 | checkpoint | 2.5 Installation of Pandatac Granite Tactiles
8b7e0cb1-d6a5-595b-bafc-875a14b170e7 | note | FREQUENCY: Each Lot
4822926b-103f-5c48-9722-54682465514b | note | ACCEPTANCE CRITERIA: Granite tactiles shall be placed in accordance with Standard Drawing 1P50200 & drawings.
dd1903fa-2b65-57bb-acfe-5663594b9917 | note | REFERENCE DOCUMENTS: Dwg 1P50200
9d260bbd-3dce-5ba5-b926-c89f26867d51 | note | INSPECTION/TEST METHOD: Visual Inspection
468145c9-e7aa-5afd-88c4-d3fd4734d987 | note | RECORD OF CONFORMITY: This ITP Signed off
47f67a6d-ded6-5e3a-ae4d-748891b5e7fb | note | IP
4367f07a-bc04-5ec9-87b3-6f1ff9c39752 | note | RESPONSIBILITY: Fulton Hogan Engineer
4ce9a59a-0d13-53cd-a8bc-f26b7e2af66a | textbox | Date Completed:
bde4f4d3-6719-4e2a-82f9-514aa749ba74 | section | Completion
f72ab9ba-4731-4772-b832-c19688e50dee | checkpoint | 3.1 Completion
0388b6d0-5435-5b26-8347-ca86f4aec718 | note | FREQUENCY: Each lot
e4a3ee74-3488-5af5-a222-3d0ed3b96b3d | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste Bluestone kerb is free of mortar stains and cleaned to satisfaction.
3a97c709-a75f-547b-ab0f-f4e61204e75f | note | REFERENCE DOCUMENTS: Visual Inspection
0f546ba3-764c-5859-948c-b19dafff4dfd | note | INSPECTION/TEST METHOD: Visual Inspection
7bc8ea4d-fa3a-5c4f-a81b-3ed78e126645 | note | RECORD OF CONFORMITY: This ITP Signed off
a27f3b59-e2d1-5890-be1e-dcc0d5c08573 | note | IP
14bd36d8-a664-5bdf-bf6e-9640e862fe9b | note | RESPONSIBILITY: Fulton Hogan Engineer
34028fe8-e367-5e02-9460-fd8ff6c26f4d | textbox | Date Completed:
8e042ab4-897b-4c7e-9d1c-d9a731260d9e | checkpoint | Final Inspection
6285094f-aacd-5f3d-9b4f-1d2e792c841c | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
be1085f2-e4d7-579c-9d5d-5205917669a2 | textbox | Print Name:
7f8a57c8-06e5-5cc6-93c1-f3df770ae309 | textbox | Position:
e8f5ee14-63a2-530b-a9ce-127c470f5a85 | textbox | Date:
25d7565f-5736-496a-8704-c9660d16debf | checklist | ITP-036 - Kerb Access Ramp Bluestone Footpath |  | ITP-036 - Kerb Access Ramp Bluestone Footpath
0b3593f3-1c12-471b-9301-c32445cfa140 | section | Preliminary Works
688e3f50-14fc-44e3-aa1d-6ffbe222eb41 | checkpoint | 1.1 Check for Correct Documentation
52a82d19-ec0c-56e3-90c4-f85541b6c528 | note | FREQUENCY: Prior to Commencing Activity
0a74bd90-1b91-51c3-96db-97290d11357f | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
e6033190-16fe-5ebb-a278-a6b021d7c863 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
0fdcac02-c350-536b-8617-90423224d98e | note | INSPECTION/TEST METHOD: Visual Inspection
9b0e1498-cc0b-5d33-a429-c74a579f3985 | note | RECORD OF CONFORMITY: This ITP Signed off
bc19dbf7-f4b7-5be9-9480-03f3067b327f | note | HP*
584bd54e-daeb-55ae-9e8e-e8a581664b98 | note | RESPONSIBILITY: Fulton Hogan Engineer
61c4586d-1882-5917-9dda-b7d77e7a15bc | textbox | Date Completed:
039129e0-ad40-4bad-b51d-af42e7643145 | checkpoint | 1.2 Implementation of all measures and controls
49057b71-ecef-5b2f-a685-288fa05e769f | note | FREQUENCY: Prior to Commencing Activity
3220773b-998e-53ff-b214-9d46f72bd022 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
d6530e4a-d954-59d8-9f69-ef10724ae7c1 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
ec80cb64-7a70-5f74-b268-bbf5e4dfb0c2 | note | INSPECTION/TEST METHOD: Inspection
342425c4-f3da-5164-82aa-add7acece86b | note | RECORD OF CONFORMITY: This ITP Signed off
4d204ad3-588f-54f5-959f-727e514880d0 | note | IP
7ffd214e-0473-554c-8c0b-0a97f7501b02 | note | RESPONSIBILITY: Fulton Hogan Engineer
bac8af11-47ce-523d-badc-30aa39fba668 | textbox | Date Completed:
80babcc9-4562-413b-9284-021ef481d3de | checkpoint | 1.3 Existing Bluestone Kerb Demolition / Removal
ab0c6ec7-df48-5664-a433-c644aee7097a | note | FREQUENCY: Each Lot
7c6f569e-c681-5469-951c-b6f32b3ed29d | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone (if applicable) Bluestone shall be salvaged and re-used in new kerb alignment where possible
c6868cbc-1f85-568c-a273-ee239da2556b | note | REFERENCE DOCUMENTS: Work Procedure
452a9189-7249-5d0e-8fe5-757023656522 | note | INSPECTION/TEST METHOD: Inspection
39ff74cc-7862-538b-9637-2d74c8fa1de2 | note | RECORD OF CONFORMITY: This ITP Signed off
df2c841a-208d-5073-baf3-c1a411862826 | note | IP
87291d57-9dfb-5b79-b7e3-87f66f93b812 | note | RESPONSIBILITY: Fulton Hogan Engineer
4c661aaa-e156-5b1b-9818-5772d910b141 | textbox | Date Completed:
5cde3d72-e3b3-4672-9045-2ae97432a0af | checkpoint | 1.4 Check Materials
e327a5ce-2a04-56bf-9e63-07a6f66ae583 | note | FREQUENCY: Prior to Commencing Activity
e5114e7f-793d-5aeb-b212-7899edbb405b | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Granite Tactiles. Granite inlay shall be 50mm wide x 40mm thick Spring White Granite Inlay.
d60b0906-683a-57ef-b354-f6131a6f9d9c | note | REFERENCE DOCUMENTS: Receivable Inspection List
a3ccf43c-aa8d-5624-bc6f-e4af87cadb2b | note | INSPECTION/TEST METHOD: Visual Inspection
653f887a-2864-5a63-a889-9469047d19da | note | RECORD OF CONFORMITY: This ITP Signed off
72fce0d1-73d0-5bcb-9d91-d8ba1f59116b | note | HP*
4ae4f0a5-5855-5929-9a14-9aa4b40da0bb | note | RESPONSIBILITY: Fulton Hogan Engineer
299d7987-1b32-549b-a190-5a2466d28b74 | textbox | Date Completed:
3dbc03a7-a781-46f2-9167-b9f522085d07 | checkpoint | 1.5 Setting out
31a701b0-bbab-5283-a013-65a75375a2f3 | note | FREQUENCY: Each Lot
be7441cb-d317-5ac9-a567-905c33e984d1 | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
c80b481f-a8d3-523f-a117-681ae2f0a01d | note | REFERENCE DOCUMENTS: Work Procedure
56fb8338-2bc9-535d-aa08-90fa35be8064 | note | INSPECTION/TEST METHOD: Inspection
c488b3eb-16b9-599c-993c-bdc4d342f24c | note | RECORD OF CONFORMITY: This ITP Signed off
8ad4de1b-cec2-5e31-8c7f-9ed98ac861f2 | note | WP
d0c1e82b-8d20-531b-bfb5-1913a4e008cb | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
51a70221-b718-522e-b320-41d9f70a363a | textbox | Date Completed:
f153a454-fa28-4b14-b62b-23f76955f258 | section | Construction of Access Ramp Bluestone Footpath
7fba1661-5af5-4ece-a0ef-708857e702bf | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
0d1ff6d0-b93e-57a4-adb1-c002374bc45b | note | FREQUENCY: Each Lot
55d3a471-c121-5bbd-9f6f-44e019f57b38 | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels. Bluestone kerb shall be placed on a bed of low slump 20MPa concrete, minimum 75mm thickness. Formed groove of 10x25mm in concrete face shall be filled with caulk
22eaee7a-2294-5c7e-a5ba-5d072b5fe431 | note | REFERENCE DOCUMENTS: Dwg 1P50201
7f236e87-5ad0-5753-a780-441899617ca4 | note | INSPECTION/TEST METHOD: Visual Inspection
706a4b98-7524-538c-8659-9dc8bab16046 | note | RECORD OF CONFORMITY: This ITP Signed off
9ecc27c0-3db7-59e1-ad16-77d88ad763ac | note | IP
cebfa0cd-ffd2-56e3-9955-233ca351c406 | note | RESPONSIBILITY: Fulton Hogan Engineer
fc5c889d-fff5-535a-8fde-38ca6da7cfe6 | textbox | Date Completed:
042aa90c-a509-472f-b5ac-6d72ecd09ceb | checkpoint | 2.2 Base preparation
7df007d9-7ae9-5fd3-b023-82de931cfe8c | note | FREQUENCY: Each lot
aeca823e-e1d2-5390-8d6a-c1c0aed0f7e9 | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
76ef5fc8-1ddb-5638-aadc-d6fd4bee5f04 | note | REFERENCE DOCUMENTS: Dwg 1P50201
4ab996dc-a468-5533-8cb3-a0c63065891d | note | INSPECTION/TEST METHOD: Visual Inspection
d349eac5-20f1-5325-a65d-3967645a8e18 | note | RECORD OF CONFORMITY: This ITP signed off
126ef5e5-d3ec-5281-bacb-5f85e4df5b45 | note | IP
5542865a-c848-5c99-aaeb-edc79837339e | note | RESPONSIBILITY: Fulton Hogan Engineer
8ecbfcfa-0c61-56df-9f99-890fb8491392 | textbox | Date Completed:
3728a1ab-e6e2-4213-b04a-6465381b89f1 | checkpoint | 2.3 Installation of Kerb & Gutter Blustones
3ee56d97-6244-52f8-b626-dedb4d282e9c | note | FREQUENCY: Each lot
2f169779-f6ea-5dcb-b9ca-6c84a782f3fd | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar.
d96020f9-5fb3-58a3-8b02-aabd3172594f | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
e83e726c-2c9a-529a-bcf3-c055bba54cdb | note | INSPECTION/TEST METHOD: Visual Inspection
4ba37a8c-1618-5e0d-9e47-21b35b8d59a4 | note | RECORD OF CONFORMITY: This ITP Signed off
e033e206-77c1-5eaa-bfbb-61e99887aa1d | note | IP
8772d12f-73b6-53a5-8a33-3c84d68cf539 | note | RESPONSIBILITY: Fulton Hogan Engineer
10f67431-785f-5894-873d-1322f8c80891 | textbox | Date Completed:
1cc76863-1dcc-4b2c-b6af-d98c26bdbb59 | checkpoint | 2.4 Placement of bluestone pavers on mortar bed
63988fc2-7712-55a0-87b8-56793eba1d3c | note | FREQUENCY: Each lot
d4eb2237-1cb9-5ab9-8f02-8232163227d7 | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402 on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying Kerb access ramp wings shall be at an angle of 45° or as per design and the ramp gradient shall not exceed 1:8. Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
973179b1-9cb0-5536-ace3-d115afe3c676 | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
ad173cdf-6b60-5b28-8eff-84d93d5de3cf | note | INSPECTION/TEST METHOD: Visual Inspection
8376f787-b372-5107-902d-8167260aa378 | note | RECORD OF CONFORMITY: This ITP Signed off
effe72bb-0052-56b9-aa57-061e3965e23a | note | HP
9f1fc268-f65e-5a4b-9877-2764f5a6482c | note | RESPONSIBILITY: Fulton Hogan Engineer
628b10d1-9f77-5e22-9ee2-997cf6e4452a | textbox | Date Completed:
49f87046-fb34-4c98-b711-340be5f3b8bd | checkpoint | 2.5 Curing
d5ac25e0-f0ad-5752-a9e1-6a6266adcd8f | note | FREQUENCY: Each lot
6a36d447-30e5-5b37-ae96-33b18aaa5c22 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic Where required, ply shall be laid over area of works
d5bdb2c7-84ad-59c0-abfc-77aec2f77c41 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
736083fa-21c5-5cb5-b8bc-47d838a48aa7 | note | INSPECTION/TEST METHOD: Visual Inspection
f0f41911-799e-5ddb-be56-80e9aeeea1ad | note | RECORD OF CONFORMITY: This ITP Signed off
af9bc0ab-1618-5f93-a027-a3ab842d1275 | note | IP
33c88afc-cda9-59c9-beeb-6c4c5c447b6b | note | RESPONSIBILITY: Fulton Hogan Engineer
6bf64d62-09f9-58e8-a1cb-406e18404e0c | textbox | Date Completed:
bf4fa1c9-857f-4f9f-9db1-5c1dd779e5e1 | checkpoint | 2.6 Grouting
d19502a1-9960-5cec-bc53-009c2d977e62 | note | FREQUENCY: Each lot
7c515a70-dc99-5d8f-8e48-2bb3ecdb9fb8 | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using Lanko Durabed to specified mixture content. Grout shall be spread & clean appropriately as required.
2dafafdd-ae9c-58b2-bda1-7a51aad5c511 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
88dbcd67-b5b2-516f-b38f-828ddf17fb00 | note | INSPECTION/TEST METHOD: Visual Inspection
334fe15c-402b-5249-b75c-3ae13a316f6d | note | RECORD OF CONFORMITY: This ITP Signed off
8b25f0f1-80e5-5799-90d2-7db921648b47 | note | HP*
6114bd38-f29d-5d37-a89c-3eff7cf43448 | note | RESPONSIBILITY: Fulton Hogan Engineer
69045bf6-7f4c-52dd-8217-b7cef302796f | textbox | Date Completed:
486c5cac-73d1-4652-9665-0178fc5ef76e | checkpoint | 2.7 Installation of Versatac Granite Tactiles and Granite Inlay
4a83cfb9-5a64-5b66-9d18-7475ce6ff673 | note | FREQUENCY: Each Lot
5b5463ad-6499-5cfb-912d-ad1edaad7579 | note | ACCEPTANCE CRITERIA: Granite tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201 with surface deviation of under 5mm.
b64b0af9-12b7-5db3-be49-486c3d23a90f | note | REFERENCE DOCUMENTS: Dwg 1P50201
f14ebd65-f4cf-5f6e-a21e-7452d3f1a0fa | note | INSPECTION/TEST METHOD: Verify
a362edf4-2729-5f81-9603-3eeea2cd7c2c | note | RECORD OF CONFORMITY: This ITP Signed off
f9a31461-2dda-508d-bc15-b0accd859462 | note | HP
424d42bd-6df8-5c61-8f20-3df21f3653ac | note | RESPONSIBILITY: Fulton Hogan Engineer
a32b07ee-a476-58e3-97dc-bddfd37a0a19 | textbox | Date Completed:
f72932ed-29f9-4250-bfd4-50f5ea7cc1f4 | section | Completion
efefcfa7-dc38-4cac-b277-c7c189ae47dc | checkpoint | 4.1 Completion
87451054-568e-5756-be2b-c9decdbddd27 | note | FREQUENCY: Each lot
535a060e-b0e0-5a29-ae29-219c485f6502 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste Bluestone pavement is free of mortar stains and cleaned to satisfaction
d864fa9a-bacf-53c9-9deb-5bf0ca8c3c44 | note | REFERENCE DOCUMENTS: Visual Inspection
2d0a96b0-2057-5ca0-aa9e-08f9551d7a5e | note | INSPECTION/TEST METHOD: Visual Inspection
2a2402e2-84ee-5333-8167-d18ca640043c | note | RECORD OF CONFORMITY: This ITP Signed off
5cc4fe1d-22d7-5540-a9ba-2f7a1f41b6b2 | note | IP
dc1f0f4a-e91a-547a-90d3-138d09beaed3 | note | RESPONSIBILITY: Fulton Hogan Engineer
6e2b4d67-5d9e-5672-9845-2205c6eb2d9c | textbox | Date Completed:
ed32126a-613f-4a19-a7ea-e326df4104db | checkpoint | Final Inspection
5c8f6d1c-fc16-5ec6-84e5-58c8b623e131 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
dec04793-661d-57b6-a2b9-7c1562f14aa9 | textbox | Print Name:
210132a6-9b5d-5fd8-8f62-a36ef4d0da1d | textbox | Position:
be62c7f8-80d4-5ddf-ae58-6d043228323e | textbox | Date:

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
22c8d4e2-43c1-4ff1-b352-8a3b479c7241 | checklist | ITP-001 - Subgrade Preparation Rev2 |  | ITP-001 - Subgrade Preparation Rev2
db55e8a9-6c59-44d3-9ff8-b7f2f2545ac2 | section | Preliminary Works
20c42753-6745-4aed-81d7-89cf1fb184fb | checkpoint | 1.1 - Check for correct documentation
6d135741-fdf3-5c81-afc0-4d84950658bf | note | FREQUENCY: Prior to commencing any activity
47524701-92e3-5f37-82e4-7d4ef1e770fb | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
76f9954f-9670-5a46-9775-19d03d5f507b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
0229de79-9ea0-5940-b602-91ed8408e2a5 | note | INSPECTION/TEST METHOD: Visual inspection
460a2005-8ea1-5249-afd7-a94a00d01aef | note | RECORD OF CONFORMITY: This ITP signed off
31791835-317e-55ba-a5c1-020440375591 | note | WP
65dc333c-1cc0-5148-86d2-39f79cd9ecde | note | RESPONSIBILITY: Fulton Hogan
057255ca-b48a-5e4b-aa4f-9303d896529d | textbox | Date Completed:
c0d99d65-557d-41e6-9f3b-f3f90e086c59 | checkpoint | 1.2 - Implementation of all measures and controls
0c7bf44d-ada5-5e4b-8654-f5c03c745add | note | FREQUENCY: Prior to commencing any activity
38c9ec1c-705e-5ca6-98ab-8c10cdd9782c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
493b071c-4c03-5875-a887-a1d18dd2b444 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
4b198fde-1396-5b3c-8afa-f1eeb76a5956 | note | INSPECTION/TEST METHOD: Visual Inspection
25a2a432-32a8-57d3-9f64-389983207e4d | note | RECORD OF CONFORMITY: This ITP signed off
308786a3-3156-56db-b24c-3da8df99552c | note | WP
a08c9c16-93c3-5c74-ab84-a7aff6b7100c | note | RESPONSIBILITY: Fulton Hogan
94c7ab95-c3f1-5442-89aa-fafe47debb06 | textbox | Date Completed:
e6c30e0c-07bb-4d80-b368-ac190dc2516a | checkpoint | 1.3 - Selection and approval of Disposal Site
d7df21a6-21de-5e27-b4d6-72e68d8d46e9 | note | FREQUENCY: Prior to commencing any activity
ad5dba16-dcca-5765-85df-43fcb2b64f74 | note | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accordance with Yarra Trams site classification report. It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
be9e1cc1-4f83-588a-a84b-d6f6d21f8159 | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019- ST-0033 CL. 4.2.1.5.
63dc52e4-82bd-53d2-954a-4e1363bcfc5c | note | INSPECTION/TEST METHOD: Verify
e3f13a5f-0717-5bb7-b478-44f439e32acf | note | RECORD OF CONFORMITY: This ITP signed off
d2bcba75-4ddf-5372-9304-8e7fe8b30747 | note | WP
8901fc9a-7fbd-5665-8028-308081cd81d9 | note | RESPONSIBILITY: Fulton Hogan
990b7e2e-13a6-5ce1-a1a1-ef96ebea32df | textbox | Date Completed:
1e581036-cffe-4b6b-9aad-abcd2b4d9d27 | section | Construction Works
80edc72c-c9d7-44af-a152-27f28da51875 | checkpoint | 2.1 - Excavation
16f17000-7de3-57af-aa57-ed36321f4b16 | note | FREQUENCY: Each lot
e8d5cf5f-7bed-585e-a006-81d84cc78f1c | note | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of works
fb590a42-d484-551a-98b1-2b9840f5f6b0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4. Subgrade Preparation Work Procedure
e110f9ef-8965-573c-b0b1-53c0ffcb974f | note | INSPECTION/TEST METHOD: Verify
46b088ae-baf0-5df3-9a8c-b08e13d584df | note | RECORD OF CONFORMITY: This ITP Signed Off
4f1092e8-4b66-53d6-b139-02c091e2fca6 | note | IP
257aea00-e6b6-54bf-ae25-63dc62281497 | note | RESPONSIBILITY: Fulton Hogan
9d5a5aff-6434-5275-a348-062a983bb709 | textbox | Date Completed:
db2ff37a-2207-4651-a644-fb345bce26e8 | checkpoint | 2.2 - Reinstatement of bonds
1ebd15df-916e-580f-9e5e-ae5091a6b337 | note | FREQUENCY:
aa0ed375-65c6-5300-9a95-dcb6e79a3a4b | note | ACCEPTANCE CRITERIA: Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables. All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
1a56239e-6949-5ca4-9da3-b7670f8275ac | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
73185c80-011c-551d-a12d-b80e13a81305 | note | INSPECTION/TEST METHOD: Verify
904cd888-39f5-5372-a16a-98ed437c40f0 | note | RECORD OF CONFORMITY: This ITP Signed Off
88d5dac0-ec3e-57c8-8a79-a205f996c50b | note | IP
73d88a77-0fa9-5df9-86b8-e46c84afae1b | note | RESPONSIBILITY: Fulton Hogan
57e8ca6c-ef0e-5d93-a5fe-aae82932e948 | textbox | Date Completed:
6bbddad1-0611-4cb2-8f29-b3daedff44ae | checkpoint | 2.3 - Inspection of Subgrade Material
2db97c07-19eb-5391-bc89-36b2cee65b34 | note | FREQUENCY: Each lot
cdf12a30-ad66-5c35-b2b8-c102ca36e155 | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
c51c6b86-83af-5b56-889b-bdf7ce71668e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
ff3d915d-4943-57c2-a423-01e4bdcbf02b | note | INSPECTION/TEST METHOD: Verify
39a69f92-9dc3-5fd3-adfa-e43406656e4b | note | RECORD OF CONFORMITY: This ITP Signed Off
3fb5df61-986c-5dfe-a767-333f11326929 | note | HP
d78058bd-5d8b-50c8-9902-f0fc620cd80c | note | RESPONSIBILITY: Fulton Hogan Engineer & Yarra Trams Superintendent
c799a581-5f43-5aef-80a6-b130319e3e83 | textbox | Date Completed:
dcd1ea8c-81a4-448e-ac65-2614a44eda68 | signoff | Authority holdpoint
0525ccb1-b0ab-412a-bd74-ad5ca7310b6a | checkpoint | 2.4 - Width and Level conformity
5d7b7517-3caa-5754-87fe-f9f13530d6dc | note | FREQUENCY: Each Lot
0ba71506-d1ec-506c-bb8a-d032ad45ef92 | note | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings. No point in the general surface shall vary more than 12mm from a 3m straight edge. Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
4b0aa6cf-41e2-51a5-a0ac-1b24d0956389 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
4c77d631-e276-5ab8-88de-363681d637ef | note | INSPECTION/TEST METHOD: Survey Report
f95a3082-8ead-554e-bc63-d90b40c9d403 | note | RECORD OF CONFORMITY: Survey Record
ef134f40-3ac4-5c5d-881e-63543cce5159 | note | IP
de6e9b33-be31-5930-b7d3-77ba6e182b47 | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
ee5c315c-07e3-5773-8b53-c1b788d9eb93 | textbox | Date Completed:
1e17e98b-a914-4fc1-a28c-fb81d59042d5 | checkpoint | Final Inspection
f96b6138-4a05-5ff7-a8a3-f0491dce67d8 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
8e6193d4-0cb2-536a-a3a4-9cf8a9b526bd | textbox | Print Name:
5f1712c0-8255-56f1-a703-1a9890861ba1 | textbox | Position:
acdaba52-13e2-536e-9bbe-263c5cd5dfbb | textbox | Date:
525e6345-032d-4c2b-a3c8-a393f58ffb6b | checklist | ITP-01-021 - Type B Fill Placement |  | ITP-01-021 - Type B Fill Placement
f58dad54-61c3-4b6f-826d-7ba2e8ff38d2 | section | 1 Preliminary Works
3215eacf-f935-40d7-baa2-deb84c363024 | checkpoint | 1.1 - The current revision drawings/documents are being used including subcontractors copy.
abf02d93-676e-5a06-a5fd-ced81b925390 | note | Frequency: Prior to commencing
bc87cd60-f0a7-5bfe-aee2-ee61b3ddc099 | note | Acceptance Criteria: Current revision drawing/documents are being used including the subcontractors copy.
24d4d74e-89f7-507c-a655-9fa6af420e43 | note | Reference Documents: Drawings and drawing registers
ef21e2fd-2ce7-5f92-8f17-07a95f93c57b | note | Inspection / Test Method: Visual Inspection
e2d2031b-009f-5cf6-abfa-be9a9b60b3a6 | note | Record of conformity: This ITP Signed Off
589568ff-dfe1-54e5-8920-afca7da24cba | note | HP*
7e91c435-82da-5277-a0ed-3084f2b01890 | note | Responsibility: Site Engineer / Site Foreman
6ec6606f-d55f-4e5b-9141-f569d2760278 | checkpoint | 1.2 - Implementation of all measures and controls
a7d4d55a-05e3-5662-a871-358f98404811 | note | Frequency: Prior to Placement/ Each Lot
926deed0-2753-574c-9074-6b6326f49c90 | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
81648378-47d1-571a-a5b7-a1f0daaaa204 | note | Reference Documents: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS, WP001.02
253907e8-8eef-5fa2-861f-aec7aa4a2a71 | note | Inspection / Test Method: Visual Inspection
c05e6437-c8cf-56c4-a4a1-6973fcba92c6 | note | Record of conformity: This ITP Signed Off
f3058006-7d82-5bb3-a0fa-3723cec9520d | note | HP*
42e8b35f-8340-54b2-b4bc-788c3a12bc67 | note | Responsibility: Site Engineer / Site Foreman
4183dc8b-b7ed-400e-b9bd-0d70b57cf17d | checkpoint | 1.3 - Verify Material
17bbb551-87fe-5dd3-b62b-fe0e06eb98bb | note | Frequency: Prior to Placement/ Each Lot
4e6cdd74-2598-501d-917c-de53a73c29ab | note | Acceptance Criteria: Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20. Materials that exhibit swells greater than or equal to 2.5% shall be classified as expansive and shall only be used as Type B material if approved by the Superintendent. Material within the top 400 mm of top of Type B material shall have a swell less than 2.5%. Materials that exhibit swells of 5% or greater are not permitted.
72c69b86-6532-5430-9c14-86d414f48876 | note | Reference Documents: VicRoads Spec. Cl. 204.04(c)
1edba67c-12d4-501c-919f-875f467a3a79 | note | Inspection / Test Method: Site Inspection
9787d39e-4a99-59bd-84f8-a83ead95d15e | note | Record of conformity: Test Record (If silt is observed)
25b5afe8-d8f6-50ac-856f-f0a478353688 | note | HP*
386b51db-218b-5623-90f2-e3ec938f83b1 | note | Responsibility: Site Engineer / Site Foreman
68fca1b3-301f-4f8a-8ae9-5f882d030ba5 | checkpoint | 1.4 - Excavation Permit
48b1176e-f2f9-50b7-9d01-e3ed62d16869 | note | Frequency: Each lot
64431473-5b19-550a-b241-7fea34d19dc2 | note | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
49c72e1e-b838-5c17-841e-c43453d3af74 | note | Reference Documents: Excavation permit
ee609b69-0cc0-5bb8-a44e-8346a8d77085 | note | Inspection / Test Method: Verify
9e16c2db-f208-5385-9330-26259d49ea1c | note | Record of conformity: This ITP Signed Off
b4294489-d31a-5e6e-91e2-3fc82658cf89 | note | HP*
ecc0d3ff-6653-51d4-b1b3-9a14512555c4 | note | Responsibility: Site Engineer
d9f8c167-3d1d-4bf7-b04d-12e5c20e3762 | section | 2 Construction Works
d0b3f5fb-1f74-4f8a-af1b-f42da1594d3e | checkpoint | 2.1 - Survey set-out
107b7e98-5ae9-59f1-aebf-7f61271b6934 | note | Frequency: Prior to Commencing Excavation
334339a0-0809-5159-9702-8af7e312ef0c | note | Acceptance Criteria: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
2e5f07da-e432-52d5-b07b-4b43f0891e43 | note | Reference Documents: Latest IFC Drawings
64019f21-0627-5cc2-b955-0b71d15c16d0 | note | Inspection / Test Method: Site Inspection
48a22c4a-1a9a-5961-a921-1afc9572f7be | note | Record of conformity: Survey records & pegs on the ground
68979ed7-cfea-5163-b13f-655f3d0cab63 | note | SCP
5072e097-55e4-5d88-896f-e5994f99eb79 | note | Responsibility: Site Engineer/ Surveyor
da0948ec-6903-4684-bf5f-6d66e7cdda89 | checkpoint | 2.2 - Inspection of fill area
a85e798c-2216-5c3c-b9a8-59dee94c4b0c | note | Frequency: Each lot
dbcfb3c3-2755-52b2-b975-9194aa6800e4 | note | Acceptance Criteria: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
932ce244-db82-54f1-8277-a0a851456bb1 | note | Reference Documents: 204.10 (b)
36e305d6-0ab0-5b6e-b712-019d20ee4066 | note | Inspection / Test Method: Visual Inspection
48c06dc3-9cdc-5c89-a27b-12eba627b303 | note | Record of conformity: This ITP Signed Off
b4858186-9abf-5382-b85b-9aa167150d54 | note | HP
ca154947-dc1a-5646-8ea0-b73bddef753d | note | Responsibility: Site Engineer / Superintendent
eb56bd2d-737a-4ff7-9894-e74555d82f55 | signoff | HOLD POINT AUTHORITY
7814d9dd-bf0a-44df-90a5-916ea57d84e2 | checkpoint | 2.3 - Keyed fill layer
c6125bea-274e-509d-8412-6875d6417561 | note | Frequency: During Excavation
4eb605a1-3daf-5398-a3b2-cc21776b350d | note | Acceptance Criteria: Placement surface textured to ensure layers keyed into each other.
047278d8-feb7-589d-8045-4b36a9cfabc0 | note | Reference Documents: VicRoads Spec. Cl. 204.10(d)(i)
6d1fab4a-18b2-5e55-bac6-a10032f380df | note | Inspection / Test Method: Visual Inspection
bb29f5ac-9715-59d6-9bdb-1ba0d5d58558 | note | Record of conformity: This ITP Signed Off
ae45117d-a838-5a5a-8a48-f428516dbb3f | note | IP
fb4c4fd5-33ae-50f9-b75a-c28358962ced | note | Responsibility: Site Engineer
57375684-a634-4789-8881-c283656f5d65 | checkpoint | 2.4 - Layer Thickness
1dc934e4-f0e8-5c70-b8b4-05baaf7fd65d | note | Frequency: During Excavation
e0f626ec-2447-55ea-a358-226fe7ea2683 | note | Acceptance Criteria: Layers placed and spread in uniform compacted layers not thicker than 200mm.
975bd54a-8617-5631-a34a-5a7955fb152a | note | Reference Documents: VicRoads Spec. Cl. 204.10(d)(iii)
3d214b8c-c878-556a-b77b-cdbb5c38b4aa | note | Inspection / Test Method: Visual Inspection
81bca8fa-7449-5ad2-a263-d0d7517d9369 | note | Record of conformity: This ITP Signed Off
0c348ae3-416a-54de-aa05-27f281d5e2e8 | note | IP
e96a64cf-7d83-52d8-8a56-83cef7528076 | note | Responsibility: Site Engineer
e91ca279-44f7-4f55-b930-f8e32d50ecfe | checkpoint | 2.5 - Maximum Lot Size
cbfda2f9-909f-5ad2-bcac-21ce09e29dab | note | Frequency: During Excavation
2040b526-f58f-5c7b-85b0-d281185c1924 | note | Acceptance Criteria: Lot size for testing is to be one day's production or 10,000m2, whichever is lesser.
e2e30d18-1352-5e76-95b9-bc9be70e22bf | note | Reference Documents: VicRoads Spec. Table 204.142
e60f45d4-819a-56f3-b716-fdfaeb995a6c | note | Inspection / Test Method: Visual Inspection
78b00aad-4a31-5f59-9623-bc018460caf8 | note | Record of conformity: This ITP Signed Off
7982bbbd-0bfb-5194-9f88-09a54e66f866 | note | IP
6111595c-cd54-5208-a65f-e6d8cde94bfc | note | Responsibility: Site Engineer
d64c151e-548d-4efc-add5-b9ac1e91f51c | checkpoint | 2.6 - Type B Placement
e2b75956-c60e-5def-a750-8ea1a349ec5a | note | Frequency: Prior to Placement/ Each Lot
8dd34ec0-bcdf-5920-b29c-f7423b2b3c80 | note | Acceptance Criteria: Type B material shall be placed in locations shown on the drawings, or if surplus Type B material is available, it may be used in locations specified for Type C material. The highest quality Type B materials available shall be reserved for placement in the higher levels of Type B fills being constructed. Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm. Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm. Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed. The material shall be placed and compacted such that voids are completely filled with fine material. Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones.
d1d6fff4-fca6-5eab-92d4-cc911ce9190e | note | Reference Documents: 204.10 (d) (iii).
6cdfb30a-cfc9-590f-a464-e8e8b0a9bb84 | note | Inspection / Test Method: Visual Inspection
42af26e0-09f5-57c9-ae22-96175a408030 | note | Record of conformity: This ITP Signed Off
d35205aa-f4e5-5859-b54b-5fb39900d61b | note | IP
955c106a-5e4e-5c17-96c8-56496916c167 | note | Responsibility: Site Engineer / Site Foreman
10274ad1-6248-47f1-8238-76c2438d75ea | checkpoint | 2.7 - Proof Roll
65250fe2-3026-5832-a705-ce7744cc420f | note | Frequency: Each lot
7478ed90-126f-5a8b-9636-2ebcd5f2f5a8 | note | Acceptance Criteria: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
3ff48d84-9d24-5b58-8194-9db29f2f5114 | note | Reference Documents: 173.03, 204.12), 204.10 (b)
1567980e-70b2-5b3d-8bbe-8506327ff3b5 | note | Inspection / Test Method: Visual Inspection
46ebb2f9-45f2-549c-9fd5-28d4a253f396 | note | Record of conformity: This ITP Signed Off
89c78fb3-d16f-5b29-a0c0-5cceb00aa0e4 | note | WP
e6aa4833-3766-5474-b07f-be171ec9cb3c | note | Responsibility: Site Foreman/ Superintendent
c3b36d5b-d613-4be4-9f19-18d8a882f0ef | section | 3 Testing
463dc20c-4649-4b65-87b4-3416448ed375 | checkpoint | 3.1 - Reduced Test Frequency
1295929b-dd05-5f05-a82f-465f8c544e18 | note | Frequency: Each lot
826122cd-5ade-58e2-a0b3-a8d1b6a9829c | note | Acceptance Criteria: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
a523546d-f558-5475-98e5-7001f05bcb8e | note | Reference Documents: VicRoads Spec. Table 204.131
bd12a017-f106-5902-b49e-ed4a87b85db2 | note | Inspection / Test Method: Test Record
b87534a6-9f74-53a2-b22a-29ce9980cd44 | note | Record of conformity: Test Records
6904cbf8-c9c9-5be6-997b-36c9a330ae31 | note | AP
278b314c-01b3-544b-9a39-c139ee603319 | note | Responsibility: Project Engineer/Superintendent
054aede5-726d-4ef0-abd8-f4ae54efdc8f | checkpoint | 3.2 - Compaction Testing
c2905fc7-f315-5011-ae96-2d362f49ced0 | note | Frequency: First lot then every Second thereafter
1f21e6a2-7721-58d9-b3b3-50ace6e9deac | note | Acceptance Criteria: Type B compaction required for Scale B is 98% Characteristic Value of Density Ratio
6d4cc83d-49a8-5dc0-8b76-a08dec52709d | note | Reference Documents: VicRoads Spec. Table 204.131
63eadbe4-3f87-59e6-a400-b12ab8d04e37 | note | Inspection / Test Method: Verify
3bc353b1-be49-5c83-a60d-94c79170c6e0 | note | Record of conformity: Compaction Test Records
eb22b45b-0905-5be0-8afe-94584b2f6cbe | note | TP
531d9057-5f34-585f-99da-5045a513b412 | note | Responsibility: Site Engineer
5a4ca3e0-f384-4c3b-8a41-c15ac747264e | checkpoint | 3.3 - CBR/Swell
6a96aad4-8aa0-5b8a-accf-e0d768dee5f9 | note | Frequency: 1 lot test to determine assigned CBR and Swell
3718eecc-ea5c-5730-ae47-f3ddbf38472e | note | Acceptance Criteria: CBR: ≥ 2%, Swell: ≤ 1.5%
affd2c93-2e93-5ff8-8bef-5cb3da64d654 | note | Reference Documents: VicRoads Spec. Cl. 204.14(a)(i), Table 204.141, Table 204.041
12ebe1f7-e631-53e4-bd9d-f0467fc678aa | note | Inspection / Test Method: Verify
9e5d61ab-1971-5f78-8320-f1e319018150 | note | Record of conformity: CBR/Swell Test Records
d3ac8005-7696-5253-96f1-71e0a5260d0b | note | TP
69f441a0-e368-5eee-9508-db9b70fc7f1d | note | Responsibility: Site Engineer
8e377dc9-52a7-4bad-a2b5-d33a750b6259 | checkpoint | 3.4 - Survey Conformance (at Subgrade Level)
6e040397-116a-5bcd-b78f-2619680d3c95 | note | Frequency: Each lot
62266b1b-6a5c-56a2-918f-609d27a7b008 | note | Acceptance Criteria: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031. Scale B: Range x = +5,-25 Max S = 15mm 40 measurements per lot
bd6aa618-f92f-5d47-b970-7094f8e9f221 | note | Reference Documents: 204.03
b69ddcf0-9245-5ec6-a329-2332a2f59b77 | note | Inspection / Test Method: Survey conformance point
e5d780ed-fabc-5a90-864c-21fc5d8badfc | note | Record of conformity: Survey report, Lot Register
4ab01587-7323-510a-8dae-17d0f18ddb41 | note | WP SCP
ae5ac75e-f50e-530f-b49c-361260f67e0f | note | Responsibility: Site Engineer & Surveyor
c87d9ea1-8ff6-467c-bfdf-8078bc2094bc | checkpoint | Final Inspection
b3272154-4558-527b-8ff7-9f7931cd057c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4389177c-3d7a-5fb6-9fdc-c21b459b36e0 | textbox | Name:
e5907c42-cb0c-5b2e-9b09-f7c5b8ae1b5c | textbox | Position:
4de7fa79-424f-46f2-8ec5-0b8bb89716c4 | signoff | Add Signature
d8fde116-e561-403e-9e51-c6833007ccf1 | checklist | ITP-002 - Feeder conduits and pits Rev2 |  | ITP-002 - Feeder conduits and pits Rev2
39d74475-7ab8-4186-822a-d85cba718bf4 | section | Preliminary Works
231c022e-1511-4917-bdcf-29e56be3e13c | checkpoint | 1.1 - Check for correct documentation
43e374b5-7ee7-5d51-9118-a75b3fcdd647 | note | FREQUENCY: Prior to commencing any activity
c0840a9b-9a9b-5bd0-900d-e17ca61da43b | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
a707df61-65fe-55eb-8d9a-fba11ae9ac87 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6a5d3777-7e37-59dc-9d34-4f75c6f572ab | note | INSPECTION/TEST METHOD: Visual inspection
a9f5a454-ae2e-577e-86d2-c083bed82d5d | note | RECORD OF CONFORMITY: This ITP signed off
505de367-675a-5780-bb1c-6b63ae75f43a | note | HP*
34f4ac7f-dce3-5158-b527-a569bcc99a40 | note | RESPONSIBILITY: Fulton Hogan Engineer
03386592-d0ab-53df-8cfb-2fd37241a4cc | textbox | Date Completed:
7a8cfed4-4241-4f42-b488-90ae30aa94f6 | checkpoint | 1.2 - Implementation of all measures and controls
7e82635e-59c4-5658-b169-7000c388ad18 | note | FREQUENCY: Prior to commencing any activity
a0a80747-5b50-5721-b774-b9df5da625d3 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
8a09ea4d-81a5-5e94-b067-3fdb8a0e8fc5 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
1b5db3c6-cdbb-50d2-a98f-374f48191bcc | note | INSPECTION/TEST METHOD: Visual Inspection
87816054-64b3-5cad-98f4-e5abad337883 | note | RECORD OF CONFORMITY: This ITP signed off
a2fe30bb-047a-5091-a722-24bae8e55413 | note | HP*
f008a17a-f892-5415-b143-2ca484690ed5 | note | RESPONSIBILITY: Fulton Hogan Engineer
b6a2cd34-b034-5bda-be15-62f6a87db006 | textbox | Date Completed:
acd834de-5b30-4daa-b7a9-b42e39941d69 | checkpoint | 1.3 - Materials
5f636788-2511-5925-bf63-948cf98eb7a0 | note | FREQUENCY: Per Batch
9184aae4-6432-5014-bb96-52e56b4ede9f | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be Orange • Heavy Duty 100mm diameter UPVC •Modula Stakka pits to be used for feeder pit, entry for conduits to be cut with hole saw •All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
049f746b-2f72-5e5a-94cf-d7d0f2e70b8b | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4 AS 2053
105ebf04-df2c-5b3f-bac0-e84a2f99f43a | note | INSPECTION/TEST METHOD: Verify
f451f3e2-d58a-524b-bd71-bdff0557391c | note | RECORD OF CONFORMITY: This ITP signed
298f647c-a431-5d57-86e6-d232f7909f80 | note | HP*
8647baac-fb54-590f-9264-632f2a1265e8 | note | RESPONSIBILITY: Fulton Hogan Engineer
40b3b52c-c292-58d0-8e0f-b3affc0e06ec | textbox | Date Completed:
82043891-8b9c-4e50-a52e-819739373e63 | section | Construction Works
0dd544c7-cef2-4f8b-a286-108f959844ae | checkpoint | 2.1 - Survey set-out
97128d13-8dcc-522f-945a-b253f6b6dd49 | note | FREQUENCY: As required
8cf247b4-1d6a-57b4-a045-bb59a6bb88be | note | ACCEPTANCE CRITERIA: • Work is set out in accordance with drawings. • Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
3fa0a9ad-38c4-5107-8335-46777b90e97d | note | REFERENCE DOCUMENTS: Work procedure
a9dfe9bb-effe-5e58-ae59-3a10ab3d0cf5 | note | INSPECTION/TEST METHOD: Verify
901e1ef3-bcf1-5319-bb44-f9a4dc74936d | note | RECORD OF CONFORMITY: This ITP signed
a5c345b0-b940-5b02-86c2-3b1a42eb99db | note | HP*
232dbd75-0da6-5201-9044-9f2d43eb21e1 | note | RESPONSIBILITY: Fulton Hogan Engineer
f1be2d24-b5fb-55ad-9328-5147759fa2bd | textbox | Date Completed:
67e96c4c-f107-401c-843c-9f8582e8f92c | checkpoint | 2.2 - Excavation and Trenching
d8ddd43a-19d4-55de-9a43-681b261e8ff8 | note | FREQUENCY: Prior to Installation
c0e75137-9e07-59ac-be1e-f6766ca0a34b | note | ACCEPTANCE CRITERIA: • Minimum cover for underground conduits shall be 600mm • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
41548724-28c4-54ba-acf5-28e05e3196a8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
17e11fff-1fcb-5e19-af4c-27851bc05489 | note | INSPECTION/TEST METHOD: Verify
2a2e6126-4abf-5503-9bd9-0de99f32ec29 | note | RECORD OF CONFORMITY: This ITP signed
4d899ada-3dde-5483-b134-30358cc39860 | note | WP
949bc3e2-efe1-5562-9805-f36ed2d57048 | note | RESPONSIBILITY: Fulton Hogan Engineer
4c00e858-0e3b-54e6-a792-6634626556ae | textbox | Date Completed:
356c644d-4c55-433a-99b9-dbbd854f00d6 | checkpoint | 2.3 - Installation of Conduits and pits
c4b7a6eb-e737-5e69-a7da-d2f36acfb316 | note | FREQUENCY: Each Lot
a35477c8-9fb8-5811-9ada-27eb5c308e0a | note | ACCEPTANCE CRITERIA: • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
4cf3eb36-039e-553f-92e2-eb94d91e5a97 | note | Conduit shall be embedded in not less than 50mm sand and covered by
fcd87adb-673d-5ccd-a809-68dbb7eb2906 | note | >50mm - 75mm< sand
7e51973a-2835-53a9-9ff1-ae7639b09fe5 | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
80ef35cd-c33b-56c4-9da7-93377f3f508c | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
d20fe4da-1969-550f-b7c0-814dccc0cc5e | note | • Conduits shall not be subject to construction loadings
292c9a0d-253f-5d6c-aa13-17695c91afee | note | • Pits shall be constructed as to allow for class D rated covers
71d7166f-c345-5560-95de-f768399ed393 | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor, a 50mm gap between conduits shall be maintained as they enter pit face.
3ae7dddd-2605-52c4-aaa5-e4394930a2a6 | note | • Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mm beyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
aa4f5bba-061d-5426-a8b2-230620d62639 | note | • Conduits shall be placed a minimum of 100mm above pit floor
5f4b77c0-25fd-54b6-8c55-91207a8f84a8 | note | • Conduits installed for future connections shall be installed to the track Margin
6a7630fc-fcbd-59b5-873a-4741c749d3b3 | note | • 100mm of concrete around and under pit lid
d76d3c83-203f-5b2f-9c1b-f242a5b92966 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
6ced8e7a-ef96-54db-9e81-157f0aa6fcef | note | INSPECTION/TEST METHOD: Visual inspection
6c5f3945-596c-57e7-b35b-a2a88bd8ac5d | note | RECORD OF CONFORMITY: This ITP signed
19eb792e-b7b3-523f-998b-d5c445f2b159 | note | WP
8dc1b45d-e7f4-58de-b137-ca2784394190 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
793740c2-0012-5d4c-9f77-c34543b6705a | textbox | Date Completed:
ccad494c-16a1-4fc8-b1a1-078ff63a25ae | checkpoint | 2.4 - Inspection of conduit installation
05112f02-4b5c-58ad-9a6c-ef5dee17fda4 | note | FREQUENCY: Each Lot
85b0e118-307c-5ebf-89a8-b6cde67211c9 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
02184761-b9ec-5392-96c5-aed0068ad00b | note | REFERENCE DOCUMENTS: Work procedure
aab4f03f-648a-5dd1-8823-3f6216bf772b | note | INSPECTION/TEST METHOD: Visual Inspection
443a3d45-b56d-50f0-9723-41f53e2e33e0 | note | RECORD OF CONFORMITY: This ITP Signed
c79ed974-e419-5276-9f83-698757d990e8 | note | *HP
bcf71617-d76d-5fb4-a9e8-87bc8fb726c3 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
715e830a-d546-5955-8e5f-b8289dd6099f | textbox | Date Completed:
0b839c17-881a-41f6-9c04-9800bed07d23 | checkpoint | 2.5 - Backfill of Trenches
605e7b3c-3c8f-502f-8c0a-537ef2353f1e | note | FREQUENCY: Each Lot
9fa3fa37-e7ae-545b-869d-6e568f87b7a5 | note | ACCEPTANCE CRITERIA: • Backfilling (Only to be used for road crossing trenches) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
a36b1927-c4cb-52e2-bb92-c1bc3758b0a0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
b07367cc-eeac-5cb0-968b-afdeb2cd237e | note | INSPECTION/TEST METHOD: Verify
c6def280-9014-5a1b-919c-e20bae2fe1c1 | note | RECORD OF CONFORMITY: This ITP signed
45deccc8-f747-53b0-8b43-9807ab57e8a0 | note | WP
ac192b07-5ea1-5d6e-9425-a1759a89e6cd | note | RESPONSIBILITY: Fulton Hogan Engineer
78df8ba3-b9db-5869-81bb-2a6b17b37760 | textbox | Date Completed:
3798a197-ecf4-40b4-91ea-1f3451269c19 | checkpoint | 2.6 - Installation of Draw Cords
0aff344b-ae75-5429-aa59-4e490578a007 | note | FREQUENCY: Each Lot
1fc03312-9264-5c1d-b5bc-ff47492d56ef | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'
3b7642f1-cda8-55f9-b4d1-cf778a49dddf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
a5b18cf3-2946-5060-9946-d53d543263d4 | note | INSPECTION/TEST METHOD: Verify
391b69c2-aab3-5381-b359-3e1a90ac8a16 | note | RECORD OF CONFORMITY: This ITP signed
36869ed9-6a13-5ef1-be83-1034dabaefa8 | note | WP
f4cd9551-6bbb-55b3-8497-4af251a0e73e | note | RESPONSIBILITY: Fulton Hogan Engineer
20571d11-b473-5b96-9d5b-d699ebc4d71b | textbox | Date Completed:
fe8a5359-cf5f-4aef-94c6-3657b7b3d470 | checkpoint | 2.7 - Compaction
6f8c222f-e46a-5289-87a3-e143b7efea0c | note | FREQUENCY: Each Lot
7c8c9f17-87de-5036-8369-1841e4f6aced | note | ACCEPTANCE CRITERIA: • Bedding and backfill material to be compacted using mechanical plant During compaction optimum moisture content of bedding and select fill is within 85% to 115%
8ec89b2d-bfb7-58ab-8875-3bd9c60d00ce | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
021c2acd-14ed-5a69-ac42-ee642befa7dc | note | INSPECTION/TEST METHOD: Verify
8ca1155b-8d7f-58d1-951b-99fe7f266445 | note | RECORD OF CONFORMITY: This ITP signed
32e8cec9-7244-50b6-9158-b7efe625edd1 | note | IP
31ac3178-a253-5674-906a-628536794738 | note | RESPONSIBILITY: Fulton Hogan Engineer
fcc0f319-29b1-587f-b054-3f7eaebbfacc | textbox | Date Completed:
89367a02-56f3-414a-9200-b81e8298b22e | checkpoint | 2.8 - Feeder Pits & Pit Lids
51ad89b2-572e-5644-bf8e-0f5b66478dea | note | FREQUENCY: Each Lot
e6bc9ed6-d0c3-5388-b6e4-d917abf0d65b | note | ACCEPTANCE CRITERIA: • Feeder Pits constructed and installed as per drawings
48b4c8f0-b1c1-518f-b1bf-86f5219128d3 | note | • All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar
d7adf6ea-e62a-5f59-8120-a337454d06b8 | note | • Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
180ac4e6-4306-52ad-82e6-a1914f6c7bbc | note | • Gatic pit lids shall be filled with structural grade concrete.
f2002aaf-1166-5f96-9841-d981e383bfcf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
4ed3e65c-41ef-51d0-ac43-367d7cbf201a | note | INSPECTION/TEST METHOD: Verify
60d0155b-470e-5d2b-9ec9-db15921ac718 | note | RECORD OF CONFORMITY: This ITP signed
e8b821bc-33bd-5eff-8a1e-faa48ad84f09 | note | WP
938c6592-ab5d-5dcb-9f76-8bd70c5c0505 | note | RESPONSIBILITY: Fulton Hogan Engineer
16ec117e-8a3c-5166-8536-fb784f71f30d | textbox | Date Completed:
4a6571e7-005f-4672-ba97-f6de4d0ae476 | checkpoint | Final Inspection
83d7f5a3-ed82-5dd4-831b-73e006ee7ef4 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
1e5f2973-30ee-59d4-a546-9daad608a977 | textbox | Print Name:
234b8073-5338-5cb4-ab8d-d0758a185788 | textbox | Position:
76175f8d-c5fd-50a3-8b33-71977f6d2ace | textbox | Date:
f0c81a02-8b75-4b7c-9849-ba28563df29c | checklist | ITP-003 - Electrical and Communication Conduit Rev2 |  | ITP-003 - Electrical and Communication Conduit Rev2
a0ae7dc2-a1da-4111-8a48-bba8919bff70 | section | Preliminary Works
981651af-ea68-4210-b3c7-cb2c7df0e6c7 | checkpoint | 1.1 - Check for correct documentation
06e8682c-136c-5db6-9935-1787beaae7a3 | note | FREQUENCY: Prior to commencing any activity
36fa740d-1053-54fc-b857-f39b3f943b51 | note | ACCEPTANCE CRITERIA: Employees and subcontractors shall be issued with the most current and complete construction drawings
59c1704e-7ed9-5c43-bbe2-9e8dda5c636e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
bdb1db5e-cfda-5a29-95e5-e18390f6a830 | note | INSPECTION/TEST METHOD: Visual inspection
22f98707-1302-53f9-8985-16c36b6c5d9c | note | RECORD OF CONFORMITY: This ITP signed off
06e90bac-5b52-577b-be00-dcead05abdc0 | note | HP*
6c55d5e2-ec37-517f-aaf0-006d5b8f2c90 | note | RESPONSIBILITY: Fulton Hogan Engineer
249d867b-72f9-5fbd-8365-08befec514d5 | textbox | Date Completed:
9cd7cbec-f375-4769-b9a4-857be69643cf | checkpoint | 1.2 - Implementation of all measures and controls
708b39c0-a605-5e36-9cee-01970c3f03c5 | note | FREQUENCY: Prior to commencing any activity
7ed890a8-c534-570a-a950-04aaf8c34639 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
d2afbdf4-faef-5080-8429-b3e2b0cfc20b | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
6e79aee4-3be7-5aba-8584-b1f8fa425ceb | note | INSPECTION/TEST METHOD: Visual Inspection
c6705e57-c2cf-5eac-9417-8517aefdf53a | note | RECORD OF CONFORMITY: This ITP signed off
93eae288-cfd1-5b74-ac1c-39a39d9e1516 | note | HP*
be10e8da-3339-5627-8657-0d9e5ba27c78 | note | RESPONSIBILITY: Fulton Hogan Engineer
226341aa-0d80-5495-94e9-7484416f1cc5 | textbox | Date Completed:
85880ca6-ff9f-4215-9f9f-453d6a5932ae | checkpoint | 1.3 - Materials
513d8532-a0c3-5650-a5b0-c676adac6082 | note | FREQUENCY: Per Batch
cee968c2-d23f-5b0a-b2e9-a0566719e5ec | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be Orange and rigid HD UPVC of sizes as required. • Communications conduit to be White and rigid UPVC of either 32 or 50mm size or larger as required.
229f8e0e-f828-5057-94b8-9f9be627e69e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.1 AS 2053
b3d2f4f6-1961-5e29-b151-0281cdb2c6c6 | note | INSPECTION/TEST METHOD: Verify
841267b9-7c6d-569b-b316-a082e7af348f | note | RECORD OF CONFORMITY: This ITP signed
299de2ad-8796-5ccf-bc19-08b8a4f791ec | note | HP*
9ae0bc65-3817-53ee-ada6-7a32db5f6009 | note | RESPONSIBILITY: Fulton Hogan Engineer
cbad8832-0da9-5ba9-b2c1-ab08d057f30e | textbox | Date Completed:
db66efff-3c40-451a-b769-e9d0ab556af9 | section | Construction Works
e5c797f7-4242-4829-8768-fe36930d5ece | checkpoint | 2.1 - Survey set-out
8e150e6d-1556-55fc-9112-f21552198041 | note | FREQUENCY: As required
2916b399-fb91-5d87-aab5-5b3d3cda246e | note | ACCEPTANCE CRITERIA: • Work is set out in accordance with drawings.
c060ab6a-a589-5ea5-89c1-166844d487f1 | note | REFERENCE DOCUMENTS: Work procedure
16ba5403-077b-5e60-b44f-4752477b912b | note | INSPECTION/TEST METHOD: Verify
f30c80fa-78c6-57db-b6ad-7afdee31bad0 | note | RECORD OF CONFORMITY: This ITP signed
6d965503-6cf1-59d3-a2c8-6c0fd964eac4 | note | HP*
bb30dbd1-7693-55bc-b082-038045a06044 | note | RESPONSIBILITY: Fulton Hogan Engineer
e90db474-b4f3-52bb-b4e6-f12d8b690b44 | textbox | Date Completed:
9d00347b-1243-4cbc-9d01-869fb9cafa01 | checkpoint | 2.2 - Excavation and Trenching
33e605fa-dcec-51dc-a99d-29dbe1cd3fb6 | note | FREQUENCY: Prior to Installation
89ce8171-32e8-52b5-9978-944520c1b143 | note | ACCEPTANCE CRITERIA: • Minimum cover for underground conduits shall be 600mm • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
30cda68c-5120-5b3b-8781-898cfa0b2da0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
0c40d486-570d-5cdc-8362-8919dd3583b9 | note | INSPECTION/TEST METHOD: Verify
fe52016f-7cd1-5bcf-a18f-e9f8e1b1d00a | note | RECORD OF CONFORMITY: This ITP signed
5c7418e8-230c-53d1-ad49-930b80ae8221 | note | WP
6077bb1b-0f37-5ece-b33e-7228d7801420 | note | RESPONSIBILITY: Fulton Hogan Engineer
005af2df-a4e8-58a2-8a92-9b2b93b97f47 | textbox | Date Completed:
6552002d-ad73-4d83-9861-92b8305a4552 | checkpoint | 2.3 - Installation of Conduits and pits
6a472128-781f-5d09-b40f-8e653d257dd7 | note | FREQUENCY: Each Lot
9a3eede9-c440-5cac-b83b-bfe77a402863 | note | ACCEPTANCE CRITERIA: • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
dd60636b-26bb-5af0-aa50-2656626cbb98 | note | Conduit shall be embedded in not less than 50mm sand and covered by
452cf3a4-c5f0-5b67-99a7-7f35b1c57198 | note | >50mm - 75mm< sand
26c21b7f-db6d-590f-98a3-4ac050abf5da | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
5b7aa355-1005-50af-a1cd-e4550d0cd011 | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
816fe57e-f9d5-58d6-824f-ff3b827f9d53 | note | • Conduits shall not be subject to construction loadings
f95ed3c2-e694-5d98-864f-85cf2eee3b13 | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor
c8528809-60ed-5da5-8236-7d6d6a99daed | note | • Conduits shall be capped with UPVC electrical caps
ee0f892a-53ce-5987-a2f9-07b606d943f2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
f2df2aeb-1994-5887-9365-09a76180a143 | note | INSPECTION/TEST METHOD: Visual inspection
8ad7ce2b-5ba0-52eb-8f57-165a5aee5420 | note | RECORD OF CONFORMITY: This ITP signed
4244c4c6-7e7c-5e75-a365-f60ab53c6156 | note | WP
540d1be9-1709-5b5d-bc2a-0f45fddda1ee | note | RESPONSIBILITY: Fulton Hogan Engineer/ YT
3c610bd8-045b-5782-976f-05c9b74a51b5 | textbox | Date Completed:
8a9d6b1a-e26a-4815-bbcf-ed9cda0b5d41 | checkpoint | 2.4 - Inspection of conduit installation
7635b0c5-fca7-571e-8e70-e03e6b890b24 | note | FREQUENCY: Each Lot
948c7d77-ebcb-5f15-9c8e-f44c9142eae3 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
4988f914-cd25-5725-b5b8-52bfd4cc626c | note | REFERENCE DOCUMENTS: Work procedure
faadf6d6-579e-506b-9486-c6778a0ccafe | note | INSPECTION/TEST METHOD: Visual Inspection
ff1d7705-0210-5d56-8323-d8ba03df91fe | note | RECORD OF CONFORMITY: This ITP Signed
f0c4cb87-44ce-525e-bdc3-1e14f17e32ef | note | *HP
b0b96361-57c0-5e79-925c-79ebed9147db | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
f9e9513c-e446-5b49-9783-9f25c77646d6 | textbox | Date Completed:
85dae795-8157-45f9-9d91-e766871e96de | checkpoint | 2.5 - Backfill of Trenches
2bd48be6-bbd1-567f-b703-eadbe30c81fd | note | FREQUENCY: Each Lot
6231323d-d6fa-5fb6-becb-3f5a69371709 | note | ACCEPTANCE CRITERIA: • Backfilling (for trenching or road crossings) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction using handheld mechanical plant
846d074f-f7df-53a7-bdaa-c81bc759027e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
64358a92-3e04-5e36-8017-5a973310130c | note | INSPECTION/TEST METHOD: Verify
7b7bee5a-bc52-52e4-99c9-c41f6176567a | note | RECORD OF CONFORMITY: This ITP signed
35465fde-9016-5e9f-a5b4-9c9a865616f2 | note | IP
5a12c02d-dbb5-5d48-b3e0-1117427c7f49 | note | RESPONSIBILITY: Fulton Hogan Engineer
bd34ba0f-800c-564b-b20c-255bab5473aa | textbox | Date Completed:
7be6175d-abde-4f70-a197-17caff3d5144 | checkpoint | 2.6 - Installation of Draw Cords
65916674-d883-542f-8e5d-1fcbba8ec570 | note | FREQUENCY: Each Lot
0e374dbe-65e9-5bee-a469-5b2fc5a1d7b0 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit, material to be used shall be 6mm 'telstra rope'
93cbdfe3-5707-5426-8ebc-5b08ff89662c | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
fc33ca0d-4eb9-5249-a524-0223dcb59060 | note | INSPECTION/TEST METHOD: Verify
ef38e94a-f25c-5a72-a255-5ccac2738a15 | note | RECORD OF CONFORMITY: This ITP signed
2d69af37-96cb-5cd3-a0cc-e5a4941777f2 | note | IP
e8c8476d-ae94-5770-b3ad-7f9dfa48eef5 | note | RESPONSIBILITY: Fulton Hogan Engineer
dcff48e9-51e9-5920-8f0f-b24cfcb9454f | textbox | Date Completed:
8d46fb30-3253-4173-bed0-3b61715236a1 | checkpoint | 2.7 - Compaction
2affc1e6-4d1a-5ba3-bc7e-ade088f07237 | note | FREQUENCY: Each Lot
949c73bc-0bfd-5886-ae50-2d124b31e36a | note | ACCEPTANCE CRITERIA: During compaction optimum moisture content of bedding and select fill is within 85% to 115% as provided by suppliers
cbfe0f07-65e1-5b7b-8701-b840ac433542 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
2d123f94-9ef7-5b18-894e-28863e4b1656 | note | INSPECTION/TEST METHOD: Verify
48d70642-999f-5be0-a3fb-934ae00e4699 | note | RECORD OF CONFORMITY: This ITP signed
b076e1bb-10ac-5ed8-92a9-dbf49ec88832 | note | HP*
da13a73b-46fb-50e6-a0d8-0f46ad56f76c | note | RESPONSIBILITY: Fulton Hogan Engineer
ce7e89c5-b185-564c-bad0-de9700468a42 | textbox | Date Completed:
e83e3c05-8837-4d6c-a3e4-8792493f6219 | checkpoint | Final Inspection
ce2ce716-8b82-5d8c-b550-c058213570df | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
000259b5-2f7f-5020-ae9d-dce8ed848619 | textbox | Print Name:
bc4903e6-3b18-53c4-86f4-f46a12041b49 | textbox | Position:
0309ef50-e946-54b0-ab4f-79876038c103 | textbox | Date:
3f7faa69-8fe1-4fb2-8555-786ad3feae31 | checklist | ITP-004a - Class 2 Base Course Placement Rev2 |  | ITP-004a - Class 2 Base Course Placement Rev2
8a71eb5c-2235-49d4-9166-a0ae45572fac | section | Preliminary Works
55e07994-324b-4148-9232-8eb665d0e12e | checkpoint | 1.1 - Check for correct documentation
845835d2-9e9f-56b8-b9fa-b37f85e1a489 | note | FREQUENCY: Prior to commencing any activity
2ab86ab9-6282-55c3-9650-8fa1ccb0a874 | note | ACCEPTANCE CRITERIA: Ensure that employees and subcontractors are using the most current and complete set of construction drawings.
896ee5bf-9a6b-549d-a5a0-270c74fafadf | note | REFERENCE DOCUMENTS: Drawings and drawing registers
829dff9c-5400-5cf5-adb8-116f39d4d679 | note | INSPECTION/TEST METHOD: Visual inspection
4200bcad-292d-5729-892b-18a44c4c7f62 | note | RECORD OF CONFORMITY: This ITP signed
2c571c34-028f-5dcb-9d74-e0ddc93a372a | note | HP*
193f0528-bac1-50c6-8d58-b2f166c32651 | note | RESPONSIBILITY: FH Engineer
b8a41091-67eb-5fa0-baff-6095653b8149 | textbox | Date Completed:
80430580-62ea-4126-8a13-ee234640c547 | checkpoint | 1.2 - Implementation of all measures and controls
c102ca52-0ea8-5430-aacb-fbd4f399ca38 | note | FREQUENCY: Prior to commencing any activity
224f229a-3642-5eaf-ac73-f49995206f70 | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
f391c018-e2aa-53e9-9f6c-c15ecb58e19a | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
b67dd9ca-650e-5fc9-95e3-a453d5715711 | note | INSPECTION/TEST METHOD: Verify
f155fb5b-f473-5ef4-a571-24bfe2712eeb | note | RECORD OF CONFORMITY: This ITP signed
d7df76e1-ffe2-53f9-97a5-9a40c1e0a6ae | note | HP*
99f4eacc-ddc9-523c-a2da-b390202bec78 | note | RESPONSIBILITY: FH Engineer
9b5053cd-1537-5b0e-8010-ca2a30310f95 | textbox | Date Completed:
5f833eb1-c200-484a-a7a6-8cce851ef1f4 | checkpoint | 1.3 - Material Compliance
4d0ea9f5-5ddc-518f-9143-40402306dbc0 | note | FREQUENCY: Prior to commencing any activity
8e5c7dc3-fc50-5698-975c-3958fd43280f | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
9d8abe72-b52e-5960-a3f6-d681659a2249 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
f9e3065a-2033-5a01-af86-3f128deedd40 | note | INSPECTION/TEST METHOD: Document Review
4c5159d6-3d47-5376-bb26-d37fd1af4455 | note | RECORD OF CONFORMITY: Test Reports from supplier
74831704-c5a6-517b-85a3-cfb3fcba7188 | note | HP*
2b0a0fd2-d2ee-5256-8892-4eadfbeec012 | note | RESPONSIBILITY: FH Engineer
c8c1ce12-b155-522d-8194-1dc3304dc49e | textbox | Date Completed:
ea6b32e1-09c8-4ecd-840e-59a5cb08bb5e | section | Construction Works
416a63ff-9785-474b-ae33-776ab1f9bcde | checkpoint | 2.1 - Sub Base
ac939b0d-d817-5389-89a9-c6c7e84da327 | note | FREQUENCY: Each Lot
20bfd12c-e34b-57c7-b606-91e911e0212f | note | ACCEPTANCE CRITERIA: •Sub grade has been inspected, no visible ponding, springing presence, or visible deformation. •ITP-001 HP for subgrade inspection signed off
8b9ee007-ef73-5fad-8e60-b934378791f4 | note | REFERENCE DOCUMENTS: VicRoads 173.03
9b438bd8-00eb-543b-88a7-69dbce6c4e98 | note | INSPECTION/TEST METHOD: Inspection / Test Method
42f03498-db88-5a5f-b4c2-15ad0f364e9b | note | RECORD OF CONFORMITY: This ITP signed
582e7471-e490-5039-8834-40de17236df0 | note | HP*
4376efc4-720b-5733-85de-24f862922c40 | note | RESPONSIBILITY: Fulton Hogan Engineer
48b60aa3-ba66-5cce-a35f-a7fe5c02a51c | textbox | Date Completed:
f53b17bd-7082-4479-a01e-9b6269e2ae51 | checkpoint | 2.2 - Spreading material
77e0d481-21af-55b9-afc6-c8fd2c4b73b0 | note | FREQUENCY: Each lot
6aa48770-ad88-573c-b55e-30af4dc46ba0 | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
915b5ae7-4551-57b1-a304-247240605f43 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
e0d32678-3d6b-5efc-bc39-e713e05dc387 | note | INSPECTION/TEST METHOD: Visual Inspection
3f041893-8227-51d8-92c2-64ff6a8ecfc7 | note | RECORD OF CONFORMITY: This ITP signed off
91788ebc-8e1d-524f-91cf-eaf020b16389 | note | IP
6c28ec8f-296b-58f7-ac1b-d135d791f47e | note | RESPONSIBILITY: FH Engineer
129e3480-1ab4-5794-997e-0b73b5468471 | textbox | Date Completed:
be109228-03d7-4f81-996c-91d2e12fc0c4 | checkpoint | 2.3 - Compaction
1a8ebf1d-3ac6-5644-b2a3-7b3f82eb758f | note | FREQUENCY: Each lot
cdb1173b-bc72-5dec-b521-611814d1ef31 | note | ACCEPTANCE CRITERIA: Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content. Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test. Compaction testing shall be carried out once per days production and shall comprise of three samples
1f3da786-ec4d-599e-9ddb-d08e11b39beb | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
1cfaeb62-0153-58bb-8670-a0c04edeaa90 | note | INSPECTION/TEST METHOD: Visual Inspection
efe36dae-5b0b-5dd5-8bf2-048a6d9a2986 | note | RECORD OF CONFORMITY: Test Results
ec2280b9-7fd7-5f5c-8b34-5ced97acc8fa | note | TP
27969a89-1f11-5c59-b628-84728a249a5f | note | RESPONSIBILITY: FH Engineer
e860389e-0668-5576-80a6-364a275f200d | textbox | Date Completed:
d1758b4f-31da-4de7-8cea-2f15d5223016 | checkpoint | 2.4 - Level Checking and Conformance
92cdb025-ecb9-5e08-8b1c-e34576410220 | note | FREQUENCY: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
26994c92-f426-53b1-8df8-279b3c02708a | note | ACCEPTANCE CRITERIA: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
f07ba5ab-0740-5e38-95b4-395606d748c1 | note | REFERENCE DOCUMENTS: Verify
acbca7a2-40b5-5ea4-b5f2-0c0e3ec65bf8 | note | INSPECTION/TEST METHOD: This ITP signed off
7b84353b-9dc3-589e-975f-7a722fadc13a | note | RECORD OF CONFORMITY: IP
436dcffa-e6e7-5ed6-98d4-043c8d5b1fb5 | note | FH Engineer
62ebb103-a413-50fd-8219-021eb4c32d71 | note | RESPONSIBILITY: N/A
4fbe232e-252e-53e2-8476-6de0042a86d8 | textbox | Date Completed:
205b1366-27ea-404e-ae77-3124e2e5bd3d | checkpoint | 2.5 - Finished surface
ca75a1df-61a9-52a2-b10c-77fa0857a2e6 | note | FREQUENCY: Each lot
f93c34fb-7eb6-5ca3-aac5-bc341596e914 | note | ACCEPTANCE CRITERIA: Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
cc09ce5d-1ca0-5c09-9777-fd4b9c04195b | note | REFERENCE DOCUMENTS: •CE-019-ST- 0033 CL4.2.2.8 •Contract drawings
786b6a98-7ff6-5517-b71f-60aed139dc45 | note | INSPECTION/TEST METHOD: Visual inspection
84985b3b-3f4f-5445-afcb-845166f39545 | note | RECORD OF CONFORMITY: This ITP signed off
40022dc3-c2f9-527d-96ba-8c9d5e276616 | note | SCP
8c997c6c-f547-511e-9fd5-ce14a166be0d | note | RESPONSIBILITY: Surveyor/ FH Engineer
d7b627bf-0acd-50d3-a5fa-9d89a4651737 | textbox | Date Completed:
3fd64ff6-73a2-47ff-8306-3bc3105c247f | checkpoint | Final Inspection
03e41e47-9cb4-5efb-bb4d-39bba851b449 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
52de56cb-cf8d-5214-be0c-ead3b924e014 | textbox | Print Name:
da533c6d-ebb5-591a-a886-54fe0cd4022c | textbox | Position:
d1b9e408-583b-5d33-8edf-ce91e4e3a553 | textbox | Date:
005f1a1f-e06b-47b3-a189-435a5cf54b0e | checklist | ITP-004b - Cement Treated Crush Rock Sub Base Rev2 |  | ITP-004b - Cement Treated Crush Rock Sub Base Rev2
006df819-e794-405e-a476-623640703fff | section | Preliminary Works
ad571157-be50-4f41-ad37-71a47b9eb886 | checkpoint | 1.1 - Check for correct documentation
23bc4cdc-4143-5395-9609-0c64d207a203 | note | FREQUENCY: Prior to commencing any activity
fa7bee1e-ba18-5c6b-a00f-d42161095893 | note | ACCEPTANCE CRITERIA: •Ensure that all employees and subcontractors are using the most current and complete design drawings
4994a7b0-9fc1-58d4-ad3c-b7e6c3a0f4b1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
83373731-3399-593d-abb6-16cece3ff1df | note | INSPECTION/TEST METHOD: Visual inspection
f123fb3d-60da-539d-a364-c38189d9cb29 | note | RECORD OF CONFORMITY: This ITP signed
161426e4-aa52-5629-8830-6960165aa2ff | note | HP*
bbdc2c3f-de88-5cc0-a87e-daa94d7fbbda | note | RESPONSIBILITY: Fulton Hogan Engineer
0f4782c9-85d2-5262-beca-c8100f3b971f | textbox | Date Completed:
ddd60d7f-d8b7-4afb-9cd0-de3a6f629b91 | checkpoint | 1.2 - Implementation of all measures and controls
170ebbfc-2bf3-5750-9896-19c19f6168aa | note | FREQUENCY: Prior to commencing any activity
3eab3188-db30-5ff8-b182-8024773c5049 | note | ACCEPTANCE CRITERIA: •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
342e3db7-86f9-5dbe-8066-7c1e99a695d2 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
879e49e7-06bb-5f5d-89e2-79b74a31b92b | note | INSPECTION/TEST METHOD: Visual Inspection
8af5de34-9c4a-5f87-b417-222db95d2b10 | note | RECORD OF CONFORMITY: This ITP signed
b2417ef8-fe21-5c65-97c1-f439100e80a2 | note | HP*
a415c3a7-05e0-5206-84f2-d39dd06f9c2d | note | RESPONSIBILITY: Fulton Hogan Engineer
f08403e4-8cb4-5d21-b6b6-ab19ffb99f91 | textbox | Date Completed:
6dad8d54-8adf-4407-9f76-4f8735d17f1c | checkpoint | 1.3 - Confirm CTCR is Appropriate Mix
21248ff6-8f9e-53db-bd7f-bc910fd164f9 | note | FREQUENCY: Prior to commencing any activity
e6792653-b387-5c9c-bfc2-a2d5c9902361 | note | ACCEPTANCE CRITERIA: •Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product. •CTCR shall be tested in accordance with 815.141 by supplier
4b1fa2d6-1b72-5d3c-950d-bc51239c4e9b | note | REFERENCE DOCUMENTS: Design Mix
94d60a66-1daa-5a49-8a91-67d0cdd0c875 | note | INSPECTION/TEST METHOD: Inspection
4641492a-ccc7-5ad6-a1f4-988937553ad4 | note | RECORD OF CONFORMITY: This ITP signed
02a7aeec-8caa-5728-b4a8-8d10a2e2df89 | note | HP*
1494afeb-8dab-532c-8810-5b737bd6fc53 | note | RESPONSIBILITY: Fulton Hogan Engineer
33f2c699-faa9-5089-8de1-80e1c9553317 | textbox | Date Completed:
9ff65a01-961b-483c-b393-75da6a4e0753 | section | Construction Works
b39e3ecb-d5b5-41c8-8469-f5628da8a275 | checkpoint | 2.1 - Sub Base
6f890de3-27a7-5c3f-af25-c23f04cc09e9 | note | FREQUENCY: Each Lot
c89c1219-21fe-575f-98d2-61392935e393 | note | ACCEPTANCE CRITERIA: •Sub grade has been inspected, no visible ponding, springing presence, or visible deformation. •Proof Roll shall be conducted by plant compliant of 173.03
0fcdbb5d-3545-5263-ae94-c9aa18cbf72a | note | REFERENCE DOCUMENTS: VicRoads 173.03
f2245d91-f374-52e1-be13-d00c48c6fe51 | note | INSPECTION/TEST METHOD: Inspection / Test Method
209cabe8-3599-54b9-a604-b6ecacd2216e | note | RECORD OF CONFORMITY: This ITP signed
5180fcca-da54-51ee-9001-8a7886d7290b | note | HP
c22ba1c7-0c33-51d1-80d1-f9f5131613cb | note | RESPONSIBILITY: Fulton Hogan Engineer
869b4d83-3c2f-527f-aa82-6739fa969371 | textbox | Date Completed:
4ea29b26-e531-4afd-8e8c-8115c53fdca0 | signoff | Authority holdpoint
c4819b52-f7f5-41c5-8857-f4b290c404e1 | checkpoint | 2.2 - Moisture Content
6ce7cb5b-9c3b-5247-a963-27dba0bb950f | note | FREQUENCY: Each Lot
5a3f6ac1-18be-5fc7-8ecb-a21c914556a5 | note | ACCEPTANCE CRITERIA: •Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
0ed855d9-dc81-564f-a464-7ae1e99fe321 | note | REFERENCE DOCUMENTS: Vicroads 306.05
3ae5377f-1435-5bb5-b4f2-aea35050189e | note | INSPECTION/TEST METHOD: Inspection / Test Method
b97e929c-9de3-52ec-9349-e9b0c85e9ca3 | note | RECORD OF CONFORMITY: Record of conformity
31b5d998-24de-517a-8502-5c2d6a681936 | note | IP
6b17ffcc-01fe-5c2f-9ee0-f745f4c403bf | note | RESPONSIBILITY: Fulton Hogan Engineer
b661cce1-cd56-5c77-8891-abc6f75288b0 | textbox | Date Completed:
73e2efc2-f946-4e9c-8644-26c6ac3f6c00 | checkpoint | 2.3 - Jointing
46125b2b-6963-5bc2-9141-c2ed9995d55c | note | FREQUENCY: Each Lot
1a0d57d6-455e-5714-a814-a6de0f0f602d | note | ACCEPTANCE CRITERIA: •Material shall be spread to minimise number of joins
ec5c2a81-3d17-554f-8fea-7188165d5ef0 | note | •transverse joints in adjoining paver runs shall be offset by >2m
5c3087d6-c858-54d9-bc57-b98d3b741f02 | note | •Longitudinal joints shall be offset from each layer
122e2e69-1bad-5eeb-b784-eb6ea426e889 | note | >150mm
be400956-f70a-5db9-8d74-227a6d55a22d | note | •Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
93f19c3e-f0ab-5400-88ab-d12438d96f89 | note | REFERENCE DOCUMENTS: VicRoads 306.08
a80f63ae-061a-5a6e-82b9-be0ed077d0fc | note | INSPECTION/TEST METHOD: Visual inspection
10f8384d-55c3-5f5b-8ba5-066e0e7b6159 | note | RECORD OF CONFORMITY: This ITP signed
339d07fd-5edb-5ee8-9928-69a0325fe9fa | note | HP*
bc903982-c6fa-5715-96d1-f37c71a4cf4c | note | RESPONSIBILITY: Fulton Hogan Engineer
e14fb8e6-eb0d-5b77-9494-895d4941c892 | textbox | Date Completed:
ba79a192-228a-439a-abcb-c7bc5b01c55a | checkpoint | 2.4 - Conformity with Drawings
9daf5168-65cb-54eb-9bc4-546acfcf22db | note | FREQUENCY: Each Lot
e33bd602-535a-596a-bb14-f5c032a474c2 | note | ACCEPTANCE CRITERIA: •Pavement sub base shall be finished to smooth and uniform surface
45a663ba-1d6b-5030-b3fb-a0a63100fa43 | note | •Surface of sub grade shall not lie more than 12mm below a 3m straightedge
763de658-7e56-5c6e-80a0-b4b00a037657 | note | •Subgrade height shall lie within +15 to -25mm
dec61990-8884-5f28-8ec1-4e8c7291fc42 | note | •Sub base height shall lie within +10 to -25mm
196fb642-2c2e-5f6f-abe2-c0df99988385 | note | REFERENCE DOCUMENTS: VicRoads 306.03 306.11
6e33610c-dde4-5d14-a534-749403a141d5 | note | INSPECTION/TEST METHOD: Visual inspection
09e728f2-7be5-5ca6-bea1-18b8b6203852 | note | RECORD OF CONFORMITY: This ITP signed
c5f7d4ee-4e04-5886-b4a3-08d8c71d5929 | note | WP
b7896d6a-6905-5fbc-845d-673277dda7e9 | note | RESPONSIBILITY: Fulton Hogan Engineer
664bc7c6-c5bb-55a5-a8bf-2ea0527b2e13 | textbox | Date Completed:
fbc6be36-deb9-4e02-9450-378d3828caa7 | checkpoint | 2.5 - Curing
d871691d-07b6-5ada-bcab-f5da3b4a09cf | note | FREQUENCY: Each lot
e0aef747-6431-52d7-8aae-2333fc5e3e06 | note | ACCEPTANCE CRITERIA: •The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane. •As per VicRoads, 4000m2 shall be maximum lot size •No trafficking before 24hrs unless approved by superintendent
67f51cfb-38ad-5d33-87b4-f4fe4892f412 | note | REFERENCE DOCUMENTS: VicRoads 306.11
987075d4-09d6-5572-8a58-4a70d89d30ac | note | INSPECTION/TEST METHOD: Visual inspection
e698348c-0db0-5cee-87c0-20675b87683a | note | RECORD OF CONFORMITY: This ITP signed
df3169a6-073a-5ee6-96f9-482a4f525b18 | note | IP
6306bb51-32bf-5a87-886a-053ce098dcf9 | note | RESPONSIBILITY: Fulton Hogan Engineer
5f489e1a-9801-569b-9be9-5c57e5578eb9 | textbox | Date Completed:
77715b69-7ae4-4add-92d5-a748d83c0c06 | checkpoint | 2.6 - Compaction Testing
43f9456a-e304-5b8c-b2ba-abec1beaa53a | note | FREQUENCY: Each Lot
b3dd3a49-f9f1-5095-8f01-c96005273c8c | note | ACCEPTANCE CRITERIA: •CT material shall be placed, trimmed to level and compacted within allowable working time (306.091) •At completion of compaction, any segregation shall be rectified •>500m2 96% modified compaction 6tests <500m2 98% modified compaction 3 tests
aaf4f2a6-b6b2-5c5b-92f8-2a8273d69d14 | note | REFERENCE DOCUMENTS: VicRoads 306.09 306.11
c57589ad-5011-5dcd-b088-354f195962fe | note | INSPECTION/TEST METHOD: Visual inspection
ba18394b-7f32-50a6-a64f-ecb5c014fc8f | note | RECORD OF CONFORMITY: This ITP signed
2302e5b1-4986-5d28-90af-28fcad80e653 | note | WP
d3d84e2c-ed93-5be0-a705-564f303dcd22 | note | RESPONSIBILITY: Fulton Hogan Engineer
983c3fe3-60f8-5c6c-8abb-f51cc1aec89f | textbox | Date Completed:
44851756-9444-4628-a0f1-0ddb113d7aec | checkpoint | Final Inspection
632727a0-864b-502d-9a88-7ad2a3a3fdb5 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
08d191ff-023e-553e-8abf-6e282d589a40 | textbox | Print Name:
f044604c-e66c-57b2-8785-a4c8c2241311 | textbox | Position:
d6271d25-ea59-5e9a-86b0-592b0774e833 | textbox | Date:
997b67f5-2bae-4855-b624-99d9be617889 | checklist | ITP-006 - Track Placement Rev2 |  | ITP-006 - Track Placement Rev2
8638e701-162f-4008-9337-878e4ad88515 | section | Preliminary Works
0bc5d70d-6a4f-45d0-992d-65c84c0f6eb2 | checkpoint | 1.1 - Check for Correct Documentation
a9f6101b-eddd-546d-8d6a-c6904b30897a | note | FREQUENCY: Prior to Commencing Works
bff15343-dd02-5c8d-a2c5-4ac4b3c0d217 | note | ACCEPTANCE CRITERIA: •Ensure that all employees and contractors are using the most current and complete set of drawings
416ae3ad-8658-5257-ac5a-2f8be0f26787 | note | REFERENCE DOCUMENTS: Design Drawings and Register
d347d83d-5870-5e06-a8c5-0d3c9149111b | note | INSPECTION/TEST METHOD: Visual Inspection
c68f4856-c159-58cb-a4a4-ef1a3b88a4f3 | note | RECORD OF CONFORMITY: This ITP Signed Off
9b43bead-4dbb-5f17-83c0-a5fca91f8fcf | note | HP*
757882e5-d2b2-54cd-ba82-8ee761d94fcd | note | RESPONSIBILITY: Fulton Hogan Engineer
cb94ba8a-7e7c-50d6-a2e4-695c186bee25 | textbox | Date Completed:
5b2a0718-f024-4c96-860f-4b18a71109a3 | checkpoint | 1.2 - Check Materials
2e9d3d50-f3f6-5c75-b842-36416e9a2150 | note | FREQUENCY: Prior to Commencing Works
78530731-9096-57bd-a261-c5c996c6e609 | note | ACCEPTANCE CRITERIA: •Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used •Check condition of rail sleepers •Ensure rail jewellery is of sound condition
25758be3-e9b5-5613-bc92-619c16c10117 | note | REFERENCE DOCUMENTS: AS 1085
b90e76a8-65be-55d6-a439-a551b9edfb2a | note | INSPECTION/TEST METHOD: Visual Inspection
228d9b0d-33c6-56b1-996b-a46d1e347d62 | note | RECORD OF CONFORMITY: This ITP Signed Off
72ed37d7-6b71-51cc-a773-da7d2ec95535 | note | HP*
2a4f9b36-7a21-5e2f-93c0-174776e6264e | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
2290a2dc-d2dd-56a9-b159-ac10169ddc13 | textbox | Date Completed:
34bc923d-e357-4463-b7e8-f7fd6549c6f9 | checkpoint | 1.3 - Check Special Works Components
8443d6fe-d67f-55e0-9a31-4924bd864938 | note | FREQUENCY: Prior to Commencing Works
5cf35b45-b37b-5181-900c-8bee1299cda0 | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending. Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and separate rails. Superintendent to visit yard for initial inspection of the rail and fabrication plans.
91d996e4-4a91-5e7f-aa6a-61ab375dc5db | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
58544c2f-b5ad-5e3c-855b-7f28e8b91227 | note | INSPECTION/TEST METHOD: Verify
57e32c06-06b8-5ef8-b813-875ac6291fa6 | note | RECORD OF CONFORMITY: This ITP Signed Off
4c158ef7-b7b8-556e-b2ab-06fa1e901653 | note | IP
796ddb62-f7cc-5bb9-b633-8145e821e3b0 | note | RESPONSIBILITY: Fulton Hogan Engineer
17ff1f69-aef6-5ce8-89d2-1196d6851b11 | textbox | Date Completed:
18119e14-dfa4-4c74-99e2-99e9675339df | checkpoint | 1.4 - Check Curved rail
47c54ec1-7fdd-5dd8-9fd4-68a39a5a668c | note | FREQUENCY: Prior to Commencing Works
abeed3f9-46ae-5cd9-9f72-ca422a95806f | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent. Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails. This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
48ecda73-3300-5da0-b9e2-71f1be01237f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
2e23ca6c-62b4-5fae-bcca-f25232bf0e6d | note | INSPECTION/TEST METHOD: Verify
d80a6ebb-f1f2-5162-812d-7892f42b2947 | note | RECORD OF CONFORMITY: This ITP Signed Off
e5184fa7-0d07-5a2e-9496-f0c53b087513 | note | HP*
87ca4108-7697-53ee-8754-aececfd7ecc0 | note | RESPONSIBILITY: Fulton Hogan Engineer
1ce13343-5bc0-580d-8e32-468b2af3f7a7 | textbox | Date Completed:
efc53d57-c637-43b6-9d1b-369590723279 | checkpoint | 1.5 - Welders Qualifications
cde514c1-ae37-53b3-ae7c-09eba3d3d438 | note | FREQUENCY: Prior to Commencing Works
8de4f531-0eae-585a-9b86-c98ebbb280db | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements; TLIW2012 Grind Rails TLIW3015 Weld Rails using Aluminothermic welding process TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
5aa8d607-d2fa-577f-9fa2-9f9aace9501c | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
6cf60e81-95d1-56a1-b7ea-7f908c6b2425 | note | INSPECTION/TEST METHOD: Verify
0d4cb18c-f207-5fc2-882f-d9126911d598 | note | RECORD OF CONFORMITY: This ITP Signed Off
90fd63fe-6138-53c8-b6be-8f7d0bcae14b | note | HP*
6734c3b2-81d0-504c-86b3-efea242f77ec | note | RESPONSIBILITY: Fulton Hogan Engineer
7ce9fa70-c72a-5557-833e-8eb60ff42ea6 | textbox | Date Completed:
b8e08c80-e2fa-427d-8596-9bde1e08f27c | checkpoint | 1.6 - Ultrasonic Testers Qualifications
0e22d080-1c68-5038-91da-f41ac01da751 | note | FREQUENCY: Prior to Commencing Works
1cbae80e-3faa-5225-9401-732fe5e73ee0 | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
202c8676-9e1c-50b6-a9b1-5d53bb34893d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
fc8c65ad-4a23-52ec-809f-5c76ad728587 | note | INSPECTION/TEST METHOD: Verify
0816cf96-344c-5d88-bd33-5a34763a22d3 | note | RECORD OF CONFORMITY: This ITP Signed Off
a2ce11fd-a067-5f24-b921-7054eb9abf41 | note | HP*
55eaee17-955e-5134-9a74-8e63d91a0d47 | note | RESPONSIBILITY: Fulton Hogan Engineer
d20ed51d-5f93-5d3c-939f-ff597c0f296d | textbox | Date Completed:
d1ecb7cd-e7fe-4496-977d-ffb48caef99a | section | Construction Works
77a9d75d-0c81-4bd6-bfe4-b9fefc746737 | checkpoint | 2.1 - Installation of Sleeper
df22f35a-cf0e-580f-bcc1-95ffbc387d68 | note | FREQUENCY: Each Lot
5cd8058c-4998-51de-a858-b8d48459b895 | note | ACCEPTANCE CRITERIA: •Dual block sleepers shall be installed at 700mm intervals, tolerance of +/- 50mm in placement •Dual block sleepers shall also comply with the design offsets at each chainage
a3e5c21f-d175-5775-b5b4-dfd7a74b6a94 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
af660b11-d091-5e09-9bae-3cb10f23e339 | note | INSPECTION/TEST METHOD: Visual Inspection
d2f2d266-201d-579f-8c04-e90d9d01c545 | note | RECORD OF CONFORMITY: This ITP Signed Off
549a774e-0b02-5534-bac7-7e76eb651e74 | note | IP
385d4547-9663-5739-bedb-df169d544c69 | note | RESPONSIBILITY: Fulton Hogan Engineer
d7f14de3-9540-55c1-b488-3f3bd134a12d | textbox | Date Completed:
e4a2508f-024c-4b77-aa3a-fde51e021f12 | checkpoint | 2.2 - Placement of Rail
0f95bb5d-00b8-5dd6-91c6-0f6b7f24d9ba | note | FREQUENCY: Each Lot
5732dcc6-f34b-5b46-8ab5-7ce4c781fcaf | note | ACCEPTANCE CRITERIA: •Ensure rail strings conform to rail plan
7f6dc1b2-610e-52d4-b394-9dae7826f3a7 | note | All track work, including points and crossings shall conform to alignment, offset, level and Can't as per design drawings and track charts
4fe10e08-e5ed-54b6-bcde-ead3b7fdae72 | note | •Bottom of rail and bearing surface shall be clean of foreign materials before laying
d8714265-5c8c-5d73-a354-9880887c8bb0 | note | •Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
18fc5a74-0337-58a3-8839-52ac9a073708 | note | •Geometry tolerances as follows:
87bcde24-ceec-5b7a-bc86-898387769a48 | note | - Centreline location: +/- 3mm
4cfa837f-17ee-58fb-a83a-6001b8848331 | note | - Level: +/- 3mm
378be735-5a39-5dea-8cfb-782bf4c9f1b4 | note | - Line measured (>10m chord): +/- 3mm
75e4a92a-e484-5b78-8793-0b5d043e75b3 | note | - Twist (3.5m chord): +/- 2mm
619ab36e-586f-55bf-8a74-eeeeec10296a | note | - Can't: +/- 3mm
ff47b5de-3bc3-518a-a000-17278683c98e | note | - Gauge (open track): +3mm, -0mm
fcc14020-6b0c-585d-830b-1a193050477a | note | -Gauge,Turnouts (opposite crossings):+2, -0mm
14e5909e-9981-5008-82e3-e1cdee0ba4e4 | note | -Gauge, Diamonds and ‘H’ Crossings:+2, -0mm Note: Can't shall be applied uniformly over transitions
d4a3d66c-b9cb-5920-a196-b7e85c90b1fd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
bd288dce-5d88-5ee8-84fa-870b8ea53fa6 | note | INSPECTION/TEST METHOD: Visual Inspection
96ea284a-2ac7-52d0-a308-0166013e379c | note | RECORD OF CONFORMITY: Completion of track charts
b8c13e4c-7fe6-5502-9af0-dc5685164398 | note | HP*
edb6b90a-fba4-5b67-834a-d6ea47269af1 | note | RESPONSIBILITY: Fulton Hogan Engineer
c3e79bf3-9b94-57aa-a0ef-41ae58e5fe51 | textbox | Date Completed:
3f023e15-6e17-4552-a48c-909ad353ee16 | checkpoint | 2.3 - Placement of Jewellery
24f151f6-c8fb-5096-a597-f9c1dbe28c3c | note | FREQUENCY: Each Lot
d6cdb11e-d06b-5224-81fe-c4dc6fd7ea21 | note | ACCEPTANCE CRITERIA: •Each sleeper shall be fastened to track with approved jewellery and rail clips •Clips shall be installed with panpuller or equivalent •All fasteners shall be sealed as per agreed method with Yarra Trams
2c9f7e66-9ac5-5c6e-9279-a45cb7800099 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
e614028f-7cd5-5d15-93ef-215aa603664a | note | INSPECTION/TEST METHOD: Visual Inspection
1d2102d0-c05f-5c04-99dd-1f6e79b9b349 | note | RECORD OF CONFORMITY: This ITP Signed Off
2de1062d-66ef-525b-803c-fa4a85814903 | note | WP
1bc56117-a97b-5b16-9ac9-e015dd270e8c | note | RESPONSIBILITY: Fulton Hogan Engineer
6ac948b7-01e2-57b3-b510-2a2bafb52b3f | textbox | Date Completed:
daaf1f15-480e-4d0e-8769-506ec38427cb | checkpoint | 2.4 - Rail End Preparation
057315c3-c4da-55f6-a505-b58ae302041c | note | FREQUENCY: Each Lot
49af8f14-f611-5908-9bb2-875b1cdd80d5 | note | ACCEPTANCE CRITERIA: •Rails shall be saw cut or flame cut •Minimum closure length from proximity of welds shall be 2m •Rail end conditions shall match (i.e flame cut - flame cut)
28aa1fcf-5a32-57c2-8ff5-356ca4f77e93 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
32e6e4f8-2dd4-508c-b882-01ab6e70d5db | note | INSPECTION/TEST METHOD: Visual Inspection
cca06b3c-f71b-54ab-bd9a-a1b186b47502 | note | RECORD OF CONFORMITY: This ITP Signed Off
17b2a9a2-e638-5506-af7a-810f7ca1e95c | note | WP
303fc521-f788-5fff-a884-381dcfd9b3d6 | note | RESPONSIBILITY: Fulton Hogan Engineer
bacd9f85-e9e1-5f6c-9e9d-fc76f4dd32eb | textbox | Date Completed:
2e05eb83-d171-4f8c-a603-3f0fa4687c56 | checkpoint | 2.5 - Welding of Rail
a9189a2b-4101-5c9f-adca-b3092e0f05c5 | note | FREQUENCY: Each Weld
fde0cb35-d0e7-5803-ab32-446358817ad5 | note | ACCEPTANCE CRITERIA: •Joints shall be square across the track
71bb8f2e-6027-520c-b5a3-2b141ab22c75 | note | •Maximum skew at square joints shall be 65mm
9ff24d72-12f7-5d35-9f21-f5bf2946a51a | note | •Portions shall match rail type (i.e HHR, Ordinary)
b35d1f26-debd-59cd-b70d-9e81b3f6a2a0 | note | •Welds shall not be within:
47932dfd-2480-59e1-b987-e233104244fa | note | - 3m of another weld
25541faa-5e88-5c68-8e28-2abbc6b34955 | note | - 3m of a rail end
5432dcc7-1713-5698-a61a-7ef7a5d625d3 | note | - 1.5m of a glued insulation joint assembly
aa0df4d8-33f8-5133-8a22-3c117dc761cc | note | •Field welds shall be +/- 50mm from centre of bay between sleepers
9d9311f6-b66a-5fea-9ff9-f0a51065f42a | note | •Weld Return forms shall be completed by qualified welder
a9edabaf-1636-56dc-b759-3fd9d0f082dd | note | •Welds shall be grinded after 1 hour
0b111886-d4e5-57b3-88e2-322d49e91e56 | note | •Welds shall be free of water
a276fa79-a9e2-528e-a6b8-1832387a4c17 | note | •Post grinding, welds shall be cleaned for visual inspection
168293a7-737b-5f4b-ae0d-0b5b02bd9566 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
274749eb-deaa-5ecb-862d-48db066cf2dc | note | INSPECTION/TEST METHOD: Visual Inspection
c8043bce-9501-5155-8439-df38e6186995 | note | RECORD OF CONFORMITY: This ITP Signed Off
dc41bac5-9a36-5f8e-b3bc-f4d2337fcfb6 | note | TP
fb23dfce-644e-5d92-8206-a507f13d3c84 | note | RESPONSIBILITY: Fulton Hogan Engineer
ebb948b2-6b5a-5291-87aa-791842a18fbd | textbox | Date Completed:
324feef5-8e32-49c8-a887-32a69d84a930 | checkpoint | 2.6 - Grinding & Cleaning Welds
9fd541df-38dc-5c64-bdbb-5021668304cc | note | FREQUENCY: Each Weld
ac910870-f383-5f4d-8f78-3200c4575d01 | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld. Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
f20dc132-4ac6-52f4-890c-116115032b7b | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
7be70835-f71b-512e-ac4b-20814a133b78 | note | INSPECTION/TEST METHOD: Visual Inspection
759e9cb1-95f5-5522-a6bd-5325056d9f1e | note | RECORD OF CONFORMITY: This ITP Signed Off
ba48cefc-5656-5cfd-90e4-ae2ccfe97029 | note | IP
4dc04e9f-8489-5632-a90a-a64f8b6299ee | note | RESPONSIBILITY: Fulton Hogan Engineer
fa3b1335-ce5d-51df-814d-9ee8789f4288 | textbox | Date Completed:
9d951fdb-c4d3-47f9-b920-9d27b24cbc2d | checkpoint | 2.7 - Track Adjustment
adb014ae-4178-5326-b3f3-62767e21ceb0 | note | FREQUENCY: When required
8a38d4ef-8bc7-5eec-9d8a-920c94e660a6 | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with an approved type of thermometer. In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep. Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
8229bf3b-fcb3-569f-a183-2ca32c2d5831 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
b79a152e-968b-57b9-bce8-3f451ea6ec50 | note | INSPECTION/TEST METHOD: Visual Inspection
76d38373-87df-572e-9412-fa5945a93d70 | note | RECORD OF CONFORMITY: This ITP Signed Off
ec4c33bd-7508-5c4d-80e5-1ca619c475d0 | note | IP
331c59b7-ba53-53b8-b945-c66dac444491 | note | RESPONSIBILITY: Fulton Hogan Engineer
e0eb5341-a94f-54d5-bff5-a80e24a006e2 | textbox | Date Completed:
0ac65c38-894f-4c76-8774-c2d053d1cc81 | checkpoint | 2.8 - Track Bonds
ae76a8fb-2aff-534e-bfb3-21998b205810 | note | FREQUENCY: Each Lot
2f20d85b-e068-5295-8f58-902e80ea582a | note | ACCEPTANCE CRITERIA: • Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications • Ensure bonds are sealed as per agreed method with Yarra Trams
59dd48f3-bc30-5280-a828-32cba52e8edd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
4987c46d-fdd6-5eb8-aa49-c4f587859519 | note | INSPECTION/TEST METHOD: Inspection / Test Method
bc2b58b9-3feb-59eb-a9fd-5959751fde78 | note | RECORD OF CONFORMITY: This ITP Signed Off
fc52c414-2b0b-5c22-b99e-da055b028830 | note | IP
84e45103-4c14-5f02-bc5f-424f94e50f32 | note | RESPONSIBILITY: Fulton Hogan Engineer
2808b6f7-bafb-5611-a73d-903c74d942be | textbox | Date Completed:
d4dd96ee-3838-49a7-833f-ab90eb8be860 | section | Testing
2153f2d9-074a-4d69-861b-89721e574235 | checkpoint | 3.1 - Track Testing
da3125dc-031e-5d3d-871a-daab46d381c5 | note | FREQUENCY: Each Weld
2f6172cc-15a2-52c9-9d2b-56136267a2af | note | ACCEPTANCE CRITERIA: • All welds shall be tested by qualified NDT operator • Failed welds shall be cut out and replaced • Testing documentation shall be recorded and supplied to the superintendent
2e06ef44-e4a8-57ef-ac38-015ae5d48ac4 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
f879568a-6747-5ef4-b7a1-87e662008bc4 | note | INSPECTION/TEST METHOD: Inspection / Test Method
a731faf1-2d6c-559d-bd3a-c67402c27f72 | note | RECORD OF CONFORMITY: This ITP Signed Off
24a0557f-4539-5489-b865-09b542f2f525 | note | TP
2136d20d-86c4-5b6f-ad09-e979d48bb61a | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
3802323f-4488-56a4-8c52-4514b6cbe0e2 | textbox | Date Completed:
7f092257-2b54-4e74-b262-9e9e46837cd7 | checkpoint | Final Inspection
0c805cf6-be36-5257-9048-99270e04c62b | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
22b5c30f-37fb-59c6-84bd-f5ec6dafab80 | textbox | Print Name:
ef39e119-9b2b-5a31-89ee-3f92a6bd92da | textbox | Position:
c1f630ac-5228-5180-aec3-9c00643afce9 | textbox | Date:
61551740-e4cb-4d0d-a079-9303211f7010 | checklist | ITP-007 - Concrete Track Slab Pour Rev2 |  | ITP-007 - Concrete Track Slab Pour Rev2
35169eb4-1f34-47ae-bcf1-a7d7730ab329 | section | Preliminary Works
49962ae4-d301-4e1e-be59-a9cc1497a2eb | checkpoint | 1.1 - Check for correct documentation
4cb6654c-e644-59c9-a142-487021c852e1 | note | FREQUENCY: Prior to commencing any activity
d5095a0b-23ea-526d-bb54-596696d16239 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
e5a1bcec-44b0-5e8d-a51a-e45f1f5c9752 | note | -using the correct and complete set of drawings
08ef62b1-34f7-57e1-a1b8-a3181ccf47ad | note | -all drawings are the latest revision
019f9f11-ac49-5d70-9c4f-8dd4ac561e95 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
b365a7dd-63b5-5f56-b5cf-69f36f2c426c | note | INSPECTION/TEST METHOD: Visual inspection
53cd2e55-b78a-5bd5-99e8-e629389657a2 | note | RECORD OF CONFORMITY: This ITP signed off
38b57c69-8140-5b42-87cf-ac47712460fd | note | HP*
1d3047d8-e2f6-5c17-a87f-c31c25255c34 | note | RESPONSIBILITY: Fulton Hogan Engineer
c48f802e-a619-57c5-b35a-e2c5bcf44d2d | textbox | Date Completed:
2b09f9d7-23f9-4936-a916-00beccb3090f | checkpoint | 1.2 - Submission & Approval of Concrete Mix Design Prior to Commencement of Project
8e319edb-c9e8-57a9-aa47-c31048897edc | note | FREQUENCY: Prior to first concrete pour
42bf6101-2f51-5c4e-85e2-a42007e723d2 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
c2534037-e242-522f-a39f-251c6fbf1851 | note | Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
540b69ca-87d7-5669-aa16-bbee29025e63 | note | Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
fce67552-e748-5cab-9211-26d3e2626528 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
328e3276-77f7-5daa-b542-af7ef0793465 | note | INSPECTION/TEST METHOD: Verify
ff34d1a7-d0d4-541f-9e8f-1ed7a0d8b82e | note | RECORD OF CONFORMITY: Mix Design ITP
befcdaac-854a-59e0-8c72-f58207a41a04 | note | HP*
9c91155b-49b1-5912-9f59-5809b94b6d12 | note | RESPONSIBILITY: FH Engineer / Superintendent
d1e49297-3fad-5f65-93b6-e88dad3021b0 | textbox | Date Completed:
077cd25c-25d9-45d4-b3da-fe1db8339460 | section | Construction Works
79c8a8b5-2396-4c4e-9820-4eb0c43df1b8 | checkpoint | 2.1 - Weather Monitoring
d3d726c8-d552-53b3-9825-157ec9e76052 | note | FREQUENCY: Prior to start
fce31f30-fcaf-5b67-8be8-328489573765 | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
198624f6-ad18-5370-9636-5d149dc868a9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
ad2acb2f-d40b-5833-94bd-f422c9794dd8 | note | INSPECTION/TEST METHOD: Verify
7c941d88-9eb0-5b0b-99b5-5069cba63783 | note | RECORD OF CONFORMITY: This ITP signed off
449cc161-7805-59a2-adad-255cca512c12 | note | HP
99a277c6-838f-538f-8c43-ace706a19a6b | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
76e38191-4a5a-50d3-8950-f330396fb39e | textbox | Date Completed:
118cae00-1b3e-420a-b087-862c774d3bc1 | signoff | Authority holdpoint
2579aa4c-af51-4362-a326-0088ba6214c8 | checkpoint | 2.2 - Surface Preparation
38a5f8e6-d3ad-5393-8ae7-a2a84ccc89a7 | note | FREQUENCY: Prior to start
020624a4-61ac-5568-94c3-3713bb2efb9d | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thoroughly cleaned of all foreign and loose matter prior to pour
55358064-b6de-5b5d-a725-64d0f4e0d08f | note | REFERENCE DOCUMENTS: CE-019-ST-0033
6684db5f-0fab-5b70-80bd-6caacdd01ef0 | note | INSPECTION/TEST METHOD: Verify
a8917dff-d536-50b3-8e9d-376935e4f04c | note | RECORD OF CONFORMITY: This ITP signed off
86f57996-1f21-5348-81e3-5dc75c3ec4a9 | note | IP
19074b8d-9c7e-54a4-a248-b4a9fee60ff4 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
81d1d4e8-ae92-52c7-bd07-980e30b9625e | textbox | Date Completed:
9c39c975-59b8-4bce-8e48-59050723808f | checkpoint | 2.3 - Setting Out
530214c1-86f7-5059-a6f5-01e7102a76d5 | note | FREQUENCY: Prior to start
30e3a984-414c-5264-9287-d8e391fecce7 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications. No survey/level pegs to be removed by any persons until completion of works.
ff06f841-05c5-5179-8c72-0b0e93ed2aab | note | Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
c30adfde-903e-5518-8482-1a44265facb6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
007057c4-87f8-52fd-adae-a4f306878d45 | note | INSPECTION/TEST METHOD: Verify
c59267b6-afc8-5388-9234-df17ff4d7eab | note | RECORD OF CONFORMITY: This ITP signed off
2ae98cdd-f337-530d-93af-523eb7315292 | note | IP
57811909-371d-54e9-9c42-2737d91b6575 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
8b45aee7-ee92-58ef-810a-bb0e62d1bec0 | textbox | Date Completed:
c1835001-d52d-4f22-a26a-1bb981e5a50a | checkpoint | 2.4 - Formwork
b9a6f471-86ca-52f1-9a90-48e9c06bdbfa | note | FREQUENCY: Prior to start
fe3b729a-157e-5ec7-baa6-ba9ebbd8c662 | note | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
71400142-725c-56d4-a1e0-ba692d78e6d7 | note | The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
8a6c5b58-c01b-5730-b41b-c36b760444c2 | note | Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
88f82a7e-973e-5985-bcc6-ab0ea0c33777 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
fc6bd558-bec0-562f-8d2a-4dacbb186d73 | note | INSPECTION/TEST METHOD: Verify
ca6788d7-7122-54f0-8a5d-b10a1977b707 | note | RECORD OF CONFORMITY: This ITP signed off
a815330e-3447-553e-94d2-9cbb10da673b | note | WP
08510476-d9f1-5aab-812c-a4fb682e4672 | note | RESPONSIBILITY: Fulton Hogan Engineer
bdb76cde-c219-5fde-840b-7eb6950f58a5 | textbox | Date Completed:
448b0f44-d649-4322-9a48-cd830908f0e8 | checkpoint | 2.5 - Reinforcement
22fa4d89-13a3-54a4-bd3b-ccdc9eca107c | note | FREQUENCY: Where Required
94f05174-a545-56e1-b784-1dbea6e6054d | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
e0677cb4-272d-5d02-9744-1cad3b7f0236 | note | All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
f974b13e-31a8-5c24-8b50-bd5c69a8e031 | note | Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and ied with wire at a maximum spacing of 500 mm.
a9b42a34-b194-5eb1-ab5d-025cc1799537 | note | Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
38a03c06-d3a3-5dd1-afdc-01077a7a6786 | note | Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
a9c1d7c1-fc30-569b-a991-c5a372bb514c | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
86cd96cb-a18b-5bee-8d60-b126f8e614df | note | INSPECTION/TEST METHOD: Verify
10d36a5d-9457-5a31-91d3-6b9611035a9f | note | RECORD OF CONFORMITY: This ITP signed off
beb36c87-eeed-5223-ae82-c8f7f946ad87 | note | IP
a352277c-98b6-5da6-bc57-f80b719f514b | note | RESPONSIBILITY: Fulton Hogan Engineer
9b007475-8e66-50e0-9562-d6364b053c46 | textbox | Date Completed:
cdd044cb-9201-4121-acc9-34dbadacd33e | checkpoint | 2.6 - Dowels
c7e7f46c-916a-5349-a264-16b84ec47420 | note | FREQUENCY: Where Required
ace65bd4-0bb6-53e1-b47e-61d9c92f295b | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
b34b2dec-28e4-5946-a86c-37e63fd849d5 | note | All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
09bf7fee-a8a7-589b-bdad-07975fb7247c | note | Dowels shall be clean and free from mill scale, loose rust or oil.
52c21aef-b949-5d75-aabe-ef367fcee69e | note | Ensure that all dowels are securely held in their correct position until the concrete has set.
960c8f49-6046-5e5a-b453-7c745c42fce0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
7a143a24-bf25-59e5-acd1-866145bf9bc0 | note | INSPECTION/TEST METHOD: Verify
0346b619-bb25-5537-aa1c-a11833107b9e | note | RECORD OF CONFORMITY: This ITP signed off
0a0f7e6f-5700-5387-b075-347fedf3ecd9 | note | IP
9bdbf464-61c2-5577-93ec-f96ddd85a0c5 | note | RESPONSIBILITY: Fulton Hogan Engineer
dd5bea46-82b0-5fa5-b049-76040c0ef02e | textbox | Date Completed:
8df80abc-00e3-4628-beaf-ce60980adb7c | checkpoint | 2.7 - Pre Pour Inspection
27354edf-9e22-5440-9423-86a5e1254ab3 | note | FREQUENCY: Prior to start
143a0393-f523-5ac2-9f29-2faeb52d85c8 | note | ACCEPTANCE CRITERIA: • Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180degree difference in gauge placement
c34df935-26de-51d2-b593-0ae7c91aebd0 | note | Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
a38b60dc-2dd6-58f8-8baa-139f8946e893 | note | Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
7d3073c5-1f93-5f23-a09c-044c951f65fb | note | REFERENCE DOCUMENTS: CE-019-ST-0033
56da5d10-fa73-584f-b69f-675961218efe | note | INSPECTION/TEST METHOD: Inspection / Test Method
14dbb503-4d7c-5ade-a366-45c80d241f80 | note | RECORD OF CONFORMITY: FH Track Inspection
6243edb1-cb60-5bda-91df-1b3ae217fe87 | note | HP
0eb64a17-f9dd-5d96-8416-763cea0bf99b | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
ccf83ec1-ba9a-59d0-a3e1-81dd81c1637e | textbox | Date Completed:
39a09ed8-01e3-440b-8c2a-82ccfa8f186a | signoff | Authority holdpoint
76b0f63b-5567-44c5-a581-9be9e0f61278 | checkpoint | 2.8 - Carry out sampling of concrete
484ba315-86c5-5300-b58b-1b53cc5ba519 | note | FREQUENCY: Each concrete pour
70712f89-1da0-5705-a581-f17022150213 | note | ACCEPTANCE CRITERIA: Slump:
535ab5ea-5999-54c5-b8de-4f907a777fdb | note | Concrete Slump shall be 75mm +/-20
8cb20999-2201-593f-aa71-edce9ea163ea | note | Compressive Strength:
126d3bf0-ee30-571e-b04f-96e00bd29c36 | note | Shall be measured in accordance with CE-019-ST- 0033
4792da5d-ec65-52df-91ce-9de537743fb0 | note | • Testing frequency =
a3ccd1e9-cf0f-54d3-9462-83eb3ac49480 | note | - 0-50m3, 1 sample
03bb8ed4-7d94-5592-851a-62104e91778a | note | - 50-100m3, 2 samples
cbe9cd37-de5b-5e55-a3e1-34f37eab3871 | note | - 100m3 +, 3 samples
15c6f53b-f2c0-5497-a9e3-5c655a11612a | note | Each sample shall consist of 4 cylinders
e1f4a866-fb77-5d3a-a418-5abd54f48732 | note | Test Results will be provided to the Superintendent
4ddcaca1-e8c5-5d9b-b806-189ab4c0c76e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
9c6c3c61-879f-5077-b554-a6bbbe7821eb | note | INSPECTION/TEST METHOD: Verify
b317adcf-e781-5a07-aeaf-fcf90bdc0c66 | note | RECORD OF CONFORMITY: Concrete supplier test sheet
d5a5389f-e670-578a-898d-48061c34c37f | note | TP
6044ea3f-740d-57f2-aeb0-fba98b27a40b | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendent
04c67199-287d-5eb9-8811-d68f4d7092af | textbox | Date Completed:
5b064ce1-d940-4ec4-ab29-294ea7b5b496 | checkpoint | 2.9 - Concrete Placement
cd2cab6a-af63-5254-9ac9-9cb8e793ab4b | note | FREQUENCY: Each Lot
380e88c8-7c62-52a1-b141-9809511fd3d5 | note | ACCEPTANCE CRITERIA: Ensure formwork is clean
2162c610-9b84-5f6a-93b4-7e043d61335c | note | Concrete shall be entirely discharged 60 minutes after batching,
16e81e03-b5d8-5c6e-966f-ba430e158c74 | note | Ensure that pouring does not occur from a height greater than 1200mm
11f1d96c-d543-58c2-b88d-828b5b292849 | note | Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
f3220f10-671c-5c9a-904b-dfe56d9648b0 | note | The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage
383841f9-ccee-592c-85a8-ba655a726c19 | note | There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
d07d15f4-21ca-58dd-b132-ae99b9574421 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
1454ec1f-47b7-5bef-acbb-f159702c1eef | note | INSPECTION/TEST METHOD: Visual Inspection
09d30224-778c-5c89-9ce5-daeb5de68f72 | note | RECORD OF CONFORMITY: This ITP signed off
ab7447e3-5b12-5ab4-afb5-1bd00b0cc0d1 | note | WP
234c3115-a9d8-504d-b64a-d83eb2c78e34 | note | RESPONSIBILITY: Fulton Hogan Engineer
78732b87-32c6-58b9-a1bd-d642448ded2e | textbox | Date Completed:
725bb135-e8d4-4033-bcbc-c49f17e884f2 | checkpoint | 2.10 - Compaction
76339f15-b7ca-5e2c-976c-fc538b664a08 | note | FREQUENCY: Each Lot
62d67682-0d8e-5a62-888a-e5623a5b3363 | note | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator
a94965db-9272-5fe2-8d1e-7315dcaa5f69 | note | Vibration shall take place until exposed concrete surface is free from air voids
db25feac-74b5-5c0f-be98-bf186f306923 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
753aa743-645c-5920-9103-858651d44dcf | note | INSPECTION/TEST METHOD: Visual inspection
595108f2-0156-5c63-ab7f-59e558e90edb | note | RECORD OF CONFORMITY: This ITP signed off
ec375ddd-4a3e-55a0-9f31-3d9d5cdb7ef4 | note | IP
5483b2f4-2e3b-513e-89aa-c18338f2b70c | note | RESPONSIBILITY: Fulton Hogan Engineer
caf1afa5-a5e8-5ab4-aad3-51e20b2cbd0b | textbox | Date Completed:
e894cbb9-fd27-4b40-b894-225c6df90766 | checkpoint | 2.11 - Record location of each batch
4f021060-7e90-524a-8afd-8eaec5ef805c | note | FREQUENCY: Each concrete pour
f5f31bfc-41d4-5e58-87ca-74f9558d6555 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
0365a058-5a40-5325-a882-ea3aec27c28e | note | REFERENCE DOCUMENTS: CE-019-ST-0033
3903622e-3282-5ecd-8925-a0b3428b0564 | note | INSPECTION/TEST METHOD: Checklist
f7ca9e5f-fa65-571f-bbca-799e7e175c3f | note | RECORD OF CONFORMITY: This ITP signed off
34e0fc08-3fcd-5515-aa3c-aaa8e4a89017 | note | IP
9269e226-6eab-5cfb-9c63-32aa8c1c0ffb | note | RESPONSIBILITY: Fulton Hogan Engineer
c44c4182-c8d5-50c1-a181-bdb4fe6d533b | textbox | Date Completed:
7884dab2-f2ac-4544-bb9c-326d2f767629 | checkpoint | 2.12 - Curing
fbd1b915-4100-5ab8-b74b-328337b58d66 | note | FREQUENCY: Each concrete pour
6058fb00-6d8a-520e-886b-198d8afe7ff9 | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming
52f38f53-3108-5288-a839-4b91ca7ef681 | note | Concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (Concrete to surface).
32a905d7-46b0-5028-bb38-99d17a38f80a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
47267e8e-e178-5f70-82f1-d894a8eb01c6 | note | INSPECTION/TEST METHOD: Checklist
45297b0a-a97d-5576-9e27-769fb266d462 | note | RECORD OF CONFORMITY: This ITP signed off
56e209b5-bca3-5d83-b296-4b9cc40acf7c | note | IP
cecb30ae-c9d6-5aca-ab87-1632f831e4d1 | note | RESPONSIBILITY: Fulton Hogan Engineer
417fcd07-3541-5f44-b65e-e8c2b71bc188 | textbox | Date Completed:
228e10d9-1705-4438-aecb-f4203b75697a | checkpoint | 2.13 - Tolerances
5912b5ed-0a68-56a1-b670-afc6b1730eba | note | FREQUENCY: Each concrete pour
8c5377ba-3bea-56bd-b747-034e2154b2cd | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
07a37b96-22de-5ce5-9066-6fb973fe9576 | note | Plan dimension of slab +10,-10mm
9c4acd30-e352-55a6-a917-0d1a32f9111c | note | Thickness of slab +10,-10mm
95b1b32b-3877-5891-8ebd-033c1e1b80fa | note | Cover to reinforcement +5,-3mm
91ffb1c1-e2d5-526e-bed8-5767dfc9ccbb | note | Finished level of slab +3,-3mm
abb122b3-c855-552d-85eb-e453d3dc3785 | note | Foundation level of slab +0,-20mm
5c6d1568-f73f-53af-a849-35c80157590a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
dc02d59b-1ab7-550a-a537-5b799855fc78 | note | INSPECTION/TEST METHOD: Checklist
366cb432-a2b7-54e0-a132-472a16f2c8e4 | note | RECORD OF CONFORMITY: This ITP signed off
eebafc34-b70f-54de-8bd3-dc02c1d4ede5 | note | IP
63a096d3-75bb-5a91-80bf-f14bf056a07e | note | RESPONSIBILITY: Fulton Hogan Engineer
e67259f3-c79c-55f4-958a-69482254088e | textbox | Date Completed:
f31f29a1-69ca-43c8-a265-616993cd63a9 | checkpoint | 2.14 - Slab finish
a305712c-f2e8-5c03-964a-00cdf8b3c453 | note | FREQUENCY: Where applicable - if track is Type 1 structure
4b4cbfec-2711-5a91-ab91-d5981c3d0541 | note | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities. All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections.
ce49c189-401f-5362-a874-cc8290cf744a | note | A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C.
8f15f547-e0bd-59b8-83f6-cab579eb33f6 | note | The slab surfaces shall be broomed to provide a non- slip finish.
56f8826d-afb5-5049-83b1-99f99ece9232 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
2702120e-e0fc-5dee-9d8c-b01e1ae0001f | note | INSPECTION/TEST METHOD: Checklist
248750f7-0dd3-54ec-9520-e01155b8de3e | note | RECORD OF CONFORMITY: This ITP signed off
49646a8e-70b0-506f-b506-919644be45c5 | note | IP
da1d2ba4-2ba4-5bf5-a009-b98a9342fc06 | note | RESPONSIBILITY: Fulton Hogan Engineer
72e8e345-b720-533a-8fa0-63e76e198a91 | textbox | Date Completed:
a551c717-febd-4bc0-9c08-d73953f19923 | checkpoint | 2.15 - Post Pour Inspection
3eae991a-0d68-5199-9058-873a30e2242e | note | FREQUENCY: Each Lot
fd503f9f-bbb4-5adc-82cc-c622f8a31361 | note | ACCEPTANCE CRITERIA: • Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
a970b890-8dd5-53f7-a245-ce94e418f44f | note | Ensure no defects are present in slab
4713f483-474e-5fb1-ad13-93d8ca8e85e6 | note | Complete Fulton Hogan Post Pour Checklist
c129dbba-f650-56bd-bc74-b5a7a1ed9248 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
9238ffc2-e1d2-592d-b9e2-5bae63ac8c76 | note | INSPECTION/TEST METHOD: Visual Inspection
7f5efedb-dc43-5562-98c6-879e12234567 | note | RECORD OF CONFORMITY: Post pour checklist
02515bef-7137-5377-b32c-41fb1a5add60 | note | IP
3409bac0-70b2-53c1-814e-bd8d1c16aa2f | note | RESPONSIBILITY: Fulton Hogan Engineer
8687213a-c616-5575-9bf7-e1584d7c9fb3 | textbox | Date Completed:
5ea148fe-a51c-4e46-b318-ce4c9d905157 | checkpoint | Final Inspection
1e9c2de3-6352-5c5f-980d-429d0833c6a9 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
cb9340e2-c8b0-52ff-b46c-79d49b049d88 | textbox | Print Name:
53ae5daa-ae2e-5899-ba84-9e540068f62a | textbox | Position:
3a4d8936-b51d-560f-822b-b1e0e4b0fb80 | textbox | Date:
2b4fac09-8d7b-40ab-bcd2-d1c13a64ef7c | checklist | ITP-008 - Hot Mix Asphalt Rev2 |  | ITP-008 - Hot Mix Asphalt Rev2
32f00d8d-c034-474d-b009-9d3bd33322f1 | section | Construction Works
a4510563-085e-4b2f-b9fb-e847b7de9026 | checkpoint | 1.1 - Submission of Mix Design
f8adddd8-0af6-5f8c-978e-9e7988146ab9 | note | FREQUENCY: Prior to commencing paving
189c1ed2-2c1a-5fec-a627-acb0197687e1 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
ee8b0ece-bcb3-5af0-a152-d1ea6401558c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
aeb3f2ac-4ce6-5713-bc8a-35f57ac97f03 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
6425ba00-b2d3-5f46-807b-5d36b05fc6a1 | note | RECORD OF CONFORMITY: Superintendent approval Completed ITP
cf950d0b-9933-5c09-b759-0b5eed8e65a7 | note | HP
3abc45d5-4960-55ad-b7a8-ef4b7429fc10 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
1818c2b1-80fe-54ec-aa85-29bdf25b2999 | textbox | Date Completed:
85ebae40-778a-4b0d-b8ea-6585099d9c79 | signoff | Authority holdpoint
445d0dff-891b-48a9-8ad2-4eb6b9c43028 | checkpoint | 1.2 - Site Inspection and Base Condition
2eb3e779-f165-59c5-89d3-d15ed9da8dc7 | note | FREQUENCY: Prior to commencing paving
a404b5d7-cc9e-59a5-9a20-b9c549e1d51d | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
ba70d87d-3497-5d6b-b1d8-d91a1bcf383c | note | REFERENCE DOCUMENTS: 407.17 AS2150 10.1 AS2150 10.3
4da89fb3-8a1d-5b59-9e0d-92fb6854ee88 | note | INSPECTION/TEST METHOD: Visual Inspection
10c79282-730a-5a61-ba87-8ccf7ceddf3a | note | RECORD OF CONFORMITY: ITP Signed
df4354b1-47a2-55b6-b75c-06313500687f | note | WP
a12e9de0-1142-56e6-866a-81c590a7ef92 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
26696bf6-69c8-5675-9dc5-11f1a00ae104 | textbox | Date Completed:
2cb7f277-5aac-4eea-95e8-eb30d570839d | checkpoint | 1.3 - Ambient Conditions for Placing
70ba1188-632b-514e-8dad-59da10de15a7 | note | FREQUENCY: Prior to commencing paving
6ef813a4-6428-5d3b-aab0-7e632e14aa85 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following: Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600 Wearing Courses: 10°C for conventional binders or 15°C for PMBs
d70e170c-498b-5ed7-9ada-ba339dfb2531 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.17
8710945b-12e1-581a-b1b4-9bcdd442e498 | note | INSPECTION/TEST METHOD: Verify
bf716b93-a929-5905-b18b-75ee0b728ae1 | note | RECORD OF CONFORMITY: Thermometer
302bd114-9800-514e-ab59-917895108cc5 | note | IP
3c3e5aa2-44b5-5a98-9f7b-47890b4ce67e | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
5252f3e0-51b1-5f01-88d3-a2c3f1cff5b5 | textbox | Date Completed:
8c2bdcb9-6aa0-4efa-911f-944668513d65 | checkpoint | 1.4 - Planning of Joints
79235922-4389-5dc2-95e1-078dc114c60d | note | FREQUENCY: Prior to commencing paving
73fb1a00-6796-58b9-b597-d441516b9cf0 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
08932d38-c504-5cd1-9146-0ea7040c70ad | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (b) & (c) Pavement Drawings
4c219313-89e8-529d-92e9-e2843ef26abb | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
23d510d3-789d-5a6e-9df5-f953781eea48 | note | RECORD OF CONFORMITY: Paving Plan
b9eff1e5-2a44-57cf-ae3c-8e9ce30de296 | note | WP
9ff0ee8c-4678-564c-8fec-655d6f613e6e | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
3333a269-c3a4-53dd-a106-a6a5cfc9d4c4 | textbox | Date Completed:
7bd8bdc7-f07d-4680-9df4-e124bb60ca66 | checkpoint | 1.5 - Longitudinal Joints with existing Pavement
b7724878-1988-5049-9cdc-2fb3cc4dc861 | note | FREQUENCY: Prior to commencing paving
d5db8b2e-a9d9-5b21-b147-5ef5d54dc6e7 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each individual layer.
39a644b8-0b78-5f69-8a7e-e099c5e65cbb | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (c) Project Specs. Section 3040.06 (d)(vii)
eb871a97-97bc-5e55-89a0-9817841e4ca5 | note | INSPECTION/TEST METHOD: Visual Inspection
a240c831-9a16-51ff-bd8f-26d26950593e | note | RECORD OF CONFORMITY: ITP Signed
e6b47fcb-cfbb-5ba0-b8c2-f917b258a4da | note | WP
5883ef0f-4a7e-5170-ae28-d3e321d01179 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
ac7de028-a81d-5000-81c0-10ea1a26d0af | textbox | Date Completed:
c2507be2-ddc0-49d1-81a7-992047f0cf67 | section | Asphalt Placement works
87235caf-2b70-4238-9320-43dcef13163f | checkpoint | 2.1 - Commencement of Placing
4065c301-794f-5b75-86a6-76248d5e2163 | note | FREQUENCY: Prior to commencing Paving
5c3769aa-655b-50c2-9626-421fce0e2dca | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
9554a3f4-4888-5ebe-a483-70726b0b8207 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.23
a5acd4f8-7d47-5df7-8f08-3836296c312b | note | INSPECTION/TEST METHOD: Visual Inspection
1863ba75-ffff-50ff-a435-1879ae190a9d | note | RECORD OF CONFORMITY: ITP Signed
81d80eb5-23e4-5ffa-8923-1b80368182b9 | note | HP
841f1b57-1ce8-58eb-ab53-07ae6f834310 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
192dbb74-a26a-57f9-8ae4-7a06c9e60254 | textbox | Date Completed:
18b19453-1027-4656-9993-bc7122878aa2 | signoff | Authority holdpoint
912efe65-541a-4262-88cb-6255ec9ce354 | checkpoint | 2.2 - Mix Design Confirmation
f78317ab-4c18-5f91-86ed-47cab3f43a92 | note | FREQUENCY: Each lot
dcef9324-00f7-5514-9a2d-c47154bd6846 | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt mix shall be 10H in accordance with Yarra Trams Track Structure standard drawing.
fdf43544-82f6-5c0e-bae7-0aee1b0e9120 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
4e85887b-4934-56e1-aa69-c4588dc378ee | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
6edae49e-595b-5a7b-981c-f56093dc26f1 | note | RECORD OF CONFORMITY: Delivery docket Completed ITP
f888f4d4-8e18-519c-8413-d48db64dc13b | note | HP*
e75b2311-8d44-53a1-81bb-5f2e09fdd840 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
2abd47b3-e877-5826-bb6d-e191ea29bd29 | textbox | Date Completed:
a03d927d-fcca-41c3-8d32-7c10c1997515 | checkpoint | 2.3 - Delivery of Mix
7d71cf62-e584-5a25-9870-b2f9dff8b65d | note | FREQUENCY: Each load
59e57862-a8ae-53bf-a706-c742d2897f3b | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
9060d016-e6b3-5d68-9df5-ac7c2eada43e | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.20 Table 407.111
ae063e9b-82c0-5751-9b25-9a06e49c655c | note | INSPECTION/TEST METHOD: Visual Inspection
f1e282a4-1f04-5bb0-bef7-09685d65fa68 | note | RECORD OF CONFORMITY: Delivery Docket
6731206d-15db-5af3-aa5e-7a2f9731c197 | note | WP
d01d81cf-a13c-5d95-8c81-889354a3a60c | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
e76e1440-5e7c-5f87-99aa-cdfc7a2ffce0 | textbox | Date Completed:
25eb6ec8-eb3c-43d1-95c8-29dca5ca804b | checkpoint | 2.4 - Traceability
ae1eb695-4d31-55ea-84f9-6464e62b0b35 | note | FREQUENCY: Each lot
505753d0-98c6-53bf-ab97-ce338612d289 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
7e6597b9-9abf-502b-808e-e2cf7f667ebc | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
8562a6d5-0418-5da4-a5e5-711b75ecd17c | note | INSPECTION/TEST METHOD: Verify
4ddacf46-cc8e-5ec4-960e-0a3ea9ff22f1 | note | RECORD OF CONFORMITY: Daily Lot Record
bb37fe59-e8d3-5ab5-8ec8-7b858705859e | note | IP
333ee25d-26a9-5944-9e3b-e5614f3673f5 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
96a49ff2-ca54-589d-82d1-991d3a3f58ab | textbox | Date Completed:
5b119ff8-ab1f-4003-a878-e6eb38e7942a | checkpoint | 2.5 - Layer Thickness and Level Control
cf1ac65c-6e3b-5444-92a8-530ba151bec0 | note | FREQUENCY: Regularly during paving
2c137a29-3ed2-5e2f-91c6-fdf35d50055f | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
4bc224f4-7021-510c-ab2e-4f8a2033df06 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.27 (a) & (b) Drawings
09a91901-db60-5389-b0db-bbe0a7ff2b95 | note | INSPECTION/TEST METHOD: Verify
0623e871-db0b-50a6-9ce8-5fd555bfbc39 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
bd5884ec-947e-502f-9d49-d13401445722 | note | WP
5d366e77-f234-5878-a76d-c22cf272fd0f | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
b5529fbe-4640-5e8e-b055-4d301a8edc5b | textbox | Date Completed:
9ad34018-268e-4364-8632-88399432316c | checkpoint | 2.6 - Surface Finish of Wearing Course
e48de210-7aa1-5040-a2b9-8a25234aac1f | note | FREQUENCY: During paving and after final roll
af12a86a-c440-50d2-bb95-da3d7e56f1c7 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
b12e7702-246c-5096-a8b9-c165b69fa30e | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(i)
306cd69c-70ea-5370-8c47-4e18f4cbd15e | note | INSPECTION/TEST METHOD: Visual Inspection
88ec0e51-2102-5542-8961-7d91a0eae093 | note | RECORD OF CONFORMITY: ITP Signed
11dd8956-9eb3-51a1-8321-81c7dec9d6fa | note | WP
5ea75d32-781b-5da8-8779-8daa04f10365 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
96266eb2-5c5b-5278-80d4-3a44b0c99fc5 | textbox | Date Completed:
b1eea0dd-c68b-4eed-bde7-84b3b6370419 | checkpoint | 2.7 - Alignment of layers not placed against concrete edge
ee4244f9-9e13-50e5-a0fd-1e4a1fa25a64 | note | FREQUENCY: During paving and at completion of work
36eab995-b7d2-5676-bc3b-81a6cf9b6ba1 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
701e0eaf-aa2b-5c67-99b4-5f330260fcea | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(iv) Drawings
1ea588b3-3f99-580a-9984-adf6932c13ed | note | INSPECTION/TEST METHOD: Visual Inspection
e965d1ad-f5b8-53e9-a33b-e2bca95af9a8 | note | RECORD OF CONFORMITY: ITP Signed
5af305df-321a-53b1-8016-a31a011f371d | note | IP
36ce58bf-8de6-5c03-be4d-175f13773d80 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
70c73c67-545a-5042-82e3-0fcc6cf2955b | textbox | Date Completed:
60973a3e-f96f-4b0c-b296-267b30bc2270 | section | Testing
36b5cad7-1c81-4d6e-8cdb-217e82175e3d | checkpoint | 3.1 - Compaction
a21e8455-f783-5225-a037-ffe5e7bb2f61 | note | FREQUENCY: Per Lot
b9bcaa13-aa1f-5207-8244-202822bce9c4 | note | ACCEPTANCE CRITERIA: For wearing course layers <50mm, if characteristic density ratio is: 94.0% or greater Accept lot 91.0% to 93.9% Lot may be accepted at reduced rate Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
565808b1-27c8-55bc-bc39-8373fb82bdd6 | note | REFERENCE DOCUMENTS: VicRoads Spec Table 407.271
d09c1111-c671-5802-9788-a6b5342a8123 | note | INSPECTION/TEST METHOD: Verify
7d6cc303-cd34-5ad6-84fc-36e8fba6393d | note | RECORD OF CONFORMITY: Test Report
a18f1084-1f11-546c-9711-d18ae4a6b9d1 | note | TP
23f04d34-f15d-58fa-8d8a-a8869ec03b0a | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
a8eb3d47-efb9-560d-9e44-51b9d002defc | textbox | Date Completed:
15d77fdd-4e5f-4477-9b17-5259c3cf976c | checkpoint | Final Inspection
f4632e0b-6bb8-5097-83b8-f7a749730f63 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
54886e99-fcc7-536e-adfc-9afc574a2032 | textbox | Print Name:
cc9f7232-9fd3-5c80-8835-675da8d23b16 | textbox | Position:
317285bb-6ae7-5cfc-9832-5d955fd770af | textbox | Date:
b5e88eb6-cab6-4e02-a771-18eaa39a91ff | checklist | ITP-037 - Structural Concrete Construction | itp | ITP - 037 - Structural Concrete Construction
f497e80a-a796-48e0-ac94-460989565962 | section | Design and Submissions
3ee02a01-dedf-4cd8-be20-ab3d646c2cc8 | checkpoint | 1.1 Check for correct documentation
10867538-2aa7-41dc-a905-feb98750ae31 | note | FREQUENCY: Prior to commencing any activity
70251ed3-c36b-4277-bd8f-7b0c4ac06a74 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
1a34dcff-ca4c-4da8-a88a-0b9e0aab1f08 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
3e8d9101-7728-465d-adb2-7c76cf5e575d | note | INSPECTION/TEST METHOD: Visual inspection
dc226a37-d59e-4958-b256-4b8a527e0d3c | note | RECORD OF CONFORMITY: This ITP signed
8114c6d4-a80f-40ef-a0da-30b96f57f274 | note | HP*
909092ba-a767-4cba-9008-cdec4d57dace | note | RESPONSIBILITY: Fulton Hogan Engineer
d494c5d2-9033-4a1b-8144-95bd559ba962 | textbox | Date Completed:
68b2e736-2851-4e04-80a6-d468932cb03e | checkpoint | 1.2 Implementation of all measures and controls
d8f36d48-9962-4c11-8a15-7d999df5ca76 | note | FREQUENCY: Prior to commencing any activity
1a98fadb-e11f-4bcc-86af-9cd7bbf83a3a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
c3b1be3b-1703-493b-936f-dc2f67514e64 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
5a3fb175-cf79-4d83-a4fd-353f6458d1ce | note | INSPECTION/TEST METHOD: Visual inspection
d59f6772-8936-4438-9d02-ef523eb7656b | note | RECORD OF CONFORMITY: This ITP signed
78b91eb9-ca04-466b-b3c7-7122153101fb | note | HP*
15846b91-27de-45af-bd9d-0daea8be34d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
dd645d3e-2497-451d-817e-3ffcc1209b23 | textbox | Date Completed:
9cf51436-c262-4af9-840a-f4b17da5d1e7 | checkpoint | 1.3 Approval of Mix Design
8d91ba3a-9d85-4a85-85ae-680babdbd616 | note | FREQUENCY: Prior to the first concrete pour
fc25cefd-c662-41a9-b4d0-e769458d7e37 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
6b85be64-be52-463c-b0a5-9f8ffb37041c | note | REFERENCE DOCUMENTS: WP 01
d5568340-fffb-4d12-a036-97b56a6423c1 | note | INSPECTION/TEST METHOD: Verify
8ec1954b-9e02-4d19-8981-f7867be1cc14 | note | RECORD OF CONFORMITY: This ITP signed
7d4caa8a-a2aa-43b1-8c38-2f5c58a5930a | note | IP
71523cc5-8446-48f4-9720-257e5b2fdfad | note | RESPONSIBILITY: Fulton Hogan Engineer
f210001a-e554-4b5c-8585-7081985ff93c | textbox | Date Completed:
a23770a4-ee21-4cec-8901-3eeb58651baf | checkpoint | 1.4 Reinforcement schedule
1172d2ac-91f9-4908-b1b8-2b24e80307b4 | note | FREQUENCY: Prior to concrete pour
54916229-d0c5-4f70-ba81-1debdd380a5a | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
49c4c6a1-e6c8-4328-8a70-e6af441cce5c | note | REFERENCE DOCUMENTS: Cl 611.04
d3cf1a27-9d7a-43a6-90dc-bb0d48a656f8 | note | INSPECTION/TEST METHOD: Verify
eb0ef6a7-9a73-4f96-8bb9-e50809857fa6 | note | RECORD OF CONFORMITY: This ITP signed
02ba46be-f354-4e8f-8dde-7b625e79350a | note | IP
5a7f0fe7-6a20-4dae-b1a5-4c31f53a2587 | note | RESPONSIBILITY: Fulton Hogan Engineer
0debaf6f-ccff-4a20-9155-cae027c4bbf0 | textbox | Date Completed:
2669a1e5-0a9d-4e81-ab8f-5a050e722061 | section | Construction/Erection of Formwork
941df967-2d33-4bf2-b914-44753ff3a5d8 | checkpoint | 2.1 Excavation
51e06fc5-ffaf-448f-a38d-a74d37791560 | note | FREQUENCY: Prior to concrete pour
b5a651dc-36c3-48a1-940e-9a747899b365 | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
84618964-c7ba-48b4-abef-8210887395e7 | note | REFERENCE DOCUMENTS: WP 01
2e188f4d-254f-4954-9353-6b7f81e3d6bd | note | INSPECTION/TEST METHOD: Inspect
9f13ee02-7ac9-4802-8bd4-399943f83c21 | note | RECORD OF CONFORMITY: This ITP signed
4de7053c-b08b-48ad-a295-359b08c0bb75 | note | IP
57b50d8f-e89f-4815-b41e-9acab9a98b59 | note | RESPONSIBILITY: Fulton Hogan Engineer
9fbd4a04-e66b-4cb2-b84b-89265af6b4d0 | textbox | Date Completed:
8eb9cf3c-3a29-4384-b5af-6106875cfb8e | checkpoint | 2.2 Construction Methodology
c1c38146-ca24-4e3f-9dc2-bce407701d48 | note | FREQUENCY: Prior to erection
1b9edb1c-bf60-4bad-b5b1-551e6bb31f17 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
9dcab8ae-c6ca-47bd-b1b0-a98b3e3dcc08 | note | REFERENCE DOCUMENTS: 614.04 614.06
45642352-0c3d-4801-9d6d-59b88a8ab8d3 | note | INSPECTION/TEST METHOD: Verify
9e1d047e-b6ac-4862-86af-d1c617e869a4 | note | RECORD OF CONFORMITY: This ITP signed
f892b8f4-de08-4d80-a1ea-f6a2de1dc750 | note | IP
37bcfb9f-df1d-4b65-9ed5-97d6816ded81 | note | RESPONSIBILITY: Fulton Hogan Engineer
4a31fa64-afb4-4f83-8b9d-f1946f4fb2eb | textbox | Date Completed:
9ab67fa0-b2d4-4c07-9619-9fa18b863ce7 | section | Pre-pour Planning and Inspection
2607b5d5-e269-49f5-886f-8723e3930964 | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
eb14d022-57f2-4465-8cb4-fc51e87e4011 | note | FREQUENCY: Prior to concrete pour
2a0fc54d-4095-476b-9b0f-6badd7c2e79c | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent.
4f66fdef-ee45-4197-9ba4-11650327bc57 | note | REFERENCE DOCUMENTS: 602.03
2d2d89cf-74b6-497b-b126-f495719f47fb | note | INSPECTION/TEST METHOD: Verify
84230696-cb8d-4b40-8b6d-d8d1d8fd03b2 | note | RECORD OF CONFORMITY: This ITP signed
f0892976-a7b2-4b72-8624-e9055d9c0894 | note | WP
b9973106-de6a-4555-aea4-9b8a85bfcbec | note | RESPONSIBILITY: Fulton Hogan / Yarra Trams
74cbae5d-c1aa-4cf1-96c1-c0b7b0c3e861 | textbox | Date Completed:
de2248e9-936a-4947-a4db-27d8d23d69cc | checkpoint | 3.2 Formwork levels and position
199f3526-1b7d-4442-98fa-29aba31201d8 | note | FREQUENCY: Prior to concrete pour
a27e44bc-39e8-4799-99e0-c63fb6c3c1f6 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
7fb008c3-d125-4812-ab2d-8debe9991bb5 | note | REFERENCE DOCUMENTS: 614.06
6b81a006-1e43-40bb-a882-5337385865fc | note | INSPECTION/TEST METHOD: Verify
7d580410-24f2-4854-8795-3853bdf0bce8 | note | RECORD OF CONFORMITY: This ITP signed
cad34c7d-529f-4069-a50e-171ef9a87445 | note | SCP HP*
0b611445-ce8b-4d0b-ac64-17675477da5b | note | RESPONSIBILITY: Fulton Hogan Engineer
3049e76a-44ec-4296-9301-a7770640d07c | textbox | Date Completed:
c0133c69-1e91-4063-9da6-9206ae1d95fc | checkpoint | 3.3 Location of splices
ecbdbc35-07a6-4481-8400-aed20870e310 | note | FREQUENCY: Schedule Review
9584ef3c-87d5-4f8f-b49b-619368f06e5c | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained. Where necessary the reinforcement shall be spliced with 40 times nominal diameter of bar.
ea35f784-8d4f-439a-bc27-5a8006455aac | note | REFERENCE DOCUMENTS: WP 01 Cl6.3
df1abb3d-12a1-4382-a527-71401733ebc7 | note | INSPECTION/TEST METHOD: Inspect
e8d78836-3822-40a4-97bc-69b2d17e4c5d | note | RECORD OF CONFORMITY: This ITP signed
5b72d23d-a3bf-463e-9c9c-3d654d6fd56a | note | IP
f1d95388-0a9a-457d-8848-14eae698e999 | note | RESPONSIBILITY: Fulton Hogan
ab2d05cc-8862-4548-8bcb-43ee36d108f2 | textbox | Date Completed:
db300c79-a43a-4b24-9deb-583d00f99a2e | checkpoint | 3.4 Cleaning formwork
609d0b97-8e68-48fe-84a2-c6b56a260992 | note | FREQUENCY: Each concrete pour
cb921a9c-c882-42f3-9aa7-1276c6767701 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
4b7b46d3-5874-4041-b667-c26e8812c7da | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
601e95a7-8bed-4000-8222-7198f9479f31 | note | INSPECTION/TEST METHOD: Verify
3802176b-d9a0-4240-96db-546f21aec767 | note | RECORD OF CONFORMITY: This ITP signed
37c3186a-1ff1-4034-969c-18474fd50cdd | note | IP
7893a330-8b58-4cbc-9789-3a55a93fa853 | note | RESPONSIBILITY: Fulton Hogan
b4e7d19f-b8b5-49b6-945b-19e88f5689d1 | textbox | Date Completed:
6f2ed6dd-30d8-465f-bcc6-5ceee4c103c6 | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
b748eb38-a56a-4232-b4ee-e61f6c0fc32c | note | FREQUENCY: Prior to concrete pour
cf625bcb-f0c3-412b-a01c-896a604e5e05 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. CL01A – Pre-pour Checklist completed and signed.
7231ba48-ffdc-440a-9cfe-683b5b8df7ba | note | REFERENCE DOCUMENTS: 610.18 (a)
3a18cdd7-19c1-4a24-8154-09856f3ec72b | note | INSPECTION/TEST METHOD: Verify
7f75eea5-6be8-408f-9a6c-0ef25179fc4c | note | RECORD OF CONFORMITY: This ITP signed and CL01A
950e7515-0e3d-484b-9639-33b1a9980992 | note | WP
dc1adc95-e5e2-4a74-9fb7-0efa8f8d9054 | note | RESPONSIBILITY: Fulton Hogan / Yarra Trams
02c48e7e-68ec-4a65-8993-3134c4042258 | textbox | Date Completed:
331268b9-cca4-467e-8ce6-d8659da0bf0f | checkpoint | 3.6 Monitoring weather
f37f95db-5b9e-47b6-8155-7a28720f582b | note | FREQUENCY: Each concrete pour
9b490dac-4125-4c59-9827-2dde9e7bb6d9 | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C. All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
088a0853-b3a2-4656-a0be-5160bd152e9f | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
7a3ae2e1-f4c5-4b5b-a833-bb5b4159c392 | note | INSPECTION/TEST METHOD: Verify
ba5be445-816f-49a7-8344-5425400070f5 | note | RECORD OF CONFORMITY: This ITP signed
8d4052a7-fdcc-4bc7-9104-885f089d0abd | note | IP
0b87ac01-ca86-4c70-853c-c86b39ef683a | note | RESPONSIBILITY: Fulton Hogan
ea983163-0d13-4104-90b7-da33d8ff6164 | textbox | Date Completed:
a3d99ee4-f6f0-4b7c-b362-7b3e1452d26b | section | Placing and Finishing Concrete
eee43301-06e6-4972-942c-80a71d924a37 | checkpoint | 4.1 Carry out sampling of concrete
94210c68-7d71-499e-af95-5cd0588b2330 | note | FREQUENCY: Each concrete pour
a24dad36-43cb-491e-aaaf-b2b411207e6d | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
8aafe55d-2ca0-4868-a43c-8296172e9896 | note | REFERENCE DOCUMENTS: 610.16
a88874ec-4067-4390-9e8e-a5d0177f051f | note | INSPECTION/TEST METHOD: Checklist
9eefb3bc-f6ed-4414-ae41-5c77224600c7 | note | RECORD OF CONFORMITY: This ITP signed
2bdcc4f7-7083-4981-9074-430bc84ab5a4 | note | IP
2397b2e3-d970-4dff-9661-fa4a8410800f | note | RESPONSIBILITY: Fulton Hogan
c99380d6-e94b-4da1-8a13-daaa91788992 | textbox | Date Completed:
fa576c5c-fb90-490c-8c9b-3ae800685141 | checkpoint | 4.3 Discharge time
4770a92d-e167-43e2-a7c6-25d67c191a31 | note | FREQUENCY: Each concrete pour
5a04315d-fa77-4fe9-bf4d-a5d4536bd6b4 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
669fd7d7-f802-43e6-9706-0b029ab00ad6 | note | REFERENCE DOCUMENTS: WP 01 Cl 8.2
d9007967-9a29-488d-9e4f-6144609c3ba9 | note | INSPECTION/TEST METHOD: Checklist
13687bb9-8a77-41bf-a7ac-54447db447de | note | RECORD OF CONFORMITY: CL001B
0ccf7d5d-74a6-4be2-8742-c79361f17357 | note | IP
a23bcec7-2e92-4c96-b326-32b702bb985a | note | RESPONSIBILITY: Fulton Hogan
25b5e215-1d65-444b-86a4-23d902ba2eda | textbox | Date Completed:
d9033ae7-b063-4f1d-8904-b6294b9d4031 | checkpoint | 4.4 Methodology of placement
99a7812a-bf2f-4f1f-9838-53b73418ddce | note | FREQUENCY: Each concrete pour
b61867a1-da27-4f05-8029-5ed9cbee6f2a | note | ACCEPTANCE CRITERIA: Concrete shall be transported, handled and placed in a manner that will prevent segregation or loss of materials. Concrete shall not be moved horizontally by vibrators. In continuous pours the max. time lag between truckloads on site is 25 minutes
a6ba842c-2c3b-4799-97d2-cd5c967bee2e | note | REFERENCE DOCUMENTS: WP
2b6dc3ce-ca1f-4b64-afce-2d7df1e7365b | note | INSPECTION/TEST METHOD: Verify
52737135-c8d3-429e-a061-9f3e6bad66a7 | note | RECORD OF CONFORMITY: This ITP signed
611812ad-6d60-430f-ae18-a5681b743f6b | note | IP
bcf7f1d2-f359-4ad7-8f55-dda055d7373c | note | RESPONSIBILITY: Fulton Hogan
6c276df3-1a46-4bb6-bf38-ce0e33d0edb8 | textbox | Date Completed:
f87e5359-8f5c-42e9-9eda-7d1c7bc8b134 | section | Post-pour Details and Inspection
fbcb2ba4-e75e-40a3-8221-0dcc1a560405 | checkpoint | 5.1 Formwork removal
fec2e4ec-1278-4ab4-9fdf-921991224a92 | note | FREQUENCY: Each concrete pour
6d8f7ea9-34e1-4586-a9f0-8ea0d505fe1d | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
4b03cd99-d01b-4c2b-ab11-48df860813ba | note | REFERENCE DOCUMENTS: WP01 Cl9.1
b8ca32a5-923a-430d-ac1c-b200f3069acf | note | INSPECTION/TEST METHOD: Verify
0c722068-a64a-4a30-877b-cf3a3beb8e22 | note | RECORD OF CONFORMITY: This ITP signed
6ef0bc97-ad5b-408e-aeb9-e455018b6b49 | note | IP
fbb9408e-4703-437c-b067-dac0c5df424c | note | RESPONSIBILITY: Fulton Hogan
31ef9ff5-b4f0-44df-8f25-1a9701d87fbd | textbox | Date Completed:
7d9bb0cf-329a-4165-850e-3a5b4e1575f2 | checkpoint | 5.2 Cracks in the concrete
5741c699-a11d-473c-9180-da7b8ba361c3 | note | FREQUENCY: Each concrete pour
c37d79e2-d266-498b-bdf6-d0a3a47a9e8f | note | ACCEPTANCE CRITERIA: Cracks investigated and NCR raised. Repair procedure submitted to the Superintendent.
356e3446-b91e-4da2-801b-539b9b7cf0e8 | note | REFERENCE DOCUMENTS: WP01 Cl9.3
6e8b7c51-e079-45d8-8bb3-15471fd8f83a | note | INSPECTION/TEST METHOD: Inspect
406d124c-79e5-40fe-b324-57cd3271dd2e | note | RECORD OF CONFORMITY: This ITP signed
32440c5d-9a4d-42f7-bf25-8f996affe477 | note | IP
33d13f66-98ba-47ff-a88b-abc089727b62 | note | RESPONSIBILITY: Fulton Hogan
b1db2169-300b-42d2-acd0-951c3b3e97b3 | textbox | Date Completed:
a6fd2d7c-f426-4738-812d-111e88b1d957 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members
014adbfc-6a2d-42b1-b49f-4d200eca51c2 | note | FREQUENCY: Each concrete pour
0c8824eb-91a6-49d1-a342-c00b55705e2d | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
7f1dbae1-22a8-4c35-ba85-adeebb84fe2d | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5
579eb7b6-83d1-403a-8790-f3c3c42c2134 | note | INSPECTION/TEST METHOD: Verify
28b64429-f807-4fea-b76e-7d9ba188b694 | note | RECORD OF CONFORMITY: CL01C
6b91ffd7-a99c-4a2d-88a1-2be3e5f1cea5 | note | IP
dc6573ee-4984-4c80-95f2-5c649cc3be04 | note | RESPONSIBILITY: Fulton Hogan
1037217d-898e-4636-b9c7-5bcbbf673377 | textbox | Date Completed:
9bfd3071-c69d-4a93-913f-c661e6d43883 | checkpoint | 5.4 As Built Drawings
359350ea-b49e-4f06-9b95-3aed78d5582d | note | FREQUENCY: Prior to lot closure
e4f658af-cb4d-42c4-a570-a605aec8d134 | note | ACCEPTANCE CRITERIA: The location of the footing and centre of pole is recorded on as-built drawings
e132c869-780c-4e16-be05-5e4eb3e2dfe0 | note | REFERENCE DOCUMENTS: WP 023
1202cc4c-dc63-4e39-b68b-f6be6055f1b4 | note | INSPECTION/TEST METHOD: Verify
a9903378-0d18-4ec4-9000-7050f1c7da50 | note | RECORD OF CONFORMITY: This ITP signed
43864597-a625-47fb-ad47-9bcb6db1f8e2 | note | IP
33c3b749-9e66-4cec-bb44-083eea211906 | note | RESPONSIBILITY: Fulton Hogan
f079d1ac-08e9-498e-9d3f-91686240cc9e | textbox | Date Completed:
0f83e561-9cf6-4ef6-9c42-0df819f96328 | checkpoint | 5.5 Concrete Sampling and Testing
a8f956eb-db6b-466c-8fc8-6c5df43a4e1f | note | FREQUENCY: Prior to lot closure
ffe36561-acf0-4c5a-b82a-9d65e1e8f259 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and slump
9561f75c-0127-4674-b85b-ffd506e252bd | note | REFERENCE DOCUMENTS: WP 01 Cl 9.4
62fa0a5d-5498-4fd0-875e-8a406181299f | note | INSPECTION/TEST METHOD: Verify
ab4d34e2-23ae-4fe7-adf6-59213078752d | note | RECORD OF CONFORMITY: This ITP signed
e171df6f-eb6e-424d-9626-51309c2bed87 | note | TP
53754690-b0d7-4e39-9b33-6213ef7d76dd | note | RESPONSIBILITY: Fulton Hogan
0c3226ad-e7c6-43f4-bc82-94e453c8b4cf | textbox | Date Completed:
ada95d3d-e8e8-4bea-a9d6-2b408a4815db | checkpoint | 5.6 NCR
bfc30203-a341-406d-8b69-b51beaf862a8 | note | FREQUENCY: Prior to lot closure
20dbd986-833d-4878-b3c0-42a9e1d67de5 | note | ACCEPTANCE CRITERIA: Details of any NCRs to be recorded
4cffa78a-6147-4deb-9b9f-65479b9c4337 | note | REFERENCE DOCUMENTS: WP 01 Cl 9.3
083312ee-7d21-4319-82af-e069c75a5a36 | note | INSPECTION/TEST METHOD: Verify
b45ab1bd-cbc5-4b33-a2be-8d53801f1d1b | note | RECORD OF CONFORMITY: This ITP signed
34275254-0e59-49d4-a1d9-48b4d6a1978d | note | IP
ef85bace-4a80-4c8d-819d-f0274d38cc99 | note | RESPONSIBILITY: Fulton Hogan
07b4d4ac-cb4f-407c-8d80-90becfa23adb | textbox | Date Completed:
efe68ac9-62b8-4fb1-8885-f0fd93f97472 | checkpoint | Final Inspection
004c51ec-2ac6-4827-88d0-b834bdfe452c | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
6013fef4-8392-4d83-a4bd-4bbd762095f4 | textbox | Print Name:
398dd287-ae40-4d1f-ae1c-e085e7608eeb | textbox | Position:
3db5451c-d836-4585-8390-c9164ae31227 | textbox | Date:
02deafed-e9cd-42fb-af24-26fabac01a82 | checklist | ITP-038 Bridge Deck General Demolition |  | ITP-038 Bridge Deck General Demolition
eb9f2d4a-bb46-4484-8aa1-57a2dad087b7 | section | Preliminary Works
f2fe7197-1c98-4edd-ba99-281992bddc6e | checkpoint | 1.1 Check for correct documentation
db44fbb9-594f-5a28-abe6-9ac1f095b0da | note | Frequency: Prior to commencing any activity
2c98832a-da2e-5f20-81cb-e092f10d2d1a | note | Acceptance Criteria: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
c049e74a-74b5-54df-8b31-b02c1a165409 | note | Reference Documents: Drawings and drawing registers
a9ff143f-c8f2-546c-927d-0c5999a30264 | note | Inspection / Test Method: Visual inspection
bdb50b66-5b73-58fc-8cce-ae412f2ac986 | note | Record of conformity: This ITP signed
416787da-4a5e-5238-b2de-6619c1ce5c98 | note | HP*
cda2f890-eb42-5f42-af48-3f2a31e7b4aa | note | Responsibility: Site Engineer/ Site Foreman
ad886946-9a7d-56d4-abbd-38f2e7aec412 | textbox | Date Completed:
5ab52bd1-7fda-43ba-a2a6-bba160c0c52a | checkpoint | 1.2 Implementation of all measures and controls
408f9e63-b868-5200-b001-9d31d26566dd | note | Frequency: Prior to commencing any activity
345fc28b-dffb-5d48-8ef1-d0b13ff99975 | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
930fc81c-18fa-55d1-9d6c-1d4d37238fa7 | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
90ae9adc-782b-52f4-ac5a-4ffca27acbd0 | note | Inspection / Test Method: Visual Inspection
faed2496-3b47-5374-bdb3-7ac86cc58f08 | note | Record of conformity: This ITP signed
46f725c1-85c9-5b5c-9bb6-020207bbfcd4 | note | HP*
f929b7ff-cfaa-55bc-a547-276e81f0127e | note | Responsibility: Site Engineer/ Site Foreman
3a12caee-7595-5c6d-bc7a-f8c077d57557 | textbox | Date Completed:
0e386831-9706-46ca-b4c4-9982cdbdda79 | checkpoint | 1.3 Service Identification
d72d4607-33ee-5906-aacc-4a002dcd7186 | note | Frequency: Prior to start
64525611-4e9e-5392-b3ec-93bc58c7a1d6 | note | Acceptance Criteria: Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected
b26d9614-94c1-53d2-93b9-347537a89083 | note | Reference Documents: ITP sign off
9d53d41f-4a70-51c2-b3cd-b038dca24510 | note | Inspection / Test Method: Verify
c471c44c-bc02-5cae-8875-04095faa1760 | note | Record of conformity: This ITP signed
c2e8d56d-5570-50e1-a103-b131e3a295fe | note | HP*
b56780d0-1e74-5910-8b41-f51db8d07e6e | note | Responsibility: Site Engineer
14812cc3-ef00-57dd-8810-cd9f97b43415 | textbox | Date Completed:
45c7bd3c-a1b9-42d7-b5a9-6b571b38bd55 | section | Construction Works
38c3a856-c282-48da-b73e-701c087d941e | checkpoint | 2.1 Saw cutting
f8491626-ccb5-58ba-a3fa-e4449cdadffa | note | Frequency: Where required
3dffbb02-9694-5e26-978e-248804e990bc | note | Acceptance Criteria: Extent and location of cuts to be clearly set out and checked prior to saw cutting
f567edfb-9e51-5a45-89c1-9d17db5f62fc | note | Reference Documents: ITP sign off
2904afbe-effb-5c50-b991-79ba88c1e97e | note | Inspection / Test Method: Visual Inspection
922d3ced-8446-57f3-bde6-4de7e80aa81c | note | Record of conformity: This ITP signed
ee57e1af-4200-5b89-b292-b015a807850b | note | WP
ca2a9c8d-f989-5e68-ada1-a5e96672a386 | note | Responsibility: Site Engineer
baedbda4-f700-5391-bd93-676be9b6ea9e | textbox | Date Completed:
a3564025-b4f6-405e-8562-8c336f85329b | checkpoint | 2.2 Excavation Permit
b587665e-b1de-5fc4-912a-581f475312ab | note | Frequency: During excavation
a1f43ae8-6834-5ba9-bc65-af7f4bb18ab6 | note | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing.
6f6ddc66-a4b2-51c2-8450-522b035f980d | note | Plant and equipment shall be appropriate for the task
70b9bc3f-530f-59d6-b894-0bf144d55c31 | note | Excavation operations shall not disturb areas outside the limit of excavation
ac9119e9-39b6-59eb-82a8-f2370a8a8795 | note | Reference Documents: VicRoads 204.06
14909cb8-bdd4-537d-b8d2-5a02b44c2b6f | note | Inspection / Test Method: Visual Inspection
db4a4d42-b7f6-5a9a-af37-8004e7a1406e | note | Record of conformity: This ITP signed
70e78c1e-8759-58c1-a833-119e558fa8cf | note | HP*
15ee65ab-cbb3-576e-82f4-091d3964c0ee | note | Responsibility: Site Engineer
b242d9c7-a848-5b96-a7e3-0a1f15b174f6 | textbox | Date Completed:
3f8a52e6-60ff-4810-8f36-9987911dba7a | checkpoint | 2.5 Disposal of Material
adcee180-78ee-5e29-9462-adee96a26647 | note | Frequency: All times
9054ddb7-454d-53c6-a963-07418897ec9d | note | Acceptance Criteria: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
32af565c-148e-5ab2-8e33-bfe3e7e8167f | note | Reference Documents: ITP sign off
fcdba47d-016f-599b-b35c-769448710600 | note | Inspection / Test Method: Visual Inspection
d0c64da7-5206-56e2-a924-7267590976fc | note | Record of conformity: This ITP signed
18908911-d35a-5d29-895d-ed0edcff0112 | note | WP
cefeada9-ff40-5149-b973-1a7463e1c4c3 | note | Responsibility: Site Engineer/ Site Foreman
de328489-1637-537d-bd87-03a20578111f | textbox | Date Completed:
02358c27-da7c-47ca-b96b-904b71273aa9 | checkpoint | 2.6 Maintaining cleanliness of site
d66bbcc8-c945-517a-a350-fe1a8deb6485 | note | Frequency: All times
b0b240a4-fa01-58ae-8f36-c22a33996b8c | note | Acceptance Criteria: Site and surrounding environment are to be maintained at a good standard of cleanliness
321dad59-05cc-50f0-af8d-222f8cc559fc | note | Reference Documents: ITP sign off
b79ca457-90f7-5e93-b950-e58a6d4ce6a2 | note | Inspection / Test Method: Visual Inspection
d8b0fa3b-3e10-54e9-b0d7-c75d66fd0820 | note | Record of conformity: This ITP signed
d9a6c74e-39fe-5ee1-9d04-539780b3ab07 | note | WP
86d8058b-e246-5a5f-b497-9166e240a280 | note | Responsibility: Site Engineer/ Site Foreman
5b8dbe1b-cf1a-58ac-b8ef-c18c6eb1b276 | textbox | Date Completed:
3929e22d-33d8-4e4c-be22-674e77d16107 | checkpoint | Final Inspection
dc069886-56d3-54ff-be13-8d90ae871375 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
281cf0e6-483f-5655-9f30-938997cf420b | textbox | Print Name:
a76be922-55fe-5912-805c-52c46dd1775c | textbox | Position:
0d9977b7-b489-50cb-a851-4677139cd181 | textbox | Date:
726708b5-a763-40f7-9836-a57a4e9f7234 | checklist | ITP-039 Hot Mix Asphalt (Bridge Deck) |  | ITP-039 Hot Mix Asphalt (Bridge Deck)
b07abd05-f171-4cb5-b55f-7beedefe8feb | section | Preliminary Works
aa46c975-7731-4b0b-a8c2-5157c949625f | checkpoint | 1.1 Check for correct documentation
48341f3b-3cc8-5e0b-84e4-ca57d3056b77 | note | Frequency: Prior to commencing any activity
fca0e112-47f8-56ca-b4ae-40a8d7323935 | note | Acceptance Criteria: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
1aa8aad7-28c0-5bcc-9eab-5f11ee13875c | note | Reference Documents: Drawings and drawing registers
276616a5-2ce5-5e63-8085-a4ffd42056cd | note | Inspection / Test Method: Visual inspection
1b8d67ae-df77-5dc0-b632-f653d6742dff | note | Record of conformity: This ITP signed
c50ae1d5-4b38-52c6-b31b-37f50b6b55d7 | note | HP*
10f8f4e1-6b8a-5f9e-b595-3ba5044ffca0 | note | Responsibility: Site Engineer/ Site Foreman
bf4f8d29-d6d2-5c31-92e2-28e5bff21f7a | textbox | Date Completed:
d66a4ce4-96d0-4a22-94b4-0805ae066906 | checkpoint | 1.2 Implementation of all measures and controls
0b9974ea-1457-51b1-b3ab-490c08aebca9 | note | Frequency: Prior to commencing any activity
e000e82d-7c03-5273-b642-e2d377a8ba16 | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
3f47b534-d3f4-585c-b5bf-d6f919724148 | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
76ef1c95-f1a6-5cb4-a159-de466cbb8334 | note | Inspection / Test Method: Visual Inspection
654c5e5a-d548-54e2-b400-fa306a2c4a05 | note | Record of conformity: This ITP signed
f5229b92-acdd-52f1-87e3-806e29c75113 | note | HP*
ad92710d-b86a-5c17-971c-cbd52ab4ffd2 | note | Responsibility: Site Engineer/ Site Foreman
4752867c-a853-538d-94cf-67ef9fa8ed39 | textbox | Date Completed:
1a95a519-c8cf-48bf-babc-ac1e6d98ac3e | checkpoint | 1.3 Service Identification
e5a9f9bb-e624-5aed-8e82-1681a752db0e | note | Frequency: Prior to start
7a3cc980-7587-5452-8ab2-4dd8b35a299e | note | Acceptance Criteria: Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected
dc813a47-aa53-5122-8ecb-4f69253c9968 | note | Reference Documents: ITP sign off
5b15ab2b-5250-544a-859b-61f3a35c9b64 | note | Inspection / Test Method: Verify
46a6e005-a691-51e8-bdf0-9a470b425437 | note | Record of conformity: This ITP signed
451fd540-4081-5543-8405-424152014312 | note | HP*
e470199d-5e3a-5497-96a2-3aa7a58a5bf2 | note | Responsibility: Site Engineer
325fccbf-b20f-598b-a616-eb4be95fdb6c | textbox | Date Completed:
75c42133-7946-4536-9399-3e37feb90ae1 | section | Construction Works
572d945e-0478-4534-a77b-04a9e9985980 | checkpoint | 2.1 Saw cutting
5c1d2cb1-c665-5535-a0fb-657ffbc08de3 | note | Frequency: Where required
eddc6690-6ce4-53fe-a09d-fc9f06afc54c | note | Acceptance Criteria: Extent and location of cuts to be clearly set out and checked prior to saw cutting
4a482d27-be6c-5651-86ad-e1991b456a31 | note | Reference Documents: ITP sign off
3b07fb46-323a-5c69-a059-41f501cbfad7 | note | Inspection / Test Method: Visual Inspection
7cfed9e9-456b-509c-b4c4-483c46255d2b | note | Record of conformity: This ITP signed
dc155829-f9e9-5300-92e7-c85fec522ae0 | note | WP
87bf6779-4eaf-5183-bbbd-9fa508cec406 | note | Responsibility: Site Engineer
c06191cc-ead6-5064-99a1-01d3a1620365 | textbox | Date Completed:
2cd57333-c05a-4201-8141-75726709a0ca | checkpoint | 2.2 Excavation Permit
71d7f0f5-d0e6-5ef4-81b1-b9ffab6d6be1 | note | Frequency: During excavation
56986b1e-cf0c-56a1-8ea8-ea85c4d24859 | note | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing.
2e69f9a5-13ef-5098-896d-7d97fd390035 | note | Plant and equipment shall be appropriate for the task
98a22de1-6ac2-5a75-a833-bb3d7de2719a | note | Excavation operations shall not disturb areas outside the limit of excavation
bb900bcf-6f81-552a-9162-268f4b39d8db | note | Reference Documents: VicRoads 204.06
e4778fcc-6b55-5cdc-bdd5-e85d634decba | note | Inspection / Test Method: Visual Inspection
b5785b91-aa10-5a4b-9cd4-dc1f80848497 | note | Record of conformity: This ITP signed
d43623af-35dc-52f3-9c3f-a6fcd557cd63 | note | HP*
2ca33a29-0553-5c8d-99c7-e1f23dd613f6 | note | Responsibility: Site Engineer
8f972068-c8b7-51ba-9146-d4c1bb89a070 | textbox | Date Completed:
73e92270-a6d4-4494-a11b-7e6c40ffb14b | checkpoint | 2.5 Disposal of Material
05b05c18-a429-52de-99e5-c7f20ac50a2e | note | Frequency: All times
a649ca04-a1ff-5c39-a703-06f7b926bde8 | note | Acceptance Criteria: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
628a8993-30e5-50bf-b06e-0ff0c6216a1b | note | Reference Documents: ITP sign off
886f02f2-a523-5cc8-a147-77b8fe01f77c | note | Inspection / Test Method: Visual Inspection
37b44d63-b1cd-5696-b1fc-86a3e37a7d9e | note | Record of conformity: This ITP signed
9bb4814b-c4f9-56f9-a781-3aa9807fe485 | note | WP
13572d83-ed01-5094-bf8e-eef13a454e5c | note | Responsibility: Site Engineer/ Site Foreman
50916234-4407-5b43-915b-ef6789411319 | textbox | Date Completed:
df405411-96e7-4aa9-a7d6-a7f136aeadb8 | checkpoint | 2.6 Maintaining cleanliness of site
77283b5a-263d-534d-befd-62e4eee6da80 | note | Frequency: All times
ae7796e5-9441-5237-9c79-a9da321ced70 | note | Acceptance Criteria: Site and surrounding environment are to be maintained at a good standard of cleanliness
01d1b806-bb80-562b-9079-441d8d904762 | note | Reference Documents: ITP sign off
2a1c441e-dd87-532d-a946-d74be27cec17 | note | Inspection / Test Method: Visual Inspection
81b6feb3-32f6-523e-8fff-6d1b41ce8cad | note | Record of conformity: This ITP signed
b4a53489-fe40-584a-995d-5b00e4d26c6c | note | WP
61abdea5-34ed-5493-854c-c7be65afd4c9 | note | Responsibility: Site Engineer/ Site Foreman
04cd60ec-187c-51d4-bb3f-a58d241fbf70 | textbox | Date Completed:
0111a1e3-e699-42b2-8485-273ce0819c96 | checkpoint | Final Inspection
206a84a0-afa7-5399-a7e0-dccfc72536cd | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
db202f4e-2015-55f4-aa7c-5dfed4313a84 | textbox | Print Name:
619a67af-6495-54ff-a163-d214b941d016 | textbox | Position:
d8fb3b83-0bc5-5313-993f-7cb6d4108f72 | textbox | Date:
2132fc48-d1c9-45fc-a023-78a7df11b2f1 | checklist | ITP-040 Profiling |  | ITP-040 Profiling
56c1fc32-9839-41b9-b926-c6b2f3ea6dec | section | Preliminary Works
e5cf3128-c16b-4ff9-bf47-91bee904d4d2 | checkpoint | 1.1 Check for correct documentation
ba0199ea-031d-534e-a312-b092be3b92e6 | note | Frequency: Prior to commencing any activity
bab0d8ab-5d55-5807-b489-8215ed585d26 | note | Acceptance Criteria: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
f38eeedf-5f2a-5685-b851-1e83a36f24b7 | note | Reference Documents: Drawings and drawing registers
acf87801-5873-59e1-bf8d-c794ea9f8291 | note | Inspection / Test Method: Visual inspection
1f9f9307-708f-50d7-8f81-edfca40ecb30 | note | Record of conformity: This ITP signed
e9d2248d-a329-5199-b6db-1a63404a0dce | note | HP*
ea3e57fb-7695-5290-8eae-2b08276d5656 | note | Responsibility: Fulton Hogan Engineer
b89d5245-43eb-5368-8d08-0284de038e52 | textbox | Date Completed:
caacf88e-3f8c-4a74-8e23-217a684bc0f2 | checkpoint | 1.2 Implementation of all measures and controls
9c742692-6457-52bf-ac2e-eabbc4f05d8d | note | Frequency: Prior to commencing any activity
6b956b58-5b4b-51f8-b2bc-5bc088513f91 | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
a2e62e5c-217c-507b-81ea-d55d8d6acecf | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
451f3165-a4d0-5f9a-964c-0047e530296e | note | Inspection / Test Method: Visual Inspection
3e6a88ec-6f25-5f29-985d-483d68a1d90d | note | Record of conformity: This ITP signed
9a3ed651-e26c-5a59-80bd-259f982e600c | note | HP*
abedd0a2-e5af-5860-9e92-0d7f2141e3f3 | note | Responsibility: Fulton Hogan Engineer
33d836e8-2d7a-5c85-8454-2ed550b6a7ac | textbox | Date Completed:
3cacfda1-d571-4ba9-bfa3-ee9ca98d3e7a | section | Construction Works
6ebf2cd9-3cb4-4635-9304-7e820615b60c | checkpoint | 2.1 Profiling Works
61ef5f4c-4dc9-5000-8def-fc929f035678 | note | Frequency: Each lot
a9eb40c0-ffd9-5381-9917-8ed050de77dd | note | Acceptance Criteria: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
ee617313-207b-5751-be48-7a8335ac0c35 | note | Reference Documents: 402.02
994abff2-20a7-5523-ab77-c81185236c0c | note | Inspection / Test Method: Visual Inspection
90afd4bd-2520-592a-81a6-3d7ce15c0da6 | note | Record of conformity: This ITP signed
dc6ce8f0-24ba-5761-949e-8c5d20f239b2 | note | WP
4bb910cc-7df8-5c9d-964c-07512125d3be | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
7450c73e-d40c-5010-856d-82965275cb99 | textbox | Date Completed:
9ba81121-1db0-41e1-8c06-09137dc002ae | checkpoint | 3.2 Depth check
172e906c-9247-5c6e-b914-1a0c1f68fa82 | note | Frequency: Each lot
9dc8fe1b-dbc5-53af-917c-3234cce4c0fd | note | Acceptance Criteria: Ensure average depth of pavement removed is in accordance with relevant methodologies. Ensure a maximum of 50mm to be removed per pass. After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straight edge placed on the planed surface in any direction.
830a630d-b51f-5e04-8769-34f14fbee987 | note | Reference Documents: 402.02
f0edab6a-9886-5ca8-a772-6f65b68f3feb | note | Inspection / Test Method: Visual Inspection
d5a530ba-fc6d-5a71-8173-5a8606d22724 | note | Record of conformity: This ITP signed
7deeb2e9-518b-5811-8219-5edf788a0435 | note | WP
2e56cccf-fff3-5a30-b3d5-5d596d528343 | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
314b98fc-ebd2-54c7-b764-256b6e0bdfa7 | textbox | Date Completed:
9ed7c69f-385c-4042-b3b9-12bf9529840b | checkpoint | 3.3 Temporary ramping (longitudinal)
1bbf3ae5-a65c-5756-91c7-3a26b2e5775d | note | Frequency: Longitudinal edges
9a45c92c-a115-523e-af0b-1540a1b26072 | note | Acceptance Criteria: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
96b22a61-167a-5ac3-9b4f-a8bade90d828 | note | Reference Documents: 402.05
62f475c4-a369-5a7b-8d32-d0613460ab60 | note | Inspection / Test Method: Verify
b8c86cda-08ef-5087-9473-b5a5b7ae7b30 | note | Record of conformity: This ITP signed
75dbc8e1-fb0f-5452-bf5e-2e9577de9f25 | note | WP
fdf6b888-da8f-5cc3-8936-73b181a4df23 | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
de36b0dd-26c2-5f7b-a17c-bccdd8eafd0b | textbox | Date Completed:
8a3e3e8a-2741-4140-80aa-070f2570ef50 | checkpoint | 3.4 Temporary ramping (transverse)
44950853-420f-5bc3-8d6b-984804a3a355 | note | Frequency: Transverse Edges
757b4f2b-d2ac-591e-9549-631ca05b766a | note | Acceptance Criteria: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
aa420bc3-a079-5152-b1dd-fddfbe2c1d73 | note | Reference Documents: 402.05
7b2bfe8a-7987-53ce-8f46-a052320fd58d | note | Inspection / Test Method: Verify
e8d8b995-c98c-5b61-ae2c-e7d73c69b9d4 | note | Record of conformity: This ITP signed
c7a66c63-d576-5c9a-bcaa-0c898ee3a07c | note | WP
71ea865b-bd3d-5b8f-97b7-2366b7034c1c | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
456c5891-00be-572f-8a37-e6ec38e86635 | textbox | Date Completed:
4173cf38-60f1-401c-8e64-60a9b1551f60 | checkpoint | Final Inspection
36e21462-7e1a-5dfa-a847-8d86d669516a | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
bbefe9f1-cbfc-563a-a948-f62f5c53c5a6 | textbox | Print Name:
e472d5ae-968e-5007-9d5b-dd323280892c | textbox | Position:
ffb5b101-23e1-5c12-8623-7184a7c8ccf7 | textbox | Date:
9fbb1b7f-8925-49f8-870c-98eedc8016b1 | checklist | ITP-041 Platform Bonding |  | ITP-041 Platform Bonding
b8e8d2ce-de75-4e40-bd3d-d420dcf147e9 | section | Preliminary Works
61788916-03d5-4f21-8e58-08d8a74068c9 | checkpoint | 1.1 Check for correct documentation
f802d907-91bc-55bf-bfc0-94b63e1d957b | note | Frequency: Prior to commencing any activity
be3ecff3-a904-5867-ad7d-6b2d09d8d701 | note | Acceptance Criteria: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
3a172332-57fb-5251-b3e9-6f92b0c88904 | note | Reference Documents: Drawings and drawing registers
ea178f0f-d37c-5154-94c6-e8c5ec0c391d | note | Inspection / Test Method: Visual inspection
00ab8732-712f-5f18-8e01-63f44e6b2efb | note | Record of conformity: This ITP signed off
97444983-9820-5488-8264-55a1474a64d5 | note | HP*
656a40e6-e205-56f5-9472-2a67d3387712 | note | Responsibility: Fulton Hogan Engineer
a5f2a89c-b281-5282-aa45-a110037e9cf6 | textbox | Date Completed:
7b8e6f0a-62f0-4097-9f6e-d14192cdc0be | checkpoint | 1.2 Implementation of all measures and controls
f5d6d5ad-a6ea-5274-a4f9-07c4ed3f7b1b | note | Frequency: Prior to commencing any activity
32ec0eec-28fa-5312-96f8-9e8e6298f802 | note | Acceptance Criteria: •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
8c8f6b7b-1be1-57ec-bef6-5d22e44feffc | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
b17db05f-ccb0-5b0b-a62d-7d7604833d24 | note | Inspection / Test Method: Visual Inspection
35f751c1-c413-561a-b826-27a5b517c749 | note | Record of conformity: This ITP signed off
3610675f-f24f-53d8-b443-8a1e5fd28893 | note | HP*
1e72a79b-27c0-5d21-9219-e0f27397b869 | note | Responsibility: Fulton Hogan Engineer
096feaa8-de49-575e-88b9-4602dda22ac4 | textbox | Date Completed:
dce47c3a-4e9c-435b-a311-1da13bf6fdbd | checkpoint | 1.3 Check Materials
4b5f8c50-193c-5685-a50c-62372a41ebc2 | note | Frequency: Prior to commencing any activity
bb91a91b-d7ba-5674-b9bf-a38b30931501 | note | Acceptance Criteria: •Confirm bonding cable material & size is correct and in accordance with design drawings. •Confirm correct mould type and size is used for required CAD weld connections.
0507d602-2e62-54d5-92b4-4002071da42d | note | Reference Documents: Construction Drawings
4188c103-da98-5b4a-b74f-d1d52cffe5bb | note | Inspection / Test Method: Verify
a3f438b6-5ed9-5e55-aecf-d2a7f9463851 | note | Record of conformity: This ITP signed off
4b97c518-04ed-5148-aad0-405d2f648e41 | note | HP*
74825ac8-e9e4-5678-88b2-bf27b636e1bc | note | Responsibility: Fulton Hogan Engineer
9793f195-93ef-5f42-9a00-2afeae2865da | textbox | Date Completed:
8a4bef5d-4059-4f1f-b250-cd0686f776d3 | checkpoint | 1.4 Bond setout
ccf51437-fcb9-5265-9717-7a29ecd2b245 | note | Frequency: Prior to commencing any activity
ba7ba52d-86fe-50a6-9bf7-82887232f009 | note | Acceptance Criteria: •Confirm bonding loop and connections are positioned in accordance with the most current and updated set of construction drawings. Ensure that all locations are reviewed by a Fulton Hogan engineer.
45ed368a-9705-562f-97d2-d18fe97fe7a3 | note | Reference Documents: Construction Drawings
4b26fa79-be02-5d5c-abe7-45a2b420b754 | note | Inspection / Test Method: Verify
24aed5f2-3349-523f-850b-f5c720be2f50 | note | Record of conformity: This ITP signed off
98f76639-9fd4-5792-9059-5d4983086d4b | note | HP*
866e3a21-ae8e-5cfb-9439-e8daf3313e15 | note | Responsibility: Fulton Hogan Engineer
695f5fbe-7779-50da-a5a3-55b7149766d4 | textbox | Date Completed:
b8ed05da-0caf-42a1-9841-15ab742210b9 | section | Construction Works
6d0d146a-e61c-49da-8604-fcc974bb1955 | checkpoint | 2.1 Laying of Bonding Loop
28125a63-3573-5dd4-b931-8a184524184a | note | Frequency: Prior to Asphalt
dad8bb00-5a2a-5e40-9b8b-e70960a87d2e | note | Acceptance Criteria: Lay bonding loop in accordance with construction drawings such that it connects to the electric cabinet correctly.
08c67b1b-7d18-54bd-a360-bcfea169febf | note | Reference Documents: Construction Drawings
ec02584b-40f4-5bc7-92ca-2da2b4da058d | note | Inspection / Test Method: Visual inspection
e660086a-5ada-5065-ad16-7a631e258576 | note | Record of conformity: This ITP signed off
4aa7b0c9-bd49-5ac9-b225-3fef7a0e6031 | note | IP
62f88866-cf30-56b3-bde6-4c4a69a94a9d | note | Responsibility: Fulton Hogan Engineer
fbf8b387-eb63-5705-89bb-2718101dca95 | textbox | Date Completed:
c7649757-ae1f-4d4f-8f8b-6f6f7c51fec0 | checkpoint | 2.2 Laying of Bonding Furniture Connections
ef26bb15-5206-5a78-85b4-a9ab7746b4cb | note | Frequency: Each Lot
0f53e8cd-c082-5444-b2e4-8d61e17d04fa | note | Acceptance Criteria: Ensure furniture connections align correctly with structure and are positioned in accordance with the design drawings.
75d887ea-4e21-546f-b4f8-a194925f23f6 | textbox | No. of Furniture Connections:
55c001c4-5286-5438-8193-1d1ab4ba4888 | textbox | Furniture Connection Cable Size:
292353e3-3557-577c-bb0d-65caa51bac4e | note | Reference Documents: Construction Drawings
ee4a1765-8e84-525d-874f-c0cd11759106 | note | Inspection / Test Method: Visual inspection
91a33180-9828-5d25-a1cd-c971a4256e1e | note | Record of conformity: This ITP signed off
cc2a616c-6fb7-5d61-9f48-bc22c851bc65 | note | IP
da65c28f-3b66-5821-a18a-f0bf08e96c67 | note | Responsibility: Fulton Hogan Engineer
2d9eee9f-33dc-56c4-b452-0dc7abfcf430 | textbox | Date Completed:
f1374855-24f6-490b-8889-db83d9670c5b | checkpoint | 2.3 CADWELD Furniture Connections to Bonding Loop
5f586e4b-e236-5831-830b-f08f2f454936 | note | Frequency: Each Lot
c9db4738-cbc9-5b6a-883d-d77e9acb9d27 | note | Acceptance Criteria: Ensure correct mould is used when CAD welding furniture connections to bonding loop.
cf564043-150c-5861-8eab-27add1a2dfc1 | textbox | CAD Weld Mould Dimensions:
b0d835be-4265-572d-98bd-9f1815aaa0a9 | note | Reference Documents: Eritech CADWELD Exothermic Welding Manual
7d6fed0b-084d-5ca7-9b6d-2a570d456e40 | note | Inspection / Test Method: Visual inspection
9805b041-bf87-50cd-8c31-9bfdd029d10b | note | Record of conformity: This ITP signed off
03994efe-422d-5503-b520-181a682f9068 | note | IP
580aa4d1-81ba-5b8b-b6ca-814630edea3b | note | Responsibility: Fulton Hogan Engineer
801fffbb-d973-5e90-9c99-281de407a302 | textbox | Date Completed:
4b0a14e2-1ffb-4dac-a22e-97d9c71c9ac7 | section | Construction Works
fa28fad7-5779-47c8-ab88-bf312e0e822b | checkpoint | 2.3 Weld Review
9e47e7ed-ec72-53dc-a1f0-5c14e498db3d | note | Frequency: Each Lot
233e625d-dbda-5b59-822c-75bc665ea207 | note | Acceptance Criteria: Ensure each weld is inspected and that a quality connection has been made. All welds shall be inspected by a Fulton Hogan engineer.
25b95965-b208-5ced-8db7-ffbf995c7ee0 | note | Reference Documents: Eritech CADWELD Exothermic Welding Manual
556b5e2e-9a45-5e30-834f-9920a206a3b6 | note | Inspection / Test Method: Visual inspection
d6315c68-a3ef-54e7-8985-c19b87cf678e | note | Record of conformity: This ITP signed off
193de907-8147-564a-be6b-c897bfd13318 | note | TP
203e53c1-a1b3-5fb8-8f5f-3b48469ed8fc | note | Responsibility: Fulton Hogan Engineer
842b803e-cdff-5dac-93d0-c65b0402a078 | textbox | Date Completed:
86a1162b-645b-4b5b-85cd-7fe18268e201 | checklist | Order Acceptance Certificate |  | Order Acceptance Certificate
4ef209e3-3893-41a9-8f60-cc2121d60068 | section | Details
3342290c-066f-4546-8c7c-1982fbfd81fc | checkpoint | Order Acceptance Certificate - Details:
6c0892f3-5f96-5778-bf97-5ec6fe79b727 | textbox | Subcontractor (full name of Subcontractor, ABN, Subcontractor's ACN and ABN)
e5d61f58-590d-5007-a614-0648fe000b3b | textbox | Order No.:
4b82dc68-458d-52dc-9342-a414d0d04ef3 | textbox | Delivery Site:
e30b08be-3b24-5949-a7c6-77a41ae4df3f | textbox | Date on which materials delivered:
14ef5238-0471-5e79-9fd1-9cf9833f2b37 | textbox | Delivery vehicle (registration number):
df3ccb11-a254-5bea-b3af-d1fa06369db2 | textbox | Subcontractor's delivery personnel (full name)
d9f29ba9-dcd3-4cb7-bf0b-026160cbd39e | checkpoint | The Subcontractor has checked all Materials included in this delivery and is satisfied that all of the Materials comply with the Subcontract.
5a8602df-b1fb-48ab-8b74-98a2e1d4f57a | section | Packaging Inspection
9ce9f86a-b4ba-464b-82f0-7b7521a471c1 | checkpoint | Fault ID:
f822ffc2-18e5-5286-887f-e7e35b49d5c4 | note | OK = Meets all criteria
6c741c4d-9607-5dad-9e4e-551b317101ac | note | QI = Quantity incorrect
906e98aa-a77c-531c-a03d-37f8262c236f | note | IN = Item incomplete
a57e94f4-6b32-5c7a-95e9-4ac6535fa877 | note | MI = Make or type incorrect
54d0265b-c5f1-5339-beb6-e18c778d5a8e | note | TD = Damaged in transit
76faa4af-1cd3-54b1-97c6-f083982381ec | note | NI = Not properly Identified
12ede4bc-59a2-46b0-93dd-087534ae121e | checkpoint | 1)
6c375c9c-9e53-5c7e-be73-ac1ee87f6f76 | textbox | Item ID:
750f5227-7113-5145-892c-35c5c391c084 | textbox | Item description:
86ae7d75-37e8-55a0-ae25-f5947b99bc4b | textbox | Units ordered:
555a3246-4d3e-514d-ba40-b4f3c12159c6 | textbox | Units delivered:
1d722e7f-e0d8-5f2e-841b-5411610ab1c5 | textbox | Special Storage/ Handling Requirements?
e1bd88a1-2713-577e-bb44-789f7c7fc916 | note | The following is for completion by Fulton Hogan
01863d3d-4f85-589e-8b56-beb032d92e91 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
76883c1e-b147-5058-a614-16260b71da5c | textbox | QA Docs Delivered?
b4300d3a-cddd-5aee-8f22-f9632183e031 | textbox | Defective?
a2d12bf8-d7ef-5dd3-94bc-98535ac1b0af | textbox | Number Accepted / Number Rejected?
40775021-0e8a-548d-a8b6-55f549bc9b37 | button | Fault ID: | IN, MI, NI, QI, TD,OK
b05e77b9-1dd8-4ecf-bde6-e87998b389b3 | checkpoint | 2)
82c9ec2a-ef9c-586e-81ad-a4b43ab1a5ad | textbox | Item ID:
cc9459c6-39f6-5e7d-8f04-4d2536d2158e | textbox | Item description:
1ca0190e-959d-54c1-85af-8270d985fe19 | textbox | Units ordered:
59ad9cbd-d2f1-58d3-a970-21f3f58a41c2 | textbox | Units delivered:
f56612fc-b82c-54c2-ac98-37065b1788a6 | textbox | Special Storage/ Handling Requirements?
492fecce-97a9-5fed-ba4f-2180b3a40425 | note | The following is for completion by Fulton Hogan
c231cb15-fc92-562d-8b59-c174c5b8bceb | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
36b65373-23ee-587e-aedc-327a385b8a6d | textbox | QA Docs Delivered?
f5a14f29-9338-5754-b206-43a72a2aea9c | textbox | Defective?
61c4b2eb-885f-5b26-badf-f1599b9a568e | textbox | Number Accepted / Number Rejected?
e9b626ba-cb61-5bf8-a042-3f0feb8f6a16 | button | Fault ID: | IN, MI, NI, QI, TD,OK
b44f9e28-4b90-4376-9956-ce8cab68cfaf | checkpoint | 3)
67db6a5b-a71e-5afd-80c3-d2fc38355e1b | textbox | Item ID:
72ddd06a-0c87-52a0-a1aa-eb9494c1af17 | textbox | Item description:
13bd5fe1-adc8-5a89-b04f-009e27ab8986 | textbox | Units ordered:
36efb32b-ca97-5c11-82ea-db43cf18906c | textbox | Units delivered:
b1f7d999-f1a5-522e-badb-d399b4ce14af | textbox | Special Storage/ Handling Requirements?
abd0b010-ee6a-5266-a332-bbf53fb10643 | note | The following is for completion by Fulton Hogan
ac1678dc-aad8-5324-8024-9b2f18581e14 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
c673aa30-9957-5bc4-976c-b8912cca0415 | textbox | QA Docs Delivered?
63e2b521-2849-5d2d-b958-7c02415e56d3 | textbox | Defective?
2f816e09-ae89-5d22-b769-6d488efcf931 | textbox | Number Accepted / Number Rejected?
12637f6c-0e23-5ec9-b793-313ca92619fc | button | Fault ID: | IN, MI, NI, QI, TD,OK
c582b61b-74c2-4fdf-94bb-93b4a247d9a9 | checkpoint | 4)
98b50f6e-4034-5cb7-a33b-197bc1906757 | textbox | Item ID:
68b3ec0c-0244-5f19-8e0e-69dab85cbd54 | textbox | Item description:
7746b79b-3741-5934-8656-03fb5985732f | textbox | Units ordered:
9d6e0b48-a323-5d86-8f1c-8fb9c9eb4cc0 | textbox | Units delivered:
b52b834f-3d23-586f-8341-9d85fd64d0d7 | textbox | Special Storage/ Handling Requirements?
178659dd-6192-5095-a605-376947e33738 | note | The following is for completion by Fulton Hogan
8f071c48-bf76-5195-a34e-98758b87df9f | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
4bfc1653-d8c8-5bfc-b20d-af3ce56cd15c | textbox | QA Docs Delivered?
bf78ef1d-670a-5f12-b0f1-f136d48026b8 | textbox | Defective?
67f07fab-220c-520b-a3b7-bd8734ab4806 | textbox | Number Accepted / Number Rejected?
4cf7e81b-b91f-52d8-9b35-3404e309f960 | button | Fault ID: | IN, MI, NI, QI, TD,OK
200b9714-171e-42f4-85bd-85e3bf68b123 | checkpoint | 5)
13dcab48-dd2c-5b4b-aca7-401a9aa608e0 | textbox | Item ID:
24b5d445-acce-5b11-b978-2a58ff7224d8 | textbox | Item description:
ad847799-dd59-59bc-8161-4757b4ee498b | textbox | Units ordered:
58bdc04a-3a20-50bb-a9be-da0cdb3c7fc9 | textbox | Units delivered:
e78b21d2-6f02-5bc2-b6f0-39a291854dcb | textbox | Special Storage/ Handling Requirements?
3c3b9e57-8c9b-55d6-9ff9-784580067197 | note | The following is for completion by Fulton Hogan
15023bfb-1cef-56a2-a9c4-900d9a82919a | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
8c7c235b-2f46-53b6-b513-338892c1ca6a | textbox | QA Docs Delivered?
5540dafb-730d-551c-9850-d6456c3d32cb | textbox | Defective?
18a78ff4-c5ad-5a2d-be12-eae78f2efb5b | textbox | Number Accepted / Number Rejected?
2c8ae2ef-f266-58af-bb41-7aea41b578ed | button | Fault ID: | IN, MI, NI, QI, TD,OK
19e37700-1977-49ff-beff-f10f2708a62b | checkpoint | 6)
fb532f77-a745-5f60-8490-c457bb908c48 | textbox | Item ID:
1f2636f8-2315-5f79-a4ed-9656a9483976 | textbox | Item description:
1dc8e2b1-6e6e-5b5b-9b09-4abc628cbf07 | textbox | Units ordered:
b4783af4-efb2-5bf3-bce6-092f042b6d88 | textbox | Units delivered:
0f948242-5620-51fb-90bc-5d343182f348 | textbox | Special Storage/ Handling Requirements?
82cfd152-c05e-5d46-8a65-a2f6baa71946 | note | The following is for completion by Fulton Hogan
7dd600ce-5f34-5a96-860e-dd3d4c8dd889 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
3f9c898d-0832-519e-be78-5c208fa8372d | textbox | QA Docs Delivered?
975a057c-f4cb-5301-85a7-9f9857b302b3 | textbox | Defective?
d15a037d-9dfd-5452-84db-e192e3423c69 | textbox | Number Accepted / Number Rejected?
fe948a97-8f12-522a-a057-8f5d50c76231 | button | Fault ID: | IN, MI, NI, QI, TD,OK
e84c1e02-7bf3-447b-8588-5df1b56a758b | checkpoint | 7)
23903d21-f2d8-5623-a8b8-8c3db9b1c166 | textbox | Item ID:
af1499d5-74f8-51d9-b191-a5ed06eb0360 | textbox | Item description:
591f6877-2021-546f-b5b9-a1ff18a38220 | textbox | Units ordered:
95542f4b-f7cb-5b85-b6e7-6fc5f99a5800 | textbox | Units delivered:
ddb3344f-0321-53b1-954c-af87e2dcb0b0 | textbox | Special Storage/ Handling Requirements?
96f0ca66-5b5c-5fe1-95e6-0ffb254c6c71 | note | The following is for completion by Fulton Hogan
57326580-12c5-5ebe-a9bf-fc8391f492d7 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
424dbf13-35f7-5b8f-8467-db8fd0c102f6 | textbox | QA Docs Delivered?
964a1cde-ed0c-54d6-abef-2aec2f24f82c | textbox | Defective?
c7b0f908-0c69-5bb8-b2d7-481ad7c24a8d | textbox | Number Accepted / Number Rejected?
e103f7a7-8820-5eec-9d23-8c8bd432f933 | button | Fault ID: | IN, MI, NI, QI, TD,OK
90cfc1d3-b485-4460-a915-e861add05649 | checkpoint | 8)
39c1b7a4-262a-5287-9803-ce8f0a46c9c8 | textbox | Item ID:
33932c10-fbfe-59a2-8d13-a829d853e1ab | textbox | Item description:
4ef2706f-2ecb-5b1b-b1bf-83dff6f5b55c | textbox | Units ordered:
d10dbc2e-979e-5a67-8fba-10a26bb82291 | textbox | Units delivered:
57f30ec8-ea54-580c-ac6f-328a0e4b5f4d | textbox | Special Storage/ Handling Requirements?
325ccb94-5c52-53aa-8b40-d9178193058e | note | The following is for completion by Fulton Hogan
09ab655c-d6aa-5f82-85da-265a127117d2 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
3bb81d76-5bf0-5928-89c0-46430a4d669f | textbox | QA Docs Delivered?
1eaa74fd-0ab0-5397-945a-b7dee8da4c45 | textbox | Defective?
7f28d089-c79e-5039-a139-cab67a39942c | textbox | Number Accepted / Number Rejected?
49d02e70-a92b-5181-be91-6fa60ee9cb76 | button | Fault ID: | IN, MI, NI, QI, TD,OK
ab3e5555-8473-484c-858a-5d86ce8876dd | checkpoint | 9)
f4d76f6c-3c05-5eab-8674-83646840f5e7 | textbox | Item ID:
71206260-df54-5597-aa1a-f086c95e730c | textbox | Item description:
9efc754b-ac31-5534-8128-80b21c92b74d | textbox | Units ordered:
8472663c-8a0d-595c-975c-cae8adac1f48 | textbox | Units delivered:
7208a713-f0a6-590c-bf54-d86c28de6d00 | textbox | Special Storage/ Handling Requirements?
4f76d39a-b686-5c39-a741-9e2aa193f6d7 | note | The following is for completion by Fulton Hogan
29ddc4a3-a28d-504b-a32b-16d6d3621e6f | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
4e71244d-eeaa-5670-addd-090ed8adf4d7 | textbox | QA Docs Delivered?
933a45ba-ee24-53fa-926f-c95751fc4b1d | textbox | Defective?
1c59616f-08fd-576b-978c-e3f7236ca535 | textbox | Number Accepted / Number Rejected?
786f18e9-c986-5b99-949d-f473cfde2a3a | button | Fault ID: | IN, MI, NI, QI, TD,OK
bea6c953-41c6-4ba9-b969-c10381ed1e4a | checkpoint | 10)
c86130f2-c01e-5523-8f34-f7dbf831ed39 | textbox | Item ID:
31dbd390-3232-57dc-9720-bcc8bf5027b0 | textbox | Item description:
a4202bd9-9e35-57d9-a34a-450d0edc9157 | textbox | Units ordered:
9b96f0d1-3843-5b1f-853f-00e153fac8e0 | textbox | Units delivered:
689c10a5-6391-5f89-93b0-1fb78c4ae061 | textbox | Special Storage/ Handling Requirements?
53875c03-adc2-5b27-a4dc-4979c1a67d99 | note | The following is for completion by Fulton Hogan
7455b6d9-c148-5710-b1aa-27045fadef84 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
0f51235b-1ef5-58b8-83d6-e3a3cf21e966 | textbox | QA Docs Delivered?
9ed54654-cee8-57bc-84aa-741c8a721bb0 | textbox | Defective?
a69874f7-9ad7-5883-b187-e0f4d95b7de7 | textbox | Number Accepted / Number Rejected?
d6f649f3-f146-5183-a697-cf5af12229fa | button | Fault ID: | IN, MI, NI, QI, TD,OK
6bd6780b-d187-4050-bb6c-b661d301f322 | section | Sign Off
096aaf0f-ffdb-45ef-ad61-dae455e7fb2c | checkpoint | Accepted by Fulton Hogan
5ea94bc5-10f7-4df9-9b76-81a77408e8c3 | signoff | Sign Off
8b7a0ef3-00c0-421c-b56e-716247b6731d | checklist | SYS - ITP-001 Subgrade Preparation |  | ITP-001 Subgrade Preparation
16058403-2ce4-4719-ad0a-0754277b9449 | section | Preliminary Works
3c7db296-6a9d-4649-88b4-64bc07662ecc | checkpoint | 1.1-Check for correct documentation
8b09b15c-9cd8-5385-ae31-441689e1170c | note | Frequency-Prior to commencing any activity
060b35c3-03aa-59fd-b80d-ee99a6a17b4c | note | Acceptance Criteria-Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
c46a312b-ef40-5d63-addb-b85400ae0b70 | note | Reference Documents-Drawings and drawing registers
5d26ba9c-6e3d-5143-8037-0404a7e36200 | note | Inspection / Test Method-Visual inspection
e5c3345a-acc3-5d5f-a0ab-4279914134a0 | note | Record of conformity-This ITP signed off
1362e222-bd6c-5443-9d29-e77f02bad231 | note | Witness Point
05972c95-55db-5383-b84e-220db44fe3ff | note | Responsibility-Fulton Hogan
3dc3a71e-d02d-5c94-8daf-e6e402d658e7 | textbox | Date
b56b18e0-87ad-49d5-a4dd-51190c7857c5 | checkpoint | 1.2-Implementation of all measures and controls
67055d48-3814-5d75-bec1-da7dec804b41 | note | Frequency-Prior to commencing any activity
f0e81f4b-96f9-54e8-9a88-af2376637fff | note | Acceptance Criteria-All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
5ac5d878-06fe-53a4-b43c-0e2000668ec8 | note | Reference Documents-PSP, EMP, TMP, JSEA, SWMS, WP
31c3b86d-2b0a-5631-aa7a-2c7f940b7cde | note | Inspection / Test Method-Visual Inspection
e580b9da-3cfd-5200-bb0c-9537941ad698 | note | Record of conformity-This ITP signed off
d610c8c2-812d-53c0-9e92-824b6621d09e | note | Witness Point
e8b73fd2-472f-5432-9dfb-3c8a7ba6ea97 | note | Responsibility-Fulton Hogan
5ba9c1d0-acc1-5ebf-8572-2528b480878e | textbox | Date
c328b780-da2c-44c8-9f3b-7bd2e00ecf1a | checkpoint | 1.3-Selection and approval of Disposal Site
2b7309dd-69f9-58d0-b7bd-22d28584dfd4 | note | Frequency-Prior to commencing any activity
4f754262-5600-592b-bcbc-6726085d3479 | note | Acceptance Criteria-Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accordance with Yarra Trams site classification report. It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
115248fe-90f7-5258-8197-09483410360d | note | Reference Documents-VRIOGS 005.2 Pt 1 cl6.7; Site Classification Report
31d47c8d-bbf5-591a-9371-b54dabfab79d | note | Inspection / Test Method-Verify
a681bbdd-3134-5ff5-9400-2315d9c74e71 | note | Record of conformity-This ITP signed off
205cdba1-329d-5296-8b18-2bc42f8afd72 | note | Witness Point
7efb8c67-0620-5d5d-ad15-3d7e515a1173 | note | Responsibility-Fulton Hogan
9cdeece0-fec2-5e9a-ba49-88c97e9be12e | textbox | Date
3dfca813-fc34-4bd7-a528-41e2da3f8678 | section | Construction Works
0c18b218-f0e7-4ba1-94a8-100fe1497d49 | checkpoint | 2.1-Excavation
17876d3d-8d22-5c1f-bba8-dde8d332b61b | note | Frequency-Each lot
31ff139d-7ee5-5cec-abed-44f5b007b2f8 | note | Acceptance Criteria-Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of works
e1d27f7b-d893-5a4d-a52b-fb4937f6ee5d | note | Reference Documents-Subgrade Preparation Work Procedure
2276f6e1-0e84-5b08-b4cb-d531b3c5e6cb | note | Inspection / Test Method-Verify
ffdacd2d-6e40-52cb-924c-32ea55a69686 | note | Record of conformity-This ITP Signed Off
ff5edb42-a25c-548a-bda6-1f5cdb8bbd97 | note | Inspection Point
d6cf3d63-c979-5bde-8bda-f00297329e48 | note | Responsibility-Fulton Hogan
e39c3501-9d4b-5ba1-aca2-fb9539a2e1ec | textbox | Date
a471d883-928e-48fa-ba9d-61e9a38de09f | checkpoint | 2.2-Reinstatement of bonds
4ffa383e-b1c3-5613-a113-c138e1241944 | note | Frequency-
7d237a4c-007e-5f68-b6ef-2a24b0a5c948 | note | Acceptance Criteria-Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables. All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
425968e3-bf80-530e-94f4-a5ec31456e33 | note | Reference Documents-VRIOGS 005.2 Pt 2 cl2.2.1
9fb76579-3919-576a-91af-cebbb52c9625 | note | Inspection / Test Method-Verify
4c736f6f-19d5-57c6-aa4a-f30216fcf140 | note | Record of conformity-This ITP Signed Off
e6395275-ccce-5520-b43a-a050974e8183 | note | Inspection Point
ef702f5b-0c2e-57e7-9edb-d41f3172e483 | note | Responsibility-Fulton Hogan
7277a5d4-8be5-5e76-a8ee-e517af373de7 | textbox | Date
c11117b9-566f-4806-9049-c1db6535f024 | checkpoint | 2.3-Inspection of Subgrade Material
eb5e6c24-e6d1-5b9d-a2b9-b128413e0d10 | note | Frequency-Each lot
e48ba6f2-d212-5479-bf5d-8e16f7ae13b2 | note | Acceptance Criteria-Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
ad61357e-e5a8-584c-8099-5ed7e1e57743 | note | Reference Documents-VRIOGS 005.2 Pt 2 cl2.2.2
8fa698b1-5ef2-51dc-a280-6c701bd7f4f8 | note | Inspection / Test Method-Verify
61377c5e-c5df-5c47-88f2-830b766419a1 | note | Record of conformity-This ITP Signed Off
a6a883bc-63e4-57a6-995e-144469cdd0de | note | Inspection Point
ba798bfe-3997-54d3-9e82-eec59579d534 | note | Responsibility-Fulton Hogan Engineer
5dfe0ebe-a4ea-5b2a-87e3-64cf77878fd3 | textbox | Date
79e476b5-f8f2-4908-9305-3ada7098e5f4 | checkpoint | 2.4-Width and Level conformity
ea52f79c-ae4c-5311-af34-16aaa5d6d281 | note | Frequency-Each Lot
173f373d-ffbe-5245-90d5-93ac9bcd740f | note | Acceptance Criteria-The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings. No point in the general surface shall vary more than 12mm from a 3m straight edge. Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
d9ff47f8-17df-5c0f-9cec-9bf9944b385d | note | Reference Documents-VRIOGS 005.2 Pt 2 cl2.1.4
05cf6320-4fbf-5029-8282-2c2000a33b17 | note | Inspection / Test Method-Survey Report
4416a446-0804-5feb-be90-01d7315b297e | note | Record of conformity-Survey Record
c4fc4284-69d9-554d-8cae-f524d461c5f9 | note | Inspection Point
c89ae18e-b164-56fb-a86a-87257ddbaffb | note | Responsibility-Surveyor/ Fulton Hogan Engineer
c885d955-2c37-5da7-877d-eb6514ee9a29 | textbox | Date
ae9fca7f-2c40-4bf0-83bf-e7d84ff6bc86 | checkpoint | Final Inspection
ecb5076b-1e3e-53ad-82db-7dc2b3333ada | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
d9d6f120-dea4-5b38-802b-dc82f9681659 | textbox | Print Name:
ebd6e6d4-6de6-55d7-96f0-b4e424d6cc80 | textbox | Position:
d0fc67d2-2454-57cc-af41-ac98479cbb1f | textbox | Date:
8a63385e-62ae-4599-adf8-d7d21a5db388 | checklist | SYS - ITP-002 Feeder Conduits and pits |  | ITP-002 Feeder Conduits and pits
34f5c3f4-fc9d-4375-9ede-4915d5d4556c | section | Preliminary Works
64fa93b8-c295-47d6-a06c-51a42d07a1ff | checkpoint | 1.1-Check for correct documentation
56a513f0-2452-57d0-85d8-497e16872926 | note | Frequency-Prior to commencing any activity
9e43aaf3-8e32-593a-bc3d-90c2759f3cd5 | note | Acceptance Criteria-Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
3320502d-3a45-521c-b13c-192a37c30567 | note | Reference Documents-Drawings and drawing registers
f525df3f-e303-5eef-a6cb-c833abc3dcee | note | Inspection / Test Method-Visual inspection
b1dec722-a05b-5719-94a7-9e586dbff4df | note | Record of conformity-This ITP signed off
8eacf366-9e5a-57bc-add1-27354df923c3 | note | Witness Point
6ed0110e-8f04-5f00-b408-f63ecb342d4d | note | Responsibility-Fulton Hogan
16779e53-308c-5add-89ed-d687e09c0fd7 | textbox | Date
ee1c8e74-a47e-47c0-855b-35d55223b391 | checkpoint | 1.2-Implementation of all measures and controls
94d25fc2-0d71-580b-a773-3254311cf2c2 | note | Frequency-Prior to commencing any activity
4c59f33c-2b7a-51d9-924f-95752f252f5a | note | Acceptance Criteria-Prior to commencing any activity
44128cd4-278b-5f64-b8c6-0d76be3a320d | note | Reference Documents-All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
b3687183-b8f3-545f-a119-3d2d5e638561 | note | Inspection / Test Method-PSP, EMP, TMP, JSEA, SWMS, WP
b8dcdb89-36e5-50a9-be37-f2075d797dc0 | note | Record of conformity-Visual Inspection
79e07127-37d9-5d33-a00e-aa579761e182 | note | HP*
18853dd3-4b7b-5a2d-8496-c27106afd047 | note | Responsibility-Fulton Hogan Engineer
321976a4-797b-5c6d-b687-02db11d6eb57 | textbox | Date
377f686b-b465-4334-b47a-b692a59bc368 | checkpoint | 1.3-Materials
da810f60-c61c-51bf-8a4b-b629dd93479b | note | Frequency-Per Batch
f19d9488-328e-5a11-a141-d78ddafefa74 | note | Acceptance Criteria-Per Batch
65f94ddc-9976-50c7-bc7f-037ff77eb275 | note | Reference Documents-• Electrical supply conduit to be Orange
ce26f636-b4cf-5122-a3fd-5cf84ce6a442 | note | • Heavy Duty 100mm diameter UPVC
d934ed48-7962-587b-b4b8-75744b56228f | note | •Modula Stakka pits to be used for feeder pit, entry for conduits to be cut with hole saw
5d7bccb9-0ed6-5d2e-8098-a6dd6d760d38 | note | •All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
1fbd9d68-4715-5d94-895b-46fbc16b1d47 | note | Inspection / Test Method-CE-021-ST-0044 cl 4.4 AS 2053
755bffc5-fd32-5aa6-9ddc-2f01ec211027 | note | Record of conformity-Verify
71af8cf6-acea-5b45-9209-8104d3b68418 | note | HP*
139be20c-d343-5a1a-bfb9-94c06aab6870 | note | Responsibility-Fulton Hogan Engineer
727f6d87-a538-52c1-a096-00ecc2e5a131 | textbox | Date
9954f842-e1c1-484b-a0a8-cf7edaef1581 | section | Construction Works
d61ccc67-3602-4ebb-9302-abdac7531164 | checkpoint | 2.1-Survey set-out
c0f530fb-302e-5e47-9ef4-0451991b94ea | note | Frequency-As required
9c8e83d4-8860-58cc-9a9f-c7c4d9c96659 | note | Acceptance Criteria-As required
c9904804-b26c-5839-a0d1-9ab2e98c65ef | note | Reference Documents-
e17529cd-44f1-511e-8d38-e68db0250ac2 | note | • Work is set out in accordance with drawings.
a0e93efb-ec4e-56b9-bf96-0b3a5ddc6bd4 | note | • Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
6c320071-9218-51b1-80ba-9287b2f4b03c | note | Inspection / Test Method-Work procedure
b04dedc9-c172-5604-b890-db29a1f14486 | note | Record of conformity-Verify
c553a9b8-8ead-5f12-8c63-1ce5105c75d0 | note | HP*
39d88a80-07ec-5651-ad55-658c3437c9fc | note | Responsibility-Fulton Hogan Engineer
d4d7163d-635b-5243-aafc-f822d2ffa986 | textbox | Date
351f503c-be5c-4051-a9ba-2a66bec88eb8 | checkpoint | 2.2-Excavation and Trenching
ccd00799-7c0e-5ae9-90c3-afe01eed033b | note | Frequency-Prior to Installation
de832be8-cfc1-5069-a8bf-b3b651749cd1 | note | Acceptance Criteria-Prior to Installation
a8b74194-8026-5672-b02d-fc5f98c9f5df | note | Reference Documents-• Minimum cover for underground conduits shall be 600mm
2c61554c-64f9-52cb-9a49-7af48d972aa8 | note | • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
7b0b001b-363a-52d2-9768-48e089574995 | note | • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
e66700ba-c1fc-5623-973f-1739235e1e4f | note | Inspection / Test Method-CE-021-ST-0044 -cl 4.2.5 & 4.2.8
6dace30a-e7e0-5f4c-99c0-fac9bba66773 | note | Record of conformity-Verify
b3254df8-d4e4-530b-a1f4-9160d43d96d2 | note | WP
09154a68-e737-557e-bce0-acb18add5620 | note | Responsibility-Fulton Hogan Engineer
7059f86b-f77c-5b71-a0f5-b01a2639a5a3 | textbox | Date
2129c3a2-2dfe-48c1-8044-956ebe3b7fe7 | checkpoint | 2.3-Installation of Conduits and pits
92e5f934-b25b-54c3-b83c-876d2d36d6e4 | note | Frequency-Each Lot
79544e14-f008-5361-b93c-94422edc46ac | note | Acceptance Criteria-Each Lot
e41863b8-5d12-57bf-94ee-969f5475405e | note | Reference Documents-• Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
27066955-1bd2-59c4-bf33-9e62bfba45fa | note | Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand
3869658a-9d90-56bb-83c1-9d4e4dac00c8 | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
3f1b6482-eec5-5194-a739-75cf633f1fc7 | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
bf2d4a2a-4bbf-5d6c-a7d9-bf428cbe968e | note | • Conduits shall not be subject to construction loadings
13071e0a-8932-5b6b-a1ef-bf7b595fcf08 | note | • Pits shall be constructed as to allow for class D rated covers
d6554fa0-60f1-5c3a-9cf1-a9a25ce8953a | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor, a 50mm gap between conduits shall be maintained as they enter pit face.
7fee57ff-010a-5a98-aefc-c5f95aa027dd | note | • Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mm beyond the pit face and shall be fitted with a spigot end and capped to prevent contamination to internal surface.
786d8241-26a6-52c3-aafa-453d1c21da71 | note | Inspection / Test Method-CE-021-ST-0044 cl 4.4
c1ee0843-fcac-52e9-92d9-ef9512a6a908 | note | Record of conformity-Visual inspection
ea2da56c-0e70-5465-ab07-56d6cbfce580 | note | WP
daf792bb-b751-55fe-94f9-c43b874744a3 | note | Responsibility-Fulton Hogan Engineer
3929c981-bef3-59cd-9ffc-9d1aac1ffbce | textbox | Date
e33760c0-a4a3-4e5e-965f-a76381fd4762 | checkpoint | 2.4-Inspection of conduit installation
a76cbbaf-8e97-570a-b3ff-357bb47d7fd6 | note | Frequency-Each Lot
ab4c4604-3929-5cfe-a671-76070c676d1f | note | Acceptance Criteria-Each Lot
2711a932-e6f2-5762-bf07-a3734210a9b8 | note | Reference Documents-Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
147418dd-06be-5407-b3cd-37f88832d20a | note | Inspection / Test Method-Work procedure
a608859d-15e2-5873-ac59-2bd031937c61 | note | Record of conformity-Visual Inspection
f0c6135e-b9f4-5205-bf31-6fc5f322fad0 | note | *HP
be658752-952e-559d-abbc-b2e3e915f792 | note | Responsibility-Fulton Hogan Engineer/YT
18dd6f7c-4f7c-5505-a2a9-7f3c8ab87cc7 | textbox | Date
7c6dd2c4-c1a3-4c3f-81de-b4b7bd7cd77f | checkpoint | 2.5-Back Fill of Trenches
dd89540d-8db8-5405-89d9-df50c56d58a8 | note | Frequency-Each Lot
3b74bb0e-531e-5d59-af0c-2fead9085bac | note | Acceptance Criteria-Each Lot
896dea62-7c63-5b9a-ab50-a2ab90642d7a | note | Reference Documents-• Backfilling (Only to be used for road crossing trenches) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
0173c72b-e724-5147-95c2-4860b3c66722 | note | Inspection / Test Method-CE-021-ST-0044 cl 4.2.5
a1fcef91-73ec-5b1d-868e-5ac81e1e46dd | note | Record of conformity-Verify
51281e29-fd16-5a1f-892f-266b17d3ee09 | note | WP
b73822b3-13f5-5d1f-98ea-16b51ff59d0d | note | Responsibility-Fulton Hogan Engineer
af629f43-5459-517e-9a86-733010ec3d3f | textbox | Date
69c586cf-fb57-4b55-8311-6cb693e5d49f | checkpoint | 2.6-Installation of Draw Cords
fe2ac184-a50e-5aca-845a-731b359084f9 | note | Frequency-Each Lot
f9d12b82-d045-53fc-92dd-92d120e5bd6b | note | Acceptance Criteria-Each Lot
b8f629cc-fd26-5c2c-9308-d8690d8361b0 | note | Reference Documents-Draw wire shall be provided for each conduit, with extra 3m length at each pit.
97fd1aff-25ea-53c0-80ea-0e5983639c74 | note | Inspection / Test Method-CE-021-ST-0044 cl 4.4.6.2
e91e3e15-fd8b-587c-8be3-3d8d9bdeb932 | note | Record of conformity-Verify
19c12951-4551-5210-a9ca-c4bd33e3fab7 | note | WP
d809a349-22d7-5366-9e08-768ba60ab80f | note | Responsibility-Fulton Hogan Engineer
825f9495-f330-59a9-9650-477c7ca9b59b | textbox | Date
5526ed8e-f779-4e15-b9d9-447d85ae075b | checkpoint | 2.7-Compaction
b208bce7-e6ef-5ebd-a76e-d608f6b43477 | note | Frequency-Each Lot
6026b1a5-2329-5d4a-99cf-bf0d30d0d299 | note | Acceptance Criteria-Each Lot
a75997de-7dff-527c-bc0e-1e8de7e3e84f | note | Reference Documents-• Bedding and backfill material to be compacted using mechanical plant. During compaction optimum moisture content of bedding and select fill is within 85% to 115%
c414a1a7-c6f8-5d89-8774-00d9bea82c62 | note | Inspection / Test Method-CE-021-ST-0044 cl 4.2.8
cc3efe05-2376-5aa0-ac1b-499c91b93b85 | note | Record of conformity-Verification
9c97f5db-8d35-5adf-b3d6-526e218bae23 | note | IP
b5380b64-b81a-5284-b4bd-c0c38e03bf78 | note | Responsibility-Fulton Hogan Engineer
d832df07-73aa-5a65-9e84-fd58add72ebe | textbox | Date
0b824423-88d8-48f9-826b-4f8a0cd81364 | checkpoint | 2.8-Feeder Pits & Pit Lids
9bf666a7-170b-5d96-846d-e1a5864a5760 | note | Frequency-Each Lot
aaecadf6-f81e-5835-af9a-2969abdac962 | note | Acceptance Criteria-Each Lot
f11fddbd-b992-5ff8-84cd-3b8e73c2dd32 | note | Reference Documents-• Feeder Pits constructed and installed as per drawings
9e7f80ed-d34e-5947-9c24-923c71ce24a4 | note | • All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar
39b2b093-d967-56b0-8256-06b93b505fed | note | • Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
d2e78eac-5a8b-5b1f-a9c6-956ec8b5533d | note | • Gatic pit lids shall be filled with structural grade concrete.
f20b3bbb-5f07-5138-be29-7f73ce7a478d | note | Inspection / Test Method- CE-021-ST-0044 cl 4.4.7
4b4d4bac-6e43-5d80-8115-ef40087435b6 | note | Record of conformity-Verify
c7a13896-986c-5110-b0c1-4d9f77a3d3a2 | note | WP
9b73676a-d291-5771-adec-b34703ad1adf | note | Responsibility-Fulton Hogan Engineer
94ebcf44-ceb0-55eb-8a16-62aea35cbdb5 | textbox | Date
3fde15b5-5061-40a8-ad89-0d8b829e29c7 | checkpoint | Final Inspection
6585198f-cd89-52b1-a2c2-f71f86dd3207 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
7ed1bebc-a674-595a-830e-5be2f7649b19 | textbox | Print Name:
d59db192-a8cb-514f-b9f4-819b6396f30a | textbox | Position:
80ab27d4-1f0a-55f3-92c8-68d3cec29a02 | textbox | Date:
f20a5c5d-3e46-4289-9fca-3df0574d3a54 | checklist | SYS - ITP-003 - Electrical and Communication Conduit |  | ITP-003 - Electrical and Communication Conduit
8aebde8c-ac76-444c-a81d-f6db0505ec04 | section | Preliminary Works
84cfaf08-6a42-4c5a-a407-3029c730527a | checkpoint | 1.1 Check for correct documentation
98ab550f-7911-5619-8da2-ab361dccbb9a | note | FREQUENCY: Prior to commencing any activity
229f38c1-964b-5e62-b41a-7d418cfedbd9 | note | ACCEPTANCE CRITERIA: Employees and sub contractors shall be issued with the most current and complete construction drawings
9176bcbd-896b-5a66-a1e5-8323b17356d0 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
73c25791-f2ac-537a-93b1-d67cc4dcd666 | note | INSPECTION/TEST METHOD: Visual inspection
59803e94-b078-5878-9047-21e724a30ed8 | note | RECORD OF CONFORMITY: This ITP signed off
99589d15-4b67-5bb4-accb-b8b151ebaed1 | note | HP*
aff1ad0a-9deb-5ba0-b8d0-d713d37939a8 | note | RESPONSIBILITY: Fulton Hogan Engineer
1ae08a6b-4593-52b4-8368-9a68c5cab449 | textbox | Date Completed:
0034ec93-7813-4965-8783-47ff9c78a49a | checkpoint | 1.2 Implementation of all measures and controls
89570147-502e-5cc0-8673-e85df0b862ee | note | FREQUENCY: Prior to commencing any activity
1b3e97f1-38e8-563c-96ed-1085c7b0551b | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
44195c5b-2078-5ff6-a899-a7c676c316e0 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
d00ceb90-961c-519c-9ddb-e335be9c3ffb | note | INSPECTION/TEST METHOD: Visual Inspection
f3c58bc7-7c4d-5072-a673-6cb1d41b4a9e | note | RECORD OF CONFORMITY: This ITP signed off
a14f2922-9694-5416-89b7-7b36e46bb48b | note | HP*
4d030a0e-dd8d-5dc7-b859-61146892c214 | note | RESPONSIBILITY: Fulton Hogan Engineer
067f6caa-4c26-50c3-9418-f5c4b2462b89 | textbox | Date Completed:
c3710429-6462-477f-942d-f7d692c31f4a | checkpoint | 1.3 Materials
d2e1f81c-9928-5257-b999-937f97e04151 | note | FREQUENCY: Per Batch
916acb14-8a6c-59f9-b469-d865e59787ff | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be Orange and rigid HD UPVC of sizes as required. • Communications conduit to be White and rigid UPVC of either 32 or 50mm size or larger as required.
f51b338e-7fa5-5f28-9c9d-25269d438704 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.4.1 AS 2053
26e3a3ad-f795-5030-a65b-e2c396812fd4 | note | INSPECTION/TEST METHOD: Verify
d0ff4fa6-0226-52f3-a756-1ce8de04ec9d | note | RECORD OF CONFORMITY: This ITP signed
f62b104d-84a8-54ef-80e9-3a7107ce5a7f | note | HP*
5c485128-2a3e-5100-a8e2-ddfa0d15ed07 | note | RESPONSIBILITY: Fulton Hogan Engineer
f0e8e66c-b68e-5f6c-9dfa-500dcfc833d6 | textbox | Date Completed:
5ab4ece0-f0b3-4b08-9a2e-b35d69a4f931 | section | Construction Works
ad11a597-a84b-4d75-a9e2-d20b80aadf94 | checkpoint | 2.1 Survey set-out
3f5a063a-7699-5d9a-a3c6-914bee8dafa3 | note | FREQUENCY: As required
1d5a5bc6-9ebd-56e1-a087-b8a3275b8886 | note | ACCEPTANCE CRITERIA: • Work is set out in accordance with drawings.
ce6b949f-42d5-589c-ada7-6d86be64016c | note | REFERENCE DOCUMENTS: Work procedure
38362e79-1f74-598e-9d10-60089544dcf4 | note | INSPECTION/TEST METHOD: Verify
dc6cc9d6-bd52-568a-a9bc-625e58a51938 | note | RECORD OF CONFORMITY: This ITP signed
345fa09f-4559-5710-84ee-4deda2141436 | note | HP*
9b554394-3a2d-5b2f-88b9-080f7db4bd57 | note | RESPONSIBILITY: Fulton Hogan Engineer
de452874-b0b3-5bfb-8984-f90ea54d7e8f | textbox | Date Completed:
f6cdff7b-a93f-4b71-b56d-02a2bf92b287 | checkpoint | 2.2 Excavation and Trenching
59bef4e0-4fe2-5d57-80a6-69f97bbcef32 | note | FREQUENCY: Prior to Installation
8807e647-a73a-594d-bab8-408f15949d62 | note | ACCEPTANCE CRITERIA: • Minimum cover for underground conduits shall be 600mm • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
6c556731-d726-5c16-b419-66367c20fefb | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.2.5 & 4.2.8
9166784e-643c-52bd-9388-9194cf4ed8f5 | note | INSPECTION/TEST METHOD: Verify
c0d6d1c6-b5f0-52b5-9c08-3406bab779c2 | note | RECORD OF CONFORMITY: This ITP signed
1f15c858-ba04-5648-985c-72e1d7a2b8a7 | note | WP
11ecc767-4447-5a01-a18e-8c65fa632d83 | note | RESPONSIBILITY: Fulton Hogan Engineer
da39b442-bf41-5abc-bcb2-d673551cb9ec | textbox | Date Completed:
92660964-ff2d-451d-852d-b6f22f6150c5 | checkpoint | 2.3 Installation of Conduits and pits
a0f02460-244f-54b1-9539-6cd3c0e58826 | note | FREQUENCY: Each Lot
5ccdca95-8be3-5035-9dab-9b9acac5b28d | note | ACCEPTANCE CRITERIA: • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide. • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining. • Conduits shall not be subject to construction loadings • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor
7f4da481-b0d3-53ab-85fb-40ec7795d79c | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.4
0805909d-e119-50da-8a9a-d404c73e7bc9 | note | INSPECTION/TEST METHOD: Visual inspection
2884cd6c-3e42-5fa9-a5db-802765f848a7 | note | RECORD OF CONFORMITY: This ITP signed
26a4a01d-dbec-5e4c-8120-0f2e73f760af | note | WP
f6786efb-440c-54e6-b58c-fcf1ecc8e0b2 | note | RESPONSIBILITY: Fulton Hogan Engineer
26d226e6-d50e-5eca-b68b-209d8a0c437f | textbox | Date Completed:
3e167660-21ed-4188-9307-e2bfade779d5 | checkpoint | 2.4 Inspection of conduit installation
d07e78bb-776c-507b-8b63-ec15e175fdc8 | note | FREQUENCY: Each Lot
6063d5c6-9033-52ba-820e-32292be28ea3 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
40dbd1bb-9cf6-5a99-a111-86a138411875 | note | REFERENCE DOCUMENTS: Work procedure
d56501a7-837d-5723-a332-b08b0911c2b1 | note | INSPECTION/TEST METHOD: Visual Inspection
890bcf54-249e-5b42-a9a8-a975e733f700 | note | RECORD OF CONFORMITY: This ITP Signed
d55ac5b6-ae5d-5960-bf03-687fb653beaf | note | *HP
65986718-30b2-5eef-bdc9-45723fb083bc | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
5b09a047-029f-5efe-b8cc-a3bf7b48d5f6 | textbox | Date Completed:
3b8d3e81-4344-47c2-a694-dd5738e62691 | checkpoint | 2.5 Back Fill of Trenches
7a2b89c6-0fd8-5c93-a02a-ae34bb81ac75 | note | FREQUENCY: Each Lot
fdce616a-201b-52ca-a308-7cc4d0549d16 | note | ACCEPTANCE CRITERIA: • Backfilling (for trenching or road crossings) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction using handheld mechanical plant
8772ae26-3fa5-59f4-8f0a-85b6851a1641 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.2.5
59134692-8a9e-5982-8f22-366205e49594 | note | INSPECTION/TEST METHOD: Verify
8034faaa-c04a-5ffe-995a-45c44d7ad1ea | note | RECORD OF CONFORMITY: This ITP signed
4993e861-6a45-5970-8540-e7424491c2dd | note | IP
1fe28065-1edc-5632-8ce8-a8f330794707 | note | RESPONSIBILITY: Fulton Hogan Engineer
a63bf00e-54ee-5bf0-a56e-e6900c55c273 | textbox | Date Completed:
361bc415-b049-43a9-8379-3f80bc9908f6 | checkpoint | 2.6 Installation of Draw Cords
2ae2c1c9-b6ee-5f25-b4d4-bfe807e8db24 | note | FREQUENCY: Each Lot
5ddd08ff-e8e4-5571-9684-fde917a4fc79 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit.
3fd88271-2098-5f7a-af0f-75b03d5bcc52 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.4.6.2
e6b01935-c00e-5347-a3aa-9f98d88ab23a | note | INSPECTION/TEST METHOD: Verify
0672eef7-20df-50b4-b501-15d165695966 | note | RECORD OF CONFORMITY: This ITP signed
a63dcd1d-606d-5e75-bc65-5fce98140c7e | note | IP
ee31b246-d4c6-55cf-a95c-fd07b2e7718f | note | RESPONSIBILITY: Fulton Hogan Engineer
e226c20d-5a08-53c5-a5e8-3239a0168a76 | textbox | Date Completed:
c8f28be5-bf0a-4d74-84cc-3a91c337e442 | checkpoint | 2.7 Compaction
b93656b3-b674-52fd-a499-128794438f41 | note | FREQUENCY: Each Lot
fa9aeb90-2c69-5458-87f3-10bbbaf7536a | note | ACCEPTANCE CRITERIA: During compaction optimum moisture content of bedding and select fill is within 85% to 115%
56dec4be-6765-5c1f-98f3-a916ad9bd5e8 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.2.8
cd7a00b7-4c82-5eda-a9d4-6d06a867e8ab | note | INSPECTION/TEST METHOD: Verification
011ce431-2d27-56cf-a44f-7a619871c33f | note | RECORD OF CONFORMITY: This ITP signed
068a95c0-6ea3-586c-826f-e72eecc533de | note | HP*
df2efc41-7778-5b52-a2ae-8f6145b6d75d | note | RESPONSIBILITY: Fulton Hogan Engineer
09777c84-10bd-5ed3-b272-911eb14ec6cf | textbox | Date Completed:
f6853edf-91be-41f5-a45c-a2b1f0b01e96 | checkpoint | Final Inspection
f8482866-d7da-576c-a8e4-05b7eb1df86f | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
81d3dfbe-63fa-5706-aee6-6fe7e7512235 | textbox | Print Name:
d8474888-da0f-55c7-9ac5-fb54b521ca2e | textbox | Position:
0a5b8c53-9a15-5f65-8e50-54790a27b468 | textbox | Date:
87db8175-2874-4e8e-8955-61de169f8a75 | checklist | SYS - ITP-004a - Class 2 Basecourse Placement |  | ITP-004a - Class 2 Basecourse Placement
c06b3e36-5d96-44ca-b262-41f238b164fd | section | Preliminary Works
5156c0e8-8836-44b6-9c3c-e89e4f9b49a6 | checkpoint | 1.1 Check for correct documentation
2546f30e-a38e-5c6c-8244-5b10f508c75a | note | FREQUENCY: Prior to commencing any activity
1e2d3c30-6425-52c3-91c7-da49d5d2c667 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub contractors are using the most current and complete set of construction drawings.
513d25bc-da78-5b67-8f96-72cc66a39fa7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
695f457a-299f-5f47-8f32-bfacb24ebbc8 | note | INSPECTION/TEST METHOD: Visual inspection
b0db0d88-78b0-5628-9859-bdf813d8eb5e | note | RECORD OF CONFORMITY: This ITP signed
0944264d-21c8-561b-bea1-f980fe53434b | note | HP*
4c5b1fcd-12fb-5c06-8a1c-9a0d04523e04 | note | RESPONSIBILITY: FH Engineer
f8c95498-4833-5449-9e35-2c7e8417f2a0 | textbox | Date Completed:
9af4855a-bc84-415b-8ebb-573f77c4585c | checkpoint | 1.2 Implementation of all measures and controls
846dc604-9f3d-5a9a-a3c8-d848af7dd54e | note | FREQUENCY: Prior to commencing any activity
6b1b87d2-456f-5e9d-9834-9325bf8ed09c | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
dba9f380-993c-5e0f-bf3b-49567f22f424 | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
d0b7c097-70bd-533e-b200-db6a04328a1d | note | INSPECTION/TEST METHOD: Verify
0d1a3181-a12a-56e0-b71e-ba66c564ac81 | note | RECORD OF CONFORMITY: This ITP signed
31e2a2cb-4b1b-5537-9d0b-bde2410379f2 | note | HP*
695a6d92-1c46-53a1-a487-821486ffea8d | note | RESPONSIBILITY: FH Engineer
40710167-1590-5b24-9533-35830fefe65e | textbox | Date Completed:
a2139380-a472-4d89-a20c-14bdaf0ef0be | checkpoint | 1.3 Material Compliance
228acc48-1bb8-52ed-bd2f-17804838c24b | note | FREQUENCY: Prior to commencing any activity
9b640adc-50f4-5c5d-8d7b-9e7da5c98db7 | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
9a1f2bc7-6797-5d1f-b9bd-31a2d0385266 | note | REFERENCE DOCUMENTS: Cl 2.4.2, VRIOGS 005.2 - Part 2
4c606a1c-1b1b-5c0f-9cf5-a43f9dfae069 | note | INSPECTION/TEST METHOD: Document Review
09d24e75-12c0-5606-aa35-ca83fa08f726 | note | RECORD OF CONFORMITY: Test Reports from supplier
82ac466d-a7d4-5366-b0ab-4bb1f3ea1dc5 | note | HP*
f3bfc46c-89c1-581f-8e0f-32994a795303 | note | RESPONSIBILITY: FH Engineer
d6eef60d-1876-5acd-b221-ff6a764e5fff | textbox | Date Completed:
49704dc7-ff20-44e5-9e93-b84ea126d280 | section | Construction Works
74871dae-ccb4-4066-ba18-586b0e6ad677 | checkpoint | 2.1 Spreading material
275bff30-e562-51e5-bab5-2feed8522126 | note | FREQUENCY: Each lot
6293c5b9-b6f3-5a0a-9400-6aa332943bae | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
16573957-293d-5442-b0fd-0b205a2e837b | note | REFERENCE DOCUMENTS: Cl 2.5.2, VRIOGS 005.2 - Part 2
d9e0c83f-6b7e-5016-87e1-c9d6de8b2df1 | note | INSPECTION/TEST METHOD: Visual Inspection
4de4200c-01f2-58f6-a902-5a0d16a9fddc | note | RECORD OF CONFORMITY: This ITP signed off
243c5b28-f693-56b4-b630-f0569bcbc081 | note | IP
744c52ee-4ca0-5886-8fe7-c6c9f943c74d | note | RESPONSIBILITY: FH Engineer
bc170449-e027-5ffc-8cd7-737b3ea7af6e | textbox | Date Completed:
9a0a1771-63b3-48cb-a650-9a83a4441c92 | checkpoint | 2.2 Compaction
00f6e450-b4b9-5330-bd34-f6d77617976e | note | FREQUENCY: Each lot
71de91ac-c834-5887-a320-599b07cc4b93 | note | ACCEPTANCE CRITERIA: Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content. Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test. Compaction testing shall be carried out once per days production and shall comprise of three samples
99f42c30-c1ea-5bb4-be75-0bec7a409b38 | note | REFERENCE DOCUMENTS: Cl 2.5.3 & Cl 2.5.6, VRIOGS 005.2 - Part 2
e9fb9fbd-c77d-5c99-a605-21ae186a39d6 | note | INSPECTION/TEST METHOD: Visual Inspection
0ca05f60-8975-53c8-be5c-9cab97c80f92 | note | RECORD OF CONFORMITY: Test Results
64d01bba-a6b0-5cf9-bd81-ab0507a37f80 | note | TP
4effdd9b-0a1b-5601-a674-e3e804462107 | note | RESPONSIBILITY: FH Engineer
ab43cecd-d296-5000-a92d-d8abfaa09fff | textbox | Date Completed:
1327ac16-b008-4645-bcda-c80bd27e7627 | checkpoint | 2.3 Level Checking and Conformance
48d5dabc-8c24-5b21-b2b5-0acb68b696b3 | note | ACCEPTANCE CRITERIA: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
0c56bf6c-9b03-59ba-bb3e-9286f811344e | note | REFERENCE DOCUMENTS: Cl 2.5.3, VRIOGS 005.2 - Part 2
0cf09c06-455e-5884-ba98-df1e4f7299ee | note | INSPECTION/TEST METHOD: Verify
06d1eeab-e8cc-501b-b6c4-93c8a4c6423c | note | RECORD OF CONFORMITY: This ITP signed off
c5491737-1792-5c1a-ac20-6b9fd02f9b03 | note | IP
bedc9f99-a069-54f8-9567-5402f2108eb0 | note | RESPONSIBILITY: FH Engineer
e1122ddf-ba15-5772-a0ae-4a1951380c13 | textbox | Date Completed:
00a29c18-ba43-4932-b0b4-f9776ff5dbc4 | checkpoint | 2.4 Finished surface
f851dbdd-f644-55e0-9df8-bdbeadd921c8 | note | FREQUENCY: Each lot
cd437428-101e-5fcf-9a25-845e041ef78e | note | ACCEPTANCE CRITERIA: Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits. Heights of basecourse shall be checked and recorded at a minimum of 10 chainages (inbound and outbound) at random per 400m
4eb584c7-944d-5dfb-9fd4-ba1653cbb4b3 | note | REFERENCE DOCUMENTS: •Cl 304.06(b, d, i) •STD 9010C •Contract drawings
a575f04d-363c-5493-8931-557c6f003138 | note | INSPECTION/TEST METHOD: Visual inspection
e9acd724-76fd-51bf-8407-e2183243ce6e | note | RECORD OF CONFORMITY: This ITP signed off
c7ec39c0-095e-5804-b5b6-9efaf5f40edd | note | SCP
4bfc9b49-7050-5248-89ed-bced46bf3345 | note | RESPONSIBILITY: Surveyor/ FH Engineer
f75100ac-4d68-5d42-972a-3823f0bd483f | textbox | Date Completed:
c21f848f-46d8-4a98-91cd-39acb9e353ae | checkpoint | Final Inspection
3004e9f4-bff4-508c-afcc-5e5f2aa41bca | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a98ab253-bf87-5b5f-8f8b-712beb2b22ba | textbox | Print Name:
7a134fe7-5ece-546f-9165-c99d39739dda | textbox | Position:
dd796b73-3d4e-53f7-a002-7b69c54edef9 | textbox | Date:
8c622c41-88d0-47b8-a529-8aab464ad8bb | checklist | SYS - ITP-004b - Cement Treated Crush Rock Sub Base |  | ITP-004b - Cement Treated Crush Rock Sub Base
59399e95-28e4-4ac1-9865-7ca2dd640479 | section | Preliminary Works
d218e425-73d9-4fde-a5f7-68b794a70e06 | checkpoint | 1.1 Check for correct documentation
42a31c19-e082-5cc3-99f9-794cb160162a | note | FREQUENCY: Prior to commencing any activity
80e70f33-47e3-574e-af09-87fda5f0db0a | note | ACCEPTANCE CRITERIA: •Ensure that all employees and subcontractors are using the most current and complete design drawings
ce1316fc-fc51-5a8d-bfba-168b0c945502 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
69f19929-cc1a-5ff2-bf14-4212d1698de8 | note | INSPECTION/TEST METHOD: Visual inspection
de6e74ab-931f-54f6-bee3-566e0951e6b0 | note | RECORD OF CONFORMITY: This ITP signed
4773fe9a-b97c-53ff-8242-b92c24606f9b | note | HP*
0f026c61-c90f-5aab-a67e-71f71bff93ee | note | RESPONSIBILITY: Fulton Hogan Engineer
854c884b-d8ef-5eb1-9347-5fe3bf2acef6 | textbox | Date Completed:
a885d607-368e-4244-9a97-22fb6071cee3 | checkpoint | 1.2 Implementation of all measures and controls
e450d20f-f3fd-5d8b-9b04-6e6b4191a18c | note | FREQUENCY: Prior to commencing any activity
709b2380-db04-59f7-b038-0f925a99eb35 | note | ACCEPTANCE CRITERIA: •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
0f0e774b-62f0-5dbd-908b-565a619d4e53 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
6a402c1d-8c07-51ba-a3fd-d9a11c3973e7 | note | INSPECTION/TEST METHOD: Visual Inspection
c2d616a3-7d65-585c-939e-169807dce8db | note | RECORD OF CONFORMITY: This ITP signed
3293f223-afdd-5db6-bf6c-feaa73192cfb | note | HP*
20e9a45a-5e3f-57d7-97d4-7de3a6fa2d01 | note | RESPONSIBILITY: Fulton Hogan Engineer
7ff4b694-294e-5043-a5ca-d2f1fb897270 | textbox | Date Completed:
c5842fe3-ce37-484c-a1d9-9a2f7c924d51 | checkpoint | 1.3 Confirm CTCR is Appropriate Mix
288d2876-bca2-52db-8916-1187f07126ed | note | FREQUENCY: Prior to commencing any activity
c0b5d56e-fbae-5084-808e-2fe26a624146 | note | ACCEPTANCE CRITERIA: •Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product. •CTCR shall be tested in accordance with 815.141 by supplier
69382497-3a59-5692-84e9-5c74d4c2b92e | note | REFERENCE DOCUMENTS: Design Mix
d70b78e1-d23b-5428-9e32-d0d1db036da9 | note | INSPECTION/TEST METHOD: Inspection
1fc1e5b7-e834-553b-9ade-4e2ae2aeb5ee | note | RECORD OF CONFORMITY: This ITP signed
52701c20-e3bd-5ef3-a814-cdf349e554ab | note | HP*
e96b3735-e390-58d9-b817-1c13ec2f84b7 | note | RESPONSIBILITY: Fulton Hogan Engineer
06aaa02a-3c87-5d8f-bb11-e4da75f70ca2 | textbox | Date Completed:
b5927a60-9ddf-4929-8103-f83887bb5b31 | section | Construction Works
3ff176cd-4942-4566-83e1-0454104b6fa4 | checkpoint | 2.1 Sub Base
9db22e56-25ef-5549-be61-7c6955b31a9a | note | FREQUENCY: Each Lot
8596a213-1a93-535c-bf84-2ef85e9e0ec1 | note | ACCEPTANCE CRITERIA: •Sub grade has been inspected, no visible ponding, springing presence, or visible deformation. •Proof Roll shall be conducted by plant compliant of 173.03
5c5a4f25-7c2a-5b58-b889-f74862510104 | note | REFERENCE DOCUMENTS: VicRoads 173.03
efdada3e-8a5e-597d-80a8-e07504e039a6 | note | INSPECTION/TEST METHOD: Inspection / Test Method
5d974303-b681-5dcf-b19b-bba32c036648 | note | RECORD OF CONFORMITY: This ITP signed
c46718f8-7c7a-5a62-a2a1-72f21a347c05 | note | HP
8fb9d8dc-91c6-5918-81b4-1ef65177b8b3 | note | RESPONSIBILITY: Fulton Hogan Engineer
8ff882d0-8398-5453-872d-7d83c3e5fcbb | textbox | Date Completed:
ddcce788-5059-4a01-b340-0cf5ec3dee8d | signoff | REQUEST HOLD POINT SIGN OFF
566be968-47c6-4d85-87a4-eb1769c8e0e7 | checkpoint | 2.2 Moisture Content
3ca635bb-2773-5780-b457-13d14bf3b871 | note | FREQUENCY: Each Lot
93733038-f3b7-5bc8-a5c3-3fea33dfe61a | note | ACCEPTANCE CRITERIA: •Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
dbb1ccdd-2c36-58e5-b6b6-efa2aefa5f66 | note | REFERENCE DOCUMENTS: Vicroads 306.05
50f63c6c-5aec-5a7a-a06e-00d62a2c0d46 | note | INSPECTION/TEST METHOD: Inspection / Test Method
af9cf455-eb37-57f0-9b3c-e3385967900b | note | RECORD OF CONFORMITY: Record of conformity
12faa561-c697-5a89-b071-af0c30907aea | note | IP
1d950cf4-cdec-5593-a596-66a20e6a3235 | note | RESPONSIBILITY: Fulton Hogan Engineer
56bbfd9f-e7ae-5fb1-9486-4d43a52923cc | textbox | Date Completed:
65b721ac-a747-4a7e-bd42-ddeebaa565a5 | checkpoint | 2.3 Jointing
d8181fc4-0a24-5bf6-b5db-9e2d500eba24 | note | FREQUENCY: Each Lot
f47c193c-495d-554e-ac88-7abacfcf6916 | note | ACCEPTANCE CRITERIA: •Material shall be spread to minimise number of joins; •transverse joints in adjoining paver runs shall be offset by >2m; •Longitudinal joints shall be offset from each layer >150mm ; •Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
0dad1def-6eff-53fc-beeb-d26fbd6c066f | note | REFERENCE DOCUMENTS: VicRoads 306.08
56983765-607c-5971-8303-2b5668983f34 | note | INSPECTION/TEST METHOD: Visual inspection
00291447-f3cb-5d0f-8103-a13cf307dfdf | note | RECORD OF CONFORMITY: This ITP signed
5277b5f7-f643-52ec-9ee4-fa690e85ab95 | note | HP*
d705d0fd-ffc2-5288-9a6b-fb6ec4907fd3 | note | RESPONSIBILITY: Fulton Hogan Engineer
5199116e-3b2e-5aa9-b48e-81b22f4b3c3f | textbox | Date Completed:
8f2e2557-3d66-46eb-b9e8-7c43aa6cb0f7 | checkpoint | 2.4 Conformity with Drawings
51556033-7776-55a7-b7ee-d74a5dc242b8 | note | FREQUENCY: Each Lot
f0f6d25f-fab2-5e4c-b431-7cc1a7e4857a | note | ACCEPTANCE CRITERIA: •Pavement sub base shall be finished to smooth and uniform surface •Surface of sub grade shall not lie more than 12mm below a 3m straightedge •Subgrade height shall lie within +15 to -25mm •Sub base height shall lie within +10 to -25mm
9972dfa4-a32a-5f41-8590-48d3385d7210 | note | REFERENCE DOCUMENTS: VicRoads 306.03 306.11
98f38a8b-9f27-5d93-8d8c-dd96fca175ee | note | INSPECTION/TEST METHOD: Visual inspection
a4018910-6f15-5c5f-99c0-8b647b66c913 | note | RECORD OF CONFORMITY: This ITP signed
8c6809b0-c86a-57a8-843a-c6d876218c62 | note | WP
b89cb067-be19-57ed-8454-815b52c3ea1c | note | RESPONSIBILITY: Fulton Hogan Engineer
5f1cf0c8-4cd7-50cc-91b7-b087991251e5 | textbox | Date Completed:
ed8457d7-7d46-45eb-b9b9-7cdba3cf950d | checkpoint | 2.5 Curing
9b2331df-43a4-5ba4-a80d-3f58da55a434 | note | FREQUENCY: Each lot
dee38083-c397-58f7-90ac-0f4fd9970875 | note | ACCEPTANCE CRITERIA: •The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane. •As per VicRoads, 4000m2 shall be maximum lot size •No trafficking before 24hrs unless approved by superintendent
224275ae-5edb-50f8-978b-f00333b41bdc | note | REFERENCE DOCUMENTS: VicRoads 306.11
22e5f97b-59a2-51fa-b1e7-6e54338f6f90 | note | INSPECTION/TEST METHOD: Visual inspection
4959a029-02a5-568e-ba2a-871d1a4642ab | note | RECORD OF CONFORMITY: This ITP signed
8b678751-3f10-5869-b62e-8cc8d07476c6 | note | IP
dbdfd456-bd8b-5771-8293-1be981d82e41 | note | RESPONSIBILITY: Fulton Hogan Engineer
11db96a9-74d6-52ed-9222-abfc53256529 | textbox | Date Completed:
63b6a7fb-8574-4bfe-bfe5-22e53884048c | checkpoint | 2.6 Compaction Testing
4939ac27-6156-5f0c-a7f0-4417523b6b48 | note | FREQUENCY: Each Lot
21cd6b90-f4fd-57f3-a070-fa0b218fc9a9 | note | ACCEPTANCE CRITERIA: •CT material shall be placed, trimmed to level and compacted within allowable working time (306.091) •At completion of compaction, any segregation shall be rectified •>500m2 96% modified compaction 6tests <500m2 98% modified compaction 3 tests
3a58e3bf-956c-581e-a45f-451800215ab1 | note | REFERENCE DOCUMENTS: VicRoads 306.09 306.11
6f266141-107d-53bc-8e52-af6697f07f70 | note | INSPECTION/TEST METHOD: Visual inspection
c4e639ab-c63a-51e9-b2c1-088703e4d0e7 | note | RECORD OF CONFORMITY: This ITP signed
b0ab15d5-8ba2-52b1-baf1-142d76cf8687 | note | WP
57476e73-0b56-5d05-a2f2-8986b82d9bc0 | note | RESPONSIBILITY: Fulton Hogan Engineer
7c297c7b-781d-541a-91fc-aac914bb04a1 | textbox | Date Completed:
503db2ba-02b3-4097-b07a-98be53cc50e4 | checkpoint | Final Inspection
2b5ecd41-f22a-58c9-b1e2-60381b19f456 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
2d09003c-8feb-539c-9985-feb9773cbab2 | textbox | Print Name:
30f70aa4-d87b-5190-bffc-024c0b8e8544 | textbox | Position:
22f1870f-ee54-568f-b203-e949dbf3c118 | textbox | Date:
312f8361-df00-4056-9858-460566ec17cf | checklist | SYS - ITP-006 - Track Placement |  | ITP-006 - Track Placement
d275ca7c-f5d6-4852-8afe-c63ddce09309 | section | Preliminary Works
29bc8485-97ba-4ab3-bb09-996425e2bbb5 | checkpoint | 1.1 Check for Correct Documentation
daeb0388-731f-57c1-a2a6-978892d59275 | note | FREQUENCY: Prior to Commencing Works
16aece01-8ebb-5d14-8836-81a715c2a255 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
92821313-ce3a-5001-b716-5372b7b087c5 | note | REFERENCE DOCUMENTS: Design Drawings and Register
3d66dde8-0e77-57ae-8cb8-a5df46312990 | note | INSPECTION/TEST METHOD: Visual Inspection
f7bdac01-bd6a-5975-b7a7-fada0b55bd31 | note | RECORD OF CONFORMITY: This ITP Signed Off
d0adf627-6e27-56fb-9584-ba99cc1bf5b1 | note | HP*
312907d5-8aff-5f75-b196-1206bf155653 | note | RESPONSIBILITY: Fulton Hogan Engineer
4e49987c-68e8-534d-8f2c-93530a6ab782 | textbox | Date Completed:
4f0af518-79fb-43f9-9fe5-8af0e6ab5d5a | checkpoint | 1.2 Check Materials
37cdc1e6-fc87-5972-b118-89a9dc90eb6e | note | FREQUENCY: Prior to Commencing Works
4f20d0b8-5856-50f6-96c2-21b3f902afbe | note | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used; Check condition of rail sleepers; Ensure rail jewellery is of sound condition
27be80d3-0afa-5b2d-8607-38ca409c279b | note | REFERENCE DOCUMENTS: AS 1085
0bba4caa-4595-56d0-8ce2-1ed56bdc6d8a | note | INSPECTION/TEST METHOD: Visual Inspection
415e5ba3-0ea9-5362-9ee7-8694cf54c587 | note | RECORD OF CONFORMITY: This ITP Signed Off
c0e05af8-762e-512a-846c-371ba559d5be | note | HP*
bdb7b7ff-584a-5edc-a76f-1235a6430cb0 | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
db7b0747-1c70-56e0-8884-1ae6a093de21 | textbox | Date Completed:
a4fb866b-febe-45d9-a8fd-c44195e26a66 | checkpoint | 1.3 Check Special Works Components
1c96be09-5aa8-50df-83a7-71b4fa5e59c1 | note | FREQUENCY: Prior to Commencing Works
1f8d47f0-252d-5bc3-83f3-c95412a1f318 | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending. Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and separate rails.
bd97ed07-2190-5787-9922-49b3411c689c | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.6.2
87138bc7-008f-536a-a8a1-22ae2d5c33b0 | note | INSPECTION/TEST METHOD: Verify
07074e11-c243-581c-93fc-abadf3c58829 | note | RECORD OF CONFORMITY: This ITP Signed Off
f440db75-e2f6-5254-b705-5466bbb7ede0 | note | IP
3e126154-078e-5963-b195-f07e997a36a7 | note | RESPONSIBILITY: Fulton Hogan Engineer
e1d59a9c-502f-59f3-9364-6f3bb00c9071 | textbox | Date Completed:
a5e9172e-2fa1-4ce5-a231-2318e2a769d2 | checkpoint | 1.4 Check Curved rail
b3be2d24-a327-5933-a268-b5682ef97ab9 | note | FREQUENCY: Prior to Commencing Works
54f7c595-cb65-5cb4-a278-df5d62d8c6a9 | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent. Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails. This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
54dc501b-f404-5c8b-9b14-59134e63e4fa | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.6.3
c5a690a8-60eb-5ddd-acf9-be748a0e676c | note | INSPECTION/TEST METHOD: Verify
12957ef0-5db8-5927-bc28-c3d75e5cddc4 | note | RECORD OF CONFORMITY: This ITP Signed Off
b3b9031e-d0df-5929-93d5-ce120ce5d107 | note | HP*
7d989498-5bd9-5bc1-aa5a-cc72363187fb | note | RESPONSIBILITY: Fulton Hogan Engineer
ee994d75-bc1e-528b-916b-0742a528b868 | textbox | Date Completed:
da078a6d-1ecb-449c-a4e3-ac20dccf3175 | checkpoint | 1.5 Welders Qualifications
15c6a8ff-3f77-5689-ba4d-f167872d8d52 | note | FREQUENCY: Prior to Commencing Works
83bef318-9464-5dbc-a3a3-470d8272489a | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements; TLIW2012 Grind Rails; TLIW3015 Weld Rails using Aluminothermic welding process; TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
1e83ae9a-9f09-56ac-b7c1-e85bcafa9b6a | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C
8973092c-38db-51ec-ab62-dc68523844ea | note | INSPECTION/TEST METHOD: Verify
d9c29d0d-c23b-5b97-82fe-3667c202ef25 | note | RECORD OF CONFORMITY: This ITP Signed Off
fede9095-6758-5702-bf34-09709981ae9c | note | HP*
78a97821-b557-5289-b923-2141ef409ad5 | note | RESPONSIBILITY: Fulton Hogan Engineer
48288a18-1c92-592b-9e2b-f0d115c2e2d6 | textbox | Date Completed:
dc2f7fa6-b7bc-4b96-81a2-6b7da8c5b53c | checkpoint | 1.6 Ultrasonic Testers Qualifications
37b6674a-f421-5bea-8b21-a845c4e137b9 | note | FREQUENCY: Prior to Commencing Works
8e88fce8-dfe9-55c1-a27d-9e502112d225 | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
6a0b7a0c-af60-5982-b7a4-ec7c0be86d8a | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C
d9458a17-6639-5368-97db-86540d5455ee | note | INSPECTION/TEST METHOD: Verify
126e60ec-5421-5ebc-8c2a-892225a9f2d0 | note | RECORD OF CONFORMITY: This ITP Signed Off
437ef9b5-49f7-5601-8033-5e0cc9f4ee4f | note | HP*
91baff2e-7cea-504b-b680-1f0696603632 | note | RESPONSIBILITY: Fulton Hogan Engineer
53a2a0de-bf80-5317-ad89-17d7cfed8246 | textbox | Date Completed:
5a54d750-d458-455e-aa33-06d1862b37ef | section | Construction Works
ffa6743a-0436-484f-bf7b-e626cf29cfe8 | checkpoint | 2.1 Installation of Sleeper
824fe86f-fb9b-5aac-99f4-ff8cd702f889 | note | FREQUENCY: Each Lot
5481066b-becd-5cc8-95fa-31c06b9feacb | note | ACCEPTANCE CRITERIA: Dual block sleepers shall be installed at 700mm intervals, tolerance of +/- 50mm in placement; Dual block sleepers shall also comply with the design offsets at each chainage
d15c1d62-55a3-56cf-a21c-324543916be3 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.7.4
de489319-99f7-5462-9de4-feae8b00d3e5 | note | INSPECTION/TEST METHOD: Visual Inspection
b4597e19-ecf1-52b8-830d-e61fede539f3 | note | RECORD OF CONFORMITY: This ITP Signed Off
de84f0a9-1601-5487-9c45-1a9c7d5979bd | note | IP
a3d85723-b3c1-5f79-9f71-77ea063929c9 | note | RESPONSIBILITY: Fulton Hogan Engineer
7d3df303-e7ce-5603-aa2f-5a2d17eb1fb1 | textbox | Date Completed:
c2f6a45c-ea5e-46f4-bcba-20f68d892a7a | checkpoint | 2.2 Placement of Rail
f3f968fb-30e6-5766-8c9d-378a967e9773 | note | FREQUENCY: Each Lot
750efe12-5c60-5ed4-8d61-d411644ec4e0 | note | ACCEPTANCE CRITERIA: Ensure rail strings conform to rail plan
04bb22ea-8870-569d-8b0e-ce667d7e94b9 | note | All track work, including points and crossings shall conform to alignment, offset, level and cant as per design drawings and track charts
ceefc1b1-5701-5efe-b01e-96af1a6c26f4 | note | Bottom of rail and bearing surface shall be clean of foreign materials before laying
31db06e6-09d2-5067-82e1-f65c7ffebd03 | note | Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
d27a61bf-5bf1-5a0b-a8a6-db800f24b5ca | note | Geometry tolerances as follows:
e96addbc-ed21-5c12-aae2-cd764e597bf1 | note | Centreline location: +/- 3mm
f97f9d92-ecf1-5e71-adb2-099791b89d59 | note | Level: +/- 3mm
032e3e1f-bcfd-5059-9e52-98f0537d4462 | note | Line measured (>10m chord): +/- 3mm
ee31c231-e4ef-55e6-af19-5e0e85034054 | note | Twist (3.5m chord): +/- 2mm
dcf83f2c-4a4b-5e31-9c05-c6ccd54158e4 | note | Cant: +/- 3mm
e253d08d-7f78-5f2c-af4a-7326743ac397 | note | Gauge (open track): +3mm, -0mm
023d0ca2-e762-5cc5-8b5c-8f800b945bd4 | note | Gauge, Turnouts (opposite crossings):+2, -0mm
ce61a01f-fc25-5b1d-9e55-2651fd650cb1 | note | Gauge, Diamonds and ‘H’ Crossings:+2, -0mm
9cc7345a-49ae-553e-b95e-a9fe8b2bb091 | note | Note: Cant shall be applied uniformly over transitions
6c0c7082-cdb0-5b16-a68c-198f9a782c77 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9
8cfdc8d1-ce63-529f-8f7e-87c6c7a3c305 | note | INSPECTION/TEST METHOD: Visual Inspection
83042739-6434-54fd-9465-2d5fe504d273 | note | RECORD OF CONFORMITY: Completion of track charts
3c05c3a5-303d-5e90-a15b-fbf43da8400b | note | HP
74add96b-2428-5f91-8f21-23b49bcc0d30 | note | RESPONSIBILITY: Fulton Hogan Engineer
c8afd505-607c-501e-bf47-a86d252aac52 | textbox | Date Completed:
ff52b9b6-e6e8-4baf-9afc-542f40d0a060 | signoff | REQUEST HOLD POINT SIGN OFF
af93fd2b-2c25-45ea-a512-917b2a1c86cd | checkpoint | 2.3 Placement of Jewellery
a21b5346-6fa0-55ac-840a-0dc6b59c0ae4 | note | FREQUENCY: Each Lot
cc654ec3-cd86-57d2-957a-dc961fa79bc9 | note | ACCEPTANCE CRITERIA: Each sleeper shall be fastened to track with approved jewellery and rail clips; Clips shall be installed with panpuller or equivalent; All fasteners shall be sealed as per agreed method with Yarra Trams
87d02d8d-7100-5c75-884c-642e86040da3 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.6
278f3046-3602-5e55-b3bd-fae6b1dac021 | note | INSPECTION/TEST METHOD: Visual Inspection
64c901b5-1091-5890-b03e-ffce490dbca3 | note | RECORD OF CONFORMITY: This ITP Signed Off
a67d06ea-f5d9-5799-a78e-241d877186f1 | note | WP
94075d64-349a-55be-ab02-825c33c0c34a | note | RESPONSIBILITY: Fulton Hogan Engineer
b9a3d0db-db0a-5764-b396-9405d18787d6 | textbox | Date Completed:
83739199-1d2c-49b7-83c5-a37e958ba853 | checkpoint | 2.4 Rail End Preparation
cbb39be1-8dfe-5d42-b707-43a281374f4c | note | FREQUENCY: Each Lot
ce7bdf4b-2493-51bd-833a-ce6921900628 | note | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut ; Minimum closure length from proximity of welds shall be 2m; Rail end conditions shall match (i.e. flame cut - flame cut)
6192dd24-703d-584e-9fa8-b0d7be1d8281 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9 & Appendix C
a68e95d8-3205-576c-babd-9e56c4867af4 | note | INSPECTION/TEST METHOD: Visual Inspection
a8bea0f5-87d8-53f3-b369-178fb4df22fb | note | RECORD OF CONFORMITY: This ITP Signed Off
eb469fd4-a706-5fc9-b9b4-05328de9cf76 | note | WP
2c821295-382e-51b6-a546-eac4b7de5771 | note | RESPONSIBILITY: Fulton Hogan Engineer
47b5d574-8908-5fe1-9670-808ae5e51845 | textbox | Date Completed:
3647827f-379a-4de4-88f3-d4582417fab2 | checkpoint | 2.5 Welding of Rail
9f68afb4-1ee2-594f-a6d7-df91b36309d4 | note | FREQUENCY: Each Weld
dc723f4e-7830-58c7-9ca2-d45a8e7fb1c6 | note | ACCEPTANCE CRITERIA: Joints shall be square across the track
61fcf8ee-c9a5-5d01-b587-af87445af16e | note | Maximum skew at square joints shall be 65mm
cd907f86-8635-5092-a799-662402a59b18 | note | Portions shall match rail type (i.e. HHR, Ordinary)
8662f06a-97aa-503f-8f0d-ebf939da5fc8 | note | Welds shall not be within:
244036fb-5b41-5d90-b99e-2d0bbb28d6dc | note | 3m of another weld
6af5c8c9-aa69-539a-ad95-647f3828dd2a | note | 3m of a rail end
f855d9a0-a065-53ae-a7ad-30f7c92134f8 | note | 1.5m of a glued insulation joint assembly
cbeb089a-7eb1-5778-bd17-76122b6aa8ef | note | Field welds shall be +/- 50mm from centre of bay between sleepers
d9e7325f-e54f-5b13-b6f8-5ae7245820ae | note | Weld Return forms shall be completed by qualified welder
74898ac3-39ad-5d7d-81ed-0ed3710d7e16 | note | Welds shall be grinded after 1 hour
fc0e2bc9-a9f0-5df9-9656-79e3e70e23f5 | note | Welds shall be free of water
ca57556b-7404-5687-b945-7345f3f8508d | note | Post grinding, welds shall be cleaned for visual inspection
07534355-b98f-5f66-8fc1-778e7f52a7bd | note | REFERENCE DOCUMENTS: CE-021-ST-0044; cl 4.9. & Appendix C AS1085
6391c974-f2cf-5f53-a393-c78a196c000b | note | INSPECTION/TEST METHOD: Visual Inspection
346c3cd5-b153-5a66-9f2a-70b87c4a175e | note | RECORD OF CONFORMITY: This ITP Signed Off
6531a3f0-1226-59ca-b79e-069a37a8a026 | note | TP
d31dd995-dbbd-5083-8630-4e191579a4f7 | note | RESPONSIBILITY: Fulton Hogan Engineer
4ea2a4c8-1501-5647-b7b3-0b85d51925fe | textbox | Date Completed:
022afa6c-f09f-4aac-85ce-7bc2bb73fb61 | checkpoint | 2.6 Grinding & Cleaning Welds
3283008f-e3b4-5307-9152-8f021337616d | note | FREQUENCY: Each Weld
6ac14808-c2a5-5f3f-bb5f-dd30b474a231 | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld. Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
ca621e2b-496a-5ff8-801c-3d730cc3c315 | note | REFERENCE DOCUMENTS: VRIOGS 005.2 Pt5 cl 3.4.9 & 3.4.11
180f0f0a-f0ff-57cf-b8c5-5ab282c3d8a6 | note | INSPECTION/TEST METHOD: Visual Inspection
ad7c90b1-f397-56e2-89dc-a6db35c51b36 | note | RECORD OF CONFORMITY: This ITP Signed Off
d62a015d-0290-5baf-adbe-5d41242cf90c | note | IP
72794fbf-6722-5fae-bcd7-78bf6c394c70 | note | RESPONSIBILITY: Fulton Hogan Engineer
3ea1c841-1215-558b-86cf-e9bf7c6d4507 | textbox | Date Completed:
e58199e7-fc85-4be9-992c-341f4b289ed3 | checkpoint | 2.7 Track Adjustment
cb87cad7-ce7a-5e73-a22a-6e37d1c0dd79 | note | FREQUENCY: When required
e4286746-f554-5c26-b884-eadf4710a313 | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths, which shall be measured with an approved type of thermometer. In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep. Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
26c71ec8-212f-5732-9599-a8038aeb406e | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C STD T9008
2f2085bc-3b21-5b9b-8294-71fd9f6269a8 | note | INSPECTION/TEST METHOD: Visual Inspection
7b242363-eb0f-5e08-857d-c93b626e777d | note | RECORD OF CONFORMITY: This ITP Signed Off
e0bdedc4-f3eb-552a-9371-f7871846bd0c | note | IP
1630be21-25dc-5654-ab07-c9fa18320701 | note | RESPONSIBILITY: Fulton Hogan Engineer
43596d22-06d3-5254-9ade-51fe27898fd9 | textbox | Date Completed:
bb9c45bc-6fc1-4232-be22-3c857fa5bd4d | checkpoint | 2.8 Track Bonds
58e498cf-af80-571f-9def-3b21edf43185 | note | FREQUENCY: Each Lot
b4dfa552-ea0d-5aa5-998b-bcee71d1076f | note | ACCEPTANCE CRITERIA: Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications; Ensure bonds are sealed as per agreed method with Yarra Trams
f56b1a4d-8b4b-5918-a075-78b23078cedb | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.5.4 Appendix C Design Drawings
9faf067f-4449-5391-aee4-97584c706c9c | note | INSPECTION/TEST METHOD: Inspection / Test Method
fcae3461-746b-5d83-a992-9c5b5203c2dd | note | RECORD OF CONFORMITY: This ITP Signed Off
0231db8c-8b94-5fbd-9cf9-ab75da42a0c0 | note | IP
507c895d-00cb-5a7b-b404-ae93c9f7eebd | note | RESPONSIBILITY: Fulton Hogan Engineer
ec1dece2-f270-5f75-a55a-cd37e4f5a002 | textbox | Date Completed:
047d3f74-3a09-4be7-8867-6374580d9380 | section | Testing
fd6eef99-6939-4ed0-89b6-f1a705d8e8c7 | checkpoint | 3.1 Track Testing
f674bb80-cbca-505e-aede-4e3b7fd02b20 | note | FREQUENCY: Each Weld
77cf7d26-8cbe-5a19-bd3b-4dbd571cae2f | note | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator; Failed welds shall be cut out and replaced; Testing documentation shall be recorded and supplied to the superintendent
8ff56b98-e6b3-52c9-8bba-e01235509cdf | note | REFERENCE DOCUMENTS: CE-021-ST-0044; Appendix C
14bfc9c3-3def-5fd5-a63b-70ce7359f5be | note | INSPECTION/TEST METHOD: Inspection / Test Method
34c0966d-3a26-593a-b947-8665472c8b92 | note | RECORD OF CONFORMITY: This ITP Signed Off
f678da5a-f8df-5af6-8364-5a895e3cc002 | note | TP
94fa322c-e922-599a-b0ab-003e835f773c | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
939dae50-7b93-5259-8458-213cbce56f51 | textbox | Date Completed:
7691cf54-1f11-493d-894c-55dc10878463 | checkpoint | Final Inspection
886ba3c7-c992-50ee-aa6f-316b72ba9e9b | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
cadd189c-e8a6-55d5-b3f7-9f48a5e77e2b | textbox | Print Name:
1062fa81-6e74-5d1c-b864-1a864156dad6 | textbox | Position:
f85ddf70-87e9-50c7-a293-a9ed6b097cac | textbox | Date:
ae9dc749-38f7-41c3-ad3b-d91366ee0c09 | checklist | SYS - ITP-007 - Concrete Track Slab Pour |  | ITP-007 - Concrete Track Slab Pour
498cf36e-4155-407d-9d1c-5eb22f2b3533 | section | Preliminary Works
f1fa08cd-8477-4fc7-b06b-6bb28770385e | checkpoint | 1.1 Check for correct documentation
b485713d-f8b9-5f85-8873-f84c81c75426 | note | FREQUENCY: Prior to commencing any activity
c16c913c-b8dc-575e-85ab-cb1ac1558cd0 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: using the correct and complete set of drawings; all drawings are the latest revision
06d4a4d3-b726-5dd1-a2f7-0d64fb75426e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
28c66725-83b7-5644-933b-c2236a5e2668 | note | INSPECTION/TEST METHOD: Visual inspection
8244b69e-11d5-5ba0-9a71-87ddf4cb68f0 | note | RECORD OF CONFORMITY: This ITP signed off
4d9afff3-69c7-5947-b585-4f3cdf37ff1a | note | HP*
78853022-2f4f-5d3e-b147-d0842aab80c0 | note | RESPONSIBILITY: Fulton Hogan Engineer
c21073ed-8a7f-5085-9273-8c8814e8536e | textbox | Date Completed:
e76699dd-5b59-489f-b7fc-889c7069d346 | checkpoint | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project
75c755a8-259a-5939-b055-7523569a7831 | note | FREQUENCY: Prior to first concrete pour
4dcb1e33-7c97-5c7d-a2c9-3f28969d9394 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour. Mix shall be minimum 460 kg/m3 cement content (for special 50 mix). Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
3aa6a924-e0aa-528a-980f-06d32aaa28b3 | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.2
a492c582-6b12-507b-a141-a8fd9a75e772 | note | INSPECTION/TEST METHOD: Verify
7c4e2a7a-7296-5d41-a5bf-a186ad083129 | note | RECORD OF CONFORMITY: Mix Design ITP
a033c99d-49b9-58a6-8262-77a4f9747426 | note | HP*
e5355464-c0e5-5fa4-b625-771080369543 | note | RESPONSIBILITY: FH Engineer / Superintendent
a300cfa8-ff97-5214-a6c4-4b1be45e8401 | textbox | Date Completed:
6c16286e-d0cc-419b-84e4-0a6b5d339c85 | section | Construction Works
01271106-c138-498b-a295-d807d354d55b | checkpoint | 2.1 Weather Monitoring
27339a0e-7639-5f8a-b56e-75bbe5cccdef | note | FREQUENCY: Prior to start
74c3a60e-962a-5ab1-8476-7d52c5f312eb | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
be16b78c-0302-5402-9e25-4ec1bb5c9a0f | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4.6
c6e3c45d-ab12-5eb1-acb7-8875695f6b3d | note | INSPECTION/TEST METHOD: Verify
5076f75d-5401-5f5e-95ee-3f3723e1f0e0 | note | RECORD OF CONFORMITY: This ITP signed off
09f10f2c-8612-5614-9563-5f46fdeae41c | note | IP
9c36a17c-56ca-5760-92aa-56bad5e4b4c4 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
73d3c9a6-2e34-5363-8d4f-5a06f5ffc39b | textbox | Date Completed:
3f758fbf-b35f-4891-9de4-0904dab103a9 | checkpoint | 2.2 Surface Preparation
9e939d97-6ca0-5eed-80a7-77ca0bff27c7 | note | FREQUENCY: Prior to start
31e7cf09-bd6d-51d8-beb8-b03496a4bf05 | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thoroughly cleaned of all foreign and loose matter prior to pour
0e5a43bb-204e-5288-b45a-b1f4f210521c | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4
650f2bca-3ec1-5aea-9b02-01ba687e5b8c | note | INSPECTION/TEST METHOD: Verify
bd78bb86-5684-5a3a-a4e6-cae860208ae0 | note | RECORD OF CONFORMITY: This ITP signed off
36560db5-5eb5-5a32-ab89-98df023c6dc0 | note | IP
2274fe0f-9fdb-50a8-8b82-31d057e84934 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
e7499360-5aed-5770-9e2d-0c36375b324e | textbox | Date Completed:
23baf899-d255-4b1f-9e0b-82ee252fc5c5 | checkpoint | 2.3 Setting Out
ff9e53a4-eae4-53c4-8f76-44ad6f2359e4 | note | FREQUENCY: Prior to start
dc9d6ba5-80ab-51b4-a61e-5c0e3342ed57 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications. No survey/level pegs to be removed by any persons until completion of works. Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
c9738952-1e6a-57d0-97ab-591f9ba7e895 | note | REFERENCE DOCUMENTS: Work Procedure
ed7aed6b-9cd0-52f7-b89a-5993c2f97b06 | note | INSPECTION/TEST METHOD: Verify
3f871f4e-3f68-5398-a061-c444bfbc917e | note | RECORD OF CONFORMITY: This ITP signed off
9c04c46b-5d08-54cc-be45-c5eb33ed5816 | note | IP
e7e66c7e-0798-5ed0-996a-03199a902710 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
d94e0580-ae31-5a32-a781-14feff9cfc17 | textbox | Date Completed:
90ca2d1b-85d4-4ddc-9440-2fb7be5c7920 | checkpoint | 2.4 Formwork
150baab9-b822-5f18-bc2c-4eb295f8d668 | note | FREQUENCY: Prior to start
4cbdd58a-5589-5212-9f59-a4c5b23eb653 | note | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement. The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings. Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
13859aaa-10db-5f04-8685-5b09a430562e | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4.5
3597e27a-7715-5476-8dcb-6a77ae8cdb1a | note | INSPECTION/TEST METHOD: Verify
fb82e252-99dd-5417-ab42-b88f00856c4e | note | RECORD OF CONFORMITY: This ITP signed off
4d707684-f19f-57d2-9b4b-8a5200e17fb3 | note | WP
1f7ddf3a-83e7-51f9-9c04-f499b4d6515c | note | RESPONSIBILITY: Fulton Hogan Engineer
97c738ad-2f99-53a8-9048-a8e9d2ea18b8 | textbox | Date Completed:
9ed62968-cc35-481e-b44b-64c83d4d714a | checkpoint | 2.5 Reinforcement
bb97b553-6728-5618-bd47-25ab446794c1 | note | FREQUENCY: Where Required
cf7ee2f1-2b7f-5db6-95b4-1bff81f6720c | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings. All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc. Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and ied with wire at a maximum spacing of 500 mm. Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints. Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
8c14f487-d2d2-5dd2-96b7-73dbb3f34c20 | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4.3
c547a9b1-743b-57c3-b402-74b57630f0ce | note | INSPECTION/TEST METHOD: Verify
617e8425-d4b6-51dc-9c7e-26546bf6ba9e | note | RECORD OF CONFORMITY: This ITP signed off
dc20c178-1e5f-524e-87f9-520c6e4daead | note | IP
c373ca9d-f1cc-55a8-9781-fb5f8b06cb35 | note | RESPONSIBILITY: Fulton Hogan Engineer
f59bed5b-7208-560e-8dd6-731574a6c0d6 | textbox | Date Completed:
e74138de-485a-4757-9440-e7e85ea7f63d | checkpoint | 2.6 Dowels
a9ca1cc6-a7df-5769-8ec2-8b8540c67917 | note | FREQUENCY: Where Required
54e1dc3c-e7e4-53b1-94eb-39c57f6beb68 | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings. All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings. Dowels shall be clean and free from mill scale, loose rust or oil. Ensure that all dowels are securely held in their correct position until the concrete has set.
91fe9ea2-3738-58b9-b7d5-f28674efbccf | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4.4
2c592cf0-6765-583a-b026-1efb1fe617b1 | note | INSPECTION/TEST METHOD: Verify
34fc748d-05b7-5c9d-af85-13621f6b998a | note | RECORD OF CONFORMITY: This ITP signed off
099666cc-b209-5d45-89fe-619a269de3eb | note | IP
c0b97997-f95e-558d-8c66-bdb32eacc044 | note | RESPONSIBILITY: Fulton Hogan Engineer
a9e4addd-0429-5353-bf57-9482aa8c83fb | textbox | Date Completed:
e48c6056-cbf8-428b-a334-76d8ed4fd80b | checkpoint | 2.7 Pre Pour Inspection
045647ba-39b1-5246-89b8-64aa1b6d8678 | note | FREQUENCY: Prior to start
2d582021-e58d-5ee3-bc75-c1dcb33702aa | note | ACCEPTANCE CRITERIA: Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure. Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
40887599-ee14-5c2b-aedf-9cf217ffb076 | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4
8ead8922-3659-52f7-accb-6368a0edff88 | note | INSPECTION/TEST METHOD: Inspection / Test Method
dae9fa63-8600-544b-99ae-0f7d74f4cbca | note | RECORD OF CONFORMITY: FH Track Inspection
f08173f5-357c-5a61-b97c-bb80ba5431e0 | note | HP
9ca55a36-9733-5b4a-9884-3f72d976f5a0 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
07a33bba-6ff2-5ecc-9f0b-9feef9e789e1 | textbox | Date Completed:
92859e82-d272-4f1e-b335-5862a10f86f0 | signoff | Nominated Authority Hold Point
71368a47-4cff-40ef-b8ce-6825dae5e6fe | checkpoint | 2.8 Carry out sampling of concrete
b991f781-1d14-586a-acdb-6c87cdeeb4ea | note | FREQUENCY: Each concrete pour
b5c73d47-7ca4-58d1-be7e-d1d99c59aed5 | note | ACCEPTANCE CRITERIA: Slump: Concrete Slump shall be 75mm +/-20
dc3a9302-31e5-566c-b246-8050b691abe8 | note | Compressive Strength:
d0d21e24-528b-5cf7-86fe-3ac26149cc46 | note | Shall be measured in accordance with VRIOGS
d38ac645-3a87-59c1-8afa-4c7cc7e5214b | note | Testing frequency =
a4d3c99e-89ab-5adc-8df2-23aa2074f589 | note | 0-50m3, 1 sample
105b2a12-0e02-5c50-999a-1b8b17d1376c | note | 50-100m3, 2 samples
27d6c679-c6c0-5f09-85d3-ac3e0c218b7f | note | 100m3 +, 3 samples
49db35a1-b764-55e5-bcc1-b62f471e24c3 | note | Each sample shall consist of 4 cylinders
09f24234-15c5-5a15-bc48-5ecba8fb15d2 | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.5
3db12e8d-c6bd-572d-8ca5-1cf628d8d0d4 | note | INSPECTION/TEST METHOD: Verify
46d295d0-3a3b-535a-b432-37abbcbe6c1f | note | RECORD OF CONFORMITY: Concrete supplier test sheet
105f1155-70ae-5f0a-ada1-ab438011f1ee | note | TP
f6bdc8cb-9f7b-5f1e-a10a-53b4302fd797 | note | RESPONSIBILITY: Fulton Hogan Engineer
0bb92cc4-d953-5f68-bc20-01c374acc56f | textbox | Date Completed:
ecd35021-2561-41a9-a6fd-b6a5c8abd349 | checkpoint | 2.9 Concrete Placement
f945ce87-b9ad-5138-aca3-d05ddb41ddda | note | FREQUENCY: Each Lot
26c76241-e568-5fc8-a22a-4fcb5ea7b7de | note | ACCEPTANCE CRITERIA: Ensure formwork is clean. Concrete shall be entirely discharged 60 minutes after batching. Ensure that pouring does not occur from a height greater than 1200mm concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation. The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage. There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
5b3c5e3b-9381-5707-9c21-2c0d91e68d75 | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4 & 3.5
7524e62c-82c2-53fe-8e04-d509995cc6f3 | note | INSPECTION/TEST METHOD: Visual Inspection
19f07092-28b8-5113-a5d7-9fab3997b056 | note | RECORD OF CONFORMITY: This ITP signed off
b3fabcb3-0ffd-59c8-a17b-5818b9b62d15 | note | WP
a05caf0a-b196-5454-9f79-6787e4090d2a | note | RESPONSIBILITY: Fulton Hogan Engineer
33e93dca-8b02-5154-a934-602d8cf5c15b | textbox | Date Completed:
36a9059e-d693-4903-acf4-cd269f814ce6 | checkpoint | 2.10 Compaction
e80708bb-c6de-5219-8827-b8716733fd9f | note | FREQUENCY: Each Lot
f8067e01-f872-5f0b-95e5-d96385aa3500 | note | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator. Vibration shall take place until exposed concrete surface is free from air voids
b1218f2d-6d71-51cd-97d2-11671b36cb65 | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4.8
fb6447c8-b9d2-57af-8eef-3213f193b045 | note | INSPECTION/TEST METHOD: Visual inspection
32daac22-daef-5d8f-9608-e8e1752fecfe | note | RECORD OF CONFORMITY: This ITP signed off
cdfcdd76-d227-5d2d-bec4-9854f79f8c43 | note | IP
5f067bbf-a54f-505c-b890-72dcdc92a2f3 | note | RESPONSIBILITY: Fulton Hogan Engineer
1a66621c-a282-52d8-b768-4455301f5f42 | textbox | Date Completed:
f00f6b08-01a3-4d25-8e1e-858293cd757e | checkpoint | 2.11 Record location of each batch
4a71e322-5da6-5f26-8d48-6d1eecffdfe8 | note | FREQUENCY: Each concrete pour
28797d52-835d-5c5e-9e82-5966b3d8bad3 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
3989c84a-e21e-5464-9074-23e4d42cc664 | note | REFERENCE DOCUMENTS: CL001D
5969ceec-ce1f-560c-abf6-54a0d7e1c8e3 | note | INSPECTION/TEST METHOD: Checklist
d6ee5bda-219b-5c9e-bd0c-cbc219a85ca3 | note | RECORD OF CONFORMITY: This ITP signed off
36eaa39b-5fe1-50f1-8462-07ff779b3bd6 | note | IP
ca3d6522-448e-5e13-8cff-556d4ee8ca90 | note | RESPONSIBILITY: Fulton Hogan Engineer
375ac57c-d2e1-5a4a-a889-cb48bba62b25 | textbox | Date Completed:
bdd0ccf4-23bd-4bb0-b795-9c3b3a8f14fb | checkpoint | 2.12 Curing
87ba4a40-2afc-5169-8bfb-7e889988eacb | note | FREQUENCY: Each concrete pour
a5d3fcb0-9941-5ee0-ab35-3f5dc0c54834 | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming
a95e1c2b-7a7d-555b-aa5e-62e4e588d0f7 | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4.11
dfbcb8ee-fe7c-52e3-9f4a-2477a51f7d80 | note | INSPECTION/TEST METHOD: Checklist
829c9228-4087-55ec-be63-ae4eede37614 | note | RECORD OF CONFORMITY: This ITP signed off
297123a8-4550-5ad5-84c8-843962fc146f | note | IP
c394c41f-e932-5f2e-8747-8c726b5ef720 | note | RESPONSIBILITY: Fulton Hogan Engineer
bad66420-9dee-5a19-86c2-1596a4d55e52 | textbox | Date Completed:
e19ed592-ae5a-4be7-91b3-b95a9a726bd8 | checkpoint | 2.13 Tolerances
ea931063-a374-5571-b82d-dc0e9ad43cb4 | note | FREQUENCY: Each concrete pour
ae4ab6fb-318b-5ac7-9984-8a5ee73d6485 | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply: Plan dimension of slab +10,-10mm; Thickness of slab +10,-10mm; Cover to reinforcement +5,-3mm; Finished level of slab +3,-3mm; Foundation level of slab +0,-20mm
48c32cf5-8c75-5e10-b542-b121a7007dac | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4.12
63deada5-e2a5-54a4-bd7f-f3df4acc2a47 | note | INSPECTION/TEST METHOD: Checklist
f8c8ea20-5a09-5dc8-bf36-11d8b6658336 | note | RECORD OF CONFORMITY: This ITP signed off
77a93343-3092-5356-bdc9-4d9e35a80203 | note | IP
79f41ee4-9b40-5335-bcb4-5fc0b6cece8e | note | RESPONSIBILITY: Fulton Hogan Engineer
a117f8c3-d01d-54d4-9ea9-7e6ab80f6138 | textbox | Date Completed:
6ae9ea87-5603-4ab8-816e-e48416592b25 | checkpoint | 2.14 Slab finish
bfa158a2-f1a0-5305-9687-63b93e636cbf | note | FREQUENCY: Where applicable - if track is Type 1 structure
60042dce-22db-5e33-a4f4-d229869f4d16 | note | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities. All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections. A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C. The slab surfaces shall be broomed to provide a non-slip finish.
822382b7-9047-55b5-a87a-95b8f84ebb07 | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 cl 3.4.12
015d7eb6-7bae-57ba-810b-0f50a5cde0e2 | note | INSPECTION/TEST METHOD: Checklist
cf438d82-e7e7-5734-bd3f-559f8f96a0c8 | note | RECORD OF CONFORMITY: This ITP signed off
49ee508c-de85-5a1a-bbd8-4f94d2a85c03 | note | IP
f44deb64-0d16-5544-a2ba-029cc2d380e0 | note | RESPONSIBILITY: Fulton Hogan Engineer
05ffab96-9339-51e9-b942-ef098db25545 | textbox | Date Completed:
597b5866-0823-4dea-ab2e-c689d1a46e8d | checkpoint | 2.15 Post Pour Inspection
c7ae1f61-8618-5b6d-8d4d-20f6995bd340 | note | FREQUENCY: Each Lot
692a054a-3cab-5da3-a025-9a4774e852dc | note | ACCEPTANCE CRITERIA: Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings. Ensure no defects are present in slab. Complete Fulton Hogan Post Pour Checklist
142b44bd-01a1-5a68-b785-255e4a4d2f0a | note | REFERENCE DOCUMENTS: VRIOGS Pt 4 3.5.8
e2c10a27-5e60-55c6-8d4f-a3d2b0faa113 | note | INSPECTION/TEST METHOD: Visual Inspection
facb4d13-91fd-5a59-86bf-41f99944afd8 | note | RECORD OF CONFORMITY: Post pour checklist
a65a2b35-b21b-580b-9cd9-d1222958c94e | note | IP
05698ba3-9a74-5017-b27a-804765e7b415 | note | RESPONSIBILITY: Fulton Hogan Engineer
be6c62d9-965a-5cfc-b883-1d2984955487 | textbox | Date Completed:
a863c419-1afc-4843-9d34-0fc3aade4998 | checkpoint | Final Inspection
f32a2366-8cf4-52e2-aa6c-e6fd4bb988ce | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
fdcdaf78-9b60-5b30-84f1-69092a7cf970 | textbox | Print Name:
3a8d5757-75ee-5419-92ae-281820070174 | textbox | Position:
86543a98-8986-54eb-a368-e1523ac5be2e | textbox | Date:
8b8eba42-4b57-4bac-b0ec-09f7e865b494 | checklist | SYS - ITP-008 - Hot Mix Asphalt |  | ITP-008 - Hot Mix Asphalt
436898cd-423a-4bec-82d4-6a0fde85d4f8 | section | Construction Works
4cc62d00-0e28-48fd-87b7-9661c5a9a295 | checkpoint | 1.1 Submission of Mix Design
9a39d2c7-0f1b-5726-b35e-be2a2132f26f | note | FREQUENCY: Prior to commencing paving
f15c64e7-b5d9-5b9c-b7db-322ee934b660 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
65e890a3-976a-5ee1-996f-9d4336b5b115 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
9dff0e9d-ec8c-5cb5-9c04-83d0e144e07d | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
412a28e1-ea89-5e7c-b51b-7afa199dea86 | note | RECORD OF CONFORMITY: Superintendent approval Completed ITP
067c9129-a9f3-588f-8d38-a4ca9eea0796 | note | HP
222975cb-2be7-599f-a920-9f22f90cd45c | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
f9e36f32-cf75-5949-86a4-54a7753838d8 | textbox | Date Completed:
1a936936-fa7c-4e31-8b5d-36ece12f614f | signoff | REQUEST HOLD POINT SIGN OFF
2ad05bf2-d3b0-4f3b-92a7-c2ae97d98f9a | checkpoint | 1.2 Site Inspection and Base Condition
cf9e77a2-e7b7-5a53-ab80-bc21879abc57 | note | FREQUENCY: Prior to commencing paving
cdbb0cb0-3171-58e9-92f4-b8a6a86292c7 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
609432ee-cfe9-50ed-8ce8-6b67ed58e6a1 | note | REFERENCE DOCUMENTS: 407.14 AS2150 10.1 AS2150 10.3
72f83109-a85e-53d4-a509-b7748b86454a | note | INSPECTION/TEST METHOD: Visual Inspection
d86582f6-f781-55ff-9bbd-91d980cfd5e8 | note | RECORD OF CONFORMITY: ITP Signed
26ed6d0f-efd8-5aea-a297-aa4fe3613ed3 | note | WP
71fefc16-a66b-5df1-83fd-374275d54a52 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
fc47a218-8a37-52a7-9974-570faf6e587b | textbox | Date Completed:
45693353-316d-4980-b406-e3e0e6ea652e | checkpoint | 1.3 Ambient Conditions for Placing
7998fcaa-f78a-5251-ac2a-883837882a4a | note | FREQUENCY: Prior to commencing paving
eef0e0dc-8696-5fe3-a4dc-6d3a9c13d882 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following: Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600 Wearing Courses: 10°C for conventional binders or 15°C for PMBs
50687433-38a4-52e9-8eaf-03f79ab186e8 | note | REFERENCE DOCUMENTS: 407.13
7f959185-07c6-5eee-8725-325da5d8493a | note | INSPECTION/TEST METHOD: Verify
f01e6836-4979-5f24-88f9-1207cbe013d0 | note | RECORD OF CONFORMITY: Thermometer
6ef20217-f870-518b-9d0b-1e37b85dbc10 | note | IP
494cb1a1-a765-53ec-a19b-e3c94b7236e6 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
241d05ce-6b72-52a8-a5b2-d0acd3ce6552 | textbox | Date Completed:
27ec015a-8f8f-4ba8-8fb4-7dec66e46a3b | checkpoint | 1.4 Planning of Joints
b7339812-d0c3-5089-a741-f4f286a49c7d | note | FREQUENCY: Prior to commencing paving
22544a0c-1b79-5bbc-9159-7c4971b1a87f | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
a1723cb3-bd35-53e5-8afb-ca3731cba24e | note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
618cec00-3724-57a1-8679-3a8bc40bc7dd | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
e87e9e81-0c2b-543d-a73d-716d1d9c1e20 | note | RECORD OF CONFORMITY: Paving Plan
d5f3c333-3400-52c0-8762-7e173b307e47 | note | WP
af1ab585-5143-54b9-9115-83f6097fc845 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
a841cbb2-1dad-5f6f-b576-143242782cb8 | textbox | Date Completed:
3ab8fed8-808c-4068-a22f-5dae1b0160e6 | checkpoint | 1.5 Longitudinal Joints with existing Pavement
d8bffe91-a643-5681-af1a-477721ceec0b | note | FREQUENCY: Prior to commencing paving
3367d6c2-9377-5de4-81da-5d176e2e14d9 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each individual layer.
a683e141-ce1a-550c-9e44-1a7dd5ec24e9 | note | REFERENCE DOCUMENTS: 407.16 (c) Project Specs. Section 3040.06 (d)(vii)
031e220a-58e6-52a4-8ecf-16852f7b0eea | note | INSPECTION/TEST METHOD: Visual Inspection
2cd99785-30d0-5b9d-bf7d-cce16367261d | note | RECORD OF CONFORMITY: ITP Signed
397794fe-0f88-532d-b5bd-c4e1d1ad6ec3 | note | WP
ff15541f-9c41-5644-a64c-485b99d47fd9 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
db2ca62d-6127-5794-95c5-58534f081a80 | textbox | Date Completed:
59cb3359-54d8-4f8f-addb-90d3d5848aea | section | Asphalt Placement works
d8c982ba-4fac-48b2-8479-2fa944094362 | checkpoint | 2.1 Commencement of Placing
341ebd79-dea6-5d52-a278-c4a656743a78 | note | FREQUENCY: Prior to commencing Paving
44ebe5ff-13ae-5aaa-a7a7-1331030619d8 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
4d43952f-2597-5d91-adf2-544c2b56473a | note | REFERENCE DOCUMENTS: 407.18
6baa5eaa-f3f8-5c8a-8dfb-827a0fac94aa | note | INSPECTION/TEST METHOD: Visual Inspection
2507e501-30fc-5af9-9b10-e01e5ffa6306 | note | RECORD OF CONFORMITY: ITP Signed
84dd1347-0b72-5244-9edb-99ade62c584c | note | HP
33512ec0-ef42-5ca8-8de5-3d0c0c66efc1 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
b43ee0a9-80b3-5c7a-bdfd-96bbafff011b | textbox | Date Completed:
6b9b64f9-a925-481e-912d-101b50f3d029 | signoff | REQUEST HOLD POINT SIGN OFF
f29ffec3-9464-4f18-9e5d-8fb9989f9c68 | checkpoint | 2.2 Mix Design Confirmation
be3500d3-7c08-50d0-bf84-89e05be7ed5b | note | FREQUENCY: Each lot
30c16915-6ee2-5ca5-8f17-395110f1ca1f | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt mix shall be 10H in accordance with Yarra Trams Track Structure standard drawing.
750dae1c-d99f-5c76-ba49-911f6454dc23 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
56d7df6f-1fb8-5c28-8297-ce0fbca99b29 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
a6db31e4-4938-5e60-8194-aeab06f39e3d | note | RECORD OF CONFORMITY: Delivery docket Completed ITP
a9075500-b7fa-51d8-aee7-41528fdfcfe1 | note | HP*
e475d827-93af-5525-85df-a3d4a4cfa564 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
201be9f6-afce-5757-90fa-b49639d8a03e | textbox | Date Completed:
d56c2285-3844-44b5-8e1b-dd2737650e09 | checkpoint | 2.3 Delivery of Mix
15cf1c2e-a78e-56fe-b8f8-e13c625b3b5f | note | FREQUENCY: Each load
e4305d1e-19fc-58bb-8e69-734c54d53900 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
8d70b724-7477-5030-8c80-75f93e8e14fe | note | REFERENCE DOCUMENTS: 407.16 Table 407.081
08b7a9b6-a8ca-58e4-b185-13caa8b88422 | note | INSPECTION/TEST METHOD: Visual Inspection
a73bb0d9-9c15-5d94-8c8c-18cce569f628 | note | RECORD OF CONFORMITY: Delivery Docket
b10c6667-c4a1-5621-99d2-5b0f7f172815 | note | WP
1041f12b-ad95-5261-9fc6-d961cfa98234 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
c8b3156d-0f31-5670-adb4-c442f5fb43d9 | textbox | Date Completed:
5c8e5fe9-26c2-469d-a168-f1193c558cdd | checkpoint | 2.4 Traceability
9c6aa440-71b0-56a1-9055-782c4bf31273 | note | FREQUENCY: Each lot
3b683f35-5225-557c-a1da-6b5569daf5cb | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
c88a68d9-2285-56cd-be63-727512fc8fbc | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
a2733cf2-c606-5f53-89f2-9d43a24bdc62 | note | INSPECTION/TEST METHOD: Verify
176cf10b-102f-5b14-8338-c67568fdd6b7 | note | RECORD OF CONFORMITY: Daily Lot Record
a5f14e2f-e8c2-5ab7-a22f-a1b2f48f0731 | note | IP
6a4744e9-1db5-5911-819a-d1e669616dda | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
2129b626-ba01-509a-b75e-69b48b410400 | textbox | Date Completed:
d27ea92b-4a52-4816-89b4-1acadc8dc340 | checkpoint | 2.5 Layer Thickness and Level Control
e3c49f26-647c-53de-96d5-a1f62cda569d | note | FREQUENCY: Regularly during paving
6347a3bc-4486-5ca1-af9e-155175fa8520 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
2f2bcc38-4b48-5dfc-84c5-96f43b1e0478 | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
898c33a8-91ef-5013-919f-1681dfebeafe | note | INSPECTION/TEST METHOD: Verify
0dcd6ae7-12de-5db4-8360-1042c1e5f2ff | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
7e5b0cf4-dad7-54ea-a3f5-e51056a6dcc6 | note | WP
32683f1d-ee11-5cad-8e9b-5d822dcdccda | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
1aba1566-4794-5b77-9ace-5203a7ef70de | textbox | Date Completed:
8b275150-a158-41f2-8f9e-d756fef4841d | checkpoint | 2.6 Surface Finish of Wearing Course
13c6d978-5810-5970-86d3-1e465834d07b | note | FREQUENCY: During paving and after final roll
a29ab9e2-278d-5756-9396-435863c059cd | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
74d6d8b4-5fbe-5934-ba21-f64a06930bbf | note | REFERENCE DOCUMENTS: 407.23 (a)(i)
8b89f7fb-7310-5e46-bc4c-be7efa7f8e9a | note | INSPECTION/TEST METHOD: Visual Inspection
94d61505-7ade-5505-a8c0-292136a3d5e5 | note | RECORD OF CONFORMITY: ITP Signed
9fa1710a-3b93-544d-a0c9-384d365b9b1e | note | WP
04489c5f-db76-5079-914a-a9204e435390 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
ff3c0ad4-239c-5150-a775-18f668f31bd0 | textbox | Date Completed:
92f46ea9-c216-4f25-9430-2761b515ee06 | checkpoint | 2.7 Alignment of layers not placed against concrete edge
834b1d25-8298-55d6-b653-bd486e41ba96 | note | FREQUENCY: During paving and at completion of work
45f174ca-0a3b-5376-84df-a117344998cb | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
8d44cc9c-50f4-56dd-a129-01fe9e390686 | note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
1eca1488-7e52-5e10-a704-d21108a208a0 | note | INSPECTION/TEST METHOD: Visual Inspection
89b10b57-42a2-58c0-acd7-8342e4b9033f | note | RECORD OF CONFORMITY: ITP Signed
6610ed67-60d1-5970-91f4-f64bfef8f0aa | note | IP
c38a6d7b-a039-5302-9d83-cce8b7276ff2 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
8e8dd1cd-9180-5eac-b5d9-85bcb1a2c4d0 | textbox | Date Completed:
51707d0b-19de-423c-84d8-d5d201890763 | section | Testing
4679b917-386e-4532-9ca2-b6e230bca54d | checkpoint | 3.1 Compaction
38809b62-8373-5fd6-8a29-a70a739ab840 | note | FREQUENCY: Per Lot
0b3bb14f-c4cf-502a-8411-7e67d86ccc05 | note | ACCEPTANCE CRITERIA: For wearing course layers <50mm, if characteristic density ratio is: 94.0% or greater Accept lot 91.0% to 93.9% Lot may be accepted at reduced rate Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
887d85e8-ef2e-5d97-a8d6-d25520516851 | note | REFERENCE DOCUMENTS: Table 407.221
e7be3d59-4399-54e8-a1e1-a654481081a1 | note | INSPECTION/TEST METHOD: Verify
4d555cce-5cc8-5412-8a10-8b699d87c3b9 | note | RECORD OF CONFORMITY: Test Report
6092f6a1-320a-5fa2-b11b-a338e3ef479a | note | TP
a607b0b5-0343-52b1-a6ef-ed1936aba331 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
c86fbf88-874b-5b0c-ba8d-ac1f2b1e6eb6 | textbox | Date Completed:
8de0c5e3-6ffe-49e4-9d57-8d75cbd9f43e | checkpoint | Final Inspection
077948c4-3bc1-5a96-8cbd-eed65d7eefe0 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
b115fe27-e88e-597f-8aa3-35dfa75feb0d | textbox | Print Name:
c4afa765-372a-5204-bfed-bd1b83241aa4 | textbox | Position:
ac27a23c-8afa-5e28-87ab-e931658b47f2 | textbox | Date: