## Master List Templates
Id | Type | Name | Values | Prompting Name
f2fde9e7-9c31-4b6a-b1b5-5c987f27409a | checklist | Contract HoldPoint Checklist |  | Contract HoldPoint Checklist
96a78813-95b0-48fa-9a93-357ec9a1b8cb | checkpoint | Holdpoint Release
e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 | textbox | Enter Name
1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b | textbox | Enter Description
60a1eb35-e850-40c9-a4b9-af7b0196da59 | signoff | Contract Holdpoint Release
b314e121-8c94-48c9-bbe8-c6f019a8f561 | checklist | ITP-001 - Subgrade Preparation Rev2 |  | ITP-001 - Subgrade Preparation Rev2
92735ee7-00d4-4047-b531-1157dd1ffab2 | section | Preliminary Works
8aa120f7-5d64-41d8-a81c-d1dee6f35f05 | checkpoint | 1.1 - Check for correct documentation
45188c88-c52b-57af-b3b7-03ffb2fa8f30 | note | FREQUENCY: Prior to commencing any activity
55e0b00f-b175-5332-9d35-8d2ea8fd0fda | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
43ba18bb-5e67-5b1d-a0d6-f4dfd23fa27d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
cae04579-468a-5bb0-bcbb-188f602e5329 | note | INSPECTION/TEST METHOD: Visual inspection
15d4dbc5-9fd7-5653-89ab-df14a395fcae | note | RECORD OF CONFORMITY: This ITP signed off
44705a3e-a804-5ef6-bd00-c3a1b5801b76 | note | WP
77cc26f7-3555-5973-83aa-3e09b928ae51 | note | RESPONSIBILITY: Fulton Hogan
b0ce8c95-decf-5071-bb9c-7112e16c0c02 | textbox | Date Completed:
c1deca52-bf51-465b-a0ca-c6f0eaa74d09 | checkpoint | 1.2 - Implementation of all measures and controls
bba017b4-8f81-5c61-8c44-f5d8cb094182 | note | FREQUENCY: Prior to commencing any activity
9120371d-d575-5d35-babf-69ea8bded992 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
aa908750-6bad-52a7-b547-cbbaf48c1487 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
b5e9cb4f-3b12-5054-a26b-6a13f91dfa58 | note | INSPECTION/TEST METHOD: Visual Inspection
874839a3-bf07-5f70-aee1-bd340fd598a7 | note | RECORD OF CONFORMITY: This ITP signed off
88e4c18a-b299-5358-b7b1-f0d3ddf5adc1 | note | WP
87f0a977-25a9-5acb-b28a-466cc1433823 | note | RESPONSIBILITY: Fulton Hogan
751321f2-27c7-51ae-9c8f-a44d48accc4c | textbox | Date Completed:
7e640079-d376-4885-9402-3fa9ad0544c7 | checkpoint | 1.3 - Selection and approval of Disposal Site
9cb26a5b-8903-5b22-9685-09c730343609 | note | FREQUENCY: Prior to commencing any activity
67c61ce2-8eac-5a1a-9265-4122e349bae2 | note | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accordance with Yarra Trams site classification report. It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
5ed4e0c4-0358-592c-ab96-6b7db0e4f962 | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019- ST-0033 CL. 4.2.1.5.
a91157d9-da51-5096-b8d9-f25d2a95b07d | note | INSPECTION/TEST METHOD: Verify
840d1327-464c-5e0f-bf9c-0b174666cae7 | note | RECORD OF CONFORMITY: This ITP signed off
b1d0dc7a-d5d3-58a7-bcb8-10f370d9d38b | note | WP
53c3aeff-b9eb-552f-9fa7-fa7614d171b2 | note | RESPONSIBILITY: Fulton Hogan
416f0ccd-cc2e-5d38-b3bc-6ec260c9f0b7 | textbox | Date Completed:
4dd63ab3-dd6b-4529-9b9b-dd6f5f3c7794 | section | Construction Works
a0b41a9b-f81b-4ed8-b6cd-3dbd76ae77bd | checkpoint | 2.1 - Excavation
5dafd1cc-eb05-5463-a582-b13de1af5907 | note | FREQUENCY: Each lot
a338bb55-9b70-51b0-ad00-da39de2e595f | note | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of works
bf0d3fa9-f92b-5dd5-8c6e-ff8e54386b6f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4. Subgrade Preparation Work Procedure
bc767fb1-3969-50a2-b592-64172ca170ea | note | INSPECTION/TEST METHOD: Verify
77f22b39-80c6-532b-8add-3c3a0073877d | note | RECORD OF CONFORMITY: This ITP Signed Off
3240cc15-9d09-54aa-86f3-87a34ff7ba81 | note | IP
2bf90b48-ba07-57d7-9dfb-23536a96f782 | note | RESPONSIBILITY: Fulton Hogan
6da904e9-ee0a-5b76-ac22-f75341946855 | textbox | Date Completed:
0207bb47-3385-4a28-a899-6f3a63f201ee | checkpoint | 2.2 - Reinstatement of bonds
96e709ff-698e-5f3e-8024-5af4d199a873 | note | FREQUENCY:
d84ba202-6a80-507e-ac30-7e6e715dda43 | note | ACCEPTANCE CRITERIA: Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables. All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
eb176fda-5b9a-522e-9824-b0cb052f5bf5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
212381da-8a54-561b-8012-27623ff5f5c4 | note | INSPECTION/TEST METHOD: Verify
3d6cd25a-a502-53c7-acbd-84fb464c4175 | note | RECORD OF CONFORMITY: This ITP Signed Off
9fe48eaf-dfd2-53d4-a56c-5787003855b0 | note | IP
6e521760-12a5-566c-a298-7e6113cd9f22 | note | RESPONSIBILITY: Fulton Hogan
a4d2f4b7-c5d2-53f8-a65e-e823ddfab736 | textbox | Date Completed:
616761f3-455c-4949-85c9-645e8d1dfd16 | checkpoint | 2.3 - Inspection of Subgrade Material
576eb2d8-a672-5a4f-9081-312eb8e5fc3e | note | FREQUENCY: Each lot
2d2796c2-c1ed-5a62-aa52-9ce2626eda06 | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
047d2ad4-f790-5158-a697-a0cb0123e5f7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
35a3a40a-bd2d-5df2-bd64-6fe6802f96d8 | note | INSPECTION/TEST METHOD: Verify
3a007820-922f-57b9-9070-a9892866b1a2 | note | RECORD OF CONFORMITY: This ITP Signed Off
8e7fff5c-a388-5e73-af58-37279c679e42 | note | HP
c2abe582-1979-5c5d-984d-f454996ca911 | note | RESPONSIBILITY: Fulton Hogan Engineer & Yarra Trams Superintendent
b56f1584-fd36-5878-940d-7f33e1d23eaa | textbox | Date Completed:
67fb1652-94c5-4358-922a-2618c31553a4 | signoff | Authority holdpoint
bcd29c89-3f91-4435-87a7-bc7878d471e7 | checkpoint | 2.4 - Width and Level conformity
4e71c4f6-a39e-5344-945d-99f2452efa35 | note | FREQUENCY: Each Lot
752dc8fe-1994-5dc5-9516-3f518929d091 | note | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings. No point in the general surface shall vary more than 12mm from a 3m straight edge. Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
659f292c-4e11-58f6-87c5-625d56098bea | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
d306a058-1fa8-5b7d-aa90-2f7a27fc7a14 | note | INSPECTION/TEST METHOD: Survey Report
2552991b-495c-57e1-a371-4ca5a52bd262 | note | RECORD OF CONFORMITY: Survey Record
54cc9d94-6e86-534f-89ee-f5d16efaacba | note | IP
fccf15a3-d2b7-5ff9-972c-d9dda69557f8 | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
442e49be-7cbb-532c-b42d-621f0ccc41c3 | textbox | Date Completed:
50d8f268-73e5-4b7f-ac48-71a44a9a7497 | checkpoint | Final Inspection
75654e3b-f502-5dbd-af74-d2dc98ede34a | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a69e878b-32cf-5909-b04e-d062802050ec | textbox | Print Name:
36759aa4-7b2a-5d81-8b7c-d0fcc420108b | textbox | Position:
a1625a23-a2b3-58ac-a423-4d707d7d2454 | textbox | Date:
5dad7ec0-5a2a-44e1-8e93-4b0f83edd146 | checklist | ITP-002 - Feeder conduits and pits Rev2 |  | ITP-002 - Feeder conduits and pits Rev2
8aef01c2-8302-4b66-aaa0-7cfc9e3ea3f3 | section | Preliminary Works
078b9a38-5f90-4077-8609-dfd03d43bf0b | checkpoint | 1.1 - Check for correct documentation
d51dd484-9c6d-5853-b8aa-b9db28924a95 | note | FREQUENCY: Prior to commencing any activity
d9a1b59a-b349-594e-84d5-f8d76dafd64f | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
bd529b6a-8653-58b5-9f43-5b588c99c963 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6dfac36e-0b0a-5f25-9daf-d74ce2720bb5 | note | INSPECTION/TEST METHOD: Visual inspection
43c464c7-ca22-5ee3-8d5a-e8eccaf7aa1f | note | RECORD OF CONFORMITY: This ITP signed off
85ebb617-aae5-5c30-9e46-1fa332216229 | note | HP*
c920840b-32a8-58c2-94e3-b2da315adcfe | note | RESPONSIBILITY: Fulton Hogan Engineer
25cc67f6-8fa8-543b-ab4f-28a618b7ff52 | textbox | Date Completed:
905f422e-df0e-477a-a591-6cd067bb2239 | checkpoint | 1.2 - Implementation of all measures and controls
27e5a31c-f489-5daa-afda-a574f4f0fc05 | note | FREQUENCY: Prior to commencing any activity
3a037c4e-663e-5ab4-a5f0-2b809d2383b0 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
75c43fb9-f7c8-55c6-8a40-a869e21e7cce | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
03c168b1-b530-5624-b639-2ee34ec329b0 | note | INSPECTION/TEST METHOD: Visual Inspection
1178321b-b6b1-5494-a825-d516a2740650 | note | RECORD OF CONFORMITY: This ITP signed off
d86abb2f-af58-5e6b-9b24-9dde622bdd27 | note | HP*
9fdf781a-7964-56b1-9b78-d02d90c81bf9 | note | RESPONSIBILITY: Fulton Hogan Engineer
fb4bd187-bf60-5262-aa0b-3992c55f2233 | textbox | Date Completed:
0f9645e0-e9ad-40ac-87ad-b552f95a4dbd | checkpoint | 1.3 - Materials
f3233e4b-fed9-5267-b276-e798ead44f25 | note | FREQUENCY: Per Batch
80f2cc42-40a0-5877-a6dd-f2c93f08f382 | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be Orange • Heavy Duty 100mm diameter UPVC •Modula Stakka pits to be used for feeder pit, entry for conduits to be cut with hole saw •All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
57429af1-2504-55d4-bac6-79e8c8376bf0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4 AS 2053
97ece864-7cdc-5590-972e-9fbf88d4159d | note | INSPECTION/TEST METHOD: Verify
3aeebf58-74e5-521d-b3ed-5e5800b830a3 | note | RECORD OF CONFORMITY: This ITP signed
5e399b9b-85d8-52cc-8162-89589d9a1853 | note | HP*
c886d838-6476-5d54-af10-1dfb8f175886 | note | RESPONSIBILITY: Fulton Hogan Engineer
23606c3b-7e04-5583-b276-e7abd00b490e | textbox | Date Completed:
e1b57d4d-6752-4528-9434-ff0322f14be6 | section | Construction Works
f26712d4-8a67-488a-bc16-4a4fb2783da5 | checkpoint | 2.1 - Survey set-out
d4621f17-83dc-5ec3-8be0-d5c5bff87a0a | note | FREQUENCY: As required
b40990ca-90d0-58aa-a302-ec08ea1b45d2 | note | ACCEPTANCE CRITERIA: • Work is set out in accordance with drawings. • Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
acc81278-9c82-5777-8604-6356d9730b40 | note | REFERENCE DOCUMENTS: Work procedure
6fb1735a-c1a5-5ff6-8a23-0174678b6489 | note | INSPECTION/TEST METHOD: Verify
47ffc079-c89c-56fc-b657-8f0446d83d78 | note | RECORD OF CONFORMITY: This ITP signed
51c8e4df-01c7-50a3-8b7a-1692369bd1e1 | note | HP*
aa92b1c7-6f58-5f34-b2f9-863393a3b7fd | note | RESPONSIBILITY: Fulton Hogan Engineer
3617d15f-48c3-5141-8207-8ea4ad584e80 | textbox | Date Completed:
5c3b09f9-5694-4f4d-a5d8-b9d0250297f0 | checkpoint | 2.2 - Excavation and Trenching
5195388b-b415-583d-9f8a-1075787dab9c | note | FREQUENCY: Prior to Installation
5a3b164e-f14f-5cbd-beea-53935f060e54 | note | ACCEPTANCE CRITERIA: • Minimum cover for underground conduits shall be 600mm • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
9bfae568-b3b6-5ede-ac29-ae153a04cdce | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
1381b0c0-64c8-5f2e-a2f2-89363b1de9b1 | note | INSPECTION/TEST METHOD: Verify
da1bedd7-9329-56a6-b52b-f231955e9274 | note | RECORD OF CONFORMITY: This ITP signed
714b1fa0-5d96-5b53-a09e-0a83e8ac4067 | note | WP
e43c850e-a56d-5c21-9858-cf22d41c80cd | note | RESPONSIBILITY: Fulton Hogan Engineer
80a407f1-269a-523f-a35e-9819efd7ac47 | textbox | Date Completed:
c18b7741-da4c-486f-86f1-8c9a5dbdba56 | checkpoint | 2.3 - Installation of Conduits and pits
59f317ee-f69b-5cfb-bc33-c4ffef6a2cfb | note | FREQUENCY: Each Lot
705c6f9c-f73f-50a5-ac7d-34f7bd058c06 | note | ACCEPTANCE CRITERIA: • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
7864db51-ed20-5439-9338-91188ee2452a | note | Conduit shall be embedded in not less than 50mm sand and covered by
4644165f-7ef7-5db6-9d8e-9a53adf7c186 | note | >50mm - 75mm< sand
a5576bc8-a83d-505b-8414-82ef7b0572c1 | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
6e519764-3a05-5565-a93a-9dd19fb666a0 | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
f5b40ae3-3e12-5116-b6c6-a18a868bc205 | note | • Conduits shall not be subject to construction loadings
f2865fcf-3759-599b-9659-fe56c93ac02b | note | • Pits shall be constructed as to allow for class D rated covers
bd1ae1a6-99fa-5aca-90b4-d6b1e3a1a053 | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor, a 50mm gap between conduits shall be maintained as they enter pit face.
b6079c11-5857-5d94-9a64-418cd2d23f2c | note | • Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mm beyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
79ad57fe-6052-5d9a-9d54-404aea514051 | note | • Conduits shall be placed a minimum of 100mm above pit floor
b40bd866-6d16-55b4-b9a2-2cdc30d2a02e | note | • Conduits installed for future connections shall be installed to the track Margin
a25b6ab1-4553-5bf2-bc83-c1d11185d972 | note | • 100mm of concrete around and under pit lid
5a7e9c26-2e6f-5fb1-a867-9fc91beb85da | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
bdb991ef-92df-5cb4-9ce1-dbefe7bf031e | note | INSPECTION/TEST METHOD: Visual inspection
96907488-a721-5a3a-895f-997e61564d9e | note | RECORD OF CONFORMITY: This ITP signed
367ef7dc-f8b3-5821-ba9c-fbb3220785b9 | note | WP
37a4b8a1-58f1-5d4a-a021-f7f441232491 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
fb223460-d9b5-5582-8acb-d579847aed2f | textbox | Date Completed:
b3f383df-aa05-4b2b-bdf2-c9e47e93b19b | checkpoint | 2.4 - Inspection of conduit installation
7eeea24d-5f10-5a2f-88e0-e4243a7d1a4e | note | FREQUENCY: Each Lot
5ce68162-4e36-5a8a-9d69-580608fcd6b7 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
a2976cf9-6bda-5f2e-a37a-15104961d302 | note | REFERENCE DOCUMENTS: Work procedure
32abdd24-8ce1-5851-b2eb-3856299d993f | note | INSPECTION/TEST METHOD: Visual Inspection
44823288-e7af-5497-9420-7619cf4a1a62 | note | RECORD OF CONFORMITY: This ITP Signed
fdef59a4-c710-593d-999b-fe39b7f05707 | note | *HP
2c5acbe8-ace8-571b-875a-9289025cc9ea | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
5d3d0e3c-6c18-52c5-9471-3ea1a2cfe6ef | textbox | Date Completed:
56aa524c-0e02-4ee9-83ee-20cac1859af8 | checkpoint | 2.5 - Backfill of Trenches
ec1541c4-c2a8-5294-950d-ca3d8a447c7b | note | FREQUENCY: Each Lot
d386fbc1-cc06-5bff-bac5-f52649917a27 | note | ACCEPTANCE CRITERIA: • Backfilling (Only to be used for road crossing trenches) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
734bf98c-f71d-5686-8029-66df36e4e2ed | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
21afa69d-217f-5a08-89d4-53415482fdc2 | note | INSPECTION/TEST METHOD: Verify
d7d35586-77a0-5504-bc20-b4e3132a5367 | note | RECORD OF CONFORMITY: This ITP signed
4256365c-84e6-5a58-99cc-e94700b7972e | note | WP
fa636460-20bf-5746-8f95-25840d46ba5b | note | RESPONSIBILITY: Fulton Hogan Engineer
59b9d26d-1034-50e0-a21f-399cc1d329be | textbox | Date Completed:
1350a87e-99e1-4b8e-99f2-a961540213d4 | checkpoint | 2.6 - Installation of Draw Cords
e4264c8c-2c06-5553-b9f0-4e0deb2ed7ec | note | FREQUENCY: Each Lot
92764ba0-38df-5353-9b65-62d03a243064 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'
39d907d1-de65-5bca-80f4-4e37faff9aa1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
6d7a2af3-0330-5af2-86de-98656a29f440 | note | INSPECTION/TEST METHOD: Verify
71fdc941-35c3-585c-9ea8-68253dd4656f | note | RECORD OF CONFORMITY: This ITP signed
cd070514-a63e-5273-8452-f565b2eec374 | note | WP
8d3e36bb-f303-5fa3-ba8b-90b24c065af5 | note | RESPONSIBILITY: Fulton Hogan Engineer
c35af4aa-28b5-52da-92aa-2870d0b3f634 | textbox | Date Completed:
c97c5d79-e370-46bb-9b2f-1f2df001dcc0 | checkpoint | 2.7 - Compaction
79ec26a0-8d61-5b17-bce7-5f0b49dd4e88 | note | FREQUENCY: Each Lot
4cbb1931-060b-5e0d-8153-28848408f7e4 | note | ACCEPTANCE CRITERIA: • Bedding and backfill material to be compacted using mechanical plant During compaction optimum moisture content of bedding and select fill is within 85% to 115%
8ccd19af-2f12-56fc-bd46-34f0b00bc6c7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
bebcea1d-c15a-524d-93c3-1dc3e4068bff | note | INSPECTION/TEST METHOD: Verify
7b629d97-6a0e-5eeb-aac0-064529a370c4 | note | RECORD OF CONFORMITY: This ITP signed
f643d678-fd04-581a-ad48-f84f8486438e | note | IP
3f92c428-d6c8-58db-9470-dfbc2e44184c | note | RESPONSIBILITY: Fulton Hogan Engineer
e83d6940-d37c-5b8c-883f-27df6430c8bf | textbox | Date Completed:
c4f33e45-de55-44a6-8c32-6d0b8e912850 | checkpoint | 2.8 - Feeder Pits & Pit Lids
2eff92ae-1e2c-532b-9a12-f14a64a3a23e | note | FREQUENCY: Each Lot
3b4a4b01-a703-578f-8e3e-70e839873e57 | note | ACCEPTANCE CRITERIA: • Feeder Pits constructed and installed as per drawings
0943805a-59b5-52e5-b08d-4e0fa3be7a95 | note | • All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar
9378cceb-3f25-5740-92e6-db4e73c9a47f | note | • Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
420676b4-90f8-5ecf-a24f-5ad57d6714ef | note | • Gatic pit lids shall be filled with structural grade concrete.
e8b57501-98d0-58be-9f08-13586c50f3d4 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
38888b6f-ed35-5855-af46-c722d56f4597 | note | INSPECTION/TEST METHOD: Verify
bb5f0b9a-82f9-5207-8af1-c60b85e7e64c | note | RECORD OF CONFORMITY: This ITP signed
7e6e3025-7f8d-58fc-b14a-e6b911d3b4f0 | note | WP
448a0cdd-d744-5cd2-bd05-b5e342ac6fb9 | note | RESPONSIBILITY: Fulton Hogan Engineer
8f616542-944d-57fd-88a8-6e5f13899074 | textbox | Date Completed:
b5b069e0-627c-4ece-bb90-ffd38e39ca68 | checkpoint | Final Inspection
c830c928-6a42-50e5-bf4f-a3ad780a3359 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
3d46f1f4-facf-568e-8c10-8ac93b238201 | textbox | Print Name:
705c52d1-f37a-5f5d-8226-cc38137ef254 | textbox | Position:
92527a12-74dd-58d9-bad4-efeb991d8dd5 | textbox | Date:
47906b50-33c5-4d76-a8c1-d5539885dce7 | checklist | ITP-003 - Electrical and Communication Conduit Rev2 |  | ITP-003 - Electrical and Communication Conduit Rev2
31176222-5868-42a6-bb6f-70b3fa7bc207 | section | Preliminary Works
c4076e9f-5b28-437a-aa27-ae85b621c52f | checkpoint | 1.1 - Check for correct documentation
f37cf723-2f76-53d9-94e9-2e96fff13d88 | note | FREQUENCY: Prior to commencing any activity
ae645317-a5ad-589f-905a-71c064836b2a | note | ACCEPTANCE CRITERIA: Employees and subcontractors shall be issued with the most current and complete construction drawings
a50bafcc-8b88-5fe0-afe0-a620d24bb08a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
74d178c9-73e1-5003-8b2b-93943c629d79 | note | INSPECTION/TEST METHOD: Visual inspection
a068f500-591b-5867-853b-ad3090b869f6 | note | RECORD OF CONFORMITY: This ITP signed off
b37978f2-6fa2-53cb-abd9-d5776574be22 | note | HP*
82064103-dee7-567e-85ea-c82a8b233bff | note | RESPONSIBILITY: Fulton Hogan Engineer
da404d0c-65f9-5333-ba6a-b33234c60693 | textbox | Date Completed:
69c305eb-d475-4543-9b12-45328c843a66 | checkpoint | 1.2 - Implementation of all measures and controls
ae913ecc-9439-5ad4-9a0a-027f004c3416 | note | FREQUENCY: Prior to commencing any activity
8574ffb5-8b67-5cf0-8efb-268d21f481ad | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
aa8c78e1-e348-5e3a-a8fd-6db13c054eb1 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
bd534ec6-fa6c-5d01-8507-9a37bba98e63 | note | INSPECTION/TEST METHOD: Visual Inspection
c39abd1a-9de1-5533-84ff-a29f3e6277c4 | note | RECORD OF CONFORMITY: This ITP signed off
937796af-5546-5fbe-92ed-09ffc2513c2d | note | HP*
b22b05e2-8a17-5fcf-90b3-99535c764dd8 | note | RESPONSIBILITY: Fulton Hogan Engineer
a0cb0867-664b-5a56-8dcb-926d53c9c6d8 | textbox | Date Completed:
9eb92c43-4630-4ea5-ae2b-f7e214a055db | checkpoint | 1.3 - Materials
dc176250-0282-5527-af6b-0055d60ed351 | note | FREQUENCY: Per Batch
b1913a11-7022-5da0-a291-1f77b0f15742 | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be Orange and rigid HD UPVC of sizes as required. • Communications conduit to be White and rigid UPVC of either 32 or 50mm size or larger as required.
5928abd0-863d-583e-bc69-3ca4dd91da16 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.1 AS 2053
6e77ad37-ef14-5bac-9031-5e1f7dfd7b6f | note | INSPECTION/TEST METHOD: Verify
911b61fd-3340-58ac-8390-b7b975cab988 | note | RECORD OF CONFORMITY: This ITP signed
e12ca152-124e-5c61-883f-228b0edfbaab | note | HP*
080f4a39-e2ab-517e-9775-b1bc89c2285d | note | RESPONSIBILITY: Fulton Hogan Engineer
013729c2-7255-56a0-a988-f7273795f1fb | textbox | Date Completed:
8f8dad74-0b7f-4230-92a1-d59f9f1bc4d2 | section | Construction Works
159bdd7b-b662-4a7a-a299-3a4c728efc71 | checkpoint | 2.1 - Survey set-out
60d591cb-05a7-5cf2-9f0d-64252dccf918 | note | FREQUENCY: As required
b2c92a45-2d8a-507a-83dc-4a62bbe33d6b | note | ACCEPTANCE CRITERIA: • Work is set out in accordance with drawings.
b80e7a36-72f3-5606-9cb0-99534f07df78 | note | REFERENCE DOCUMENTS: Work procedure
dae80f44-de96-5808-b6bc-3caa90fb1eb2 | note | INSPECTION/TEST METHOD: Verify
799ab4c8-6484-51b5-aed3-dc59e36e9198 | note | RECORD OF CONFORMITY: This ITP signed
6adaf214-c4a7-5836-9915-aa873f33cb9b | note | HP*
cbf7c7fe-53a3-53e7-b632-1f3e4c968129 | note | RESPONSIBILITY: Fulton Hogan Engineer
c00cf6e3-28c4-51b9-bcf4-5653a40fe34b | textbox | Date Completed:
507a3076-d057-42e7-b6a2-f1193eaf3dd5 | checkpoint | 2.2 - Excavation and Trenching
35447bc8-77dc-5774-8394-590bc5ad78f6 | note | FREQUENCY: Prior to Installation
b56623b1-ce6f-5d67-bf05-87746c51be9e | note | ACCEPTANCE CRITERIA: • Minimum cover for underground conduits shall be 600mm • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
84d38c2b-edeb-5fb7-8ee2-b6adf38a1050 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
ee7ce9e2-79e2-58f3-9dad-5135a2b0f85f | note | INSPECTION/TEST METHOD: Verify
23afe5bd-1722-533a-84f4-4beeb3fe80e4 | note | RECORD OF CONFORMITY: This ITP signed
ae99b891-6b48-5254-afda-942081f0bf53 | note | WP
e76fe0b8-541f-5d1a-8f0a-8ec87117c0fd | note | RESPONSIBILITY: Fulton Hogan Engineer
7f3920c8-7c54-5e4a-b6d9-1a21c5ea977e | textbox | Date Completed:
a2e74203-22e8-4fad-a248-ebbefc8fce75 | checkpoint | 2.3 - Installation of Conduits and pits
b40e944e-dfc4-530e-8b33-02f0e89515d4 | note | FREQUENCY: Each Lot
d9043b88-a333-5e2f-b1d9-b7774872441e | note | ACCEPTANCE CRITERIA: • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
a7d158d7-6b4d-585d-9ea6-cd77a1c454f2 | note | Conduit shall be embedded in not less than 50mm sand and covered by
cd52ca9e-13ac-507b-8ea9-1bf86352807c | note | >50mm - 75mm< sand
023cd43d-5c8e-51fc-b26e-36c8f6cb33d2 | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
6d837a21-8ea3-5e12-be7e-c63b46deed3b | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
ab1979e5-c80c-5c01-bd97-4ae0e9ba776c | note | • Conduits shall not be subject to construction loadings
f5afc207-2756-5e47-bf7f-08f577e10c7e | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor
dcf0571d-1608-5677-8491-bb35d544fd70 | note | • Conduits shall be capped with UPVC electrical caps
81847ff6-2342-5bbb-ab13-7b7ba57d21a2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
0b03f992-28dc-508b-b642-98740e54a9e5 | note | INSPECTION/TEST METHOD: Visual inspection
4972551c-b706-512a-a01e-f5d680e7d8cf | note | RECORD OF CONFORMITY: This ITP signed
ce55d0e6-3eda-5d45-a9b9-8d1583abf411 | note | WP
8c4e53d4-4f65-5b9d-b012-356dc59f8e7c | note | RESPONSIBILITY: Fulton Hogan Engineer/ YT
385fa5e9-e597-5960-bc0c-8b25cceb837d | textbox | Date Completed:
1ac0b196-096a-4e8f-99cb-89e32ff4e5ff | checkpoint | 2.4 - Inspection of conduit installation
bdaa746e-a432-51ab-a931-840fc43f6791 | note | FREQUENCY: Each Lot
69d453be-573c-598d-845e-95b7efaad486 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
3edd8ea6-d590-5bfc-952d-242663fb550c | note | REFERENCE DOCUMENTS: Work procedure
f8f08e89-f712-56da-849e-28563f6fb8e8 | note | INSPECTION/TEST METHOD: Visual Inspection
9c654764-ecca-5323-8240-2b169b3ab393 | note | RECORD OF CONFORMITY: This ITP Signed
66a072a3-6977-5c71-9e5e-ad9624d525ff | note | *HP
abfd7e95-0bf6-5027-a6f4-c83f14e18476 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
35494e49-1d21-5a9a-9a17-37272c298f28 | textbox | Date Completed:
fb1d7401-50d1-414a-b0f7-3ee86dd4e8ec | checkpoint | 2.5 - Backfill of Trenches
db9899f3-a206-55d3-9e9b-071958316181 | note | FREQUENCY: Each Lot
eca85508-0a4a-5cce-983d-729edd60ad9b | note | ACCEPTANCE CRITERIA: • Backfilling (for trenching or road crossings) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction using handheld mechanical plant
64016342-46c1-5f7d-a686-34e7563db3a8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
66ab2d74-64e6-5164-9ee1-9f4973ea3b47 | note | INSPECTION/TEST METHOD: Verify
0d91d238-b4ce-5903-bce2-c7c44f2f19de | note | RECORD OF CONFORMITY: This ITP signed
eee7953d-a751-5398-80bd-c400383657fd | note | IP
d243be8e-4e36-5cc7-848b-e056fdfcaefe | note | RESPONSIBILITY: Fulton Hogan Engineer
cb574033-cbc4-5a9c-ad03-71a398cf2618 | textbox | Date Completed:
dadde7ac-36de-4ff7-8e37-74bf8d880fd4 | checkpoint | 2.6 - Installation of Draw Cords
3656be04-ed75-5de1-91b1-a734d9bdde60 | note | FREQUENCY: Each Lot
5b6e178a-9419-56f6-a88c-6d3e3d309614 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit, material to be used shall be 6mm 'telstra rope'
97ef5f82-d9b8-582c-9600-70b4f8fd90fd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
93007efc-86a5-5a3e-9d28-c7e23bc4cae1 | note | INSPECTION/TEST METHOD: Verify
cd8e3906-b84c-565b-b574-0a0d761e2f8e | note | RECORD OF CONFORMITY: This ITP signed
8452fc5c-cd0c-5ec9-bee0-22ad94954821 | note | IP
777b7c52-4da8-56ff-908c-79a98ff1d2e4 | note | RESPONSIBILITY: Fulton Hogan Engineer
ffe26cc6-1bd4-542e-b7fe-6c8d804154b6 | textbox | Date Completed:
38a5c65a-99d4-4a15-b1ba-20091fa98c60 | checkpoint | 2.7 - Compaction
d26efa9a-710c-580a-a6e0-1381a2b1ed36 | note | FREQUENCY: Each Lot
f199c0c6-7ddd-5f98-84ff-3acc41d92a08 | note | ACCEPTANCE CRITERIA: During compaction optimum moisture content of bedding and select fill is within 85% to 115% as provided by suppliers
0e7898a2-ba62-5def-b2c7-0b567f51f71d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
241c05f9-45af-5382-9ac5-552c469484b3 | note | INSPECTION/TEST METHOD: Verify
7f6171fa-4efd-5595-9f2d-82095df6d6f2 | note | RECORD OF CONFORMITY: This ITP signed
43a0280e-d7bf-57c3-b278-537d3bdfe116 | note | HP*
bb277407-16c6-578f-96d2-607e81a90df8 | note | RESPONSIBILITY: Fulton Hogan Engineer
0c9d4779-cf39-5a1e-a6ba-f2a69a952eba | textbox | Date Completed:
71feae13-4c38-4bef-ba49-95dfcf092fba | checkpoint | Final Inspection
4f331889-36c4-5a9e-bc2f-7a66ecd1d5af | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
18d00a23-909a-5255-846d-69678ec738a3 | textbox | Print Name:
f726574b-0634-56b8-b804-75d6385ae977 | textbox | Position:
4bfa6c5e-99c8-5d4c-8cd3-dacd49324069 | textbox | Date:
61b0af87-1424-4859-b3d0-cf322d0d5c7a | checklist | ITP-004a - Class 2 Base Course Placement Rev2 |  | ITP-004a - Class 2 Base Course Placement Rev2
0dcded0f-6911-427a-b297-aeb69d34c2d7 | section | Preliminary Works
aa9057b8-6923-4779-808b-6ce9e42f2c4f | checkpoint | 1.1 - Check for correct documentation
eef91d5a-f837-5839-930f-5473b2497aab | note | FREQUENCY: Prior to commencing any activity
84db9e43-3dd8-5df6-be5f-62c69ddde189 | note | ACCEPTANCE CRITERIA: Ensure that employees and subcontractors are using the most current and complete set of construction drawings.
d02c4a52-4474-5194-910b-4c7161923dcc | note | REFERENCE DOCUMENTS: Drawings and drawing registers
30c0e7a3-73f5-5b72-a7eb-f13a26e15dbd | note | INSPECTION/TEST METHOD: Visual inspection
5a4ac37e-af0a-5ead-8598-72047698c2c1 | note | RECORD OF CONFORMITY: This ITP signed
62535004-9aa8-594f-8daa-aa3f02596fa3 | note | HP*
ece700da-f66e-586c-9256-f71cfc6ec07b | note | RESPONSIBILITY: FH Engineer
b0384619-674c-5c6c-985e-58ee3d37a1f6 | textbox | Date Completed:
b8dfa60f-643e-424c-bbc8-40d0ef911d3f | checkpoint | 1.2 - Implementation of all measures and controls
fc7dcc62-2082-5c5c-8cc1-52bc0a723c98 | note | FREQUENCY: Prior to commencing any activity
1a680cde-7660-5501-bb79-5ddc5578053f | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
e7851ce6-2936-5ed5-b5be-65dee865138e | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
0b551fb5-d5b9-58c4-8844-af21ff81c2f1 | note | INSPECTION/TEST METHOD: Verify
5ed90e30-9a9b-5a2f-9388-dc44e7a89477 | note | RECORD OF CONFORMITY: This ITP signed
a069b083-00bd-549c-9e05-30f28dfc61e2 | note | HP*
f0f6985b-2521-5b9d-98dc-a5d2c732ac7f | note | RESPONSIBILITY: FH Engineer
327a8ca3-d198-5ff9-a867-d6ba43fc9043 | textbox | Date Completed:
3ec7999d-fe67-4e4d-89df-5043215e03e6 | checkpoint | 1.3 - Material Compliance
e82ac387-ff02-5e15-ab93-3eefc5250091 | note | FREQUENCY: Prior to commencing any activity
1bf9ab70-5939-5955-a56f-ae13922abd44 | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
e904aa9d-c9fa-5645-a247-8ee3a53e8d93 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
a358e1e5-8eeb-5535-a9dc-f3f257f7f5c3 | note | INSPECTION/TEST METHOD: Document Review
eb0466f9-bd69-5d68-95f4-1046c3bfe706 | note | RECORD OF CONFORMITY: Test Reports from supplier
1dac424b-f976-5139-bb61-b381a7b925bc | note | HP*
ced59007-5c8b-5fc4-9c04-c979b360e1f6 | note | RESPONSIBILITY: FH Engineer
8adf8e0b-46ae-5575-bd2a-eaa29414b272 | textbox | Date Completed:
e2218d35-1110-4789-a69e-5876e619e25f | section | Construction Works
65b2037f-7e03-43ce-b996-a938436deb28 | checkpoint | 2.1 - Sub Base
8daeafc4-a682-5c4e-af73-522275246ecd | note | FREQUENCY: Each Lot
b888a4e1-9d3b-5cc3-902b-eaadd50ad384 | note | ACCEPTANCE CRITERIA: •Sub grade has been inspected, no visible ponding, springing presence, or visible deformation. •ITP-001 HP for subgrade inspection signed off
ba22bed7-ddc4-58b2-9505-94dfafbcf2cf | note | REFERENCE DOCUMENTS: VicRoads 173.03
66e97eea-806e-54e5-b4d2-0e243fd0e8db | note | INSPECTION/TEST METHOD: Inspection / Test Method
e174b0f7-6cd8-5d29-874f-38508af138f6 | note | RECORD OF CONFORMITY: This ITP signed
3d3aa363-9310-5347-8030-7fb946a02060 | note | HP*
7f97e0fb-e641-5fb2-84c6-dc5a3f07648a | note | RESPONSIBILITY: Fulton Hogan Engineer
1099080b-28cb-5b02-aff0-bdf51ef921dc | textbox | Date Completed:
ccd23935-1f11-4dfb-8437-9b4fc9e1c91c | checkpoint | 2.2 - Spreading material
9e2b7c62-1dc5-58c3-b5c9-67b03ea11e9a | note | FREQUENCY: Each lot
8f966443-2fd9-52c2-a085-1ce0f0d2b7d9 | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
ed078c52-eda9-5ee9-849c-3c8eeaed2936 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
187ad34a-5dec-5c13-b603-cb88931b35ae | note | INSPECTION/TEST METHOD: Visual Inspection
8d744c30-ed30-584f-a72c-401373f8cfc7 | note | RECORD OF CONFORMITY: This ITP signed off
28099315-bed7-5049-8c33-d3bce69d5758 | note | IP
eddcbe64-d787-5c47-99ae-67faa5c4d88c | note | RESPONSIBILITY: FH Engineer
65e3ad3b-761e-56a2-9fb1-1a5af70933ad | textbox | Date Completed:
e8aa4bbf-c360-4e34-bcea-1681091275fa | checkpoint | 2.3 - Compaction
5d7ad225-482c-597d-9110-863daa2445f7 | note | FREQUENCY: Each lot
dabf21ad-be7b-5980-8c10-68e910937fb3 | note | ACCEPTANCE CRITERIA: Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content. Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test. Compaction testing shall be carried out once per days production and shall comprise of three samples
b94ad6da-b02f-5a95-854f-fb0045334c40 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
96f757bd-8e2c-5c0d-bb6d-135467a3032d | note | INSPECTION/TEST METHOD: Visual Inspection
1a326134-5b92-5d5d-937d-561080adccf0 | note | RECORD OF CONFORMITY: Test Results
fc686ef0-37a9-562d-b112-dcfbaa564523 | note | TP
58387605-66b9-52cd-82e4-bcfa483a3bd2 | note | RESPONSIBILITY: FH Engineer
f32ea8e2-a01f-5968-80a6-0c6e9b99fa3a | textbox | Date Completed:
f701963b-3aa8-415e-83ae-ee60218748ce | checkpoint | 2.4 - Level Checking and Conformance
475275c0-ac92-5903-abe8-352c2068a9a4 | note | FREQUENCY: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
bc73e642-60d7-59ef-b134-f4937154e1f3 | note | ACCEPTANCE CRITERIA: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
ab119d18-cb8c-5197-a5e9-c43f6801d4f3 | note | REFERENCE DOCUMENTS: Verify
5328e5bc-46fa-5a60-9297-617d1cf4ea83 | note | INSPECTION/TEST METHOD: This ITP signed off
de698c9b-1185-5d02-8800-6059665c9de0 | note | RECORD OF CONFORMITY: IP
b173bd24-e549-5951-a7b7-2eee0d9a4f28 | note | FH Engineer
d3fc8745-778b-5c1a-8b80-8fa72dc44efa | note | RESPONSIBILITY: N/A
11fe45d4-30a7-5de7-8745-e29cb13176b8 | textbox | Date Completed:
c85ac2be-0fd2-4780-b5fc-567c81c47969 | checkpoint | 2.5 - Finished surface
f7166abb-ad84-5d87-affb-0f1e1122a1b0 | note | FREQUENCY: Each lot
7433e2e8-359c-50fd-9d34-47f24856ec75 | note | ACCEPTANCE CRITERIA: Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
c3c4ecdb-915b-5342-994d-27176ae51f97 | note | REFERENCE DOCUMENTS: •CE-019-ST- 0033 CL4.2.2.8 •Contract drawings
254a6555-18b0-5c68-b418-7d974169d062 | note | INSPECTION/TEST METHOD: Visual inspection
db50be59-4048-5051-a90d-119c974582c8 | note | RECORD OF CONFORMITY: This ITP signed off
c0aad2f6-6bda-54d9-ad08-36b1a9085c9b | note | SCP
066992cc-acb5-5974-96ee-5f62d6bf7713 | note | RESPONSIBILITY: Surveyor/ FH Engineer
a1daa22c-f86e-584b-a6bb-298e8ef9d48d | textbox | Date Completed:
d7bd8cb7-f657-4c48-93d6-b1745b4d9c0b | checkpoint | Final Inspection
00bf2141-6f55-5909-bd01-9750e86e105e | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
cb1f4194-31b5-5522-82d2-405c7f380264 | textbox | Print Name:
fa211b4d-6b05-51c2-ac9b-f724283170f4 | textbox | Position:
f049c979-d774-5cfd-8d1a-26564e4caf7f | textbox | Date:
7d7261fe-15da-4958-999c-0a311bebf277 | checklist | ITP-004b - Cement Treated Crush Rock Sub Base Rev2 |  | ITP-004b - Cement Treated Crush Rock Sub Base Rev2
2d7b8342-653a-41d7-8560-f48ed38a2bba | section | Preliminary Works
024a39ca-a139-4995-87e5-19ae019e4c54 | checkpoint | 1.1 - Check for correct documentation
b979d9aa-6a01-57f7-b64b-44610b82fecc | note | FREQUENCY: Prior to commencing any activity
9870f5cf-cfaf-5dba-b457-c668a7c550c4 | note | ACCEPTANCE CRITERIA: •Ensure that all employees and subcontractors are using the most current and complete design drawings
76c84cb3-7c1f-5e9a-ba2e-ed583e27bbd2 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
fe97673e-860b-5a8e-86c6-2f15c213662c | note | INSPECTION/TEST METHOD: Visual inspection
2621deaf-610f-5cd1-a82b-85b922385cb9 | note | RECORD OF CONFORMITY: This ITP signed
00ba2b62-1e42-5fe1-8118-ca1b3cca3cfc | note | HP*
cafc0b61-3dd1-522d-a5a8-8492d32229cf | note | RESPONSIBILITY: Fulton Hogan Engineer
30421942-5ed1-5cba-a24a-c8fdb6223279 | textbox | Date Completed:
38b9add4-d930-471c-875b-40b75f294906 | checkpoint | 1.2 - Implementation of all measures and controls
9969843f-fc55-5ffe-89b7-70184a77ce13 | note | FREQUENCY: Prior to commencing any activity
01573ea4-5ec8-5d86-a74e-a721e2fe8eb7 | note | ACCEPTANCE CRITERIA: •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
3083eff3-0da3-5fba-903d-21e59becd9b8 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
2f320348-f001-5b91-9e67-736279484241 | note | INSPECTION/TEST METHOD: Visual Inspection
c406ceb9-a796-580d-bccd-de6e3e773343 | note | RECORD OF CONFORMITY: This ITP signed
9a75c135-7e1f-57c3-bfc3-c44fe3bb2cbc | note | HP*
767668ad-c44d-5906-8136-e6bb37a40970 | note | RESPONSIBILITY: Fulton Hogan Engineer
dbbc1e78-a90f-590b-8829-c0c6d953c370 | textbox | Date Completed:
9c1a91b2-1c8c-4843-90af-74ee7295c8ba | checkpoint | 1.3 - Confirm CTCR is Appropriate Mix
ec19e46f-6476-51a3-9ee1-22721cc8407e | note | FREQUENCY: Prior to commencing any activity
2e9df7a5-2770-54a3-86e7-3247ff257886 | note | ACCEPTANCE CRITERIA: •Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product. •CTCR shall be tested in accordance with 815.141 by supplier
2127715f-9d09-5c78-ab52-7c9b6732fa3f | note | REFERENCE DOCUMENTS: Design Mix
b82d4654-3b95-51b5-8d79-3e1bded313ed | note | INSPECTION/TEST METHOD: Inspection
6de37178-036c-500d-9c73-2e312127e89b | note | RECORD OF CONFORMITY: This ITP signed
95df40be-2565-581f-a82e-913b1eb1387a | note | HP*
175600bf-c89a-57a9-829a-ed62cfd1375e | note | RESPONSIBILITY: Fulton Hogan Engineer
dc1c1b5e-908d-53c3-98bb-bb81c32d4148 | textbox | Date Completed:
6efd4fe2-bc3e-4648-ab49-6f80e86a7796 | section | Construction Works
fbda8ad6-3ca7-4b61-9c33-d6b699f703d8 | checkpoint | 2.1 - Sub Base
8743efbd-bd54-5179-8b2f-1df0f578bd89 | note | FREQUENCY: Each Lot
314edfb3-4aba-51cc-87eb-de74e0463355 | note | ACCEPTANCE CRITERIA: •Sub grade has been inspected, no visible ponding, springing presence, or visible deformation. •Proof Roll shall be conducted by plant compliant of 173.03
8f3112a7-cfc9-5a7a-b441-6587963245ea | note | REFERENCE DOCUMENTS: VicRoads 173.03
b305b37b-1a09-5f6f-a2e5-f614f36a9fba | note | INSPECTION/TEST METHOD: Inspection / Test Method
70bd699d-d974-54aa-8a71-5c5d6b448c37 | note | RECORD OF CONFORMITY: This ITP signed
42ee9c2a-e61f-54b3-9c63-e295db3db12d | note | HP
1ff63e5f-82c9-5653-b565-5186bfaed950 | note | RESPONSIBILITY: Fulton Hogan Engineer
9d3e2796-84e0-57ac-969b-5709d1c63152 | textbox | Date Completed:
b8c5fc30-d268-4d08-b2b8-2dbcedf0ccc9 | signoff | Authority holdpoint
87270b10-1274-48fd-b7bc-f7373d27fd8b | checkpoint | 2.2 - Moisture Content
8774b2ca-6d58-5916-b9c2-b10080f7702c | note | FREQUENCY: Each Lot
738fbb1f-947a-59d9-88ee-a30ac66a036f | note | ACCEPTANCE CRITERIA: •Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
dc7e1006-332f-52e0-89ef-8744e43a6b81 | note | REFERENCE DOCUMENTS: Vicroads 306.05
aa76258d-15f7-5dec-b42c-8d000b1f4a5e | note | INSPECTION/TEST METHOD: Inspection / Test Method
5f91932b-4875-5560-bdd5-a9869ffdc049 | note | RECORD OF CONFORMITY: Record of conformity
54061f89-7253-5242-87cd-b09aaae2484c | note | IP
81632bd8-3b97-5051-be66-e34577e5530c | note | RESPONSIBILITY: Fulton Hogan Engineer
a42ebae5-9e84-57a4-959f-ea1952ef4851 | textbox | Date Completed:
be302b2d-928a-4902-9709-149fe1ba3637 | checkpoint | 2.3 - Jointing
8410b6d2-8b08-50d8-8b21-9550cbc0b0d8 | note | FREQUENCY: Each Lot
ec70281c-1174-5ba6-be32-c062064f2b32 | note | ACCEPTANCE CRITERIA: •Material shall be spread to minimise number of joins
849bb7e5-af89-56e0-a70a-828ff9135513 | note | •transverse joints in adjoining paver runs shall be offset by >2m
d3f33619-9214-5996-a66e-d923606a3f5a | note | •Longitudinal joints shall be offset from each layer
a1d8117e-7b56-5819-b3d5-fb616c61839c | note | >150mm
a03edf84-9461-5735-a263-c70a6cb41bbc | note | •Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
730428fc-523c-5400-9e87-3ebd46c0f14c | note | REFERENCE DOCUMENTS: VicRoads 306.08
8d3c6204-dec9-58c1-9665-f8a66c52f4fc | note | INSPECTION/TEST METHOD: Visual inspection
91adcf2a-309d-54a5-a294-104fc92735a9 | note | RECORD OF CONFORMITY: This ITP signed
2e3c665e-54d0-50ea-9039-18d4351d6b72 | note | HP*
0b546cc6-aa3e-560d-8106-76caf2c6486e | note | RESPONSIBILITY: Fulton Hogan Engineer
62969414-c646-53c4-bb92-381d921ca92c | textbox | Date Completed:
fc8c2543-06ab-45a7-ac0e-7a1bbc090008 | checkpoint | 2.4 - Conformity with Drawings
4b4b77a3-c7a9-58b9-aefd-c89bfa91bd60 | note | FREQUENCY: Each Lot
8b372d5e-e242-5122-9cbb-b0f19545ee6f | note | ACCEPTANCE CRITERIA: •Pavement sub base shall be finished to smooth and uniform surface
e2aecb7e-74d5-575d-ad04-068e1e5ffd29 | note | •Surface of sub grade shall not lie more than 12mm below a 3m straightedge
e8475bfb-6f18-54d0-b8ce-fafc9416adcd | note | •Subgrade height shall lie within +15 to -25mm
a95f964e-7b85-561c-8e4d-f428143df434 | note | •Sub base height shall lie within +10 to -25mm
90cf01f7-33e1-5262-afe8-1295db124424 | note | REFERENCE DOCUMENTS: VicRoads 306.03 306.11
ea782bf8-5070-5599-bac2-17bf7c14e333 | note | INSPECTION/TEST METHOD: Visual inspection
fa89c1cd-6348-534a-bb0c-6acfa5b3e6a6 | note | RECORD OF CONFORMITY: This ITP signed
d789ab5b-50f9-532b-bbb0-d9c1dc464c82 | note | WP
64f8e23e-501e-5278-9110-b5b5e43d3c57 | note | RESPONSIBILITY: Fulton Hogan Engineer
0084edbb-1f9b-5765-9706-5c68078b7b57 | textbox | Date Completed:
5ebaa305-85a5-4add-bb85-15c93669bb2e | checkpoint | 2.5 - Curing
5f8cdfda-3f3d-5f4c-8aaf-e0761736d8ad | note | FREQUENCY: Each lot
1831e497-d46a-57d3-81e4-8cbed0a8fe56 | note | ACCEPTANCE CRITERIA: •The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane. •As per VicRoads, 4000m2 shall be maximum lot size •No trafficking before 24hrs unless approved by superintendent
ab299939-c62e-512a-916f-0d3068515f8f | note | REFERENCE DOCUMENTS: VicRoads 306.11
1a7e923d-f8c4-5bf4-a25c-a61cbd2e2580 | note | INSPECTION/TEST METHOD: Visual inspection
0a05f2f5-9117-52f5-a0fb-f2b8a73d51a9 | note | RECORD OF CONFORMITY: This ITP signed
b4f63502-ec89-5dea-802d-9cc70976b287 | note | IP
4057a548-26d3-5908-a2a6-aade18b7d452 | note | RESPONSIBILITY: Fulton Hogan Engineer
6a0f8167-f20a-5236-bdba-03f5fc7bf9f5 | textbox | Date Completed:
b3fb593c-6e8a-4b00-aefc-72ab6138eef7 | checkpoint | 2.6 - Compaction Testing
c0653381-983d-5f36-8057-481dc9e54989 | note | FREQUENCY: Each Lot
d5f02a96-a45d-51d5-9446-c15dd1f8fae4 | note | ACCEPTANCE CRITERIA: •CT material shall be placed, trimmed to level and compacted within allowable working time (306.091) •At completion of compaction, any segregation shall be rectified •>500m2 96% modified compaction 6tests <500m2 98% modified compaction 3 tests
a51049ac-3b77-5158-a378-627440286866 | note | REFERENCE DOCUMENTS: VicRoads 306.09 306.11
4fca6769-a0d3-53f2-bae1-12bd818f2bde | note | INSPECTION/TEST METHOD: Visual inspection
db02e54a-fc81-5dbe-8be6-2c1c1f295550 | note | RECORD OF CONFORMITY: This ITP signed
185b0ca0-212c-595d-9c67-894a76db742a | note | WP
875c0d4e-4207-565e-adf9-3faac60282bb | note | RESPONSIBILITY: Fulton Hogan Engineer
2779c6ea-8367-5f07-ae42-4f778ebbd858 | textbox | Date Completed:
c69ab091-cb63-4d3d-905c-d25aeeea708e | checkpoint | Final Inspection
98d167ad-83f6-5040-b39f-dcf0a76f0e85 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
bc93a8bf-6f8c-5243-801d-abefbf44d679 | textbox | Print Name:
918266b1-a04c-58b4-8e76-defcc838ef5f | textbox | Position:
5cc70b78-4fc2-51ca-ab5f-e7df651f4596 | textbox | Date:
ecaed04e-332b-4e70-8e7d-0d34d827131e | checklist | ITP-005 -Track Drains |  | ITP-005 -Track Drains
eac7f392-1c24-451e-bef2-a2ace5255a3b | section | Preliminary Works
f2051218-07ec-40f1-b3ca-1d75662d25ce | checkpoint | 1.1 Check for correct documentation
9e719214-6f4c-522a-a6cd-8392c44ccdb9 | note | FREQUENCY: Prior to commencing any activity
139d3e82-c1be-5d58-8955-208cf82d45a6 | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwarded to the superintendent
8f2a61a5-b312-5f92-8888-1b93eb7e5495 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
86c0aaa8-b18d-50b5-8605-5514dd478421 | note | INSPECTION/TEST METHOD: Visual inspection
86e70454-672b-53a3-8ed7-3869e180b07a | note | RECORD OF CONFORMITY: This ITP signed off
47ad83f4-0d5e-550a-b12d-bdf6ac4668c5 | note | HP*
44c17bdc-3d8a-5b41-8d12-6f82fb650741 | note | RESPONSIBILITY: Fulton Hogan Engineer
7c64b342-81bb-5d5d-b737-3664f9ccfe76 | textbox | Date Completed:
0f8b0809-12b8-4d9d-aa84-9c6f757c5bfd | checkpoint | 1.3 Materials Check
201b920b-fff7-53fb-a870-f2e6543c6a66 | note | FREQUENCY: Prior to commencing any activity
1b3ccf73-4750-56ad-84be-0170f69ad3b9 | note | ACCEPTANCE CRITERIA: Ensure drainage pipes are of correct classification and are without damage Check triangle drains are of adequate quality, and are design according Ri57A rail profile Ensure lid and j-bolts being used are in accordance with STD T9022
503fc156-3cab-59f1-aa1b-be63ee508c71 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A STD T9020 STD T9022
62c931ab-d295-583c-983f-44dd2009f59d | note | INSPECTION/TEST METHOD: Visual inspection Inspection Checklist
2cb56583-da6b-5213-9c22-b0c108412b4e | note | RECORD OF CONFORMITY: This ITP signed off Receivable Inspection Checklist
58d8df27-e9ff-5bfa-aa47-909e3008f527 | note | HP*
9d48d4d1-305c-57c6-ae7f-418261af225e | note | RESPONSIBILITY: Fulton Hogan Engineer
c613a3e8-8884-51fe-87c4-51d2ef2ada77 | textbox | Date Completed:
6b955491-33fa-4d74-bd51-491f6c27398a | checkpoint | 1.4 Bedding Sand
be7f4aa8-56d6-5470-b0ee-e2088df95052 | note | FREQUENCY: Prior to commencing any activity
0a61d9ee-c190-52d9-bfdb-20b31ec4de3b | note | ACCEPTANCE CRITERIA: The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following: Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities, Consisting of hard durable particles, and well graded.
12b85dcc-a727-5564-b1ca-04242d428bff | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
49d72c40-2574-5953-88aa-67494223445a | note | INSPECTION/TEST METHOD: Visual inspection
17698916-737c-595e-8736-0cf94fd3fc2a | note | RECORD OF CONFORMITY: This ITP signed off
f26b99bc-fcd7-5ad0-9536-25fae0c2836b | note | HP*
dcf78e96-d86b-5266-bdc7-61bb5d8b69dc | note | RESPONSIBILITY: Fulton Hogan Engineer
5b343919-49cc-5fbd-ba3b-98d52a0c3281 | textbox | Date Completed:
d1d4e554-e4fe-4411-91de-96068a99e672 | section | Construction Works
2c85e9c6-3137-4630-ba3c-e1dde5464374 | checkpoint | 2.1 Set out drainage
caaae469-153e-5cc3-acef-277af5c4474d | note | FREQUENCY: Prior to commencing any activity
ad9c3afa-56dd-5492-8e71-aaf93898aaa0 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent Track drain locations are to be identified and based off IFC drawings and sections.
9a68a058-3867-5080-9914-5aa1bbdf7b21 | note | REFERENCE DOCUMENTS: Design Drawings and Register
064b1ee0-969a-5c23-8298-a379df9fc504 | note | INSPECTION/TEST METHOD: Visual inspection
245db1aa-66ed-5cac-983d-38884a4e574c | note | RECORD OF CONFORMITY: This ITP signed off
425074ba-d042-5055-8167-1925612e9994 | note | HP*
bb1dbb91-5f3d-507d-aaad-1e4bfc4cf12d | note | RESPONSIBILITY: Fulton Hogan Engineer
01db7acf-86c9-5424-848b-934d6dbea948 | textbox | Date Completed:
86ddaf8d-b21d-4bce-89b3-0207d2e63957 | checkpoint | 2.2 Excavation (pipes)
bf991b72-e9f5-5704-ab45-3b2270b14b48 | note | FREQUENCY: Each Trench
7141dcb5-2981-53f6-bcdc-c847bc298ee6 | note | ACCEPTANCE CRITERIA: Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
0005575c-c604-5029-8a8e-a710b26761a6 | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
298cb14e-25f3-5992-b46e-cff5236cfceb | note | INSPECTION/TEST METHOD: Visual Inspection
34067c0e-3af7-5e54-8198-2bfb5e571e8b | note | RECORD OF CONFORMITY: This ITP signed off
049e91f2-9006-573a-b4d9-3522339d240d | note | IP
400cdc14-1eb5-5cdb-b30b-abdc5b532723 | note | RESPONSIBILITY: Fulton Hogan Engineer
e53e65d6-3f8c-5b04-9f51-3fb137c6a005 | textbox | Date Completed:
ceae9883-25a2-462b-ac45-ab3d538284f5 | checkpoint | 2.3 Bedding
73c9f0d8-b0bb-5508-81fc-60e8ae3c0a0f | note | FREQUENCY: Each lot
b2ce27e0-5219-5f2d-b51f-57e4b990dd9d | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
7f2bc204-3460-5ca9-bcda-a544d15b1647 | note | REFERENCE DOCUMENTS: STD T9021A
0687c0d7-ff21-519f-8601-7c9730189f4e | note | INSPECTION/TEST METHOD: Visual inspection
a2edf9f4-6b0c-5c5b-9eba-b35fd6d744bc | note | RECORD OF CONFORMITY: This ITP signed off
ad361632-a777-5d09-bc13-2b473ab9bef6 | note | IP
c32c9e71-a5da-5238-8370-7f0395f44ee7 | note | RESPONSIBILITY: Fulton Hogan Engineer
fd377ac5-3462-58d7-9325-b7c7059a283e | textbox | Date Completed:
038769a5-34f1-4317-9f47-f4cbcb11d8f1 | checkpoint | 2.4 Joining
a94f0cdc-9b05-5d9b-a208-2de8953bacac | note | FREQUENCY: Each lot
79f92300-c431-5b2d-880b-2d0916abf8dc | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends. UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
4b4afdd1-c36b-54d7-8dc5-1fcad749e3f4 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
a5b02335-b8ab-5e24-ae7a-edabbf4aa38c | note | INSPECTION/TEST METHOD: Verify
e3c9e811-2635-515f-b699-d5f5f7fc6df6 | note | RECORD OF CONFORMITY: This ITP signed off
0a1eb945-08ac-5d4d-8419-b374df341353 | note | IP
b7ee8190-0104-5e7d-9f61-fe91f31e1f6a | note | RESPONSIBILITY: Fulton Hogan Engineer
bcdf340a-0c97-5499-bcf1-73c35e1d851c | textbox | Date Completed:
7404b6b8-f380-44b6-8893-86e9ae3d5771 | checkpoint | 2.5 Track Drain Installation
bcb9e419-0c30-58e2-a589-911be6f63c8a | note | FREQUENCY: Each Lot
60775f54-b8b5-5e44-9f11-378cdc08e3fb | note | ACCEPTANCE CRITERIA: Track drains shall be welded to designated positions, and cleaned of all weld splatter . Weld shall be sealed after installation Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
af44239c-bc5a-5595-8463-f5e0465063f1 | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
17397136-4493-5a90-863b-4cc6073c7c5a | note | INSPECTION/TEST METHOD: Visual inspection
40d3ddd1-703b-5466-8cc0-e9748af75f69 | note | RECORD OF CONFORMITY: This ITP signed off
7712113a-ee3e-5cc8-ae7d-fc28660963f4 | note | IP
cff7c239-1375-5488-889d-acbc26e26f4a | note | RESPONSIBILITY: Fulton Hogan Engineer
04e22a8e-dbe6-5ea4-af6c-61d4fa3f8460 | textbox | Date Completed:
85285304-8566-4134-a131-ff0b566340b7 | checkpoint | 2.6 Points Drainage
fbd7ddc6-4b76-5d56-939b-a9497f761e8b | note | FREQUENCY: Where required
4fccfa6e-7221-5447-a2aa-4b4ffe8e22a7 | note | ACCEPTANCE CRITERIA: The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit. Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
8e137636-5107-5c62-8a9b-b5840eaa00b6 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304 STD T0305
fc87165e-8a07-53a6-a3a0-a3c04a4b3b6a | note | INSPECTION/TEST METHOD: Visual inspection
6d521cb0-cc98-5d40-b5de-d8192ef268ad | note | RECORD OF CONFORMITY: This ITP signed off
8e64e7f8-a85b-5db2-9a34-6f6d5a717f80 | note | IP
aef69ae8-9e63-59b0-a6f4-2a0837003fd7 | note | RESPONSIBILITY: Fulton Hogan Engineer
62b33a48-1ead-5979-b570-1158f4a4ff71 | textbox | Date Completed:
3a851b00-e731-45bc-84ec-31257adfb249 | checkpoint | 2.7 Concrete Pour
b0f20b78-72e1-5c15-b42c-20412d0cdc86 | note | FREQUENCY: Each Lot
5b83efcd-c52c-5e90-a3ce-8e2e42be8687 | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
a91e4d76-8c95-5912-a0e3-137ceaad966d | note | REFERENCE DOCUMENTS: STD T9021A
ba9b49a0-0288-577a-a42d-1ba812e56b5f | note | INSPECTION/TEST METHOD: Visual inspection
7de4930a-a1f4-5d1c-9d6e-829361583ee6 | note | RECORD OF CONFORMITY: This ITP Signed off
5d59bb42-4d3c-573a-97bf-b143f9e147d1 | note | IP
20ca46b3-6049-5f3c-8e6b-06ff285f9fd4 | note | RESPONSIBILITY: Fulton Hogan Engineer
635780ce-b909-5130-b541-a1e26f8c15fd | textbox | Date Completed:
8d012a0c-1f5e-4070-be78-d5e006f4ff97 | checkpoint | 2.8 Connection to local drainage
305ef7df-44af-5943-a00a-71b7279fa183 | note | FREQUENCY: Each Lot
cd115ee8-3add-5d8f-abd0-e570dc7d2a7e | note | ACCEPTANCE CRITERIA: Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority. The minimum pipe size shall be 150 mm.
cae01919-f869-5ebc-8777-eca12e7fe323 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
d79f1177-d76d-50df-8fd4-49977bd413b3 | note | INSPECTION/TEST METHOD: Visual inspection
2ac641e7-770a-5b33-9f41-0431d6fd0644 | note | RECORD OF CONFORMITY: This ITP Signed off
6bda4e3c-2d2e-584e-bb67-b8d1c8e77017 | note | IP
8c4fc595-790b-578a-aefc-5aaedb4a854c | note | RESPONSIBILITY: Fulton Hogan Engineer
087dcad1-d2f7-503d-971e-45f7e1db9f50 | textbox | Date Completed:
81b2f811-b347-4215-b94a-a67a53782d71 | checkpoint | Final Inspection
1bbceff5-f8d0-58c7-b622-91d67342ba2a | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
9cb10ab5-7b2a-5756-b173-077872aa5869 | textbox | Print Name:
23931154-332b-5613-8fa5-5dee83d1ee32 | textbox | Position:
965abdee-ad61-53de-b310-88c0839c6fad | textbox | Date:
727b69dd-b616-4163-8bb7-fdb597ea07f9 | checklist | ITP-006 - Track Placement Rev2 |  | ITP-006 - Track Placement Rev2
8880267c-a095-471a-9fb2-b5e410d97e74 | section | Preliminary Works
e401a622-281f-4b4e-a278-206d8a46ec72 | checkpoint | 1.1 - Check for Correct Documentation
cd29fb98-d34a-5d83-b67d-d4b33fd61046 | note | FREQUENCY: Prior to Commencing Works
964c440f-9bf0-529d-ab9e-4b6375494ce2 | note | ACCEPTANCE CRITERIA: •Ensure that all employees and contractors are using the most current and complete set of drawings
405f74cc-26c0-500b-9a62-a6d76810e729 | note | REFERENCE DOCUMENTS: Design Drawings and Register
9be3e37c-2c3c-5298-a0d9-a3c7a29c436f | note | INSPECTION/TEST METHOD: Visual Inspection
7e901ad5-b7d5-5a50-9e29-46bca7e72f31 | note | RECORD OF CONFORMITY: This ITP Signed Off
5e815861-37d7-5c6e-939c-d242661bbe85 | note | HP*
2f70d30f-0345-57bf-9c7b-f1fcdedcf44e | note | RESPONSIBILITY: Fulton Hogan Engineer
4b6c2314-b0cd-5349-b3b6-5602885559ee | textbox | Date Completed:
1b3976e9-5c71-4580-8c72-4d69ccb4ebbd | checkpoint | 1.2 - Check Materials
0b610a55-6723-5063-ba69-5697cf1f2c1c | note | FREQUENCY: Prior to Commencing Works
b657224c-619e-5f44-bec6-1095da352f2a | note | ACCEPTANCE CRITERIA: •Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used •Check condition of rail sleepers •Ensure rail jewellery is of sound condition
18386822-fe52-574d-b598-9e655687d446 | note | REFERENCE DOCUMENTS: AS 1085
78c574ce-6411-5123-91d2-7ac4a0cd74cf | note | INSPECTION/TEST METHOD: Visual Inspection
bb98e93b-fd93-579d-aa19-36096a3c1725 | note | RECORD OF CONFORMITY: This ITP Signed Off
7646fd20-86a1-5f5b-a71d-a98158afd41e | note | HP*
e599347c-b5a8-5639-84ee-c52ae83a24f4 | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
1874dca2-92d8-5d96-a892-6df537bf2f87 | textbox | Date Completed:
9ae86133-3c7b-49cd-a026-3dd54cc2e735 | checkpoint | 1.3 - Check Special Works Components
a05837b8-43de-57b7-ac96-144b1856913b | note | FREQUENCY: Prior to Commencing Works
474de2ce-c6c3-569d-b155-ada77142232b | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending. Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and separate rails. Superintendent to visit yard for initial inspection of the rail and fabrication plans.
25046c45-97b8-5a97-b1ee-b253816a8033 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
b4848578-6b52-5c59-9df4-81ef37018436 | note | INSPECTION/TEST METHOD: Verify
25358b36-35b1-59ad-a490-44c8057f65d8 | note | RECORD OF CONFORMITY: This ITP Signed Off
8eb15827-921f-5dec-b7f7-eb437cedee9f | note | IP
818b6dfc-fe63-5a0a-b5b6-f33114de415d | note | RESPONSIBILITY: Fulton Hogan Engineer
44ba37d0-09b1-519d-93a2-de488331cdd0 | textbox | Date Completed:
cab3bb1f-fe3c-4b73-bb11-11ba60f7af89 | checkpoint | 1.4 - Check Curved rail
d8d9ede7-59eb-5144-98d8-cbe9133fec94 | note | FREQUENCY: Prior to Commencing Works
17560a09-b7af-547d-82d4-fd31a8cb2a60 | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent. Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails. This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
5624175d-8b13-5288-93ad-2f6c5bdd1acf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
46f3f00a-f241-5e4f-b4ed-652e53db778c | note | INSPECTION/TEST METHOD: Verify
796e8825-225f-582b-a9fc-425c8a2a5d81 | note | RECORD OF CONFORMITY: This ITP Signed Off
c7b53874-548f-583c-a6e3-dd5cf9394af8 | note | HP*
314dfd77-d240-5839-b3bc-5341e0ab6949 | note | RESPONSIBILITY: Fulton Hogan Engineer
67209292-68cf-5abd-a0b1-5a80e5fd6d81 | textbox | Date Completed:
19d593a2-92c3-4796-a9c8-785fda0b5d29 | checkpoint | 1.5 - Welders Qualifications
e0e7d274-1fbc-5dd5-bf85-2fcdac646c56 | note | FREQUENCY: Prior to Commencing Works
64b0e2a3-5dd5-5ac2-b0a1-0981e4732c06 | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements; TLIW2012 Grind Rails TLIW3015 Weld Rails using Aluminothermic welding process TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
ea8adda3-63fb-5f59-ad0c-e4fd4349e786 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
6890baf7-b1db-52ae-8fc6-b3f084f8c88f | note | INSPECTION/TEST METHOD: Verify
80539802-dd39-52b5-9440-2328a95d320d | note | RECORD OF CONFORMITY: This ITP Signed Off
e8af5b79-190d-5f0a-acf8-878b8da4d60b | note | HP*
cfbe0754-e9ad-52b6-bbd6-d7292f8a052d | note | RESPONSIBILITY: Fulton Hogan Engineer
2d492f74-22fb-5fe6-ba5e-fb6e232c3bed | textbox | Date Completed:
4899bd3e-4728-49c9-8db7-10e7744c7ff7 | checkpoint | 1.6 - Ultrasonic Testers Qualifications
7d7a4e2f-26d7-576a-8eb5-abd6c83ee16a | note | FREQUENCY: Prior to Commencing Works
d8971465-e451-51fc-a459-5ee5ffa29b04 | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
1acb5bff-9e9d-5b6c-98d2-98c331de6e63 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
ebf347c9-33c6-59f1-8ddf-6c8cba71d1ef | note | INSPECTION/TEST METHOD: Verify
a4002dbf-9600-5737-a9ce-b8fe15253f85 | note | RECORD OF CONFORMITY: This ITP Signed Off
f2cc989a-cf12-5e51-b397-f481d693eae9 | note | HP*
3ef36531-d56e-5233-b8ef-1f6c0c3a9805 | note | RESPONSIBILITY: Fulton Hogan Engineer
a7d57174-9100-572b-aedf-8b48a3c2fbf9 | textbox | Date Completed:
ea49d8ff-41bb-4887-9557-ee411727a6cc | section | Construction Works
82a6623f-ead1-4f57-ba2e-5a17767688c1 | checkpoint | 2.1 - Installation of Sleeper
1af28c5d-5e85-5392-a3f2-7276b93771bd | note | FREQUENCY: Each Lot
96620156-a6c6-587b-abb8-5d8d6e3dc570 | note | ACCEPTANCE CRITERIA: •Dual block sleepers shall be installed at 700mm intervals, tolerance of +/- 50mm in placement •Dual block sleepers shall also comply with the design offsets at each chainage
d3bf5394-99c9-5011-8a1a-320c0bb233f6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
9e0723eb-45ae-59b3-bf47-728921b20db9 | note | INSPECTION/TEST METHOD: Visual Inspection
f8b5bc31-fbe2-5f96-b851-21ce47bac4e3 | note | RECORD OF CONFORMITY: This ITP Signed Off
dac7d3ee-aedc-5d75-8c93-5f1db2c2060d | note | IP
78caf6b1-d1d2-5794-84ca-c72246a12d9c | note | RESPONSIBILITY: Fulton Hogan Engineer
1ecc71d6-3820-5fa4-945d-82e6938ca330 | textbox | Date Completed:
b4313002-f592-46d8-bc80-c2fb194a402b | checkpoint | 2.2 - Placement of Rail
9e4882f9-95ed-576b-beb8-91423a4fe3da | note | FREQUENCY: Each Lot
81de4f35-0ec9-5fb4-b614-e440666d6b93 | note | ACCEPTANCE CRITERIA: •Ensure rail strings conform to rail plan
de65fa73-6f41-5de3-a756-9ad7b20704b0 | note | All track work, including points and crossings shall conform to alignment, offset, level and Can't as per design drawings and track charts
981ab85f-0749-51e4-9ac7-c2ace21994fd | note | •Bottom of rail and bearing surface shall be clean of foreign materials before laying
8fb10fb9-bdb0-586f-831d-7cac9c404e76 | note | •Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
19405d0b-67d1-5d59-8bab-27667942c77f | note | •Geometry tolerances as follows:
98fc0d85-612b-5263-b8ed-74652c7cd131 | note | - Centreline location: +/- 3mm
a7d4cfe0-8cec-5cce-90b6-de3bf1d4dce2 | note | - Level: +/- 3mm
16e1e851-1d87-56e2-86dd-366c0b925470 | note | - Line measured (>10m chord): +/- 3mm
431c5373-d5c1-5bbd-90d0-e3a09db40aa8 | note | - Twist (3.5m chord): +/- 2mm
7c96322b-25e7-5583-9442-b2b336132a45 | note | - Can't: +/- 3mm
d05bf438-e2ac-5f32-a190-9b9d12c17657 | note | - Gauge (open track): +3mm, -0mm
4c40abc0-c672-5baf-8a0a-33cac251b69e | note | -Gauge,Turnouts (opposite crossings):+2, -0mm
21e310b6-d87c-5063-b917-a002df5a8c3d | note | -Gauge, Diamonds and ‘H’ Crossings:+2, -0mm Note: Can't shall be applied uniformly over transitions
20e6cb06-1ef9-5f6c-9023-688f9e9c4111 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
ba0b22f6-106a-553f-aadc-f14711e8b518 | note | INSPECTION/TEST METHOD: Visual Inspection
2da2726e-2a7f-5618-a421-49359cde75dc | note | RECORD OF CONFORMITY: Completion of track charts
12d24ea5-3bd5-5a03-8140-e32dc1fd656d | note | HP*
17b2e038-7a96-5e65-9806-c142ddad861f | note | RESPONSIBILITY: Fulton Hogan Engineer
5e78a8a8-8835-58ce-9dc0-86c8a823770e | textbox | Date Completed:
b5d082f9-a636-44be-93df-66f796304f70 | checkpoint | 2.3 - Placement of Jewellery
db7ec983-05bd-5369-9920-18ed1f278787 | note | FREQUENCY: Each Lot
494eed0f-a9df-5deb-8dc1-32dad77dbf86 | note | ACCEPTANCE CRITERIA: •Each sleeper shall be fastened to track with approved jewellery and rail clips •Clips shall be installed with panpuller or equivalent •All fasteners shall be sealed as per agreed method with Yarra Trams
32f42f5d-e237-535f-b00c-789904d523df | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
bce1160d-b5d9-5515-913b-c9534819b257 | note | INSPECTION/TEST METHOD: Visual Inspection
eb193498-4949-54ae-a77c-36777da14e67 | note | RECORD OF CONFORMITY: This ITP Signed Off
636ee210-c86b-5509-b9e4-02b7982c18e3 | note | WP
9dbb0d67-d5d8-590a-a8d5-60a772a1502a | note | RESPONSIBILITY: Fulton Hogan Engineer
f97de18a-8d57-5b76-bc92-1bdfc0b109f6 | textbox | Date Completed:
110bf15f-1fa5-40bc-b29f-c0e355144d63 | checkpoint | 2.4 - Rail End Preparation
6104b9aa-139b-52c9-b8b2-d11585fe3d39 | note | FREQUENCY: Each Lot
5e2f5c5e-3418-57a7-be92-b75939ed7529 | note | ACCEPTANCE CRITERIA: •Rails shall be saw cut or flame cut •Minimum closure length from proximity of welds shall be 2m •Rail end conditions shall match (i.e flame cut - flame cut)
a2372a8d-9009-5b53-8cf1-5d3c03e14f5e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
8390e013-b665-5b70-bc4a-47baa14d1202 | note | INSPECTION/TEST METHOD: Visual Inspection
732e8c69-ef33-57b4-8578-3d11fecfeafe | note | RECORD OF CONFORMITY: This ITP Signed Off
cacab564-386e-50f7-b663-c2dcd3e8cdb2 | note | WP
cd5d3c55-8e0f-53ae-8bde-f28aac3ec574 | note | RESPONSIBILITY: Fulton Hogan Engineer
44dcc52e-22c2-5f2d-b271-efc15d91e30c | textbox | Date Completed:
cb9bdf51-ed60-406b-b20c-b3d2554ef2ae | checkpoint | 2.5 - Welding of Rail
085ca19e-ee90-5b7a-97da-68ff827dd62a | note | FREQUENCY: Each Weld
03439012-86e6-5fed-9cb7-7adf8df0c8f7 | note | ACCEPTANCE CRITERIA: •Joints shall be square across the track
09e398d6-d71d-54e4-bbc5-b0d624f4cc93 | note | •Maximum skew at square joints shall be 65mm
a47d6280-bb4b-5e8a-94ad-619801d5a930 | note | •Portions shall match rail type (i.e HHR, Ordinary)
1b21b353-c893-50f6-a8c8-dcf5373a6131 | note | •Welds shall not be within:
6a223772-158e-5892-9b7a-03485820596e | note | - 3m of another weld
1a9200c6-f296-5074-8d7f-d2f482b6e837 | note | - 3m of a rail end
d55c108e-8df0-579f-82ad-15d24551d9f4 | note | - 1.5m of a glued insulation joint assembly
979c87d8-47ec-5e19-b4cf-1f492c4d5f09 | note | •Field welds shall be +/- 50mm from centre of bay between sleepers
859ab0a3-f034-5519-b1de-b588eff41ee7 | note | •Weld Return forms shall be completed by qualified welder
51879caf-fd2f-5a94-9d21-b0de4e7c5536 | note | •Welds shall be grinded after 1 hour
b2840a06-bd4a-5e48-8b66-ea6c7acc96c6 | note | •Welds shall be free of water
69ad301a-5480-57f4-91da-cfc0931fdc68 | note | •Post grinding, welds shall be cleaned for visual inspection
77a27b10-9b9f-58fc-adf1-56a8937a0ba4 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
d19dfaa8-fffa-5dd2-b94b-beb24f507615 | note | INSPECTION/TEST METHOD: Visual Inspection
8d27ef80-1755-50a9-838a-161f0a766f2e | note | RECORD OF CONFORMITY: This ITP Signed Off
25f20dd3-680d-56a1-bb6c-766a45cdbff3 | note | TP
8c8a9d11-3b1b-55bb-b9ad-90a3a8e96be2 | note | RESPONSIBILITY: Fulton Hogan Engineer
ae31bbd2-3535-546c-ba33-3e567491aaf0 | textbox | Date Completed:
a8a7e9fa-2d44-4b24-b4da-d6f11661deb3 | checkpoint | 2.6 - Grinding & Cleaning Welds
42f38b73-3bbe-5328-8d15-301b92d305c7 | note | FREQUENCY: Each Weld
fe6226e5-599b-5a1d-b0e6-12f74a3c8320 | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld. Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
f40d88d2-6be6-51b2-a3a6-8a3edac56835 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
8257a3d5-91ea-5dfc-8bdd-adfc68fadbd3 | note | INSPECTION/TEST METHOD: Visual Inspection
3e837ce5-809f-5cbe-8357-864f9418656d | note | RECORD OF CONFORMITY: This ITP Signed Off
f0b9a9b9-3834-506c-91a2-7541746fda5f | note | IP
6be05ff1-c1a5-54dc-b3fe-2d436b2582fb | note | RESPONSIBILITY: Fulton Hogan Engineer
1b206d17-7851-5c0c-8231-36656b8334e2 | textbox | Date Completed:
8e374ad4-0f87-420c-911d-e7553c1fcfb8 | checkpoint | 2.7 - Track Adjustment
d52394ef-6a66-5064-8c70-c3fa92e7f587 | note | FREQUENCY: When required
227a89fc-aa63-5e0c-ad93-557efd7fca8c | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with an approved type of thermometer. In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep. Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
6b2dbab1-ddf0-522e-ad2b-c951b4e60017 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
7040af63-aeca-5e47-9d60-df450cc0663f | note | INSPECTION/TEST METHOD: Visual Inspection
82adc131-930c-58d4-892c-96e7167efc2b | note | RECORD OF CONFORMITY: This ITP Signed Off
5f587d22-36af-51ec-a184-1d25812a01e0 | note | IP
6ea11ca1-f9cf-515e-ae37-7dd760b43d07 | note | RESPONSIBILITY: Fulton Hogan Engineer
7d27f81b-26c7-5941-9008-ec501bbeb88f | textbox | Date Completed:
14cb2c02-5d84-4580-bba0-3f7c6409b65e | checkpoint | 2.8 - Track Bonds
5975dd3b-dec2-57c0-80c9-ae1b7f325f87 | note | FREQUENCY: Each Lot
5de95e3d-1f67-5565-a032-d12dc4ef76b6 | note | ACCEPTANCE CRITERIA: • Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications • Ensure bonds are sealed as per agreed method with Yarra Trams
9889d286-ae7d-50c0-9991-39ce083f0147 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
9debfd48-fb3e-561c-876e-6619de86e594 | note | INSPECTION/TEST METHOD: Inspection / Test Method
340bbcd5-17a1-5c10-944f-7bb469086b37 | note | RECORD OF CONFORMITY: This ITP Signed Off
adf4ffca-7a9d-50f3-b758-2206898c51ef | note | IP
0a8c29c6-b981-55d8-966d-85f05ecb592a | note | RESPONSIBILITY: Fulton Hogan Engineer
0a8cb9a4-9751-5404-a367-f625d5b1c4ed | textbox | Date Completed:
013a36bf-2ef1-4221-9de6-0b766c041b65 | section | Testing
e71cf6f0-3c03-4d02-ba35-4c297feda1e7 | checkpoint | 3.1 - Track Testing
f82612f6-b828-58a6-ad21-bb1c2e8f9a35 | note | FREQUENCY: Each Weld
8e013ac7-2c48-5646-a49c-f7a20c4f2144 | note | ACCEPTANCE CRITERIA: • All welds shall be tested by qualified NDT operator • Failed welds shall be cut out and replaced • Testing documentation shall be recorded and supplied to the superintendent
c3ddcd00-283b-5c3c-a779-6700f7f6fe9e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
af6273d3-11e0-51d7-928a-642776e445ea | note | INSPECTION/TEST METHOD: Inspection / Test Method
3df59ac5-37a3-5a51-bdcf-4ea290a0d340 | note | RECORD OF CONFORMITY: This ITP Signed Off
13bdb075-0886-5f92-a4f9-222340b31820 | note | TP
1102627a-fe53-5a67-9460-6bbc450d6eb3 | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
8960344a-fe92-5e6d-8ab2-73512c63d8fb | textbox | Date Completed:
c512471f-d2df-4b17-a9b7-d22552ce20ae | checkpoint | Final Inspection
6699681f-4c7a-5d96-9484-aef0f57c74e6 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f843731e-d52c-5835-a89d-28823de89ec9 | textbox | Print Name:
01296558-d969-5629-b097-9b16dbf63a4b | textbox | Position:
55e7840c-1f26-51a5-bbda-17567ffd309c | textbox | Date:
1ce6797f-d51e-4033-9607-d5923e46636c | checklist | ITP-007 - Concrete Track Slab Pour Rev2 |  | ITP-007 - Concrete Track Slab Pour
7573ddb6-51e4-4823-a3b1-1525b3f16f5f | section | Preliminary Works
95f4a151-8f9c-4ae3-baa9-5d62264affa6 | checkpoint | 1.1 - Check for correct documentation
ee857424-c0fb-538e-9f68-ac109d69fae2 | note | FREQUENCY: Prior to commencing any activity
df932296-2db0-550e-93ae-de804f34ba07 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
667f2216-43f3-54f3-b6a0-dc9bc4e425fe | note | - using the correct and complete set of drawings
280cc5bb-df7f-5b6c-9571-6d2989b9d460 | note | -all drawings are the latest revision
09b20c06-7140-5799-beb5-d3b19bfb8d0a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
7c7c3d8b-a184-5db6-a0a7-c50cd53ee161 | note | INSPECTION/TEST METHOD: Visual inspection
9cab7367-16df-52bc-8412-e8fc3db44066 | note | RECORD OF CONFORMITY: This ITP signed off
e2a570ba-2c5e-5b2f-8874-6069489c9f4b | note | HP*
1ba1ce18-77b8-503b-a515-a354ae2a7721 | note | RESPONSIBILITY: Fulton Hogan Engineer
c64fe870-941d-5743-8757-87fa80de2f78 | textbox | Date Completed:
b74895e9-1c0a-4413-8fe2-39f1007662a1 | checkpoint | 1.2 - Submission & Approval of Concrete Mix Design Prior to Commencement of Project
ff5b598d-4a85-5fe2-9675-943fc266d23f | note | FREQUENCY: Prior to first concrete pour
96b80d78-31d4-5f4c-a98f-e5c8695239b9 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
67137bfe-d298-5930-b25a-63052b392f41 | note | Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
722fef58-1b6a-5b00-8ad8-d3973623aa4a | note | Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
6752e1da-5584-56f9-8121-b04b8350c669 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
b100e7d1-1c41-5759-b4de-69fc8b8302bd | note | INSPECTION/TEST METHOD: Verify
2b063d62-76b9-596d-b6e7-139cdb3d6165 | note | RECORD OF CONFORMITY: Mix Design ITP
abfd35c4-34cc-5f79-bdd2-f3d5b0dc192a | note | HP*
0bf96026-6b55-5bb8-b787-af69bf130beb | note | RESPONSIBILITY: FH Engineer / Superintendent
515c8055-41fa-5e2d-a6de-d35cc164a2ce | textbox | Date Completed:
285581b7-4bd3-4240-8dac-82e6f3592690 | section | Construction Works
077e157d-05f0-4cbf-bb61-f5183db8a93c | checkpoint | 2.1 - Weather Monitoring
9b81781f-b0ec-5c27-86f9-8dc8974c5913 | note | FREQUENCY: Prior to start
59055cb9-0c5e-57b6-9141-8b765e0f1ef7 | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
be58d2ab-671f-525f-93b5-dfd05415f689 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
27fd0530-f40f-57ae-90aa-f8ca57f2627c | note | INSPECTION/TEST METHOD: Verify
37d938f4-3c87-543c-9215-3aa10d512b4c | note | RECORD OF CONFORMITY: This ITP signed off
682d2c61-dcc2-5c6c-bcfd-9e7f686e467e | note | HP
173ddbfd-e7bb-5357-816c-fa1b14570cea | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
709dd92a-1d37-53aa-b867-0a96d68804e4 | textbox | Date Completed:
cdb9a3fc-2b16-4d57-a1a8-db02cdef6a06 | signoff | Authority holdpoint
81c139af-a909-421f-b89a-30809d6f4564 | checkpoint | 2.2 - Surface Preparation
55d84d11-2861-5384-aee4-eecee09a62ab | note | FREQUENCY: Prior to start
346afd86-0f65-519d-ab61-2ec80e8a2820 | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thoroughly cleaned of all foreign and loose matter prior to pour
6a58cbc9-82c0-5090-9109-c3ee90082332 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
c49010e5-41b0-514f-80af-368a00ec17f3 | note | INSPECTION/TEST METHOD: Verify
dd742909-cee2-5d20-81eb-9f3fa0a01faa | note | RECORD OF CONFORMITY: This ITP signed off
636dce9e-7f3b-539d-bf18-29dac39b82cd | note | IP
59ae8e94-f00b-5a41-8909-c0c9ab87e715 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
23269c63-10e9-5332-a6ab-88b523c8b1f6 | textbox | Date Completed:
bacc303b-97ab-4a91-8a07-e5d28b68c8eb | checkpoint | 2.3 - Setting Out
88bac1e6-6379-50e9-8e62-d5bcdd126fe1 | note | FREQUENCY: Prior to start
5b847524-8eed-5288-a2d6-c062dc3596a4 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications. No survey/level pegs to be removed by any persons until completion of works.
c97d97a1-87a5-5947-9070-5ea26aa91a70 | note | Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
fcf77c11-eb57-5edb-b3f5-ba355a618de9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
3f132706-6d2f-513b-b2ad-5312fe152b08 | note | INSPECTION/TEST METHOD: Verify
2923c12d-8d2f-558c-a122-a4875ee3a04a | note | RECORD OF CONFORMITY: This ITP signed off
149b7d97-87f6-52d9-ace8-f04d4ed80062 | note | IP
bac245a9-264f-545c-82c7-1faff91d7395 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
7b1e6a40-043a-53b3-a7ff-a04c9626d75f | textbox | Date Completed:
afcdcadb-cf75-45d6-8dd7-2e7ee849dbcb | checkpoint | 2.4 - Formwork
dc92854c-cce3-55fc-adc8-3893dc98d871 | note | FREQUENCY: Prior to start
f99bb01d-d5d7-5dbb-aa06-9b63aa4f93a8 | note | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
e4575ac9-c560-5ec1-b628-c9dc42c2bacb | note | The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
0e3d0a05-828d-5443-a2e4-3ba857914cc0 | note | Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
785e66be-b1c4-54e5-b182-77b42835632e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
de7db1d9-7358-56f0-b3d8-0bf85a6a7f16 | note | INSPECTION/TEST METHOD: Verify
8c36e20d-cad7-57d5-8f86-83946eb61369 | note | RECORD OF CONFORMITY: This ITP signed off
6a4ba589-dd7a-5eec-9ab6-79275642de07 | note | WP
2cb850d7-5029-5829-ab94-11e2d44c9361 | note | RESPONSIBILITY: Fulton Hogan Engineer
34619dad-c35f-5b42-a9ac-fde25f581172 | textbox | Date Completed:
227f7cb0-a882-403b-b85b-c814e91bc347 | checkpoint | 2.5 - Reinforcement
fed8968b-ec9b-5fd3-97b5-64fdae48896c | note | FREQUENCY: Where Required
57500128-42c5-5782-a50c-fa651eb83896 | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
8e57bb31-1c5a-5e0b-b2e7-608e43197f89 | note | All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
f8042961-c72d-5f0c-9610-fbf49417b412 | note | Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and ied with wire at a maximum spacing of 500 mm.
5c9d6253-e208-5419-a9a4-5982ac1af5e7 | note | Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
53b6c89c-9d28-5e9d-8bfe-44e9129b7857 | note | Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
52de4106-4316-5729-b49b-71a3b0118468 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
bbc4abbe-5752-55fe-92dc-80b2641fa87b | note | INSPECTION/TEST METHOD: Verify
00277aa0-f849-5f09-b213-313a785413dd | note | RECORD OF CONFORMITY: This ITP signed off
7a69909d-9a27-564a-a2e9-120cc9744aab | note | IP
ec132ec0-988b-552a-829b-06f896cfaa72 | note | RESPONSIBILITY: Fulton Hogan Engineer
2ba1e866-0ed2-5976-bcca-dc9073e7d57d | textbox | Date Completed:
b99e4786-f44a-4073-8cec-6b06962c6d91 | checkpoint | 2.6 - Dowels
86f62947-55cf-5c24-bf41-2ad02ab7ab62 | note | FREQUENCY: Where Required
ad65bc98-efc3-5b94-b6f7-59af1ef28bff | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
1e3cc1b0-47dd-5403-8007-5bee65de76c5 | note | All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
a0566b04-6102-596e-b857-ffde4e0b3d86 | note | Dowels shall be clean and free from mill scale, loose rust or oil.
2810edff-3e7a-559f-b14a-22ce80d7111e | note | Ensure that all dowels are securely held in their correct position until the concrete has set.
52e4c036-868c-5c2f-a190-d5bce12e2610 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
ff0f2061-49f9-5ec1-8a90-02aacabbd8c5 | note | INSPECTION/TEST METHOD: Verify
6a6ce224-a5d7-5256-9738-6e704cc89d85 | note | RECORD OF CONFORMITY: This ITP signed off
407c16c9-735a-55a3-ae5b-f6309ba12de7 | note | IP
9a3a64ad-18d8-537e-8a15-28ec6425b0f3 | note | RESPONSIBILITY: Fulton Hogan Engineer
1b516b76-2e40-5ba6-b071-27f22884b08e | textbox | Date Completed:
c35ff610-a18d-4607-ba58-049848f0c7d5 | checkpoint | 2.7 - Pre Pour Inspection
de203b85-5c77-5ce8-89c6-6ea1d68e6453 | note | FREQUENCY: Prior to start
c0038681-3e78-5172-8b46-f4d1fd8f0631 | note | ACCEPTANCE CRITERIA: • Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180degree difference in gauge placement
c1124da6-e29a-5126-a8ed-20ccaaf43ab2 | note | Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
b42dab07-a8ca-5956-b377-b1625f874104 | note | Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
0d9f4777-c629-5b19-b3c4-66df6083016d | note | REFERENCE DOCUMENTS: CE-019-ST-0033
4ecc14e3-8935-5bfd-bfb1-1dc581703433 | note | INSPECTION/TEST METHOD: Inspection / Test Method
ae292319-e7e1-534b-9d0e-3588dd80850a | note | RECORD OF CONFORMITY: FH Track Inspection
453f01ad-c13a-51f8-9632-be2e6dcd1d99 | note | HP
c9856493-ae69-504c-bdc6-c38a92b98885 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
e8a3d328-941e-5c36-ad1c-27f42893ad70 | textbox | Date Completed:
dbbdf0fc-eb6e-4fd7-8968-94a2eedb6049 | signoff | Authority holdpoint
a2488d4f-f070-441f-b37f-0cca5d9c6fcc | checkpoint | 2.8 - Carry out sampling of concrete
99c66ec4-33a9-5770-8143-744c9f37199f | note | FREQUENCY: Each concrete pour
65686a19-5707-5b89-95a0-7bc137055684 | note | ACCEPTANCE CRITERIA: Slump:
57ef3a76-e9a3-5914-9352-74fd4b35e6fd | note | Concrete Slump shall be 75mm +/-20
ee5ee354-280c-506b-b24c-b4020872d612 | note | Compressive Strength:
1f54b83e-ae63-5ee6-92a1-3dabebf9b309 | note | Shall be measured in accordance with CE-019-ST- 0033
6d5429ea-44d6-5687-99c1-5de7c591fafb | note | • Testing frequency =
3b7fe8c1-80f0-5c86-ae7d-8b1801d24e15 | note | - 0-50m3, 1 sample
c401e829-1f36-50dc-bc4f-63075430e43b | note | - 50-100m3, 2 samples
dc32b76c-6750-502c-9438-d530dcae6383 | note | - 100m3 +, 3 samples
9c184d68-620a-55e7-be13-fae9627e379c | note | Each sample shall consist of 4 cylinders
c7c36110-b17b-5851-b662-e28ef124a17f | note | Test Results will be provided to the Superintendent
0a7326b7-dcb5-5035-a33a-0f99ab7b8361 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
2bc27874-6ef5-5482-9d5e-0890f15b8219 | note | INSPECTION/TEST METHOD: Verify
7b577220-9dc0-5802-95e3-6b79df573a86 | note | RECORD OF CONFORMITY: Concrete supplier test sheet
c45af8e7-a824-5ce1-85e8-fd33df8a5ceb | note | TP
20cc6289-d26f-507e-bffc-5f3b3e0d3000 | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendent
9c3b0335-8145-5073-ae07-5914f3e100a9 | textbox | Date Completed:
1fb87705-8d95-4ce6-8c42-11de6e92264a | checkpoint | 2.9 - Concrete Placement
b27d8f08-e2ce-5579-abc1-22502136fef2 | note | FREQUENCY: Each Lot
a2583a0a-6d66-5f5f-840b-0d17acaf5240 | note | ACCEPTANCE CRITERIA: Ensure formwork is clean
7a2b4018-d96d-5435-9234-23c1f82e3527 | note | Concrete shall be entirely discharged 60 minutes after batching,
94ae6b2e-e4ba-5aef-b8d4-939f6e08d06a | note | Ensure that pouring does not occur from a height greater than 1200mm
bd18e3c1-ce6a-5c36-b262-6bb899434a3d | note | Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
ae5dc2a6-41b3-5781-a807-2a1ed1e3b6fb | note | The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage
48854429-7daf-5eff-9b76-7297528a39a2 | note | There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
c2dc1fd6-5271-5df3-b76f-3d0b881192f2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
9e082f55-b5ff-5f44-8bba-4cdd551aa37e | note | INSPECTION/TEST METHOD: Visual Inspection
7c58e271-bd69-5f67-86ff-9bcf155d86b3 | note | RECORD OF CONFORMITY: This ITP signed off
93773ae1-ca10-51bc-b18e-b7499ed68496 | note | WP
10a48503-e40f-5e98-a738-05a64b161972 | note | RESPONSIBILITY: Fulton Hogan Engineer
595bf7b8-8439-5cae-9952-0d133f289b1f | textbox | Date Completed:
9559c3f6-a684-4549-ac56-818fece1d92e | checkpoint | 2.10 - Compaction
89cf7682-5439-5166-aff1-854b54d2f8ef | note | FREQUENCY: Each Lot
e6fbcb0f-9c1b-5f59-bb68-6179a22c6bd6 | note | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator
cdfdcb50-af60-5255-8224-e19d30366214 | note | Vibration shall take place until exposed concrete surface is free from air voids
9e17ef20-dc8a-5aeb-8487-bd043006e616 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
9f2c99ba-7590-557c-8430-673ac7e7ce5f | note | INSPECTION/TEST METHOD: Visual inspection
e2f3469e-9f67-5033-95b1-7a4094433224 | note | RECORD OF CONFORMITY: This ITP signed off
c6f2dc56-00f1-5a3a-aaab-56372a0aeeab | note | IP
aaf0f5e0-c8d9-593b-b7ba-43aaef90b1bd | note | RESPONSIBILITY: Fulton Hogan Engineer
145ff878-eef1-5dad-b0e9-b6fb390a3d25 | textbox | Date Completed:
1a0b6e06-10b6-4f93-bc5f-7e57634e7891 | checkpoint | 2.11 - Record location of each batch
ac5a70bf-b8a8-5326-bc88-8fa75edbd284 | note | FREQUENCY: Each concrete pour
ed1f0d35-040e-56ee-8dbd-4d6c54469f45 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
ed5cdaac-b529-5a01-9331-7e5413c0abce | note | REFERENCE DOCUMENTS: CE-019-ST-0033
d11e68a8-6bf8-5ac5-a917-1644ff3a9d3e | note | INSPECTION/TEST METHOD: Checklist
be03f9c8-e730-5227-a432-6016d190a0e6 | note | RECORD OF CONFORMITY: This ITP signed off
1a3467fe-58c3-51c4-9e87-9eb434cf15ee | note | IP
a0c3f4d3-f6a4-51e5-9ed5-c2dc1236bc7f | note | RESPONSIBILITY: Fulton Hogan Engineer
2e99c1d6-c3c0-5530-a0c2-a6802d7110bd | textbox | Date Completed:
becc21b1-ceb9-4418-aa74-644241e19c24 | checkpoint | 2.12 - Curing
3f8f2d4d-354e-5182-b897-b60e32865cc4 | note | FREQUENCY: Each concrete pour
4729015b-e57e-5c50-ab06-a1e81f4c11c3 | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming
1205bdef-7f37-5324-ba72-9e064244e4e2 | note | Concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (Concrete to surface).
c7cc748e-de7d-59ce-b67f-3714eeb51151 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
4d10fc7d-ad76-57a0-ad4c-d97d55eb7534 | note | INSPECTION/TEST METHOD: Checklist
bbbbf519-c6ce-5522-beee-4e6b0c6bfb00 | note | RECORD OF CONFORMITY: This ITP signed off
e0495389-9f3c-53f3-b39d-1b744b519214 | note | IP
0f5c7335-8ed5-55c9-822a-941bd33c4640 | note | RESPONSIBILITY: Fulton Hogan Engineer
3fccf8a6-8e27-5461-a658-d73212281cee | textbox | Date Completed:
e1306be6-50f6-4dde-a1e5-f90a65680b32 | checkpoint | 2.13 - Tolerances
5d7ac8c6-2daa-5f26-a0c5-19813130b1bd | note | FREQUENCY: Each concrete pour
0e73cf87-17ae-5e55-8f2e-40561a0af132 | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
b8d278a0-d66e-5bb7-8e50-68b4be681fba | note | Plan dimension of slab +10,-10mm
24594932-2d14-5681-975a-4d33369afe96 | note | Thickness of slab +10,-10mm
d0966fdc-fd4e-5acc-aa40-8289626a7ba4 | note | Cover to reinforcement +5,-3mm
a49151c7-37d7-5558-a336-7ffd745f35bb | note | Finished level of slab +3,-3mm
5ce53748-897a-5d74-a6c6-90d853c31636 | note | Foundation level of slab +0,-20mm
77686c58-859f-5516-b0ef-4cff54bb2969 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
2e73a78e-0cf3-591f-b00f-25919afef0a1 | note | INSPECTION/TEST METHOD: Checklist
1a7e3e41-09dd-55e7-9153-deef1b4ed9d3 | note | RECORD OF CONFORMITY: This ITP signed off
0903f12e-0075-5a34-8d15-bc1932e93d64 | note | IP
a1a9b94a-1518-5ea4-954b-ed5c1d79a4de | note | RESPONSIBILITY: Fulton Hogan Engineer
6f6e6220-b363-59e0-ba57-dd430d6e9a1a | textbox | Date Completed:
a0bca0b6-9fa8-4d36-9d6a-a3a9bc4ff942 | checkpoint | 2.14 - Slab finish
d3b36911-b163-52a8-9baa-c1f5f7f43a9f | note | FREQUENCY: Where applicable - if track is Type 1 structure
abc8befb-4ca7-57f5-9474-9a0c31f0212f | note | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities. All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections.
48a2f81c-556a-5be4-91a4-6e833833c8c0 | note | A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C.
c9b3c88b-5322-579f-8c4d-2c072a9458ab | note | The slab surfaces shall be broomed to provide a non- slip finish.
01579e79-f3a1-5660-bb58-004f150e4644 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
87ed8d9b-3b7d-5519-ac73-e39f7d3cb86d | note | INSPECTION/TEST METHOD: Checklist
a1526ff6-5af9-5067-b3ba-ca21fe997d40 | note | RECORD OF CONFORMITY: This ITP signed off
d4bdb06c-342e-50c4-80e4-9c7b6d78975d | note | IP
a1e03b47-f3a6-5145-9c8a-bc28c1f076a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
f0f41690-eafc-5958-93a1-de52182c0dc0 | textbox | Date Completed:
bb8c182e-c8e8-4e0b-9aef-cb20e89cd0ae | checkpoint | 2.15 - Post Pour Inspection
7cc1f174-4ba2-5ab6-b6d3-31e6893fd9ca | note | FREQUENCY: Each Lot
ddae189f-952b-558f-a474-eb2d2b7d10ab | note | ACCEPTANCE CRITERIA: • Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
b43f74ea-e40a-51b9-8a9d-a5896ec00ee0 | note | Ensure no defects are present in slab
0c14ab92-abc3-5d8b-b053-fe9581c071ca | note | Complete Fulton Hogan Post Pour Checklist
43608c17-a3bc-5364-b8bb-3ecf34f13d07 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
57cf9234-707f-5ae1-ae49-4d7a10d85bb5 | note | INSPECTION/TEST METHOD: Visual Inspection
02fa2d51-8844-528c-9d45-e27dc9d7c8d4 | note | RECORD OF CONFORMITY: Post pour checklist
5d3ef81b-e998-5d4b-bb79-4303d236a702 | note | IP
00006a23-488a-5239-89bb-6cb62837bff0 | note | RESPONSIBILITY: Fulton Hogan Engineer
2b7741f5-0dfd-5c63-8618-31604700b047 | textbox | Date Completed:
cb652dcf-ad5a-4982-9db4-f0865dbf0643 | checkpoint | Final Inspection
a85b2083-49c9-593c-905c-2d1b35e0cb24 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
03facfaa-e37c-5e08-8a88-8c3c7ab055b5 | textbox | Print Name:
aa29a5da-bd80-5f5c-b6c2-688a457dcfcf | textbox | Position:
bccc0b8b-2322-5347-a8e9-065cce305ec4 | textbox | Date:
ef9adb73-4025-4c46-b76c-9fd74476ae5e | checklist | ITP-009 - Site Survey |  | ITP-009 - Site Survey
27d38ee6-7096-4ac2-a0d6-39853269658e | section | Preliminary Works
958b804e-2684-4468-bef7-5939180f8782 | checkpoint | 1.1 Check for Correct Documentation
ff6ace04-9922-546d-8976-3e06dc5ee2bc | note | FREQUENCY: Prior to Commencing Any Activities
60129060-88e2-5013-8ff1-448c1ec17ca0 | note | ACCEPTANCE CRITERIA: •Ensure that all employees and subcontractors are using the most current and updated complete set of drawings
7e1bbb17-09b5-58ee-9024-bdacb5168d9f | note | REFERENCE DOCUMENTS: Design Drawings and Registers
27c69a3f-4567-5811-9a9a-1ba7e2999558 | note | INSPECTION/TEST METHOD: Visual Inspection
2ac2d28a-8b83-52ef-b5be-fa191013505c | note | RECORD OF CONFORMITY: This ITP Signed off
db8480bc-a597-58b1-ae1a-7d8acc0c0eaf | note | WP
86a70e5d-98c3-5dbd-899d-ce9e77937000 | note | RESPONSIBILITY: Fulton Hogan Engineer
a70d21b5-cceb-550f-99e4-646b8b8f1d95 | textbox | Date Completed:
56b8f698-22bf-46ac-b13d-32951dafca24 | checkpoint | 1.2 Implementation of All Measures and Controls
c1cd39ed-c47a-52fe-a314-dd4a369c79ec | note | FREQUENCY: Prior to Commencing Any Activities
6d5ea1cf-06f6-5c57-b5b8-f3207b68b1a3 | note | ACCEPTANCE CRITERIA: •All necessary measures and controls are implemented, including: SWMS, WP, TMP, EMP, PSP, PMP and QMP
4ea6ee31-211b-5fae-8c7e-810064e214c8 | note | REFERENCE DOCUMENTS: SWMS, WP, TMP, EMP, PSP, PMP, QMP
eeeb9014-3641-5e03-8e56-9c325ea6864b | note | INSPECTION/TEST METHOD: Visual Inspection
93a08f4a-41db-5d26-9b1c-074ef7b7133b | note | RECORD OF CONFORMITY: This ITP Signed off
457921e1-5219-50d8-b6ac-2c6a5ba3527b | note | WP
2715a98e-dabf-5342-869e-0f7b86f95ea3 | note | RESPONSIBILITY: Fulton Hogan Engineer
3796228a-6e73-5600-a5f7-4c947e7d597b | textbox | Date Completed:
71c9df2a-1cf5-4f55-8898-1ace8a255d20 | checkpoint | 1.3 Confirmation of Design Drawings
c7766e33-6cdd-5013-8390-2fc8e141e342 | note | FREQUENCY: Prior to construction activities
a013b26a-5341-5d88-ba78-08a90af967bd | note | ACCEPTANCE CRITERIA: •Surveyor shall validate RL points, kerb, pavement, platform and track dimensions, measurements and levels specified in design drawings based on bench marks and control points specified by superintendent •Superintendent shall be made aware of any discrepancy between design and actual values
eaac8b96-084a-5bfc-8db4-a9e45c241dbc | note | REFERENCE DOCUMENTS: Design Drawings and Registers TS 1313 cl4.2.5
45ceb344-1bf8-51c6-bbd2-cc90944c93dc | note | INSPECTION/TEST METHOD: Verify
02128d6e-618d-5b72-8cd3-1312eb548425 | note | RECORD OF CONFORMITY: This ITP Signed off
8258a5dc-8b3f-59a2-babe-f33d1c7b54e3 | note | HP*
1a5ed7b3-c3c0-57e0-909b-b79c474ee4ac | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
77e89f07-c37c-526e-bf0c-1b3d9533fe77 | textbox | Date Completed:
2febd351-12b5-4af4-94d9-e341bfecfdee | section | Construction Works
89ec485e-d888-469f-917f-68e738907db4 | checkpoint | 2.1 Set Out
778ed5bc-3017-55e6-8370-02eab34ce32a | note | FREQUENCY: Prior to start
33a63fee-2847-533c-8538-c54a0e862ef7 | note | ACCEPTANCE CRITERIA: •Tramway track shall be set out to an accuracy of +/- 3mm, based on bench marks and control points specified by superintendent design drawings
8cb9ba7e-ae21-5a6e-ab91-a8a6a83a3a84 | note | REFERENCE DOCUMENTS: VRIOGS 005.2 Pt1 cl4.0
d521a8f7-4b42-5d8f-ae67-8b95f357bdac | note | INSPECTION/TEST METHOD: Visual Inspection
a87a3f09-3a2b-517c-a64f-ec2e70d8e8cb | note | RECORD OF CONFORMITY: This ITP Signed off
4fa5fdf7-337d-5206-9e00-016933d7a618 | note | IP
bbe692c8-b801-5f56-b645-89e7afdcb770 | note | RESPONSIBILITY: Fulton Hogan Engineer
ce0de9f7-cfba-505f-8584-8eda970eb2b5 | textbox | Date Completed:
2d9a987b-76a2-4856-a98a-cb2bc7586075 | checkpoint | Final Inspection
05f25f34-af5e-594a-a75b-bf1401819c15 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f66262ef-f319-5007-b503-3ead941c7393 | textbox | Print Name:
6591a265-f154-5da5-81e1-8318aa7efc4a | textbox | Position:
6cc3d668-f717-5684-9642-64a5624e2de5 | textbox | Date:
d03f0845-e8cd-47ce-8852-ec86c20aece8 | checklist | ITP-010 - Kirby Welding |  | ITP-010 - Kirby Welding
6ce9e30f-12bc-45cd-9aa0-c09a091c93be | section | Preliminary Works
051f4121-146b-4d86-a108-0be9f86526f4 | checkpoint | 1.1 Check for Correct Documentation
c4135c7d-f290-5049-9631-86d7201e6f4e | note | FREQUENCY: Prior to Commencing Works
ad3b879e-b855-5f56-99a8-13b7e096f41e | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
cdeef963-9471-5f44-8d02-c41b531e3b95 | note | REFERENCE DOCUMENTS: Design Drawings and Register
6de449b4-fb10-5b05-ba4e-a4bc02977b0d | note | INSPECTION/TEST METHOD: Visual Inspection
e50a247c-39a1-553f-848b-0bc66b04ddb4 | note | RECORD OF CONFORMITY: This ITP Signed Off
7e8acf33-25ec-5d0d-8ab1-4c24fce13230 | note | HP*
1d0ca30a-a16f-5f72-b401-a7e636a607eb | note | RESPONSIBILITY: Fulton Hogan Engineer
149c0676-5a9d-5ea8-8273-bf05c5cd6d91 | textbox | Date Completed:
5771f382-d89a-4d14-8e9a-82b6b134021a | checkpoint | 1.2 Welders Qualifications
cfb90772-86e5-541b-8d67-8450eec546ad | note | FREQUENCY: Prior to Commencing Works
f0cce697-1374-5bd6-a950-64e893efa9f7 | note | ACCEPTANCE CRITERIA: Welders shall be trained and qualified for the brand and each type of weld used, e.g. standard gap, long preheat, short preheat, junction etc. Certification shall be provided to and approved by the Superintendent prior to commencement of welding.
00207a98-7ecd-567e-a888-429e8b150190 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C
e77cd084-179f-5674-80ad-e016b96493e2 | note | INSPECTION/TEST METHOD: Verify
fb3c56d2-4f35-5a76-92c1-abccbc18a108 | note | RECORD OF CONFORMITY: This ITP Signed Off
b3f2a0ec-bccc-5d29-8524-816665c1a93d | note | HP*
bb4df4b9-0bd1-5566-ad93-64848a82cf41 | note | RESPONSIBILITY: Fulton Hogan Engineer
afedd8f0-9aa0-59c2-bdc0-e76b2a2bce6d | textbox | Date Completed:
41f3b9be-f7da-43c2-a73f-9d4d28c8b696 | section | Construction Works
b5c2963f-0605-4e1d-84e4-1495201687ff | checkpoint | 2.1 Cutting Rail Ends
f0722c4e-e6e1-5b5c-8e14-f8e50ecf0147 | note | FREQUENCY: Each Weld
4be6dc8d-0666-59b9-a64c-b141b5d6d5b2 | note | ACCEPTANCE CRITERIA: Rail ends shall be saw or friction cut. The cut ends of each rail shall permit butting of the rail heads to within 1 mm across the full head of the rail. The prepared surfaces shall be visually inspected for cracks and reground if any are detected.
11c1640d-f60c-521a-874f-0753f7e36699 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.4.6 & Appendix C
b90a7230-d04d-5b1a-af0c-cda3a6b0cbac | note | INSPECTION/TEST METHOD: Inspect
7a36dbbc-db97-5c81-92f1-bb67330c58b5 | note | RECORD OF CONFORMITY: This ITP Signed Off
0276a335-eec4-5fa7-b0fb-8aff26bedec4 | note | IP
49f547d0-fe16-5599-9c9b-f8ddd084b264 | note | RESPONSIBILITY: Fulton Hogan Engineer
b0b63861-3f55-5156-9a67-7b630c849482 | textbox | Date Completed:
57b8639d-0bc6-431b-b2b3-14a40a05da14 | checkpoint | 2.2 Butting and Aligning Rail Ends
2efc677b-d2d8-5702-8dd5-e3fba854c8af | note | FREQUENCY: Each Weld
8baaaf2a-f69c-5243-9ecb-c8bc6eeed8a9 | note | ACCEPTANCE CRITERIA: Rail ends to be welded shall be butted together as closely as possible, preferably with no gap between rail heads. Care shall be taken to ensure that the rails are not pulled together excessively, forcing the feet of the two rails together and producing a peaked or high joint. Rail ends shall be butted and aligned, and assembled with base plate and spacer blocks, if applicable, prior to commencement of pre-heating.
5f96e2fb-6888-5aec-835e-ca46b76ed0c2 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
8ee5942f-e4c7-5a25-8e84-b5b57ff757e8 | note | INSPECTION/TEST METHOD: Inspect
0e1d7fcb-ce36-5f6d-b1b1-3bbdb179c93f | note | RECORD OF CONFORMITY: This ITP Signed Off
e2fa2f17-147b-52e6-b391-4064b5de6f17 | note | IP
36bd4369-06f9-5086-b685-6d1d3d11623e | note | RESPONSIBILITY: Fulton Hogan Engineer
002c4ff9-619b-5084-81ee-fbf05e1795ab | textbox | Date Completed:
cb88010c-b72e-4a28-85f6-9e8491681ac0 | checkpoint | 2.3 Preheating
6c62c2fe-d42a-5a9e-97d9-5572beb6a080 | note | FREQUENCY: Each Weld
b3eb1232-aea8-57cd-acd3-35420a2a38cf | note | ACCEPTANCE CRITERIA: A correctly adjusted, suitable oxy-LPG pre-heating torch shall be used. The preheating torch shall not be applied closer than 30 mm to the rails being pre-heated. Both sides of each rail end shall be evenly pre-heated from the rail ends to150 mm beyond the rail ends. Pre-heating shall be confined to the top surface of the foot of each rail and to half the height of the web. Preheating shall be such that during welding, the foot and web of the rail shall be at a temperature of between 270°C and 350°C
1a4a7a41-ba0f-5204-8017-19d83a96b559 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 Appendix C
4da2f7ab-9e37-50d4-a862-0f5800769bb9 | note | INSPECTION/TEST METHOD: Inspect
94b02f7c-a747-567d-bc47-3b7fae7de6ce | note | RECORD OF CONFORMITY: This ITP Signed Off
6d9288b0-3412-55c3-9cf7-0344e447054b | note | IP
67418c94-9042-54f6-a518-feb429ea44be | note | RESPONSIBILITY: Fulton Hogan Engineer
81132e57-781b-5205-bf2a-cbcff8314f5d | textbox | Date Completed:
adf58520-86c4-47d1-a243-43a5f4a40ec7 | checkpoint | 2.4 Welding
8f4cc3d2-a15a-518b-9b41-956740ad4ca5 | note | FREQUENCY: Each Weld
1829aff1-1535-5897-8776-d50c66b5017a | note | ACCEPTANCE CRITERIA: Rails and components shall be clamped in position prior to welding. Welding of the joint shall be carried out as a continuous operation. A disruption to the procedure may require additional preheating. All weld ends shall be welded using an overlapping back welding technique over the weld for a minimum length of 20 mm to ensure that all craters are fully filled to the full cross section of the weld.
90fcbbc0-3804-5730-879c-5e8247854d51 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.9 & Appendix C
d9d08cf6-bbca-52d4-b0ea-fab0a1821a3c | note | INSPECTION/TEST METHOD: Verify
332d1979-a0c6-5e73-b709-32ed40318008 | note | RECORD OF CONFORMITY: This ITP Signed Off
b8e0de61-3036-5ade-ac71-a095d76dcdb8 | note | IP
962774ca-7607-56dd-b744-5c514ceaa794 | note | RESPONSIBILITY: Fulton Hogan Engineer
95e02d87-edb1-5bae-8a44-6801b27caa5e | textbox | Date Completed:
caf878d5-2a10-48be-96e6-cc7c32c804a6 | checkpoint | 2.5 Cooling Weld
be7c2430-8121-519c-9176-0d2b514e2c14 | note | FREQUENCY: Each Weld
744989a2-860a-5d48-96a8-2048873e0cf9 | note | ACCEPTANCE CRITERIA: The welded rails shall not be permitted to cool rapidly. Heat blankets shall be used to cover the welded portions of rails (i.e. web and foot on each side of the rail ends. The blankets shall extend a minimum distance of 300 mm beyond the extremities of the welds, i.e. minimum length 900 mm. The heat blanket shall remain in place for a minimum period of 15 minutes after completion of welding.
6a7e27bb-4680-55ad-9d4e-18db254b5370 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.9 & Appendix C
d4390b9d-dc49-54e2-8556-48dc7ff14243 | note | INSPECTION/TEST METHOD: Verify
7f204b56-e8eb-5c93-8177-83f965714724 | note | RECORD OF CONFORMITY: This ITP Signed Off
877bc161-443b-5464-92f0-4387635bf43f | note | IP
8b5d4aa0-58c0-53d1-8b4a-0356b18cb3e0 | note | RESPONSIBILITY: Fulton Hogan Engineer
f72a56f2-77ec-5891-a3a6-f12777ca2c82 | textbox | Date Completed:
c027ee32-7767-46d8-8976-f32f7b3be326 | checkpoint | 2.6 Grinding Weld
b6cbf54e-f1f9-51d9-9946-db15e1d8b585 | note | FREQUENCY: Each Weld
8464a60e-9d86-552f-bba3-7641318a691a | note | ACCEPTANCE CRITERIA: Grinding of the rail head, as applicable, shall be performed only after the rail head has cooled to below 50°C. A rail profile grinder shall be used to grind the rail head weld. A spindle (straight) or disc grinder shall be used to grind the rail check and groove. A 1 m straight edge shall be used while grinding the rail head (wheel running surfaces) to ensure a good straight surface and profile.
7175a633-6788-56ea-ae7e-681b0b57f0f2 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
8a597317-5d3c-5c47-8278-e7d90f64d1c6 | note | INSPECTION/TEST METHOD: Verify
3a4815cb-1c4b-51e4-8933-360072aacf19 | note | RECORD OF CONFORMITY: This ITP Signed Off
d975281f-616d-58b9-8e9d-7fbd653604c3 | note | IP
4e0d9898-d90d-578f-8a71-994e8fc98f2c | note | RESPONSIBILITY: Fulton Hogan Engineer
24c64d01-6b5b-5492-bd39-0e568e1209bc | textbox | Date Completed:
34d1791a-5010-4168-aa9d-ce9e84763fab | checkpoint | 2.7 Flushness of joints
3f8312d4-d8cf-5673-a90b-129972d94155 | note | FREQUENCY: Each Weld
84cb6a30-8bc8-50e2-94a7-9da79d06186b | note | ACCEPTANCE CRITERIA: Misalignment of rail heads on the running and gauge surfaces, due to different amounts of rail wear, shall be rectified by grinding. The slope of transition shall not be greater than 1:25. Misalignments of the groove and check not exceeding 3mm shall be rectified by grinding. The slope in transition shall not be greater than 1:10. Any grinding required to make joints flush shall extend to 500 mm each side of the joint
1ac262bc-c6fd-5c9f-aa4c-6c6cea28f828 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.9.6 & Appendix C
a38b15e8-6693-5608-b52d-ed696ee3a8f2 | note | INSPECTION/TEST METHOD: Verify
59fedffe-b35e-5351-b462-3c69579240fa | note | RECORD OF CONFORMITY: This ITP Signed Off
b9bd3c31-63d9-57fb-82f0-a9190eccca59 | note | IP
c8e29fbd-a43a-536d-8cf1-15c4eb9f61d8 | note | RESPONSIBILITY: Fulton Hogan Engineer
be68efcf-f874-5b48-9ae0-5c03472fd780 | textbox | Date Completed:
6f153477-065b-4671-ac37-2cb8a80467f3 | section | Testing
d9408c89-b47c-4bf2-886c-b4e43a7be02b | checkpoint | 3.1 Weld Review
99a7f5de-dbd8-56ed-9ff7-d183c46bf2d6 | note | FREQUENCY: Each Weld
6676ea1b-79f1-5b7b-8d15-49bc1a1b226e | note | ACCEPTANCE CRITERIA: All welds shall be inspected by the Superintendent & Fulton Hogan Engineer; Unsatisfactory welds shall be cut out and replaced
4fe24971-21f1-584c-b853-e2bbc77dc753 | note | REFERENCE DOCUMENTS: Works Procedure
6540be9c-be9a-52ba-99c2-fd6a965fe788 | note | INSPECTION/TEST METHOD: Inspection
b2a6ae53-e3d5-5de0-94b8-a79ff9ff6ff5 | note | RECORD OF CONFORMITY: This ITP Signed Off
59dd73a0-f399-5e16-9eee-167b3970abd4 | note | TP
2004bc84-3009-5664-9660-1e39b03304ec | note | RESPONSIBILITY: Fulton Hogan Engineer
8ba95dd6-8f3b-5aa9-a18b-7502d08d0c08 | textbox | Date Completed:
1222cb7a-e022-4002-a00a-6b6987c55519 | checklist | ITP-012 - Signage Installation |  | ITP-012 - Signage Installation
a3504402-fb6e-4be1-9968-c9e4dc246c89 | section | Preliminary Works
59218fd9-56ec-447b-b971-319d8263f4f4 | checkpoint | 1.1 Check for correct documentation
5b55b167-d026-501c-8827-496e53cc2c99 | note | FREQUENCY: Prior to commencing any activity
a2bbe5c2-e40a-516b-8d6a-5bd338064f3d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
1dc872bc-603e-5c1f-8c2c-51ab396f3a31 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
d047aa87-a871-54e9-bba3-fbcef3254131 | note | INSPECTION/TEST METHOD: Visual inspection
997f144a-5452-5f6a-8496-46a3f5935a99 | note | RECORD OF CONFORMITY: This ITP signed off
c3ff9d1e-afe6-57f5-9f09-5fb7c9914da2 | note | WP
073c5a2e-9218-5b2e-a926-e7f0815dc495 | note | RESPONSIBILITY: Fulton Hogan Engineer
c246c574-34b4-5aa5-a1a4-0af831e4032f | textbox | Date Completed:
5a9a42c2-574c-49dc-8407-3a1c7c2b823b | checkpoint | 1.2 Implementation of all measures and controls
54d00be6-a510-5435-b05f-ef3b2bf18253 | note | FREQUENCY: Prior to commencing any activity
4451c61c-67b3-5309-bf9d-998b0a8153ee | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
0b24013b-7218-5674-a8b9-d5ddb4ec8cf1 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
35e74f4f-00d5-55c2-9ea8-9fae5c02b358 | note | INSPECTION/TEST METHOD: Visual Inspection
514978bb-6d92-5132-952c-f741fcb0a156 | note | RECORD OF CONFORMITY: This ITP signed off
7a686923-c73a-549b-9038-134e6f733e96 | note | WP
b580089b-ab1a-5576-97b1-86c2a82b4eb3 | note | RESPONSIBILITY: Fulton Hogan Engineer
f1adc6a5-3426-5078-a2f6-954f75314887 | textbox | Date Completed:
ff943067-b05f-430d-86e6-77d43279198e | checkpoint | 1.3 Signage Conformance
d6dfd112-7563-53ee-8ee0-b15d67538f0e | note | FREQUENCY: Before commencement of activity
757d46d8-9e93-5d69-9982-0547b32395a6 | note | ACCEPTANCE CRITERIA: Ensure sign size and image correspond with contract drawings and meets specification
838ef221-7600-57a7-b5e1-afc9721a8221 | note | REFERENCE DOCUMENTS: Drawings AS 1742
da6f0f2a-80a0-563f-8197-093ca535beff | note | INSPECTION/TEST METHOD: Verify
c710acb3-4ef5-50a4-bc63-aa4dd73fad7b | note | RECORD OF CONFORMITY: This ITP signed off
67ffedcb-e52d-5de5-a61d-17ed98f0fc0b | note | WP
2ea98616-5bd9-5484-ade0-860f258b5af3 | note | RESPONSIBILITY: Fulton Hogan Engineer
1aa05846-88a1-5db5-90f4-a3d91d1d4b5f | textbox | Date Completed:
f315cbe4-cfac-4c52-88c4-b0f5a40eb144 | checkpoint | 1.4 Service Identification
d3a40923-9164-54e3-a8be-1127e62894e4 | note | FREQUENCY: Prior to start
2859eaec-d183-5b60-abbb-1971ffaa4507 | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
4921dd9e-fc81-5235-ae02-d9a75879af53 | note | REFERENCE DOCUMENTS: DBYD
a2ca2c7c-6e74-529d-bb4c-98bc0c8513e1 | note | INSPECTION/TEST METHOD: Verify
96810005-6e0c-525b-a740-d4dd959435c5 | note | RECORD OF CONFORMITY: This ITP signed off
0165270b-667e-509e-95e9-15923e4bcebd | note | WP
9c78692b-6fd9-5653-b8ff-89ef15177f05 | note | RESPONSIBILITY: Fulton Hogan Engineer
8548e621-9ed6-5bc4-b52b-76359d87bf4c | textbox | Date Completed:
0442a90f-cd5e-4d48-8c8f-757f335c94a5 | section | Construction Works
f12adca8-db8f-4b1d-a87c-2799d8dc3816 | checkpoint | 2.1 Setting Out
490ef352-e2bb-5f23-82af-bc35fd975863 | note | FREQUENCY: Prior to start
d5c39923-eaa4-5bf7-8cf3-2cf39be4afb2 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
2d32d08c-77e3-5317-84f7-3323793b1ca4 | note | REFERENCE DOCUMENTS: Drawings
23e504d8-7158-531e-b6ed-55efe689fe60 | note | INSPECTION/TEST METHOD: Visual Inspection
2c7080b6-372e-554e-9702-97060ba4aa2e | note | RECORD OF CONFORMITY: This ITP signed off
91388a12-4cce-5e5f-9587-6e06242aaa5a | note | IP
8be419db-8384-5fc3-8b32-6e7c7b0259d6 | note | RESPONSIBILITY: Fulton Hogan Engineer
edd7d644-0a85-5a17-b369-a046513845d9 | textbox | Date Completed:
1c3cbc98-4927-40b4-ae31-81834e3636be | checkpoint | 2.2 Signage Install
001a8804-fc11-5e93-8de4-fad871ab7dba | note | FREQUENCY: Each Sign
8ce4d4de-dfc4-54f5-844b-cbae46592b04 | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position. Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
89cc30a2-29cb-55e3-a273-89117f2ed837 | note | REFERENCE DOCUMENTS: AS 1472 TS 1313 Drawings
399a2021-dcae-51db-8557-991ba0b867d8 | note | INSPECTION/TEST METHOD: Verify
c0eb98ee-56f6-53ea-a83a-8398da7e20fd | note | RECORD OF CONFORMITY: This ITP signed off
8ad17730-f3f4-5e2e-9204-44480e88a5f3 | note | WP
54413ac4-6ccd-5ddb-8472-611ddfaed9dd | note | RESPONSIBILITY: Fulton Hogan Engineer
7e44db39-f4a0-54c0-a2d2-e71983c52afd | textbox | Date Completed:
44b3c2fa-3d72-4db4-b802-56e8a2427706 | checkpoint | Final Inspection
a044ca53-f4b0-5c8d-acdc-77469c77b6a4 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
9fe4154e-b069-5888-9cfe-afd49da76428 | textbox | Print Name:
c90e1941-725a-5840-a525-5d9b21ac2cde | textbox | Position:
89a9edd3-9241-5394-bab0-064c79dd5fee | textbox | Date:
aaa6dbf5-cf25-4126-9ef5-dd082805c45c | checklist | ITP-014 - Bluestone Kerb Installation (MCC) |  | ITP-014 - Bluestone Kerb Installation (MCC)
2823aaee-1362-4792-93f9-179a7c3f7d3b | section | Preliminary Works
7c0e8567-8c47-48d5-99d9-faceb15a0103 | checkpoint | 1.1 Check for Correct Documentation
88036de9-7ada-5464-85b7-b679c7e3891e | note | FREQUENCY: Prior to Commencing Activity
b2e6c174-701c-571c-b0a8-4c8e5c56b2d5 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
38302d59-ddc4-595f-ba4a-9b2aa8397ce4 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
751797ce-b577-5ce9-b69a-db4d45c15c41 | note | INSPECTION/TEST METHOD: Visual Inspection
cce78733-5588-50de-be57-50ac3789ce18 | note | RECORD OF CONFORMITY: This ITP Signed off
49c3a646-1df9-5add-8228-e5d47f6900e5 | note | HP*
de51f12c-4f08-5e02-9e77-a6f4f6da252b | note | RESPONSIBILITY: Fulton Hogan Engineer
34bbfe26-e321-57c4-90a9-ee8b55c5af20 | textbox | Date Completed:
7320f1d3-a27f-43e8-b34f-de1de9ba4123 | checkpoint | 1.2 Implementation of all measures and controls
361113f3-84fb-5b87-82eb-4c9b21544828 | note | FREQUENCY: Prior to Commencing Activity
708cbc8d-fb46-5a50-8943-1ba09fae27d4 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
cb7fb956-6921-5cba-8bb0-d65aa8d29927 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
413db448-f729-5032-9a80-1b844c1929e6 | note | INSPECTION/TEST METHOD: Inspection
f8d6e1f3-caa6-5ddb-9083-dddb67d69860 | note | RECORD OF CONFORMITY: This ITP Signed off
a8bde62d-497b-5cb1-8435-e3534d0c440c | note | HP*
640d0896-6e76-57fb-8c09-feb4c2d5739b | note | RESPONSIBILITY: Fulton Hogan Engineer
3be7282b-72d7-5eea-a59c-f62a599a390c | textbox | Date Completed:
1a1d61a1-7b17-420d-a14d-96fbb268e9b9 | checkpoint | 1.3 Existing Bluestone Kerb Demolition
30f6f458-e137-5c4d-ade4-8e5225257661 | note | FREQUENCY: Each Lot
da606d4e-055f-5ae7-b652-9ffe5331fb9c | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone Bluestone shall be salvaged and re-used in new kerb alignment
1fefcf1c-4ea7-5dd8-9efe-86247802a13a | note | REFERENCE DOCUMENTS: Work Procedure
9bc7bbd8-778b-5f1a-9ab6-6c20bea90c83 | note | INSPECTION/TEST METHOD: Inspection
0e67b9b0-15e3-588d-ae43-daf61b8c28b1 | note | RECORD OF CONFORMITY: This ITP Signed off
3d0bc8eb-1a34-5568-b4f3-d7d925a16179 | note | IP
c848906e-758c-5263-9434-5e814428b2fd | note | RESPONSIBILITY: Fulton Hogan Engineer
a95c0d53-c25d-5a5f-9e7f-5f054228c9aa | textbox | Date Completed:
312baa09-c14c-46dd-b295-5e2f3e9df60c | checkpoint | 1.4 Setting out
e94980ea-8d29-5e02-a6a0-30f13f375372 | note | FREQUENCY: Each Lot
61ee84b1-729f-59e5-b4da-db59ee653aa8 | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans Alignment of new kerb shall be marked out using string line
bd4ed746-87f7-5573-8073-bacccf93399c | note | REFERENCE DOCUMENTS: Work Procedure
e092313f-9c6b-5af0-ae07-0f46fdfecaea | note | INSPECTION/TEST METHOD: Inspection
fb78a4dd-1947-5d6e-a3cd-4bea09650435 | note | RECORD OF CONFORMITY: This ITP Signed off
13a0e05e-4387-5bad-a8d9-05172c62f96c | note | HP*
b05f8309-8deb-513a-bdee-00a2142f20cf | note | RESPONSIBILITY: Fulton Hogan Engineer
5fad23b2-527d-5612-8adf-b6bc51511eb9 | textbox | Date Completed:
25305b7f-a4e6-4531-90d0-9e9052aef347 | section | Construction Works
d0ad7f30-7d55-4deb-884f-6b6bd19c96f3 | checkpoint | 2.1 Saw cut (if required)
39fe1332-6f05-5e21-9b2e-90531da2a94f | note | FREQUENCY: Each Lot
4ec90fa0-ffcf-5cd2-b47b-6f4803974f8d | note | ACCEPTANCE CRITERIA: Saw cuts shall be made to the following depth for existing asphalt pavements: - Footpath: Minimum 75mm - Roadway: Minimum 125mm Excavate to allow for design heights
e80053f8-492f-5662-9dac-00c4639e56c2 | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 2.0
72df02b5-bb95-5570-b8c3-139f6d3fe936 | note | INSPECTION/TEST METHOD: Visual Inspection
76eb9fca-68a7-5293-8af1-1a93d2a83d5b | note | RECORD OF CONFORMITY: This ITP Signed off
a0fe31b6-91e3-5672-a873-89c2c6cd34be | note | IP
45e26502-b55a-5cdc-9a97-831f2d38e4f4 | note | RESPONSIBILITY: Fulton Hogan Engineer
64f30b8f-88f7-5211-b601-10d285f7b784 | textbox | Date Completed:
212cca58-f25d-47b4-9b81-14f7530aa2e2 | checkpoint | 2.2 Concrete Placement and Setting
6e95ae52-be72-5a0b-8eef-b049d61dd8e3 | note | FREQUENCY: Each Lot
a87ba097-ef71-583f-abdc-d0a38e48478d | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar
c3e08ea0-0658-5c7c-b288-4102345d0539 | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
2b762a49-fcca-50c4-b0cf-331c84caa425 | note | INSPECTION/TEST METHOD: Visual Inspection
c667295e-304e-5fd2-9e6c-288ca9711e32 | note | RECORD OF CONFORMITY: This ITP Signed off
f03124bc-f0d7-523a-9869-5c5379157a30 | note | IP
3b4bc136-1efc-5027-8758-29ac8be0e860 | note | RESPONSIBILITY: Fulton Hogan Engineer
f068f975-84e8-579d-9fd2-e5f0875c84f2 | textbox | Date Completed:
fbfe8fae-f22f-494c-9467-f696f9ae5a78 | checkpoint | 2.3 Mortar Mix
c2488668-22fd-54ca-bd7d-193b1fe5e30b | note | FREQUENCY: Each Lot
ce510f21-dff7-5b9f-99f2-66203e047cbe | note | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following: - 16% cement - 16% stonedust - 67% blended wash sand - 1% lime ready mix grout
d8ac4772-aa1a-5987-81e8-a436bc6ccc95 | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 4 AS 3972 CoM SD 1P 50406
c38262b9-795b-5af8-a5ab-d60fd99d0737 | note | INSPECTION/TEST METHOD: Verify
c3bcea6d-e6bd-55ba-b97d-bec4ed7f55d9 | note | RECORD OF CONFORMITY: This ITP Signed off
599fbdb7-2358-5e0f-a086-cc445fe77c3c | note | IP
0ebbcf15-296b-5d56-bd33-73951a8bb5e6 | note | RESPONSIBILITY: Fulton Hogan Engineer
2db6f630-19e1-558d-a142-dd1bc8fabfad | textbox | Date Completed:
7f422229-6fbe-415d-9265-be7d128b6f38 | checkpoint | Final Inspection
b5c507e6-a4d8-502c-9ba2-49e49291973d | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
21b0693a-3131-59aa-9377-735d5461a9ea | textbox | Print Name:
438dd459-8e7d-5a2e-80cc-7e6f23da0581 | textbox | Position:
956ef8a0-e733-59a2-bd30-02ac69ebb754 | textbox | Date:
c363c2e6-1b72-4efc-aacc-74b399d8031c | checklist | ITP-015 - Energy Absorbing Bollards |  | ITP-015 - Energy Absorbing Bollards
e172fd22-06cb-44ba-8172-b884fd33bfe2 | section | Preliminary Works
36af9d91-ee2e-4bad-b057-7e9ed21d4953 | checkpoint | 1.1 Check for Correct Documentation
9f4f69df-d072-5720-bce3-18d43ae69cc8 | note | FREQUENCY: Prior to Commencing any Activity
1d44aacb-ef88-5260-aef7-c196b15acf73 | note | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
f351a2fb-d004-56f1-bca4-0da3b9ad82ea | note | REFERENCE DOCUMENTS: Design Drawings and Register
0aa4c29f-3be2-50b3-b4c8-f8a4b36afd58 | note | INSPECTION/TEST METHOD: Visual Inspection
efdfe11a-9fb4-51eb-87bc-3df25a98e36d | note | RECORD OF CONFORMITY: This ITP signed off
9b72c6e9-1439-5aee-af89-7847f77b83da | note | HP*
233b1c24-0237-5b79-a574-55e4e7d0900e | note | RESPONSIBILITY: Fulton Hogan Engineer
d5237858-faa4-5dc4-948d-d487d64d946a | textbox | Date Completed:
75824eca-e856-4de3-83ff-0d1a349ccaf2 | checkpoint | 1.2 Implementation of all measures and controls
38b41293-ac5b-58af-aae7-5eaf7571a213 | note | FREQUENCY: Prior to Commencing any Activity
5b764db0-ba0b-5269-8f66-edb9836a1604 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
dd875f2a-fe79-552e-90ba-d3109a820ad8 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
503b4015-7efc-5282-a49b-1e12122f2dfb | note | INSPECTION/TEST METHOD: Visual Inspection
aae83b35-00ab-5779-9504-be57d00e846a | note | RECORD OF CONFORMITY: This ITP signed off
a82a5ae0-a06a-5b9d-9d99-cba2ab3a83ad | note | IP
57439984-5d45-5a2a-8935-af9daebfdf9b | note | RESPONSIBILITY: Fulton Hogan Engineer
d82630c6-39b4-5301-ad86-05c5be65a069 | textbox | Date Completed:
f9a5c7d5-fee2-42cd-b7df-1f9b646d67ce | checkpoint | 1.3 Service Proving
310b8360-2283-58d5-bc5b-4ad38a579b8b | note | FREQUENCY: Prior to Commencing any Activity
659eb53a-0546-5c1d-a74c-fc192fb9a18c | note | ACCEPTANCE CRITERIA: Service locating shall be conducted in form of DBYD and service location
51d6886c-9b3e-5dc9-b52f-703e66043ddc | note | REFERENCE DOCUMENTS: DBYD Service Locator
3da7bbb6-5e16-5375-b114-91ca50519bc8 | note | INSPECTION/TEST METHOD: Verify
0ab53de5-6821-599f-9446-0092238049b2 | note | RECORD OF CONFORMITY: This ITP signed off
a6c79647-ce42-5a78-af67-068648b758d2 | note | HP*
8a3681c6-be37-5594-bc57-0cb2b085355f | note | RESPONSIBILITY: Fulton Hogan Engineer
18477a0a-3d4c-5baf-8b89-40b59560cc37 | textbox | Date Completed:
13be9a81-02f4-4ccd-a262-57793fbe58d6 | checkpoint | 1.4 Excavation Permit
540277f4-580d-595d-a8d1-18229d3536f9 | note | FREQUENCY: Prior to Commencing any Activity
c5cc9e19-28cd-5dce-93d0-60a790e6d11c | note | ACCEPTANCE CRITERIA: Ensure excavation permit has been obtained for the specified tasks
af6bca3d-8ce3-56d7-bc5b-9ed38a087347 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
dc4883ba-38a4-5b69-b6bb-a9ba7784ba17 | note | INSPECTION/TEST METHOD: Visual Inspection
bdd2fca9-92f7-5a0b-89b0-50d8be919953 | note | RECORD OF CONFORMITY: This ITP signed off
d8d8b0d9-f291-5832-be15-0b2dac49a5a9 | note | HP*
9ed95b37-6804-5a34-afa0-194134e0f1cc | note | RESPONSIBILITY: Fulton Hogan Engineer
ffa8b8dc-8600-538a-bcaf-e62c629b380c | textbox | Date Completed:
26848522-0c60-4e59-8c27-9e19938b02e7 | checkpoint | 1.5 Materials
b13102e7-4d36-5218-923a-5c11c326ba75 | note | FREQUENCY: Prior to Commencing any Activity
593d62ec-a13c-5915-bd08-06521e2e41d4 | note | ACCEPTANCE CRITERIA: All materials shall comply as per technical specification Ensure materials are not damaged
72fa504b-f5e3-549a-8332-0e4ddad1618a | note | REFERENCE DOCUMENTS: ASE TS
089f9c08-bd4a-581f-832e-3a1fea469878 | note | INSPECTION/TEST METHOD: Verify
1f4793b8-f897-55b9-aca5-118aa61d26a6 | note | RECORD OF CONFORMITY: This ITP signed off
e35374a2-214a-576d-84f6-dfea4624de7d | note | IP
11018413-7491-51e1-8546-4527280ab0f4 | note | RESPONSIBILITY: Fulton Hogan Engineer
2acae374-2ff7-5781-beef-698295de090b | textbox | Date Completed:
774823cb-bdec-4943-b97c-4c9a47726737 | checkpoint | 1.6 Setting Out
fea5aac5-e7c2-59e0-a0dd-0736823bae40 | note | FREQUENCY: Prior to Commencing any Activity
af697200-8074-53cd-883c-981d10865b5b | note | ACCEPTANCE CRITERIA: Ensure location of bollards conforms to design drawings Mark hole centre position at location
6d3088ce-4520-5ee4-9dec-0684d335221e | note | REFERENCE DOCUMENTS: ASE TS cl1.1
f506c76e-6b9e-5b39-83cd-873be1a6deb4 | note | INSPECTION/TEST METHOD: Visual Inspection
1e42c83e-a96d-566d-a186-a2e9783dd786 | note | RECORD OF CONFORMITY: This ITP signed off
49f6d2a7-1d57-583d-8af7-9ba7ae117d82 | note | WP
33510672-4bef-5f96-8279-4e56adf14fb9 | note | RESPONSIBILITY: Fulton Hogan Engineer
52b275a4-e79f-55f2-be3f-8491ea1bce0e | textbox | Date Completed:
9b0e8397-283d-493b-ac3c-ac3352b91ac5 | section | Construction Works
8655134f-3589-4149-997e-21c6fd8926ea | checkpoint | 2.1 Excavation
00174762-ad83-5413-812c-8b9ead00993d | note | FREQUENCY: Each lot
370141b6-755e-579f-b616-edadc853d745 | note | ACCEPTANCE CRITERIA: Care shall be taken in excavation Hole shall be minimum 600mm dia and 1000mm in depth
17baf021-ffe4-5760-a160-683bc0b82d8a | note | REFERENCE DOCUMENTS: ASE TS 2.2
569adde8-a081-5db3-81ce-2f577e456ac6 | note | INSPECTION/TEST METHOD: Visual Inspection
cef3e82b-1b36-53bf-b7b7-1b4185ce74ef | note | RECORD OF CONFORMITY: This ITP signed off
7ba44245-6fb6-554f-9899-aa7afefdc168 | note | IP
89ff7549-db8c-5d9c-a4fb-8e5c2c2fbc42 | note | RESPONSIBILITY: Fulton Hogan Engineer
41b8231c-27e4-5398-b35b-5af7e88dab46 | textbox | Date Completed:
2045e5aa-ff2e-429d-b9ec-3b257e810bd2 | checkpoint | 2.2 Placement of block
81780c18-7125-548f-af38-61247c8f6c3b | note | FREQUENCY: Each lot
42567b17-2afb-5ff4-86c1-deb15e6007c8 | note | ACCEPTANCE CRITERIA: Block (brick, wood, foam) shall be placed at hole base Ensure base is supported by solid ground, and block is level
63a81bd0-3717-51c2-abe0-51dfbc5d7c7d | note | REFERENCE DOCUMENTS: ASE TS 3.1
b8366b6e-f659-5039-a335-9c635b7d7903 | note | INSPECTION/TEST METHOD: Visual Inspection
9dafcee9-94fa-5f35-b15d-c5010dba393e | note | RECORD OF CONFORMITY: This ITP signed off
20f050ab-a20f-5965-824f-fca56436b3c0 | note | WP
f2667b32-edfd-5396-9a4a-0bbcb81c2028 | note | RESPONSIBILITY: Fulton Hogan Engineer
e1880d0b-4cc8-5fed-bc5d-319e71fe9e8f | textbox | Date Completed:
a0be6617-409e-4f22-ab8b-134c8baf4246 | checkpoint | 2.3 Installation of Cartridge
3b51db39-f597-57fc-9011-6abf4a4c3233 | note | FREQUENCY: Each lot
66f31a3e-9259-5529-ba32-d592314cda8f | note | ACCEPTANCE CRITERIA: EAB cartridge shall be placed on level block
ad5bf4e1-eaef-5dd2-bde3-53088542a664 | note | REFERENCE DOCUMENTS: ASE TS 4.1
83e9fac4-276c-5f21-8901-1208684807c2 | note | INSPECTION/TEST METHOD: Visual Inspection
51741062-097f-56a1-a03e-5d4c91db5954 | note | RECORD OF CONFORMITY: This ITP signed off
5cdb81ea-bc49-50c2-a48f-c5d7e61c7d9d | note | WP
2c3c11b4-273d-5d5d-9ad4-10795cff31d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
ef580cfb-01d3-5468-a57b-682a50142882 | textbox | Date Completed:
07ba979b-1ff8-47f4-aad9-7e9bc6a5dbdc | checkpoint | 2.4 Pre Pour Checklist
0d45af90-3c30-5030-9619-575a3c2dfc90 | note | FREQUENCY: Each lot
a5ea5f5b-b0e4-517c-b44f-fe4eedc336f6 | note | ACCEPTANCE CRITERIA: Ensure minimum clearances are provided, no foreign materials are present, and EAB cartridge is level
837ab97c-4e35-500d-b482-0a6d55035269 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
7f2a32ec-6f0e-5e71-a1a3-0a168ee13b20 | note | INSPECTION/TEST METHOD: Verify
fb7afaa3-2e52-5ac7-8e0f-1645b6c1c51c | note | RECORD OF CONFORMITY: This ITP signed off
72fc6f3f-adeb-545f-ba34-5d90d58fe230 | note | IP
0a02357a-35c5-5605-9720-298398a04cf6 | note | RESPONSIBILITY: Fulton Hogan Engineer
029f52f6-60c5-556e-83aa-9aead1095319 | textbox | Date Completed:
4dafe5d7-c730-44fb-b28b-75f784334d3e | checkpoint | 2.5 Installation of Concrete
0fa2d619-5293-5fdd-9e0d-d17b46a4c8a3 | note | FREQUENCY: Each lot
c54d81ac-2a54-5aa4-8d0b-60b2e871cc06 | note | ACCEPTANCE CRITERIA: 32MPa concrete shall be placed to cover reinforcement cartridge and fill hole Concrete shall be compacted by use of vibrator If surface pavers are to be used, allow 25mm gap from finished surface Ensure cartridge is level post compaction
ab12431b-8fc6-58e4-88a3-30042e5977f5 | note | REFERENCE DOCUMENTS: ASE TS 4.2
cde6445a-577f-5463-8d3a-f4a05b8b0012 | note | INSPECTION/TEST METHOD: Visual Inspection
7e920cdd-8ee2-5061-9a6f-f52227d0c293 | note | RECORD OF CONFORMITY: This ITP signed off
b8a1e715-2e58-58c0-b79a-ebd6d95c7c27 | note | IP
7920b3b1-9149-5fa5-9dd7-73d8fe2ed545 | note | RESPONSIBILITY: Fulton Hogan Engineer
a54fc4b9-8ed7-5948-ac35-24d297e063d7 | textbox | Date Completed:
b39c109d-3d50-4ab4-9af8-36dcc6944d78 | checkpoint | 2.6 Installation of Bollard
a310f99c-5879-5dec-b737-b189b1d3adf0 | note | FREQUENCY: Each lot
62a59d39-edb9-5d22-8801-e762cdef7b11 | note | ACCEPTANCE CRITERIA: Ensure bollard is installed, and bolts are tightened adequately Concrete, pavers or bitumen shall be finished to specified requirements
313f1b56-8b5c-5ddb-a49f-399a63a99d4b | note | REFERENCE DOCUMENTS: ASE TS 5.2
be9a29a2-b3f0-5911-a802-15d84f418bb0 | note | INSPECTION/TEST METHOD: Verify
b05a7ffb-3323-5830-b1ad-f8d1bb6e864a | note | RECORD OF CONFORMITY: This ITP signed off
44bdfa7f-602e-5d44-b4fa-6cdd8b5c121b | note | IP
c07446a4-7162-5267-a3ea-163668b807cd | note | RESPONSIBILITY: Fulton Hogan Engineer
106a18d8-2d93-5d12-83ed-c6efa7cf83ee | textbox | Date Completed:
f8408594-98b4-4b76-8a4b-7d901849428e | checkpoint | Final Inspection
7ddcd1ca-83e4-5c71-b725-aaaaffb44c48 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f8b1c20a-0f3a-5521-952f-4a1243a20c09 | textbox | Print Name:
2631b7fc-a95b-5d75-98a0-468fcabd2099 | textbox | Position:
dce930d2-37dd-5911-9be8-198c0c293b8e | textbox | Date:
4021f14a-48fd-40a8-acd1-152d16690d08 | checklist | ITP-016 - Platform Bluestone Kerb |  | ITP-016 - Platform Bluestone Kerb
80341959-40c4-4fad-b47a-fe6dbfbb360b | section | Preliminary Works
d0acd62d-23cb-49de-ac05-f87f51002f72 | checkpoint | 1.1 Check for Correct Documentation
a2548de4-5c7a-5e89-9e80-2d7280378a5b | note | FREQUENCY: Prior to Commencing Activity
442d5e1e-9fd7-5e37-950e-55fcffb2e3e1 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
35505b02-60af-5afd-b61f-c19eeca0be5c | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
9143e769-18d4-5f6c-9742-36481ea6b2e9 | note | INSPECTION/TEST METHOD: Visual Inspection
d039153c-c0d3-5735-ae27-aa3fa69c3def | note | RECORD OF CONFORMITY: This ITP Signed off
cb8db0b0-e55a-5f2e-82c4-49ae13dfb24f | note | HP*
d92a7554-2a30-5006-b8cd-62f895881157 | note | RESPONSIBILITY: Fulton Hogan Engineer
5f3928e1-26ac-5600-a0d3-73b3cb60dc66 | textbox | Date Completed:
e62ff21e-031d-4733-8578-51404186517e | checkpoint | 1.2 Implementation of all measures and controls
c5e2b3f9-2965-53b4-afe9-e493d8ee83b8 | note | FREQUENCY: Prior to Commencing Activity
339c9aec-e1bb-5253-9003-1fcc9f709fad | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
ae2f27a8-478f-5fdb-831e-026d28e7e734 | note | REFERENCE DOCUMENTS: Work Procedure
95158c27-b862-561b-8441-97dd15674345 | note | INSPECTION/TEST METHOD: Inspection
65f88381-ca6a-5755-be78-882effa1423e | note | RECORD OF CONFORMITY: This ITP Signed off
b10bd37c-75bf-50f1-80fa-a43a749d7193 | note | HP*
9524b755-9d3a-51fe-8db6-d0b9597ec82d | note | RESPONSIBILITY: Fulton Hogan Engineer
2bdeaf86-1d47-5722-92cf-07d202e7072f | textbox | Date Completed:
b477b789-8f1b-4afe-b7ee-c5b104163247 | checkpoint | 1.3 Check Condition of Material
7eda0ea8-ad97-5b89-a48a-ac656fd4232a | note | FREQUENCY: Prior to Commencing Activity
01105d52-b3ea-5761-bac6-dd3bf03d8c14 | note | ACCEPTANCE CRITERIA: All bluestones shall be inspected at delivery for visible damage
e13af6eb-7611-505a-ba14-ebbdd888c1ad | note | REFERENCE DOCUMENTS: Work Procedure
97b83582-6907-57c5-ba13-67611673cafb | note | INSPECTION/TEST METHOD: Inspection
ddd1b6b9-64a4-57a9-b441-768e51e3d9c9 | note | RECORD OF CONFORMITY: This ITP Signed off
16d40d2b-789b-501e-91e2-f8340e486580 | note | HP*
57bafc94-b97c-5e41-ac88-14aa6fbb2d20 | note | RESPONSIBILITY: Fulton Hogan Engineer
f9519560-6553-52d3-9b60-492c7daaa7ec | textbox | Date Completed:
548eb07d-8904-4aba-aeea-81025079e62e | checkpoint | 1.4 Lifting method
8f3009a4-2edd-52ac-9cfc-1e02160ce34a | note | FREQUENCY: Prior to Commencing Activity
90ae9b66-46f1-561d-8c60-cc54bbc42a1c | note | ACCEPTANCE CRITERIA: Bluestones can be moved with excavator and grabs/slings or with a vacuum lifter.
19893db3-0002-5118-97f8-849c6c5b0194 | note | REFERENCE DOCUMENTS: Work Procedure
78079a0a-a702-5928-8ea7-d349d3bbf6e5 | note | INSPECTION/TEST METHOD: Inspection
3671fafe-1116-51ca-aec6-5cd0297883a3 | note | RECORD OF CONFORMITY: This ITP Signed off
8e112798-fcb7-526b-aaf7-e3c541219a1a | note | HP*
31a022a9-699b-539e-953f-5b9ff456198f | note | RESPONSIBILITY: Fulton Hogan Engineer
934d19c9-41c9-5e6b-89cf-0af21b1ec1b3 | textbox | Date Completed:
81ce272e-1839-481c-a3c0-00f773f4d8b0 | section | Construction Works
6945bfc5-6823-4c3d-ac94-3a548b525cb2 | checkpoint | 2.1 Base Course
df2cdd04-a4f2-5928-90aa-5f8ba780d258 | note | FREQUENCY: Each Lot
43ad9c04-717c-5640-9e39-b678375ddeb9 | note | ACCEPTANCE CRITERIA: Class 2 compacted rock (98% modified density) shall be compacted to 100mm thickness. Soft or areas deemed unsatisfactory shall be removed and rectified
b93b58fa-66ad-5113-b713-91618255027b | note | REFERENCE DOCUMENTS: STD_T6111
d17ce53b-de0e-5ef6-8156-e2ad71292c7c | note | INSPECTION/TEST METHOD: Visual Inspection
c87e6fd0-dbd2-582a-b25e-52cef81b4c75 | note | RECORD OF CONFORMITY: This ITP Signed off
8fc9f920-8b21-5218-8918-f6ae4bc06758 | note | IP
9b7cb503-e4f7-50ea-980b-68dd7e806ccd | note | RESPONSIBILITY: Fulton Hogan Engineer
c701b563-1866-5592-8080-e20fe11ae464 | textbox | Date Completed:
002f722b-4cba-45c0-be4a-9592446b3b85 | checkpoint | 2.2 Concrete Placement
5467dda5-9d09-58f3-994c-9e90fb20cf45 | note | FREQUENCY: Each Lot
633c3079-ee33-503d-bda5-e211bd4afe2a | note | ACCEPTANCE CRITERIA: Bedding shall be >100mm 32MPa concrete with 6mm aggregate
8cf704b0-5737-5005-82da-87683f7dba8e | note | REFERENCE DOCUMENTS: STD_T6111
22ae1d88-2d57-5ffb-a0dc-12b0bef821cc | note | INSPECTION/TEST METHOD: Visual Inspection
8ee73d6e-0397-5c55-a6b2-94596a8eed37 | note | RECORD OF CONFORMITY: This ITP Signed off
1c7213a3-4ccb-56e4-bdbf-2c8d1cb69e83 | note | WP
93fe0ac8-55aa-57b7-93cc-c1bd48321385 | note | RESPONSIBILITY: Fulton Hogan Engineer
8238da5a-c039-5712-a107-b0af0b934838 | textbox | Date Completed:
d483adcc-c504-4c88-b1fd-21132ac600d0 | checkpoint | 2.3 Setting
9fda5c45-e6ec-5194-b171-903831e7b28c | note | FREQUENCY: Each Lot
b2335ecb-db47-5cf5-b465-58de02e444de | note | ACCEPTANCE CRITERIA: Tie rods shall be N12 (300mm long) and chemset 100mm into kerb, 2 per stone. Tie rods shall be installed with bond breaking compound specified by superintendent. Bluestone shall be laid 150mm below finished surface level
09a3f1a2-7d46-55a3-b243-35ca92c6ec67 | note | REFERENCE DOCUMENTS: STD_T6111
7ced3642-be25-5a53-a4ac-ead42286e5b7 | note | INSPECTION/TEST METHOD: Visual Inspection
4a0fafb2-a83e-5d70-b079-9c328f3e7dab | note | RECORD OF CONFORMITY: This ITP Signed off
a440a053-ede6-51ca-bcb2-bb82e3536669 | note | WP
8991cd87-206f-510b-b422-9ead3712fc67 | note | RESPONSIBILITY: Fulton Hogan Engineer
2c20f57c-be04-530d-a1d7-6e2055600b6b | textbox | Date Completed:
0088aed7-4fbe-41c7-a1b6-607df81ce210 | checkpoint | 2.4 Sealant
36b74be9-38aa-507a-8ca2-cf4c8ce5f647 | note | FREQUENCY: Each Lot
1602cc34-fb4d-5d7c-a864-d901185c7167 | note | ACCEPTANCE CRITERIA: Sealant at construction and expansion joints at back of kerb shall be 'Gun Grade THC 900' by Tremco, of black colour. Loose materials shall be removed as not to impair adhesions
7fed2930-1f76-511e-bcf7-a11431289edf | note | REFERENCE DOCUMENTS: Work Procedure
ad95e78f-3348-5e7b-94bd-d4095d4ce5c0 | note | INSPECTION/TEST METHOD: Visual Inspection
3f20adc4-5ada-5913-836b-4ef18b97912d | note | RECORD OF CONFORMITY: This ITP Signed off
2d09d70a-4586-5fbb-b669-26d88b4a706f | note | WP
54dff88f-bc42-5fe7-bec0-0ae5f83772a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
9bc4e390-4e92-59d6-8c5c-0a463a75bdd0 | textbox | Date Completed:
9965b26d-e31e-4414-99fc-c5881786f830 | checkpoint | 2.5 Platform line marking
130986b2-14da-50cb-bff4-ade747cbf2ac | note | FREQUENCY: Each Lot
3eec5748-9193-5020-b042-549c6ad13cbc | note | ACCEPTANCE CRITERIA: 50mm yellow lines shall be placed along the edge of platform, one on the top face and one on the front face of the kerb.
84f0efd7-39e7-5a49-b82e-bf5aaa6524d9 | note | REFERENCE DOCUMENTS: VRIOGS 005.3 Cl 7.9
4fc7bb84-e0b7-5e98-a0d5-d434727ff397 | note | INSPECTION/TEST METHOD: Visual Inspection
bab7fdfa-098f-5f80-aa59-2e6f0aba4996 | note | RECORD OF CONFORMITY: This ITP Signed off
3e2d50fb-91d0-559e-a125-5c4ae5572182 | note | WP
708737ac-7cd0-53d1-9bc7-f40a6c688a79 | note | RESPONSIBILITY: Fulton Hogan Engineer
887c1057-f440-5fe6-adde-27e80ae44a62 | textbox | Date Completed:
05db137c-415f-46a6-a565-031f66e844bc | checkpoint | Final Inspection
9edd7723-aab9-5b7b-9ab2-fb9dcd3b997d | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a4416711-96fb-5d71-972f-2db1cdd0a460 | textbox | Print Name:
61f72a9c-1db5-58d8-9a6c-3d0503e4ee78 | textbox | Position:
4f054cac-e682-539d-b1c0-60ee385087bb | textbox | Date:
e25de9b9-6ed1-4c2a-a425-b5f501e3686f | checklist | ITP-017 - Bluestone Paving Works |  | ITP-017 - Bluestone Paving Works
9c653a61-6004-4a61-9bbb-4d8a22309fb8 | section | Preliminary Works
9630952a-79fe-4e1f-9cc6-6e89fb6e0e94 | checkpoint | 1.1 Check for Correct Documentation
da852508-2839-5929-8d3a-115c3403a5b7 | note | FREQUENCY: Prior to Commencing any Activity
175ddb91-e267-5ba2-be28-7cfbe7335219 | note | ACCEPTANCE CRITERIA: Ensure all employees and subcontractors use all current and complete set of design drawings
ca961dac-661d-5b53-8257-89a892ca0357 | note | REFERENCE DOCUMENTS: Design Drawing and Registers
52a11ca3-ec01-5bcf-916d-cdcf44ae671d | note | INSPECTION/TEST METHOD: Visual Inspection
958f424a-381c-562a-a847-39027df1d2bb | note | RECORD OF CONFORMITY: This ITP Signed off
05940d70-10cc-5a27-ad9c-117ecd33011b | note | HP*
e126a03c-8c52-57cc-85d7-82cf610194d5 | note | RESPONSIBILITY: Fulton Hogan Engineer
ed547ee2-192b-5935-a332-fd88dd9d28fb | textbox | Date Completed:
f9513f63-413d-400d-a3d2-d53624c9ecd4 | checkpoint | 1.2 Implementation of all measures and controls
2b9c722f-1c2f-56fc-9d15-e5b2b9b6d497 | note | FREQUENCY: Prior to Commencing any Activity
c8ac200a-0987-5b1d-b120-8feb1378c5d1 | note | ACCEPTANCE CRITERIA: All necessary measures and controls shall be implemented, including: EMP, PSP, SWMS, TMP and WP
c8e087c6-751b-5797-8b1a-f8e6b9f5d3e7 | note | REFERENCE DOCUMENTS: EMP, TMP, PSP, SWMS, WP
76451bcc-5c01-5fa5-917a-1a5b3fe6e4b7 | note | INSPECTION/TEST METHOD: Visual Inspection
afec54ee-b630-5d42-b8e1-c603131b464c | note | RECORD OF CONFORMITY: This ITP Signed off
4937d070-9cd6-533b-805c-efefed4f7350 | note | HP*
70a5345f-9a59-5716-83c0-5030b411907d | note | RESPONSIBILITY: Fulton Hogan Engineer
5462603a-52ce-5cb9-ade1-2a604faac659 | textbox | Date Completed:
4baad907-dad8-4ec2-bcc8-c04d1f43da28 | checkpoint | 1.3 Check Materials
dbfad4f1-2dfd-58ca-b50b-f0f252b899f2 | note | FREQUENCY: Prior to Commencing any Activity
46d06369-6f5c-5770-82fa-3c8e1848b9fb | note | ACCEPTANCE CRITERIA: Inspect materials for any chips, cracks or other visible damage.
3aa662f4-028e-5782-98ef-724c023ba7ba | note | REFERENCE DOCUMENTS: Receivable Inspection Checklist
4b5b4347-d3cf-50fc-9be4-84f206ea61c1 | note | INSPECTION/TEST METHOD: Visual Inspection
37a4f2b5-14ab-58e5-b21f-4ca972b44f8f | note | RECORD OF CONFORMITY: This ITP Signed off
f8f24a4f-640e-5aa6-9afe-e4601fbb744e | note | HP*
cac8a09a-fecc-5802-9d83-102eb5d5eb12 | note | RESPONSIBILITY: Fulton Hogan Engineer
1eae1869-d569-5563-a1a0-2a57f4797868 | textbox | Date Completed:
f1472b87-ce40-425f-a00a-93773b90d8dd | section | Construction Works
63383330-6a63-4ec5-bec9-5440a10c9b8c | checkpoint | 2.1 Base preparation
8898c624-325f-5e92-b1c9-b9f66f71ca09 | note | FREQUENCY: Each lot
d7ab0d21-2052-5ef3-909c-c34df4663568 | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign materials and water pooling. Formed groove of 10x25mm in concrete face shall be filled with caulk
4c5d05b9-31a1-5b3e-ae76-4930fe1689bd | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
05b291b7-6421-5ef6-860e-99d78f4d0fbb | note | INSPECTION/TEST METHOD: Visual Inspection
d3d3e42f-237d-52c2-a33e-3bd96d253c94 | note | RECORD OF CONFORMITY: This ITP signed off
e3696ee3-363b-5ff4-b6d3-a19f28957d30 | note | WP
966f178a-8783-5942-9ae9-9363d49f46a6 | note | RESPONSIBILITY: Fulton Hogan Engineer
05f855de-b302-507a-9bdd-2573812be780 | textbox | Date Completed:
7c64a3ed-e2a9-49b3-a772-1bbd5c727820 | checkpoint | 2.3 Mortar Bed
40763fe9-0be8-5291-ad39-a68c2c0e71a6 | note | FREQUENCY: Each lot
1c267cc9-af08-5ea7-a52f-7c17403d3f1d | note | ACCEPTANCE CRITERIA: Mortar shall be applied at average thickness of 30mm to concrete base. All pavers shall be coated in mortar slurry on rear face before laying
d9b1b95e-da34-588b-ae56-0c1277258cc6 | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
0bd139bb-837e-5278-a65b-99ae5a854372 | note | INSPECTION/TEST METHOD: Visual Inspection
4ad10e17-0ea0-5752-a148-79591572f173 | note | RECORD OF CONFORMITY: This ITP Signed off
53051dd4-cebe-5d85-86ea-2f05dd295d80 | note | IP
e13db657-5d85-5879-8b70-5683d3e33b95 | note | RESPONSIBILITY: Fulton Hogan Engineer
8b14e489-3743-549c-ade7-443d15e58c7c | textbox | Date Completed:
a1380dcc-d3d6-4699-b47f-cca7e7ed7cba | checkpoint | 2.5 Cutting of Pavers
a3d3bb09-4527-52d2-84be-cbe84e67384e | note | FREQUENCY: Each lot
28ebcb66-d6f9-55c7-953b-825f7dbaa5f4 | note | ACCEPTANCE CRITERIA: Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
98955e67-a02c-5a59-b573-48e7aea516e5 | note | REFERENCE DOCUMENTS: DWG MMR-AJM-NPDM-DR-DD-640054
a5b4052f-77b5-50ae-bec9-df5698b39d2a | note | INSPECTION/TEST METHOD: Visual Inspection
72ce4eb5-a640-535e-9b5a-2a37d506d48a | note | RECORD OF CONFORMITY: This ITP Signed off
e4ad5e8e-9513-50f3-bf8e-7fab4c80ad55 | note | IP
86106bf2-0fcc-5965-bf44-0ab5c4633f86 | note | RESPONSIBILITY: Fulton Hogan Engineer
ed5560bb-68d1-5c79-8b9f-dcb64ae77b12 | textbox | Date Completed:
cfe890a3-1b78-4f1d-8ebd-319dfa7c5039 | checkpoint | 2.6 Curing
7eef6d4c-da3c-5469-9ce7-93776e6d82dc | note | FREQUENCY: Each lot
8141e62d-7ea1-5b60-8a4e-fefda6a46dc8 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic. Where required, ply shall be laid over area of works
c58f3e15-c489-5e13-804a-c2971fc08f0e | note | REFERENCE DOCUMENTS: Manufacturers Specifications
c0646f52-78df-5ae3-a893-e58d0d4967d0 | note | INSPECTION/TEST METHOD: Visual Inspection
e4266fb5-61b1-5a2b-8223-9998d11faca1 | note | RECORD OF CONFORMITY: This ITP Signed off
f2c2b2c7-37bf-5282-a020-a5097cb0ccca | note | IP
164e64a9-1e09-5a51-85b2-40f916e462bf | note | RESPONSIBILITY: Fulton Hogan Engineer
b0088dce-e5d6-5bb6-970a-7145ab28a5c5 | textbox | Date Completed:
d561adf7-334e-432f-b4f9-6da169e9b719 | checkpoint | 2.7 Grouting
2bd0ff4b-4353-566a-ac83-a3ff51e03452 | note | FREQUENCY: Each lot
6e8648d0-a067-5891-ab3d-3739adaf5fb8 | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using agreed colour and mixture
a4633d92-7e59-57f4-b214-161f0e47d6c0 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
1cbfa87d-7038-573d-9dcd-60aa305acb5b | note | INSPECTION/TEST METHOD: Visual Inspection
57053a4f-c69e-5334-ac1e-07a494a5b14d | note | RECORD OF CONFORMITY: This ITP Signed off
e163b2d5-6406-5b19-ae05-66ec66490bc9 | note | HP*
367cfa0a-e6ac-585e-9fa8-ac0e93215746 | note | RESPONSIBILITY: Fulton Hogan Engineer
b6adbf9a-c500-5cdc-992c-b64feddbd1fc | textbox | Date Completed:
d482e4d5-980c-43f6-bcc3-c269da74813e | section | Completion
5c258841-3f54-4b01-86c7-68e4d2be0262 | checkpoint | 3.1 Completion
9a9e700d-e0f7-571d-ade2-febc6408be5a | note | FREQUENCY: Each lot
f5a04fd5-a9ed-5687-9035-ddcc9cd607f2 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste. Bluestone pavement is free of mortar stains and cleaned to satisfaction
6b898521-1124-5796-9219-9a1de667a0a8 | note | REFERENCE DOCUMENTS: Visual Inspection
e3d700a1-20dd-595b-8f7d-3227be8cc470 | note | INSPECTION/TEST METHOD: Visual Inspection
1f5c5f8f-8b91-5710-abfd-f8664b91f3f5 | note | RECORD OF CONFORMITY: This ITP Signed off
397520c1-e255-5c50-baa1-538a9096df03 | note | IP
a6a50501-4ca5-592b-82ff-815316a4d1b2 | note | RESPONSIBILITY: Fulton Hogan Engineer
ba027320-2903-530e-a4ab-b8f253da3146 | textbox | Date Completed:
c44a7ce0-99e3-483b-9f37-908d07e37bba | checkpoint | Final Inspection
e89590e4-4186-5bf4-b60b-ab4eb7184e65 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a2c7b2e5-85c4-5e91-bcf6-968e75228cee | textbox | Print Name:
90f91f29-ca67-5965-a9c9-3aef5df87012 | textbox | Position:
efa56ab8-ad83-53ba-878b-c45b1d8905f9 | textbox | Date:
feaccad0-1cc6-4852-b305-10633d349c6e | checklist | ITP-019 - Fencing Installation |  | ITP-019 - Fencing Installation
4a42966f-d30b-4e74-80d8-628c0857a678 | section | Preliminary Works
aba07417-a9fa-4b0d-9419-7a41a5e10222 | checkpoint | 1.1 Check for correct documentation
86fde12f-5661-568a-a3df-36093d4a7645 | note | FREQUENCY: Prior to commencing any activity
790bbcc5-870b-500e-95f0-51685ba38c79 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
e30f1a54-fc0f-52c1-9bcc-3b9d0bc7af30 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
39f9a67f-3453-5f8e-a8a3-0e25ac221937 | note | INSPECTION/TEST METHOD: Visual inspection
fb67d309-1a47-5ed6-a6b4-936dc3c1951a | note | RECORD OF CONFORMITY: This ITP signed off
a92c3aac-bf91-5a0b-a83e-43fc7c3efaf4 | note | HP*
58ef852f-1386-5cb2-a0c7-ebd63118066e | note | RESPONSIBILITY: Fulton Hogan Engineer
bc6760f0-d553-591b-909e-35db646f8f1c | textbox | Date Completed:
39d5b15b-3a73-4bc2-b531-2c232f638ad8 | checkpoint | 1.2 Implementation of all measures and controls
e61787cd-986a-5b1e-83ad-acb6027d00be | note | FREQUENCY: Prior to commencing any activity
cdb43d3c-e5e5-5f75-8ec6-a6f5c8598c02 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
3037b6ce-4972-5164-9635-d013b4e09f6f | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
0323f1e8-eae6-5808-9cd4-68a11c805e68 | note | INSPECTION/TEST METHOD: Visual Inspection
2a7aae24-1d7a-5cf1-ba4b-190ba749da4c | note | RECORD OF CONFORMITY: This ITP signed off
ac0e4a7b-cecf-5973-9df8-4be7888d0df8 | note | HP*
4abdf5c3-9d8e-5f7a-95f1-a575878377ff | note | RESPONSIBILITY: Fulton Hogan Engineer
8a1ffe2e-5909-5aab-9ebc-4ed864513bbf | textbox | Date Completed:
3c0aec95-6a38-49c5-9b6a-5cfaa6bd3518 | checkpoint | 1.3 Check Materials
d4f7c5de-adf6-52e2-b396-1df50a565327 | note | FREQUENCY: Prior to commencing any activity
9d1b317a-8f11-5209-8556-3dfdc605ebf4 | note | ACCEPTANCE CRITERIA: Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish, linished, pickled and electropolished. Welding shall be in accordance with AS1554. Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000
e62792f1-0920-5a3c-b412-137e40f5e936 | note | REFERENCE DOCUMENTS: STD_T6000, CE-021-ST-0012, cl 4.3.1.4
8349d94e-5b0b-58b1-8201-a973a4eff7f1 | note | INSPECTION/TEST METHOD: Verify
a8069f06-f02b-5205-a94a-620353aaeba5 | note | RECORD OF CONFORMITY: This ITP signed off
024921b1-926b-5578-adb3-ab6c8988afd4 | note | HP*
4021779d-0ec2-5564-bbc1-4779540072fc | note | RESPONSIBILITY: Fulton Hogan Engineer
21941661-f36f-5959-83ae-9dcb0889f2a4 | textbox | Date Completed:
6ecc4b94-46aa-4405-9539-5ea73adfdafd | checkpoint | 1.4 Confirm Footings position
119b20df-c82b-5572-a8a6-8f74fa74330b | note | FREQUENCY: Prior to commencing any activity
4b0c3afe-1076-5efb-bf26-4834be217a75 | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
1f2a5d57-7c0d-54ad-9c8a-777f1427277b | note | REFERENCE DOCUMENTS: Construction Drawings
db3b173d-e600-5af0-8b8f-57ce054d1b64 | note | INSPECTION/TEST METHOD: Verify
7d00e8e7-cfd1-5916-bebf-43e9df0ec90c | note | RECORD OF CONFORMITY: This ITP signed off
efc3b4c3-42a4-5bac-8ffd-91e6f8f79b24 | note | HP*
a287fe8b-ca5a-5123-8eb7-099b5b298218 | note | RESPONSIBILITY: Fulton Hogan Engineer
c567e8bf-6014-5b36-986c-2a6c8bdae3b3 | textbox | Date Completed:
0d662e65-602e-4cb4-8fcd-f966f812bd1a | checkpoint | 1.5 Bonds
0824e45e-faf1-54bf-a5e9-05332fc4812a | note | FREQUENCY: Prior to commencing any activity
abaeef60-6b3b-541e-86a8-1c999bfa6af5 | note | ACCEPTANCE CRITERIA: Ensure fencing is isolated and earthed to achieve electrical isolation. Lug shall be fitted to baseplate at specified fencing location
67cab031-5460-511b-b332-1b781443aaf9 | note | REFERENCE DOCUMENTS: STD_T6000
a0d1634e-2e93-5b83-ad16-f526a88a8f2d | note | INSPECTION/TEST METHOD: Verify
6a0992a3-606e-534e-a697-9fa908b19acd | note | RECORD OF CONFORMITY: This ITP signed off
d5861211-1759-5f22-963c-e5a239fa3b73 | note | HP*
11c6fdfd-9856-503d-97d0-d581a1d34157 | note | RESPONSIBILITY: Fulton Hogan Engineer
924a1afb-4bb2-58d5-971c-190b794bb827 | textbox | Date Completed:
7d1e8369-e34e-4757-955a-bdd3f66716c9 | section | Construction Works
5cf3a7e8-5d12-4fd9-893a-7b79a38ed373 | checkpoint | 2.1 Footing Installation
530bfb72-3729-511b-8052-f3d982c87b0f | note | FREQUENCY: Prior to Asphalt
704d4e59-b220-5ee6-b75a-6ad49118df71 | note | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20. 4 M16 hot dipped galvanised bolts shall be chemset 175mm into embedment, per footing
ad8c0df6-4c16-5ae5-8d6e-f3afdaaeff09 | note | REFERENCE DOCUMENTS: STD_T6002
a7f280b7-7fc3-5f5c-a7b4-2e7a1224292a | note | INSPECTION/TEST METHOD: Verify
b49f42e4-f631-50e8-afc7-a131a343d2a3 | note | RECORD OF CONFORMITY: This ITP signed off
0a682e0b-3ec2-558d-9c14-c9b0a9ba5de9 | note | IP
eb1ceb8c-bd89-5f7c-b8cf-d6a1080ff909 | note | RESPONSIBILITY: Fulton Hogan Engineer
2d42928e-883a-56c7-9a51-f4bbc566137e | textbox | Date Completed:
7fcc8f7d-1b57-4ab2-ac1f-fcca80c31ead | checkpoint | 2.2 Post Installation
e91b5e1e-4cf0-5776-877f-86dc8eaa582d | note | FREQUENCY: Each Lot
12e277d0-2c90-5545-ba21-bd35fed3cd3b | note | ACCEPTANCE CRITERIA: Post shall be installed to designated height and level. Installed to footings with bolt assembly. All bolts shall be insulated from base plates, using non metallic sleeves and washers. The top of fence base plate shall be level with surrounding pavement.
3a4effde-9177-5ca0-94fc-a3040553d95a | note | REFERENCE DOCUMENTS: STD_T6002
153cc8b7-f8d1-5ecb-9ed0-2b69d63a01d5 | note | INSPECTION/TEST METHOD: Verify
cfb389bd-85db-536d-867e-b80081af4143 | note | RECORD OF CONFORMITY: This ITP signed off
a363507f-a075-5110-a4a4-e63c5deb26bf | note | IP
e4ea7d3a-812b-5317-8b03-5991acae9399 | note | RESPONSIBILITY: Fulton Hogan Engineer
fe4c4abf-f176-54af-885f-81902b63b048 | textbox | Date Completed:
2884354c-6021-46dc-bfea-6226b6d2392a | checkpoint | 2.3 Grout Installation
815ec29e-c34c-5b13-8cf6-076ab75cf170 | note | FREQUENCY: Each Lot
f0ef7231-df0c-5776-9e7e-fc5cc838ff9d | note | ACCEPTANCE CRITERIA: Footing surface shall be cleaned and roughened before application. 50mm of Non shrink dry pack grout shall be placed under base plate
576e5f0a-7aff-5280-aba7-e9fd972b3080 | note | REFERENCE DOCUMENTS: STD_T6002
b621e1ce-8a3d-5ca9-bdad-9a8694d3f8c4 | note | INSPECTION/TEST METHOD: Visual inspection
f66e8eae-6b03-568e-b3c1-e7926eb5b475 | note | RECORD OF CONFORMITY: This ITP signed off
63be8778-224d-5bda-92af-996de4b2989b | note | WP
63d168ea-ee15-576e-98bd-67b4f6a5ad19 | note | RESPONSIBILITY: Fulton Hogan Engineer
c2d01ad0-1d7f-5a32-868d-e994d13a5c22 | textbox | Date Completed:
c7610ba6-d217-4480-ab75-46866c30c725 | checkpoint | 2.4 Continuous Handrails
f83684e5-5b78-5aff-b474-e47fd2d260eb | note | FREQUENCY: Each Lot
1bd5f1df-9e65-5459-a34b-9a8b91e35988 | note | ACCEPTANCE CRITERIA: 5mm cap plate on handrail returns. All sections to be welded as per AS 1554. All sharp edges and welds to be ground back to smooth finish. Domed buttons to be welded on top of handrail 150mm from the post centreline.
ac8a3f30-b8a5-5b4e-8723-3451c4e5efe2 | note | REFERENCE DOCUMENTS: STD_T6001 & T6002
e0f42eb1-9502-589c-9e0e-7ceb0ad4b6d8 | note | INSPECTION/TEST METHOD: Verify
7d4259b4-64e9-5d61-9708-2130d18b6322 | note | RECORD OF CONFORMITY: This ITP signed off
24719845-0f5d-5dbc-a6c1-456eb527d3a6 | note | IP
c0aa6569-652c-59b1-8226-6a8a4e311f32 | note | RESPONSIBILITY: Fulton Hogan Engineer
e0c9178f-5e96-5a11-a91c-20dee2942434 | textbox | Date Completed:
a0ddcf8d-d95c-490f-a76b-cef4546e7154 | checkpoint | 2.5 Wire Rope Tensioners
4f0a7ef7-c213-5298-94f8-f2a9abeb90e9 | note | FREQUENCY: Each Lot
562a3c3f-1700-5c61-aa94-b4df2f78dba3 | note | ACCEPTANCE CRITERIA: Architectural wire rope cables to be inserted into ferrel on fence post and to be tensioned with tamper proof fastenings (Loctite 243 Threadlock)
9c8eea9b-d819-5d49-9fb3-3224faf7ade2 | note | REFERENCE DOCUMENTS: STD_T6000, T6001 & T6002
168a2387-8ca4-559e-bc90-151c5ceb1219 | note | INSPECTION/TEST METHOD: Verify
d2d139c7-d47c-5289-a6ab-fcb1c34e7515 | note | RECORD OF CONFORMITY: This ITP signed off
afb2e819-fee4-5464-b62f-1cb3f1d537c5 | note | IP
42bd34b4-c022-548e-b0be-64aad8546e64 | note | RESPONSIBILITY: Fulton Hogan Engineer
885fdd8e-5f5e-55e8-a44f-e962c1d9ec7f | textbox | Date Completed:
2fdf12ee-2167-4bdd-9472-05524417183a | checkpoint | Final Inspection
ad178de0-99db-537a-a948-ddedb327fef3 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
bf42e633-c6ad-5391-899e-322476b1386c | textbox | Print Name:
703c9e86-6dc3-5af9-9577-2ec2f819ea6c | textbox | Position:
9846a06d-672a-5758-93aa-65a24ca508a1 | textbox | Date:
144a62ff-d937-42c8-aed8-e070e93130b3 | checklist | ITP-020 - Exothermic Welding |  | ITP-020 - Exothermic Welding
1de85215-d329-45f4-91af-4cbfdb59cd35 | section | Preliminary Works
5b89e1c0-f82f-446b-abd8-3a322c5483a6 | checkpoint | 1.1 Check for correct documentation
5737a2e5-ab17-5742-af36-4c0929d81c87 | note | FREQUENCY: Prior to commencing any activity
555905d4-f59f-59f6-bb4b-bc9015110c63 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
d7e1a8d4-1fda-583b-aff3-450afc6ef321 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
15841062-e649-5bed-8773-1d08a8f7e184 | note | INSPECTION/TEST METHOD: Visual inspection
1e6025d9-1a6d-5444-af4d-c3930647b11e | note | RECORD OF CONFORMITY: This ITP signed off
8b34f132-1111-5e48-8dca-5cbfb7812037 | note | HP*
6cd44bb3-0168-5dcd-9081-09ddc2b8d537 | note | RESPONSIBILITY: Fulton Hogan Engineer
93a4d347-85d1-5229-be6d-c1c60ab675d3 | textbox | Date Completed:
8478ab02-ab79-4742-8802-10c6119e72f7 | checkpoint | 1.2 Implementation of all measures and controls
141cc903-1e99-5079-919b-8beaf2659c58 | note | FREQUENCY: Prior to commencing any activity
3d270118-7b9f-53f5-87f6-21bde4e48224 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP. Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit
24a13351-3266-54c0-bb1d-b58e7612f558 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e067120b-951e-5014-b441-cce06ebcfbc8 | note | INSPECTION/TEST METHOD: Visual Inspection
9aa47274-60f4-5a98-b690-66f7d48c9776 | note | RECORD OF CONFORMITY: This ITP signed off
82dee1d2-4ae3-5f2e-87f6-bd59ff3fee40 | note | IP
abc8ba22-f6fd-5eda-ac40-2184e81cb02c | note | RESPONSIBILITY: Fulton Hogan Engineer
69e0bd2a-602b-5efb-9aee-84dd05d3d085 | textbox | Date Completed:
9190b21a-5cc8-48ba-bcf9-058160918646 | checkpoint | 1.5 Materials Check
2e8d2da0-10c0-5337-8f47-32fe9b261f5d | note | FREQUENCY: Prior to commencing any activity
32eec5ba-ce2e-5b5c-a972-97a79726096f | note | ACCEPTANCE CRITERIA: Ensure the materials and equipment gathered are for the correct type of connection being made. Inspect the mould ID tag to ensure that it corresponds to the application, indicated by the following parameters:
6cd3cb08-6977-5108-8f13-939415c26a55 | note | 1. Mould part number:
e3085b7a-c123-5864-bcbe-cea63d3bfc62 | note | 2. Conductor size:
ff5a1219-8caf-58ea-b2ff-9f07ee5e84bf | note | 3. Welding material required
85203a54-acc5-5d52-bca5-7c3357c255bd | note | Check to ensure the graphite mould is not worn or broken, which could cause leakage of molten weld metal during the reaction.
d5c1916c-6153-52c4-80ca-f2ccbecaf5d3 | note | Ensure a working fire extinguisher is available within 10 metres of the working area.
480fce13-7862-5158-9f13-b3d7e89d6951 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
44704c48-abea-517c-a779-1e8fa4d0ed74 | note | INSPECTION/TEST METHOD: Visual inspection
1b5896b1-847b-55bc-a701-10fd71936bac | note | RECORD OF CONFORMITY: This ITP signed off
58a209ca-249a-5177-937e-376618bb6510 | note | HP*
ee240a90-4a30-5981-9d65-505e86dafa24 | note | RESPONSIBILITY: Fulton Hogan Engineer
5d4aa062-9b8f-5069-8a18-7f13014a7f58 | textbox | Date Completed:
37560977-beb2-4c13-9241-d0362dc8a225 | section | Construction Works
d585d52c-faeb-4325-9ce0-cdf114bcca4d | checkpoint | 2.1 Preparation
e05b7f0f-7739-5e5a-b823-799072a1c8f7 | note | FREQUENCY: Each Weld
51c919b1-c094-5481-b275-e1f5bcd0842a | note | ACCEPTANCE CRITERIA: Ensure the position of the conductors being welded is correct. Heat mould to ensure it is dry. Strip & clean conductors, ensure they are dry & clean.
41cdae8b-0e39-521f-902d-790581224b43 | note | REFERENCE DOCUMENTS: Design Drawings and Register
885bda41-4138-5f44-88e2-8fa4ac8ccb2c | note | INSPECTION/TEST METHOD: Visual inspection
663fdf37-3ac6-5cff-a954-b8b1397bf3b0 | note | RECORD OF CONFORMITY: This ITP signed off
0b0e2e67-87e7-589a-934c-2ca86e399977 | note | IP
5d8ff630-fd50-5355-8d00-c068f7f4763b | note | RESPONSIBILITY: Fulton Hogan Engineer
f6ccf044-bb96-54f0-b658-dcbb60541fce | textbox | Date Completed:
3959a5ef-0740-42fd-bf8d-ba3b9f85fc6e | checkpoint | 2.2 Welding
3f69303a-5f5a-5d8e-8340-6d2124b1dc4a | note | FREQUENCY: Each Weld
cdf94c59-85f5-5b28-a32f-358f1abb95d7 | note | ACCEPTANCE CRITERIA: Ensure conductors are correctly positioned in the mould, allowing the mould to close tightly. Ensure welding material has been inspected and is intact. Ensure reaction is completed and molten material has solidified (allow 30 seconds post ignition)
a8db93ee-8900-5f45-bd07-6394d484814c | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
bb2eb571-5e08-5997-a9d3-0bc8303aeb90 | note | INSPECTION/TEST METHOD: Verify
a7fcd6b7-4f18-5fe2-9865-2714d763e3da | note | RECORD OF CONFORMITY: This ITP signed off
6a81fced-e910-5354-b5c0-c03a6ef0cb9f | note | IP
0b60f5e4-906b-54ae-b9e7-6910cc6e0c52 | note | RESPONSIBILITY: Fulton Hogan Engineer
7f02524f-5c97-554b-ad4d-f9c6203bbc7b | textbox | Date Completed:
7b1c6888-4c2c-482c-9591-a0b245f7c0d2 | section | Testing
7cb79786-abe3-4e66-b6ba-49db04981b28 | checkpoint | 3.1 Weld Review
40886372-ffb2-5bc0-818d-02b1ba7496aa | note | FREQUENCY: Each lot
d0d9c1cf-e7c1-5b27-b32a-9db32aa6374d | note | ACCEPTANCE CRITERIA: Ensure weld is inspected and that a quality connection has been made. All welds shall be inspected a Fulton Hogan engineer.
2f0f6626-0e58-5812-b2d8-1bd286bbe3f9 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
a670037f-24d6-54d1-860f-a15486475ab8 | note | INSPECTION/TEST METHOD: Verify
883ffe5e-c3b9-5190-93b9-6fe79d9603cb | note | RECORD OF CONFORMITY: This ITP signed off
75ff4990-aac6-59e4-a5cd-a4a518682e0d | note | TP
e94d4a8e-7df4-5a0c-b636-646e348f6b2c | note | RESPONSIBILITY: Fulton Hogan Engineer
82c6b158-5f97-5091-acf3-45e22b985b6f | textbox | Date Completed:
48cf313d-e667-4c0d-a644-a09ff72e7668 | checkpoint | Final Inspection
5cb96962-5184-5919-afe6-94ac0528e8ea | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
e2a9991b-31f7-533b-bf6e-db9008abe381 | textbox | Print Name:
499aa2b6-8c69-56dd-8834-4c08ca22afcb | textbox | Position:
56e67e63-fc15-594a-829b-b897e3213996 | textbox | Date:
42c8acff-71af-4fb9-aea4-30fa0b4e2efe | checklist | ITP-025 - Platform Concrete Footing |  | ITP-025 - Platform Concrete Footing
41ca733f-34da-4447-bd2b-a38816e32f29 | section | Preliminary Works
0cf5f343-70e5-4d90-ab04-3b0a1b146991 | checkpoint | 1.1 Check for Correct Documentation
6a36c141-8362-57de-baf0-a15b4a1f93ce | note | FREQUENCY: Prior to Commencing any Activity
80313078-903e-5930-8aec-327d1c284dcc | note | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
ddc2d1fa-cb8b-5513-bfed-2453a32bbb92 | note | REFERENCE DOCUMENTS: Design Drawings and Register
cd78cdc5-e5b5-5bd7-bf97-8ad132a7d8ca | note | INSPECTION/TEST METHOD: Visual Inspection
a47b013f-027c-5e57-9494-d0fe92cb2368 | note | RECORD OF CONFORMITY: This ITP signed off
fa9514f3-778b-5d93-9e8e-dca761d41800 | note | HP*
6ada61db-0340-5e44-b377-86f5f78b542f | note | RESPONSIBILITY: Fulton Hogan Engineer
70fc659f-12c2-5ee4-be4c-a5d6495713f0 | textbox | Date Completed:
9f97b57a-11ef-4dfa-84e5-a84b321a6eec | checkpoint | 1.2 Implementation of all measures and controls
ad20030e-946a-5a72-b52d-4d3ced538247 | note | FREQUENCY: Prior to Commencing any Activity
65eb5c25-3647-5f8f-a6a6-c692ce081e0a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
e564021e-1ee5-5c85-9518-4a921f532fac | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e0cd75ef-ed59-5e26-a8dc-89fb62136bc3 | note | INSPECTION/TEST METHOD: Visual Inspection
884cd2bf-9f1e-5def-bca3-4adf8c634bcb | note | RECORD OF CONFORMITY: This ITP signed off
82a1edca-041a-5855-8b2f-9ad0dddedef3 | note | HP*
80d37b3d-695e-5728-b2da-189091ac09f1 | note | RESPONSIBILITY: Fulton Hogan Engineer
9b4237d2-c1c3-5b33-9ba5-723773d6bd0a | textbox | Date Completed:
f0a30300-e7e0-470e-841f-82b57e9c38b3 | checkpoint | 1.3 Setting Out
cb46810c-7805-5f65-be53-d5a2cfab48ca | note | FREQUENCY: Prior to Commencing any Activity
26d21657-ec54-526a-a40b-ecdfe75de39e | note | ACCEPTANCE CRITERIA: Ensure that position of footings has been correctly identified according to design drawings
67ab7e21-dbbe-5636-9f61-163e05571f15 | note | REFERENCE DOCUMENTS: Design Drawings and Register
cb790f6c-5704-53a5-b5f1-3f4abe1b0fe0 | note | INSPECTION/TEST METHOD: Visual Inspection
b804c4e1-55cb-51b5-882a-5fa89808c433 | note | RECORD OF CONFORMITY: This ITP signed off
d9f29269-e0df-507d-850a-ec1af5f53b63 | note | IP
4741c425-5531-5d83-8dec-d75e231ea5c9 | note | RESPONSIBILITY: Fulton Hogan Engineer
42612588-b5a6-5bfa-87d6-2a3ecab7d243 | textbox | Date Completed:
5e0b5595-ce2a-4b88-a878-ae48ccf0f3d0 | checkpoint | 1.4 Material Check
f8c4c644-f58e-56ab-8c16-8b7766ab9a48 | note | FREQUENCY: Prior to Commencing any Activity
21c25a39-6622-5cf8-bbdc-f406f7078129 | note | ACCEPTANCE CRITERIA: Ensure that materials have been correctly ordered based on the intended use. All bolts shall be hexagon head class 4.6, unless otherwise stated. Ensure bolts are of specified length and grade
8df893d0-2363-59d5-935f-2b76a8da71cb | note | REFERENCE DOCUMENTS: STD T6100
98f5744d-9217-5ac5-88c7-965326325ce4 | note | INSPECTION/TEST METHOD: Visual Inspection
a9d0ce9b-4e3c-5ee6-b07c-c5a02ca7722c | note | RECORD OF CONFORMITY: This ITP signed off
9fbeaa8e-a2a2-5b1e-b3b2-c213d077ceb1 | note | IP
ca7ada39-27d7-54cd-b736-0171d1a2ebfa | note | RESPONSIBILITY: Fulton Hogan Engineer
fbcd0aa7-2b13-545e-a5f5-658d0446137e | textbox | Date Completed:
9e2d8971-fc81-4aa5-b96c-4c6f6b87012c | checkpoint | 1.5 Concrete Slab Check
71d5d95b-f1cb-5c10-8152-56522d8ac720 | note | FREQUENCY: Prior to Commencing any Activity
c53b3eb5-d0e4-562a-a204-69e44d092de7 | note | ACCEPTANCE CRITERIA: Ensure recess has been provided in concrete at location of footings, ensure recess is to correct depth. Refer to Adshel specifications
36554759-e1d1-518e-9b72-79c2a107f4d3 | note | REFERENCE DOCUMENTS: STD T6102
c4908493-ec9f-5216-8b0d-68c73a19e4de | note | INSPECTION/TEST METHOD: Visual Inspection
66540f13-57bd-515d-aa76-397f98a84bd1 | note | RECORD OF CONFORMITY: This ITP signed off
352b4413-7a34-5f6a-8330-fddee7cd60d6 | note | IP
b0c23e8c-d3c3-5c88-8976-2b22250514d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
60688346-c119-5a5e-8482-2996e1675adc | textbox | Date Completed:
ca8baaf7-6371-4eef-aaa7-3bb3bf0c063b | section | Construction Works
422be50b-fec9-4e50-90d4-32506f06ba14 | checkpoint | 2.1 Bolt Installation
f69eb442-c6f0-5b65-a166-e30bcf58ab44 | note | FREQUENCY: Each lot
98f85a62-2937-57de-95a7-43fd31e9b20c | note | ACCEPTANCE CRITERIA: Install bolts as per specified minimum anchorage depth. Ensure anchorage procedure conforms to standard"
8afe35c3-22fc-5302-b743-72f91ff2bf33 | note | REFERENCE DOCUMENTS: STD T6102
93232f4c-0842-5a56-998c-762fae90c427 | note | INSPECTION/TEST METHOD: Visual Inspection
46eade24-def5-53ef-b7e8-62c81383e06d | note | RECORD OF CONFORMITY: This ITP signed off
58857e25-c735-582b-aaf8-92035f3df3bb | note | IP
86349776-bd7c-5e26-97bc-d7b7c5af79ed | note | RESPONSIBILITY: Fulton Hogan Engineer
ed8afd91-2676-5a20-9676-adcf55007aa3 | textbox | Date Completed:
29c34348-5f14-48f6-8b3f-6f68463d4392 | checkpoint | 2.2 Placement of non shrink grout
1d4dee20-e96f-5d9b-9552-a9d195b8a2c9 | note | FREQUENCY: Each lot
de240681-251e-529a-a69b-e4fb94f3a18b | note | ACCEPTANCE CRITERIA: Non shrink grout shall be placed between concrete pavement and base plate, at thickness >35-75<mm
83d01077-2aef-52fc-b77e-4eda79a6e9db | note | REFERENCE DOCUMENTS: STD T6100
b8da7315-8f16-54f7-bb52-6dac8b6e2aaa | note | INSPECTION/TEST METHOD: Visual Inspection
dc09ed1e-9319-54e1-8ed8-d64ead867202 | note | RECORD OF CONFORMITY: This ITP signed off
33aaed3a-9e87-56d0-b48a-d057a1e9af65 | note | IP
0680d148-37c4-5b87-9968-7cc2dc3794e1 | note | RESPONSIBILITY: Fulton Hogan Engineer
4627ba81-1703-586b-ab8d-33ddc4998cd0 | textbox | Date Completed:
687084c7-c21f-4bdf-ab21-6baf6640c9f9 | checkpoint | 2.3 Placement of Grout
20f14e68-7de9-5764-9a03-5caa40251058 | note | FREQUENCY: Each lot
14e09f59-1586-57c0-91eb-8613c916f250 | note | ACCEPTANCE CRITERIA: Grout shall be placed as to fill the gap between baseplate and level height of concrete
5aca15db-53a1-540b-b729-95028f89a9f1 | note | REFERENCE DOCUMENTS: STD T6100
e43cf61f-0cc5-5989-9dca-aa1ca12af140 | note | INSPECTION/TEST METHOD: Visual Inspection
91009604-3842-5c1c-8b93-6a47b72a5c07 | note | RECORD OF CONFORMITY: This ITP signed off
4cc2a084-bef2-5486-af6d-906cbee14e27 | note | IP
7645155d-9b39-56de-839e-ce1f1292033a | note | RESPONSIBILITY: Fulton Hogan Engineer
7417d717-42b4-5697-a78e-9edd4a52daf2 | textbox | Date Completed:
dc8e77d7-4cda-497b-b574-61c1ad9dad47 | checkpoint | 2.4 Pavement (if required)
d3254f0b-225a-5bfa-9b08-3b343fb9ebf6 | note | FREQUENCY: Each lot
63f41f09-7f56-5036-8afb-b53bdc17daf5 | note | ACCEPTANCE CRITERIA: Minimum depth of specified pavement shall be 50mm, ensure the bolt assembly is not covered by pavement
c1fd2181-cbfa-5069-a546-1b5d11a3eada | note | REFERENCE DOCUMENTS: STD T6100
053188d2-1cfe-5848-909b-ea3986ae52cd | note | INSPECTION/TEST METHOD: Visual Inspection
77169c7f-cbe5-5d44-9eca-fac25dc32b24 | note | RECORD OF CONFORMITY: This ITP signed off
9d34ae26-5120-5c0b-bd17-600f98d80b56 | note | IP
47cbe41a-7762-5efe-b26e-2b2b7a69b6bf | note | RESPONSIBILITY: Fulton Hogan Engineer
f30b7946-61df-51d9-8b19-e0b875b59575 | textbox | Date Completed:
0077eb53-bb02-4057-b92e-2be723e92f10 | checkpoint | Final Inspection
cb786e83-fd78-501b-9d58-5708e7634fe0 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
d5deb707-ab10-52c4-95ef-ca97eec9d8cd | textbox | Print Name:
e8daf0df-a571-575e-90ca-acd52e0df1c3 | textbox | Position:
76b7f067-1ecd-559f-bd03-a554293f44a1 | textbox | Date:
76779e58-1098-478f-a652-5807cc405494 | checklist | ITP-029 - TGSI Installation |  | ITP-029 - TGSI Installation
9d5f2181-a699-437b-9014-e9af1562ebe8 | section | Preliminary Works
72dec241-57cb-4be8-8df1-8997ab41ea73 | checkpoint | 1.1 Check for Correct Documentation
58512ea7-b77d-5e20-8a7b-475aeeafb400 | note | FREQUENCY: Prior to Commencing Activity
26a879f6-047e-591d-b091-6bea99caefdc | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
d8a5b310-bb4d-5a9b-a73a-ff0a13699629 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
eebee218-17ad-58a8-9eae-3dfd95b70389 | note | INSPECTION/TEST METHOD: Visual Inspection
3c0a9ed6-5091-57b2-81a7-639ad953fe84 | note | RECORD OF CONFORMITY: This ITP Signed off
0fb1f4d3-102e-5c60-a055-e8253610859e | note | HP*
50546b5b-7f3f-5967-bdad-49d9aec1b90f | note | RESPONSIBILITY: Fulton Hogan Engineer
73d98214-a900-568a-b724-26a5e8ab3999 | textbox | Date Completed:
054b5a87-a7c5-4727-8954-c54572c54629 | checkpoint | 1.2 Implementation of all measures and controls
040389a3-a39b-5d7e-87dd-cf3a8c928630 | note | FREQUENCY: Prior to Commencing Activity
74fbdbfe-2296-5d74-830c-17feae25274c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
850dea4a-3ce9-58a2-b077-07e0c1d65952 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
f040fcf1-e4f3-5314-bf50-eec8ac9ece07 | note | INSPECTION/TEST METHOD: Inspection
17074e00-8c2b-5829-a082-2c9b0aa1ad65 | note | RECORD OF CONFORMITY: This ITP Signed off
9cd76f2f-69f6-56c2-94e4-acdd4a66b2fb | note | IP
22b0733f-a1c9-5bbc-8610-d3c973b5f7fa | note | RESPONSIBILITY: Fulton Hogan Engineer
93786f4c-b348-52a9-9717-6ab2aae0ddc2 | textbox | Date Completed:
f5f47abd-4aae-4fdf-9719-e35a2a415e49 | checkpoint | 1.3 Check Materials
fc43b9d8-4a85-5760-a5c8-afaadb1d36b6 | note | FREQUENCY: Prior to Commencing Activity
58d25e05-90bd-5d00-935d-9f5818a6fa3f | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Bluestone / Granite Tactiles. Tactiles in asphalt areas shall be Pandatac Granite Tactiles.
708a5c66-ebfb-5386-bb52-e446a7b1eb7d | note | REFERENCE DOCUMENTS: Receivable Inspection List
dc14ded3-3911-5dce-bfa3-6abe545a9f77 | note | INSPECTION/TEST METHOD: Visual Inspection
7a2f3996-490e-51d8-8a7a-afd3380a1b1b | note | RECORD OF CONFORMITY: This ITP Signed off
050b8703-726a-55da-8263-610f63e7bd56 | note | HP*
7cb5ad01-8613-595c-b057-98adcbc89700 | note | RESPONSIBILITY: Fulton Hogan Engineer
80156d47-4943-54c0-bf0c-f36d15ea9cf4 | textbox | Date Completed:
92b9f671-f9e9-40b6-8b55-fd56429eceea | checkpoint | 1.4 Setting out
5c0690fc-fb8d-5252-83c2-7908c174a6f5 | note | FREQUENCY: Each Lot
f29f5923-6b5e-5350-8d3a-5c71d05f596a | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
185241d9-34a4-57e4-903b-cc38d329f1db | note | REFERENCE DOCUMENTS: Work Procedure
8873ab8a-58d4-581f-8fbc-231a17c26ca5 | note | INSPECTION/TEST METHOD: Inspection
98a06d18-bca3-583c-9cde-e79b235320a9 | note | RECORD OF CONFORMITY: This ITP Signed off
d003c7a7-c5f5-5cc2-80ed-487e2c5d3a01 | note | WP
4176e7be-6c24-523e-80c2-6230ce466a55 | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
844d0cd3-0a9d-59a8-a2f1-6b7732e9732e | textbox | Date Completed:
b5f632f7-d226-44c9-b023-d04adca08381 | section | Construction of Access Ramp Bluestone Footpath
63ed54f7-5f8a-4844-b14a-b3d4e897f19e | checkpoint | 2.1 Base preparation
bc295a75-ca07-5c7c-bb3b-d950a1849cd7 | note | FREQUENCY: Each lot
026356d3-860e-5bf7-88c3-f807c21faf54 | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
9a6d7c68-2897-5bd5-8b7b-5e610dc5d830 | note | REFERENCE DOCUMENTS: Dwg 1P50201
5ab8edea-1529-5cef-aebc-7ee1cb0a4b12 | note | INSPECTION/TEST METHOD: Visual Inspection
9aeeed16-682a-53c5-81fd-fc422cb53b41 | note | RECORD OF CONFORMITY: This ITP signed off
f9b7b0d8-129c-5f22-a7d8-e71a0f11965e | note | IP
745c0ee7-5d55-5fc1-9f5e-2a1999ea132d | note | RESPONSIBILITY: Fulton Hogan Engineer
970d87b0-c72e-5592-be1b-ab9e699dd0d4 | textbox | Date Completed:
0001697c-1d7a-4335-8f76-0bec0e304d44 | checkpoint | 2.2 Placement of bluestone pavers on mortar bed
142277e1-b7c3-562d-ba06-a975d6757590 | note | FREQUENCY: Each lot
fb029f77-0549-5f7c-b4c6-232eb3a47b31 | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402 on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying. Kerb access ramp wings shall be at an angle of 45° or as per design and the ramp gradient shall not exceed 1:8. Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
3cff16c3-a237-5170-8713-68c87968756f | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
f0b2a502-3a56-5470-ae1e-488939f79a3d | note | INSPECTION/TEST METHOD: Visual Inspection
6218e6eb-ff61-5258-9d83-99501f514ad2 | note | RECORD OF CONFORMITY: This ITP Signed off
bf02fa11-c03e-58f7-8f86-8df634856b9d | note | HP
f1f0efad-cb76-54eb-973c-c429564e3a27 | note | RESPONSIBILITY: Fulton Hogan Engineer
812fbfd2-bd44-54ec-8a31-2f52c034580c | textbox | Date Completed:
fe0e76c9-6bc6-4b8f-8aef-b5d256eed844 | signoff | REQUEST HOLD POINT SIGN OFF
d3ba9b27-d408-4820-bcbf-d59897a9a2b6 | checkpoint | 2.3 Curing
eafb2a3e-8d65-5689-97db-1d3856a63489 | note | FREQUENCY: Each lot
697d9fb7-53cb-50d0-9836-9fff5997f247 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic. Where required, ply shall be laid over area of works
018244ae-13e0-56c7-a0cb-00fb585d21b5 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
ae6191c5-b455-5596-9c1c-da2f30b1d483 | note | INSPECTION/TEST METHOD: Visual Inspection
66a69c17-6945-58e0-9b14-836394f552fc | note | RECORD OF CONFORMITY: This ITP Signed off
fb919fdd-51a1-50a6-8b39-ba4a30885ac3 | note | IP
3f475cb3-ec35-5e5a-bedc-85916a133eb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
5329c1e4-4b54-565d-9b5a-a88de1f51bc5 | textbox | Date Completed:
71b4ee5f-e481-4883-8714-4be2c8f9e29b | checkpoint | 2.4 Grouting
624d0230-f2ee-5d4d-b2ca-97774ce6a563 | note | FREQUENCY: Each lot
0410b7ca-d319-575a-a538-9d789043b9f4 | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using Lanko Durabed to specified mixture content. Grout shall be spread & clean appropriately as required.
2ac2d53e-425a-57ef-aa9c-8a50eb21cf13 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
0013bf4b-96ad-520d-9459-d33d207f0dae | note | INSPECTION/TEST METHOD: Visual Inspection
af2e5ce4-6b9d-5f8c-9752-00f05614ff0c | note | RECORD OF CONFORMITY: This ITP Signed off
317ba425-7186-54c1-a058-38eea202305c | note | HP*
e013bb63-1cb3-5764-9992-e926b6d0de98 | note | RESPONSIBILITY: Fulton Hogan Engineer
38609131-229b-5e95-b11c-3a08fd974abe | textbox | Date Completed:
2dddb408-4816-4aa0-a6cf-2c93686f9c1b | checkpoint | 2.5 Installation of Versatac Granite Tactiles and Granite Inlay
d2e20344-0a4f-5c08-b52f-761db9b6d38e | note | FREQUENCY: Each Lot
5b46034a-c1f4-5b7b-986a-a2ad9155b12e | note | ACCEPTANCE CRITERIA: Granite tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201 with surface deviation of under 5mm. Tactile Pavers shall be placed on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying. Tactiles shall be cut with a diamond blade and allow a 5mm grout.
5996e517-121a-5436-92f6-bda4c207319b | note | REFERENCE DOCUMENTS: Dwg 1P50201
d4e16df7-8a3d-5fbf-8c65-4b2fee305e75 | note | INSPECTION/TEST METHOD: Verify
5d57676b-5612-5bf0-8317-ad2d4a804c5c | note | RECORD OF CONFORMITY: This ITP Signed off
6f395c1f-bbad-57ae-ad12-3eff1bf7704d | note | HP
e5bd8232-8f33-573f-acf1-a05a38306b7e | note | RESPONSIBILITY: Fulton Hogan Engineer
cb41ed74-357c-5781-a1ed-baf819222a11 | textbox | Date Completed:
76c39ebc-62d0-4c3d-be2b-25f0c5964a49 | signoff | REQUEST HOLD POINT SIGN OFF
2c2f50b5-bb9a-4e45-9ba2-91ce89116d77 | section | Completion
ee7535d6-fbb5-4a6f-8fd4-5783b14a88ff | checkpoint | 3.1 Completion
382d5dd1-9e0b-53b0-93f5-1b3e3766919c | note | FREQUENCY: Each lot
5642da93-e1b9-5f43-ba90-7de163daf3d7 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste. Bluestone pavement is free of mortar stains and cleaned to satisfaction
77b89f3a-6712-5853-8e3d-e75aa01021cb | note | REFERENCE DOCUMENTS: Visual Inspection
b33e71e0-fbc5-51f4-9e9b-f853da82e949 | note | INSPECTION/TEST METHOD: Visual Inspection
4c407344-98db-5b2d-b9af-994897943ec1 | note | RECORD OF CONFORMITY: This ITP Signed off
eac5c9f3-89e9-509b-9737-7d2845ff7085 | note | IP
70e307a4-fced-5f79-b6f9-be82596888d7 | note | RESPONSIBILITY: Fulton Hogan Engineer
494d6bc7-7028-5fd9-807b-8116c1ac1716 | textbox | Date Completed:
fc4c4352-1444-4831-947b-04ed65da7e5a | checkpoint | Final Inspection
920badbf-d7cf-5263-a798-b907ed9a2c10 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
da5e0cbb-0608-5ba6-9d86-0fecb14305cc | textbox | Print Name:
9b7aa94a-118f-508d-be5f-eaed31536ef4 | textbox | Position:
3aedafbd-670b-5dee-89aa-3d6f4d1f5fe2 | textbox | Date:
80871329-bdcd-4bec-bc5b-7dbcc7b3791d | checklist | ITP-031 - Precast Stormwater Pipe Installation |  | ITP-031 - Precast Stormwater Pipe Installation
cb43fa44-2e2f-4f09-a104-2dc9bfefd580 | section | Preliminary Works
a2a3d341-e729-4e40-ad3a-6323202934eb | checkpoint | 1.1 Check for correct documentation
cdb385f3-3512-50b9-b475-c64ebf73e732 | note | FREQUENCY: Prior to commencing any activity
3223ec45-8b20-503c-be2e-f8e99623ea65 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
344bc3b2-8cf7-59ad-ad94-75c86b12ef54 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
485dd589-3c0b-543a-952e-a853f08dfe6d | note | INSPECTION/TEST METHOD: Visual inspection
a0eb09eb-9b24-5853-85dc-efcb2842ef6a | note | RECORD OF CONFORMITY: This ITP signed off
bc3de693-93aa-589b-bfa6-acf051b58987 | note | HP*
1b6d53a8-7c69-5bc2-a9ed-af1c5a97a653 | note | RESPONSIBILITY: Fulton Hogan Engineer
941b4ab1-2373-515d-a94c-eaaf196f9890 | textbox | Date Completed:
8b90be19-3f22-4b8e-ab5a-1a5838fa4d0e | checkpoint | 1.2 Implementation of all measures and controls
e546188b-8d64-593b-97d4-f1330b917fbf | note | FREQUENCY: Prior to commencing any activity
fe58b9cd-e1e4-5bb9-96ff-68562039ffaa | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
e0e5ea83-5b98-5c82-b570-3f1963bf0fb9 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
9c55124e-7aed-533e-bc2c-5c601641be2a | note | INSPECTION/TEST METHOD: Visual Inspection
07202c91-1ef7-50c2-870d-214470a7cb75 | note | RECORD OF CONFORMITY: This ITP signed off
3381c12c-3b65-5811-9468-e12bedf3932c | note | IP
d51edbab-c0dc-5806-9d8d-aba7630aafda | note | RESPONSIBILITY: Fulton Hogan Engineer
84074ef2-79a1-5e06-9502-20202539d8ec | textbox | Date Completed:
7451c7b7-9a9e-400f-8582-b9b4ee6c91f5 | checkpoint | 1.3 Pipe classification and delivery
6636086a-ff0a-5815-886c-3934b91f8126 | note | FREQUENCY: Each delivery
d8457e97-33d1-5fdc-81cb-81edd352653c | note | ACCEPTANCE CRITERIA: Pipes shall be of the size specified on the drawings and either: Socketed reinforced concrete to comply with AS 4058 - 2007, with rubber ring joints complying with AS1646 - 2007, or Fibre reinforced concrete including fittings, to comply with AS4139 - 2003. Condition and compliance of the pipe is to be inspected upon delivery.
4ad543a7-5c1c-5a36-9153-08a8179fd4de | note | REFERENCE DOCUMENTS: Cl 4.1; Appx 2: Cl 7.0; Dwg 1P50318
d731092f-ba4e-572d-9a53-99dadb855cc4 | note | INSPECTION/TEST METHOD: Visual Inspection
f8f56355-9f3e-5db8-9c85-0f268b41da80 | note | RECORD OF CONFORMITY: This ITP signed off
28613be2-7be2-50af-9b7f-130945927c20 | note | IP
810da3be-fd16-5996-9fc6-8777f77746ce | note | RESPONSIBILITY: Fulton Hogan Engineer
e2f36268-4752-5449-b990-874e5978eb43 | textbox | Date Completed:
8c14e83e-996b-4c28-89c5-1f0b86aff113 | checkpoint | 1.5 Backfill and bedding material classification
e28d78de-a8b0-5334-97a7-1d3e7b80ea31 | note | FREQUENCY: Prior to start
0ddb8a98-ced0-5ee7-b65f-dafcc28fd861 | note | ACCEPTANCE CRITERIA: All crushed rock used in the works shall be Class 2, 20mm nominal size. Sand shall conform with the requirements of AS2758 - 1998 and AS1141 - 1997 and shall have grading within the limits as defined in the code.
09477858-8880-57d1-b01e-1baea9e7059a | note | REFERENCE DOCUMENTS: Cl 18.0
6adb6493-bb3d-5675-8f7a-d08296b5bad5 | note | INSPECTION/TEST METHOD: Verify
1e3fb593-8b99-56e4-bb31-eb319f2b8fcf | note | RECORD OF CONFORMITY: Test reports from supplier
a5fd55e8-1d1c-5c45-a3dd-c19bd608ee9e | note | IP
54cc624b-4aac-5c79-97da-2e1579f73a0e | note | RESPONSIBILITY: Fulton Hogan Engineer
6e5f7b57-9f3b-58fc-9d21-ccc1d78a944e | textbox | Date Completed:
1652d220-3d6d-413f-9016-05fdfd080820 | section | Construction Works
c9dfcfed-faa1-478a-8a40-b4aa15fe3807 | checkpoint | 2.1 Set out drainage
3ade98a2-a1f1-5962-96c6-24143585ab97 | note | FREQUENCY: Prior to backfilling
8ebe8b22-50a9-5660-8108-0e355db0a2a4 | note | ACCEPTANCE CRITERIA: The line and level of all drainage lines and pits must be in accordance with the provided design drawings. The position of all drainage lines and pits are to be confirmed with the superintendent if ambiguity arises.
7f59848e-fcd8-5819-a790-806ae318cb3d | note | REFERENCE DOCUMENTS: Design Drawings Appx 2: Cl 8.0
1dbc62af-ede6-5d19-999f-db4c5072208a | note | INSPECTION/TEST METHOD: Survey Conformance Report
bef5083d-01e0-51bd-bbf0-44391cd55b75 | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off
d5efc9ec-1fd1-5641-bb73-25ab44d9ec21 | note | SCP
09f4a1c6-f2e4-5e6e-9684-bc84b2741af7 | note | RESPONSIBILITY: Fulton Hogan Engineer / Survey
283fa5a1-3d5e-5f25-ba55-15d07724b473 | textbox | Date Completed:
a97767c5-9bf1-4b3a-99fb-7d2767b2a5a6 | checkpoint | 2.2 Excavation
29979228-4ba5-59d5-aa15-c5431eb5b241 | note | FREQUENCY: Each trench
d15de657-eefb-5b55-b411-79be71ad78d3 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth greater than 75mm below the specified level of the invert of the pipe to allow for appropriate bedding. Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed. Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m. No stockpiles within 2m of end of the trench to reduce bearing pressure.
dfdff10a-bf31-5740-b6ff-568f0525f657 | note | REFERENCE DOCUMENTS: Appendix 2: Cl 8.0, Cl 9.0, Cl 11.0
376f4c1c-184d-5aa7-badd-196a474956ae | note | INSPECTION/TEST METHOD: Visual Inspection
e14fb186-30d6-555a-89a4-cf9f4ee492df | note | RECORD OF CONFORMITY: This ITP signed off
c16ecb21-eb9e-5b00-b2b1-a28f72944a0c | note | IP
30cf57c3-f7fb-508e-a143-4cdbc726b2ab | note | RESPONSIBILITY: Fulton Hogan Foreman
66ea3e69-e808-5bf1-911d-f613dbae3f18 | textbox | Date Completed:
0b96481b-6cff-4f9f-8320-aaf6b4111b90 | checkpoint | 2.3 Inspection of trench base
a5f6937d-9830-5a89-b76d-2ba4dbb060f2 | note | FREQUENCY: Each Lot
69b780c8-bb58-52ca-8015-55e547b04015 | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
fffe9e58-2185-5f52-8cc6-748167e45cbe | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0
d2995ae2-9497-5c33-9a30-fd59c5104be5 | note | INSPECTION/TEST METHOD: Visual Inspection
cc89e7d0-d6b2-5986-bf70-79dd231a6ccb | note | RECORD OF CONFORMITY: This ITP signed off
c43cff28-f122-5889-b092-abfd6fee1dd7 | note | IP
8404bc4a-4f50-5b16-ae22-f372a2214498 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccef1801-bf59-5aca-9f3d-bd75e78aeebe | textbox | Date Completed:
aa14746f-b4ac-44c6-ae43-e93fc970384f | checkpoint | 2.4 Placement of bedding material
bbe7347d-de94-50b0-81a8-b855607480c1 | note | FREQUENCY: Each Lot
9e147125-8df4-5016-8200-00f6db8b5206 | note | ACCEPTANCE CRITERIA: A 75mm minimum layer of consolidated sand shall be used to bed the pipes of the diameter specified on the drawings.
ad6afd50-f18d-55a7-b673-a0f6802cf2e8 | note | REFERENCE DOCUMENTS: Appx 2: Cl 9.0
9561e6f9-a877-5153-8e47-da823440fa48 | note | INSPECTION/TEST METHOD: Visual Inspection
056fb510-f9e5-5c6c-b736-6184d2dc948f | note | RECORD OF CONFORMITY: This ITP signed off
9fe5f03f-dd59-502e-94b1-1905b78a1405 | note | IP
4b9686e5-24c9-5ee8-aaaa-5e8fd24a2506 | note | RESPONSIBILITY: Fulton Hogan Foreman
4ffd3a91-b584-51d3-8c47-03af5d0567d0 | textbox | Date Completed:
dfdb1146-6342-4482-be2e-57b1e39aeb5e | checkpoint | 2.5 Placement of pipes
1847c87e-05eb-5a46-9b5e-61591b6f1cf1 | note | FREQUENCY: Each Lot
78db297f-9736-5dbc-b6de-df49dd95d25c | note | ACCEPTANCE CRITERIA: The pipes of the diameter specified on the drawings shall be laid on the bedding firmly for their entire length. All pipes shall be laid true to lines, level and grades, and shall be butted tightly together with lips. Rings must be in place between pipes and not dropped to be visible.
d3889d01-1343-56ec-913d-61852363bf69 | note | REFERENCE DOCUMENTS: Appx 2: Cl 9.0
6b959ded-69f6-539d-9996-03b9c12eceb7 | note | INSPECTION/TEST METHOD: Visual Inspection
3449efcf-80c3-5a6e-8aaa-0e392dc21a30 | note | RECORD OF CONFORMITY: This ITP signed off
62329db1-ded9-5bf4-8aba-367c89ce692d | note | IP
1268ef48-a80c-59bd-9d6c-990503fc0d24 | note | RESPONSIBILITY: Fulton Hogan Engineer
fe2e1a0d-8e05-5690-905c-54fd924f7d54 | textbox | Date Completed:
c5c21459-0294-4516-9404-c9714f85b0ce | checkpoint | 2.6 Sealing
a3bc3b0e-3c25-58a0-a4d2-1544ad711a27 | note | FREQUENCY: Each Lot
f58738ea-fcf8-50f4-bce4-03a839bcc261 | note | ACCEPTANCE CRITERIA: All pipes connections to pits shall be neatly made, and the ends of all pipes properly trimmed off and stopped with cement mortar.
d8e5e53b-17d0-5a6e-93de-968cc2f1bb8a | note | REFERENCE DOCUMENTS: Appx 2: Cl 12.0
ff9113be-1dc7-5dba-92bc-c02698608d15 | note | INSPECTION/TEST METHOD: Visual inspection
5f0a78a4-48dc-534b-81bd-23938637dd2c | note | RECORD OF CONFORMITY: This ITP signed off
2535a53d-ab42-52e6-b267-30991bebe6c3 | note | IP
3ee4f68c-9bd7-5aa0-84b8-015514975287 | note | RESPONSIBILITY: Fulton Hogan Foreman
f10727f6-d36c-5e8b-a901-32b692034e99 | textbox | Date Completed:
ccdb1fc8-038a-47b6-bd26-af6a42bf7357 | checkpoint | 2.7 Bandage Joint
c623ab40-df90-5c8d-8279-ae53ad4c9bd1 | note | FREQUENCY: Each Lot
f5e6bced-f5d5-586e-aa46-846778ab981e | note | ACCEPTANCE CRITERIA: Construction bandage must be constructed where 750mm pipe connects to existing in accordance with Melbourne Water standard 7251/08/420 with SL82 mesh and 40MPa concrete.
a1ad2f94-249c-5e36-ba40-80d67d7ce3d9 | note | REFERENCE DOCUMENTS: Melbourne Water Standard Drawing 7251/08/420
bc1edb9d-a705-53e9-be68-a8fd08baeb54 | note | INSPECTION/TEST METHOD: Visual inspection
0b5aa4e3-585d-5281-9327-fcdba8313a28 | note | RECORD OF CONFORMITY: This ITP signed off
caa311c7-185e-5ad7-85fd-eae1cf9bb93a | note | IP
b0617a17-ab1d-55c3-adcb-a2ff980b69af | note | RESPONSIBILITY: Fulton Hogan Engineer
0ee28f16-a922-578d-ab73-63c46a772df6 | textbox | Date Completed:
9c3e2911-c2c4-4d8d-8ca1-bf1524d8daf9 | checkpoint | 2.8 Inspection of Pipe Installation
350a1c87-2100-5cba-bd6f-1ff110ec486c | note | FREQUENCY: Each Lot
9ea370c5-ca53-5c78-b967-bef1e625ca7b | note | ACCEPTANCE CRITERIA: No further backfilling shall be done until the Council's Supervisor has inspected the work.
8b325c9f-b4e1-5448-a5cd-80a7a67cb9c4 | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
a63ca885-f223-5ffc-b872-a7a8da4a4506 | note | INSPECTION/TEST METHOD: Visual inspection
d4d7d5ba-9824-5438-8ff6-63081657a092 | note | RECORD OF CONFORMITY: This ITP signed off
5e014a38-e8d0-5272-a8a4-27d642c48893 | note | HP
6de879cd-f08a-59f6-9174-8ba2649ed7e1 | note | RESPONSIBILITY: Fulton Hogan Engineer / City of Melbourne Supervisor
bf3e9c8e-4144-5759-b858-65d2af2c03a2 | textbox | Date Completed:
a86a5ca1-724c-44cf-afd7-a2cea166302f | signoff | REQUEST HOLD POINT SIGN OFF
acca8e23-d483-4d37-86d4-952e4aa8a6bc | section | Testing
52af1f48-fac3-4548-b40e-b605207c3272 | checkpoint | 3.1 Crushed Rock Placement & Compaction
d550144e-abb4-5ebc-b5fb-5ad940bf7087 | note | FREQUENCY: Each Lot
1acbdd59-fec3-5d30-9ae7-0dad2f55866a | note | ACCEPTANCE CRITERIA: The trench shall be backfilled with Class 2 crushed rock to the springing line of the pipes immediately after completion of laying. Further backfilling shall be with layers of crushed rock, Class 2, no thicker than 150mm compacted to 95% Modified Relative Compaction.
acfa716b-e823-5685-916d-400da1bc343c | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
ae0cc798-69a0-5a82-be68-2317dfbb4cb6 | note | INSPECTION/TEST METHOD: Verify
d9356e2d-5908-5af6-87b3-f683a990f847 | note | RECORD OF CONFORMITY: This ITP signed off
14ae4068-d88a-5818-82dc-c06e9ef412bd | note | TP
33d10156-f16e-5610-be03-e42c64707863 | note | RESPONSIBILITY: Fulton Hogan Engineer
ac201eb2-56cb-55b2-8637-e60dc118db93 | textbox | Date Completed:
0dc87804-d4fe-4ff7-b887-513f06582e0b | checkpoint | 3.2 CCTV Inspection
11116eba-1ffe-5657-a4ea-dfdc706aadd3 | note | FREQUENCY: Each Lot
a3af7d5d-1d63-5f14-80b3-f278b2ccde80 | note | ACCEPTANCE CRITERIA: All drainage lines constructed beneath pavements are to be inspected by CCTV.
ae940c40-b7df-5357-8fa6-a468f0e93763 | note | REFERENCE DOCUMENTS: Appx 2: Cl 18.0
751d2cde-3587-549a-91e0-aab80be65f3d | note | INSPECTION/TEST METHOD: Verify
709f5b6a-a5fb-5d2e-8ef1-090a285630f1 | note | RECORD OF CONFORMITY: This ITP signed off
8638d594-d8b6-5831-804f-5e4f6a18982b | note | TP
4d2da017-a61c-57a9-8fd6-d0b792a150cb | note | RESPONSIBILITY: Fulton Hogan Engineer
d6207561-9220-5a5e-a4f2-a885ede980fa | textbox | Date Completed:
98bce6ce-fec3-47bb-9fa4-13a9f670efb4 | checkpoint | Final Inspection
b70a0e05-4f4b-564f-9faa-aca495cc2f70 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
0355a40b-3d40-579a-a7d4-b951aacc73a4 | textbox | Print Name:
ff00e4c4-80f0-5e54-8c32-af0b733f9f11 | textbox | Position:
9f74a7a5-a468-55ec-972f-d221dca76024 | textbox | Date:
c5c88ae7-98b9-4060-a672-3dd414d8ef27 | checklist | ITP-032 - Orca Island Installation |  | ITP-032 - Orca Island Installation
85cf0213-5784-4b70-8a66-549d5f606344 | section | Preliminary Works
a7a6e5fc-0ece-47b6-9fa2-4a489c493b68 | checkpoint | 1.1 Check for Correct Documentation
59cfbaa8-a8b8-52cc-984e-418aa3abab55 | note | FREQUENCY: Prior to Commencing Activity
de752495-8dbe-5ce0-87e1-a214fcb25283 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
50739957-d3b7-5213-b2ac-6a55c57a6042 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
f051c969-1b2e-51a9-8e32-bbc81da0c353 | note | INSPECTION/TEST METHOD: Visual Inspection
e2561d01-0e6e-5723-8dd7-16cd6801f121 | note | RECORD OF CONFORMITY: This ITP Signed off
2b91a9dc-5f6e-527f-94ed-3df5bb0b7b36 | note | HP*
9d7a9c82-b320-54cd-8721-7022bd92d0c5 | note | RESPONSIBILITY: Fulton Hogan Engineer
daa30b17-1d35-5595-be4d-b98c19223f63 | textbox | Date Completed:
2c4f5d3e-e19a-4d76-aa8f-e4e72a16bdb6 | checkpoint | 1.2 Implementation of all measures and controls
18892569-6400-5e8e-bb15-8543283ff710 | note | FREQUENCY: Prior to Commencing Activity
7f5fcadd-e5e0-50e1-8af5-94146e8d3758 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
7b93c346-79ba-5028-a300-5d0a83c46dd4 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
a099a9a4-c5c5-58fd-b572-1bd66339343d | note | INSPECTION/TEST METHOD: Inspection
cc182ecc-16ab-5a93-b63b-fe364238659f | note | RECORD OF CONFORMITY: This ITP Signed off
9f57672d-303c-5434-b77a-1476ca4f6e20 | note | IP
d0072b76-bb7d-5738-98bc-36749a1027f2 | note | RESPONSIBILITY: Fulton Hogan Engineer
84731356-2d73-58f0-b197-bbb78e5cfb27 | textbox | Date Completed:
6c9c5be7-7b5b-4092-87f7-ebc12396b499 | checkpoint | 1.3 Check Materials
ab3bb1d0-5e1f-5ddc-be71-53f460185139 | note | FREQUENCY: Each Delivery
af0b7a77-2f2b-5ff7-b246-daf2154649a7 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
105381bf-c010-5bc1-afa7-841aab593d59 | note | REFERENCE DOCUMENTS: Receivable Inspection Checklist
c74c084a-5fbc-54bd-b858-f3c3725644ce | note | INSPECTION/TEST METHOD: Inspection
3bc0eaae-005d-54e2-8810-b2733cfe41a9 | note | RECORD OF CONFORMITY: This ITP Signed off
0c368bf9-522d-5cff-8be5-480fdcb7b9a4 | note | IP
a09df259-f857-5138-88b6-d246bb2f7afe | note | RESPONSIBILITY: Fulton Hogan Engineer
9f6b177f-7e9a-5ac6-9ac4-911b2682be50 | textbox | Date Completed:
ad863e19-1786-446c-85a6-f5500dec3653 | checkpoint | 1.4 Setting out
8363cd56-0c35-5fd4-9628-2e9389e84b0b | note | FREQUENCY: Each Lot
e35f60c7-5ba7-5436-818a-8f8a58359ef6 | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans Alignment of new separation kerb and islands shall be marked out using string line
609681cb-f391-53ee-b5e7-b0fe6ea37bf8 | note | REFERENCE DOCUMENTS: Work Procedure
e55fb4aa-546f-5a72-9747-077e2a8d7531 | note | INSPECTION/TEST METHOD: Inspection
3f21009f-a27a-53ed-8b6a-1b5f6d86c61d | note | RECORD OF CONFORMITY: This ITP Signed off
b7b83f67-5d8e-54e4-95fc-2fad2bd30483 | note | WP
4804fdc3-9edc-513e-b639-a7b775cd4426 | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
75fb96ee-80a6-5dbf-bb87-17dac0f4538e | textbox | Date Completed:
bddce686-383c-4e55-98ee-f10f01ee2c68 | section | Construction Works
91905c5a-b9b7-4914-a5c2-2595b0671442 | checkpoint | 2.1 Base Preparation
8c9a7879-2992-5855-a24a-85c5f715dcf4 | note | FREQUENCY: Each Lot
6c4e87ab-04a9-5db9-8793-719843610c6a | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign loose materials and water pooling. IF required glue foam tape to the road where channel will be placed to ensure containment of adhesive.
a897b5f9-184b-5e23-809e-12896cc2ca7e | note | REFERENCE DOCUMENTS: Orca Installation Guide
2f1ed3a6-dd2b-57b7-bd91-311d8b401644 | note | INSPECTION/TEST METHOD: Visual Inspection
ee121277-4464-51fb-a579-9d93956ec3b4 | note | RECORD OF CONFORMITY: This ITP Signed off
cc3d8ec2-59ea-59c0-a2c5-a24f46bb5dc3 | note | IP
4552939d-5805-5fd5-9343-366dd5f1f8f2 | note | RESPONSIBILITY: Fulton Hogan Engineer
638befcd-3f0b-5cd2-87d8-d7ccee31caac | textbox | Date Completed:
b3d49de4-d310-4462-9188-ef57e778a2e4 | checkpoint | 2.2 Preparation of Orca Polurethane (Adhesive Agent)
2426beb4-a069-589f-97d0-07ac63a56746 | note | FREQUENCY: Each Lot
9e61fb96-8f08-5768-b1c1-1059b835114d | note | ACCEPTANCE CRITERIA: Mix Orca Polyurethane as follows: - 2 parts of Part B Polyol Black - 1 part of Part A MDI Using a paint stirrer in a drill, stir for a minimum of 4 minutes. Once Part A & B have been mixed, add 1:1 Part C Rubber Compound in the mixed A+B compound and stir again for 2 minutes. Ensure even mix throughout the adhesive.
308d4521-d8d7-53e5-92ec-493f57ef816d | note | REFERENCE DOCUMENTS: Orca Installation Guide
d1956aef-160d-5e21-81b0-d9c6286274eb | note | INSPECTION/TEST METHOD: Visual Inspection
4ed7fec6-570b-51df-8146-841ab259ead4 | note | RECORD OF CONFORMITY: This ITP Signed off
3d6c3a94-8c20-5a9d-882d-1dffcf3891c0 | note | IP
a69cf8bc-1d2e-556d-b01f-52779f5da28c | note | RESPONSIBILITY: Fulton Hogan Engineer
b1adbf5b-413a-5118-9492-deae056494f3 | textbox | Date Completed:
a22e4f17-81a1-41ee-8a4f-5df05d5b498c | checkpoint | 2.3 Placement of Orca Polyurethane
3f93e246-1555-5ba5-b798-53dc8c80b7a5 | note | FREQUENCY: Each Lot
318cdded-0d31-5371-9830-88432aede8cf | note | ACCEPTANCE CRITERIA: Pour the Orca Polyurethane compound onto the road, spreading to a thickness of approximately 2mm.
ebb14c76-76a5-5f3c-9158-33b230ca9edc | note | REFERENCE DOCUMENTS: Orca Installation Guide
dfdcb997-e5bc-5f82-a102-ee5769427b95 | note | INSPECTION/TEST METHOD: Visual Inspection
c5784f2e-74fc-5be7-bcd2-63dbda4fd356 | note | RECORD OF CONFORMITY: This ITP Signed off
af043eca-3f1f-56dd-8a2a-6f4d08d15fdc | note | IP
30aa9523-c787-5d64-bf2b-53721d91f8a3 | note | RESPONSIBILITY: Fulton Hogan Engineer
8650bab4-bfe4-5567-bb11-0609e03c1bae | textbox | Date Completed:
e824f497-e4d6-4bd4-983f-d79a772833b9 | checkpoint | 2.4 Placement and Securement of Orca Island
2cd0053c-bd8d-5426-ad86-af06edf33814 | note | FREQUENCY: Each Lot
712e9f31-5a40-5aff-b5c5-d072b442d033 | note | ACCEPTANCE CRITERIA: Lay the island on the polyurethane material. Drill holes through island fixing hole into road surface, then screw island down securely with 12mm x 150mm coach screws and mudguard washer. Ensure screws are all the way down to secure island. Plastic plugs to be put in bolt holes.
2794af55-5736-5c9f-a490-38c5a376b4fd | note | REFERENCE DOCUMENTS: Orca Installation Guide
549d46d8-a420-5860-a7f5-84a95554dee5 | note | INSPECTION/TEST METHOD: Visual Inspection
6aed28a8-b3c6-5827-afe7-0fa44c7ffb48 | note | RECORD OF CONFORMITY: This ITP Signed off
d43ccbd0-db13-5199-aeab-a7eda4fcb2ac | note | IP
9f8345b7-a2ff-5f64-b712-470b59091b81 | note | RESPONSIBILITY: Fulton Hogan Engineer
bbe7fe02-d3cf-59ff-aba1-9c9dfadd0363 | textbox | Date Completed:
9d07b370-f253-4724-b615-ee430c262e98 | checkpoint | Final Inspection
31d3b027-31ec-5a5c-9892-35cd1a8c0dca | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
8bac44dd-5e18-5316-8fc2-ded1d7d59227 | textbox | Print Name:
93da29e9-afd7-5b14-88c3-f97695f4ebb1 | textbox | Position:
bfef5598-cac3-5682-bc07-3481aacfd539 | textbox | Date:
b9a3bbcf-ee0a-4fd2-aa2f-d22e69a2c7eb | checklist | ITP-033 - Insitu Concrete Pit |  | ITP-033 - Insitu Concrete Pit
646bbf3b-f00c-4265-9df6-fc3ffe83fa29 | section | Preliminary Works
816c912c-71f7-4b5c-a899-47cdacbc53c2 | checkpoint | 1.1 Check for correct documentation
d2990ba7-ada6-5dff-afab-1ae3beb16e7e | note | FREQUENCY: Prior to commencing any activity
63293069-7df6-5ec3-b1dd-751e8b83b91d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
6d13e60b-beab-5241-9770-0155b4bd607a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6f560b21-261e-5e7c-9849-f9b33ccec8bc | note | INSPECTION/TEST METHOD: Visual inspection
dab88ffd-4497-50e7-a52f-22399e3a2bf6 | note | RECORD OF CONFORMITY: This ITP signed off
038293bc-89e4-5919-94a5-4827d580315a | note | HP*
04f121a8-22a9-5a39-80a3-1e297b31d3b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
f6480e2b-b21a-5a60-806c-daf90c9e56d3 | textbox | Date Completed:
d689c02a-55ef-4e47-a8bf-27db1cc06bdb | checkpoint | 1.2 Implementation of all measures and controls
638c1463-12a8-5456-8c4c-26eaf673f9df | note | FREQUENCY: Prior to commencing any activity
aa74b322-eb0e-58c0-92c8-f63b86386a99 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
e8b3c9a0-7217-5b16-994a-3d677aca2c20 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
a38d568b-a126-5a43-b889-068eb26e5c00 | note | INSPECTION/TEST METHOD: Visual Inspection
6bdc116e-84e2-5358-9a2e-5f633e0b4a6d | note | RECORD OF CONFORMITY: This ITP signed off
73c4c175-3c36-5b31-9e93-c8779c8a3c29 | note | IP
799747d3-09c2-53b1-91d1-e0957c9ae2dd | note | RESPONSIBILITY: Fulton Hogan Engineer
664aa47f-c4b1-5f6d-af37-f745e228ac0c | textbox | Date Completed:
a2b67dfa-0e67-447e-b0bb-029d77de0c3e | checkpoint | 1.3 Pit material classification
52187fa1-7f56-55a4-94d4-b48ae8228cc4 | note | FREQUENCY: Each delivery
22f19105-e74c-5056-8576-d521d8d7f2c7 | note | ACCEPTANCE CRITERIA: Concrete used shall have a minimum strength of 32MPa and be. Steel fabric shall be SL82 reinforcement and conform with the requirements of AS4671-2001.
7710b1e0-cec9-55dd-8ff4-acf553536261 | note | REFERENCE DOCUMENTS: Dwg 1P50318
53d5aa47-b908-5db3-9dbe-4d199c5adc01 | note | INSPECTION/TEST METHOD: Visual Inspection
14d9745e-32a7-5edc-9973-1436e7babc4b | note | RECORD OF CONFORMITY: This ITP signed off
5c333421-a415-544b-a03b-344d095a2b64 | note | HP*
bc70b1dd-d03d-5a1f-a916-586d069a29a4 | note | RESPONSIBILITY: Fulton Hogan Engineer
067eb19b-2524-5ce2-8f93-5c85c823c8de | textbox | Date Completed:
9b2863ee-4f72-4a12-8c5a-df0fea285b1c | checkpoint | 1.4 Backfill and bedding material classification
efa19785-4b3d-58a2-af49-1eb78a3b3046 | note | FREQUENCY: Prior to start
78e0ca57-8f95-5955-a33d-d040d823cd70 | note | ACCEPTANCE CRITERIA: All crushed rock used in the works shall be Class 2, 20mm nominal size. Sand shall conform with the requirements of AS2758 - 1998 and AS1141 - 1997 and shall have grading within the limits as defined in the code.
60adfc2f-6599-5bf8-94e6-90bcb3f4b00d | note | REFERENCE DOCUMENTS: Cl 18.0
6e47baed-507d-5f60-adad-af102cdb2e28 | note | INSPECTION/TEST METHOD: Verify
a6782468-f064-5a2b-a3a1-7d92135769a3 | note | RECORD OF CONFORMITY: Test reports from supplier
17dc9f1f-7ef8-5aac-8b3e-26ee4fb88e02 | note | HP*
e4f4ebae-a019-533f-904d-8283d04ff9c5 | note | RESPONSIBILITY: Fulton Hogan Engineer
aae5d3a4-a4e8-57c4-8a21-ed7de60a8747 | textbox | Date Completed:
5b76516d-cced-4238-8319-96e7f28760b7 | section | Construction Works
12a3c39c-578c-4049-958d-665038e9bdbd | checkpoint | 2.1 Set out pit location
d01e5ea9-aa28-5be9-9f2d-a789d24b2810 | note | FREQUENCY: Prior to backfilling
ec261a44-49cb-5c84-9fc5-0c43e11f2dd8 | note | ACCEPTANCE CRITERIA: The line, level and location of all pits & structures must be in accordance with the provided design drawings. The position of all pits are to be confirmed with the superintendent if ambiguity arises from the drawings.
f6d52be1-d21b-5be8-9efb-308c8eadd428 | note | REFERENCE DOCUMENTS: Dwgs Appx 2: Cl 8.0
018895b1-d81b-5534-956a-0e98de49f6f5 | note | INSPECTION/TEST METHOD: Survey Conformance Report
8a6617fb-72cc-52c0-8978-22454a04befa | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off
e8d394bf-a8ad-5102-8af5-09588d3bf89f | note | WP
3a8f319a-ae62-5d04-8d41-c6dd1f36b38b | note | RESPONSIBILITY: Fulton Hogan Engineer
88edc0e5-f855-58f6-a2a1-049d89444b86 | textbox | Date Completed:
d16a4fcb-63bc-405a-adf6-0e99543fbd4f | checkpoint | 2.2 Excavation
edb206f1-efba-51d0-908e-cfb682d5b2c2 | note | FREQUENCY: Each trench
04606e24-96a4-5bdd-80ac-e8d90feb1c6c | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth greater than 75mm below the specified level of the invert of the pipe to allow for appropriate bedding. Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed. Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m. No stockpiles within 2m of end of the trench to reduce bearing pressure.
a24221a7-4bbf-597d-ba7a-f52c128627f2 | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0, Cl 9.0, Cl 11.0
bf157885-cdc9-505b-8789-90543c1ab74f | note | INSPECTION/TEST METHOD: Visual Inspection
4d1ff526-2648-5065-8b6e-f3abf7f10f84 | note | RECORD OF CONFORMITY: This ITP signed off
14389dbd-f4cd-56cc-b21d-bd56f0ac1e63 | note | IP
c4ed7ca7-e8d5-5423-8503-281d27c9d29c | note | RESPONSIBILITY: Fulton Hogan Foreman
425f52c2-dc6e-5bbd-b448-a1d0a6edbf4a | textbox | Date Completed:
2e664806-7cc3-4d6e-8ae3-0540f81e97d5 | checkpoint | 2.3 Inspection of trench base
ae5fb236-84ad-50db-bda2-052999efbded | note | FREQUENCY: Each Lot
55c13594-c890-509c-9e8b-60c301270cd4 | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
a738f250-d073-5130-8374-fd321a8334f2 | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0
b95d1139-9bb2-583b-8452-54c30ba3c6d5 | note | INSPECTION/TEST METHOD: Visual Inspection
21ff7196-04a1-5bd6-8ff5-109925bdc0b8 | note | RECORD OF CONFORMITY: This ITP signed off
6cb370ec-6a79-5d19-9924-dd36095f07d4 | note | IP
c501ec82-5ac1-5434-9174-b0c466f2bafb | note | RESPONSIBILITY: Fulton Hogan Engineer
24693771-460f-5093-be28-85a9ee305a42 | textbox | Date Completed:
30e06b91-471b-41ec-bd46-8c5f0aa9784d | checkpoint | 2.4 Placement of bedding material
26a66305-6d77-5fb2-a77e-6207e18a4384 | note | FREQUENCY: Each Lot
a605daeb-63fe-5055-a7a4-628c19507a3d | note | ACCEPTANCE CRITERIA: A 75mm minimum layer of compacted class 3 crushed rock shall be used under base of pit
fd47632d-c7fd-5171-b1ee-8cfc56bec5e6 | note | REFERENCE DOCUMENTS: Dwg ELPOD-2021-17
62698e4b-41a3-5ac8-a751-0ac570659e26 | note | INSPECTION/TEST METHOD: Visual Inspection
b3326d67-fb3e-5455-8f15-3d8b73e932ed | note | RECORD OF CONFORMITY: This ITP signed off
aa46cb81-973b-56ed-814e-eaba03bf59de | note | IP
8d4cf218-5f80-5e00-a634-c82cbca04dc9 | note | RESPONSIBILITY: Fulton Hogan Foreman
997ef97c-2e67-55bd-868a-dcbd41ad91c3 | textbox | Date Completed:
80dc04e1-6994-4848-8319-eaf5ff3bc1af | checkpoint | 2.5 Concrete pre-pour inspection
ea8c0afe-3f1d-505e-a26d-4e05faeb4137 | note | FREQUENCY: Each Lot
449a5ea6-468b-5dc4-b7db-806a8ffc1a47 | note | ACCEPTANCE CRITERIA: The site of the concrete pour for the cast in-situ pit shall be inspected by a client supervisor before proceeding. Reinforcement shall be check for correct cover & lap as per drawings
371828bd-af62-571d-8be8-558a2dfcd8a5 | note | REFERENCE DOCUMENTS: Dwg ELPOD-2021-17
ef24a2ff-6cb0-5e20-baf4-c95246d5d265 | note | INSPECTION/TEST METHOD: Visual Inspection
76118506-9aae-5621-9948-ab7c6ddbc99d | note | RECORD OF CONFORMITY: This ITP signed off
ff1f006c-76f3-5550-8186-b206a4c9e111 | note | WP
12a8556f-1599-5d28-9d68-f50b3b9d0ead | note | RESPONSIBILITY: Fulton Hogan Engineer / City of Melbourne Supervisor
f5f0cc6e-276e-5ada-9530-79b096e0d367 | textbox | Date Completed:
47efbf3e-a587-489c-8cef-40fd5995c832 | checkpoint | 2.6 Concrete pour and pit construction
0ff62b93-8da6-5522-be77-2d3704c5d182 | note | FREQUENCY: Each Lot
def4888d-7ed5-5d92-933a-807141feec8e | note | ACCEPTANCE CRITERIA: All pits are to be constructed in accordance with City of Melbourne's Drainage Specification 2012 and Standard Drawing 1P 50318. All pits are to be constructed in accordance with City of Melbourne's Drainage Specification 2012 and Standard Drawing 1P 50318. Pit should also be constructed in accordance with site specific drawings. The walls and slab of the pit shall be 150mm concrete reinforced with SL82 mesh placed centrally. Minimum concrete strength of 32MPa.
4ff4150f-d9fa-52c7-ab18-0284e00abc9b | note | REFERENCE DOCUMENTS: Cl 4.1, Dwg 1P50318
a6ee1354-8f7c-5207-9c10-4b8166b71b6d | note | INSPECTION/TEST METHOD: Visual inspection
1b39a138-b509-5b62-adce-17b399e188e6 | note | RECORD OF CONFORMITY: This ITP signed off
b6da5a3c-c1d4-5159-8374-354cdeb44198 | note | IP
8f4012ec-c34e-52a7-aa3e-2a3cf0d830a5 | note | RESPONSIBILITY: Fulton Hogan Engineer
d75493db-4e8f-5fa9-8948-972befe8d8d1 | textbox | Date Completed:
e8f172e9-04cd-44cf-8d8b-d5840b9edc41 | checkpoint | 2.7 Pit base shaped with concrete to match pipe invert
f7b0ff29-9899-5709-b2e9-3dbd0cb81ca2 | note | FREQUENCY: Each Lot
37e66c5d-6931-5e15-981d-ebcb2a91e20e | note | ACCEPTANCE CRITERIA: Construct as shown on Standard Drawing 1P50318
2ecf2ac4-b917-5d2a-863e-b6e1b09d1e95 | note | REFERENCE DOCUMENTS: Dwg 1P50318
59638440-a14c-5845-80de-5950a6ddfa17 | note | INSPECTION/TEST METHOD: Verify
c3a9914b-5bca-5ded-8756-2595a076eba3 | note | RECORD OF CONFORMITY: This ITP signed off
fccf87b7-b1c6-50e0-9796-88fe7f476534 | note | IP
98e4c6d8-3485-5eee-9743-5466adacc5e9 | note | RESPONSIBILITY: Fulton Hogan Engineer
6ac3f5ba-f4b1-59d8-bbfe-152f301b14aa | textbox | Date Completed:
6010dca2-a345-4382-815c-6ffd8d2528c1 | checkpoint | 2.8 Placement of pit covers
352f595b-ac23-56ca-8e4a-58a02442e51e | note | FREQUENCY: Each Lot
7bbd7b1e-aed8-5e00-abdb-e52c3b8eaafb | note | ACCEPTANCE CRITERIA: All pits shall be fitted with standard City of Melbourne covers specified on the drawings of appropriate class.
b6412b0a-3e1f-5192-a46a-f9ee4856761d | note | REFERENCE DOCUMENTS: Appx 2: Cl 12.4
e125a20d-a409-56e5-8b07-0d0d56f98c40 | note | INSPECTION/TEST METHOD: Verify
7659c38a-be9d-587f-88b4-9fa9978e5160 | note | RECORD OF CONFORMITY: This ITP signed off
44e5bb05-8228-53de-b643-c7fda1be682d | note | IP
fc4d5db1-1238-581c-9415-ba5177d1c0c9 | note | RESPONSIBILITY: Fulton Hogan Engineer
b307e88c-14d2-5d7f-888d-96f6554592ca | textbox | Date Completed:
b9ed2fa3-829c-4132-a728-8f41a71a85c4 | checkpoint | Final Inspection
7d0e95c0-1c3e-58ba-b54c-befa51eab828 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f39cbd64-9a05-5b33-b558-cf761ca1fdd9 | textbox | Print Name:
5a181708-1c96-5923-9c11-4e97db3564d6 | textbox | Position:
0c00c6ee-5226-566c-ac47-8d90c75f7190 | textbox | Date:
de86af6c-b39a-49c1-a9dd-950af0bdeb03 | checklist | ITP-034 - Safety Zone Construction |  | ITP-034 - Safety Zone Construction
592c053d-4de9-4506-8dda-832c102b4c8f | section | Preliminary Works
c32c0172-a1c0-46a4-b021-57207240eab9 | checkpoint | 1.1 Check for correct documentation
0fc069c3-8a9d-52b5-a723-d58e8e039d47 | note | FREQUENCY: Prior to Commencing Activity
ec4adba3-fe97-5e02-847f-1b169713e6c7 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
a8fce97a-0e78-58fe-8dbf-d52940da31fc | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
bfa90eb7-bf54-5484-b943-0dfa2e20d87d | note | INSPECTION/TEST METHOD: Visual Inspection
59457f23-7141-5d47-bd79-933af3af11c6 | note | RECORD OF CONFORMITY: This ITP Signed off
ef4bcf8a-9cee-5098-bb97-154007e55d23 | note | HP*
c8f62898-1f30-579e-81d7-d340f9a8de7c | note | RESPONSIBILITY: Fulton Hogan Engineer
ccf61aaa-8350-52da-8a46-f8682e51996e | textbox | Date Completed:
5214b235-c8ad-4fef-9db4-e8dd7f1a021b | checkpoint | 1.2 Implementation of all measures and controls
fca4106f-7482-5365-b02d-fe624cb043e6 | note | FREQUENCY: Prior to Commencing Activity
23733788-acf7-50e7-8d05-d43c78afbc29 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
61050be2-503c-5e9c-89e2-c8f20eaa2c08 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
f3759995-54c0-5dc9-a98d-a274902fbc98 | note | INSPECTION/TEST METHOD: Inspection
d9808507-6595-50d2-a1cb-a707ca4be3f2 | note | RECORD OF CONFORMITY: This ITP Signed off
fa980c01-1c2e-5296-ba07-4f869d577686 | note | IP
8b71d6e4-e095-5595-8f23-a25198fe0a66 | note | RESPONSIBILITY: Fulton Hogan Engineer
5d3b30d9-c8f3-5124-803a-4c452768c15c | textbox | Date Completed:
cb65326e-08f3-4d13-9700-34748f090501 | checkpoint | 1.3 Material classification
bcc1c52b-0370-572c-ae6d-0fe4d4b99fa4 | note | FREQUENCY: Each Delivery
9abfabb2-c969-51c3-8e43-717fc78dca2b | note | ACCEPTANCE CRITERIA: All kerb shall be inspected at delivery for visible damage. Ensure correct single panel Type A fencing & sleeves are being used and are free of damage.
4b8235b1-f359-5717-af71-d899cab72604 | note | REFERENCE DOCUMENTS: STF T6107
9904d9cd-7d4b-5027-8454-9e0741a6cd91 | note | INSPECTION/TEST METHOD: Inspection
de7c5b00-50c3-5061-bf01-64e986344444 | note | RECORD OF CONFORMITY: This ITP Signed off
baeb4500-b721-5948-9b0a-0b03db131bf2 | note | IP
a05e7f13-b47d-556d-96b9-ce8784cd6337 | note | RESPONSIBILITY: Fulton Hogan Engineer
5ab49eb0-efc2-55da-aca0-50bf3f8bf455 | textbox | Date Completed:
5361fbc1-13d3-47a4-ac64-4394e55e3185 | checkpoint | 1.3 Setting Out
1a2ab982-973d-5d83-a6e8-606e1887f37d | note | FREQUENCY: Each Lot
708050d5-a8c4-5004-8900-0cb624671cf5 | note | ACCEPTANCE CRITERIA: Line and level of kerb, fencing & linemarking shall be set and marked out according to the design and standard drawings.
37af523d-bf54-5d53-ac0c-94b13060f6de | note | REFERENCE DOCUMENTS: Design Drawings Dwg P15671
94aaa178-18fc-5ea2-a934-93a373ef2640 | note | INSPECTION/TEST METHOD: Inspection
900df7a1-6ee8-5d5c-8d00-6b8b00310a38 | note | RECORD OF CONFORMITY: This ITP Signed off
e1352696-9da5-515c-b9fe-8dda823e7e17 | note | WP
8f87863d-7e44-519d-a55d-c1110be9016f | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
50fe781f-0784-52af-bbd4-5576bbbaa7f6 | textbox | Date Completed:
76dc6b2a-c524-4f0f-9e4c-3f64cd7a521d | section | Installation of Concrete Kerb
c2c597d3-805c-44e7-ba42-3c76f61a44ac | checkpoint | 2.1 Base Preparation
81dac243-3175-5ddb-8bb1-8ca1b0eda300 | note | FREQUENCY: Each Lot
573f5f6a-b550-501b-99bf-699b87db47da | note | ACCEPTANCE CRITERIA: Pavement base shall be inspected to be solid free of loose materials.
74648c53-7a77-58be-adfd-692c85fba7b6 | note | REFERENCE DOCUMENTS: Dwg P15671
d9f7cbac-2559-5694-b4fb-489fe862907a | note | INSPECTION/TEST METHOD: Visual Inspection
dd179456-965a-5262-a092-8c46f58300c8 | note | RECORD OF CONFORMITY: This ITP Signed off
d0ebf45c-11a7-57c8-b0d1-06a25268c0de | note | IP
55ea7807-de49-5831-b4a8-0eacdcd881b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
cbae07f7-e235-559e-a0d5-6a3d3a00eefe | textbox | Date Completed:
b2c8db37-84b1-4d1c-8a64-461608f0bf6d | checkpoint | 2.2 Drilling of Holes
95ebc4af-41c4-5a55-8504-9ac24fffda38 | note | FREQUENCY: Each Lot
dfb44868-9816-58dc-af5d-d3084c61a2e8 | note | ACCEPTANCE CRITERIA: Location of holes drilled must align with the provided design drawings. Two holes per stone shall be drilled to an approximate depth of 130mm. The width of the hole drilled shall be minimum 4mm larger than the width of the pin to allow for Chemset material.
b211d74f-4380-55cd-a54b-dcfe42fbedae | note | REFERENCE DOCUMENTS: Dwg P15671
b4d8ee3c-3c18-5b99-8111-c47a4472f84f | note | INSPECTION/TEST METHOD: Visual Inspection
c0f1d7eb-479e-5f85-9b32-e3ef5d2c31f6 | note | RECORD OF CONFORMITY: This ITP Signed off
8487bee7-c608-5f7a-8252-151a62252e97 | note | IP
e9646013-db5d-5a5c-bbdf-c6e59ba6c86d | note | RESPONSIBILITY: Fulton Hogan Engineer
2daba6f7-b059-588b-bce9-dc6a0aa0a236 | textbox | Date Completed:
25b49dbe-e8a4-4003-b64f-6769eda84bb2 | checkpoint | 2.3 Placement of Kerb
cbbc7fe1-9c83-50d5-afb7-b2190b597323 | note | FREQUENCY: Each Lot
c001d2d9-fd9a-594a-ba8b-d4d38cf75c20 | note | ACCEPTANCE CRITERIA: Apply Chemset material and position kerb stones such that the pins sit in the holes allowing the stone to lie flat on the pavement.
e7399f23-f6bd-5a7d-a03e-ef8b33935d0b | note | REFERENCE DOCUMENTS: Dwg P15671
d67ff664-d461-5293-a2ab-9c3bfb7d13a5 | note | INSPECTION/TEST METHOD: Visual Inspection
6021cebf-35bb-5157-8071-b0e3a82ded04 | note | RECORD OF CONFORMITY: This ITP Signed off
abdc4403-8049-5977-a8a9-26bcc64e4b53 | note | IP
83b6cf50-c75c-50ac-893f-28ce235d7a5b | note | RESPONSIBILITY: Fulton Hogan Engineer
a4826c22-1842-50dc-92f1-d436fb9c75f7 | textbox | Date Completed:
5e9af24b-6a18-4eb4-832d-bfabcc2d3324 | section | Installation of Single Panel Guard Rail
bac37641-fd11-4bfa-a767-9560f5229b03 | checkpoint | 3.1 Installation of Rail Post Sleeves
913f1405-6715-5511-ab95-af09b6d9aef6 | note | FREQUENCY: Each Lot
d115328d-68f8-5337-b164-0e9210f8a0c9 | note | ACCEPTANCE CRITERIA: Location of post sleeve's must align with the provided design drawings & 2.4m spacing. Core two 100mm diameter, 300mm deep holes per panel at 2400mm centres. Insert post sleeve and secure using non-shrink structural grout.
cae17f7e-6158-5750-bcfe-e3b10fada6a9 | note | REFERENCE DOCUMENTS: Dwg P15671
135e1168-14e7-5a91-82df-a93ec5fdff14 | note | INSPECTION/TEST METHOD: Visual Inspection
aa24cbc8-d4db-5d56-8ad9-95f62d66d608 | note | RECORD OF CONFORMITY: This ITP Signed off
5fd1bab7-7b8b-5e14-9a41-207e3bc371bb | note | IP
869bfc51-ebc0-53a4-9774-1cc48477e078 | note | RESPONSIBILITY: Fulton Hogan Engineer
087a78dd-4cf1-5043-ae46-ffe9cf53baaa | textbox | Date Completed:
9750ec5f-1fb0-4e4d-acb5-41329d3cce55 | checkpoint | 3.2 Placement of Fencing Panel
ab80a9ff-c698-5d78-b3c6-0b0151d92d42 | note | FREQUENCY: Each Lot
244697dd-6d76-54d7-863e-b581a07c2d5d | note | ACCEPTANCE CRITERIA: Align fencing panel such that the posts sit securely in the installed post sleeves. Ensure fence panel is free of damage and is positioned in accordance with the design line and level.
9768a069-6d83-54cf-8384-4c416452c71e | note | REFERENCE DOCUMENTS: Design Drawing Dwg P15671
c1b00404-fc1a-5a27-a9d8-739f8f47f149 | note | INSPECTION/TEST METHOD: Visual Inspection
dd535384-0703-51ff-8836-9a226a10d492 | note | RECORD OF CONFORMITY: This ITP Signed off
bd13d590-95c5-5a26-be0f-e27a358c47ca | note | IP
41bb2732-1785-52d5-82b8-8942d76e0cad | note | RESPONSIBILITY: Fulton Hogan Engineer
ccc1de5d-4ffe-52f5-8a20-4347cd72f15c | textbox | Date Completed:
d4fa836e-4ee1-4f5b-b985-1fed84806a0a | section | Linemarking
268686da-d1ba-4589-99b6-a97b373a68c3 | checkpoint | 4.1 Linemarking
376d91c2-4301-575c-8fe7-53faf9174d33 | note | FREQUENCY: Each Lot
1af6d83f-1030-5fe2-b79b-e244bba53283 | note | ACCEPTANCE CRITERIA: Linemarking to be completed in accordance with design and standard drawings.
40f6c336-475f-50d0-8c1b-12e0a0cc8393 | note | REFERENCE DOCUMENTS: Design Drawings Dwg P15671
71482c99-e856-5500-ba96-68694b9df0e5 | note | INSPECTION/TEST METHOD: Visual Inspection
3ba0a6b3-9148-535a-8264-6220eb9daa9d | note | RECORD OF CONFORMITY: This ITP Signed off
717c228d-0020-53c1-afcb-2720934319c8 | note | IP
5734164f-925f-5655-b62b-3b23904445ec | note | RESPONSIBILITY: Fulton Hogan Engineer
03aada48-0183-5207-917f-8d4cd8c44572 | textbox | Date Completed:
f90328e9-877d-4a8e-9f8a-e86bfbb6f883 | checkpoint | Final Inspection
e1de1ee9-e9e2-5a8e-9b23-3bd8b7df9da5 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
1cc3aef9-c3bc-557c-befd-353b428987ed | textbox | Print Name:
754b0f78-c289-505c-99f5-10f7ba9a5274 | textbox | Position:
a2921bcd-2e25-5174-b756-098eae9ed6a3 | textbox | Date:
26cb2541-6f44-4ead-8bce-fc05ea3994db | checklist | ITP-035 - Kerb Access Ramp Asphalt Footpath |  | ITP-035 - Kerb Access Ramp Asphalt Footpath
ee591d63-d5a1-4949-b367-249005efe442 | section | Preliminary Works
dcf7ea66-bf3d-4c2e-8c00-b5f6e55cc594 | checkpoint | 1.1 Check for Correct Documentation
269c50c5-4335-55f2-ac6f-ce08f4fc37a2 | note | FREQUENCY: Prior to Commencing Activity
77af6e24-9151-5d13-ba57-c42ac783f492 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
30618744-9a56-51fa-8182-80a91779a366 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
f4df79ce-43a3-5c8e-81b8-cfee3e0fcae5 | note | INSPECTION/TEST METHOD: Visual Inspection
0619d166-deb3-5e8a-9fc3-5e55dbe86675 | note | RECORD OF CONFORMITY: This ITP Signed off
c123da8e-0eff-5219-b590-f52f8f9e8bf5 | note | HP*
f4def454-72c7-5039-9f1a-0f57a352cfaf | note | RESPONSIBILITY: Fulton Hogan Engineer
da10a0da-6aa5-5e2d-a744-634ade79f635 | textbox | Date Completed:
ade28501-ab03-49e7-9912-5bb448d38aad | checkpoint | 1.2 Implementation of all measures and controls
aeba95b4-3a17-5c88-b544-fbb6234856b2 | note | FREQUENCY: Prior to Commencing Activity
343a329a-9a31-56ce-96a2-f657c5dd77b5 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
e65b2830-cef6-51d8-8f5f-98ff17f8f2ad | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
7ff5a8e8-2a99-5c4e-92b4-31e3fe65dfeb | note | INSPECTION/TEST METHOD: Inspection
0f546919-5ade-53d4-85cd-2fbad021a06e | note | RECORD OF CONFORMITY: This ITP Signed off
ba3b6931-2be4-5426-9415-d3739884af79 | note | IP
327739f9-5412-5552-a528-197f83a088dd | note | RESPONSIBILITY: Fulton Hogan Engineer
c101e5b4-b4c4-5c0d-aaed-b62c6fd09001 | textbox | Date Completed:
c43b00d1-6ee1-434d-aee5-a4197382f1fd | checkpoint | 1.3 Existing Bluestone Kerb Demolition / Removal
63aa5d71-12ae-5a19-8194-f94d650ff5d1 | note | FREQUENCY: Each Lot
199e214c-c1f2-574f-af9c-cbbd6c150192 | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone (if applicable) Bluestone shall be salvaged and re-used in new kerb alignment where possible
c8d82dc9-03c2-540d-9bc4-d2a7c8330b67 | note | REFERENCE DOCUMENTS: Work Procedure
6f01147f-870f-5f04-a732-dfd276ee9907 | note | INSPECTION/TEST METHOD: Inspection
b30ccc84-9218-5fc3-a506-d4cad5c29c2c | note | RECORD OF CONFORMITY: This ITP Signed off
ebd94304-45e5-50c4-a673-25dc975d69dc | note | IP
a271eb68-6ef4-5bc0-990c-9ebc1b654b7d | note | RESPONSIBILITY: Fulton Hogan Engineer
30e9c808-b302-5c4f-840e-ab577a607ea4 | textbox | Date Completed:
3a4b20fa-2c0f-4abb-9e47-b27afb48e5d3 | checkpoint | 1.4 Check Materials
17bc89cb-f743-5d0a-8870-73a92af336d2 | note | FREQUENCY: Prior to Commencing Activity
10e3a094-a533-5662-807c-1833997a6f61 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Granite Tactiles. Granite inlay shall be 50mm wide x 40mm thick Spring White Granite Inlay.
8d676394-9d79-5f49-a4c8-472e57c25ea4 | note | REFERENCE DOCUMENTS: Receivable Inspection List
7442db3b-e6bf-5e0b-9606-258528ab1f27 | note | INSPECTION/TEST METHOD: Visual Inspection
a135e28d-9746-5571-9ae5-91d641514379 | note | RECORD OF CONFORMITY: This ITP Signed off
3d5801e0-0b5c-55f0-96ae-e54787c86615 | note | HP*
53a2386f-cac4-5db7-9c76-a7c5524c69d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
0fb8885a-5876-5074-bd8a-7740ad45997b | textbox | Date Completed:
e0ffc64d-1f7b-482c-92e8-514375da89c5 | checkpoint | 1.5 Setting out
3db4c3c4-8cab-5611-9d7a-2c6b11eb71ec | note | FREQUENCY: Each Lot
ae527ad0-9330-57bd-a3ca-5429f47629ee | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
73ef6965-526b-5b66-b8ea-c746597e9646 | note | REFERENCE DOCUMENTS: Work Procedure
fcef10d2-ebe5-569e-b6ba-5328c590dfec | note | INSPECTION/TEST METHOD: Inspection
de6f5fb2-8d39-59d9-8abd-f7d55d42f20d | note | RECORD OF CONFORMITY: This ITP Signed off
df210f57-6257-5faa-83f1-cd086162390b | note | WP
4c183b5d-2855-5068-989a-846d983c870b | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
a2e69996-dca1-5a08-a190-5b69839b60bb | textbox | Date Completed:
b1444a37-4b0f-4003-b880-5fc71fd49574 | section | Construction of Access Ramp Asphalt Footpath
68e7085c-a8f2-40b0-9482-bb0eedb7e5b7 | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
2cc31c67-71d9-5ffe-8afd-5d88d3a41105 | note | FREQUENCY: Each Lot
efec4ea2-75c5-549b-b2be-cf455fbaed8a | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels. Bluestone kerb shall be placed on a bed of low slump 20MPa concrete, minimum 75mm thickness. Formed groove of 10x25mm in concrete face shall be filled with caulk
ec0ca6b0-02e7-5205-b77e-cfe202aa76ae | note | REFERENCE DOCUMENTS: Dwg 1P50201
8981377f-f8f7-544a-b319-27ac1327632a | note | INSPECTION/TEST METHOD: Visual Inspection
d8f9045b-0ca2-5126-a21b-13a406077acc | note | RECORD OF CONFORMITY: This ITP Signed off
ffdb29a2-bb86-5657-8c6e-bc431105b9bf | note | IP
d79a940e-8808-572c-b08e-f1645fe02782 | note | RESPONSIBILITY: Fulton Hogan Engineer
e64188b9-5608-5e5d-b587-358f4c3bdcc4 | textbox | Date Completed:
f1ab9b20-1f03-41dd-aaf7-dc82de986846 | checkpoint | 2.2 Base preparation
a78f242e-276c-5cbf-b6f8-f067beead71b | note | FREQUENCY: Each lot
79801543-d9a5-5a97-8e02-a3bce7cab18d | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
78aa16c9-ef2c-5b7f-9108-869532fce6e7 | note | REFERENCE DOCUMENTS: Dwg 1P50201
7b09f44a-565c-575b-b899-f38531ba83a7 | note | INSPECTION/TEST METHOD: Visual Inspection
331a8893-dd6e-5474-9806-68b9476597ca | note | RECORD OF CONFORMITY: This ITP signed off
20a9d807-5e8b-5bfd-8671-fb64209c1b07 | note | IP
fba4ff62-cca0-5e3a-ab73-b309a6eb52bb | note | RESPONSIBILITY: Fulton Hogan Engineer
5bbcbd19-4182-5772-97a8-681d6023473f | textbox | Date Completed:
b47cedcf-ada7-45e3-9674-7d41a61bda12 | checkpoint | 2.3 Installation of Kerb & Gutter Blustones
47da9a64-ee82-58a9-b014-aab198dc4806 | note | FREQUENCY: Each lot
bf5e0ba8-97b9-5f18-ac49-397e5bef506e | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar.
bacfed7c-16c6-5d83-95e5-abb0ae0480df | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
7521dc29-fbd2-5066-92ba-0bee7084d7de | note | INSPECTION/TEST METHOD: Visual Inspection
ef3d88fd-327f-5924-96ef-e0a4d0b42aaa | note | RECORD OF CONFORMITY: This ITP Signed off
70e7f742-7b14-5493-9f07-340adefdf355 | note | IP
bbd3f038-93f9-54c3-b32a-3790b11babd2 | note | RESPONSIBILITY: Fulton Hogan Engineer
a82d928f-9e2b-55e8-a259-d2af5adf4dd4 | textbox | Date Completed:
845e7533-ab04-485f-8a4c-4ec0e91f84ca | checkpoint | 2.4 Asphalt placement
3ae8f9ac-ca4c-50fe-9ea3-305d8b264a0b | note | FREQUENCY: Each Lot
2482b55c-510f-5ea2-9133-e1d03bc5c413 | note | ACCEPTANCE CRITERIA: Asphalt ramp to match adjoint asphalt footpath and sit flush with channel at grade of ramp using 7mm type N hot mix asphalt. Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8.
f4648241-1193-5d13-a6ed-3ed43f209c8f | note | REFERENCE DOCUMENTS: Dwg 1P50200
39db275a-08f4-5014-92a7-f5428c9cdc32 | note | INSPECTION/TEST METHOD: Visual Inspection
6697926c-8549-5892-a76c-4a289c043502 | note | RECORD OF CONFORMITY: This ITP Signed off
a9a9a300-6586-5bb3-afec-d038e6d28f72 | note | IP
40ca199a-74c9-5f0b-a5b5-b5565dd13ec1 | note | RESPONSIBILITY: Fulton Hogan Engineer
aaab07b5-21f2-5661-99ae-2754b67ef078 | textbox | Date Completed:
dab9ad62-4b20-42c8-a898-301463f72471 | checkpoint | 2.5 Installation of Pandatac Granite Tactiles
8b7e0cb1-d6a5-595b-bafc-875a14b170e7 | note | FREQUENCY: Each Lot
4822926b-103f-5c48-9722-54682465514b | note | ACCEPTANCE CRITERIA: Granite tactiles shall be placed in accordance with Standard Drawing 1P50200 & drawings.
dd1903fa-2b65-57bb-acfe-5663594b9917 | note | REFERENCE DOCUMENTS: Dwg 1P50200
9d260bbd-3dce-5ba5-b926-c89f26867d51 | note | INSPECTION/TEST METHOD: Visual Inspection
468145c9-e7aa-5afd-88c4-d3fd4734d987 | note | RECORD OF CONFORMITY: This ITP Signed off
47f67a6d-ded6-5e3a-ae4d-748891b5e7fb | note | IP
4367f07a-bc04-5ec9-87b3-6f1ff9c39752 | note | RESPONSIBILITY: Fulton Hogan Engineer
4ce9a59a-0d13-53cd-a8bc-f26b7e2af66a | textbox | Date Completed:
bde4f4d3-6719-4e2a-82f9-514aa749ba74 | section | Completion
f72ab9ba-4731-4772-b832-c19688e50dee | checkpoint | 3.1 Completion
0388b6d0-5435-5b26-8347-ca86f4aec718 | note | FREQUENCY: Each lot
e4a3ee74-3488-5af5-a222-3d0ed3b96b3d | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste Bluestone kerb is free of mortar stains and cleaned to satisfaction.
3a97c709-a75f-547b-ab0f-f4e61204e75f | note | REFERENCE DOCUMENTS: Visual Inspection
0f546ba3-764c-5859-948c-b19dafff4dfd | note | INSPECTION/TEST METHOD: Visual Inspection
7bc8ea4d-fa3a-5c4f-a81b-3ed78e126645 | note | RECORD OF CONFORMITY: This ITP Signed off
a27f3b59-e2d1-5890-be1e-dcc0d5c08573 | note | IP
14bd36d8-a664-5bdf-bf6e-9640e862fe9b | note | RESPONSIBILITY: Fulton Hogan Engineer
34028fe8-e367-5e02-9460-fd8ff6c26f4d | textbox | Date Completed:
8e042ab4-897b-4c7e-9d1c-d9a731260d9e | checkpoint | Final Inspection
6285094f-aacd-5f3d-9b4f-1d2e792c841c | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
be1085f2-e4d7-579c-9d5d-5205917669a2 | textbox | Print Name:
7f8a57c8-06e5-5cc6-93c1-f3df770ae309 | textbox | Position:
e8f5ee14-63a2-530b-a9ce-127c470f5a85 | textbox | Date:
25d7565f-5736-496a-8704-c9660d16debf | checklist | ITP-036 - Kerb Access Ramp Bluestone Footpath |  | ITP-036 - Kerb Access Ramp Bluestone Footpath
0b3593f3-1c12-471b-9301-c32445cfa140 | section | Preliminary Works
688e3f50-14fc-44e3-aa1d-6ffbe222eb41 | checkpoint | 1.1 Check for Correct Documentation
52a82d19-ec0c-56e3-90c4-f85541b6c528 | note | FREQUENCY: Prior to Commencing Activity
0a74bd90-1b91-51c3-96db-97290d11357f | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
e6033190-16fe-5ebb-a278-a6b021d7c863 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
0fdcac02-c350-536b-8617-90423224d98e | note | INSPECTION/TEST METHOD: Visual Inspection
9b0e1498-cc0b-5d33-a429-c74a579f3985 | note | RECORD OF CONFORMITY: This ITP Signed off
bc19dbf7-f4b7-5be9-9480-03f3067b327f | note | HP*
584bd54e-daeb-55ae-9e8e-e8a581664b98 | note | RESPONSIBILITY: Fulton Hogan Engineer
61c4586d-1882-5917-9dda-b7d77e7a15bc | textbox | Date Completed:
039129e0-ad40-4bad-b51d-af42e7643145 | checkpoint | 1.2 Implementation of all measures and controls
49057b71-ecef-5b2f-a685-288fa05e769f | note | FREQUENCY: Prior to Commencing Activity
3220773b-998e-53ff-b214-9d46f72bd022 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
d6530e4a-d954-59d8-9f69-ef10724ae7c1 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
ec80cb64-7a70-5f74-b268-bbf5e4dfb0c2 | note | INSPECTION/TEST METHOD: Inspection
342425c4-f3da-5164-82aa-add7acece86b | note | RECORD OF CONFORMITY: This ITP Signed off
4d204ad3-588f-54f5-959f-727e514880d0 | note | IP
7ffd214e-0473-554c-8c0b-0a97f7501b02 | note | RESPONSIBILITY: Fulton Hogan Engineer
bac8af11-47ce-523d-badc-30aa39fba668 | textbox | Date Completed:
80babcc9-4562-413b-9284-021ef481d3de | checkpoint | 1.3 Existing Bluestone Kerb Demolition / Removal
ab0c6ec7-df48-5664-a433-c644aee7097a | note | FREQUENCY: Each Lot
7c6f569e-c681-5469-951c-b6f32b3ed29d | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone (if applicable) Bluestone shall be salvaged and re-used in new kerb alignment where possible
c6868cbc-1f85-568c-a273-ee239da2556b | note | REFERENCE DOCUMENTS: Work Procedure
452a9189-7249-5d0e-8fe5-757023656522 | note | INSPECTION/TEST METHOD: Inspection
39ff74cc-7862-538b-9637-2d74c8fa1de2 | note | RECORD OF CONFORMITY: This ITP Signed off
df2c841a-208d-5073-baf3-c1a411862826 | note | IP
87291d57-9dfb-5b79-b7e3-87f66f93b812 | note | RESPONSIBILITY: Fulton Hogan Engineer
4c661aaa-e156-5b1b-9818-5772d910b141 | textbox | Date Completed:
5cde3d72-e3b3-4672-9045-2ae97432a0af | checkpoint | 1.4 Check Materials
e327a5ce-2a04-56bf-9e63-07a6f66ae583 | note | FREQUENCY: Prior to Commencing Activity
e5114e7f-793d-5aeb-b212-7899edbb405b | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage. Tactiles in paved areas shall be Versatac Granite Tactiles. Granite inlay shall be 50mm wide x 40mm thick Spring White Granite Inlay.
d60b0906-683a-57ef-b354-f6131a6f9d9c | note | REFERENCE DOCUMENTS: Receivable Inspection List
a3ccf43c-aa8d-5624-bc6f-e4af87cadb2b | note | INSPECTION/TEST METHOD: Visual Inspection
653f887a-2864-5a63-a889-9469047d19da | note | RECORD OF CONFORMITY: This ITP Signed off
72fce0d1-73d0-5bcb-9d91-d8ba1f59116b | note | HP*
4ae4f0a5-5855-5929-9a14-9aa4b40da0bb | note | RESPONSIBILITY: Fulton Hogan Engineer
299d7987-1b32-549b-a190-5a2466d28b74 | textbox | Date Completed:
3dbc03a7-a781-46f2-9167-b9f522085d07 | checkpoint | 1.5 Setting out
31a701b0-bbab-5283-a013-65a75375a2f3 | note | FREQUENCY: Each Lot
be7441cb-d317-5ac9-a567-905c33e984d1 | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of bluestone pavers, tactiles and granite inlay shall be set out according to design levels to suit new kerb heights.
c80b481f-a8d3-523f-a117-681ae2f0a01d | note | REFERENCE DOCUMENTS: Work Procedure
56fb8338-2bc9-535d-aa08-90fa35be8064 | note | INSPECTION/TEST METHOD: Inspection
c488b3eb-16b9-599c-993c-bdc4d342f24c | note | RECORD OF CONFORMITY: This ITP Signed off
8ad4de1b-cec2-5e31-8c7f-9ed98ac861f2 | note | WP
d0c1e82b-8d20-531b-bfb5-1913a4e008cb | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
51a70221-b718-522e-b320-41d9f70a363a | textbox | Date Completed:
f153a454-fa28-4b14-b62b-23f76955f258 | section | Construction of Access Ramp Bluestone Footpath
7fba1661-5af5-4ece-a0ef-708857e702bf | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
0d1ff6d0-b93e-57a4-adb1-c002374bc45b | note | FREQUENCY: Each Lot
55d3a471-c121-5bbd-9f6f-44e019f57b38 | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels. Bluestone kerb shall be placed on a bed of low slump 20MPa concrete, minimum 75mm thickness. Formed groove of 10x25mm in concrete face shall be filled with caulk
22eaee7a-2294-5c7e-a5ba-5d072b5fe431 | note | REFERENCE DOCUMENTS: Dwg 1P50201
7f236e87-5ad0-5753-a780-441899617ca4 | note | INSPECTION/TEST METHOD: Visual Inspection
706a4b98-7524-538c-8659-9dc8bab16046 | note | RECORD OF CONFORMITY: This ITP Signed off
9ecc27c0-3db7-59e1-ad16-77d88ad763ac | note | IP
cebfa0cd-ffd2-56e3-9955-233ca351c406 | note | RESPONSIBILITY: Fulton Hogan Engineer
fc5c889d-fff5-535a-8fde-38ca6da7cfe6 | textbox | Date Completed:
042aa90c-a509-472f-b5ac-6d72ecd09ceb | checkpoint | 2.2 Base preparation
7df007d9-7ae9-5fd3-b023-82de931cfe8c | note | FREQUENCY: Each lot
aeca823e-e1d2-5390-8d6a-c1c0aed0f7e9 | note | ACCEPTANCE CRITERIA: Sound base should be achieved with 50-100mm for bedding materials
76ef5fc8-1ddb-5638-aadc-d6fd4bee5f04 | note | REFERENCE DOCUMENTS: Dwg 1P50201
4ab996dc-a468-5533-8cb3-a0c63065891d | note | INSPECTION/TEST METHOD: Visual Inspection
d349eac5-20f1-5325-a65d-3967645a8e18 | note | RECORD OF CONFORMITY: This ITP signed off
126ef5e5-d3ec-5281-bacb-5f85e4df5b45 | note | IP
5542865a-c848-5c99-aaeb-edc79837339e | note | RESPONSIBILITY: Fulton Hogan Engineer
8ecbfcfa-0c61-56df-9f99-890fb8491392 | textbox | Date Completed:
3728a1ab-e6e2-4213-b04a-6465381b89f1 | checkpoint | 2.3 Installation of Kerb & Gutter Blustones
3ee56d97-6244-52f8-b626-dedb4d282e9c | note | FREQUENCY: Each lot
2f169779-f6ea-5dcb-b9ca-6c84a782f3fd | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness Gaps of >10-30mm< shall be provided and filled with mortar.
d96020f9-5fb3-58a3-8b02-aabd3172594f | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
e83e726c-2c9a-529a-bcf3-c055bba54cdb | note | INSPECTION/TEST METHOD: Visual Inspection
4ba37a8c-1618-5e0d-9e47-21b35b8d59a4 | note | RECORD OF CONFORMITY: This ITP Signed off
e033e206-77c1-5eaa-bfbb-61e99887aa1d | note | IP
8772d12f-73b6-53a5-8a33-3c84d68cf539 | note | RESPONSIBILITY: Fulton Hogan Engineer
10f67431-785f-5894-873d-1322f8c80891 | textbox | Date Completed:
1cc76863-1dcc-4b2c-b6af-d98c26bdbb59 | checkpoint | 2.4 Placement of bluestone pavers on mortar bed
63988fc2-7712-55a0-87b8-56793eba1d3c | note | FREQUENCY: Each lot
d4eb2237-1cb9-5ab9-8f02-8232163227d7 | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402 on average 30mm thick mortar bed of sand & cement mixture. All pavers shall be coated in mortar slurry on rear face before laying Kerb access ramp wings shall be at an angle of 45° or as per design and the ramp gradient shall not exceed 1:8. Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
973179b1-9cb0-5536-ace3-d115afe3c676 | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
ad173cdf-6b60-5b28-8eff-84d93d5de3cf | note | INSPECTION/TEST METHOD: Visual Inspection
8376f787-b372-5107-902d-8167260aa378 | note | RECORD OF CONFORMITY: This ITP Signed off
effe72bb-0052-56b9-aa57-061e3965e23a | note | HP
9f1fc268-f65e-5a4b-9877-2764f5a6482c | note | RESPONSIBILITY: Fulton Hogan Engineer
628b10d1-9f77-5e22-9ee2-997cf6e4452a | textbox | Date Completed:
49f87046-fb34-4c98-b711-340be5f3b8bd | checkpoint | 2.5 Curing
d5ac25e0-f0ad-5752-a9e1-6a6266adcd8f | note | FREQUENCY: Each lot
6a36d447-30e5-5b37-ae96-33b18aaa5c22 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic Where required, ply shall be laid over area of works
d5bdb2c7-84ad-59c0-abfc-77aec2f77c41 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
736083fa-21c5-5cb5-b8bc-47d838a48aa7 | note | INSPECTION/TEST METHOD: Visual Inspection
f0f41911-799e-5ddb-be56-80e9aeeea1ad | note | RECORD OF CONFORMITY: This ITP Signed off
af9bc0ab-1618-5f93-a027-a3ab842d1275 | note | IP
33c88afc-cda9-59c9-beeb-6c4c5c447b6b | note | RESPONSIBILITY: Fulton Hogan Engineer
6bf64d62-09f9-58e8-a1cb-406e18404e0c | textbox | Date Completed:
bf4fa1c9-857f-4f9f-9db1-5c1dd779e5e1 | checkpoint | 2.6 Grouting
d19502a1-9960-5cec-bc53-009c2d977e62 | note | FREQUENCY: Each lot
7c515a70-dc99-5d8f-8e48-2bb3ecdb9fb8 | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using Lanko Durabed to specified mixture content. Grout shall be spread & clean appropriately as required.
2dafafdd-ae9c-58b2-bda1-7a51aad5c511 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
88dbcd67-b5b2-516f-b38f-828ddf17fb00 | note | INSPECTION/TEST METHOD: Visual Inspection
334fe15c-402b-5249-b75c-3ae13a316f6d | note | RECORD OF CONFORMITY: This ITP Signed off
8b25f0f1-80e5-5799-90d2-7db921648b47 | note | HP*
6114bd38-f29d-5d37-a89c-3eff7cf43448 | note | RESPONSIBILITY: Fulton Hogan Engineer
69045bf6-7f4c-52dd-8217-b7cef302796f | textbox | Date Completed:
486c5cac-73d1-4652-9665-0178fc5ef76e | checkpoint | 2.7 Installation of Versatac Granite Tactiles and Granite Inlay
4a83cfb9-5a64-5b66-9d18-7475ce6ff673 | note | FREQUENCY: Each Lot
5b5463ad-6499-5cfb-912d-ad1edaad7579 | note | ACCEPTANCE CRITERIA: Granite tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201 with surface deviation of under 5mm.
b64b0af9-12b7-5db3-be49-486c3d23a90f | note | REFERENCE DOCUMENTS: Dwg 1P50201
f14ebd65-f4cf-5f6e-a21e-7452d3f1a0fa | note | INSPECTION/TEST METHOD: Verify
a362edf4-2729-5f81-9603-3eeea2cd7c2c | note | RECORD OF CONFORMITY: This ITP Signed off
f9a31461-2dda-508d-bc15-b0accd859462 | note | HP
424d42bd-6df8-5c61-8f20-3df21f3653ac | note | RESPONSIBILITY: Fulton Hogan Engineer
a32b07ee-a476-58e3-97dc-bddfd37a0a19 | textbox | Date Completed:
f72932ed-29f9-4250-bfd4-50f5ea7cc1f4 | section | Completion
efefcfa7-dc38-4cac-b277-c7c189ae47dc | checkpoint | 4.1 Completion
87451054-568e-5756-be2b-c9decdbddd27 | note | FREQUENCY: Each lot
535a060e-b0e0-5a29-ae29-219c485f6502 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste Bluestone pavement is free of mortar stains and cleaned to satisfaction
d864fa9a-bacf-53c9-9deb-5bf0ca8c3c44 | note | REFERENCE DOCUMENTS: Visual Inspection
2d0a96b0-2057-5ca0-aa9e-08f9551d7a5e | note | INSPECTION/TEST METHOD: Visual Inspection
2a2402e2-84ee-5333-8167-d18ca640043c | note | RECORD OF CONFORMITY: This ITP Signed off
5cc4fe1d-22d7-5540-a9ba-2f7a1f41b6b2 | note | IP
dc1f0f4a-e91a-547a-90d3-138d09beaed3 | note | RESPONSIBILITY: Fulton Hogan Engineer
6e2b4d67-5d9e-5672-9845-2205c6eb2d9c | textbox | Date Completed:
ed32126a-613f-4a19-a7ea-e326df4104db | checkpoint | Final Inspection
5c8f6d1c-fc16-5ec6-84e5-58c8b623e131 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
dec04793-661d-57b6-a2b9-7c1562f14aa9 | textbox | Print Name:
210132a6-9b5d-5fd8-8f62-a36ef4d0da1d | textbox | Position:
be62c7f8-80d4-5ddf-ae58-6d043228323e | textbox | Date:

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
314df96e-6216-40bf-bf29-6dce4a5572c2 | checklist | FHC-ITP-001 - Clearing and Grubbing |  | FHC-ITP-001 - Clearing and Grubbing
b1f51dee-eb5f-47f1-8b1b-06180590a4a1 | section | Preliminary Works
7f5ed00f-2365-46ba-ab25-c0b7f54178c4 | checkpoint | 1.1 Check for correct documentation
39fbf2cc-08fd-54e6-a9db-60112d9f9cce | note | FREQUENCY: Prior to commencing any activity
8275dffe-5a04-54b3-a7b1-5920bc802058 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
65d0afbd-fc2e-5c92-bd59-67a493ae1a3a | note | – using the correct and complete set of drawings
bde09ab9-a9a1-5e5a-a41f-1c381db7766c | note | – all drawings are the latest revision
ad175522-f770-598b-b91e-a073ab1957ec | note | REFERENCE DOCUMENTS: Drawings and drawing registers
35209bd6-1e5f-55c4-815b-f4c134057444 | note | INSPECTION/TEST METHOD: Visual inspection
2e6f700e-5feb-5186-acdc-d6a13f35aad7 | note | RECORD OF CONFORMITY: This ITP signed
f6d7eead-8bcf-5fc6-adb5-aadb1320d47d | note | HP*
c92c1302-b556-5957-8017-2caf62785607 | note | RESPONSIBILITY: Site Engineer / Site Foreman
a9b4d64a-6b9f-58af-a1d1-0644d658ba37 | textbox | Date Completed:
b7acf3ca-6123-4ac5-bda0-6388fe30c22e | checkpoint | 1.2 Implementation of all measures and controls
6bb7ba75-f7d4-5b1c-9971-88f9a47ac77f | note | FREQUENCY: Prior to commencing any activity
ecb329fc-72eb-5133-a8a5-0ad59e8582b1 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
1966b727-e8d6-5c53-828b-833064aa66a1 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
d306a701-d84d-5028-b7d4-92d7e9e38d68 | note | INSPECTION/TEST METHOD: Visual Inspection
cde20328-2a47-539b-b13d-07c417f32639 | note | RECORD OF CONFORMITY: This ITP signed
b71a67e6-65da-52bb-9ca9-7dd1879f36cf | note | HP*
cab9eb0e-67f7-5f62-8347-55b77d8b6c06 | note | RESPONSIBILITY: Site Engineer / Site Foreman
d65b06e9-3af1-5dab-9d12-7f46a131b361 | textbox | Date Completed:
f2dbc168-b33f-4a2b-a9b7-a55ff86614bc | checkpoint | 1.3 Flora & Fauna
ac2f7eb0-ba78-596d-bf61-27320c436522 | note | FREQUENCY: Prior to commencing clearing
04382cae-9759-5f46-b21d-7b05e987dfb2 | note | ACCEPTANCE CRITERIA: A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
12aead53-987d-5b67-ae52-7a382d7da38b | note | REFERENCE DOCUMENTS: EMP, ECP
39ddfb96-e2a7-5e1f-b1ae-1e1b8b67e49f | note | INSPECTION/TEST METHOD: Visual Inspection
e77e1e1e-1269-5c3e-8ac3-965e825aae14 | note | RECORD OF CONFORMITY: This ITP Signed off
aaa9a470-9dd9-5b4c-ab3c-f98457b7838a | note | IP
49039b51-deab-5f79-ab1c-85dbe95356e4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
bc54371c-6417-5487-92c2-20abf5219aa1 | textbox | Date Completed:
27362893-6669-455c-8dc6-7d0a7d0c7ecd | checkpoint | 1.4 Permit to distrurb flora & fauna
24e3aefe-ae23-5e9a-a52e-e3fff5cf5a7f | note | FREQUENCY: Prior to commencing clearing
547fb212-597e-513a-84ba-24b80e317b8d | note | ACCEPTANCE CRITERIA: MRPA has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
f7e7c141-f21d-557e-a00d-36689033f091 | note | REFERENCE DOCUMENTS: EMP, ECP
6d18783c-a80a-5862-bcd5-7904d94d203f | note | INSPECTION/TEST METHOD: Visual Inspection
068f1514-3050-530c-b5ae-6049a14a46c2 | note | RECORD OF CONFORMITY: This ITP Signed off
d816a5c6-34c8-5ff9-9ad2-b369f5cf485c | note | IP
f329fa5e-ca64-5d66-9988-47b11477bcd2 | note | RESPONSIBILITY: Project Engineer
87c89721-b1d2-55ac-8ed6-da960a7553f8 | textbox | Date Completed:
2d5e95a3-0a66-4ddc-9875-34c6fe9cae4b | section | Clear & Grub
3a891335-2363-4378-8e56-82e059373a52 | checkpoint | 2.1 Define work area
db333f05-5eb8-5c24-aafd-f27fd5fb6755 | note | FREQUENCY: Prior to commencing clearing
c6837b1c-bf5a-5b19-a525-57765d88f3ad | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
f6ba2240-9aa4-52f7-838e-b6f5acd6dcb9 | note | REFERENCE DOCUMENTS: 201.03
542ca4f5-0fed-58ac-a6e0-b31c133edbcf | note | INSPECTION/TEST METHOD: Inspect
dd241abe-094b-5dc2-8ca2-1a49812e3906 | note | RECORD OF CONFORMITY: This ITP Signed off
7bd6c8b3-72cf-5474-8125-bc22c0618dd2 | note | WP
538c921e-3b07-5f60-84de-b4f9d48441f7 | note | RESPONSIBILITY: Project Engineer/ Superintendent
894423cb-3d7d-5381-8b3f-0930a2de8e25 | textbox | Date Completed:
df0bdb35-2be9-4b1f-8d38-50e7b6d9a6a0 | checkpoint | 2.2 Joint Inspection to Mark vegetation or habitat to be removed
02c36023-7f69-53d3-a6f9-2acf969937a2 | note | FREQUENCY: Prior to commencing clearing
7b975ba5-d54a-5e77-82ed-c3376f4029ff | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent to confirm and clearly identify and mark trees to be removed, consistent with Appendix O Tree Assessment Report.
541330ed-d224-5f5e-b699-b0ab6dc76119 | note | REFERENCE DOCUMENTS: Drawings 201.10
cb1e11a2-64af-57f6-ba85-5c1596764255 | note | INSPECTION/TEST METHOD: Visual Inspection
61886d35-bae7-5492-a2e5-07f89b0c9ca9 | note | RECORD OF CONFORMITY: This ITP Signed off
10c694ef-6265-553a-8ec6-2a0a63b2d143 | note | HP
deef27ca-81b0-5e4c-9b81-02536e1f8f03 | note | RESPONSIBILITY: Project Engineer/ Superintendent
077c2735-c84a-56e3-8d9a-74f1dd9c6467 | textbox | Date Completed:
8d52c389-3420-4941-a99a-b92c00147413 | signoff | AUTHORITY HOLDPOINT
3fe871ca-2612-444a-b021-84a5688de157 | checkpoint | 2.3 Identify No-go Zones
d63987ac-5aa3-5ca6-a610-d522179b0e00 | note | FREQUENCY: Prior to commencing clearing
805c09f0-d2ce-5c75-a6ce-bd0064349715 | note | ACCEPTANCE CRITERIA: Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing.
08bb3e82-05aa-5636-83b2-1c4b4756eca4 | note | • Signage shall be erected outside the limit of the of the vegetation or the habitat site, at intervals no less than 20 metres apart or as per the SSEMP
bf5517ce-b23b-5077-9f94-a4757f9431da | note | • Prior to any work onsite the contractor shall fence and sign all no go zone sites as per the EMP. Any works required inside TPZ shall be completed under the supervision of an Arborist
887b4198-0c64-5630-876d-3358b2307ff8 | note | REFERENCE DOCUMENTS: Drawings 201.10
3341eade-019d-553a-a824-c81bf6572653 | note | INSPECTION/TEST METHOD: Visual Inspection
a44cd133-98c8-5cda-9533-6b1e71322dd2 | note | RECORD OF CONFORMITY: This ITP Signed off
97e0fc6a-89aa-5d1d-8865-1ef02450d5fa | note | HP
de7fae8e-d669-58b3-b3f8-5dc5eabf9a85 | note | RESPONSIBILITY: Project Engineer/ Superintendent
cdeb2eaa-5391-563b-b7e1-60121e246c13 | textbox | Date Completed:
2ae4ff65-02ee-4b73-84c3-0662aed75bac | signoff | AUTHORITY HOLDPOINT
c7efaa77-58b8-44bf-bdf0-69de75715143 | checkpoint | 2.4 Clear felling distances of trees are adequate.
acc29fbf-b5ec-5a00-9f71-f4e7c5883430 | note | FREQUENCY: Prior to commencing clearing
e0c9e23d-44d1-50cf-9ce4-03547c0e47f3 | note | ACCEPTANCE CRITERIA: Ensure the clear distances are adequate and signage is inplace as planned. Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
efffe11c-ac88-5fb8-a93a-cccff7ed62b5 | note | REFERENCE DOCUMENTS: 201.04
25ab0a27-19a2-50ee-b582-b44a28cd7f99 | note | INSPECTION/TEST METHOD: Visual Inspection
562dc863-eedf-561d-902c-7d8aa1c6c6d0 | note | RECORD OF CONFORMITY: This ITP Signed off
6c95a7a7-3838-5d49-aef1-8e681d73ad64 | note | IP
ce0cfc83-f6f9-55fd-b2ed-6ac33ae88d7f | note | RESPONSIBILITY: Site Engineer / Site Foreman
10bf4798-a701-590d-8b24-e29fcdf3808e | textbox | Date Completed:
3468c7f8-3248-4ec4-b015-8a3d1dd8c324 | checkpoint | 2.5 Clear and grub trees and vegetation
f0ea50a6-7916-5acf-9a8a-cb592bacd780 | note | FREQUENCY: After clearing
57f215f0-7bf7-53a3-a116-86c45f0cbb91 | note | ACCEPTANCE CRITERIA: Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level
f3a98bfd-4de6-5078-9251-31d9118848b5 | note | • Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
39409575-45b1-5a65-90c0-689c4145d3f8 | note | REFERENCE DOCUMENTS: 201.04, 201.05, 201.06
87eec913-f3fe-545c-8e83-36c11a940593 | note | INSPECTION/TEST METHOD: Visual Inspection
123dc45e-9b1f-504c-b10a-a07576cde177 | note | RECORD OF CONFORMITY: This ITP Signed off
ce6ea02c-bc39-58b9-bf2b-a5e4753b7e71 | note | IP
6cbfdb42-3b4d-502a-9863-847749681800 | note | RESPONSIBILITY: Site Engineer / Site Foreman
1c300fd6-b4a6-5644-aed9-6ab6c14feed3 | textbox | Date Completed:
c404990b-cbf4-4a80-ab1d-d596b2e7462a | checkpoint | 2.6 Backfill holes
71d67b15-495c-553e-9439-75d8ddf8d317 | note | FREQUENCY: After clearing
88116849-a025-5d75-ae3f-694bc62b5758 | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material to the sorrounding material and compacted to the same degree to the sorrounding material.
895c8d1b-c622-52fe-b3ac-d7fa0670d796 | note | REFERENCE DOCUMENTS: 201.05
873f4338-529b-57f0-9c50-55ee72ad29d1 | note | INSPECTION/TEST METHOD: Visual Inspection
637650f5-96f4-5c67-82b5-257abc37e4c1 | note | RECORD OF CONFORMITY: This ITP Signed off
a4166a97-e49f-5d2b-8631-e4776962182c | note | IP
280c4212-5ea8-54e4-8aa2-1e59aeb50c39 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f9c43ef2-c161-507b-8584-4e169f1ab069 | textbox | Date Completed:
1aca605c-5d4d-41bd-88a9-84d6916d24d7 | checkpoint | 2.7 Dispose of Trees and vegetation
511bc937-f653-58f5-99e2-89b8c7d7cc6f | note | FREQUENCY: After clearing
535c8e2e-baa0-5dae-9c8a-e2aabef7f66e | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works. Noxious weeds shall not be mulched.
ff7e090c-2d4e-5d1f-ab9c-bc20c705852a | note | REFERENCE DOCUMENTS: 201.07
78e8eda6-ed17-584a-bf2c-7ed15037d7db | note | INSPECTION/TEST METHOD: Visual Inspection
417683d4-7096-5763-8424-9fc46a9b51c9 | note | RECORD OF CONFORMITY: This ITP Signed off
a1959c4f-da4c-567c-b74d-4dd3fce25866 | note | IP
ed28d872-9f14-51d7-9448-7a05de0df891 | note | RESPONSIBILITY: Site Engineer / Site Foreman
fe564535-890a-5266-841b-f7ec47063737 | textbox | Date Completed:
9b4d3f63-d6c9-492e-bfa2-a60fc1027f0c | checkpoint | 2.8 Dispose of concrete, bituminous and other recyclable materials.
5bf0a424-4207-5787-a558-8427ef55d935 | note | FREQUENCY: After clearing
b81b9ca8-8f6d-56d7-88ad-f64c84534073 | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
c26e9a8e-0816-5b2a-a2f1-f5102188e105 | note | REFERENCE DOCUMENTS: 201.07
bd89e7bf-f0ea-5af6-94ae-ff0d75c14b26 | note | INSPECTION/TEST METHOD: Visual Inspection
042bf563-a333-52d9-b21b-9fc2aa172500 | note | RECORD OF CONFORMITY: This ITP Signed off
5c8e8be6-0fb5-5adb-86aa-899e4a39554b | note | IP
8a0c655a-a5c4-53a1-a8c4-50c82748a0f4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
3d9fdd3c-13e5-5176-9f1e-e7cdeac1392e | textbox | Date Completed:
3f414ad3-ab7c-4309-aa9e-0c5a22522250 | checkpoint | Final Inspection
ddc4761d-96ac-5df1-9d49-3dbafd1b0e3b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
497d4553-8bea-50fa-a307-9f90c085d956 | textbox | Print Name:
4018a216-7eb0-5f83-a27e-807de86becfe | textbox | Position:
6d7b0c6f-13b2-57ae-823f-e599b06fb87a | textbox | Date:
d3a3610e-cebf-4bb3-bcec-83838e842267 | checklist | FHC-ITP-002 - Stripping Topsoil & Topsoil Placement |  | FHC-ITP-002 - Stripping Topsoil & Topsoil Placement
424d5ac0-00c1-49a1-9e0a-a3cbc0ce1dab | section | Preliminary Works
a050f071-7407-432e-bf4a-30efc8728213 | checkpoint | 1.1 Check for correct documentation
510cacd0-b8d3-58d4-9051-c51d68b55f86 | note | FREQUENCY: Prior to commencing any activity
8140057d-ccbf-5930-b639-c4d10b6d6625 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
9ba8bf99-e580-5205-8310-3e62f4069955 | note | – using the correct and complete set of drawings
b46b8195-7426-5fb4-bd3b-e07583d9d278 | note | – all drawings are the latest revision
0170f0ee-cc46-503e-8838-8de9058e43e1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
68285b29-9ce9-56ba-9a43-642dc4342c83 | note | INSPECTION/TEST METHOD: Visual inspection
3ea38df5-450e-54cd-997b-17d8c7a961ba | note | RECORD OF CONFORMITY: ITP Signed
6e8aeaee-b027-593e-b03f-28df779a9cc3 | note | HP*
b34fe8f2-5ce7-56db-bd10-1ffb2c078713 | note | RESPONSIBILITY: Site Engineer / Site Foreman
090b77b5-b567-5015-9e32-0e307ce122c3 | textbox | Date Completed:
faf0b7a9-7efb-447a-97f0-c1f4dea2e667 | checkpoint | 1.2 Implementation of all measures and controls
b3eac3f8-f550-503a-9b03-34b210e3cd68 | note | FREQUENCY: Prior to commencing any activity
19c6ba87-44f3-5fa3-a249-fff35c0d270b | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
4287c94b-f468-5baf-9768-17af28711775 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
58a9fecd-b0ca-5f77-b323-88336fa56a7d | note | INSPECTION/TEST METHOD: Visual Inspection
671e59a9-795b-52f3-94e8-8b393a13c0d9 | note | RECORD OF CONFORMITY: ITP Signed
2f20b84d-3dac-599f-b7c7-613cceb6b8c5 | note | HP*
464eecd3-b41a-589e-b871-312108c806c0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
17864a95-b91d-53ef-984a-1ef162e13547 | textbox | Date Completed:
8070fbc5-f556-4567-a689-ebc6db45abdc | checkpoint | 1.3 Ensure correct materials are being used
de418698-e309-5615-8965-1cc6a747224e | note | FREQUENCY: Prior to commencing any activity
d3f9ae9f-eacb-5dc2-bd56-45e00c0fa78d | note | ACCEPTANCE CRITERIA: Topsoil placed on formations and disturbed areas shall be capable of supporting healthy, full cover of grass growth, and contain organic material
22b8e94f-a3d6-547c-8228-d6897e4e69f8 | note | • Topsoil material shall be free from subsoil, tree roots, clay balls, stones, rocks, rubbish, contaminants, weeds, pathogens and toxic levels of any element with a pH in the range of 5 to 8.
8cdec6dd-0b5e-5e00-b79f-c49fff5df3b1 | note | • Imported topsoil shall conform to the material properties outlined in Table 720.042
d54dc042-722d-5884-9b88-52d6a5dea41e | note | REFERENCE DOCUMENTS: 204.04a
c5df5221-205d-52e9-99de-7440dc83f5a6 | note | INSPECTION/TEST METHOD: Verify
2ebf948c-8039-5a2d-8f22-eaecd5d48133 | note | RECORD OF CONFORMITY: ITP Signed, Material Test Report (Import Only)
e5fde6bf-e58b-5a63-ae3b-e9f92a383e0a | note | TP
5f2483fe-11c9-5e55-9d77-6adffc21ade8 | note | RESPONSIBILITY: Site Engineer
b40a8a82-27c2-596b-90c6-3c614a7b53f5 | textbox | Date Completed:
2d346eaf-20de-4931-9cf4-986b13c369cf | section | Stripping Topsoil
07f42a96-1c6b-4edd-804f-f60e74c7f760 | checkpoint | 2.1 Survey Set Out
2bca5289-c793-505b-9c3a-86811fbf6891 | note | FREQUENCY: Prior to commencing stripping
e3019296-9298-59bf-9fdd-2d707116b8c4 | note | ACCEPTANCE CRITERIA: Area has been pegged out in accordance with the drawings
94eb6515-8ca6-5d2a-a68c-89e9f631d823 | note | REFERENCE DOCUMENTS: Work Procedure
ff748029-80ab-5d2e-9f69-fd3fab63d216 | note | INSPECTION/TEST METHOD: Verify
8f74ca33-2a1d-5f66-aa5a-3a639cf7b577 | note | RECORD OF CONFORMITY: ITP Signed
93c07277-8247-5209-9c19-ef098dd58a4a | note | IP
eaa2cd3e-e615-512d-9473-1bc39f3a3041 | note | RESPONSIBILITY: Site Engineer / Surveyor
88eb8dd7-f868-5d12-85a0-a0938bf232b6 | textbox | Date Completed:
b1aaf72d-90cc-42c5-86cf-8d0449e1b450 | checkpoint | 2.2 Archaeological monitoring
0b254151-ccd7-518d-8c00-5800d5bf4c67 | note | FREQUENCY: Prior to commencing stripping
0aac6229-8a85-51db-828c-a2df8d577116 | note | ACCEPTANCE CRITERIA: The Contractor shall immediately notify the Superintendent if an archaeological site is encountered, or if any suspected artefacts are found. A ‘No-Go Zone’ shall be established for identified Cultural Heritage sites that are to be protected during the work under the Contract and in accordance with the CHMP
54ac3bc8-539d-5fab-824a-aaa3450e56b9 | note | REFERENCE DOCUMENTS: CHMP
d5cb03d9-0f49-5241-ae84-ddd5c7edd4fd | note | INSPECTION/TEST METHOD: Visual inspection
f79a08b9-9012-5762-8d27-6a8f7d2aa049 | note | RECORD OF CONFORMITY: ITP Signed
0ac39d9e-c6c2-5861-bafc-9cd358a4a5fc | note | IP
953853dc-37b6-5cb8-82ed-ee0f7896ca67 | note | RESPONSIBILITY: Site Engineer / Site Foreman
4e4f4b65-5aa1-5ae9-b391-ff89cf2675be | textbox | Date Completed:
34c15877-c508-48a4-847e-c750a4c6e857 | checkpoint | 2.3 Excavation Permit
1ad83268-9376-5ea9-8646-833e3df59179 | note | FREQUENCY: Each lot
c5f46632-8354-5208-8ae2-1c710504c30b | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
7a60502e-73e6-5349-b468-d27b6207486e | note | REFERENCE DOCUMENTS: Excavation permit
d9e9afb6-d1dc-5d34-a79e-538c8ce0dcc2 | note | INSPECTION/TEST METHOD: Verify
823d1d7d-5639-5080-967e-5831a39001f2 | note | RECORD OF CONFORMITY: ITP Signed
19715857-e1a1-5ca9-8b41-fe8efb35eddb | note | HP*
2f778c6e-4041-57c0-8f2f-d3daa7dcb75b | note | RESPONSIBILITY: Site Engineer
39d457e5-5e92-5b9c-8313-3007a6dc8550 | textbox | Date Completed:
786b9031-16f6-4715-a11b-3f97730463ba | checkpoint | 2.4 Designation of stock pile area or disposal site
6265a75f-5227-57f4-87ba-a225e91f946c | note | FREQUENCY: Prior to commencing stripping
a7e09c75-92a6-5371-be80-3d5f696a379f | note | ACCEPTANCE CRITERIA: An area for stockpiling has been designated or a disposal site identified
dc45442f-c57f-5af9-92f5-f5e7f0d8d58a | note | REFERENCE DOCUMENTS: 204.05c
d78a61b0-8d05-543b-9a95-07a3c01b7813 | note | INSPECTION/TEST METHOD: Visual Inspection
9af49074-c98a-5f34-902e-182129b7eaf0 | note | RECORD OF CONFORMITY: ITP Signed
fe12d9bb-8dc0-548f-a08d-fcb51d123ce6 | note | IP
96c45b3d-0596-5655-a06e-bf269cb3001f | note | RESPONSIBILITY: Site Engineer / Site Foreman
f6eb240c-1c89-5883-8a23-24690a80acc9 | textbox | Date Completed:
e999fa97-f494-408a-a4aa-dcfb3859761f | checkpoint | 2.5 Weed treatment
860f8f21-52ef-59ed-8942-bfb16af0cbff | note | FREQUENCY: Prior to commencing stripping
44b310cb-a357-5141-93cc-9a2b1c60ccc2 | note | ACCEPTANCE CRITERIA: Site has been inspected for noxious weeds and weed treated if present
86c91d0a-1cdd-59dc-bd8f-0308692c14ec | note | REFERENCE DOCUMENTS: 204.05c
b094a0fe-6eb5-582c-ae3b-be0f8d09e5d9 | note | INSPECTION/TEST METHOD: Visual Inspection
1d4be337-5831-53fe-9b33-620d6d0e5d76 | note | RECORD OF CONFORMITY: ITP Signed
ea8d8e03-eca6-59c3-abdd-27bc35ec2b0c | note | IP
8d40dcac-cfb2-5b76-a88f-0bdb1d9e73d0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
d6751721-36e4-5e68-adf2-8b3c31273ab5 | textbox | Date Completed:
da6d182d-bb83-4e22-b83e-bd377369d9c8 | checkpoint | 2.6 Maintenance of stockpiles
4a6390cb-8e7d-547d-861a-2f773e827578 | note | FREQUENCY: Each lot
fe0e676b-3e17-532f-9a02-87028c0c9843 | note | ACCEPTANCE CRITERIA: Stockpiles maintained neatly and away from stormwater drains
86848581-3a7f-5894-b97c-0eb67ff252ea | note | • erosion controls in place
fdd4927e-c54a-5f48-b074-7c4830580f76 | note | • stockpile treated to minimise spread of weeds and pathogens
445dbabf-f4f5-52b8-a4b6-96319350697b | note | REFERENCE DOCUMENTS: 204.05c
b58143d8-5117-5b2c-a177-90adf5c1750b | note | INSPECTION/TEST METHOD: Visual Inspection
2dce3c92-ad52-52fd-b5d7-ebc6ed616961 | note | RECORD OF CONFORMITY: ITP Signed
d23512a0-5b3d-59b6-a24b-dd588f0de0e6 | note | IP
fa582af3-0aba-5e00-a19d-f69995946d9c | note | RESPONSIBILITY: Site Engineer / Site Foreman
3af5e2bd-0913-50cd-85c7-ceea9689a659 | textbox | Date Completed:
d2bec96b-5943-4f7f-84bf-edfe75c21af2 | section | Placing Topsoil
2240f874-4687-4cbb-b3c6-d03d9a7283b3 | checkpoint | 3.1 Surface finish of cut and fill batters
f9cf8ef5-3836-5c25-96ba-be375984dd26 | note | FREQUENCY: Each lot
a275c7d8-d73b-5099-a5da-64fdc310e207 | note | ACCEPTANCE CRITERIA: The surface of cut and fill batters to be topsoiled shall be textured by scarifying or horizontal grooving
5b1612bc-86ac-5c94-a157-303cc50fd94a | note | REFERENCE DOCUMENTS: Cl 204.06 (i)
4fb9e9c5-0acf-5d1b-bde3-2634e91f5539 | note | INSPECTION/TEST METHOD: Verify
5f2254a1-8d1c-5eb2-a8de-12c9f9fe3eb7 | note | RECORD OF CONFORMITY: ITP Signed
d345d409-632f-5ff0-948a-c3e1dc4088e5 | note | IP
d7371ad6-0080-5522-b757-b2734d90a85b | note | RESPONSIBILITY: Site Engineer / Site Foreman
0dc96d3e-cb23-558f-8f2e-73ef3f124f1b | textbox | Date Completed:
a9ed4f39-bb11-4522-ace7-c5f6a4a317d8 | checkpoint | 3.2 Topsoil Placement
b5500351-bb54-5926-985c-e553591d5eed | note | FREQUENCY: Each lot
ba362a36-42a9-5fc7-a2d7-279f935cf82f | note | ACCEPTANCE CRITERIA: Confirm underlying cut/fill areas comply with Cl204.03 before placing topsoil. All disturbed areas not paved or landscaped topsoiled to the following depths:
34b79bd0-5e52-5621-9a4e-d794b692eb26 | note | • batter slopes > 2:1 = 50mm min
f6538ce1-4cc7-5299-bd4c-f8e4a72fc1a4 | note | • planting beds = 100mm min
fdc05903-44f3-5234-a828-974581f57cff | note | • verge - 50mm outer edge to 20mm within 100mm of seal
48328dcd-3f67-57dc-9a99-6d698a5e20f9 | note | • all other areas – 75mm min
c1eeaf56-84b1-553f-8206-a127983b56fe | note | REFERENCE DOCUMENTS: Cl 204.17
2e8ac151-8461-5ec3-8c6f-f84b6dfde4e5 | note | INSPECTION/TEST METHOD: Visual Inspection
f80ba88c-c4ee-513e-98c4-7a13a07e490f | note | RECORD OF CONFORMITY: ITP Signed
05c85c28-a24e-52b6-96be-8fac344124fe | note | IP
63ba507c-b5bf-575f-9d78-5f25939ff022 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0d23b297-8c04-50ad-9121-206c8fe908d3 | textbox | Date Completed:
5bfe4399-d461-46bd-8e5c-2eb1094847e1 | checkpoint | 3.3 Surface level
f088bfa2-e055-576c-ab59-e55c76207464 | note | FREQUENCY: Each lot
64beddf5-6b1b-50dd-8bda-51dcdbb5b1c0 | note | ACCEPTANCE CRITERIA: Area topsoiled spread, levelled, but not compacted (except verge area).
5a812eeb-c41b-5113-9972-8b5e0a244cc7 | note | REFERENCE DOCUMENTS: Cl 204.17
1e0e3512-a6d2-56f9-a7e4-6dbae649339d | note | INSPECTION/TEST METHOD: Visual Inspection
4fe2e8d1-7d5c-5b1e-9b44-3cedf80958d7 | note | RECORD OF CONFORMITY: ITP Signed
e1f953f4-c6ab-5c63-91f0-35af14403048 | note | IP
b882e38e-c4d3-5682-a82a-4674e42fd7a3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
3f819dfe-d887-52cf-9e81-b83aaf774e6f | textbox | Date Completed:
17333048-5daf-4384-a15c-97cc6c8de487 | checkpoint | Final Inspection
a770be01-b0d2-5e8f-b128-f04d389c3655 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
aaa5baac-8b8d-5a3f-81d3-b1e6784777cf | textbox | Print Name:
b697f175-6518-55f1-818c-54b0818e5fd5 | textbox | Position:
92296b97-6cc0-5682-9a8e-11b9aeb603ac | textbox | Date:
1d82aa6b-e62d-4045-ae94-cbbfff455c62 | checklist | FHC-ITP-003 - Subgrade Preparation |  | FHC-ITP-003 - Subgrade Preparation
01f0bc8b-6d3a-41cb-b1d6-01769b7da132 | section | Preliminary Works
095b852a-15f3-43d3-b4d7-755b44dc59a6 | checkpoint | 1.1 Check for correct documentation
fd1c03de-1c55-59ed-9171-2ef34ad5daf8 | note | FREQUENCY: Prior to commencing any activity
89b186d2-7990-54d2-8d60-23b1cdf9a45d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
41930f79-e7bd-530f-a2f2-62666074bd93 | note | – using the correct and complete set of drawings
425548d4-c1a5-5939-b67c-c3cca6b8a149 | note | – all drawings are the latest revision
ed6e3fda-15b9-5c23-8173-e798b6bdf960 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
a9a72881-e384-5175-9ed8-0592323cbc42 | note | INSPECTION/TEST METHOD: Visual inspection
1a960a2d-224f-5227-a4d2-f6cc6c1c8288 | note | RECORD OF CONFORMITY: This ITP signed off
59c8a33a-0423-5848-b19a-adb4412c0442 | note | HP*
21063b3d-7dbf-5c76-ac96-e0b5f012cfa9 | note | RESPONSIBILITY: Site Engineer / Site Foreman
82913a6e-4e79-5254-8427-0b0eae86368c | textbox | Date Completed:
9f39fd5f-3799-4a40-a6c1-7734d1f257f8 | checkpoint | 1.2 Implementation of all measures and controls
0d4da8e8-d533-5819-acf7-c9c9a7df8ec8 | note | FREQUENCY: Prior to commencing any activity
e71023e9-2f47-55a8-80f0-3b3715d243e1 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
f2fc96b9-dbb0-5e30-a2b1-9382f5d2c92d | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
88e060d1-f33d-54c2-81e0-6f23c6846feb | note | INSPECTION/TEST METHOD: Visual Inspection
0f778720-fecd-5066-b9e8-050067e8359d | note | RECORD OF CONFORMITY: This ITP signed off
4874052e-7eed-5e14-8ec3-1411fb8dc2aa | note | HP*
4a9ac26d-4d45-5ce6-a7b2-0d75df824e26 | note | RESPONSIBILITY: Site Engineer / Site Foreman
635d27ca-7c62-52ba-a014-5fc49415b147 | textbox | Date Completed:
109e0002-a726-4180-8e29-2060dc705738 | section | Construction Works
70acb7a1-ae9c-4949-b56c-6cd11168da9c | checkpoint | 2.1 Survey Set-Out
df6d608f-6ffd-57dd-8452-8e3efede885b | note | FREQUENCY: Prior to commencement of excavation
d26b4e09-961b-56ed-99de-d381c5723a11 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
736fc137-75a0-5e06-8a87-eec5ce0b586d | note | REFERENCE DOCUMENTS: Drawings, Work Procedure
4846929a-1735-539e-a552-89c0d0698ea1 | note | INSPECTION/TEST METHOD: Verify
e5c737c3-81f5-59e3-b7c9-c5c5fd75cf74 | note | RECORD OF CONFORMITY: This ITP signed
2ea116e4-bdbb-5103-ad91-dff691b6eec8 | note | IP
639ea2b9-d478-5c19-a48d-c7e6fdc8d7ac | note | RESPONSIBILITY: Site Engineer/ Surveyor
cde71340-f5de-5ed9-b06d-666a2084bc3a | textbox | Date Completed:
873d973c-b4e9-4f76-b065-ad21b1b1e34c | checkpoint | 2.2 Excavation Permit
4f90193d-16d6-5b41-89d9-900c74eab1eb | note | FREQUENCY: Each lot
801225b2-3f98-5817-83ed-b68e69eb74f7 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
ebec2e0c-e6f5-5023-a2c5-586e293d4c0b | note | REFERENCE DOCUMENTS: Excavation permit
88cc4cf2-f355-5657-bb59-c8d635decad6 | note | INSPECTION/TEST METHOD: Verify
0554e96b-e801-587a-a20a-d9146887a16f | note | RECORD OF CONFORMITY: This ITP Signed Off
42dc7b48-fc24-53dc-a92a-a09152be3252 | note | HP*
7c4bb7bd-c933-5b86-97a5-8f0c143ab730 | note | RESPONSIBILITY: Site Engineer
6a42045f-a7c4-5740-a998-324260dd0b36 | textbox | Date Completed:
d01a3326-f97a-4caa-b036-03bc47b24de4 | checkpoint | 2.3 Subgrade Material Properties
f2d33670-ed2b-5a24-8a3e-3d006578018c | note | FREQUENCY: Each Lot
b88fb4af-24ac-5e8f-92e2-4765ec8f5b62 | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
64f81929-6cc4-57e0-ac07-2c3a22334838 | note | • If parameter met rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
301842de-a6ef-5e4c-ad27-73d5a8ce6877 | note | REFERENCE DOCUMENTS: 204.06 (e)
df4bb027-ffd3-5457-997d-a4ac81692c22 | note | INSPECTION/TEST METHOD: Test Point
44228ff5-6df1-511b-88fc-4cd27669c724 | note | RECORD OF CONFORMITY: Test Reports
7b42bebb-781e-5ad9-aca0-ba7c5295eb3d | note | TP
cf374141-120d-59d2-99f8-382814015267 | note | RESPONSIBILITY: Site Engineer
2bd5b6ef-87a8-5730-8199-794da0b1881a | textbox | Date Completed:
f323f226-d8a3-4e39-96e6-198fc75534e4 | checkpoint | 2.4 Inspection of Subgrade Material
07dd4569-05e8-5d32-9704-95a2d797a5ec | note | FREQUENCY: Each lot
a088bbe6-f48b-54be-b4c3-44291fc0bc9e | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
b183881b-dc30-5b25-855b-87e8ee6d0986 | note | REFERENCE DOCUMENTS: 204.06 (c)
a3ce3821-72e6-5b77-b5ad-23a3fb33d4f2 | note | INSPECTION/TEST METHOD: Verify
0aefe4e9-3350-57d8-b92e-ec148e338871 | note | RECORD OF CONFORMITY: This ITP Signed Off
e266d1a6-ff3e-57dd-9349-588ab4bcafa8 | note | HP
72dc8b51-bcaa-54d3-a43d-10daf6aa8c03 | note | RESPONSIBILITY: Site Engineer/ Superintendent
55ab5e88-56a1-5813-b4e8-6204c1d7aecc | textbox | Date Completed:
6137ef2d-024b-48fe-825e-578b6565513a | signoff | AUTHORITY HOLDPOINT
343e99d8-a3f7-4004-b9b5-665d03cba3f3 | checkpoint | 2.5 Acceptance of Rock Subgrade (when applicable)
c7bd1dfa-a611-5de8-903b-bc9c80e6cf79 | note | FREQUENCY: Prior construction of the regulating layer
5125ffcf-39fe-5ff1-90ed-31f6dafdda7a | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
304a11d9-2672-5222-9725-1291553b9969 | note | • Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
d2977859-34f0-5d12-961a-56dbd98882d7 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
451d5595-2ee0-519f-a5b6-eafa9446c37b | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
663247d9-7301-5023-9744-85d8021d958e | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
25531731-6839-57ea-a2b7-b641012738df | note | HP
d776c38c-f1e6-5625-9e8d-40cb6cc18dad | note | RESPONSIBILITY: Site Engineer/ Superintendent
bd1ab34d-a99f-55a0-b31e-335d9fc21c2f | textbox | Date Completed:
27655877-14bf-483b-b40e-33817e23dba6 | signoff | AUTHORITY HOLDPOINT
4d988f98-b086-41e1-8ee7-c3df8950b5d2 | checkpoint | 2.7 Unsuitable Material
b416cdfe-4bc3-50db-a078-dc7bd88f5bba | note | FREQUENCY: Each Lot
2abd14b3-6d8d-5d86-8bc5-694868290e98 | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
a5a2b1b5-8e38-561f-ba22-979f75e35834 | note | REFERENCE DOCUMENTS: 204.07 (d)
af94ea20-1cbc-5608-87de-b36e3ad47f70 | note | INSPECTION/TEST METHOD: Visual Inspection
6dd42687-8fab-5904-9ac7-16dab85a69b7 | note | RECORD OF CONFORMITY: This ITP Signed Off
98e4d80c-8008-5e66-b17b-3d8ffff009bb | note | HP
37167d88-2065-5388-88d6-0c2471ca3871 | note | RESPONSIBILITY: Site Engineer/ Superintendent
774adb9d-8fc7-55fc-8e12-12809c43e495 | textbox | Date Completed:
df149b82-7853-48dc-8fac-a3fab388b3d9 | signoff | AUTHORITY HOLDPOINT
5a2e8ca7-1ddf-4edf-865e-1be832989378 | checkpoint | 2.8 Groundwater
c973e410-4701-5b16-b74d-0f8d5b341ae2 | note | FREQUENCY: Each Lot
c0dac556-8574-5397-9342-ce81cc64eba4 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
d8f37b7b-f556-5b48-b913-2bb527e63723 | note | • The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
f7c02b59-9a46-5dc3-a3c1-ff43e3deb76a | note | REFERENCE DOCUMENTS: 204.06 (h)
ed97d883-243f-5096-868c-1e510d7abc5a | note | INSPECTION/TEST METHOD: Visual inspection
a7bea266-9366-5e24-b3ab-88af44ead859 | note | RECORD OF CONFORMITY: This ITP signed off
ae65a00e-ed43-5635-b29f-18fde8c9b87d | note | HP
31dac92e-934c-55cc-984d-414eee91cb74 | note | RESPONSIBILITY: Site Engineer/ Superintendent
e42da126-dd4b-5dd5-acf9-2628345c05bd | textbox | Date Completed:
fadeffa8-db2b-406d-8d42-265ba9273e33 | signoff | AUTHORITY HOLDPOINT
abd3dae2-876a-4fc3-a7f7-b614cb95dbf2 | checkpoint | 2.9 Trimming and Level conformity
324855ec-9bb0-52b3-a0a7-551c9a323539 | note | FREQUENCY: Each Lot
b042da88-ee71-5e95-8624-19b4c866a941 | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2.
832f0cc2-2760-5579-b3ef-231e9b52caa4 | note | • Level tolerances:
d6f3f2e0-6b5c-543f-bc67-6f06aabc3254 | note | ○ Range x = +15, -30mm
16a7c7c7-0778-5490-8d90-90b0178d79fd | note | ○ Max S = 12 mm
606ec90b-2ed2-571f-85bd-c0e233c896c5 | note | ○ 40 measurements per lot (Scale B)
9eceb44b-ec3a-579b-8eaf-553a438b48be | note | REFERENCE DOCUMENTS: 204.03(f)(g)(h)
f2da68ba-d550-59e4-83f0-061247248bc5 | note | INSPECTION/TEST METHOD: Survey Report
4ed13018-0468-5548-90d9-dec33802befa | note | RECORD OF CONFORMITY: Survey Record
474e4eab-cdf9-532b-afe3-6b70fcaa103a | note | SCP
f4b672f5-4b16-5c4f-85ac-c9e50260d91a | note | RESPONSIBILITY: Site Engineer/ Surveyor
14ef3b2f-b2ed-56f1-b85a-2d57daaa8e42 | textbox | Date Completed:
921fbd9f-80a4-46fd-9727-6310bdf3b01e | section | Testing
8da5275d-5f10-49cb-8a04-3f8d7d8201b2 | checkpoint | 3.1 Proof Rolling
55072042-cfcf-53bd-9f67-c72cabd8db50 | note | FREQUENCY: Each Lot
0e14bfd1-92ed-5c71-9868-8eafedce822f | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
db5edc99-7d2f-5759-b0af-a79da0a1ac1b | note | REFERENCE DOCUMENTS: Section 173
28f5a843-5c16-52f9-9d5a-8ed90d31dd38 | note | INSPECTION/TEST METHOD: Visual Inspection
2762c37f-ab5e-53e2-95f3-c0c8effb106d | note | RECORD OF CONFORMITY: This ITP signed off
b443e68c-9085-56aa-a1bd-d81cd274ace9 | note | HP* / WP
d5f7e103-9d85-5b95-bdbc-8f1825fae63a | note | RESPONSIBILITY: Site Engineer/ Superintendent
5ce9889f-6389-501f-ae57-313afef4219f | textbox | Date Completed:
35a1041e-de11-4186-9060-ad645f29c4be | checkpoint | 3.2 Minimum Testing
1fd4ab6d-15e2-50d7-855b-7c2d2f79358b | note | FREQUENCY: Each Lot
3729432c-78a5-5359-ae2c-ab521167b316 | note | ACCEPTANCE CRITERIA: Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test.
3caa05ac-4aaf-5c08-a879-50ddc55c8e53 | note | • After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
71ab5924-96ab-5dec-bdec-09025de63a74 | note | REFERENCE DOCUMENTS: 204.14 c
6260e967-2cf9-5719-9e7d-d31f7aba8f94 | note | INSPECTION/TEST METHOD: Test Point
a57b62fd-46c3-57f0-b247-824c2e4d7027 | note | RECORD OF CONFORMITY: This ITP signed off
a1501556-46c2-57e7-9e33-f7e167dbce12 | note | HP* / WP
a9f22d17-9369-57a4-967f-1482733c1da0 | note | RESPONSIBILITY: Site Engineer/ Superintendent
c209015d-3c5b-5f28-9023-716bdbcc0546 | textbox | Date Completed:
6aebfc8c-4485-46c3-9f1c-1c67674a6667 | checkpoint | 3.3 Compaction Testing
f20286b5-d522-5fe4-a49a-8c19ed1b0e75 | note | FREQUENCY: Each Lot
9884cef7-cbd0-50da-b03a-df22f752feaf | note | ACCEPTANCE CRITERIA: Ripped and re-compacted material below Cut Floor Level = minimum compaction 98% SDD.
1d285a71-3462-5dc3-8888-c0172ecbe327 | note | • Type B Material placed within 400 mm of top of Type B Material = minimum compaction 95% SDD.
474bad58-f59e-5da3-9476-bb27ea8928b0 | note | • Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 95% SDD.
5850daa2-cb70-5c26-8f29-ff7d53f3679f | note | REFERENCE DOCUMENTS: Table 204.131
c40754a9-9496-524c-a62e-b495e99b356c | note | INSPECTION/TEST METHOD: Test Point
c5f45c59-3781-5495-9924-44a8e0e340bf | note | RECORD OF CONFORMITY: Test Records Lot Register
096062ff-22a7-5e09-a5d6-4a715d224eb9 | note | TP
4906478d-45fe-504d-be20-f22e564a23f7 | note | RESPONSIBILITY: Site Engineer
aa240404-f124-5a87-8465-1b42d52bce76 | textbox | Date Completed:
ce38d981-8974-4cce-aac2-e082e0d2d5c7 | checkpoint | Final Inspection
67039d6b-85c7-5091-9992-3dd37ee40294 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0d1a90e8-3fb5-592e-a17d-ad5b20c99f12 | textbox | Print Name:
9df18da1-4893-5a56-b497-608da2469009 | textbox | Position:
dae8bdcc-2ccf-53d6-ae47-4c54e057e836 | textbox | Date:
a6a7faa1-af68-4a4e-92a8-c0bc6493fb31 | checklist | FHC-ITP-004 - Type A Fill Placement Rev3 |  | FHC-ITP-004 - Type A Fill Placement Rev3
09261102-6d73-4eee-bafa-c47b0a5ed206 | section | Preliminary Works
b8081cd0-a487-495f-b178-ec0064065f44 | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
5b906f7f-e843-5c09-96dd-561f80421dec | note | FREQUENCY: Prior to commencing
26db5b55-685d-5d3b-855a-7a674d3c139f | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
5959fc49-bbf3-5f14-a4b3-5003f10d6dc4 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
cc35019d-d70f-5092-8fe8-f84cf5d56ac7 | note | INSPECTION/TEST METHOD: Visual Inspection
608bae5c-1683-58a8-b5df-5f38ca517d5c | note | RECORD OF CONFORMITY: This ITP Signed Off
c995c3bf-da10-5686-a5c7-8073486f5ad4 | note | HP*
feea664f-d59a-59cf-9a8c-89c5ad219769 | note | RESPONSIBILITY: Site Engineer / Site Foreman
79dd3916-128a-54be-9400-642b19c7af9c | textbox | Date Completed:
1c6dbd35-5699-4c8a-8b61-a4c68f8214d2 | checkpoint | 1.2 Implementation of all measures and controls
ae3b3ab6-2386-5072-bd5b-6b271525adbd | note | FREQUENCY: Prior to Placement/ Each Lot
58999dbd-9b35-586d-b9b1-fab78cd58a2d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
8c9c134d-21b8-51ab-91d0-539812a65115 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
1e5fe1bf-1d87-5a1e-bc34-168031ceacb9 | note | INSPECTION/TEST METHOD: Visual Inspection
594e7ee5-2956-5875-9071-ee44d752a5f2 | note | RECORD OF CONFORMITY: This ITP Signed Off
0832987e-9fe3-5d6c-898b-633cc1318576 | note | HP*
785d8a64-65a8-5de9-87a5-b9d7e08cd63a | note | RESPONSIBILITY: Site Engineer / Site Foreman
15092416-67f5-5515-8f61-3c6d1900fd77 | textbox | Date Completed:
9b776f67-54b8-4c67-a85f-ca86719c936a | checkpoint | 1.3 Verify Material
b78fd87d-1224-5e20-ad35-823bc7fbfcfe | note | FREQUENCY: Prior to Placement
e30c7178-ae40-5514-80d7-21645f11b194 | note | ACCEPTANCE CRITERIA: Assigned CBR to be greater than 6% (<10%), swell is to be less than 1.5%, unless approved as expansive.
3a9183f6-e9ae-5bb7-ad2f-875ddbbcf4da | note | • Soil is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075. PI between 6 and 25. Permeability of less than 5X10^-9 for capping and verge material
531f8b62-bbf1-5529-83e7-4aaffbd1c7b5 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(b), Cl. 204.06(c), Table 204.041, Table 3020.052
7fb19c4b-7f12-59e4-897c-68007538128f | note | INSPECTION/TEST METHOD: Site Inspection
eae2a746-5f2f-51ca-8da6-f91d332c78b3 | note | RECORD OF CONFORMITY: Test Record (If silt is observed)
f642c184-967b-59f5-9e7d-4066d3cb63a6 | note | HP
39ed6d17-d178-591f-ac3b-0eed9e4ef0f1 | note | RESPONSIBILITY: Site Engineer & Superintendent
1c3e61c4-6383-561d-bed4-f86b9e1ec944 | textbox | Date Completed:
ccffa5d9-5913-4525-a084-0823d3ab6ef6 | signoff | AUTHORITY HOLDPOINT
406040b7-c9c0-4d55-9429-6d2e9d12b510 | checkpoint | 1.4 Excavation Permit
3e795432-689f-561c-bc8a-eabb2365349c | note | FREQUENCY: Each lot
0bb2a92b-3a9f-5729-9d3a-02a01aee2f96 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
404bda5a-e5ca-58da-8e7b-9bea62d02af1 | note | • Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
2d5fbd41-6dc5-5a61-9c38-5b29b48e31a6 | note | REFERENCE DOCUMENTS: Excavation permit
5f99417b-b330-536d-8fa4-5f84585adfab | note | INSPECTION/TEST METHOD: Verify
9cc06216-db4e-5a5d-999b-025eb678718b | note | RECORD OF CONFORMITY: This ITP Signed Off
83354864-ab65-5a93-8e96-7e71110c48a2 | note | HP*
1c46958a-0308-5e6d-94b2-49118e666bd1 | note | RESPONSIBILITY: Site Engineer
bd5315d4-8de5-5fbf-b86a-e30d2ef83f9d | textbox | Date Completed:
d0ebd69a-c438-4a16-948e-afafc100c145 | section | Construction Works
595e42bf-1513-4f9b-a2a3-36164aac3738 | checkpoint | 2.1 Survey set-out
0c1e920d-3409-55a7-a7d1-659e4e41f317 | note | FREQUENCY: Prior to Commencing Excavation
fdd19e97-a57f-528b-9537-0c91fe13e58b | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
5a07b119-0454-5eda-bf74-e8e485ca5262 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
87adbc6a-c518-5a0d-9ba0-fe7cfe122e97 | note | INSPECTION/TEST METHOD: Site Inspection
517a55a0-7539-510f-a03d-807391bcee4f | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
fcac60f0-1b85-5134-b9e5-3f9ee13a0793 | note | SCP
292dfc49-5376-5652-a127-55044edff736 | note | RESPONSIBILITY: Site Engineer/ Surveyor
93d12152-e4cf-5941-a322-ed7cf48b8392 | textbox | Date Completed:
72ef5fac-8887-4af0-b608-480df865e609 | checkpoint | 2.2 Inspection of fill area
b631eda6-771a-5244-8277-4772f413ec5c | note | FREQUENCY: Each lot
08ca371a-9bf6-565e-84d5-f248c7620997 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
c9089a9c-9ab5-5e04-84f8-188ea781542b | note | REFERENCE DOCUMENTS: 204.10 (b)
97ea7110-503b-5206-af22-32525f22c49d | note | INSPECTION/TEST METHOD: Visual Inspection
15fba5e1-f46b-5dd1-9512-aa859c85883a | note | RECORD OF CONFORMITY: This ITP Signed Off
ca3a8bf8-e845-535e-af95-03d61ead9382 | note | HP
1a5b266a-2a8a-5268-a647-e2163488305e | note | RESPONSIBILITY: Site Engineer / Superintendent
024b7727-4df7-5597-a0c6-2559bf8adc6a | textbox | Date Completed:
86dc9a4f-b9e5-41eb-9a18-b7fbf5ca109c | signoff | AUTHORITY HOLDPOINT
ab010cc9-ee06-41cb-add5-09d3a122bed4 | checkpoint | 2.3 Layer Thickness
8335b70d-7d73-5db1-81b7-fcbdd5086873 | note | FREQUENCY: During Excavation
19750e47-bba1-5bf7-b11c-29653a1cc6c4 | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
115117f4-8aff-56d0-9d45-ff6073dd2801 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
5f8212f3-3364-57d8-929b-0607239cc116 | note | INSPECTION/TEST METHOD: Visual Inspection
2495dd61-dd91-5d0e-8f07-c16825058088 | note | RECORD OF CONFORMITY: This ITP Signed Off
937d5115-8ae5-511c-9ecb-8266bd8be452 | note | IP
0adfff96-8c86-5d16-81eb-3b8b88dee7a7 | note | RESPONSIBILITY: Site Engineer
4b2db727-74a4-573f-8682-c6252d08ab89 | textbox | Date Completed:
c47d5d75-893b-4ab4-9480-4a219199b19d | checkpoint | 2.4 Maximum Lot Size
fd44a932-2842-5b92-8537-931051725f87 | note | FREQUENCY: During Excavation
4ce333d1-b2fc-5636-836d-a853c45a0885 | note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 5,000m2, whichever is lesser.
7e7e1232-ff43-55a7-9f72-ba611b8868f8 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
0179240f-0b41-515f-9ce8-e05fb0d2d314 | note | INSPECTION/TEST METHOD: Visual Inspection
34bfa388-fe62-51e5-b0ec-b84591c430dc | note | RECORD OF CONFORMITY: This ITP Signed Off
737929ed-2614-509c-9311-56555e5693bc | note | IP
61c27e76-939a-572c-bcb9-cf037c575bf6 | note | RESPONSIBILITY: Site Engineer
41eb4c31-66b7-511c-ba7d-0e3eef1e52a3 | textbox | Date Completed:
9721c6f7-0319-457e-8751-ed6f7edc2968 | checkpoint | 2.5 Type A Placement
ce88ed41-fe6a-548f-807a-4279faffe02d | note | FREQUENCY: Prior to Placement/ Each Lot
fd29e17b-d1c6-567c-97ae-d0cf36dd3964 | note | ACCEPTANCE CRITERIA: Top of fill must be shaped and compacted to minimise damage due to wet weather note 12 on Pavement Details 009-0001 "Capping Material can be substituted for (3%) Cement treated Stab Sand in confined areas
92289c7e-64a0-514c-babb-4497934c67e5 | note | • Any rocky material present must be uniform throughout the layer
dd4fcab2-eab5-5ff0-a954-9fc917225e9b | note | • Each layer shall be kept generally parallel to the surface of subgrade
a8755eac-6156-5dae-a25b-fbd8b0c9a59b | note | REFERENCE DOCUMENTS: 204.10 (d) (i)., 204.10 (d) (ii)., Table 3020.052
d2db07d9-d2d6-5f93-b0e4-03119a46c718 | note | INSPECTION/TEST METHOD: Visual Inspection
f217fab5-62f0-58c9-bd71-3f1144da614a | note | RECORD OF CONFORMITY: This ITP Signed Off
5d3391ba-5c77-56f1-9a08-707491bf11a9 | note | IP
9060fcfe-4598-581e-995d-e296fafc5d30 | note | RESPONSIBILITY: Site Engineer / Site Foreman
9da80596-7898-5848-8bb4-dff1278c2624 | textbox | Date Completed:
37b80c9f-94d3-49de-a1c6-65ea4dbf2b42 | checkpoint | 2.6 Proof Roll
634ffcfc-f782-5ee4-88de-a8bb4ebfab77 | note | FREQUENCY: Each lot
b4fbe3ea-369e-50bd-8607-31ba42dc164f | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
00ccd4ac-bf96-5e12-bf1a-97b7be75630e | note | REFERENCE DOCUMENTS: 173.03, 204.12), 204.10 (b)
051ee913-1547-5b76-8bc0-24d627410710 | note | INSPECTION/TEST METHOD: Visual Inspection
e490d850-c6ea-58a0-921c-227b8f442cb7 | note | RECORD OF CONFORMITY: This ITP Signed Off
747e57a0-24d5-55f3-ad85-566b26996af6 | note | WP
794693b6-29f2-5abb-909f-917e104d7191 | note | RESPONSIBILITY: Site Foreman/ Superintendent
bcf3224f-4060-5781-8501-56ec5ed2c116 | textbox | Date Completed:
118d4195-4300-4b0d-89b3-f494ffcc5557 | section | Testing
10d7f815-9074-42b9-8885-76d2c26e6136 | checkpoint | 3.1 Reduced Test Frequency
6d41e939-cba6-5abc-b8a6-eefc85d4c7ac | note | FREQUENCY: Each lot
cbf4956d-1910-59da-9d88-91ef336c9823 | note | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
e86afc41-b1d9-5737-8d72-ff4e1eb3632e | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
85a18bdf-5af0-53c8-8cfa-db353f6ac9b4 | note | INSPECTION/TEST METHOD: Test Record
e6da775b-534b-54e9-86b8-90d33801ece6 | note | RECORD OF CONFORMITY: Test Records
9506f452-8c7a-5961-adbf-5975d2ea57a9 | note | AP
33cffc0f-82dd-5c11-bdeb-aaed758a77fc | note | RESPONSIBILITY: Project Engineer
91f9b730-a0ab-5a31-ba3c-1e98871325c7 | textbox | Date Completed:
ae776d9b-be76-41c4-9fd4-2d078f429bd6 | checkpoint | 3.2 Compaction Testing
30c8cfb5-2187-5f26-977c-443dd021573c | note | FREQUENCY: Each Lot
d28bc116-1619-5071-bf52-1c5695ef3b19 | note | ACCEPTANCE CRITERIA: Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B).
b5786b1b-326a-561e-8901-b7d53f43893d | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
321368ab-8004-5181-b83d-b63061216514 | note | INSPECTION/TEST METHOD: Verify
c0fdeb25-6c8f-53c5-be4d-df321498f372 | note | RECORD OF CONFORMITY: Compaction Test Records
4a8c5e89-1dd5-51a4-89d5-e9d6489b0469 | note | TP
fca21fac-46ff-51c3-adb2-09a0cb85c697 | note | RESPONSIBILITY: Site Engineer
2ae29a9a-6f54-5ba6-ad33-2cc2525e7f16 | textbox | Date Completed:
3219c8a7-e376-4928-a952-2a5f4b764e61 | checkpoint | 3.3 Maximum Particle Size
235e2b4c-550f-5fad-9118-2aa88da447d5 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
bde27580-e0d8-5911-bb64-64340411c8de | note | ACCEPTANCE CRITERIA: Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075
0cc35501-c65a-5150-9197-464234d34654 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii), Table 204.141, Table 204.041
d0973d44-9994-56db-9fb7-509a4b1e2fff | note | INSPECTION/TEST METHOD: Verify
d33ad4e5-068f-574d-b718-db86d9037020 | note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
4b596e92-9b45-510b-a5d8-34bcb4fea0e5 | note | TP
422d43ba-5e7d-5b17-9762-1abd92296b83 | note | RESPONSIBILITY: Site Engineer
b5fdc094-0d0c-583c-8c61-ad6ea7b60846 | textbox | Date Completed:
dc65ec40-69ac-47fb-9349-80864bb6f745 | checkpoint | 3.4 CBR/Swell
143ef58c-b138-5fda-83e3-477e55c15c53 | note | FREQUENCY: First lot then every Second thereafter
447f03fa-c5c9-5a28-95e0-a8f1ce6a6a65 | note | ACCEPTANCE CRITERIA: CBR: ≥ 6%, Swell: ≤ 1.5% (Verge material less than 1.0%).
039ae721-5039-55c0-a68f-4e5e11f368d7 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(i), Table 204.141, Table 204.041
5271553d-f6a5-5155-8170-25a1dfdfc993 | note | INSPECTION/TEST METHOD: Verify
1661e5b1-7ea3-594a-b67d-593bf5173672 | note | RECORD OF CONFORMITY: CBR/Swell Test Records
955e4629-e6c3-587c-8d3c-9f5683d3883e | note | TP
eb01dd7f-2806-5334-b2a1-f380a838913a | note | RESPONSIBILITY: Site Engineer
dfb15b34-2b97-5977-89cd-83044bc79f79 | textbox | Date Completed:
6505298a-4a6d-4719-a1fa-7a594356259e | checkpoint | 3.5 Atterberg Limit Tests
3c36e66c-1f02-5b27-99c2-b331ca0b056e | note | FREQUENCY: Each lot, unless reduced frequency has been approved
2a83ee71-97b4-5d04-9db4-1f2252a8d58c | note | ACCEPTANCE CRITERIA: PI between 6 and 25, PI x % passing through 0.425 to be less than 1000
5fed27c3-72ac-57c6-958f-f9be261ea8cf | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii), Table 204.141, Table 204.041
3ac35b59-af13-59ee-a95c-d24c2a793055 | note | INSPECTION/TEST METHOD: Verify
5068c0c6-73b2-50e6-970a-c2d2ba85d47f | note | RECORD OF CONFORMITY: PI Test Records
07b352be-3a9a-5e74-96d8-443d99043d8f | note | TP
f1b9933f-9426-55ee-ae9e-8d44dcff453f | note | RESPONSIBILITY: Site Engineer
8cca190e-1d80-536b-b007-57eb561517cc | textbox | Date Completed:
3ccfcae5-daf6-41fa-839d-a714ea5ecd40 | checkpoint | 3.6 Permeability
37d2e7e3-adff-5611-a589-2f7fcc378ab2 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
2a41d763-ba8c-5d3f-b79a-103d5606088a | note | ACCEPTANCE CRITERIA: Permeability of less than 5X10^-9 for capping and verge material
68e5e52b-0c47-50af-8540-95ed4541797d | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii), Table 204.141, Table 204.041
fd1c0712-1552-52ec-a291-058107f3038c | note | INSPECTION/TEST METHOD: Verify
309e79d4-211f-5ccf-ac21-7f0f29180998 | note | RECORD OF CONFORMITY: Permeability Test Records
7768d4c1-6ecd-538c-a202-38928c736a32 | note | TP
02937c57-25c4-5340-9504-fe8562baee82 | note | RESPONSIBILITY: Site Engineer
6a291638-f634-56a2-9e7c-f220b0b47e2e | textbox | Date Completed:
e5608e91-e2f2-4e31-a35a-55718f4cc4c2 | checkpoint | 3.7 Material Property Testing (Scale B)
bba1fe1b-bad4-5143-8c90-0530df1047bc | note | FREQUENCY: Each lot, unless reduced frequency has been approved
662beacf-3948-567c-beb9-77ce248e8916 | note | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
238604e8-adec-5d17-a9cc-21465cc550e0 | note | REFERENCE DOCUMENTS: Cl 204.04, Cl204.14
6953ba56-30d7-50a2-8dd8-810bf81146b5 | note | INSPECTION/TEST METHOD: Verify
4c17adbe-32ed-5741-ac7b-145d6d77b9ab | note | RECORD OF CONFORMITY: NATA test report
b53d5011-8cd2-5edf-8913-693c5714ef28 | note | TP
086fab91-8469-5b5d-b955-c80877fec5e5 | note | RESPONSIBILITY: Site Engineer
75222d69-9f7b-57c6-ad80-64d10864ed90 | textbox | Date Completed:
6543e0f5-fb81-4ccd-9659-90410b9f7421 | checkpoint | 3.8 Survey Conformance
b7963c98-e88e-546c-b46d-d5bd2bb01df4 | note | FREQUENCY: Each lot
db040f01-a0e4-5b70-8325-5753db1a8d74 | note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
411169cf-84fa-5b78-b9e8-9e26782da85c | note | • Scale B:
2b1fdc71-9ba1-5ee4-ab08-5422a24c33fc | note | ○ Range x = +5,-25
9ef3e60f-4fd8-5980-8596-a05f90b6724f | note | ○ Max S = 15mm
a2c2b99d-74d1-5030-9062-1356be2c8c80 | note | ○ 40 measurements per lot
f5fce085-0c13-5afb-8381-e3e60ac60ccf | note | REFERENCE DOCUMENTS: 204.03
43e0557e-da81-512f-ba44-bf5826824d66 | note | INSPECTION/TEST METHOD: Survey conformance point
1a4171a7-7383-5bb0-9801-2270b80404e2 | note | RECORD OF CONFORMITY: Survey report, Lot Register
7b1f5a44-09b8-539a-8371-844219face58 | note | WP / SCP
c62d9a4b-ffb4-541e-871b-47501e87bf3b | note | RESPONSIBILITY: Site Engineer & Surveyor
3600ca19-0fef-55fe-b72e-8c860093718b | textbox | Date Completed:
e0e892ff-2a2a-404c-998d-bd588382fd31 | checkpoint | Final Inspection
83899aed-525d-522b-afec-8effaff42d11 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
db5c8dd7-5640-51b1-aff2-0bde810757df | textbox | Print Name:
439bbb21-1d00-5887-8637-a9a963541853 | textbox | Position:
624de624-cb66-5643-a867-c7a43dd2aa9d | textbox | Date:
e673bc81-aed1-4503-8767-9fb67b9fa2d6 | checklist | FHC-ITP-005 - Class 2 Crushed Rock Rev3 |  | FHC-ITP-005 - Class 2 Crushed Rock Rev3
9274a996-a154-40e5-9150-17bbf5d4c53b | section | Preliminary Works
c0b8e181-0a26-4d3f-a600-62274182d759 | checkpoint | 1.1 Check for correct documentation
9ff8c0c7-b857-59d2-8a1f-9d61dcd27492 | note | FREQUENCY: Prior to commencing any activity
3bd1a184-e8cc-51c2-afe8-78778f2400d5 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a6645242-d3fb-593d-a95a-7a4f0836c38a | note | – Using the correct and complete set of drawings
0a53d8eb-37e0-5e0f-b91a-1c2cbea10972 | note | – All drawings are the latest revision
c7ef0138-6943-5855-ad71-f0b34dc6c312 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
42f61f92-1d01-5183-b1e7-528fb35edb23 | note | INSPECTION/TEST METHOD: Visual inspection
e7851454-0de7-5dd3-8ee1-fc64c4e05307 | note | RECORD OF CONFORMITY: This ITP signed
cbcef7ad-bf2a-565a-82f6-092a3d8cdf66 | note | HP*
0b7f64cd-53e7-50ef-9055-2fbf852d591e | note | RESPONSIBILITY: Site Engineer / Site Foreman
aa4825af-7709-58ba-8f23-61d1dc61cfee | textbox | Date Completed:
59e08350-ed5d-42ea-ae69-b337f70a9140 | checkpoint | 1.2 Material Mix Design
7f2e137b-a196-5577-8652-2400e6ffd950 | note | FREQUENCY: Prior to commencing any activity
202e042c-ae13-5ade-ad5b-98608bb0dbf9 | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
ae33d5d3-91f7-50c0-af55-409679923913 | note | REFERENCE DOCUMENTS: Cl 812.04, RC 500.02
f9fbf38c-a36c-59c5-8174-a82b1cb7fa3a | note | INSPECTION/TEST METHOD: Document Review
153a4f0b-fed4-530d-af78-3198e43aefb2 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
b809e53b-d0ef-59b2-b42a-79d3e5447b96 | note | HP*
f6ff632a-fcb8-5496-b663-05c2e52b7260 | note | RESPONSIBILITY: Site Engineer
d6a22e0d-4dc0-5e6e-8f88-37d894dda060 | textbox | Date Completed:
7556b61f-d68c-4f10-8ac0-74fefb33d3e5 | checkpoint | 1.3 Implementation of all measures and controls
7a663b87-0fd9-5dda-9b83-8a54167b35ee | note | FREQUENCY: Prior to commencing any activity
3be3ec54-c8eb-583e-a52f-2058e2cba1b6 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
01d3c84e-f41d-5b76-b0c6-9d6556a0c7af | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
3aa9efa9-5317-5c6f-84f4-4ee87aa63240 | note | INSPECTION/TEST METHOD: Visual Inspection
2b1f5a7c-25bd-5739-a554-059462428332 | note | RECORD OF CONFORMITY: This ITP signed
87837b54-86b6-5c23-aa19-2610117e38d6 | note | HP*
109d91df-a028-5d8e-893b-5ea163df1287 | note | RESPONSIBILITY: Site Engineer / Site Foreman
e3a1805c-75f1-56a6-826f-76685f24c1ab | textbox | Date Completed:
dbce9919-c9c8-488e-b58f-1ce85f0d3b58 | section | Construction Works
1cd1e500-4e10-437d-9211-031d6dcacf40 | checkpoint | 2.1 Transverse Joints
b18ba1eb-6861-5e87-9981-6efbf03c9d37 | note | FREQUENCY: Check prior to placing material
293b005d-7e8f-5291-91b0-1ffe7fde9401 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
be398a0f-5e40-57f8-9c0b-7c1d0def6f4d | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
285ebb44-3043-59e7-8dc7-35e345e6551f | note | INSPECTION/TEST METHOD: Visual Inspection
bcfaf592-8b58-5446-ade4-c6955d7aeb80 | note | RECORD OF CONFORMITY: This ITP signed off
89d0fbb4-7425-5242-8b54-603673a34ddb | note | IP
b529539e-723f-5979-b01b-a287e66d0e1f | note | RESPONSIBILITY: Site Engineer
adaeb60e-6c78-5256-ac6a-212b8cc61d9d | textbox | Date Completed:
212d5e0d-4610-4611-84e0-ba0ade980f5a | checkpoint | 2.2 Longitudinal Joints
743b4f7f-a7e0-575c-8d37-7316d51668f5 | note | FREQUENCY: Check prior to placing material
82a1fc4f-2753-59f7-84a9-603df820becd | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
7bac3cfb-85c1-53d9-bdb6-52b71a3c3990 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
d9c337a0-003c-5df2-b6da-d8c2c9aebee0 | note | INSPECTION/TEST METHOD: Visual Inspection
13b1a2bf-f71b-568b-a2ba-5f9a750d0d51 | note | RECORD OF CONFORMITY: This ITP signed off
4567481a-21c6-58bc-b752-e7d91f272597 | note | IP
9c0a78d7-ae6f-5617-9752-ab92bd1724f3 | note | RESPONSIBILITY: Site Engineer
2c40cdd8-c939-55f9-ae5f-97cada39977e | textbox | Date Completed:
08f750c8-ea27-46b4-96fa-5401509f30fc | checkpoint | 2.3 Lot Size
541dae93-d2ce-54a8-9ca7-f422dc7230dd | note | FREQUENCY: Check prior to placing material
69dc3b51-70e6-5f21-93e8-f3863cba757a | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
6efd68f0-c000-5a55-aae7-741ccb28d954 | note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
298e8ef1-b1b5-5cc8-9978-e9266fbe8812 | note | INSPECTION/TEST METHOD: Site Inspection
bc150513-54c8-5eac-aca8-bc96abb719a4 | note | RECORD OF CONFORMITY: Signed ITP
e2a0b5bf-9306-50fb-90e1-db758efd4c70 | note | IP
a00adf04-40b6-5405-9073-776724eb13db | note | RESPONSIBILITY: Site Engineer
1b76cd05-58c0-5a83-9922-1e6944d82743 | textbox | Date Completed:
031bf32a-aeb1-4882-bbba-549b4ffcac7e | checkpoint | 2.4 Layer Thickness
989757ce-9267-5f8c-870b-1fb236e21fdf | note | FREQUENCY: Each Lot
f8704018-1499-546f-b4da-350b303823d6 | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
a8a39fd5-857e-51d4-8d5f-11b64b55bccd | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
55462100-162d-5139-a092-ee1f9a109b20 | note | INSPECTION/TEST METHOD: Site Inspection
4ff2ad67-4b6d-511f-bea8-263078d613fe | note | RECORD OF CONFORMITY: Signed ITP
3cec2528-f398-5799-a29b-602a52331759 | note | IP
155eb0b3-86fc-5904-b728-8ced33a02e22 | note | RESPONSIBILITY: Site Engineer
86836085-2d28-5e85-9c7b-55a108cd0af8 | textbox | Date Completed:
9cfa010b-280d-437b-aa9c-bc0b74eee6e3 | checkpoint | 2.5 Proof Rolling
8306e697-451b-5589-a31e-54d75544c2e2 | note | FREQUENCY: Proof Roll each layer
e8ef6c37-7f82-5011-872e-114684aec992 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
91667630-3948-5a6b-81fc-b4757e87493d | note | REFERENCE DOCUMENTS: 173.03
3caa2056-bbac-5d2a-b647-affb5884f4fe | note | INSPECTION/TEST METHOD: Visual inspection
fb4c04c6-3975-55c0-be5a-e7a7897586da | note | RECORD OF CONFORMITY: This ITP signed off
c54e626f-0eb8-5759-bb85-a724b7093eb0 | note | HP / WP
232787df-6bbb-5c05-a0c3-5f38e36f1301 | note | RESPONSIBILITY: Site Engineer & Superintendent
5b059a23-fd42-5552-bec1-2383f08a2b24 | textbox | Date Completed:
1a41f75c-0ed0-41da-aca7-3ce390c098ff | signoff | AUTHORITY HOLDPOINT
1fc52a43-ba6d-4731-be70-cbb806afd389 | section | Testing Requirements
d0f06c61-4c6c-4c8b-970d-1efff44b59b8 | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
54ca3c35-91cd-5d79-886e-60f0360e549f | note | FREQUENCY: Prior to Testing
3c05b801-0948-57dc-9964-5ea0691571c2 | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
fe0c0349-a242-53de-a93f-9a0fa2f3b375 | note | • Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
5ed508b0-b1d6-51df-9a30-a26a1caf79b8 | note | REFERENCE DOCUMENTS: Table 204.161, Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i), Table 304.111
eb30f29a-7932-5391-81de-0fb1bbabfea5 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
00807fc5-112e-53c2-bdc0-68ac0c95464d | note | RECORD OF CONFORMITY: Signed ITP
662eed08-0e81-5271-8c51-96d6d55cdbd8 | note | AP
cc80c093-22ec-5ffb-8d6e-5ea72e2fe1fa | note | RESPONSIBILITY: Project Engineer
ca29376a-c524-5a9a-b18b-37e578c51c3f | textbox | Date Completed:
584fd0a5-4763-4146-b1d2-abe8ff957bfc | checkpoint | 3.2 Compaction Testing
e81e59ec-e2ef-5321-a99e-0b96f33fd360 | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
8de68878-9caa-5c46-9909-7732f44fb0d8 | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
6bb0e74f-0b0d-5398-b87f-f79583d0af81 | note | REFERENCE DOCUMENTS: Cl304.08, Table 3040.061, Cl 304.11 (b), Table 304.111
7297fcf9-48fa-5b11-a409-b2572ed513dc | note | INSPECTION/TEST METHOD: Test point
8cb87fac-ccac-5ad4-b228-2bbd52e8eb59 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
43a4665d-ceb6-5b66-b5cf-3a30af6dbe46 | note | TP
749085fd-8731-5f5f-94fd-8a16f9cd179f | note | RESPONSIBILITY: Site Engineer
164d3091-4bcd-56e7-8ad0-0114cc92ac6a | textbox | Date Completed:
e741b35b-6a1e-4540-962e-9d89f6547108 | checkpoint | 3.3 Material Grading - Post Compaction (Class 2 & 3 Only)
62c9f6f9-0353-5c0d-ab75-9bf8857706c0 | note | FREQUENCY: First Lot Only
7d400c87-02dc-56fb-82c7-f7a7ddcfe54e | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
1d94d4e2-de17-521b-8bf9-3f4006eb0e39 | note | • Class 4 - N/A
65a13f1b-f4a9-5f02-ba4c-99fbd09b61e1 | note | • Class 3 - As per Table 304.101 - VR Spec. 304.10
c89d89b3-7591-5028-90fd-21da115263f4 | note | • Class 2 - As per Table 304.101 - VR Spec. 304.10
de762fc4-a14c-564f-beaf-4a4c358bbb94 | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
dd0f0e23-972f-54e3-879d-8c3253e4f536 | note | INSPECTION/TEST METHOD: Test point
75c5fe0a-166b-5f7a-9955-66071efd740f | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
00ad1482-cd07-5c18-8c38-cc69ecd664d6 | note | TP
5a40993a-f462-5de8-86e4-60c55fb5014f | note | RESPONSIBILITY: Site Engineer
12c9285d-78fd-5d32-a534-da6039d54d48 | textbox | Date Completed:
e18aff9a-ada7-46e7-a6a5-4246d270d92a | checkpoint | 3.4 Plasticity Index - Post Compaction (Class 2 & 3 Only)
d55cca52-e8f5-55e2-a316-17025066cdef | note | FREQUENCY: First Lot Only
8652a1dc-3bf8-5405-a5f7-b6f5d7b0d7fb | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
e0f0146d-c9d2-51a9-bcd6-980bf65f78c8 | note | • Class 4 - N/A
b0900a4e-e728-57a7-a3d9-70bf63accf32 | note | • Class 3 - 0 to 10
19f48f4b-5162-5718-8efb-dee1edada1b8 | note | • Class 2 - 0 to 6
25e2b697-3221-5b89-abd3-7470ef05c818 | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11, Table 304.103
402dfd4e-c36d-5199-bd03-0374c183ea5e | note | INSPECTION/TEST METHOD: Test point
d0f0ac14-4b8f-5869-9840-4f8a31ee01d8 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
c9606e35-547c-5017-8f94-e75e8be356f0 | note | TP
b0560dad-bae3-525f-a67d-331576c07d98 | note | RESPONSIBILITY: Site Engineer
9c215f3a-bc53-5a1e-8908-58742f4aaf30 | textbox | Date Completed:
c216e9d6-3fcb-4e8f-b663-f4a1796c23f4 | checkpoint | 3.5 Survey Conformance
60641b33-4a98-5a37-a3cd-95922cc64dff | note | FREQUENCY: Each lot
71acc42c-c830-5b9f-8375-6f08199a51b5 | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
6d6f934c-5343-5f52-b135-4355eed8124a | note | • Shape: no point deviation > 8mm from 3m straight edge in any direction
9f90acc7-b216-59b8-82c0-733b36c6cc74 | note | • Surface level tolerances:
8b722da0-a9a0-5ea3-96f2-5718329d0919 | note | ○ Range x = +6, -16mm
1cfbceb1-771e-59cd-8c22-44e27222bf67 | note | ○ Max S = 15 mm
9973ca3b-e825-5ca6-ae09-c878b846caac | note | ○ 40 measurements per lot (Minimum)
88e3bc14-bab8-5917-8617-f10e58dfbbf6 | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i), Drawings, Table 304.062
b84ca01a-8799-57a9-bd48-60ae1af54eb3 | note | INSPECTION/TEST METHOD: Survey
9a4448f0-247a-554f-8499-4ca7ca8592ee | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
b6f73260-6bc4-536b-ad08-a4c7a671e61e | note | SCP
56e958bd-65a7-5901-9c82-276c564a1640 | note | RESPONSIBILITY: Site Engineer/ Surveyor
731bbeef-f107-5fa3-a31a-6f97ce535889 | textbox | Date Completed:
f6929f05-41d2-4702-8428-4230116f3d12 | checkpoint | Final Inspection
c54bc640-3d12-5968-bd6a-daccbb325d38 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
856fe35d-03cb-5159-b5fa-6e4d0806c3e5 | textbox | Print Name:
ff3ec278-19e0-556c-9506-4ae19c2a1105 | textbox | Position:
70db8702-5370-52db-a643-fe201d8660ef | textbox | Date:
b1ba180e-b45c-4e94-bd9a-a8c821bfddb8 | checklist | FHC-ITP-006 - Class 3 Crushed Rock Rev3 |  | FHC-ITP-006 - Class 3 Crushed Rock Rev3
c8a1c16b-747e-4a39-bd58-73d67cc72323 | section | Preliminary Works
bb9eb944-13cd-44e0-97c0-cd4932380987 | checkpoint | 1.1 Check for correct documentation
9991a54c-deed-514a-8cee-3a60faeb312a | note | FREQUENCY: Prior to commencing any activity
98bb3a68-366d-525b-bf67-f806aa74c1a2 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
e0292137-59b9-5856-b8b9-cb6839ef6a19 | note | – Using the correct and complete set of drawings
718edb93-1fea-540f-83e8-f8bcd5339a9f | note | – All drawings are the latest revision
4435cde1-a5a3-5ae1-817c-a82f89228d76 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
54d7152f-6eec-5751-b50d-173f51f8b6bf | note | INSPECTION/TEST METHOD: Visual inspection
ba640248-dcdd-5f14-a6ee-34e030ed369a | note | RECORD OF CONFORMITY: This ITP signed
aeb2dfc7-92a3-5656-8e64-8420f6afed69 | note | HP*
154fbeb3-1c0b-5992-ab43-d7455aa5c377 | note | RESPONSIBILITY: Site Engineer / Site Foreman
15ced100-6fa5-53aa-ab11-7ffaaabffe99 | textbox | Date Completed:
e319c20d-3f8f-4f2b-a7eb-720c6d4ad1c8 | checkpoint | 1.2 Material Mix Design
8cfcc76d-b7f1-54cd-88c5-9bfa3523b8ca | note | FREQUENCY: Prior to commencing any activity
e80e39bc-59c7-5125-984a-74937639b5ed | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
1a1cfb59-9c2e-55f0-9d83-a5393d06ce4c | note | REFERENCE DOCUMENTS: Cl 812.04, RC 500.02
e88fdcd0-6f70-53c7-a548-24b6a8cd0ecd | note | INSPECTION/TEST METHOD: Document Review
78c7a3b8-220d-5a75-aecc-86969659733f | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
f452c345-393c-5d92-8afc-e626250b994d | note | HP*
a47d92c7-f8f5-5326-b66f-dc33bd95f013 | note | RESPONSIBILITY: Site Engineer
2a65f7e3-6d74-5196-bdaf-7c8cb54abbe7 | textbox | Date Completed:
60241293-babd-4805-a223-6c57057e0818 | checkpoint | 1.3 Implementation of all measures and controls
ad88dc04-49c2-529d-9613-8e77fd9091d1 | note | FREQUENCY: Prior to commencing any activity
748e1d6b-44a5-5c44-a6e2-0dc31fd74717 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
465e47d8-2b15-52e3-81d2-cfa6c673a375 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
e363bd2d-2905-5d12-aa07-234aff8f6a3b | note | INSPECTION/TEST METHOD: Visual Inspection
6f4941ee-875e-58ee-9bdf-8a796808d8a0 | note | RECORD OF CONFORMITY: This ITP signed
c5fcbfbc-ee3b-5f78-9e5b-6a6a6a272489 | note | HP*
86e7df92-60ab-590a-8d38-617519b99181 | note | RESPONSIBILITY: Site Engineer / Site Foreman
17bc16ff-3067-5bcf-a06f-0c8babff10fb | textbox | Date Completed:
0fbc2bd0-7c80-4e1e-8c88-50d69d150a93 | section | Construction Works
db493eb9-5f08-4d4f-9f13-7cb3bee0f29f | checkpoint | 2.1 Transverse Joints
e5ecaca6-d5e3-5b27-b718-f26fd5a8c32d | note | FREQUENCY: Check prior to placing material
8b545ab2-ce08-55d0-a861-8d93d22a1a86 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
d61d6c54-3d1a-5414-8d5a-e0d83d506866 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
4cc203aa-703a-5c45-96bf-e7a114d0e843 | note | INSPECTION/TEST METHOD: Visual Inspection
cdbc115d-7852-55d2-b5b6-3b86052628a4 | note | RECORD OF CONFORMITY: This ITP signed off
91ad8f10-60b9-5ee8-b857-b4cdb11f8d15 | note | IP
c8d78908-2e24-5ac9-80a5-9275947e2ca5 | note | RESPONSIBILITY: Site Engineer
de4d0df8-a8c6-555a-afea-69506355f4ad | textbox | Date Completed:
73927f2e-737b-4b1e-aca6-a812fd8f2822 | checkpoint | 2.2 Longitudinal Joints
d67f185e-6064-52ed-a575-d0c0dada077c | note | FREQUENCY: Check prior to placing material
18a7c64f-2c3e-5175-a71d-82ac6ffca048 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
03cae0b4-0f31-51f7-9f98-6ca321d6016c | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
ba0a3fe9-d148-57fc-bab6-adcab595fe06 | note | INSPECTION/TEST METHOD: Visual Inspection
9a050511-ea56-5bcb-9969-215fccd5370d | note | RECORD OF CONFORMITY: This ITP signed off
34b5af27-dcb1-5792-9844-287176182b29 | note | IP
00114b2e-0208-5a97-877e-5f2b34f77b8f | note | RESPONSIBILITY: Site Engineer
97a827e9-c900-56ac-91b1-94bc447c0834 | textbox | Date Completed:
4abd413b-b97f-4bec-bbb5-97862482d2cf | checkpoint | 2.3 Lot Size
dd2376a7-fa16-5379-8c68-674067a8d35c | note | FREQUENCY: Check prior to placing material
516357e6-7977-543c-b122-cee24ca444cb | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
8f3f73f4-8e6a-5b8f-900b-f3add3b624bd | note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
e0793e77-6a55-54e6-b5cf-79fe812fe8ce | note | INSPECTION/TEST METHOD: Site Inspection
0157c6f5-10be-5ac3-88e3-e4cf1402dd69 | note | RECORD OF CONFORMITY: Signed ITP
9e5033d6-bc47-5d5f-a4f0-9cf47da1ab35 | note | IP
c6e6712c-8a06-58e3-9b87-bbe459380c68 | note | RESPONSIBILITY: Site Engineer
32dfe2ad-75ba-558e-ac69-bf841035c379 | textbox | Date Completed:
fbb83ab5-6ad1-4055-a7d9-ace8a9bb78a4 | checkpoint | 2.4 Layer Thickness
161439fe-2890-5b31-bb53-53636e2a9665 | note | FREQUENCY: Each Lot
6dbb6a62-c53c-50f6-bcaf-18157c42eeab | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
e44ff787-86fe-5ebc-9547-e83956d8a9ed | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
3e85604c-cf75-5557-aa72-90541585584f | note | INSPECTION/TEST METHOD: Site Inspection
ccf5b83d-449d-5eb0-a1ab-6209f925fd1c | note | RECORD OF CONFORMITY: Signed ITP
81be1d19-d8a1-5d69-8cc5-32132d2745c1 | note | IP
54f50ef2-2cd2-516c-8381-ced011de9e08 | note | RESPONSIBILITY: Site Engineer
4f170e82-b176-5b63-bcf2-ef3bb2492633 | textbox | Date Completed:
b47c52a7-faa0-4eb8-823b-bc3b5b41970b | checkpoint | 2.5 Proof Rolling
3f5a049b-108e-5237-8207-97ceea21301c | note | FREQUENCY: Proof Roll each layer
8ca57f7c-3ba4-5258-b5e5-c0ee921b8a6b | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
b24559a5-ab0a-5fb7-bcc5-7e7543c40184 | note | REFERENCE DOCUMENTS: 173.03
43db1b14-5f20-58e3-9d5a-9e0f62be64f5 | note | INSPECTION/TEST METHOD: Visual inspection
51b42ec7-9be0-54e5-90c8-da35c486ab56 | note | RECORD OF CONFORMITY: This ITP signed off
2b6f6405-2221-51df-8645-3791bfab5b9e | note | HP / WP
87edd149-584d-5c7b-ae4f-53eec9b6e98f | note | RESPONSIBILITY: Site Engineer & Superintendent
0caa97dd-742c-5196-bfb3-566adafd75cd | textbox | Date Completed:
a61cbfcd-35cb-4ab5-a0c6-f59513ecd036 | signoff | AUTHORITY HOLDPOINT
99e5da0a-d996-4d5f-b4d7-39f3bf2768a9 | section | Testing Requirements
0e48ec0a-6443-4212-8a94-771c350f91dd | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
c082edeb-3776-5038-8b90-109610e2ad6f | note | FREQUENCY: Prior to Testing
ee2a9a7d-b722-5459-9b0f-1892163167d8 | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
73eb2dee-0732-59b1-8a8f-ec39227e14a6 | note | • Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
962f4e44-acdd-5ca8-ae10-554a50e218eb | note | REFERENCE DOCUMENTS: Table 204.161, Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i), Table 304.111
bae3ab15-f742-5fae-a014-2d3da9466fe2 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
831d01a3-75e7-54b7-8c9f-7ab1a8b9e22f | note | RECORD OF CONFORMITY: Signed ITP
529b5475-a6c0-5507-aec7-0360b9112350 | note | AP
f8b53731-f002-5ab3-acde-697d63f6707f | note | RESPONSIBILITY: Project Engineer
e09ce982-5988-58f8-9075-95202bb561c6 | textbox | Date Completed:
b1f9bbdd-2c0e-4272-9c9f-bd1a98113bbe | checkpoint | 3.2 Compaction Testing
177d458e-0d13-50af-982b-95d5de05453e | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
0e09e207-1950-5368-b79f-c0edfcbb9262 | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
6e60f8fe-a617-55d0-804b-580224647d2a | note | REFERENCE DOCUMENTS: Cl304.08, Table 3040.061, Cl 304.11 (b), Table 304.111
0d85596d-640e-5bf1-8326-1a907064dd2d | note | INSPECTION/TEST METHOD: Test point
f1c49e9c-9dac-57a0-9062-1b88b0b7c896 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
ffd0b522-2784-5e8f-8dd1-031499c2e8e6 | note | TP
3a933e77-1d86-5544-b392-c5f19cfc003b | note | RESPONSIBILITY: Site Engineer
6bf2c21d-544b-5c7e-841e-f58fd84a7dfe | textbox | Date Completed:
5ded9472-9ad8-42f8-bdfc-3dad4014925f | checkpoint | 3.3 Material Grading - Post Compaction (Class 2 & 3 Only)
54a50481-0d3f-50a2-b061-68847f5ab204 | note | FREQUENCY: First Lot Only
62790a95-51c5-55ab-9ff4-7d76650a0689 | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
78925405-fc26-515a-a700-e1309c00a246 | note | • Class 4 - N/A
0bd02ffe-666c-508d-a287-80a487bd4cf3 | note | • Class 3 - As per Table 304.101 - VR Spec. 304.10
0ee1f99e-9b6f-54d7-b882-e203d1e2fd84 | note | • Class 2 - As per Table 304.101 - VR Spec. 304.10
e7dd17b5-784f-5784-836d-459cec84e2df | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
eb67a340-9198-5f8b-9b7b-a792bbd37955 | note | INSPECTION/TEST METHOD: Test point
5fe40600-e2c0-50a7-ab10-642093bf3ae0 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
da971adb-0dbe-5fc4-881f-2a55b2012664 | note | TP
517f49bc-f83c-5638-953b-d3e6b2c92980 | note | RESPONSIBILITY: Site Engineer
8000463f-452a-5e0f-a5d8-a20c2557319e | textbox | Date Completed:
8ea8201e-170b-4d8a-a917-290c692603be | checkpoint | 3.4 Plasticity Index - Post Compaction (Class 2 & 3 Only)
dc674c11-75d8-52d9-bb15-bf93dfc7f6fc | note | FREQUENCY: First Lot Only
f33bd554-4368-55b6-9091-56acfcafb44e | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
a222150b-effa-5b74-8558-f9cb32478b4a | note | • Class 4 - N/A
6c1dbef3-ce42-5836-b8b8-c45819546b24 | note | • Class 3 - 0 to 10
cefdcc3b-77bc-57e5-bd50-026f1bcef6fd | note | • Class 2 - 0 to 6
8e8fd354-4b31-5363-bae2-718c9d36b800 | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11, Table 304.103
0b88ac18-4356-556a-90fe-e9a2f5bf99b1 | note | INSPECTION/TEST METHOD: Test point
0f8bfbbe-cef2-5cff-b998-ae1f4fc1c5de | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
73d2fdb5-c0a6-5562-a21a-e090665f6baf | note | TP
d6575c48-76af-5969-8106-79ee23c05b6c | note | RESPONSIBILITY: Site Engineer
702c125c-a00b-55c5-9f3a-2a6921374351 | textbox | Date Completed:
c6b720d8-073b-4c89-8e5d-a2b093502817 | checkpoint | 3.5 Survey Conformance
dc0ae1df-d268-583c-b6ce-8776c78bad79 | note | FREQUENCY: Each lot
07578e8f-a708-5b35-8ba9-9fa5e9d8c568 | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
366c2275-1ec2-5fa4-8da0-2940a5548f17 | note | • Shape: no point deviation > 8mm from 3m straight edge in any direction
d2d170cd-5a83-5d87-92db-292563eb5b2b | note | • Surface level tolerances:
a24b4fd2-8bda-5ef1-9e27-de3fff7cda19 | note | ○ Range x = +6, -16mm
456a6065-7771-5c44-a8c6-483e06c60709 | note | ○ Max S = 15 mm
60518b55-f911-59db-a2a6-3631abf6e600 | note | ○ 40 measurements per lot (Minimum)
5f11bbb7-a40d-5102-a64b-5a5a29be165e | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i), Drawings, Table 304.062
d951f572-eb03-5a81-8f2e-05374c65106f | note | INSPECTION/TEST METHOD: Survey
b80a8897-ae2b-5d1f-98f3-a94ce299f292 | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
e7872885-187f-5ce9-bf07-a23ee7d18094 | note | SCP
4ac76999-68d5-50c6-98fa-874ab40b05a6 | note | RESPONSIBILITY: Site Engineer/ Surveyor
9706f850-af08-5fa5-9aed-a39bb81fd49b | textbox | Date Completed:
c860c509-3784-477e-8688-e5511abd14f1 | checkpoint | Final Inspection
192a4386-9a8f-5853-9d89-78c10dc7b42b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
73b7772d-8f43-5bbb-84d3-e277adbea161 | textbox | Print Name:
652c1da6-3e33-5fb8-909e-66ea1a7db2e8 | textbox | Position:
9469fe4b-9c09-5c25-a69c-bcc1432b7f6c | textbox | Date:
71891498-700b-44c8-9e80-fc804ebb27ea | checklist | FHC-ITP-007 - General Demolition Rev1 | itp | FHC-ITP-007 - General Demolition Rev1
5b91ba68-31e6-4772-81ad-fe6a03cbd647 | section | 1 - Preliminary Works
83490f50-307d-4a3c-a6e0-0798f4653df2 | checkpoint | 1.1 Check for correct documentation
c9ce3e70-8f26-515b-8b25-1daf121a0f9d | note | FREQUENCY: Prior to commencing any activity
7976bdf6-b756-5415-bf44-005c3312a466 | note | – – – – – – – – –
79f86748-a569-522f-8d46-8d515e883feb | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a76580ad-fd6e-5ab8-917e-8fee0be63185 | note | – using the correct and complete set of drawings
50ae3927-bb80-5ae9-a9ea-8e7db520ce54 | note | – all drawings are the latest revision
22febe2d-cc49-5a3a-b517-513d83da7305 | note | – – – – – – – – –
35523087-0721-5ff2-be5f-041559983e90 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
de567890-d3c0-573a-aecb-1505377e7936 | note | – – – – – – – – –
469866e7-9c84-5e11-92df-ba737ed137f3 | note | INSPECTION/TEST METHOD: Visual inspection
41b58669-fc47-5384-bb71-48b87ffffaca | note | – – – – – – – – –
021d518e-d4c7-512d-b04a-bcd6cac4ca10 | note | RECORD OF CONFORMITY: This ITP signed
7b429a75-0e11-5d42-a3fb-5ebe09bbc142 | note | – – – – – – – – –
db19d176-5c31-5283-8a89-2d7d5a2285ea | note | HP*
05898deb-6b61-5a3e-a5cf-73adad5ab580 | note | – – – – – – – – –
e458f9f1-206a-5d87-a592-747cf005a754 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
433a84c6-2b84-5bdd-82f1-683e62c5e999 | note | – – – – – – – – –
aaedb184-9c39-579b-b4eb-7ab59f7c0b6b | textbox | DATE:
dbb5da56-5416-4ecc-9fe0-2ef8030d82c9 | checkpoint | 1.2 Implementation of all measures and controls
4dcf36b3-21a7-5ad0-adca-2daa09ebe101 | note | FREQUENCY: Prior to commencing any activity
68e327c5-8adb-5914-b3da-b526df21cb6b | note | – – – – – – – – –
39a5b319-c15a-52fa-bb00-125db09a7b7a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
cd8539ef-a4e1-5538-b435-ea3d5e95f719 | note | – – – – – – – – –
bdddcfee-300f-5731-9506-6411b9eac732 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
fa04ab5a-fcfc-5f3b-8fe4-34dbf2b79a64 | note | – – – – – – – – –
5a33612b-996f-5a28-b670-e7f44bf71fc8 | note | INSPECTION/TEST METHOD: Visual Inspection
b50ea67c-ae10-5da1-bc7c-4eb4cfd6d17d | note | – – – – – – – – –
a08a5f92-e652-5a8a-aac2-4a656bbe3e27 | note | RECORD OF CONFORMITY: This ITP signed
e4c12f76-7eea-5725-b9d6-f2900bf23e01 | note | – – – – – – – – –
c13daa2b-e860-5fdf-9120-9ce35b939fcc | note | HP*
84786945-f4e1-5fef-91b4-883cef455e07 | note | – – – – – – – – –
6c1bb840-a4e7-53a7-a4dd-82f9db87523d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
aadafdf5-2d0b-58c3-9919-111c7943be67 | note | – – – – – – – – –
57cce0ed-cada-56e3-9271-b715077c4a8d | textbox | DATE:
d9e494a5-cf72-41f3-a61c-752e8565d2c9 | checkpoint | 1.3 Service Identification
2a7c19af-b17b-51c0-9d5c-d3a872689d5f | note | FREQUENCY: Prior to start
d8a99f2a-d120-5b62-a078-8882ef5beac9 | note | – – – – – – – – –
30eb5489-d711-56ac-91e1-c5b1d970cbee | note | ACCEPTANCE CRITERIA: Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected
145a375e-a3c3-562a-b9fd-d4316f0c8b41 | note | – – – – – – – – –
7d9c8c89-4e45-530e-8a15-feab1b0cccbd | note | REFERENCE DOCUMENTS: ITP sign off
5941f3bb-886c-598c-b796-f83a7481991b | note | – – – – – – – – –
9c25ddcb-ca00-51a1-8963-799b5a458bc2 | note | INSPECTION/TEST METHOD: Verify
0a0bf5b3-5019-5b21-9aea-bbbf1c81badd | note | – – – – – – – – –
abefba64-a1cc-561d-8c2b-65b3913724af | note | RECORD OF CONFORMITY: This ITP signed
a5298a77-9b23-564d-9c32-dc4ddcec0608 | note | – – – – – – – – –
ccbc5818-dc9f-5f9e-8c9f-609dd995a142 | note | HP*
98a8b0b7-a4cc-5460-9794-d398806e12f3 | note | – – – – – – – – –
759c81a4-f993-5ea6-a689-477e9ac32a31 | note | RESPONSIBILITY: Site Engineer
541b4b20-0e72-59ba-8bce-094dd6c15bb7 | note | – – – – – – – – –
fb460602-eeec-545d-a7ef-2753dbd92189 | textbox | DATE:
1e495180-042b-4f06-856f-0fad42fb6473 | section | 2 - Construction Works
8a2640f6-3581-4069-910a-950a47489cbb | checkpoint | 2.1 Saw cutting
8875c8c9-25a6-5bb5-b768-596ceec1fbef | note | FREQUENCY: Where required
0bf43e7d-835f-550d-b590-1126b5818e08 | note | – – – – – – – – –
8cd5916c-9db5-513e-8507-ce3a6e0a93b3 | note | ACCEPTANCE CRITERIA: Extent and location of cuts to be clearly set out and checked prior to saw cutting
1bc82503-d118-5324-a7b3-a281827c59e1 | note | – – – – – – – – –
2c9e404e-3912-557e-a20c-ff8727c2d370 | note | REFERENCE DOCUMENTS: ITP sign off
99c7f48b-64e5-5a16-9f64-916427fa3d93 | note | – – – – – – – – –
a45e601e-c24c-5891-a29a-8cdc0c532f91 | note | INSPECTION/TEST METHOD: Visual Inspection
9e3b499a-299b-5e61-9ee8-3f27b2af1212 | note | – – – – – – – – –
c147e0c0-0945-5fa7-85cf-f765ca1fbe8c | note | RECORD OF CONFORMITY: This ITP signed
8fbc40f4-2b7c-5245-86ed-d3427050424e | note | – – – – – – – – –
40b79466-3cc2-5fa8-be80-7f3a94d13641 | note | WP
d88cd694-6857-5a37-b61d-c87b3ad0b1a7 | note | – – – – – – – – –
5e67822c-0871-5bf6-808b-83012949e93d | note | RESPONSIBILITY: Site Engineer
d7fb6fed-aefa-541a-a80e-1be4258c7260 | note | – – – – – – – – –
43639c90-3385-50b5-b8ec-c8b8e36849f3 | textbox | DATE:
9ef26426-31da-4c87-b10d-c5ce90cf2f47 | checkpoint | 2.2 Excavation Permit
f5fa5ad4-cd1d-51bf-b3f8-0ab08e38ead0 | note | FREQUENCY: During excavation
e424adb8-f22d-5a80-87ff-451a4574f857 | note | – – – – – – – – –
df4fd310-25b9-5a4a-bd1e-3bb8f25a175e | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
d417786c-6e65-5b0e-936b-37ff0a281c20 | note | • Plant and equipment shall be appropriate for the task
a0b2f6de-43fe-57ce-9908-d7c675f87488 | note | • Excavation operations shall not disturb areas outside the limit of excavation
a390af78-1873-5bb1-a2f1-15b66ed9beb5 | note | – – – – – – – – –
2f8ed750-12b7-5005-8cf3-20ef31e311e3 | note | REFERENCE DOCUMENTS: VicRoads 204.06
ce21c953-65e7-5090-9700-79a38bbf9c3d | note | – – – – – – – – –
d8f0030a-6545-56fe-ab5f-12702e20646b | note | INSPECTION/TEST METHOD: Visual Inspection
67233e93-97de-5ef4-bd55-aaa0c579a1c5 | note | – – – – – – – – –
41b3fafa-6cc5-53fc-a5d0-0a4b5dd257f0 | note | RECORD OF CONFORMITY: This ITP signed
325621b2-4cff-538c-95de-aac7557ef7f7 | note | – – – – – – – – –
d8e627bb-ff17-55a9-a5a5-e9f691e26fb8 | note | HP*
1374ef3a-8dc7-5283-8df7-94d4de1926c9 | note | – – – – – – – – –
7e719943-d3e6-5f68-b9ee-325987014264 | note | RESPONSIBILITY: Site Engineer
fe1bd7af-784b-5141-a7c4-e8c9df020a3a | note | – – – – – – – – –
934b40dd-ab6e-5495-836c-fe2f83ab849e | textbox | DATE:
bbafad6b-2bb5-49a5-9ac1-1f43ed5399be | checkpoint | 2.3 Redundant Pits
9e6ea32e-1af1-537c-9f95-59186acce8ed | note | FREQUENCY: After clearing
fd7ef72c-4a77-5855-9826-4843d9e8a428 | note | – – – – – – – – –
5589a511-1edd-5f38-b100-7e4b7be925bf | note | ACCEPTANCE CRITERIA: Any redundant pits, are to be removed to a depth no less than 0.3m below the stripped surface or no less than 0.6m below finished subgrade (wichever is lesser)
a792ea22-b50a-5750-8342-2af75682ff44 | note | • Seal any pipe openings with concrete and backfill pit area with material and compact to a density ratio of 95% (standard compactive effort)
eafd784b-ab16-576f-aeb6-1d5a0976135f | note | – – – – – – – – –
abb8d4f1-e67c-5a2e-9247-a9cf7bbbc3e4 | note | REFERENCE DOCUMENTS: 201.05
69d01587-b169-5ab1-b375-688f074e41d6 | note | – – – – – – – – –
67f2c35a-e828-502f-a684-27572a1ba7dd | note | INSPECTION/TEST METHOD: Visual Inspection
41f758f0-944d-5ff3-8e36-95a89e87e51e | note | – – – – – – – – –
2bbb40b7-fc96-5fcf-836e-90216bd315de | note | RECORD OF CONFORMITY: This ITP Signed off
861da8fa-d370-5133-91ea-56632ffd9ad7 | note | – – – – – – – – –
7eaae485-a7da-5fd9-bce0-d27fc0a9cae2 | note | IP
31a6f240-9994-5666-8dfe-2135d4fb2782 | note | – – – – – – – – –
7074203b-6dcc-51ac-a21c-33eafa87b686 | note | RESPONSIBILITY: Site Engineer
fa2bc423-dd9c-50ca-b908-116f65cccbca | note | – – – – – – – – –
8b24c71b-dc1a-586e-af09-9424c7c1b9f8 | textbox | DATE:
dc9de289-e52c-42ef-b08e-866dd590d19f | checkpoint | 2.4 Disposal of Material
d8a4f53e-f272-5fec-a5ef-798a1df647b3 | note | FREQUENCY: All times
efb7a9e8-76b7-5af5-9d16-901b354ad2fb | note | – – – – – – – – –
fa9e50ac-f7e9-53ee-bfc4-693bce965d89 | note | ACCEPTANCE CRITERIA: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
265233e5-dfa1-5b93-9847-404f12ebc921 | note | – – – – – – – – –
a500caf5-b844-5113-86ea-571ea92e15e0 | note | REFERENCE DOCUMENTS: ITP sign off
9fe334bb-3b08-5bf5-bf0d-2933a316fd7c | note | – – – – – – – – –
fd9c60ff-a75a-5252-849d-45f768667dc6 | note | INSPECTION/TEST METHOD: Visual Inspection
63c5683d-0d7b-5fb7-907a-500aec842481 | note | – – – – – – – – –
77da3162-ee2f-57a3-b925-1117f38a6591 | note | RECORD OF CONFORMITY: This ITP signed
e743e37e-c257-5836-86d5-a88c28daa94f | note | – – – – – – – – –
4843c059-17c6-59d1-a4d9-dc1f4fc0e074 | note | WP
ed8da309-a806-5e93-b183-2ceccd79dc5f | note | – – – – – – – – –
3d659aa2-d8a5-55fa-b656-0e12fb97010c | note | RESPONSIBILITY: Site Engineer/ Site Foreman
c892ef8b-ee34-5a66-bfca-9849e21aec94 | note | – – – – – – – – –
9e940d38-35d2-5a4f-a36b-bd72d249a124 | textbox | DATE:
923b1c23-a405-42c5-9a9d-1699c6ea48b1 | checkpoint | 2.5 Maintaining cleanliness of site
96680073-4b3f-5010-8759-5a133c2f5019 | note | FREQUENCY: All times
0e066a72-ad5b-57e9-ad92-132e7f26aa0f | note | – – – – – – – – –
4ce6662d-a409-5f1c-80d5-eb55846e7efd | note | ACCEPTANCE CRITERIA: Site and surrounding environment are to be maintained at a good standard of cleanliness
3a014d7d-41ab-5e68-bc17-e200decd4a29 | note | – – – – – – – – –
f63f1948-829d-571c-98f6-8a8cdf66979a | note | REFERENCE DOCUMENTS: ITP sign off
e666c498-4ed0-5c71-8c66-3ebf44e5d2bc | note | – – – – – – – – –
1a0e71bc-ad01-56ca-8c28-fd5cfeadc5a7 | note | INSPECTION/TEST METHOD: Visual Inspection
2fe3dde2-49f8-5c31-982c-06e6273b2fa1 | note | – – – – – – – – –
2af41817-7881-5716-89d2-2930b0708a82 | note | RECORD OF CONFORMITY: This ITP signed
74194d93-d13c-578c-8855-98bee1b99c93 | note | – – – – – – – – –
bd62e53d-7b2e-5463-bd69-97c406f9277e | note | WP
cb4694d8-7ae5-53fd-9fb3-1fbc0efcef87 | note | – – – – – – – – –
2861760b-4f9e-5636-a501-2b7228bc4833 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
df1af8ea-26c1-59d9-b5d8-06a0a7c9a215 | note | – – – – – – – – –
98f50ae4-86ff-54a2-9dd2-7e6b2c98dd05 | textbox | DATE:
5e785127-97f5-4226-ad51-c732ea755187 | checkpoint | Final Inspection
12e8889c-7149-5666-b770-719861a03b83 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
dcae6f2e-9d6e-55f3-a3c8-4f85b8cfcbe7 | textbox | Print Name:
2aa37969-116b-5414-bcb4-9188bcd02f0c | textbox | Position:
c06cabea-350a-5bcd-a5f3-ae2a188029ef | textbox | Date:
f787b70d-1386-4fdd-8f66-fb56b8514274 | checklist | FHC-ITP-008 - Stormwater Drainage Rev3 |  | FHC-ITP-008 - Stormwater Drainage Rev3
04a2312d-dd73-40bf-b7d7-405efcca0514 | section | Preliminary Works
a4410b06-f469-4a06-9beb-27e8708cf51e | checkpoint | 1.1 Check for correct documentation
5eb4c583-b31d-5983-ac13-9faefe73cdae | note | FREQUENCY: Prior to commencing any activity
42cd1717-afe3-532d-8788-03a9957ef9f9 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
09502a8a-7e94-5402-8015-b59debce51f4 | note | – using the correct and complete set of drawings
2eb6e71e-68b6-54e2-92f9-dd78d1df69ab | note | – all drawings are the latest revision
dcb77484-7543-5130-91ec-0c68b93060e1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
48b323e4-76da-5e85-a112-b4e34b4d03ad | note | INSPECTION/TEST METHOD: Visual inspection
9f28670f-29e2-5a4e-b877-e10fb4925662 | note | RECORD OF CONFORMITY: This ITP signed off
2f5e4ca6-044b-5b89-87ec-19dea39404be | note | HP*
daacfa98-589c-535a-8cc5-bd76ca759cd8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b07c4b38-6a41-5455-9e60-7d88223c6ffa | textbox | Date Completed:
fc0c2bf3-624d-4219-b01c-f5fd25ea40a7 | checkpoint | 1.2 Implementation of all measures and controls
bc54652b-a3fc-5c14-862e-38e51ae63906 | note | FREQUENCY: Prior to commencing any activity
97030944-fea1-5f68-b06c-afcb01847896 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
43ce85cf-6190-5f14-a316-38d3cbc650a9 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
efa5290a-8f77-5859-840e-ec80c2014733 | note | INSPECTION/TEST METHOD: Visual Inspection
66cdfe1e-a094-5d7a-b48c-e07863756d4d | note | RECORD OF CONFORMITY: This ITP signed off
59d3bbec-89ca-5911-a65f-745bfa2eba08 | note | HP*
99718f6a-908e-5467-9068-3afff42b03ae | note | RESPONSIBILITY: Site Engineer / Site Foreman
b393012b-2192-523f-9237-57de659443eb | textbox | Date Completed:
11e6e24c-6271-4582-bf92-1a01886240a9 | checkpoint | 1.3 Precast Materials acceptance
cf4fe55f-9f11-57f3-9c13-acccbb642af6 | note | FREQUENCY: Each Delivery
7a74f1b1-faed-5249-a8aa-2b0f5cca7061 | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
7e8e7a36-3085-5de6-b605-0f88a94fc014 | note | REFERENCE DOCUMENTS: Cl. 701.05e
0d8f1a0a-2a27-5f41-9c0f-54bf5524e4aa | note | INSPECTION/TEST METHOD: Visual Inspection
b8793bdb-283a-5491-bb2d-9be9c7198a85 | note | RECORD OF CONFORMITY: This ITP signed, Receival and Inspection Checklist
6d85a2d1-23c4-564e-bc21-329fa039755f | note | IP
dd59de0c-bd02-5382-b176-b396594178a4 | note | RESPONSIBILITY: Site Engineer
530c6ead-768c-58d1-acde-808469f851af | textbox | Date Completed:
9cab7a31-0e4d-4c66-a32c-dabff2cbdcdf | checkpoint | 1.4 Precast Pipe & Culvert Compliance
f7334127-bdf0-5f08-ae4f-61555a7ce878 | note | FREQUENCY: Prior to Commencing
12cbf435-3e4f-5341-8fe5-831326713943 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
ffad6b19-3838-50bf-a908-e182f4b658e1 | note | • Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058
febffec0-d7c9-549e-a332-815259203b00 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04, Cl. 701.05(a), AS4058, AS4680
c36fca58-d038-55a2-8a09-5e00000055b0 | note | INSPECTION/TEST METHOD: Document review & Site inspection
fb78bd2b-bf32-5976-b851-bc8fa3159fcf | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
89c9a82d-e553-5137-900f-41776ddf9832 | note | IP
dbdba86b-75e5-5528-a58f-b304c1e1cfd7 | note | RESPONSIBILITY: Site Engineer
1be99576-ab72-59ec-81d1-7e67f08010fb | textbox | Date Completed:
fb04954e-83ed-4ce3-a20a-f82a79c9f3ff | checkpoint | 1.5 Precast Drainage Pit Compliance
4a152cdb-a623-597d-bcde-161b89babad5 | note | FREQUENCY: Prior to Commencing
82c85c0c-64bf-59bc-9787-023798a5638c | note | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
3821aea5-09de-5b01-aa0e-a6c02ca916f3 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.610, Cl. 705.04, AS5100
9bc6a483-dbe5-5db2-8be9-7602b426006d | note | INSPECTION/TEST METHOD: Document Review
b1995905-80c1-5393-8f65-efd143db4216 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
baa5b769-1a85-5e51-9e50-54053f788d00 | note | IP
8e22bea1-666f-52c1-aab8-e5e1b646d77b | note | RESPONSIBILITY: Site Engineer
6351c990-b4f6-515e-a4cd-649a137cb958 | textbox | Date Completed:
58a0188c-0a30-4272-8a28-f46fd52a6bc8 | checkpoint | 1.6 Bedding material classification
3235a54a-da15-5bf8-998b-44664bbd7343 | note | FREQUENCY: Prior to start
e5d98ac7-dc10-5088-997a-7c23e93bce60 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
cb4aa42d-2974-5212-a282-168f0610e859 | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
1fb34494-3450-533c-ae67-de86818739b0 | note | INSPECTION/TEST METHOD: Verify
7a387982-34ff-5712-a16e-8033abb18956 | note | RECORD OF CONFORMITY: Test Reports from supplier
321130a0-a09e-558c-aa3d-dd07c4dbea27 | note | TP
8cc57a74-7cf7-57f5-8bf1-e782dc262d29 | note | RESPONSIBILITY: Site Engineer
566c9a45-2648-589a-be74-3fa3a3c87dfc | textbox | Date Completed:
741a2f2b-f6b1-47e3-bf83-58d14a7e7641 | checkpoint | 1.7 Backfill material Classification
818a0c24-823d-5f45-ad41-169096a3bf20 | note | FREQUENCY: Prior to start
52f16f54-1b55-5ac6-8d9d-2f79f77d23b4 | note | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
81980716-df2f-5e7f-b4b8-0917dfb0ef78 | note | REFERENCE DOCUMENTS: 701.09(d), 701.091
0ac2cf6f-e666-5a48-abb8-84b670894618 | note | INSPECTION/TEST METHOD: Verify
52ccf04e-7677-5c9a-ad69-380e696d1793 | note | RECORD OF CONFORMITY: Test Reports from supplier
e1288b6c-90fa-5e15-ab82-658595e5d087 | note | TP
dcd1bb54-c270-5f28-81c5-35ae53caeb83 | note | RESPONSIBILITY: Site Engineer
8fb5a540-1d7d-538a-a914-ac527d2859e2 | textbox | Date Completed:
fc8a883a-37c7-4a4c-9e51-fb57f867d6c8 | checkpoint | 1.8 Mortar material classification
dc3b25fd-9e21-5382-9491-345e897e0902 | note | FREQUENCY: Prior to start
724ba2e0-f689-5979-923f-f21fa52097a1 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
5c7af6e5-b054-5b73-9e4e-3d779486d2e3 | note | REFERENCE DOCUMENTS: 610.33
16d38bc2-23cb-57e2-8cd2-72b1b10d42e2 | note | INSPECTION/TEST METHOD: Verify
a39d1a74-8daf-559a-8db0-5793349695d4 | note | RECORD OF CONFORMITY: Test Reports from supplier
787e44bc-1a68-560b-9cca-3949f1bef665 | note | TP
8b33c708-6a81-58c8-ac98-92fadbe8f822 | note | RESPONSIBILITY: Site Engineer
66677dfb-5945-54bb-bd9b-5388fe41d9cb | textbox | Date Completed:
eaf50f3a-ddd8-4480-ac78-c07350cc4d21 | section | Construction Works
09c21f03-42c6-483f-9f9c-577a260d4263 | checkpoint | 2.1 Excavation Permit
95ca60e5-3b27-56b8-87d1-2bcdff8a94f9 | note | FREQUENCY: Each lot
c7750df3-99e4-50ad-9802-b6b725d77f93 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
b0493b22-e889-5cca-8a83-2a384055a6c3 | note | • Plant and equipment shall be appropriate for the task.
0af1879a-3a7a-5f4c-b43c-fac01a7ef810 | note | • Excavation operations shall not disturb areas outside the limit of excavation
cadd43e2-8e7e-555b-94c4-dfd9c7c9a486 | note | REFERENCE DOCUMENTS: Excavation permit
81ecba19-2fe8-5b52-90f8-d3695e78e6d4 | note | INSPECTION/TEST METHOD: Verify
ed893d80-bfc1-537f-9243-2e5c747b3ba5 | note | RECORD OF CONFORMITY: ITP Signed
a64dd245-c77f-51b5-859e-3a81e9a9e15c | note | HP*
d4b16738-c73f-5a6a-9427-a1cbe320c72f | note | RESPONSIBILITY: Site Engineer
5f481b35-3819-5219-a4e7-e9a3a7425215 | textbox | Date Completed:
46058e83-07d2-4816-b40c-440aec57c2ec | checkpoint | 2.2 Set out drainage
9aa17ce2-f4a4-588f-a780-ed1be471b412 | note | FREQUENCY: Prior to backfilling
945becec-c9e0-5b64-903f-a40c2c754a59 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
a62c2b51-c22e-5dff-8a9e-720b0dc187a8 | note | REFERENCE DOCUMENTS: Drawings 701.10
308b80d6-fc4a-5a1d-86ac-d75924dd9e4e | note | INSPECTION/TEST METHOD: Visual Inspection
e9011ddb-a42c-589b-a165-57aa2bcdf854 | note | RECORD OF CONFORMITY: ITP Signed
4b819305-8698-59fb-adcf-d2adbc5ed9b9 | note | HP
7e15acac-9a1d-51ef-b73a-ae69d4aad210 | note | RESPONSIBILITY: Site Engineer/ Superintendent
f8d37800-c4ed-5777-8581-bc405cacdc69 | textbox | Date Completed:
f33cb5ab-cfc6-41a5-9432-fc5581ce75c0 | signoff | AUTHORITY HOLDPOINT
3f18bde0-7190-43eb-90fe-da377dd9eb08 | checkpoint | 2.3 Excacation (pipes)
89a422d9-3d09-5357-b8b9-473a783b2c9f | note | FREQUENCY: Each Trench
3b337efb-06da-5fe2-b225-9afe5c63df49 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
15413baf-829d-5add-afa2-0ef2e6a7c49b | note | • Depth of trench:
477700d2-e071-5749-b78d-17d51510d13f | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
1c640dc6-6a3f-5612-bdff-ddda3c3b5605 | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
f2b2a37a-6264-5005-b934-4952f6d57a48 | note | REFERENCE DOCUMENTS: 701.151, 701.15
5d01b8be-2aee-54da-9f8f-9a4db880c2b6 | note | INSPECTION/TEST METHOD: Visual Inspection
7586a819-387b-51ea-bdab-4386e3eed0c2 | note | RECORD OF CONFORMITY: ITP Signed
016ae0b0-0f8b-52d4-8a83-9d01d77bcf10 | note | IP
e80b29b7-0d58-5072-8a4b-4ff09d3e157d | note | RESPONSIBILITY: Site Foreman
48044c1f-6001-577b-ad1b-8d3db6ea1cf5 | textbox | Date Completed:
c9b15504-c7ba-4e2b-914e-fec2b310c5e5 | checkpoint | 2.4 Excacation (pits)
f642478f-3680-5a60-800a-18e4de88b1de | note | FREQUENCY: Each Pit
591ef6cf-a95a-51ee-b5e6-9575fd64f586 | note | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
f4373594-0850-5b0a-a685-f6d8cb748e97 | note | REFERENCE DOCUMENTS: 705.05b
aa249563-fb90-5111-ae80-fc00ce50e64c | note | INSPECTION/TEST METHOD: Visual Inspection
0618627e-c6d8-5c63-a41b-fc53399db18f | note | RECORD OF CONFORMITY: ITP Signed
cb8fc5d3-42ed-5841-9cac-32c774f9d78a | note | IP
a3a0974f-2936-5cda-a7db-96c4d3529bf4 | note | RESPONSIBILITY: Site Foreman
d011361c-952f-5bc6-be63-6ffb1a8423ed | textbox | Date Completed:
d17feadc-9f4b-4629-8089-e71509577e62 | checkpoint | 2.5 Compact base of trench
8151a98c-35b7-5f67-82fb-c4642df66f61 | note | FREQUENCY: Each Trench
4094354c-1519-53a1-a49f-afaf2b935ae2 | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
78310fdf-45d9-5d89-8f46-5a9544e69895 | note | REFERENCE DOCUMENTS: 701.15
8efc59e1-64a8-57af-97f4-9284040f24e6 | note | INSPECTION/TEST METHOD: Visual Inspection
a9715a48-ccfe-5e8e-93ff-6d1937fa72af | note | RECORD OF CONFORMITY: ITP Signed
100252f0-d20c-514e-8109-385b1049d36c | note | IP
0ebb2610-6e97-5546-87d3-b5a109a487f9 | note | RESPONSIBILITY: Site Engineer
fb7969e3-610a-5492-8434-c69af239adef | textbox | Date Completed:
c81ead22-94dc-47ba-8c1a-78c8fff3a4fc | checkpoint | 2.6 Place bedding material & compact
9f5046f5-9b27-5555-a638-5fc56de0e137 | note | FREQUENCY: Each Trench
a159d968-6a1d-585b-8ee8-f95e0cb57524 | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment.
0e28d97c-7f2e-5e59-ba69-2c184e69e10f | note | • Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
33616c11-6dae-5375-bdbf-f3b65b9e2439 | note | REFERENCE DOCUMENTS: 701.20, 701.20a
b9c9f0e4-fc44-5920-a15f-ed27756a2def | note | INSPECTION/TEST METHOD: Visual Inspection
4f7948f0-f854-5466-ac22-6dda8fbe947f | note | RECORD OF CONFORMITY: ITP Signed
401ddd8e-632e-519f-8555-164939dfcfc4 | note | IP
76b0bbf3-ded3-5358-ba21-9f706fe0ba05 | note | RESPONSIBILITY: Site Engineer
63d1c30b-e421-5b35-9d94-a23f5184638f | textbox | Date Completed:
a5e9e37a-2386-4472-b926-85ddcec9b68c | checkpoint | 2.7 Place pipes & precast pits
8c313814-871c-5b9e-9dac-b37b1c503d93 | note | FREQUENCY: Each Line/Pit
20839e7a-1e10-5a74-ad34-2e0994d7b070 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
ea86b51a-a8f2-549e-a13b-0385f3fc9343 | note | REFERENCE DOCUMENTS: Drawings
fecac02d-eb44-51cd-b3ea-e8585f7d686e | note | INSPECTION/TEST METHOD: Visual Inspection
c6e4d57b-e62b-5d99-ac10-685972025dc3 | note | RECORD OF CONFORMITY: ITP Signed
d9dbe725-6c9d-5593-81e7-9b746233fd6c | note | IP
cfa2e809-f1d1-5bc3-ab1b-7cdb598f48c1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
2fc6c50c-a278-5414-9841-6fe7d2f5754c | textbox | Date Completed:
651866d6-a699-40e3-b8d7-d3031aa99471 | checkpoint | 2.8 Jointing pipe sections
94ab3bbf-2650-5feb-ae28-a10039183f40 | note | FREQUENCY: Each Line
3760fb33-2cd5-5fee-890b-b807adeeb1fa | note | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
65e4963f-407b-5d39-88fc-810dcaf0496e | note | REFERENCE DOCUMENTS: 701.18
4dae5a15-4ed6-5ef0-aa1f-d041a509a2de | note | INSPECTION/TEST METHOD: Visual Inspection
dc38b1af-324f-5d6a-b409-2c371a581a04 | note | RECORD OF CONFORMITY: ITP Signed
27bcdba3-4d76-578c-8551-5d21a6ec6a76 | note | IP
daac1327-6553-52da-ac17-1102510dc96b | note | RESPONSIBILITY: Site Engineer / Site Foreman
92c0373e-320e-50e1-8fa8-f39a11e305be | textbox | Date Completed:
28e07525-6c1b-42dc-95b7-cff76be72178 | checkpoint | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
da9c1b3f-7223-5f80-9d77-36ed24530688 | note | FREQUENCY: Each Pit
94501918-bc73-59b5-baf3-4d6350d97a66 | note | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared. The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
f406c17b-b851-582f-82d4-ceff6b15d68e | note | REFERENCE DOCUMENTS: 610.32, 701.17c
8631425d-a95e-53b7-8ecd-ae411a3361f3 | note | INSPECTION/TEST METHOD: Visual Inspection
90daf3e4-4111-58e2-a93c-c2aae8e9b5cc | note | RECORD OF CONFORMITY: ITP Signed
a10d69bc-f1e1-5f5d-a093-a6c614f865ee | note | WP
5876bbf7-db09-5356-8b60-3bfe703b4a54 | note | RESPONSIBILITY: Site Engineer / Site Foreman
5153866b-239a-52f7-b7a9-004bc3e53640 | textbox | Date Completed:
fab64bee-30d5-4d25-8628-83afee691503 | checkpoint | 2.10 Survey of laid pipe or pit
a317479b-f378-5287-b3d5-17697488f7c3 | note | FREQUENCY: Prior to backfilling
ed1534ad-a7dc-5c69-a05a-0bb71c182ede | note | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances:
45c48e7b-2bb3-5519-aba1-f7eb4315f786 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
7e3013ce-1f72-557e-aa3a-529616443038 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
6bdc3353-44e8-57dd-bd00-4699435bf251 | note | (c) invert level of pipes at pits ±50 mm
070840ea-b3ba-59f5-a7cd-ad2a8f4cb007 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
c1eb8830-d234-5da0-b98f-3bc6ac567a36 | note | REFERENCE DOCUMENTS: 701.1
4106799d-1b57-5bb5-be29-0b7d4dc40c82 | note | INSPECTION/TEST METHOD: Survey Conformance Point
d3bc80d4-5311-57b9-907a-47da12f4661c | note | RECORD OF CONFORMITY: ITP Signed
99d90d72-0797-5e3d-b2fa-b3c6ab8e9dbe | note | SCP
e38a9601-71c1-5525-9efe-4ee1eb03f04a | note | RESPONSIBILITY: Site Engineer/ Surveyor
dfae62ff-d052-5683-9866-1c753c52717d | textbox | Date Completed:
c117f4c6-7705-4320-a4bb-d617ce3d8db6 | checkpoint | 2.11 Haunching & compaction of bedding material
f661e792-4cb9-5e20-9a3a-ce8ddc24c04a | note | FREQUENCY: Each lot
5b383c44-9e12-5494-85b8-b2c8555f23ae | note | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
e2e88d82-4032-5da6-8a93-65e2b5e1563b | note | • Loose layer thickness <=150mm
5b84a3c2-d348-5e90-b8b0-db81a6b8cda0 | note | • Compacted to refusal using hand held mechanical equipment.
d54ec91d-b31f-51d6-91f3-f2bbac2d9d59 | note | • 1 lot = 150mm layer
2de4b631-64e3-510d-a98a-1312cc173714 | note | REFERENCE DOCUMENTS: 701.16, 701.20
51a433d9-cf8e-5010-bdc7-9b0d3d6b53f8 | note | INSPECTION/TEST METHOD: Visual Inspection
be0d9e38-f563-5aeb-8840-ed7fe1dfe744 | note | RECORD OF CONFORMITY: ITP Signed
a6e725ff-ace0-5c61-bbe7-023f3f03574d | note | WP
cba8f1ed-d6df-57c6-8457-34ea2e4c9d12 | note | RESPONSIBILITY: Site Engineer / Site Foreman
526c0eee-02ca-549c-aeec-eba15f684d8d | textbox | Date Completed:
546bb702-c6b5-463d-af6f-03009c1bf8c1 | checkpoint | 2.12 Place & compact backfill material over pipes
56a95a28-6957-5355-96b7-504dd0b0ab26 | note | FREQUENCY: Each lot
6243ac34-73e8-5c02-94ec-c9cd847c63c1 | note | ACCEPTANCE CRITERIA: Backfill under paved area:
2497ff26-7cc2-5b01-85aa-b777eb65f192 | note | ○ fill trench with selected back fill material to subgrade level
43377d14-84dd-5a8a-9356-ae1379410aef | note | • Backfill under area not paved:
26b93206-5914-59b0-b3d2-fcd5c7afd710 | note | ○ Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
a4c5bd51-af2b-5803-ac6c-79f0a3fa85bc | note | ○ Loose layer thickness <= 150mm.
8be1c1a0-1a63-5561-9be9-df382cf1efc1 | note | ○ 1 lot = 150mm layer
3111c8f8-d7f3-528a-9937-687bd055086b | note | REFERENCE DOCUMENTS: 701.19, 701.20
780e8e56-93d3-53e1-a048-dc748e8625b8 | note | INSPECTION/TEST METHOD: Visual Inspection
5484c29c-ab6f-558e-98f3-04ce835a6de8 | note | RECORD OF CONFORMITY: ITP Signed
27871f38-dcb3-5352-aaee-ca706de43b7a | note | IP
adad41a3-e1f5-523f-8a75-b17470dedf88 | note | RESPONSIBILITY: Site Engineer / Site Foreman
228e3aa1-e803-5b59-8920-bb5a41f95892 | textbox | Date Completed:
0fb942a4-b870-4270-a3ef-515a5d63699f | checkpoint | 2.13 Place & compact backfill material around pits
b04a9284-3416-5688-acda-aaccca993333 | note | FREQUENCY: Each Pit
a2d35655-103f-567f-ad70-f33715c8949b | note | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm. Compacted to refusal using hand held mechanical equipment.
c3898a0d-7456-5809-b9c1-c680294002c5 | note | REFERENCE DOCUMENTS: 705.18
cab3ff43-bd35-58b8-991d-ba0f1f76caa1 | note | INSPECTION/TEST METHOD: Visual Inspection
f0b23bf5-1e67-5237-9523-4a69d16dc396 | note | RECORD OF CONFORMITY: ITP Signed
28b3ffea-a3f0-59d2-9add-9982b61b2040 | note | IP
3a959403-5b86-5f93-9326-13778e8b024a | note | RESPONSIBILITY: Site Enginer
7d9a53c5-fca4-5e9e-9bb0-510d943f2067 | textbox | Date Completed:
a406dc9e-3dc9-4792-a487-dc477a23d099 | checkpoint | 2.14 Backfilling with cement stabilised sand
c646bb5c-0e94-5d80-99a9-d9bec88a1036 | note | FREQUENCY: Each culvert
01f360b6-b896-5f36-8c8d-e02e7eacf75c | note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
efbfc9f5-1e68-5b4f-a38c-3b645eaf8f94 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(a)
b6dd2d3e-91fb-57d4-ac86-fbbae9d64989 | note | INSPECTION/TEST METHOD: Site Inspection
9a08f694-b5b5-5066-b3d9-fdef9ae28a32 | note | RECORD OF CONFORMITY: Superintendent approval, ITP signed
3f1ab154-d202-5ad2-94c5-0d004b4a0db3 | note | AP
6d4b15c2-b6b6-5ef1-9c93-6c7be151f466 | note | RESPONSIBILITY: Project Engineer / Superintendent
f343ba8d-ed24-5462-8748-d2803f85a6b2 | textbox | Date Completed:
1eca386b-af5f-4f74-ab7d-f0c53e5e0cfa | checkpoint | 2.15 Install step irons
6d32320d-c505-5fa6-ae60-81825b9dfad1 | note | FREQUENCY: Each Pit
441ce306-16d5-59b1-a0ab-8ec28871f171 | note | ACCEPTANCE CRITERIA: For pits > 1m deep.
25a09a24-698e-5fef-a749-8c6527bfc8f4 | note | REFERENCE DOCUMENTS: 705.12
df034aad-dbc7-58c0-ad14-f48b50f41d52 | note | INSPECTION/TEST METHOD: Visual Inspection
5dbbc80f-34c1-5409-b2d2-b1a5d1d45191 | note | RECORD OF CONFORMITY: ITP Signed
8929f538-3bc2-5786-8d4e-94a881510ae3 | note | IP
b2e87b91-5cee-5ba8-94c4-40e8334249c9 | note | RESPONSIBILITY: Site Enginer
bb67c830-0c3f-5076-8233-41d6f956f2cf | textbox | Date Completed:
3a20be73-4ea0-4cac-a141-f1bd9f4b298c | checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
14a562fb-e06d-5bbe-aff3-3ba0a06c9ba2 | note | FREQUENCY: Each Pit
20934d10-387b-51e1-84db-2f932655c326 | note | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
9ac7475a-a9b7-5ca7-82c8-7464ac16856d | note | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
49b2b80c-41a8-58d3-b005-8483ba95b6fb | note | INSPECTION/TEST METHOD: Visual Inspection
0bcaf372-5363-5cc9-8ce2-98da6053f8f0 | note | RECORD OF CONFORMITY: ITP Signed
9010dffd-99ef-59cd-95b5-e7d0fcb576fc | note | IP
4e36e51b-5e5a-578a-9d9a-d58f0a885fef | note | RESPONSIBILITY: Site Engineer
18012217-0c56-59b7-b271-ed73d7c3d7d7 | textbox | Date Completed:
e923c5ab-738d-4b60-b709-978a0ea6b200 | checkpoint | 2.17 Place pit covers
a330bad2-be92-5ca7-877f-83f9f0a35a9c | note | FREQUENCY: Each Pit
e6ba1f1c-547c-5162-ac21-6347a71bb8af | note | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
b2dc8ff0-2e78-5d85-9ec3-265688505824 | note | REFERENCE DOCUMENTS: 705.17
9d82c968-ace5-5c2a-8750-2890b9f16bf1 | note | INSPECTION/TEST METHOD: Visual Inspection
955346e9-dee9-5eb0-bd5e-089149d036af | note | RECORD OF CONFORMITY: ITP Signed
84f9b8a5-a63e-5350-9a6a-619467be2251 | note | IP
183575db-5e33-5f0f-8c46-a3e351c30946 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ff1d349e-911e-594f-9f5a-2f1b6b934897 | textbox | Date Completed:
6c9ac448-af3d-4b3d-bf4d-0db3e8867ca9 | checkpoint | 2.18 Repairs to damaged pipes and box culverts
8d612c4e-8069-5cfa-8c70-dad3b806d037 | note | FREQUENCY: Each damaged pipe or culvert
13bedceb-1364-5057-9569-d90e0b52e538 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
90a3877d-c482-5b97-aa0c-3d7f78803ff5 | note | • All repair procedures undertaken in accordance with Cl 701.25
b31b18f6-7c1e-5e14-9697-4c9cd0ecfdcc | note | REFERENCE DOCUMENTS: 701.31a
cf18e3cc-893d-5cd1-8e0e-02f79974bdc5 | note | INSPECTION/TEST METHOD: Verify
6b3fe3c7-ba0b-5496-b4fe-071c8466ac58 | note | RECORD OF CONFORMITY: ITP Signed
89c3949b-9b48-5ed7-9e3b-182c4c78b40c | note | HP
b2721ee5-6683-5e72-bfc9-723fd40cdcc9 | note | RESPONSIBILITY: Site Engineer/ Superintendent
3f132b80-89ac-53db-869b-dd94892dbe31 | textbox | Date Completed:
85f6e7e4-f8ce-47a8-82d6-5765187f4d52 | signoff | AUTHORITY HOLDPOINT
89321de0-adc2-494d-8473-53947acdafc4 | section | Testing & Completion
39a04629-c731-4127-85a9-384546855d15 | checkpoint | 3.1 Compaction and moisture content of backfill & bedding material
16de96c4-2e71-5b6f-87d4-1f8c2bdafaf4 | note | FREQUENCY: At least 20% of all lots
7a2919f1-7395-5b42-8bc8-4ab649db6966 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 97% using standard compactive effort.
e8e29792-0d5b-54d1-a1fa-9f3a8889d4ae | note | • Bedding shall be compacted to refusal using hand held mechanical equipment.
92c233a7-f8fa-590f-af39-7fb278ce69c8 | note | • Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
14b7c1b6-f6d0-5074-971e-81118283ff76 | note | REFERENCE DOCUMENTS: 701.20a, 701.20b
42f2da3a-6a83-54fc-be24-7495753aadc2 | note | INSPECTION/TEST METHOD: Verify
033f594d-4f5f-5d80-9cf6-e9dc3906f4c9 | note | RECORD OF CONFORMITY: Test Reports
e60c9ce7-398f-5ae3-aa5d-0f594b6065c0 | note | TP
dfdba811-b583-5f9a-9b58-9c5e8c12a817 | note | RESPONSIBILITY: Site Engineer
8da024b3-82d0-573d-b93d-33f4a232d7a7 | textbox | Date Completed:
da4b2db6-70ad-43cc-98e4-111b90b08767 | checkpoint | 3.2 CCTV inspection
7b255922-8452-5e30-9e1c-48806c9a1e5d | note | FREQUENCY: Each lot
f4618844-f83c-5295-9491-7979401554ce | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
e1e21816-a8f0-5361-bf24-e150ed34e93b | note | REFERENCE DOCUMENTS: 701.3
13762f29-3e4a-5973-a461-ed667dcf768d | note | INSPECTION/TEST METHOD: Visual inspection
b07e113f-a092-5254-8e32-58f9710aa81c | note | RECORD OF CONFORMITY: CCTV Report
e98375c6-0ab6-5e1c-8543-c977e6934e8f | note | HP
f5b83299-7984-56f5-a562-abd04a226710 | note | RESPONSIBILITY: Site Engineer/ Superintendent
e4d8f780-441c-56fb-9420-6c894ce60513 | textbox | Date Completed:
e286a11f-072c-4c36-b4ac-db5927760a27 | signoff | AUTHORITY HOLDPOINT
ef91a6ba-e763-40ba-abb1-95a59de8fbc7 | checkpoint | 3.3 Flushing of pipes
1343e9f6-7539-5fa8-be09-841d9f590225 | note | FREQUENCY: Each line
916f43f1-83ac-50de-8c16-9bb550c4d3d4 | note | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
b2283218-63af-541b-9932-4bfcf6890622 | note | REFERENCE DOCUMENTS: 701.28
cc9ae568-bc0c-5069-a5ba-3295813571d9 | note | INSPECTION/TEST METHOD: Verify
b09aa5a8-36dc-52c0-a25d-573e70cc64ba | note | RECORD OF CONFORMITY: ITP Signed
45e6e3eb-e86d-5233-9041-c7aed24f6de4 | note | IP
e8a6b829-4a0b-5d28-a1be-5210fc4a7e1e | note | RESPONSIBILITY: Site Engineer
fc9cac0b-2009-5bf8-8ffc-77deeab1bc14 | textbox | Date Completed:
5c225614-7a9b-4837-abbf-21a98c397010 | checkpoint | Final Inspection
d95fecea-a1b2-55e4-807e-b164ce02dbe4 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fe88ec9b-4348-50e0-913a-a60158995ad1 | textbox | Print Name:
8b544b2b-c8bd-52f9-a702-03f2426d020d | textbox | Position:
fd10eb10-bbfd-5a66-a5dd-5f0425bc0880 | textbox | Date:
d45b29bb-6907-446d-b77d-579bf08f792a | checklist | FHC-ITP-009 - Profiling Rev1 | itp | FHC-ITP-009 - Profiling Rev1
38b6da79-dc4a-44b9-bc57-7558d5e70076 | section | 1 - Preliminary Works
e234fa64-f44c-413c-a11e-6d9a36b0e671 | checkpoint | 1.1 Check for correct documentation
c7ff752e-960b-597a-b652-50891df0f5c8 | note | FREQUENCY: Prior to commencing any activity
6bc01f8d-d6d3-56f8-9eff-c34190002c40 | note | – – – – – – – – –
8a5b5a19-fcc6-58a9-8caa-6e25cfc8cfff | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
953d503e-c5d2-53bc-8e9f-a89c3d68d007 | note | – using the correct and complete set of drawings
f8e132b2-d111-5ef5-8ebe-618a23c15461 | note | – all drawings are the latest revision
f54a5710-eb60-5ede-a762-827e8e06d9c0 | note | – – – – – – – – –
43edc3a2-40c7-593b-8b02-8705c68345d7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6d8a7fb5-e484-5920-9cab-5d4b5b05a494 | note | – – – – – – – – –
65101af9-770a-54a4-b9ff-74443d64448b | note | INSPECTION/TEST METHOD: Visual inspection
e09e2105-d014-570b-9ac5-2e93d59a40bb | note | – – – – – – – – –
72cf5cd7-ae7a-5cf7-9a81-0004d6c29e2e | note | RECORD OF CONFORMITY: This ITP signed
10069511-9660-5a14-9f73-b00411c2a4e7 | note | – – – – – – – – –
6ed01f06-e437-5738-9ea8-d22a0ed91a6e | note | HP*
c24058bc-6d88-5ecc-a9b4-ac0d74f2bfb8 | note | – – – – – – – – –
e76fb41a-01fb-5c2e-8d0b-08bbe8f0b095 | note | RESPONSIBILITY: Fulton Hogan Engineer
d4e4bc4c-b615-5010-ac5b-109df3a59126 | note | – – – – – – – – –
5a2a452b-4c4c-57e8-8950-9b0bbf55cd69 | textbox | DATE:
f96e1134-5550-4338-a340-e2e673854e4b | checkpoint | 1.2 Implementation of all measures and controls
68ee036e-6087-52a6-a2d3-182e4e47c899 | note | FREQUENCY: Prior to commencing any activity
6e7f278c-914d-51f4-b670-3e377520ebdb | note | – – – – – – – – –
75459f9c-7e82-547b-8dfb-fd754f73f251 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
3c806db8-3dbd-5401-86ce-c839e8345762 | note | – – – – – – – – –
ddae1fc0-d51a-5102-ba7e-548f227f9b39 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
5da9d713-a6bb-5e33-a146-6df9c7a5f077 | note | – – – – – – – – –
5256a58b-a25b-5348-9bdb-02dd94f204ed | note | INSPECTION/TEST METHOD: Visual Inspection
af9ba3d6-a76c-5817-b797-ddd16934568d | note | – – – – – – – – –
384d1172-7637-53e4-9e6b-1ffef64c1518 | note | RECORD OF CONFORMITY: This ITP signed
2ab2d961-1538-5c33-8a92-3ff93d36db14 | note | – – – – – – – – –
f4fbd606-0289-5ba6-a690-c951578a7c7e | note | HP*
faac8337-3974-585f-8706-0ed0ea482844 | note | – – – – – – – – –
4fb9196a-ea3f-5e06-864d-562c567c7a1f | note | RESPONSIBILITY: Fulton Hogan Engineer
bd44768f-7e74-5858-ad00-a55f62e63171 | note | – – – – – – – – –
e3591c6d-a7c0-55ea-a2a5-ea6b91282568 | textbox | DATE:
489ac8b6-bc14-457a-8c40-8dbead70898a | section | 2 - Construction Works
550fd228-59dc-4f26-a187-18e75d44b81d | checkpoint | 2.1 Profiling Works
5654d3c5-a0ff-5298-acc5-51bc293fcb70 | note | FREQUENCY: Each lot
a9435286-9e28-559b-8d12-253e27141e31 | note | – – – – – – – – –
561350b2-aa54-52e5-ae34-2fa2bd66ec82 | note | ACCEPTANCE CRITERIA: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
def87743-1369-5220-ba81-ac6d334eafda | note | – – – – – – – – –
e3b3aa4b-bae1-57bc-8bef-83ccaa7ed73c | note | REFERENCE DOCUMENTS: 402.02
ca80820e-c4d1-5e62-98a9-8a10c909f03a | note | – – – – – – – – –
16781603-9a01-56f9-a2a4-b61fa472514d | note | INSPECTION/TEST METHOD: Visual Inspection
f3e6b228-771b-5081-8dc0-eab4d2ae3230 | note | – – – – – – – – –
a1df8c5c-444f-5797-b837-cc9061d1bbe5 | note | RECORD OF CONFORMITY: This ITP signed
4f5690e2-cd24-54c9-833a-22c3c256f915 | note | – – – – – – – – –
c7de9d9d-bd65-5beb-89fd-1201bd02302a | note | WP
5a0b4255-4f07-5610-a870-91a50178cbc5 | note | – – – – – – – – –
8269a943-914b-5851-b4a6-fd717a3dc09d | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
fd712ac7-398e-51e2-91c0-f05ecba3eb4a | note | – – – – – – – – –
2e8de51f-a60d-52f1-823b-54da7758a4de | textbox | DATE:
b2bd1060-936d-48fa-a0c7-589c6c78935d | checkpoint | 2.2 Depth check
171525ef-777d-55ac-b1d1-0a687b452acf | note | FREQUENCY: Each lot
6057b818-8a0a-54bd-bcc0-9c4c70b5e377 | note | – – – – – – – – –
d256c98b-dd07-533a-8275-21a3b452f350 | note | ACCEPTANCE CRITERIA: Average depth of pavement to be removed shall be 40mm ensuring that all Wearing Course is removed.
8a65b8ed-5dfc-5ee4-bcf4-6d4d79ab4c11 | note | • After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
ef5339d1-aaa6-580e-958f-32c0aa6a2c44 | note | – – – – – – – – –
b4ac8c90-36f1-5489-806c-c8cabfac779c | note | REFERENCE DOCUMENTS: 402.02
87ccb13e-889d-5caf-8e14-13ecd1093c22 | note | – – – – – – – – –
beb59242-8395-5c14-94f0-58b80b2f7d4d | note | INSPECTION/TEST METHOD: Visual Inspection
55c14a5a-15ea-5f1b-bb74-25ee93246160 | note | – – – – – – – – –
b29963ac-bbe6-58a8-8e27-4090fbdd3f0c | note | RECORD OF CONFORMITY: This ITP signed
80f7e49e-c795-5453-a238-164f08189b23 | note | – – – – – – – – –
274a9cef-303d-5013-863d-803e31cb5339 | note | WP
1ea01838-2c5b-55bd-9195-92fd208a3bf3 | note | – – – – – – – – –
975b4053-f246-55bc-8d0b-d31ed7642ae1 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
111fefe5-37bb-5859-bbc4-ad1927596aed | note | – – – – – – – – –
d447500a-2fd9-580a-ad08-a586fc1e1517 | textbox | DATE:
9f3d484c-6b09-4abb-b240-0c58e8d66141 | checkpoint | 2.3 Temporary ramping (longitudinal)
fa232026-9ad5-5d9f-ac0c-a51d4c19d629 | note | FREQUENCY: Longitudinal edges
f7ee7d98-83ba-539f-ac4e-5c50772648fd | note | – – – – – – – – –
d3cfd178-3a36-537c-a72d-849ccaf56b54 | note | ACCEPTANCE CRITERIA: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
fdbe2871-bfe7-50fa-8edd-34021287427e | note | – – – – – – – – –
02bb84ae-7329-58ce-a33f-31b6a06487fe | note | REFERENCE DOCUMENTS: 402.05
71f27c69-774f-560a-bc51-b9fb8046fdab | note | – – – – – – – – –
753bcf7e-8bd7-5c8c-a11b-78cc54f49674 | note | INSPECTION/TEST METHOD: Verify
07f05ca7-b339-59b2-9bc1-b3c2750ee99b | note | – – – – – – – – –
efe697ce-7358-599b-b8d4-4cc7b8572b9d | note | RECORD OF CONFORMITY: This ITP signed
f9b01b5a-3be2-57de-9716-36baf2b9d03c | note | – – – – – – – – –
d0716901-e07a-547b-99ab-c91dd11c316d | note | WP
f0f3817d-5771-5c22-af63-c5f000d0865f | note | – – – – – – – – –
2823d434-ae5e-54fe-8670-d6d23fb601d9 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
b7c18c35-4c35-52ed-a1ce-bb35bc43831c | note | – – – – – – – – –
713ca707-d908-5f5e-9607-4dc6380932ab | textbox | DATE:
513618ae-10b0-444b-b261-f5858912e966 | checkpoint | 2.4 Temporary ramping (transverse)
e8d6d36c-5d42-5883-9dd8-7265d0950f22 | note | FREQUENCY: Transverse Edges
88e4fa65-7428-5404-8b40-8fd28d2bb3e8 | note | – – – – – – – – –
bcaf0667-40df-5c6f-aef0-7933760dfa19 | note | ACCEPTANCE CRITERIA: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
c3967d38-b2b0-5448-a45a-84ffd0dc5c1a | note | – – – – – – – – –
fbb11cd3-2f59-53cf-9a6e-999ccc7047e5 | note | REFERENCE DOCUMENTS: 402.05
46ac1a47-b2f4-5c56-b7f6-fa0cdabfabf5 | note | – – – – – – – – –
cec4cb1c-1287-5324-81ce-4731ecf3d5b1 | note | INSPECTION/TEST METHOD: Verify
120941d2-e134-5ee7-80a9-3238cad9bdc7 | note | – – – – – – – – –
2c8eb547-7898-5e9a-9ef1-ae102afa4886 | note | RECORD OF CONFORMITY: This ITP signed
61b4f12f-47cf-52c0-bfae-62e3f8f6c5f0 | note | – – – – – – – – –
051f6d04-d883-5a4a-a7cb-43454a2d390c | note | WP
23dbb691-4754-54f0-81d0-2360863182e0 | note | – – – – – – – – –
fb7a566b-5bec-57d9-b129-9547ad6c1b57 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
aa2605db-4206-5790-b3c4-87f05198e225 | note | – – – – – – – – –
72c73648-80c5-5cf0-8048-db27d483be7b | textbox | DATE:
8cd4aeb5-a25a-4abb-918d-37ce70e6edb1 | checkpoint | Final Inspection
ec7fd4d9-6f68-5071-88a4-d36986c9067f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
42b1a9e0-9cea-5dcb-b4c5-066cdeb504cb | textbox | Print Name:
3f8967a2-726f-5fa8-8960-deb9f77f0f05 | textbox | Position:
e9ef6d99-4c4a-5c7b-a4b5-d63ae46a1d86 | textbox | Date:
95410473-17b1-4e8c-b7e7-58be171e9e12 | checklist | FHC-ITP-013 - General Concrete Paving |  | FHC-ITP-013 - General Concrete Paving
cbbd73ed-6151-4217-9782-6a4c5c3bc804 | section | Preliminary Works
fb28e7dd-48d3-4373-9849-b35df137cd84 | checkpoint | 1.1 Check for correct documentation
86a8673c-ad58-55ba-b3a9-27226028ac46 | note | FREQUENCY: Prior to commencing any activity
ec5c66b3-2bba-5408-a7d1-297d4d348179 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
460493e8-5c58-543e-91ba-a78a242514df | note | – using the correct and complete set of drawings
ad9c7a63-e497-5c45-87de-d50b6fa6611e | note | – all drawings are the latest revision
b0ffbafa-b004-5daf-b349-e84e4007b825 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c1117bec-8ab4-5488-9520-55604b17209c | note | INSPECTION/TEST METHOD: Visual inspection
fc508ca4-92f1-5c05-a458-43e9736bd2c6 | note | RECORD OF CONFORMITY: ITP Signed
dfccf7e9-668c-5810-8c5e-ed345b78f9d6 | note | HP*
d21ca931-486e-5260-b396-8422b8aa3cae | note | RESPONSIBILITY: Site Engineer/ Site Foreman
9fa46421-254e-5fef-8d1a-268b999cd35e | textbox | Date Completed:
8827ea6e-c6db-4f71-ac55-8e6064dbe0d1 | checkpoint | 1.2 Implementation of all measures and controls
47a626f5-1852-54e0-ae8d-7d750605cf2c | note | FREQUENCY: Prior to commencing any activity
eb00f50a-73a5-5f8d-bb4d-151e2a88de62 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
c7df4ffc-c514-5ab7-8d6a-20a785272820 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
859a45a6-830d-5632-849f-6a0ae36366f7 | note | INSPECTION/TEST METHOD: Visual Inspection
28d1ae1d-5075-5908-a3bb-7335b0b7e6c1 | note | RECORD OF CONFORMITY: ITP Signed
acedbb3a-9578-5c93-9b8d-34bf32d03345 | note | HP*
3c2f633a-6355-5646-ba1a-ab2e837941b2 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
5996b312-51c5-558e-a0fa-9f3f225426c3 | textbox | Date Completed:
9dc5a511-1def-4027-b9d4-cf6083abd00b | checkpoint | 1.3 Submission & Approval of Concrete Mix Design
7679cb28-9428-5d4d-8663-4782b4662ce2 | note | FREQUENCY: Prior to first concrete pour
658c058d-bacd-5eac-b16f-be3754ef5d0d | note | ACCEPTANCE CRITERIA: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
cb74efc8-9b06-5a89-a2db-59a17697bcaa | note | • Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
acbd1700-a382-574a-a98c-f7c5189dc2f9 | note | REFERENCE DOCUMENTS: 610.07(b)
cb8aedfd-3670-528c-9db0-263ac0dd1b1c | note | INSPECTION/TEST METHOD: Verify
f3628516-c822-54f8-8c89-c47022259212 | note | RECORD OF CONFORMITY: ITP Signed, Mix design approval
f0095a2b-f0d5-56cc-87d8-f413ca8b89f0 | note | HP
46b7d4ef-b4d1-592e-b55e-b726473c7ca6 | note | RESPONSIBILITY: Site Engineer/ Superintendent
3b3cfea8-ecc7-59a2-907a-0062b2640a2c | textbox | Date Completed:
bf1c400a-f5f3-4681-960f-ba969e8a10a3 | signoff | AUTHORITY HOLDPOINT
7aafa859-4b51-4c24-bba3-bd228a5584d0 | section | Construction Works
ad96f94c-14c0-47f8-a8d8-4946dd2a2b26 | checkpoint | 2.1 Setting Out
64b36dc9-ced5-5e49-9b85-86b24cbd1d36 | note | FREQUENCY: Prior to start
715b37e8-4e7b-5aed-a25c-43e2c59064b1 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out.
03c76b05-7bb6-57fe-90ae-1a1e5a9a71fc | note | • The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
40f06707-d98c-5702-9fd4-8b1efae92eea | note | REFERENCE DOCUMENTS: 703.17
c301981a-0cbe-5d62-abe8-3520d5c4f309 | note | INSPECTION/TEST METHOD: Verify
a123ae03-3e99-52f1-a6d3-8bffbf3e5694 | note | RECORD OF CONFORMITY: This ITP Signed
6e0f9fab-123c-567f-adb0-458d54f8349c | note | HP
9e0eb2f7-b769-5793-8a4e-0e926108d7e3 | note | RESPONSIBILITY: Site Engineer/ Superintendent
5cc662d5-1ca2-568f-9a74-a6196e14b8c8 | textbox | Date Completed:
1236b292-742b-43b7-a208-f27f08caf33c | signoff | AUTHORITY HOLDPOINT
04ef8c93-200a-48ff-8e81-dca40f745462 | checkpoint | 2.2 Excavation Permit
e2999a25-ae60-5bb1-a5aa-f1fe56b3200e | note | FREQUENCY: Each lot
020667b5-f192-55f2-9471-878aed3d9191 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
dc612b71-d564-52f6-95e9-f6d877988a36 | note | Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
057accde-12cd-505d-a40c-a7de04e558fd | note | REFERENCE DOCUMENTS: Excavation permit
08febcd8-bd25-5848-be71-dbe2f0fb0ede | note | INSPECTION/TEST METHOD: Verify
5eb3162d-5a36-5a23-9b2c-0f6a37a18509 | note | RECORD OF CONFORMITY: ITP Signed
b62c2770-e820-5d8e-a991-f18a9df84e13 | note | HP*
071adf7f-e9a3-5694-925e-4f3edbcfd31e | note | RESPONSIBILITY: Site Engineer
e1d2130e-e0dc-5652-be47-edebdd65ec15 | textbox | Date Completed:
6d408198-d0c2-446a-954e-dc60d07de47e | checkpoint | 2.3 Excavation
a9af7f50-cb76-5c50-a223-2565abee0bdd | note | FREQUENCY: Each Lot
08830bef-b9c4-59b5-9822-a14c072f6726 | note | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
260d9769-0fa6-5c88-a970-395bb474f9e2 | note | REFERENCE DOCUMENTS: 703.2
ef32af8c-9fc2-5504-aec5-7a64c0475de3 | note | INSPECTION/TEST METHOD: Verify
5a067a47-98e6-5d3f-aaed-f69fc25fc2cf | note | RECORD OF CONFORMITY: ITP Signed
1fe260b0-d097-5bac-b936-aa6cc61fe4bd | note | IP
418b89af-cce9-51d9-86f6-4b42321cde9a | note | RESPONSIBILITY: Site Engineer
ebdc807a-23a3-50c5-ae71-8894b8acb7a2 | textbox | Date Completed:
3df2bf48-9d78-41f9-9d85-1fd78c613229 | checkpoint | 2.4 Bedding
67fc02bf-2463-5892-8afe-021cd8d6cd1b | note | FREQUENCY: Each Lot
2c04eb77-68df-5668-9969-0daa44c382de | note | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
623b19f2-21d3-5faa-b25e-ebdb4e915cd6 | note | – 100mm thick layer of 20mm Class 3 crushed rock bedding for median infill
49f636b1-3ad4-58f4-9a36-92f7c347b54a | note | – 150mm thick layer of 20mm Class 4 crushed rock bedding for footpath/pram crossing
37371409-5f0d-5b80-8fd8-306f54557bff | note | – Bedding trimmed, moistened, and compacted as per Section 304
e17d5117-92a3-556a-af61-a7847be2c40d | note | REFERENCE DOCUMENTS: 703.21 Drawings
bd8a0679-b269-5a76-8e3a-8aefd27c15eb | note | INSPECTION/TEST METHOD: Visual Inspection
d7bef63b-f50c-5a18-96b6-44b5b2c6e9d4 | note | RECORD OF CONFORMITY: ITP Signed
572b0089-4804-5078-b9ce-7df8daed1447 | note | IP
600d5bcf-dccb-5e3b-b82b-69e41e2c97e5 | note | RESPONSIBILITY: Site Foreman
6686189d-3728-5b6b-9793-2f3471836525 | textbox | Date Completed:
fc33d313-b3bc-4a56-89ad-7c5939e18217 | checkpoint | 2.5 Formwork
83051fc6-a1e7-50b3-9045-eac86a1da3fc | note | FREQUENCY: Each Lot
c1d43a30-f23b-5d2c-bace-955e6a8318d4 | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
575d16c6-c0bb-5fc2-86fc-dcc8a348341e | note | REFERENCE DOCUMENTS: 703.12 AS 3610
b46cbb78-5008-5d76-8247-545ef90d297c | note | INSPECTION/TEST METHOD: Verify
f4c3a67c-0182-5d14-aa7f-c3b6eece8206 | note | RECORD OF CONFORMITY: ITP Signed
fa483284-20ea-5254-a595-b45b37b03642 | note | IP
189fed02-5505-5300-85ea-8df2e19aada4 | note | RESPONSIBILITY: Site Engineer
700268d9-aedf-5598-a0e5-e260dd7415f9 | textbox | Date Completed:
568452f8-37d0-4f3b-a449-67f5d4bcae9d | checkpoint | 2.6 Reinforcement
8d31098a-4de1-51c3-9c73-0cdd73d94924 | note | FREQUENCY: Each Lot
d73334f4-7df5-5c1d-b554-82dc9316b7d4 | note | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL82 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
1f5d305d-4f70-5438-b055-99aaf5175ef5 | note | • Reinforcement must comply with the requirements of AS/NZS 4671.
bbab2de9-31a9-58d1-988d-0772a5f9b458 | note | REFERENCE DOCUMENTS: 703.13
57802bd6-dc91-5cf8-b0ca-81b55ae45235 | note | INSPECTION/TEST METHOD: Verify
215bec41-8cc5-5c8d-802f-6b7dd84c269c | note | RECORD OF CONFORMITY: ITP Signed
06b1a0a6-8133-5c04-b4b4-aa36ff451eb1 | note | IP
1c58ba18-420a-5af1-8af7-088893f3470b | note | RESPONSIBILITY: Site Engineer
9723da75-9e9c-52ad-9fb9-130efcaa2b1b | textbox | Date Completed:
2d13131d-486c-4353-8267-e2b300728ce4 | checkpoint | 2.7 Concrete Placement
2358af30-8240-5c15-8273-cdd9b276dc28 | note | FREQUENCY: Each Lot
903be54b-cf32-5100-b979-d3bd0ff38926 | note | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
997083c7-b6a1-5e1e-b61e-9d00a537c564 | note | • Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
63ac9bec-f713-599e-84d4-6c51463df418 | note | REFERENCE DOCUMENTS: 703.05(a), 703.08
06cba657-8589-53bb-b641-0404079c0992 | note | INSPECTION/TEST METHOD: Visual Inspection
3d9c92ba-84f4-5fbe-ac43-0c3cd58effed | note | RECORD OF CONFORMITY: ITP Signed
c22e2ae8-d58e-5753-8d31-99b2cba2155f | note | IP
fd67b7fb-8815-5299-9589-9990b3242e50 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
61bcc583-ae4d-5bf2-98c8-303090521b67 | textbox | Date Completed:
229deef8-eee7-43e8-b34c-fa7a7a05d305 | checkpoint | 2.8 Surface Finish
7f8d2a84-f99f-5d6a-9357-50fd4a6ea629 | note | FREQUENCY: Each Lot
db8de109-75bc-5d41-8830-99e0c886b311 | note | ACCEPTANCE CRITERIA: Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
3f5f8995-2a50-5bcd-9dd0-b3bd90a9f606 | note | • Footpaths and other Surfacing shall be compelted with a wooden float.
b0d12a7c-54c4-57b7-95f9-64935340476e | note | REFERENCE DOCUMENTS: 703.25
7cc43d77-3f3b-5f5f-a919-aa52c434e2c3 | note | INSPECTION/TEST METHOD: Visual Inspection
cfa361a2-755b-574d-bc26-0c215777338e | note | RECORD OF CONFORMITY: This ITP Signed
8972ea1d-146d-5fd2-bbb6-06c0a57af3a8 | note | IP
7a86ced4-b888-59ef-96a0-1c482d671fef | note | RESPONSIBILITY: Fulton Hogan Engineer
701636ed-db92-5b54-8b5c-cdce92ce74ce | textbox | Date Completed:
1dabf85f-be75-48e8-b575-d941c5f4c5a2 | checkpoint | 2.9 Pram Crossings
aecd363f-25f2-5b33-9f42-f245795097f5 | note | FREQUENCY: Each Lot
296ada8d-1fc1-5e85-83b8-6f2f9a2d9327 | note | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
6fe638fd-fab6-59ef-be82-843c54c82b5e | note | – For pram crossings within concrete kerb refer to Figure 24A of AS 1428.1
b210085d-6b28-53f6-9792-e7084a573e75 | note | REFERENCE DOCUMENTS: Figure 24A AS1428.1 Design Drawings
a552ebaf-cf84-5848-ad24-24802d6308be | note | INSPECTION/TEST METHOD: Verify
45fda808-b090-59cb-b3eb-a23471ad3503 | note | RECORD OF CONFORMITY: This ITP Signed
cb837a57-88e7-5175-a052-e9e7c026716e | note | IP
bfb4f57f-dfa2-58e5-9de7-fa29488d88b0 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
742e2b05-4073-5ec8-9738-359bcb8c2e30 | textbox | Date Completed:
373123e8-a001-435e-bd74-57585f09755d | checkpoint | 2.10 Joints
9bd3b4fb-3629-57ef-b939-512e3a9b674f | note | FREQUENCY: Each Joint
dda9abee-856c-5d71-9ff3-d3223c04fd7d | note | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
17231b10-ae74-5951-b18b-0a76c4455503 | note | • Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
051efbe7-f278-5832-a224-312939303222 | note | • Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
bbca85ae-0eb3-5eb9-b603-43fd57cfce0d | note | REFERENCE DOCUMENTS: 703.26
2d3111d4-21d1-5822-9f69-9762d915d4f8 | note | INSPECTION/TEST METHOD: Visual Inspection
a51160e7-26fa-59c9-9ffd-eb226ad18974 | note | RECORD OF CONFORMITY: This ITP Signed
5edd439f-9aa2-52e6-aebb-54c75183da64 | note | IP
2327402c-8cbf-53c5-ab57-7d4222a5c2d3 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
42d7cbd8-1517-5874-a81a-bb8515b0a69f | textbox | Date Completed:
45b9b1e7-8a79-4619-9d44-3369777aee64 | checkpoint | 2.11 Protection of concrete
9b4e992c-cdff-5a43-8d1c-be1298cb8838 | note | FREQUENCY: Each Lot
bb23741f-b6bf-5c51-9b92-f453d1cb8943 | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
ccc2bb81-1ce9-523a-80c6-d6395f370c53 | note | • Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
4fac1cd8-9b36-5df1-ba82-a2805551c8fc | note | REFERENCE DOCUMENTS: 703.27
7b92f292-65c4-5202-9dc7-4d507ee5a9ba | note | INSPECTION/TEST METHOD: Verify
b035f456-59af-54d4-b807-72eaf8b9ed1c | note | RECORD OF CONFORMITY: This ITP Signed
f303e6f6-7db5-57ce-88fc-32b94dbe05d7 | note | IP
1297c975-1aeb-5927-b558-00f062ceadac | note | RESPONSIBILITY: Site Foreman
fb9c017b-3437-531b-8440-5b03899e154b | textbox | Date Completed:
35255598-7512-416f-ba1d-6f85e4c85427 | checkpoint | 2.12 Curing
f9e35014-0896-51a5-b8cd-25b54fb6992b | note | FREQUENCY: Each Lot
d0768090-50ca-5803-b2e5-36f2f1ae7d3a | note | ACCEPTANCE CRITERIA: Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
36d6b6a4-b860-5a99-a5a0-1d1ea4c1b602 | note | • Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
ed515e18-8af4-5f32-9cee-40f0a17d7b56 | note | REFERENCE DOCUMENTS: 703.1
90af0cdd-3c77-59d3-9909-2d797c7ebbf4 | note | INSPECTION/TEST METHOD: Verify
d1c14a66-87dc-559d-be01-22906f608103 | note | RECORD OF CONFORMITY: This ITP Signed
2c405c6c-9fcd-53fb-8895-3bb3564d70ef | note | IP
0d9bd45c-87ec-5fa0-9e21-3999652a9e73 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
56100aa0-4443-5c4f-8cc7-0d4077e947c1 | textbox | Date Completed:
407bdcb0-bb78-448e-941d-daa629c5f575 | checkpoint | 2.13 Ambient Weather
75caff5b-a92d-5d57-90af-b2e3cd91a2ce | note | FREQUENCY: Prior to commencing any activity
f4f64232-ef0a-586c-905b-4e84b7c010fc | note | ACCEPTANCE CRITERIA: Concreting operations shall comply with the requirements of clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for limits, restrictions and treatments to be applied for concreting in hot, cold and wet weather, except that curing shall be in accordance with clause 703.10.
81b58508-c266-5253-bb26-98253df3337a | note | REFERENCE DOCUMENTS: 610.17(a), 610.17(b), 610.17(c), 610.17(d), 703.09
68830eee-327a-521d-8c3a-3a20731fafe1 | note | INSPECTION/TEST METHOD: Verify
96b45a6c-0d05-5527-9b5f-f096fabb1273 | note | RECORD OF CONFORMITY: This ITP Signed
a839cd21-03ec-5072-9eab-d835241ed2dc | note | HP*
d9f0266e-2a0a-51ac-b235-8d38614eeaef | note | RESPONSIBILITY: Site Engineer/ Site Foreman
f81e981a-0783-544a-aeef-17e4b327c298 | textbox | Date Completed:
ce0d24d7-a676-40a6-96ba-6a5b9147d01b | section | Completion
a44a2f6a-52ce-4716-9407-5eed263b4ae2 | checkpoint | 3.1 Carry out sampling of concrete - strength and consistency
8332e1b8-c20d-57e6-b4a5-96bf38861f09 | note | FREQUENCY: Each 50m3
44b0c005-ccfd-5b8f-a47d-eb1506241d6c | note | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
6ddfec5c-3777-5a33-987b-6c1b3e67d8e3 | note | • The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
63217e17-e2f6-5229-b7cb-63abbca8b424 | note | REFERENCE DOCUMENTS: 703.11
6b18e900-0383-568c-83d8-9a70da6c4680 | note | INSPECTION/TEST METHOD: Checklist
edd384ae-664f-560f-8edc-e94c349d0ca1 | note | RECORD OF CONFORMITY: ITP Signed/Test Records
bdebc1b9-56e1-5a8e-8866-c33d6ea08533 | note | TP
95313aff-54e3-5e57-b3aa-09c926efe185 | note | RESPONSIBILITY: Site Engineer
18a2ea4c-be5b-55de-927d-deb858551734 | textbox | Date Completed:
0236220b-18b2-423b-ac67-709f728b9756 | checkpoint | 3.2 Tolerances
935ee2c0-bf78-5d34-8232-1ab7a3e12d83 | note | FREQUENCY: Each Lot
b4854054-b0ed-59ad-a2c3-70061dc38088 | note | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
7b2509db-11e8-56a6-82dd-fee20db55c84 | note | • Section dimensions shall be constructed within the following tolerances:
992f5db9-4770-5604-b541-e90c4fab10a5 | note | ○ 5mm and 15mm for width; or
1653b774-30d7-5c2b-b498-4e22d39c37b3 | note | ○ ±3mm for dimensions less than 25mm.
9aaecbb8-a830-58e7-abe5-868119f933fa | note | REFERENCE DOCUMENTS: 703.15 Drawings
cacf923d-3adb-5a3c-97f3-b890dfa536f6 | note | INSPECTION/TEST METHOD: Visual Inspection
1fd1545f-55f6-532e-bed6-89090bf36e72 | note | RECORD OF CONFORMITY: This ITP Signed
1eeaf646-d178-580d-9eab-2f02b5588723 | note | IP
3ecb6b0f-eeb5-5d9d-b08e-1efd0c0d4fe3 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
e6b9429b-394a-580a-a11b-f70bc50f2263 | textbox | Date Completed:
0174d95b-9b8a-4c63-92c1-4702132eed20 | checkpoint | 3.3 Backfilling
6d5459a5-1263-5464-8e53-e4cc889a3c40 | note | FREQUENCY: Each Lot
c310b7c0-9e43-525e-bc92-fe98509d5912 | note | ACCEPTANCE CRITERIA: After curing, no earlier than 3 days, backfilling shall be completed as per the below:
5e870a6c-5c6b-52b4-83f9-1f2e58606d74 | note | • Topsoil compacted in layers < 150mm
f1a55e91-2766-5af3-a4d5-5e76faa6e3f2 | note | • Width ≥ 300mm behind edging to top of edging
4b9a3fae-4286-5a6e-9b79-d496706aa2f6 | note | REFERENCE DOCUMENTS: 703.29
c46fdcb8-7f21-5b16-8799-a902dbf5bfa0 | note | INSPECTION/TEST METHOD: Verify
5b7c22d7-2bed-5cf2-b8a8-8ef1a6d234b8 | note | RECORD OF CONFORMITY: This ITP Signed
20bb21eb-8835-535d-8341-01e6a5221f07 | note | IP
63c23b37-9c25-5ef2-b925-8f89935bc8aa | note | RESPONSIBILITY: Site Foreman
fd7d3901-0e09-5527-8c37-058346da6263 | textbox | Date Completed:
9905f15c-2bb6-4737-95a5-95900272211c | checkpoint | Final Inspection
c09a8a3a-b594-5e11-b6be-f90478a6f131 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e4d804f3-965e-59e5-9f28-829e99bafb44 | textbox | Print Name:
20a0f535-494c-5618-b505-31abcac95e3f | textbox | Position:
4dd6e999-abce-5da7-84b9-7c07b80486e1 | textbox | Date:
bfe6a002-d500-4446-a796-c5f67a4d74bb | checklist | FHC-ITP-014 - Subsurface Drainage Rev2 |  | FHC-ITP-014 - Subsurface Drainage Rev2
7657e8fe-b2d5-4b67-8967-bd3022b97eba | section | Preliminary Works
96045076-e74b-42b7-a1c0-747e3e8a1d56 | checkpoint | 1.1 Check for correct documentation
d76bdbcc-00f5-57a3-9a01-a6454dfb7c8a | note | FREQUENCY: Prior to commencing any activity
c915b7f4-1581-57bd-8e3a-8eef8cdcff3d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
7629d1f6-e2e1-541b-8888-34e8c2948782 | note | – using the correct and complete set of drawings
8fcc810c-7837-5261-b8fe-71b74a2a3c43 | note | – all drawings are the latest revision
c859129f-3d0c-5195-ab43-661fc8ff66c9 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
b3d12377-4f95-5040-879b-e2eb11e06e23 | note | INSPECTION/TEST METHOD: Visual inspection
1db4fc60-f899-5880-b07d-9fe2f0e9259b | note | RECORD OF CONFORMITY: This ITP signed off
cd3190ee-e0c8-5f94-a75c-2c73dec172d0 | note | HP*
16354bc0-dee4-5339-9f5a-52c8381e181c | note | RESPONSIBILITY: Site Engineer / Site Foreman
eab7f809-7b22-5ce0-9879-1b0514241bbe | textbox | Date Completed:
49d2940c-551e-4d72-8f44-126c7ce3b055 | checkpoint | 1.2 Implementation of all measures and controls
ccbf0eba-be90-5ff5-9787-0efd3f93c0ca | note | FREQUENCY: Prior to commencing any activity
8b3edabc-8bd9-55f2-aeb1-5c4ee1681f47 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
135c75a7-654b-500a-827d-956b3e64cf82 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
a13a0201-acff-57e1-9e23-a592f0d62b81 | note | INSPECTION/TEST METHOD: Visual Inspection
572ee4db-6670-574f-8b7f-02a72872cd5b | note | RECORD OF CONFORMITY: This ITP signed off
7460cc3d-91cb-57e1-9977-10a9d9fa2c62 | note | HP*
8828229e-6a7a-500d-a7eb-b572470a3bc5 | note | RESPONSIBILITY: Site Engineer / Site Foreman
cb342a6f-244c-519f-97aa-4e1b3f91da52 | textbox | Date Completed:
15ce85cd-9bcc-47b0-99df-ef21ec70ff3e | checkpoint | 1.3 Placement of no fines concrete
8e06b350-7900-5c48-933a-0c23d4faa89f | note | FREQUENCY: Prior to works commencing
81fefe80-e0ca-5de0-9b2d-8e0aa5290eec | note | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures
4b99dfd1-0ace-584a-baea-b6b5f861d612 | note | REFERENCE DOCUMENTS: 702.09(g)
8b9ff6bd-1de3-5e5a-b276-6ffba3e2b43a | note | INSPECTION/TEST METHOD: Verify
62f82f2d-b9ef-5180-8c7f-65f139586f4c | note | RECORD OF CONFORMITY: This ITP signed off
6ed56045-105c-50e7-ae44-d0fabfe8022d | note | HP
9669ffd9-081f-5f99-b6b9-3d0fccc0ef40 | note | RESPONSIBILITY: Site Engineer/ Superintendent
bcac7508-1612-589f-ae40-516eaf3f7ba9 | textbox | Date Completed:
7c95fa2a-4fd6-4e43-9513-a3c7e47a1f78 | signoff | AUTHORITY HOLDPOINT
dfd095de-7637-4c86-b66c-cb1e260b7d21 | checkpoint | 1.4 Material Classification
44cb2c62-d235-55e0-bf59-ce567feca21c | note | FREQUENCY: Each Lot
a37dfe11-f80a-50da-a83e-82efc7930e4a | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes:
73f2b438-a830-55a0-9e35-836966c71b45 | note | ○ 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
8b69fe28-6c72-58d9-b4be-2277aaad5355 | note | • Granular filter material for bedding and backfill:
5523c366-87b5-5fea-8da2-e9e331560b1b | note | ○ Trench backfilled and bedded with specified material on drawings
fc14a978-f181-54cc-9ed0-ac3ead60a57c | note | • Geotextiles:
8bbf94c4-fafc-5c42-8df2-8c8da43b4a44 | note | ○ Shall comply with Cl 702.06.
0a517e52-2785-590a-868d-a5eb0ffaeab0 | note | • Subsurface drain pits:
79c8d2ed-ecdd-547c-8cbb-c34b606bd736 | note | ○ All subsurface drain pits shall be Type S1 to the specification of SD 1611
a547b6cf-8649-5427-9e23-29bf19c71111 | note | • Pit Lids:
a3fb0bb9-529a-5734-8537-f0569cfd06de | note | ○ Type M3 circular lid (as per SD 1051) for Type S1 pit
702d6137-d9bf-53d2-81bb-fc255be7d3aa | note | • Flushout risers:
899a6f9d-44f3-564f-b44f-9efae6afa07c | note | ○ Constructed to the detail of SD 1631
47fdc63b-ae24-5c31-a9e2-41837187bd0b | note | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
200e7725-6f36-5133-8b36-39d303ced46c | note | INSPECTION/TEST METHOD: Verify
9a2f323a-83a8-5a0e-88d6-17de69c47ef4 | note | RECORD OF CONFORMITY: This ITP signed off
1e389f56-8056-55ee-8841-0d38384180a8 | note | WP
4c0b6d93-4b6a-5b62-8eb6-cabe7c6a9409 | note | RESPONSIBILITY: Site Engineer
c60bdc9b-faaa-5e71-ae8c-2f12f23158b0 | textbox | Date Completed:
786caca6-734c-4d99-907e-cb88f423522a | section | Construction Works
20658997-d0b5-47f0-9fc1-8bb92e5a228f | checkpoint | 1.5 Excavation Permit
521ed360-6b3a-58b4-ac26-f3bf144d434f | note | FREQUENCY: Each lot
14f7116b-eec9-5257-b4c1-4c296200de11 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
cf62fbfc-2b65-51ac-afb7-44a3f15b1727 | note | • Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
d26458da-fbd1-56be-b622-c861a0e78bef | note | REFERENCE DOCUMENTS: Excavation permit
97b73506-84f7-52b2-ab01-8e00c2411828 | note | INSPECTION/TEST METHOD: Verify
15650e84-b1a1-570b-99e2-75dab1d33bfe | note | RECORD OF CONFORMITY: This ITP Signed Off
1b4b0b81-484e-500c-8920-50154aea3450 | note | HP*
f566fed2-11be-5dd1-8fd1-8e958ce378fd | note | RESPONSIBILITY: Site Engineer
4b525cdb-cb6e-5de5-98d1-9e450a0b7131 | textbox | Date Completed:
85aa5df4-d2c5-451b-99a3-511dc400d96a | checkpoint | 1.6 Excavation of Trench
2a01d192-f41e-5ba7-89c6-071b95450b4f | note | FREQUENCY: Each Lot
ad4ac447-db77-5d63-b7e1-1d8544f49d53 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
fe264c88-c9c0-598e-aeaf-a548a735c792 | note | REFERENCE DOCUMENTS: 702.08
165583a5-6e15-5ea4-aaa8-0e9b1a6a4219 | note | INSPECTION/TEST METHOD: Visual Inspection
2cf43879-5de9-56a5-ab67-0de50f2baf17 | note | RECORD OF CONFORMITY: This ITP signed off
2b3a2e9a-b750-5982-ac91-0b2bd4d75508 | note | HP
4fe039c6-8f7f-5443-a1bc-4ed5da5b1903 | note | RESPONSIBILITY: Site Engineer/ Superintendent
eef02022-0306-5257-abe0-692e7586ac2a | textbox | Date Completed:
6e4a8644-64be-4ffb-9349-fe324378a7f8 | signoff | AUTHORITY HOLDPOINT
fc55f6b9-72d3-4716-85e8-b129043aa6cb | checkpoint | 1.7 Placement of bedding
f22b2fda-2c61-5345-9e1e-89f6b19b3e74 | note | FREQUENCY: Each Lot
bc6453f0-f1b1-5100-8f30-62fad412b6ae | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
239d28ba-8b32-5b98-a8fb-eecf2f4a5869 | note | REFERENCE DOCUMENTS: 702.09 (c)
c14e7e82-f8ad-524c-80c6-782429c13f39 | note | INSPECTION/TEST METHOD: Visual Inspection
9f4c1616-579d-5f94-ab02-8c6b59ee6023 | note | RECORD OF CONFORMITY: This ITP signed off
604b1d46-d904-5498-8df0-8be150175942 | note | IP
5c01b31f-50cf-5a30-a2d2-954682f731fd | note | RESPONSIBILITY: Site Engineer / Site Foreman
eb9083b0-3636-5eee-b8d2-33a3b7170b29 | textbox | Date Completed:
2b3179f2-5715-4931-9f44-32127aa6af72 | checkpoint | 1.8 Placing pipes and geofabric (if required)
1949b0e1-7776-5cba-9ed1-a30b29ebc22f | note | FREQUENCY: Each Lot
ec5e3776-ec2c-5e96-87de-648c3fefb6fb | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
17eb19f0-839c-5d09-8df3-30687f8758e9 | note | • If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
2d06bc7a-211a-5895-9612-b37362d66daf | note | REFERENCE DOCUMENTS: 702.09
e834089a-9cfb-5f47-a09e-4bd54fe190f8 | note | INSPECTION/TEST METHOD: Visual Inspection
bf435e74-8025-5429-a953-1c656f1e72e3 | note | RECORD OF CONFORMITY: This ITP signed off
fa2bbb1a-c179-505e-8b39-1333368edb12 | note | WP
b8e47c08-6aab-5e43-a210-34b1e07fa601 | note | RESPONSIBILITY: Site Engineer / Site Foreman
5003672b-8f23-54e1-b2b4-2e57e9b96ce4 | textbox | Date Completed:
b9eabeba-0388-4043-a76f-8de28c7c4b89 | checkpoint | 1.9 Placement of backfill
834ac410-9c3f-5dce-81ee-d11b44cc6b40 | note | FREQUENCY: Each Lot
de377f36-7b8e-5a56-b7aa-9d25e5287ee1 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
ac4415eb-b414-5940-a8a6-29122db91e2d | note | REFERENCE DOCUMENTS: 702.09 (g)
36b39b24-3829-5b40-8a31-c5bc83d846df | note | INSPECTION/TEST METHOD: Visual inspection
141ac290-d21a-51ae-9d80-6f43e16f3a53 | note | RECORD OF CONFORMITY: This ITP signed off
605def6b-3440-5319-9527-b9590046487e | note | IP
4a78a4f3-393f-5fc6-9228-eb6ae432d667 | note | RESPONSIBILITY: Site Engineer / Site Foreman
fd9adbeb-dc6d-5262-ae1a-c55c7b586898 | textbox | Date Completed:
92834a6d-e647-4cab-8ce3-2ef0200adf93 | checkpoint | 2.0 Install Pits and Flushouts
98ebb4e4-0fb1-5294-b5a3-92be5f1d6b19 | note | FREQUENCY: Each Lot
ebed21fb-b219-521e-ba24-a06781bee07d | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
385d418f-5793-52c3-9489-c6c8031a6201 | note | REFERENCE DOCUMENTS: 702.1
788c341b-ad0f-5fba-bab6-21fb44f29a95 | note | INSPECTION/TEST METHOD: Verify
b0709d05-d731-529e-b1bf-b60d36283008 | note | RECORD OF CONFORMITY: This ITP signed off
aad3d821-056f-5374-b8ee-809865737e91 | note | WP
a9f53e90-cfd0-5e46-8008-4a174de5961a | note | RESPONSIBILITY: Site Engineer / Site Foreman
86dcee05-5327-5ba4-8abb-f6a974d93f14 | textbox | Date Completed:
1ce5a445-3e03-46cf-950d-0302398d2550 | checkpoint | 2.1 Flushing Test
2e01c034-d2af-551e-8fd8-8c80abb22c8d | note | FREQUENCY: At completion of stage
0e5ca091-26dd-580f-a59e-bc32828210e1 | note | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
1e394334-ffb4-59c0-912f-eee5a126c77a | note | REFERENCE DOCUMENTS: 702.09(i), 702.09(h)
95d07592-8adb-5338-a37c-1fff375cec59 | note | INSPECTION/TEST METHOD: Site inspection
253fa59f-c765-5a9c-8424-e48ac6d1c710 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
70c95c15-58bc-5bf3-8b2a-7f82e4acdc89 | note | WP
df410109-d1a4-5fd6-ba4c-e6c38a3103ce | note | RESPONSIBILITY: Superintendent / Site Engineer
a833b7d2-d174-5ba5-9572-7c4a5074cfd5 | textbox | Date Completed:
a77e2467-243c-40d2-bb57-a2e1c762245b | checkpoint | 2.2 CCTV
55685f44-0b6f-5844-b04e-b26f9c6623af | note | FREQUENCY: At completion of stage
82601c02-dcad-5657-97ac-64fc3723bd5a | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
8ecfff77-68c3-5392-a9ad-82d0e40cfa6b | note | REFERENCE DOCUMENTS: 702.09(i)
3a3c634d-6822-5130-801d-72ff1f719c09 | note | INSPECTION/TEST METHOD: Site inspection
fb0be029-657f-557a-9048-a7b517afd78c | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
fbe240aa-e5c1-54ae-81fb-b9e27e830f57 | note | HP
c0ffad6c-9add-5760-9a6c-5596003e150b | note | RESPONSIBILITY: Superintendent / Site Engineer
18511d45-c61d-5fb2-b4d3-75ed6383d479 | textbox | Date Completed:
bf248a50-9d45-4176-8a0c-4b8207f48260 | signoff | AUTHORITY HOLDPOINT
44709c2e-0bf2-4988-a347-9b5c348c61f1 | checkpoint | Final Inspection
03c72611-ea05-5fae-8d31-bb94d4f905ac | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b13cdf1f-cfd7-5864-8843-0ca738cc5ffa | textbox | Print Name:
a1e8280b-9e2e-525e-b961-cb8dd872ee5c | textbox | Position:
58300eee-33f3-555c-a6b3-f022b36bd23b | textbox | Date:
41ac19ad-c853-412a-b95e-39afce79affd | checklist | FHC-ITP-015 - Kerb and Channel Rev2 |  | FHC-ITP-015 - Kerb and Channel Rev2
a5234780-3ad9-42e8-931e-ce547233cfab | section | Preliminary Works
57d81b5a-c2ed-46e9-92a6-b7c719dcd4aa | checkpoint | 1.1 Check for correct documentation
fa4634a7-e08b-5a5c-b2a9-fadba7c4a26a | note | FREQUENCY: Prior to commencing any activity
3afe1f8d-42e1-5236-8a63-01a93c9d6ceb | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a12ba839-1eeb-5f31-89f8-70f7d2a1073d | note | – using the correct and complete set of drawings
3b10fd5b-349b-5b61-8cc7-1bb36539be18 | note | – all drawings are the latest revision
9cde66fd-9d92-521e-a60f-f88ec30a3737 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9d8f568e-3763-5501-a907-8314e81e0cfb | note | INSPECTION/TEST METHOD: Visual inspection
708dceb5-f44b-5abc-8301-628dae292e78 | note | RECORD OF CONFORMITY: ITP Signed
ce380feb-df02-512d-8587-37b4e7f40c43 | note | HP*
a436b542-c205-57c6-ab44-cdbcee4835de | note | RESPONSIBILITY: Site Engineer/ Site Foreman
cb2c7089-a27d-5da9-8f3f-94078efa05ac | textbox | Date Completed:
d36a076a-b66a-4031-87bd-fb6fd1c8d6bc | checkpoint | 1.2 Implementation of all measures and controls
33c76ed1-7520-5843-aadb-c1261ccc529f | note | FREQUENCY: Prior to commencing any activity
3f6a00c9-918f-5ac2-8cc1-b4d5d67e7cd1 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
478b1909-4a91-506d-9e86-eb0dbd4faa74 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
ecd0032d-92f6-5cf2-8b2e-e159c3206a0a | note | INSPECTION/TEST METHOD: Visual inspection
efed91c1-5a18-5e3a-b84b-ba0c8925ff55 | note | RECORD OF CONFORMITY: ITP Signed
33647ff8-b22d-5f42-b7b2-917f1d38bc3d | note | HP*
648e5014-1133-5130-8f13-180c91d666f8 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
5c930e87-0ea3-5360-8d0c-afb2cad14234 | textbox | Date Completed:
fc6c42d0-2651-471c-9c3c-cbe28a68089a | section | Construction Works
625a942a-3744-4ea3-bb77-ac63557c2672 | checkpoint | 2.1 Setting Out
cec24bea-067c-5f51-a38c-fb2e71bd2b63 | note | FREQUENCY: Prior to start
cdcc6ddc-7168-5496-a4ea-f72210b44980 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
2d435a14-e76d-5b80-b83d-a6e99a734532 | note | REFERENCE DOCUMENTS: 703.17
3efb5754-539c-5a76-9bb0-3d7cc379b59e | note | INSPECTION/TEST METHOD: Verify
c4c93398-5e57-5be5-9bd5-5c8692106d5f | note | RECORD OF CONFORMITY: ITP Signed
1abb0a00-0d45-5bb0-885c-9d37116c5f15 | note | HP
6368515c-8d3f-5ea3-8c56-9a1a760c1dfc | note | RESPONSIBILITY: Site Engineer/ Superintendent
a7d935dc-67a6-5a9d-981a-99d62011c341 | textbox | Date Completed:
a5deef88-ecde-46d5-aeaf-29ff3a0b6937 | signoff | AUTHORITY HOLDPOINT
39d30ecd-d9b0-4ba3-8dde-0991345a28a4 | checkpoint | 2.2 Temporary Drainage Provisions
718209c7-e1ff-57c3-a6fe-f13648cf6f8b | note | FREQUENCY: If Required
5279ce03-48f9-57c8-b26f-9fcdc02668e9 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
824e692a-a2c9-5607-bcf4-cef5b960e9d3 | note | REFERENCE DOCUMENTS: 703.18
84ce2b76-b02d-5b71-a031-9e5d81966461 | note | INSPECTION/TEST METHOD: Visual inspection
2d503de0-78e8-5e46-bc0b-36da579fe7cd | note | RECORD OF CONFORMITY: ITP Signed
5308c175-32c0-543f-af56-fe449da3a101 | note | WP
6518e470-1413-5ec1-be4f-d876a3390fa7 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
47df24a7-1891-50cc-817d-1ce8f6ef808a | textbox | Date Completed:
3c71f5ba-5bf1-4fbf-9561-de5998640d06 | checkpoint | 2.3 Bedding
0e198999-ad39-5105-9772-f3e6e3556919 | note | FREQUENCY: Each lot
ccdb1d3d-f2f2-5366-a4df-05c85ada48a8 | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
55188123-8748-5f3a-9c55-d6706ab03b26 | note | • Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
5c26f201-7cfd-5af5-bd85-e050d97bcf40 | note | REFERENCE DOCUMENTS: 703.21
6429e6e2-e9d2-5807-9675-675d2480fea5 | note | INSPECTION/TEST METHOD: Visual inspection
344e9c1e-9770-50c0-8576-2198424ed120 | note | RECORD OF CONFORMITY: ITP Signed
b32c6d59-3960-597f-b799-c975ce44217e | note | WP
fba2b517-f00b-532a-bcc7-961d15eaee6b | note | RESPONSIBILITY: Site Engineer/ Superintendent
a9d6b67b-e8bc-5ff1-8e4b-898596fd24fc | textbox | Date Completed:
3f86e535-de0d-4f49-abaa-44b9a5f42690 | checkpoint | 2.4 Pre-concrete check
6f63f201-20db-5675-9d6b-e85bf1e6fcd7 | note | FREQUENCY: Each lot
d04194cf-926b-55c1-b770-78d2976064ab | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
ad3032bd-d9dd-503d-9aa4-97a7bdd87f4f | note | • Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
ec5836dc-a3b2-5ecd-8635-895525f61fd8 | note | • Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
46a7ed4d-3796-56ba-8498-0e99aaa670ff | note | REFERENCE DOCUMENTS: 703.08, 610.17(a)(b)(c)
5a634ed4-05d0-5a1c-88eb-62886955bb6f | note | INSPECTION/TEST METHOD: Verify
9bc0de27-9bd2-5bed-bcd0-81f8d19bf0af | note | RECORD OF CONFORMITY: ITP Signed
db37bffe-208a-57cf-8b67-05291b441d1b | note | Ambient Temperature |  |  | °C
87baf0c9-eecb-51d3-895e-93aa9094cb3f | note | Concrete Temperature |  |  | °C
a5d3bfad-974d-5a26-bbab-2440266f1626 | note | HP* / WP
1e727fbe-3a22-5459-bdfb-44315cd26df4 | note | RESPONSIBILITY: Site Engineer/ Superintendent
4fda74d2-f62f-570b-b3ce-e1de4555883c | textbox | Date Completed:
415710e7-76e1-4874-92a3-7acbf1d81af1 | checkpoint | 2.5 Concrete Placement
08dcef12-25ea-559e-9322-87b03b8f4af6 | note | FREQUENCY: Each lot
2e2563c0-5f7e-51f8-80cf-4295d3ab2df8 | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
ca48bc03-74e9-50bb-a0dc-ceb6c4fcef4b | note | REFERENCE DOCUMENTS: VicRoads Spec 703.23
830d84c8-7bc4-50bf-bf4e-d04d02e2c76a | note | INSPECTION/TEST METHOD: Site Inspection
ec5a4777-2644-5cb8-ab0c-fb828b474dbc | note | RECORD OF CONFORMITY: ITP Signed
7f56e0bf-92e1-5fa6-9191-26c4e89788b2 | note | IP
c8f18152-c948-5eb5-ae40-742825329f9c | note | RESPONSIBILITY: Site Engineer
f5cedcb7-0cc5-53a3-8805-437c27a7aeeb | textbox | Date Completed:
0927d8ee-4237-43d9-ad79-798e2769f179 | checkpoint | 2.6 Finish Surfaces
7f471281-2db9-5a1f-977c-d7c0bbc6016a | note | FREQUENCY: Each Lot
6eeb648d-9ba7-5ade-b7e6-7c14b8adb8e5 | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
a7fe0cd2-2a7a-5346-933a-d29b9921345b | note | • Concrete to have a neat appearance and uniform colour.
10e70a16-8ca9-52cc-8102-0be52e7f0883 | note | REFERENCE DOCUMENTS: 703.25
95cbb82f-2f46-537c-9aa9-957c3bf843ad | note | INSPECTION/TEST METHOD: Visual inspection
52745ffd-ba24-532e-b318-f2182b788eef | note | RECORD OF CONFORMITY: ITP Signed
651743fc-4136-5ed3-8d67-88a84c1ab403 | note | IP
5940b353-4a5e-5c65-88c1-0915b7d14e65 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
0b4f7340-0413-5c6d-b42c-32dcbdcd4d86 | textbox | Date Completed:
d04df8a8-417f-4a39-8fa6-318a12320d0b | checkpoint | 2.7 Tolerances
96ba2cf3-6a33-5334-ac7d-949751cd4290 | note | FREQUENCY: Each Lot
3c4b3b7d-eb66-5294-96ed-eef46c00c6eb | note | ACCEPTANCE CRITERIA: Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of ‑0 to +10 mm.
8c089690-db60-5b70-a138-8e230dce299e | note | • Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
400f99a6-62e2-532b-a7e2-c3293f1cff6f | note | REFERENCE DOCUMENTS: 703.15(b)
32a9d70a-a3cb-5bb5-a6a3-2c3b04acb23f | note | INSPECTION/TEST METHOD: Verify
da3ffd38-ebb4-5bbe-895f-86e70df8b3d3 | note | RECORD OF CONFORMITY: ITP Signed
e0f1b95d-9e49-576b-887a-2700907434a1 | note | SCP
e91167c8-35ec-5327-ae2a-0726cdabceb1 | note | RESPONSIBILITY: Site Engineer/ Surveyor
625d60dc-4d41-5715-a20e-d96cf0e3cfcf | textbox | Date Completed:
d34b3c6e-7ffb-47cd-83bc-d512b4a510f8 | checkpoint | 2.8 Joints
83c75d25-53ff-5e40-a200-4a5224c1cdb8 | note | FREQUENCY: Each joint
7b4afb14-b152-5ac8-99fc-0f0eacd0f96d | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
a9c41812-25a2-5e49-8964-94d3ae6e7b91 | note | • Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
7b8cddc9-1882-58c7-ac79-7119810239af | note | • Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
8d511b6c-ccb9-517e-92b2-91455d8023d1 | note | REFERENCE DOCUMENTS: 703.26
fd58e62a-26f5-5854-a8ae-62473d7e6092 | note | INSPECTION/TEST METHOD: Verify
61d6ca73-60b3-57dc-ae94-72bcc784a4e4 | note | RECORD OF CONFORMITY: ITP Signed
4294be61-8122-5991-a750-366607720710 | note | IP
4151846e-337c-57cc-b8b7-bdb6ccab4bc5 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
2407fdcb-7779-55dc-9fbe-d655365e5f78 | textbox | Date Completed:
a0fe5488-40e2-4b32-87dd-579eb14403af | checkpoint | 2.9 Backfilling
1f2cbb3b-a79d-5067-beea-2c251682f699 | note | FREQUENCY: Each Lot
7421025b-e3b0-50b4-bc55-d5a7d7696055 | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
fecb4412-4096-5eba-ac96-3ea49e326206 | note | • Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
24070a43-f982-5516-a3fb-a0d71a13ec27 | note | • Layers shall not exceed 150mm compacted depth.
b8e04fed-ae3f-58c8-8388-7493f91b9530 | note | REFERENCE DOCUMENTS: 703.29
be457c69-3ee4-5f2f-9c3c-46c05b3256ab | note | INSPECTION/TEST METHOD: Verify
4991d3b6-eb21-5c87-bbbc-80ab1b571258 | note | RECORD OF CONFORMITY: ITP Signed
5476e155-6a8d-54c9-8848-16b225b9b0c9 | note | IP
948751fe-2fd1-5612-8b3f-74f561f5d43f | note | RESPONSIBILITY: Site Engineer
acd3ce7c-8d28-5b86-a5f8-6cebce59c363 | textbox | Date Completed:
c8fd3dce-d644-4c09-ade4-0403f1d0ba1f | section | Completion
aa6022a4-e708-4fb6-980e-3775cf68f918 | checkpoint | 3.1 Survey data captured for as-built purposes
59105971-3120-5a66-a976-0e7c1dc6d6b0 | note | FREQUENCY: Completion of each lot
5f82e6a8-38a6-5532-9deb-3cec55de1d6e | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
9e7ffc66-16e7-5a27-a078-b6e389c27dc8 | note | • As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
31e698d9-5332-59f4-a556-1e0566f7dd87 | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
8362c04e-dd67-5d66-a89a-29586415b996 | note | INSPECTION/TEST METHOD: Document review
b8ebee31-a699-501a-867b-4786607a9e28 | note | RECORD OF CONFORMITY: As-built survey records
9723c27b-ae59-5555-9916-d9b6b78c6283 | note | SCP
586c03a4-8e78-52a9-98ef-d749088cf356 | note | RESPONSIBILITY: Project Engineer/ Surveyor
32b7e0ed-22db-584f-9ef5-4cc75eca7ace | textbox | Date Completed:
aefcd804-77ae-4998-93b1-e9f87eaf897e | checkpoint | Final Inspection
8230e424-aa64-5db8-a763-41eddcae6e13 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c175fb79-506e-5a6a-aca5-a2082aee7893 | textbox | Print Name:
108c8bfb-a8db-5943-b11c-8f53e426c00d | textbox | Position:
f182073d-a8e0-5385-9664-e61c937c6218 | textbox | Date:
0dcbf319-bcca-4888-a3d9-c8edfabd622b | checklist | FHC-ITP-017 - Basin Construction | itp | FHC-ITP-017 - Basin Construction
bc562df1-8218-4045-ad5b-7bf024589362 | section | Preliminary Works
7fd27e3b-2fed-4775-bce3-0b13c694ff69 | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
74a1096f-bd09-5780-a7b7-a22926c3dcb7 | note | FREQUENCY: Prior to commencing
b795f295-9607-52df-9d23-31e4ea9908da | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
5989e1bd-34bb-5f96-82eb-134e3ddfb8b1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
32ead106-2587-5a5b-824c-18d22e213051 | note | INSPECTION/TEST METHOD: Visual Inspection
32c6a526-d859-58de-9d9f-5d9549b75292 | note | RECORD OF CONFORMITY: This ITP Signed Off
751c9bb0-5c98-5676-9c5d-be90bd217e57 | note | HP*
016da6ee-7f74-5bbf-a764-6fe6bbf0c64f | note | RESPONSIBILITY: Site Engineer / Site Foreman
4d38cddd-30ab-5fd9-8c3c-910fdc2d2edc | textbox | Date Completed:
77eab2f0-7f93-4392-84de-a4108d163ac7 | checkpoint | 1.2 Implementation of all measures and controls
70952d33-3f3b-580b-896e-83286de50b29 | note | FREQUENCY: Prior to Placement
271dbff9-d9ea-5d35-89a0-1ec2ba963061 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
308f1d88-660d-5838-9286-159913b969ca | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
a2b6f971-a526-5545-9697-218ff9e7faf9 | note | INSPECTION/TEST METHOD: Visual Inspection
0917d635-6f97-59ac-92d2-832a3d9b04b6 | note | RECORD OF CONFORMITY: This ITP Signed Off
b6b28dc2-1c96-554d-86cd-6fd23c0d03d6 | note | HP*
5207d3ee-714e-56db-85bb-a182b34e12b8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
507052af-57ca-57e2-8d4f-24a4d3ab7ca5 | textbox | Date Completed:
3aeec9c6-fad2-439c-87f4-f0f6d6764b23 | checkpoint | 1.3 Excavation Permit
f8ff9905-b097-5483-bc9a-a259bfa6bf2e | note | FREQUENCY: Each lot
8c7327f4-1363-5e85-8624-82431ed888c2 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
89547524-98ca-5a67-89fb-fd2bc80b1d64 | note | • Plant and equipment shall be appropriate for the task.
1ddfcaf3-ba3b-5aaa-b8f0-7541d139c754 | note | • Excavation operations shall not disturb areas outside the limit of excavation
09b9a5de-6e2c-55ef-8d27-b33882e2619c | note | REFERENCE DOCUMENTS: Excavation permit
2df9a97a-d31e-51ac-87b7-b45c5e60c280 | note | INSPECTION/TEST METHOD: Verify
bab293a3-4978-5e8e-9f73-cad6e2d6c042 | note | RECORD OF CONFORMITY: This ITP Signed Off
b673adb9-d1b7-5094-9a28-82eddebd3dfa | note | HP*
11c30bb1-f5ff-5561-a205-918baadb2c9d | note | RESPONSIBILITY: Site Engineer
ec62bbf6-a2b2-5686-87e9-18a05fc33146 | textbox | Date Completed:
4e785177-71e4-42c0-84cb-839c39a251c7 | checkpoint | 1.4 Materials - Drainage layer
3fa77536-d3cd-5558-a2fa-27222fb96a13 | note | FREQUENCY: Each lot
f41d7981-3094-5506-b73e-bf5fa58085d9 | note | ACCEPTANCE CRITERIA: Material to be clean, Fine Gravel: 2-5mm washed screenings
f4af8bab-d6d7-588c-b4c4-524f58c8bae9 | note | • Particle distribution size: D
415918db-a8f4-5aa6-bfc0-a4ad826a98d7 | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
238691e6-b757-5dd9-8c5f-d0dd4076c210 | note | INSPECTION/TEST METHOD: Verify
a7e054dc-7e51-567d-bfbf-415e676a0cfd | note | RECORD OF CONFORMITY: This ITP Signed Off
f749d7b1-faf6-59f5-9219-331a6f69f845 | note | HP*
d8f59c4a-f24b-504d-84c0-229ff37f203b | note | RESPONSIBILITY: Site Engineer
d4ecc0ec-8c13-5cd5-a782-a21b3d2b2da6 | textbox | Date Completed:
888e54fc-9f86-4cbd-969d-31d4651e8624 | checkpoint | 1.5 Materials - Transition
64b3f25c-8f5e-5d71-bf8e-e5c96733ae10 | note | FREQUENCY: Each lot
a3aefece-fd90-542f-ba0c-010ff96bf8df | note | ACCEPTANCE CRITERIA: Material to consist of clean well graded sand containing 2% Fines.
91ffa5ba-cc64-564a-ba49-9cc50c6dc97f | note | • Particle distribution size: D
2315d2dd-28d0-55c2-9c44-82e289b84581 | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
86d77756-6c51-5177-bef8-abff2dcffd1c | note | INSPECTION/TEST METHOD: Verify
1ac35ed7-1c4e-510c-a57a-6bd679e3dd0d | note | RECORD OF CONFORMITY: This ITP Signed Off
899462a7-323a-5adf-9487-4e8385d97b1b | note | HP*
46aed25d-fabd-534e-acba-ba5c03826cb5 | note | RESPONSIBILITY: Site Engineer
784fb0eb-47fc-54a6-be8c-8c9cc95608a0 | textbox | Date Completed:
f3b98a05-3c5d-4e1b-967b-82256d1d36a0 | checkpoint | 1.6 Materials - Filter
589a5267-5a78-5509-847a-725fc4f6f7ad | note | FREQUENCY: Each lot
dacf3f78-f3cf-5110-b7d2-bb3416544074 | note | ACCEPTANCE CRITERIA: The filter media shall be a natural or amended natural soil meeting the following requirement:
cf465d1b-6a16-5d99-b4ac-7ef449090022 | note | ○ Hydraulic conductivity (ks):
421cbd8e-43cb-56c0-a906-0342fa8d2605 | note | – 180mm/hour as tested using astm F1815-06 method particle size distribution as follows:
d5a6a03e-0479-5ca9-8ef0-3fc9343f8219 | note | – Clay & silt <3% (0.05mm)
31bd51d9-b25f-52de-b6c8-4bf6a6cbab45 | note | – Very fine sand 5-30% (0.05-0.15mm)
b1e0f314-fbbd-5100-aad3-b37c8dc400f5 | note | – Fine sand 10-30% (0.15-0.25mm)
4d6f95d3-af9a-5d81-ae75-655e16e1be02 | note | – Medium to coarse sand 40-60% (0.25-1.0mm)
42dcf2db-2a56-5c71-aac9-177ec138e893 | note | – Coarse sand 7-10% (1.0-2.0mm)
82d8dd95-4fea-59a5-bf97-dd4e0ecb8d97 | note | – Fine gravel <3% (2.0-3.4mm)
ecf540bb-6fc1-510f-a1c3-3a3bd266fc4c | note | ○ Properties:
79d6ed45-7de9-582c-bb72-c188d2b92e0b | note | – Total nitrogen (tn) content <800mg/kg
8934d7af-61a7-5a36-92b9-0f4783853510 | note | – Orthophosphate (po) content <80mg/kg
54e4ed0f-c65a-5887-abdc-336b4af7788b | note | – Organic matter content - at least 3% (w/w)
b9183fdb-b777-5ca3-9a29-ab965f4658de | note | – pH: 5.5-7.5
914739f1-60e0-55c9-a9ad-14a65ed62222 | note | – EC: <1.2ds/m
a4497f23-593a-54fb-afe1-e93843595bb0 | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
5a553b57-fec9-5153-abb7-ab2e0e88b8f8 | note | INSPECTION/TEST METHOD: Verify
8f017329-ca40-54b0-a6f6-e861076050ec | note | RECORD OF CONFORMITY: This ITP Signed Off
2a5e6d8e-960c-519c-8853-b0a8223c2be6 | note | HP*
ca4c80c1-711e-5e43-a078-fff3356d212f | note | RESPONSIBILITY: Site Engineer
72c0e2c6-beac-5ddb-a1b2-ef71c0a8d9e7 | textbox | Date Completed:
2ada2d1e-c1ec-4b7a-b4ee-0388aa13e9ba | checkpoint | 1.7 Material - Rock beaching
762ab2f7-7299-56b8-9580-7acb256a0faf | note | FREQUENCY: Each lot
1418e7ac-a6c9-5120-8e35-92cec668843f | note | ACCEPTANCE CRITERIA: Larger (e.g. 400-600mm dia) placed rock
ee19f4a2-ea51-5491-8980-4b3826189c74 | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
d5d75916-782a-56dd-8f9a-1d14bd0eb55f | note | INSPECTION/TEST METHOD: Verify
33185361-018e-5137-9cce-744af72e7b8a | note | RECORD OF CONFORMITY: This ITP Signed Off
930f7a91-766a-5910-b855-a2bf973f11d6 | note | HP*
07097807-a18f-5e68-be66-fb17dd653e08 | note | RESPONSIBILITY: Site Engineer
d31509ae-b6b1-5a89-ad6d-73160ff9a0d5 | textbox | Date Completed:
b56a1dbd-b1cc-4160-86ac-53ecaf38af11 | section | Construction Works
e39cdd5c-587f-491c-9fb7-584029737711 | checkpoint | 2.1 Survey set-out
09ea05e4-1546-5bf0-83b3-45eaec4ed527 | note | FREQUENCY: Prior to Commencing Excavation
1883f40d-8b05-5661-a514-ee7212430025 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
26aee719-f775-50c5-ae1a-8429a9e693da | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
a889c6cf-98f5-5c90-8c6c-a48cfc94cb8b | note | INSPECTION/TEST METHOD: Site Inspection
896d839c-799b-50ac-b1e1-337662d642bc | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
102fc11b-6dfa-5b50-9369-5e980ea62fc8 | note | SCP
14ee2175-db54-5771-b44f-56bae65c9cef | note | RESPONSIBILITY: Site Engineer/Surveyor
be3af316-70f5-5dbe-8c83-84d96a9400c2 | textbox | Date Completed:
13caf3e8-a18e-4961-b8f0-44ec29ea48f3 | checkpoint | 2.2 In situ Material
9c453673-2bfb-5270-a1e1-d4fe410a992a | note | FREQUENCY: Initial
a7c70936-bd3d-52d7-9f94-d41bd25f512a | note | ACCEPTANCE CRITERIA: In situ material ripped and re-compacted to provide a smooth, stable working surface. Material to be free of debris, roots, sticks and sharp rocks/ boulders larger than 50mm
2a360b95-0e18-54f3-ba21-c18f3b76964f | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0021
cfbcb7d8-3c8c-5d20-922b-0c6fa9a8ae14 | note | INSPECTION/TEST METHOD: Visual Inspection
e2fb2557-d13e-5131-99a4-9ae563e98842 | note | RECORD OF CONFORMITY: This ITP Signed Off
fb821fcd-0fc3-5432-8102-92fae3d32955 | note | IP
a9554dd5-6751-538f-9945-352ef54eb6d3 | note | RESPONSIBILITY: Site Engineer
3dc3124f-3b70-525b-826e-5c8a1660072e | textbox | Date Completed:
192d1181-2e8c-401c-a855-e3df26e44594 | checkpoint | 2.3 Bentofix GCL Installation
b55cc56d-dd21-58fe-9537-329cd8698b59 | note | FREQUENCY: Prior to compaction of natural subgrade
aa99b18a-e2b0-5751-90ea-b0c9c6744bd7 | note | ACCEPTANCE CRITERIA: Geotextile clay liner (GCL) shall be installed in accordancewith the manufacturer's requirements.
ce693728-ff69-57af-9c5f-9a0caba4371c | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0021
1f9700ef-3cad-597b-9d20-cad1b69168da | note | INSPECTION/TEST METHOD: Visual Inspection
0f6b362b-871a-5619-baf2-64449d567acd | note | RECORD OF CONFORMITY: This ITP Signed Off
7c700871-e82f-5aa9-9b3c-3b221a271fe3 | note | IP
0bdb0257-c98f-5e0f-993a-779a1e8ab2a7 | note | RESPONSIBILITY: Site Engineer
2f96bcbe-ac9b-5778-ad36-541091818200 | textbox | Date Completed:
0c0478e1-a6c2-4aaf-86a6-7f4bab8dcec0 | checkpoint | 2.4 Installation of Peforated Pipe
84644335-b975-57b5-964c-1372a85a4577 | note | FREQUENCY: Once GCL has been installed
05bcafca-95bf-5d94-8b24-8ee20673861f | note | ACCEPTANCE CRITERIA: Contractor to install 150mm DIA uPVC perforated pipe as per the manufacturers specifications.
d7f78974-d18e-5ebe-8168-d1309eb0d3d8 | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0021
7d4b8b89-308a-5a8c-afdc-9dea1f38208d | note | INSPECTION/TEST METHOD: Visual Inspection
cf886f7f-48a2-596e-a097-20364845db1f | note | RECORD OF CONFORMITY: This ITP Signed Off
15f9c9f9-ab8f-57ea-8e0b-1568ed0dc402 | note | IP
ce674895-0ea4-5eda-9509-065d44d52811 | note | RESPONSIBILITY: Site Engineer / Site Foreman
399a66db-3265-5e60-9e26-f9ea386333e0 | textbox | Date Completed:
530aef08-88ad-45c4-973e-a44f2905b3fa | checkpoint | 2.5 Drainage layer
eca87c44-d539-517c-8fba-9126a96796ff | note | FREQUENCY: Once perforated pipe has been installed
c596a826-31a4-5422-9bb8-553527cac964 | note | ACCEPTANCE CRITERIA: Material to be clean, fine gravel of 2=5mm washes screenings.
4176fc80-30e3-5a77-9bc6-635b0be023c9 | note | • Install layer to 150mm thick as per the detail.
a9122726-33e7-5a5a-9830-4a810b5a993b | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0021
4e617691-365b-532e-a329-07482e974954 | note | INSPECTION/TEST METHOD: Visual Inspection
25985257-415c-583a-8151-24b5f6e1b53d | note | RECORD OF CONFORMITY: This ITP Signed Off
7b2f0c69-e712-55e9-a956-3c8f13180867 | note | IP
7685eff2-7e8f-5cf8-ac9a-2116eed76ec2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
4f33c88a-16a9-525b-918f-019bd3f9e1e2 | textbox | Date Completed:
3bb16edc-6439-448c-8a25-dc1eab57ef71 | checkpoint | 2.6 Transition layer
c0fe3148-bc6d-50ea-a595-1d18c902da8f | note | FREQUENCY: Once drainage layer has been installed
e8a67b5d-a3de-50b7-86cd-c8ef77add1b7 | note | ACCEPTANCE CRITERIA: Material to consist of clean well graded sand containing 2% fines.
110d76be-77c9-5572-a23d-4669ee48ee44 | note | • Install layer to 100mm thick as per the detail.
7cf31f9e-4838-5e8b-a159-7851b8b2b8e9 | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0021
f25beef8-3e2c-5b0f-be66-2e8b31dfe8ce | note | INSPECTION/TEST METHOD: Visual Inspection
8b08984c-a299-500a-ae08-7d0554c2df0f | note | RECORD OF CONFORMITY: This ITP Signed Off
9270c7b9-1214-5279-81b0-360d362aba73 | note | IP
2796e60f-a051-5ee6-8193-a0d1c0569142 | note | RESPONSIBILITY: Site Engineer / Site Foreman
d20aca5f-405b-5467-b67a-752db682c91a | textbox | Date Completed:
5e6a4315-3cab-49c4-8bdf-bd2fa2d2416f | checkpoint | 2.7 Rock Beaching
f0276d75-4e28-54e5-bd63-de1c96813555 | note | FREQUENCY: Once transition layer has been installed
2d0a932e-4f56-5a95-b34f-1bc9a1a882b8 | note | ACCEPTANCE CRITERIA: Install a 300mm rock beaching and lightly compacted with a single pass of a vibrating plate as per detail.
fc165ad7-81d5-54b0-9d89-82a74cb88940 | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0022
de7cf1b8-cfbc-5eee-b9e9-cd46fb115261 | note | INSPECTION/TEST METHOD: Visual Inspection
a9511bc7-e0f3-5e84-8a9c-cad1b0198d20 | note | RECORD OF CONFORMITY: This ITP Signed Off
219314ba-3c68-5dce-bddf-39721e4da681 | note | IP
56808a30-39fb-50f6-9d11-8579c02de331 | note | RESPONSIBILITY: Site Engineer / Site Foreman
99eb975e-2582-5d5e-b34e-bacea19765fb | textbox | Date Completed:
2047f4c5-cbe8-4055-b1ed-d742d0073703 | checkpoint | 2.8 Filter layer
99c3379b-60a1-5de1-b4e0-7104113aaa17 | note | FREQUENCY: Once transition layer has been installed
56310fac-b5bc-52fb-8816-0826695c9661 | note | ACCEPTANCE CRITERIA: Filter media to be a natural or amended natural soil.
407e71fe-4c49-5a20-8dab-2b3d033abf04 | note | • Install layer to 300mm thick as per the detail.
6d27dfe7-b56c-58d6-97bb-027d22ed4f13 | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0022
4e9ea023-f228-5a19-a111-c9c38aa66d8b | note | INSPECTION/TEST METHOD: Visual Inspection
d775ee73-2ef9-583f-a31b-10dec7f4974d | note | RECORD OF CONFORMITY: This ITP Signed Off
4e89edbe-9d92-51eb-aac8-43e571f709d4 | note | IP
2fabcc6d-6155-54b1-a0c5-95f5b83e449d | note | RESPONSIBILITY: Site Engineer / Site Foreman
16e40774-ec6e-5e2f-8bdf-e2b67bd1a637 | textbox | Date Completed:
10754ca1-1076-4e06-965c-4c86fa09fe55 | checkpoint | 2.9 Type A and Bunker Rock Bund
d6d23046-e8b8-526d-b457-4510127b1890 | note | FREQUENCY: Once filter media has been installed
29c0a3c8-abcd-5fdc-b392-2edc6fc79f55 | note | ACCEPTANCE CRITERIA: Install 100mm type-A capping for the bund base. Once compacted, install 75mm - 150mm bunker rock.
2ef1e212-2ab5-590e-bd20-320fb92ffb47 | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0022
6e393bac-7dfa-505d-9be7-ff26fec64107 | note | INSPECTION/TEST METHOD: Visual Inspection
06d30826-e19b-567a-a84e-adcef4bcf277 | note | RECORD OF CONFORMITY: This ITP Signed Off
ab110a64-fad4-55d0-a2ff-43afc26d0941 | note | IP
4cfeb2c2-b62a-59aa-a52c-55ccfd0f59b9 | note | RESPONSIBILITY: Site Engineer / Site Foreman
93fe9e57-0d8e-5f11-8da1-479be34c4469 | textbox | Date Completed:
cd257e22-d7b5-40af-b561-c5cc9ec2ef44 | section | Completion
b3333cf5-b190-464a-a169-44efdcdf8c49 | checkpoint | 3.1 Survey conformance
c09f8775-1641-5612-a83e-0441d402d304 | note | FREQUENCY: Each Layer
79d73312-7b2a-5586-88b1-f35df2442aad | note | ACCEPTANCE CRITERIA: Base layer of basin and top layer of batter to achieve specified finished surface level as per detail.
648926b9-156e-598c-9b6f-1b8ac5624d12 | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0022
b972b4df-a984-5667-aaee-619fa16eefb4 | note | INSPECTION/TEST METHOD: Site Inspection
d21a6871-2ba8-5e20-9843-af77bc738134 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
4337a724-5a6e-5c0d-ad7d-c1871a444307 | note | SCP
cf39f104-755e-59b2-aae5-f3352640cc4d | note | RESPONSIBILITY: Site Engineer/ Surveyor
1f7f8e64-f545-56a0-bd26-8b44c235534b | textbox | Date Completed:
6e1bdde0-1b55-4b81-a85c-fd5e450836fd | checkpoint | Final Inspection
ec2fa760-96bb-535f-8e63-659f6900b502 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4bf15ca4-ca8c-5b65-b4ac-531b4348d08a | textbox | Print Name:
80cab1b1-cc38-58de-ae60-dee7258d8a8c | textbox | Position:
1bfd6627-13c1-5fb7-93b4-9c56d997bdad | textbox | Date:
574924dc-c1bf-48d6-9149-7ec5762638ed | checklist | FHC-ITP-018 - General Landscaping Rev0 | itp | FHC-ITP-018 - General Landscaping Rev0
ffc3ec43-5b67-4390-93e2-ea993979b200 | section | 1 - Preliminary Works
2d6cba01-0d7b-4cf3-b4cc-95c088ced77c | checkpoint | 1.1 Check for correct documentation
c72aa6e4-0003-5772-8b68-0ea69ac4d380 | note | FREQUENCY: Prior to commencing any activity
61df1e6f-4274-5125-90e3-408f6ee7067f | note | – – – – – – – – –
d86ba81a-154e-555e-8429-8fa1f4057282 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ebc65b60-ed26-5469-9bf8-92400ca97ac6 | note | – using the correct and complete set of drawings
df6b7a11-871b-5ab7-b875-5d846ccb9111 | note | – all drawings are the latest revision
0c1586bf-b853-5194-a628-a45db046934a | note | – – – – – – – – –
d045d294-0454-51de-bd32-0e6170cb21b0 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
5ade7e1f-94a1-59a9-83dd-e9818f7151c8 | note | – – – – – – – – –
7059a5b1-3230-5f87-9d0c-2e7917eb05ec | note | INSPECTION/TEST METHOD: Visual inspection
8e1d9310-6c37-5876-81c3-0d58acbcdb47 | note | – – – – – – – – –
5b5e5a73-ee4d-5b76-9e39-a06b0b8603ec | note | RECORD OF CONFORMITY: This ITP signed off
b0afe5e7-a488-57fa-9dee-0e1026af2de3 | note | – – – – – – – – –
69c03537-b521-5380-af5f-6454a49462de | note | HP*
16cbbd2d-bb13-55d3-9e84-ad061f9f0410 | note | – – – – – – – – –
92770712-e90c-550f-bb19-48a1d6146781 | note | RESPONSIBILITY: Site Engineer / Site Foreman
50df6604-4956-5e6a-a9c5-51e8cf1fa17b | note | – – – – – – – – –
20a97677-359c-54b6-a0c9-80253f08ab90 | textbox | DATE:
20eb51ee-5d77-4069-941a-a0f1804c9b11 | checkpoint | 1.2 Implementation of all measures and controls
d70b90d4-d137-5b1a-9ca1-21ffd36bdb50 | note | FREQUENCY: Prior to commencing any activity
859ec043-a813-5a98-be30-5f7da0623721 | note | – – – – – – – – –
0cc6f63e-44bd-5b55-a745-35f01a9ea3a2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP
6dd744dc-231b-5067-ab0f-de844b4020cb | note | – – – – – – – – –
8080897b-a0f2-509a-bb17-f32a2ea64a5d | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP
c2521533-3acd-5717-81e3-443df7a321e7 | note | – – – – – – – – –
031adf05-4e12-51a0-9dea-7403e7a0090d | note | INSPECTION/TEST METHOD: Visual Inspection
a57daea3-548e-5593-8d3d-adbcf99ccac6 | note | – – – – – – – – –
3aae1d3f-2c9f-5f50-b2ef-4f1577a15d7c | note | RECORD OF CONFORMITY: This ITP signed off
9d94e884-ab0d-59e1-b3f7-e0827c877912 | note | – – – – – – – – –
b6951bcc-1497-5797-9645-5ffff17d646f | note | HP*
3dd2777b-f217-5d63-9965-7d755a79775b | note | – – – – – – – – –
ba7d1b0f-a60f-5427-945a-947fad718457 | note | RESPONSIBILITY: Site Engineer / Site Foreman
39be91e4-eb72-564e-ab9d-0e9330ed608f | note | – – – – – – – – –
070208ad-909d-53a8-825f-65e74f474b1e | textbox | DATE:
fe7d0a06-511c-40ae-9164-0c052730acff | checkpoint | 1.3 Submissions and Records
b8a8f3f0-02f1-58d3-9629-ebab07fbc525 | note | FREQUENCY: Prior to commencing any activity
cffcfb94-56bd-5b02-a4a8-b2ba248de777 | note | – – – – – – – – –
4aaa6ca0-19e5-5114-8a28-a28b39291d06 | note | ACCEPTANCE CRITERIA: The specified inspections, samples, records and certificates shall be made available or submitted to the Superintendent for acceptance prior to the commencement of associated work.
57ca1494-97d3-5c47-a8d7-ea617230a019 | note | – – – – – – – – –
bd254b44-eaa1-5bc7-81e9-a0abbbd52d36 | note | REFERENCE DOCUMENTS: 720.03
0406bd69-2324-5b4b-b320-db6b67a026f8 | note | – – – – – – – – –
739980e8-45d0-5d96-a0bc-6a1a62fa5191 | note | INSPECTION/TEST METHOD: Visual Inspection
438e83aa-8205-56d3-8f34-603f25180082 | note | – – – – – – – – –
e1d2d014-2968-56c0-8733-913664a69818 | note | RECORD OF CONFORMITY: This ITP signed off
56bf0dc1-abd2-5ecb-aa8f-b94dbd8dde02 | note | – – – – – – – – –
2b82d34d-d56b-592d-be67-7ebce4df730a | note | HP*
c8692a4d-e67d-58b9-984b-1e26e42fa080 | note | – – – – – – – – –
1b920ebf-0e6b-566e-b6eb-c98fa689710f | note | RESPONSIBILITY: Site Engineer / Site Foreman
0537540c-2dd5-56b7-9869-d679e75b0b38 | note | – – – – – – – – –
a3619172-688c-57a8-93e3-b1d035214f37 | textbox | DATE:
92e9aaa2-458a-4e77-b7b1-32d6288c46b9 | checkpoint | 1.4 Permits
7909bc16-8c1c-5af9-9e81-92b8a95ca061 | note | FREQUENCY: Prior to commencing any activity
ee0196c4-ba3f-50b0-b35e-27205a51db41 | note | – – – – – – – – –
aa81f637-73bc-5232-baec-691aaf4ef3ee | note | ACCEPTANCE CRITERIA: The Contractor shall obtain all necessary permits and obtain approval from the Superintendent prior to the pruning or removal of local native vegetation.
435327ce-3d9d-57cd-9aa9-a7c5e7d9369f | note | – – – – – – – – –
8c5178c0-1305-5784-96f2-20f47e515328 | note | INSPECTION/TEST METHOD: Visual Inspection
87a50bb6-c2ce-5163-9960-c24b0891102c | note | – – – – – – – – –
c51c84be-c6e0-5934-960d-23c979be2173 | note | RECORD OF CONFORMITY: This ITP signed off
7d77d378-0248-5030-bbed-be4754a7b7eb | note | – – – – – – – – –
dd5f6e0c-ea2f-58f8-93f8-24c5e1d6f500 | note | HP*
eaed4a62-2d4e-591f-8f17-41f344a1ee12 | note | – – – – – – – – –
41c8496f-0c92-5a0c-bf5c-199b7bb835f3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
67a2c95f-c965-5734-a72b-690ff1e11da8 | note | – – – – – – – – –
fbac8fe6-b3ee-582f-b42c-bbea2fd43cc8 | textbox | DATE:
117af9d9-ffc5-4339-a639-e34b6feaf715 | section | 2 - Construction Works
3faca5f0-41ca-4538-85c9-625f339edf8c | checkpoint | 2.1 Excavation Permit
15b196e3-7428-544b-8364-59846bb244ad | note | FREQUENCY: Each lot
618c5713-6350-59bd-9533-1c80b26cec1a | note | – – – – – – – – –
f330304b-2736-5a7d-aed8-f1ba8edc8956 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
4e6d6606-743e-5959-9467-828429ea3169 | note | • Plant and equipment shall be appropriate for the task.
8c6a0040-47e0-502f-8667-0645721c0d2a | note | • Excavation operations shall not disturb areas outside the limit of excavation
65fa96e0-9b43-5fe3-b3d3-7f031d636588 | note | – – – – – – – – –
4a2d0611-5fa3-5a35-9064-9bbfc459b7cf | note | REFERENCE DOCUMENTS: Excavation permit
20ad4c0f-05dd-5f98-b3c0-20685f5cb22f | note | – – – – – – – – –
3bf04c38-dbfc-5c7f-8606-bdd21a40c72f | note | INSPECTION/TEST METHOD: Verify
19b3213f-35e9-5b09-b0f7-9157fdd5b910 | note | – – – – – – – – –
06123328-dc6c-536d-a35d-07e1e7058d34 | note | RECORD OF CONFORMITY: This ITP Signed Off
be0c5dbb-54a7-5215-9aa9-b189e1565ab3 | note | – – – – – – – – –
62b21720-1617-5271-8672-fcd4b7cad452 | note | HP*
43d91d01-de90-5c85-8e4e-0c34cba2930a | note | – – – – – – – – –
d919ae95-958a-5d8f-bc1a-d9a01de8651e | note | RESPONSIBILITY: Site Engineer
d60aeaae-5e7a-5f3a-9508-7125ba752fc7 | note | – – – – – – – – –
f4aa8e84-e005-57bb-85b3-b6e29fb304ad | textbox | DATE:
855f5511-0804-4961-bab3-cfca8ba7f28f | checkpoint | 2.2 Setting out of landscape softworks
8d91355d-2680-5ac7-9f99-c80b51297151 | note | FREQUENCY: Each lot
a207dcf3-3156-597b-b937-150c4850f7d2 | note | – – – – – – – – –
d651c629-ebef-5825-bca6-e24779559ceb | note | ACCEPTANCE CRITERIA: The Contractor shall set out the location and shape of planting areas in accordance with the Landscape Drawings.
d0826ec7-8336-5063-921f-e2dc9a0c2178 | note | – – – – – – – – –
423cee8b-9f69-55c2-ae0a-d0fc4fea4ede | note | REFERENCE DOCUMENTS: 720.06
dab8cbb7-50aa-5ad1-a103-07a0cb4f48ae | note | – – – – – – – – –
a5bc6da7-4f1f-5000-890d-bf6a498628ed | note | INSPECTION/TEST METHOD: Visual Inspection
93211a78-54db-5ac6-853d-bedc221bc58f | note | – – – – – – – – –
bb18ebea-a877-5409-bf16-0025c591cb04 | note | RECORD OF CONFORMITY: This ITP signed off
c91a93fc-5284-5bca-a9ac-ebe16b24339a | note | – – – – – – – – –
23adf30b-09c0-5196-9286-2058a456a502 | note | HP*
dc7c0b54-0a30-515f-89b1-832f5d9a58ef | note | – – – – – – – – –
45f9c477-cb67-5ae4-9f91-c21992ad01fa | note | RESPONSIBILITY: Site Engineer / Site Foreman
e978f556-ed34-57bf-82dd-e5c52a1b0372 | note | – – – – – – – – –
97c1b7eb-cb53-5db2-a45e-f430739db233 | textbox | DATE:
49dce8d1-86e6-4dd5-bc82-9206c745e2f0 | checkpoint | 2.3 Supply of Materials
e4838034-e3af-5dfb-94ad-3998b1d66694 | note | FREQUENCY: Each Lot
4eff42af-83f9-500d-a1ec-58445ac89ca4 | note | – – – – – – – – –
3f94ebd0-728a-54a5-9716-852c61ffb68b | note | ACCEPTANCE CRITERIA: All materials shall be supplied by the Contractor unless otherwise noted. If any materials are supplied by VicRoads, a joint inspection of the materials shall be made by the Contractor and the Superintendent following delivery of the materials to the site. The materials, if satisfactory, shall thereafter become the responsibility of the Contractor.
c54693bb-d4df-59fe-8727-1892ec5b1594 | note | – – – – – – – – –
23956d1f-e550-5292-a4ab-818991f4fa7c | note | REFERENCE DOCUMENTS: 720.04
65d7bc6e-6723-5947-8845-1097e7ab7b29 | note | – – – – – – – – –
a5c4a83d-e827-5f82-a867-274108778934 | note | INSPECTION/TEST METHOD: Visual Inspection
6f817c9c-6509-5bc7-86ec-5230ac9b3c94 | note | – – – – – – – – –
763d8c90-3df4-51b8-9c94-04c0153d8a46 | note | RECORD OF CONFORMITY: This ITP signed off
39b028de-ad8e-5ff7-a66d-da67306ee602 | note | – – – – – – – – –
0d74fc1a-7d11-5feb-b6ac-fe15c7cb149d | note | WP
2c7ab8f9-d8a9-58c2-ae68-6a4760a4aef4 | note | – – – – – – – – –
b2f1b7ab-4c14-5154-9660-3fd2e44e48da | note | RESPONSIBILITY: Site Engineer/ Superintendent
e0adb894-6222-55a8-aa08-cc7f8b4557b0 | note | – – – – – – – – –
0618f667-c0d6-5fa9-8a20-c3a7fab3e8df | textbox | DATE:
bdf735e1-17b8-45e4-970b-2112e62d8522 | checkpoint | 2.4 Pest and Weed Control
f7fe1b3c-1e7a-5692-a51c-408d60697902 | note | FREQUENCY: Each Lot
a20ed104-73b3-55af-bece-300876b9134e | note | – – – – – – – – –
22cd9bf2-1c9e-538f-9635-6342ff3d4382 | note | ACCEPTANCE CRITERIA: Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing. Weed control shall be programmed and implemented to deplete the potential weed seed bank within the topsoil to be used in planting beds.
148febda-0173-5bb2-9b3f-ae0a5380bbfb | note | – – – – – – – – –
104e134a-d479-5945-83e6-d36ae1a34f6a | note | REFERENCE DOCUMENTS: 720.05
5ac7df82-9f72-537f-a7ca-a23d37e832d2 | note | – – – – – – – – –
a1b1e9c8-4aac-565e-82ab-db757a364a18 | note | INSPECTION/TEST METHOD: Visual Inspection
18b70029-8a32-5007-bfac-de522c9dfa42 | note | – – – – – – – – –
8fa4d0c3-e9f3-52ca-bf1c-78db77226e51 | note | RECORD OF CONFORMITY: This ITP signed off
a565b3b1-950c-5cd2-b8d9-c449f4e971b8 | note | – – – – – – – – –
d9d8f171-1854-5363-b3c2-43a519ac2dd3 | note | HP*
6463b269-af8c-523c-b24f-d194b37c3ce4 | note | – – – – – – – – –
674dece2-b29f-5c2f-878f-5a73c0fb0c3c | note | RESPONSIBILITY: Site Engineer / Site Foreman
71608b4b-e105-51cf-83bc-5a5939207201 | note | – – – – – – – – –
99161fa7-e772-55a6-b3a2-7ee0aea0691e | textbox | DATE:
b102ee14-6dad-4d59-acdb-e3dea0be9909 | checkpoint | 2.4 Fertilisers
f8d8bdca-08a2-5c97-b9a5-8d3dfdb4e060 | note | FREQUENCY: Each Lot
c2593ef0-59e5-560d-a9e6-5dbb461ebbe4 | note | – – – – – – – – –
861e4a45-fb14-5935-85df-565e0918b30b | note | ACCEPTANCE CRITERIA: Fertilisers for planting areas and advanced trees shall be slow release with a 9‑12 month release period and suitable for the establishment of plant types, sizes and species specified in the plant schedule(s).
c076d51b-8a5e-524d-a7c0-be3d29d8467f | note | – – – – – – – – –
c89b9147-7061-5888-b401-88f8466b2b09 | note | REFERENCE DOCUMENTS: 720.04(f)
0b846bb3-8df7-5c1a-a04d-020e606aedbe | note | – – – – – – – – –
0a931ae9-8ff7-59ca-bb9f-8769e986d57b | note | INSPECTION/TEST METHOD: Visual Inspection
6a8df964-3f14-54ba-a8f7-f8fb4e513d1a | note | – – – – – – – – –
3dd1af7e-af35-5ae2-b2a4-5e5a2c97c85b | note | RECORD OF CONFORMITY: This ITP signed off
ed369e64-b62e-5994-906f-25656ecf1b45 | note | – – – – – – – – –
0a10ce69-352b-5eda-9ed5-3c658589bbca | note | IP
8c93ca4a-048a-57e6-8c81-64877d9bd2e1 | note | – – – – – – – – –
b51d2f8e-7ba0-5201-bf45-d11cf510480b | note | RESPONSIBILITY: Site Engineer / Site Foreman
81ed9887-bcbe-5939-aa78-3a52662645c0 | note | – – – – – – – – –
472a1b8d-e6d1-5793-b57f-0ad2113cff4e | textbox | DATE:
25964dec-1235-4938-8bc3-c6c263da783a | checkpoint | 2.5 Mulch
5853e784-5e9c-54fc-8d6c-c23b808488f4 | note | FREQUENCY: Each Lot
315991fa-7a19-520f-abb4-37b8861c5790 | note | – – – – – – – – –
4a192cd9-253a-5dd9-a862-f288f8ddafa9 | note | ACCEPTANCE CRITERIA: All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454.
5b0932e1-2d87-5bb5-a6f2-ee26f9a74bd0 | note | – – – – – – – – –
f7c5763e-e238-53a8-8b1f-95c96f157ce3 | note | REFERENCE DOCUMENTS: 720.04(h) AS4454
7ae54efb-ebe9-5d11-8c7a-3a4e680a3d78 | note | – – – – – – – – –
cd27c4aa-4d08-5408-9362-58113abbcdb7 | note | INSPECTION/TEST METHOD: Visual Inspection
fb33de8b-b8c9-59fa-8189-c2b4f0bbabc3 | note | – – – – – – – – –
afa91c9e-e231-54fc-9b74-2127267da837 | note | RECORD OF CONFORMITY: This ITP signed off
04484afe-871b-5a36-8fc8-1cee510373ed | note | – – – – – – – – –
32032168-5eef-59a2-a8f0-7fe91f89a89a | note | WP
b0988194-28dd-576c-b70f-76e62071587f | note | – – – – – – – – –
e05b1ef2-a6fc-5392-bf9d-9e9ec62784c2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
6c67b22e-93a1-56bb-af6e-7005844cd4ca | note | – – – – – – – – –
57290c94-11c7-583d-89cd-16e92cddaba7 | textbox | DATE:
de224b49-2956-4929-b31c-0c963c1677bd | checkpoint | 2.6 Weed Control Mat and Erosion Control Mat
0f404eab-abe0-5167-a7f6-557f2c0c0bdf | note | FREQUENCY: Each Lot
829bdea9-81fe-593d-bbb7-4edddca04163 | note | – – – – – – – – –
d74a0753-e053-55cf-a0c1-ad71286b3df6 | note | ACCEPTANCE CRITERIA: The Contractor shall supply and install jute or approved equivalent, biodegradable, fire retardant weed and erosion control mat as indicated on the Drawings or as specified. Weed Control Mat shall be minimum 700 grams per square metre and Erosion Control Mat shall be 300 grams per square metre. The surface of the mat shall permit water infiltration.
0d73ea58-bb28-5563-a52d-d8faa54aa61b | note | – – – – – – – – –
1c59019c-78b0-59be-ab6f-c0fdb3c59485 | note | REFERENCE DOCUMENTS: 720.04(i)
12ebbf0d-94f2-5d3b-925a-e7fc45cd77fa | note | – – – – – – – – –
af298aa3-cce9-5b3e-abf2-e85099c24728 | note | INSPECTION/TEST METHOD: Visual Inspection
606705b5-5427-54b9-8295-1b207a69dbe0 | note | – – – – – – – – –
f88150f3-b09a-5bad-b080-b1dc932dc914 | note | RECORD OF CONFORMITY: This ITP signed off
abaa99b8-17ff-5092-b488-bc381f7c9529 | note | – – – – – – – – –
7205afe5-036d-5465-afff-69ad1f53333e | note | IP
64e902d1-e8a2-53d6-9ce4-860032e05517 | note | – – – – – – – – –
fbd851d6-3eed-5bb7-a013-87b849ecef7b | note | RESPONSIBILITY: Site Engineer / Site Foreman
bde738b2-dd9b-533a-a585-80fa140130fd | note | – – – – – – – – –
53c5f98d-efc1-5334-981f-90ef09b7e3df | textbox | DATE:
6e61ada0-30a9-406e-bb5a-fad61e1e9316 | checkpoint | 2.7 Ripping
03cff12e-c522-55c0-ad50-343efdb5a8fb | note | FREQUENCY: Each Lot
b28235d7-b272-53a9-9121-30a77c0c1db1 | note | – – – – – – – – –
1b8206bf-2398-57cf-8008-9779f7cb4a08 | note | ACCEPTANCE CRITERIA: The Contractor shall make available each ripped planting area, individual tree planting and grassing area prior to mulching, planting or grassing. The Contractor shall not proceed until the Superintendent acknowledges requirements for ripping have been met. In areas where ripping is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
e53f7c46-b0a4-51cd-bec5-c62a362dd09e | note | – – – – – – – – –
303d5315-11d9-533b-b759-f2b67acf8933 | note | REFERENCE DOCUMENTS: 720.07 (b)
87ea9ec9-1f0e-5437-9852-6a2bc372020f | note | – – – – – – – – –
1a7c5606-372d-5a11-a562-b25e7668f423 | note | INSPECTION/TEST METHOD: Visual inspection
cf895de6-f1e4-57a2-9cc4-fb34b58f0a1e | note | – – – – – – – – –
4ccd0b07-3b33-55cd-b6ea-7ceba2f49d8f | note | RECORD OF CONFORMITY: This ITP signed off
cd9fcc15-f1ad-5c51-a492-f1078d15f912 | note | – – – – – – – – –
208a0f51-d28a-5837-a4fa-0fc07f62bd27 | note | HP
483e9935-7ab7-5b65-b922-ed20438ae07f | note | – – – – – – – – –
d803aa47-d657-57b5-bf5c-6b73738f481c | note | RESPONSIBILITY: Site Engineer/Superintendent
8539d4a8-c770-5c26-b67f-833eb5ba299d | note | – – – – – – – – –
22ee57f5-6095-5f03-8baa-52c37407493e | textbox | DATE:
8a9e626d-c673-4a09-84d2-4c92aa647409 | signoff | AUTHORITY HOLDPOINT
820c357c-5b66-4603-88e1-669b4923dafb | checkpoint | 2.8 Topsoil Finished Surface Levels
73ddc579-a672-550b-aacb-403659d3223e | note | FREQUENCY: Each Lot
2bfb3912-fe57-527d-bc47-9896744f4330 | note | – – – – – – – – –
2399b264-b5e8-5da7-8c8b-baeb30eed496 | note | ACCEPTANCE CRITERIA: The Contractor shall make available each ripped, topsoiled and cultivated planting area, individual tree planting and grassing area prior to mulching, planting or grassing. The Contractor shall not proceed until the Superintendent acknowledges requirements for topsoiling and cultivation have been met. In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
1d708eb6-3454-5ddf-b473-fae965aa59ea | note | – – – – – – – – –
cde0f8dc-7c65-5504-849f-25346ff996e3 | note | REFERENCE DOCUMENTS: 720.07 (e)
c7080357-384b-5c5d-a620-2ef3bfec8527 | note | – – – – – – – – –
07f4dbc1-9a4d-52e8-acd7-bf9c15216f7c | note | INSPECTION/TEST METHOD: Visual inspection
3ab1ae68-60d1-54f2-a89c-944c77c0f73e | note | – – – – – – – – –
568f7a82-385b-54e1-a9ed-b0a3b8131c96 | note | RECORD OF CONFORMITY: This ITP signed off
f9177c66-b7b9-52a1-a5f6-97a7bcea220a | note | – – – – – – – – –
69b9d21b-4532-53b4-b5de-a5cae370bcc7 | note | HP
33835dd8-b7c7-5a72-9683-6e56cafa97a9 | note | – – – – – – – – –
17d33b51-d70d-5c77-a7ed-c724bf2518fe | note | RESPONSIBILITY: Site Engineer/Superintendent
eb88eef6-e022-5b84-8b46-b25e7c581ce4 | note | – – – – – – – – –
ccc6ecf2-e43c-5397-b5d7-022aba9ba573 | textbox | DATE:
13c26f32-f804-4d82-8732-46a2ca4fa3d5 | signoff | AUTHORITY HOLDPOINT
c126bfc3-7d87-497d-9cab-0867843916f5 | checkpoint | Final Inspection
e271a09e-0eed-512a-8af4-7666265b612e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
267edaab-e6fc-561c-8477-f53d211d5971 | textbox | Print Name:
7230f729-853a-5a6c-95e0-e7623b612b8c | textbox | Position:
6c8ca7dd-9efd-5cd5-8b84-3889b40f5d4d | textbox | Date:
be52b47a-7df4-4273-aed0-3efdbd241959 | checklist | FHC-ITP-021 - Type B Fill Placement Rev3 |  | FHC-ITP-021 - Type B Fill Placement Rev3
da1e0983-b407-42f3-bbfe-8ae3acf98c19 | section | Preliminary Works
443728c9-f2a8-4b48-9608-ff5fe6ad620d | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
2df7392b-f42a-5a8e-b208-2f8b772ff1d7 | note | FREQUENCY: Prior to commencing
c9268c01-a270-56c4-9453-3af108b041c4 | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
aa2a3511-cbb1-5f0f-9a20-63336957dddd | note | REFERENCE DOCUMENTS: Drawings and drawing registers
60ca952a-210c-5f90-81ee-ea9d72e57031 | note | INSPECTION/TEST METHOD: Visual Inspection
52cbb7f7-39c8-51ea-bb40-09555690d760 | note | RECORD OF CONFORMITY: This ITP Signed Off
8b18d46c-9db3-55b2-9483-0ecdc08d351c | note | HP*
ee2976c9-5253-56dd-9691-6bb06b5cdd1c | note | RESPONSIBILITY: Site Engineer / Site Foreman
be8e1e70-521f-5f86-b43d-12147f2d7752 | textbox | Date Completed:
608cf78c-6320-4601-98a3-64b43972fc33 | checkpoint | 1.2 Implementation of all measures and controls
3c93c7c9-20e3-5c81-bce9-8dd5d968d9f0 | note | FREQUENCY: Prior to Placement/ Each Lot
2a19e08e-60b2-5065-a6a6-b8aa8071b150 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
f79615f8-b85e-552c-9d06-cb6d520310a9 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS, WP001.02
e064bde0-08c2-519d-8c53-26745c5f65b8 | note | INSPECTION/TEST METHOD: Visual Inspection
5a94d709-636c-5393-99ba-648fe452c9cf | note | RECORD OF CONFORMITY: This ITP Signed Off
b0e331f3-262c-5265-837d-330792a1c9c9 | note | HP*
c11e17eb-d883-552e-9339-01af5ff86697 | note | RESPONSIBILITY: Site Engineer / Site Foreman
7e8aa8fa-4a5b-5402-bc67-6b9eca6e8730 | textbox | Date Completed:
5c5e856c-b327-4eb4-a535-7b95bbc613ff | checkpoint | 1.3 Verify Material
12a7c730-b12b-5185-a239-99da76d2c0bd | note | FREQUENCY: Prior to Placement/ Each Lot
d9da775b-5236-5e3f-81b2-6db6fe133501 | note | ACCEPTANCE CRITERIA: Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.
8a4975bf-4982-56bf-bb1a-f821856e0996 | note | • Materials that exhibit swells greater than or equal to 2.5% shall be classified as expansive and shall only be used as Type B material if approved by the Superintendent.
cfa22f5b-59b9-575e-91e1-ce5b2cf988e0 | note | • Material within the top 400 mm of top of Type B material shall have a swell less than 2.5%. Materials that exhibit swells of 5% or greater are not permitted.
68d3d0e3-273a-54ba-a1a0-7329dcaeedfb | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
0acaca54-156e-5ee5-a384-4a54a0aeff6f | note | INSPECTION/TEST METHOD: Site Inspection
dca6eacf-e8c4-5a38-8c33-7ff852629fd3 | note | RECORD OF CONFORMITY: Test Record (If silt is observed)
d03717ae-a6e1-5867-a227-944ec2d87bd9 | note | HP*
a50380cf-92e2-5363-8863-bbbeb04f4d1d | note | RESPONSIBILITY: Site Engineer / Site Foreman
dfb9ef48-d0cb-5d95-81c5-1fc426bba126 | textbox | Date Completed:
caa8c339-7a39-4e83-97cc-3f91abe93a75 | checkpoint | 1.4 Excavation Permit
9e1c90aa-9f4c-554b-9a6c-736efd266795 | note | FREQUENCY: Each lot
d63ced20-a6c8-57ac-8676-ad483d818e15 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
8acb8d19-f7c7-560c-b322-abbd353c5562 | note | • Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
b27b020c-c16a-5f82-b357-1d59f16b46de | note | REFERENCE DOCUMENTS: Excavation permit
b21976d8-6c94-56d7-acfb-5b72e4b630b8 | note | INSPECTION/TEST METHOD: Verify
5b7045db-9289-5070-b3c4-e4ff817c0d7c | note | RECORD OF CONFORMITY: This ITP Signed Off
867b376a-1dd9-5f75-bd78-1b7d65069fc2 | note | HP*
89db0442-9a45-5556-b786-55010f2a8160 | note | RESPONSIBILITY: Site Engineer
109178fd-6b53-53a4-a167-0abc916f339e | textbox | Date Completed:
0f806547-40a5-4bb1-8885-66154eee0def | section | Construction Works
b93892dd-2520-453c-8d28-fc3ca06aefae | checkpoint | 2.1 Survey set-out
457e8240-8644-588b-a6e9-3aeae7e276d0 | note | FREQUENCY: Prior to Commencing Excavation
6b669708-13bf-5000-b3c8-26285bb5c847 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
b1e4ae5a-75d5-5a5d-8a92-41ac0fba3640 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
d692f30a-7eaf-5ab6-8667-ef3721bd3b5d | note | INSPECTION/TEST METHOD: Site Inspection
2babddbf-0dc4-5cb6-9959-f7fdf044cb69 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
f7cc9563-85a9-576b-ab7f-b21d3dda0860 | note | SCP
314a81a7-0736-5f70-a044-5309d92757cf | note | RESPONSIBILITY: Site Engineer/ Surveyor
6eb898ca-0ef3-5c40-8a33-1b6e923aebad | textbox | Date Completed:
5136984a-cff9-4b2f-90a4-66b1df26095f | checkpoint | 2.2 Inspection of fill area
a4e281f1-e748-59bc-8eeb-12429250a56d | note | FREQUENCY: Each lot
f11e07ea-7d9a-5697-94d2-dab6658dc1ab | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
34288c2d-abbb-5f91-a0ad-8dd81f6d760a | note | REFERENCE DOCUMENTS: 204.10 (b)
00ff5100-27ed-5aba-8c5a-8fbac5e9de51 | note | INSPECTION/TEST METHOD: Visual Inspection
088d3208-9e5d-5740-80db-c2f4e852750e | note | RECORD OF CONFORMITY: This ITP Signed Off
de2495de-83d7-5059-a6b1-4e70e45046ff | note | HP
0a5ac6b0-1619-5a06-b9e4-318531c21723 | note | RESPONSIBILITY: Site Engineer / Superintendent
eec6be48-1cdc-585b-8acc-22df8ab6f1e3 | textbox | Date Completed:
0884c766-b4ec-42d2-a98f-84ac4f572a6a | signoff | AUTHORITY HOLDPOINT
f648bd99-c068-4dce-97c9-4353151dafd0 | checkpoint | 2.3 Keyed fill layer
1f50615b-471c-5abb-8dd9-8a48ca06dda2 | note | FREQUENCY: During Excavation
173ee7f7-4b61-52ca-9352-eba3032a76c0 | note | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
855109bf-470d-54e6-820e-e03470cb7d9f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
410e1c3d-ea25-556f-9e76-8f7668d3b388 | note | INSPECTION/TEST METHOD: Visual Inspection
4063c276-0b6b-5975-84a0-cad5bfebda4d | note | RECORD OF CONFORMITY: This ITP Signed Off
2d555aa0-168f-562f-a2c8-f0e248da3e50 | note | IP
644dbb1d-220f-53c5-82e8-5813df6a99a7 | note | RESPONSIBILITY: Site Engineer
6c1b3829-53dc-50ae-b148-d7f38287f158 | textbox | Date Completed:
b5981cd8-f7bf-453d-b8c3-7d03a440b29e | checkpoint | 2.4 Layer Thickness
1aab42a8-607e-52f5-9a31-2d04a0abe022 | note | FREQUENCY: During Excavation
384e3c0d-4263-54da-b03f-60f0230295a2 | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
b30ecc9b-f404-5f66-8600-061ea56bb3ca | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(iii)
7062df98-1b7b-5574-ab21-8d3dac6e4d9a | note | INSPECTION/TEST METHOD: Visual Inspection
ff6ecb74-a613-553d-8020-7e9e8aff6b86 | note | RECORD OF CONFORMITY: This ITP Signed Off
9844f548-70b4-5bf8-82c7-f207c76586bc | note | IP
d694308d-d8fc-5024-9307-4a17e0e8f6bd | note | RESPONSIBILITY: Site Engineer
60eda4e9-c845-51fc-9779-6b7911bceab9 | textbox | Date Completed:
9d46a913-ba7e-4200-b62f-f6bdd4c1698c | checkpoint | 2.5 Maximum Lot Size
0fb0bab5-b30c-5c91-a8a7-79621481fc23 | note | FREQUENCY: During Excavation
c25d48e4-954e-53cd-a69f-cf467bed340f | note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 10,000m2, whichever is lesser.
8fa6279c-f89b-5fe0-abe9-cbc0246dc050 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
57f629b7-7285-5add-b85c-1cd8157499b9 | note | INSPECTION/TEST METHOD: Visual Inspection
84ccd31f-64bd-58ae-9eba-5d4030cb9705 | note | RECORD OF CONFORMITY: This ITP Signed Off
d257d522-ac8b-51f9-b621-8f991359935c | note | IP
d077389d-5607-5f05-bf40-cdcbfa139b8a | note | RESPONSIBILITY: Site Engineer
4dfc0344-288d-5ac2-a72f-4751f3aab772 | textbox | Date Completed:
afb30aaf-88af-4f8c-98f9-abec16b41351 | checkpoint | 2.6 Type B Placement
d2937b06-70c4-5873-ba07-8f357087ac83 | note | FREQUENCY: Prior to Placement/ Each Lot
bbd26ede-59d2-552b-8470-61ab4d2a5db4 | note | ACCEPTANCE CRITERIA: Type B material shall be placed in locations shown on the drawings, or if surplus Type B material is available, it may be used in locations specified for Type C material.
e779e6f4-1eee-57f0-97ec-ad1d146990a5 | note | • The highest quality Type B materials available shall be reserved for placement in the higher levels of Type B fills being constructed. Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
32e7e4de-29dd-5c5d-8bc4-81cd0fb5fb97 | note | REFERENCE DOCUMENTS: 204.10 (d) (iii).
8cc9e4a8-1b8a-5e3c-a2fe-8914730b2680 | note | INSPECTION/TEST METHOD: Visual Inspection
3f79f307-940e-51f5-8732-c00d2dd96263 | note | RECORD OF CONFORMITY: This ITP Signed Off
514b6bae-33df-5a36-aa16-7f0647b5cfe8 | note | IP
a9499e9a-4013-5d50-8727-28538a01f083 | note | RESPONSIBILITY: Site Engineer / Site Foreman
77cf7726-f1cc-5509-b2a6-33634371813c | textbox | Date Completed:
7f292491-cb0d-47cb-a1c6-ac1b3a24543a | checkpoint | 2.7 Proof Roll
c69053e0-c2fa-5524-9b35-e80d0ab3c37c | note | FREQUENCY: Each lot
ec3a5256-2bcd-5f02-9fef-4e8248d8631a | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
a1d81849-ddaf-57fd-9722-fa8cba6dbd52 | note | REFERENCE DOCUMENTS: 173.03, 204.12), 204.10 (b)
d0f624a5-898d-55b3-88d4-7c17cd315ec5 | note | INSPECTION/TEST METHOD: Visual Inspection
b0c8bd28-53fd-5bd6-8c8a-c9ee356c431f | note | RECORD OF CONFORMITY: This ITP Signed Off
23801017-56ed-5f25-b817-f52bd95a729f | note | HP
97afe83f-9ed0-516f-84ed-505e088f9c24 | note | RESPONSIBILITY: Site Foreman/ Superintendent
87782e98-291c-52cf-bf46-a3096112af6d | textbox | Date Completed:
16f80b60-5651-4c8a-8a3f-7c5f544cdbf7 | signoff | AUTHORITY HOLDPOINT
18027d9c-8dc2-4f5a-aa33-83ad5e7d2e48 | section | Testing
ce80dd62-3dab-4555-a6fc-25551dc66d49 | checkpoint | 3.1 Reduced Test Frequency
9f617529-ff92-52e7-b700-0e7a95029db3 | note | FREQUENCY: Each lot
26885649-948a-5edd-8d72-dc88370ffa06 | note | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
1be0c93a-c85d-584c-ac25-a657a60c05a0 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
c774dae1-6411-5e32-8d69-8a74223816e4 | note | INSPECTION/TEST METHOD: Test Record
c4c80450-d2db-5254-a5b9-fc3c370bf27f | note | RECORD OF CONFORMITY: Test Records
a398f8ef-2b33-537b-8cd0-53433684b0d4 | note | AP
ca3060c5-20e0-553e-857a-920039170212 | note | RESPONSIBILITY: Project Engineer/Superintendent
fd4534b6-d2d7-55ac-82ea-4331247c017f | textbox | Date Completed:
df201ba5-0629-4254-8bd9-7620ec0ec514 | checkpoint | 3.2 Compaction Testing
d11f146d-1319-58c9-82c9-0529523f3346 | note | FREQUENCY: First lot then every Second thereafter
223097be-b3c9-5b56-a454-9c18ff30601d | note | ACCEPTANCE CRITERIA: Type B compaction required for Scale B is 98% Characteristic Value of Density Ratio
13e9a828-8bc0-5ea6-84b1-d56a8d3eb1ef | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
22513274-7c21-5b65-bb23-a3e58a66efb4 | note | INSPECTION/TEST METHOD: Verify
6ba6e540-c3ab-5a66-8677-a8a23f97e0d9 | note | RECORD OF CONFORMITY: Compaction Test Records
be3f17f2-80f3-58e6-bdb3-d66e65fc844f | note | TP
97dbb70b-7897-5e77-b062-0d7791fe72a1 | note | RESPONSIBILITY: Site Engineer
b1357d2a-fbdb-5ad2-9713-dd9f106f0f49 | textbox | Date Completed:
1d3fd244-236f-4382-a958-a3b39a1d5319 | checkpoint | 3.3 CBR/Swell
d8ae865a-f8d5-5f00-b221-c5c3596f4dae | note | FREQUENCY: 1 lot test to determine assigned CBR and Swell
678e4d8e-3854-5c68-830e-f35f161d5e9a | note | ACCEPTANCE CRITERIA: CBR: ≥ 1.5%, Swell: ≤ 2.5%
1a305f83-254e-54c2-8dde-6f7f7bc5a3c5 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(i), Table 204.141, Table 204.041
d7427608-25e7-5085-aa96-51edb3451444 | note | INSPECTION/TEST METHOD: Verify
c47ee136-6ca6-5a5d-aa92-e89534aada5a | note | RECORD OF CONFORMITY: CBR/Swell Test Records
36d14ee8-443d-56cb-bac5-7770657d35ef | note | TP
0ba34368-1426-5aa4-a940-dc510df4e46d | note | RESPONSIBILITY: Site Engineer
5f092c77-25bc-5bb0-b00b-7058c7c6f5f0 | textbox | Date Completed:
2d1c7bb9-9850-4dc5-88ed-15f2f5ca3e87 | checkpoint | 3.4 Survey Conformance (at Subgrade Level)
76e61464-1ea8-5d90-8332-b6efdec69d78 | note | FREQUENCY: Each lot
190b03fd-2dd3-5a17-b80b-04765f11dff1 | note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
256dca3b-f045-5efe-9b46-aaef3b3c771f | note | • Scale B:
40e6f029-704a-512b-b9d2-a1e33c068221 | note | ○ Range x = +5,-25
c086806e-4a1e-5791-a4c8-ef3e2e2faf6e | note | ○ Max S = 15mm
989b649c-5126-5336-a147-196881eb1e16 | note | ○ 40 measurements per lot
d1af104c-17b7-5437-9786-1be9d8db6392 | note | REFERENCE DOCUMENTS: 204.03
054fd189-5e0e-5f5c-b473-39a4b9108da6 | note | INSPECTION/TEST METHOD: Survey conformance point
871c06d5-491c-56a7-9fd3-a43177429d60 | note | RECORD OF CONFORMITY: Survey report, Lot Register
2b569940-1dab-545c-b9e9-594917d9bf6e | note | WP / SCP
d668e997-bbd2-5d15-92ea-898d2587944d | note | RESPONSIBILITY: Site Engineer & Surveyor
5b398f0a-4a8c-5564-a526-e2561d2d25c2 | textbox | Date Completed:
f38c94c4-bf95-4a74-b43f-ca873d1b5655 | checkpoint | Final Inspection
02a86f77-8e90-51a4-99a1-63cedca8adc9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f49d2445-1620-5ab6-b68a-03e90a9d9757 | textbox | Print Name:
6aa4e753-f627-59d5-bb0d-c5da276a9497 | textbox | Position:
9b31cc63-e137-56ab-9f36-a947da66af90 | textbox | Date:
e62477c8-6804-4b32-b495-0eacbe9fca07 | checklist | FHC-ITP-023 - Conduit, Pit & OCS Installation |  | FHC-ITP-023 - Conduit, Pit & OCS Installation
349b9ba6-ce41-45d0-a13b-d83aa66ef436 | section | Preliminary Works
51a8cd70-b9e8-4c8a-a3aa-e2829cb3cf12 | checkpoint | 1.1 Check for correct documentation
e388ed70-7a27-52fc-8ff6-9f17e11c6619 | note | FREQUENCY: Prior to commencing any activity
31a4c7dd-dcd2-593c-9ee0-1fa43fa70a34 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
8ff873aa-3805-59da-a591-fd06d123b85b | note | – using the correct and complete set of drawings
ad21d950-11a5-5636-a95d-307a9f5e16a4 | note | – all drawings are the latest revision
b3632dc2-005f-5518-b347-3e514c78dd88 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
fe7ac0d0-e0ab-58c3-88bc-4623233baf9f | note | INSPECTION/TEST METHOD: Visual inspection
c6a1e6cc-2656-5db1-9873-6e3a2b88c560 | note | RECORD OF CONFORMITY: This ITP signed off
d535519e-df3b-5093-a1f4-0f77b3cb7ea3 | note | HP*
80d2951a-b026-5f4b-805e-3b51d699f84c | note | RESPONSIBILITY: Fulton Hogan Engineer
3a1179e5-15f3-5019-94f5-da49f14a4a1f | textbox | Date Completed:
0a2a06be-2118-454e-b05a-c144edce9340 | checkpoint | 1.2 Implementation of all measures and controls
e31f7bbd-addd-5e45-8aeb-9b0f517ba3ba | note | FREQUENCY: Prior to commencing any activity
0fd620c9-5658-5ab3-9dae-aab1120629ad | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
e76fc6fe-67b4-5134-921e-c6170e35f25a | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
b3de4c34-d3f5-5200-b8f0-d178bc60ce5b | note | INSPECTION/TEST METHOD: Visual Inspection
475437b6-8f17-53ec-b145-8fdf79e9da30 | note | RECORD OF CONFORMITY: This ITP signed off
f392cd5f-6dfb-5d0c-9411-d0f34f60bfda | note | HP*
a69b51f1-f578-51df-8571-af62dc734c44 | note | RESPONSIBILITY: Fulton Hogan Engineer
8bfe461d-bbb5-5fb5-81fe-ca99f0ed8fd6 | textbox | Date Completed:
c331455d-7ecb-4b97-887d-cb855a3b030b | checkpoint | 1.3 Materials
d6f3f5f5-fe87-5c43-926f-36d3365dfb8d | note | FREQUENCY: Per Batch
2305d252-7c5c-5a99-a53d-b36d30797000 | note | ACCEPTANCE CRITERIA: Carpark Lighting A pit is to be installed adjacent to each lighting pole with 1 x 100mm HD conduit and 1 x 63mm conduit installed between pit and the point of supply. 2 x 32mm HD conduits are to be installed between the pit and the pole mounting base.
a0512117-c508-5754-bcc3-781ef2381be8 | note | • Electrical supply conduit all conduits for underground mains shall be heavy duty 'Orange' underground category PVC pipe complying with the most recent issue of AS/NZS 3000 Australia/New Zealand Wiring Rules.
d4d0fac2-1890-5a08-b103-5edc058f4b50 | note | • Communications conduit to be white 1C50 HD PVC conduits and 1C100 HD PVC conduits
a3a073f8-4daa-54a5-92ed-853875a67c25 | note | • Camera mounting poles and structures shall meet AS47806.2 (2006) Section 5.4.1 (k)
2693173a-4241-5c24-b528-0ae9c331f860 | note | • Cable pit lids shall be VicRoads type approved, impressed with 'VicRoads' and 'Electrical', 'Communication', 'Traffic signals" as appropriate as per VicRoads Standard Drawing TC-1220
879caf27-594a-51e6-bb79-d7aec489d126 | note | • All equipment labelling to comply with requirements of NIST-013.4
74022da6-1e52-51c7-8992-19a3833dc8b2 | note | • Cable pits shall be 435mm dia x 550mm deep, Type 43 plastic HDPE – Aco Cablemate cable pit with concrete lid or equivalent
50dbf71e-1293-5f49-92b2-3ccb8cf1497c | note | REFERENCE DOCUMENTS: NIST-5031 3.2.2.5 (f) Drawings
6b425963-eeb5-5170-8cad-9805f5e694f7 | note | INSPECTION/TEST METHOD: Verify
9147d638-34f0-5d6f-b6b7-04a2f2519e6b | note | RECORD OF CONFORMITY: This ITP signed
2e9d917d-16b9-54f5-89bc-ad5d95913c3c | note | HP*
af258653-d454-5327-ac8d-7e58e098ce0c | note | RESPONSIBILITY: Fulton Hogan Engineer, Electrical Subcontractor, Vline representative
bdbe43b3-30c1-5a18-a140-d111c81e2b56 | textbox | Date Completed:
648abe84-c5ad-457e-b128-0bfb510d0c52 | section | Construction Works
56c963d1-8822-4e60-8cc7-6aaed85e93cd | checkpoint | 2.1 Survey set-out
7393acdc-318b-58f2-adf6-74e8128e803f | note | FREQUENCY: As required
6de77a38-0389-5b7d-900b-f6a623359a53 | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
bab24e62-5adb-5e95-b81c-45f8f0b2d955 | note | REFERENCE DOCUMENTS: Work procedure, Drawings
e2ea4374-d52b-505f-8f0a-44fcb699c5d4 | note | INSPECTION/TEST METHOD: Verify
ea307a30-9106-5533-b3c5-e55987e3032c | note | RECORD OF CONFORMITY: This ITP signed
732deb68-5d8c-5a31-8076-63b71da0e90f | note | HP*
9395a79d-7adf-5063-9d22-b6fc0bd286dd | note | RESPONSIBILITY: Fulton Hogan Engineer
54136aab-f179-5192-b8c6-716144cff4e7 | textbox | Date Completed:
414b4af1-67ae-4b97-9f94-4cfd5418b3c8 | checkpoint | 2.2 Excavation/Boring & Trenching
189cdd5e-3771-5faf-925b-23dd5e3b3bf6 | note | FREQUENCY: Prior to Backfill
7659018e-cfd8-5314-b19d-748c33694545 | note | ACCEPTANCE CRITERIA: Trenches shall be excavated to a depth required to achieve the specified depth of cover and drainage slope, plus an over-excavation of approximately 50 mm to allow for bedding sand. The width of trenches shall be as required to fit all the conduits and pipes for services sharing the trench with specified separations, plus a further 50 mm minimum clearance from the outermost pipes or conduits.
edc9f51c-86d6-504f-8381-9c4adef6c58b | note | • Where trenches are excavated across roadways, car parks or paved areas, the Electrical Contractor shall backfill the trench with 20mm of Class 3 crushed rock. The crushed rock shall be placed in layers not exceeding 150mm finished depth and compacted to a minimum of 95% of standard density. The backfilling shall extend for a minimum of 1.0m outside all paved areas and shall be subject to the supervision of the V/Line delegated representative.
453dcb36-767e-5e8e-a01a-9f4a4bcd8a73 | note | REFERENCE DOCUMENTS: L1-CHE-STD-077 Sect 6.10.6
f8359423-ebbe-584c-81f6-5657c8c4035a | note | INSPECTION/TEST METHOD: Verify
8258dfec-1c67-5fb7-8f8e-e11e5e5a5d67 | note | RECORD OF CONFORMITY: This ITP signed
45ff6db4-07fd-5f75-84a4-f5fd37d0226a | note | HP
725b0d3f-36e9-56ba-8bcd-62195c2ba16a | note | RESPONSIBILITY: Fulton Hogan Engineer
a04b21f4-f25b-5b30-ba60-c71bbe5ebd14 | textbox | Date Completed:
e9a7457e-cdbe-45b1-a563-3240b890eb47 | signoff | AUTHORITY HOLDPOINT
59aef49a-6c2a-4ff7-b172-73375c29e0d8 | checkpoint | 2.3 Installation of Pit and Conduits
32924a6e-c5e5-5d7c-99ab-2e7dc8256dfa | note | FREQUENCY: Each Lot
101043df-fd3e-53a4-b603-fa05d275cc03 | note | ACCEPTANCE CRITERIA: Underground conduits shall have a minimum 450mm cover if around the site but away from the track corridor, should only be in the non-trafficable areas. If exposed to traffic, the depth should be 650mm.
a57e9fcd-7aa5-5714-8c80-c790e96cc275 | note | • Upon installation conduits shall be cleaned and tested using a mandrel of at least 90% of the conduit inner diameter and length three times the inner diameter.
f5203859-462e-579b-b736-5d93891b6212 | note | • Multiple conduit entry penetration holes on a pit wall shall be spaced at least 50 mm apart in horizontal and vertical planes
c539b5e6-36cc-5cc2-acbe-7897de258863 | note | REFERENCE DOCUMENTS: NIST-013.3 Sect 4.2, L1-CHE-STD-077 Sect 6.9
adfafc0d-8fe3-5c75-b10e-ba1def746b28 | note | INSPECTION/TEST METHOD: Verify
dd0f6907-953c-5eef-9fe5-00247819b8f8 | note | RECORD OF CONFORMITY: This ITP signed WP
08608eba-03fd-5975-bfd6-1adca200f59f | note | IP
ab66bc19-3ead-55c0-ae78-b0aaf20020b3 | note | RESPONSIBILITY: Fulton Hogan Engineer
ad920b2c-6bed-5a59-b097-617cb4db1a74 | textbox | Date Completed:
2e83e0c5-d22b-4031-944d-dbf5e57ea065 | checkpoint | 2.4 Back Fill of Trenches (Trafficable)
d116ac0a-4b07-5877-aaec-7b38db20571d | note | FREQUENCY: Each Lot
eaac733e-527f-537e-a6bd-503b0dde4a77 | note | ACCEPTANCE CRITERIA: Bedding: Graded recyclable glass in accordance with MTM standard L1-CHE-SPE-313
57c0d6ff-6be2-52dd-beed-e810e819c17d | note | • Backfill: VicRoads 20mm class two crushed concrete base compacted to 95% of standard density in 150mm thick layers
02aab76b-b6b2-549c-8f64-cef266dd9bc1 | note | REFERENCE DOCUMENTS: NIST-5031, L1-CHE-SPE-313, MRP-708-C-AUR-DRG-20-TNT-CLT-0810
4a66e0c8-bc89-51a5-9b9d-28e53df7fc4f | note | INSPECTION/TEST METHOD: Verify
d5b8d2ea-37e7-5b92-a49a-618f869ea4cc | note | RECORD OF CONFORMITY: This ITP signed
14db038b-34e9-597e-8ec4-7dd2a8782a32 | note | WP / IP
5339fc86-f520-5b65-b9c7-617ab55a5319 | note | RESPONSIBILITY: Fulton Hogan Engineer
b85aa48f-62c1-5de3-a909-c7cf21024cc5 | textbox | Date Completed:
b4c5f25d-988d-43d5-83c8-5fcd8148ea44 | checkpoint | 2.5 Installation of Draw Cords
59e523d9-034b-5152-a02c-fb2c38ca9763 | note | FREQUENCY: Each Lot
9e900045-18c3-537e-9b56-cefb6a650147 | note | ACCEPTANCE CRITERIA: A draw wire of 6mm polypropylene blue/yellow rope shall be placed in each pipe and suitably anchored at each end. Pipe ends shall be sealed using pipe end caps or an approved equivalent to prevent the ingress of dirt or sludge into the pipes.
94e0c5d1-0222-5614-9922-1c523c207265 | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.12(d)
41b4cd76-4ecd-5134-87d8-f908f24b4760 | note | INSPECTION/TEST METHOD: Verify
0d7e816d-46a8-5572-986b-772599cfba91 | note | RECORD OF CONFORMITY: This ITP signed
f397ee3a-ec51-52d5-a19a-956c28e49dd0 | note | IP
7706c424-6a37-5bb6-b272-3c368090f54d | note | RESPONSIBILITY: Fulton Hogan Engineer
e91fcbc6-ac2e-5c07-82a2-4a6b6bdb3451 | textbox | Date Completed:
db7006a1-cbbe-42dc-abf4-5e9e80a486d7 | checkpoint | 2.6 Installation of Marker Tape
a1166b49-0b18-5fd8-ab33-68f4c4f2b816 | note | FREQUENCY: Each Lot
32817046-c2cb-5396-9915-fce0e40e27f8 | note | ACCEPTANCE CRITERIA: A 150 mm wide orange coloured PVC marker tape with the words “DANGER BURIED CABLES” shall be installed in all trenches at 300 mm below ground level except where cables are permitted in shallow trenches due to rock. In this case the depth of the marker tape shall be at the discretion of the Infrastructure Manager.
6d11a738-987e-51f1-916e-f0d67db6fb9d | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.11.1
72e4874d-16d6-5df1-8300-1d277fd6abde | note | INSPECTION/TEST METHOD: Verify
1cdf9ec5-2584-561c-ba1b-2e08f5313095 | note | RECORD OF CONFORMITY: This ITP signed
c0bc4182-df96-5db3-89b2-547255cb09df | note | IP
8fb2ee4c-fbcf-5a07-918f-a65e466d005e | note | RESPONSIBILITY: Fulton Hogan Engineer
379c5dcb-1b4b-53e7-bc70-0c91b2ce0810 | textbox | Date Completed:
edaf4cb5-fbc4-4fcc-a767-78bc5c29a787 | checkpoint | 2.7 Cable Pits & Pit Lids
85f2627c-d928-5d25-ad2f-61ad638e8a4b | note | FREQUENCY: Each Lot
2da0fa02-0da3-5866-81f8-c6dfc23b6c08 | note | ACCEPTANCE CRITERIA: Cable pits constructed and installed as per drawings
9680fc1a-9699-55bb-8c94-c31d3edb702e | note | • Pits shall be placed at each horizontal change in direction or at spacing no greater than 100m
c8064cea-ec8b-5ad3-9c12-0da8a59588a8 | note | • Seperate pits shall be used for power conduits (orange) and communications (white).
60b99e31-9b9e-5ef7-9259-883e8ac7f638 | note | REFERENCE DOCUMENTS: OCS Drawing Package
f542fe02-b529-5209-87b4-053e621937f2 | note | INSPECTION/TEST METHOD: Verify
53b8347f-2129-580a-82ed-006814f379fd | note | RECORD OF CONFORMITY: This ITP signed
023e0bfa-9411-5108-a618-437212b2a844 | note | IP
77de6567-27cd-5733-8e97-d04daa0170bb | note | RESPONSIBILITY: Fulton Hogan Engineer
bce8d391-8268-5c63-b25e-c59de2a3ecce | textbox | Date Completed:
cdcc7ecc-c2fc-4569-9bd0-fab079fd2b7b | section | Completion
42d2fd28-5a4d-4959-ad6e-ef363ccb6eee | checkpoint | 3.1 Cleaning of Site
4455f41e-1481-538b-9fc2-a9828179fb5e | note | FREQUENCY: Each Lot
bff31e99-d3f4-59dc-8c6a-c0c4d95fd45f | note | ACCEPTANCE CRITERIA: All obselete cabling to be removed during installation and disposed of appropriately.
dec1343e-4936-5de5-a916-be4d822c0166 | note | • Upon removal of all redundant signalling equipment; the site shall be cleared of all project scrap and associated rubbish.
a111a9a1-ec64-5c02-b371-64194d3c1149 | note | REFERENCE DOCUMENTS: NIST-012.2 Sect 23
90f9f580-7c06-5bde-acda-bcc7939dc348 | note | INSPECTION/TEST METHOD: Visual inspection
61758c95-f4e5-5baf-be5d-c00b169c1f32 | note | RECORD OF CONFORMITY: This ITP signed
b342e58f-4568-5333-b291-69376dd8d791 | note | IP
e5b5f5d1-b510-5916-b8ef-c98b61b6c4b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
1a206939-c717-59bd-b7f2-c64cda0e504d | textbox | Date Completed:
8e73fa2a-8eee-4a1e-a892-ef5a81171aeb | checkpoint | 3.2 Recording/As Built
d453bc9c-c336-5139-837d-7a6940ef0810 | note | FREQUENCY: Each Lot
e08dda89-ffee-58ce-aed7-1f86fc1d07e3 | note | ACCEPTANCE CRITERIA: As-built drawings will be completed by the Contractor based upon the installed system by a process of editing the approved ‘for construction’ drawings.
e7d2efb6-ffac-5bec-89ea-00c2087e36d9 | note | REFERENCE DOCUMENTS: NIST-013.3 Sect 5.1.3
5e80e393-2be4-55cf-9954-d5aa8f544fbf | note | INSPECTION/TEST METHOD: Verify
469a690a-a489-54db-8fe7-2490d85d4c8c | note | RECORD OF CONFORMITY: This ITP signed, As Built Drawing
a5c5f040-2a5f-5c9b-8802-4a4d8064611c | note | IP
b723ffd7-9b42-5785-a242-7280720b78ba | note | RESPONSIBILITY: Fulton Hogan Engineer
6878cfe4-4559-5f6d-ae1b-25e2a92905f3 | textbox | Date Completed:
1e7338d3-1ba4-47bf-982a-abfd7dad80e1 | checkpoint | 3.3 Commisioning
7807dc59-acd8-5bd1-84d4-689d6728956f | note | FREQUENCY: Each Lot
6675ce5a-bcfd-5ad2-a79e-ed9b75fcdc70 | note | ACCEPTANCE CRITERIA: Commisioning to be checked against V/Line checklist. For OCS Only
fe36a94c-3764-57ef-af7c-c8ca464abdcb | note | REFERENCE DOCUMENTS: V/Line Commisioning Checklist
4b087fde-7853-5b58-a066-52cbce45eeea | note | INSPECTION/TEST METHOD: Verify
ddd79ad4-76e4-57ec-b6e7-5497f7807af3 | note | RECORD OF CONFORMITY: This ITP signed, V/Line Checklist signed
47dc8bbb-38c0-5e31-9670-ef77ada4f1e7 | note | WP / TP
dfa60a84-68c7-5d11-b83d-83f346e22d3b | note | RESPONSIBILITY: Fulton Hogan Engineer
a4d4b2aa-2dea-5ab8-9eba-69d1e432f60f | textbox | Date Completed:
92bd98ad-9854-4e4b-8813-08ceaac504d9 | checkpoint | Final Inspection
5872b5e4-878f-5e15-a1bf-054c422c8115 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ab967568-2161-59c9-bbc6-b8f83ff03836 | textbox | Print Name:
208447d8-a6fa-5abc-b47d-09b4cea9a5b4 | textbox | Position:
817d8e14-ca1e-59ed-ab85-d578da733ecc | textbox | Date:
56ddb9ab-5fec-4f5a-a4d2-cc48df5a9057 | checklist | FHC-ITP-025 - Structural Concrete Construction |  | FHC-ITP-025 - Structural Concrete Construction
e1d52698-d9a0-4057-aada-34ab1d975414 | section | Design and Submissions
4b2cf01b-4188-4bf9-80c0-cc8d0865cc91 | checkpoint | 1.1 Check for correct documentation
2f3af4d2-eafc-56d3-b9e5-f0b5de902035 | note | FREQUENCY: Prior to commencing any activity
9c8b319b-4382-5175-86ef-62ed57818a0e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
95d48f20-3b22-552b-9c99-b3f19ec29355 | note | – using the correct and complete set of drawings
ec2a1feb-e559-5a13-acdb-56bed77c5736 | note | – all drawings are the latest revision
5f6d4260-7ad7-54f8-b781-ff3cb04dc920 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
7d66c718-85a5-52e4-a044-b9fbde1e236f | note | INSPECTION/TEST METHOD: Visual inspection
66fc257b-0147-5529-b71c-b37f95148caa | note | RECORD OF CONFORMITY: This ITP signed
7096ba45-9087-5d50-9669-88d0669d6668 | note | HP*
6ae4e75b-9068-572a-9595-3923f1dd8de6 | note | RESPONSIBILITY: Fulton Hogan Engineer
bef24aca-7bbd-5702-b1cb-88485721e84c | textbox | Date Completed:
00249fcc-2ee0-4721-b563-5cdcc8cd1651 | checkpoint | 1.2 Implementation of all measures and controls
effbbc0c-6d66-54f3-a958-6ad95c631cb8 | note | FREQUENCY: Prior to commencing any activity
70b5112d-8b95-52bf-971c-44bef333c74e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
ccdc9f71-a691-5d98-b907-bde57a1a8192 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
479463cc-fbf5-5e96-bf6b-6861397c8690 | note | INSPECTION/TEST METHOD: Visual Inspection
fbed62ec-8517-55e7-ba82-207c0823b2e4 | note | RECORD OF CONFORMITY: This ITP signed
6627cc1c-bbfa-5536-9f58-18e8f643e87c | note | HP*
035fa52c-dd27-5572-b571-c7d5bbb72011 | note | RESPONSIBILITY: Fulton Hogan Engineer
c20ad8b5-e0c0-5a53-aa45-9c10ae41e688 | textbox | Date Completed:
b5a24648-277e-41f4-ac4b-36f2536f331e | checkpoint | 1.3 Approval of mix design
6877a467-b688-5f9c-9097-63ed34787b46 | note | FREQUENCY: Prior to the first concrete pour
bade0721-07bf-5d62-a74c-ac985229650c | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
0ea13510-d178-531c-86af-c97d017bc1ea | note | REFERENCE DOCUMENTS: 610.07
062b0d2e-41f1-5d59-b2c3-a047624cb803 | note | INSPECTION/TEST METHOD: Verify
0048e45c-1029-5317-9541-83f564461fea | note | RECORD OF CONFORMITY: This ITP signed
2619810b-64a1-5b7e-a186-aa3313d14e3c | note | IP
228ae94a-4f8e-544f-9fd5-f33cbfff01e3 | note | RESPONSIBILITY: Fulton Hogan Engineer
e6c44e81-9afa-5048-9d1d-bfb6e47e77fb | textbox | Date Completed:
9c3ea31d-accf-419b-89f2-48160887e2d4 | checkpoint | 1.4 Reinforcement schedule
c7a2de2c-0987-517d-8e43-a9e9182a98aa | note | FREQUENCY: Prior to concrete pour
c49a4d42-70a5-5fac-a509-1dc066c1064e | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
19072f7a-a7de-5641-8602-3a7116f9e3d0 | note | REFERENCE DOCUMENTS: 611.04
dd35b0d9-607d-5125-8adb-d604143ce508 | note | INSPECTION/TEST METHOD: Verify
5161f6bc-7927-598e-a88e-579facb0cfef | note | RECORD OF CONFORMITY: This ITP signed
4bc9738b-6c19-5b4b-bbc8-7f0a75b61688 | note | IP
6f55633d-957a-5867-8b6b-554cbf07279d | note | RESPONSIBILITY: Fulton Hogan Engineer
154a4283-807f-55cf-9aa3-2e676053533e | textbox | Date Completed:
e5e9580c-8888-494a-888a-0453d2bbbba2 | section | Construction/Erection of Formwork
b3aa1dd5-2e0f-4751-b962-ff69ec495eca | checkpoint | 2.1 Excavation
ed820a07-a1f2-584f-8fc0-805d50de5391 | note | FREQUENCY: Prior to concrete pour
3c259ee2-cdcd-5a3b-80f6-ad2bdcd5e413 | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
76905105-71c3-547b-944a-3fd7a7999cd1 | note | REFERENCE DOCUMENTS: Contract Drawings
226780fd-de6d-545d-9efe-b23c286461ab | note | INSPECTION/TEST METHOD: Inspect
ff25f56e-80d9-52d9-b9ba-ea6bbc80c353 | note | RECORD OF CONFORMITY: This ITP signed
5f557cc1-9ec9-5fb2-8896-45760f75c2a9 | note | IP
014ea15a-04d2-502c-92a8-31a2b07ac5b4 | note | RESPONSIBILITY: Fulton Hogan Engineer
bb91e6a0-781c-5b3e-8209-7f06646bab2a | textbox | Date Completed:
c102f509-db26-4156-a35a-19061c8b41bc | checkpoint | 2.2 Construction Methodology
6658c88c-5cdd-5c9b-9797-ef8c7f609880 | note | FREQUENCY: Prior to erection
04b6e7d6-0fc9-5141-8892-42d1b880a9ca | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
c4021219-af84-578c-92d6-bc63e4893565 | note | REFERENCE DOCUMENTS: 614.04, 614.06
cd79be22-6e59-5c50-a542-17808c2297ac | note | INSPECTION/TEST METHOD: Verify
7e865f34-4a37-5f89-9941-0bcded87a429 | note | RECORD OF CONFORMITY: This ITP signed
a4500a7b-c52c-575b-af2d-0c74826c9585 | note | IP
ca336bfd-4a91-55dd-973e-d0f6afb5780d | note | RESPONSIBILITY: Fulton Hogan Engineer
f9406824-7ac1-5cc1-a623-9873f4e8cf3f | textbox | Date Completed:
4d10e75e-87d2-4b40-a081-938ad817efd8 | section | Pre-Pour Planning and Inspection
619e7098-00e8-4fd7-9ba6-335df9373189 | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
339b3ea2-1905-57c5-850f-18f8ffe68c93 | note | FREQUENCY: Prior to concrete pour
1dd924b7-eeb4-5d59-a36c-690d8e3c1405 | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent.
c3821b51-5f0e-5521-9747-a977022bcec7 | note | REFERENCE DOCUMENTS: 602.03
678ef115-7426-5f8a-b293-992af6ce6e76 | note | INSPECTION/TEST METHOD: Verify
aafc1841-b036-5d55-a9c3-77df921bbbf2 | note | RECORD OF CONFORMITY: This ITP signed
268a394a-1989-5d0e-a3aa-8aa0bfa486b6 | note | HP
48165789-7b34-566d-9e45-95faa80e3e5d | note | RESPONSIBILITY: Fulton Hogan / VicRoads
0725a3ff-3cd8-5056-83c1-da5d0faf2ca2 | textbox | Date Completed:
5edf08b4-50d1-490a-86aa-4702558874f3 | signoff | AUTHORITY HOLDPOINT
a6e1bf7e-9786-4f63-b361-bc98eb725fd8 | checkpoint | 3.2 Formwork levels and position
45425875-60ae-5b7a-959f-7351d0f7347f | note | FREQUENCY: Prior to concrete pour
b4461aae-0096-5ea4-abad-150dc8d96dc6 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
f2295876-7e9d-5d15-8282-0eddb4b7d3ae | note | REFERENCE DOCUMENTS: 614.06
2fd6bd70-b5d0-5dbe-aeb6-ebddb41402b1 | note | INSPECTION/TEST METHOD: Verify
3e7fde5d-d477-5003-95ce-f3ea94a8cca7 | note | RECORD OF CONFORMITY: This ITP signed
b056e925-9ced-58f7-bb0a-97c9ed06f5b8 | note | SCP / HP*
7ab9582e-e867-58f1-9bde-f82db9b3da30 | note | RESPONSIBILITY: Fulton Hogan Engineer
71bc3cda-f366-5473-8c4e-fccf02c25580 | textbox | Date Completed:
85c10479-c9f4-4847-94d4-415b12cf1abd | checkpoint | 3.3 Location of splices
cd416037-b968-57a7-8ec6-c35ea9bcc204 | note | FREQUENCY: Schedule Review
60e15fb3-88f1-59f1-8766-2b4fae575b84 | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
d228a8b2-fb75-5cea-ae67-626b0e696c70 | note | REFERENCE DOCUMENTS: 611.11
e5fcb0f0-6952-5f53-b309-c89a4f473b26 | note | INSPECTION/TEST METHOD: Inspect
a75588c8-b578-5da3-8163-8ec29b8d857e | note | RECORD OF CONFORMITY: This ITP signed
c15f18d4-82f8-5aa2-b350-81e400437136 | note | IP
be9ae700-45ed-55d0-888f-d80ead307c33 | note | RESPONSIBILITY: Fulton Hogan
67113ebe-43e1-502e-bba9-5939be09371f | textbox | Date Completed:
166c0ed2-c05b-4170-9c91-8843f15e03b4 | checkpoint | 3.4 Cleaning formwork
ac13a68d-a574-57e1-a668-587dce04f1a7 | note | FREQUENCY: Each concrete pour
dca9f153-17c1-59bf-8ba2-e96a7a0e8d38 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
ef4558ac-fe29-530a-b82e-5e7bf522a5b1 | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
b904e5ec-d336-5450-9b95-af565a52ec67 | note | INSPECTION/TEST METHOD: Verify
20c50fc0-dc84-56e0-90ff-480129cb3dd3 | note | RECORD OF CONFORMITY: This ITP signed
c060a912-82ed-5b59-8d70-014e6e1a3fa8 | note | IP
bf2277d7-5f3c-5e7d-9fc8-62e73a740f6a | note | RESPONSIBILITY: Fulton Hogan
29afb29d-2976-58b7-8ce9-82c06059d3e5 | textbox | Date Completed:
c8b12319-4fff-4e04-916c-fa0b7623a6d1 | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
22f6e83d-6f49-5f70-9afe-8ad9bc0fd118 | note | FREQUENCY: Prior to concrete pour
13488d6d-51d5-5620-8fa1-1cf95b9509f3 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
21646ae3-c65f-53b0-ab30-f60c48cae5c2 | note | • Pre-pour checklist completed and signed.
d6d33aaf-cf88-5d99-988f-e61e759eb5c6 | note | REFERENCE DOCUMENTS: 610.18 (a)
0418b99a-9f6b-5e78-8d99-5587ea7bbd3c | note | INSPECTION/TEST METHOD: Verify
a0ace3b6-b68a-590a-b1be-c79f6c8b6073 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
c27b9c05-b2c4-53e8-a7d9-fa6286633d45 | note | HP
7b2a4ee1-b8a3-5632-a6e0-2f9f644eb151 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
6ffeafae-c226-5058-aeb4-fc765d296781 | textbox | Date Completed:
92243fe6-8431-486c-ad32-c4efce7cd12b | signoff | AUTHORITY HOLDPOINT
0644362e-3c16-4a9a-99d4-cff53074f8a4 | checkpoint | 3.6 Reinforcement assembly of piles
01820401-6941-5a15-8bf1-f409fa39be31 | note | FREQUENCY: Prior to concrete pour
70003b91-c24d-5c85-b06d-75627f1ba734 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
3de7beb5-89ef-5cd8-9677-2c95ea3aaab3 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
f35eaa06-dd84-5aa5-b5a2-c0124e9d0f19 | note | INSPECTION/TEST METHOD: Verify
67775513-d0ae-5168-a657-f87a0a1dc266 | note | RECORD OF CONFORMITY: This ITP signed
2df1a54f-c531-5853-9eae-7c0eab18ff90 | note | HP
28f1fc23-3c5f-59e8-9aa3-77cdc132a394 | note | RESPONSIBILITY: Fulton Hogan
ac8e57d4-0af2-5cf3-b200-7ddea574641d | textbox | Date Completed:
5a793446-d33d-4293-a4c0-ca6f39fcd64f | signoff | AUTHORITY HOLDPOINT
d18ed252-ea6f-40af-9d25-85f50c1f5e1f | checkpoint | 3.7 Monitoring weather
2b0297d0-fca9-51f2-a07f-fa0817617ac8 | note | FREQUENCY: Prior to concrete pour
5511dd6d-59fd-5af4-8431-90ad32cc0973 | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
1c0ec519-3ceb-5a74-9f6f-f972b2ceb443 | note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
57948e79-5275-5f58-a576-0318583aaac7 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
caf3ffdd-06e6-5434-8340-6bb4a35fa978 | note | INSPECTION/TEST METHOD: Verify
c6dfeb4f-6243-5e82-b3c4-5565c4a55794 | note | RECORD OF CONFORMITY: This ITP signed
e3a8dd14-ed8e-5ba7-b9b7-8146fab30d2c | note | IP
295e6d16-e8f8-585b-8031-ee18c849c4ec | note | RESPONSIBILITY: Fulton Hogan
36a1dffd-0025-5c9e-8591-f905bcae6039 | textbox | Date Completed:
5733ae93-ac6a-4a65-b0e0-60e576f6df6a | section | Placing and Finishing Concrete
09f80731-551e-4618-a7f7-31790dcf6745 | checkpoint | 4.1 Carry out sampling of concrete
bf504474-3cae-5095-a99e-422c6ba0b991 | note | FREQUENCY: Each concrete pour
cbec7be5-ce3b-5599-8bcd-18b8c33e314b | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
f8589bd5-29a4-536b-a1da-e421de5a1ab8 | note | REFERENCE DOCUMENTS: 610.16
6ed4c9e2-9579-5af7-a6c8-dbaa8e3ff98f | note | INSPECTION/TEST METHOD: Checklist
7ad13dfa-dac4-549c-ba47-0da36333c817 | note | RECORD OF CONFORMITY: This ITP signed
386a86a3-86ce-5c2a-91b7-ac3cf59364b3 | note | IP
7509cb55-f932-5d59-b9ca-0fbe7a2ba970 | note | RESPONSIBILITY: Fulton Hogan
5ae59790-679f-561a-a04b-c50d1d738765 | textbox | Date Completed:
dd7c21f7-4b8a-420b-bce9-a3f742769671 | checkpoint | 4.2 Discharge time
40b27793-e128-5ba3-9d64-eadf9a28d885 | note | FREQUENCY: Each concrete pour
c1a68e81-8dad-5163-9a0b-f583bafe2c3c | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
207753e7-6df0-5408-a097-000c97327dd2 | note | INSPECTION/TEST METHOD: Verify
1c0a057d-320d-51a6-9f21-e3c4a913a146 | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
eaa00c6d-5ac0-558c-ac4a-8ea2da9d70b7 | note | IP
b6dea6a0-3556-5201-a8df-dfac477ea412 | note | RESPONSIBILITY: Fulton Hogan
5aa3618c-1bbc-57f5-be71-b3477a180388 | textbox | Date Completed:
cef4e079-40f9-473b-bc21-07b0d4c0dc7c | checkpoint | 4.3 Methodology of placement (structural)
53ddd1cc-aa0c-59fa-bef9-625792f37cdc | note | FREQUENCY: Each concrete pour
10a86a10-5fce-5046-9758-8f16d874e3b5 | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
5ac75070-7071-508c-bc1f-17eb0c45a860 | note | • Concrete shall not be moved horizontally by vibrators
fe7669a1-8704-54b7-8c91-df0bde05ef56 | note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
990773f5-0ae2-5e4a-92f9-6f25a4cf830b | note | REFERENCE DOCUMENTS: 610.18
71f3b6f4-eab3-55f3-899f-9dac74c0032c | note | INSPECTION/TEST METHOD: Verify
54855e7f-0267-5063-a209-be72011a60ee | note | RECORD OF CONFORMITY: This ITP signed
ba0fc21f-cd1e-5ce6-8635-f4048237ceb0 | note | IP
c6b3c0c1-50a9-5354-b252-035f8a4f3d4f | note | RESPONSIBILITY: Fulton Hogan
e103ef8f-1f73-58d2-b92a-7a523dd845a9 | textbox | Date Completed:
fa5b1445-a2cc-4367-9945-9555723959a8 | section | Post-Pour Details and Inspection
7d53415f-26b6-4140-9c18-93f9776f656d | checkpoint | 5.1 Curing
70959640-cfb6-52b0-8f4c-ad32204bbeb5 | note | FREQUENCY: Each concrete pour
74cedb45-1493-5b37-ae0f-1964eabcb3d8 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
14ec4ff3-c66f-5bbf-a1da-eeca9794df0f | note | REFERENCE DOCUMENTS: 610.23
eedb0983-a044-583f-bc61-3ba023152056 | note | INSPECTION/TEST METHOD: Verify
de53635b-f004-5c5c-b16a-9e157e62af2e | note | RECORD OF CONFORMITY: This ITP signed
827894d5-6788-51a6-9196-fb270636335e | note | IP
c22f6688-63f1-5594-8be3-f710f3160c40 | note | RESPONSIBILITY: Fulton Hogan
c4ecfe96-3d53-5d47-ae31-b6635f96785d | textbox | Date Completed:
b79a3d7e-304e-4648-98c5-07b02adf0a37 | checkpoint | 5.2 Formwork removal
b1c0518f-87b0-5df1-8423-d3368e3cb2d3 | note | FREQUENCY: Each concrete pour
3b1c2ed6-f865-5a4f-bb63-0321e5beaa09 | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
00f36d0a-cbde-5980-9093-bfd9f908dc7c | note | REFERENCE DOCUMENTS: 610.25
5166e9e5-ed75-5d14-aa14-d27c5fa14147 | note | INSPECTION/TEST METHOD: Verify
651d011c-ad7f-5e14-b2d8-fcc0f6405a25 | note | RECORD OF CONFORMITY: This ITP signed
e3de1b40-5a76-595d-8d7b-4a069a808f72 | note | IP
3bcbd4ac-f998-5e69-92d8-f5a85063fa80 | note | RESPONSIBILITY: Fulton Hogan
ca3e7eb2-bd14-5491-9b66-99c7696fdc69 | textbox | Date Completed:
4e721e00-e7be-46a6-bbdc-68089c1e02c6 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
9f16b21b-3df4-528b-9435-ce2a81cfbbdf | note | FREQUENCY: Each concrete pour
868ca64b-8745-5bbc-a7fc-cbf8c86b7a3b | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
1af2205c-a7ad-5973-959f-b4030d89edc5 | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5 607.06
882a1a47-bec2-5468-bf57-29bc8167c435 | note | INSPECTION/TEST METHOD: Verify
7f353b0e-ac31-5014-bf7a-6103a66cf23b | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
8d8f0df0-4c92-5da4-9447-bd211ba88d0f | note | IP
e96a0f06-5d46-50f6-82c7-9b9df22d9ea7 | note | RESPONSIBILITY: Fulton Hogan
26e0e86d-5daa-5662-8637-bd9cb343bb08 | textbox | Date Completed:
5754445c-48ea-4be7-8f3a-2eaa0bc4e3b5 | checkpoint | 5.4 Concrete Sampling and Testing
e4ed1464-8649-5471-b7ba-0e3907aa90ae | note | FREQUENCY: Prior to lot closure
487dd86a-37df-5189-9a70-cd3284c1dca9 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
4519631b-c845-51a6-8746-5f61cda5131a | note | REFERENCE DOCUMENTS: 610.16
536e9ceb-66f2-5ffc-b06e-dd62f789a1ed | note | INSPECTION/TEST METHOD: Verify
c05e4e1b-3739-53be-bc55-4b3587d44351 | note | RECORD OF CONFORMITY: This ITP signed
41548452-22e9-539b-bfc2-765d2cf61c98 | note | TP
8b2e825b-f8b6-55de-b2a3-7905b654ffc5 | note | RESPONSIBILITY: Fulton Hogan
8ecd0767-bbf5-53d3-b4f4-3a95a18d8cf2 | textbox | Date Completed:
df68974c-4c7d-4aac-93c4-a9cf8accfee2 | checkpoint | 5.5 As Built Drawings
6ff53475-a979-5524-b055-5f0d40cbe7b2 | note | FREQUENCY: Prior to lot closure
d7ffb596-890f-531a-b978-214200a27ba6 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
c2ec2232-138a-589e-b38b-f4c7692de7e6 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
6357747a-3d51-51af-9a70-21e744f9d332 | note | INSPECTION/TEST METHOD: Verify
c3ebe508-f985-5e39-a41d-430c4738ef84 | note | RECORD OF CONFORMITY: This ITP signed
483e3afa-437d-53f5-a372-861ad938342e | note | IP
164b4c49-f5ad-56a7-8ee0-7282a474570e | note | RESPONSIBILITY: Fulton Hogan
8d52a580-a59f-59fd-842d-bcd26fbbb5d1 | textbox | Date Completed:
4bd8662a-4ebc-4c11-853d-3cd0b82dd48b | checkpoint | Final Inspection
94fd923d-3957-5691-8e8a-0e9337aa935f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
a197f908-1030-5450-ba07-b4d45216e96f | textbox | Print Name:
c032a7e9-9e05-5408-9909-34668eac5916 | textbox | Position:
ac9978d2-735b-50aa-82f2-c9ed8fd01531 | textbox | Date:
dba06dd3-4932-4ee0-a3f4-c6d7dc3c3e35 | checklist | FHC-ITP-026 - Safety Barrier Installation |  | FHC-ITP-026 - Safety Barrier Installation
ff653406-e8dd-497d-a81a-94422d34c668 | section | 1. Preliminary Works
94c65f10-eb9d-46bc-9dd7-d88143657c0a | checkpoint | 1.1 - Check for correct documentation
07f47756-db2a-5bf5-b2bb-5ef55b1a2d1b | note | Frequency - Prior to commencing any activity
d98d14e0-52e4-519a-b862-c75543fb8c17 | note | Acceptance Criteria - •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
3911e794-e916-5ab2-87dd-091ac922a1c4 | note | Reference Documents - Drawings and drawing registers
2b05edc6-e14c-54fb-a006-bfb25170aaea | note | Inspection / Test Method - Visual inspection
a21ea844-cf10-5a8b-add9-a817bb9bdac4 | note | Record of conformity - This ITP signed off
98d2e25a-b10a-526b-a4b6-59f362aaea61 | note | HP*
14177828-97c6-5f44-a7ab-4556eaa582d5 | note | Responsibility - Fulton Hogan Engineer
404dd972-bce9-4013-b632-2889e594d003 | checkpoint | 1.2 - Implementation of all measures and controls
e4709899-cec5-5845-8e00-187be425bf23 | note | Frequency - Prior to commencing any activity
0980380e-94fb-57e9-911c-107a19ba2d24 | note | Acceptance Criteria - •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
ca27d802-2287-5802-aa09-74b92af219c6 | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
5371e004-65c3-5ccd-8abe-a686ffaef137 | note | Inspection / Test Method - Visual Inspection
092996e1-1e95-5a9d-9263-8ed42a285b51 | note | Record of conformity - This ITP signed off
c2b6c63e-4d5c-593e-9528-4db41f0312b8 | note | HP*
373b52e7-9365-5aca-b282-1c65ece6f2da | note | Responsibility - Fulton Hogan Engineer
60e70390-9a80-4f87-8cd6-7b968732ad6c | checkpoint | 1.3 - Material Approval
783e83ca-6d2a-5970-9dba-d3c6a4ec0cd0 | note | Frequency - Prior to commencing any activity
5110cc65-9820-5117-b249-6b7fdef738c0 | note | Acceptance Criteria - •Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used, FHC shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
6346e7e6-65a0-5d25-8dc8-bf14557fb984 | note | Reference Documents - Fencing Plan RD06-04 708.04 708.05 (b)
06aed3b0-cabe-5f17-ba08-0573f0583e9e | note | Inspection / Test Method - Verify
e7c01f20-a508-5f68-b132-75c93a9f3fe4 | note | Record of conformity - This ITP signed off
f97d25d4-3e0a-599b-bded-f96ea2e99c0f | note | HP
4c798307-7480-5725-8cfc-f6d993ff7a85 | note | Responsibility - Fulton Hogan Engineer/Superintendent
d8456ef2-37ba-4790-84ed-92c36b0b3272 | signoff | AUTHORITY HOLDPOINT
931fda74-48ba-412f-9064-fad1990b53a5 | checkpoint | 1.4 - Location of Works
e3983597-5566-5ed2-8943-a8e9969dda72 | note | Frequency - Prior to commencing any activity
aaf73f78-21f9-5d40-8496-1b3b56c6bfd1 | note | Acceptance Criteria - •Prior to installation the Contractor shall confirm with the Superintendent the required location and length of all guard fence.
2924aabd-ade8-516c-a32c-9b7b5bd39cd1 | note | Reference Documents - Fencing Plan 708.08
c0d407eb-1668-5090-84cb-0fa13923144d | note | Inspection / Test Method - Verify
0235b3b2-916f-5167-a34d-87d347f518e1 | note | Record of conformity - This ITP signed off
73af5f31-7f6b-5f70-911d-47d0f42f16c1 | note | HP
095871cb-1872-5186-961d-2c22b165dd1c | note | Responsibility - Fulton Hogan Engineer/Superintendent
66ebdf7f-5452-4f29-98fa-73879ddca9a7 | signoff | AUTHORITY HOLDPOINT
63f0e07c-70c7-4129-8b4b-b98619b54cbd | section | 2. Construction Works
d3e5a2c5-c661-4de2-adb1-7f73489b7b2e | checkpoint | 2.1 - Inspection of Materials upon Delivery
0dff0715-133a-51cf-8c30-76a3049a956a | note | Frequency - Each Delivery
f8bafbf2-b0b1-59f4-9e92-af2eae9c321e | note | Acceptance Criteria - •Posts shall be inspected upon delivery for compliance and damage. If scratched or missing coating, this may be rectified with a minimum of two coats of a zinc-rich inorganic paint
8b127e1a-d353-5478-8f2f-64f43fbc8284 | note | Reference Documents - 708.07 (b)
289c7d53-dace-5ced-8b18-524297242f19 | note | Inspection / Test Method - Verify
61d648a1-8359-5a09-89d0-f939475761fd | note | Record of conformity - This ITP signed off
ac0c5e1c-81b7-50b1-81c1-c1c0ea30077b | note | IP
754dcddc-1911-5d38-8e19-0b8a32f773e4 | note | Responsibility - Fulton Hogan Engineer
d7dd1821-da35-43b6-8922-006ffa571b9b | checkpoint | 2.2 - Post Installation
fc5e8957-7f34-5f17-a02a-0ebd661e7c48 | note | Frequency - Each Lot
52c690c2-aded-5278-b6c8-f327c4e52227 | note | Acceptance Criteria - •Posts shall be installed to the depth, line and spacing shown on the drawings, and to the tolerances in clause 708.07(d). •Posts shall be installed by driving, provided there is no distortion or damage which may reduce their effectiveness.
ebe38201-7e06-5276-89d3-b1a62d92c95e | note | Reference Documents - Fencing Plan 708.08 (a) 708.07(d)
c9d8ebdf-508b-5d42-9102-4f2d170c413d | note | Inspection / Test Method - Verify
3e2a2da1-5c26-5641-a52d-667d740c4b92 | note | Record of conformity - This ITP signed off
894d2ba2-0f10-5c2a-99fa-7464f9c65f92 | note | HP*
47b0a0a5-cc91-5dac-a4d6-38c89e2449fd | note | Responsibility - Fulton Hogan Engineer
c0e79c9d-822d-40c1-847f-05c240c5432c | checkpoint | 2.3 - W-Beams
40fd4ed2-90f0-56da-8e7a-5ce6d4c2ceac | note | Frequency - Each Lot
2c5ef29f-f2ff-56fe-be17-abb5095ff84f | note | Acceptance Criteria - •The w-beam sections shall be lapped so that the exposed ends face away from near side approaching traffic. The edges of the w-beam section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened. All bolts on the traffic side of w-beam installations shall be flush with the w-beam
1bfe10f2-1117-59a1-8ab6-ba01203149c8 | note | Reference Documents - 708.08(b)
b2eae3be-0be5-5298-8653-d9168362e260 | note | Inspection / Test Method - Verify
107db52d-aaff-530d-8b4e-0c6e0e50d763 | note | Record of conformity - This ITP signed off
8a507918-9ebd-5975-b67e-47bb50d03381 | note | HP*
61622865-b2c2-5c14-bd6c-a7ec1d13e249 | note | Responsibility - Fulton Hogan Engineer
894efc42-ebba-424f-b518-2e46288d3332 | checkpoint | 2.4 - End Treatments
d4f8bfd9-7f04-550a-900f-17212c512295 | note | Frequency - Each Lot
21d5d814-91b8-5abe-ab1c-7ad74fe69bfb | note | Acceptance Criteria - •During installation of wire ropes in the end treatments of w-beam, the Contractor shall ensure that no twisting of the rope occurs. When rope assemblies are used, the nuts at each end of the rope shall be tightened to a minimum torque of 50 Nm on the assemblies or as per the manufacturer’s requirements. The Contractor shall maintain tension in the wire ropes in end treatments until the Date of Completion, by keeping the nuts at both ends tightened to 50 Nm or to manufacturer’s requirements.
7c1847d4-df77-53cb-ba2f-d1cc79221c2c | note | Reference Documents - 708.08(c)
dd80d2b3-1a60-5490-b7f1-e1aec8d97359 | note | Inspection / Test Method - Verify
63878a52-9595-54de-87db-7681624d3d8f | note | Record of conformity - This ITP signed off
ba8abbb2-3104-524b-8c23-817f35ed5649 | note | HP*
0824d666-fcff-521b-91d7-0ae384329a67 | note | Responsibility - Fulton Hogan Engineer
b581737d-b9f8-4290-9dd3-1c948f488ae2 | checkpoint | 2.5 - Delineators
eb7fb324-0f17-5f0b-be3b-afca8d30cf44 | note | Frequency - Each Lot
49d465fd-285f-5a47-be64-1b7c6d45e6fc | note | Acceptance Criteria - Delineators shall be fastened to the top of w-beams, comprising of a flexible plastic mounting brackets fitted with 100cm2 of Class 1A retro-reflective material
66abdf83-7d6e-56c1-a331-f391afdd7280 | note | Reference Documents - 708.11
fb8ddf11-7179-5c5a-ac2f-e8d97c586f18 | note | Inspection / Test Method - Verify
169cd3f4-0d48-5c51-b043-ccd7967d94c1 | note | Record of conformity - This ITP signed off
16046928-db45-5968-964e-4828239e3a24 | note | IP
e381c259-0453-54fa-9c8f-5c00085939d9 | note | Responsibility - Fulton Hogan Engineer
c2cc5e51-862b-400d-994a-afb7000ad056 | checkpoint | 2.6 - Concrete Maintenance Strip
990c39e4-13c9-5a39-a92a-9c5b3fad279b | note | Frequency - Each Lot
2f7d9f26-f92b-50e3-98b6-d925debb5644 | note | Acceptance Criteria - •The Contractor shall provide maintenance strips beneath the guard fence and terminals as indicated on the drawings and/or as nominated in Table 708.121. The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock. Where the concrete maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced. Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post.
0117a389-5b95-54ed-ae01-a3e2f7349807 | note | Reference Documents - 708.12 708.12 (a) Table 708.121
830f2fba-e5a0-5d86-8332-e3d29269f066 | note | Inspection / Test Method - Verify
b7dcb80c-b517-50f5-9984-e7359d6382fb | note | Record of conformity - This ITP signed off
5d629728-d78b-5d58-8776-7c5b2ce3341f | note | HP*
2a391164-8176-5fe3-88d9-29827c1bcd12 | note | Responsibility - Fulton Hogan Engineer
93563f16-28e4-422a-b568-8f71f86fa5f8 | section | 3. Completion
6b37b4b0-201b-4f97-9d87-15a96f5a902b | checkpoint | 3.1 - Tolerance Conformance
665272ec-223e-503d-9acd-4c51f86599b5 | note | Frequency - Each lot
bd4fd00d-4152-549f-8927-7ab897f54e71 | note | Acceptance Criteria - •W-beam guard fence shall be erected to the following tolerances: (i) Variation from true plan position of posts ±20 mm (ii) Variation of line of w-beams from specified vertical profile ±10 mm (iii) Variation of w-beams from specified horizontal alignment ±20 mm (iv) Variation of posts from vertical +0mm, -15mm (v) Orientation of block &/or post w-beam +0mm, -15mm (vi) Dimension of holes -0mm, +50mm (vii) Top of bolt head relative to W-Beam -0mm, +5mm
d4bb4a25-bc29-5230-ab3d-e57eb4376604 | note | Reference Documents - 708.08 (d)
07e9004f-9f92-52b7-9b6d-5ca03966bc9d | note | Inspection / Test Method - Verify
5049be64-92f7-54c5-a95e-4e0a798348ef | note | Record of conformity - This ITP signed off
55d10e3b-9bdb-51f2-a9a5-72bb654325dd | note | IP
71fce3c5-1170-5265-a84b-0a16f43b9a2b | note | Responsibility - Fulton Hogan Engineer
ec69b706-0b62-4dde-9436-32fa7a9842c3 | checkpoint | 3.2 - Certificate of Compliance
c4a571ec-9237-5924-8a96-a28653b811f0 | note | Frequency - Prior to practical Completion
47a4995c-139b-521c-9259-fdb06770fde7 | note | Acceptance Criteria - •Further to clause 708.07 Installation, and prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract.
c3033788-e23b-50f7-b727-80148c37246c | note | Reference Documents - 708.1
c2a42967-db86-5b55-a1b5-302b55441166 | note | Inspection / Test Method - Verify
9b41e97c-86c4-5b6c-b78b-fb592ec774c9 | note | Record of conformity - This ITP signed off
5c22c211-1f4a-506e-9ac5-04e152aa752f | note | HP
3f7026fe-9428-522e-b4cd-62cf5df7fabb | note | Responsibility - Fulton Hogan Engineer/Superintendent
9adcaf2f-91d6-4357-8ebe-0282a261c728 | signoff | AUTHORITY HOLDPOINT
012b503a-2f15-4a80-9be4-c4de34de34cb | checkpoint | Final Inspection
dd8b8cff-9683-5226-bfcd-5011b42d5793 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ca8039ce-53a8-514a-acf2-286a78f4ebdd | textbox | Name:
bfbf2cf2-8951-5699-9108-bc758923e334 | textbox | Position:
5753d082-25e2-5527-8d68-f3fce184a0fd | textbox | Date Completed:
3b1014f6-17d5-4eec-94fc-a493f7843883 | signoff | Sign ITP
b44c53f5-2775-437c-a27e-382ef6cef6b0 | checklist | FHC-ITP-027 - Pile Footing Construction |  | FHC-ITP-027 - Pile Footing Construction
a9606d97-83a6-42bd-91f8-5f82cf6691c5 | section | Design and Submissions
6aed04b1-273d-4082-aa0c-2d2c06c25eff | checkpoint | 1.1 - Check for correct documentation
41b5fbfa-0c65-55f8-b8ec-2faa4920aa1f | note | Frequency - Prior to commencing any activity
d5cc93cd-55b2-547a-aada-21008d730254 | note | Acceptance Criteria - Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
5089950e-c80f-5435-b5f9-e658365c603a | note | Reference Documents - Drawings and drawing registers
9111c2bf-499b-5d3f-965b-1b1d616658cf | note | Inspection / Test Method - Visual inspection
dea63f20-213b-5aaf-8ced-3bd1091dcea6 | note | Record of Conformity - This ITP signed
84cb033c-daca-5e01-997f-3e89d32aefbc | note | HP*
29fa5ad2-b165-52af-9639-39630c863223 | note | Responsibility - Fulton Hogan Engineer
63278886-be38-4500-8788-af26c2095326 | checkpoint | 1.2 - Implementation of all measures and controls
ea76ea31-532f-55c2-9b86-d7d890adf4fe | note | Frequency - Prior to commencing any activity
68241834-6fda-587d-a3f2-753aae4a832c | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
a9ba51de-8f61-5a9b-8eb9-a856a13f19f3 | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
d93df1f8-33e4-53fa-83ed-e78584fc8df4 | note | Inspection / Test Method - Visual Inspection
27264cdb-f599-567a-a42e-1562aa52c91f | note | Record of Conformity - This ITP signed
a6b067f1-d2ed-5e57-bb6a-4db6f0ff7b4d | note | HP*
ff2d8007-1e3e-53fa-b409-5858451a86cd | note | Responsibility - Fulton Hogan Engineer
ca5438c8-ec72-43c7-af9e-bb86a9bd2747 | checkpoint | 1.3 - Approval of mix design
9e346216-a2f8-5c3a-a245-fb88a8604a97 | note | Frequency - Prior to the first concrete pour
c5c90217-dd4f-5eb0-aba8-33c1bcdfe4db | note | Acceptance Criteria - Structural Concrete Design & Submission ITP completed and signed.
cae5060d-a254-57c1-ad04-249a2157a854 | note | Reference Documents - 610.07
50feb7a6-d997-5b8a-8592-ed8c5fcd7970 | note | Inspection / Test Method - Verify
fb8b9322-83b6-588e-af87-6727f6ec55cb | note | Record of Conformity - This ITP signed
4d200d9a-c088-5d71-84a5-b35d440a0124 | note | IP
c3990c24-021a-5a85-a4a2-afc90ace4b68 | note | Responsibility - Fulton Hogan Engineer
77999047-2ff3-43c4-a3cc-d40bcc0e672e | checkpoint | 1.4 - Reinforcement schedule
55110260-2523-5174-af97-effa788da9d3 | note | Frequency - Prior to concrete pour
55b119ae-5ff3-58e3-a8e4-393b81ac0991 | note | Acceptance Criteria - Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
6f6f2bf9-d07e-5383-a41a-506ce80874ae | note | Reference Documents - 611.04
c285b9a7-ee78-5aac-b8e9-857101a1cd5e | note | Inspection / Test Method - Verify
8eb8ad1c-55ee-5ed5-8546-1faba1fb1bc7 | note | Record of Conformity - This ITP signed
8e79e002-9f44-5765-9ef9-4aa7a1cd60d2 | note | IP
35ae1da2-880f-5d46-915c-4fa82c4ec01d | note | Responsibility - Fulton Hogan Engineer
6a2de901-1239-4a24-bf1b-30ae5c9c5f15 | section | Construction/Erection of Formwork
55c3e925-f079-45ae-bed5-f25d88341991 | checkpoint | 2.1 - Excavation (Pile)
104e6d5d-d9db-542b-9c38-0df46a00178e | note | Frequency - Prior to concrete pour
8f6f5052-15db-53b0-b708-0281df1914ab | note | Acceptance Criteria - The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent. Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
732e1646-fbc2-5c4f-9bda-64971da9b889 | note | Reference Documents - 606.05
d2341ece-bd8a-5fbc-b916-beb8d7721e76 | note | Inspection / Test Method - Inspect
801b9b68-5fea-5454-9378-d7c6c7e9606b | note | Record of Conformity - This ITP signed
74ff7e1a-5463-56e6-8dba-6625c96e44cd | note | HP
a013ca08-b549-56f1-b157-f9e71392ddb8 | note | Responsibility - Fulton Hogan Engineer / Superintendent
ec1f205a-e28b-4f0e-a188-ee48b4ad0295 | signoff | AUTHORITY HOLDPOINT
17205d50-a2e9-4b0a-8456-4b27f996a539 | checkpoint | 2.2 - Construction Methodology
6948f667-bda9-5cac-b198-8327c2edcc85 | note | Frequency - Prior to erection
65fd2c44-e188-50eb-a88f-0c3fcf42479d | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
f35a01a1-e2e9-5f47-91a3-30e7bea414cf | note | Reference Documents - 614.04 614.06
21182d8c-272f-510e-81c8-6f68e02e0442 | note | Inspection / Test Method - Verify
d447e2ce-9cbe-5602-b203-250168abbbc7 | note | Record of Conformity - This ITP signed
e61fcd87-86bf-5412-b727-23ee52beb229 | note | IP
bf91616c-3cc2-5ea9-a3ad-220864fe4af9 | note | Responsibility - Fulton Hogan Engineer
9d26adc6-abcd-4f3c-96aa-ab8cbe38391a | checkpoint | 2.3 - Construction Methodology (Pile)
eccf29bc-83a4-5944-9713-1999ea6ccfdb | note | Frequency - Prior to construction
11fe077a-b0a8-51e1-a0c7-87d5668b385e | note | Acceptance Criteria - Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained. Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
1ff6f786-7e10-5fff-a123-45881c3e24d5 | note | Reference Documents - 611.10 606.06
7ac7d958-a9fe-57ac-91e4-c7d89ff30e2f | note | Inspection / Test Method - Verify
6be7516d-97d9-5875-9ceb-2ff616ae00ff | note | Record of Conformity - This ITP signed
4ba494f4-a406-51a1-8d40-9d482adc26e6 | note | IP
21875110-e14f-5b02-89e1-78347f66eb9e | note | Responsibility - Fulton Hogan Engineer
dd1745e9-9a7a-4110-ab19-7bb6a9270019 | section | Pre-Pour Planning and Inspection
19f0ab39-100d-4f55-bfb4-ed91ab89ad99 | checkpoint | 3.1 - Cleaning formwork
e266b62e-0aab-5cc0-9f3c-8c6a18532bbc | note | Frequency - Each concrete pour
fc2b384d-582f-573c-99ac-4e08baf63918 | note | Acceptance Criteria - Concrete shall not be placed until all foreign material has been completely removed from the forms
38dc67d8-e1b3-594d-970c-1f033bbb495c | note | Reference Documents - 610.18 (a) (iii)
0d851ab0-053e-5194-a2c9-54ab91cb0abd | note | Inspection / Test Method - Verify
29e51262-4b6c-5fce-a36b-c5fa1dae30ec | note | Record of Conformity - This ITP signed
aa2a2062-c5f1-5eb7-b5e2-f755ccb59765 | note | IP
a99b692e-e797-55ea-8da9-4436256e0df6 | note | Responsibility - Fulton Hogan
ba276b2f-ca59-4f68-9e57-30d791ac92f7 | checkpoint | 3.2 - Correct forms, reinforcements, rag bolt assembly and embedments
54e6d429-3681-5931-8731-015fc8d7c1f4 | note | Frequency - Prior to concrete pour
0d8cc00f-536e-55ea-885e-6d77f679628f | note | Acceptance Criteria - Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. Pre-pour checklist completed and signed.
9ffb4e76-cecb-5eda-b50f-810ad09fe976 | note | Reference Documents - 610.18 (a)
9d1195ca-283e-50dc-94b7-16b69b16e8dc | note | Inspection / Test Method - Verify
f9635a85-c86b-5b08-8bb0-f7bec1da408c | note | Record of Conformity - This ITP signed & Pre-Pour checklist completed
39ae11c6-5e5e-53fc-ab8d-35a1ebc1c93e | note | HP
55762235-099b-5d8b-9833-bfbe662e6241 | note | Responsibility - Fulton Hogan / Superintendent
1bcdc184-7551-4e98-9022-449d472b8025 | signoff | AUTHORITY HOLDPOINT
59e1fa3f-5c96-4dc0-bbe8-6a9cf6b0fc07 | checkpoint | 3.3 - Reinforcement assembly of piles
80d032e7-90e4-5566-8d31-31aa7096a40b | note | Frequency - Prior to concrete pour
7fe3e4bd-af03-5ff7-b139-f3bf2a4b6293 | note | Acceptance Criteria - Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
2b7e5ef5-a494-514b-ba6e-e709e5a6d939 | note | Reference Documents - 610.17 (b),( c), (d)
11be937b-083e-516e-bb3d-3c569ba932d8 | note | Inspection / Test Method - Verify
763cc17b-d87e-5830-b119-0de7e58f5675 | note | Record of Conformity - This ITP signed
24ffe73d-2479-5b7d-9683-21972940042b | note | HP
42629505-5ab9-5e9c-a867-45b62ceaa243 | note | Responsibility - Fulton Hogan
f9cfa77c-c435-4c1d-9ecb-41df250c24f4 | signoff | AUTHORITY HOLDPOINT
79676b3d-6c02-4ca8-948d-008ec9baed98 | checkpoint | 3.4 - Monitoring weather
6c4637e7-4ac8-5d64-a011-3a6754014dde | note | Frequency - Prior to concrete pour
152e0784-f8b1-56b6-8684-6a57e79013bf | note | Acceptance Criteria - Concrete shall not be place when temperature is <5°C or > 35°C All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
c5995841-d4f7-58b8-a78b-784a4b2567fe | note | Reference Documents - 610.17 (b),( c), (d)
e86fd3a5-03e6-5b94-ae1a-71b0c2bc075f | note | Inspection / Test Method - Verify
8baa2e9d-cefc-5d08-a3ed-38bb1ce35663 | note | Record of Conformity - This ITP signed
04c43df5-0f35-59e3-8605-c2f780f0a29a | note | IP
b6023ca2-16cb-5781-84ec-19046c0bbe60 | note | Responsibility - Fulton Hogan
d160cb7d-efb0-407d-b9b4-bb5bb32d9110 | section | Placing and Finishing Concrete
06f7f196-c73a-43fb-ab64-cefb6226feca | checkpoint | 4.1 - Carry out sampling of concrete
faee9827-b11d-598d-8cde-da7ee69d4187 | note | Frequency - Each concrete pour
dd88ce79-7eb7-526a-bcfe-8e84335fbda8 | note | Acceptance Criteria - Sampling in accordance with 610.16
ba56bd2d-8e7e-531b-8811-e9f150ab5bf0 | note | Reference Documents - 610.16
44342323-a7cd-516c-860d-fb497500dcda | note | Inspection / Test Method - Checklist
2b8f272a-e701-5daa-9692-fef959cf4fb0 | note | Record of Conformity - This ITP signed
dd1679b4-7e6c-52c1-a214-98acd2b4c7a9 | note | IP
b6c21dd2-17c1-5f28-bced-acb0435f8dc6 | note | Responsibility - Fulton Hogan
38fd1056-9930-4a44-aa43-20482f6dd8dd | checkpoint | 4.2 - Discharge time
dad6b884-d4d4-5be8-9bde-e3d30b319f25 | note | Frequency - Each concrete pour
de46c082-818a-52d4-9667-c1b729bb9b13 | note | Acceptance Criteria - Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. Batch to be used has a discharge time of 180 minutes.
33282b20-955b-5962-99e3-a39de2d849c1 | note | Reference Documents - 610.13
25f0b82f-ffdc-5861-9a49-45459af90b34 | note | Inspection / Test Method - Verify
acd2881d-cb67-5284-a970-7ee840a796bc | note | Record of Conformity - This ITP signed. Accurate Site Notes & Load Mapping
d6c7f8e0-03fd-5a70-bdb1-5f88fa26db3f | note | IP
71a193bc-0cf1-5cb7-ba40-5ef170ebee8b | note | Responsibility - Fulton Hogan
2c760b5c-1d46-4bbf-871f-c77200b573ef | checkpoint | 4.3 - Methodology of placement (structural)
5191d644-6362-5021-a4dc-9ee9255c9342 | note | Frequency - Each concrete pour
e72d49ff-6adf-568b-99f9-1a8a0d6bfb6f | note | Acceptance Criteria - Concrete shall be transported, handled and placed in a manner that will prevent segregation or loss of materials In continuous pours the max. time lag between truckloads on site is 25 minutes
60620b75-3adf-5718-9a40-9b26ecfb9a37 | note | Reference Documents - 610.18
3384093f-d743-53db-96b5-52ca61313fba | note | Inspection / Test Method - Verify
35ccd945-f007-5aa4-a080-a90a73ed21b7 | note | Record of Conformity - This ITP signed
435ccc89-1b94-5123-a666-c838d7e91ec4 | note | IP
a235b76b-499a-509f-8354-063ee8a3b024 | note | Responsibility - Fulton Hogan
d41a7348-257d-4c22-9354-9be74bc96e0b | checkpoint | 4.4 - Methodology of placement (piles)
d62e3a04-2ad7-553f-a867-23db2c60ba86 | note | Frequency - Each concrete pour
d40e2577-0309-5433-b92f-6055db88b3c5 | note | Acceptance Criteria - Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation. Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
9f98a56c-3d0e-5e6a-a936-cb7252789ef0 | note | Reference Documents - 606.03(b) 606.05
472dbe60-9d17-5669-8f60-a5c91dc116e2 | note | Inspection / Test Method - Verify
d872d330-c818-597d-aff1-96695a23698a | note | Record of Conformity - This ITP signed
e59cfb15-2488-571c-9005-517251794ba4 | note | IP
7bbdcd88-b0b1-5b93-88e2-cef4c90b0db8 | note | Responsibility - Fulton Hogan
340c9a40-014e-4119-b2d7-4cb5bf6139eb | section | Post-Pour Details and Inspection
97201dd0-7470-4848-911e-97b8348ca8dc | checkpoint | 5.1 - Curing
6b2ec9f9-26e7-5c4f-a7f6-f0c54df1498a | note | Frequency - Each concrete pour
b77ffcd8-01df-59e0-aefc-a9bcc69ebb73 | note | Acceptance Criteria - Sufficient time shall be given for the concrete to cure prior to loading.
924bc59d-e5bf-569f-830c-8955c19313b9 | note | Reference Documents - 610.23
f48c59d3-0c42-5c5b-90c5-5ffbebad1853 | note | Inspection / Test Method - Verify
eec77213-632c-5d99-98e4-37f8d5faf11e | note | Record of Conformity - This ITP signed
f76c478a-f448-5857-a287-b40547b4a573 | note | IP
814fdc63-3d0f-5338-8aa9-c4c772db32e8 | note | Responsibility - Fulton Hogan
d416af72-8ef1-4f05-837b-ab35a4c3e107 | checkpoint | 5.2 - Formwork removal
62c75727-4e20-5d69-b8bd-6ae76fb0093d | note | Frequency - Each concrete pour
30956ed4-2d67-54a2-85da-514daac270ea | note | Acceptance Criteria - Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
11460b4f-fffd-5851-98a4-1ef2ddbb3856 | note | Reference Documents - 610.25
cf54a589-066b-55e8-8bf9-802c0cab5bf5 | note | Inspection / Test Method - Verify
cef41683-1980-5506-be0c-685c3bb96fb0 | note | Record of Conformity - This ITP signed
c5fc8f30-71f4-53df-ba79-bac53dc2f563 | note | IP
ca7d804c-dd0f-5cba-9d41-cce29e50774d | note | Responsibility - Fulton Hogan
fe0a317d-c234-4f51-99b6-9c771b3654f1 | checkpoint | 5.3 - Positional tolerance and dimensions of concrete members and piles
be793b8f-8805-5c94-9006-a5911b7761ea | note | Frequency - Each concrete pour
ead02442-53fd-5ff2-9656-27cf9da3086f | note | Acceptance Criteria - The centre of the pile head shall be in the specified plan position ±75 mm;
c80f312e-1a92-5043-9c85-e1ff51916959 | note | Reference Documents - 607.06
b3cebe4d-1cc7-5fc3-ac47-f0377a83e72b | note | Inspection / Test Method - Verify
8d0ec1e8-28a7-58f7-a540-3c98c1caeb99 | note | Record of Conformity - This ITP signed Post Pour Checklist completed
1f8f02b9-cea6-5ec5-915b-8356b80b89fe | note | IP
59b4166c-f7bc-5a3e-a681-cee2829555fd | note | Responsibility - Fulton Hogan
4d00edab-6aac-49d6-a3a7-81ee24c361ad | checkpoint | 5.4 - Concrete Sampling and Testing
a09c58dd-dd0b-576e-b7e6-dafe3f6ced57 | note | Frequency - Prior to lot closure
1691a350-b210-59b7-845e-2f9324914400 | note | Acceptance Criteria - Concrete sampled and tested for Compressive Strength: - 2 cylinders @ 28 days Compressive Strength=32MPa - 1 cylinders @ 7 days for Compressive Strength=20MPa
bb036c42-6f29-5742-8a7e-da9915f28b1d | note | Reference Documents - 610.05 610.06 610.13 610.16
1d7416e5-d528-546d-bf77-21274c7ccf38 | note | Inspection / Test Method - Verify
95fb1b75-5ee6-5c2a-83f4-f2fbf92e91ac | note | Record of Conformity - This ITP signed
5726aa87-1c3a-51da-988f-05da1bbb3298 | note | TP
9cf89bae-1b5e-551c-9486-1ed071d0a994 | note | Responsibility - Fulton Hogan
98102819-03e1-481a-ab26-68af6f449bd4 | checkpoint | 5.5 - Protection of Adjacent Piles
2d2fc5a0-0c39-508c-9be6-a6688672a2e2 | note | Frequency - Prior to commencing any piling
b2e8ac37-bff0-518a-842c-e7fc1b76d8a3 | note | Acceptance Criteria - No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa. Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
86eb7f8c-3ab7-5e46-a3bf-81e630b8527e | note | Reference Documents - 606.04(a) 606.04(c)
e6e14890-595c-507c-94e8-eaf3b7fbd743 | note | Inspection / Test Method - Verify
2351f335-8221-5b4c-a897-5b118a1b2427 | note | Record of Conformity - This ITP signed
3c4cc24b-eaea-54c0-9b0e-20878168a82c | note | HP*
8a3240af-7eca-5d38-b292-cf63ca5d21c5 | note | Responsibility - Fulton Hogan
4fd8e4ce-331c-4d7c-863e-142326f7e3c3 | checkpoint | 5.6 - Testing Post-Pour
e1797f58-9370-5757-b5f3-11569e77fab2 | note | Frequency - Prior to lot closure
413b5e4f-993e-5d82-ace1-7ac592732849 | note | Acceptance Criteria - Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
13801b1b-5146-5cc6-b435-99e55b00741a | note | Reference Documents - 606.07
0e7f76c6-0588-51af-ad12-cb20a22bcdaa | note | Inspection / Test Method - Verify
33bde039-ac34-53c4-9804-2acb9bfba7e9 | note | Record of Conformity - This ITP signed
4e97a354-3c72-5172-96a4-a4126c64da03 | note | TP
fe3ed722-af6a-58a3-9679-98b9acaad95b | note | Responsibility - Fulton Hogan
66c81391-2390-4652-9da1-2114912acd1e | checkpoint | 5.7 - As Built Drawings
fc5624dc-f5b1-5e19-8f57-612a07e96b01 | note | Frequency - Prior to lot closure
c826f6f4-31ea-5541-b538-241403f8ba89 | note | Acceptance Criteria - Recorded of as-built drawings
ca3d3e80-e4de-5149-be29-91406315d872 | note | Reference Documents - Fulton Hogan Procedure
1fd47524-96d1-57dc-b4b1-1746c7931d24 | note | Inspection / Test Method - Verify
19995901-d6d7-5e4d-8332-decd8eaa709a | note | Record of Conformity - This ITP signed
a1030f85-90d4-56da-af70-ffa7df4b4ecb | note | IP
010bdfda-ddee-52b7-91e4-2d557d9c0f33 | note | Responsibility - Fulton Hogan
d3d581e3-d49d-4d8e-a579-369bb77cb50e | checkpoint | Final Inspection
7addda81-6635-50fe-ad77-0aacdf678c00 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5b88f1cc-2273-504c-a2c0-5e1442b31792 | textbox | Print Name:
613a9401-f597-5261-a635-af34abe6abca | textbox | Position:
33c004a5-b7fa-57ff-b9cc-5653b0f99fc4 | textbox | Date:
76baba92-18e4-41b5-a110-1b32d1d19bf3 | checklist | FHC-ITP-028 - Chainwire Fence Installation |  | FHC-ITP-028 - Chainwire Fence Installation
f84e2d69-673c-4d6c-8bce-b211dd2c5c35 | section | 1. Preliminary Works
6f2ab2a2-3620-4a64-a16e-3ea807bd42ff | checkpoint | 1.1 - Check for correct documentation
f1f848dc-ea0f-51b3-b492-45d29abb503c | note | Frequency - Prior to commencing any activity
6b8bedf0-de2e-57c9-a689-4c8962e4201f | note | Acceptance Criteria - •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
29d000db-9534-51ae-9069-126f206ca957 | note | Reference Documents - Drawings and drawing registers
2f506c04-b794-55cc-997b-f1225fd83fa4 | note | Inspection / Test Method - Visual inspection
8de5c2c5-daa8-52ab-96ac-69d7ad1e6940 | note | Record of conformity - This ITP signed off
a3bcb40a-8175-5252-a0db-1b119d9ec668 | note | HP*
934bf545-e668-5531-9f78-1c7fbc897cd0 | note | Responsibility - Fulton Hogan Engineer
265e3327-bdef-4f38-98c0-b3ff998ffd84 | checkpoint | 1.2 - Implementation of all measures and controls
fe54d71d-784e-5033-a319-a7f4595fc122 | note | Frequency - Prior to commencing any activity
f85b078b-2474-5f39-afc2-0685eb2e38b0 | note | Acceptance Criteria - •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
3a530e2b-85dd-5ca6-b907-420ed1d81d77 | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
7acfa4f9-a16c-5602-be1a-dda95e8263d1 | note | Inspection / Test Method - Visual Inspection
cf4886e2-f3df-56b0-b0f5-b9d27bc5881d | note | Record of conformity - This ITP signed off
a822cb14-253b-5ba4-9658-2ac96a0041fc | note | HP*
1b1852fb-0224-5794-82df-ccc789253eec | note | Responsibility - Fulton Hogan Engineer
fd4c1950-0f22-416e-8cee-ee7656f2bfa4 | checkpoint | 1.3 - Check Materials
02db23d2-1454-5e5e-8a07-803eb9870b61 | note | Frequency - Prior to commencing any activity
63e2f963-30ad-53e5-9f8e-5410ae056ae7 | note | Acceptance Criteria - •Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of this specification 707 and drawings.
3b84b0b6-0495-56ba-9332-e54852a70a53 | note | Reference Documents - Fencing Plan
3c57a8a3-d952-5996-9065-2eae448428a6 | note | Inspection / Test Method - Verify
c72f86d2-467b-5d39-a2b5-b2744e996613 | note | Record of conformity - This ITP signed off
78e0f710-58a7-5a8c-9528-00d2eec1092e | note | HP*
bbbb8cc1-861e-5437-9cf3-f2891c344602 | note | Responsibility - Fulton Hogan Engineer
c77d6a45-3d14-4f71-95eb-f89fe9859fac | checkpoint | 1.4 - Confirm Footings position
160ab173-1896-5e83-8141-5e6912b968be | note | Frequency - Prior to commencing any activity
5ad43c81-a8ad-560d-9edb-14f7d8a178ca | note | Acceptance Criteria - •Confirm footings are set out to locations specified on design drawings
12afa890-549b-5881-8721-4f9a95562d85 | note | Reference Documents - Fencing Plan
1df55258-d226-5c14-866e-49eb967501fe | note | Inspection / Test Method - Verify
18f8d9df-1d9d-507e-ac91-669dfc64a5ac | note | Record of conformity - This ITP signed off
7a8af642-3e58-5651-8944-c0ea01fced64 | note | HP*
78a3d0bd-d37d-5ecd-906f-49b9f5eb8531 | note | Responsibility - Fulton Hogan Engineer
662fe7b2-a5a4-4f93-880f-b8e4110c2627 | section | 2. Construction Works
69bb0463-6849-4f30-a2da-444007474ab1 | checkpoint | 2.1 - Footing Installation
d4c3bb71-2d04-5366-b4ce-6a5d7857e81f | note | Frequency - Prior to post installation
5e3b9970-659a-54c1-a59f-ca15d4c899c6 | note | Acceptance Criteria - •Concrete shall be of minimum strength N20 •Concrete footing shall be 600mm x 300mm for intermediate posts •Concrete footing shall be 900mm x 300mm for end panel posts
709bfc32-5e1a-5a49-90aa-f7f4bf981c13 | note | Reference Documents - Fencing Plan SD3131
5114ef6e-b0d2-58c5-87bf-46391b9b8736 | note | Inspection / Test Method - Verify
0d1a433c-f1b6-57d5-919a-1a74c19b793f | note | Record of conformity - This ITP signed off
d63543f1-a5eb-5f19-9ba3-62aa965c1d5e | note | HP*
39cc1ba8-c8c0-5a6d-b7ff-a76f15090339 | note | Responsibility - Fulton Hogan Engineer
9cc67355-8465-48eb-a234-a0420990109b | checkpoint | 2.2 - Post Installation
70d1e8de-2c51-5c62-9925-e46fb2ad60d6 | note | Frequency - Each Lot
1e5681c0-ea52-568c-9a21-6b081e385cac | note | Acceptance Criteria - •Posts shall be set in concrete footings of the dimensions shown on the drawings •Posts shall be Installed to concrete surface in culvert area with baseplate and bolt assembly
9b6831de-9083-56f0-a4b7-b1b6e58063e9 | note | Reference Documents - 704.04 (d) AS1554 Fencing Plan
beeeb6c8-666c-5e6e-a85e-8e14ef61e9a2 | note | Inspection / Test Method - Verify
d42ee11e-5c84-5fac-b265-9effb313a893 | note | Record of conformity - This ITP signed off
37a9ad2e-410c-5516-9da4-be1d2d0d0062 | note | HP*
6a69d380-a5ed-55d4-9a26-2596c8294ec7 | note | Responsibility - Fulton Hogan Engineer
e754c90a-bef3-407e-90b5-bf8001cf9b65 | checkpoint | 2.3 - Grout Installation
2b1aa9f7-9834-588c-9a8a-df0b8a7f8b4b | note | Frequency - Each Lot
99b56842-b91c-5c76-a593-a4c7c65f41b9 | note | Acceptance Criteria - •Footing surface shall be cleaned and roughened before application •Non shrink dry pack grout shall be placed under base plate where applicable in culvert area and footpath areas
5a3bc675-819a-5fd0-8e05-7286105beb97 | note | Reference Documents - AS1554
b4eafce0-127e-5dbd-a656-560bbdaa4629 | note | Inspection / Test Method - Visual inspection
f0728167-80c1-5255-973a-80b720c02c37 | note | Record of conformity - This ITP signed off
4bcb7323-c6f5-5850-aba7-6c272043679c | note | HP*
cfc0c3e6-8bf8-59c4-a098-2c0c7df7b727 | note | Responsibility - Fulton Hogan Engineer
c5752fac-2c62-4787-af36-ff0bb58900f9 | checkpoint | 2.4 - Chainwire mesh fence
39752257-91ed-5ea0-b550-af98be6d7a6d | note | Frequency - Each Lot
0f2e228d-54d1-5397-bdbc-b10409a8bc7f | note | Acceptance Criteria - •End, corner and gate posts shall be braced as shown on the drawings. Line posts shall be braced as shown on the drawings at not more than 120 m intervals. Chain wire shall comply with the requirements of AS 1725.
e416d5bf-0e67-55a6-87d8-5da2fd80cc45 | note | Reference Documents - 704.04 (d) AS1725
0f482765-a0ed-5b79-a7de-40ace47465de | note | Inspection / Test Method - Visual inspection
b79f944c-7795-533c-ae05-ec3ca374a5e8 | note | Record of conformity - This ITP signed off
669c7527-133c-5872-ad7d-5573136d9d59 | note | HP*
fd37c1b4-21ff-51b0-9db9-b065120448e8 | note | Responsibility - Fulton Hogan Engineer
ec6b6e7c-29ef-442c-9e51-5e216cad40f5 | section | 3. Completion
a34d3411-f254-4ad2-b363-b65b5e5ec021 | checkpoint | 3.1 - Clean up
642344e2-86c9-5bbc-8f04-f4236fa7ed0f | note | Frequency - Post Completion
321c720b-c37f-5696-9f4a-c441055406e3 | note | Acceptance Criteria - •Personnel to ensure all chainwire is tied off and that work areas are clean and free of excess materials
b9ee018b-fb23-5a29-8389-0eaf0ec1a497 | note | Reference Documents - Fencing Plan
37fb5f30-3016-552c-995e-28f031f0fe86 | note | Inspection / Test Method - Verify
6c918e78-f54b-5fb3-aea0-3b62a4ffe71b | note | Record of conformity - This ITP signed off
f2dc229e-b872-54a6-83e2-37364806398f | note | SCP
93689d7c-e633-5bd1-b3dc-fb972649a840 | note | Responsibility - Project Engineer /Surveyor
3e25983d-388b-4481-9564-712e1f81b8dd | checkpoint | Final Inspection
6d1536f7-1642-5030-ad66-a4be6526dbfd | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
8bb6916f-6319-5952-a733-4004649fcf52 | textbox | Name:
2d4541f0-3854-5b03-87e8-7e64a6640585 | textbox | Position:
87927487-63b9-5bf7-b33c-c9b7d4f99fa0 | textbox | Date Completed:
44b9fb03-70f2-4133-a931-aedc20387dba | signoff | Sign ITP
5dac2a26-33a3-4b02-bf16-93bd762cf9aa | checklist | FHC-ITP-029 - Farm Fencing Installation |  | FHC-ITP-029 - Farm Fencing Installation
5b2dab98-e2db-4ee7-bae8-f16c600d8f4d | section | 1. Preliminary Works
d7e137d9-9087-4e29-aca0-d8e4858721e4 | checkpoint | 1.1 - Check for correct documentation
58e15f3c-ad94-5204-bcef-0edc3a7d5d47 | note | Frequency - Prior to commencing any activity
17636e9f-2b5e-506a-817d-a5608c538e4e | note | Acceptance Criteria - •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
cf7f62dd-8b1c-5dd0-b495-a2c0bfbbf0a6 | note | Reference Documents - Drawings and drawing registers
765c34f8-bcf1-5fdc-b3ba-53f566783983 | note | Inspection / Test Method - Visual inspection
f9c4c1e9-3ba1-5346-a999-0cd2ec8c7de9 | note | Record of conformity - This ITP signed off
bf1230ae-ce3e-5568-9963-5ff2bbacbaf4 | note | HP*
ffa00218-dea7-5cd6-b034-40d0a5b40cf1 | note | Responsibility - Fulton Hogan Engineer
f9512a37-b163-49a9-b6c5-e5f322c422ff | checkpoint | 1.2 - Implementation of all measures and controls
83f577c1-3228-556c-aac5-1a7c1fcdfe21 | note | Frequency - Prior to commencing any activity
a52d2f04-417e-5c31-81e5-8ce971540b09 | note | Acceptance Criteria - •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
49dba2ad-4a95-57ca-b27d-b6f0a93589cc | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
c2babec4-860b-5cb4-8d35-c9918e780fe4 | note | Inspection / Test Method - Visual Inspection
d5fc0b08-59ea-5788-beee-c393eb863f29 | note | Record of conformity - This ITP signed off
713f87e9-3df1-5e14-bb0a-c4059cbba2a3 | note | HP*
ff3c6058-151b-5eb2-b7b8-9ca5deda038d | note | Responsibility - Fulton Hogan Engineer
3f679507-340a-4cbf-98e9-76bca33a7c41 | checkpoint | 1.3 - Check Materials
e593f8c3-b0d5-5867-8ada-9325ec8521e5 | note | Frequency - Prior to commencing any activity
2f210596-9b35-5781-bd29-89a724a734e2 | note | Acceptance Criteria - •Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of this specification 707 and drawings.
4fd81507-79fa-5da9-8408-85877dde7666 | note | Reference Documents - Fencing Plan
a1dfaf04-3794-5b05-82ae-e2a668aeaab9 | note | Inspection / Test Method - Verify
f43befb5-ef93-5249-b95d-dcdb062146a2 | note | Record of conformity - This ITP signed off
bf451e1d-476e-5b07-99f3-a21bb8606cd8 | note | HP*
905392db-93bf-5074-893f-14e73897c77d | note | Responsibility - Fulton Hogan Engineer
e80a4d1c-229b-434a-8a51-fb3a4073eedc | checkpoint | 1.4 - Confirm Footings position
5afb240e-8365-58c0-8909-e4f9d5039b29 | note | Frequency - Prior to commencing any activity
9eb2ee5e-af8a-5a3a-98de-b357e4f05c05 | note | Acceptance Criteria - •Confirm footings are set out to locations specified on design drawings
167b0d1f-20de-540b-a1c4-910725a54b78 | note | Reference Documents - Fencing Plan
4c67d7a9-7438-502d-8108-beada4ed734d | note | Inspection / Test Method - Verify
7cab2207-7de3-5599-8fc5-5a29c965108d | note | Record of conformity - This ITP signed off
b2f6a6f1-a064-520a-8460-06dfcacbb289 | note | HP*
4c4ca6a5-bf47-5622-80b3-273dc6b4a8c4 | note | Responsibility - Fulton Hogan Engineer
4ec4cf8e-3169-4947-ac4d-14ab34c22fed | section | 2. Construction Works
94a1a846-fba5-4e84-8ffa-3e04c17066e8 | checkpoint | 2.2 - Post Installation
02c414db-e485-5e62-b6dc-3f46bc8a3b65 | note | Frequency - Each Lot
7993839d-19d8-54f0-94e0-b1a3bbe53406 | note | Acceptance Criteria - •Timber and concrete posts shall be set in dug or drilled holes •Posts shall be set solidly and any space left around the posts shall be backfilled and the backfilling compacted. • Concrete Shall be 20MPA strength grade complying with the requirements of AS 1379/1991
2f390824-b88b-573e-b6b0-b6cffcbe5239 | note | Reference Documents - 704.04 (a) AS1379 SD3161 Fencing Plan
074bf359-d7ae-530e-95af-386252113ece | note | Inspection / Test Method - Verify
6bd2b0b8-a0dd-5315-a15d-51fab368271f | note | Record of conformity - This ITP signed off
f6391452-885c-560f-8cc3-5c015abe3462 | note | HP*
438533ff-98a8-56a6-82f3-b6843d4edf3c | note | Responsibility - Fulton Hogan Engineer
65bd9b2e-f09e-4ae5-a1d1-e204e5388d9b | checkpoint | 2.4 - Strainer Assembelies
e1fc5fb4-eee9-5ec2-9073-c22daa8bf8ec | note | Frequency - Each Lot
0a2bb904-acb7-52f8-aea4-ac226ef33ea6 | note | Acceptance Criteria - •Strainer assemblies shall be provided at all ends, angles, abrupt changes of grade, and intersections of cross fences as shown on the drawings. Intermediate strainer assemblies shall be provided on straights at intervals not exceeding 200 m, and spaced to the best advantage in the circumstances.
06398d3c-4b05-5284-9f95-cd4bee6525ea | note | Reference Documents - 704.04 (a)
f74b69b2-3afe-58d2-980e-b61dbc8d7210 | note | Inspection / Test Method - Visual inspection
b1fbf030-b136-5d1a-8843-4a76a957939b | note | Record of conformity - This ITP signed off
a1fb2f0f-fd5a-5f79-940d-5f2881d54d18 | note | HP*
1448f066-1149-5c00-80fe-eda13d0fad60 | note | Responsibility - Fulton Hogan Engineer
0ae35c30-3451-4a58-a28e-b1da3804b050 | checkpoint | 2.5 - Strainer Assembelies
877dea77-21c5-52f4-8a8c-e3428f72b0c3 | note | Frequency - Each Lot
c695a180-019b-54f2-8ab0-1ee0639da8d9 | note | Acceptance Criteria - •Plain wires shall be reeved through holes drilled in the posts except that where treated round posts are used wires may be attached with staples after straining. The length of staples shall be 50 mm for pine posts and 40 mm for hardwood posts. Barbed wire shall be secured with galvanized tie wire of not less than 2.5 mm diameter passed through holes bored in the posts, and twisted to the barbed wire on each side of the post, or shall be stapled to treated posts with staples.
fe3ec95b-a578-5179-9ed2-a9e967061ff4 | note | Reference Documents - 704.04 (a)
d9e3290e-cc8a-5d6e-9a7f-387724628b21 | note | Inspection / Test Method - Visual inspection
77ef5a65-cf3e-5621-8612-8bbfde697f61 | note | Record of conformity - This ITP signed off
c4cd5ce3-cf6a-593a-9964-44aed147c568 | note | HP*
4eec887a-410b-54ee-8b97-674d68b7091b | note | Responsibility - Fulton Hogan Engineer
dbdb67ee-1a35-4248-8780-bc29e4e3931d | section | 3. Completion
f143f55d-1f43-4f8f-a7ce-008d3ab5830e | checkpoint | 3.1 - Clean up
097a9a10-9d54-5d35-ad99-bab87b25e513 | note | Frequency - Post Completion
1ad9e8af-7299-521a-ab77-8b459f897cad | note | Acceptance Criteria - •Personnel to ensure all chainwire is tied off and that work areas are clean and free of excess materials
0e3d0f88-d7c0-56f9-b4c5-dea6ae05b724 | note | Reference Documents - Fencing Plan
792692e0-ad58-5db3-b64b-993f6ced06fb | note | Inspection / Test Method - Verify
166478f7-1142-5352-ab0b-b340b3935d76 | note | Record of conformity - This ITP signed off
5188103c-7762-51d8-aa67-327c54d47347 | note | SCP
e0cec0ea-7f0a-50af-89d2-dc97600cc9c9 | note | Responsibility - Project Engineer /Surveyor
914c182f-fe7a-4aa4-868c-6fda68393cb8 | checkpoint | Final Inspection
3329fad5-4dff-51b0-9874-f6ae43bd06e7 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
bcc9ec5e-7105-54e0-b2c1-2006340a5302 | textbox | Name:
b9e19729-ec6a-5e07-92ad-b7beb92bd8e0 | textbox | Position:
ab15945a-be45-53cb-807c-c47c54a77198 | textbox | Date Completed:
d8d9e0a9-6915-4837-83b7-fc9230118aa5 | signoff | Sign ITP
280e55ce-e6f0-4e29-9b8d-448eea942652 | checklist | FHC-ITP-030 - Handrail Installation |  | FHC-ITP-030 - Handrail Installation
830d8c59-4c8a-4e4a-9202-99fa52905ea2 | section | 1. Preliminary Works
c7e3a08d-7b11-41c7-87dd-c27df4892e0b | checkpoint | 1.1 - Check for correct documentation
cdef91a5-e9bf-54d1-a621-58c796a9468f | note | Frequency - Prior to commencing any activity
998ef057-fbda-5276-a9b1-775c1561ef3b | note | Acceptance Criteria - •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
db9f1c5e-730c-54fb-947e-2e420ece11d0 | note | Reference Documents - Drawings and drawing registers
e50af984-fab9-5891-ad1b-c079c8fc6b23 | note | Inspection / Test Method - Visual inspection
cf513f00-031d-5c47-9ad2-eabe25086163 | note | Record of conformity - This ITP signed off
c335e963-e668-52cf-9f67-409ed72a8415 | note | HP*
d73dea9b-eab7-5751-bf92-ae6c1521d5a4 | note | Responsibility - Fulton Hogan Engineer
b09f8d05-13fd-44c6-a332-952012dd1100 | checkpoint | 1.2 - Implementation of all measures and controls
8f0d822e-b386-53c5-add1-7c7302b2ed8e | note | Frequency - Prior to commencing any activity
b6e57b06-496b-55bb-ba9a-87575be23d32 | note | Acceptance Criteria - •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
c2c3070a-5df3-5d67-a49f-8a4c4aaed1bd | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
cb76cbe2-6bef-5718-873c-8285fd06f035 | note | Inspection / Test Method - Visual Inspection
5daeee91-e8fb-5d88-8ae6-2e8f1ac28641 | note | Record of conformity - This ITP signed off
622d1a50-07b6-557d-8e15-9efd2f41af57 | note | HP*
96a943c3-ced1-5717-a61c-2760511f5c96 | note | Responsibility - Fulton Hogan Engineer
ec113164-e2c8-4f3f-9bda-b178d092c96b | checkpoint | 1.3 - Check Materials
5637fc7d-f6dd-53a0-a64d-b25cb6435641 | note | Frequency - Prior to commencing any activity
5912c938-2f8f-516c-aa29-ee3023b83819 | note | Acceptance Criteria - •Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements.
f3100c31-415b-5222-afc1-3e71d487fb5d | note | Reference Documents - Fencing Plan
39a412c3-aa0c-5675-aaf6-2f3e0d03d540 | note | Inspection / Test Method - Verify
87ed748b-c829-52fe-b0dd-3c9b378984cf | note | Record of conformity - This ITP signed off
65c47753-c863-5526-b8bc-382aab07ceb0 | note | HP*
40676ad0-3514-5f07-9d6a-1327a05c133d | note | Responsibility - Fulton Hogan Engineer
d9cc29f2-be4f-49f3-b90c-a41d47e370e7 | checkpoint | 1.4 - Confirm Footings position
56687d8d-60be-5197-9e1b-1e43eecebe2f | note | Frequency - Prior to commencing any activity
8adcbd97-1fb3-5c2b-8086-87ba690bf3d6 | note | Acceptance Criteria - •Confirm footings are set out to locations specified on design drawings
1f43ee87-16b0-5d6b-8797-bbb6dfff42ce | note | Reference Documents - Fencing Plan
a2c023ca-2a28-5c8c-b25a-c5ef4e70f593 | note | Inspection / Test Method - Verify
428d5046-9ef7-5454-bc90-d15dd9f141e9 | note | Record of conformity - This ITP signed off
7efbe9c1-ca5b-5cd5-9150-f5a868d30978 | note | HP*
f14b2c4b-2a12-545f-86ee-ba6dd321eb14 | note | Responsibility - Fulton Hogan Engineer
fc17b64a-b668-48b5-964f-6684b8448fc0 | section | 2. Construction Works
11a4c844-5131-4935-93fa-df36f04d584b | checkpoint | 2.2 - Post Installation
12a53c20-bf24-5c2d-a373-18475535fc85 | note | Frequency - Each Lot
366cd23a-03c6-5734-bcb5-4b326d132e4b | note | Acceptance Criteria - •Hand rail stanchions spacings to be 2000mm maximum •Hand rail base plate to be fixed into concrete with 2 x M12 x 100mm screw bolts
2e49fa10-f369-50aa-93d9-ee0c5bf1aebf | note | Reference Documents - MDX installation guide Fencing Plan
b52f2498-f2b8-5a9f-9c50-2d42ba2ae032 | note | Inspection / Test Method - Verify
69fa3c85-d4ee-5de3-a853-e63f20c156f9 | note | Record of conformity - This ITP signed off
08d5b668-a010-5155-9a78-f37e133bbd29 | note | HP*
518721b9-d6bb-521d-9605-3437937682e0 | note | Responsibility - Fulton Hogan Engineer
c96a55f1-4c26-40a9-bfea-e1e36df79356 | checkpoint | 2.4 - Rail assembly
de80c316-6a9a-5044-b9ef-1a8a9792d95a | note | Frequency - Each Lot
47eb042f-988a-50f5-8c00-fe184f264bba | note | Acceptance Criteria - •The minimum rail insertion length for all horizontal or angled rails is 30mm •All critical dimensions to be checked and to be installed as per MDX hand rail installation guide
6ef1bca8-bd42-5d60-9329-b94ff0249506 | note | Reference Documents - MDX installation guide Fencing Plan
af4257bb-8920-5613-af85-d6c8d469b79e | note | Inspection / Test Method - Visual inspection
0eab05de-5b27-5c55-89ac-58e88ddda7ca | note | Record of conformity - This ITP signed off
ec29be4f-6a5a-5a72-8421-f7cc038774fc | note | HP*
9f79ba52-8f9e-5e35-877c-cb10ecd10cef | note | Responsibility - Fulton Hogan Engineer
8a5f906d-f0e1-4e0e-93f7-39758f05207c | section | 3. Completion
d69d5ad6-d363-4a9e-a042-5647b81a8b5e | checkpoint | 3.1 - Clean up
18769cb7-4c7b-5c66-93b2-23ad99f2fc69 | note | Frequency - Post Completion
75f0f89a-9538-52d0-8c20-1c0a43602399 | note | Acceptance Criteria - •Personnel to ensure that work areas are clean and free of excess materials and safe for public use
49535a43-f025-5bf8-b46d-d944236e8aec | note | Reference Documents - Fencing Plan
28c1c8a9-9f06-5440-bcdd-8143eb63e632 | note | Inspection / Test Method - Verify
9f5f5003-18bf-593a-ab14-53a6eda12280 | note | Record of conformity - This ITP signed off
362213f5-07f6-5ec9-aadf-08026b862beb | note | SCP
d1b8a8ca-84ef-5471-8c63-2c34921737c6 | note | Responsibility - Project Engineer /Surveyor
bca4dccc-2381-4729-a4cc-21813faf81a7 | checkpoint | Final Inspection
03ca6090-3ce8-572e-b80e-a96a81551851 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1388252d-7147-5e44-a807-03a89bbb38a3 | textbox | Name:
973ae07e-98d3-5f54-aeea-33569c8077f4 | textbox | Position:
adedec42-9b6e-5473-afba-a063a683a7f5 | textbox | Date Completed:
a9d3edaa-9d94-418f-9a66-06bd42aa9da9 | signoff | Sign ITP
284ae1d7-ada1-4b6c-a6ff-7b7ff0dd6b9a | checklist | FHC-ITP-032 - Concrete Base and Lean Mix Concrete Subbase Rev1 | itp | FHC-ITP-032 - Concrete Base and Lean Mix Concrete Subbase
221deae3-a216-4ded-84dd-bbcb89aaafa3 | section | 1 - Design and Submissions
4b0d48c2-fe9f-4c07-9615-0271466f4a71 | checkpoint | 1.1 Check for correct documentation
8ebe2514-b8ee-51cc-b122-ac657e785a3e | note | FREQUENCY: Prior to commencing any activity
abc62abb-233d-5b96-959a-4460d8e6f9be | note | – – – – – – – – –
a97d0f92-56ac-5473-9a85-c0681e83082c | note | ACCEPTANCE CRITERIA:
5fde551c-3d4d-5360-9a11-e37ed438b163 | note | • Ensure that all employees and subcontractors are:
6bda0648-6d0c-50c4-b4d8-1d327726b1f9 | note | – using the correct and complete set of drawings
6f383a79-dcec-5a3f-b4fb-4f26680671d9 | note | – all drawings are the latest revision
04783001-775b-529e-bc4b-97bc06c1a1ce | note | – – – – – – – – –
9f5c205e-dacb-5ed0-8360-e8ed8ab05464 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
b995db6d-2a9e-56c3-923f-be6cc49d9fe4 | note | – – – – – – – – –
3c681c69-5014-5182-ae04-a9bcf22012a4 | note | INSPECTION/TEST METHOD: Visual inspection
ef9aa3cd-1304-55c0-afbe-bab48b8baab9 | note | – – – – – – – – –
b6848bbb-5e4c-547e-b9ee-3fdc7567dd71 | note | RECORD OF CONFORMITY: This ITP signed
fd4a646a-e04b-5155-bbd2-edfc672aa0eb | note | – – – – – – – – –
1f05e62c-aca9-556c-921a-aa013aaabaac | note | HP*
284ecdc1-330a-5ed2-85e7-f4d7f27f8cca | note | – – – – – – – – –
edc1f2f1-3292-53a6-9761-7404461b2e20 | note | RESPONSIBILITY: Fulton Hogan Engineer
8db9137d-1d00-556a-b6c4-cd1afcb28a36 | note | – – – – – – – – –
43bc98f0-08c3-5a5f-9d9d-f9df4d8c5efc | textbox | DATE:
38be048a-8871-4941-9d1b-fec38b2cdfc7 | checkpoint | 1.2 Implementation of all measures and controls
9d604ad8-3bc1-5c06-ab58-362069927e8f | note | FREQUENCY: Prior to commencing any activity
0f42bbb4-1674-53fd-a3bb-97b62be1aff8 | note | – – – – – – – – –
cdd15ab5-bf10-549d-96ea-d44e17299936 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
08a620af-6b9f-56f0-9fdf-a14b8d30e5ee | note | – – – – – – – – –
799fdb86-3444-5e6f-9792-9e75ceb4f63f | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
fb14001b-afff-58be-bc20-75add0b85926 | note | – – – – – – – – –
e0013903-603e-565a-8010-55d3563b7dae | note | INSPECTION/TEST METHOD: Visual Inspection
6096cf68-eb35-5b49-9d48-e914590aa7d8 | note | – – – – – – – – –
e790ffeb-d286-5de0-b7c7-a2f4dffd5b92 | note | RECORD OF CONFORMITY: This ITP signed
ca552277-6dd5-5529-9139-050cc6780dcf | note | – – – – – – – – –
84db0113-9b1a-5110-89d3-b29d23b032f3 | note | HP*
dcc31909-1b61-5ae7-a877-e19b4bf32733 | note | – – – – – – – – –
3e0e3d32-1895-5515-9834-cbce36edb004 | note | RESPONSIBILITY: Fulton Hogan Engineer
d176a49a-4700-577f-9c80-e3037f045594 | note | – – – – – – – – –
c889941f-d189-5269-8f7e-1d276b605698 | textbox | DATE:
fceaad37-0ba5-4826-9953-c0c51799bc44 | checkpoint | 1.3 Approval of mix design
22075041-2e21-5776-bb1a-d521d7ce145d | note | FREQUENCY: Prior to the first concrete pour
e5e375c7-c71d-5885-a694-d4244af60523 | note | – – – – – – – – –
460731e5-6334-51d5-a5c1-d9a4511b2b6a | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
50dc2a04-1a35-594a-8064-ff0bb6a9c748 | note | – – – – – – – – –
6f0e8d66-b981-5e48-990f-a32256511556 | note | REFERENCE DOCUMENTS: 503.04
1ded2a6b-2e37-5625-ae51-a68ee9f9c334 | note | – – – – – – – – –
bb567169-c5b5-518d-b5fc-568acdf466c9 | note | INSPECTION/TEST METHOD: Verify
2328b212-1135-5438-962c-eccf197d6f23 | note | – – – – – – – – –
269a4e80-c4c8-568e-bc96-9a6b3d547763 | note | RECORD OF CONFORMITY: This ITP signed
6e9e2287-c781-5057-915e-2054e3dd5859 | note | – – – – – – – – –
fcc87cba-54fa-53a0-989c-df927b869160 | note | IP
9a7fe70d-6528-5c41-977c-647b5268e809 | note | – – – – – – – – –
f352936f-c4c0-51bb-8b2e-e3e4ffafb403 | note | RESPONSIBILITY: Fulton Hogan Engineer
4ae399b6-678a-5ff9-9e12-a6052183d1db | note | – – – – – – – – –
d1cf3deb-aabb-5178-a4c0-e68e61655317 | textbox | DATE:
5b562e6a-1863-4f55-b2d9-f0378c2891ab | checkpoint | 1.4 Reinforcement schedule
d9162392-17e2-524b-8fb8-0359fd61beec | note | FREQUENCY: Prior to concrete pour
d5fd159c-c3f3-5e66-bfd1-97ca8715f006 | note | – – – – – – – – –
94d3af07-bd65-52e4-b8f1-d05adc955a8e | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
956b9a42-9282-559a-b7a4-ec0b091e9489 | note | – – – – – – – – –
b39e70a4-0de2-5a28-8c34-35954724b5b9 | note | REFERENCE DOCUMENTS: 503.09
fb629bb3-15fc-52b0-9843-17d6811ccc66 | note | – – – – – – – – –
c5dc8112-be8b-567c-b9be-8447e6302d32 | note | INSPECTION/TEST METHOD: Verify
335d9c06-a9ac-5004-a5f4-e7eac028a966 | note | – – – – – – – – –
258112ad-f439-5cc7-8acb-93d3da2c5eb1 | note | RECORD OF CONFORMITY: This ITP signed
21aca579-6d69-5c81-8ac1-777f1ab128c3 | note | – – – – – – – – –
06c4880f-d154-5d72-9888-3ec865639085 | note | IP
12fd2c7f-b9b1-5b47-8279-8e4a61635e5e | note | – – – – – – – – –
9b8fd568-6136-58d9-93eb-50aed6e428e9 | note | RESPONSIBILITY: Fulton Hogan Engineer
e72c45e4-9ff9-5422-a1f5-8ecc3913d841 | note | – – – – – – – – –
89b8c21e-6f8a-5907-bde5-f12de5a0ca9f | textbox | DATE:
048cc4c6-49c4-4f73-9ccf-f6f42f49b7b9 | section | 2 - Construction/Erection of Formwork
b985b903-ed22-4b5e-8b0e-a3a3d736a928 | checkpoint | 2.1 Excavation
3dbc8b5d-9697-5865-9cb5-7f75f388ca28 | note | FREQUENCY: Prior to concrete pour
aea258dd-91bf-5734-9f6a-23f6ae3f23de | note | – – – – – – – – –
1a27ccd1-2070-5095-b257-f98dd7bfc99b | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
e8256902-552f-551c-b418-204c1a22f975 | note | – – – – – – – – –
6f877732-5239-5b8f-941b-b3a23682baee | note | REFERENCE DOCUMENTS: Contract Drawings
6ae3093a-435e-58c0-a263-488f947de185 | note | – – – – – – – – –
316b4787-3f7a-5ba3-8853-90649f14061d | note | INSPECTION/TEST METHOD: Inspect
ed0f2c06-796a-5528-8bb4-79a470c9ff2a | note | – – – – – – – – –
3c811017-d81f-57af-9cea-46d81ec5365e | note | RECORD OF CONFORMITY: This ITP signed
caf657bd-6805-5dc8-a47a-888790536a9c | note | – – – – – – – – –
62bafd14-9710-5d43-aaaf-b4628214655d | note | IP
3bc0babb-5235-5f1c-8f2e-ea05d21df721 | note | – – – – – – – – –
639304d6-930c-5665-a798-17a962b82f04 | note | RESPONSIBILITY: Fulton Hogan Engineer
196a1ce5-060c-54ec-a5f8-4d12eb022297 | note | – – – – – – – – –
7763c78b-2846-530d-89ac-054197828780 | textbox | DATE:
490eeaff-1796-4415-a72b-d41d3d5afbb9 | checkpoint | 2.2 Construction Methodology
6ea5c748-aafc-58c6-906c-f6c25dd0bf38 | note | FREQUENCY: Prior to erection
54c5e716-4296-5154-8148-b8bfffec8dee | note | – – – – – – – – –
34cc7000-6177-5931-a7dc-5ce2a8585360 | note | ACCEPTANCE CRITERIA:
eb4de255-6182-5ff5-a53e-8dca95da07ad | note | • Designed and constructed in such a manner so it can be removed without damage to the concrete.
997d1b26-9016-584c-bf3e-6f8e280bdf65 | note | • Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
2db7a90d-1526-5c7e-bc7c-c322f9715a68 | note | – – – – – – – – –
e7ac8476-1615-53ab-8da9-0ddeee63a70e | note | REFERENCE DOCUMENTS: Contract Drawings
e132ca5b-72a6-50d0-a34a-dc34c74d8828 | note | – – – – – – – – –
5522ace0-b0a0-52ff-b1b1-1f19b60a10a1 | note | INSPECTION/TEST METHOD: Verify
57c4a392-9259-5380-ad20-1c28f61bbfa6 | note | – – – – – – – – –
ccdcda96-10da-5b6e-8a2a-3cc9231cc109 | note | RECORD OF CONFORMITY: This ITP signed
0a9fbb92-41eb-55a2-950c-c86b7bf3ae39 | note | – – – – – – – – –
97d7e075-db10-50ec-a709-63c4c5a091e1 | note | IP
afa686d3-72b8-54d3-9b66-99719856cfbe | note | – – – – – – – – –
9aef9859-b7a4-5c13-80cb-96bf3b1820f4 | note | RESPONSIBILITY: Fulton Hogan Engineer
8c62232f-44cb-539b-85d8-9f33adc1db96 | note | – – – – – – – – –
307e75a6-a3b2-5446-a031-74809ed3db27 | textbox | DATE:
bcc13dcc-d219-4e47-ad68-ebab7b6839a7 | section | 3 - Pre-Pour Planning and Inspection
ecae251d-1ded-4238-9bfd-8a17410ede1d | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
02c9914c-95d2-52cc-857f-d0e5c0bbab79 | note | FREQUENCY: Prior to concrete pour
b2cf59f1-fc3b-513c-987d-cc7a41f833f9 | note | – – – – – – – – –
18e9feec-9649-5d4f-a8e2-c5577f89e8ab | note | ACCEPTANCE CRITERIA:
c7577d4e-2718-5cab-8e6b-e8c6d1132d93 | note | • Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent.
710ba905-ab2b-5200-8aad-53207cfa5469 | note | • Inspected and approved by the Superintendent. Hold Point released by the Superintendent.
ebebfb3b-ce09-563c-a6d9-d867ac821115 | note | – – – – – – – – –
95d97baf-3a81-5e54-952d-ccd800e48f83 | note | REFERENCE DOCUMENTS: Contract Drawings
c8254bc0-3bdf-529d-a337-7c813955aef1 | note | – – – – – – – – –
07b2963a-fd82-580f-970b-104a38f9337a | note | INSPECTION/TEST METHOD: Verify
11bfc96d-278a-5f03-81a2-92f401434051 | note | – – – – – – – – –
f6d360ca-e167-5f67-887d-9bde978749bb | note | RECORD OF CONFORMITY: This ITP signed
0ec6ebb5-80b2-5c2d-81e7-a2f0b9d45813 | note | – – – – – – – – –
84968545-aa65-51b5-96e1-62003f6d4512 | note | HP
169a8748-ef82-5150-9756-56409e0b8b41 | note | – – – – – – – – –
e1693281-c578-5a36-a3f2-66651b381233 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
a930888b-56fd-5009-b320-2e75723dec5c | note | – – – – – – – – –
4dd79ae4-2f74-5aa2-bfd2-0861c30b6ced | textbox | DATE:
8a95d7a3-d112-4d09-8d96-ad2c2dbaf9d4 | signoff | HOLDPOINT AUTHORITY
cfe806eb-83ce-4c4a-b508-8c95c57814df | checkpoint | 3.2 Formwork levels and position
00fee86d-d5fa-57cf-94d3-462f0db81af2 | note | FREQUENCY: Prior to concrete pour
9b8ce6c9-dcaf-56bc-b401-61a98079254f | note | – – – – – – – – –
5d77801a-62c8-5836-9923-c574efb67b5f | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
44d53e39-76a9-54ed-980c-9bf393febdc7 | note | – – – – – – – – –
e215e9f1-ffc9-5ad6-9ba8-89b64635d263 | note | REFERENCE DOCUMENTS: Contract Drawings
5da86b80-3ec6-5171-b802-29b4e897457e | note | – – – – – – – – –
d7934fe4-445c-5153-baf1-582b58cf9e32 | note | INSPECTION/TEST METHOD: Verify
bb9ca188-9776-5022-b3df-bfce5ac117f7 | note | – – – – – – – – –
0bc410c2-526c-52aa-9e86-327eed5624cc | note | RECORD OF CONFORMITY: This ITP signed
8e978d7e-f5b8-56ef-b754-7b6093e101d0 | note | – – – – – – – – –
a4ecff31-8c4d-5ba9-a1d6-f71ece5739c4 | note | SCP / HP*
f05d4d00-4404-5c87-b133-3efc234c41f4 | note | – – – – – – – – –
7261611b-3edd-570d-a214-2a36b6ec7ab7 | note | RESPONSIBILITY: Fulton Hogan Engineer
6ed4c909-ce16-5b39-a932-1414cec0650d | note | – – – – – – – – –
df154778-3081-5c45-895a-ccf0c633bad8 | textbox | DATE:
da74c6fe-7e65-4fbb-bac4-365e9772df1c | checkpoint | 3.3 Location of splices
5c5582a2-93e4-5ca4-9e66-f3811460bd94 | note | FREQUENCY: Schedule Review
a76772c5-9450-520c-a5ac-63c31e7c9ce8 | note | – – – – – – – – –
f47eb088-8ee1-5800-a727-f848e803f8e8 | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
c2a4eb98-849c-53a0-8708-3ad5bc58ac0a | note | – – – – – – – – –
77c77eb4-a793-5d8b-aa94-dd0f3cd110c0 | note | REFERENCE DOCUMENTS: Contract Drawings
e2001604-782d-517c-b0e2-1dbbb250e899 | note | – – – – – – – – –
538f105d-9877-5e49-a4f7-6bc14a41f3df | note | INSPECTION/TEST METHOD: Inspect
77074f2c-6949-52f3-a8aa-b5b03fc34deb | note | – – – – – – – – –
6a50efc8-43e2-50b3-8808-1806761ae327 | note | RECORD OF CONFORMITY: This ITP signed
8efa3597-fa51-5827-89d3-a2700cfb398b | note | – – – – – – – – –
1b251a2a-b113-5a11-a8bf-f5d498845d45 | note | IP
8c6c894e-cd0a-5560-8d67-042524f2d376 | note | – – – – – – – – –
eb9ebad1-04c0-5136-a52b-7da9136de5bb | note | RESPONSIBILITY: Fulton Hogan
f2e9940c-a2b0-59ea-b58c-42da02d0eeca | note | – – – – – – – – –
80d5e457-7cb3-5829-9a8c-891638a9a522 | textbox | DATE:
e93d2261-3a72-48f7-948b-99481debbf4a | checkpoint | 3.4 Cleaning formwork
8931bb8b-1346-5733-9558-cb9c7727f291 | note | FREQUENCY: Each concrete pour
11f6a083-7c6a-5688-a892-3c4452998af3 | note | – – – – – – – – –
a839ff09-bf9a-5c1c-92f6-34117d852fdd | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
02e083c6-8a97-5f84-8021-dd088afbfb37 | note | – – – – – – – – –
59659777-3f4c-5fc7-996e-0838d06c8415 | note | REFERENCE DOCUMENTS: 503.13
db170984-36f2-5ec7-bf41-40f265fe5054 | note | – – – – – – – – –
d421accc-ea03-5fd7-9e24-28bb3958372e | note | INSPECTION/TEST METHOD: Verify
8d647652-780b-5002-9eea-3d2c86de87ef | note | – – – – – – – – –
71e88161-0232-5d30-b643-bc87092e00f5 | note | RECORD OF CONFORMITY: This ITP signed
542147e0-a487-5ea2-825e-b99e1e8f1f80 | note | – – – – – – – – –
10265053-3500-56a1-a7e8-9c6fe02cc200 | note | IP
919db740-9d5a-546a-a056-abe8737c6715 | note | – – – – – – – – –
c0e5c4c9-3ce3-5366-85cc-7a0862728e31 | note | RESPONSIBILITY: Fulton Hogan
570564eb-b0b5-5268-8413-fa606d99aabb | note | – – – – – – – – –
8993b1f0-8d9d-5b2a-97e8-2d62f3102132 | textbox | DATE:
e29c5b11-41b1-4e69-b34d-611d43494058 | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
c7681103-839f-5c27-bb49-e22fdcc6f319 | note | FREQUENCY: Prior to concrete pour
2353b01e-1c9a-52dc-88a4-a3543d218339 | note | – – – – – – – – –
78ac49f9-f5f0-55c9-8e85-7750ef7b7949 | note | ACCEPTANCE CRITERIA:
89120630-15ed-5569-b80f-15782c55f326 | note | • Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
cc93fa7a-c280-5894-8630-bc640bfb059c | note | • Pre-pour checklist completed and signed.
f8780795-980c-5af7-856a-df54fb33b140 | note | – – – – – – – – –
af320f87-3fd8-5afb-a7d0-61d46fe30e22 | note | REFERENCE DOCUMENTS: 503.07
f8d0850f-a4b4-56c1-ba11-28131a5b2366 | note | – – – – – – – – –
0ea1e9a2-0954-55dc-8536-4d5688f16524 | note | INSPECTION/TEST METHOD: Verify
c46148d7-c59d-5b2a-b9f9-caaa06f10951 | note | – – – – – – – – –
d6479621-8dd8-5358-9cf7-45091864e623 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
73855902-0f3f-56ff-b4a9-f6ed54fc6c16 | note | – – – – – – – – –
e17ab690-7621-5024-9282-b0fe636c0ce1 | note | HP
a640ae60-50da-5fe3-ac50-8d0bca7c77df | note | – – – – – – – – –
3835feab-0f07-5235-9d9d-f5719cdbb1c0 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
7fb80860-7dd1-5846-8ac5-e30c8e755c24 | note | – – – – – – – – –
c0c38fb7-18c4-5272-8041-163a91287314 | textbox | DATE:
e6f23620-aef6-4247-979d-069b767ab2b4 | signoff | HOLDPOINT AUTHORITY
3c119ea9-a94e-4f1d-8019-cad96f3a88b9 | checkpoint | 3.6 Reinforcement assembly of piles
13a4f5b5-8f2c-5198-b1b6-337ab1ca6262 | note | FREQUENCY: Prior to concrete pour
5a8ef167-7111-59c4-b1b5-27b4f4f17a75 | note | – – – – – – – – –
1e930289-6a2c-5449-8d9a-b0d46ee47347 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
b34a220e-a4c2-5757-96fe-68f1533d63ba | note | – – – – – – – – –
ce6489b1-5c04-5a97-9eb4-e8a88b541ee3 | note | REFERENCE DOCUMENTS: 503.07
5bf1f17a-5f1f-5455-959f-48d1e8ab49dc | note | – – – – – – – – –
bb7ac79f-45b7-5e8e-8645-8c54154b7017 | note | INSPECTION/TEST METHOD: Verify
c843f223-fdf3-5023-bcbc-0eccb31fcb2c | note | – – – – – – – – –
5fbfe61f-e076-52ed-9f1b-72a9cd7c2e10 | note | RECORD OF CONFORMITY: This ITP signed
8a4a062a-6848-530e-8f70-584c02777740 | note | – – – – – – – – –
076325a0-a7a2-5855-95a0-1a97658113ef | note | HP
61ab8791-6ab1-5339-937f-dae782129483 | note | – – – – – – – – –
3c81b7d6-1f0e-5250-a80d-e5aac1954d1e | note | RESPONSIBILITY: Fulton Hogan
c0f42724-395a-5c7e-bae7-d3eb495c6ff7 | note | – – – – – – – – –
f0c76ad2-d6c2-5175-942a-1aa46feccbde | textbox | DATE:
15aa4f5a-d45a-42fa-b54f-36da2880d82d | signoff | HOLDPOINT AUTHORITY
cec60b4d-fc11-4107-9995-c3fdc6d1256f | checkpoint | 3.7 Monitoring weather
88a371b1-32ef-5337-884a-4a74c6c0bcf0 | note | FREQUENCY: Prior to concrete pour
f0253bee-2ae0-5f06-bd79-154249d8cd39 | note | – – – – – – – – –
db4d5baf-2a1b-543f-a35c-f49ea1c50c77 | note | ACCEPTANCE CRITERIA:
64860f21-916f-538b-ac11-c872557a7103 | note | • Concrete shall not be place when temperature is <5°C or > 35°C
a6452a3b-dc57-52b7-8124-f53514d4aa90 | note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
44acf2d5-edab-589a-95ed-2737ecfe29b3 | note | – – – – – – – – –
6c52e604-6bbe-5db5-b4b2-4b047a27f135 | note | REFERENCE DOCUMENTS: 503.07
574ec2d9-ffaa-566a-9da9-3b7103113ba2 | note | – – – – – – – – –
daf662f9-bc8b-5239-8c3a-fd8da46eaff5 | note | INSPECTION/TEST METHOD: Verify
09aebd7a-5b38-51ac-8e55-9a32bf5af3f6 | note | – – – – – – – – –
8ad4d4a4-fcd9-579b-8525-5c8a689ff44b | note | RECORD OF CONFORMITY: This ITP signed
a32aa2c6-b4ad-5844-80b2-c7babd8fc524 | note | – – – – – – – – –
1bb812bb-a6c0-50b6-bfa5-05853dac451a | note | IP
aba8fe6e-8279-5d61-bccc-2e64e9ebd44e | note | – – – – – – – – –
fc375338-6f80-5ca4-bbda-06923deae432 | note | RESPONSIBILITY: Fulton Hogan
d04452fc-0ce8-567c-b737-d31600c63c7f | note | – – – – – – – – –
6a36afab-96a0-5e7e-a27c-36ac74a2cbc6 | textbox | DATE:
8ef68862-2adb-4ad2-a490-6cc6e393149d | checkpoint | 3.8 Assessment of Base Thickness
b7907f72-314f-5603-883b-413d44d9649a | note | FREQUENCY: Prior to lot closure
4616cd21-b423-596f-a679-59dad6e82c74 | note | – – – – – – – – –
c951b0c6-eb40-5ed4-adc7-cf267d2357d0 | note | ACCEPTANCE CRITERIA:
3b222685-a845-5d7c-9238-933d214b6a88 | note | • Within the lots defined for assessment of compressive strength the surface levels of the subbase shall be measured as specified in Section 173.
131a4acf-ec9b-578c-9957-4a893339120f | note | • Levels of the base surface shall be taken at the same locations as taken on the subbase.
772153ac-a8c4-5fcd-b4f4-f38842b94e4e | note | – – – – – – – – –
24a5cb23-d8d3-54a8-ad8f-2eeacf17ed2c | note | REFERENCE DOCUMENTS: 503.05
8bcbaa00-7406-5465-bd19-8bce537b752f | note | – – – – – – – – –
7c1a88fa-bf19-585f-8305-e66d7f6813d0 | note | INSPECTION/TEST METHOD: Verify
3ee9600c-cba2-5d91-87bd-e30938d37f07 | note | – – – – – – – – –
0a252852-ef01-53fb-9003-62e0fee99d82 | note | RECORD OF CONFORMITY: This ITP signed
df921ad3-3da1-5c67-b772-7fc076920d03 | note | – – – – – – – – –
c8d05381-9e12-5447-8463-02e6a1848742 | note | TP
2d87edda-5704-5976-840d-a85a5964097c | note | – – – – – – – – –
a09e7d8b-e8a2-5b06-a709-00712d845d11 | note | RESPONSIBILITY: Fulton Hogan
85a95a18-4056-5c2a-831a-e5239dff33de | note | – – – – – – – – –
27d41193-e721-5ef7-8b3c-5305770d6c39 | textbox | DATE:
c0b41b9f-f693-46a4-a96c-8b82c493f33f | checkpoint | 3.9 Concrete Sampling and Testing
d5af46fa-c91b-5ded-bce6-5b23f853a029 | note | FREQUENCY: Prior to placement
9349b41f-d639-5c38-be64-99fe972b86f2 | note | – – – – – – – – –
64e8d16b-42e8-5543-8c9b-c1d2d2eb2120 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for slump test.
61cced1f-6af6-5d6a-92a6-2a919d0381d3 | note | – – – – – – – – –
47f1f0a5-1a26-599b-b3bc-0e3520205303 | note | REFERENCE DOCUMENTS: 503.05
65279693-16ca-5374-9c3b-653258620a55 | note | – – – – – – – – –
b8fdda0f-a085-5cf7-a601-6e80ab098166 | note | INSPECTION/TEST METHOD: Verify
8819b0b2-ef9a-5c48-81e1-0eb4a2cd4160 | note | – – – – – – – – –
59d74c7f-e09b-5b65-86e6-04913fced305 | note | RECORD OF CONFORMITY: This ITP signed
1befb80f-1311-54e2-a992-9b6dc9ee0517 | note | – – – – – – – – –
c46d6eb5-85c4-501a-841d-65d908ab641c | note | TP
76faeb43-74a3-5315-ae8e-e782d85d68a4 | note | – – – – – – – – –
c268dc46-8764-506b-97e7-1a0049c4b49c | note | RESPONSIBILITY: Fulton Hogan
a06c777e-17a9-544f-adac-0c163c741817 | note | – – – – – – – – –
546fc66e-9887-530d-b63b-de043d059bb1 | textbox | DATE:
0bb2e836-c6c0-4f5a-9d61-fb63ae86e0bc | checkpoint | 3.10 Sampling and Testing of Cylinder Specimens
f6fb8d9f-4f41-5d77-9edd-2914827c8a71 | note | FREQUENCY: During concrete pour
a54e2e75-246f-548a-959d-ddc93071cdbb | note | – – – – – – – – –
72524a6a-a978-5f8f-bfd1-9402f99cd27a | note | ACCEPTANCE CRITERIA:
02f496c9-fb8a-573c-88d3-b4804f88c298 | note | • The Contractor shall record 3 sample, prepare, cure and compression test of 12 cylinders cast on site in accordance with AS 1012.
308571ee-03c4-56ae-908d-ecabb7cd80d5 | note | • The concrete shall be sampled at the point of discharge to the roadbed. Each sample shall consist of two cylinder specimens for testing at age 28 days.
82ad44fe-0de5-509f-aca7-cc8807b079eb | note | – – – – – – – – –
6eae1b46-973a-5a0f-b1c5-042300582802 | note | REFERENCE DOCUMENTS: 503.05
58b91fdc-babd-5df3-8d08-8af3891e6f60 | note | – – – – – – – – –
4b9dda14-a16a-5159-a48c-4d602e3b2637 | note | INSPECTION/TEST METHOD: Verify
6173f765-8aa6-5a4f-8e66-aac84b39f7b4 | note | – – – – – – – – –
c0e76570-bf58-526a-a94f-226f8b543e37 | note | RECORD OF CONFORMITY: This ITP signed
37b69abd-ef2a-55f7-a7a0-3b3cc2381226 | note | – – – – – – – – –
d1c3e955-eb70-5246-bee6-a7d7e31c3a30 | note | TP
408237db-eeed-55f1-b19d-54f392c57852 | note | – – – – – – – – –
ed78e5db-3138-5d86-b19d-4167a0a9cbc1 | note | RESPONSIBILITY: Fulton Hogan
f9d92bf0-65db-5941-badb-045fb60fff0f | note | – – – – – – – – –
e00db20e-9690-5455-84b4-61c62f3138e1 | textbox | DATE:
dfd6c703-16fc-45c9-9881-52d369d3e386 | section | 4 - Placing and Finishing Concrete
9da0bb4a-d137-41a1-bc64-82fbff6d1f94 | checkpoint | 4.1 Carry out sampling of concrete
3994ba7c-850b-55b6-9a1d-40044ae7ef5a | note | FREQUENCY: Each concrete pour
8ec02fba-9faa-5048-9059-64e64ce07cd6 | note | – – – – – – – – –
e0ec853a-a70a-53f5-95c6-6516caa1eafe | note | ACCEPTANCE CRITERIA: Sampling in accordance with 503.05
8a1901e2-1787-56b5-96f5-b3dda678066b | note | – – – – – – – – –
a58ea3b9-d345-558f-a537-d8afa33e88fb | note | REFERENCE DOCUMENTS: 503.05
9c3faccc-5817-5233-a8cd-e6dce541810f | note | – – – – – – – – –
0f82d1bc-dc65-5f5e-914a-b72e1416c600 | note | INSPECTION/TEST METHOD: Checklist
d5d60543-4e41-5d72-aa74-368fc0a7817e | note | – – – – – – – – –
f6e11b28-bd0f-5368-a4bc-9a1dbc7322a7 | note | RECORD OF CONFORMITY: This ITP signed
b091a072-3a44-541e-9442-f40085efb4e6 | note | – – – – – – – – –
e9a6e1bb-6275-56e3-b3e6-52c07d060590 | note | IP
3443e2f7-bece-5b4a-8580-ac6dc7f9beb9 | note | – – – – – – – – –
77658c75-7604-5671-8cff-0c89f84eeaef | note | RESPONSIBILITY: Fulton Hogan
31f9b5df-1353-5d0c-9b61-419d0ae88fd4 | note | – – – – – – – – –
bc6cb325-dc08-520f-8afd-77e2f6dc2d97 | textbox | DATE:
1b7f9c8d-bdeb-49b4-a07d-68e599cfa74d | checkpoint | 4.2 Discharge time
50b3352e-af08-5d53-a982-385ff4aa697e | note | FREQUENCY: Each concrete pour
7bd2c791-862b-50bb-b342-fb0d81c69434 | note | – – – – – – – – –
2e0ae3e8-f131-5c6e-a888-18608ff6612b | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
d6776ff7-ec88-573b-855e-a15119f982dc | note | – – – – – – – – –
e422b690-6585-5336-b746-da1720cf6bda | note | REFERENCE DOCUMENTS: 503.05
dad724cf-372a-5e2c-a71f-9cf1adfce493 | note | – – – – – – – – –
31588e8c-4a55-55d4-a3bf-8f67c041a668 | note | INSPECTION/TEST METHOD: Verify
fc9b9b26-860a-506e-b208-ef6eaf4fc1c3 | note | – – – – – – – – –
ae78276b-949a-5da9-8160-6e6c1f487d25 | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
90eadf4d-ae85-5167-99c2-a41547146a36 | note | – – – – – – – – –
6a97ca90-8b34-5c22-a834-c4af8fb8f3c1 | note | IP
95e94aeb-d6b5-538c-82e7-5db2468856c3 | note | – – – – – – – – –
ba798609-ca2f-55ff-aac4-989d85fe1b21 | note | RESPONSIBILITY: Fulton Hogan
cfaf161e-9f3c-5d81-8bb9-3b53c81be689 | note | – – – – – – – – –
6340a96e-1e9f-515c-b190-04ef586e736a | textbox | DATE:
a556119a-11b8-48a0-b658-63ccdbfc1379 | checkpoint | 4.3 Concrete Placement
81e1a233-5d40-5715-b399-d4600cd946af | note | FREQUENCY: Each concrete pour
18ba3839-87f4-5b76-8cf5-66140f93d90b | note | – – – – – – – – –
4cfd81d1-e49b-51e1-902f-4b2a32ff2788 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until the proposed method of placement, spacing of planned transverse construction joints and the provision of dowels, constructed formwork, reinforcement and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Superintendent.
2907b8a4-4d84-53db-9258-fd0f994ab926 | note | – – – – – – – – –
e65e4c6e-c890-5e85-9a8f-55ded01f162c | note | REFERENCE DOCUMENTS: 503.05
e243d06f-77ff-50ce-bf65-452e617a5bea | note | – – – – – – – – –
626194cb-1260-5591-b5b8-7d146c06d300 | note | INSPECTION/TEST METHOD: Verify
eb471035-c743-53a8-ba1c-3770ab6ea94e | note | – – – – – – – – –
69765889-a57a-50e1-9bbf-aafe8363dd97 | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
91d943a4-4f03-5cad-8daf-5443ea6be90b | note | – – – – – – – – –
acdf99dc-1beb-5d06-a220-8ba1af2ece3c | note | HP
22aaeefd-c3c6-5d4c-bae0-67b64d5c849d | note | – – – – – – – – –
0cda08a9-2c41-527f-a6e9-db37512a83a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
da2be487-2e57-524e-a2d9-00355072e6ed | note | – – – – – – – – –
239ece28-bff6-51f7-a7c6-bf2f2a6da56b | textbox | DATE:
b52bb2a3-ab3a-4a24-bfac-cf3594a08a16 | signoff | HOLDPOINT AUTHORITY
201c85ab-2912-4029-b08e-6715cfb8a058 | checkpoint | 4.4 Methodology of Placement
2bdea576-ee89-5578-8fd2-fb9a388eba2f | note | FREQUENCY: Each concrete pour
9c04667d-5b5e-5bd2-bf16-d423873405aa | note | – – – – – – – – –
a1bb86ba-0e7c-597d-ae0f-86c2af95dd8c | note | ACCEPTANCE CRITERIA:
d1bfd9f8-37b5-5079-8806-534a0a814a6d | note | • Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
e34be550-913b-50be-a299-266e671d8b7b | note | • Concrete shall not be moved horizontally by vibrators
bdf1f9af-83e2-5cce-b381-576b206078d1 | note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
739ec81e-b0c5-52fd-a259-9ef6b363cad1 | note | – – – – – – – – –
ebe0413d-1c9c-5247-bd5a-a307dc7af7e9 | note | REFERENCE DOCUMENTS: 503.07
31dde3a3-7ecd-57bd-9856-26ee2deed63d | note | – – – – – – – – –
422a976a-a2b9-5984-9aa3-7654d2097e7a | note | INSPECTION/TEST METHOD: Verify
e2a9b1b7-c524-55a0-9cee-2d0697a2d62d | note | – – – – – – – – –
03a5e736-23ed-521c-a7ba-7e5ce81c6ce5 | note | RECORD OF CONFORMITY: This ITP signed
00e27132-430b-5e8b-9a2e-1418d308a7d5 | note | – – – – – – – – –
b2508be3-dd94-574b-8884-8e3e7b1e627a | note | IP
26995787-3730-5648-b9ff-e733c0942511 | note | – – – – – – – – –
ddc92a32-960c-5dee-8c2a-aa434d7cd611 | note | RESPONSIBILITY: Fulton Hogan
d5d4d378-e406-5c92-856e-e7211cf22f17 | note | – – – – – – – – –
0b02b1a4-b54d-5203-9cc0-ff1658d5095b | textbox | DATE:
eb6f4973-e769-4ed4-9f46-4b321401b116 | checkpoint | 4.5 Compaction
449dd4ba-d4ef-53b8-b9a8-a050abd82dc7 | note | FREQUENCY: During concrete pour
26b1559a-4f3c-59fa-aa64-c457a3d64ec9 | note | – – – – – – – – –
535086d8-3dec-5e0a-9cac-75ce45451d91 | note | ACCEPTANCE CRITERIA:
8e378027-a4dd-5574-962c-3f3a1aa3dfc6 | note | • Base and subbase concrete shall be compacted to meet the requirements of clause 503.05.
cd721c18-af9c-5319-9396-c4e1778cf30b | note | • Concrete placed around dowel bars shall be carefully vibrated without the vibrators touching the dowels.
a1c8236e-650b-5ff6-8485-ea7ee2f91165 | note | – – – – – – – – –
073df880-025a-5c15-9d0e-5332a2a73363 | note | REFERENCE DOCUMENTS: 503.07
06620758-c34a-5395-8dd0-5c6166283bd7 | note | – – – – – – – – –
9a5e020c-7bba-5a8d-8d70-85b9bb22bc61 | note | INSPECTION/TEST METHOD: Verify
be9cf798-b4f7-577a-9733-289128ac05c6 | note | – – – – – – – – –
e3e56b3a-0e6c-5ecd-b926-f84d4d047572 | note | RECORD OF CONFORMITY: This ITP signed
17bee3cb-712a-517a-8ecf-eb67af5af8f7 | note | – – – – – – – – –
a72b7200-cbff-5520-86de-5dedf0d575ce | note | IP
6004aa53-d235-574c-be8e-ff585a9a1772 | note | – – – – – – – – –
ed191f4f-1d06-57e8-b894-ebd9c1d938ea | note | RESPONSIBILITY: Fulton Hogan
658e284b-ce74-5363-ba2e-5aeb51447368 | note | – – – – – – – – –
5166b372-f663-5c6c-bedc-3c9bb5a2f775 | textbox | DATE:
cab14178-6ae9-4136-a26d-26f3d0feb3d2 | checkpoint | 4.6 Screeding and Finishing
2f162f27-64b5-556c-af66-12d8c60fb503 | note | FREQUENCY: Post concrete pour
51e2d8a0-ed9f-59ae-bec1-cd2bb3bd68c5 | note | – – – – – – – – –
cd09102e-4d68-52b4-ac54-1236d1f5af3d | note | ACCEPTANCE CRITERIA:
06bca5a4-0779-59fa-871e-06f88a75a86d | note | • The concrete shall be finished to provide a dense and homogeneous concrete surface satisfying the requirements of clause 503.03.
1693a86b-7cdf-5e67-9745-20a900f25b79 | note | • The subbase concrete shall be finished to a uniform non-textured surface. The base concrete shall be finished to a textured surface as specified.
cf08f1ed-7514-55eb-ad4e-96ed7b70c63c | note | – – – – – – – – –
cab4e24f-7d80-5b64-acde-576051b30807 | note | REFERENCE DOCUMENTS: 503.07
11f542cb-bad2-5c8e-8361-7e18c53f27a4 | note | – – – – – – – – –
fccea9ea-f89e-5bd3-9f96-ddfd089e3978 | note | INSPECTION/TEST METHOD: Verify
5cd8434d-9641-5bec-8cd7-64c78cb56be6 | note | – – – – – – – – –
cc70da21-0a96-5e84-b2d5-9e2a55bcf1b0 | note | RECORD OF CONFORMITY: This ITP signed
78f46b1a-e11f-5689-bae1-5d69afd72188 | note | – – – – – – – – –
661ff529-15a5-5a36-8592-d7207c303df9 | note | IP
1f7b12ef-05ea-5d15-aa18-400128ae501c | note | – – – – – – – – –
8c56a239-32c7-5266-9d2a-b8204e3e9f83 | note | RESPONSIBILITY: Fulton Hogan
8ec50f3d-65eb-5bd1-931c-1049e862c166 | note | – – – – – – – – –
d15ee34d-301c-5d5b-9fae-fe41108d5357 | textbox | DATE:
748fc01f-0b45-4f00-b19e-34679f00867a | checkpoint | 4.7 Joint Sealants
d0bc56fc-b8f6-53c6-b966-7594c20fa090 | note | FREQUENCY: Post concrete pour
3ea9e94b-6547-540f-b2e1-2896031a05b9 | note | – – – – – – – – –
429543c9-656b-5703-b523-4028af0605fd | note | ACCEPTANCE CRITERIA:
974fd5a7-3d77-557c-9ef1-4c7906cfa947 | note | • Permanent seals shall be either a neoprene compression seal or an in situ cast silicone sealant.
da465ad8-c44c-59eb-a19c-6222a5e4a020 | note | • A full technical description of the proposed sealant and method of installation recommended by its manufacturer shall be submitted for approval by the Superintendent at least four weeks prior to installation.
82228972-2ca3-5e3c-b984-da562f73750f | note | – – – – – – – – –
2b09c1a2-0e5a-5dff-9781-7fd7dcc9542b | note | REFERENCE DOCUMENTS: Contract Drawings
784a8345-76c7-5eb9-a063-acffcfeff7ce | note | – – – – – – – – –
6dcc65fe-1175-5a06-bca9-332039c98c96 | note | INSPECTION/TEST METHOD: Verify
5e639a8d-615a-5706-9844-e26679e63e4e | note | – – – – – – – – –
893fe42d-d810-5a8a-8d82-3ff31463baf2 | note | RECORD OF CONFORMITY: This ITP signed
7cffb10b-f1d3-597f-9047-7d2dc3a51dba | note | – – – – – – – – –
c28c4209-d641-5a7f-afeb-9e2aff38a105 | note | IP
4f5109d9-c370-5076-9118-b66cf51bd7ca | note | – – – – – – – – –
7284c4df-7f53-5e50-817b-fcda7c70af8a | note | RESPONSIBILITY: Fulton Hogan Engineer
703bf1c1-d1b3-5894-b6b8-cda586684388 | note | – – – – – – – – –
feb4f652-4f5f-5a1e-9e26-1238d078b2d6 | textbox | DATE:
7663d30f-880f-4d4e-8016-78611961595e | checkpoint | 4.8 Joint Sealants for Base
e66a0ac9-da87-5fe7-ae4c-82e1407ec969 | note | FREQUENCY: Post concrete pour
e83e102e-9528-565b-8557-4f5fb48c4e29 | note | – – – – – – – – –
4db2aa4d-6eec-5acf-bb1e-6cd166c751e2 | note | ACCEPTANCE CRITERIA:
194a06db-22ac-50a1-aed1-c847b6da81de | note | • Joints shall be constructed as specified and shown on the drawings. Joints shall be straight and vertical.
95df4fe2-786a-58b6-8482-1aff1b95fc5d | note | • Transverse joints shall be continuous from edge to edge of the pavement. Tie bars shall be installed such that anchorage strength of at least 85% of the yield strength of the bar is developed upon hardening of the base.
a7530bac-6d50-5feb-b374-398d476ad881 | note | – – – – – – – – –
6d20b591-c70b-5f88-90f6-5620b5c55faf | note | REFERENCE DOCUMENTS: 503.13
46e7e89b-cdc8-5472-9cc5-d1c9d0ddf055 | note | – – – – – – – – –
50fdc15b-af90-502b-a9fb-fc0c17d59544 | note | INSPECTION/TEST METHOD: Verify
0f94195f-3a59-5df1-a9f9-e9bbc221d1ea | note | – – – – – – – – –
38389124-4813-54a2-b995-8af968c10070 | note | RECORD OF CONFORMITY: This ITP signed
123f46a9-d80f-566a-ae23-85016ce75518 | note | – – – – – – – – –
5d684bd4-e047-5b71-86de-fe9ba017ca68 | note | IP
93dc7f53-24c9-56e1-b70f-691bca29e4ef | note | – – – – – – – – –
edfac307-6b1d-571a-9b61-694e2454d443 | note | RESPONSIBILITY: Fulton Hogan
79a4d00f-faa1-502c-a09b-f1868fcf273e | note | – – – – – – – – –
5fda0a62-a361-5d4e-aca4-637eef32ae97 | textbox | DATE:
06c69bae-55cc-4ba7-8c19-f9529638e256 | checkpoint | 4.9 Texturing of Surface
8af4ab37-568a-577e-90d2-930de3146334 | note | FREQUENCY: Post concrete pour
77ff40d7-c2ba-5de8-af82-d4242e1fc0e1 | note | – – – – – – – – –
9d26ccfb-5e79-5fb0-8a46-2c26943cd6cb | note | ACCEPTANCE CRITERIA:
a5cca5ff-e0de-59c9-b944-1c5086a49581 | note | • Texturing of the concrete surface shall be carried out to the standard of surface specified in clause 503.21 using a hessian drag or steel tines. The textured surface shall extend across the full width of the base and shall be uniform in appearance.
7d823483-0574-50e2-b23e-db6edde5d902 | note | • The concrete surface shall be finished to achieve an average texture depth between 0.40 mm and 0.70 mm. The texture depth shall generally be achieved using steel tining equipment which shall comprise of rectangular shaped tines of flat spring steel, approximately 0.6 mm thick. The width of the tines shall be 2 mm.
6e32e291-e289-5c31-8e30-7cf7c5c7809b | note | – – – – – – – – –
0e585961-b0a0-5ade-a613-ff03e045e636 | note | REFERENCE DOCUMENTS: 503.17
9f18ca5c-1377-5f2e-b7cb-df0671b926d7 | note | – – – – – – – – –
f07d207d-44e4-5720-9d00-29bab6572084 | note | INSPECTION/TEST METHOD: Verify
17f155d2-cd3d-5933-9461-8bea707d08f5 | note | – – – – – – – – –
a1120a78-57d6-5bab-9b55-8f79d4d5a179 | note | RECORD OF CONFORMITY: This ITP signed
edbc9ad4-1c9d-5d2c-bc68-c2c7df5b7753 | note | – – – – – – – – –
83aa363d-8446-5043-9f33-7f71f0a55e14 | note | IP
39e1ca9f-7cd9-5d56-96ee-36f6f55b891b | note | – – – – – – – – –
49fc726d-b6a8-52e7-bec7-64daab606638 | note | RESPONSIBILITY: Fulton Hogan
a60fb53a-3013-588d-882e-9d3b18f48f55 | note | – – – – – – – – –
36d84369-ea98-5c05-b9b0-b189b77a4245 | textbox | DATE:
d501e4ac-7f81-453b-b4d0-507e8b296f49 | section | 5 - Post-Pour Details and Inspection
fbc6d5a8-ade0-4dd6-8bc6-77b7a382ae3b | checkpoint | 5.1 Curing and Protection
5aee4985-5dbc-542d-b338-ae7b8a75a45e | note | FREQUENCY: Post concrete pour
6483a8f4-21c5-50dc-8e7d-95e52da4eae0 | note | – – – – – – – – –
da709de4-9ca5-5150-87f4-4e72d8675e78 | note | ACCEPTANCE CRITERIA:
b048d696-1207-559a-afb0-31096ef8c6ad | note | • Curing of the base and subbase concrete shall be undertaken by the use of a curing compound sprayed onto the freshly laid concrete at the application rates specified in this clause.
721b03ec-3b22-5203-bc86-58eff565eca9 | note | • Curing compound shall not be sprayed when bleed water is present.
f2c3047a-21cd-5ccc-832a-119c7f688a62 | note | – – – – – – – – –
94c3961a-8c99-5709-bbef-5089719843fe | note | REFERENCE DOCUMENTS: 503.18
9ab3524e-0f83-58d9-bb27-fecfd520ae74 | note | – – – – – – – – –
3f914199-74e5-51ea-8501-894576a25c72 | note | INSPECTION/TEST METHOD: Verify
a59c91f3-99fd-5e13-b77e-e5e82f1bd854 | note | – – – – – – – – –
1f15d1c3-37fc-5cd5-8d5d-33c7ff09a720 | note | RECORD OF CONFORMITY: This ITP signed
7e83dcad-aced-53de-a79f-d55ff9ff9882 | note | – – – – – – – – –
039c1cc4-0bea-5fa2-ae8a-6168b30e4903 | note | IP
e13bfb25-fa10-554f-a6da-33b24a3e55ca | note | – – – – – – – – –
083ad73b-68cf-538d-ad79-a1d2429fc1df | note | RESPONSIBILITY: Fulton Hogan
d55f3c8a-9784-5773-ba65-58b93fdfea08 | note | – – – – – – – – –
0fef38e2-00dd-5328-b4ef-a7fc497a07e1 | textbox | DATE:
7b7cc085-27fb-4a68-96ed-e6d5832ed9b6 | checkpoint | 5.2 Curing Compounds
a496e26f-12f0-5939-87a3-e36ee2f9f46a | note | FREQUENCY: Post concrete pour
b2922dc7-05a0-500f-a837-adf5d8472ba5 | note | – – – – – – – – –
4ba63996-3f35-5fdb-84f0-64281d0f98e1 | note | ACCEPTANCE CRITERIA: Prior to the use of curing compounds, the Contractor shall submit to the Superintendent for review not less than four weeks prior to placement of concrete
18956815-8a2d-5f83-adbe-23677c6263d2 | note | – – – – – – – – –
6d01855c-b989-5389-b775-22838339288c | note | REFERENCE DOCUMENTS: 503.18
e7ed932d-6ae4-58d6-ba9c-770468081b13 | note | – – – – – – – – –
68ed3f60-3ad1-5769-b3cb-fecc95a82de0 | note | INSPECTION/TEST METHOD: Verify
e4502019-9b15-5761-a269-c86de1032ec6 | note | – – – – – – – – –
79be4cb9-8460-523f-a7d1-6e19db6c9cbf | note | RECORD OF CONFORMITY: This ITP signed
67afc834-8eb6-51fc-a92b-e61d889b9303 | note | – – – – – – – – –
8e53afda-e853-56c6-9d7b-4651125b5aeb | note | HP
b6bd1f05-400d-509d-8fdf-4460f374f153 | note | – – – – – – – – –
bb6c10dd-d9cd-5d89-bbd8-ab8ac8cfd297 | note | RESPONSIBILITY: Fulton Hogan Engineer
ed2b2cae-fc13-5ea9-addb-f2b654144727 | note | – – – – – – – – –
512b4446-5c46-5421-9965-9c8c69ef9e4a | textbox | DATE:
7fd30fca-8d9e-4fe6-a9ff-28da931d03ae | signoff | HOLDPOINT AUTHORITY
3bfb20c1-bc96-4d95-9023-d2739164feda | checkpoint | 5.3 Formwork removal
02908397-e3a1-5d58-9485-117fe274abf5 | note | FREQUENCY: Post concrete pour
1077f11d-f739-5e66-ad05-17bf05547965 | note | – – – – – – – – –
a4c9a125-5ef9-536b-90c0-d19e4529509e | note | ACCEPTANCE CRITERIA:
796bfb9c-a67d-5398-b43c-fc46e19017aa | note | • Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal.
f5c0d365-b559-523e-920e-69870f55d77d | note | • Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
d1b89b7d-e949-5c29-91d8-0f9a3f682064 | note | – – – – – – – – –
7e02c10a-a00e-5637-a218-7878c4e04e41 | note | REFERENCE DOCUMENTS: Contract Drawings
0eee0284-a918-5622-b346-bfa1562847d6 | note | – – – – – – – – –
2c36070e-5164-5617-9077-646d45e0093e | note | INSPECTION/TEST METHOD: Verify
b3b43498-2701-512b-a486-ab7a62c409f8 | note | – – – – – – – – –
7aa8cb5b-674e-51ce-8432-ca413aff2bd1 | note | RECORD OF CONFORMITY: This ITP signed
e53208fc-f3c0-50dd-8328-51cdf14c68aa | note | – – – – – – – – –
cb3e415d-95fa-5390-9d79-e186129e1130 | note | IP
d1966af1-b608-5c28-87b0-f393d157d355 | note | – – – – – – – – –
334f9d08-c618-5509-b3a8-9913192a5c18 | note | RESPONSIBILITY: Fulton Hogan
bb2b48de-ba1b-5da1-82b0-5f0d4fc2efb1 | note | – – – – – – – – –
15a4bc1f-c9d6-5277-b825-a82cd1faaf40 | textbox | DATE:
068dbaa1-1054-4b95-9f95-0423278612ef | checkpoint | 5.4 Concrete Base Course
73c933c8-aae2-5b87-a915-d25adcd2956c | note | FREQUENCY: Post concrete pour
2a03f533-5ec4-545b-b75a-233d9c3b74ac | note | – – – – – – – – –
5fd095b2-304c-5396-a400-bc60315020ef | note | ACCEPTANCE CRITERIA: With the exception of concrete saws, personnel the concrete base course shall not be trafficked until the in situ compressive strength has reached at least 20 MPa based on concrete cylinder testing.
488eb4e0-2703-562d-a94e-bd349dbc1326 | note | – – – – – – – – –
a206320f-7ec6-54c2-b95b-e79adfcb749d | note | REFERENCE DOCUMENTS: 503.19
be3a6efb-9433-59b0-b4fa-a5cc78145de6 | note | – – – – – – – – –
5d833113-8ab7-511d-b07d-35a22601910d | note | INSPECTION/TEST METHOD: Verify
47de5eed-8e0a-5f6f-9187-931b38457540 | note | – – – – – – – – –
03bd2fe5-4b4f-5da2-a5db-d519def95e0f | note | RECORD OF CONFORMITY: This ITP signed
fab3c7b1-2a61-5466-977d-42b4b766fdc8 | note | – – – – – – – – –
cfe7dc2f-f409-5388-b5ea-1603a9f6d300 | note | HP
336444a1-699f-535b-a137-e13cf01163bb | note | – – – – – – – – –
796337c0-8f9b-5b97-a9d0-93477d29cd4e | note | RESPONSIBILITY: Fulton Hogan Engineer
8eb1b6b7-f59a-5f45-9c38-74176ec71286 | note | – – – – – – – – –
1d2f3fa9-0a44-52e4-b51e-9f6418744b56 | textbox | DATE:
d1067343-8b17-4757-a96c-b25111783c3d | signoff | HOLDPOINT AUTHORITY
3db6bbb8-25e2-4dd3-aead-e88863363207 | checkpoint | 5.5 Positional tolerance and dimensions of concrete members and piles
c227ec16-3b62-536e-aaaf-0f7b653d049f | note | FREQUENCY: Each concrete pour
202b8d93-0356-5f64-9e19-539e13577d63 | note | – – – – – – – – –
6f6b7753-5e29-5063-b300-f0fb03d20773 | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
63bdce5c-55fd-5430-97ca-dd635181d7e4 | note | – – – – – – – – –
438619e3-fe6b-5f5e-bbb1-b5faf412c46a | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5
8122f790-f97c-5534-b9b6-ddc93dba8906 | note | – – – – – – – – –
4b040536-e14a-51f8-bdfd-2a484ef841c8 | note | INSPECTION/TEST METHOD: Verify
f6f8b534-7131-594e-b5ea-fb8278501c92 | note | – – – – – – – – –
fd940223-7154-5683-8404-8e5332e5f48d | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
3d4806ef-0a1b-5ebd-b6e9-6de12de6f02d | note | – – – – – – – – –
078d786a-8e57-5246-ac39-fd3b65f87e08 | note | IP
64203ea1-59d9-5f52-b976-ad3379feee08 | note | – – – – – – – – –
65f6382d-5a34-5cfb-9269-2f857427edb0 | note | RESPONSIBILITY: Fulton Hogan
a9d90569-212d-5b7a-aa19-2162837c44b8 | note | – – – – – – – – –
302ad769-466e-5f65-9e99-b638f377d3a3 | textbox | DATE:
c53ef328-2d75-4ffc-b97d-8cbd9a6c588d | checkpoint | 5.6 Concrete Sampling and Testing
585451ea-45b5-554c-befa-d6af9d0334b3 | note | FREQUENCY: Prior to lot closure
dfd55318-7bcf-5254-8a38-6219018b9e76 | note | – – – – – – – – –
6782d615-b49a-5e7b-b35f-be54255c60c4 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for compressive strength. The required strength of concrete must be in accordance with the drawings
79681cc9-ac5a-5e9b-b7c1-1019390c7f33 | note | – – – – – – – – –
f1fea4df-4938-52fa-8dd6-f7e2d2a2aa7f | note | REFERENCE DOCUMENTS: 503.05
a4b9ee70-2823-50a0-831e-d3cbdaeaec0c | note | – – – – – – – – –
82f6f1bc-e386-574e-a1b0-2677ee4afe42 | note | INSPECTION/TEST METHOD: Verify
48aef6de-d7f5-5b20-90b7-fbe0eaf61fdc | note | – – – – – – – – –
2a2f2c04-cce4-5d38-a7b0-d9dcf975704d | note | RECORD OF CONFORMITY: This ITP signed
6f43e087-107f-5516-b61e-5b9ec3ed56f1 | note | – – – – – – – – –
cc7f7ca3-c37d-59ab-b2ee-03e89fa1730c | note | TP
76dd34c5-8080-5968-86e8-f4fbe7e30874 | note | – – – – – – – – –
3eea812e-df97-5311-ae4d-508f3ae6e012 | note | RESPONSIBILITY: Fulton Hogan
4a973fcb-1e28-54ae-b28e-ad261fb6a3f0 | note | – – – – – – – – –
b71c0aa9-406e-5b12-884c-d1e224a115d5 | textbox | DATE:
9da065ba-bd97-411a-a677-c58f90d2cf40 | checkpoint | 5.7 Curing and Protection
23de9044-b237-5dd8-87bd-1e0a624803e7 | note | FREQUENCY: Post concrete pour
f78c2190-47d7-52f1-841c-54216c249eb4 | note | – – – – – – – – –
21e8af2a-25a5-5ffb-b8d7-e24242b455d2 | note | ACCEPTANCE CRITERIA: Saw cutting and joint sealing shall be allowed on the finished base concrete until the in situ strength of the concrete is at least 60% of the target 28 day compressive strength.
1461c7bf-9634-5039-a8c1-34b069816693 | note | – – – – – – – – –
f90c6e8c-cea3-5d45-9cd7-eb97eb051452 | note | REFERENCE DOCUMENTS: 503.18
240816c7-80c7-52e9-94b9-6889df6a0a12 | note | – – – – – – – – –
6c99f9de-f074-53aa-9bec-a62431d457bd | note | INSPECTION/TEST METHOD: Verify
dfe2ffac-7a98-5471-a514-0e76f13099ed | note | – – – – – – – – –
6f362005-8568-59a6-899c-c533b14e8d2b | note | RECORD OF CONFORMITY: This ITP signed
220583bc-ae71-5161-a121-240949a6fa12 | note | – – – – – – – – –
bac76049-a190-5141-a696-234711c862da | note | IP
438cb36b-bbf0-5d20-b48f-f88efeaf44db | note | – – – – – – – – –
172d7161-e2b6-59f9-bd46-e6677f746f5c | note | RESPONSIBILITY: Fulton Hogan
6f460028-682b-56d0-932e-4ee4144f145a | note | – – – – – – – – –
94032e61-4f49-5707-8bf6-a792b99e67e2 | textbox | DATE:
e69b1228-88b8-4221-8089-f58bae5268fd | checkpoint | 5.8 As Built Drawings
c6377be3-d2c8-50bd-bb79-abb439e7f230 | note | FREQUENCY: Prior to lot closure
070475ed-09cd-5ebe-9f98-84f695a4432c | note | – – – – – – – – –
e4fa48e5-3ee5-5c29-865f-49fcd0b8b489 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
d1233c32-e33a-504e-abdd-f9205521de4c | note | – – – – – – – – –
75149a2e-935e-567b-a57a-79eb8c5d1886 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
ec9922bb-5f71-5233-bced-84c48ab981fe | note | – – – – – – – – –
defa51ac-0e8d-52f4-89e0-28288161943a | note | INSPECTION/TEST METHOD: Verify
6d230859-b8a5-5c15-9eb6-82581d9469cb | note | – – – – – – – – –
4e813252-2238-5ac4-b2e1-0093de4b0a03 | note | RECORD OF CONFORMITY: This ITP signed
91523d1f-8b70-54b8-a80e-04ab84a7c51d | note | – – – – – – – – –
542c82a1-67c6-538e-aa89-a0d120ab7f7a | note | IP
70dcda1e-b9d4-56bd-8d9b-fee38a55f766 | note | – – – – – – – – –
e74090ae-1c29-52a8-9469-db2ebe1301bb | note | RESPONSIBILITY: Fulton Hogan
79aabfa5-e8bb-5c1b-91c7-41e32b740ef6 | note | – – – – – – – – –
f35453e4-fbb4-5bdd-aede-dba19cf2d22d | textbox | DATE:
f1c32671-756b-45bd-a4dc-c32c2376db1e | checkpoint | Final Inspection
b0474615-6403-5fd1-baed-c139b061c548 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
39988717-4e75-5df4-b17e-4a6fe55c5fd5 | textbox | Print Name:
781e5eef-a7f6-532d-b050-592bf3346219 | textbox | Position:
4478069d-6b06-5ec3-98d8-856e3fb5dd56 | textbox | Date:
c6677bfc-611e-4fe4-886f-969cca6a369b | checklist | FHC-ITP-032 - Concrete Structural Slab |  | FHC-ITP-032 - Concrete Structural Slab
2af8524b-d59d-4537-87a7-05b1d3e98f11 | section | 1 - Design and Submissions
fa16628a-95bd-481e-9168-d2486c6f8008 | checkpoint | 1.1 - Check for correct documentation
a64dacad-f5bf-5a81-99ad-b52d2eddf305 | note | Frequency - Prior to commencing any activity
cb95fe31-253f-5159-8529-06d71c3c6084 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
38581fd8-a091-52f0-ad8d-d556906ed629 | note | - using the correct and complete set of drawings
e66574e3-c0c3-523f-b30a-f9f4b3612ea6 | note | -all drawings are the latest revision
9b511bb0-71cc-5cfb-83f9-819586403914 | note | Reference Documents - Drawings and drawing registers
6a8897db-aa28-5b87-b56a-ce5580d78f04 | note | Inspection / Test Method - Visual inspection
b596ab2a-e111-50de-9504-c647000f6e7c | note | Record of conformity - This ITP signed
f8185113-9414-5600-9f99-3e7c618a9d07 | note | HP*
115a1e3e-8eb8-5e46-8242-d86c39e5033a | note | Responsibility - Fulton Hogan Engineer
340c2fba-417c-5f20-8655-dd4730271f99 | textbox | Date Completed:
60753bae-5fae-4f91-ba7f-23c1bcee1ff2 | checkpoint | 1.2 - Implementation of all measures and controls
2e5e7f24-0018-5406-bb2d-15f24d15daad | note | Frequency - Prior to commencing any activity
192366a8-8505-5166-9a94-21c06398367d | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
1526b9a5-7333-57fd-bb2d-2ecdd45b488b | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
db46111b-78f7-563f-a40c-dcb5e6b34b32 | note | Inspection / Test Method - Visual Inspection
64384ecd-dd1f-5af6-8286-e1d603d8b37e | note | Record of conformity - This ITP signed
754720ab-9693-59df-8cd6-d86d77ed907f | note | HP*
52240a0d-4b93-57fb-b011-1d9f080a26e9 | note | Responsibility - Fulton Hogan Engineer
0a07ed5f-a289-52ec-99ba-e6b4ef85e95b | textbox | Date Completed:
49587e67-5ee0-4aca-97a5-20d923eeffd3 | checkpoint | 1.3 - Approval of mix design
d620acc7-1823-56b2-9efe-5484f8ef601b | note | Frequency - Prior to the first concrete pour
8651389f-e33b-591d-bd5e-46ca380b4a26 | note | Acceptance Criteria - Structural Concrete Design & Submission ITP completed and signed
e7c5fe38-1ea3-54d6-81b6-cf3d411374c3 | note | Reference Documents - 503.04
b2d3c2b7-217c-5683-bb19-ddb42890a597 | note | Inspection / Test Method - Verify
b7cc0e4d-adaa-572b-ada7-a81428a4bde2 | note | Record of conformity - This ITP signed
9869b96c-1285-5e74-906a-0220e04f8d97 | note | IP
c21ad24b-5d18-5d6e-9d5c-8dd36705a042 | note | Responsibility - Fulton Hogan Engineer
d73f9580-bfaa-5e3a-9614-29ff3f1bee8a | textbox | Date Completed:
c73718d8-23d8-480e-ab4e-aafacf8c2e39 | signoff | Authority holdpoint
90254d4c-f574-493e-a624-138e83b3df2c | checkpoint | 1.4 - Reinforcement schedule
a18814f9-f571-5922-8431-a1ed2c9d0b6a | note | Frequency - Prior to concrete pour
dc99ba99-8a7e-5346-b4b8-63b642d8e013 | note | Acceptance Criteria - Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
3bfdf46f-9bb7-5b3c-aaef-b30ea336b6fe | note | Reference Documents - 503.09
3989a104-3556-5878-abfb-da90abb2f23e | note | Inspection / Test Method - Verify
1158c253-03cc-59e4-b579-7be33ccf197e | note | Record of conformity - This ITP signed
164cd2d7-ecf0-514d-bbcd-191255472dda | note | IP
eba4439b-c70f-5514-b729-bf441a761cc0 | note | Responsibility - Fulton Hogan Engineer
f4354ed8-f77b-5285-82f1-04765056f744 | textbox | Date Completed:
b3506ec3-4832-49bb-baae-10a6bc579705 | section | 2 - Construction/Erection of Formwork
051c7d21-fdcd-4acb-bbae-2483c7f49c13 | checkpoint | 2.1 - Excavation
0e246c9d-c2f7-57cf-8a41-9d29edeb40e2 | note | Frequency - Prior to concrete pour
bef48ac8-b3d8-5126-bd96-9050700a4ec1 | note | Acceptance Criteria - Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
5a51e2a6-e3bc-551f-bd35-1346ffac883c | note | Reference Documents - Contract Drawings
c4d42083-4d26-5ff2-95bc-f5962e8b9b1c | note | Inspection / Test Method - Inspect
79d1200c-a179-5737-b3ce-22a3d76e04e5 | note | Record of conformity - This ITP signed
809f3fcb-6840-5c57-bcbf-108675f11d7c | note | IP
9b48c425-defb-59bd-aa7e-0144ab7c1730 | note | Responsibility - Fulton Hogan Engineer
cb415193-ae65-57ca-98a4-a65a70151b04 | textbox | Date Completed:
60a80b2d-40dd-4fea-ae93-add6a0ebc92f | checkpoint | 2.2 - Construction Methodology
7d0e85a2-31a8-5307-b364-7b860d540270 | note | Frequency - Prior to erection
7dcedade-ff5c-546e-ba76-c827e654f3d6 | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
6465fe29-2524-5b02-af98-085818506ec6 | note | Reference Documents - Contract Drawings
ed352c0e-6744-5a26-bcb6-58442536af6e | note | Inspection / Test Method - Verify
d443f332-baa2-5243-bd8b-6fbda53086c2 | note | Record of conformity - This ITP signed
1a7c3343-a394-5c22-b903-605249ad762e | note | IP
2863c312-2583-5bb2-808a-c24f9a1bed50 | note | Responsibility - Fulton Hogan Engineer
3cc87cb9-d698-5f81-b8f8-904a6de16742 | textbox | Date Completed:
c92f78c7-f6ca-42c2-872b-8f172966a948 | section | 3 - Pre-Pour Planning and Inspection
4f26e500-d1e9-47bd-adec-9e137b19203a | checkpoint | 3.1 - Excavation/Foundation – Blinding, sealing or foundation concrete
941d4f4c-2fd4-5745-8c67-67db8a3e047c | note | Frequency - Prior to concrete pour
2385140b-5974-59d8-a3b7-c2804356628a | note | Acceptance Criteria - Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent.
a1a38731-e326-5363-9468-b428783369dd | note | Reference Documents - Contract Drawings
ecad2959-dba5-536d-8b0b-6a22868b8212 | note | Inspection / Test Method - Verify
f9baac72-782a-513f-9b6b-ebb52e358208 | note | Record of conformity - This ITP signed
34a97182-5b7b-5e3a-8b07-cd872e7056ec | note | HP
741058e9-4617-500e-bad1-d9f1e24e1d32 | note | Responsibility - Fulton Hogan / VicRoads
922ec005-25a2-578e-af1d-a863563fd1c9 | textbox | Date Completed:
f4438769-020a-4610-a4ad-dabe879a8580 | signoff | Authority holdpoint
49af312f-fc22-4c16-9332-7d78229a1691 | checkpoint | 3.2 - Formwork levels and position
937c11df-e793-5549-bbf4-f71130c91ac5 | note | Frequency - Prior to concrete pour
9e2a63ce-e259-5190-b3ff-c3158a932c46 | note | Acceptance Criteria - A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
92dd986c-1e45-5d50-b332-c7c516b04eef | note | Reference Documents - Contract Drawings
a09b71e5-c532-5886-95ad-055a4d9a7554 | note | Inspection / Test Method - Verify
f93e3f73-9076-58d7-9182-ca1efa7736ee | note | Record of conformity - This ITP signed
5cfc02cb-bd59-5da4-9755-74fd2bcdfa25 | note | SCP HP*
718e97fb-4c99-52c8-b7c6-01154f282abb | note | Responsibility - Fulton Hogan Engineer
d0994eb2-8c97-53d2-877d-47d20b3ef781 | textbox | Date Completed:
7c099630-38f0-4878-bb11-970fb6974529 | checkpoint | 3.3 - Location of splices
c723cd61-7e5b-5cc5-b4f4-135b5c9486e8 | note | Frequency - Schedule Review
9676aeb2-fc2d-538f-b519-a44242719008 | note | Acceptance Criteria - In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
7fd3ef0b-d83e-543b-964d-91a74f3304fe | note | Reference Documents - Contract Drawings
d6387c7f-2a25-5c17-9cf0-82b06375ff6b | note | Inspection / Test Method - Inspect
b674c288-adaf-55d8-a59d-e3cb604b32c3 | note | Record of conformity - This ITP signed
e31b360a-4c33-5864-a263-b92171b62fcd | note | IP
90e54313-94c8-5487-9783-9d5ecdefdbd9 | note | Responsibility - Fulton Hogan
d6e53d58-3130-5ce2-a489-e253487de5b6 | textbox | Date Completed:
3daa8232-5b2d-498d-9a84-3b034dc13c47 | checkpoint | 3.4 - Cleaning formwork
af971fbd-f971-56d1-a59b-b38105fe3254 | note | Frequency - Each concrete pour
4e9fa2c0-41c8-5ca7-b397-b5950a25661b | note | Acceptance Criteria - Concrete shall not be placed until all foreign material has been completely removed from the forms
186e2f13-958e-5a19-b8f3-056756e1ba3c | note | Reference Documents - 503.13
665ca306-821c-5910-b7bf-b8ecc5433f31 | note | Inspection / Test Method - Verify
7c35bd2d-e3dc-5796-9825-9eea6853a457 | note | Record of conformity - This ITP signed
78e37429-dbc7-5978-86b4-3c6e873f725e | note | IP
92361395-9139-582c-877e-15640c2abd5f | note | Responsibility - Fulton Hogan
681cb6d0-5bcb-5c35-a8c4-47a55ca5ec7e | textbox | Date Completed:
5ddb1ff0-c27b-4b79-bdf5-9e4ce228079b | checkpoint | 3.5 - Correct forms, reinforcements, rag bolt assembly and embedments
73387954-bef4-54b1-acb4-e6d37cf284f0 | note | Frequency - Prior to concrete pour
f9a8bc3e-ec60-5d4a-a146-6853834fbb11 | note | Acceptance Criteria - Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
83ff3ff6-1bce-5116-954a-b718c3cd5eca | note | Pre-pour checklist completed and signed.
19d079fb-0b13-57ea-a647-b00c28fc37f4 | note | Reference Documents - 503.07
4f5670ba-1c67-5fdf-9336-6abb5782c34b | note | Inspection / Test Method - Verify
1a9b23f6-369d-5259-89ec-5370426710cc | note | Record of conformity - This ITP signed & Pre-Pour checklist completed
1ddccf5c-a1c4-5317-8b8f-73714e52cedb | note | HP
a6a2fb3e-724d-5592-9c98-d997278ca534 | note | Responsibility - Fulton Hogan / VicRoads
7a599b3c-ff3b-5909-998d-01decf9914bc | textbox | Date Completed:
643000dc-d150-4589-a019-b3dae982fff7 | signoff | Authority holdpoint
a69e1198-599c-4bba-aa61-17c157cb7578 | checkpoint | 3.6 - Reinforcement assembly of piles
7629b8a4-7128-5c87-bea0-6e50f67b293c | note | Frequency - Prior to concrete pour
48b05d8f-f875-57a0-a040-630e911dd589 | note | Acceptance Criteria - Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
e0676f2c-6478-5dcc-8590-057154ca2896 | note | Reference Documents - 503.07
cffbb346-274b-5840-98ad-b157ea34fcc8 | note | Inspection / Test Method - Verify
a9d017ea-e1ec-55d1-a033-9b0b90924b9f | note | Record of conformity - This ITP signed
dde211ae-10c6-5a7a-ad75-2528094aaa0b | note | HP
92a2e608-6d0c-5cef-b3e5-f950bf46830f | note | Responsibility - Fulton Hogan
93152b04-cd98-5724-822f-5173fb8d88cb | textbox | Date Completed:
4cf2e4c2-29ed-4f97-8961-c15b94854d32 | signoff | Authority holdpoint
546f23af-c450-4cae-9204-b4a4d9ab20f0 | checkpoint | 3.7 - Monitoring weather
043818aa-e455-5a30-bd73-383cef5ec38f | note | Frequency - Prior to concrete pour
7a853882-fd6d-5ad7-82ee-c2b143a9f11f | note | Acceptance Criteria - Concrete shall not be place when temperature is <5°C or > 35°C All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
506974b3-b528-50df-904a-5c4be3eac64c | note | Reference Documents - 503.07
01869af8-42d5-5379-909a-022a325dfb72 | note | Inspection / Test Method - Verify
b4bc2566-4ad9-5088-b18f-141e3358df3f | note | Record of conformity - This ITP signed
542784ad-e1d1-59dc-8e32-6f84eb0c74c8 | note | IP
5dc25060-095b-5fef-86b4-426373e5784e | note | Responsibility - Fulton Hogan
405dccac-d756-5536-a0f5-9a62ae14717e | textbox | Date Completed:
c5765c70-5cbc-49da-91ba-d900c6998c96 | checkpoint | 3.8 - Assessment of Base Thickness
52e03bdd-efca-509f-a89a-4814efc38278 | note | Frequency - Prior to lot closure
f8e75a5f-2bfe-5ea9-9ea9-fb6b17e6698a | note | Acceptance Criteria - Within the lots defined for assessment of compressive strength the surface levels of the subbase shall be measured as specified in Section 173. Levels of the base surface shall be taken at the same locations as taken on the subbase.
82ab62dd-a177-55a3-9d67-8a3b6ab0398b | note | Reference Documents - 503.05
10abfb28-8ddf-50d1-8463-7a2eec604e1b | note | Inspection / Test Method - Verify
e503b111-a9bb-54a8-95a2-9aff3307b35f | note | Record of conformity - This ITP signed
41a9b90f-24bc-5a21-827a-39093af4ef0d | note | TP
451fa690-f436-5cf8-ac02-fd269dce6479 | note | Responsibility - Fulton Hogan
7908ef17-25b4-518b-b108-fca063ef1182 | textbox | Date Completed:
6a09924e-340e-4075-ad07-4c1a8c8b6e3d | checkpoint | 3.9 - Concrete Sampling and Testing
762d8089-abdf-5d5c-a973-54911f5f90df | note | Frequency - Prior to placement
fd62dd5b-3409-53be-8700-d83ee1efef19 | note | Acceptance Criteria - Concrete sampled and tested for slump test.
330b50ed-73f7-5a2d-a5c7-43bf3f1804eb | note | Reference Documents - 503.05
4b4e6873-e229-508c-bf3c-046b6418eea1 | note | Inspection / Test Method - Verify
9d4638b1-3841-5962-8cb4-76bebef2da75 | note | Record of conformity - This ITP signed
6520312c-e3c2-5ce9-a518-dd873d23b700 | note | TP
704f3189-f2e8-51be-ac04-b19ce0eef93e | note | Responsibility - Fulton Hogan
de28ae2e-ac68-5141-8f06-2613191c7d84 | textbox | Date Completed:
5e6b10c9-79f4-4499-830d-5002776882a8 | checkpoint | 3.1 - Sampling and Testing of Cylinder Specimens
f2fee333-1e54-5832-9a1e-2dcec99f3f6f | note | Frequency - During concrete pour
09f0d591-e0b4-59b5-b47f-8130a9b6d97a | note | Acceptance Criteria - The Contractor shall record 3 sample, prepare, cure and compression test of 12 cylinders cast on site in accordance with AS 1012.
38b223a5-3ae0-517d-bae6-341499d7ce27 | note | The concrete shall be sampled at the point of discharge to the roadbed. Each sample shall consist of two cylinder specimens for testing at age 28 days.
32637529-8a54-5ae6-9ec6-d59d5dbc9ba4 | note | Reference Documents - 503.05
06cd8c02-7ccf-59ee-8c3b-5ef420178f60 | note | Inspection / Test Method - Verify
f6dd4367-591c-5fb9-9661-ea53ab0bcc74 | note | Record of conformity - This ITP signed
6e55c3f4-7660-561f-9866-83e5bca76fc7 | note | TP
5bedd6e8-ebea-5544-a7a4-181729926e3c | note | Responsibility - Fulton Hogan
fa64e2f0-b496-5070-975b-d8e7e5319bd0 | textbox | Date Completed:
1374ff07-5519-4365-89c6-e117ce70b4d7 | section | 4 - Placing and Finishing Concrete
0ba67865-f29e-4e43-a19b-bf7ddaa32c8b | checkpoint | 4.1 - Carry out sampling of concrete
b2376706-aa13-5f49-8884-70c9172cd844 | note | Frequency - Each concrete pour
21a87f2b-501b-583f-9e92-d74ea355ceb2 | note | Acceptance Criteria - Sampling in accordance with 503.05
ce2f5204-54cf-55cf-8756-808076caea61 | note | Reference Documents - 503.05
2d27c938-0680-5562-baf0-1bcc02013fcc | note | Inspection / Test Method - Checklist
2e5c14ef-28e2-58e8-b209-fd1dc5e299f8 | note | Record of conformity - This ITP signed
6c9a4922-c614-5c73-94d7-a3bda1a1bb4b | note | IP
73b01c0b-e2f6-5e99-af7a-c05d15da3618 | note | Responsibility - Fulton Hogan
5a9187ae-68d3-58c8-af5c-402b8eba6fd2 | textbox | Date Completed:
40c6c646-3521-476b-9d8b-8f637308179a | checkpoint | 4.2 - Discharge time
0fb9f2c4-ddec-51cc-8fa7-e8257144840d | note | Frequency - Each concrete pour
7ed912bc-b7ad-50bf-bf6f-41ab46d077a9 | note | Acceptance Criteria - Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
012a7ced-f36a-56e8-ab85-8810f8173be6 | note | Reference Documents - 503.05
4d295692-c479-5720-937f-620743ee377c | note | Inspection / Test Method - Verify
f959a468-53ef-5a86-aaca-7b3ff452ad7e | note | Record of conformity - This ITP signed. Accurate Site Notes & Load Mapping
87afede7-73d8-5a02-a9b8-f714f712641d | note | IP
c977387d-ac9d-508b-9656-18a7f204f70a | note | Responsibility - Fulton Hogan
bc691aee-02eb-5032-9a75-b3d2c745b27a | textbox | Date Completed:
a3c257ee-7f6b-41d5-9a1c-115cef378310 | checkpoint | 4.3 - Concrete Placement
bbd8efa7-28f4-5f77-bcc2-9779b8cd56d3 | note | Frequency - Each concrete pour
51f02ec1-b151-5ffd-b868-28d3ffa68838 | note | Acceptance Criteria - Concrete shall not be placed until the proposed method of placement, spacing of planned transverse construction joints and the provision of dowels, constructed formwork, reinforcement and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Superintendent.
7c4d147c-8e78-5b36-81f4-675cba6167c7 | note | Reference Documents - 503.05
9c4f8370-7703-593a-ba0a-1da35f6e2996 | note | Inspection / Test Method - Verify
47a2f2a3-cef2-5cac-b7e3-2b0a5d86a0d7 | note | Record of conformity - This ITP signed. Accurate Site Notes & Load Mapping
0a706c19-a081-5f11-bd7e-bdea6907a322 | note | HP
513254ae-8291-5565-9c32-ffd66b84a8b4 | note | Responsibility - Fulton Hogan Engineer
bab03ae9-ebee-5b85-b9d7-5f91a2f3bec1 | textbox | Date Completed:
6e0b814c-20d7-405a-b8b7-6e8eb5c0fd0c | signoff | Authority holdpoint
c985641c-ebb5-404d-9931-44fddac7a974 | checkpoint | 4.4 - Methodology of Placement
d9503c10-e755-585c-b170-b16544ffae3c | note | Frequency - Each concrete pour
4f0acffb-6ba6-5cd0-ae01-d6f67068531b | note | Acceptance Criteria - Concrete shall be transported, handled and placed in a manner that will prevent segregation or loss of materials Concrete shall not be moved horizontally by vibrators In continuous pours the max. time lag between truckloads on site is 25 minutes
9f3be893-1882-575c-acad-329451cfaeeb | note | Reference Documents - 503.07
0b238aa9-2b45-591c-9d2a-539df4d5ead1 | note | Inspection / Test Method - Verify
ca90833e-2640-5023-85d0-4e6eb23b1c6a | note | Record of conformity - This ITP signed
2c9ef4d9-e2fd-5886-b5af-7e50637c2010 | note | IP
f761368f-636c-5baa-a24d-e753a1fa9dd1 | note | Responsibility - Fulton Hogan
15362978-276d-5b20-8774-506e526c9e51 | textbox | Date Completed:
9f0271f4-d9b5-4fbf-a9f8-fe76c657f424 | checkpoint | 4.5 - Compaction
b7f7732f-5215-5ee5-b49e-c6f61d128cf3 | note | Frequency - During concrete pour
2d7c4e17-62d6-5dad-8210-401bfec948fc | note | Acceptance Criteria - Base and subbase concrete shall be compacted to meet the requirements of clause 503.05. Concrete placed around dowel bars shall be carefully vibrated without the vibrators touching the dowels.
f5188b9a-c5d9-5f73-aa63-df286c953943 | note | Reference Documents - 503.07
f8ae1baa-2511-5965-b481-adbc81aa2eb9 | note | Inspection / Test Method - Verify
aafe9137-9379-591c-8010-657bae0ac81a | note | Record of conformity - This ITP signed
f9b5661a-bd23-5d48-b821-82fd582f59d7 | note | IP
6dc23e92-a8e1-5f07-b8d2-3ee8b7999312 | note | Responsibility - Fulton Hogan
664e12cc-ac59-57f2-853e-9255d6111f4c | textbox | Date Completed:
cb61d7a5-b867-4d36-86bf-3ddd6dc22eba | checkpoint | 4.6 - Screeding and Finishing
1dee11c7-466e-55b4-b92d-1effc783534a | note | Frequency - Post concrete pour
db412193-8fb9-5bb7-9f51-7b2cff2e4653 | note | Acceptance Criteria - The concrete shall be finished to provide a dense and homogeneous concrete surface satisfying the requirements of clause 503.03.
df5662f6-53e7-5baf-bf84-27d13c94bd51 | note | The subbase concrete shall be finished to a uniform non-textured surface. The base concrete shall be finished to a textured surface as specified.
532ea8e9-83f7-57ba-b7f2-cc53afdddbc4 | note | Reference Documents - 503.07
e3448db4-647b-5250-89fb-7f8034fa39de | note | Inspection / Test Method - Verify
302d2f6b-b6d8-5cca-a32a-731ffec142df | note | Record of conformity - This ITP signed
6930514f-5c6f-5f81-8514-e735e3c21e84 | note | IP
a025d3a6-729e-566c-b438-b2470c827f30 | note | Responsibility - Fulton Hogan
bcc05c1c-8eca-5851-9cf8-1d5b054023d1 | textbox | Date Completed:
a195acef-a7b2-4dc6-864b-5ce11b4125ec | checkpoint | 4.7 - Joint Sealants
aa5f0743-b5ed-5253-a363-d7cad50b6aca | note | Frequency - Post concrete pour
d96bb3b5-84c9-5e37-845e-ac3145baf827 | note | Acceptance Criteria - Permanent seals shall be either a neoprene compression seal or an in situ cast silicone sealant. A full technical description of the proposed sealant and method of installation recommended by its manufacturer shall be submitted for approval by the Superintendent at least four weeks prior to installation.
68437d16-f577-5f22-bace-635b1cd417ec | note | Reference Documents - Contract Drawings
b760d507-b10e-5bcf-9cc1-b0847257918c | note | Inspection / Test Method - Verify
c348b633-bf0d-50fe-b1a2-1fd7f70f577a | note | Record of conformity - This ITP signed
d03017e3-4dce-59f5-b413-e59097f2018e | note | IP
9c690c6a-2780-502c-8095-a647fc25e5c8 | note | Responsibility - Fulton Hogan Engineer
95d4c959-1afd-5cee-9029-8242717eb6f0 | textbox | Date Completed:
c1e8003d-ede9-4b8e-87e6-7f88857ad119 | checkpoint | 4.8 - Joint Sealants for Base
bddf1675-2b74-535c-8e40-6abd5d284c85 | note | Frequency - Post concrete pour
05748a2c-9d82-57d0-ae7e-dd3c2fd58da8 | note | Acceptance Criteria - Joints shall be constructed as specified and shown on the drawings. Joints shall be straight and vertical. Transverse joints shall be continuous from edge to edge of the pavement. Tie bars shall be installed such that anchorage strength of at least 85% of the yield strength of the bar is developed upon hardening of the base.
11ff1cc4-1e36-5526-8d6b-15f54b8a664b | note | Reference Documents - 503.13
e12ae7ec-a3f9-5da5-a276-70c995c06320 | note | Inspection / Test Method - Verify
b2fd621d-a63a-5fcb-86f3-30bce537e8fa | note | Record of conformity - This ITP signed
5b25b3b7-6204-51a5-a24c-a4f2a4beae5c | note | IP
a5258db2-0675-59bd-9e78-ade1a40d85a0 | note | Responsibility - Fulton Hogan
e2462fe3-5e42-547a-9a70-8d16520037b2 | textbox | Date Completed:
fb7c1973-5859-4d3d-bc0b-47bac99ea327 | checkpoint | 4.9 - Texturing of Surface
05287d64-37c2-5ad1-b431-6536e716cce2 | note | Frequency - Post concrete pour
266ccce8-7dfa-577b-9a23-24bc1df1ceb8 | note | Acceptance Criteria - Texturing of the concrete surface shall be carried out to the standard of surface specified in clause 503.21 using a hessian drag or steel tines. The textured surface shall extend across the full width of the base and shall be uniform in appearance.
6f1e727f-f025-5796-9d67-ac1651f4910a | note | The concrete surface shall be finished to achieve an average texture depth between 0.40 mm and 0.70 mm. The texture depth shall generally be achieved using steel tining equipment which shall comprise of rectangular shaped tines of flat spring steel, approximately 0.6 mm thick. The width of the times shall be 2 mm.
b4c285c2-9467-58ed-a8bd-de8e7dd9b286 | note | Reference Documents - 503.17
4ae8a1b1-3f97-516a-ab23-ddb45000ead1 | note | Inspection / Test Method - Verify
d75c649b-0be7-5f7c-bbf7-3a0ae80c2b31 | note | Record of conformity - This ITP signed
2ec144d6-3bb0-57ed-bad4-d936eb113f27 | note | IP
fd355cd3-0a75-595d-ba67-7cc59609ebf7 | note | Responsibility - Fulton Hogan
f75e6d9d-d31a-5a47-b3bd-1f566af16493 | textbox | Date Completed:
b9488e81-8f06-4b01-9f76-6b023b92a002 | section | 5 - Post-Pour Details and Inspection
4fc5fad9-ab59-4a29-9dcc-e4c614890a8a | checkpoint | 5.1 - Curing and Protection
0be384da-fe4d-5e2b-8e37-eb56aef9fe05 | note | Frequency - Post concrete pour
e9c83509-42c8-5bfe-b360-2124b113ca41 | note | Acceptance Criteria - Curing of the base and subbase concrete shall be undertaken by the use of a curing compound sprayed onto the freshly laid concrete at the application rates specified in this clause. Curing compound shall not be sprayed when bleed water is present.
cf9912b5-85f1-50d0-ba5b-9d84a709ce06 | note | Reference Documents - 503.18
e166746f-e866-5764-837e-9a84b4e9d92d | note | Inspection / Test Method - Verify
0d18b0b0-ecac-5e28-872e-c5d2e615c77b | note | Record of conformity - This ITP signed
33432849-207c-5d59-ad4a-09e55d8b4fb4 | note | IP
e9047663-07bc-5843-a4d7-041ed1d05f3a | note | Responsibility - Fulton Hogan
e7725c57-121a-56b7-8472-a7ab54d51853 | textbox | Date Completed:
1727b1d5-c581-40f7-986a-b4547754de4c | checkpoint | 5.2 - Curing Compounds
3a2a0136-459f-58ad-a7b3-261b7d4aaac4 | note | Frequency - Post concrete pour
9aaff64b-deda-57a6-af13-8792a9228798 | note | Acceptance Criteria - Prior to the use of curing compounds, the Contractor shall submit to the Superintendent for review not less than four weeks prior to placement of concrete
2bc89255-8544-54e9-87d3-1d694e524b91 | note | Reference Documents - 503.18
0ce55507-1146-5a17-8495-ed0b8a23645b | note | Inspection / Test Method - Verify
b2bddd01-39f9-5bcb-8383-ee38bdae0257 | note | Record of conformity - This ITP signed
5fe59527-cfdc-5208-ba9c-48255660fab4 | note | HP
6ed838b4-9571-5b3c-882e-686d5d5288d7 | note | Responsibility - Fulton Hogan Engineer
29c08053-2a65-51f7-b3b7-351dcb7b82b8 | textbox | Date Completed:
db91f69b-0b5e-477b-b4e4-3d36ba99c42b | signoff | Authority holdpoint
19e7be70-9238-4ea8-8a74-bbf78847adbb | checkpoint | 5.3 - Formwork removal
7b3a8652-2d0f-5595-ab9c-b254dc458705 | note | Frequency - Post concrete pour
c360b1b7-785f-5721-8fc3-ffe3da6905ce | note | Acceptance Criteria - Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
8e9182dc-9219-5565-97b6-cfefb53a9abe | note | Reference Documents - Contract Drawings
e4a3a69e-fa0e-5f98-b19c-537ae5cf68f3 | note | Inspection / Test Method - Verify
772d53d9-3c2e-5a65-8b0b-4d254e00d7ca | note | Record of conformity - This ITP signed
45d4da4e-4487-543e-8a59-f684289c9386 | note | IP
3f757626-7c9c-503e-94e0-b830b8e6f9b4 | note | Responsibility - Fulton Hogan
d85525a4-33d5-5313-a76b-541ba63bfda7 | textbox | Date Completed:
5898efe7-65ab-4326-98b5-b865346a0335 | checkpoint | 5.4 - Concrete Base Course
88b3d27f-3790-5982-aa6e-3cb93cddcf29 | note | Frequency - Post concrete pour
b38e60df-2a64-5552-9512-bbe70c5af606 | note | Acceptance Criteria - With the exception of concrete saws, personnel the concrete base course shall not be trafficked until the in situ compressive strength has reached at least 20 MPa based on concrete cylinder testing.
3eacd1c8-df1d-5e7c-a7c8-38faa2b027fb | note | Reference Documents - 503.19
9617879d-d6e8-565e-911b-def61b2f25e5 | note | Inspection / Test Method - Verify
9c904597-59be-5f9f-ab77-e0df9b99409d | note | Record of conformity - This ITP signed
47cef988-0e21-5cee-a1fe-918aa18bdef8 | note | HP
8930eb0e-51bc-5972-87f5-a524be7af5ec | note | Responsibility - Fulton Hogan Engineer
a2ef35d0-5f14-5092-b111-441045531c0a | textbox | Date Completed:
aef415d4-b721-4582-a939-ee9a6822d1fe | signoff | Authority holdpoint
08e8de86-d757-4677-be39-189f8112c917 | checkpoint | 5.5 - Positional tolerance and dimensions of concrete members and piles
f37c2005-52d3-5f00-a96e-b342ddd04d97 | note | Frequency - Each concrete pour
7aad3f0a-809c-5088-ac55-643cb8482045 | note | Acceptance Criteria - Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
97248d5b-e8d8-5fd8-a31c-5cf661220ddc | note | Reference Documents - AS3600 Cl 17.5
eeb8d931-cef5-5787-9b0d-edcbe7767ab0 | note | Inspection / Test Method - Verify
b302397d-f090-5937-865e-6834afd701f1 | note | Record of conformity - This ITP signed Post Pour Checklist completed
4efaf050-f878-5ef9-9b34-9baa4ebac5b9 | note | IP
b4ca42fb-8426-5772-a833-ca7e80d01a8b | note | Responsibility - Fulton Hogan
0e6f2dd1-c9b7-5ad1-b01d-3d3f6168fb56 | textbox | Date Completed:
9689e52e-6abd-449e-8dbc-714b4be86d3f | checkpoint | 5.6 - Concrete Sampling and Testing
1e24edd3-9ca8-5195-b49f-4e5c5973ed42 | note | Frequency - Prior to lot closure
7c373751-8a59-5b75-946d-b15e56f2ea60 | note | Acceptance Criteria - Concrete sampled and tested for compressive strength. The required strength of concrete must be in accordance with the drawings
1c8fd0c3-8dcb-5cd6-bc03-97cf9a9928f5 | note | Reference Documents - 503.05
47049516-f9f5-50d5-a3fa-73d8ca424ac7 | note | Inspection / Test Method - Verify
45e4711b-0701-52e7-a08d-33234074af69 | note | Record of conformity - This ITP signed
00949568-09e1-5ef9-8b94-d8e993e9c92b | note | TP
a94eff57-8d57-5d40-8e98-2bd465915e5a | note | Responsibility - Fulton Hogan
a047ca69-73d3-556e-91cd-8565555d656c | textbox | Date Completed:
c7548dee-15f8-4318-b35c-4d76d3bbec8c | checkpoint | 5.7 - Curing and Protection
e9257585-05bb-55d7-b233-e31597eb2b9f | note | Frequency - Post concrete pour
6c7452d0-3ab8-5c48-8b72-28bbc4ff66e9 | note | Acceptance Criteria - Saw cutting and joint sealing shall be allowed on the finished base concrete until the in situ strength of the concrete is at least 60% of the target 28 day compressive strength.
eccaaf91-5ba5-5cb2-adc7-5f9161b4e9b3 | note | Reference Documents - 503.18
326b1ae1-e467-5a88-96a1-2ac75cef78de | note | Inspection / Test Method - Verify
2538f1cd-9ce4-579e-902a-af8d841bc122 | note | Record of conformity - This ITP signed
e34c2bde-59a5-547b-a72e-6c0164254da5 | note | IP
558e493a-b9d4-52bb-8150-11585c812346 | note | Responsibility - Fulton Hogan
1ca95007-e3fe-5c00-b318-2ccce4fa8073 | textbox | Date Completed:
1cb577c4-07de-45e6-a66d-d7f90eff2b5f | checkpoint | 5.8 - As Built Drawings
fb4abdb4-c125-52ec-818e-2a130786b7ad | note | Frequency - Prior to lot closure
606605af-3768-5df2-9f96-2cb98bb9a4b1 | note | Acceptance Criteria - Recorded of as-built drawings
20d3dd15-6455-5f4b-bde0-d503f55926ce | note | Reference Documents - Fulton Hogan Procedure
1b81897d-e4fd-5324-a768-b0a3701fa40e | note | Inspection / Test Method - Verify
ffbb5512-0c42-5d1f-9295-32e6ee210a38 | note | Record of conformity - This ITP signed
f28e39cb-9cb1-5978-aa7c-2f102e45a751 | note | IP
a8b22c77-e7ba-564a-a549-e858c4161549 | note | Responsibility - Fulton Hogan
9f7c3eec-fb75-5c7c-9e07-aa6ac5c5fcd5 | textbox | Date Completed:
dcdba9cc-19eb-4a14-9906-f275d3fb7b54 | checkpoint | Final Inspection
9a1c0e05-74b8-5165-853c-b67b1649645a | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
53728886-67b9-5d01-a392-6f267e7d6d0f | textbox | Print Name:
a4093b5c-49b7-500f-ac4f-c6151981f24a | textbox | Position:
0daeb65a-8392-56e5-9599-6b07e1dbb60a | textbox | Date:
69542b4c-f6e7-4076-8cc3-06db21170893 | checklist | FHC-ITP-033 - Concrete Nib Wall |  | FHC-ITP-033 - Concrete Nib Wall
06dd2957-23f6-40a9-bc03-fc196d3e64ee | section | 1 - Preliminary Works
1098a3f8-3042-4cf1-a7b5-0effc9a192f7 | checkpoint | 1.1 - Check for correct documentation
aa22e37f-329a-588a-a892-26ef8af83e15 | note | Frequency - Prior to commencing any activity
3cb0bdc3-4fa5-5205-923a-a22e672a68f2 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
93e14ca0-7586-53bc-8f1e-6f5846427796 | note | - using the correct and complete set of drawings
0be017a1-ccc6-5352-9f38-a1ef26147d57 | note | - all drawings are the latest revision
b0c18c13-1f41-5341-9da2-36bd1b58715a | note | Reference Documents - Drawings and drawing registers
70d235e5-1d77-51b3-a3d8-777b7331b202 | note | Inspection / Test Method - Visual inspection
da07680f-1f23-5899-ac03-7fa1392e270b | note | Record of conformity - ITP Signed
35555d33-05e6-5b8e-8c9c-476f09a4d1cf | note | HP*
c4d81fa8-c93b-5323-8e47-b5cd3cf9a033 | note | Responsibility - Site Engineer/ Site Foreman
3da20d26-7349-5c00-8c76-64ec346ed564 | textbox | Date Completed:
48fe2bb2-53bf-4008-8cde-ec1515bfd36b | checkpoint | 1.2 - Implementation of all measures and controls
8df67ae8-e9bb-50f7-9b7e-cf2ea651a197 | note | Frequency - Prior to commencing any activity
9b687fbe-8e89-590d-8e0a-73cd821a42ef | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
9ca48168-b5a9-51e0-a7ea-d640a64816cd | note | Reference Documents - OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
8009d7a4-8120-516b-a830-fc14d8a35795 | note | Inspection / Test Method - Visual Inspection
b758b2fc-0fbc-53d1-b323-808835d0940c | note | Record of conformity - ITP Signed
8cf17271-b53d-5056-bfce-71280e036cbe | note | HP*
938fcb55-0393-581e-aafd-d26672d1d021 | note | Responsibility - Site Engineer/ Site Foreman
453433b1-662f-5421-95d3-e290a2bc6ce9 | textbox | Date Completed:
48f24473-5103-432b-8337-90f6640fb1b5 | checkpoint | 1.3 - Submission & Approval of Concrete Mix Design
ab40c333-1f0c-548a-ad8b-5e14cfee0ca1 | note | Frequency - Prior to first concrete pour
0face48c-762c-5d19-bff6-e370ef68fbc8 | note | Acceptance Criteria - The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
9982d49f-b7b4-5999-a8a5-a5b2baa8852b | note | Reference Documents - 610.07(b)
e5af3836-9c66-5b8a-b873-5ee659029b36 | note | Inspection / Test Method - Verify
7abc3f4c-66b1-5955-bd76-6ad9159fdca8 | note | Record of conformity - ITP Signed
304df73b-90d7-5706-872b-e1f29f45e6da | note | Mix design approval
e5bd2db0-b1bd-5125-872c-91becd95ce65 | note | HP
6456d43f-f355-5255-98d6-7d927acbeee4 | note | Responsibility - Site Engineer/ Superintendent
c2a6ce0b-04c4-5450-8199-573bb1e96f1e | textbox | Date Completed:
9bb218ac-81e7-4c40-81a1-3de7f04fb7b2 | signoff | Authority holdpoint
d24103be-ddee-49e0-9cd7-4c306371bc84 | section | 2 - Construction Works
6ba83733-9610-414c-979f-83c07a0f8a78 | checkpoint | 2.1 - Setting Out
431cf173-2fe6-5e0e-86c9-52f0a8dd5e2f | note | Frequency - Prior to start
db0ade98-25f5-5dd4-9835-66f95d048875 | note | Acceptance Criteria - Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
5b0934f6-6715-503c-b351-387a36604bf9 | note | Reference Documents - 703.17
df31882c-7294-5a24-bb93-3307fde0e07d | note | Inspection / Test Method - Verify
f23efbea-5d5f-528b-86c7-f29da7000638 | note | Record of conformity - This ITP Signed
ad18904d-053a-5f26-b241-b6f7d4436180 | note | HP
1a6af372-34fa-5836-972e-f7bc6a8c507b | note | Responsibility - Site Engineer/ Superintendent
0907308b-3626-5008-ba40-f9a235d64afd | textbox | Date Completed:
72339dad-5c2e-4247-8bb9-218044914610 | signoff | Authority holdpoint
da7301eb-904b-4589-9ba1-2f3dd6fbc0ce | checkpoint | 2.2 - Excavation Permit
5b4dd828-20fc-5c49-b25f-55ec8ff43e0f | note | Frequency - Each lot
20412de8-3398-5d2b-b2c7-a3c6818f8c89 | note | Acceptance Criteria - An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task.
cc0be9ab-495e-542a-9fa8-cb63fdedb64a | note | Excavation operations shall not disturb areas outside the limit of excavation
8dc111fe-60fe-56f7-b925-14a88fc51c3d | note | Reference Documents - Excavation permit
45791982-fe77-5837-9ffa-5c7df4c0bf3f | note | Inspection / Test Method - Verify
893c1a3c-4dea-54fd-bde9-c7129293c24f | note | Record of conformity - ITP Signed
3faf7842-9a13-529b-ada6-c85335cd2422 | note | HP*
75656684-2707-55d0-b356-3df3ab128750 | note | Responsibility - Site Engineer
cc89c1ae-d168-538b-b74d-accb0078c0fd | textbox | Date Completed:
dabddd42-46e8-49b5-9a1e-58855dea5e5f | checkpoint | 2.3 - Excavation
31fa97b1-4738-58fb-9feb-af7a46ddd295 | note | Frequency - Each Lot
83aa56f6-ec9e-5870-b0b9-f9d35bd80b99 | note | Acceptance Criteria - Excavation completed to required depth to allow placement of the bedding layer
c2e80040-a129-5b13-ae99-d02eed5cc6c7 | note | Reference Documents - 703.2
826caaac-038c-5392-8558-0bffdf2a5993 | note | Inspection / Test Method - Verify
ecc5c04d-20b0-5cf2-bb67-6c09cdb4dedb | note | Record of conformity - ITP Signed
d932631c-4419-5c83-be86-66062c140548 | note | IP
de4b8ee8-de81-5b99-8313-c7a5bea241f8 | note | Responsibility - Site Engineer
d554dcb8-6fb8-5f18-b548-94894449dd83 | textbox | Date Completed:
dcd3e85a-bef7-4741-8251-9a8c3f0a879d | checkpoint | 2.4 - Bedding
4edca6cb-5f4f-5603-9214-dea9cebaab74 | note | Frequency - Each Lot
64c561d2-1776-5529-b2d1-376ff873ba8f | note | Acceptance Criteria - All bedding material used shall be as follows:
35114c0b-b3ce-5385-9bb1-2a9ff64432f7 | note | - 100mm thick layer of 20mm Class 3 crushed rock bedding for median infill
9d4e80bf-99d5-5d68-9e70-8b4a7b8543a8 | note | - Bedding trimmed, moistened, and compacted as per Section 304
c6f26451-8057-5002-944c-a3d84ed4c1a5 | note | Reference Documents - 703.21
7dcce26a-a1a8-5ae1-ace8-a5009e978c4a | note | Drawings
31cd901c-6638-51a1-a905-7924422c1e2c | note | Inspection / Test Method - Visual Inspection
1d084d19-2f48-54b4-9e4d-f0c879ed341b | note | Record of conformity - ITP Signed
a6f10188-763c-5bbb-bf4f-64d41852ae1f | note | IP
64e026db-8fff-5e1e-bc2d-0ed9f80c22b9 | note | Responsibility - Site Foreman
a9008f03-3553-5931-b8fc-7bf589159671 | textbox | Date Completed:
c98b3e21-482a-4c0b-bcdc-d8292b31cd2b | checkpoint | 2.5 - Formwork
35e08d06-0e32-5005-ac47-eff70b7aeccb | note | Frequency - Each Lot
d66139e6-4add-50cb-9c8b-64731ec23984 | note | Acceptance Criteria - Formwork shall comply with the requirements of AS 3610
9563f6bc-4139-5242-bd65-dbcc794644cf | note | Reference Documents - 703.12
1a14762d-17ce-5f5a-a3cd-195c7b627b78 | note | AS 3610
43e4f995-7df5-5146-bf42-a8f95da3aeb3 | note | Inspection / Test Method - Verify
f00284f7-9b78-51cd-8a6a-50941d98768b | note | Record of conformity - ITP Signed
20cdbfa2-c283-50a0-8416-ec25f7e6a9e4 | note | IP
d9f35d2b-163c-5cf3-a2fd-ee1e26094a53 | note | Responsibility - Site Engineer
05efc5c4-a957-5031-82f8-f50b72808141 | textbox | Date Completed:
5ceffc02-e3c9-4c6d-aab9-69e4406bc9a1 | checkpoint | 2.6 - Reinforcement
c2c30ba4-3af1-5ff2-826e-887a22b321ad | note | Frequency - Each Lot
ad03f47c-8a43-58bd-92ac-256d3d0f0ff4 | note | Acceptance Criteria - Reinforcement used shall consist of SL82 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
868e3ab9-9a04-521d-9152-b68054fcdf0a | note | Reinforcement must comply with the requirements of AS/NZS 4671.
1cb8f31c-41a7-5256-a524-39147e7568b8 | note | Reference Documents - 703.13
ceb0869e-52c5-5d42-a9f2-b3c296857906 | note | Inspection / Test Method - Verify
e3f23f4c-f7a6-5533-b353-c718fa2b255a | note | Record of conformity - ITP Signed
44638043-ee3c-5a7f-8102-32e79af506af | note | IP
d925ae88-60a8-5ab8-8cfc-4631d3d8866b | note | Responsibility - Site Engineer
18566c58-efb8-5fbf-bb7b-6489ea122edd | textbox | Date Completed:
a2423de1-302d-4040-86a8-2b067673a390 | checkpoint | 2.7 - Concrete Placement
808dc6fb-88de-5e6a-9d01-34b19fa5334a | note | Frequency - Each Lot
2168be1a-af92-56ef-9b30-02b994fa2706 | note | Acceptance Criteria - Concrete shall be thoroughly compaction via continuous tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
7481c8b6-3063-5384-919d-a607f7ca43c2 | note | Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
6b4fbdce-ea4a-5a4d-9fc0-da6208a0ed9b | note | Reference Documents - 703.05(a)
1ae55d7a-a258-5ec6-ab9f-c076785e9834 | note | 703.08
6c35a74b-74b5-56f8-9c9a-f3fdd2f33a21 | note | Inspection / Test Method - Visual Inspection
62e153df-40d4-5556-b86f-9d676c85a3da | note | Record of conformity - ITP Signed
ef5913bc-1096-5a25-9e30-dc080d017e24 | note | IP
f2f04d3d-26cb-51b7-b012-1a70007da304 | note | Responsibility - Site Engineer/ Site Foreman
4ffc7235-575f-5b8d-a2bb-55fe0b421553 | textbox | Date Completed:
999c6309-e726-4bb9-88b3-9e1ffe4dab10 | checkpoint | 2.8 - Surface Finish
68952166-4eb1-53ac-a1e0-f06dccdb4d99 | note | Frequency - Each Lot
f9ec9d6f-813e-51f0-81d3-a38805b32497 | note | Acceptance Criteria - Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
3c65a443-52cd-5c1f-9b44-7ebfde0a12fe | note | Footpaths and other Surfacing shall be completed with a wooden float.
12958f8d-64cf-58e3-91ec-17fc5450ae87 | note | Reference Documents - 703.25
74d714c3-a8ba-5dcf-9508-6ee0fc3e6f1b | note | Inspection / Test Method - Visual Inspection
7ed25855-0d32-5121-9167-b0db38d87ed9 | note | Record of conformity - This ITP Signed
272c7d46-aa6c-5d23-9893-81849b258cbb | note | IP
e02682f7-88f5-53ca-af69-ab1f98906a4b | note | Responsibility - Fulton Hogan Engineer
00b89fe7-b7e8-5939-90f1-09d2bca0895c | textbox | Date Completed:
02042b0a-cde3-4009-8bed-f2b0bcf6a3ac | checkpoint | 2.10 - Joints
a2b1cd79-2280-5981-95ac-ac101049359d | note | Frequency - Each Joint
3cf200f6-a85b-54ff-b897-39c98350ab76 | note | Acceptance Criteria - Expansion joints shall be installed at 10m regular intervals using 15mm wide cork or bituminous integrate particle board.
9fa667e7-e64a-5a85-b761-32c75b6455b7 | note | Control joints at 2.5m regular intervals,
d255666e-1b54-5286-b43e-6a5f8b6c64f0 | note | 25% of pavement depth and 5mm wide
f81367bb-5f20-500c-bb0d-40835313166d | note | Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
00116231-900a-57d0-ba75-5cd0d7848403 | note | Reference Documents - 703.26
91635421-0808-5293-92d2-43b660137d76 | note | Inspection / Test Method - Visual Inspection
7466bc49-e043-5a41-ab89-4dee891e5c5b | note | Record of conformity - This ITP Signed
0a52ba55-f156-5c77-ab3b-56718ce695cd | note | IP
4aeeb5ec-79ed-5bce-8e40-eac4042ca649 | note | Responsibility - Site Engineer/ Site Foreman
2cb17738-243d-56d9-8372-2f63baff8333 | textbox | Date Completed:
1ac21ee3-9782-48df-bc31-7791d9d3d5e4 | checkpoint | 2.11 - Protection of concrete
eaa5d191-1915-5e15-b4ce-199af1895db7 | note | Frequency - Each Lot
5a97c8e4-3b78-5da1-87a4-e71fff3fccd6 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
02357926-47a7-522f-ab83-b601fa95112d | note | Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
cf4f51f9-e0be-5991-ac96-7cab92f4f7a6 | note | Reference Documents - 703.27
4c04f15a-0b31-5444-8a72-20eb52545c8a | note | Inspection / Test Method - Verify
72f1be18-1259-589a-a8ed-69e8dcd438b5 | note | Record of conformity - This ITP Signed
3bf58389-8838-5759-bb86-b53a6af24fd8 | note | IP
058f32cd-4aa7-5727-ae0d-48ae122c4ef3 | note | Responsibility - Site Foreman
75348216-49aa-55ab-adbf-78c4322f4eb4 | textbox | Date Completed:
314b91bd-2d1f-430e-94c7-19bc8fbc29c6 | checkpoint | 2.12 - Curing
b495b996-7278-53cd-9c80-fbf482fafb0b | note | Frequency - Each Lot
ff20bbf5-43b8-59b9-bcb0-8870918ef073 | note | Acceptance Criteria - Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
35ce04cf-fb96-5aa5-9355-8341c322ab90 | note | Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
248ec1df-8247-5ea5-a594-0a4174c957c2 | note | Reference Documents - 703.1
8f24ebda-4ace-50eb-aa14-b914b93c9e69 | note | Inspection / Test Method - Verify
8af232db-c6e6-5e11-b488-28996f5247d6 | note | Record of conformity - This ITP Signed
5c55cc5a-f449-598a-a4f5-4d53c22c3343 | note | IP
f9bde652-5718-5538-86d5-5bb7f0ed8ed4 | note | Responsibility - Site Engineer/ Site Foreman
543ed2aa-c8c4-5519-9eeb-d037becdd189 | textbox | Date Completed:
6f6bef8a-24dc-4e49-b4cf-0997450651cd | checkpoint | 2.13 - Ambient Weather
3f4ac8cf-754e-5937-81cd-8461f90b21d6 | note | Frequency - Prior to commencing any activity
c70cc1a7-b30d-5a94-8440-370007f312e0 | note | Acceptance Criteria - Concreting operations shall comply with the requirements of clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for limits, restrictions and treatments to be applied for concreting in hot, cold and wet weather, except that curing shall be in accordance with clause 703.10.
5510f0c4-7e7b-57bd-9e50-40ab9719e2c6 | note | Reference Documents - 610.17(a), 610.17(b), 610.17(c), 610.17(d)
91f223e1-20d1-5671-8b1a-c9c3183a10dd | note | 703.09
6f8aa68d-9ac0-5ede-8ada-75c8c2a64133 | note | Inspection / Test Method - Verify
319faaf9-ff7c-5f34-ae2b-36e6460ac896 | note | Record of conformity - This ITP Signed
4a9ff9f7-0241-51f6-854c-c8fd52feaa07 | note | HP*
ce5e86ba-4161-52f0-8a42-9d20302b8ad6 | note | Responsibility - Site Engineer/ Site Foreman
d43e6560-5b39-5bed-9a54-7a75a0f8960f | textbox | Date Completed:
109b453e-85ba-4326-a365-45af2363f400 | section | 3 - Completion
a8d41f70-6bac-4529-9860-30287e8af3dc | checkpoint | 3.1 - Carry out sampling of concrete - strength and consistency
0b026d6b-4fc6-5b4f-8821-ecbcdc0a5a9b | note | Frequency - Each 50m3
1ad96f5b-f121-56db-ae42-0a45f2035d4e | note | Acceptance Criteria - Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
6421c46b-adfb-5359-a069-3d11d2d55c7e | note | The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
c1ac7ed9-46a1-520f-82aa-5d4bfc651066 | note | Reference Documents - 703.11
ddbc6032-31de-5b91-9805-0cc84edfb3bd | note | Inspection / Test Method - Checklist
5450df2b-585b-5432-93f7-dad4ff06edf6 | note | Record of conformity - ITP Signed/Test Records
985ba4df-bdc1-5675-bac1-1de6087f1d83 | note | TP
a39e6d4a-f159-5ca1-bfdf-d5300868b823 | note | Responsibility - Site Engineer
e3de50d5-53bb-5c4b-8c5c-e5584fa05fd1 | textbox | Date Completed:
b0b55d01-35db-429f-b6de-e03071d0ae98 | checkpoint | 3.2 - Tolerances
ea93184c-466b-586b-acd5-a125f60fe46e | note | Frequency - Each Lot
dac09101-11bc-5f75-83d3-b6f6f44bdb18 | note | Acceptance Criteria - Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
6462959f-8cb7-5551-85ce-707e3e663fe1 | note | Section dimensions shall be constructed within the following tolerances:
67d217a1-419b-56a4-bb63-886cc51cf089 | note | - 5mm and 15mm for width; or
74678dda-c9cf-56ff-88db-ea70a544cfcf | note | - ±3mm for dimensions less than 25mm.
47857e30-5974-5a75-8305-19826d40ffba | note | Reference Documents - 703.15
3e633587-35ab-5e08-9f9a-1332dee0917c | note | Drawings
3ab9afb0-0d79-5fef-b1c6-38cc802fcafc | note | Inspection / Test Method - Visual Inspection
eabc7853-6357-56fb-ac6a-8d1a21f7be98 | note | Record of conformity - This ITP Signed
22f9245f-9b58-506c-89ab-ac027e2d1be8 | note | IP
ba5cc95d-ba5b-5a36-a307-17617c7663c2 | note | Responsibility - Site Engineer/ Site Foreman
f3cdc96f-f047-5ceb-9488-0714c89bbbc1 | textbox | Date Completed:
1ec6d787-16c6-4845-a878-bae7c66bb0ef | checkpoint | 3.3 - Backfilling
a1cdfda4-faff-566f-8690-72c6ab690ca6 | note | Frequency - Each Lot
a3ed8a64-23a6-56bb-960d-2daf73f33d60 | note | Acceptance Criteria - After curing, no earlier than 3 days, backfilling shall be completed as per the below:
d614c5c6-62cd-5b5b-ad4c-823d2758bce7 | note | - Topsoil compacted in layers < 150mm
8ec8030d-5610-5220-bbb7-8c6ecb49e690 | note | - Width ≥ 300mm behind edging to top of edging
94b61f6b-2c86-59ed-9eb8-4f8435da13cd | note | Reference Documents - 703.29
c5512c21-9d41-5f87-a971-b0db2876f6d0 | note | Inspection / Test Method - Verify
207df659-97f3-5d2e-9b12-1c9cf11d2018 | note | Record of conformity - This ITP Signed
17874f67-7544-5bfb-84de-1a36a482941a | note | IP
551ec7c9-c699-5306-a774-d56a4342b2fe | note | Responsibility - Site Foreman
3b31dbcf-dc43-53d4-8c16-7571c65e7870 | textbox | Date Completed:
c6307f03-28dd-4945-be81-2219bd4a7745 | checkpoint | Final Inspection
afea1627-492c-5b0e-b6d9-338e4d41dfb7 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
33608836-acbb-549d-ac9b-59d38ee086ff | textbox | Print Name:
429ad647-4b7b-57d8-b130-7d1701cf6171 | textbox | Position:
9ea52dbe-53ee-5f0b-8071-3938b97b49df | textbox | Date:
0d3c9b69-afb5-4b6e-9154-84c2e58292ed | checklist | FHC-ITP-036 - Furniture & Bollard Installation Rev1 | itp | FHC-ITP-036 - Furniture & Bollard Installation Rev1
1afa65f4-bbce-4222-b449-da1956702dd4 | section | 1 - Preliminary Works
fee84392-bbbb-4d05-be76-5a1d725384c1 | checkpoint | 1.1 Check for correct documentation
4c04fef2-fc30-571b-b3dc-9ec5bb29ed8a | note | REFERENCE DOCUMENTS: IFC Drawings
965865ac-cc1f-50d5-ab00-39f90fe60191 | note | – – – – – – – – –
37ac4d2a-1628-573c-8821-e2060bfcb6ba | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
e441eba6-ee01-5602-92df-8407922b2405 | note | – using the correct and complete set of drawings
c735cb7b-298e-55e0-a843-5fb48ba54a21 | note | – all drawings are the latest revision
c68c5b2a-88f6-543e-a574-7b95ec3cfd86 | note | – – – – – – – – –
cc0091ae-2555-5ce9-b08b-153e70782cf3 | note | INSPECTION/TEST METHOD: Visual inspection
d2cfb83d-2e26-53fd-ac5c-822b97f2785a | note | – – – – – – – – –
72585e10-4185-50ca-80b3-2a6a2ac58d1a | note | RECORD OF CONFORMITY: This ITP signed off
5afc3aa9-80c5-5421-9182-3fd155c0fdc9 | note | – – – – – – – – –
6c8c94d7-26a8-5080-8076-d799dd5384fe | note | WP
6f49a9fd-d5bb-5d20-b649-da41d3560166 | note | – – – – – – – – –
ec0e9556-5d20-5a7d-9b6b-534609b19b04 | note | RESPONSIBILITY: Fulton Hogan Engineer
165245c6-09c6-548c-aac8-fbcdd89861de | note | – – – – – – – – –
55178ed1-c3a5-5081-a81c-2648cd6a7daa | textbox | DATE:
1c363efc-6c6b-414e-a684-277296f7caed | checkpoint | 1.2 Furniture Type
ae9ff58a-ce8b-5cf7-9526-7341c1752c42 | note | REFERENCE DOCUMENTS: IFC Drawings
4227d5c8-b703-5ef2-b457-29c401ca4f74 | note | – – – – – – – – –
292ec603-d732-53cc-a50e-4349797a2b88 | note | ACCEPTANCE CRITERIA: Furniture to be installed:
ae35e1ba-ccdf-5184-9fcb-c6bde9bfcf42 | note | ☒ Wheel Stop
7ace1402-c7a8-542f-8fc2-494eef0c6ef8 | note | ☒ Bike Hoops
06dfdf9c-3678-57ff-a0ce-a2389ede3b3e | note | ☒ Bollards
21a92313-14a5-5a35-bfd6-a9ae1770ab84 | note | ☒ Tactiles
25901e62-7698-50e7-9c0c-eb6f94d2b9b5 | note | – – – – – – – – –
622d2460-394e-55da-becb-b31de2b2686e | note | INSPECTION/TEST METHOD: Visual Inspection
90dd5086-9581-598c-806e-10f1dd84a1bf | note | – – – – – – – – –
cf871127-7e46-58d8-b939-58c31ef412e3 | note | RECORD OF CONFORMITY: This ITP signed off
cd50caa8-1c31-5a8b-af2d-d171ab7e81d6 | note | – – – – – – – – –
6f26b220-330d-5359-aa6a-8936d3e87f98 | note | WP
0159edf9-f6ad-5147-8fa6-65f8bf74f57e | note | – – – – – – – – –
68c10046-a6c1-595d-a048-df365c70f1c0 | note | RESPONSIBILITY: Fulton Hogan Engineer
ac4eeeca-655f-51f9-883b-2267726fca30 | note | – – – – – – – – –
b5784d1c-68af-5b60-8b94-a1832cf97a74 | textbox | DATE:
721ec144-6b9f-490a-9b45-b134934467de | checkpoint | 1.3 Service Identification
d4e3846a-f0d4-53fc-910f-7f7e2d660047 | note | REFERENCE DOCUMENTS: IFC Drawings
e7aca13e-58d4-5c5d-a571-05b26120d5d0 | note | – – – – – – – – –
08e584e5-05e3-500f-9529-768eb03f7d80 | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
1e973264-d945-5808-89c6-6cbfda5d2835 | note | – – – – – – – – –
94fbfea4-2602-5aa4-b726-264cf4bc50a9 | note | INSPECTION/TEST METHOD: Verify
f4a0ba05-f869-5034-9b94-df6fe63e639f | note | – – – – – – – – –
10a6056d-af73-51ce-8440-051d791336f5 | note | RECORD OF CONFORMITY: This ITP signed off
b6638b93-d209-5080-a5f6-caface113e3b | note | – – – – – – – – –
d077cfee-52f7-5b89-8948-226339d336f4 | note | WP
cade1adc-8a14-5d19-9915-77bbb6ccc72d | note | – – – – – – – – –
69fcfb52-b887-5a58-b501-3527811335a0 | note | RESPONSIBILITY: Fulton Hogan Engineer
01d34c0d-3ad0-5bc7-a12e-a8f9209746ed | note | – – – – – – – – –
a317cadc-ce4d-50bd-9c5f-5213688bbea7 | textbox | DATE:
43a6688d-1c52-4329-826a-e98edd523094 | checkpoint | 1.4 Material Conformance
8c6dc1d8-9e41-533a-837c-77c593e84445 | note | REFERENCE DOCUMENTS: IFC Drawings
f00c8cda-5a3b-521a-8325-2210a77e73a7 | note | – – – – – – – – –
f935c928-a9bc-5fb5-902c-bbde5f001865 | note | ACCEPTANCE CRITERIA: Concrete mix design to be approved in teambinder prior to pour.
9f5d322c-39c2-53f3-88db-dbdc986ce4a6 | note | – – – – – – – – –
7324f5aa-3423-5432-b123-1f4f01897bfd | note | INSPECTION/TEST METHOD: Verify
61a93608-b4c6-522d-b55a-2e42356bce03 | note | – – – – – – – – –
ca09301c-fae9-526d-9174-7d6bedb32d8c | note | RECORD OF CONFORMITY: This ITP signed off
ec8eb787-559c-594d-906c-2a686ba5986d | note | – – – – – – – – –
ad996cec-49d2-5b6a-9d5a-6c251d12e560 | note | WP
89919119-eeb5-583b-a87d-2275d161e5f3 | note | – – – – – – – – –
b402e530-8a6b-5565-9c6c-f7fe3835e47f | note | RESPONSIBILITY: Fulton Hogan Engineer
bff584be-3e42-5e91-839e-300857cd3308 | note | – – – – – – – – –
4ed88438-1890-5808-a2fb-4daaada5bff4 | textbox | DATE:
0efbe9a4-2cbb-46f2-aa5b-b62aeab99225 | section | 2 - Construction Works
3751a81f-9f38-4b4f-b61b-808010932229 | checkpoint | 2.1 Setting Out
3363d4a8-fe4e-5271-b11d-64219c5c5e03 | note | REFERENCE DOCUMENTS: IFC Drawings
e0a536bb-f2e1-5210-b22a-287808281f8f | note | – – – – – – – – –
6269c719-0b15-56a8-a891-aea22b4092ff | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
a6eb4348-bfd8-53eb-83c7-8ed59fe04e5f | note | – – – – – – – – –
6076632d-fdc9-58fa-b80a-7a6e48ba13d4 | note | INSPECTION/TEST METHOD: Visual Inspection
4afcd6ab-f4a4-5f84-87cb-5214b4af3f1a | note | – – – – – – – – –
b336b03b-ac79-5cd5-9b53-754b407b1c67 | note | RECORD OF CONFORMITY: This ITP signed off
25ce4299-2c8b-54f1-9857-d1c668c89806 | note | – – – – – – – – –
4209408e-10eb-5f72-bf72-c34394fad548 | note | WP
f576c8c7-1c8f-5eb7-b222-f8f765f64dfd | note | – – – – – – – – –
b4705b43-57e7-5782-883a-168b9b708f61 | note | RESPONSIBILITY: Fulton Hogan Engineer
3c96f9fa-609f-5c22-a913-5812e40adf8a | note | – – – – – – – – –
bd93b7c4-0022-500a-b55f-32d89c4a7045 | textbox | DATE:
2c6e1d78-f796-433d-b9b5-660d4cb902b9 | checkpoint | 2.2 Post & Foundations
0860a81a-e731-5758-abdd-f0e5ae940dd8 | note | REFERENCE DOCUMENTS: Manufacturer Specification
b31c1e98-e7a9-5467-bdf3-6d940ea7eaa0 | note | – – – – – – – – –
b98f4f6d-0614-5cf1-926f-3435770734fe | note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
e555bdb7-d873-5db4-8b00-745a8b64fdb0 | note | – – – – – – – – –
fec03e70-3a5a-52d4-b8cb-0409dc3ad440 | note | INSPECTION/TEST METHOD: Visual inspection
766a34ad-4480-5764-9038-82a83655cb18 | note | – – – – – – – – –
91422a5f-e668-59d2-b5ad-d566809dbc70 | note | RECORD OF CONFORMITY: This ITP signed off
928c8d63-fbce-53b2-bb8c-90f495029bfa | note | – – – – – – – – –
a3164259-dcf6-53cb-bfab-8464854b514b | note | WP
777b0a74-8357-5907-9100-ff681a8935d0 | note | – – – – – – – – –
3542ab53-9c3d-5c97-a829-e28df06a58ba | note | RESPONSIBILITY: Fulton Hogan Engineer
fa3295c7-42cd-56ca-9313-69a48d59323a | note | – – – – – – – – –
3bc700a9-7fd6-5fa3-8e65-bd6053885540 | textbox | DATE:
2a766615-e63f-498b-86eb-d625c49118a1 | checkpoint | 2.3 Positioning
ff99c35b-5f52-5405-8bc2-0a05b8ccf66e | note | REFERENCE DOCUMENTS: IFC Drawings
318a521a-9053-5b14-85fc-e73e6717e626 | note | – – – – – – – – –
37d20efb-4acd-5b3c-992a-db59177627d0 | note | ACCEPTANCE CRITERIA: All furniture to be positioned and installed as per IFC Drawings
8a5429e8-4aee-56f3-9043-4800ae0b5ae4 | note | – – – – – – – – –
64f27995-31ac-5356-a336-d7587efec20b | note | INSPECTION/TEST METHOD: Verify
a9ef2efb-aa66-58a8-a43e-e183750d5ddf | note | – – – – – – – – –
f5155724-715a-5d22-892f-07ddb2cd3b01 | note | RECORD OF CONFORMITY: This ITP signed off
3556ebd4-7f2d-57ea-bb3f-85e6d975d4fa | note | – – – – – – – – –
daa5f6ab-1ede-5c03-a3e6-3184743de9f0 | note | WP
d073098e-6b96-5288-a8fe-b19632017897 | note | – – – – – – – – –
956ba0ae-abae-556e-b983-2cb4d750c42f | note | RESPONSIBILITY: Fulton Hogan Engineer
8cc47c47-c8a0-5614-973e-606111647976 | note | – – – – – – – – –
2c026238-13f4-53d2-9bf4-fd6715292715 | textbox | DATE:
1198e98f-228f-4295-a0ec-bd609b78cc1a | section | 3 - Finishing
db7ac457-1e3c-40e0-b443-5c2d641b6b32 | checkpoint | 3.1 As-Built Survey
a63d5a23-e5aa-5baf-b89e-ab34e9f6fe7a | note | REFERENCE DOCUMENTS: IFC Drawings
0c59b9fd-8153-51a5-acbe-194026055252 | note | – – – – – – – – –
a0b97f0c-4274-59b2-8c49-a40d57c259c1 | note | ACCEPTANCE CRITERIA: Has the furniture been installed as per the IFC drawings?
fdf71e34-7da2-5a15-9073-cc931b2e8334 | note | • Is the location of the furniture required to be included in the as-built survery
a8a20f1e-7f2b-51c9-8475-9738aadd8e8c | note | – – – – – – – – –
81533d78-f7fb-5ffd-826a-f9b31c44f257 | note | INSPECTION/TEST METHOD: Verify
263e1a60-9dac-5d43-8a9d-3915ba0eceb5 | note | – – – – – – – – –
96081f0d-9e9f-5a4d-bea6-c5461ffcd957 | note | RECORD OF CONFORMITY: This ITP signed off
4aed4c08-8314-5f1d-8ce8-99b398ba50b8 | note | – – – – – – – – –
c7a81b31-f1b9-5dd4-9a31-f4932de1b926 | note | WP
a853cae0-d059-5f8d-80c2-ee6360511d40 | note | – – – – – – – – –
19117ec5-7b67-5c30-8959-25ea71c71650 | note | RESPONSIBILITY: Fulton Hogan Engineer
ee6a6394-ccdb-5733-b294-5722a425e100 | note | – – – – – – – – –
248df121-aad6-5f76-abb4-911059e205a9 | textbox | DATE:
44871788-c6e2-4788-9520-3bd93f3c2de3 | checkpoint | Final Inspection
2d3f8a31-5e14-5a7f-8588-1f30436f729f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
83ddc0e7-9e86-57eb-bc9a-f17087d7c35c | textbox | Print Name:
6262baf1-0392-5c21-b3b2-962c8301dc2b | textbox | Position:
e996cb8a-facf-52fc-a1c1-dfc517daeffa | textbox | Date:
082dc25f-55be-4c15-b077-2087e52c5e86 | checklist | ITP - 019 Line / Road Marking |  | ITP - 019 Line / Road Marking
ee8d605c-62bb-4383-9cd3-e566d6ecc993 | section | 1. Preliminary Works
6fdd38ee-ab66-43d1-8e7f-6140d11cf71b | checkpoint | 1.1 - Check for correct documentation
de5d93ff-1dde-50fa-9de3-5ec4e6d438aa | note | Frequency - Prior to commencing any activity
e59e3ca0-bf17-50c1-aef5-22e705a454bb | note | Acceptance Criteria - Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
d9cfea5c-6596-5cd4-bbe3-572abba88d6e | note | Reference Documents - Drawings and drawing registers
5b024ab5-0576-5f08-b5f1-705d0a8b1632 | note | Inspection / Test Method - Visual inspection
d7ab2f37-3f93-5a5e-8086-e5c0c101900b | note | Record of conformity - This ITP signed off
fe6ab210-3e1e-5930-9986-03cb0aecb13c | note | WP
16e67647-0492-57e8-8ac5-6add6bd09a3d | note | Responsibility - Fulton Hogan Engineer
83f5ed66-5728-499a-85db-dcdfa80446f0 | checkpoint | 1.2 - Implementation of all measures and controls
b82f08ae-c77e-5928-aceb-5f670e57b5cf | note | Frequency - Prior to commencing any activity
35cb71ef-58ef-597c-a952-7f1153793b41 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
d49a0dc5-7877-502d-bbe4-f478b2d5e90b | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
1fb2d0bd-2ae9-5df5-97ec-58f39675b1ad | note | Inspection / Test Method - Visual Inspection
fd701eed-bcf5-52a4-bda4-0e01a6a76c7a | note | Record of conformity - This ITP signed off
050cde0c-0d78-56f5-984f-80e7f834b363 | note | WP
d437b4a2-77c1-540c-923a-5f8e7f843023 | note | Responsibility - Fulton Hogan Engineer
3e2c64cc-7f85-4cf2-868b-f7fd1570a8c7 | section | 2. Construction Works
6b17d570-705a-4a3f-9093-ea3f7a3d8c9f | checkpoint | 2.1 - Setting Out
d98dbeda-862e-52a8-8eba-7204a0b15e5f | note | Frequency - Prior to start
3e80185b-c3fa-5a48-ba25-1fe73a430a6f | note | Acceptance Criteria - Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
73ab3f9a-636a-50c8-a6bd-4bdbfd34ac2f | note | Reference Documents - Drawings
d2e7e8f8-7093-50b7-bcf2-ff33438ccec9 | note | Inspection / Test Method - Visual Inspection
6f54f0e1-321c-545d-934a-dabe45017bd0 | note | Record of conformity - This ITP signed off
01f93dc5-e836-5995-9909-b088156055ce | note | IP
d013e1fe-8e40-591e-892d-34b919a083a6 | note | Responsibility - Fulton Hogan Engineer
f978a66f-314d-48d7-842e-d25ada45b418 | checkpoint | 2.2 - Position of Markings
fe172c8f-8c60-5a5c-8982-aebfc64054aa | note | Frequency - Prior to application
86aa784b-75f5-50c8-8044-5f080e00f3b1 | note | Acceptance Criteria - Painting/ application of material shall not commence until the Superintendent has inspected the setout and given approval to proceed, unless an exemption is granted. Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2
97a51786-9388-58ae-8e2e-44f2c1fa73f9 | note | Reference Documents - VicRoads Traffic Engineering Manual Volume 2 Drawings
04e94c0c-488d-5ebe-8d7e-b944786c1004 | note | Inspection / Test Method - Visual inspection
5b9e4081-ec3c-55a4-83c8-8a2f6c519707 | note | Record of conformity - This ITP signed off
773b9bf5-f404-5fe2-8e17-d9b0cb6c989b | note | HP
6cebe441-b6b1-53c9-bef3-8da006827fa0 | note | Responsibility - Fulton Hogan Engineer & Superintendent
4f4542d2-fb49-4ecf-a4d7-0706ec0eb907 | signoff | AUTHORITY HOLDPOINT
6e7ff942-b445-4b57-a7dd-0cd43f9a669f | checkpoint | 2.3 - Materials
02bfb42b-3a1d-5cf8-a5af-c7a6cb9e4936 | note | Frequency - Prior to commencement
c53ef3d8-e9cb-582f-bafc-0187fbfe4bb4 | note | Acceptance Criteria - All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent‑borne paint or AS/NZS 4049.3 for water‑borne paint as listed in Section 175.
28333bdd-0750-5343-98e7-21c0869d368f | note | Reference Documents - 712.A04(c)
356750fb-45ca-58d0-bae1-b0a243870a53 | note | Inspection / Test Method - Visual inspection
14243f4d-b260-5519-8976-39b79884a32a | note | Record of conformity - This ITP signed off
229fb86c-f738-584c-91b4-bf6c23a5f15c | note | HP*
8e21e3c3-290f-5918-b94c-6f41a92b8a12 | note | Responsibility - Fulton Hogan Engineer
86bccac9-955e-46ce-9d0f-f3a358c462d2 | checkpoint | 2.4 - General Markings
4df3ef46-877a-51fd-a156-5eeadfd84a68 | note | Frequency - Prior to commencement
2145af3a-113c-58d9-ac33-e90e18e5aade | note | Acceptance Criteria - Linemarking shall be applied by a self propelled machine, and stencils shall be used with all roadmarking. All work must be undertaken by a contractor eligible for accreditation under the Painting Contractors Certification Programme (PCCP). This programme is administered by the CSIRO.
61952728-6d0d-5c73-9025-23b06a6c89b8 | note | Reference Documents - 712.D01(c)
fcb8ad2c-4395-5dec-9740-332fb39d2ea6 | note | Inspection / Test Method - Visual inspection
267f1f32-d331-5587-a6ea-d1e13beb3634 | note | Record of conformity - This ITP signed off
7bbe2181-a8fd-5dc8-8d5f-0a0c1e5d57d0 | note | HP*
1f9f0b92-6c1a-53c9-8f6e-dbb0d3fdccba | note | Responsibility - Fulton Hogan Engineer
1921fe91-4c73-487c-b766-30fbadb0b277 | section | 3. Completion
c1e652eb-8bdb-4d04-adaa-bc7fec9701a0 | checkpoint | 3.1 - Tolerances
a07df667-2811-55ce-a871-b2a0b800c4c3 | note | Frequency - Each marking
e8c68821-e739-5e07-a72d-7e929e3ea7f0 | note | Acceptance Criteria - The Contractor shall comply with the tolerances as shown in Table 721.A101 when installing pavement markings. (i) Distance between centreline of marking and set out marks <30mm (ii) Width of completed paint markings <15mm (iii) Length of completed stripes and blocks 0 to +10% of specified length
cd7a78fc-a1d4-53ce-9fbb-395f58b6e0c0 | note | Reference Documents - Table 712.A101
0a687b33-3cf0-5b3c-9d30-a8e8e4db5fe5 | note | Inspection / Test Method - Verify
26fdd9f5-bf24-5333-bd59-460780072550 | note | Record of conformity - This ITP signed off
ec2dd2b7-f88f-55e1-90c3-7e59c6018d70 | note | HP*
61931cc1-477e-5fdc-869b-72344b4448bd | note | Responsibility - Fulton Hogan Engineer
42b65f75-11cd-4cbe-acae-29780c89c242 | checkpoint | 3.2 - As-Built
c35090b9-4da7-5249-93fb-08ddcce4e22e | note | Frequency - Post Completion
3401ce10-ad0a-5862-b75a-bc1b6d3db12e | note | Acceptance Criteria - As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
d8d65f10-7b1d-5ce8-a750-b74c35ab7ded | note | Reference Documents - IFC Drawings Survey Records
ee4b863b-16e2-5dbe-9ada-8aaee338a41a | note | Inspection / Test Method - Document Review
3814542d-443e-5225-b1da-7274c6846264 | note | Record of conformity - This ITP signed off
e5ca86b2-9047-53a4-9198-956190fc5570 | note | SCP
a844a5a3-5976-5da3-92c3-0fde269bd6b7 | note | Responsibility - Project Engineer /Surveyor
2dc4dfe2-c700-47c8-a368-042c36ddd60c | checkpoint | Final Inspection
6c6d4634-f4a5-543a-802a-93baaf62d61e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
33657742-3211-53dc-aa81-472528814e29 | textbox | Name
d5c25123-6a18-5ff1-8a4d-faa660cbfb20 | textbox | Position
9580bbe3-7314-5fec-aa7d-4b65ff77f483 | textbox | Date Completed
3dca99db-2f5d-46b7-b1ec-37581e6a265d | signoff | Signature
a457623e-20f0-4b8b-8fd2-f46e15461d0d | checklist | ITP-037 - Structural Concrete Construction |  | ITP-037 - Structural Concrete Construction
ecda2940-3ebe-4436-bee2-a4d24c76ff36 | section | Preliminary Works
29f7a61a-c1b6-4c11-9c6d-f6785eec1b56 | checkpoint | 1.1 - Check for correct documentation
5521bd36-754f-5dea-834b-f3ef6b0155a8 | note | FREQUENCY: Prior to commencing any activity
e3668f9c-2410-5353-b0e4-3458471d65c1 | note | ACCEPTANCE CRITERIA: Employees and subcontractors shall be issued with the most current and complete construction drawings
cfe69189-f11d-5228-b45b-4b6b434925ac | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6763970c-f515-5a47-b7f7-3cdd128519cd | note | INSPECTION/TEST METHOD: Visual inspection
431132e3-9241-5def-9763-9705ed5030e9 | note | RECORD OF CONFORMITY: This ITP signed off
5522dea6-3fbf-5097-8b6f-07e56e4ec1db | note | HP*
426a7cf0-b0fd-5cb4-afe2-22b967cc2dad | note | RESPONSIBILITY: Fulton Hogan Engineer
2ddfa45b-2f2c-5c3e-9d36-58499b7500f6 | textbox | Date Completed:
1f9e9583-5b02-4e4f-8b38-3042cd76be24 | checkpoint | 1.2 - Implementation of all measures and controls
eafc2302-c0b3-5c17-bf82-f81106e49f82 | note | FREQUENCY: Prior to commencing any activity
33709b35-ca8c-50ae-95a4-13087d31e1be | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
7db5f4b4-84ce-56e4-a058-001c3bda60cd | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
53dac207-243e-5a80-acd7-6924403e2d02 | note | INSPECTION/TEST METHOD: Visual Inspection
9a72913d-dadd-573a-b744-d907e5bb0141 | note | RECORD OF CONFORMITY: This ITP signed off
4dd666b7-b9fc-5c40-bf43-c64cd257f131 | note | HP*
c635a36c-e59b-5d26-8249-c4928e731c3c | note | RESPONSIBILITY: Fulton Hogan Engineer
4b960711-f4db-50f1-8198-ae5c0bdf2334 | textbox | Date Completed:
002dd0d3-f5fc-4a4e-99e6-a733232f477b | checkpoint | 1.3 - Materials
527f6c55-1fe8-53df-b5c6-af265c78649f | note | FREQUENCY: Per Batch
94455991-4fea-5b0a-ac34-8b6b21e81f76 | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be Orange and rigid HD UPVC of sizes as required. • Communications conduit to be White and rigid UPVC of either 32 or 50mm size or larger as required.
53ea2719-931d-5a9e-b53d-951dc94ea004 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.1 AS 2053
0c981afc-8410-5095-81a4-8701554b80b6 | note | INSPECTION/TEST METHOD: Verify
d0c4fca2-021c-5ae1-ae48-73b517e5ecf4 | note | RECORD OF CONFORMITY: This ITP signed
701d08b9-0c1c-5cd8-9c89-086280020a51 | note | HP*
a72cc69c-2e3a-59a1-9298-4297fa0261df | note | RESPONSIBILITY: Fulton Hogan Engineer
61cef4b6-3b4a-5ed5-93b2-337d97cddf8a | textbox | Date Completed:
aa69c2a7-ffd5-4d17-a671-b358cb6b7961 | section | Construction Works
46ea653d-12e3-4a7c-a13e-a4ecc320eabb | checkpoint | 2.1 - Survey set-out
8bc90a47-39bf-5f66-b91c-38ec9d75df34 | note | FREQUENCY: As required
7990311e-8a14-5a16-b3b3-32783b836213 | note | ACCEPTANCE CRITERIA: • Work is set out in accordance with drawings.
467f89bf-9c5f-5a10-af04-1445d45eeb31 | note | REFERENCE DOCUMENTS: Work procedure
3ca7276e-3b0b-5a2d-a8e1-51ebcdae6fec | note | INSPECTION/TEST METHOD: Verify
73643bc7-872e-52c9-a7b7-c225c1d84ed3 | note | RECORD OF CONFORMITY: This ITP signed
55694ef1-276d-5111-ba3c-8b8bd7f9edcc | note | HP*
9137a75f-c2e3-5a98-910c-1b1a100571f3 | note | RESPONSIBILITY: Fulton Hogan Engineer
6b72fa62-d834-58f4-b8db-bfd29e6f66c7 | textbox | Date Completed:
7e4d2e3a-d13d-4f68-848a-3a0cde34f1d4 | checkpoint | 2.2 - Excavation and Trenching
f9b11a9b-55f2-582e-a63c-a2ca8efacb8d | note | FREQUENCY: Prior to Installation
7c8f32c7-3954-5071-9ec0-91737dfc8534 | note | ACCEPTANCE CRITERIA: • Minimum cover for underground conduits shall be 600mm • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
ce6c9cf4-5f06-5c69-8085-5a6dc0c4d09f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
956dfa99-e7c2-5867-9af6-e3ddb8908f15 | note | INSPECTION/TEST METHOD: Verify
ec88b3a9-e7d6-5d89-ac1b-108b4cb227c7 | note | RECORD OF CONFORMITY: This ITP signed
9e2cb7fa-9acc-558c-8022-1396493db7ac | note | WP
9d6faafa-2d5c-5d48-9704-b243fd78400b | note | RESPONSIBILITY: Fulton Hogan Engineer
02e598cc-8cdf-5937-ba4f-59fa549c8c42 | textbox | Date Completed:
c7a0507f-0bfc-4989-b3ae-35a9339f2f91 | checkpoint | 2.3 - Installation of Conduits and pits
edc1d6f8-64fa-5319-a880-ca2e44c58514 | note | FREQUENCY: Each Lot
69fb2c02-0c34-50a1-ac0d-9f383972fe78 | note | ACCEPTANCE CRITERIA: • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
29c24c14-fa39-52e2-be0a-f5be68320002 | note | Conduit shall be embedded in not less than 50mm sand and covered by
d94ec453-d159-539a-803d-c88f269f7399 | note | >50mm - 75mm< sand
c8b522eb-d1f9-5670-b97d-cba9d4adb072 | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
982edfaa-66aa-5767-9252-ae975765603c | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
bc5ebfa1-a452-52e5-b0b8-e5efd70e706a | note | • Conduits shall not be subject to construction loadings
733c9704-9021-5fe1-9932-b0185fba6148 | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor
47a6544c-cfc3-5ce6-8795-79fd6a506183 | note | • Conduits shall be capped with UPVC electrical caps
ae411233-2f61-5346-bd97-f6e8d452f64d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
60edd2d9-651f-52b2-a584-38208081a0b7 | note | INSPECTION/TEST METHOD: Visual inspection
cec1afa1-9c99-5c03-a2cd-1157f5541e4e | note | RECORD OF CONFORMITY: This ITP signed
c1aa11ed-46c6-5c23-a66f-a8855db72c7f | note | WP
965047ea-f94e-5e23-af54-47db9f1f31ed | note | RESPONSIBILITY: Fulton Hogan Engineer/ YT
53c1b52b-045f-5022-9549-b6d993594165 | textbox | Date Completed:
57266568-5bfb-4c41-a774-e2357c243ca2 | checkpoint | 2.4 - Inspection of conduit installation
03086017-b6ad-5445-8597-fe1bb1bc6213 | note | FREQUENCY: Each Lot
eda577de-2cc1-555c-974c-cfa7f8ec6a88 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
f6ccb4a0-4b76-5b37-ac1e-edfb6433b879 | note | REFERENCE DOCUMENTS: Work procedure
a7696d8b-2865-5195-b73b-72e32806953e | note | INSPECTION/TEST METHOD: Visual Inspection
febe31cf-f60b-5e76-acb1-d53ffcd8fca4 | note | RECORD OF CONFORMITY: This ITP Signed
55b3dd12-499d-58ca-94ab-9fa2d8b58ba3 | note | *HP
80d4780f-0b81-5e97-9e40-6a4858259593 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
6d75b3dd-b5ec-5350-9bdf-094ad243ee52 | textbox | Date Completed:
aae537a2-fad5-4cc3-933f-894b9d20833e | checkpoint | 2.5 - Backfill of Trenches
57d27a08-c284-55c3-8c07-1c4eb7b6f23f | note | FREQUENCY: Each Lot
2556764d-a662-5dc8-85a9-70ae4e7d517d | note | ACCEPTANCE CRITERIA: • Backfilling (for trenching or road crossings) - conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction using handheld mechanical plant
86550297-b4eb-59ca-9e47-a92767e58987 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
c890da27-44ce-51a6-b09f-1ef70009a707 | note | INSPECTION/TEST METHOD: Verify
dbfd10c2-3971-542c-9850-e5c595eeea38 | note | RECORD OF CONFORMITY: This ITP signed
284cd29e-c8a3-5d40-8db3-b83c93627592 | note | IP
d3d9f6dd-d07d-5445-aece-feb5d99d1928 | note | RESPONSIBILITY: Fulton Hogan Engineer
0f8dc54d-62af-540c-934d-7a86fdbc06de | textbox | Date Completed:
ddbe5089-6eb8-498c-90cd-4edbbf6caccc | checkpoint | 2.6 - Installation of Draw Cords
0c3ee2f1-266d-5c22-9cea-b16d7aa37714 | note | FREQUENCY: Each Lot
391f9df3-f53c-559d-9d66-f2379f164209 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit, material to be used shall be 6mm 'telstra rope'
4da26a89-fbaa-59c3-98d6-28ff7110716e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
af5e4795-9056-5989-96e9-44cbed1529e4 | note | INSPECTION/TEST METHOD: Verify
200ab82c-3305-5f11-893a-555411fbeb41 | note | RECORD OF CONFORMITY: This ITP signed
01db276f-d1cb-5155-a08f-65cfa1d10cc6 | note | IP
d7bb95bd-959a-5db9-b17a-72a34038d207 | note | RESPONSIBILITY: Fulton Hogan Engineer
01057c64-464c-5ab4-869b-dba0cfbd5e8b | textbox | Date Completed:
0ccfb48d-fdeb-4348-b73b-b6f82fb1c128 | checkpoint | 2.7 - Compaction
95c819ef-f205-53da-bb57-e579758945be | note | FREQUENCY: Each Lot
ba17678e-3bc0-5a5a-8f8b-b075e8cec4ed | note | ACCEPTANCE CRITERIA: During compaction optimum moisture content of bedding and select fill is within 85% to 115% as provided by suppliers
4446ffe9-b36a-5712-9ffc-5b94b3942f36 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
06c1d433-03e5-5980-a0b4-b1f3da3530bb | note | INSPECTION/TEST METHOD: Verify
d813b5e9-becf-5641-a191-3a455fc9019a | note | RECORD OF CONFORMITY: This ITP signed
f18bd1ed-7202-5010-ba52-05d857f241b4 | note | HP*
c641acc7-c467-5388-b961-ef0b92ab2c19 | note | RESPONSIBILITY: Fulton Hogan Engineer
69bd172e-559b-5307-8a13-19367d4ad789 | textbox | Date Completed:
dbbbee71-c024-40c7-add9-b2130911ce32 | checkpoint | Final Inspection
58e27d9a-35a9-5dac-98e1-56c07c613185 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
540aca48-9261-57c9-86ae-7f607656ac6a | textbox | Print Name:
ba6ce0d0-4982-558d-9a7c-9989c258c9f7 | textbox | Position:
de8bf85b-23eb-5c0b-9acd-4973b9d42288 | textbox | Date Completed:
b2157816-4ec1-4fca-b981-ca7d0fc94c54 | signoff | Add Signature:
786b7461-11e0-4b9e-8441-28d505bfbc10 | checklist | ITP-039 - Hot Mix Asphalt (Bridge Deck) |  | ITP-039 - Hot Mix Asphalt (Bridge Deck)
ef772824-af3c-4c62-bc03-2727030e5d64 | section | Preliminary Works
8e59783b-37f9-4439-8370-691f3aede616 | checkpoint | 1.1 Check for correct documentation
de8e6dc1-a05b-5090-b012-245b8690392b | note | Frequency: Prior to commencing any activity
be4df5e0-8dfd-579f-a51f-29d2491e804f | note | Acceptance Criteria: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
147a1514-c1ca-57d2-9ed9-104c6d7191ca | note | Reference Documents: Drawings and drawing registers
42e53a88-d300-55dc-859d-946a59dc7dca | note | Inspection / Test Method: Visual inspection
7366d5bd-2d46-527f-a167-0f3b9cc706d6 | note | Record of conformity: This ITP signed
f0f61bc5-7f8f-55ea-9d90-8e077d2ef0d8 | note | HP*
be332454-eaff-5426-bdf1-3070244082aa | note | Responsibility: Site Engineer/ Site Foreman
405b5304-afc1-5a1f-9ea3-5bfebe11f6a1 | textbox | Date Completed:
45e0dfa3-3efd-4b28-8b9a-8cd9bc86e9dd | checkpoint | 1.2 Implementation of all measures and controls
63f6b417-0fe2-57ca-9918-5ae81143acbd | note | Frequency: Prior to commencing any activity
b3d10ff5-ec81-541c-afe5-bdc3c2817e9e | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
5b0477e5-0148-5c7e-a3f2-024a553413ca | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
035b8320-32a3-53cc-925b-564494d2d6ba | note | Inspection / Test Method: Visual Inspection
637e877d-d3d3-5f22-8584-0dd3048346c4 | note | Record of conformity: This ITP signed
1a838f2e-ed53-5a5c-95ee-6731c7a6f92f | note | HP*
a7a5b3eb-e598-5f6a-8d52-33ed78aae485 | note | Responsibility: Site Engineer/ Site Foreman
40d153f9-6524-528b-b0e9-aa0ffc776768 | textbox | Date Completed:
039ef9eb-b0dd-4dd2-8338-7b933731da93 | checkpoint | 1.3 Service Identification
ee948ca5-9641-5522-9e5f-ada0c827bb90 | note | Frequency: Prior to start
9fc8f64b-3701-54a6-90ca-0880be9852db | note | Acceptance Criteria: Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected
dc12b774-6322-58b2-946c-17df047d79d9 | note | Reference Documents: ITP sign off
02c7a3d9-753a-5dcf-ba55-df16e386fe78 | note | Inspection / Test Method: Verify
a4dea3df-4915-58e0-b0e9-e665f6c56a1e | note | Record of conformity: This ITP signed
3007edd6-b4bd-5361-83cf-f30222e82832 | note | HP*
ed15e7e1-c6b2-53d3-848b-0c5095fb6b63 | note | Responsibility: Site Engineer
c22b0622-bc80-5540-a868-fe19305a89cb | textbox | Date Completed:
06fe3fe5-2f15-4e5c-a298-6a06844f5476 | section | Construction Works
4b251d8c-57f9-423e-b47d-349aeba9f83b | checkpoint | 2.1 Saw cutting
75b05263-de97-5ae1-a55f-afe9e4098934 | note | Frequency: Where required
889000e3-cf4e-5056-bdb2-14cf3cb4cb52 | note | Acceptance Criteria: Extent and location of cuts to be clearly set out and checked prior to saw cutting
1e5b7218-e4ce-59d3-b44d-4f4e1e4268a9 | note | Reference Documents: ITP sign off
85ac15cc-d8d8-51f0-9807-a30318011c08 | note | Inspection / Test Method: Visual Inspection
b88bbf25-3bbc-5582-85c1-a250f6d7eb8d | note | Record of conformity: This ITP signed
4e65481f-e71e-5cfb-aa5c-3e337531d92d | note | WP
cfa47a64-cd99-5cd2-8795-fa95b2bc3228 | note | Responsibility: Site Engineer
10fb30c1-3195-5c2b-854e-373df27acc3e | textbox | Date Completed:
41aa5e7e-f933-4bb1-8fd7-cbec1ff39b0a | checkpoint | 2.2 Excavation Permit
05b3bce0-7fa4-5875-935c-d7435468c54d | note | Frequency: During excavation
146799aa-f6c7-52ef-af2a-7bbbd3b0a6b8 | note | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing.
8b7a95a7-1b17-5473-8c3c-fce084274993 | note | Plant and equipment shall be appropriate for the task
dc69ade5-7a3f-5e7b-9585-624112e7f044 | note | Excavation operations shall not disturb areas outside the limit of excavation
60b7a91e-c735-5321-9668-84acb3def815 | note | Reference Documents: VicRoads 204.06
fb8e7d9e-ee76-50f6-ad79-2bc387764947 | note | Inspection / Test Method: Visual Inspection
c8eb4de5-a82d-5a15-80f7-9bc3930cb887 | note | Record of conformity: This ITP signed
efbb50da-1840-5ead-8e08-fb1f0dc7a7f8 | note | HP*
9427f683-0259-5f7a-9ceb-f3841de39405 | note | Responsibility: Site Engineer
c9e9c37d-a710-515b-95f9-ef92d70fa9de | textbox | Date Completed:
09e0ca99-dbd6-49fb-841b-6c25d5418c59 | checkpoint | 2.5 Disposal of Material
438125b3-75e9-5904-a9e9-d5f382b74d7a | note | Frequency: All times
dab71666-6363-584c-a04c-331845307ae0 | note | Acceptance Criteria: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
32923349-c81c-58e3-99e4-61a2e1dffad8 | note | Reference Documents: ITP sign off
e57b6cc8-a2d1-5c77-a781-e7d13c33c18d | note | Inspection / Test Method: Visual Inspection
a8e77ae4-76be-544c-84ee-c4e23c59fc3e | note | Record of conformity: This ITP signed
96bcb862-b332-5d9c-b61d-58bfa29c07e5 | note | WP
1d638397-15aa-5108-82f7-b4548f8789ac | note | Responsibility: Site Engineer/ Site Foreman
e2817c47-9fb5-538a-a4e0-824fa3194172 | textbox | Date Completed:
6c955b74-e50b-4696-b12a-a8e9ecca6578 | checkpoint | 2.6 Maintaining cleanliness of site
d99fd201-3700-50f7-976f-bf57d5a63ff3 | note | Frequency: All times
abc3151b-e317-5d3a-9ea0-d19d457ac7e8 | note | Acceptance Criteria: Site and surrounding environment are to be maintained at a good standard of cleanliness
ac0171be-e2f4-5686-b68e-8b31f9075d0a | note | Reference Documents: ITP sign off
f4d91862-5f1d-5a4e-82ec-5fe23173cad6 | note | Inspection / Test Method: Visual Inspection
b861b9f5-e7db-55c5-8162-78470be313b6 | note | Record of conformity: This ITP signed
5f06258f-e3fd-5357-8ea9-338bcea1ce18 | note | WP
a34ad6d3-12b5-598b-b1e5-c8c048bb403d | note | Responsibility: Site Engineer/ Site Foreman
e09d9022-434e-56eb-b8fc-bf2b68bb7aca | textbox | Date Completed:
fe389afa-0b7c-49ae-88c1-a0c666be2760 | checkpoint | Final Inspection
9a2eeb5e-82b0-5bee-b217-8aacf7753309 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
56688841-bc7f-5a55-ad01-5c69780e1e95 | textbox | Print Name:
d511ed4b-8978-5e31-8e42-a49086e42593 | textbox | Position:
e663285e-42a3-5b61-abdf-57733996423c | textbox | Date:
80404ef5-9024-464c-b2d7-338941e32001 | checklist | ITP-040 - Profiling |  | ITP-040 - Profiling
3578bb46-25d8-48a6-bc40-4b351282515c | section | Preliminary Works
bf20107f-758f-405d-ba43-cab886aa13d7 | checkpoint | 1.1 Check for correct documentation
37e8a65e-e6ce-56f9-87e1-854c78d390cd | note | Frequency: Prior to commencing any activity
4c3bdad0-07b0-537a-8b7b-4346d49279e4 | note | Acceptance Criteria: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
551c5723-b23d-5600-ae02-5712d3372efa | note | Reference Documents: Drawings and drawing registers
97e7a2d4-a377-561f-901e-df0578889a74 | note | Inspection / Test Method: Visual inspection
85ee7058-6d3c-5cee-9408-3e4ef131b3ff | note | Record of conformity: This ITP signed
3a5c799a-865b-5a77-b76b-57cc73e17dcb | note | HP*
e46149f8-f4a5-541a-9f49-513df9e55b3c | note | Responsibility: Fulton Hogan Engineer
4eb771c0-89ad-596c-8314-b94cc21217ad | textbox | Date Completed:
3bc7a1ab-c355-4e9b-b229-4cd33da40ef6 | checkpoint | 1.2 Implementation of all measures and controls
b349f2a6-4ea7-5fbb-a323-5de068559def | note | Frequency: Prior to commencing any activity
c863dd9d-d4e6-5669-83ba-b99c21ef779e | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
551c0100-75c2-5ad5-86e2-42a8fd810bb2 | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
14ae3a55-fbe7-5b8e-8a5a-e7b9dcda8819 | note | Inspection / Test Method: Visual Inspection
13b6d658-67c5-5fbc-8386-b751cf067d4c | note | Record of conformity: This ITP signed
81a0f569-9c1a-54eb-8b1e-bf24b2df0705 | note | HP*
a019c8e9-be6c-532f-b6ec-04cc645588f9 | note | Responsibility: Fulton Hogan Engineer
a7b7c997-6bd9-5dd7-9ed3-094894c1ce5e | textbox | Date Completed:
e3615868-f700-4172-9ced-539fb007640c | section | Construction Works
162774a7-8642-4ff2-a749-fe38069e7b1d | checkpoint | 2.1 Profiling Works
de3851af-e40a-5601-94ab-39a01a1fb80e | note | Frequency: Each lot
0ce9c1c5-0f68-53eb-92d7-b89856836290 | note | Acceptance Criteria: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
6f93a524-9016-5281-8757-d2801fce846b | note | Reference Documents: 402.02
897ef39d-6fc7-55fa-822f-582808b34b96 | note | Inspection / Test Method: Visual Inspection
1554e260-5c96-5ae2-ba2b-a11ddd749988 | note | Record of conformity: This ITP signed
a7076b19-538c-57a6-931c-bdde92a626e2 | note | WP
1d63fdba-d2b2-56dc-9352-1c4111fc1080 | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
a58a48ad-5363-5986-97ef-da9a646d4c05 | textbox | Date Completed:
bba0d97e-6122-44cb-b6f2-0c4b4fac8da2 | checkpoint | 3.2 Depth check
d9745d96-2f26-5d97-9807-1adef111cfd7 | note | Frequency: Each lot
f186f036-8106-57d8-9d10-737f561ac6e1 | note | Acceptance Criteria: Ensure average depth of pavement removed is in accordance with relevant methodologies. Ensure a maximum of 50mm to be removed per pass. After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straight edge placed on the planed surface in any direction.
cf3050a8-3f08-52dd-a9e9-91ed91ab60a0 | note | Reference Documents: 402.02
899b8b29-fa65-52e4-b8ee-2c0d11979817 | note | Inspection / Test Method: Visual Inspection
1af64992-a1f4-559a-b1eb-43b8af08363b | note | Record of conformity: This ITP signed
f53ae0a5-4fc8-5e75-b404-b6f1a4565234 | note | WP
e96da8bb-2924-544e-91da-6c5ed0c637b4 | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
a361a6c1-0469-59a3-b9e2-4888de0882ed | textbox | Date Completed:
777c170e-88e6-47ef-b071-f52d99c39228 | checkpoint | 3.3 Temporary ramping (longitudinal)
6015e59f-6e8e-5c73-a719-3b82948fa0fb | note | Frequency: Longitudinal edges
c020dcf9-17ad-596a-ae22-8918184e2671 | note | Acceptance Criteria: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
fa89876b-0478-50d2-84fb-62cdacb22b92 | note | Reference Documents: 402.05
4d5cba19-c880-5f6e-a44b-39bb126608f6 | note | Inspection / Test Method: Verify
4a2e3bfd-9e92-535a-8e73-74bdc278c6c1 | note | Record of conformity: This ITP signed
63b87bf4-ce6a-5ba8-9160-22afbac8e252 | note | WP
aa76ca36-19d8-59fd-acbf-cccf6195ee41 | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
1f81a9be-e53d-53d7-975a-9244d4394a28 | textbox | Date Completed:
3e2c1e90-2f61-4632-98b7-fa76bc043ed3 | checkpoint | 3.4 Temporary ramping (transverse)
aaf6a6a0-4e9e-52c4-b2d1-7570f8a0470f | note | Frequency: Transverse Edges
9e34b994-b90b-5be4-af03-97246a393124 | note | Acceptance Criteria: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
313a2660-1126-5cf4-98f2-740668a07d46 | note | Reference Documents: 402.05
b672a065-fe47-5172-9c86-49ed292df970 | note | Inspection / Test Method: Verify
0fa2ab31-6af5-5e98-b2e6-286b8d26ad02 | note | Record of conformity: This ITP signed
db8e7103-56e7-5d12-8247-a37b6dd005d1 | note | WP
db90e5ae-1ea3-5ca4-be64-6c6ddc108078 | note | Responsibility: Fulton Hogan Engineer / Foreman/ subcontractor
b23f0632-19b4-5041-bf16-928976148ff6 | textbox | Date Completed:
5e19e932-d09b-46cd-b0e9-41927fde66f8 | checkpoint | Final Inspection
e591a037-ed3a-5eaf-b9bb-8398bec4fe4a | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
45879ed7-9129-554a-a06c-99ab997af72b | textbox | Print Name:
43879150-2840-57e2-9c20-3d90622e7eeb | textbox | Position:
7509f744-8316-59d5-9b00-b8412767998c | textbox | Date:
5b47b29a-1ee6-4bbe-85c7-39d21760f62f | checklist | ITP-041 - Platform Bonding |  | ITP-041 - Platform Bonding
5fa95cb4-395d-45f7-ab20-bc93b3810194 | section | Preliminary Works
5cbe4b89-9b15-4e51-9bd7-604612156b03 | checkpoint | 1.1 Check for correct documentation
862e053a-c288-57c9-94c4-b8c7071356b7 | note | Frequency: Prior to commencing any activity
79dfafd5-cb7b-59a2-b7d3-bd3edbcb5057 | note | Acceptance Criteria: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
f159d32b-6de6-5d86-841b-5c881c31fafa | note | Reference Documents: Drawings and drawing registers
b87662e8-491c-5c2a-96e8-8dbdbaf26eda | note | Inspection / Test Method: Visual inspection
80989926-cbf2-5718-9ac0-d48bd1a1bcd9 | note | Record of conformity: This ITP signed off
fd68fadc-799b-5be7-bf35-2133a5a4e989 | note | HP*
a8dac2eb-fdc0-5559-a0e7-619e4e0fd324 | note | Responsibility: Fulton Hogan Engineer
c7d9f21c-7fbb-5871-b3bc-9f7a29059962 | textbox | Date Completed:
f2113eff-78bf-4b78-9b15-c698941bd6e8 | checkpoint | 1.2 Implementation of all measures and controls
26f95e48-5ba0-5484-a3b4-d9bb8748dd76 | note | Frequency: Prior to commencing any activity
da55e5b0-3bed-5c77-8edf-a6204cdf0db8 | note | Acceptance Criteria: •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
5227e3d8-92b1-5bdd-b7fc-ed9b84787d59 | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
75fa052a-b3b5-5f33-bc84-4114ee7db418 | note | Inspection / Test Method: Visual Inspection
b377350c-f0a5-5aad-b1e7-2f94b56b9c07 | note | Record of conformity: This ITP signed off
e66b7082-015a-5f05-8643-17f4d21e2a05 | note | HP*
c4802cc7-de77-5274-b756-da950a578fcc | note | Responsibility: Fulton Hogan Engineer
25019b80-a140-5e22-8fc6-60e024e1e8a3 | textbox | Date Completed:
c3c7b9b8-b1cb-4de6-8b25-f53d892988f6 | checkpoint | 1.3 Check Materials
3bd30c72-6f1a-5e06-b6d6-b9116eaf7fb1 | note | Frequency: Prior to commencing any activity
b3b6f2d0-199c-5f06-95e4-17807603a1e4 | note | Acceptance Criteria: •Confirm bonding cable material & size is correct and in accordance with design drawings. •Confirm correct mould type and size is used for required CAD weld connections.
08ea2031-d51f-509d-9c9f-fd9d1a6dbe27 | note | Reference Documents: Construction Drawings
80e6022a-0bcb-56a0-a5e2-3772efb7d90c | note | Inspection / Test Method: Verify
eda83697-5e4a-5b15-bf0d-d3ff482402db | note | Record of conformity: This ITP signed off
e842c73b-2682-5c2e-b437-515fb5e8fa62 | note | HP*
d10ddda3-01ee-571a-afdd-563f86fc83fd | note | Responsibility: Fulton Hogan Engineer
9a3c28f5-5d40-5563-ad98-e4e629bca915 | textbox | Date Completed:
f9c4677f-0c9c-4954-911c-8e5b97ff6cb4 | checkpoint | 1.4 Bond setout
7944db51-9530-5dae-b9e0-3ac9def1df1c | note | Frequency: Prior to commencing any activity
7e3c62df-cbd6-51ec-b61b-e9f8ad01ee15 | note | Acceptance Criteria: •Confirm bonding loop and connections are positioned in accordance with the most current and updated set of construction drawings. Ensure that all locations are reviewed by a Fulton Hogan engineer.
3a7dfcac-faf9-5323-8902-0848a03363e6 | note | Reference Documents: Construction Drawings
f3b9bc6c-9cff-58a6-8f20-e5e89479d60f | note | Inspection / Test Method: Verify
35d238b3-0216-5787-8c21-b992f8b62c50 | note | Record of conformity: This ITP signed off
30cc2038-119b-54f8-bcca-0eac25831a42 | note | HP*
20f0c14f-b4a6-5888-9701-d39b19fa42c3 | note | Responsibility: Fulton Hogan Engineer
821e515b-2835-5c28-b202-641e03c57d70 | textbox | Date Completed:
d61f7859-c906-4578-b6cd-10c5ee3f461e | section | Construction Works
d0eb6d09-5de4-4392-a4c9-5e15884d5c7f | checkpoint | 2.1 Laying of Bonding Loop
02ea6930-b75d-59db-b668-82dc64228b3b | note | Frequency: Prior to Asphalt
b9d4faaa-bb17-53f5-b16d-2309f36e5db2 | note | Acceptance Criteria: Lay bonding loop in accordance with construction drawings such that it connects to the electric cabinet correctly.
df7bb9ea-9258-5c9e-b38f-7fe2272b603f | note | Reference Documents: Construction Drawings
bce2ce05-7a7d-54c4-8b8e-389e9c6dc104 | note | Inspection / Test Method: Visual inspection
ba3b61a6-dcff-50a4-8222-92700c13429e | note | Record of conformity: This ITP signed off
85f31ecf-bedf-5242-a185-a03021a350bd | note | IP
cccbc360-7d35-5251-9ee2-1e9a44e0178b | note | Responsibility: Fulton Hogan Engineer
08a7518f-9391-5e0d-939e-cf18b922491f | textbox | Date Completed:
13ead5a7-a149-4d12-98de-dc80e053185a | checkpoint | 2.2 Laying of Bonding Furniture Connections
d68a3b99-857f-5fda-866b-4c37018d04e7 | note | Frequency: Each Lot
4e52f5db-b392-575f-b32c-10338b89045a | note | Acceptance Criteria: Ensure furniture connections align correctly with structure and are positioned in accordance with the design drawings.
ce35758e-e876-5fe4-987b-b50f2610a61a | textbox | No. of Furniture Connections:
c71b06c4-affa-555e-b166-b197ff72dc89 | textbox | Furniture Connection Cable Size:
628158f6-0f09-5e02-b101-6717162847e2 | note | Reference Documents: Construction Drawings
a3eb959f-2f0b-5a73-9938-c61b574a4ef1 | note | Inspection / Test Method: Visual inspection
b7c05a24-aa09-5507-8a2a-189a69ea368b | note | Record of conformity: This ITP signed off
703c5963-2590-5664-938a-d996f8a0acee | note | IP
34bbc1bc-b2a1-5423-9dc5-11c21daae183 | note | Responsibility: Fulton Hogan Engineer
940b817d-819e-580c-bad8-ac4c8aec9f65 | textbox | Date Completed:
e0f674d9-1455-4c8e-a0b1-ae135f15df50 | checkpoint | 2.3 CADWELD Furniture Connections to Bonding Loop
b709444d-ced3-5f56-86cc-901a76fc0641 | note | Frequency: Each Lot
0251ec19-f6dd-56d6-870a-a820233e6294 | note | Acceptance Criteria: Ensure correct mould is used when CAD welding furniture connections to bonding loop.
860a3a8e-61fe-5a2c-9d25-bf702c1c4dcf | textbox | CAD Weld Mould Dimensions:
28010fc5-b22c-5d66-b6ae-b8ae717963af | note | Reference Documents: Eritech CADWELD Exothermic Welding Manual
5c1bc16d-727f-5742-85fe-2bbef022d027 | note | Inspection / Test Method: Visual inspection
4c2bbe04-50f5-5e41-ad51-614c1a155c6e | note | Record of conformity: This ITP signed off
47c8190c-f21c-5b52-9901-879c02322a51 | note | IP
4da2cd3d-329d-5fef-b0de-89b901c9a32d | note | Responsibility: Fulton Hogan Engineer
c0b6ca45-64ea-56ab-9f71-4ba8aaed4f12 | textbox | Date Completed:
63fe8fbe-6be5-4a1d-bf6e-1d2bf25adb99 | section | Construction Works
4eaec95c-4885-4f21-ba50-13e8ab4801e7 | checkpoint | 2.3 Weld Review
23108a4d-f394-5dce-94ab-03e461a8091c | note | Frequency: Each Lot
3c12bf1f-72e0-5ae0-928c-64a097648daf | note | Acceptance Criteria: Ensure each weld is inspected and that a quality connection has been made. All welds shall be inspected by a Fulton Hogan engineer.
5b973cc6-c04a-51a7-a664-134514984e7f | note | Reference Documents: Eritech CADWELD Exothermic Welding Manual
4de8fdad-cdbf-5d2b-ad02-a215f89f37cf | note | Inspection / Test Method: Visual inspection
bd426ae9-b421-57db-aab7-23bd2d60dd4c | note | Record of conformity: This ITP signed off
08076672-18dd-551c-aa59-a8dbbfc59344 | note | TP
68608670-dcb5-519a-ad57-332622a15125 | note | Responsibility: Fulton Hogan Engineer
dff885c0-b695-580d-8667-f76110765c2f | textbox | Date Completed:
44df5032-9d5d-4e4e-a1ff-5eaa1257059c | checklist | Order Acceptance Certificate |  | Order Acceptance Certificate
ab656ae3-e21c-4151-a29a-39979cdb1606 | section | Details
c9890bc1-acf6-4a2d-9d79-70b3507b7d56 | checkpoint | Order Acceptance Certificate - Details:
51d48d05-1cf2-5d3a-8d9a-e0d6f78d9347 | textbox | Subcontractor (full name of Subcontractor, ABN, Subcontractor's ACN and ABN)
dffb1e2f-69a1-5eb2-bef4-1f8c6bea1c0b | textbox | Order No.:
fc03ca52-c6f6-5f5a-9dbb-1d1e554b6ddc | textbox | Delivery Site:
e85009bc-bd67-5b25-a94f-097a18fab117 | textbox | Date on which materials delivered:
4f9d6e05-e8db-50d4-923a-60af1bab92a5 | textbox | Delivery vehicle (registration number):
15286555-37ee-5b27-9154-ad038676dfcd | textbox | Subcontractor's delivery personnel (full name)
066e22bc-23ae-44ea-87e3-408f2f29e662 | checkpoint | The Subcontractor has checked all Materials included in this delivery and is satisfied that all of the Materials comply with the Subcontract.
f76b476c-4dde-437f-bc58-64ea1991d99a | section | Packaging Inspection
61edb8c5-478f-4b4f-9247-2d6b067c9722 | checkpoint | Fault ID:
f877d951-2000-5bb5-b727-69cdd5d56d95 | note | OK = Meets all criteria
dfc18ef6-2ef9-54ea-b591-55c124b3680a | note | QI = Quantity incorrect
827a1cc1-4962-5a48-a3aa-2954e6b4ba7e | note | IN = Item incomplete
bafd20c5-81d4-567d-aeef-48bc2d30b1dc | note | MI = Make or type incorrect
f6bd0acd-4888-5fe9-887a-108cd7d9ad76 | note | TD = Damaged in transit
c831916a-0314-55c7-b2fa-5cfd11584b23 | note | NI = Not properly Identified
606d8e6b-25e5-4e55-8d1c-1b35f0c5a8c6 | checkpoint | 1)
dc44c709-5df6-5a0b-bbc1-ac325d813acf | textbox | Item ID:
1642fa57-7f05-5296-a8b9-dd07ed88ad73 | textbox | Item description:
5dee18ce-651f-5d8a-adb4-d92159205119 | textbox | Units ordered:
db40a5e4-e4de-5af9-8a12-25d342844d59 | textbox | Units delivered:
c11e2441-9fca-581b-836b-21da2df948b9 | textbox | Special Storage/ Handling Requirements?
fe44b4f9-eb49-5c92-ab08-4540521a298f | note | The following is for completion by Fulton Hogan
b68a1686-6cf5-5ea3-b757-f0e09f0ab8f0 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
0921631a-83a2-5e7b-9993-01127f4d22c0 | textbox | QA Docs Delivered?
9d44585e-7399-54c0-bce3-7bb3a8b34a75 | textbox | Defective?
448e7326-3481-5624-a53d-a426f8285812 | textbox | Number Accepted / Number Rejected?
0bed41b3-25b3-55b4-be59-b63ce36be5d3 | button | Fault ID: | IN, MI, NI, QI, TD,OK
1e198acb-146a-4eba-8c46-1f944fee5dbf | checkpoint | 2)
ef79583e-3b0a-5b4a-93aa-9987791b020d | textbox | Item ID:
504122f6-0472-56bf-804b-ce91acdc79d9 | textbox | Item description:
20a62c23-1c90-5bf2-8eb7-82914e249618 | textbox | Units ordered:
8c97add0-5031-59d8-a738-61b68a955edb | textbox | Units delivered:
9af935b2-e754-5503-a66c-13a980870c16 | textbox | Special Storage/ Handling Requirements?
987f6926-e13c-52b4-9a92-a167d455b79f | note | The following is for completion by Fulton Hogan
7c483704-92c5-519d-8af0-2fa2365d4b15 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
00306bc9-6497-58fa-88f5-aa5c6071079f | textbox | QA Docs Delivered?
d522d2fe-986b-5902-955d-70f6e03b45a5 | textbox | Defective?
954f4fcc-f364-58c7-bb27-455e26d59be9 | textbox | Number Accepted / Number Rejected?
eb812967-c74b-55b3-a181-3dee1918ed21 | button | Fault ID: | IN, MI, NI, QI, TD,OK
b1fe9237-56f5-44a6-9048-a1a96d6368fa | checkpoint | 3)
a462f94e-1138-53fb-9f92-c12db66fe475 | textbox | Item ID:
9c0fc573-2f8e-5be8-a7eb-0615ee058fda | textbox | Item description:
557966cc-fa2f-5e6f-838a-93fad43eb925 | textbox | Units ordered:
1e651eb2-8c1d-500c-ae8d-e6772e68ef13 | textbox | Units delivered:
0819f607-233c-5f4a-8af2-2949a85193c9 | textbox | Special Storage/ Handling Requirements?
07a14d1f-dc44-594d-85b1-42e99c9d34a3 | note | The following is for completion by Fulton Hogan
f5ea3fa6-ff41-59ae-85e0-942a6b58c668 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
203b9a7f-e2ae-5d0a-824f-da889a9860d8 | textbox | QA Docs Delivered?
bbd9ef7a-82e8-5385-8f31-6c13f3e20a2f | textbox | Defective?
10d6cfed-5d37-5546-b724-318aec062e4e | textbox | Number Accepted / Number Rejected?
74778f94-2460-50f5-a103-7e43199cbbbb | button | Fault ID: | IN, MI, NI, QI, TD,OK
c085eab2-0d0b-4537-9880-2eaf821c94b3 | checkpoint | 4)
c604fcf6-c9ae-568a-af71-02d4d30231ce | textbox | Item ID:
fa525e74-a720-515f-b606-88b86b05f665 | textbox | Item description:
2baf7293-1ccc-5a4c-8c50-e9681f128b45 | textbox | Units ordered:
2d8712a1-d53c-5723-8786-9b63814e5b54 | textbox | Units delivered:
468282fd-116e-589f-88da-06325ee6f686 | textbox | Special Storage/ Handling Requirements?
8eebb0da-d475-56fd-986e-b44f1d7f3eb7 | note | The following is for completion by Fulton Hogan
4010010d-8ab6-5f93-a5cb-25b897c75f9a | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
1cefd491-b910-5a2a-9418-be2c910f0860 | textbox | QA Docs Delivered?
53b841c4-ba4b-5780-a735-615bbc89087a | textbox | Defective?
87324ff8-94bd-58db-8fef-c167f1c3affa | textbox | Number Accepted / Number Rejected?
8632ee03-999b-57c5-9116-81d3e06a3bb1 | button | Fault ID: | IN, MI, NI, QI, TD,OK
8c1f0c03-5678-47e3-a0e6-c9fd22f5398d | checkpoint | 5)
dcf78c2f-39fe-5413-9e5e-5abf054e85e9 | textbox | Item ID:
8a5953f3-9b6c-57f1-892d-c63d4bba5885 | textbox | Item description:
0dd0a138-59d2-5a86-bc66-854fa9814b07 | textbox | Units ordered:
7fb82603-9b9f-5d8a-bf32-0ac27a4be711 | textbox | Units delivered:
2ef372de-82c7-5e15-84db-b461cb0452d6 | textbox | Special Storage/ Handling Requirements?
75725361-9bfb-5f5d-a33e-187b63332d1f | note | The following is for completion by Fulton Hogan
293932ed-1d31-593e-9ca0-923a92e42ff1 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
fca98827-1d6b-56d3-9779-447e8ce4f55f | textbox | QA Docs Delivered?
0229423d-85ef-51b3-8fc1-e6a66a12dc47 | textbox | Defective?
e85df69d-6a64-55a9-8f1e-f626e2c71cdc | textbox | Number Accepted / Number Rejected?
ddd7afdc-30aa-5377-9d7c-758f3f31be22 | button | Fault ID: | IN, MI, NI, QI, TD,OK
470d4eee-cd04-4c99-ac4d-9aaadf40bacb | checkpoint | 6)
c1826c0a-145c-5c0d-b550-f9b381a15e5c | textbox | Item ID:
b7621153-6cb4-5da2-b792-1988f58d3753 | textbox | Item description:
de0fd64a-9190-5b12-830a-4b6cb5da0da3 | textbox | Units ordered:
11eebaab-16e1-5c0c-a2c8-b12b3bb75aea | textbox | Units delivered:
26452890-fb15-5fda-ab06-274c6b900c93 | textbox | Special Storage/ Handling Requirements?
ec5362ab-42f2-5471-b5a1-5a71f7ca1f64 | note | The following is for completion by Fulton Hogan
2501d7c7-a3bb-55a9-968a-4ec55dfeb300 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
3d7b63c0-e935-5776-b2f8-216783eb4fc6 | textbox | QA Docs Delivered?
8e0f1ed5-6608-550b-ac4c-b33ac4a9c209 | textbox | Defective?
c2c16a93-12ad-577a-80b6-5087a3d3eecf | textbox | Number Accepted / Number Rejected?
e9136f22-cfd1-5886-ad3f-c3092c7f9dac | button | Fault ID: | IN, MI, NI, QI, TD,OK
eeaf7b2f-3043-4204-ba22-c2b1d6dd19df | checkpoint | 7)
234cd816-f5a9-55e2-9312-5eb8a95476a4 | textbox | Item ID:
35621948-7f6b-5312-8c44-ef1ca602814e | textbox | Item description:
7276f33b-8351-55a6-83cc-ae49113ddfc2 | textbox | Units ordered:
c064bb13-8419-5e30-8306-f15bb008b462 | textbox | Units delivered:
7bcf6071-5f12-5643-85a5-5ea54e4cb04b | textbox | Special Storage/ Handling Requirements?
5f1153a2-e64d-5187-8dba-c62d0d5a7070 | note | The following is for completion by Fulton Hogan
2845420e-5a39-54ff-888f-de0ee26c48e6 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
f712f750-1b45-5df3-8d36-3ccad31d59c3 | textbox | QA Docs Delivered?
b0dc094d-180f-508b-ad28-456af1e4936d | textbox | Defective?
8132ad5d-e593-5b0b-8aa4-29ba03077da1 | textbox | Number Accepted / Number Rejected?
0314ba62-9157-50b8-b733-423aff67ad03 | button | Fault ID: | IN, MI, NI, QI, TD,OK
9d702271-3618-47f5-a864-8a353e6c46a5 | checkpoint | 8)
a34e04ab-4bba-5019-8499-053847477ba6 | textbox | Item ID:
d136a55f-e67f-5818-ba9c-b6c5ab0a0301 | textbox | Item description:
0a451d45-ab9e-506d-a2bc-26a364a238a3 | textbox | Units ordered:
cc3fc7cd-d623-5469-8fbb-7c1913c73280 | textbox | Units delivered:
37b8b92e-d162-51ff-9ffa-316cc70cd4ad | textbox | Special Storage/ Handling Requirements?
3a22533d-0480-506b-8b2b-c4a13ebce748 | note | The following is for completion by Fulton Hogan
f8a663ca-f84f-5590-b2db-c5f1791b024c | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
f09db5c5-fbf5-5f1a-a07a-0c8c6adfe210 | textbox | QA Docs Delivered?
5e9a66ad-c763-51b1-862a-85a85877932a | textbox | Defective?
f85d1af8-5cd1-5497-9065-436f674d454e | textbox | Number Accepted / Number Rejected?
cae9b41c-cfd5-5a20-85ba-d9ef4c767de9 | button | Fault ID: | IN, MI, NI, QI, TD,OK
7564a994-214d-40ff-ae55-bb209d4b1205 | checkpoint | 9)
9297305a-f5ad-57bf-8c88-c934d46ae658 | textbox | Item ID:
bfc0e972-55e7-5c7e-91ff-d8b03fc75271 | textbox | Item description:
7b051003-fdf3-5369-be58-2cb15044a90c | textbox | Units ordered:
c29a91d3-2d9e-5393-a141-8f706d532c18 | textbox | Units delivered:
ba1cc5ad-8cbf-5102-bd37-34fd5dfe3f48 | textbox | Special Storage/ Handling Requirements?
6739e4ea-1f09-5cd9-9827-36e477124a73 | note | The following is for completion by Fulton Hogan
990f5aba-500d-571d-b840-ad1d9681d74a | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
a7e19db7-4c38-5f77-94eb-a344587aafd1 | textbox | QA Docs Delivered?
a7a39f0d-d786-5b7b-a23a-64144c9008c4 | textbox | Defective?
9e04a28c-51c4-52e4-8344-dbec4d1a3f7a | textbox | Number Accepted / Number Rejected?
f32524f3-fa31-5f49-86ba-e1f17f86ef1c | button | Fault ID: | IN, MI, NI, QI, TD,OK
5176fa42-b9bb-4e31-b2c7-bf4eae34e0a9 | checkpoint | 10)
e9bc594d-b108-51ef-ad3e-22aa1a298127 | textbox | Item ID:
76f21996-5239-5766-900f-43f398f17b16 | textbox | Item description:
f15b5ecf-484b-5d85-815b-31935fe0fb85 | textbox | Units ordered:
20868c11-f957-5552-8cd7-9921c3c7af4a | textbox | Units delivered:
00559114-1763-5b4c-b4e5-25fb70d4921b | textbox | Special Storage/ Handling Requirements?
dc7f8f2a-d24d-5870-b708-a28e8e9776ce | note | The following is for completion by Fulton Hogan
2f89fad1-6d26-5330-ba4a-de2be2cf550c | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
c3f129cf-6118-5ea5-911b-d5c526a268e5 | textbox | QA Docs Delivered?
4bf7ea1b-e8e4-5cf8-b8e7-0214cf456e21 | textbox | Defective?
279af3af-c175-530d-9994-d98b10b70092 | textbox | Number Accepted / Number Rejected?
3a768b4a-0ba6-5dbd-bbe7-73bc90746f5f | button | Fault ID: | IN, MI, NI, QI, TD,OK
793f4f81-089b-49d4-b0ad-74b252c2eaf0 | section | Sign Off
110b4de5-4872-4e25-a140-164d983ca582 | checkpoint | Accepted by Fulton Hogan
88be2cc0-de42-40c4-9680-7743645736ed | signoff | Sign Off
c075c020-9178-4c28-a5b0-54f5f083d92f | checklist | SYS - FHC-ITP-017 - Basin Construction (old version) | itp | FHC-ITP-017 - Basin Construction
7b3b7c05-e853-4ab1-bc83-0d244a7bc3c1 | section | 1 - Preliminary Works
e8010f52-d37a-4b5b-bfe6-8f01411e69ac | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
28359e3b-4e90-5f86-8198-13213b6f7489 | note | FREQUENCY: Prior to commencing
7e747f49-8529-54f7-a498-4bd9683197fd | note | – – – – – – – – –
4b3040b8-8f60-5a90-9954-bb18af7a2e45 | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
3f57c364-f068-53ff-91a7-ecc70d2bb932 | note | – – – – – – – – –
5a1b6548-e19d-52a7-9d2e-db3157fc1759 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
64704952-7455-58ef-9593-59461533185c | note | – – – – – – – – –
f0df6cef-e746-5d2f-b2a8-0910a1b9d7fa | note | INSPECTION/TEST METHOD: Visual Inspection
8cc0a007-4767-576e-8412-4bdf890ebc01 | note | – – – – – – – – –
3c16aa71-61b0-5b5b-88c0-4f34b78a0a12 | note | RECORD OF CONFORMITY: This ITP Signed Off
1de3980d-1fcc-5648-b4b3-fec31115be02 | note | – – – – – – – – –
f8fef1ff-cff1-5944-84b8-53748ecb0c36 | note | HP*
4184250f-6908-55ba-a920-0d934bfb210b | note | – – – – – – – – –
8fb8d68a-42f1-5d70-8078-b076acc878c8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
54864fb8-1610-5510-800a-8e4ba247f2a2 | note | – – – – – – – – –
755e1c8a-59f0-5af1-9b29-6c304db07328 | textbox | DATE:
629fdec8-d905-492c-9cbd-9266a637c32a | checkpoint | 1.2 Implementation of all measures and controls
af39c37c-be2a-5803-b6c4-b37c20bc88ea | note | FREQUENCY: Prior to Placement
ce29591e-8c58-54d7-bacf-17b544cde867 | note | – – – – – – – – –
fb30d665-d0ef-58ed-ae36-21a157e7d262 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
340a2180-4481-5168-81bb-780aed54c338 | note | – – – – – – – – –
ec78db87-35ac-53e2-a58a-8e8e07eaf193 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
7d735305-dae7-5e97-a1e1-f445883d8d9d | note | – – – – – – – – –
2464b93d-dd67-536e-a977-d69f3155bdf2 | note | INSPECTION/TEST METHOD: Visual Inspection
5547d6f3-f032-5e87-bc3b-2d448dc70a0b | note | – – – – – – – – –
a82523de-d9fa-5783-a253-c4b0a81c2e37 | note | RECORD OF CONFORMITY: This ITP Signed Off
876d2f2c-a293-5431-a155-840fdceb04ea | note | – – – – – – – – –
7841ed62-5104-521c-917b-2b056cde7fdc | note | HP*
47713a20-0b2b-5927-bfbe-f8463f65d21a | note | – – – – – – – – –
a12230e5-47db-5e2b-a50f-3b7635096d0c | note | RESPONSIBILITY: Site Engineer / Site Foreman
e81b058c-cf99-54f8-88ee-186f0b6aa4fa | note | – – – – – – – – –
cabbff09-3ba8-54d1-8409-61a1d70fcb4b | textbox | DATE:
0f535b39-2a96-47ba-9dd7-d909520af23e | checkpoint | 1.4 Excavation Permit
b6f22048-c608-501c-a75f-57cea03c8641 | note | FREQUENCY: Each lot
af51a307-05f2-545b-9b0a-8232e4e65f99 | note | – – – – – – – – –
4e56f9ef-8759-5ee4-ad78-5651eb65d7d4 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
7b9cc6fa-69d2-548e-9e3d-83be16c0efba | note | • Plant and equipment shall be appropriate for the task.
4f211e4d-0778-5b24-b0da-d8eb507c4fdc | note | • Excavation operations shall not disturb areas outside the limit of excavation
3160ed12-a3ee-56aa-bef4-0d1a8d839abb | note | – – – – – – – – –
9d28f3c6-1f0d-56c3-b1fd-58c88affc398 | note | REFERENCE DOCUMENTS: Excavation permit
2f020d54-f207-592a-8e35-9bbe4e14eb76 | note | – – – – – – – – –
cd1cfd35-caac-58c4-b6f4-8c069b933ed6 | note | INSPECTION/TEST METHOD: Verify
2a6b8815-152a-5d66-859d-cb634eac71c7 | note | – – – – – – – – –
46e311da-6798-5ba5-b393-18f0160eed37 | note | RECORD OF CONFORMITY: This ITP Signed Off
6dd95749-fb07-554a-9469-5250fec81afd | note | – – – – – – – – –
e62a49ff-f41c-5895-8df9-efb4f82140e2 | note | HP*
b77791d6-78ce-58ba-a523-d9d020f0b3bc | note | – – – – – – – – –
c9ddde84-f8e8-5925-981c-fc463e157181 | note | RESPONSIBILITY: Site Engineer
327acdc3-3f4e-5e31-88ef-f0da26c78466 | note | – – – – – – – – –
f8bc024d-bc77-5f77-a9f2-8fd2b2023396 | textbox | DATE:
9203b184-4469-46e1-9491-295a067f27a7 | section | 2 - Construction Works
6a30e09d-c3b2-4839-9b3c-5d7037ecab19 | checkpoint | 2.1 Survey set-out
04e3e402-3ba9-5c9b-b401-4930b939d70d | note | FREQUENCY: Prior to Commencing Excavation
8ff0d771-0c8b-502d-86e1-7f6f2ef6510b | note | – – – – – – – – –
bd5c9686-ef4e-5720-bc6b-f480d2e273e6 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.
b6cdd15d-7675-541a-a488-e4c22ff21207 | note | • The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
f9244485-4589-5198-bfca-495230ae13a4 | note | • IFC and latest available revision used
334b0945-0f20-52ab-bf84-c0643998c133 | note | – – – – – – – – –
0fd1633b-491e-576a-ad5e-3fe9eb2f3eaa | note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
dc678645-0ac4-59e5-b8a5-664662921752 | note | – – – – – – – – –
6f0f7c93-50ff-526f-84ad-793aeeba2cd3 | note | INSPECTION/TEST METHOD: Site Inspection
21860984-20f1-5ffb-b29a-bb7c140a737a | note | – – – – – – – – –
d2df3ee2-7392-5107-b5db-078edae5a1d6 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
ae33d023-1a67-50c2-9295-fb8e94ff0e49 | note | – – – – – – – – –
2f52e4d6-9f39-569d-92ff-382cf04ad306 | note | SCP
70b4c5f0-9130-5b73-a2a8-b4627cb87aed | note | – – – – – – – – –
9cad766c-7ad2-5ce2-b0da-39553c0e8cb8 | note | RESPONSIBILITY: Site Engineer/ Surveyor
876480bc-77b2-5a68-ba99-7589bd226560 | note | – – – – – – – – –
f2c704b2-a86d-5c46-9310-4024951f5a6e | textbox | DATE:
2172dde7-7b55-4e34-a1c9-388221d02778 | checkpoint | 2.2 In situ Material
1d86a565-ae87-5691-9a69-eb8c893bf142 | note | FREQUENCY: Initial
22f4e2b8-f708-531a-b724-8cceead36fb3 | note | – – – – – – – – –
377bd40f-9459-5c45-aa3d-df524762b904 | note | ACCEPTANCE CRITERIA: In situ material ripped and re-compacted to provide a smooth, stable working surface.
067c85bb-bac9-5a31-94f7-be1090de42bf | note | • Material to be free of debris, roots, sticks and sharp rocks/ boulders larger than 50mm
d4c73758-2286-51c2-afbf-91f00db45006 | note | – – – – – – – – –
7db05eef-5738-5eaf-baf0-8a9566c76b0d | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-10-TNT-CRG-0013
ebe6e36b-c431-59b3-85cd-0ec58bd4c3e4 | note | – – – – – – – – –
e9900102-aca8-52b7-85d2-8d5ce234d8df | note | INSPECTION/TEST METHOD: Visual Inspection
ca47a5d9-3442-5ebf-9eec-a262eb1847c4 | note | – – – – – – – – –
6cc21f4f-812b-54fc-a645-e40c7e155b5a | note | RECORD OF CONFORMITY: This ITP Signed Off
07d16db7-2c64-57d9-8e5a-5f8aaeca6a43 | note | – – – – – – – – –
0295a190-a98e-5ec3-802a-0c87e138f036 | note | IP
fc60bd03-4127-50aa-9e5a-1de72c3a8c4c | note | – – – – – – – – –
fdf393a3-f35d-55b3-9f41-88b372bc4a44 | note | RESPONSIBILITY: Site Engineer
7628ed3f-dcee-5873-aecd-9bd41615a142 | note | – – – – – – – – –
74c85cc8-e338-5eec-91ff-041bfca0ef64 | textbox | DATE:
7ce2c9c6-12ac-4fb5-bbe9-0e7919c3c34c | checkpoint | 2.3 Bentofix GCL Installation
5e245e33-8fb4-5baf-8c93-125ed2c29461 | note | FREQUENCY: Prior to placement of Type A
a1569f37-ba05-52e6-8bf6-b31c929477ba | note | – – – – – – – – –
ec6ebd3c-7c82-5347-a483-35e161905b49 | note | ACCEPTANCE CRITERIA: Geotextile clay liner (GCL) shall be installed in accordancewith the manufacturer's requirements
58d802bf-432f-5067-a2a2-42f829b895bc | note | – – – – – – – – –
3cd0977a-b9ae-5bbf-818a-4a9655446f73 | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-10-TNT-CRG-0013 NSP4900
3208c3e1-9dab-508c-ad27-183f6547b1ce | note | – – – – – – – – –
bad6d405-284c-52a8-8e3d-0da6c8d0b4c0 | note | INSPECTION/TEST METHOD: Visual Inspection
23c81999-88a3-5c67-be9c-75929b4677ed | note | – – – – – – – – –
f73337b1-dfe3-5fd3-8c34-ed8e3e864aa5 | note | RECORD OF CONFORMITY: This ITP Signed Off
88fe44d1-c284-550d-a07b-e916af6a361b | note | – – – – – – – – –
d42eceda-f543-5fbe-8fb8-de7e291188f3 | note | IP
9c550a8f-69d0-508c-84d3-13571675c08f | note | – – – – – – – – –
babfdd3d-e2dc-507e-a9b4-90641139930c | note | RESPONSIBILITY: Site Engineer
d77ac08d-44be-58d6-a370-2912960e3539 | note | – – – – – – – – –
44366ca1-c748-502a-977f-8cf6e92bee46 | textbox | DATE:
16afd807-3aa4-4e18-8abd-f7af52e97ba4 | checkpoint | 2.4 Type A Placement
c3d48172-555d-535e-aa40-b5392eb94a42 | note | FREQUENCY: Once GCL has been installed
7057273e-8818-516e-b62f-da512f8995e9 | note | – – – – – – – – –
a1c668fa-667d-56b8-b2e3-63b9b7ee0d36 | note | ACCEPTANCE CRITERIA: A minimum 300mm thick Type A fill layer shall be placed over the Bentofix GCL that has been installed
5b6caf95-790a-5db5-9c92-0ccb9e759c90 | note | – – – – – – – – –
1279c07e-57c9-50b6-b6a6-245d22126f06 | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-10-TNT-CRG-0013
053231b6-a533-59df-8262-259bcb4fd653 | note | – – – – – – – – –
5b3cf4b8-b296-56d2-9a74-d875b5238951 | note | INSPECTION/TEST METHOD: Visual Inspection
3dea1b16-2ba5-57c8-a503-e6c967baa75b | note | – – – – – – – – –
213d5705-23e2-5d19-84ff-0090c5bafe96 | note | RECORD OF CONFORMITY: This ITP Signed Off
8c0cee58-7f29-5ee4-a683-8a799f0ffcfc | note | – – – – – – – – –
9f2772bc-d415-5210-91c4-d346cc5ad5b4 | note | IP
c5545531-7c9a-5773-b42b-5c885336d95c | note | – – – – – – – – –
7ec9c94a-5878-56ab-938e-c2021428b5a3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0427896e-5d8f-5bda-9591-01f6d46e1335 | note | – – – – – – – – –
2ea2d5e9-689a-588e-8253-74b7bd318ac6 | textbox | DATE:
11cc4428-97b9-4e3f-bedc-779ae6ea8473 | checkpoint | 2.5 Base Construction
471b61fe-c8ab-5c75-befa-e6c26d50748d | note | FREQUENCY: Once Type A fill layer has been installed
e3133016-8175-5765-abf8-e03cc1466464 | note | – – – – – – – – –
a2b0a85a-3144-5807-ad9f-4693a821d562 | note | ACCEPTANCE CRITERIA: Provide a compacted 400mm thick hard base.
175456c0-e9ee-5bc3-955e-d69c4c3103b1 | note | • Approximately 50% 300mm size.
c2708fa0-e270-54af-a511-86ee4d8905f0 | note | • The remaining 50% made up of 0-100mm graded rock, premixed with 300 dia rocks and spread and tracked so as to form a compated base.
331c02b2-31a1-5141-8676-affe889f239b | note | – – – – – – – – –
0b3a34b7-b3f3-5fa5-b665-8a480fd13b0c | note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-10-TNT-CRG-0013
f820c51a-e3c7-5600-a43b-e38eee8e7ef0 | note | – – – – – – – – –
5a621c10-e456-5141-b058-5a126b24d1f3 | note | INSPECTION/TEST METHOD: Visual Inspection
df846252-07ca-5af5-bb3f-91a75bc4f29f | note | – – – – – – – – –
9b890538-e2a3-577d-9335-b87b9383e460 | note | RECORD OF CONFORMITY: This ITP Signed Off
61e96599-9fb9-57b5-8026-080ba078277b | note | – – – – – – – – –
15779b3a-b79d-54f7-a44d-b43809b7bed5 | note | IP
1852030f-375b-5d7e-aa25-1c0c6d2e4ae8 | note | – – – – – – – – –
7ac996e2-f2a2-56e2-be39-37b9b140697e | note | RESPONSIBILITY: Site Engineer / Site Foreman
6406e3ad-7293-5398-a3ff-87699f1425d9 | note | – – – – – – – – –
4a5f36f3-5d77-5952-bdb0-2b3a46615c5d | textbox | DATE:
9cec3f73-1e6d-412c-be82-29de3f7b6901 | checkpoint | Final Inspection
e11fac9e-0fba-58b9-aa79-d261474f4be1 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
bc83e3ba-c59a-5f13-89f5-21d3b78c4f0c | textbox | Print Name:
5d38bdac-45a9-5f91-8e70-0b6bff19326a | textbox | Position:
c031ba4b-9f8f-5a6d-a385-ed651e415418 | textbox | Date:
f514e91c-18a0-4176-be7d-ad12e6228f44 | checklist | SYS - FHC-ITP-027 - Pile Footing Construction (archived version) |  | FHC-ITP-027 - Pile Footing Construction
2a96eff8-3fa1-44da-8c0e-d654df952f6e | section | Design and Submissions
acfa2984-974d-4f18-ab55-197a20061feb | checkpoint | 1.1 Check for correct documentation
56b8fbd3-73b6-552a-b2f4-bb2cdc316a37 | note | FREQUENCY: Prior to commencing any activity
565167e3-8e0f-5cae-9782-800b3fd2f140 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
fbc05eec-8695-5e51-b364-902ebd269217 | note | – using the correct and complete set of drawings
7608a426-bf86-52b5-a7d4-4ca978f3c49e | note | – all drawings are the latest revision
85eddf2e-41b8-552c-b843-69ac548ec474 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
353118ae-672b-594c-860d-ea62a5ba42bf | note | INSPECTION/TEST METHOD: Visual inspection
89814cfe-a6b8-5c62-a322-3fcc6aa12f52 | note | RECORD OF CONFORMITY: This ITP signed
063be84b-a3a7-5840-8ef1-617af5ca632e | note | HP*
8b4fb251-6102-5a5b-a047-c446fed05fca | note | RESPONSIBILITY: Fulton Hogan Engineer
2acd9dc2-3cca-5d16-8941-d1fe80ff5b27 | textbox | Date Completed:
00581430-78fb-40a9-9e18-a7fd617bca0a | checkpoint | 1.2 Implementation of all measures and controls
6f2b38fa-66b0-5b33-b51f-84a8866dedbc | note | FREQUENCY: Prior to commencing any activity
6455d9ed-ab9c-5632-8663-18a0f05e0fc9 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
503a59e3-154e-5dbe-a3b6-1a04699343c3 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
6bc17d2f-34c5-5865-82c7-dcfb09f63bab | note | INSPECTION/TEST METHOD: Visual Inspection
877e85d1-10a2-5bbe-9ec4-f60343c1255e | note | RECORD OF CONFORMITY: This ITP signed
97276a3e-15ee-5429-af23-8e3014aadb89 | note | HP*
3fc3d639-8ddc-580b-9323-9e347f62a1ae | note | RESPONSIBILITY: Fulton Hogan Engineer
a7304a69-58eb-5b50-88f0-e24a5b928627 | textbox | Date Completed:
cd4b3124-1d76-4cdf-93d4-ec5893dfc9fc | checkpoint | 1.3 Approval of mix design
fb6e31e0-2321-54d1-b5f2-6193fab87417 | note | FREQUENCY: Prior to the first concrete pour
030d7464-78cd-5ee8-8e83-b37050927cff | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
f4370b24-2f58-5dd8-8530-ae07041446d4 | note | REFERENCE DOCUMENTS: 610.07
097f4b62-9569-5bce-b044-eeb28f98734e | note | INSPECTION/TEST METHOD: Verify
644b8db0-31f2-59f3-9b2a-0f135baff35d | note | RECORD OF CONFORMITY: This ITP signed
b6418480-8be1-5c8d-ab0c-8ae4945dacf8 | note | IP
f547baba-0437-5ff8-822f-c9d8addb426a | note | RESPONSIBILITY: Fulton Hogan Engineer
6cba5bb3-4279-584b-9242-1600c070eee7 | textbox | Date Completed:
2f633fd1-e0fc-49d5-a70d-050b09886a24 | checkpoint | 1.4 Reinforcement schedule
2dc00f6e-1095-5db0-a39a-6e30e2fa78d4 | note | FREQUENCY: Prior to concrete pour
7305eaa2-72c8-5947-abe7-88e0c76a07b5 | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
4c91490b-ca14-5eea-a389-aff7d0cbc504 | note | REFERENCE DOCUMENTS: 611.04
3948c179-7178-5336-94ea-de49ec8c7d56 | note | INSPECTION/TEST METHOD: Verify
bc7cd386-e618-5ad6-904d-d3b16230ee84 | note | RECORD OF CONFORMITY: This ITP signed
dd184420-8f92-5c15-b278-c3bd7b041ff7 | note | IP
1094265a-f6d6-553f-91a7-b207f5d61c8a | note | RESPONSIBILITY: Fulton Hogan Engineer
59a48784-1e43-5a8e-af64-83e9d2cd4fae | textbox | Date Completed:
3113d3b3-763b-4fa2-a2cb-07b732646dc0 | section | Construction/Erection of Formwork
c56e5c91-923b-4067-a420-0ccb65a92d8e | checkpoint | 2.1 Excavation (Pile)
c9159199-8369-5f4c-a97e-cf8309410512 | note | FREQUENCY: Prior to concrete pour
4a85f162-eea9-544e-a4f0-b3fcabd0a26e | note | ACCEPTANCE CRITERIA: The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent. Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
06433840-4921-536b-b16f-f99c6f148689 | note | REFERENCE DOCUMENTS: 606.05
78b4baab-70b6-5017-a328-b77fcc2cc6d3 | note | INSPECTION/TEST METHOD: Inspect
f0d3a527-1abe-5322-aa45-2e57ae7b5d82 | note | RECORD OF CONFORMITY: This ITP signed
b8d357ba-b28c-5190-921c-b30c0b16e6fa | note | HP
ea21338b-083d-5a46-b3de-7534153959e7 | note | RESPONSIBILITY: Fulton Hogan Engineer / Suprintendant
6da816e2-e9d6-5a3e-a0e5-5f25f8601f9d | textbox | Date Completed:
bbdf1b4d-40fe-4107-b7bb-557cf8eb790f | signoff | AUTHORITY HOLDPOINT
51ca5dc9-aa8d-43d0-be3d-5541c819e564 | checkpoint | 2.2 Construction Methodology
fd98462d-aadd-58f9-a868-32033939bf31 | note | FREQUENCY: Prior to erection
916f6064-579e-5589-b0bd-6a063af59299 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
ca1a0259-89ff-5774-8f02-ef63e6a482df | note | REFERENCE DOCUMENTS: 614.04, 614.06
46d0d2b1-d543-55b6-9837-16cb39eade47 | note | INSPECTION/TEST METHOD: Verify
17625678-8df1-5484-986e-6bf955c62829 | note | RECORD OF CONFORMITY: This ITP signed
fc9c9a9b-db92-5b60-beef-53fef1141292 | note | IP
b9ce648b-d19f-568c-93b8-9ca67c459db9 | note | RESPONSIBILITY: Fulton Hogan Engineer
5f040426-9d8b-5103-88d0-f30661e3d09f | textbox | Date Completed:
be9e4a42-39a3-4226-919a-74591bfcbc72 | checkpoint | 2.3 Construction Methodology (Pile)
d58a492c-9d93-5e8f-822b-0142a8030caa | note | FREQUENCY: Prior to construction
fec83b10-655e-54ec-869f-4bad6219bb66 | note | ACCEPTANCE CRITERIA: Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
5673fc8e-73e4-5767-b2d3-c85d8a048999 | note | • Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
7ed17d59-0285-5405-8df0-e12a109857a8 | note | REFERENCE DOCUMENTS: 611.10, 606.06
d8ac2014-7639-5acb-952c-808fa0ab3dcf | note | INSPECTION/TEST METHOD: Verify
a67774c7-c930-5b8c-abc6-dcee7ebce958 | note | RECORD OF CONFORMITY: This ITP signed
d6059f6e-45cd-5317-93f4-d059583fe2e1 | note | IP
c54354cb-e802-5e40-b202-6bebca866904 | note | RESPONSIBILITY: Fulton Hogan Engineer
2c283696-192f-5b7e-814f-58a068fa1b88 | textbox | Date Completed:
71bde9b5-3e4f-46b4-b824-7077aa1b401a | section | Pre-Pour Planning and Inspection
f90600b6-73ee-4cf6-a2ed-059edc36e9da | checkpoint | 3.1 Cleaning formwork
347c989e-4625-5445-a612-f96f74331d18 | note | FREQUENCY: Each concrete pour
fbb99708-3acd-56d7-8ef6-f4cc78ab99b5 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
141c4fa4-c5a6-598f-837b-14b36d7c2b18 | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
408a310e-601f-5808-b64e-49c4835d1015 | note | INSPECTION/TEST METHOD: Verify
02486279-c7aa-5958-8cd9-789ab07908e1 | note | RECORD OF CONFORMITY: This ITP signed
7055c419-ffda-58d4-92ce-b2a6153e0ccf | note | IP
fd6cdf2d-6991-583b-b6d2-0c0b2838315c | note | RESPONSIBILITY: Fulton Hogan
c8e48a21-0669-508e-abaa-a42b4f2bca9a | textbox | Date Completed:
c838135f-517c-4595-81d9-9f7151d9fe99 | checkpoint | 3.2 Correct forms, reinforcements, rag bolt assembly and embedments
460a7da1-638e-5b9c-a4aa-27283a1afb58 | note | FREQUENCY: Prior to concrete pour
7b895fb3-b057-5ccf-8023-aa2e1bffa710 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
9cea621f-c5cb-5ea0-aabc-fd03d2e97914 | note | • Pre-pour checklist completed and signed.
14e79a5c-89f3-56db-9043-eea00b5d7d74 | note | REFERENCE DOCUMENTS: 610.18 (a)
615b0c40-4346-5878-bec0-16e0c0385fbf | note | INSPECTION/TEST METHOD: Verify
d266d670-f275-5365-a78c-a92569e3f9bc | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
de6e74a7-9a82-545a-9f03-fe83c8e67841 | note | HP
3e2eeb34-b5b8-5def-ad73-4f84af33ff4b | note | RESPONSIBILITY: Fulton Hogan / Superintendent
68f1c809-0e9b-57f1-8f14-0f968864a7b9 | textbox | Date Completed:
acd23c68-f667-49af-94f4-93a2e81586f0 | signoff | AUTHORITY HOLDPOINT
61578325-bdd0-41df-923d-8f8e3cb27a0d | checkpoint | 3.3 Reinforcement assembly of piles
45431b63-e8df-533c-a2bb-5b156feb7917 | note | FREQUENCY: Prior to concrete pour
6998064d-ca71-5078-bdf1-d2d60989f871 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
29edbe0d-2706-57df-90b5-5da819287acc | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
1e5ad811-b600-5a8a-b974-3d4e899ef5d1 | note | INSPECTION/TEST METHOD: Verify
5590b8c1-f135-5063-9549-4428c93d9315 | note | RECORD OF CONFORMITY: This ITP signed
ecdcca66-9ac4-54bf-9c3c-51f63ff18d22 | note | HP
c6cf1003-08eb-5eca-b44e-c816415130b7 | note | RESPONSIBILITY: Fulton Hogan
0932035d-074d-5067-a1c2-9353babeac69 | textbox | Date Completed:
0d5a273a-3e21-425a-8682-9d2768beaa4d | signoff | AUTHORITY HOLDPOINT
d8941df9-80a5-4c16-b936-aef84b73d386 | checkpoint | 3.4 Monitoring weather
85fec341-db37-529e-91c7-5bd4601d9094 | note | FREQUENCY: Prior to concrete pour
2ffcf783-fd15-559e-abb9-8361599fa7e2 | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
1ab7bb6e-0ec9-56eb-a0e9-6696e83359e9 | note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
4436fbf8-bf05-52c5-b2b4-59a8abbebf69 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
e754113f-8ebf-5da1-833c-03133fb185f2 | note | INSPECTION/TEST METHOD: Verify
287c2d30-84fe-50eb-b07f-18cc32724b82 | note | RECORD OF CONFORMITY: This ITP signed
9c2573b0-c5c9-528c-bc81-1f7606848840 | note | IP
d092d8c9-d380-59d8-a259-d88eb97c5811 | note | RESPONSIBILITY: Fulton Hogan
f9c6fbcf-1708-5a26-b6e9-fa16b33f05f2 | textbox | Date Completed:
50ee2779-4730-427f-8df4-9a030d38024d | section | Placing and Finishing Concrete
220c44b3-0caf-4743-9e72-dd24c271686b | checkpoint | 4.1 Carry out sampling of concrete
355a96cf-9c43-5ea9-ac84-48e40b3059b0 | note | FREQUENCY: Each concrete pour
49ab2be7-a468-5980-ba8f-94ac2cf4f982 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
f87c0ee9-4829-5e60-aaec-f8e75c851f4b | note | REFERENCE DOCUMENTS: 610.16
2f146824-224f-572a-9ffc-64541296bd17 | note | INSPECTION/TEST METHOD: Checklist
3d1c2814-d78b-5767-8ce9-a242664a2837 | note | RECORD OF CONFORMITY: This ITP signed
253b76ee-50c9-5ce7-80bb-3e315db684d1 | note | IP
f01596af-96e7-51d9-a488-0691cf697560 | note | RESPONSIBILITY: Fulton Hogan
427ff673-6370-5985-8d84-fa2d0c2cf4ff | textbox | Date Completed:
10a13a0e-5e7e-400b-b2b4-56d4270c2558 | checkpoint | 4.2 Discharge time
611b3d64-6c2d-5342-9e2f-d3834de92462 | note | FREQUENCY: Each concrete pour
3df202c7-db0d-51e6-917e-08d4a74ca25b | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
08e07e38-b58b-5c18-8340-401f937fecb3 | note | • Batch to be used has a discharge time of 180 minutes. Boral VR400/40 (SCC) (180min')
920a9fd7-4209-5574-a048-5e019951d806 | note | REFERENCE DOCUMENTS: 610.13
8d1d7eae-882c-5641-8ff5-d42b88f4b9f5 | note | INSPECTION/TEST METHOD: Verify
23409ca0-8164-5082-b17c-fd7b5269f68f | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
c39d4100-4656-5362-bbab-bb52a39da754 | note | IP
9d9a40f3-86d1-5fa2-a2d5-558e2d7a8016 | note | RESPONSIBILITY: Fulton Hogan
01e236b0-0241-5fbd-8056-85be303c4b25 | textbox | Date Completed:
6590c790-a6d1-46c9-bc1e-c8d59e7eeb1c | checkpoint | 4.3 Methodology of placement (structural)
d82cfe4a-1c0a-520f-aa48-5a2a7d5ec9d3 | note | FREQUENCY: Each concrete pour
85ae7030-1754-5507-b376-448d7ed385db | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
c5ace7f9-d08d-58af-9e4c-2bf92d5db655 | note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
b4fae8a3-7f9b-5ef8-bcc0-49feff4a719d | note | REFERENCE DOCUMENTS: 610.18
139cae00-a3d0-51a0-956d-0507f63a8fee | note | INSPECTION/TEST METHOD: Verify
ab7c8ff3-5039-5816-8b4c-e47ba1c77dda | note | RECORD OF CONFORMITY: This ITP signed
d8d4dd9d-531d-5b91-b942-cad0f05f0a78 | note | IP
3f524e79-cbb9-5eb2-9633-b65c21e5a24e | note | RESPONSIBILITY: Fulton Hogan
5643b1fa-c16a-5389-b26c-50051efd98dc | textbox | Date Completed:
fb98866a-a76f-49a5-b3ca-d65f077b14ad | checkpoint | 4.4 Methodology of placement (piles)
7980553f-fbf0-579e-8bf8-7e0420b1b816 | note | FREQUENCY: Each concrete pour
c4717f44-d5d3-587b-98fb-987c9f0b4d24 | note | ACCEPTANCE CRITERIA: Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation.
109a5a73-932a-5a45-bcbb-b5aeed02570d | note | • Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
ea7704d1-1739-5c90-b105-6cfb2f87fd67 | note | REFERENCE DOCUMENTS: 606.03(b), 606.05
3b9adef1-97a1-5c7c-b4d6-53b4df6c4a86 | note | INSPECTION/TEST METHOD: Verify
1e1ab9ab-19e5-5b01-ae06-cb617f64e89d | note | RECORD OF CONFORMITY: This ITP signed
e562b75e-6d57-5c72-833f-a6164d1c2812 | note | IP
d5219586-f9ce-5dee-a296-6cf62db60e0b | note | RESPONSIBILITY: Fulton Hogan
76afe3ae-83e8-5cea-a264-870a44797b27 | textbox | Date Completed:
2e1c9e27-5003-4bc3-86f9-41257de420b2 | section | Post-Pour Details and Inspection
09a7d7c7-877a-4867-b251-7a5c9cbef56a | checkpoint | 5.1 Curing
7bf1a058-ff83-5171-99b2-4eaa0d146fdf | note | FREQUENCY: Each concrete pour
80973ebf-a53c-5a53-8bdd-29790ca9a5a8 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
0142c091-7e29-5a1d-824a-ee4f18444151 | note | REFERENCE DOCUMENTS: 610.23
fe7194d3-341f-5ffe-9d28-f3fe159b0fb0 | note | INSPECTION/TEST METHOD: Verify
d49b154f-a55b-55cf-bb98-826221ac7a44 | note | RECORD OF CONFORMITY: This ITP signed
f44cd10c-cd86-5194-b6c2-e0f10df56ee7 | note | IP
5f5515d3-0d08-59a7-a2ba-c83e36eb124b | note | RESPONSIBILITY: Fulton Hogan
1c2fa45e-be83-59c5-a4fc-d4866d6087b8 | textbox | Date Completed:
242fc751-a48b-4354-9094-0d227dc3f37a | checkpoint | 5.2 Formwork removal
34cb7ba4-58a8-5aeb-98fd-d4065357a357 | note | FREQUENCY: Each concrete pour
5a49ad29-87ad-5c66-8a54-7a63c3ef7a6d | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
599fb84e-e7be-56df-b84c-1a48a7937f22 | note | REFERENCE DOCUMENTS: 610.25
34553fd5-9c98-5781-83f8-7ac4510cde91 | note | INSPECTION/TEST METHOD: Verify
d9830e26-acdd-5caf-8d1d-f5fe8a3f0ff4 | note | RECORD OF CONFORMITY: This ITP signed
dd6fbdbc-764a-5f08-8897-58ab7ab5a1f8 | note | IP
4d1fbcbd-0129-570f-9b1c-175f3a6240ef | note | RESPONSIBILITY: Fulton Hogan
e94bbbec-b4c0-50c8-ad66-196061689e19 | textbox | Date Completed:
f36fefd1-0eab-481b-8e81-ebc15f87a882 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
33d49d3f-8250-5a29-8662-4b92d7913340 | note | FREQUENCY: Each concrete pour
739c4a71-c39b-598f-a911-0fa1d73f96e5 | note | ACCEPTANCE CRITERIA: The centre of the pile head shall be in the specified plan position ±75 mm;
f9284012-7f5c-551b-91f3-de0c3d426e75 | note | REFERENCE DOCUMENTS: 607.06
c02a2cb1-329c-51eb-92a7-91467eb54351 | note | INSPECTION/TEST METHOD: Verify
47b1ecff-9be5-5623-8dab-b72a6485f8e5 | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
57411d88-3fab-560d-ad3b-7b4642bfe065 | note | IP
09ab1ba3-342c-5bbe-ab64-d1cc67550997 | note | RESPONSIBILITY: Fulton Hogan
4127118b-9b8e-56a5-87ef-232a3085d030 | textbox | Date Completed:
d6eddbc3-fe7f-4bb8-b968-b814f6008aa7 | checkpoint | 5.4 Concrete Sampling and Testing
e8098e2e-a175-587d-9291-4d1692fca9e5 | note | FREQUENCY: Prior to lot closure
fbbf5a62-b24f-5103-89b2-23c41aa06487 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength:
745cdec5-c238-5918-a542-e4608f8fef5e | note | – 2 cylinders @ 28 days for VPV=13% & Compressive Strength=40MPa
0fd6d472-dcc2-5df9-b6f8-de9197787e65 | note | – 1 cylinders @ 7 days for Compressive Strength=26MPa
093320d5-cb7c-5053-a075-3799e7a98db6 | note | • Slump flow of 550 - 800mm spread
bbf92500-a6d3-5c5a-bc75-0aa08a02e81f | note | • T500 of 1 to 5 seconds
e591a0e2-06fe-5b99-9ff5-d46ec3d50fab | note | • Passing Ability of less than or equal to 10mm
5171bbf7-6f5f-5a90-ade2-2f5c09dc9e67 | note | REFERENCE DOCUMENTS: 610.05, 610.06, 610.13, 610.16
4a83cb8c-0bbd-52cc-8ee1-4425ead2e26a | note | INSPECTION/TEST METHOD: Verify
2cd2d5a4-506b-55c3-aa6f-e4a66290cba6 | note | RECORD OF CONFORMITY: This ITP signed
40edfc1e-c742-586b-9b70-e18042538a77 | note | TP
129abf87-b5c1-5284-9083-e619f231ac6f | note | RESPONSIBILITY: Fulton Hogan
95b53709-67e1-5527-95b2-a46fcaa3fd78 | textbox | Date Completed:
03687f0b-a093-4b32-8ed2-221f0c095267 | checkpoint | 5.5 Protection of Adjacent Piles
9f824957-a8c1-5183-8e3f-7684a5da4eaf | note | FREQUENCY: Prior to commencing any piling
1770f251-c8ef-5e63-9f0a-71123bc16aa7 | note | ACCEPTANCE CRITERIA: No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
d66467bd-8a3d-57c1-b11e-70c02a2875c2 | note | • Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
6413e891-22fa-56a5-b36a-968a203794b8 | note | REFERENCE DOCUMENTS: 606.04(a), 606.04(c)
9c84a457-a51f-5fe1-9d68-bfe292d48ed8 | note | INSPECTION/TEST METHOD: Verify
70db3930-241a-5a85-ac04-ac761f1f08af | note | RECORD OF CONFORMITY: This ITP signed
63325be2-2810-5393-801e-a149ffca1dcc | note | HP*
6f65d5d3-556e-5d9e-9026-655beb61745c | note | RESPONSIBILITY: Fulton Hogan
28bf048e-52d9-55f6-bffa-1a21f51d96e3 | textbox | Date Completed:
9efcaab2-1987-4078-b87a-9a3cbb615e0f | checkpoint | 5.6 Testing Post-Pour
65b30fb3-3d82-570f-b474-a7b45da019fb | note | FREQUENCY: Prior to lot closure
133625af-2022-5f31-b1ae-04417633dfce | note | ACCEPTANCE CRITERIA: Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
580965c4-1bf7-56f9-930b-de0a87ba9f46 | note | REFERENCE DOCUMENTS: 606.07
1b1ceffc-1502-5bf4-98c9-d27a21c905d1 | note | INSPECTION/TEST METHOD: Verify
69b5723e-33dd-57c6-8ba8-590c784ddf5f | note | RECORD OF CONFORMITY: This ITP signed
f0f9d4e7-1968-572b-8019-29a1939ca02e | note | TP
cc8af969-999d-5ebe-bcda-e7ed394c3cfd | note | RESPONSIBILITY: Fulton Hogan
b53ff53b-9d94-5a44-8f9b-e971f4753336 | textbox | Date Completed:
f702948d-0cae-4b02-b3c7-9e7a5b7aefb3 | checkpoint | 5.7 As Built Drawings
3160047a-995f-5a0e-9138-ceeaeec6c711 | note | FREQUENCY: Prior to lot closure
23c6c594-cf65-52c3-8f76-8c723ac53e39 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
1adb4f60-aafe-5a70-9868-b8cee844e143 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
8d82a9e1-7372-5a13-a064-336acf8ca6ca | note | INSPECTION/TEST METHOD: Verify
b457f585-8ba0-5259-9c61-cdf83ebd93be | note | RECORD OF CONFORMITY: This ITP signed
a270089d-b803-56b6-8007-6d0da86a8811 | note | IP
4f659f03-d4f7-5fe3-a30c-2c3032748382 | note | RESPONSIBILITY: Fulton Hogan
16a7c3bf-6281-5771-be5f-93906a7f14d1 | textbox | Date Completed:
e8c7ae51-7e81-4068-aafe-7d8851191a4d | checkpoint | Final Inspection
4cdb8faf-09c7-550a-80a7-40209a596d8e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
93f92349-1b68-5da4-9a0e-1568c7bdf19c | textbox | Print Name:
7cd25435-43cd-57f1-90c5-79952ca64bf8 | textbox | Position:
32c721ae-260f-533b-a266-a72743368445 | textbox | Date: