## Master List Templates
Id | Type | Name | Values | Prompting Name
f2fde9e7-9c31-4b6a-b1b5-5c987f27409a | checklist | Contract HoldPoint Checklist |  | Contract HoldPoint Checklist
96a78813-95b0-48fa-9a93-357ec9a1b8cb | checkpoint | Holdpoint Release
e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 | textbox | Enter Name
1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b | textbox | Enter Description
60a1eb35-e850-40c9-a4b9-af7b0196da59 | signoff | Contract Holdpoint Release

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
5602779b-0511-465c-93a1-d01ac8cae3a0 | checklist | FHC-ITP-001 - Clearing & Grubbing Rev1 | itp | FHC-ITP-001 - Clearing & Grubbing Rev1
5056e0ef-7061-42ad-8bf0-973f310f7146 | section | 1 - Preliminary Works
e0d7666c-e451-4d5b-8f6b-7ee897a228d6 | checkpoint | 1.1 Check for correct documentation
85790e24-e5f5-591f-b3a3-3f5e86f337bf | note | FREQUENCY: Prior to commencing any activity
6237e5a7-ad59-5eaa-ab85-c3260b2dc761 | note | – – – – – – – – –
abebb59d-b410-5d90-94ef-37586b937b96 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
86444a8f-8739-512a-8dad-ab52b734b9fa | note | – using the correct and complete set of drawings
a63d38e8-baeb-5ce0-9973-3d5635cb06bd | note | – all drawings are the latest revision
52249fc6-5811-58da-87a7-8c02d92be099 | note | – – – – – – – – –
ccfdb724-6465-5242-a029-a4c507df34db | note | REFERENCE DOCUMENTS: Drawings and drawing registers
f150e617-4d82-57e2-835f-be5b013a3320 | note | – – – – – – – – –
26e34435-0075-5ce2-b013-c7726e283c42 | note | INSPECTION/TEST METHOD: Visual inspection
fa249159-2648-5af9-bf05-aed619d60b61 | note | – – – – – – – – –
61f7bc0b-8ebb-5ad4-a5db-8d68182659f3 | note | RECORD OF CONFORMITY: This ITP signed
5490a368-000a-51b8-8279-843701f0c71e | note | – – – – – – – – –
a5c1ad82-aad7-5479-b301-df256929c818 | note | HP*
a7acbb5f-493c-5717-ac16-7523579e095d | note | – – – – – – – – –
577e7277-ed6a-5672-8c69-68b23b8fa016 | note | RESPONSIBILITY: Site Engineer / Site Foreman
9917db73-a554-5b63-aa11-382746f99e04 | note | – – – – – – – – –
b7e761f5-a1fd-51c0-8471-0ffff56e7f90 | textbox | DATE:
927f1bc9-a3f6-41d4-b623-d4e814c8785e | checkpoint | 1.2 Implementation of all measures and controls
44d15383-15a6-57ae-ad5d-374e5fdb7bae | note | FREQUENCY: Prior to commencing any activity
435e5912-d4b4-52a8-b314-4b1ef1b19a2e | note | – – – – – – – – –
b92bc0a6-9993-5135-8d1c-b71e661dc224 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
8f1bf357-c2b1-5e08-8b59-9cefb5bc2469 | note | – – – – – – – – –
08eb87f1-b3fd-500d-8d7a-b651ae30dff0 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
e259b134-da3a-5105-95d5-4880d19957ab | note | – – – – – – – – –
fc8810e8-537f-56a4-b3e6-db1ac69d85db | note | INSPECTION/TEST METHOD: Visual Inspection
764730c3-c3b6-55ea-8bf6-86a2a5fa672d | note | – – – – – – – – –
dbd0cbe9-2625-57c5-9189-ab272076e778 | note | RECORD OF CONFORMITY: This ITP signed
d8f13ad2-7e54-592e-8661-3df9c2b519f1 | note | – – – – – – – – –
001a64b6-a1d8-5779-b03f-23c4a6aa5e51 | note | HP*
1c9ce619-25e3-5bda-9fa9-4aad509f6281 | note | – – – – – – – – –
2cb675ce-dcd1-58e3-977b-8778e7a1eed8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
31b69d4a-6ecf-5fab-b75b-8c789af30a36 | note | – – – – – – – – –
f30115ea-0347-563d-b240-b9d14c351b1b | textbox | DATE:
12000731-0940-4642-a714-09a90a46c876 | checkpoint | 1.3 Flora & Fauna
751a4507-09a8-5d6f-b469-668ab7ecf5cc | note | FREQUENCY: Prior to commencing clearing
01d1e9ac-3a4b-5c92-80dd-22088218a16d | note | – – – – – – – – –
bf11dd2c-30ad-533e-8294-6bb0eaea5f0f | note | ACCEPTANCE CRITERIA: A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
0a95ae53-8388-56f3-a690-9debc7401015 | note | – – – – – – – – –
338b8cc5-7971-551c-b806-36d0b1ed7d71 | note | REFERENCE DOCUMENTS: EMP, ECP
7de4000d-3c8e-58ab-8ce4-b724b9ebf686 | note | – – – – – – – – –
3e9de13a-258a-55b5-88e6-312895651758 | note | INSPECTION/TEST METHOD: Visual Inspection
b3fb69a3-a124-5e56-8cfe-b7ba72862920 | note | – – – – – – – – –
0bbac84f-8def-50d8-980e-daddb542569f | note | RECORD OF CONFORMITY: This ITP Signed off
63d4cc05-58fb-5bcc-abc5-360756fb166e | note | – – – – – – – – –
4e0d30dd-641e-5e5f-b1fa-20163ac09663 | note | IP
fc1cdf62-09f5-5057-8485-68c69be0c545 | note | – – – – – – – – –
6d7d6c1a-7cce-5a60-bbbf-d912b09d2f70 | note | RESPONSIBILITY: Site Engineer / Site Foreman
1e4a3e19-728a-5fed-8366-aea7a007f8ea | note | – – – – – – – – –
a7486b63-c5fa-578e-8c60-f366b3460bc0 | textbox | DATE:
93fb3c2f-ce4a-477f-b513-f3e5bef63ed1 | checkpoint | 1.4 Permit to distrurb flora & fauna
25e72b6e-b3a2-5879-ba45-27f0f635841a | note | FREQUENCY: Prior to commencing clearing
d8b26a07-13d6-5f5d-82a9-b2bfdff50a41 | note | – – – – – – – – –
8eefd7b8-e81a-528f-8a4d-4467f8b0a6c4 | note | ACCEPTANCE CRITERIA: MRPA has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
e612aaa3-b64d-5ece-8b8b-a6bbbb62e47d | note | – – – – – – – – –
f1d6ecbf-4f99-517e-836d-e69d721b286d | note | REFERENCE DOCUMENTS: EMP, ECP
7550b470-c3d0-5f0f-a87f-7ed91b2e96a0 | note | – – – – – – – – –
281ea013-b6b0-5458-bff7-27b691b1fa83 | note | INSPECTION/TEST METHOD: Visual Inspection
271a2bd9-c3c2-5642-8244-7cd1b65b1a5a | note | – – – – – – – – –
cc7789a3-e786-5635-bcca-225cb9caa916 | note | RECORD OF CONFORMITY: This ITP Signed off
9e525d43-8aa1-572d-bed5-de8b8cc29fc8 | note | – – – – – – – – –
3341d8c9-dc01-56f2-9e06-5328d9d1b705 | note | IP
2cd9525d-4ca1-5aeb-b5d9-96cebdee56cf | note | – – – – – – – – –
b1baabaa-5a6e-52a6-bb1e-f81d2df948f0 | note | RESPONSIBILITY: Project Engineer
b850d379-72d3-5720-99c6-05963751f118 | note | – – – – – – – – –
6c656bb8-3e10-511d-8364-1f225979167f | textbox | DATE:
9b4e55e8-9db6-4a30-acb2-acec7ee03724 | section | 2 - Clear & Grub
11f21b79-5d9d-4434-962c-46b01c3226f8 | checkpoint | 2.1 Define work area
9ed3ed3b-8a65-5bbb-ae5f-aa70529b956a | note | FREQUENCY: Prior to commencing clearing
e1a00a1a-3171-5904-b674-5c131f9c3793 | note | – – – – – – – – –
c881ea3c-6edf-52ec-8345-95f029a9d897 | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
1601715c-b3d2-544e-ae13-21894dee7771 | note | – – – – – – – – –
e1cfe4c3-c44e-5e80-a9a1-49cdba9aebf8 | note | REFERENCE DOCUMENTS: 201.03
5a4795cf-856f-5f46-b86b-5e30e59052c5 | note | – – – – – – – – –
80cad0b8-8db8-52f2-9a49-2e32530ef343 | note | INSPECTION/TEST METHOD: Inspect
d756d229-797c-54b2-b17c-09a1564d334c | note | – – – – – – – – –
0bdbc982-d1fd-5669-b32f-cd4569f2bc3c | note | RECORD OF CONFORMITY: This ITP Signed off
185efeb4-ba5b-54c9-8650-b8b65baa94bd | note | – – – – – – – – –
460e19a1-4c4b-5fb7-9f1c-92058cd06a6b | note | WP
054ceee9-967f-57cd-a00e-20700bed7fc1 | note | – – – – – – – – –
be7fa55c-d394-5157-9684-f12028878cb9 | note | RESPONSIBILITY: Project Engineer/ Superintendent
f6ce5360-185f-5614-8126-823f1dd8ff60 | note | – – – – – – – – –
35e7d0ce-ec1b-55f9-b959-5d7be48da89f | textbox | DATE:
b255148f-c197-40f0-ac0d-f958d9fc8e66 | checkpoint | 2.2 Joint Inspection to Mark vegetation or habitat to be removed
0d943b94-53b0-5cd5-a968-57ad8528adc7 | note | FREQUENCY: Prior to commencing clearing
6152291b-d316-526b-a351-b1eaeca877df | note | – – – – – – – – –
c3955192-f2df-5a1c-b5bc-31243fd9aec8 | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent to confirm and clearly identify and mark trees to be removed, consistent with Appendix O Tree Assessment Report.
a6f26ba7-ae10-544a-9039-82339ed39fc2 | note | – – – – – – – – –
65b602fc-70bc-5e1c-ba6d-0fa35431b07e | note | REFERENCE DOCUMENTS: Drawings 201.10
ca4f7b91-f662-5551-81a0-dcb92efa8aa2 | note | – – – – – – – – –
a7f5eeab-debb-5a0b-8cad-843b20915375 | note | INSPECTION/TEST METHOD: Visual Inspection
7bc754ef-fa51-5b03-a343-6d7da2552baa | note | – – – – – – – – –
9fbc7c4c-b6ac-5676-aade-464608621e20 | note | RECORD OF CONFORMITY: This ITP Signed off
86435fbc-6849-5550-93d7-b4bd5e7d3cd3 | note | – – – – – – – – –
4516dc5d-936e-5116-acd2-c54f5add8543 | note | HP
2d94bb62-6865-5184-8343-af99bf05b89e | note | – – – – – – – – –
347c7647-c27f-563d-a9f2-aadf2a0707d7 | note | RESPONSIBILITY: Project Engineer/ Superintendent
3ad58c1c-0b7d-5c93-85a2-01f95575d999 | note | – – – – – – – – –
19d36c41-4d69-5d77-b8eb-f75dda87d9a5 | textbox | DATE:
26010539-0e24-45fb-b50e-afd2086ccf98 | signoff | AUTHORITY HOLDPOINT
bad90f2d-cfdb-468b-a5c7-e0f34b7c28d9 | checkpoint | 2.3 Identify No-go Zones
143ea1b6-7ee6-509c-a798-6d4475e1df91 | note | FREQUENCY: Prior to commencing clearing
89000ed6-b0c4-598a-beac-5d4aa203ffc8 | note | – – – – – – – – –
22d3b077-9da1-5a57-95a6-8ff8d1b1f9f2 | note | ACCEPTANCE CRITERIA: Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing.
1853b644-9cf8-5dec-a1f7-86d6f1e1c821 | note | • Signage shall be erected outside the limit of the of the vegetation or the habitat site, at intervals no less than 20 metres apart or as per the SSEMP
7e2da812-d0a7-5f52-a9a5-e1b512a6d882 | note | • Prior to any work onsite the contractor shall fence and sign all no go zone sites as per the EMP.
aa19df41-efd1-5abf-9a48-3324359e0a73 | note | • Any works required inside TPZ shall be completed under the supervision of an Arborist
1e47b39e-65aa-5a0b-b287-1c393cd9c578 | note | – – – – – – – – –
43d1f34a-5e07-524a-b895-df0558da9c04 | note | REFERENCE DOCUMENTS: Drawings 201.10
aeeb6fa4-a44c-5d9f-9ecd-62e844947a63 | note | – – – – – – – – –
af82a7b8-f34e-58ee-b236-2097261b0f33 | note | INSPECTION/TEST METHOD: Visual Inspection
3031c5e8-137a-5ba5-8eb6-88ad658c3f92 | note | – – – – – – – – –
38ace839-c42c-5ef0-9ec7-9a3221f64a02 | note | RECORD OF CONFORMITY: This ITP Signed off
d6af50ae-0c83-5e1c-9d5c-430fbd1b8f90 | note | – – – – – – – – –
0bef3e61-ab7b-55d5-8655-732d3f439910 | note | HP
6091a22f-3380-5ba2-9132-f72a506d832c | note | – – – – – – – – –
90d97e82-6575-52e0-ad8f-6fdfdd704a64 | note | RESPONSIBILITY: Project Engineer/ Superintendent
42d23c91-3002-5711-9f07-311b20b13ef8 | note | – – – – – – – – –
58a55d3c-2122-5a84-9486-df7596abcbf9 | textbox | DATE:
876fcf1b-b5a4-48aa-811d-d0ee41246053 | signoff | AUTHORITY HOLDPOINT
2e95ab62-f165-46ff-9cc4-6aee6ced7d80 | checkpoint | 2.4 Clear felling distances of trees are adequate.
2cca8de8-2709-5bcd-addf-0208f8e86dd7 | note | FREQUENCY: Prior to commencing clearing
75a0424c-c3b5-5a1b-a23f-ac22bfc67938 | note | – – – – – – – – –
0139f76a-6950-531c-b093-7c6885b60ae6 | note | ACCEPTANCE CRITERIA: Ensure the clear distances are adequate and signage is inplace as planned. Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
4f6c28a5-45ad-52f5-99fa-325fef38a6d6 | note | – – – – – – – – –
1fd1282c-47e7-50f3-b57f-9ac451ee8f95 | note | REFERENCE DOCUMENTS: 201.04
61aef769-0bd5-5cad-ab1f-39e0ff0457f6 | note | – – – – – – – – –
6b60750a-90f4-5f09-baae-53d78ae02995 | note | INSPECTION/TEST METHOD: Visual Inspection
25cd2178-11d9-5250-8598-a8cc9ea15a32 | note | – – – – – – – – –
89f9438a-2518-543a-9c74-e9187d8216d8 | note | RECORD OF CONFORMITY: This ITP Signed off
45b43b96-8b44-55f2-a33e-cadb0cf092d0 | note | – – – – – – – – –
6a942206-e8ec-5c0a-90e4-0257599229d0 | note | IP
529de333-2b96-5340-9c7d-eebc4e3179dd | note | – – – – – – – – –
b9341aab-1618-5eb2-b9e4-ef8a524ff653 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c5774739-e2ca-57f4-87d1-88948a88f1e6 | note | – – – – – – – – –
5a702f82-1d4b-5bd5-94dd-a64ab31784db | textbox | DATE:
77502b3e-ffe9-4362-b68e-5d0a91c77b44 | checkpoint | 2.5 Clear and grub trees and vegetation
336ab5ff-475a-5629-9a25-ef0e19adfdf2 | note | FREQUENCY: After clearing
83cc3712-e8d2-56fd-9c04-440ba12d2507 | note | – – – – – – – – –
c4fdea82-cff4-5c94-b934-87fbe65a2b46 | note | ACCEPTANCE CRITERIA: Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level
8a681883-37c0-5068-bfc8-e468f837585e | note | • Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
c2ad1d6d-9b31-5c74-9765-3ff35697ac5b | note | – – – – – – – – –
3f281082-2131-50b3-8302-22d174ea807c | note | REFERENCE DOCUMENTS: 201.04, 201.05, 201.06
8af60a35-c258-57d7-b5bb-b1362d9199c9 | note | – – – – – – – – –
eb68580e-2a94-5746-a8d4-a17b7fbe7f9e | note | INSPECTION/TEST METHOD: Visual Inspection
9c9481cc-3c5e-5651-a2d4-bbdf4287ab2f | note | – – – – – – – – –
f602f990-08d3-53d1-aca7-8f8289e17c0d | note | RECORD OF CONFORMITY: This ITP Signed off
9aab7197-ee1b-5a37-a97b-8262077191c7 | note | – – – – – – – – –
b3db9ffa-1ac5-5cf9-a3be-67c07ba9e75e | note | IP
db14b33f-4608-5538-932a-500b1761883f | note | – – – – – – – – –
4adc3f6f-8765-5ee0-93bc-f383b88277d0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
cb900f33-60d7-57b1-a4cd-84711fd04a60 | note | – – – – – – – – –
0556e71e-c703-5814-8991-ae9435b80e8a | textbox | DATE:
7518fa77-d771-4fb4-a887-26df387bb2a7 | checkpoint | 2.6 Backfill holes
de2e72ba-f0cf-52bc-a382-cb0f68144041 | note | FREQUENCY: After clearing
a18dd509-3df2-5f74-bf34-54b9b2cdba8f | note | – – – – – – – – –
c7293d85-593f-5eee-accb-2a039cac0422 | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material to the sorrounding material and compacted to the same degree to the sorrounding material.
19e5e9f5-a936-5150-9d04-8d611ecbd106 | note | – – – – – – – – –
97bf45b1-a2dd-51aa-985e-83050ef6f55e | note | REFERENCE DOCUMENTS: 201.05
39b45a35-f8a0-5108-83e3-3b7589414de5 | note | – – – – – – – – –
9a6f1b90-06cb-57ad-b67f-d5b38d540459 | note | INSPECTION/TEST METHOD: Visual Inspection
2f703398-80a9-5c43-9291-86e0fde779db | note | – – – – – – – – –
0eca8b64-d84f-5619-a564-59caa62cc17c | note | RECORD OF CONFORMITY: This ITP Signed off
86998011-a3a6-5679-852b-ca4f30550cbf | note | – – – – – – – – –
cb82b229-8236-51e9-b2aa-2dba61623116 | note | IP
ba6592ab-816d-57dc-bf04-8a17c84081be | note | – – – – – – – – –
c58f7cf4-93b5-580e-b752-4e78789bffc6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
e4845189-2256-5587-9029-c6ebb6d9330b | note | – – – – – – – – –
7da7683b-e0ec-5cb4-aa79-edad0a100fa6 | textbox | DATE:
c9a31d02-29a4-4ff1-b997-be292c2c13f8 | checkpoint | 2.7 Dispose of Trees and vegetation
6cfbade4-4f60-5d34-84e9-9faff42244e4 | note | FREQUENCY: After clearing
618a3da8-65ea-5048-a79d-43d7b65c7bc6 | note | – – – – – – – – –
21fc9df9-fd3f-5c60-8b39-3368e5947003 | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
bc629063-4cdd-568e-a102-d7f6d1cf7fe4 | note | • Noxious weeds shall not be mulched.
ec790847-bb29-508c-ac85-ce8491ebc79f | note | – – – – – – – – –
6506ff5c-6d13-5d94-8bcb-a637506c1262 | note | REFERENCE DOCUMENTS: 201.07
171180cd-92a1-5807-85d3-ee1e05525951 | note | – – – – – – – – –
1e57c38d-f6e6-5826-b990-fc6431f27fc1 | note | INSPECTION/TEST METHOD: Visual Inspection
eed09962-0bab-50b9-b240-9214aecc755a | note | – – – – – – – – –
e5a56c3f-7cd9-5159-a994-7b2692a831af | note | RECORD OF CONFORMITY: This ITP Signed off
da79d145-ddbe-59ac-a314-1d1fdc9ec87b | note | – – – – – – – – –
4924d4d0-4411-58ee-89ec-2cbae9254a03 | note | IP
8aa8be68-8ce1-52d0-a549-5b0c39fd286f | note | – – – – – – – – –
eae6f1bb-907a-539a-b08f-f1645b895650 | note | RESPONSIBILITY: Site Engineer / Site Foreman
27045c5b-5ec5-5415-86c8-120bc413ceaa | note | – – – – – – – – –
41a58957-2fb5-5aab-b6d3-0818821dec4f | textbox | DATE:
c593b093-df4c-4bae-8d70-a440dedcf9dd | checkpoint | 2.8 Dispose of concrete, bituminous and other recyclable materials.
f2e1bc67-dd0f-5006-9edc-716e3bb862ba | note | FREQUENCY: After clearing
abe6ecc4-401f-5397-b41f-fdbd387f6763 | note | – – – – – – – – –
065f4676-5fba-5b90-bc34-83da07ead8ca | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
212f83b7-8fdd-57d2-be8f-56a723a1f47b | note | – – – – – – – – –
fad89740-36bd-596c-969f-2414a83a3741 | note | REFERENCE DOCUMENTS: 201.07
895393ff-4dd7-5437-89a7-96b83dd81114 | note | – – – – – – – – –
9e8f2b02-f9d6-58ea-ace9-af459c339595 | note | INSPECTION/TEST METHOD: Visual Inspection
9b9440e3-d4bc-57e2-8e6d-74b1b6d9ab14 | note | – – – – – – – – –
43446636-86a3-543e-9a91-c7c702ea41c6 | note | RECORD OF CONFORMITY: This ITP Signed off
048b9b23-debf-5a68-bddd-ca71fd02e2eb | note | – – – – – – – – –
0e54203a-65b1-51c1-b029-d6caf85d6174 | note | IP
cdc3665a-f8cf-5ddf-a8c1-3d5068a4605a | note | – – – – – – – – –
d086f342-659c-56a6-95d6-bcc219e13c86 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c2011e36-927e-5e63-a7e4-19be5f141815 | note | – – – – – – – – –
613e1b20-d5c2-5851-a1fa-348ce5538c18 | textbox | DATE:
7225dbae-6537-4eb3-95ca-e0723a277510 | checkpoint | Final Inspection
a60cb05c-cae3-5325-a94c-c4cbf755ddd4 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fa47f71b-eb28-5f2d-8193-f13984ae029d | textbox | Print Name:
b1a1fce5-a4b3-50e5-9742-01cf394174e5 | textbox | Position:
b3f8d783-9a63-5356-8747-94d6fd38b7e0 | textbox | Date:
ac504198-101b-44f9-ae4b-7aef708d377e | checklist | FHC-ITP-003 - Subgrade Preparation Rev1 | itp | FHC-ITP-003 - Subgrade Preparation Rev1
38d83b7a-5627-4554-97c9-f917fdc42324 | section | 1 - Preliminary Works
b4ffbbdc-5e67-4fc4-b68a-ee060ef67b3f | checkpoint | 1.1 Check for correct documentation
1824078b-d9d4-5522-b29a-d2cd46092662 | note | FREQUENCY: Prior to commencing any activity
04d07202-1e69-5fd7-978a-8810ed26bf49 | note | – – – – – – – – –
fa0c6d31-4ace-5a98-b4b6-02a650405222 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
adcf9285-329a-5585-9af0-c59ab6607732 | note | – using the correct and complete set of drawings
1175710d-dba0-567b-9380-8ab088bbd18c | note | – all drawings are the latest revision
fdd590e2-e92f-5717-b7f0-47d5077fe8b1 | note | – – – – – – – – –
7d745fa6-6ef3-58a0-928c-3e68053f554a | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8498a099-602a-5f46-b23e-693e4d6b984a | note | – – – – – – – – –
a0a75aff-c44d-581c-b079-f8ac75b1180a | note | INSPECTION/TEST METHOD: Visual inspection
ec24fcc5-78a5-5cac-99b1-e0e4795df706 | note | – – – – – – – – –
7060298d-27ae-50cc-92fa-01a8c60e670a | note | RECORD OF CONFORMITY: This ITP signed off
84f010f7-ea71-51e8-8152-cb9c2ad483d7 | note | – – – – – – – – –
abaf86b0-606f-5fa8-867d-8625815bc46c | note | HP*
033cdabb-5060-5ced-93a2-be61531b035e | note | – – – – – – – – –
9adc2b29-1629-52df-b02a-021d11d20acf | note | RESPONSIBILITY: Site Engineer / Site Foreman
644842e5-45a1-5fd6-a991-dfd32ebf3992 | note | – – – – – – – – –
f1115986-27f9-5e82-9d17-e24ec6ae0cc7 | textbox | DATE:
48b2bce0-dcee-4f30-a32a-c0cee224d2e6 | checkpoint | 1.2 Implementation of all measures and controls
fdf7803f-1041-59bb-acb2-c15274360d92 | note | FREQUENCY: Prior to commencing any activity
dbc98cfd-7392-5f6a-8b53-577868aea875 | note | – – – – – – – – –
f622a023-e0cc-58d2-893e-806c39dfa868 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
3b06efba-963f-52f5-9b97-e304e9fcc591 | note | – – – – – – – – –
60ffb8c5-3bd1-59ba-8d8c-9dd627612a9a | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
3a2daab8-3b86-541b-b73d-27d11acbccca | note | – – – – – – – – –
703c32ef-44cf-5249-98fb-d9a88e4621fe | note | INSPECTION/TEST METHOD: Visual Inspection
adbdc851-ac55-5bea-95a1-7c4e90a52d30 | note | – – – – – – – – –
762d6637-c14d-5558-97c9-d40478f0a64d | note | RECORD OF CONFORMITY: This ITP signed off
89e3ed32-f441-53d9-b119-b1af8944746c | note | – – – – – – – – –
fd76dae2-4884-5568-938d-645286bec4b2 | note | HP*
1a4527f7-8a02-556e-9983-6ecd99a7b749 | note | – – – – – – – – –
1d03b69f-ad85-59f6-97c2-417d6cec4fd6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
1ab86946-8ce5-5500-afe9-ab00e96da746 | note | – – – – – – – – –
2b8c3386-873d-5c77-adac-4a2777913d66 | textbox | DATE:
dbf93825-4572-416d-a348-6e54ecfe1018 | section | 2 - Construction Works
57908879-16f5-4a67-8a02-273c59e15489 | checkpoint | 2.1 Survey Set-Out
cad83506-6c3c-5fae-82bd-fdfa7c1d2e6d | note | FREQUENCY: Prior to commencement of excavation
39ba6dfa-cf2d-5051-8c93-7671af98604d | note | – – – – – – – – –
fd6b5567-365a-5ab8-923e-e79f4be2bc80 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
01799a38-7cc3-5abc-9705-5d63ebe115da | note | – – – – – – – – –
5c4a6938-1655-5056-9da5-5c892dea6a46 | note | REFERENCE DOCUMENTS: Drawings, Work Procedure
6b85ba2d-612f-5c6d-8c01-b9ae69ac8c87 | note | – – – – – – – – –
4064b0b2-86fe-55d7-9ece-46aea8bd0349 | note | INSPECTION/TEST METHOD: Verify
1cb307cf-df09-56fc-9cdc-859683690c6f | note | – – – – – – – – –
e57ba0b5-3f83-55fd-b720-b8dff8e4ebb2 | note | RECORD OF CONFORMITY: This ITP signed
70f040e6-9625-53eb-b7f2-00353ab666d4 | note | – – – – – – – – –
8dca69ea-439a-5a9f-b4bc-41ab49f02cc0 | note | IP
fe144d3a-4533-5ce5-bcba-0d11bca9d5d4 | note | – – – – – – – – –
f5d5dbb6-16f0-59eb-9732-9509d3da05f8 | note | RESPONSIBILITY: Site Engineer/ Surveyor
e9b2349b-0b9e-5d3f-8847-f3efdb51008d | note | – – – – – – – – –
20dbe163-376f-5d80-a445-ffb163fe531b | textbox | DATE:
c7c77f2f-e8b6-4bf9-bbdb-15e22e2d60ad | checkpoint | 2.2 Excavation Permit
9d89f5b1-540a-5c39-a5f3-a3ee94254ca6 | note | FREQUENCY: Each lot
c5e04f90-50d6-5d00-a67a-1dc72d1157ce | note | – – – – – – – – –
1450753a-eed6-53b5-a782-15451be3a8a0 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
260a3988-166f-5403-b75e-73f24cbe4ee1 | note | • Plant and equipment shall be appropriate for the task.
a9f89916-bd69-52ca-896c-948662c9fec4 | note | • Excavation operations shall not disturb areas outside the limit of excavation
544e7578-423a-556e-a669-d9601fbbd0c7 | note | – – – – – – – – –
bb27ad79-9d98-54aa-bfb5-6f46f00bae23 | note | REFERENCE DOCUMENTS: Excavation permit
980401f5-1851-5f8a-87bf-68cb91d08eb2 | note | – – – – – – – – –
32cdd57a-e9a2-533b-90aa-c732a12c558f | note | INSPECTION/TEST METHOD: Verify
71b5f394-5ae4-540a-b590-492e9bfc3d9b | note | – – – – – – – – –
d90f40a6-574e-53e3-87de-b19d540d7fb4 | note | RECORD OF CONFORMITY: This ITP Signed Off
3203d34a-9894-52fa-93cd-851c8ecb7785 | note | – – – – – – – – –
773ea7a9-744f-562b-a13a-4f11b1474af2 | note | HP*
9abe418d-87f4-5c12-b677-50d70290ed87 | note | – – – – – – – – –
1b710d61-cea5-5304-af33-a61dbaa460b4 | note | RESPONSIBILITY: Site Engineer
154a02f8-35e8-59cb-b314-66f7de553a42 | note | – – – – – – – – –
dccaf880-b51a-577e-aa23-eab89812d7ac | textbox | DATE:
b6e14ac0-9fec-4b0c-8b20-6cdf0bc829c5 | checkpoint | 2.3 Subgrade Material Properties
d4e371c3-c308-5b10-b537-0c192168dfe5 | note | FREQUENCY: Each Lot
ba89f1d5-047a-5bb2-990a-2d67e23417fc | note | – – – – – – – – –
fd95cda4-38f9-5252-ba07-faba0cd02dbb | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
80ac9cf9-a800-522d-a759-506dd6a979ed | note | • If parameter met rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
f1445599-8d32-5b81-8834-e8fe7b5db2a8 | note | – – – – – – – – –
a57d57dd-2bba-59eb-b252-8162ed2bf233 | note | REFERENCE DOCUMENTS: 204.06 (e)
dfb0227d-2cb3-5cc1-85da-0457b26f0e24 | note | – – – – – – – – –
3990a869-8f1f-53f7-9381-3577c62f2530 | note | INSPECTION/TEST METHOD: Test Point
f4364361-08f1-5ec8-a93d-e9ba39388beb | note | – – – – – – – – –
e545a99f-9959-5e4b-a698-91f6f352ec2a | note | RECORD OF CONFORMITY: Test Reports
3ba44e5d-b555-5f8f-90f0-a979d42360da | note | – – – – – – – – –
658d720e-2cc6-5a91-9172-5c45e20ed9c4 | note | TP
0263ff3e-5198-5ffb-99a6-e2f2a0847924 | note | – – – – – – – – –
4c620043-6760-534c-97a1-263295a55531 | note | RESPONSIBILITY: Site Engineer
9639cf83-9862-5a77-a036-e381091a368e | note | – – – – – – – – –
0969ed68-ba7e-5def-a176-b19d910e4b22 | textbox | DATE:
62fdfa35-6c85-4495-a764-16d823f4b10a | checkpoint | 2.4 Inspection of Subgrade Material
2ee5b932-630f-5f2a-ada8-cf2304dd8815 | note | FREQUENCY: Each lot
3effeb7b-f94a-5a00-a116-3e6a23035473 | note | – – – – – – – – –
2efefdd3-eb95-5096-a778-69f1d59be508 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
b703a95d-50bd-5bb9-84d1-ac706d97bb68 | note | – – – – – – – – –
8ae47a8e-f517-519a-be0e-f7230efa9659 | note | REFERENCE DOCUMENTS: 204.06 (c)
b9db83b4-9957-5c4c-8e0c-c4784df48e2d | note | – – – – – – – – –
0e3e5f03-4e57-5cdb-bcad-61b01a34f6dc | note | INSPECTION/TEST METHOD: Verify
d35d15de-1fe4-53e4-8962-3f40f76521dd | note | – – – – – – – – –
0320b684-ea0a-5313-8aed-400a6e30f69c | note | RECORD OF CONFORMITY: This ITP Signed Off
bcf5ea5a-9a0e-59d6-b6a2-16f241013c92 | note | – – – – – – – – –
4c9c65a7-3531-5b24-9e55-4ce0856723b6 | note | HP
e715827d-d873-5f70-9abf-bff92ceab6f1 | note | – – – – – – – – –
d2ac115e-c167-5ebc-bb54-093d14a2737a | note | RESPONSIBILITY: Site Engineer/ Superintendent
ff5f7b8a-6cbd-55a4-8a7f-5d990f439b03 | note | – – – – – – – – –
09e4ead3-09e6-5d9f-9064-3b9b13a41677 | textbox | DATE:
9314a548-e424-448f-a1dc-40b6d16852f1 | signoff | AUTHORITY HOLDPOINT
6829693d-88a2-43bb-ab52-1a3411b83eab | checkpoint | 2.6 Acceptance of Rock Subgrade (when applicable)
ffe0f3b0-da82-541d-9c7a-4666a62e9dbb | note | FREQUENCY: Prior construction of the regulating layer
ccc57c1b-302f-5cba-b58c-d447f5af2553 | note | – – – – – – – – –
f5fef11f-5eb6-502e-a7f4-f3c7b8bbc0c7 | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
6c1fd408-a320-55cc-8606-03adef1efbe9 | note | • Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
2c5f5c8e-5fe3-5d44-a2e3-e0393f583a5c | note | – – – – – – – – –
f5dab8b5-9e8c-5b81-8d1b-83b5de261392 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
debea36d-c06c-51ce-b9e3-2ca2e3ee8496 | note | – – – – – – – – –
90459e09-3b4b-54e8-829d-2c18f5c29038 | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
315d4cbc-a848-56b1-aaf5-bcdfd38a43fe | note | – – – – – – – – –
81fda7a1-654d-5933-8f44-92799b5d3b19 | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
16886e72-5da2-58e6-96a0-47caf0a511bc | note | – – – – – – – – –
e2ece250-700c-5a70-9652-e1f317b40c62 | note | HP
1064024e-8e30-5a5f-8ca3-3f0503b73a21 | note | – – – – – – – – –
3f702e00-5e9d-50f0-81c4-cb1bc439b822 | note | RESPONSIBILITY: Site Engineer/ Superintendent
5da559d2-ced2-5ae4-9c2f-8dbc3cb1414b | note | – – – – – – – – –
cb927843-4cfc-5e78-9cd1-e9cdd4fbb584 | textbox | DATE:
20a6d157-766f-4530-81cc-7293fd24b39e | signoff | AUTHORITY HOLDPOINT
7445fb3a-791f-4a1f-9ed5-76ba89eba841 | checkpoint | 2.7 Unsuitable Material
a9eda42b-b221-5e62-99dd-e24198fcea1c | note | FREQUENCY: Each Lot
ae14c1bc-67cf-5c30-bd0e-8746f43ac1e8 | note | – – – – – – – – –
f38ea9c5-9a94-5722-8f19-5126c11ecea1 | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
9d5063b7-04fd-57c8-b08f-8c358ba8cae3 | note | – – – – – – – – –
c0f3b01d-59b4-5065-bd37-150685745efc | note | REFERENCE DOCUMENTS: 204.07 (d)
dc4a0a6f-41da-528e-bfb3-b3b76bb80afe | note | – – – – – – – – –
8999e0e6-38b1-59aa-a6de-4a4a3d1db52d | note | INSPECTION/TEST METHOD: Visual Inspection
ebc96313-c8f8-5ac7-9536-37eb0e06c718 | note | – – – – – – – – –
a25ff275-81f5-5d86-98d8-318d31c10531 | note | RECORD OF CONFORMITY: This ITP Signed Off
dd524304-9249-5e58-aba1-4ddb37ccde49 | note | – – – – – – – – –
b240bd7b-0d55-5152-a356-7a2efebe706b | note | HP
a6a44c34-8f54-5fb7-bc52-dba9c643d0d2 | note | – – – – – – – – –
a2b59c3a-850e-5eed-87b8-564a983438bc | note | RESPONSIBILITY: Site Engineer/ Superintendent
71d54fdf-ab9e-56ca-91f9-b37d25fbea83 | note | – – – – – – – – –
a1068af9-3b1b-56a7-9ffa-3a1805edcb50 | textbox | DATE:
9a3a5044-1bab-4826-b2eb-37200df5be08 | signoff | AUTHORITY HOLDPOINT
5cbf7750-3067-496b-8289-04a5073ef71c | checkpoint | 2.8 Groundwater
1c8f3b7e-54c4-55cb-a30f-079a2f3937cb | note | FREQUENCY: Each Lot
31a5cf6c-614e-53bf-ab38-ae9376c73cc6 | note | – – – – – – – – –
f4ca8451-d6cd-5ef5-aaa2-1a4fc8e66c3d | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
1e1e2a02-5325-5d6e-8c25-78b2edfdcd27 | note | • The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
febe3955-199c-5743-b283-fa1c31a176fb | note | – – – – – – – – –
e1b21896-ca1b-5bad-ab5f-a26d92e1349b | note | REFERENCE DOCUMENTS: 204.06 (h)
2eb009d7-e279-5dbc-98fd-5bea1abba497 | note | – – – – – – – – –
961a9a12-8d98-52b8-a581-bea26fc5b10b | note | INSPECTION/TEST METHOD: Visual inspection
185640f7-9981-536f-87b0-2f9b08b7d019 | note | – – – – – – – – –
be9a7e3e-236a-51a5-a920-74fd431ac46b | note | RECORD OF CONFORMITY: This ITP signed off
0ac85dbd-040b-555a-af3f-444ff909f807 | note | – – – – – – – – –
e57ebf13-eae8-5576-b0f9-83ba31211948 | note | HP
3e5cfd2d-4c3b-5d4e-964b-9f53459f5350 | note | – – – – – – – – –
4bed11bb-1564-59c8-a58b-91640e3117d8 | note | RESPONSIBILITY: Site Engineer/ Superintendent
e5882e28-df21-55a1-adb1-747342dddc78 | note | – – – – – – – – –
27d4a5ad-8114-564e-8371-fe551be95fd0 | textbox | DATE:
33c6c385-f0a1-4d6d-a4aa-f4831dcf428c | signoff | AUTHORITY HOLDPOINT
714ef4cc-fff2-4741-96ed-8fa383c460b1 | checkpoint | 2.9 Trimming and Level conformity
55da1024-afc6-540a-80ba-890378c2fd83 | note | FREQUENCY: Each Lot
3feb4d3c-02c2-578c-8d6d-91d3a9e1bd5f | note | – – – – – – – – –
0eb143c6-645b-58c9-9f02-b4c15ab4662f | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2.
f07b8baf-3787-5b97-936f-fc52747ea756 | note | ○ Level tolerances:
881daeb5-2263-508f-874a-55515cc4e6e9 | note | • Range x = +15, -30mm
5a607f5c-5d1e-55ee-8cc7-9086891ee594 | note | • Max S = 12 mm
3f7dadb3-a190-5acd-80c2-42a9008b5716 | note | • 40 measurements per lot (Scale B)
775d3a78-e05f-53fc-8611-739078ce2ce9 | note | – – – – – – – – –
b05c0e71-2e92-5be7-b86b-184ad8a955ac | note | REFERENCE DOCUMENTS: 204.03(f)(g)(h)
8c42af4f-1063-5615-a67b-b0ebb67cabc6 | note | – – – – – – – – –
b8ff3733-2a27-501b-bcc4-466780bc341d | note | INSPECTION/TEST METHOD: Survey Report
78b87a71-1e49-55c0-8d24-2e7807ede393 | note | – – – – – – – – –
f8032fa7-ed26-5d24-93a2-457fbbe0c84e | note | RECORD OF CONFORMITY: Survey Record
0cbc3e09-1183-5f65-bb2b-20e295bc93a3 | note | – – – – – – – – –
df8940c7-4ee6-5595-9da8-25570b8a311b | note | SCP
a903749f-0ee8-5bdc-91f9-74735d6bdaa5 | note | – – – – – – – – –
0217ed07-5f98-5735-a7fa-ca5f120e1df2 | note | RESPONSIBILITY: Site Engineer/ Surveyor
78949d3d-0adf-5e2c-96bf-4a80dc4d6b67 | note | – – – – – – – – –
22d3a343-fcfd-54ef-b839-5997f8a28031 | textbox | DATE:
bcf528c3-ec1e-45de-ba85-6532c400ecdb | section | 3 - Testing
6eb745c5-0e3a-451c-957c-23cc92432db3 | checkpoint | 3.1 Proof Rolling
bad23527-7c24-5c44-8b4c-92e761063438 | note | FREQUENCY: Each Lot
1a06064e-064a-59e0-96a6-5b99c09dcbf3 | note | – – – – – – – – –
a5bf020d-de55-5197-9d80-5d4ad1a1359f | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
20b9533e-7577-52e1-a4ce-0ee753f88459 | note | – – – – – – – – –
45fd86d2-d367-5abd-ba79-cebd384bc024 | note | REFERENCE DOCUMENTS: Section 173
463d7b5e-8f5b-589b-9839-88ee705e7fdb | note | – – – – – – – – –
3da7c788-fee4-5f3f-8651-2dbddf7af2b3 | note | INSPECTION/TEST METHOD: Visual Inspection
33fab8b9-1422-5d0a-afa7-c362601faf53 | note | – – – – – – – – –
08677ac2-a43b-57d4-8a24-0a8e251ef5e6 | note | RECORD OF CONFORMITY: This ITP signed off
78c35c4f-36a3-5e7f-81eb-1af634cc8b4b | note | – – – – – – – – –
43369f58-3bf5-5493-a220-4cab5038b23c | note | HP*, WP
c45082a5-c52d-5420-8233-5cbcc038aef3 | note | – – – – – – – – –
94b27b24-13d5-5f98-abaa-8666c127f85f | note | RESPONSIBILITY: Site Engineer/ Superintendent
b1dd475f-f1f5-5e08-9543-fbcc080b125a | note | – – – – – – – – –
0996d461-1246-5829-8db4-1ea8b6c0ae5b | textbox | DATE:
ad1e7384-bc7f-4acb-9bd3-4cfe7583237e | checkpoint | 3.2 Minimum Testing
d2a47a3e-576f-5617-a1be-3b0235668fa5 | note | FREQUENCY: Each Lot
93de0ce1-2c62-5d2a-9ce8-b9dee078b567 | note | – – – – – – – – –
0b3c7083-1d6c-59c7-b32a-3028b13fddcd | note | ACCEPTANCE CRITERIA: Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test. After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
6f14371c-44ab-5383-be35-db0177e1742c | note | – – – – – – – – –
fb805f6e-69c7-5a38-8e40-742f8fb42ab5 | note | REFERENCE DOCUMENTS: 204.14 c
1de16275-a328-5e25-a546-6d5f22af08d1 | note | – – – – – – – – –
992fde98-83fb-5f7c-80da-d6dd65910a3e | note | INSPECTION/TEST METHOD: Test Point
ff003c0b-0c95-5770-93f5-b185738f6609 | note | – – – – – – – – –
b55f345b-0e5c-53f0-b8b7-8cc97053dd62 | note | RECORD OF CONFORMITY: This ITP signed off
8eb499f5-a8e7-5e89-9855-cf99a9474445 | note | – – – – – – – – –
9f12190c-8678-5109-a856-1a3f6444f1b3 | note | HP*, WP
958649bf-dab1-56c0-aeb1-1065a6bf5925 | note | – – – – – – – – –
eef9e488-3a4b-5031-8372-5631a67af530 | note | RESPONSIBILITY: Site Engineer/ Superintendent
cf55e07f-b0bd-589a-acba-9d3157fd6be7 | note | – – – – – – – – –
689e67fc-d4c3-58b4-97ad-d4f5cc8e05ca | textbox | DATE:
055dd60b-e4e4-4eca-abaa-4a36763603f9 | checkpoint | 3.2 Compaction Testing
373982b5-b562-5a9e-bec7-f046a59389a1 | note | FREQUENCY: Each Lot
f93c2d69-12d8-5cad-a5a7-077f2eb72ce4 | note | – – – – – – – – –
25ec4d38-a99c-58a1-84db-e0c203a05b01 | note | ACCEPTANCE CRITERIA: Ripped and re-compacted material below Cut Floor Level = minimum compaction 98% SDD.
5f06ec57-6586-535c-b0a5-000ce0f3a76f | note | • Type B Material placed within 400 mm of top of Type B Material = minimum compaction 95% SDD.
e0ca82be-5df5-5257-80e0-b3a48f7a587e | note | • Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 95% SDD.
91f2c6cb-cf3e-57bf-b0d9-401dab3c927f | note | – – – – – – – – –
160877c0-3e15-53a2-9b6e-7ae23260f7db | note | REFERENCE DOCUMENTS: Table 204.131
0f137bca-e6b6-5ee3-8bba-8a945e013a95 | note | – – – – – – – – –
604036c0-a2c4-5ec3-a78d-b879c2a52303 | note | INSPECTION/TEST METHOD: Test Point
ec8b9677-a24e-57e4-9ff9-5c999a1a427c | note | – – – – – – – – –
ede519d4-9f5e-526c-82b7-551eb76e832f | note | RECORD OF CONFORMITY: Test Records, Lot Register
b1bc2480-3424-5aad-8438-12d155bf8973 | note | – – – – – – – – –
4ff8eef2-aad8-5571-bc92-cf80c805fa6b | note | TP
60b6bdcd-7e93-570a-b0c4-1934d87d8c83 | note | – – – – – – – – –
75518d21-98ac-5586-b0c6-c19c021ae035 | note | RESPONSIBILITY: Site Engineer
15e3b602-7bbc-5047-86a9-66174056f377 | note | – – – – – – – – –
f4250265-4b57-507c-8b8f-186cecde1808 | textbox | DATE:
35c5a817-9edd-4efc-affc-c9687977acd7 | checkpoint | 3.3 Compaction Testing (Small Lots)
81357b09-7d11-57a8-8a29-a337e70c3086 | note | FREQUENCY: Each Lot
454390ff-37c4-5652-ba10-e5e7d8f31f4a | note | – – – – – – – – –
636933af-3fea-5de2-8412-e1e85917a152 | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% SDD.
2ee610e2-1f06-5875-9259-c64690845892 | note | – – – – – – – – –
c8315f4c-fe02-5839-bc2c-65141169b645 | note | REFERENCE DOCUMENTS: 173.04 d
85599d07-70b7-5caa-b6c2-a8a7653e3db2 | note | – – – – – – – – –
844a3a5d-2e21-5c25-885a-556c28911c64 | note | INSPECTION/TEST METHOD: Test Point
50955e52-d602-5762-8400-687bc90464cb | note | – – – – – – – – –
3c16cec1-bec5-5e55-a765-15e2f07a754d | note | RECORD OF CONFORMITY: Test Records, Lot Register
37a4d476-7103-5857-a1f0-47b262df53a5 | note | – – – – – – – – –
6b003ce6-5a2a-55de-a090-340af8db02df | note | TP
772952d4-2ea8-54e8-be39-d9af1eaeecbe | note | – – – – – – – – –
7cdb3f47-8a96-5dac-983b-3ba30cf6a067 | note | RESPONSIBILITY: Site Engineer
8cca6124-f7e0-5de7-be5b-01756438e682 | note | – – – – – – – – –
3119aa78-10b3-52c5-92d8-e397abfb07b6 | textbox | DATE:
509bfc9f-ecbd-4ef8-b930-fe0a8382898c | checkpoint | Final Inspection
5201f771-0a78-5a8e-8eb6-19e1b66f494b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
219bb96d-99de-5819-b310-0cf57cd8e8e6 | textbox | Print Name:
1e6789db-9023-59a6-9d81-2b49dd4a4f33 | textbox | Position:
14e7936e-7494-5733-b229-7dbcddac418e | textbox | Date:
7908328e-0e2f-4736-80a4-b671ab3b92eb | checklist | FHC-ITP-004 - Type A Fill Placement Rev3 | itp | FHC-ITP-004 - Type A Fill Placement Rev3
431bf8ae-8b5e-4761-9953-7eddaae8a31a | section | 1 - Preliminary Works
11ba19c9-d5b2-4ed6-9660-b3d0396adfb2 | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
a5d984a3-055c-5c59-ad7e-dcc98ce305dd | note | FREQUENCY: Prior to commencing
b72a8410-09cc-5339-a486-f1d7212940b9 | note | – – – – – – – – –
d8b0a033-044a-5b5e-9dc9-7562538e2617 | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
65331b8a-63b1-5838-956c-636dc6a3903a | note | – – – – – – – – –
d8590672-aa25-588c-aa25-c1ee1067ba63 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
390a8059-8e40-553e-987d-0055551feba8 | note | – – – – – – – – –
545b32f7-887f-5405-86db-e1d2bda9568a | note | INSPECTION/TEST METHOD: Visual Inspection
ea397fb5-40d6-5b7a-9f92-82bbb1db4a58 | note | – – – – – – – – –
68efd504-d2f1-5d90-8731-a2dab91e52e3 | note | RECORD OF CONFORMITY: This ITP Signed Off
07c5d6d5-175e-5d2e-bd69-3a9da222d095 | note | – – – – – – – – –
6c5ea600-01d1-5531-9708-e0e0b6bce51f | note | HP*
aa24835f-a2e2-5729-8be1-01323de8d5c0 | note | – – – – – – – – –
66ed8394-6682-5d44-9777-f6b1a028c321 | note | RESPONSIBILITY: Site Engineer / Site Foreman
73c0e2a9-62d0-564b-be47-c6675c4c2675 | note | – – – – – – – – –
7abaafa3-a653-551d-9fa3-00bdf9c3a2db | textbox | DATE:
de7a129c-f72d-40fc-9392-e573f65b1249 | checkpoint | 1.2 Implementation of all measures and controls
188e31b4-d164-5fca-9384-9b3e1e810508 | note | FREQUENCY: Prior to Placement/ Each Lot
4c66d80c-6227-5939-b93a-3248adc06228 | note | – – – – – – – – –
e775797e-4faf-552e-8277-385281f1c81f | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
26b0238e-6ac7-5b9f-9629-44d50ebdaf4c | note | – – – – – – – – –
2dfd52b7-7caf-58e4-b441-21bad67e3f8e | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
a588543d-3278-5b40-8523-7dee2871b3b9 | note | – – – – – – – – –
2dc65420-9104-5e87-a9cd-230e42c759c4 | note | INSPECTION/TEST METHOD: Visual Inspection
2ff98e0e-16cd-5527-9bc7-23c78cc3f7b8 | note | – – – – – – – – –
1de2a81a-2d0d-5fdb-9a1c-e077c6d166a5 | note | RECORD OF CONFORMITY: This ITP Signed Off
19172f25-869d-5c3e-b5ae-7a3cd034904c | note | – – – – – – – – –
bd1d62e3-d257-59f6-95ab-af796fe4a9f7 | note | HP*
ff1bb1a3-7fa6-512a-af32-000d2e4dccd2 | note | – – – – – – – – –
59bfd478-5da3-5380-8555-798dfd90f5ef | note | RESPONSIBILITY: Site Engineer / Site Foreman
550bcc31-5a75-5743-86bf-23352e88c06f | note | – – – – – – – – –
316c9fa2-2544-58d7-8701-8eb9a2e20407 | textbox | DATE:
59d67d60-94c8-4050-af82-f586bc258489 | checkpoint | 1.3 Verify Material
360dbaf4-a2ea-5e62-8af3-12284b462ea6 | note | FREQUENCY: Prior to Placement
aa2294b3-c2d7-56e0-b64a-47305cbd22c9 | note | – – – – – – – – –
131f6684-6e84-526f-9a13-304664a65995 | note | ACCEPTANCE CRITERIA: Assigned CBR to be greater than 6% (<10%), swell is to be less than 1.5%, unless approved as expansive.
acf0e6db-dc53-5f53-8ff7-04fa8cf7caa3 | note | • Soil is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075.
1590e629-0a2e-5f4c-aa2b-716b359b5505 | note | • PI between 6 and 25.
e137146c-c9f3-53ee-82c9-62adf4853e27 | note | • Permeability of less than 5X10^-9 for capping and verge material
ffe02c39-dc10-52e0-b833-a3f9d4ed4d92 | note | – – – – – – – – –
0ac76d29-082b-537f-8a4c-f3676943d81c | note | REFERENCE DOCUMENTS: VicRoads Spec.
668e793d-1716-547f-b1e4-dc94c72828ec | note | • Cl. 204.04(b)
c9f8a244-46c1-5ef3-86ed-dd770e582140 | note | • Cl. 204.06(c)
118e1398-637d-5c52-9100-ed83abe0a655 | note | • Table 204.041
252ab28b-83d3-5aed-874e-441d7c43890c | note | • Table 3020.052
abdfb2e5-6f2e-5ffb-abc8-ea00107fae39 | note | – – – – – – – – –
9faf5524-5626-5467-8e0c-0666c8cd5db9 | note | INSPECTION/TEST METHOD: Site Inspection
5f636c6c-3f17-5d21-8b2f-5b6558558036 | note | – – – – – – – – –
3cf5f29f-f7b7-5f53-bce8-b2f2851464a1 | note | RECORD OF CONFORMITY: Test Record (If silt is observed)
01a53044-5059-585d-8415-26fd4914540a | note | – – – – – – – – –
de1c00e7-d72f-56fb-912b-4bc00adec6af | note | HP
00109d07-27ff-5c8f-a644-e45c51cfc3fb | note | – – – – – – – – –
5ffb24d6-ccf5-55a0-9af3-b472deef79c6 | note | RESPONSIBILITY: Site Engineer & Superintendent
9d7d1a68-ef30-5825-aa5a-d08ad0547148 | note | – – – – – – – – –
98f0ed82-dca3-5b59-a5b9-b84b57260364 | textbox | DATE:
39a0fcc7-d22e-42df-86df-d6c1b48e04e3 | signoff | AUTHORITY HOLDPOINT
34c59c6f-7878-43e8-aeae-13664de23dc3 | checkpoint | 1.4 Excavation Permit
a036bb37-8543-54ad-b929-2a3861a28c53 | note | FREQUENCY: Each lot
e3212340-6e3b-509d-a490-779b9490fb51 | note | – – – – – – – – –
42d78d78-616f-5ca2-9e41-3b7bf5d6e04b | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
cfb02939-cd01-50cb-be88-432032b47d3d | note | • Plant and equipment shall be appropriate for the task.
ef355372-6e58-53ad-a009-dff1ac54d3ef | note | • Excavation operations shall not disturb areas outside the limit of excavation
789bbef9-420e-52f9-b794-3bf558d6dc01 | note | – – – – – – – – –
6116af6b-e20c-5f77-909b-fc17baefe07c | note | REFERENCE DOCUMENTS: Excavation permit
d1261487-2e73-51bf-a0c1-d1a240ea2512 | note | – – – – – – – – –
5d5e24c1-7cdf-54ef-b783-fa601fa506f6 | note | INSPECTION/TEST METHOD: Verify
4d64d6ce-7bd0-5424-bbd4-9ac7d127e924 | note | – – – – – – – – –
4775e948-1e29-554f-8636-aa03ced7a824 | note | RECORD OF CONFORMITY: This ITP Signed Off
feb822f0-c3a4-5ef3-9420-3da9f61b5af5 | note | – – – – – – – – –
32dfca65-1ce2-5ec4-aedb-34351a88c54f | note | HP*
df33f347-40f3-5689-98cd-60dc8867b32d | note | – – – – – – – – –
d074842a-c910-5d3d-9460-6e3405d55b9f | note | RESPONSIBILITY: Site Engineer
184ef280-beae-5b4b-9fb8-de9be8b48530 | note | – – – – – – – – –
c23ed124-aa07-5d1f-983c-fbf7960cb1f1 | textbox | DATE:
073cdcb3-b5d7-4098-9267-05dea677487e | section | 2 - Construction Works
0f1335cd-916c-44b9-9bf4-07ac9f19206b | checkpoint | 2.1 Survey set-out
405d64e4-8cc9-58eb-9b48-63bf6fb7a10f | note | FREQUENCY: Prior to Commencing Excavation
9b112375-e3b3-5331-9f13-33d098553124 | note | – – – – – – – – –
c7d33b89-78fb-5268-adff-0aecc9e17a2b | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.
1952a017-3595-5fcd-85ac-db5390bb831c | note | • The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
05958f6d-886d-5d81-8948-4c7528b636d0 | note | • IFC and latest available revision used
2e4bf5ef-816b-58a6-9143-8a1ffd8c3425 | note | – – – – – – – – –
32681ae3-cbaa-5c90-bd20-314dba64f86b | note | REFERENCE DOCUMENTS: Latest IFC Drawings
7e3d0118-bc49-5f67-95ca-a81593cca3e0 | note | – – – – – – – – –
cab212ba-bd7c-5200-b8d9-9e4e02ac5cb2 | note | INSPECTION/TEST METHOD: Site Inspection
d9ba2db4-3ab1-5630-b998-b8b7393aebac | note | – – – – – – – – –
61c36bc8-b90e-526f-af65-94f45b596bc9 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
82f42d1c-a695-5b77-9b7c-30dd1ceab81f | note | – – – – – – – – –
400701fd-a31c-5da1-aa4d-fd3f23e080ee | note | SCP
7e59273f-7356-54ef-b1db-b0693f16ac1f | note | – – – – – – – – –
9c3ae920-7207-530c-b12b-9b85d31b58b9 | note | RESPONSIBILITY: Site Engineer/ Surveyor
dcd156e4-e97c-5a41-8a50-a9f781023035 | note | – – – – – – – – –
00e2257b-8581-5ef7-a826-d91a03dd8eb2 | textbox | DATE:
eedd5ac2-c9dc-4881-8fdc-dc356939133c | checkpoint | 2.2 Inspection of fill area
70f2d44d-c7d9-5681-88f1-696d8ac0ee9c | note | FREQUENCY: Each lot
27db335b-1fe5-5870-85dc-7d1970bb1689 | note | – – – – – – – – –
5e8956e8-c246-56b1-8b75-a95e94595978 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
f927b01c-0694-5ed9-95f3-66c9525a0e40 | note | – – – – – – – – –
3070b12b-580f-5c4b-a29b-adc5edd98e4d | note | REFERENCE DOCUMENTS: 204.10 (b)
5a4bcebc-edfe-54d1-8042-57abc7435f1b | note | – – – – – – – – –
785d42c4-d6a2-5b70-9e7c-0749ae8d8d32 | note | INSPECTION/TEST METHOD: Visual Inspection
91a7649c-18f8-5341-a3f9-fa73ba471b5e | note | – – – – – – – – –
48bf541c-f1d9-5823-82b3-2338f8d8a4c9 | note | RECORD OF CONFORMITY: This ITP Signed Off
3ab8da62-83a1-50a7-a8e5-37e883571fed | note | – – – – – – – – –
13c51497-7803-5e2e-9b1d-a03055cb4300 | note | HP
d5296611-f9c9-5ffa-91f4-4c89216f72ff | note | – – – – – – – – –
943da16a-dce2-53d6-9afb-ff0d84039559 | note | RESPONSIBILITY: Site Engineer / Superintendent
eaa8a684-5b31-52eb-b863-0b4d27778c16 | note | – – – – – – – – –
08d4b911-ceba-5cf8-925e-5ea752df1463 | textbox | DATE:
d3fed012-d43c-415b-a0c1-df08a28b6b61 | signoff | AUTHORITY HOLDPOINT
39bd98a4-9376-404b-8637-a9695100a222 | checkpoint | 2.3 Layer Thickness
c94dc0a6-9891-5e62-8827-9768d7990ad0 | note | FREQUENCY: During Excavation
9e6b9eb1-1a53-5a9f-8ae2-7e900a198e2d | note | – – – – – – – – –
a7f48170-c7f6-5a57-ac8d-83d28f5c2a8a | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
9cf52854-af0a-5ba4-935d-9428fe6c7d16 | note | – – – – – – – – –
01b6ecd4-d0fe-56ec-8136-8ddeb5575ba1 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
b1d78a89-2aa4-5cbd-a657-3a7f1d7bbf3e | note | – – – – – – – – –
7260fdba-8bf5-5e83-875b-d9ae812e3548 | note | INSPECTION/TEST METHOD: Visual Inspection
3225f008-d761-50aa-898f-609c7991c6c0 | note | – – – – – – – – –
3a00f733-c860-539e-a988-cf51abe83d28 | note | RECORD OF CONFORMITY: This ITP Signed Off
e60d1462-00a0-5382-bcb6-a7429375b53e | note | – – – – – – – – –
6e11f1a1-df90-57a8-b25a-461b4f5f3e4e | note | IP
423012e0-f566-501f-9da2-f4bc5380cdc1 | note | – – – – – – – – –
fc52bb37-5bc1-5ffe-b2b0-bbe3f631fcb6 | note | RESPONSIBILITY: Site Engineer
9a61d89a-5f76-52f5-86ab-18a19a8f9a25 | note | – – – – – – – – –
a29eb0a0-bde9-54ec-ac8b-212b1a865853 | textbox | DATE:
3293d6dd-33df-4a8a-9f47-8905014e66ec | checkpoint | 2.4 Maximum Lot Size
7627cf40-8985-5a0d-b20e-e86ba6939a21 | note | FREQUENCY: During Excavation
d6ad636a-b340-5507-af30-dad53ea32d5c | note | – – – – – – – – –
f7c701aa-eea9-5196-9e8b-c8911b50449c | note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 5,000m2, whichever is lesser.
dd72db3b-6293-50d9-a2cc-7a0371d852fd | note | – – – – – – – – –
32e44b07-aaaa-5f48-90b2-6f295504a831 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
1052fb51-94cb-52f5-a0ff-4a2322f9acd6 | note | – – – – – – – – –
a6d9fea1-ac8f-5f94-b0f1-36fa1cd72366 | note | INSPECTION/TEST METHOD: Visual Inspection
12ccb617-01f6-5b24-8f00-4afc01e4a01e | note | – – – – – – – – –
ce715f33-02ec-5a84-80c4-03368c46dd5c | note | RECORD OF CONFORMITY: This ITP Signed Off
69506b92-0556-52b3-850d-926b5db81106 | note | – – – – – – – – –
3d551a10-ba41-5b79-a0bd-0aaa2eb6854f | note | IP
e36e65f7-55df-5e21-b4c8-ba8b8b5c6cb9 | note | – – – – – – – – –
92fbb73b-4395-5e32-af13-94caffa7d275 | note | RESPONSIBILITY: Site Engineer
6ca987c7-b5fa-5424-865e-ece8912deaad | note | – – – – – – – – –
d5094d01-cc90-5fa5-a4ba-e277fc9a3e82 | textbox | DATE:
0cbb0431-2e97-48b5-aeb7-54ee04994a07 | checkpoint | 2.6 Proof Roll
f5f5173d-2889-5408-aeb7-1f99345f0bb6 | note | FREQUENCY: Prior to placement
273c1189-7a30-5f11-b039-33dfc46cd62c | note | – – – – – – – – –
e041c4f2-6b04-59fc-9e01-8c070b38940c | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
e259f7be-a462-591c-b8a4-e1e2e09bc7ef | note | – – – – – – – – –
81707c3e-4258-52a2-8004-8411a62d7564 | note | REFERENCE DOCUMENTS: 173.03, 204.12), 204.10 (b)
0c286b70-8d5d-58e4-977d-b2967b977108 | note | – – – – – – – – –
dc9ee3f8-4a81-59e6-a8a9-3b6453441fd3 | note | INSPECTION/TEST METHOD: Visual Inspection
cc449278-2f30-52d2-8bce-e709c68138f0 | note | – – – – – – – – –
406db1ce-9409-581f-9006-68bb0ad1b79d | note | RECORD OF CONFORMITY: This ITP Signed Off
1b874194-e55f-5dd8-9ed2-ffff77092fe6 | note | – – – – – – – – –
a9875015-f6ea-5c8c-99cb-aa28a286402d | note | WP
6d5fef45-5a8e-5e2e-b75a-a41166429389 | note | – – – – – – – – –
7caad16e-c76e-56ff-a4f1-71d642717241 | note | RESPONSIBILITY: Site Foreman/ Superintendent
41d2031a-34d7-53eb-bf3f-a01c4d0d99da | note | – – – – – – – – –
3503e15c-b42f-554c-9793-f2129e1b83d4 | textbox | DATE:
b5dbf244-3210-44a5-83e8-5bf4b45c3b53 | checkpoint | 2.5 Type A Placement
baccd38a-09f2-5a58-955c-23ef8418c385 | note | FREQUENCY: Prior to Placement/ Each Lot
9822642c-fe6c-5df8-8dd0-cc6887318796 | note | – – – – – – – – –
626fef1e-b1bd-575a-8fb7-9be15ed852a6 | note | ACCEPTANCE CRITERIA: Top of fill must be shaped and compacted to minimise damage due to wet weather note 12 on Pavement Details 009-0001 "Capping Material can be substituted for (3%) Cement treated Stab Sand in confined areas
98cf967f-8b4d-5ed2-8ecb-fd07b681bdcb | note | • Any rocky material present must be uniform throughout the layer
16b89026-64f6-5f38-8c31-96e5a0091987 | note | • Each layer shall be kept generally parallel to the surface of subgrade
bc6fd3c6-c4fd-54c2-bb03-7bdd85c92c14 | note | – – – – – – – – –
c944d022-5dfd-5b79-8412-a3f5ae9577c1 | note | REFERENCE DOCUMENTS: 204.10 (d) (i).
2102a029-46d1-5fd0-a116-48dfa19b5711 | note | • 204.10 (d) (ii).
e3f861ab-52f2-57c4-a189-d3a4521c35af | note | • Table 3020.052
0ca8b622-5826-5202-ac86-c964e2162d8f | note | – – – – – – – – –
96c62f73-3698-5f7e-ae20-fb7fcba88ac3 | note | INSPECTION/TEST METHOD: Visual Inspection
49b3628d-c16c-53fc-8cb6-d3c19dcb5e83 | note | – – – – – – – – –
51174f80-005e-5d9e-a753-a96ce6d2950a | note | RECORD OF CONFORMITY: This ITP Signed Off
c41303d0-344a-5056-a35e-dd669399b279 | note | – – – – – – – – –
926df8e7-a734-5883-8b6e-46ebd9b855c7 | note | IP
31a71012-9edf-51f1-8dfe-3dde42d9e5ad | note | – – – – – – – – –
bb593c37-dd58-5ce3-8149-87d0217f72db | note | RESPONSIBILITY: Site Engineer / Site Foreman
16814aec-523d-5a9c-a715-233f52dee38b | note | – – – – – – – – –
2eca47d6-f822-57f0-9159-3961f213e584 | textbox | DATE:
7c10b8c7-a7cd-4e81-8129-041aea4f3bbb | section | 3 - Testing
47f970f7-b655-4b1f-8b8b-d386d7b1fd10 | checkpoint | 3.1 Reduced Test Frequency
b76b8684-8389-56d6-a23f-0f15e0892e7d | note | FREQUENCY: Each lot
a1adf6aa-d9c9-5365-aae0-6f1c4c7f0445 | note | – – – – – – – – –
f5b0c69c-5dca-5c9d-ab13-e6618548d296 | note | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification.
5e3df8e3-c8f0-574d-aee1-d730efa7b0af | note | • Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
7b3d6e1f-152c-5ca6-8016-ecee34221d71 | note | – – – – – – – – –
a381c329-4533-5b72-9464-d23ca6fb266b | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
d788af8c-1677-5eb9-a28e-1a6033472ed7 | note | – – – – – – – – –
2f4ded4c-aee6-51f6-933f-6673724d9c50 | note | INSPECTION/TEST METHOD: Test Record
d755f229-0521-586d-8d4b-2c51ca355264 | note | – – – – – – – – –
5d516ad2-775c-5572-8d08-d8103baf8b19 | note | RECORD OF CONFORMITY: Test Records
6fc46445-f0a4-58df-8e20-87887a77d3d6 | note | – – – – – – – – –
898dba1d-9c9c-5b36-b733-0daf83de3e99 | note | AP
a909e1e4-a2db-528b-a815-40142eaf19a1 | note | – – – – – – – – –
b074ec8e-1719-5135-b595-a31ceb6e89d3 | note | RESPONSIBILITY: Project Engineer
58b35b13-3d53-5baf-a7b2-299b41cf2e95 | note | – – – – – – – – –
59f5f27d-c2d3-5e04-822c-2df3c93101d3 | textbox | DATE:
d2e77e5b-915d-491d-a803-d89bfca1e6fc | checkpoint | 3.2 Compaction Testing
34b8dca0-3d82-5d25-827e-aac466b28b6c | note | FREQUENCY: Each Lot
cc0c388f-97bb-5812-9085-9122a3f4ddf1 | note | – – – – – – – – –
016167bd-e535-5996-8a81-76711ca02120 | note | ACCEPTANCE CRITERIA: Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B).
8cf8541a-0d5a-5023-aa97-5321fb2ea2fe | note | – – – – – – – – –
cabacc4b-c376-5762-97b6-f7249f163f0b | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
bd5bc083-f331-5b43-843e-6ca71c5d694c | note | – – – – – – – – –
b1249d16-33c4-52ce-9021-1e2764eb9e4a | note | INSPECTION/TEST METHOD: Verify
147874e1-c97e-5e6a-82fc-b8d7fd80adb6 | note | – – – – – – – – –
2efe2800-4029-557e-bf04-30957ac5eab8 | note | RECORD OF CONFORMITY: Compaction Test Records
a54752ca-1c4b-5d34-96f9-c688303ee119 | note | – – – – – – – – –
8e601248-cc82-5aaa-99a0-3ebb8fbe4e5e | note | TP
3f069e00-8a0f-53fa-9b40-37dcaffb9890 | note | – – – – – – – – –
69c2bd25-c0ca-568c-8235-628e93f0dbc3 | note | RESPONSIBILITY: Site Engineer
5ce7837b-77cb-573c-bda4-047967186d70 | note | – – – – – – – – –
33f2703c-a8ad-5d90-bad7-90ae6385832d | textbox | DATE:
eda59a64-b0dc-420d-a622-4148e1002206 | checkpoint | 3.3 Compaction Testing (Small Lots)
d40b3b82-e546-53de-bb2a-a7865beca63e | note | FREQUENCY: Each Lot
fc61565c-18f9-51cb-9ee0-2772147f6391 | note | – – – – – – – – –
1da5a5a4-f556-5a4e-8c96-2adddb050e0c | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area.
70dd7402-7a24-5b5b-a31e-96a1405cdb11 | note | • Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% SDD.
1b8513dd-c541-5db3-832f-5c435b792a09 | note | – – – – – – – – –
3bcf6f7d-522b-5d2c-b888-d88ebf6e17f3 | note | REFERENCE DOCUMENTS: 173.04 d
5bd8e39e-2a7a-52d8-a0c0-7e2760809aa9 | note | – – – – – – – – –
a2669df0-746f-5280-8c79-05feb5f08c1c | note | INSPECTION/TEST METHOD: Test Point
b53222d9-066e-5712-a23d-9ae0571c047d | note | – – – – – – – – –
1f35a184-c926-5f53-bf39-0be54c89e6f9 | note | RECORD OF CONFORMITY: Test Records, Lot Register
60cf7281-3877-5504-ba62-8ef2daaf0c8f | note | – – – – – – – – –
695b498f-caa4-5353-9987-c564204545d3 | note | TP
69f5281c-e197-5ac3-b53e-452b85d24f36 | note | – – – – – – – – –
4df51fe2-cbf0-536e-a8f8-95deafe59b33 | note | RESPONSIBILITY: N/A
3544dd08-3c89-5e94-89e2-5a431a6e043c | note | – – – – – – – – –
703e2e79-d29a-5d87-8070-c470eba82fe9 | textbox | DATE:
2bda3e0f-2cec-49dd-b54f-88d3f8952429 | checkpoint | 3.4 Maximum Particle Size
63e12a72-e649-5a20-9e72-7a2dd7ffa80f | note | FREQUENCY: Each lot, unless reduced frequency has been approved
59a39622-9dfc-57c7-aa0d-3152efb3811b | note | – – – – – – – – –
42c88ed2-69ab-50b6-b525-d87fe7aa5621 | note | ACCEPTANCE CRITERIA: Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075
bb9a22d8-8504-50e3-81cc-a9c6d32a8d3f | note | – – – – – – – – –
5e8e6655-38ef-5ede-9f4f-436b23bea74e | note | REFERENCE DOCUMENTS: VicRoads Spec.
3877c5c5-8bb3-5c9d-a4a9-4c466cf1610b | note | • Cl. 204.14(a)(ii)
24591524-427b-5e04-a3b7-cda869363014 | note | • Table 204.141
937e84c1-6102-55a5-838f-1d34271b49c3 | note | • Table 204.041
9199d250-499c-5639-b2e8-5b69c692a63c | note | – – – – – – – – –
ba105dcc-a105-5c9f-a95a-cf9f2f7eb250 | note | INSPECTION/TEST METHOD: Verify
f193146a-4b89-542c-a479-c288ce947625 | note | – – – – – – – – –
27e141e8-ed65-546c-b016-85d5a71aba52 | note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
392a8de1-61b5-5d37-ad6b-60b7b4b6f28a | note | – – – – – – – – –
95608c26-11b7-5dc2-a881-9c5b7b8ced78 | note | TP
a10cd1eb-4405-5df9-b2c0-cbfbc1d633ee | note | – – – – – – – – –
ad75e59d-a215-533f-bec0-8b6c9d42f0fe | note | RESPONSIBILITY: Site Engineer
84c862db-e64a-5435-ac51-5944491aef95 | note | – – – – – – – – –
5ac2414c-bab4-5544-bcf3-f873d6a73453 | textbox | DATE:
a626e672-bed0-48d8-b1ea-dfc1437a973f | checkpoint | 3.5 CBR/Swell
7aa28b18-d0f1-585f-a300-eba2ec582170 | note | FREQUENCY: First lot only
9ce889d5-9c73-5f0f-858e-171e65650a02 | note | – – – – – – – – –
ef1092c5-fa08-5d20-b32f-e5cd587f1dc5 | note | ACCEPTANCE CRITERIA: CBR: ≥ 6%, Swell: ≤ 1.5% (Verge material less than 1.0%).
cfb8dd18-bb78-5168-a844-8b5d3ffbc3c6 | note | – – – – – – – – –
c4ed3d97-91c1-5c32-9412-0d7ed4c40169 | note | REFERENCE DOCUMENTS: VicRoads Spec.
f06c8b40-3cc0-5d0b-8e8f-cfffcb1c48da | note | • Cl. 204.14(a)(i)
55e11b60-645f-5ec5-a823-17d216a471a9 | note | • Table 204.141
2ae743f7-354d-56ce-ab26-37a4f616df44 | note | • Table 204.041
2a69ac20-ed4b-542a-8cb7-66731a50afde | note | – – – – – – – – –
40e53466-06fb-53cd-ac70-f519eec58fda | note | INSPECTION/TEST METHOD: Verify
0cc63b15-9ca5-52bf-9b4a-e94d6dd075ec | note | – – – – – – – – –
f4c44e8d-05b9-5a54-b55c-727b9228f8b4 | note | RECORD OF CONFORMITY: CBR/Swell Test Records
c78fbe88-37ba-57a5-8b48-0c857dd74d96 | note | – – – – – – – – –
ea11a43e-34db-5e6f-bae4-5d7d948301dd | note | TP
92ec4b20-d201-5153-b9bc-18de432ca718 | note | – – – – – – – – –
11a34e10-d87e-5002-bf4d-59cd506edbf4 | note | RESPONSIBILITY: Site Engineer
3db4acb0-c4f3-5104-84a0-22384077e532 | note | – – – – – – – – –
35a528b2-a812-5862-8e0d-b2caddfbec2b | textbox | DATE:
adb4be59-5a4d-4ec2-91f9-5fcdeeb5487c | checkpoint | 3.6 Atterberg Limit Tests
c71d3c19-07c3-514a-a737-4d39204a9e88 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
8b216a2c-6817-5c37-af92-953025766e40 | note | – – – – – – – – –
d4e31369-1c81-5dd9-b679-2ca0fc32dd58 | note | ACCEPTANCE CRITERIA: PI between 6 and 25, PI x % passing through 0.425 to be less than 1000
7c1f5cfb-d0a4-5b8a-909c-e47adeaecf5c | note | – – – – – – – – –
3dda9ae7-ebb8-5c6a-b29d-5f94f310677c | note | REFERENCE DOCUMENTS: VicRoads Spec.
0c7b9faf-9357-5f2f-bcc2-da98431b60af | note | • Cl. 204.14(a)(ii) Table 204.141
6e6cc2a6-8704-5ae8-ad88-d0193c9ee955 | note | • Table 204.041
10be0a9a-11c9-55ae-b7c2-e77fd498e17f | note | – – – – – – – – –
83c9c539-31ea-5def-89f4-f5ac5808de94 | note | INSPECTION/TEST METHOD: Verify
89cafd74-9376-5652-9e6a-82e9f7ed475d | note | – – – – – – – – –
3221b150-deb6-52d7-928a-e54b0027bb7b | note | RECORD OF CONFORMITY: PI Test Records
4627dc18-2950-5ff3-b5ca-5ad3cf6acd55 | note | – – – – – – – – –
4ebe6c9c-e150-5348-8521-6b94d75c4ea3 | note | TP
d7f23613-21da-560c-9902-1f1ffc4508ed | note | – – – – – – – – –
58b74fb7-4125-5f15-82cc-6cff265c2552 | note | RESPONSIBILITY: Site Engineer
161eb127-b67e-563f-8716-7a4dc966a457 | note | – – – – – – – – –
d09465f4-d74a-50be-bc83-f73dda66e6af | textbox | DATE:
a2d8fae4-d61c-4658-bd32-6ba48a8fb543 | checkpoint | 3.7 Permeability
967a1872-2905-51e4-b547-bb7f0c3233da | note | FREQUENCY: Each lot, unless reduced frequency has been approved
b50811ec-db71-578d-8302-f003d821b878 | note | – – – – – – – – –
30ec0572-0d00-5908-a18c-a36de44b515d | note | ACCEPTANCE CRITERIA: Permeability of less than 5X10^-9 for capping and verge material
ceb33ab4-3910-5c36-8a50-060b1e24b839 | note | – – – – – – – – –
bf9288c2-a84d-5bf1-994b-42ef67190570 | note | REFERENCE DOCUMENTS: VicRoads Spec.
0f43eb50-0ad6-5049-8878-b8cdfa34a30a | note | • Cl. 204.14(a)(ii) Table 204.141
5cf125d3-4e8e-5d6a-95a2-ef225f61bbd6 | note | • Table 204.041
c4c5aac7-6b79-54b2-93cd-ff1a1f27bc4d | note | – – – – – – – – –
75e93510-668c-5fcb-b59f-b995db9c6b2f | note | INSPECTION/TEST METHOD: Verify
2337c4aa-2b85-5503-845c-1a8187e3ade4 | note | – – – – – – – – –
d4fc7209-fd33-5528-9c72-e78cb964d75b | note | RECORD OF CONFORMITY: Permeability Test Records
958c1dc3-dc8d-5f86-8ab2-2b914d3b664e | note | – – – – – – – – –
788995cd-e228-5f1e-92e6-17d534340e8d | note | TP
73394e22-dedd-5fe7-a82a-6edf97bc1912 | note | – – – – – – – – –
35c26bf9-2809-5af0-9f27-043714bbd4ae | note | RESPONSIBILITY: Site Engineer
a7131f0b-fd46-5ea3-a44e-8d98f04feec1 | note | – – – – – – – – –
3d6413ce-9322-5704-8d60-7ce7675ee521 | textbox | DATE:
ec378261-bd4d-4480-bf7f-327d1d16caf2 | checkpoint | 3.8 Material Property Testing (Scale B)
19f9be2f-036d-5c6a-8895-c2f66bb288b8 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
ede01663-439b-5dc7-a310-bd8ffaf9aa0d | note | – – – – – – – – –
7d2f5666-12fa-56a8-bdad-830cff375b56 | note | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
1fac2e8f-b651-5f5e-a7a8-d07c79250910 | note | – – – – – – – – –
5b4dbad6-a72f-579c-b111-af2326c865ce | note | REFERENCE DOCUMENTS: Cl 204.04, Cl204.14
6e1e347f-1ba3-5a84-8445-b23eae5889e4 | note | – – – – – – – – –
945c8c06-c7dc-5968-828d-d0f0fe657c13 | note | INSPECTION/TEST METHOD: Verify
15c5f004-4afa-5b7e-ae21-27fd06f4024d | note | – – – – – – – – –
7117cb4b-04e7-581c-9096-147b6e599aef | note | RECORD OF CONFORMITY: NATA test report
4a749088-88c4-58ea-9160-32b212a79493 | note | – – – – – – – – –
2388df8c-7543-5f18-876d-6ff197c83e32 | note | TP
07fa3398-d1e2-5273-9546-638635d33f79 | note | – – – – – – – – –
f1049b43-3218-5cf7-9b48-93f60e4fbeac | note | RESPONSIBILITY: Site Engineer
dd748573-4f69-5af9-ab7d-fd1d0f977f22 | note | – – – – – – – – –
912db884-e931-5b12-896d-b7a1a49d6baf | textbox | DATE:
1a34e863-c5eb-4e49-9ca2-992ed2696136 | checkpoint | 3.9 Survey Conformance
1f45b53b-73f5-5740-8857-6c822944110d | note | FREQUENCY: Each lot
453cc4d3-d630-5264-9091-2478b0faa4a5 | note | – – – – – – – – –
e884e892-5461-57a4-b621-a20331fbfa37 | note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
263d3854-2b10-5efd-af9e-f4cc9b324fd3 | note | • Scale B: Range x = +5,-25
b4b972cb-5c61-5c5c-976c-6b4cf1fff429 | note | • Max S = 15mm
e2d9c394-0fb7-5b50-a651-35351db6e307 | note | • 40 measurements per lot
f0d40df4-8b63-5f73-840c-db5fa453275b | note | – – – – – – – – –
4173ee7b-7f34-57ce-9805-f0371ad379bc | note | REFERENCE DOCUMENTS: 204.03
5177530f-3579-56ce-8aa9-80d9d1abfda5 | note | – – – – – – – – –
09549b90-b2e0-5acb-bdfe-c92623f0abd3 | note | INSPECTION/TEST METHOD: Survey conformance point
8eff97a8-cb55-5a8c-9ca2-678edd8e2bf1 | note | – – – – – – – – –
df718ebd-c036-524f-b777-0f340e6428ac | note | RECORD OF CONFORMITY: Survey report, Lot Register
d30ab738-e895-52b3-9eca-3a434fc59d3f | note | – – – – – – – – –
e88974be-1f76-56b0-958b-1ebde4089467 | note | WP, SCP
c369c1bc-b529-5a0b-bd71-30ecfce930ae | note | – – – – – – – – –
526418c4-ea17-59ac-8dbb-8538db298a99 | note | RESPONSIBILITY: Site Engineer & Surveyor
864fd478-58a4-5626-aada-ba82bbecfe61 | note | – – – – – – – – –
8cee7dbb-480b-5471-8051-bcde6e2c302a | textbox | DATE:
ea0511fa-5ce0-485b-863a-8039beddefc6 | checkpoint | Final Inspection
ceadcb2e-f3e3-5848-a285-85bf14bb5d9f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d354d5bf-6871-5303-b8e3-3cdf8e8387d9 | textbox | Print Name:
879ed66a-695a-5f61-8f33-4de6bc622019 | textbox | Position:
d627fd09-06b8-5b11-8e5a-2fcebd7b5189 | textbox | Date:
8899f338-c66f-46b4-b8a6-5b203e3e62d9 | checklist | FHC-ITP-005 - Class 2 Crushed Rock Rev3 | itp | FHC-ITP-005 - Class 2 Crushed Rock Rev3
ad099f1f-2870-48dd-b6d1-594dd541e362 | section | 1 - Preliminary Works
87028718-cee9-40c9-bbac-f1f75b50c95e | checkpoint | 1.1 Check for correct documentation
ed52bd05-90a6-5b27-b17d-dc0a03c80719 | note | FREQUENCY: Prior to commencing any activity
48be33d5-530b-5830-90a3-57724ec4562b | note | – – – – – – – – –
99c37ed1-00db-577d-855b-4d75683a3078 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
997ba771-68f9-5f3f-a66a-54c2492748ad | note | – Using the correct and complete set of drawings
74750a61-98b4-51aa-b081-b8f855ec3203 | note | – All drawings are the latest revision
1944ee4a-9857-5ffa-a5f6-0230ea3aa350 | note | – – – – – – – – –
68d4fbab-fb91-5340-8fb8-aeb3c9c11663 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
a5a7417d-10ce-5ca8-a88b-469721e2c9a2 | note | – – – – – – – – –
486e9843-41b7-5bc3-b149-2e830ebf9593 | note | INSPECTION/TEST METHOD: Visual inspection
f8e3c4ed-173c-55ae-9577-c5b0499c7e2b | note | – – – – – – – – –
bf976e46-a260-50e6-8063-c94c2bce9b3d | note | RECORD OF CONFORMITY: This ITP signed
9a4cfea9-3aad-576a-ab1a-b966b11dd59d | note | – – – – – – – – –
d66611da-39ef-52e6-b8ea-52c87c5d20a6 | note | HP*
affd4eb4-7b54-5a1f-b82f-2b56a384b59b | note | – – – – – – – – –
2fe69e6d-c395-5af5-a5b2-23a18e0bdae0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
03ba5ccc-5178-5a07-9000-88574499a9f3 | note | – – – – – – – – –
f6e7d42b-112d-54c8-860c-756684797b70 | textbox | DATE:
9cde5007-610e-419a-ad07-48c87ea403a9 | checkpoint | 1.2 Material Mix Design
94ea7b34-cd0f-5296-ab50-428d94a6aebd | note | FREQUENCY: Prior to commencing any activity
877cf72b-924a-5b7d-8a0b-6bb94ca6cb34 | note | – – – – – – – – –
ee95ae0a-b124-5433-8f16-234e0141eeb3 | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
09e7b0b3-ae27-55d7-8b68-a2274696f142 | note | – – – – – – – – –
cf27f3fb-d45d-50cb-86dc-484a1452f788 | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
c1dd1806-ab31-5201-8336-b19bf3b90155 | note | – – – – – – – – –
b4b532e7-471f-5b7f-a2a0-6b0df563deb3 | note | INSPECTION/TEST METHOD: Document Review
ab9b6f42-e2fd-514e-89b7-930c3a8da0de | note | – – – – – – – – –
98603275-2f59-5fd8-a558-dd149ca20f6d | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
df602bc9-7b60-502e-8413-f3d2bb617742 | note | – – – – – – – – –
23488aff-5cf7-56f7-a9cd-78dbde9d8f46 | note | HP*
d435f056-d5cf-58aa-acd6-39b064480464 | note | – – – – – – – – –
9dae4f54-2cd6-548a-86ba-faf4197aebc9 | note | RESPONSIBILITY: Site Engineer
fc406a17-a68c-5983-8e6f-01077a3b656d | note | – – – – – – – – –
04d6c9bd-e5fc-5c30-89a3-da7030d44ffe | textbox | DATE:
097465ee-9061-41ae-9e82-9e0d6471b799 | checkpoint | 1.3 Implementation of all measures and controls
21caef6e-0d17-5bfe-8474-5cddb1b6a3cc | note | FREQUENCY: Prior to commencing any activity
5de2c5f1-97e2-56fc-8adb-ebebda02d4b3 | note | – – – – – – – – –
de0f8315-2b51-599e-bbd4-423eb3a8a96d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
4ad2a6c3-4fe2-55ed-be89-1a298a81fbcb | note | – – – – – – – – –
8b148bf5-053f-573e-af7e-a533f9914274 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
b2208b68-9c27-5a4a-808e-e6e200a3a3af | note | – – – – – – – – –
b99052d8-25b8-5d97-a94f-777cf300691f | note | INSPECTION/TEST METHOD: Visual Inspection
9559978f-f35c-5c0e-a99b-142831b6244e | note | – – – – – – – – –
43100045-cbaa-5827-853d-f199d5ebbba0 | note | RECORD OF CONFORMITY: This ITP signed
68d0ebc0-71de-513f-adaa-6339971e9931 | note | – – – – – – – – –
841fffdd-4669-5ef6-819e-99e944957ce9 | note | HP*
35389ff9-ca1c-5761-b3e5-a3da8f37b975 | note | – – – – – – – – –
ad2883e7-4bfa-51d7-9b79-f635b87b7f1d | note | RESPONSIBILITY: Site Engineer / Site Foreman
ee340aec-e8bb-5b20-95a0-21a71332e67e | note | – – – – – – – – –
3131e92b-6b5d-59ab-9f65-3c7e89d7c9a3 | textbox | DATE:
9d5de782-18f6-4cfa-bae8-ca95cd207601 | section | 2 - Construction Works
373a917a-d7ab-4794-9cfa-2557b7b325b0 | checkpoint | 2.1 Transverse Joints
1dac1cde-ec43-57a5-a610-90475ec9d60c | note | FREQUENCY: Check prior to placing material
87583f55-ffa1-59fc-822f-69f084489fc6 | note | – – – – – – – – –
c03e3946-0a44-5e06-b7a0-ee87cdce0b4d | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
6f710518-f313-5cb3-9658-7e9d70c44b4e | note | – – – – – – – – –
0f001181-fc97-5099-a898-ac6c1d4104d6 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
3ec5c1cf-2006-5d6a-939c-a34888562210 | note | – – – – – – – – –
2eb2b951-581d-5112-8113-c60070d069e8 | note | INSPECTION/TEST METHOD: Visual Inspection
c8f6e8d3-6a73-5b3c-b818-6d561a4fbdb6 | note | – – – – – – – – –
d0f99b1f-cee4-53f7-8490-865203e39f12 | note | RECORD OF CONFORMITY: This ITP signed off
f69bd207-2247-517c-9db9-012a1eeb449a | note | – – – – – – – – –
7b1ee4ba-9572-53c2-803c-42b96a9a8cf4 | note | IP
ddbd0d0b-cb42-5d04-95ee-0347cad17928 | note | – – – – – – – – –
df1d1adc-5893-5d29-9a7f-9ffe074d1f16 | note | RESPONSIBILITY: Site Engineer
8617cafa-7074-51c8-8de0-9bfd99668bd7 | note | – – – – – – – – –
61ee3399-810a-5dcb-9538-b12bf694aaa3 | textbox | DATE:
849847f6-a9cd-46a8-ae24-6b5575b52157 | checkpoint | 2.2 Longitudinal Joints
13a5add1-e0b8-5f28-89ed-27eb12c95aa2 | note | FREQUENCY: Check prior to placing material
8c3a81a3-b26a-5505-83f8-9b622d727cec | note | – – – – – – – – –
4172f853-879d-567b-8c0a-9b2e41261c4b | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
e4c19561-4e2b-5fe1-ba85-6ba6283609c3 | note | – – – – – – – – –
0813fce9-8d02-551c-9a5f-98b9adf4aac8 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
65bbd64a-db71-561c-a87d-7391e2fdd6c8 | note | – – – – – – – – –
3a742626-7f67-5b9c-b600-3a3b2c7e2380 | note | INSPECTION/TEST METHOD: Visual Inspection
3d9c070d-bf9a-5721-8dd7-c401896bfb13 | note | – – – – – – – – –
a8890ce6-460a-50c7-af0b-0e6eeaa21197 | note | RECORD OF CONFORMITY: This ITP signed off
4e7c992f-8100-55c3-9193-773f476e1069 | note | – – – – – – – – –
1f47fb0d-f56d-5aca-83b1-1f43d87e3d46 | note | IP
4bb62327-ea18-58f6-8c3a-7d335da34fe8 | note | – – – – – – – – –
5a9edc7b-1478-5b78-aaee-456971fa4ca1 | note | RESPONSIBILITY: Site Engineer
c48652bd-fef8-5548-be48-b93e9ab63cbe | note | – – – – – – – – –
69cace13-8ff7-5bdc-90a2-1b9f210626c4 | textbox | DATE:
2d77bd9c-84d5-435a-80a3-5b6b53c82c6d | checkpoint | 2.3 Lot Size
df9155d1-3d6c-57b7-9130-61c3ebbbd41e | note | FREQUENCY: Check prior to placing material
b963c1a9-0fca-5b88-b460-5ecac0abd33e | note | – – – – – – – – –
958363b0-9c45-5baa-8d96-3106c7103873 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
1eae0ba0-d6e9-51fb-b980-0306f3e698cd | note | – – – – – – – – –
f60f5de2-133e-56e2-b5c1-8443ab47d05f | note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
58182f3e-b82f-5506-8a4e-3d1d84b0ab21 | note | – – – – – – – – –
e3ed6ec5-d36d-591f-9be6-c7920e446d8a | note | INSPECTION/TEST METHOD: Site Inspection
884ea622-a0f5-53cf-880a-bc690fbe0c93 | note | – – – – – – – – –
20d75b50-eab1-5bfe-80c4-4b4dd5a9e972 | note | RECORD OF CONFORMITY: Signed ITP
96e48080-aaa9-58bc-bae1-b5d352853eb4 | note | – – – – – – – – –
9dab2d06-ae10-58e3-a5fe-a1ae9e36f3b3 | note | IP
367ee897-bcbb-5c1b-a780-9199a14c5f72 | note | – – – – – – – – –
f46a7a48-08f6-5009-817e-6baeb175d6ac | note | RESPONSIBILITY: Site Engineer
394c5d3b-d2f0-5675-9a73-5f3a6706ced8 | note | – – – – – – – – –
2264b221-cf24-5925-b20a-039f81a7c6c1 | textbox | DATE:
d353c65b-c072-4556-857e-4c958f67ea06 | checkpoint | 2.4 Layer Thickness
17e02f7d-3668-5c0c-bbd0-9fe57b50d256 | note | FREQUENCY: Each Lot
3968e365-3fb3-5709-a7e6-ce6b134172cb | note | – – – – – – – – –
4e21ad6d-19e4-56da-9d36-5b9b94c7c9fb | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
18f14edb-2aef-54da-9a66-037d45b94b27 | note | – – – – – – – – –
59a1fcca-9015-5ebf-bff1-b5c47697a55c | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
b9b3ae33-80ef-50fc-8c8a-7699ebbdbf7f | note | – – – – – – – – –
cc60f1af-65d7-517c-b62f-425d045cf7a4 | note | INSPECTION/TEST METHOD: Site Inspection
dfb1dc11-d150-5017-9fb2-dd8f43c9c2f0 | note | – – – – – – – – –
d3e84ac7-c8e2-5967-9bca-6e0a02676a3b | note | RECORD OF CONFORMITY: Signed ITP
0434da99-a76b-566b-a511-e01376ba173c | note | – – – – – – – – –
6c9535f7-d31c-5901-ae4c-8cc9ac600d24 | note | IP
77d56996-81d0-5856-ad5b-003e480afe13 | note | – – – – – – – – –
52955313-51a2-5ed8-a9ed-3cfcf83208a1 | note | RESPONSIBILITY: Site Engineer
be692117-21a8-5caa-8521-8af86ceb655b | note | – – – – – – – – –
6a82b52c-bf0a-588a-9f0a-a27e93f82d75 | textbox | DATE:
42a67da9-6c24-47b7-9348-13218217b856 | checkpoint | 2.5 Proof Rolling
43ed201f-6394-58f2-88f9-29a60404ee59 | note | FREQUENCY: Proof Roll each layer
9dfe3104-baea-53c2-9872-d85660137fd4 | note | – – – – – – – – –
b381d8db-8716-589f-983b-3ff8f536b34b | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
8fe28780-300d-5963-9a17-3e0b08909ab0 | note | – – – – – – – – –
a584633c-534c-5b31-8896-a87f0dd2547b | note | REFERENCE DOCUMENTS: 173.03
2c40e097-b901-55b3-aa41-3f9b4c85d2de | note | – – – – – – – – –
7cedf4cf-dfe1-55fe-a29b-a56bdc9589ae | note | INSPECTION/TEST METHOD: Visual inspection
8e439038-00b1-5df3-94e2-c593892b3b15 | note | – – – – – – – – –
706ef921-7549-5d96-b4e7-f11746d35bde | note | RECORD OF CONFORMITY: This ITP signed off
bb1ccf2e-8253-58ee-b256-08e0e4129497 | note | – – – – – – – – –
38601a62-2996-5c53-a466-a600f37651d6 | note | HP / WP
c9a5b80d-fdbd-56f7-b049-b3233457e860 | note | – – – – – – – – –
2d9135dc-9357-5250-85fd-ae3499fafada | note | RESPONSIBILITY: Site Engineer & Superintendent
1b701eef-38c6-5794-98e7-37de0811f410 | note | – – – – – – – – –
88c61201-8bca-5c12-b260-9ada93fc5089 | textbox | DATE:
e248f003-1d3f-4abe-a1e5-dd2e6e5816df | signoff | AUTHORITY HOLDPOINT
3e11a977-06f8-4ee5-acae-7746853095c6 | section | 3 - Testing Requirements
37500a53-aecf-493d-b9a0-1fd1d797d140 | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
109d41e6-bcd3-5ed7-ac44-9685f645fd0e | note | FREQUENCY: Prior to Testing
cead72c5-0f96-52a9-be44-6340276d1242 | note | – – – – – – – – –
bb68f1e8-92b3-51f9-af8f-76dd0b41ae6c | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
cbe7bd71-373b-5298-ba55-0dc42d38886c | note | • Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
5f16dd1c-120c-587b-9d67-f0b49c1b3308 | note | – – – – – – – – –
d8205f23-7473-5542-8d18-621bd990172d | note | REFERENCE DOCUMENTS: Table 204.161
3151ad2a-d3ca-5604-880a-37f8a85adab8 | note | • Cl.304.08 (a)
c1b70193-1962-5791-8e7f-f2821e40554e | note | • Cl.304.11 (b)
d466a81b-4330-59e0-8f06-679796140aea | note | • Cl.304.11 (c)(i)
99e12692-15a8-533a-8824-56203786e53a | note | • Table 304.111
5d6aab16-af96-5afb-a16a-437e926d32b5 | note | – – – – – – – – –
501072cc-d5d0-5c7f-94c3-357536d4b95e | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
b0b1149a-a276-584c-a39d-68ba37b9bf9e | note | – – – – – – – – –
eeeb27aa-8ac1-5051-9d5e-c40d9f7e9efe | note | RECORD OF CONFORMITY: Signed ITP
c9f2c79a-68cc-5e02-9504-ca0f2109b9a9 | note | – – – – – – – – –
840b64f4-8dc1-5fcc-bc52-0e88e685b034 | note | AP
a848cf69-b547-54f9-9745-f22d98ac35a3 | note | – – – – – – – – –
6ca5bed4-6fbe-597f-ac58-e8500bcb4bee | note | RESPONSIBILITY: Project Engineer
6f10fa43-37af-5c44-b384-67faf6a53515 | note | – – – – – – – – –
e19d57f4-5155-5669-bb93-3f4d7c29ec97 | textbox | DATE:
dbc1970f-9e08-4e66-9969-2138946b094c | checkpoint | 3.2 Compaction Testing
503fea98-c113-5736-91e8-5e60da5fd4db | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
460a5c9c-d1c9-5734-b633-cf5628cae0b9 | note | – – – – – – – – –
af471100-c877-52fd-aa16-188dd74138f2 | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
0bd05aae-326c-583c-ac7a-6f53cfff32ae | note | – – – – – – – – –
b3bae582-c77d-5698-9d95-0bfbf30b23a5 | note | REFERENCE DOCUMENTS: Cl304.08 Table 3040.061
ce28cb84-ce35-5bec-bfee-a9707589e9fc | note | • Cl 304.11 (b) Table 304.111
d13df179-0fe2-50bd-9f7c-efcaed50d7b3 | note | – – – – – – – – –
90362669-6303-5632-8087-9780ccfe00d6 | note | INSPECTION/TEST METHOD: Test point
f3f9ece5-9047-55db-bb32-0151c1dd8467 | note | – – – – – – – – –
f453aa47-caac-59a0-94c2-51b6ddbf5bef | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
2b11078f-3530-5e4f-acde-6a9eabadeaa9 | note | – – – – – – – – –
8660e4dd-f6b2-5d03-b0c1-1f51eb2a77d1 | note | TP
32174249-8058-5fc6-8dde-434132a04319 | note | – – – – – – – – –
4165c435-6aab-5d21-b506-2d4a455f1751 | note | RESPONSIBILITY: Site Engineer
545ab961-8ed0-5f56-b0e0-0b4b2c479c4a | note | – – – – – – – – –
31e44b9c-963a-521d-ba1e-845f3e9e0718 | textbox | DATE:
c3359d4d-a011-4e02-aae3-59d04baa780d | checkpoint | 3.3 Compaction Testing (Small Lots)
8aa6b78e-1ec2-5e80-b681-248062c0cf1d | note | FREQUENCY: Each Lot
c7cbf29f-1252-5f24-8c52-7dd9c65fba4e | note | – – – – – – – – –
152995b0-0a96-57ad-bab8-a06bab00a9e5 | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
3201a13f-3428-5d84-97dd-73d8d73adec4 | note | – – – – – – – – –
792b1efe-83bb-54b2-b024-79728fc2f74c | note | REFERENCE DOCUMENTS: 173.04 d
1911aea4-6a1d-5397-8ff1-1b0da8ebc9f9 | note | – – – – – – – – –
97478fea-e40a-594a-8f01-604d44579ee9 | note | INSPECTION/TEST METHOD: Test Point
6cf4c68b-4761-5267-b636-65d8307976b6 | note | – – – – – – – – –
503bd348-ba6a-59ab-8a7a-3fe2c87f0bd1 | note | RECORD OF CONFORMITY: Test Records, Lot Register
e3ea7774-e593-543e-9d12-9b710a9b3a40 | note | – – – – – – – – –
465a7125-a8e3-53c4-903f-10fb508dbb52 | note | TP
47f46b3c-975d-5652-ac79-11e735afffc9 | note | – – – – – – – – –
7696429d-bd0d-565d-ba90-28aabce14dca | note | RESPONSIBILITY: Site Engineer
5a41499c-c0fc-5b49-80dd-c73a6184f83c | note | – – – – – – – – –
c46bbc8e-e5da-53eb-8e82-8e3594c4482c | textbox | DATE:
b4d299f1-cadb-4003-b94d-5233d0aaa927 | checkpoint | 3.4 Material Grading - Post Compaction (Class 2 & 3 Only)
da8f2bb9-eb96-5e84-8fb4-384dcb39aef8 | note | FREQUENCY: First Lot Only
49bb3301-3a3f-550b-b0b5-368a5dec79c1 | note | – – – – – – – – –
c85e825c-81c4-56af-a304-91786ed1626f | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
cd95ef26-d5e4-5b51-b98a-873390022dae | note | • Class 4 - N/A
6b969ea1-8cb5-5b77-8346-e9148d67b1a3 | note | • Class 3 - As per Table 304.101 - VR Spec. 304.10
b8faf973-5cae-5618-b57b-6b719193fab5 | note | • Class 2 - As per Table 304.101 - VR Spec. 304.10
5411b274-34b7-568a-9109-0bbdfee22171 | note | – – – – – – – – –
7db49cc2-e571-5408-95fc-2d7c2e7f43da | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
a2d7a8e7-1e21-5f27-b7c4-d65a488bf58c | note | – – – – – – – – –
d780c832-9aab-51f5-9d27-05340ec2f6c2 | note | INSPECTION/TEST METHOD: Test point
425ec9cc-b0d7-5b9d-9559-5f470d455d41 | note | – – – – – – – – –
eff466c0-c7bb-5495-85eb-8c343fb78666 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
589d873e-8d9c-5808-a63c-b6c39a914cdd | note | – – – – – – – – –
0d09ae10-a9b5-59d8-af4d-8d1c9c570d80 | note | TP
8b1e0c70-81a1-5957-9242-d58d28bc752f | note | – – – – – – – – –
b01029eb-bdd1-5624-ad06-5ce01dc9248a | note | RESPONSIBILITY: Site Engineer
19c9583d-0af0-54d7-a22d-f35a2acd65e9 | note | – – – – – – – – –
7abff12a-29ab-5328-ab9b-af0e9aaf99af | textbox | DATE:
f8b38b94-1425-49b7-b410-405fabd241bd | checkpoint | 3.5 Plasticity Index - Post Compaction (Class 2 & 3 Only)
54780efe-60a4-5558-8237-a5493c4d64ec | note | FREQUENCY: First Lot Only
5cb6429d-fb04-596c-b19d-8ee01fb208f3 | note | – – – – – – – – –
d9ad298e-12f7-53ea-b9c7-362050eac565 | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
2efaa5b9-d632-5b62-9c87-727b8a53baeb | note | • Class 4 - N/A
5733f1f1-0f5d-5eb0-ab5f-ddda06780356 | note | • Class 3 - 0 to 10
18e73298-a30d-5dcc-880c-f76389df29b1 | note | • Class 2 - 0 to 6
88006f31-2899-55a1-b042-a5511104c485 | note | – – – – – – – – –
1f34aaf0-f946-5889-a5c6-56d61466edef | note | REFERENCE DOCUMENTS: Cl 304.10 Cl 304.11 Table 304.103
1798b26c-ac6b-59cd-8177-f40e30a69a26 | note | – – – – – – – – –
a4590d5f-c892-5de3-bb18-86fa36abfcd8 | note | INSPECTION/TEST METHOD: Test point
7bb12ab5-fa43-5f8c-87d7-d6ad0c3e72d9 | note | – – – – – – – – –
f7b57a79-6bdc-5391-a2e4-bdc9f09de51f | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
da2e2f39-da23-57ce-af5c-3adf9fed2e3a | note | – – – – – – – – –
54c9ab1e-17b3-5101-b64b-4c64d864dac4 | note | TP
a793af19-a506-58a6-a8bd-8b20875b823d | note | – – – – – – – – –
9e9d26c0-66b4-564d-8b5b-2f794ca682a0 | note | RESPONSIBILITY: Site Engineer
47df94f2-1dfc-5ada-95fe-667431d514db | note | – – – – – – – – –
5c533218-2595-58ff-81e7-5e2dc620ad54 | textbox | DATE:
e1d50f31-f0cb-4925-bb58-e0a7a747c77f | checkpoint | 3.6 Survey Conformance
3e587223-3d08-5a1b-9253-18923a92037a | note | FREQUENCY: Each lot
0b2d7d85-a056-53a7-98d5-4ef7c96bc43a | note | – – – – – – – – –
e32ab184-58ce-580c-9199-dc13396434a6 | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
93b3da92-33b5-52e5-bfa9-274e9d9eeb5d | note | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
8c9fc8f2-e90a-5f2b-b523-5c090d557ffe | note | ○ Surface level tolerances:
f01b66cc-e8ba-5bd8-88f9-fbf7d6b4d684 | note | • Range x = +6, -16mm
fa32fad2-867c-5d18-befc-49d723d90f7d | note | • Max S = 15 mm
3aa940c0-1174-55f7-8251-1f2fd7792b5b | note | • 40 measurements per lot (Minimum)
e1bdfde0-9eae-5b49-a1f8-45df5c4ed96b | note | – – – – – – – – –
ec0806ed-01df-5c6e-9ca1-c3cc2a99e4b1 | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings Table 304.062
54033558-ae93-5fea-8e60-36f5aa899aa9 | note | – – – – – – – – –
a9c7d798-188d-5ede-aa8e-f168e0187667 | note | INSPECTION/TEST METHOD: Survey
24b5680a-3ebf-5401-b162-37182c8ee95f | note | – – – – – – – – –
c57244f0-a4e1-5b62-804a-55fe2235cd5d | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
b337c876-6dbc-54b3-878d-412124eb707f | note | – – – – – – – – –
3626baef-30d4-578b-8e34-0c734663455b | note | SCP
534ca622-e513-5b93-bc10-a2819595d4c1 | note | – – – – – – – – –
ce36c877-6b28-5ff2-b3f4-39c41c462afe | note | RESPONSIBILITY: Site Engineer/ Surveyor
30132521-b66f-570a-9a77-4273f0c4e2eb | note | – – – – – – – – –
c15616d3-8ab7-5ed9-8afd-0f92304a60e2 | textbox | DATE:
53cd9a09-eeb7-4db5-8437-51004ea8a141 | checkpoint | Final Inspection
7d2baa44-9f77-5ba8-90f6-6da38d68187f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5961ee91-7246-59c1-9e4b-1aabb27640f6 | textbox | Print Name:
79261bbd-4ad9-517c-b115-34bcf85c33b8 | textbox | Position:
b3698eb3-3cc8-5799-8446-fc7cbece228b | textbox | Date:
d8f6abd4-20c6-435a-ac3b-1fcc82c85756 | checklist | FHC-ITP-006 - Class 3 Crushed Rock Rev3 | itp | FHC-ITP-006 - Class 3 Crushed Rock Rev3
a30e4c7e-9a5e-4b1c-9102-233c8de77683 | section | 1 - Preliminary Works
ea1bd294-bb7b-461b-8025-3b80249702d7 | checkpoint | 1.1 Check for correct documentation
e151b9e9-bd36-5db5-8d7a-fe9a0db004b7 | note | FREQUENCY: Prior to commencing any activity
11b93b0b-c312-5e9e-8116-1d7b9b6d682a | note | – – – – – – – – –
7fff74da-b562-5e3e-bb1f-394c4f6d2b83 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
8111b207-dce0-511e-9158-be666ca44505 | note | – Using the correct and complete set of drawings
0dd3588c-a2ef-55e2-b716-987a264d273e | note | – All drawings are the latest revision
cb88a438-3b37-546a-a257-e79144d9d0c9 | note | – – – – – – – – –
e2f29c5d-994e-58f9-85d0-1850fb2b83cb | note | REFERENCE DOCUMENTS: Drawings and drawing registers
66cb3191-bbac-5d17-af17-cd557994486e | note | – – – – – – – – –
11cc1e07-1830-5c46-99d1-86dd342c4549 | note | INSPECTION/TEST METHOD: Visual inspection
9a030bde-b5ac-5077-8da8-1ae61a37e432 | note | – – – – – – – – –
da0e6719-f2dd-5e0a-9c1a-e7d56cd8014a | note | RECORD OF CONFORMITY: This ITP signed
9dde0721-2bf1-5b5f-a414-da229c3b8820 | note | – – – – – – – – –
c2c2e81f-901e-5a92-be9c-f66ed0a3f861 | note | HP*
60f3a13c-c04d-5b8b-93fb-c7598acb7bea | note | – – – – – – – – –
cd156557-2154-5c3a-9cae-947a6a7ad4b7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
d4d08293-e48c-5c7f-a5b3-5e13486bce3d | note | – – – – – – – – –
1f6abf40-be81-51ec-9cfe-520322c05d5a | textbox | DATE:
ef2d7601-9469-4167-8f89-d566d314c6b6 | checkpoint | 1.2 Material Mix Design
2b50e18f-7dcd-5db0-995b-1e594188c355 | note | FREQUENCY: Prior to commencing any activity
83fd1e27-6fe9-5469-9b57-f78b1b9a9b84 | note | – – – – – – – – –
d383a059-ceec-5f98-b60c-39983c318d9e | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
d8db8125-9a99-5c99-8670-11bc3c35a963 | note | – – – – – – – – –
65843d6d-c28d-5654-84af-9797b7b8f8fe | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
1b1bf21e-412e-543e-8dbf-41b9b903166f | note | – – – – – – – – –
98b7c2cd-f951-59e4-b604-d0064e78d9fa | note | INSPECTION/TEST METHOD: Document Review
affacc0a-f72b-566a-acfd-e4c45a2aa09c | note | – – – – – – – – –
ca5104cf-ce72-51f8-8dfa-e50b214f24dc | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
600b2b07-ede6-5d59-854f-be601d2fa9b5 | note | – – – – – – – – –
cf6be215-34be-59c6-9891-5792e17d4c14 | note | HP*
9d27045c-2451-596f-b8b3-af6667dcb7f3 | note | – – – – – – – – –
60cd0eff-fc17-5147-a313-96d1cfa286df | note | RESPONSIBILITY: Site Engineer
673b60d5-d269-59b0-86d8-17f2cc275715 | note | – – – – – – – – –
c1d5fc14-f866-53f3-9464-0d25127f5570 | textbox | DATE:
211eb33f-25bf-4a0e-83f2-168019cfbca8 | checkpoint | 1.3 Implementation of all measures and controls
1fbc8bf0-fc69-5cde-a6d2-6b7ebca58eab | note | FREQUENCY: Prior to commencing any activity
666c6ee7-00a8-5596-9e06-0ff141b0c8a2 | note | – – – – – – – – –
2d013906-4363-5e30-8690-eb4899c9ed16 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
33132e12-8b59-576b-b4ae-896cc65f719f | note | – – – – – – – – –
b7e13e40-8523-51b7-bf92-af14a0316dfb | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
2005c1ce-13e0-509b-8484-5ed1a1755a86 | note | – – – – – – – – –
506b0104-4589-5f07-9f2e-6da39aed2573 | note | INSPECTION/TEST METHOD: Visual Inspection
68f11b69-12d9-50f9-b54a-f86e1479883f | note | – – – – – – – – –
8e0432b3-685c-5704-ae1e-664458eb2a13 | note | RECORD OF CONFORMITY: This ITP signed
dfb16a33-8b1e-54dd-9ea2-18d24a5af2b5 | note | – – – – – – – – –
c355ace3-f08b-53f7-a15b-9fb4fb1a1dc4 | note | HP*
f1592848-8106-59ac-b9bf-82ef9ad89cbb | note | – – – – – – – – –
69cc6efc-bfb1-564e-9e11-4ebb2d0e34ee | note | RESPONSIBILITY: Site Engineer / Site Foreman
cb34e07d-1fe9-5f42-85cf-dff173fa2724 | note | – – – – – – – – –
8f54dc11-0821-5bf3-9a07-c4a68525f9b8 | textbox | DATE:
3fbbe2a0-4b56-4a45-a7a1-238e82c53326 | section | 2 - Construction Works
f83048a3-aa1c-4bdc-99aa-a30ea1992ef5 | checkpoint | 2.1 Transverse Joints
17f35af6-e587-5a8b-9591-fa64c4075132 | note | FREQUENCY: Check prior to placing material
e0a74f98-1aea-5214-9a80-a5e8f7406e19 | note | – – – – – – – – –
787c94b2-50ce-5be5-9fe6-d1d0fbe9e56b | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
2aee5cf6-8f0f-556f-9a56-316d33168a7b | note | – – – – – – – – –
46db11f2-2bfa-5e34-880f-1a1a2406c2f3 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
170066d1-5de0-5501-becf-0c6d72181966 | note | – – – – – – – – –
c0632b07-e8b4-557e-b5b8-be83fbfe937a | note | INSPECTION/TEST METHOD: Visual Inspection
4029a8d5-32cb-5ca3-9b8e-1a0a00625571 | note | – – – – – – – – –
207b0046-e86a-58e1-a756-8014f65e47cc | note | RECORD OF CONFORMITY: This ITP signed off
d3d6dd73-9dca-5358-8f8b-88370fc9f62f | note | – – – – – – – – –
2f0188bc-e76d-5c00-a10d-a6edf6742215 | note | IP
8fa69a21-3a8a-58c9-af5a-eb6edcb78b7d | note | – – – – – – – – –
a0314594-b3f2-5c2f-ab67-405888afb197 | note | RESPONSIBILITY: Site Engineer
5231d98e-dc5c-50f1-aba5-7ce01c41a922 | note | – – – – – – – – –
dee827a9-f3d9-5669-96ad-13aceba525e0 | textbox | DATE:
1e23a84a-6681-491a-a9a2-29739e0467b9 | checkpoint | 2.2 Longitudinal Joints
daf01f4b-5b90-5be5-a895-e3358791bb6d | note | FREQUENCY: Check prior to placing material
983376c5-1038-532a-8f91-d48f759a7b27 | note | – – – – – – – – –
21d15db8-1da0-56dc-8121-f3bdc7d6179e | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
f5ccca38-55a4-5364-b726-530921fbfa9e | note | – – – – – – – – –
33d23ac9-55c3-57a2-8d54-4f025fa1790f | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
5766097a-3d01-521b-9af1-63aeffb88fc1 | note | – – – – – – – – –
94c2f87f-5002-56f4-9bc1-ecd71df020be | note | INSPECTION/TEST METHOD: Visual Inspection
9a5c1d97-b1a9-572f-8522-c3fdc8d50ee8 | note | – – – – – – – – –
db2f34a3-edf5-5678-aa59-0b2e6b67b49b | note | RECORD OF CONFORMITY: This ITP signed off
1eb5c4c3-783b-59ee-a609-8fd3da8cc234 | note | – – – – – – – – –
6e6ab02d-fb70-55e4-9f74-82c9d6efcd37 | note | IP
dfabebcf-5354-5de8-8012-ed42ca5b7164 | note | – – – – – – – – –
df61708b-3eb0-52f4-8c8a-05c91f9aeddc | note | RESPONSIBILITY: Site Engineer
75458774-f0dc-5a5b-8dab-86b22321f66a | note | – – – – – – – – –
c63e4c6e-08b9-53a1-b579-598da4acfaf7 | textbox | DATE:
05c5a61e-a7c3-465a-952c-68f07c2dd3d5 | checkpoint | 2.3 Lot Size
1f8852ad-29fe-533f-ba32-793d814098a7 | note | FREQUENCY: Check prior to placing material
e36c8554-e421-5b5b-a2d2-822feb5de47c | note | – – – – – – – – –
73b78eab-6293-5db1-bebf-f7a56f2d3bf0 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
5296bf04-92f2-5768-88bc-2cacad1fd934 | note | – – – – – – – – –
5b2e99fd-85a6-5957-bcf0-6ea2fb761c2f | note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
2aa8ac8e-0096-5409-b427-1920ff86ccc4 | note | – – – – – – – – –
598c9d68-dc18-5796-9262-f2f9d9afed28 | note | INSPECTION/TEST METHOD: Site Inspection
a02a805b-133b-5c29-a0b4-6c3983332c23 | note | – – – – – – – – –
b554507d-2a3d-56e6-be60-3daf174e8387 | note | RECORD OF CONFORMITY: Signed ITP
1d9053bc-c8cc-5e24-a413-03f782d5736a | note | – – – – – – – – –
e1e3ec90-f8dc-5df6-800b-19c5e2438598 | note | IP
698dce88-573c-5352-9a19-04bd2345aeea | note | – – – – – – – – –
ceff557a-4ca8-5c0d-880d-24d404024856 | note | RESPONSIBILITY: Site Engineer
9628b130-4ba1-50de-b271-930932d0c1f6 | note | – – – – – – – – –
5125f59b-63df-53b9-ac20-938679d11314 | textbox | DATE:
4e517ead-0eeb-48c3-8449-609a7744cfa1 | checkpoint | 2.4 Layer Thickness
ec4dff1c-b0a9-5722-b10e-d0f29ae5a5a4 | note | FREQUENCY: Each Lot
2ad2e794-d704-5d71-bbaa-33071cff2248 | note | – – – – – – – – –
96146336-5dc1-5817-9729-fbb4ad0d7c9d | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
a87d48ae-34a1-580b-b279-cb5dae2496fb | note | – – – – – – – – –
cf25db32-329b-57d1-b6f7-d33d8546975c | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
628d6d65-a49b-5087-b7b9-7e46c06c8c08 | note | – – – – – – – – –
a9c69790-32e8-5f28-ba9c-6a31fa930d7b | note | INSPECTION/TEST METHOD: Site Inspection
e1d01bdb-875e-5a98-8697-b0d3d7198134 | note | – – – – – – – – –
143a095b-0237-5bb1-8c1c-4894291dea63 | note | RECORD OF CONFORMITY: Signed ITP
4c14536f-58d7-5b6e-a8d9-a5d85e059be1 | note | – – – – – – – – –
680ccded-009d-55ef-8014-da7893ea21ef | note | IP
e36a67ad-7b2e-5cec-a262-2ce38a076c3d | note | – – – – – – – – –
b5201ec7-8c10-550e-8ca1-bd50b24fb44a | note | RESPONSIBILITY: Site Engineer
2b4927fb-1c33-5541-8841-9062eab0cad9 | note | – – – – – – – – –
3a3e08e2-11ad-54f5-8f7a-8230b3ef463f | textbox | DATE:
81b797cc-fb9c-44d0-be8b-feeac677ec49 | checkpoint | 2.5 Proof Rolling
52d2c6a2-f3a1-5dc6-86e9-5e3ff20df4d9 | note | FREQUENCY: Proof Roll each layer
3df5926a-9060-519f-a412-da4b438e9b8b | note | – – – – – – – – –
b232b218-d122-534a-960c-3b71778f95fa | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
5b8d3160-72f6-5c59-ad88-b66ec7294bad | note | – – – – – – – – –
24d2a678-d7ce-50bd-95c1-6338b2183a52 | note | REFERENCE DOCUMENTS: 173.03
e06f7188-acd9-574a-8125-a952be54d864 | note | – – – – – – – – –
3e0dced7-f711-503e-81b1-9903bfa1f59b | note | INSPECTION/TEST METHOD: Visual inspection
7bd32565-516e-53d9-9ffe-18a07ed52711 | note | – – – – – – – – –
a269afc7-384c-575c-8551-cb2be6c723c0 | note | RECORD OF CONFORMITY: This ITP signed off
819d2fd6-772e-56c9-8e3c-e4538e15aa47 | note | – – – – – – – – –
236e4c95-f34b-5b24-84ed-35e485ef50cb | note | HP/ WP
16bcfad2-8efd-5767-86ef-fe26db4704d7 | note | – – – – – – – – –
99a1053e-a594-5b04-bcef-e4f5aa6c53b0 | note | RESPONSIBILITY: Site Engineer & Superintendent
212045ba-772a-5abc-9f48-7897d22c91ef | note | – – – – – – – – –
5256c0e4-8190-5fdc-8608-9a65f1be2eb0 | textbox | DATE:
693d91aa-00e1-4968-978d-05ab96356590 | signoff | AUTHORITY HOLDPOINT
4cd5ffa2-e422-4c1a-becd-55b62bf656a9 | section | 3 - Testing Requirements
a332993a-8dcf-4008-9590-18d870fa218d | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
90cde675-589a-5d33-ac62-d95d6435257c | note | FREQUENCY: Prior to Testing
fea2a450-d847-5925-9e0a-9b52d3744c71 | note | – – – – – – – – –
9b37128e-defa-5805-9966-94ef020f6757 | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
f19a698f-fe27-5f82-8676-7e1f20c0da04 | note | • Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
b72cb5a7-9290-5516-9baa-046db6a56bd4 | note | – – – – – – – – –
bfbf863a-8be7-59f1-a444-bca11dee8050 | note | REFERENCE DOCUMENTS: Table 204.161
0aa915e8-32bb-5cac-824a-38229da08fe0 | note | • Cl.304.08 (a)
bc84ca9d-9d2b-5c6c-b056-81382c91b508 | note | • Cl.304.11 (b)
d9b6c677-189b-58a5-8f62-6df4c4d31788 | note | • Cl.304.11 (c)(i)
a99ff2a3-a4cd-5bcb-aee6-008d18564efd | note | • Table 304.111
a25b84fd-1f46-5804-b072-42f422740e1f | note | – – – – – – – – –
bdc64e77-0549-5383-8fd6-b84d13ae69db | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
d362771d-d3cc-511c-b769-606057e43bcc | note | – – – – – – – – –
efa50231-b30c-57b2-8fac-00bd64bb429d | note | RECORD OF CONFORMITY: Signed ITP
7f1ceeba-93a1-554a-8de8-637fd42a9225 | note | – – – – – – – – –
b78da926-4233-5b3d-8299-7b60eebb7699 | note | AP
e6f10b78-dafd-5de3-9358-92e3ffc6ab3c | note | – – – – – – – – –
792044a2-2c2c-53e7-8dd1-d808a40a3b2b | note | RESPONSIBILITY: Project Engineer
be5635f7-c197-5ab3-9fd4-3bb72d5d7479 | note | – – – – – – – – –
a42c7ccf-1c9f-5df5-89fa-73f87cf1408d | textbox | DATE:
00355920-f961-47c7-80a0-5c0a7f37ddd4 | checkpoint | 3.2 Compaction Testing
22b3a4b3-f2f3-5574-81ab-8332213c3a29 | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
c891e039-2ecc-5e5b-8f59-2867e2908e05 | note | – – – – – – – – –
a3502877-5b9e-5622-beb3-18071228161d | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
5e792dc8-e959-5a1d-9170-1b023dae43e5 | note | – – – – – – – – –
135f9704-7ab6-5f71-903a-b072515aac3b | note | REFERENCE DOCUMENTS: Cl304.08 Table 3040.061
b89c49f6-d675-5748-a446-e387a3a1a022 | note | • Cl 304.11 (b) Table 304.111
a4550e92-db77-5616-ae5c-f8ff8431c438 | note | – – – – – – – – –
94c727ae-68ae-5a34-b01a-b67bd677f4c0 | note | INSPECTION/TEST METHOD: Test point
142275f9-8424-55d5-a3ee-fa072dbfdce6 | note | – – – – – – – – –
b3e38774-22e8-5c46-ad58-e75c6ef73c81 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
59cb9d17-d5e5-507e-9163-09abc0797945 | note | – – – – – – – – –
f08a77e3-d4c6-5535-ab0e-fb38dd79c362 | note | TP
26a55c17-db79-535b-a082-d09a27d0d833 | note | – – – – – – – – –
afb063a3-5ee3-5485-9a56-9eff598cc330 | note | RESPONSIBILITY: Site Engineer
aa7fcebd-88f4-577f-94a0-0e6dac35c31c | note | – – – – – – – – –
7c0451a7-bd6a-5a60-a127-dc34181aec98 | textbox | DATE:
d12843b3-9f02-4c68-9c89-374dc79c0d53 | checkpoint | 3.3 Compaction Testing (Small Lots)
135848c1-d5f4-585e-bc94-c8dfad0edd80 | note | FREQUENCY: Each Lot
e5b02bd7-e56f-5536-8070-657456fae21b | note | – – – – – – – – –
e19d8d97-a66e-5326-9a35-024570d6ae1b | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
4f8df1fb-192d-564c-86a9-0b10c649f25f | note | – – – – – – – – –
0a85665f-ccc9-5818-a771-29b07de86a1c | note | REFERENCE DOCUMENTS: 173.04 d
125b7ee4-c5f7-549b-b719-8415b6e7faf0 | note | – – – – – – – – –
237fc9fc-cec8-5a9e-b400-61ca13949219 | note | INSPECTION/TEST METHOD: Test Point
07707553-6591-54f5-8c77-8d56da97f349 | note | – – – – – – – – –
5dcc7846-5bdb-5568-b8a3-718fb3aabd9b | note | RECORD OF CONFORMITY: Test Records, Lot Register
525f6ac4-7adc-5661-a67c-1ec556f4bdd3 | note | – – – – – – – – –
4e43ad90-170f-5bec-8640-84821cdc501f | note | TP
b9a12272-f51a-51f0-849c-83621640b952 | note | – – – – – – – – –
d22ba784-98d1-5e6c-853f-5c7fa114746c | note | RESPONSIBILITY: Site Engineer
92f24bda-ca88-5e4d-843a-d845f61d9751 | note | – – – – – – – – –
7fda187a-2aa6-5c93-8f6b-45314e31fa58 | textbox | DATE:
b1097e39-ad16-4dec-98e9-25a00ff41656 | checkpoint | 3.4 Material Grading - Post Compaction
177a29ab-0738-5c3a-89ab-b87af58d368f | note | FREQUENCY: First Lot Only
9316fc65-600c-5339-8b92-abdb58983153 | note | – – – – – – – – –
b1c23368-af72-5ff5-b3b7-b6c3f32676c1 | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
e1ddd6d4-2f56-5cf7-9e14-d3aaf0753aa5 | note | • Class 4 - As per Table 304.101 - VR Spec. 304.10
179a4ed7-cd99-5554-b977-b2ce6c5a45f3 | note | • Class 3 - As per Table 304.101 - VR Spec. 304.10
3300762d-a3c0-5f19-8baa-905c9ffb7219 | note | • Class 2 - As per Table 304.101 - VR Spec. 304.10
552a6e99-4dc8-5bc4-b11d-c60a52560bd4 | note | – – – – – – – – –
dc66a390-a4e5-52d4-bd11-2a7e7f2ab6bc | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
1d412e35-133c-58bf-9081-458d520de803 | note | – – – – – – – – –
af3373f4-4db4-5c71-a123-aa94b4d808e4 | note | INSPECTION/TEST METHOD: Test point
3de18131-4689-5500-96b7-9ff58e9b51ef | note | – – – – – – – – –
45ebf700-3e14-5704-b708-9a039d5149ad | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
8c14f0c5-72bf-53fe-989b-67721a10da8a | note | – – – – – – – – –
c551db7f-ee9d-5598-9d4c-3dbf5b40138a | note | TP
0c98dbc8-1cad-5b02-9ce6-795f3e82d24a | note | – – – – – – – – –
4a75e285-9865-5560-a642-818f73f092ea | note | RESPONSIBILITY: Site Engineer
938b01fe-5574-50e3-bdaf-21f5f15b8f16 | note | – – – – – – – – –
1f1eff70-bea5-5689-914f-5269bbb39be6 | textbox | DATE:
8d05e8a5-ccf9-4f75-b1d1-22d5fc50ce4f | checkpoint | 3.5 Plasticity Index - Post Compaction
b3efafda-632b-5dd2-b9a7-81bada3e6eac | note | FREQUENCY: First Lot Only
0c40b72c-b88f-559b-9771-5d850dab090c | note | – – – – – – – – –
e17fc843-757d-5935-92a6-712a99aa541b | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
425bcc13-1073-5ab2-9fd4-91f1b1e29f5e | note | • Class 4 - 0 to 10
e8c6445b-eb62-5d38-a7ee-b0fbf229bac9 | note | • Class 3 - 0 to 10
322bdbf6-8223-5ec5-a9ba-5d79fbc1b118 | note | • Class 2 - 0 to 6
155885c5-e8cb-599e-b40a-3ef4b2e6679b | note | – – – – – – – – –
c10c338d-c201-53c4-8c87-05d2bfe0dcad | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11 Table 304.103
83d87a3c-1314-5c54-bf5a-06f61cdbe01d | note | – – – – – – – – –
f996819f-ec51-52cc-9036-f8557b39a14e | note | INSPECTION/TEST METHOD: Test point
f21133e4-8c0c-5ce9-b7f8-3655fce0163e | note | – – – – – – – – –
07aefd5d-abc5-5f17-a40f-c7ed40d4a52c | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
a357b240-0b28-5132-9845-ae6c5bbe09c7 | note | – – – – – – – – –
198af113-f1d1-594a-8708-60a65dec3f3f | note | TP
d976e4ce-b7bd-53fe-bdc4-48e8549d3062 | note | – – – – – – – – –
3bef3db4-8e68-5d45-87c5-0c08d90bcdff | note | RESPONSIBILITY: Site Engineer
2687e302-9d11-5cd6-aa72-1b1888adab96 | note | – – – – – – – – –
4f4a5edf-56c1-54d5-9890-e23d92ec450a | textbox | DATE:
85dddfc6-64bf-42d4-bc55-0499d5e74f30 | checkpoint | 3.6 Survey Conformance
9d460925-9ea9-533d-9249-0076dffba24c | note | FREQUENCY: Each lot
5013764f-062f-529a-b3cb-f960e19abf10 | note | – – – – – – – – –
ad14a049-5775-5de1-87b7-c44f6df5e994 | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
25094ce2-bb2a-5f38-9e4d-53765d6630ee | note | • Shape: no point deviation > 8mm from 3m straight edge in any direction
e4d14b6f-5d5c-557c-8761-cc2c5907dd77 | note | • Surface level tolerances:
a0340739-fb66-589f-bec3-5e250b486584 | note | • Range x = +6, -16mm
d6024a36-4fd1-5a94-83c5-3f5adb4b4cb8 | note | • Max S = 15 mm
df6ac1cf-6523-51ed-9949-04dc45da3b22 | note | • 40 measurements per lot (Minimum)
ecab63ee-14ea-5986-8792-783ffc059d40 | note | – – – – – – – – –
b9f0ddbf-85bc-519d-ab39-68651a1d8e2b | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings Table 304.062
8c883d5d-1c96-5788-9ed5-ec2fb686986b | note | – – – – – – – – –
94ed5097-40a4-5aa9-bb16-c867af4e7a46 | note | INSPECTION/TEST METHOD: Survey
c7049e8e-df5b-55cd-8894-f5cb4ad83c0a | note | – – – – – – – – –
e47fb5c0-5d39-54c8-87bc-600226d25e2d | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
466b6f91-c90f-5f86-a1d0-5f545b52b496 | note | – – – – – – – – –
aa44a9a8-a747-538e-82ae-41335b9706b2 | note | SCP
76e19809-d0da-566d-8aa2-518c3bf11f48 | note | – – – – – – – – –
e68fecb0-f1a0-569b-a231-34ef65e0478d | note | RESPONSIBILITY: Site Engineer/ Surveyor
9cdf03f3-77e5-57f1-bffa-5d99d991463a | note | – – – – – – – – –
869b632e-0b5b-54b4-9bc6-636964e883f4 | textbox | DATE:
2269a98a-4fbe-4c5c-8a7e-79fc28468fe2 | checkpoint | Final Inspection
478136e9-6bd5-51a9-b7f4-b31a2a865e77 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
75c24828-54be-5571-b557-932ea6a1040a | textbox | Print Name:
5a33e069-5b20-5ca4-951a-f3944d7e1334 | textbox | Position:
db5f45c4-2b8d-50c9-99c6-9a221304e55b | textbox | Date:
7e65a7e5-d482-41a6-99d8-29409d589aca | checklist | FHC-ITP-007 - General Demolition Rev1 | itp | FHC-ITP-007 - General Demolition Rev1
debcca96-6870-4024-8e76-4f712e75f78e | section | 1 - Preliminary Works
8d3a6e5d-2184-4646-8936-cde6f2473701 | checkpoint | 1.1 Check for correct documentation
df6012eb-90d8-578a-a14e-e4ff0b7fc480 | note | FREQUENCY: Prior to commencing any activity
597e5149-918d-5ffa-8294-01257c2e61b9 | note | – – – – – – – – –
a08c2ad1-8e96-5ea3-b856-b25c5ba5c733 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
52c16e84-73f5-5171-aa4c-b116a74852ca | note | – using the correct and complete set of drawings
03acd100-5975-5275-8cb4-6a2bfa2aac22 | note | – all drawings are the latest revision
0fbff04b-1d0d-589b-96f5-21ca69f0eb61 | note | – – – – – – – – –
5514b563-ff63-5656-ae25-8fa8a2b465eb | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9121c074-aae7-5df2-b252-d09964df6ec0 | note | – – – – – – – – –
e6f53646-eef1-52a3-90c1-9715f4d14dc4 | note | INSPECTION/TEST METHOD: Visual inspection
bd7877ac-023e-5a8e-8f34-07bd8586ce84 | note | – – – – – – – – –
50852312-2e56-501c-97d0-99c88668a14b | note | RECORD OF CONFORMITY: This ITP signed
bb07ad05-2b78-5609-95b1-bb07d1ebb3ae | note | – – – – – – – – –
552aaf4b-31ab-5ea0-b962-a13dfe20db14 | note | HP*
c42d969b-c983-5f23-8ab3-99f29176ab09 | note | – – – – – – – – –
bc147509-bc74-5c27-856d-4f5a88943091 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
b760f9ee-9c08-579f-94a3-5576983b6c34 | note | – – – – – – – – –
750f67fe-048c-59b5-9901-40f9492837dd | textbox | DATE:
b9021a4f-23f5-4371-a586-f066c07d15af | checkpoint | 1.2 Implementation of all measures and controls
3f157a80-4b3c-5e09-956d-90174093ffd2 | note | FREQUENCY: Prior to commencing any activity
f40c649a-aa79-5603-8623-ec5c4867b53c | note | – – – – – – – – –
cdb1f75c-b8bd-5369-9769-6cd46525f410 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
4b15cce4-21b1-517d-86e9-9ed8ed48fc14 | note | – – – – – – – – –
8e3a6076-441a-51ab-a2a2-1bb1ac334733 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
8494aa4f-676f-59aa-b090-48a3e3c68aac | note | – – – – – – – – –
def16d3a-697c-50fe-b77a-3161f06f5f54 | note | INSPECTION/TEST METHOD: Visual Inspection
121d3109-dc0d-5239-a058-221cd0ea5bb2 | note | – – – – – – – – –
6d4c2168-7e94-52a3-b966-fcf3ccd9f2a9 | note | RECORD OF CONFORMITY: This ITP signed
c6e4b942-d1d0-5514-9868-2b52ad76332c | note | – – – – – – – – –
39a7d4e9-6d9b-5d6e-a472-206e2e390623 | note | HP*
d428a88c-bbab-54c6-8edd-8166b961346a | note | – – – – – – – – –
be7be447-b29f-51d4-8154-be64adc65d0d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
ae17996c-7529-56a0-b3b1-9483c93ff714 | note | – – – – – – – – –
89f5945a-1176-5080-9e3a-de60b3af7077 | textbox | DATE:
877c5abf-0715-4661-9780-b28f1ba6a43e | checkpoint | 1.3 Service Identification
a669f715-54c5-55bd-af60-823806b96bf3 | note | FREQUENCY: Prior to start
bf45c9ef-c6ad-59e2-874b-44620dbd9171 | note | – – – – – – – – –
8fa82c07-1c42-5db4-9f5c-a82a43c517fd | note | ACCEPTANCE CRITERIA: Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected
d31140b0-f219-5761-a670-225281b5af1b | note | – – – – – – – – –
e7779ca6-c1ec-5026-97ea-a134f58dd100 | note | REFERENCE DOCUMENTS: ITP sign off
c15fc12c-d20f-5c12-858f-a57ece666502 | note | – – – – – – – – –
b58e406a-d431-5252-8954-eb1178e594fb | note | INSPECTION/TEST METHOD: Verify
5484943b-9935-5885-a082-b086affe6d36 | note | – – – – – – – – –
793e7e3e-47e6-5be3-b9e7-f4c9b28b3d4f | note | RECORD OF CONFORMITY: This ITP signed
987641a3-566a-577a-bbc2-a407afa54202 | note | – – – – – – – – –
9cd54f6e-aa05-5f60-ad65-6f8ab9f41033 | note | HP*
453c1f05-9ddc-57ba-aa55-754374bc1138 | note | – – – – – – – – –
8525759e-4f70-5675-becb-a840bcde690d | note | RESPONSIBILITY: Site Engineer
df6001f8-e7ff-55ef-9228-5954dd79c4d7 | note | – – – – – – – – –
bc340cc3-2e3a-5523-ab5c-bf3248e505ba | textbox | DATE:
e3292e98-9bb7-4b31-85fa-ac1135bd6c05 | section | 2 - Construction Works
14b66475-10e4-458b-8013-0a388d21837a | checkpoint | 2.1 Saw cutting
727daec6-5eed-5736-8cc3-3b2798186985 | note | FREQUENCY: Where required
9693ac95-5907-56ab-baa6-f42b227d1b06 | note | – – – – – – – – –
ead4b070-dae9-5501-bbb2-42b960bdb031 | note | ACCEPTANCE CRITERIA: Extent and location of cuts to be clearly set out and checked prior to saw cutting
e7c7243e-f9cc-5b7b-9cc6-0555b6fb8284 | note | – – – – – – – – –
92cb0043-0c5c-5480-bb9e-5a6af32b86fd | note | REFERENCE DOCUMENTS: ITP sign off
c7b0a1e8-7d97-58cd-a39c-1f9063da4b8a | note | – – – – – – – – –
8dc05b7d-20b8-5080-b4bc-49ba69d2b317 | note | INSPECTION/TEST METHOD: Visual Inspection
125ec3ff-0cc4-550f-bf01-890178f3ac34 | note | – – – – – – – – –
3310c1ac-86da-558e-aa6d-ae9077098848 | note | RECORD OF CONFORMITY: This ITP signed
8aacc636-807d-5d9d-a6a4-8ee36e4ad7f1 | note | – – – – – – – – –
e55c8fd1-ddc6-5844-8774-eca692eb4d9b | note | WP
89081531-3e9f-57a1-9f3d-a3158c5ed296 | note | – – – – – – – – –
dcbc86f5-d080-5a3f-8251-7618893f8c09 | note | RESPONSIBILITY: Site Engineer
779f61c3-b20a-5451-bbbb-f30c6c16ccf3 | note | – – – – – – – – –
227d9c3d-0ad9-5feb-8a18-e1b2bf4f142b | textbox | DATE:
1a68c326-710d-4fc7-a3d7-9133a1ea96ee | checkpoint | 2.2 Excavation Permit
0685f7c7-c41d-5b57-b2a0-613ffb04d61e | note | FREQUENCY: During excavation
d46bef5a-f8fb-589f-9417-b5ec8fbf7283 | note | – – – – – – – – –
9c4b8328-df8e-5534-afe8-24217a367567 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
fa2efc0a-d754-5b8c-899a-55593cd2eab2 | note | • Plant and equipment shall be appropriate for the task
bb6bc2b3-72ff-5259-9567-7ffc3bf98af9 | note | • Excavation operations shall not disturb areas outside the limit of excavation
3113516d-f65b-5097-b2c6-313ef624bddc | note | – – – – – – – – –
a1518f87-ef3d-55b8-905a-684331b3c66d | note | REFERENCE DOCUMENTS: VicRoads 204.06
1bfd7064-6869-5a66-866b-39b396096dbc | note | – – – – – – – – –
90007c2d-53c9-5d41-8856-283771962c3b | note | INSPECTION/TEST METHOD: Visual Inspection
606311c9-448f-55db-9493-dc0dff861d79 | note | – – – – – – – – –
c8be3115-8385-51bf-a376-6519d8956191 | note | RECORD OF CONFORMITY: This ITP signed
92acbd21-96b1-5eb4-b078-0c592eee8382 | note | – – – – – – – – –
76507a6c-970e-5ab3-9bd7-02f3901c557d | note | HP*
1460fe9d-a81b-5a98-84ea-1690c0fc50b2 | note | – – – – – – – – –
ef1c3eb9-408a-5f6b-b062-b293ff8259b4 | note | RESPONSIBILITY: Site Engineer
385f222b-84d4-58a9-a1a6-b42ed23aa6fd | note | – – – – – – – – –
1d6d3a3f-a570-582c-bf53-80699b506b8a | textbox | DATE:
800a5694-e03b-4120-b9d0-bfa0fe2af0ba | checkpoint | 2.3 Redundant Pits
e4778281-ee8b-50d4-96ad-403645e4658a | note | FREQUENCY: After clearing
e3c830d6-f4f5-588e-a3ff-e547cc09b138 | note | – – – – – – – – –
b53114d2-2a14-5c91-8fbf-3704b360719a | note | ACCEPTANCE CRITERIA: Any redundant pits, are to be removed to a depth no less than 0.3m below the stripped surface or no less than 0.6m below finished subgrade (wichever is lesser)
2153616e-fc39-5d3e-a43b-0ee2318d0dcb | note | • Seal any pipe openings with concrete and backfill pit area with material and compact to a density ratio of 95% (standard compactive effort)
06385c25-a0d4-56bb-b702-387f603e7a48 | note | – – – – – – – – –
7c48c1d4-9ed0-553c-b7e5-f5d88ddc3adc | note | REFERENCE DOCUMENTS: 201.05
0a303729-db6e-5d31-b7e2-8ac48f1326d6 | note | – – – – – – – – –
e111603c-9dbb-57d9-90a2-946a538003bc | note | INSPECTION/TEST METHOD: Visual Inspection
7a75ef14-ac91-5eb3-9680-412e7918bb64 | note | – – – – – – – – –
312571b1-0e79-50bb-bd74-edf045772242 | note | RECORD OF CONFORMITY: This ITP Signed off
57f334da-edaa-5cbe-9202-089be0994c02 | note | – – – – – – – – –
e668d7dd-7cc6-597a-8724-0ffc700213a9 | note | IP
ff45c08b-f710-5976-8743-ffca18365cca | note | – – – – – – – – –
ace237ca-d4e9-510f-8c09-6d88bf7ec78e | note | RESPONSIBILITY: Site Engineer
301b3fbb-7a4c-587c-bacb-fee71a0e564a | note | – – – – – – – – –
00293c63-2d0d-5bdc-8666-9379f942845b | textbox | DATE:
48054a26-24ea-4bda-92d2-14aab1066642 | checkpoint | 2.4 Disposal of Material
ad0aa656-2e53-516b-9e08-2173f6d60fd2 | note | FREQUENCY: All times
74a44bd5-3655-5614-b249-1e374ab22750 | note | – – – – – – – – –
d2f2ca37-322b-5586-8ce5-5746c600c896 | note | ACCEPTANCE CRITERIA: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
f70db071-1240-5e62-a8dc-afca0cf91a7b | note | – – – – – – – – –
f0978719-2755-54b0-ab5c-6c1f4548f0b4 | note | REFERENCE DOCUMENTS: ITP sign off
b4bdc89c-1c46-58e1-bee8-d5785f1da137 | note | – – – – – – – – –
45da89af-2f48-5ea9-b6b2-6bd468b29072 | note | INSPECTION/TEST METHOD: Visual Inspection
abd4e96d-c0df-52b0-9c54-9af5de0eef22 | note | – – – – – – – – –
0a3b6125-0485-59d2-8189-291ceebdd7f5 | note | RECORD OF CONFORMITY: This ITP signed
610df51f-bd81-5fb4-b384-b4e2bf41eadd | note | – – – – – – – – –
4c3d4887-aab9-561c-aa8b-92ed648da9c6 | note | WP
9fc922f3-890f-5128-854e-68524c24bc89 | note | – – – – – – – – –
1cb9b201-8a42-51a4-9898-61d4a8e3b73e | note | RESPONSIBILITY: Site Engineer/ Site Foreman
9063200a-3a87-5e32-a29c-fc1fee865a1a | note | – – – – – – – – –
0d5b66dd-3496-5691-a067-13bff9281e25 | textbox | DATE:
8f82c5e2-07b1-4fa0-bc57-f97d0a519488 | checkpoint | 2.5 Maintaining cleanliness of site
0b525960-4620-527d-ac8c-ecc5fe7df4b1 | note | FREQUENCY: All times
d54bb11a-8022-5ae8-a1ad-89bb00bfbd19 | note | – – – – – – – – –
2c8959b3-afe8-54cf-9c06-714e8c47c060 | note | ACCEPTANCE CRITERIA: Site and surrounding environment are to be maintained at a good standard of cleanliness
689ecdef-b563-565f-add9-078fbfb81894 | note | – – – – – – – – –
1cbc5927-6e3f-5da8-a3e2-763fa8418433 | note | REFERENCE DOCUMENTS: ITP sign off
9b623fe5-39c5-5f78-b88b-4e123883fb3a | note | – – – – – – – – –
2f809241-68b4-54b7-930d-b88b8105f5fc | note | INSPECTION/TEST METHOD: Visual Inspection
d7576e9a-0cf1-50c3-8d3a-e841cc38eb9e | note | – – – – – – – – –
e9236435-c2f5-5f6e-8c55-76b4224123c0 | note | RECORD OF CONFORMITY: This ITP signed
086a39ec-b509-5c1d-8512-c1aae7aa5876 | note | – – – – – – – – –
9dde9364-66ef-57a3-8ea9-df735ead8986 | note | WP
1c22771b-f83a-584b-9c31-042be18ee7b4 | note | – – – – – – – – –
0e320487-f627-5be1-b34a-da952ff4eacd | note | RESPONSIBILITY: Site Engineer/ Site Foreman
f05d5fbc-e001-562e-be00-4e5a44b8b431 | note | – – – – – – – – –
1dc3ee7e-2160-5af9-8d1b-bd06195d22a9 | textbox | DATE:
887194a3-4d74-44b0-a08e-fd90c2077e65 | checkpoint | Final Inspection
2139fa7c-c198-5879-81c4-07cd5b142c7e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
668c4a4e-961b-5c48-8503-f99336c42a9f | textbox | Print Name:
2efe18cd-257c-554e-92c2-f19f63ed6d06 | textbox | Position:
7f6e2996-d6db-51bb-97f8-a644809f941e | textbox | Date:
8e099100-e0eb-4258-8bc7-f6d625bd8534 | checklist | FHC-ITP-008 - Stormwater Drainage Rev3 | itp | FHC-ITP-008 - Stormwater Drainage Rev3
fa158688-5d9e-443c-84fc-f355e18c94a7 | section | 1 - Preliminary Works
649f09f6-1f07-4a6d-981e-1c4511e74fc0 | checkpoint | 1.1 Check for correct documentation
d546597f-d884-5247-91f7-7fadd0991924 | note | FREQUENCY: Prior to commencing any activity
c1e7eacb-7f25-580e-a761-9f347ddee59d | note | – – – – – – – – –
12286196-8f21-5353-aa4e-d8ead4dfae5d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a45291f7-c7cf-55f5-b5bd-15c0e8bcac59 | note | – using the correct and complete set of drawings
2b7690da-1b58-52dc-bb35-b6bf25065a9c | note | – all drawings are the latest revision
4abbfbfe-4261-5661-83cc-b22c6bb50938 | note | – – – – – – – – –
87b8b8e1-0c21-5b79-aeab-d01ba0bb130d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
226f4a7f-70ec-5895-864f-f35d8a2f7705 | note | – – – – – – – – –
37e1c3ac-ac38-5c06-ade5-dfdc80c596aa | note | INSPECTION/TEST METHOD: Visual inspection
696d026d-2b2b-5e92-817a-ab5dc160ed65 | note | – – – – – – – – –
5cad6e0f-71ae-5f56-8fe5-cf9ee6bb73fc | note | RECORD OF CONFORMITY: This ITP signed off
1f7be475-922f-52fb-a0d5-66cb35b2674f | note | – – – – – – – – –
470556db-cbe2-50bf-89b3-28ba318bc3e7 | note | HP*
1729a02b-16b6-5cad-b180-7ddfc3244b1a | note | – – – – – – – – –
ffadf36f-0ac7-5355-9888-4bd870c4a257 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c68eea3b-d1da-50fa-9488-6cfc0174d2e8 | note | – – – – – – – – –
25defbc1-3612-5880-8a26-7ee35ac02412 | textbox | DATE:
3e93a7ca-78a0-4db7-935c-513fc0c98024 | checkpoint | 1.2 Implementation of all measures and controls
7217330e-9596-5f49-84b2-ca8016a20635 | note | FREQUENCY: Prior to commencing any activity
204b6863-cbae-5a83-b66a-e14890462f03 | note | – – – – – – – – –
54d1ba27-6e6c-54c0-9499-3dce6f7e08f2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
2f1831ee-28f2-5211-85e9-19c1291dad22 | note | – – – – – – – – –
d208f134-1bf0-50f6-bdc3-bdc81e70f482 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
bccde30f-bd44-5ca7-abdf-ec4a2b395629 | note | – – – – – – – – –
0dbbbbaa-a743-5cf2-9c08-ccc229f8a87e | note | INSPECTION/TEST METHOD: Visual Inspection
94aa573e-4af5-5cc8-8eae-016b25360b98 | note | – – – – – – – – –
f8fdadce-b07a-5c91-824f-205a73bb2a47 | note | RECORD OF CONFORMITY: This ITP signed off
90192782-6410-5fad-b8fb-5f0b3ccb1574 | note | – – – – – – – – –
f94cda4b-4cd2-5705-abe1-f905b204bb64 | note | HP*
ad52ab76-9f84-5a5f-a7da-dd034f671817 | note | – – – – – – – – –
00d7677e-3551-5106-9638-0c6c4612f71e | note | RESPONSIBILITY: Site Engineer / Site Foreman
38cb39e5-b574-5b66-972b-c1cbab346ba9 | note | – – – – – – – – –
122bb4d5-81d3-55d1-9cc1-89b1cab2c293 | textbox | DATE:
894baee8-255c-42e0-95ef-747201e47920 | checkpoint | 1.3 Precast Materials acceptance
b6aef6e7-97e4-5010-b30f-e2ee02e718c5 | note | FREQUENCY: Each Delivery
faea7071-52d4-5a08-914f-acc7ca4dc5ff | note | – – – – – – – – –
6e536bde-fb88-5c10-82be-550d1dcd9d4d | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
6112cccf-7b47-5039-b990-73ec08b92cab | note | – – – – – – – – –
8234ae2c-a6d5-5d9c-888d-92d7077cab1e | note | REFERENCE DOCUMENTS: Cl. 701.05e
18ee3a6a-4253-5d63-b483-d78db4b5c877 | note | – – – – – – – – –
53793db0-7e96-56ca-ba2e-ed734daa93a3 | note | INSPECTION/TEST METHOD: Visual Inspection
ea54a42b-fbbe-5e50-b61a-2debcb6c8e18 | note | – – – – – – – – –
dcb886c3-bee9-54b4-b846-060554b18c96 | note | RECORD OF CONFORMITY: This ITP signed, Receival and Inspection Checklist
c83fcec9-472c-51fa-ac8b-7a42a0dd2eb5 | note | – – – – – – – – –
9787c41b-f145-5e57-a59d-151ac5f3e3e4 | note | IP
938318b0-710b-587d-b956-6c13fed048e2 | note | – – – – – – – – –
fdbf9824-90a1-5a6c-9452-c0cd32dc81e8 | note | RESPONSIBILITY: Site Engineer
8e4d21cf-00f9-5fa1-b2a8-87bb2be927c7 | note | – – – – – – – – –
71a79dfb-43e9-56ee-9b91-828b591d7d71 | textbox | DATE:
040891eb-178a-4cdf-9c3e-5dd6028cdc83 | checkpoint | 1.4 Precast Pipe & Culvert Compliance
40d59723-c135-5d29-a212-03b724b52fa3 | note | FREQUENCY: Prior to Commencing
96d8d7b6-a93a-51a6-bc1d-75d6c6c85388 | note | – – – – – – – – –
c0f0f516-5ea3-5d22-8b66-33b709a2086b | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
1d9ccf08-c938-5646-94b7-13a2ab3351d0 | note | Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058
f068b1ff-0ae9-5574-bb3d-db6727c85f1a | note | – – – – – – – – –
362ef407-d678-5bf3-aa29-ac0e4d278b90 | note | REFERENCE DOCUMENTS: VicRoads Spec.
6c504ed3-f466-5ded-88d7-78b8d1063522 | note | • Cl.619
25a8e3b7-5a00-55da-b94d-094acc3dd5ee | note | • Cl. 701.04
6d461287-a6b7-56e6-be84-bbb4872cbd30 | note | • Cl. 701.05(a)
35b175a6-613d-5f91-aed4-5bb3ae5b1e03 | note | • AS4058
a65bcbda-31b7-5ceb-ad8b-096cd66b9558 | note | • AS4680
d3e0f8c9-659f-5346-8368-714f3b0ef13c | note | – – – – – – – – –
9021b46a-bad4-5998-be3b-0f53f67a7b58 | note | INSPECTION/TEST METHOD: Document review & Site inspection
3d0e8d16-f9cb-5ab3-a23a-eb7ea5c40210 | note | – – – – – – – – –
0baf92b1-7f9e-5e9d-ab92-d26254e17074 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
8a7587ba-c52d-5328-972d-9056c599db13 | note | – – – – – – – – –
25049117-1521-577f-b920-3e96695a3a81 | note | IP
ee102d44-9db8-538e-a09d-4bdddc1c22a7 | note | – – – – – – – – –
52683c5a-00b9-5be9-8ff6-4eaead697596 | note | RESPONSIBILITY: Site Engineer
ea1279b8-4762-5536-b07a-5a6ebce78795 | note | – – – – – – – – –
f3697572-0673-5dcc-aee4-2f97e58c0413 | textbox | DATE:
abd2a123-da44-43ab-b8e6-e67043b6a45c | checkpoint | 1.5 Precast Drainage Pit Compliance
a0c0643c-3c41-5708-98b9-64b75ad56dc4 | note | FREQUENCY: Prior to Commencing
32863b6d-f9b4-5349-8273-1d3028b901bb | note | – – – – – – – – –
9308fceb-d902-5a5b-a938-576dfe37e163 | note | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
2f82eb1f-5f51-5e05-8baf-4211dbf0b64c | note | – – – – – – – – –
e343c594-7089-57cd-bfbe-13c575bfa4ab | note | REFERENCE DOCUMENTS: VicRoads Spec.
05c1dc6c-a6bb-5c1b-968c-9ba3427c5560 | note | • Cl.610
014bf931-f9ba-5e38-aa4d-c52b93fc0c8d | note | • Cl. 705.04
63e2643c-d2d0-5fe7-bb55-a7d416708798 | note | • AS5100
0afd2463-d611-556c-84bb-ff57cd441ef2 | note | – – – – – – – – –
e6dbf4bc-fc7d-578e-86f0-dfe9b041adb4 | note | INSPECTION/TEST METHOD: Document Review
1de05e5e-25cf-51de-8793-8382a37f7f8c | note | – – – – – – – – –
a0823d3b-c53c-576a-837c-5d1daf440dce | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
7a3da105-da77-5e6d-8679-dba33b8119ce | note | – – – – – – – – –
a3e42306-bf90-5dc0-aec3-24f61bafd9f9 | note | IP
4f3a28c6-cf45-5413-9032-24d324269ab5 | note | – – – – – – – – –
1090eb68-f0eb-5961-a51d-3dd2523c9ba2 | note | RESPONSIBILITY: Site Engineer
0682814f-441c-5967-9e85-5835f7b4aed7 | note | – – – – – – – – –
f4333e1a-3404-57ca-8e92-e94a7ccce907 | textbox | DATE:
8a2b864d-a222-4c2e-80da-c6671cc41e59 | checkpoint | 1.6 Bedding material classification
8f6850df-a71f-576c-8dcb-6241ac0fffa5 | note | FREQUENCY: Prior to start
4629e0e6-29b6-58ce-bd05-86fc5af15e4b | note | – – – – – – – – –
c1b6f326-c1e8-53af-a50f-0773142225a3 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
39a09ea2-f0c6-5310-b16f-613205452af7 | note | – – – – – – – – –
552b3862-f97e-5c17-a88c-65b95dbacfcb | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
68fe69a9-3fe2-5082-8a16-80f060af67a9 | note | – – – – – – – – –
37b4f281-4457-5a89-b588-6d34a874a132 | note | INSPECTION/TEST METHOD: Verify
958e7949-80a8-52e8-bc86-9008a3868f75 | note | – – – – – – – – –
909fffd7-cd3c-5528-868c-287572e2d7b2 | note | RECORD OF CONFORMITY: Test Reports from supplier
52464093-a8fa-5c5f-9795-8f5e58b619d4 | note | – – – – – – – – –
594eff92-50b2-5d4b-9b81-66a83a65c421 | note | TP
a03c5b2b-4acc-5399-b36b-91cd72c500b3 | note | – – – – – – – – –
623d6c8f-d6bc-5204-9178-7287daacb1a2 | note | RESPONSIBILITY: Site Engineer
197752a0-f19e-5078-96ed-0fa05a7404c4 | note | – – – – – – – – –
fbae2111-03df-5359-bfe3-c6402d4bdf2b | textbox | DATE:
5faae101-b345-476e-ba0d-18b5f08fd22c | checkpoint | 1.7 Backfill material Classification
3c57001e-c29c-59e4-a3f7-09f785c5c0b6 | note | FREQUENCY: Prior to start
e442b6a5-f7c7-5bbc-81ca-ecea6a8a25aa | note | – – – – – – – – –
e4b7aa66-a380-51f8-9e1d-672ad06790b8 | note | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
ea579e98-4d44-5fed-b717-6f568e7bee11 | note | – – – – – – – – –
44613d6d-f73f-5027-aa84-d7e1bd762141 | note | REFERENCE DOCUMENTS: 701.09(d), 701.091
a1038be0-3eac-5d0a-974d-8fede996d89f | note | – – – – – – – – –
d0016803-1509-5953-8999-914535ab2ba2 | note | INSPECTION/TEST METHOD: Verify
1e084a2b-72de-5cec-a72e-d129f11eb847 | note | – – – – – – – – –
b88450f4-94af-5043-aeff-f2877a25aa60 | note | RECORD OF CONFORMITY: Test Reports from supplier
5ce666cf-4ae9-585a-90d8-1f56fe1e90aa | note | – – – – – – – – –
73762daa-dd4a-5960-9702-857aaf6345db | note | TP
5645d3f4-c424-5a9a-bf47-09893a6513dc | note | – – – – – – – – –
4c380bd2-93c3-5f27-8f9a-73a49c5d4804 | note | RESPONSIBILITY: Site Engineer
6d900140-3db5-54e4-8bc2-fc9ef2787899 | note | – – – – – – – – –
402d8de8-5849-5175-a38d-9967f8181459 | textbox | DATE:
db4e6b80-fbc6-4d6f-9d86-b3b9b702a439 | checkpoint | 1.8 Mortar material classification
ede7d76f-6633-5246-a40a-d0984a2949ad | note | FREQUENCY: Prior to start
5a78d693-ff80-56c7-a605-4afb3614d436 | note | – – – – – – – – –
a8ced59a-30ff-5631-b50f-2a776259f594 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
df835a20-b1c4-5dbd-8d10-97399487cec5 | note | – – – – – – – – –
7e1e7bd5-c734-51d4-a100-e463e593204a | note | REFERENCE DOCUMENTS: 610.33
ca6a0429-59d7-5aa2-a6d2-e55e13872953 | note | – – – – – – – – –
86229764-41c1-584e-83da-261be639c5f3 | note | INSPECTION/TEST METHOD: Verify
f7eb6fe1-bf55-5caa-a0a5-8544c2319933 | note | – – – – – – – – –
eeafa4b1-10a1-5e46-8bc3-f57401be6ba3 | note | RECORD OF CONFORMITY: Test Reports from supplier
a11d4d65-83fa-54b9-8335-09eefb313d18 | note | – – – – – – – – –
a1028bbd-f524-58bd-a4c3-14aa6e846953 | note | TP
4f9f5ba9-5846-5dcd-9b39-d59b9479bdad | note | – – – – – – – – –
115e263c-f0d1-597b-8cdc-ca6be7ac763c | note | RESPONSIBILITY: Site Engineer
67f5904a-d06f-5f5b-a16a-6f064071ad55 | note | – – – – – – – – –
ab9ae617-52d5-586c-8a55-bd2feec832c4 | textbox | DATE:
da6d4634-e9eb-48bc-ba82-397f3defad04 | section | 2 - Construction Works
2ad644f1-0446-41a9-914d-523b4154d803 | checkpoint | 2.1 Excavation Permit
0edc254f-1f5f-5ce7-a4f8-1a34d0530c4d | note | FREQUENCY: Each lot
ff33128d-750f-5d67-9e3a-308dc5535792 | note | – – – – – – – – –
b0ef937d-365e-5562-a5c7-f671c5ab8b95 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
5799d026-870b-5133-b16e-c94f4c83f66b | note | • Plant and equipment shall be appropriate for the task.
8ee4e531-9428-5b97-b5fb-079969c53020 | note | • Excavation operations shall not disturb areas outside the limit of excavation
2a3dca4c-417e-53b3-9a32-40e6c3906776 | note | – – – – – – – – –
04d9cfdc-269a-59af-bfb7-1786da73e98d | note | REFERENCE DOCUMENTS: Excavation permit
0143d891-c499-5f9b-b994-55719426f6d6 | note | – – – – – – – – –
23beb5e0-1f18-5824-b3e0-520effc5b184 | note | INSPECTION/TEST METHOD: Verify
e41d3c5a-c71f-5cc3-a82e-42d289159770 | note | – – – – – – – – –
950bca74-3ee8-5b41-af17-7e44f74c559b | note | RECORD OF CONFORMITY: ITP Signed
38d63006-515b-5426-b097-bbd4b285d114 | note | – – – – – – – – –
afd06ad7-8029-5edb-a518-bb9e64350c14 | note | HP*
ec0de322-999f-5b54-af1f-399eb9252e14 | note | – – – – – – – – –
45c5a4b4-aec1-5846-bd23-49d971020fa5 | note | RESPONSIBILITY: Site Engineer
a927522d-d3bc-5915-afc8-ff720ce62ec7 | note | – – – – – – – – –
29c65067-2345-55c3-ab5f-f1d7031703fe | textbox | DATE:
079407a4-15cf-4cd4-b273-24ac1dfd0ca7 | checkpoint | 2.2 Set out drainage
e6791434-e979-5e04-b031-9ba0c2310c0f | note | FREQUENCY: Prior to backfilling
7af16554-8466-58fd-9a9f-bbeecd9b594b | note | – – – – – – – – –
1242812b-a705-500b-8c41-c119ca20eceb | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
0c6fb1b2-ac8b-5740-9334-394ea2292e98 | note | – – – – – – – – –
ae960e21-e9b2-5e15-b4c8-87d63bc2298e | note | REFERENCE DOCUMENTS: Drawings 701.10
53328690-e238-5a66-8436-2c8a4754b12e | note | – – – – – – – – –
aaeb549c-662b-5729-a024-f253bf9dbbac | note | INSPECTION/TEST METHOD: Visual Inspection
6b5502bd-2378-5661-baf3-17e15458566c | note | – – – – – – – – –
53409ab9-82cc-58b4-8c7f-1487712d91fb | note | RECORD OF CONFORMITY: ITP Signed
20e666f5-3c2e-5236-8da4-abbffc8e42f3 | note | – – – – – – – – –
5e8ef6d9-8850-5731-bb6b-8c90a8964e42 | note | HP
1f0ac85d-0a7a-59cf-987f-2038e74c8349 | note | – – – – – – – – –
07bf438e-6536-59e7-90cd-e599d1aa470e | note | RESPONSIBILITY: Site Engineer/ Superintendent
754ae0f9-9cc1-52db-99e5-4e763982c070 | note | – – – – – – – – –
4b4a7073-a465-54cc-ad70-df7fea90db84 | textbox | DATE:
31664eff-ed91-4bb5-b1a1-a67e693f1a84 | signoff | AUTHORITY HOLDPOINT
03cee5e2-a011-4c0a-b2c7-b37e0603074c | checkpoint | 2.3 Excacation (pipes)
34c9f4ff-1f26-51e2-af87-a8e7b4365ce6 | note | FREQUENCY: Each Trench
ac04f539-8e10-5bb7-96bd-c20c7bceac7c | note | – – – – – – – – –
31705813-1e3b-5651-a04e-12940112b537 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
96012c68-0a7e-5056-b067-93bdc3b99b39 | note | ○ Depth of trench:
5587b7b0-1b40-5426-85e3-05a6b3135e7d | note | • > 100mm below underside of pipe (for pipe width < 1500 mm)
9c66326b-fcff-5f98-9472-c58120d32850 | note | • > 200mm below underside of pipe (for pipe width > 1500 mm)
3425168a-5160-5cbd-8c50-7e41032369e0 | note | – – – – – – – – –
be451ad1-a323-57b7-bd5b-4531cee78676 | note | REFERENCE DOCUMENTS: 701.151, 701.15
3917362d-7301-54d6-9072-a3c939864570 | note | – – – – – – – – –
13b8d065-054b-5a6c-86a5-8a5651de314e | note | INSPECTION/TEST METHOD: Visual Inspection
1f0ab38e-f20e-5f18-9e1b-e3284271f452 | note | – – – – – – – – –
2deabc08-d926-5a72-9951-94d6732abdc6 | note | RECORD OF CONFORMITY: ITP Signed
c0cf54ff-8812-52bd-ab29-7a563e0b89df | note | – – – – – – – – –
d7459d88-9be8-5dd7-8496-392a98f4adbe | note | IP
55c49eb6-6bc5-501a-971d-1a12ee0ac003 | note | – – – – – – – – –
a58688f8-ffc8-5521-92f4-0143ac9198ed | note | RESPONSIBILITY: Site Foreman
19fd8ab4-1481-5786-b4e5-958b6fd7e616 | note | – – – – – – – – –
3a333cb6-7524-5455-aa2d-8780dee3b47e | textbox | DATE:
f7b782fe-4082-461e-bc71-368786e1ff4a | checkpoint | 2.4 Excacation (pits)
3baf19d2-1759-51cc-bcae-bc32a67b0877 | note | FREQUENCY: Each Pit
35720b53-885c-5bbc-9205-1b24b4a84bc5 | note | – – – – – – – – –
af24836b-0d1a-5775-b4ca-d60bb6ada44a | note | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
7824d2bd-6ed3-51f6-a4a7-4294ff258442 | note | – – – – – – – – –
4df700ba-9e94-57e4-8b8c-3bee44e3b3b7 | note | REFERENCE DOCUMENTS: 705.05b
e9ff0d66-dd10-5a7a-95ae-7a38dffc4661 | note | – – – – – – – – –
a49915bc-25ad-5f4b-bef0-19a3a0c09df0 | note | INSPECTION/TEST METHOD: Visual Inspection
89eeafbe-96ae-5783-90f6-02159aa9e2ef | note | – – – – – – – – –
9ec2a29b-dcbe-5bd5-b91b-5340748d9f54 | note | RECORD OF CONFORMITY: ITP Signed
36a9c7f3-8db0-5340-a83f-9ecab671b6fe | note | – – – – – – – – –
8adc3f9a-0c40-5f98-b2af-6019f7ca93fe | note | IP
8da70816-8026-5846-b569-f565ad6eeae4 | note | – – – – – – – – –
1492ea17-e66c-5484-b5e4-4f960617af35 | note | RESPONSIBILITY: Site Foreman
89f664b8-7c50-5f01-9e6b-73dde858da3d | note | – – – – – – – – –
28b521cd-1542-5e80-b2d2-4eaa7fdd9709 | textbox | DATE:
47724198-d4a8-4541-a120-b127a6e0bbcd | checkpoint | 2.5 Compact base of trench
942c9167-00f5-5015-812b-c7dd829f3c39 | note | FREQUENCY: Each Trench
64b61b48-ad8e-5e46-a5c0-c67ff08260f8 | note | – – – – – – – – –
46c2f24e-89bf-5dd0-921a-a7f2f4710acd | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
fe3888cf-a458-5fab-b2c5-a23ff9e71b02 | note | – – – – – – – – –
450cd916-a0a2-5652-bf09-2c78429f2a0c | note | REFERENCE DOCUMENTS: 701.15
02e44af6-c402-5936-a742-896a8cdd4f74 | note | – – – – – – – – –
ffe8d32c-c124-5916-bf56-e7f669c58a5a | note | INSPECTION/TEST METHOD: Visual Inspection
6f61d143-7f30-5d3b-be73-85c13b80294d | note | – – – – – – – – –
68ab99f1-ab5c-5024-97a6-3f51e88e996d | note | RECORD OF CONFORMITY: ITP Signed
4bd9beb5-b693-505e-b449-b85a16120bf1 | note | – – – – – – – – –
e1787b4c-9636-5dcc-af31-90be6bc08ee5 | note | IP
dcaf23cd-48f1-56d1-b38f-80d21e783cd8 | note | – – – – – – – – –
13f739a4-514e-5651-8b91-1e5f4fd09052 | note | RESPONSIBILITY: Site Engineer
b852cce7-fe73-50b6-b215-1bbfc032873a | note | – – – – – – – – –
f5c52895-7c93-551f-a361-5bedb3ced59a | textbox | DATE:
8562b8bb-dfe4-434c-95bf-edf1f46bad9c | checkpoint | 2.6 Place bedding material & compact
8482f3df-eef8-5d42-acbd-969ba2143adb | note | FREQUENCY: Each Trench
2f318434-acf7-5391-a059-6da2f92a7082 | note | – – – – – – – – –
802b0a3f-017b-5481-bdc5-38640fb856fa | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
a1536230-2abb-5c3b-960c-d5b4d3a0b068 | note | • Bedding shall be compacted to refusal using hand held mechanical equipment.
f0112910-79b1-5c1d-84f8-37c7c36abce5 | note | • Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
7fd68a8b-6e17-562b-ae41-3f47c7ba6a79 | note | – – – – – – – – –
7dbc0e1d-d153-5a05-a72c-2aef3f66f6e6 | note | REFERENCE DOCUMENTS: 701.20, 701.20a
3665665f-8e7b-5ce6-82f8-cb48c0b45383 | note | – – – – – – – – –
2a4f18ba-0264-55b6-a30c-5c6e871b5f7d | note | INSPECTION/TEST METHOD: Visual Inspection
4efee428-026e-5aa8-b68d-269048979e18 | note | – – – – – – – – –
f1506f31-89e3-5c2d-81e4-1ab8e092fed4 | note | RECORD OF CONFORMITY: ITP Signed
9fa9e05f-338c-5dcc-abb2-f15e66d75afb | note | – – – – – – – – –
02540b14-6a0e-574b-85b9-21a6e041f6c5 | note | IP
a4bbddc4-54cc-5828-9920-e421518eb444 | note | – – – – – – – – –
d34aa26b-68a9-5ae1-a167-d0ea070fde39 | note | RESPONSIBILITY: Site Engineer
3a17e343-69c8-5f99-8139-5798558be716 | note | – – – – – – – – –
4c723051-ca5a-5bc2-a40c-09478158de87 | textbox | DATE:
47785958-2122-41cf-9af2-a8578c43a2a7 | checkpoint | 2.7 Place pipes & precast pits
3c80f99c-1375-5666-8853-9edee872ddf6 | note | FREQUENCY: Each Line/Pit
86786b16-3502-5ca7-9f2d-6b6540f7c9d9 | note | – – – – – – – – –
d59c4db4-d947-5e47-b400-1dc4727ad61f | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
fa256aba-78ae-5b5b-a186-8b2c2aeef2df | note | – – – – – – – – –
ceba75e4-fa0a-578b-9bc9-4ba0729645e5 | note | REFERENCE DOCUMENTS: Drawings
d30af5fb-920b-55a6-88c9-d08a2913b40e | note | – – – – – – – – –
a3d45cd9-c489-55f0-a750-978819492a2d | note | INSPECTION/TEST METHOD: Visual Inspection
b9f7ef81-d0ef-59a8-91a7-cd361b4c1cf3 | note | – – – – – – – – –
9a1ec911-4aad-5e15-bc49-2bf3067f8417 | note | RECORD OF CONFORMITY: ITP Signed
6a0923c1-bb73-5be7-acf2-6fc87475b407 | note | – – – – – – – – –
64715310-8814-5c71-b3d0-c40b8859a422 | note | IP
ce1e7632-9b59-5c71-8b99-7d17218bf878 | note | – – – – – – – – –
c4c4da92-a43c-5f91-80a9-653b920ba1f2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
2ee5ceda-420e-5702-bcf8-91ddc1a77553 | note | – – – – – – – – –
39702f4f-656b-587a-863e-8f5ae5fcb355 | textbox | DATE:
87f0ab3b-d5f9-4ab8-b5c8-0a264de28893 | checkpoint | 2.8 Jointing pipe sections
d8e53ce8-b4a2-5cf1-9aa8-536fb429c87a | note | FREQUENCY: Each Line
ff624d2f-ec69-59e7-ad27-f1bba74fd320 | note | – – – – – – – – –
fc6259de-0a48-500c-9bbb-93e028a0ff5f | note | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
c94dc9be-e02c-5cf0-98ec-a149a20e9216 | note | – – – – – – – – –
1f061cd1-d728-50c1-bd40-c18bef05c2af | note | REFERENCE DOCUMENTS: 701.18
5d6e64c7-fa50-5b90-8cda-d420a1963746 | note | – – – – – – – – –
44fb7718-3a97-56b9-8c11-bc5e965c5f36 | note | INSPECTION/TEST METHOD: Visual Inspection
268785b9-1528-5654-b088-311403098210 | note | – – – – – – – – –
b39029d5-b439-50da-86e8-eedb7c920388 | note | RECORD OF CONFORMITY: ITP Signed
0a9845d0-8043-5daf-bb5c-c51e7dcdecb3 | note | – – – – – – – – –
3c5a8919-ef61-5c58-a5cf-6ef6dbf70503 | note | IP
f7c47c4b-c967-5d81-b36e-a4ea1f1212e1 | note | – – – – – – – – –
34c3c6d8-d11c-5fc7-a055-17d866351ccb | note | RESPONSIBILITY: Site Engineer / Site Foreman
77fcf8db-e934-5485-9fa2-1065ab00d162 | note | – – – – – – – – –
379862ab-5e42-5f56-89c9-93c36a97f971 | textbox | DATE:
c9042e98-57fd-4131-86d9-dc91687fbe2f | checkpoint | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
cbaa70d7-7eca-58f1-b9c0-21a2fe759d00 | note | FREQUENCY: Each Pit
e84a2572-6831-57b6-b0d5-c6670ae9f28a | note | – – – – – – – – –
f17708df-8a10-54ad-bd07-339810c54364 | note | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared.
71871a37-9b10-5eba-b858-0305eaf6de24 | note | • The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
06060fde-c454-5f0b-a5dd-88cd15772a92 | note | – – – – – – – – –
a06eb006-28ac-5ea4-b0c2-6179c165d642 | note | REFERENCE DOCUMENTS: 610.32, 701.17c
de07e449-6bcb-533c-9e2c-42d0523487fc | note | – – – – – – – – –
0e48bd40-26a3-5be5-a28f-96eff3b61bd4 | note | INSPECTION/TEST METHOD: Visual Inspection
d9589e5e-1fb8-511e-857a-c0df652d90a7 | note | – – – – – – – – –
021b60ce-73fc-5c9b-a8aa-4a2220a46ea0 | note | RECORD OF CONFORMITY: ITP Signed
691c3414-d940-570c-9d93-db1286272c30 | note | – – – – – – – – –
ea3db6af-ddb9-59e2-9be9-b86768ad1886 | note | WP
e5518555-d4ad-5bd9-abe4-2d7e96e5564b | note | – – – – – – – – –
1bd4e360-4601-5cdc-a2cf-b1f69bf91295 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c81068e5-8f0b-52f8-ae59-1a7e4fb95dc5 | note | – – – – – – – – –
38011518-7df6-5973-9cf2-8e1534633577 | textbox | DATE:
cd6100b1-e65f-4e71-9cb0-692cdcc856b6 | checkpoint | 2.10 Survey of laid pipe or pit
b66bc46e-4eea-5cc8-b161-495f174c29e3 | note | FREQUENCY: Prior to backfilling
a43e1fbd-e50d-5c3b-b8cf-2f00d1881df4 | note | – – – – – – – – –
cabbc2bb-0aaa-5b45-81b0-f30423a54d3a | note | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances: (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
1dea3074-b0bd-5537-b10b-eb2465038722 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
4692957e-861d-5341-801c-4ea324591999 | note | (c) invert level of pipes at pits ±50 mm
d0edbf24-0c51-53fc-8aeb-d43c8997c17c | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
bca61451-65a9-5de7-8d7a-6d884954f44e | note | – – – – – – – – –
11c2ba71-6bc0-5ae4-a54d-965d2be79247 | note | REFERENCE DOCUMENTS: 701.1
8a103ea6-5b6e-5e9d-a2ec-0e45dad80d85 | note | – – – – – – – – –
655f27b4-080c-5961-9c27-286a1a585f20 | note | INSPECTION/TEST METHOD: Survey Conformance Point
23f26ca3-e232-52e6-99b6-516d2f81a653 | note | – – – – – – – – –
d8ef8e9d-a763-54d4-86da-ae9880cd0ffc | note | RECORD OF CONFORMITY: ITP Signed
3d811c19-676f-54cf-92be-56615d2241d0 | note | – – – – – – – – –
25ddbeb4-916d-5d84-892b-d8f9aea0f93d | note | SCP
460fc67c-4563-5749-841a-8ebf50b3c886 | note | – – – – – – – – –
11c6daa7-3b4d-52cc-be47-6e1143723b73 | note | RESPONSIBILITY: Site Engineer/ Surveyor
c15d99f1-fad7-505e-9c6f-2333615b0f04 | note | – – – – – – – – –
1d455a37-67a3-5d52-ab6b-2e510087a9ec | textbox | DATE:
560b48e1-685d-41c7-8721-b807596d9512 | checkpoint | 2.11 Haunching & compaction of bedding material
fb7aea96-422b-52f3-8698-7e7b65dab487 | note | FREQUENCY: each lot
6d64e2d6-0735-5603-b40e-0c3d4938c961 | note | – – – – – – – – –
e36f5435-1525-5226-88e3-05da25172752 | note | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
78c6c8e3-8815-5a5a-ae73-a1a9beac4c0c | note | • Loose layer thickness <=150mm
2603a2f4-9d69-58f9-a5d4-5110f8a77873 | note | • Compacted to refusal using hand held mechanical equipment.
861c3c00-2071-5142-a54c-e346c524a28c | note | • 1 lot = 150mm layer
90493dd2-c8ec-5de9-a5d4-b063057be8ff | note | – – – – – – – – –
5a2275b3-21c5-5cd3-b11a-c2972828a091 | note | REFERENCE DOCUMENTS: 701.16, 701.20
8102aa76-6a34-5beb-a355-d8dce97b6c11 | note | – – – – – – – – –
d49e0c19-b6ac-52c8-afa6-f7da866d1708 | note | INSPECTION/TEST METHOD: Visual Inspection
816cc3d1-c4d7-5b05-83b1-548180542874 | note | – – – – – – – – –
6874e54a-1cf4-5373-ba5e-c544d85e0b90 | note | RECORD OF CONFORMITY: ITP Signed
5c9370fd-ba7a-5e9e-b585-5378aff84a98 | note | – – – – – – – – –
a2f17376-90d4-5214-bac3-7bed72af6e25 | note | WP
0feb74bf-7b89-5d14-b7b5-3356278984c4 | note | – – – – – – – – –
834416b8-af91-5d03-a543-f6d6c6bf86b6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
db76c001-dc63-5c8c-b420-324ce2202b79 | note | – – – – – – – – –
3fc1752b-6859-508c-82c8-fb0465fe23f0 | textbox | DATE:
1fc6c611-e7f0-43c9-95d7-67f469de8a85 | checkpoint | 2.12 Place & compact backfill material over pipes
4a287c4c-ad02-5e44-9d5c-76305bdd7193 | note | FREQUENCY: each lot
f53e85e7-301d-5864-87cd-35fac9d34672 | note | – – – – – – – – –
a9dc921d-1781-50a6-8d9e-3e5d77d45f7c | note | ACCEPTANCE CRITERIA: Backfill under paved area:
0381dca2-2c28-5d20-bd40-32b9e73a5328 | note | • fill trench with selected back fill material to subgrade level
918900ab-cf8d-514e-9aec-56300249d693 | note | ○ Backfill under area not paved:
42336cfb-ece2-5a0f-bc7b-c6d8352a7558 | note | • Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
30243682-77d4-5758-93a5-2f54e4364d46 | note | • Loose layer thickness <= 150mm.
0f6f98f3-612e-5df2-9360-e7b87e6bbe75 | note | • 1 lot = 150mm layer
0233f343-4671-5364-ae4b-dfbfa0e7986b | note | – – – – – – – – –
ca26d191-f0e9-55b4-a5a0-0814407dda84 | note | REFERENCE DOCUMENTS: 701.19, 701.20
96cb5906-45f4-53ba-bb4e-8026d0dc1331 | note | – – – – – – – – –
bea37f8c-3c69-5d61-8147-68e151bfe652 | note | INSPECTION/TEST METHOD: Visual Inspection
c4e431ab-285f-5149-95d8-7a686766f21d | note | – – – – – – – – –
5698910d-650d-56cf-8983-e1ae310789d2 | note | RECORD OF CONFORMITY: ITP Signed
4a63bb39-7993-5a39-8abd-34c414902406 | note | – – – – – – – – –
7bd6b911-9a62-5038-a39e-0c68db6882a9 | note | IP
a68aa43b-e59b-5011-bc96-a8da42eb75be | note | – – – – – – – – –
cc0658b0-d8e7-5cb8-80b5-0fe1cd281eba | note | RESPONSIBILITY: Site Engineer / Site Foreman
b113f7cb-18e4-5629-a302-6cb4d45bbcbc | note | – – – – – – – – –
235d98eb-f9b5-5963-987f-abfc198ec7b7 | textbox | DATE:
40a80e4b-c0ed-4b8e-b37d-e8724f2ca18c | checkpoint | 2.13 Place & compact backfill material around pits
34d72838-5094-57e6-ad7b-a59adb827d47 | note | FREQUENCY: Each Pit
313379eb-b007-5e81-ba57-47cedb0a7e9d | note | – – – – – – – – –
e2c067a5-3b5f-5932-8a2c-9b852e0125cd | note | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm. Compacted to refusal using hand held mechanical equipment.
518da4f8-833f-5ee0-9330-aa65ab30e6c1 | note | – – – – – – – – –
23ce6b97-79ad-590e-9d3f-7472de83fd54 | note | REFERENCE DOCUMENTS: 705.18
a680df95-48c3-533c-9ad6-2260edb658f0 | note | – – – – – – – – –
2fb008e1-1188-5af2-ad09-e27a1b4ca50b | note | INSPECTION/TEST METHOD: Visual Inspection
8691c870-d04f-5629-9fbe-2651a7bdaeeb | note | – – – – – – – – –
43090b22-80ea-520b-a6e8-4ddace5bde57 | note | RECORD OF CONFORMITY: ITP Signed
9022fe9d-a989-58e3-87a5-a7f3c6a850ee | note | – – – – – – – – –
c24afc9c-7ec2-56f2-90a6-a901482f792d | note | IP
6dbeb05c-a76e-5f06-92fc-bb6e126dd643 | note | – – – – – – – – –
0345a5d4-9a18-56c4-aae3-cf899ecfd7de | note | RESPONSIBILITY: Site Engineer
56f6e7fe-e718-59c8-a565-33eaaaf85804 | note | – – – – – – – – –
97e79488-2edb-5f9e-9021-d3e86704358b | textbox | DATE:
eb398469-5a5a-4166-b99c-24d5d41eb9ab | checkpoint | 2.14 Backfilling with cement stabilised sand
0f8aa4dc-cddf-5d84-a9f0-48d5d2425648 | note | FREQUENCY: Each culvert
f4f99ae7-dcdb-502a-a41b-a20ad02019c0 | note | – – – – – – – – –
ccd3e686-4cd6-52ee-813e-0cca198c5043 | note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
4d735177-4e30-5d88-8869-4efecca7bbfe | note | – – – – – – – – –
778f47b6-c692-5104-96fa-04a42b2009fa | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(a)
a7298f5c-34a5-5b70-9947-460b043fe390 | note | – – – – – – – – –
fd98f313-733c-5112-9d18-f4ebbc9ff2c4 | note | INSPECTION/TEST METHOD: Site Inspection
9a5ba956-85a7-5c8f-8386-fa92dd5aca98 | note | – – – – – – – – –
1f8d40f3-c86c-58c4-b0de-b34e4a24be4e | note | RECORD OF CONFORMITY: Superintendent approval, ITP signed
c701bf8d-758f-5021-87c3-236d95cfc734 | note | – – – – – – – – –
309d0505-f78e-596c-9681-5946281c7cce | note | AP
f71fffcb-5ddf-5c5b-9445-e3036fd65a19 | note | – – – – – – – – –
9bcfdb40-176c-5198-9fb5-a1e40d6979fd | note | RESPONSIBILITY: Project Engineer / Superintendent
0898b746-0cbb-586b-93ed-bdbeb62c9b28 | note | – – – – – – – – –
c9f0990c-8e32-5ea9-9fa4-05d321d9e7c6 | textbox | DATE:
da135a98-018b-4cdc-9c90-3f7bf985f3a7 | checkpoint | 2.15 Install step irons
7ba00082-1a43-549c-a7f8-4585f4ce61c6 | note | FREQUENCY: Each Pit
0c93133d-65f5-5fe7-ac14-ce0aebad1f4f | note | – – – – – – – – –
675a40ab-1529-5589-a8e2-813908ec77bc | note | ACCEPTANCE CRITERIA: For pits > 1m deep.
0e696a95-c4e0-5a83-bd66-db71cb0bfc9f | note | – – – – – – – – –
989d60ab-bf31-5ee5-896b-549ca6e473d0 | note | REFERENCE DOCUMENTS: 705.12
22dc9c10-78e0-57c9-8a7f-429878b54900 | note | – – – – – – – – –
158b51e3-dfe0-5701-b0b3-f2917f29e791 | note | INSPECTION/TEST METHOD: Visual Inspection
058d8875-d532-575b-a81f-450df4febe27 | note | – – – – – – – – –
7add5017-3b7e-5a4b-a93d-f73069511c93 | note | RECORD OF CONFORMITY: ITP Signed
cdbfc87b-d247-5ed2-a9f3-20c9e141b7c8 | note | – – – – – – – – –
0bf579b2-7ffb-5e28-a689-198b077b2512 | note | IP
5d6d18f1-e2aa-5907-b56c-3cd2d12a205a | note | – – – – – – – – –
26531c9e-5371-5620-a6be-b507d6acdcbe | note | RESPONSIBILITY: Site Engineer
f2896125-d89b-5d6c-8230-120d7d1e601b | note | – – – – – – – – –
08123e30-4f7a-5060-8bc7-6412eafe0435 | textbox | DATE:
1dd079f0-d076-46df-9857-07257d33ad13 | checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
5fa942e1-c1dc-5a3f-bb3f-498dda50918c | note | FREQUENCY: Each Pit
464af7aa-1478-5f0a-b9f7-0cf662bf6694 | note | – – – – – – – – –
b427e78a-dcc6-5d89-9787-041cea2ff61a | note | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
c57123da-9f71-50ac-8ee4-9ebe2fccbd5a | note | – – – – – – – – –
8edd762c-1158-5a78-af05-af473feadf48 | note | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
a81cf99a-3ba3-5cd3-bc4b-b4ddc893ab36 | note | – – – – – – – – –
7114182c-0cd1-50d6-823d-b80553c25750 | note | INSPECTION/TEST METHOD: Visual Inspection
73498565-38a3-5d71-b697-782197164356 | note | – – – – – – – – –
31af69d2-5e9f-5f9c-926b-a9e5861c072e | note | RECORD OF CONFORMITY: ITP Signed
71592e7b-b06a-5614-966e-c84e1084c6ee | note | – – – – – – – – –
896b92a4-5fea-5ef7-ab41-f9de47118f37 | note | IP
66cbbb85-3089-58d9-ac8a-3acbb15d9664 | note | – – – – – – – – –
633f7a44-b2a7-5e14-a9db-95c25192b5df | note | RESPONSIBILITY: Site Enginer
8994078c-e0b0-574a-8b8c-6377d14fb382 | note | – – – – – – – – –
9e0d9cc3-3778-5788-be18-07ba3f2f70fa | textbox | DATE:
374bc933-8029-4978-98a5-c17bffbdf354 | checkpoint | 2.17 Place pit covers
81380180-eb90-51dc-9326-3a83ca527c83 | note | FREQUENCY: Each Pit
8830047d-95fa-5a0d-af9b-57ce0551a302 | note | – – – – – – – – –
4232a470-5322-52d2-8f19-bda05c7f4902 | note | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
c85919f0-4f56-5f29-aa7d-9d8d4d91ac8f | note | – – – – – – – – –
311749ea-9a8b-557d-a02c-5c9bfc8a614b | note | REFERENCE DOCUMENTS: 705.17
f564d929-3678-5c68-a7db-66da595c2a63 | note | – – – – – – – – –
cb66ca2e-25cb-55f5-b6ea-4f75aa88b496 | note | INSPECTION/TEST METHOD: Visual Inspection
28a15754-1ad3-55a1-aeab-b24ebff4c1d4 | note | – – – – – – – – –
0d8c6198-d88d-5df3-baaf-4ee961453080 | note | RECORD OF CONFORMITY: ITP Signed
39add330-4654-5df2-a4f7-5814180a2e9c | note | – – – – – – – – –
af48d8f4-8460-57d1-bb70-b6f5722643c8 | note | IP
766212e8-12e3-5265-b878-782022a4d195 | note | – – – – – – – – –
17502056-1fde-5942-8d62-adfb08427870 | note | RESPONSIBILITY: Site Engineer / Site Foreman
4058a235-67bd-5ed8-94e4-1f8654d9f5ff | note | – – – – – – – – –
488a18a9-d7ea-5ad5-bb50-b644a9e366c3 | textbox | DATE:
1bba2a62-88cf-4e17-b3f3-fc2b3cecd14d | checkpoint | 2.18 Repairs to damaged pipes and box culverts
e01355af-e7c9-5f95-95b8-1c8fee870537 | note | FREQUENCY: Each damaged pipe or culvert
a4040404-5f49-5053-a018-b3aadc6b7899 | note | – – – – – – – – –
9a9d1310-5a1a-5632-a575-f33e03d0e6df | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
fa830726-3cb8-5022-ac59-9986067f42a8 | note | • All repair procedures undertaken in accordance with Cl 701.25
9510b794-694f-57f8-bef8-5c81e8929a4b | note | – – – – – – – – –
97b0a5df-812b-5492-a73b-71c67e1f4e01 | note | REFERENCE DOCUMENTS: 701.31a
3bf34708-1453-5e4d-a11c-c356d46a8912 | note | – – – – – – – – –
d4232710-b1cf-59c3-ab22-8ba3f0a10314 | note | INSPECTION/TEST METHOD: Verify
5dae14d9-71dd-5c62-9cfe-2a0d01abd6ff | note | – – – – – – – – –
dfecd365-3c16-5dbd-a9b8-385a23e193fe | note | RECORD OF CONFORMITY: ITP Signed
0a9df478-43aa-5694-bd11-25c0c8624d0f | note | – – – – – – – – –
530ecbdd-cc76-5b8f-b10e-cb1d84eeb9c2 | note | HP
5b143385-7ad3-55c1-aa40-bc3572d9d463 | note | – – – – – – – – –
e9e9e928-2a8c-5403-92d1-f84a2111ed94 | note | RESPONSIBILITY: Site Engineer/ Superintendent
9f0b6e59-ed86-534d-920d-35cde312e37b | note | – – – – – – – – –
f6dfbf86-8ade-55f3-9259-892fda11c376 | textbox | DATE:
d2a7241d-f383-43b8-b946-47d20e9462f3 | signoff | AUTHORITY HOLDPOINT
de2ba678-23ec-4e72-8bad-a3ce4d54917d | section | 3 - Testing & Completion
c468889d-1c25-4d34-99cc-1e5b4ad96c88 | checkpoint | 3.1 Compaction and moisture content of backfill & bedding material
f2123c55-1b3e-570c-a85d-4501da979df9 | note | FREQUENCY: at least 20% of all lots
40da2fcd-e1f3-5a5c-805f-9c06bdb2501e | note | – – – – – – – – –
abd8dd31-e95b-5519-9418-8daae6133ef1 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 97% using standard compactive effort.
b5318fe2-7f70-5ac8-9ff3-1e1d664637bf | note | • Bedding shall be compacted to refusal using hand held mechanical equipment.
28caed54-12a6-584c-a184-b336faeeece0 | note | • Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
0e636ae9-051a-58a6-8431-f22d25ae01d4 | note | – – – – – – – – –
104835f3-1d93-57eb-a988-c35c9d0a5a52 | note | REFERENCE DOCUMENTS: 701.20a, 701.20b
91b84a42-8e79-55db-9c35-9047a1f6f6f0 | note | – – – – – – – – –
229b89a2-3564-57ae-943b-c69e289249f3 | note | INSPECTION/TEST METHOD: Verify
b678cddd-43b7-5f67-9a9e-9fbf7faa680b | note | – – – – – – – – –
5cdfd0e9-9375-5351-bbed-3bdf44d72c92 | note | RECORD OF CONFORMITY: Test Reports
1e99e197-6520-5e47-ab56-aa95bd888905 | note | – – – – – – – – –
af9ed0be-0dce-5b0d-9c5d-dd7acb554efb | note | TP
a0ac3a92-6940-598d-bc4e-eba4c35fc91b | note | – – – – – – – – –
79d7aa47-4b8d-5a3c-9263-ae7ccf73172d | note | RESPONSIBILITY: Site Engineer
0bff546b-ab65-5717-806e-eccd91aa29f4 | note | – – – – – – – – –
4d3f376a-ef49-5092-af84-395eed93f2a6 | textbox | DATE:
0778e13f-ba47-41e6-83cf-28dec2999c23 | checkpoint | 3.2 CCTV inspection
a00321ba-d57b-5afc-8ede-c687d189c2a1 | note | FREQUENCY: each lot
e1e8e5e0-d034-5579-931a-84e9e314b811 | note | – – – – – – – – –
f011972f-64fe-51be-8976-a32587c880ef | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
ea361b97-2ff0-5e83-9016-a2c960f51ca6 | note | – – – – – – – – –
20f8c983-ebc3-550b-b3ab-efcbad70d9e1 | note | REFERENCE DOCUMENTS: 701.3
49ee0d6f-1bfe-586b-8652-961d7d1dc5bc | note | – – – – – – – – –
b37c1c0d-2452-5aff-9a62-9cd315d57305 | note | INSPECTION/TEST METHOD: Visual inspection
e72413af-0de8-5a67-8b2b-08e14a33b648 | note | – – – – – – – – –
b909aa93-7d91-5807-a604-c9d77b806956 | note | RECORD OF CONFORMITY: CCTV Report
1bce1e6d-3173-569b-bdbc-571e0d57e03b | note | – – – – – – – – –
fbd59b1e-965d-5cd4-bf0c-ddda27b3d9d2 | note | HP
117d6dba-256e-5f0b-92d0-d4858a581fd8 | note | – – – – – – – – –
bed1c1fc-8f70-585d-b28c-6527ef7384b0 | note | RESPONSIBILITY: Site Engineer/ Superintendent
fc73545f-232a-5f4d-a5d1-a71c48aaf65a | note | – – – – – – – – –
311196c8-2fe9-5d41-bfc6-343c4d7e2e58 | textbox | DATE:
6d749eab-6f01-475b-865b-6913e2741719 | signoff | AUTHORITY HOLDPOINT
75604c67-a2af-4f6f-af70-67aeb7f82398 | checkpoint | 3.3 Flushing of pipes
8d43e5bf-d603-5d64-ae4e-06d6773abc56 | note | FREQUENCY: Each line
36856903-c862-5656-86a1-d55b5d115de6 | note | – – – – – – – – –
25cbabb1-9fbc-5088-b891-7765112457b1 | note | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
49ebf325-1122-502c-9504-4b4a776a0550 | note | – – – – – – – – –
a9df5cbc-0fb0-5518-bd3b-c3098269deb0 | note | REFERENCE DOCUMENTS: 701.28
c17e72fc-88e8-59c6-bb53-b28114f96a5a | note | – – – – – – – – –
2a24bad1-a243-5109-8b21-64e8ca0ee04f | note | INSPECTION/TEST METHOD: Verify
a6165111-d2f2-53b2-a264-3379797d2a2e | note | – – – – – – – – –
e902a610-54a6-504f-9b09-7cddfb1da97f | note | RECORD OF CONFORMITY: ITP Signed
bbab3530-beab-53d6-ba29-0cf01f37e994 | note | – – – – – – – – –
3369d242-36f7-51ed-a662-48b684915200 | note | IP
b589b919-3d5e-5d28-ab16-7c7cd75ed9b5 | note | – – – – – – – – –
d8024b48-300d-5e80-8036-0ca45c338f1d | note | RESPONSIBILITY: Site Engineer
f6311747-abb8-5269-9222-bb2f5e0c66a0 | note | – – – – – – – – –
d98b9ea1-ccc8-5c18-82db-75e9e5c5687f | textbox | DATE:
04a74e19-53d7-4a42-9900-c48fbe3de4a7 | checkpoint | Final Inspection
7c57d421-888b-541a-b2cd-1c6ccd4c830b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e96ddf66-b438-5c9e-8ede-c837dcdf1553 | textbox | Print Name:
9c32011c-a98a-5607-b20c-8ad8c420c258 | textbox | Position:
c5d07929-9b71-5f23-ace3-38bb24b574e9 | textbox | Date:
6fb24073-4612-4e53-8bc1-d451785fe85e | checklist | FHC-ITP-009 - Profiling Rev1 | itp | FHC-ITP-009 - Profiling Rev1
69f0293d-4635-46f1-8bcd-b93e795a0081 | section | 1 - Preliminary Works
f9462b4b-0c95-4003-b344-278d8cc6284a | checkpoint | 1.1 Check for correct documentation
330e73e9-3a0a-50ff-858c-91fe2bee6161 | note | FREQUENCY: Prior to commencing any activity
436a1692-04d7-514b-aa97-f748641d3dd5 | note | – – – – – – – – –
a674625f-1804-584b-81b1-e535203d77c3 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
7c9e3791-1683-5b53-a7eb-83f186e7ba13 | note | – using the correct and complete set of drawings
1979f499-a2aa-5f44-992c-16b86bfc22bc | note | – all drawings are the latest revision
a7047f78-a862-55c4-9367-686c83872a10 | note | – – – – – – – – –
4c3503d9-e137-5521-8477-f3a84e0a0541 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2782aec6-348b-5982-b8d6-e9194016748d | note | – – – – – – – – –
d2678a9e-092e-5a54-b586-013b9df9d148 | note | INSPECTION/TEST METHOD: Visual inspection
eed79a5e-b7b0-5510-9469-6f800aa581f2 | note | – – – – – – – – –
b3f175bf-4246-545c-94e5-d5c6aa772289 | note | RECORD OF CONFORMITY: This ITP signed
8c5652af-818b-5997-abfe-259ec6e1d6fc | note | – – – – – – – – –
689c0d58-134c-510a-92e3-219fce98e990 | note | HP*
da354b42-c5d2-5cc5-9d87-71a5ebf1709d | note | – – – – – – – – –
f8c18ddb-4cee-56ee-a5cc-be7d8ef4d949 | note | RESPONSIBILITY: Fulton Hogan Engineer
50acbc34-65a2-5982-9895-9e62d6c3261a | note | – – – – – – – – –
db13739a-5f85-5f87-8a51-15071c2274d2 | textbox | DATE:
6688f0da-5bc8-4378-b2aa-45fd4bda636b | checkpoint | 1.2 Implementation of all measures and controls
fd492931-8b69-5702-bb10-b6d3f1f9ff9f | note | FREQUENCY: Prior to commencing any activity
43c62598-86ca-5b36-af4b-0ac1546fa700 | note | – – – – – – – – –
2c953f87-ed6a-5589-bfdc-5b7b0b7d54a1 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
37a2b6d3-c77f-5670-a0aa-be21cc4d74e1 | note | – – – – – – – – –
65b1cc13-2b72-5932-8ff8-11331e2d3115 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
bafe42c4-42e0-5c43-81bd-f7c6bbd2c5e6 | note | – – – – – – – – –
7dcbf39d-4583-5078-bf75-aea6278732ee | note | INSPECTION/TEST METHOD: Visual Inspection
f44bd40c-d8f9-5d9d-a3c6-2824a2a43691 | note | – – – – – – – – –
38a2886d-a5ee-5507-8c5e-9603771ca57a | note | RECORD OF CONFORMITY: This ITP signed
68d113d1-6714-51b5-af9d-69a76dccb495 | note | – – – – – – – – –
8424fa29-2e3b-5cb1-84ce-d73ed94d7e0b | note | HP*
f5c82f50-2d4c-5770-aec5-24d70a336dd3 | note | – – – – – – – – –
d51793c1-e4c0-5c61-91ff-ad596c823e92 | note | RESPONSIBILITY: Fulton Hogan Engineer
1aab2079-fb1f-5b0a-8b4e-dadfade1b441 | note | – – – – – – – – –
6e0fb8be-b955-5d8e-a28a-85459f78fd1a | textbox | DATE:
85a8660c-2a3d-4dae-955f-21cbcb909db5 | section | 2 - Construction Works
4796cf22-ed2e-479b-8402-8be986da596b | checkpoint | 2.1 Profiling Works
1099a73f-f8df-5a38-b456-af924cb9adbd | note | FREQUENCY: Each lot
eba0cee0-e7d0-5506-a953-a07d6b08be97 | note | – – – – – – – – –
6c9d8c5d-9bb8-56d7-bf59-1686505aab9c | note | ACCEPTANCE CRITERIA: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
858d2199-b576-502f-86b9-c025b58b442a | note | – – – – – – – – –
51e73baf-4958-5d4c-a603-e5a2a92ba936 | note | REFERENCE DOCUMENTS: 402.02
d82fd3fc-1446-56fa-b540-8829ee591de1 | note | – – – – – – – – –
03a36cac-941a-50dd-9233-843217778010 | note | INSPECTION/TEST METHOD: Visual Inspection
9db6c544-741b-5b70-b096-d01eeb360802 | note | – – – – – – – – –
55237a5a-a01f-5f2a-9590-e498f3b1588d | note | RECORD OF CONFORMITY: This ITP signed
24d3cefc-3a5d-51b1-97b4-4064bf1bc704 | note | – – – – – – – – –
acf8bc04-837c-59dd-9974-62e065c22628 | note | WP
0f631d12-de5d-5562-9fa2-e1ebd7459390 | note | – – – – – – – – –
cc6c07ec-fc6e-5def-b383-399fb119d95d | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
b0a12475-9c04-52c3-852b-ec3a1bc37242 | note | – – – – – – – – –
fcced668-bedd-5aab-be64-dd48b3cd6f59 | textbox | DATE:
08cc5710-5798-4737-a485-566410dbcd6b | checkpoint | 2.2 Depth check
db73131a-0be9-5764-9b28-ebf5f40e02de | note | FREQUENCY: Each lot
1d449daa-13fb-5891-a95e-85e3c4d6dcdf | note | – – – – – – – – –
d33f41aa-2c5f-52d2-8927-a9b8f5742cac | note | ACCEPTANCE CRITERIA: Average depth of pavement to be removed shall be 40mm ensuring that all Wearing Course is removed.
b54af1ee-b7b9-56c4-96c4-5a4346687e81 | note | • After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
947d74c8-86e6-5ac0-96a5-de021771c5dc | note | – – – – – – – – –
7f3e3edd-d3bd-58b0-8e3d-fbd3cb058fb8 | note | REFERENCE DOCUMENTS: 402.02
5cab79fa-8bf8-5d0a-a342-44a9ae256175 | note | – – – – – – – – –
c1d316b9-ebaf-5e6b-b6c1-454904832541 | note | INSPECTION/TEST METHOD: Visual Inspection
78316e38-f1e4-5d20-bb30-1d1f46f92978 | note | – – – – – – – – –
c889a62b-d843-5458-857b-78445d87db74 | note | RECORD OF CONFORMITY: This ITP signed
ba7cece8-da6d-51db-8c46-49627d2b7762 | note | – – – – – – – – –
e6e23a33-4516-569c-ba72-078b17a3e2eb | note | WP
3b6c6ef7-500c-568f-8fef-b837cd5ec4e4 | note | – – – – – – – – –
ab6ab7c4-9d09-5e5b-9fc0-3d280795ac92 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
56d609fc-71c6-5bb0-a008-839e2e0fa4da | note | – – – – – – – – –
2aaac270-526b-587a-9f17-bf3dc64525db | textbox | DATE:
87c5738b-b219-4759-8f8e-8ba2a88535d9 | checkpoint | 2.3 Temporary ramping (longitudinal)
95f9611a-2744-58e2-8751-5cea3490aeb8 | note | FREQUENCY: Longitudinal edges
1b02d0c6-0376-5f01-a096-807c5d502735 | note | – – – – – – – – –
126efb32-049a-54cf-a7fa-25ceb8cd99f6 | note | ACCEPTANCE CRITERIA: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
27ad8924-5830-5eb1-a8f6-b81a6a7c2ee4 | note | – – – – – – – – –
183faba7-98d5-5681-ae9b-11d8b912a4df | note | REFERENCE DOCUMENTS: 402.05
28911900-541a-52c8-9345-ca1f93526f81 | note | – – – – – – – – –
8ca7c42a-678c-5826-b78a-5935d46f3a1d | note | INSPECTION/TEST METHOD: Verify
3275999c-b207-5b94-8db7-4386c1871565 | note | – – – – – – – – –
d45150d0-3fd0-5c02-9989-ace3f297c87c | note | RECORD OF CONFORMITY: This ITP signed
f044c9f0-33b6-5e74-836f-677b035f0108 | note | – – – – – – – – –
dde62919-9e4b-517d-815e-a75689870931 | note | WP
a36f7cbf-b241-5396-be5a-1355b16c8575 | note | – – – – – – – – –
862610d9-fcca-5856-bbb3-db31c453d37c | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
82ac1268-8993-5f39-b71e-7c53384916c8 | note | – – – – – – – – –
65ba2c93-b804-5988-8231-614cecfff502 | textbox | DATE:
d22bc193-13ab-4c4c-832e-993b0272dbe1 | checkpoint | 2.4 Temporary ramping (transverse)
b6fc80eb-2dd5-5c31-8d5c-5ee490c71c99 | note | FREQUENCY: Transverse Edges
bd35881b-db54-5eb9-bbda-a08734fb57d1 | note | – – – – – – – – –
cd53f918-c4d1-5545-bc73-53d50152dd0a | note | ACCEPTANCE CRITERIA: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
0d1810fa-6109-546a-8c7e-0f32c92d8dcc | note | – – – – – – – – –
6df580de-3b43-55d8-8b39-5cc266ab6211 | note | REFERENCE DOCUMENTS: 402.05
f2adb7ba-2103-5c0e-849d-8e1159deeda8 | note | – – – – – – – – –
daacf506-7554-5142-8ad7-bd23157f7b06 | note | INSPECTION/TEST METHOD: Verify
979e5616-bb44-5356-a456-01d193cae829 | note | – – – – – – – – –
1375c4cb-9c1d-5108-a9a6-097999148834 | note | RECORD OF CONFORMITY: This ITP signed
4ae697ca-7547-5d8a-ad3b-18342d4bda37 | note | – – – – – – – – –
af4a53f0-f023-58bd-b00c-12f09d725bab | note | WP
f93ec3ae-3a21-521b-8829-c7b75746876a | note | – – – – – – – – –
816a18fc-eab0-51a8-b38b-156f9c26964c | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
a5d460e0-16b3-5bce-93f9-a44e76096c36 | note | – – – – – – – – –
92ed54b5-1194-5690-88db-cc1fb74d4c21 | textbox | DATE:
4941292c-e115-448c-a512-46682f548f38 | checkpoint | Final Inspection
e0084c6e-5f02-55b6-90ad-16cf17b68313 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
580e4567-0788-5ecd-90b8-362b27cf218d | textbox | Print Name:
3bb2df73-9caa-5b44-a4b6-d04880d828a6 | textbox | Position:
b29fb01c-6e2f-58b2-8921-55f4e92c402c | textbox | Date:
05c95a1d-ece9-4142-afe5-30a27c45afea | checklist | FHC-ITP-011 - Class 4 Crushed Rock Rev3 | itp | FHC-ITP-011 - Class 4 Crushed Rock Rev3
13a05ccc-9fca-4c49-954f-3a407ec334cd | section | 1 - Preliminary Works
cf7839e9-6062-461f-835d-e293c5c34c79 | checkpoint | 1.1 Check for correct documentation
52f777d9-a4f2-5a64-ad91-ad085231b8e5 | note | FREQUENCY: Prior to commencing any activity
56fc93fd-a433-5082-8a88-c5c8a66bc914 | note | – – – – – – – – –
3a87c55c-66bf-582b-bdf6-b6a43b6430d3 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
b9f45824-bfd1-5e02-901c-6a6287af5bd3 | note | – Using the correct and complete set of drawings
e7f142b9-0d77-51c4-916f-913db59f91e3 | note | – All drawings are the latest revision
bfff3284-483a-52f1-b92e-5d7a0284e95e | note | – – – – – – – – –
3565c3b0-aa6f-5022-b1da-8ec7db50ea05 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
567cfc46-ab82-53f5-8442-c76d2605cded | note | – – – – – – – – –
b2f67a6b-ef60-506e-894e-c4e6a450a40b | note | INSPECTION/TEST METHOD: Visual inspection
9455841e-4592-5987-9d45-3ecd1400448c | note | – – – – – – – – –
f4f4ef16-22b0-5ce0-848f-49640953bf61 | note | RECORD OF CONFORMITY: This ITP signed
482093ff-2216-5c7a-99bb-d79b4428c57b | note | – – – – – – – – –
11e85779-4adf-57ee-8fbd-2218409964bf | note | HP*
1a23518d-0207-5e1a-923a-dfec6ad20782 | note | – – – – – – – – –
f5fe2c26-f9fb-5678-a93b-2d53c404d2c7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
42680a55-459b-500f-a715-8b3a2f9864a3 | note | – – – – – – – – –
5fc7b41d-3cbf-510f-9710-87123eeebacc | textbox | DATE:
21fd0523-c71f-4374-91e2-02809f8dbe86 | checkpoint | 1.2 Material Mix Design
74a8b6d6-96a3-5912-ae61-d17972c70cd7 | note | FREQUENCY: Prior to commencing any activity
0a55c5c5-e948-5f51-b9ab-3bdd7ee99722 | note | – – – – – – – – –
09e84020-2757-54b9-b056-6e3a5603758f | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
ee7dd801-f461-57e6-948b-6c16248632bf | note | – – – – – – – – –
ad4eefec-e754-53cb-a842-c9bbfc3fe87c | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
3e41b062-7289-541d-992d-140e62a38429 | note | – – – – – – – – –
1e806484-ba0c-5387-bdda-d9e59272562d | note | INSPECTION/TEST METHOD: Document Review
31248f62-7013-574e-bbf0-3f0a29410d66 | note | – – – – – – – – –
8ebae2b8-650c-5262-ae15-13ccadceeb76 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
4cb84bdf-0bf2-51a8-b9f4-266c3808dc91 | note | – – – – – – – – –
53cce32f-4336-5aba-aa38-c95fc3a9126c | note | HP*
578e8547-028a-5d36-b157-5069ccf2ae25 | note | – – – – – – – – –
b35ffc57-ea3d-56d7-86c5-6cb175678a2d | note | RESPONSIBILITY: Site Engineer
0b734c2c-188d-560b-bc38-d09cb0af1831 | note | – – – – – – – – –
41626ab0-e696-5028-ae14-4fba98f8ec10 | textbox | DATE:
5e06ad8a-42f9-400d-87a1-983091549610 | checkpoint | 1.3 Implementation of all measures and controls
ac6c4cba-8f86-5e47-9dc7-8daa5dc8efd9 | note | FREQUENCY: Prior to commencing any activity
30485c4a-ce61-525b-be84-b9727c674e51 | note | – – – – – – – – –
422a4ef2-b81d-5c80-9cce-1b72a8b7aa7d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
1e82f27b-ca49-5283-9e51-c328a98cb055 | note | – – – – – – – – –
7e9d5278-8f43-51e7-bbec-dc731b73e4f9 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
c05545d2-536c-5dbe-8982-1f73adac5c4f | note | – – – – – – – – –
5134a8a1-edc3-5a70-ad6f-dd353bfd3d2f | note | INSPECTION/TEST METHOD: Visual Inspection
146bc9b2-f4ce-5d8c-89b6-32faa7f6a1d6 | note | – – – – – – – – –
73f2d9da-3d90-5d55-adcc-29b1ea7665e3 | note | RECORD OF CONFORMITY: This ITP signed
7bb121f2-391f-5146-a37b-8fa5cd7cd688 | note | – – – – – – – – –
c995619e-d9f1-508d-9563-32d6bcc5d7bf | note | HP*
ef5832c3-0002-517a-a184-b184896ce908 | note | – – – – – – – – –
63825648-bda5-59bb-b9cb-9bf4b36f54ac | note | RESPONSIBILITY: Site Engineer / Site Foreman
d1b46b7d-8481-5c80-8799-28d4fa1bfe48 | note | – – – – – – – – –
90ce5684-2ee5-5f91-b40e-955296973076 | textbox | DATE:
334d1828-c8ee-4678-8b9f-11a3890a694b | section | 2 - Construction Works
3907ab4b-2ad2-40cd-86f0-666191169c19 | checkpoint | 2.1 Transverse Joints
64acfbec-34e9-5984-a5b4-0a2a8fdd503a | note | FREQUENCY: Check prior to placing material
c86dc8a9-63d6-5e7d-9f72-39266735db2b | note | – – – – – – – – –
c873e689-28b5-56b0-86e1-54ab08aa6e85 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
a2e31b44-5410-57a4-82eb-49241f40808a | note | – – – – – – – – –
5402bea3-ae35-5014-b4c9-80d0339695fe | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
eb8d1160-0ee9-5713-8e2d-6d514150c3c6 | note | – – – – – – – – –
0aa4d5f0-7036-597d-ba2d-31c95720ffd7 | note | INSPECTION/TEST METHOD: Visual Inspection
5d3236f4-9e00-574b-bf62-b8c09fddbf1f | note | – – – – – – – – –
5f167bcd-9aae-5030-9c0a-d6742b6d1d37 | note | RECORD OF CONFORMITY: This ITP signed off
2cc8d678-2846-579f-a428-da0a1be3d909 | note | – – – – – – – – –
4f7396eb-39c4-5eea-9b3d-a32fbd0bd02d | note | IP
d52bcbb6-8fb9-5439-8b88-1564ef3d1084 | note | – – – – – – – – –
e48305b5-c5c9-58c9-9b6b-512bf0b0ad1f | note | RESPONSIBILITY: Site Engineer
63306a61-624b-5290-90d3-5f22f6c78756 | note | – – – – – – – – –
6162bc43-2357-5bc1-849c-a25bfb60466a | textbox | DATE:
5870bd0e-cbd0-4d7d-b0b9-3a53faaa3868 | checkpoint | 2.2 Longitudinal Joints
2334312e-6020-5cd1-832e-5e9bf0413b99 | note | FREQUENCY: Check prior to placing material
59353fc6-6710-517d-94cc-8ff91d1725a6 | note | – – – – – – – – –
ba13287d-e6d2-5182-8db5-0b238592bbe0 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
c95a266b-3c4e-5927-83d3-f9434df8b6c9 | note | – – – – – – – – –
8ab37c23-3c07-5e65-9b12-8d0b44380bb1 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
4565df8c-f46e-5de7-a830-8217b57142aa | note | – – – – – – – – –
a2910e7d-6255-5230-a698-2df498ed582d | note | INSPECTION/TEST METHOD: Visual Inspection
53e84bd2-56a9-577b-ae5c-5949ff2078a8 | note | – – – – – – – – –
2bf3c335-b0df-5272-91c4-29af300fb5bb | note | RECORD OF CONFORMITY: This ITP signed off
8b2472af-5474-5d5f-bf92-b1a6468127be | note | – – – – – – – – –
58fd8593-37c7-5667-a874-9fb85119e37b | note | IP
77d81ff9-2a1c-5061-8530-94c180c81863 | note | – – – – – – – – –
ba7475b8-4a56-5342-aed8-1aeb02684072 | note | RESPONSIBILITY: Site Engineer
6a6f5f07-cc21-5e89-b70e-ca3936ea7d34 | note | – – – – – – – – –
69618b48-1b6b-5e6a-915f-cb0dcb315f52 | textbox | DATE:
448523ad-68d1-4d10-bc72-53ff2f964fef | checkpoint | 2.3 Lot Size
a80581ee-4882-5fdc-94e6-a8d77087beae | note | FREQUENCY: Check prior to placing material
3e97694f-d348-56b7-bde6-2ac7a2c94ff7 | note | – – – – – – – – –
fe931fa6-0815-5879-94f1-3f234c04b8ed | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
41feef02-95ba-5246-a96f-999145a03bb2 | note | – – – – – – – – –
7c5eccd6-3537-5039-9873-dbb78d04526b | note | REFERENCE DOCUMENTS: Cl.304.08 (b)(ii) Table 304.111
97cc8e5d-d74b-564f-97be-3b0ecdf7ef3a | note | – – – – – – – – –
fdd6752e-61bf-5cd1-87af-1a63fed4fef9 | note | INSPECTION/TEST METHOD: Site Inspection
e88a90f4-4713-53e9-9452-30ba5bfe08fe | note | – – – – – – – – –
3c70bee5-7931-55e0-bfe8-ccbecb38e6d6 | note | RECORD OF CONFORMITY: Signed ITP
063b6f19-11d1-5216-89ab-dbe0ccb5c9f0 | note | – – – – – – – – –
10482acc-0ad0-5feb-85b1-5d0c6c7f94ee | note | IP
adbe3f20-631d-5c45-bb17-0c9831c0a476 | note | – – – – – – – – –
d3b83c78-2b2e-59cc-975b-b5b32230e635 | note | RESPONSIBILITY: Site Engineer
d06137e6-560f-52d5-8fcc-f52f4a9972b2 | note | – – – – – – – – –
c4e23d15-867c-513c-814a-2754371f8fef | textbox | DATE:
b8f3829a-0a7b-4dc8-a5b7-a10192c80f01 | checkpoint | 2.4 Layer Thickness
1292d33b-9c74-5513-9dd1-a40541eba1d2 | note | FREQUENCY: Each Lot
e4a0c118-9d1c-5966-a1e9-7ac3989bc066 | note | – – – – – – – – –
68119b59-5a7a-5930-ba5e-aaa8aad080cb | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
71d3caa2-2f12-5b9e-971d-c05c6c18967c | note | – – – – – – – – –
3fac4f73-4409-5cae-bd4a-ebd32a8dc8cf | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
244ebb56-f9da-5a51-82bb-86547f4192fb | note | – – – – – – – – –
3daea68b-cd05-513d-96b8-d1188f921ab5 | note | INSPECTION/TEST METHOD: Site Inspection
59c04903-98ab-5b08-b700-babf4dce73eb | note | – – – – – – – – –
72e5beac-04c0-5dc4-ad4c-1e4a4b1674a5 | note | RECORD OF CONFORMITY: Signed ITP
91534d2c-933f-541e-8a04-975e44d26128 | note | – – – – – – – – –
5b4ea9da-0937-5f1f-bb5a-eefaece9068f | note | IP
e407e8f8-829a-5c17-80af-53d3a0b6fbbe | note | – – – – – – – – –
c9f5d1dc-cc7c-5507-9394-971b43fd8d72 | note | RESPONSIBILITY: Site Engineer
b05f385f-7c7e-5dfc-b1fb-f47e6b981e61 | note | – – – – – – – – –
3b23de9c-3c41-59cd-9179-0503f317ede3 | textbox | DATE:
21d2e5e8-9544-4212-9b43-99ac8bbe1b58 | checkpoint | 2.5 Proof Rolling
8a362a6a-1f19-5507-92c5-3c4c3eef425b | note | FREQUENCY: Proof Roll each layer
cb05dd67-437c-523c-a42d-214e4cd7702a | note | – – – – – – – – –
38eb918a-e71b-5ee7-9676-c40ebf642072 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
7717e6a7-659b-5aa4-9722-a49c13ac55c6 | note | – – – – – – – – –
cde28855-0c1d-5ff5-9365-dab266397bc1 | note | REFERENCE DOCUMENTS: 173.03
7d183582-868c-5f77-888c-8e244c35642f | note | – – – – – – – – –
f1decbc7-cb02-50ca-b892-1c4a44eae770 | note | INSPECTION/TEST METHOD: Visual inspection
622f9ff9-3e80-5a4d-843c-6d40f80025fb | note | – – – – – – – – –
78843111-c0a2-5c7f-8866-d8354a403171 | note | RECORD OF CONFORMITY: This ITP signed off
6001ecf1-f4fb-541f-9a0f-22f8cc58768b | note | – – – – – – – – –
08494f61-d637-5fce-8818-9dd82f2e7a9b | note | HP/ WP
4c2f70aa-d8e3-5421-b0df-cb2396780047 | note | – – – – – – – – –
26665c7d-5596-5a73-bd96-4809c0fdffd7 | note | RESPONSIBILITY: Site Engineer & Superintendent
44d567ca-a6bf-57ba-a7b7-1ce25215ff74 | note | – – – – – – – – –
b910d5af-4895-5038-8842-54dc98ef6439 | textbox | DATE:
7772db6f-e701-4fe6-bbce-dd56dd73cb31 | signoff | AUTHORITY HOLDPOINT
90ce4cf8-99ab-42e0-b140-1a98a28f0ece | section | 3 - Testing Requirements
1bb68dc4-0221-4f6f-adb2-e5ce5f1f7c8a | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
ebb31d1c-6d39-5333-bdc9-283b2367dc14 | note | FREQUENCY: Prior to Testing
8877183e-be87-57be-8a33-560cba21cef1 | note | – – – – – – – – –
6035885c-fcd2-545a-a04c-ee81c7cbfa6e | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
466e39a6-604e-5795-9665-226a8bdc81d3 | note | • Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
1af90ad2-2b2e-57ac-9d57-49ede4ee506f | note | – – – – – – – – –
4ad8ea79-2ab7-5828-9981-8300ae167374 | note | REFERENCE DOCUMENTS: Table 204.161
73a2f69a-9d42-52da-8166-4008a35baba1 | note | • Cl.304.08 (a)
8b7df758-68ac-5f73-b169-1bd99fe3e99c | note | • Cl.304.11 (b)
2b8971a8-6ecd-5de3-aa18-8c887ac6ca87 | note | • Cl.304.11 (c)(i)
791d8e6e-68a9-511a-9536-88a5d509ef1e | note | • Table 304.111
96624e12-b44b-56b0-897f-2f0cc4dc38be | note | – – – – – – – – –
00c51bbf-193c-54fc-a575-a70a819371c8 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
b566aeac-93ce-5a2b-839c-55f6e870dadf | note | – – – – – – – – –
a87b2522-9326-54fb-8846-a706866bf80f | note | RECORD OF CONFORMITY: Signed ITP
8587960b-f1b9-5864-88f9-b8025b8f920f | note | – – – – – – – – –
07eb4f98-fc64-5203-8e37-1e3d0c0e25db | note | AP
71a49fdd-ebca-512c-955e-ac4ce7dced40 | note | – – – – – – – – –
d7454d48-f2ad-52de-a192-c44dc284421f | note | RESPONSIBILITY: Project Engineer
8b1061a5-df97-5526-9973-4e9ba78f7118 | note | – – – – – – – – –
039aaa5d-bfb3-5229-9639-436eea318437 | textbox | DATE:
69ca73d3-7d03-4b88-844b-f3765659e749 | checkpoint | 3.2 Compaction Testing
7164db2c-997a-5607-9000-4a87a9162c23 | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
58444bca-759e-542c-bb9c-022a381c35c8 | note | – – – – – – – – –
5a722c9a-bbc2-5d65-a7c7-27ccb44870fa | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
e0463edf-146e-56c6-b332-fe47956bf8ab | note | – – – – – – – – –
ff11fbe1-9c06-59fd-994b-320680a419f8 | note | REFERENCE DOCUMENTS: Cl304.08 Table 3040.061
de96fc47-e68e-5229-9a99-0801cdf2c3a4 | note | • Cl 304.11 (b) Table 304.111
c04e4ee9-bde6-5e53-bb7c-a7a638efc09d | note | – – – – – – – – –
569c57ab-2198-568a-a812-b94f3f6f1bcc | note | INSPECTION/TEST METHOD: Test point
a73baea3-69ef-515c-af5e-181e19db0347 | note | – – – – – – – – –
5a509b12-4bf6-5df7-b490-53a4454d4238 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
2b61fd1b-dac0-5500-b774-b94f986e4d9c | note | – – – – – – – – –
d89e021d-ae47-54ea-b9bd-1edb0f795c8a | note | TP
a93d856a-1e68-5c9f-8e74-041fe122d15f | note | – – – – – – – – –
8b63fd75-5602-5cd5-b809-65f9e24d25b0 | note | RESPONSIBILITY: Site Engineer
3d3e3144-db39-5838-b7a0-9a7df25eafc8 | note | – – – – – – – – –
589f60e5-2e11-5279-999c-5d474542cd1e | textbox | DATE:
2553d43d-1f08-4ed3-98f4-bdad315739c0 | checkpoint | 3.3 Compaction Testing (Small Lots)
0ad5e02d-a7a4-5a9a-b028-5c49b342d69a | note | FREQUENCY: Each Lot
4130f84c-90a2-5c0f-841f-3e9aded3505f | note | – – – – – – – – –
8ddd7044-d852-52e1-b02d-ed7a1a174119 | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
3903b014-9649-51d4-918b-e7115d942a22 | note | – – – – – – – – –
7f7ec1f9-2412-57aa-b336-f474ed72d2cc | note | REFERENCE DOCUMENTS: 173.04 d
b62b8cc0-221f-533f-bc56-caf0ced6318f | note | – – – – – – – – –
d6898013-9ac4-5515-ba7c-d72ee3df9a52 | note | INSPECTION/TEST METHOD: Test Point
e0efdbfe-7478-5690-93ce-5d9aecda0331 | note | – – – – – – – – –
8d899e9b-f65d-539e-adec-9f5a8a962901 | note | RECORD OF CONFORMITY: Test Records, Lot Register
a0fe97b1-e9a0-5672-9d7a-9a34392c1ab0 | note | – – – – – – – – –
24316d61-bdd7-58c5-a3e7-ce04950eb96b | note | TP
228287f9-460c-5a26-9de3-2ef3a68f3009 | note | – – – – – – – – –
6a811017-b4b6-5191-9a33-17a4582172cd | note | RESPONSIBILITY: Site Engineer
e0ef418f-a1be-5eb2-abc2-34b52c04b2de | note | – – – – – – – – –
7f6dcadc-5e09-5f0b-8d5d-c3324d6d4678 | textbox | DATE:
152b38d4-58d4-4c2c-8952-f10be3b88c6b | checkpoint | 3.4 Material Grading - Post Compaction
fbe3abdd-785d-5f3d-868e-afd732ce3c9f | note | FREQUENCY: First Lot Only
65d41393-5a4c-5511-8959-0b4ac05d5cfe | note | – – – – – – – – –
c5973af6-f4bf-5c10-ae7b-4fd271283ebd | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
ebd1e8e8-8791-5d6c-90a4-f461e2e6f0d1 | note | • Class 4 - As per Table 304.101 - VR Spec. 304.10
50e211ce-069c-5dc8-a030-6ceeb71a6d38 | note | • Class 3 - As per Table 304.101 - VR Spec. 304.10
0c501e60-e7f6-5aa4-bdbc-c540b560e96e | note | • Class 2 - As per Table 304.101 - VR Spec. 304.10
d9f8dbf4-f555-53c1-91d7-a7a7270cfa66 | note | – – – – – – – – –
98bbc528-4051-5065-be5f-92499cf2f152 | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
094882a3-468a-5e66-8f33-113b299410d0 | note | – – – – – – – – –
449fdf3e-3e0e-5030-8612-b6e050d688ee | note | INSPECTION/TEST METHOD: Test point
c2afe059-c7ae-530d-9603-fe3351da3caa | note | – – – – – – – – –
ede31420-6c33-57a9-8553-091690dc71a5 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
a3901c26-5cc6-57fe-8b2e-7741792db477 | note | – – – – – – – – –
167e4a08-bd56-5367-b5a0-8c4532f4a677 | note | TP
6fdb3c7e-9dfb-5e6e-b529-92808ee1ab94 | note | – – – – – – – – –
2daf8f41-f349-564d-91c4-eba5b4731d61 | note | RESPONSIBILITY: Site Engineer
3ff4413d-b3e3-58dc-ae06-255af634840e | note | – – – – – – – – –
55da9979-b7c2-5f1a-83a8-37055802d07b | textbox | DATE:
534fc721-779d-48c9-a0c6-d6e8bf05327e | checkpoint | 3.5 Plasticity Index - Post Compaction
679ab7c2-f0d0-5284-bedd-3010072b0983 | note | FREQUENCY: First Lot Only
aacb44d9-3f7d-572d-9455-0988ee31dc7c | note | – – – – – – – – –
b9fd7a20-b383-5e37-9e73-4b4e48b911e3 | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
1055a9c7-fb22-5896-bb17-8e14d7e88849 | note | • Class 4 - 0 to 10
80435de4-5363-542a-8c76-ae6fa5dbf8b4 | note | • Class 3 - 0 to 10
9d649f10-2cc3-5368-b2af-f8267c184a0d | note | • Class 2 - 0 to 6
446b144b-a89b-58ff-bc62-ee03bbd5c8b5 | note | – – – – – – – – –
9bf798b9-4054-5753-9d28-f8474eb88efe | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11 Table 304.103
bd430a81-d8f9-5f30-bf20-49dfe3fb3fdf | note | – – – – – – – – –
19614a82-f491-5eec-ac35-e2008e2d1d5b | note | INSPECTION/TEST METHOD: Test point
912a244f-4ebb-5cae-be01-d3c5950a9d42 | note | – – – – – – – – –
9e67804b-7d3b-516f-975d-c1ece828f33f | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
50e56967-a752-53b2-a4b2-961c5cb1bdda | note | – – – – – – – – –
e4d4d178-f63c-5261-a0d9-4eddbb76d080 | note | TP
96c63afb-c456-5f51-8479-e85956fa020c | note | – – – – – – – – –
a9e74989-1f32-518d-b5c4-b4fceba0aab4 | note | RESPONSIBILITY: Site Engineer
fd3a889c-addb-56ac-bbe9-3220abd626c9 | note | – – – – – – – – –
c220174d-b9b0-56d9-bede-1c6805afbfb2 | textbox | DATE:
51700fa9-549c-4815-9580-412bc622e807 | checkpoint | 3.6 Survey Conformance
9e5ba55e-7964-50d1-9809-b06b94f39a30 | note | FREQUENCY: Each lot
582c413c-6dae-555b-8761-1374925b2260 | note | – – – – – – – – –
bafc7d1a-af31-56f4-aeae-ad4631405d3b | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
430159a4-34bc-57b9-aa4c-c34dcd554a65 | note | • Shape: no point deviation > 8mm from 3m straight edge in any direction
7ab11389-9404-5232-a226-87cd44df2f1e | note | • Surface level tolerances:
941bb0ee-0ce8-5325-8f17-a3b5c16c1489 | note | • Range x = +6, -16mm
be7687f8-fd68-5348-a8c7-7bb0355d1f30 | note | • Max S = 15 mm
22b51c84-cb43-57d7-8914-b41e2a4b6158 | note | • 40 measurements per lot (Minimum)
afd6da62-9b2d-541d-b752-6cebbe641d65 | note | – – – – – – – – –
026ed3c6-e2f6-5531-99d1-f128bd5c6574 | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings Table 304.062
ed42da8f-1b4d-5402-9a42-42eae9993e97 | note | – – – – – – – – –
7ae3a6dc-0436-514a-9bcf-c04dff93a47a | note | INSPECTION/TEST METHOD: Survey
d8afadc4-dbcc-5897-8b8f-18a3809cab0c | note | – – – – – – – – –
4c8ceef7-855a-5294-8730-3d35816a4001 | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
f709a8a6-8c3e-5dd0-ab98-b820e2004967 | note | – – – – – – – – –
7836049d-0155-52e7-98e8-b961683e68d5 | note | SCP
9228a04b-01be-5450-900d-772b3f251233 | note | – – – – – – – – –
f29a7fbc-c673-52f1-b46e-fc06ebaa10a0 | note | RESPONSIBILITY: Site Engineer/ Surveyor
bd87e28d-f013-5590-a4bd-d2de0e29797e | note | – – – – – – – – –
84946892-bdda-519a-a4f9-fe5a03112fc5 | textbox | DATE:
062e52da-69c5-4114-ba54-cf73b096106c | checkpoint | Final Inspection
c43c7e0d-ea0e-5f9d-b3fd-22f370ddfd61 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
cacc2b44-3c6e-533d-b657-0184707c6222 | textbox | Print Name:
33985be5-3b50-518a-a307-d0b02a05dd8f | textbox | Position:
b25a4e60-6e2a-554f-84db-def378be5f0f | textbox | Date:
bdbbc7e4-cf4b-4483-a039-db02621212f2 | checklist | FHC-ITP-012 - Hot Mix Asphalt Placement Rev2 | itp | FHC-ITP-012 - Hot Mix Asphalt Placement Rev2
6fb4ea5c-b245-4916-8542-38d4664795dd | section | 1 - Construction Works
2c938325-fafb-4d56-9392-03ce64cdd707 | checkpoint | 1.1 Submission of Mix Design
f97afe95-8505-54cf-8b63-33e762319b5e | note | FREQUENCY: Prior to commencing paving
783577ad-b710-5a91-9155-b3c947eaf2b9 | note | – – – – – – – – –
ef6f1392-d488-5ecb-b302-7ade80b7398d | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
7500fba3-4e3f-5e20-95a3-396b6a30c85e | note | – – – – – – – – –
9823bbb1-dad3-5464-b56d-d35bdc8c8283 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
b98e5725-6770-515d-a3d2-80eced263b0e | note | – – – – – – – – –
f1854100-6368-53cc-b32e-746f11f37d8b | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
4eb783fd-187c-5695-a481-328749493eb0 | note | – – – – – – – – –
f4e9bd86-afc0-59f2-870e-7b16bac45740 | note | RECORD OF CONFORMITY: MRPA approval Completed ITP
2645c925-3eb9-53bb-92cb-4d3941a1bf90 | note | – – – – – – – – –
68c4c276-739d-5b4d-85ce-a89aaf79e142 | note | HP
427061ce-58ed-5d9e-b23e-250e86c84af7 | note | – – – – – – – – –
f73d8dd7-5b1f-5883-9faf-9df3a319c897 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
b6f156eb-3218-5c19-b4be-82606e0a4c7a | note | – – – – – – – – –
9101260c-3b14-5893-80f1-8bcaca82e4d4 | textbox | DATE:
2ca7b26b-8e7d-42b3-b29c-8ddb93acd2e6 | signoff | AUTHORITY HOLDPOINT
c822facd-49f6-4ea2-a3c5-35c640019bb9 | checkpoint | 1.2 Implementation of all measures and controls
a073db97-0f5b-5dc0-aa1a-d23241e559c5 | note | FREQUENCY: Prior to commencing any activity
4fdb37ef-9428-5e25-a305-bac113c2ac7a | note | – – – – – – – – –
025430f4-f04f-51fd-a830-d1e74c167e69 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
3c836d01-1a2f-5a8d-8332-0414345c7fc7 | note | – – – – – – – – –
ec214c47-1083-59b5-a9a4-2c45886963a5 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
83971c03-867c-553d-a44c-dbe0581c5a4a | note | – – – – – – – – –
d49b170f-9253-545b-8412-2468f5f75b4c | note | INSPECTION/TEST METHOD: Visual Inspection
589fe5f2-483c-5acf-9a05-4aad146c20e9 | note | – – – – – – – – –
9bab4e5b-c281-5e75-a98c-9d0c4635ef97 | note | RECORD OF CONFORMITY: This ITP signed off
ded5ae2d-6361-5ba6-891b-2cb8759e6fa0 | note | – – – – – – – – –
814ba48d-10de-5e26-af22-e1bb1ed85743 | note | HP*
00533fe4-21ff-52ed-89d5-9fb99ad93885 | note | – – – – – – – – –
45170bc7-d30a-5983-9d5c-43c2a67b7025 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c61423bb-81f9-5093-ac1e-c285ec05201f | note | – – – – – – – – –
c2249ff6-7a9c-505e-a22d-0a0dfb4e6c60 | textbox | DATE:
20c1578a-d98c-4596-8700-064707477752 | checkpoint | 1.3 Site Inspection and Base Condition
0ad8cc13-0ea1-557e-81be-2bcdd4eca2da | note | FREQUENCY: Prior to commencing paving
66d6bc51-5225-5cb4-8026-797cba06f7d1 | note | – – – – – – – – –
3a3663eb-98e7-5575-80bd-b3ed414080e9 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
87fc6bc2-b085-5256-ab46-d53b9c4e45f4 | note | – – – – – – – – –
c9495cad-c12d-5188-9cef-4f91061a7d4c | note | REFERENCE DOCUMENTS: 407.17 AS2150 10.1 AS2150 10.3
689e7e03-7366-5d4d-9341-ce1bcba5f6a1 | note | – – – – – – – – –
1c5e538c-a551-5623-8e96-1dafad310463 | note | INSPECTION/TEST METHOD: Visual Inspection
b6627ede-2da9-5abd-a8dd-9dc47c55ccac | note | – – – – – – – – –
6eab4ab2-c509-5e7b-b48f-c7e37b9335f8 | note | RECORD OF CONFORMITY: ITP Signed
90149c9a-e472-5f15-b320-600faaa4b598 | note | – – – – – – – – –
c3c49fc4-137e-5b12-b220-2ecfd90daa73 | note | WP
46ee0a64-cd18-5da6-bf25-a3607d5edcb4 | note | – – – – – – – – –
3702f2dc-e08f-5daa-a4b3-4cc55dab8164 | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
e02240b7-e2fe-574d-b753-e824096eee19 | note | – – – – – – – – –
abf36fa9-4cad-55f8-bb42-7197c19fff8e | textbox | DATE:
47ca063b-848e-4502-bd81-97ee7aacdaa9 | checkpoint | 1.4 Ambient Conditions for Placing
6c86a7d4-3dd1-59da-bf1c-a1f2e4c5f978 | note | FREQUENCY: Prior to commencing paving
c1cb5989-d876-5374-8fcc-27b7daaf6407 | note | – – – – – – – – –
caab6e13-17ec-532f-a2f2-be0064702f05 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
b6cd7efc-4f0e-5e68-ba19-d80926373827 | note | • Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
719dd8c4-4039-5b93-8490-bfe7f6e9e907 | note | • Wearing Courses: 10°C for conventional binders or 15°C for PMBs
9205b59a-9470-51be-9486-09e648447816 | note | – – – – – – – – –
ef1dc244-59a0-56d9-a7fb-71306a47ee6b | note | REFERENCE DOCUMENTS: 407.17
38a895ef-362d-57ff-b831-b4e1bbe90d69 | note | – – – – – – – – –
9398c185-4e9f-5386-b29a-5bdbe2ea1df0 | note | INSPECTION/TEST METHOD: Verify
51c5a57c-924d-5668-9938-bd73e5bd70ef | note | – – – – – – – – –
70a2768d-f346-5a26-a180-3e54797c270c | note | RECORD OF CONFORMITY: Thermometer
2b2c4a1d-f942-5419-980b-d29b0073d9fd | note | – – – – – – – – –
844544da-9dc2-5391-b39d-cb4ff52c3e72 | note | IP
57787f9b-3426-547f-98f0-c9eda09a8d76 | note | – – – – – – – – –
425ce01d-7eaf-5b70-92d7-dca7f481b963 | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
eef35316-8432-507a-bd13-678ee6a47660 | note | – – – – – – – – –
41ffe1f8-1c6b-54d7-8112-cfc94968d0ad | textbox | DATE:
0a813cfc-13d0-4b4c-9ddf-6368965bc687 | checkpoint | 1.5 Planning of Joints
0747ba46-a608-5510-b76a-2d9a8b3ec840 | note | FREQUENCY: Prior to commencing paving
50025e12-1e99-5a32-96c6-18e97d3fc52d | note | – – – – – – – – –
3e83f9ba-9484-5010-86e2-de5eab43b109 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
5956f8dd-c7ad-5fe1-bea4-9e29848f960c | note | • Transverse Joints Offset from layer to layer by at least 2m
136d85b6-85e4-56a0-87de-e5a1d94c35b0 | note | • Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
9166e807-eac1-5984-ae57-423c5b2a8180 | note | – – – – – – – – –
b6d996ca-f128-506e-a64d-8469d4135f94 | note | REFERENCE DOCUMENTS: 407.21 (b) & (c) Pavement Drawings
fcce0d08-111e-51e3-aee6-1427186b60e4 | note | – – – – – – – – –
85873081-369c-5952-8f8b-11aeef79fc73 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
a7cf44a9-cc89-55e5-9f03-eaedd5156dc1 | note | – – – – – – – – –
b6b396f8-02c4-5479-924c-04f311db4af5 | note | RECORD OF CONFORMITY: Paving Plan
57d2e1f5-f2c5-5cfb-950b-52b16fe2fdcf | note | – – – – – – – – –
5001b2a6-45dc-5a9d-bc82-05b22173339c | note | WP
8f6a5a33-9735-581c-a2a0-e50538b6be9f | note | – – – – – – – – –
272b8513-a59e-5c70-b102-ecf4fb02a082 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
c57afdcf-3350-501d-bee0-3392fb6cd887 | note | – – – – – – – – –
4e80005f-d496-545e-ade5-d689941bf1b0 | textbox | DATE:
36f99cf3-2a94-4cf8-b9a8-13f9463038ed | checkpoint | 1.6 Longitudinal Joints with existing Pavement
9df191bc-9592-5fb4-9ba3-9eb0d8e506a4 | note | FREQUENCY: Prior to commencing paving
54000f6e-e2f9-5993-8e24-0641fc4402bf | note | – – – – – – – – –
9bbf3bcc-3ca8-5a5b-8088-77f161f9aef8 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
b77e2d60-1fd9-50c5-bcab-9d76f46254ba | note | • Depth of step to be cut to the full depth of each indiviual layer.
94761df4-edb6-50dd-8935-4067903f699f | note | – – – – – – – – –
4074eadc-2556-536c-899b-c8dec7fb0a03 | note | REFERENCE DOCUMENTS: 407.21 (c) (ii)
d961960f-cb52-54fa-bb59-453fc7cde94c | note | – – – – – – – – –
94733fed-af8e-5fc2-bcaa-920acf4daa50 | note | INSPECTION/TEST METHOD: Visual Inspection
f5070f61-ca08-593e-9ec0-d8844f46349e | note | – – – – – – – – –
d39ffbbf-ed3a-5a0e-8aaa-fdc99d42d689 | note | RECORD OF CONFORMITY: ITP Signed
8be9430f-7c8e-5fff-8766-56378edda085 | note | – – – – – – – – –
4968f3a2-3d69-5a07-982f-c6749b35152e | note | WP
d6eeb71b-2ef0-5c28-bc21-9e6bf36a43c9 | note | – – – – – – – – –
90e6ebc2-5517-5c16-a7ea-fc6b772b8f51 | note | RESPONSIBILITY: Project Engineer/Asphalt Supervisor
0c7b89eb-d912-5698-90f2-2abbf6b6a415 | note | – – – – – – – – –
422ca578-f46d-53c5-bae2-baae7e8e5641 | textbox | DATE:
d7d884ef-8fd0-46f6-b8a9-515dec9750ff | checkpoint | 1.7 Lot Size
50c30fbc-080f-501c-813e-ac46f25121dd | note | FREQUENCY: Prior to testing
329b53ee-1add-51d6-b79e-3b8055274d07 | note | – – – – – – – – –
76fdaebc-0569-5075-ab81-3df243e321ec | note | ACCEPTANCE CRITERIA: Lot size for determination of testing shall be in accordance with 407.27 (b) (ii), where less than 500 m2, reduced testing may apply
398be5b8-d033-52ad-a72a-50c1bfec26b8 | note | – – – – – – – – –
1a4ff768-d00b-5040-bb38-6a495f118b53 | note | REFERENCE DOCUMENTS: 407.27 (b) (ii)
572ec4f6-ae69-55ce-976d-a26cef55002b | note | – – – – – – – – –
26327f6f-255a-5cc7-b4a4-b014e322460f | note | INSPECTION/TEST METHOD: Visual Inspection
5330ab98-6dab-5fd2-98d9-036f337fb6bf | note | – – – – – – – – –
d742a037-9658-50a5-9c5b-40011e090fc2 | note | RECORD OF CONFORMITY: ITP Signed
2cdb0c5e-e7b9-538b-8eaa-f80c7a1b2f6e | note | – – – – – – – – –
ae9691f2-25fe-5b34-99c1-f4b01308a84c | note | IP
78e4681e-87a9-5616-b9d4-c235266b5eb5 | note | – – – – – – – – –
31d24177-45e8-565d-be96-aed8e3839ad3 | note | RESPONSIBILITY: Project Engineer/Asphalt Supervisor
0e6cca3c-2de3-5351-9ed3-7545582cd60c | note | – – – – – – – – –
e7e4a8be-6668-5e8b-a094-aad68f6aaeb1 | textbox | DATE:
e98adcec-b00e-4b76-bce2-b342892c6ba3 | section | 2 - Asphalt Placement works
06730e49-6dd0-43d1-a2b4-cd890aea8b5a | checkpoint | 2.1 Tack Coat
2f12d2e0-b981-5e5d-8c8a-6f778f274184 | note | FREQUENCY: Prior to commencing paving
d36fc604-c43d-5dd7-ae40-8b1d882518d8 | note | – – – – – – – – –
6d2e1640-117d-5a10-9a93-53c9f30d2856 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
de9b145d-586e-5a08-ba8a-9e4cbef5c6ef | note | – – – – – – – – –
db5103b9-bc08-5646-a6dc-179a80b01e67 | note | REFERENCE DOCUMENTS: 407.19 AS2150 11
68adcd77-2034-5dfc-802e-39cc3c4e9864 | note | – – – – – – – – –
56bddd14-0878-5c0e-a3e3-8966af987c13 | note | INSPECTION/TEST METHOD: Visual Inspection
50fbddc7-229a-5ddc-ad30-abdda3441fce | note | – – – – – – – – –
e5c2d584-22b0-5a90-8e01-081461d30043 | note | RECORD OF CONFORMITY: Spray area
5a205450-7958-5da1-8b39-51f74af76b06 | note | – – – – – – – – –
82b31999-a536-5244-85a6-a1d454c41eb0 | note | WP
a8e1377a-e458-5bf8-ae38-73de82a7b2c1 | note | – – – – – – – – –
9b9c3b3a-c4be-52fd-b7c5-cec78d641f5d | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
ea573536-70b7-5124-abd9-d735e8a85846 | note | – – – – – – – – –
298cf66b-0c9c-548c-9a6d-641bf32dd98b | textbox | DATE:
9dd25f8a-5d4e-4362-8b1d-2f617a528813 | checkpoint | 2.2 Commencement of Placing
65f1bc27-653a-5a11-afd4-6d43145d9897 | note | FREQUENCY: Prior to commencing Paving
a20b6633-ab7c-54a4-be3a-63706e996cac | note | – – – – – – – – –
bccb5763-6aac-5a81-ab68-8268d25bacdc | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
a03fc1ee-e2e7-54af-b33a-b2abb135ba78 | note | – – – – – – – – –
2387c346-9e41-569a-89e5-346623a10865 | note | REFERENCE DOCUMENTS: 407.23
9e960e7c-0131-5ab1-bb5d-0126f7fb3e07 | note | – – – – – – – – –
d667a85b-110a-5b55-854b-beb4f219e7cd | note | INSPECTION/TEST METHOD: Visual Inspection
4b6f88d3-eb31-5b29-82fd-2120a27ecf86 | note | – – – – – – – – –
d7546f4c-a81c-5766-a525-a73084cd7e0c | note | RECORD OF CONFORMITY: ITP Signed
2678e0f1-8f8c-5e7c-9f0b-cb3a07a479f7 | note | – – – – – – – – –
0db07a2f-798a-57f0-8a18-d6b5bce76e9f | note | HP
5e9223ab-39bf-5783-a769-bd7f3a4e68aa | note | – – – – – – – – –
4e8dc327-f6a4-5319-b861-5bee74fad9cb | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor/Superintendent
2586fcf8-8145-56a1-8d77-045d9170fd8e | note | – – – – – – – – –
073e5d27-d89c-5043-b6a8-3642fa469dcf | textbox | DATE:
e1d86773-fe7a-4ff6-afff-bdda5562e634 | signoff | AUTHORITY HOLDPOINT
5baabd88-be83-4e98-a1f8-3442610382bc | checkpoint | 2.3 Mix Design Confirmation
fd7af045-99ec-5737-b795-bd1f0d04b956 | note | FREQUENCY: Each lot
91179099-f637-55e8-a8ec-568171c1756c | note | – – – – – – – – –
85035d48-7e9f-562e-8e66-b8c63a77ed0f | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
1fa396a7-ecbc-5127-9453-016499dce3c6 | note | – – – – – – – – –
69a30284-dc5c-5fd1-ba92-dd5856575e7c | note | REFERENCE DOCUMENTS: 407.2
04daf13d-485c-5322-ab24-be24b7bc93ac | note | – – – – – – – – –
f86ef40d-4c9a-532b-a1c7-53eefe652ad2 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
67bca5de-9a2f-5675-99e9-15e655515810 | note | – – – – – – – – –
c8905db8-7815-5bd5-b674-1a7afc540816 | note | RECORD OF CONFORMITY: Delivery docket Completed ITP
de922346-4aea-5955-9d98-8878443844e7 | note | – – – – – – – – –
c707f8d0-5ed6-5055-8638-a5b88c36c683 | note | HP*
c4086582-bf4b-5162-b2bb-047badda5086 | note | – – – – – – – – –
3f144308-12e1-58a2-b25c-5691530641e6 | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
1dcd2450-f7c9-5d84-b9ce-222dbe3f23a1 | note | – – – – – – – – –
9b6c5379-5ae6-5792-9766-dd2cf33df0bf | textbox | DATE:
449ba649-103d-45be-bc06-2e2e48262dac | checkpoint | 2.4 Delivery of Mix
a76fbd85-4336-5d05-8ae9-7de53cb6dce2 | note | FREQUENCY: Each load
8402f59e-958d-5e35-b735-58e2af869839 | note | – – – – – – – – –
e661abdd-d807-5bc3-956f-a525273ee73f | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
3f0ab1ee-5b0a-50c6-9c6b-7f07eac33d26 | note | – – – – – – – – –
d7f8ceab-00be-5c3e-87e2-c47001db7751 | note | REFERENCE DOCUMENTS: 407.2
2ab12b0c-a707-5ad5-ae3c-f824c302e822 | note | – – – – – – – – –
286b16ca-8522-5627-9e49-12094ecdf634 | note | INSPECTION/TEST METHOD: Visual Inspection
141812a0-5ef4-5424-8b4c-7ce87c7a4fc0 | note | – – – – – – – – –
92ee6bf7-832f-5d97-a686-a226d8e88f8a | note | RECORD OF CONFORMITY: Delivery Docket
4a6e530f-7f23-5b71-96f5-90a79e157d92 | note | – – – – – – – – –
f4bead12-5447-536b-b816-3689a5ba2ebd | note | WP
b0455b72-d37e-517a-ba64-f4ea7fce1a18 | note | – – – – – – – – –
ccf58952-743e-558d-a0c7-a57ee4832573 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
8f676865-abde-57aa-b3dc-03821098abf9 | note | – – – – – – – – –
7a8c63a2-7899-5531-931d-78f84a07c1ad | textbox | DATE:
3c64a6f1-ded2-4e62-9836-fb4927d4103c | checkpoint | 2.5 Traceability
a19a4c4b-1411-5a20-b0d9-a68844fa9ffd | note | FREQUENCY: Each lot
cb17a462-d541-55f8-ab29-f982db6536ae | note | – – – – – – – – –
5e8b19e4-3b86-52ba-9546-2f6922f04e62 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
7ef4b680-c36e-5d45-96d2-f6e77a007462 | note | – – – – – – – – –
ad3115b1-744f-5d2e-9a94-dec142d4800c | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
9aade8e5-a1f6-58b2-884d-2f37b4945b7e | note | – – – – – – – – –
3b1a1fc9-db9e-59df-8236-ca42929b3dcb | note | INSPECTION/TEST METHOD: Verify
25e202a0-7387-512b-80bf-fc9eb4223493 | note | – – – – – – – – –
041e5f4b-f702-585a-905a-cf48eb8c2b3b | note | RECORD OF CONFORMITY: Daily Lot Record
19977598-f51b-5e5d-a69f-634a46484af1 | note | – – – – – – – – –
9e51af77-7cf1-5f7a-8ab8-31c94ea2cc87 | note | IP
b7d27be8-6e73-5586-bd6e-c2bd9df5f553 | note | – – – – – – – – –
0fa8e36e-3cc8-5112-9da6-7721c9154272 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
78487eca-40da-5bbb-bdb5-31c5e7214160 | note | – – – – – – – – –
2d8f5f05-c44c-52db-8ef9-d1a1bb8d7ae1 | textbox | DATE:
20f96b1b-c829-48fa-b746-c12b665fd91d | checkpoint | 2.6 Layer Thickness and Level Control
97f7f59f-6a4d-5367-9a8b-0e69ea234c6d | note | FREQUENCY: Regularly during paving
79a97f70-1bc7-53fc-94e7-f6973ecf4068 | note | – – – – – – – – –
c6c00e9a-a386-5be9-8882-6e319f231a83 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
a770cf9f-2846-5355-aae1-1cfed03a7637 | note | – – – – – – – – –
efa6a7ba-32fa-5a5a-ae0d-82b66748e94e | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
136eb6b1-c565-5f2f-8a55-27afbd7e1d0b | note | – – – – – – – – –
69251c3f-e810-519c-95bd-5911514c401c | note | INSPECTION/TEST METHOD: Verify
a69bbf69-5abe-5dd0-8316-69adf650ad52 | note | – – – – – – – – –
9a801ce4-7f32-5ff7-a8ed-8e575b189fed | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
259e8447-3ab9-5a7c-bff6-bbbd77f7eab7 | note | – – – – – – – – –
9065d4c2-37b5-5ee1-852b-454bec580d0b | note | WP
2bb5a19c-fec4-51dc-89bb-233741ebd0b3 | note | – – – – – – – – –
56b89e5b-f42c-52ac-86ad-679bdfbeb170 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
b4490d13-d521-586a-99c5-7d4bf25f41f6 | note | – – – – – – – – –
d6d27890-876e-51e8-86ee-92735c11c816 | textbox | DATE:
71b31fa0-e035-44e7-9565-ae768ee9b69b | checkpoint | 2.7 Paver Stoppages
494908b2-58af-5f92-a681-af77a098df8c | note | FREQUENCY: If paver stops
0c69ca03-1048-5643-b5c8-1dc0f1880766 | note | – – – – – – – – –
b4c7b467-2d3f-5f5f-a6a0-33c2d1dabba4 | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
865e7a77-a56a-5791-a25b-61bd8f53af82 | note | – – – – – – – – –
ff203d14-9dd6-56b0-9083-abd07c89ae2d | note | REFERENCE DOCUMENTS: 407.25 (c)
0bd86f41-73b8-582d-9e8a-93baf37b0e94 | note | – – – – – – – – –
41014689-3e49-5256-aaa9-4ecac923c52c | note | INSPECTION/TEST METHOD: Verify
58806937-89da-57d8-8e70-422661028067 | note | – – – – – – – – –
641f670c-0423-547f-8ad7-7df14d7b9fe1 | note | RECORD OF CONFORMITY: Thermometer
72a1e63a-8ec5-5050-9f8c-ea560180815f | note | – – – – – – – – –
c50f83ea-5bbd-5b0f-83f2-d8157359e6e2 | note | WP
e5e9aa48-1b3a-5a99-a1ac-8a5439f30386 | note | – – – – – – – – –
31d127fc-ca3b-52b1-8507-bcbc05a42dac | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
ae146f8f-338c-5e41-976c-57cf8c4dfae5 | note | – – – – – – – – –
97daa66a-25f6-563d-bdd3-47d6a550549f | textbox | DATE:
694ef4bc-37a7-43ff-9d31-d989775bbf63 | checkpoint | 2.8 Surface Finish of Wearing Course
cd3676a8-ff71-58cc-9e88-301f9188c7fc | note | FREQUENCY: During paving and after final roll
7621b38d-6a0a-58ff-b110-fce87cfaaf87 | note | – – – – – – – – –
4cf75668-67f0-57f8-ad04-b566062d81de | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
5e10b87a-aced-5a68-81fe-c3eb5597e48a | note | – – – – – – – – –
402f1673-4dbb-5713-af9e-f47ce9f5e8e3 | note | REFERENCE DOCUMENTS: 407.29 (a)(i)
8a6bed94-c57f-569d-847a-113c5c208b0e | note | – – – – – – – – –
2aee9d45-1b6c-58b1-a021-2c0f0b4879d6 | note | INSPECTION/TEST METHOD: Visual Inspection
986e9c51-a52b-50b2-9b5e-8037232f4e7a | note | – – – – – – – – –
8ab3bf04-2f01-5f9e-b354-abd9c03eefc7 | note | RECORD OF CONFORMITY: ITP Signed
b35c776d-cff8-589d-b0b2-b9520014103a | note | – – – – – – – – –
3df2030c-7a1b-526e-b49f-505c1f72b448 | note | WP
2baee321-1bf5-5ff7-8a3d-60049183179b | note | – – – – – – – – –
1e38606f-00b9-5bf7-930f-960d67bfaf02 | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
02514d86-4041-5586-85e1-081e7c9fb042 | note | – – – – – – – – –
2f22df72-1867-5a48-82c2-ff090bfb8d49 | textbox | DATE:
6be462e0-6137-451e-8204-1246b38db76f | checkpoint | 2.9 Kerb and Channel
bf0b7742-4c6d-59ea-ae5c-1686dfc509f7 | note | FREQUENCY: During paving and after final roll
11d6df9f-8945-5327-88b6-5677f7ddf3c8 | note | – – – – – – – – –
194a3369-b152-59ba-a5f5-268c43c61e80 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
f6bdc3e9-5f32-5d0e-a0a9-eb7ff0e61b4c | note | – – – – – – – – –
bda72973-7588-599d-acff-b6740f479611 | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
da78cf9b-a09d-5a11-90f6-d283fa15d0ba | note | – – – – – – – – –
b1df68bb-90e4-5ced-8b1b-406853522b49 | note | INSPECTION/TEST METHOD: Visual Inspection
2a984bf2-4d07-5348-98bb-3b8e4966017e | note | – – – – – – – – –
5e5f41df-77fb-5afd-a225-2c44549e2eff | note | RECORD OF CONFORMITY: ITP Signed
5cb4b623-3fef-54b2-8d06-e5850ec8a49d | note | – – – – – – – – –
801e4824-32e7-5422-9e02-98d683c92616 | note | WP
9f677a59-a3cf-53d4-bd5a-bd6521c06f08 | note | – – – – – – – – –
2a688691-be0a-5c26-835b-7219bdf2d46c | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
f935e2a4-6a23-51f7-a64d-01a6bb8edaf4 | note | – – – – – – – – –
156c4076-c723-59b4-b98d-e395a0561a6c | textbox | DATE:
3c42e7b0-a01a-4e24-b258-a8b68d7c9929 | checkpoint | 2.10 Alignment of layers not placed against concrete edge
43305dd0-bec1-5046-af6c-fab0b0385ff2 | note | FREQUENCY: During paving and at completion of work
cb9a9201-043e-50b8-8c5f-f3b846699b55 | note | – – – – – – – – –
9efd9ee0-8f8f-5c57-acf0-f916c0f2f3c6 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
525abc7d-c006-532d-8a3a-3b595a0fdb5e | note | • The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
e0011062-7d60-5429-af02-62dce8afae40 | note | – – – – – – – – –
fb1b4fce-8edc-5071-8fee-b9a194ffbed1 | note | REFERENCE DOCUMENTS: 407.29 (a)(iv) Drawings
5a71bd58-b3db-5ce5-afac-dfb16b93e089 | note | – – – – – – – – –
95d89661-1502-55f9-9aee-92e82453d50d | note | INSPECTION/TEST METHOD: Visual Inspection
b4b74c12-54b9-5a35-8070-42c64db1d144 | note | – – – – – – – – –
7be3e612-17a2-5f18-b646-0e260792aef3 | note | RECORD OF CONFORMITY: ITP Signed
d2775ff1-f662-5590-8bbf-0156177db5b5 | note | – – – – – – – – –
faeb2050-4dbb-5c44-8568-a02001f54e4c | note | IP
a59566cf-1d91-5542-8b38-2bba8e7f64d6 | note | – – – – – – – – –
a0b92fe0-aa46-5321-bd65-0896fe7f9a03 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
73dae97d-b095-5975-a740-2b978631286d | note | – – – – – – – – –
dfba9c8e-d3aa-54d9-bf4f-f1205a1cdec3 | textbox | DATE:
f55dd3a5-9eb3-43b6-8b80-a28ad37bfada | checkpoint | 2.11 Width of layers not placed against concrete edge
ec85dce4-497d-5b2f-aa30-18e113d4b152 | note | FREQUENCY: During paving and at completion of work
c5b0387f-39e3-5233-adbf-26fb92befe50 | note | – – – – – – – – –
3b7834c4-7d61-543b-849a-c1aaacd57b1b | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
59aee81e-4cc6-55a4-b693-ab445b07a7e7 | note | • The average width over any 300m shall not be less than the design or specified width
1479b665-88c7-5bda-a024-e8afda501c94 | note | – – – – – – – – –
df2d31fd-7907-5fac-895e-4d9a2e688fde | note | REFERENCE DOCUMENTS: 407.29 (a)(v)
7d783ebe-21fc-58fe-9856-2d44b1fc5557 | note | – – – – – – – – –
ce376bdc-5305-5247-8bfd-5082f6213248 | note | INSPECTION/TEST METHOD: Visual Inspection
8b5fd471-89c4-52e1-943d-9f4a39dc6848 | note | – – – – – – – – –
654fd791-e6d9-5ece-9e52-bf2ded60709f | note | RECORD OF CONFORMITY: ITP Signed
af6494c4-abca-5844-b043-8d3e4532bddb | note | – – – – – – – – –
607e3443-fc6d-545c-9a63-93858992188f | note | IP
2bb1788d-d92b-595e-97b5-37f01b5b0db9 | note | – – – – – – – – –
629ffc90-87f1-5ce5-b5d0-f117a8606f2b | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
3d6348d8-fa28-5217-903a-efb480c75d67 | note | – – – – – – – – –
d78a8999-4d56-5f63-a069-ca0bd9ee0603 | textbox | DATE:
5346b16d-7bd5-4fb8-82bc-d2c6b9b1e210 | section | 3 - Testing
67c30d46-5f0f-4709-bb28-6f25ef31e137 | checkpoint | 3.1 Compaction
d1a51cfc-1cf5-51dc-ba56-69b0e454fc70 | note | FREQUENCY: Per Lot
359bebae-6a61-5169-89b7-af5920136a08 | note | – – – – – – – – –
ca592126-1ecf-5cc7-8155-1f6eb729ddc0 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
9a60115d-75cb-5b3f-b4e4-705f6bdd3f62 | note | • 95.0% or greater Accept lot
fa563e6a-56f3-5948-9feb-6bbff8640478 | note | • 93.0% to 94.9% Lot may be accepted at reduced rate
437a46d8-e922-51d5-83b7-a18786429b1e | note | ○ For layers ≥50mm, if characteristic thickness is:
f2794590-0cfa-5e6f-850f-c4fc3501ef67 | note | • 96.0% or greater Accept lot
7df25563-14c2-5d76-abce-a449869ab7c8 | note | • 94.0% to 95.9% Lot may be accepted at reduced rate
137e8557-d78e-5ba4-88a9-655356a4cdab | note | – – – – – – – – –
e9bb6fe6-872e-514a-be5f-9ffd21cf141c | note | REFERENCE DOCUMENTS: 407.27
adf2ac00-d94c-535a-b5e8-d22d303e484e | note | – – – – – – – – –
64b6296e-5459-5c06-b559-845885e38e9f | note | INSPECTION/TEST METHOD: Verify
248cdf97-21c5-58ab-a7e6-dcca50f395b7 | note | – – – – – – – – –
5ea38709-c5e0-51c3-959b-5aca59ebdbb0 | note | RECORD OF CONFORMITY: Test Report
9a98ca27-f34a-5153-92a4-deee23f28881 | note | – – – – – – – – –
dfea7ad2-5c16-5fec-abcf-2d0ce5413468 | note | TP
c3b39cc9-b812-51be-b962-122b65453304 | note | – – – – – – – – –
96683c05-ca27-5159-9503-dc46f7c137f1 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
beb60c95-5147-50fe-846a-1044217881c2 | note | – – – – – – – – –
9c3dc098-caf2-5846-9f5b-451edaa217bd | textbox | DATE:
9c6ed09d-2b63-4af3-a83b-2e6e8a55e239 | checkpoint | 3.2 Level Conformance
0b8cf358-f2a9-5063-9b47-a14599c94e91 | note | FREQUENCY: Per 4,000m2 at completion of work
5cb8c38d-1eec-511b-998b-7a2df5a834cd | note | – – – – – – – – –
46f41ced-e20f-5855-8ec6-3a818a5f853c | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm (Scale B)
092b6730-5a98-52e6-88c5-97195b0a6b20 | note | – – – – – – – – –
771cb977-57d8-5f1e-b64b-bb042c7a71a9 | note | REFERENCE DOCUMENTS: Table 407.293
1eba613a-b02a-5d76-b5f7-bdc9ff7d33f9 | note | – – – – – – – – –
69f38230-b023-5305-9c0b-c49a1dd6d082 | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
5d7d8e3c-f050-5f8b-9e32-f11ea3492930 | note | – – – – – – – – –
3079048b-18c8-52e5-9a03-02f892de907e | note | RECORD OF CONFORMITY: Survey Conformance
bac63882-55d8-5407-b7b8-8c701828540f | note | – – – – – – – – –
7875cda6-473d-5b3a-b650-2b1c0098b095 | note | SCP
c1756423-8f91-50b0-9a0d-6d10e7e8b41d | note | – – – – – – – – –
a376802c-aed1-59fc-9479-1e073f92bde0 | note | RESPONSIBILITY: Site Engineer/Surveyor
7e81088e-5afb-5f39-8be7-fe0b703cf1b9 | note | – – – – – – – – –
520f0f32-87b6-51ff-89ee-6fa229df2e50 | textbox | DATE:
59d04351-aba1-4952-b114-893e8b757389 | checkpoint | Final Inspection
cbe02691-8a19-593c-ba7b-0de6cafc924d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c4e68cf9-b4da-5371-921e-2cd056ed0168 | textbox | Print Name:
10d75cbb-e853-57d9-a965-b187f83835e7 | textbox | Position:
2640c3c9-e074-5f9c-a28d-9da642bd519d | textbox | Date:
defe9a03-a083-4eb0-99ac-19e7b8b7b362 | checklist | FHC-ITP-013 - General Concrete Paving | itp | FHC-ITP-013 - General Concrete Paving
9e846911-8be0-4e4d-a204-0db5f8ca3601 | section | 1 - Preliminary Works
d878fd98-5144-4150-a27b-99e29b6f71ed | checkpoint | 1.1 Check for correct documentation
f9465d91-c7fe-5879-8171-f9e10d2cef34 | note | FREQUENCY: Prior to commencing any activity
8c120c3a-7a8b-5daf-9910-7f4fb7998726 | note | – – – – – – – – –
a47e9efd-1bcd-53cf-96cc-9e006d8b4db6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
7ddff2e2-0570-5b43-a53e-3a7190901fdc | note | – using the correct and complete set of drawings
c3b72808-b81c-5101-9eaa-c499eb7c408d | note | – all drawings are the latest revision
2c8e0759-5e65-5862-aeff-a2c42f509ab7 | note | – – – – – – – – –
f52d5bc6-68db-578b-8c69-06b3f79585d8 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
ec09f54d-74e1-52ed-b380-7e7fb7f74063 | note | – – – – – – – – –
f9b21664-d462-517a-ae03-b9d0872ba2ce | note | INSPECTION/TEST METHOD: Visual inspection
76b7746d-d146-5c82-9a51-635228b1e299 | note | – – – – – – – – –
8e3092de-aaf8-51dd-8bc0-87fd5138c2a5 | note | RECORD OF CONFORMITY: ITP Signed
4f6ac618-4525-5c45-9caa-56337c1eadca | note | – – – – – – – – –
2be46a5b-45dd-5325-8c2d-006f9df0aec1 | note | HP*
0d423ee5-379c-5f63-ab46-7d7029245f71 | note | – – – – – – – – –
05f3f3ba-10e8-5d43-a8b1-49350f26e3ed | note | RESPONSIBILITY: Site Engineer/Site Foreman
b37d7a61-9a17-5791-81d1-d8eac275a89f | note | – – – – – – – – –
9417ee15-033d-5eb2-858d-91b5bbc4d989 | textbox | DATE:
6185c4d4-8339-4496-85f1-92f2cf9a9c2b | checkpoint | 1.2 Implementation of all measures and controls
d33cd96a-7246-5da6-bb60-c2f394a5b0ef | note | FREQUENCY: Prior to commencing any activity
75a0f610-8c52-5a67-9bd0-54c7fa33952d | note | – – – – – – – – –
3c3b1f46-7fb8-55bc-b0cb-08e510045138 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
be6f6e37-ddb4-5912-8dd6-9ec020afde03 | note | – – – – – – – – –
7803d06e-37f9-5ae8-86b7-a31258b2dcea | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
f4830601-a45e-5718-8892-f1c3266f8cc9 | note | – – – – – – – – –
c54fa029-1284-5bc7-97a0-f4f37ccc2caf | note | INSPECTION/TEST METHOD: Visual Inspection
b6a58bc0-e105-5da1-b21e-dcd0df003f13 | note | – – – – – – – – –
1d28ced5-5844-545d-8dc1-e2d2327a856b | note | RECORD OF CONFORMITY: ITP Signed
d97b6fba-8c72-52fa-982a-459988beca9e | note | – – – – – – – – –
257d400a-cd92-5387-9fa5-f3e027313793 | note | HP*
dc4c18c7-ee52-5be8-a97f-b8c0dc9183fa | note | – – – – – – – – –
86a8232f-64d3-55cd-89f6-c3cbca5b07e1 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
61f9f2df-6747-517e-9d5d-3ac86dfb295a | note | – – – – – – – – –
09040e1e-4457-53f3-b887-50f5ca47d15a | textbox | DATE:
cb6e482b-e3e7-4cef-a86e-673fb9342998 | checkpoint | 1.3 Submission & Approval of Concrete Mix Design
4a93afb2-12d8-5c51-b575-7d4795cd6fe0 | note | FREQUENCY: Prior to first concrete pour
b33cd353-83d0-5a6b-b533-eab1dca89f6e | note | – – – – – – – – –
df4a43b9-470e-573d-ada8-cbd8670ec8c4 | note | ACCEPTANCE CRITERIA: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
f86e7549-9383-5d82-938f-670137bba852 | note | – – – – – – – – –
1d1b843c-1947-56fe-b681-a7153d77060a | note | REFERENCE DOCUMENTS: 610.07(b)
d765be0e-f42e-5196-a365-bcc7d4179d4f | note | – – – – – – – – –
d27f67d5-47cc-539a-a425-806f49942fa3 | note | INSPECTION/TEST METHOD: Verify
3f9a227b-ce38-5074-bfbe-554260b152bc | note | – – – – – – – – –
333141f2-473a-5168-8a8a-d7adc0c3f437 | note | RECORD OF CONFORMITY: ITP Signed, Mix design approval
b2fb3ffd-1ff1-5296-9197-d9d186b083c5 | note | – – – – – – – – –
35f7bfb8-560c-5876-a299-92d9a50fc2fe | note | HP
e35c5873-1034-5536-be9b-24cee5dc7f63 | note | – – – – – – – – –
2c6f751c-d20e-5fad-b60b-1cd68b3da53b | note | RESPONSIBILITY: Site Engineer/ Superintendent
05c30034-c81d-55b5-b57c-37e80a10a9c9 | note | – – – – – – – – –
213b6330-529f-5d26-a8e3-81b48c2453b8 | textbox | DATE:
6d246991-ed32-4b0e-a616-778220d58993 | signoff | AUTHORITY HOLDPOINT
09c31f33-204f-4db2-b1b0-c339042ee986 | section | 2 - Construction Works
dadb3ce5-80de-433d-8bd7-e713c39bb26f | checkpoint | 2.1 Setting Out
e1e8c0d8-35e6-5711-a6fe-2c513f4e40fb | note | FREQUENCY: Prior to start
1923ce8f-1ec9-5cca-b154-eecf3980c035 | note | – – – – – – – – –
27f89b0d-1026-504a-bf62-d1b9056e78b6 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
09a515bb-6244-515e-889b-e305e09e7db7 | note | – – – – – – – – –
5141e9de-e323-5486-9b6f-6583eba1f35f | note | REFERENCE DOCUMENTS: 703.17
c4015ce1-0c81-5b31-a1e5-6e01d401c565 | note | – – – – – – – – –
b867b445-90f4-534d-873b-7d74e4013b9c | note | INSPECTION/TEST METHOD: Verify
5d169884-26d8-57ac-a012-6e8818da038c | note | – – – – – – – – –
272c4af3-d6be-5939-a088-3f46eb38292e | note | RECORD OF CONFORMITY: This ITP Signed
c4572c8f-19db-5a8f-b02b-da45b1948906 | note | – – – – – – – – –
eaebad6d-fd08-565f-8362-a1de2e00be40 | note | HP
0294af30-34b9-5a59-a4a7-bca988b8897f | note | – – – – – – – – –
48787b9b-fb33-55f3-a746-568386d3886e | note | RESPONSIBILITY: Site Engineer/Superintendent
10ea6c27-b22b-537c-a384-7aff74a266bf | note | – – – – – – – – –
ccb548c2-d919-56e1-8162-6dd6bac7b964 | textbox | DATE:
43446162-4eff-4443-999d-2e334b0ca273 | signoff | AUTHORITY HOLDPOINT
108576b2-786b-4e21-bc82-0b12034b5a90 | checkpoint | 2.2 Excavation Permit
a4285fd3-fbed-50fb-8672-af8ebe3ca632 | note | FREQUENCY: Each lot
960e8518-4d92-560f-bd98-ea20b88805fb | note | – – – – – – – – –
59063ef6-ba46-543f-96b2-649492acf74a | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
63f69ab5-882c-51e2-b37a-943e3747d995 | note | – – – – – – – – –
e6fa166a-9443-5c78-b755-d978ed064ec8 | note | REFERENCE DOCUMENTS: Excavation permit
c5f86c2d-678d-5740-9151-27a5ba45bce7 | note | – – – – – – – – –
e619ddd2-f0dd-553c-aeb8-bb8d5cd2fd2e | note | INSPECTION/TEST METHOD: Verify
7c2d2220-2e3a-5d38-bbde-f444f6b29989 | note | – – – – – – – – –
8f3c7dfa-a853-59e4-9199-99d42ef46e00 | note | RECORD OF CONFORMITY: ITP Signed
54527bdb-4db2-5442-9344-47ecb7f7a67d | note | – – – – – – – – –
fedee9dd-b275-57f6-9ee9-0273d4b73d62 | note | HP*
5bfdec54-9f20-539d-aa4d-f6d1eec9471f | note | – – – – – – – – –
90b55767-b24e-5aef-a3fa-63f8d3528498 | note | RESPONSIBILITY: Site Engineer
9520c8a4-4f99-5d60-8ec8-373b25747ce3 | note | – – – – – – – – –
731606c9-c937-52f7-b2b9-32e1a83f76b1 | textbox | DATE:
c033f434-b7f2-4108-854c-7de796a25093 | checkpoint | 2.3 Excavation
b2ccd92f-3485-5b72-ab0b-7aaf23edd21f | note | FREQUENCY: Each Lot
a67dcfa8-cc86-585d-aa95-b056fb050834 | note | – – – – – – – – –
77bb58a5-6c7f-53a6-a260-3779ce0bcc4d | note | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
a4f04dc4-b72e-5324-becf-06b8e3fcc4d6 | note | – – – – – – – – –
616f272c-9c98-5b12-88e2-5d300dc81d62 | note | REFERENCE DOCUMENTS: 703.2
2b2cd1b0-24a7-5eb0-90fc-a34a9bcc4dbb | note | – – – – – – – – –
4846032e-c0e3-57f8-b572-fb855453cf14 | note | INSPECTION/TEST METHOD: Verify
f404ab72-52e9-5544-bd57-e9f314f0b4a7 | note | – – – – – – – – –
72075a6e-4805-55c8-83b8-c541d0e0d550 | note | RECORD OF CONFORMITY: ITP Signed
70d71475-23b4-5f72-8fb3-8da1391992bd | note | – – – – – – – – –
fd089b23-dddf-5b87-b998-af441e5c62c5 | note | IP
5281df50-e883-5f86-b559-a9cf5aa8f8bf | note | – – – – – – – – –
4c166e20-61f1-5a6d-b609-c6c0801b0432 | note | RESPONSIBILITY: Site Engineer
a39b80f7-370d-5f94-9edb-76b352c81291 | note | – – – – – – – – –
d918dc3f-3398-55a8-b44a-b47dfd2639a8 | textbox | DATE:
b027dfa4-c7cf-428a-a7d0-92ed44a1bebc | checkpoint | 2.4 Bedding
455cebaf-5dfd-5780-930f-cf50160ca2c3 | note | FREQUENCY: Each Lot
4d47c3d1-594e-589f-a210-e72ff35cb684 | note | – – – – – – – – –
409ff610-0395-57d8-a2cd-90b76da0f681 | note | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
13354b6b-e6ec-5afc-abb3-a4b267cacb9d | note | – 100mm thick layer of 20mm Class 3 crushed rock bedding for median infill
efaa2453-51f7-5cac-914b-1d71e0b01094 | note | – 150mm thick layer of 20mm Class 4 crushed rock bedding for footpath/pram crossing
4635e6ee-56ab-55f6-ac53-dffce36e670f | note | – Bedding trimmed, moistened, and compacted as per Section 304
2d67a3e4-c7cf-5edc-abc0-85c58686ba92 | note | – – – – – – – – –
0c9c211b-fcfc-5515-a625-d8f1ac64c53f | note | REFERENCE DOCUMENTS: 703.21 Drawings
bbf7eb12-1440-5e1d-88d4-768f4161e7ca | note | – – – – – – – – –
95087d94-0870-5faa-bb4d-cf203dd4d27e | note | INSPECTION/TEST METHOD: Visual Inspection
9d3a0ed5-4d70-5607-942c-b44a0b12fa17 | note | – – – – – – – – –
b9c020d6-e6a0-5da8-99f9-3d1bc2d35614 | note | RECORD OF CONFORMITY: ITP Signed
a51b79e5-e9eb-59d1-935e-afd73daca807 | note | – – – – – – – – –
225cea7f-a111-5131-9240-b4083a2d5abb | note | IP
8926eed0-7c1c-5d7e-a58d-696b198f0432 | note | – – – – – – – – –
d3b2f567-53f6-501c-b6ac-1ccf09a3d33b | note | RESPONSIBILITY: Site Foreman
99d5026f-b9cd-5138-bd26-e7ff08af7aea | note | – – – – – – – – –
7e68b873-1927-5330-80cd-38fbd30691bf | textbox | DATE:
388d1e1c-296b-41f7-a0a2-abe490c66717 | checkpoint | 2.5 Formwork
dc3f2cd4-83a0-5492-89a9-12355463ac59 | note | FREQUENCY: Each Lot
b991266b-62af-5d9e-99ed-d6ba87c90278 | note | – – – – – – – – –
c233a52a-752a-593b-9c56-22a09aee3c2d | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
bb499c57-4f11-5dc9-b1a9-6dc3d36a26f6 | note | – – – – – – – – –
8f88e360-34c9-5418-8935-0fea071c1871 | note | REFERENCE DOCUMENTS: 703.12 AS 3610
40d6a5da-a446-5036-ad99-75d3d0b86c94 | note | – – – – – – – – –
236c8474-18b7-5230-adb9-4eddf63a4a95 | note | INSPECTION/TEST METHOD: Verify
fd93e375-b5c9-5206-be20-58b0c186778e | note | – – – – – – – – –
81a75c89-9253-553a-b2f1-ac5b6e1f3677 | note | RECORD OF CONFORMITY: ITP Signed
82238152-c7da-5f48-8895-773603be13b8 | note | – – – – – – – – –
dd1b55de-1bef-50a6-b713-32a62fd1bf20 | note | IP
8334259d-30d2-5b9e-8bd4-1eec06d3a0b4 | note | – – – – – – – – –
7bec3e1d-deac-54ce-af13-f68f6dac3f69 | note | RESPONSIBILITY: Site Engineer
43c8ed23-cfe1-5f97-9f2d-ca931da4a413 | note | – – – – – – – – –
f9ee172f-2ec4-5789-ada8-1415cea7bb75 | textbox | DATE:
05c66b26-0456-4746-9989-eb4279219b31 | checkpoint | 2.6 Reinforcement
72386e21-7524-50ff-9261-0cadcd928c0a | note | FREQUENCY: Each Lot
c52ec205-7c92-53fb-8503-d6aebc883a6d | note | – – – – – – – – –
612bdb18-3dc2-5251-9a87-11985f2a31bc | note | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL82 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
9f3b8dff-73cb-5ce3-ac45-061c5801f0f0 | note | • Reinforcement must comply with the requirements of AS/NZS 4671.
60a85ab4-2c88-553a-9ebe-65c55091871b | note | – – – – – – – – –
ada26224-a924-5efd-b580-b490079d8dca | note | REFERENCE DOCUMENTS: 703.13
fe0293db-6328-58b1-9839-a4fffcf7acba | note | – – – – – – – – –
8a9dafd2-7360-5740-b779-9846d87f3b8a | note | INSPECTION/TEST METHOD: Verify
ba7840ba-8175-5f98-abf1-9d49146a5972 | note | – – – – – – – – –
2bd4c4c0-b09f-5cdf-adb2-742c3253cbe0 | note | RECORD OF CONFORMITY: ITP Signed
749b487e-b0dc-573a-bdc6-07089f57f8c4 | note | – – – – – – – – –
5682efd8-c7a5-5820-afe9-b2ba688f56cf | note | IP
4a36a6e0-adde-5a4a-b7ab-9e0d8d75eb77 | note | – – – – – – – – –
4fd7d99b-9c1c-5e0d-861a-6b7864675b6e | note | RESPONSIBILITY: Site Engineer
7cd1b05e-9350-52ce-82fe-c2cff25e0e8c | note | – – – – – – – – –
df098b5a-876e-545f-b2d0-5b593e277f25 | textbox | DATE:
739001ab-5a04-4746-a2d7-86c7e1b25871 | checkpoint | 2.7 Concrete Placement
47332797-007e-5fe8-ad7a-5c5eec9b9d10 | note | FREQUENCY: Each Lot
ad0e14af-5c6b-5985-a0f5-967971555d49 | note | – – – – – – – – –
526c9f66-556a-56cb-a8b3-022c04bd1efe | note | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
fa14502a-cff3-533e-b51a-d706d33d2c08 | note | • Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
6afff605-0238-551e-82e2-7a8adac36b04 | note | – – – – – – – – –
94f10675-7a46-5267-844f-609a8228d175 | note | REFERENCE DOCUMENTS: 703.05(a) 703.08
90457cbd-9af7-509a-af43-76d387880aba | note | – – – – – – – – –
b7efe132-8e6e-5914-9c7d-cc9ac0284348 | note | INSPECTION/TEST METHOD: Visual Inspection
69204d14-e138-5c4d-bbbd-a1c0ac8202d2 | note | – – – – – – – – –
e6787b46-4e1c-504f-8c55-8cf01dd172d5 | note | RECORD OF CONFORMITY: ITP Signed
30d65064-a970-51f8-87c7-7febce1a65a1 | note | – – – – – – – – –
2c8cd388-a1dc-58dc-ac35-77604bdb5edd | note | IP
ab2e663e-2ef4-5405-9373-7ece17d74351 | note | – – – – – – – – –
6f75a395-c563-53be-a605-c17e0d62c91e | note | RESPONSIBILITY: Site Engineer/ Site Foreman
fac4d0d7-5786-50c2-9a4f-4b65eda8b709 | note | – – – – – – – – –
72723e34-156a-598a-b3b5-9d5d2177c684 | textbox | DATE:
7e2b2060-8db9-43ad-93d5-69dd3b1f6fff | checkpoint | 2.8 Surface Finish
02b76ece-2435-57aa-8b47-740b4c8a34ca | note | FREQUENCY: Each Lot
065baa34-94b9-5d29-8150-5ecf179dae43 | note | – – – – – – – – –
1ccb507b-cddf-5114-963d-7785b98b39fd | note | ACCEPTANCE CRITERIA: Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
45f87d91-8ac0-5b55-88a6-243f77f5077c | note | • Footpaths and other Surfacing shall be compelted with a wooden float.
c9599a48-f5a5-5306-8ecb-0af05939e7ca | note | – – – – – – – – –
88a353c2-7c30-5be1-8be1-c607fd930e43 | note | REFERENCE DOCUMENTS: 703.25
e44e885f-433b-51b0-872b-e7c620f595f2 | note | – – – – – – – – –
595a2c73-e5e3-5bba-946d-88147a502ccd | note | INSPECTION/TEST METHOD: Visual Inspection
83da6897-1e26-57f9-979b-e5a62f77331c | note | – – – – – – – – –
de8aca8c-cd5d-5b7c-8db0-65cd6dfcd902 | note | RECORD OF CONFORMITY: This ITP Signed
ce68f461-77dc-5533-9b4f-ecce2994d0ba | note | – – – – – – – – –
b49fc14e-33e8-5d3c-83fe-cb67b3304ecb | note | IP
30491ae1-eaaf-5845-8c40-ebfd752d4680 | note | – – – – – – – – –
d0f24164-7b00-52d3-90d8-a4e2c114da1b | note | RESPONSIBILITY: Fulton Hogan Engineer
f401a951-393c-599e-8e14-1199adbd7933 | note | – – – – – – – – –
883d59b6-579d-5e8a-a120-1dbf6d2de530 | textbox | DATE:
a5a4e8d0-efdb-43c8-9b03-5a583a2ba717 | checkpoint | 2.9 Pram Crossings
f0495431-c852-5ad7-bd07-9a0729052278 | note | FREQUENCY: Each Lot
dbdcfc95-a1a1-534b-9e45-81956fbf6ae8 | note | – – – – – – – – –
0d712616-97de-54ad-841b-af2e11f61523 | note | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
e3afcf54-ffed-51f7-a588-7f6f5521f784 | note | – For pram crossings within concrete kerb refer to Figure 24A of AS 1428.1
6a4a6613-5dd1-52fc-8553-48b89d98f698 | note | – – – – – – – – –
e87d94bb-0413-5e24-9c2d-6600b1b513b4 | note | REFERENCE DOCUMENTS: Figure 24A AS1428.1 Design Drawings
5e2dc0a0-ad67-5043-a71e-7f2f0af1195b | note | – – – – – – – – –
ed9a4599-e1ca-5f4b-87a2-d91bbb1d9c5e | note | INSPECTION/TEST METHOD: Verify
45d561f6-8beb-59d4-beb5-4d1cc16cf224 | note | – – – – – – – – –
0dbbb626-c1a7-521c-8a81-873aa4f0ed4b | note | RECORD OF CONFORMITY: This ITP Signed
ea0bd63a-1d09-597a-8fc7-281f75c97789 | note | – – – – – – – – –
42b0b50b-891a-5e42-a735-30a23a8fd38a | note | IP
c08728b4-7a82-5004-bbe4-73807ebd0263 | note | – – – – – – – – –
f7091eb4-bc94-58ea-80f1-0ec1b8b26c90 | note | RESPONSIBILITY: Site Engineer/Site Foreman
20987e95-6d77-5be2-963d-56d00ce6c241 | note | – – – – – – – – –
7a3fef3a-e449-597e-b9bf-4a55596462dc | textbox | DATE:
d5e16ab1-3875-40ce-a92d-b365be7d85f2 | checkpoint | 2.10 Joints
75101d7f-c399-5320-a234-c6f3168383ff | note | FREQUENCY: Each Joint
d4ce1391-cfdd-5238-9cf6-382e37a4991a | note | – – – – – – – – –
5c34e332-0968-59f5-b714-3bb703d0c651 | note | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
d2d4b631-a732-5ab4-afc5-03bdf9ad4357 | note | • Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
c3b4d530-360f-5ebd-9f6a-d841c621df13 | note | • Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
8d13a81d-a2ed-5e49-91b8-d77a2f6c09ce | note | – – – – – – – – –
58f5f0a0-79be-5184-872d-348d264d9b4d | note | REFERENCE DOCUMENTS: 703.26
b48db5e8-d403-5cc3-a82d-fdd3ad868cc8 | note | – – – – – – – – –
fbbf159c-efc7-5769-9675-997283cf1884 | note | INSPECTION/TEST METHOD: Visual Inspection
12829229-3ccb-5362-8f84-b90f909c0d46 | note | – – – – – – – – –
292c0c88-d1fe-5e91-a792-1a0c3925b457 | note | RECORD OF CONFORMITY: This ITP Signed
79fef1d3-b94a-5f93-8973-70ce99f5d877 | note | – – – – – – – – –
e734246f-ea4c-5b3d-bd7c-bebe6b6fe321 | note | IP
3d20d6dc-9fbe-51cd-aa24-3f1e9f899819 | note | – – – – – – – – –
7f652907-ca91-5c6a-af0e-9cf69f7681b3 | note | RESPONSIBILITY: Site Engineer/Site Foreman
ae2c0e45-848a-55a0-9b4d-7f769bcfffeb | note | – – – – – – – – –
fb88530c-aea2-5941-9325-9c14c1ef57f3 | textbox | DATE:
50319c98-42fc-45ef-806d-6a6612781337 | checkpoint | 2.11 Protection of concrete
8478736f-8461-5989-841a-d22a9d471dde | note | FREQUENCY: Each Lot
ce330ddb-9b62-5841-9f4d-4f3e2368a507 | note | – – – – – – – – –
0c1f9faa-b7af-5a24-90ff-6e1c0947ede7 | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
7a3bcc25-abd0-573f-ae00-06b62a280fd4 | note | • Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
b52ed690-5818-5e2d-9fdc-3b9b7e60b12b | note | – – – – – – – – –
f4a4d3b3-612d-5eca-a0de-399dcd5650ed | note | REFERENCE DOCUMENTS: 703.27
b4266191-1f7c-578a-ab5f-1d61c6c82968 | note | – – – – – – – – –
b2cf798a-ed10-55b6-9df8-b7ae18436f8f | note | INSPECTION/TEST METHOD: Verify
657c46d0-efc5-5218-9fe5-e4657b29c716 | note | – – – – – – – – –
e65762cb-a16f-5b54-9f96-3a10437c0113 | note | RECORD OF CONFORMITY: This ITP Signed
515d7b87-dec0-5f2e-b479-4590eea0f14d | note | – – – – – – – – –
54ad5bd5-727b-595b-aa4e-fdd7fa52c4ba | note | IP
eb70d6e7-9bc9-59c8-b0db-3c9bb9b7ee33 | note | – – – – – – – – –
d543698d-7e3a-5221-851f-b717f43d7b2a | note | RESPONSIBILITY: Site Foreman
18036c13-4841-5650-b9be-742d2d234906 | note | – – – – – – – – –
716919b3-c137-557c-8f18-4e12374aa61a | textbox | DATE:
0bbfcf8c-36db-4fa4-95f1-93e0334d9e67 | checkpoint | 2.12 Curing
fcbe2722-3dad-563c-b02e-927990587f22 | note | FREQUENCY: Each Lot
ceee837c-b868-5e42-8751-e29d2a5fd808 | note | – – – – – – – – –
a327da1c-a3df-5ef4-8c0c-fb096688eb88 | note | ACCEPTANCE CRITERIA: Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
e9ce3770-b424-576d-8269-bd8624ad3741 | note | • Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
9d6c64cc-9fcc-5df1-bf20-ce8f5d5bac0c | note | – – – – – – – – –
a9ae4fc9-e140-5978-a6bb-c7012347b4d5 | note | REFERENCE DOCUMENTS: 703.1
5e800bc4-3fbd-5e7d-bd50-8045d7f043b7 | note | – – – – – – – – –
f82f5012-2673-52bd-bd4c-a758dc003716 | note | INSPECTION/TEST METHOD: Verify
c6e700a6-f308-549e-8639-5c90e10bfbb8 | note | – – – – – – – – –
7d31cf24-2708-5426-88b4-54f98cfa4aa6 | note | RECORD OF CONFORMITY: This ITP Signed
df90757c-376b-5344-aa41-3e32c2a778fc | note | – – – – – – – – –
bebdb306-3995-5917-a8e3-82a32b6e0845 | note | IP
7c44ec20-17a1-5a28-bb99-31b181533ec0 | note | – – – – – – – – –
2fe3a584-6c01-5f2c-ac8d-ce379cccf2bc | note | RESPONSIBILITY: Site Engineer/Site Foreman
0fa4ac82-2e77-590a-b6cb-b1878aa0bf09 | note | – – – – – – – – –
6a772d4d-73ea-59e5-a0e3-77907954a305 | textbox | DATE:
e2d8048e-4c8a-412d-8b77-7c13482403e4 | checkpoint | 2.13 Ambient Weather
3bf375a6-d2ae-5e85-aba0-41841891ecd2 | note | FREQUENCY: Prior to commencing any activity
4aa8ddb7-2305-55ad-bc8e-8e910017c37a | note | – – – – – – – – –
6ad61c1d-53d3-52b1-a56f-6ec17c922fc1 | note | ACCEPTANCE CRITERIA: Concreting operations shall comply with the requirements of clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for limits, restrictions and treatments to be applied for concreting in hot, cold and wet weather, except that curing shall be in accordance with clause 703.10.
0a23a63f-1c4e-59b0-8d26-802a26dc34b8 | note | – – – – – – – – –
800805b9-c525-5015-8b34-496bd96f65bc | note | REFERENCE DOCUMENTS: 610.17(a), 610.17(b), 610.17(c) 610.17(d) 703.09
17fdb7d4-08fe-57cf-8d0a-0be8fc0d354f | note | – – – – – – – – –
16dc791c-bbb0-5f7f-a12a-649c110c60f2 | note | INSPECTION/TEST METHOD: Verify
b39fc870-832e-543a-b5f5-56af73b63348 | note | – – – – – – – – –
67b43e49-1bbf-574c-98e0-a794ee53c36c | note | RECORD OF CONFORMITY: This ITP Signed
c4c75d5b-10c2-5db8-ab18-4a07a8340ba5 | note | – – – – – – – – –
c47f2029-b449-5f3d-9237-2be350b2b740 | note | HP*
f6eaa30d-48ca-541f-9f08-310e8ca4b318 | note | – – – – – – – – –
ce5bf52c-07bb-54e5-8d5f-ca23664e4ad5 | note | RESPONSIBILITY: Site Engineer/Site Foreman
12eda89e-377a-5e2b-b462-be37382334a0 | note | – – – – – – – – –
924488d8-574f-5331-b326-655bece0a3eb | textbox | DATE:
4731ec50-83dc-4453-a2ee-fdf3df76ae9e | section | 3 - Completion
d1bd503a-b908-4598-9cdf-a74e41e82db3 | checkpoint | 3.1 Carry out sampling of concrete - strength and consistency
08f3917e-582d-58f2-9d4c-8a264f70a5f2 | note | FREQUENCY: Each 50m3
54a24753-3ed2-5d72-8f68-49912f65e16e | note | – – – – – – – – –
8381e9a5-2f82-5e11-b058-1d61a72458ac | note | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
8bb1c910-8a36-5054-9083-e5f3238db3f4 | note | • The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
64816770-b51b-5199-979b-0d90ac1b5b43 | note | – – – – – – – – –
3c80500d-a9ea-524d-9ad3-147ac36cbbce | note | REFERENCE DOCUMENTS: 703.11
1d13ae45-f06a-55db-aadd-4037b1d41519 | note | – – – – – – – – –
b56dc46d-6fcf-5bdf-a711-44d6b4eca8e0 | note | INSPECTION/TEST METHOD: Checklist
ac7564de-75d5-5012-be0b-9aaebe8c3dca | note | – – – – – – – – –
ffbbd65b-58e0-5a5d-bac4-c28915bd71cb | note | RECORD OF CONFORMITY: ITP Signed/Test Records
775bb1ed-4fd8-537c-b5b3-374c6b10be69 | note | – – – – – – – – –
8f44a1c5-2483-5bdf-86a0-f17003f72ed9 | note | TP
dbfd6de8-47de-567b-831a-08973f62c2e3 | note | – – – – – – – – –
539550af-2899-5d02-adee-f90f724cbf3d | note | RESPONSIBILITY: Site Engineer
e7f96ca5-84c6-5975-85b8-dc4d655dadce | note | – – – – – – – – –
1015942e-84c5-5f39-ace6-cf4888caba02 | textbox | DATE:
7e8bfeb9-b25f-439b-9a30-9a427b9430c2 | checkpoint | 3.2 Tolerances
ee1619e8-552b-5421-afae-623986b24dba | note | FREQUENCY: Each Lot
b7842679-d286-57b6-89be-7bcd3d56d261 | note | – – – – – – – – –
38a9c98f-2c34-5721-8c80-8fe03fae780d | note | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
abff156e-3827-5587-9d8f-5d222f6ce4fd | note | Section dimensions shall be constructed within the following tolerances:
493fddfd-14b7-5b8a-8666-3882b63f0351 | note | – 5mm and 15mm for width; or
c6b3f09b-ea5c-503f-a857-22458bdcc9b9 | note | – ±3mm for dimensions less than 25mm.
dd426bc6-84a4-5fbe-83ef-8e959f861f77 | note | – – – – – – – – –
5ec29441-aeaf-5ced-ae70-8911f88c73f7 | note | REFERENCE DOCUMENTS: 703.15 Drawings
7bd9a6c3-a1db-5968-8c2a-0e2bb3802fed | note | – – – – – – – – –
5ecd1e96-8aed-568b-bd04-f93803d203bd | note | INSPECTION/TEST METHOD: Visual Inspection
c6c78fed-3dd6-5333-afb8-63d3bfaaf0c8 | note | – – – – – – – – –
03437d40-d19e-5bb1-a98d-f4e9c01fa80d | note | RECORD OF CONFORMITY: This ITP Signed
1573a50a-b936-569f-996f-74b59f72b18b | note | – – – – – – – – –
48f15d92-0d05-545f-babe-03df70065b53 | note | IP
06d1f9f6-b3d7-566f-ab18-6722f3c9ccf0 | note | – – – – – – – – –
2e3661d1-53e6-5e7f-8d57-ab01e56f24e7 | note | RESPONSIBILITY: Site Engineer/Site Foreman
73b7adb5-5eea-5d71-82c6-a2f18a391548 | note | – – – – – – – – –
4b78bc34-e131-58b2-b8a4-8507a7c89bc4 | textbox | DATE:
ed1e9d38-0c96-40d7-b751-7c75508b3d75 | checkpoint | 3.3 Backfilling
b600012b-2525-59fa-8dfc-eb06cdaeb4a4 | note | FREQUENCY: Each Lot
24c221ab-4d14-587a-8464-2734afb1f8c4 | note | – – – – – – – – –
45a385e0-af60-5efb-815a-457ffb82abb7 | note | ACCEPTANCE CRITERIA: After curing, no earlier than 3 days, backfilling shall be completed as per the below:
bef26981-fb0d-5327-b21e-f853eb43abf1 | note | – Topsoil compacted in layers < 150mm
26b4cde4-f503-5452-a1aa-0a8d788d2bf4 | note | – Width ≥ 300mm behind edging to top of edging
6bd4c887-3fe6-538f-a6ac-86a6bef63352 | note | – – – – – – – – –
b08c8085-3ea4-5bf7-9373-87228be8a6bc | note | REFERENCE DOCUMENTS: 703.29
50d3ae95-76f7-5865-b09d-a25ff4bacf25 | note | – – – – – – – – –
2f80597c-264a-5acc-8135-32d4ecff64b1 | note | INSPECTION/TEST METHOD: Verify
4444b1c4-3a52-53ba-a2e2-32b26b83f8ab | note | – – – – – – – – –
7f548459-b059-5b58-8bd8-b816fa0708eb | note | RECORD OF CONFORMITY: This ITP Signed
3c847534-caba-5ef9-997d-a535fa5ac38f | note | – – – – – – – – –
6e104157-33db-53b8-9cbc-d0358e125a2c | note | IP
946002d1-ae5c-5280-af3f-e9f070ff7212 | note | – – – – – – – – –
15a88cb1-8947-5f99-bc55-2b0490ba9e77 | note | RESPONSIBILITY: Site Foreman
f28d527f-662b-5826-aa30-290d336f7380 | note | – – – – – – – – –
d3a6f061-2b9c-594f-908b-dfce52278ed6 | textbox | DATE:
9b364cba-3b23-4757-aa6f-a613a086a402 | checkpoint | Final Inspection
26281345-6146-50f1-a027-3cb5309f95fc | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4ebc265d-90ce-52ae-b04e-d28e3b1fb6ab | textbox | Print Name:
b8cef6ab-9151-58c9-8763-55ff37511f38 | textbox | Position:
b04a5ad9-9ad5-5695-abc2-43993dea7c3f | textbox | Date:
01bd7efc-71f8-4c42-8962-874a95b65d1b | checklist | FHC-ITP-014 - Subsurface Drainage Rev2 | itp | FHC-ITP-014 - Subsurface Drainage Rev2
2e0a480b-193d-4ebe-98c7-300099df0616 | section | 1 - Preliminary Works
1d19c950-725c-4cc0-9084-b02fc92d73aa | checkpoint | 1.1 Check for correct documentation
e3a874f8-3461-59ba-af29-e416b1ac3e30 | note | FREQUENCY: Prior to commencing any activity
063c4623-48c2-5bf4-865d-52d04398fef3 | note | – – – – – – – – –
d491a1ac-2cdc-55fc-a191-215c7649d976 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
03e1169e-da6a-5e2c-b020-041561d5997f | note | – using the correct and complete set of drawings
c7b6d11b-9f7a-5478-9d93-621aca039bdd | note | – all drawings are the latest revision
c0a9bffd-4f94-55a6-8a87-c58e4b9026dd | note | – – – – – – – – –
4d8546a5-083f-5665-af14-90b17765cff9 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
de01ed69-02f5-5d3c-9981-fc4d28f3eac7 | note | – – – – – – – – –
e204fa49-4e89-5d04-8c2d-4f17ccf416d4 | note | INSPECTION/TEST METHOD: Visual inspection
b5c5a22b-06b9-5f06-a4b5-fb5f3289a91b | note | – – – – – – – – –
b1c0b997-fd33-564a-b3d6-cde943a8e6ec | note | RECORD OF CONFORMITY: This ITP signed off
d282fc23-977f-5b69-b37a-dc35fdd92f57 | note | – – – – – – – – –
2f466e0c-366e-5852-80d6-b8dfe5ec2471 | note | HP*
16b9159d-094a-501e-a4b2-36caf1440db2 | note | – – – – – – – – –
d8b4e7b5-f2e5-5c13-b383-31eb6ef67337 | note | RESPONSIBILITY: Site Engineer / Site Foreman
4556fefe-dfe0-526d-9885-1530c498fb09 | note | – – – – – – – – –
a24cf8db-eb35-58c9-a777-e9c1adf6341e | textbox | DATE:
2bd9a33d-4201-484a-8ebb-cfc00972c1aa | checkpoint | 1.2 Implementation of all measures and controls
1c98acbd-63be-5344-a47b-971d0100ed1f | note | FREQUENCY: Prior to commencing any activity
da854f34-df41-5551-ac3f-b0ce1f4bff75 | note | – – – – – – – – –
ba3cbf8f-f781-5465-a719-3b3f2e3868a8 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
ab3822a3-b8dc-5275-9e5e-e81ad6bbed7b | note | – – – – – – – – –
c3909108-8ad9-5584-addd-237594e1ecbe | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
6558563c-e1eb-5506-b391-61a7ffcb9e5a | note | – – – – – – – – –
3faf18e4-fa0b-5fb8-aaf3-17b373a29291 | note | INSPECTION/TEST METHOD: Visual Inspection
2cdc1771-5b5d-5afc-9856-2ba477c27a2c | note | – – – – – – – – –
b3d7cb0a-f284-5e51-a79d-550f4b19e399 | note | RECORD OF CONFORMITY: This ITP signed off
fcac3787-0cd8-5174-a8d7-5f887900033b | note | – – – – – – – – –
935dfd0c-2dbc-5107-bf5c-abc0ee239881 | note | HP*
67432755-3201-5dc5-a02c-ceb7e0bfaa7d | note | – – – – – – – – –
3d2f758a-e23c-5231-918d-bcd1d06f41ec | note | RESPONSIBILITY: Site Engineer / Site Foreman
bb42acd3-d221-5624-9904-d8f7277d51c2 | note | – – – – – – – – –
8cf26ff5-3584-59f2-8714-3b6cc5eca970 | textbox | DATE:
a72ca572-333e-41b5-abf1-ba3fad548951 | checkpoint | 1.3 Placement of no fines concrete
4c930151-8fdd-555b-9d96-6163c6f496ee | note | FREQUENCY: Prior to works commencing
713ba0ac-4687-55bf-aa26-385c998d454e | note | – – – – – – – – –
0aafb9c6-5978-5651-bc1a-7dc3fc7717a2 | note | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete.
c71218ee-9581-5c29-b991-07fd091db827 | note | • The method of compaction shall be in accordance with the Contractor's quality procedures
360c2cd0-d143-50ed-951a-f0f8f484719b | note | – – – – – – – – –
fa0b976f-22a5-5a70-aebd-eea2ffb80df1 | note | REFERENCE DOCUMENTS: 702.09(g)
bb42840c-1e1f-5e01-b59e-87dc8defae28 | note | – – – – – – – – –
07fc6f4b-2064-5bb9-bc2e-056df5bfd770 | note | INSPECTION/TEST METHOD: Verify
a1bae5f7-8d1b-520f-bad8-34567d04e00b | note | – – – – – – – – –
7d14100c-59be-5d63-b7d9-f83bd78b12da | note | RECORD OF CONFORMITY: This ITP signed off
07809632-8fb8-5179-a215-6663a9e81671 | note | – – – – – – – – –
67843b68-9ef5-5768-a5ab-8d2da4e6e4ec | note | HP
90e9b5d4-51ae-56c3-9485-4683ec636172 | note | – – – – – – – – –
795b5297-97a4-5a8a-a006-a6193971dc3a | note | RESPONSIBILITY: Site Engineer/ Superintendent
42a1c325-6795-5313-8f09-49e624b4d37c | note | – – – – – – – – –
a525c2ee-f234-5be9-9ef6-d61e29d5b64e | textbox | DATE:
73f046a5-1844-407e-8c0f-030b9a01e5a0 | signoff | AUTHORITY HOLDPOINT
30831df1-8289-4f84-b4c6-f0a4909677b0 | checkpoint | 1.4 Material Classification
9199f492-9acc-5a8c-86a8-d78232650514 | note | FREQUENCY: Each Lot
d10269a1-336b-51e8-b4be-5ffa6b390b78 | note | – – – – – – – – –
1aeb132a-e072-5ba1-8ce6-f4095b78653b | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes:
8ce75c99-bdb6-5751-bf39-3299f9df5eaa | note | • 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
a2ca498d-bc71-5617-942d-04658b7aa737 | note | ○ Granular filter material for bedding and backfill:
c388ffde-4b43-59c2-8452-9fd71575aec1 | note | • Trench backfilled and bedded with specified material on drawings
84b3de14-5c5a-5502-bdbb-dd22b017ac32 | note | ○ Geotextiles:
bca7363a-55a5-55d1-9790-c79be37989eb | note | • Shall comply with Cl 702.06.
ea1076c2-dd4b-5852-a81b-8b3f1543e257 | note | ○ Subsurface drain pits:
19a6a9df-d091-5005-9bec-6878b5daf2ba | note | • All subsurface drain pits shall be Type S1 to the specification of SD 1611
ce9fca0d-043c-5c83-8f76-75bb5188fe4e | note | ○ Pit Lids:
a1759dc7-e555-5c8d-9ee9-e5c30333ff09 | note | • Type M3 circular lid (as per SD 1051) for Type S1 pit
dc4fba0e-52ae-593e-a9d0-8ec880f00c1f | note | ○ Flushout risers:
28a64bcc-fa2d-5b92-996a-2f48149b35da | note | • constructed to the detail of SD 1631
6335e7d5-33ca-5b51-b91f-7ae74d6edd44 | note | – – – – – – – – –
7c0a4c40-d6e0-5b9a-b476-7271deb892a4 | note | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
3309d69f-5602-5d9f-97c5-a70fb0f00448 | note | – – – – – – – – –
b464b532-a501-541e-8eb8-15887e5a7562 | note | INSPECTION/TEST METHOD: Verify
29008222-172f-5d17-bad8-69b5a8eaf3fc | note | – – – – – – – – –
6c1a00ce-42d7-5c9e-b964-4119cebd3561 | note | RECORD OF CONFORMITY: This ITP signed off
4744d743-c017-505d-ab3c-ad9e2dea339d | note | – – – – – – – – –
49d8626b-68ad-5d04-b84d-4000fbf9be01 | note | WP
0a418518-6272-5cfd-ad68-4085f755c757 | note | – – – – – – – – –
1c321bd3-ef09-5b06-953e-be628c84942c | note | RESPONSIBILITY: Site Engineer
98ee20be-a405-51fd-9205-e09f89d04e17 | note | – – – – – – – – –
dc50a563-18d2-5f81-b7be-799fd7f39af1 | textbox | DATE:
ee42d9ce-33c2-4b07-887f-47da1cbd11ce | section | 2 - Construction Works
df20fb12-242e-42a8-8ff6-a67310df2eea | checkpoint | 2.1 Excavation Permit
d20dab5b-f5e2-54e4-a7d9-50cc3ce6e07c | note | FREQUENCY: Each lot
2f1a4b81-3b7e-5d9c-96a3-5c787393bbf4 | note | – – – – – – – – –
dd0b0e06-4125-519e-a0a6-204338e92f24 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
d25ebb9e-f2e2-5f31-8fd6-b1cca6584cd9 | note | • Plant and equipment shall be appropriate for the task.
bb990f25-a8a0-5713-b9f9-a5cdd299d4ba | note | • Excavation operations shall not disturb areas outside the limit of excavation
0db491e0-3eb0-5836-86ab-5cb8507f10c9 | note | – – – – – – – – –
f1b0385c-7b9f-5d5e-8b6c-137b5975bab7 | note | REFERENCE DOCUMENTS: Excavation permit
dd521745-7eeb-5719-9be4-681488ff8f6a | note | – – – – – – – – –
9beaa457-c42f-5e58-9a46-98a88295db0a | note | INSPECTION/TEST METHOD: Verify
501d23b0-1289-5f56-b01b-a01e5d6764a7 | note | – – – – – – – – –
87b051df-3ea0-5785-89ca-6ec78289f0c4 | note | RECORD OF CONFORMITY: This ITP Signed Off
283ef53f-f6b9-5f44-9b6f-d68fed99d4e0 | note | – – – – – – – – –
74ec60fd-fb90-5441-8cc1-467b4ce82666 | note | HP*
8ae2d622-8d36-50f5-a1ea-6714633becf6 | note | – – – – – – – – –
e6634db0-475e-53b2-9b5c-a9ec4f8bd6da | note | RESPONSIBILITY: Site Engineer
25db9026-617f-5066-8761-fc8a41ec4ab1 | note | – – – – – – – – –
e9cb386e-7cbd-5010-bf2e-bc50e47f851e | textbox | DATE:
f885c4db-e78e-4564-80cc-f82938ce6f11 | checkpoint | 2.2 Excavation of Trench
b3e558a0-0104-545a-a4fa-5b5fe2dfd90b | note | FREQUENCY: Each Lot
857d4bae-bd80-5c0a-866e-f94f6e34a31f | note | – – – – – – – – –
b3d22ec7-f3e3-5c2c-a98d-86672b41173f | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert.
e58a9768-6f18-5b59-8fdf-d11b7cdf9f19 | note | • Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed.
604439df-c907-53a2-a6b4-eabcdb39e6a8 | note | • To be inspected by Superintendent
340c42ea-932d-50a1-9e05-c767e1440326 | note | – – – – – – – – –
e8152846-ca31-52d1-a152-c28ab396b0ce | note | REFERENCE DOCUMENTS: 702.08
2288e16c-6069-5c63-9707-305102ebd532 | note | – – – – – – – – –
8af79426-884c-58f3-a707-82c1268c721e | note | INSPECTION/TEST METHOD: Visual Inspection
179caef7-16dc-54b3-bcdc-fb6bec9cc104 | note | – – – – – – – – –
18aa4477-16a4-5d86-b71b-60b24a6ec58b | note | RECORD OF CONFORMITY: This ITP signed off
155610da-a14e-502e-8b0a-0b26af43c769 | note | – – – – – – – – –
1993736f-f145-552c-a7dd-600c4f2a11bc | note | HP
f1d8ba55-e5ef-5b5e-8337-d12ff7318a25 | note | – – – – – – – – –
74e366e6-660e-5b31-8a37-497946deb0e5 | note | RESPONSIBILITY: Site Engineer/ Superintendent
cb943bf2-12f5-551c-a629-408677b110e6 | note | – – – – – – – – –
2b691a8d-c933-5be9-a809-ca9257d177a7 | textbox | DATE:
16131469-875a-4200-af59-02eea1ee242e | signoff | AUTHORITY HOLDPOINT
32a5429e-5b07-4f8a-b7c5-f356304a5843 | checkpoint | 2.3 Placement of bedding
3c1461f9-32ea-51e8-b5a8-b89c07b49662 | note | FREQUENCY: Each Lot
9c58eaa9-55a6-5b9a-b6b5-43be6dc8c8d1 | note | – – – – – – – – –
117d19dd-79a6-52f1-aa68-eaf27801db8c | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
304745b0-5e8e-5b0c-9dd1-58df0a1e1042 | note | – – – – – – – – –
d9bb14ba-0fab-56ed-81ee-a5979ea68f2c | note | REFERENCE DOCUMENTS: 702.09 (c)
98c707a9-948e-5f3b-a5d9-ea8db0238629 | note | – – – – – – – – –
2546e7df-6da3-5c35-80b1-e9063991f069 | note | INSPECTION/TEST METHOD: Visual Inspection
22043134-0794-5527-af6e-b97b3203f335 | note | – – – – – – – – –
50de7a7e-2a62-5db7-828d-98b3c32feb8c | note | RECORD OF CONFORMITY: This ITP signed off
efd18ebc-5fb8-555c-a00c-9083b768fd6b | note | – – – – – – – – –
99e648d6-6e15-5aaa-956f-59b76cdb5378 | note | IP
2d10c35f-3a34-5b7c-9647-d50ed43353a9 | note | – – – – – – – – –
ac77c018-ff78-5903-a1df-99b6958ac0f8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
40e16499-9c27-5fd8-81e3-43c516326c47 | note | – – – – – – – – –
8b389ddd-f4ff-55df-81c6-f28b5c31cff4 | textbox | DATE:
072c5b16-0a97-4c3d-8b8d-865837256783 | checkpoint | 2.4 Placing pipes and geofabric (if required)
5bbeb04c-7ffe-5b4b-a648-4d188de33ef5 | note | FREQUENCY: Each Lot
5da94d8c-cbdc-5f36-9759-ca327180e9de | note | – – – – – – – – –
8d83ada1-2087-5bc9-a999-d453febbd9a6 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
42dd2f33-f2b3-5824-b867-f92196838a1a | note | • If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
812c0e19-0480-5997-a3b8-8ca91ce2efae | note | – – – – – – – – –
2ca5f623-674d-57d6-bfd7-c7459a1a5eb3 | note | REFERENCE DOCUMENTS: 702.09
2c81e6c8-47ea-5c26-a1d3-2e6452eefae3 | note | – – – – – – – – –
4191252a-82a7-55ba-9402-2033f247d367 | note | INSPECTION/TEST METHOD: Visual Inspection
096c3f57-93f8-50b2-afdd-909afc3a4723 | note | – – – – – – – – –
1ec70074-203b-54ae-a3d2-b2ccda17382b | note | RECORD OF CONFORMITY: This ITP signed off
1bffcecd-6483-5cdd-aaad-ecbe3fefbe08 | note | – – – – – – – – –
065a2ab0-7178-5fdb-bd6e-890aa166bd26 | note | WP
aef9d969-e66f-5d3a-bfd9-1fa3d3f50628 | note | – – – – – – – – –
a852fccf-c789-5ae1-b435-23992c378aeb | note | RESPONSIBILITY: Site Engineer / Site Foreman
2eb9ce34-2bbf-55d4-96d4-809693ca0a8b | note | – – – – – – – – –
582a81da-c002-5d1d-ba98-e0dd71b6dcbb | textbox | DATE:
0bd1a307-6ab6-42f4-93c4-c66714de598e | checkpoint | 2.5 Placement of backfill
c1e50043-b12c-579e-bf83-a5723c687a96 | note | FREQUENCY: Each Lot
a8b8096d-6779-512c-8138-40d24bae0656 | note | – – – – – – – – –
78ddb4e7-7c65-57da-ba33-3842f9c4266c | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes.
da923ce2-f5d2-5d9f-9862-b16351836807 | note | • Concrete is to be placed and compacted within one hour of mixing
cc3ad047-dc37-5329-8bea-c0fd4a7a6591 | note | – – – – – – – – –
5c7a463a-5e70-5e21-a1f8-add3f18ff77d | note | REFERENCE DOCUMENTS: 702.09 (g)
ba22ce98-dd3a-571a-a7b1-a649de746b3d | note | – – – – – – – – –
11accd78-a869-5c99-990d-5c4b2aae41a2 | note | INSPECTION/TEST METHOD: Visual inspection
14d5c769-326a-5a2f-adac-9c6f3d8f19a2 | note | – – – – – – – – –
624cb29f-5d9d-57e8-a64f-27813865e7b0 | note | RECORD OF CONFORMITY: This ITP signed off
506eed55-1dc7-56e5-8d53-1e735fd5bfab | note | – – – – – – – – –
21a52fb5-f34a-5f27-9ccf-be1527def868 | note | IP
7dd2c495-a909-548b-9a49-957b0dc0f18b | note | – – – – – – – – –
cfac3392-6c5c-5570-b77f-0be98d41a895 | note | RESPONSIBILITY: Site Engineer / Site Foreman
aea8f946-d866-5b81-a6f7-f89eef64b58e | note | – – – – – – – – –
25970e3b-6f8f-550e-9c46-7555e2dbb047 | textbox | DATE:
57f20122-8937-4ac0-93fc-9b9040cad5e5 | checkpoint | 2.6 Install Pits and Flushouts
352edeea-72d1-5ddd-b1a1-a8205b98ae66 | note | FREQUENCY: Each Lot
03e2e9a6-0b98-52fb-9b4e-347c702665a3 | note | – – – – – – – – –
92b4d5fe-f720-57e2-9199-6027fcae0e8a | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
80c7fa07-cdda-5859-8481-e71b1490ee76 | note | – – – – – – – – –
cc41841c-b543-5f30-9ec7-1ec35527bdb0 | note | REFERENCE DOCUMENTS: 702.1
5387772c-3677-588f-abd7-fc9956f3c86d | note | – – – – – – – – –
f136f998-c61e-5e51-9710-b3567f5b024f | note | INSPECTION/TEST METHOD: Verify
b7f606c0-a2dc-5016-b137-74ea43e3d9e4 | note | – – – – – – – – –
cd593395-ff5d-588a-bf76-97d2a27bd654 | note | RECORD OF CONFORMITY: This ITP signed off
ab42215f-6b06-586d-83d5-edd723eafc25 | note | – – – – – – – – –
cd73e14d-7558-55bf-a9fe-fef38d69e9d8 | note | WP
48d5d505-6b85-5399-a409-6648fc0c8776 | note | – – – – – – – – –
cddb36a3-3544-53e6-983f-d95fe6f20785 | note | RESPONSIBILITY: Site Engineer / Site Foreman
714d6cea-fd24-55ed-98b9-a5f6c2d02314 | note | – – – – – – – – –
387782fa-a4d5-5b29-b2cc-9fb337465913 | textbox | DATE:
0c1608f3-505a-41e0-aae3-7012b198be9e | checkpoint | 2.7 Flushing Test
04769a3c-68ec-5f45-9f34-2f52331fd427 | note | FREQUENCY: At completion of stage
10792bca-d11d-5a7c-8b88-a9c1089083a6 | note | – – – – – – – – –
28ebc8b5-1279-5b47-ad9c-293ac6ed8096 | note | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
b9741883-20e1-5f9c-ae12-cde4091cf703 | note | – – – – – – – – –
cefe31f8-c900-5d09-8289-deb53ba2a9b3 | note | REFERENCE DOCUMENTS: 702.09(i), 702.09(h)
c610f2f5-279c-5f0b-b24a-9bd4c3b81caa | note | – – – – – – – – –
9562b066-9d20-515c-be52-3da1b292b6ea | note | INSPECTION/TEST METHOD: Site inspection
33729ca8-2416-5c39-903a-90af68d9c357 | note | – – – – – – – – –
6b783d32-0a86-54d9-987c-e4880738ae7f | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
640db40a-2944-5870-a8ea-df88e5c18ab4 | note | – – – – – – – – –
acff837c-579f-5f8d-8767-9e81fe91b5bc | note | WP
22b57d3c-a0e5-5cf0-aa5b-a19354cb4f7e | note | – – – – – – – – –
7f96e6a6-6565-5b38-9d57-7e1a15ccf404 | note | RESPONSIBILITY: Superintendent / Site Engineer
ad910ba9-4fa6-5bd7-be9a-429ff6dac53b | note | – – – – – – – – –
54c68165-251f-5b5e-8238-abdadb04aec1 | textbox | DATE:
d9769b10-169c-4d37-a235-805ed02a46e6 | checkpoint | 2.8 CCTV
9e69de3a-43db-5bce-aa19-84ba133361f3 | note | FREQUENCY: At completion of stage
7077780d-8e07-50c9-98af-c3b5af461c40 | note | – – – – – – – – –
6fca9033-2890-5454-b736-6bd3fcbe3c80 | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
997d8d3e-468c-55a5-bbea-babea31f14c9 | note | – – – – – – – – –
cf49a67d-bf02-5b26-aff0-45f0f9a250ab | note | REFERENCE DOCUMENTS: 702.09(i)
656c4a9e-b60f-5b77-a005-feb85c93638c | note | – – – – – – – – –
7a288178-8dcb-59f7-a111-b92f61046bb0 | note | INSPECTION/TEST METHOD: Site inspection
8166e803-f4c1-5346-8e7f-5854606caee3 | note | – – – – – – – – –
efbb5b0b-7a1b-5756-8f06-28c125e5abef | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
3971a81f-045b-5ce2-bab1-fe49400ea05c | note | – – – – – – – – –
2f6805a5-a4e4-5ee0-8d74-21bb28c243c0 | note | HP
74db2ce3-6b39-5400-8007-5533fe801d7a | note | – – – – – – – – –
f1288389-44f5-5d1c-b8c6-640d333982e9 | note | RESPONSIBILITY: Superintendent / Site Engineer
288b9b39-36de-53df-b27f-08e9c236ec99 | note | – – – – – – – – –
f7fad7e6-9ee7-5e98-9835-d303c6222f54 | textbox | DATE:
0dfc3d1a-be9d-476e-8506-e3be7cdfaad7 | signoff | AUTHORITY HOLDPOINT
12120c89-2cba-4bde-97b4-04cbb1f5d554 | checkpoint | Final Inspection
20a922e1-3165-5590-8c69-9279ba74e8d7 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7bdc869b-dab4-5399-8d87-209aacf1777e | textbox | Print Name:
533c9815-486f-5a64-8f4a-c4873841e47e | textbox | Position:
a886b4b2-1158-5a81-ba34-aaeeaa7a0e84 | textbox | Date:
8ca5aca1-f1c5-48b7-b640-1e4bd09a58dd | checklist | FHC-ITP-015 - Kerb and Channel Rev2 | itp | FHC-ITP-015 - Kerb and Channel Rev2
c299756b-221f-47b6-b91a-b8d22e405abb | section | 1 - Preliminary Works
49ee5614-90ea-4dd5-9801-0aa3601f9064 | checkpoint | 1.1 Check for correct documentation
9e382b98-0c9a-5116-ad0b-3a3bf5c2ef28 | note | FREQUENCY: Prior to commencing any activity
1a0a4532-a1e6-5fd6-a51e-4022186ca9d8 | note | – – – – – – – – –
1e466107-3bc7-5416-9319-328ee7785d68 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
c970ec51-a160-5756-b0f2-f0224fadfe17 | note | – using the correct and complete set of drawings
bdb65390-5a2c-5b31-b292-f7fd9ec9f401 | note | – all drawings are the latest revision
6e2cf3b7-2c58-5cd3-9d79-33c48a0a6e57 | note | – – – – – – – – –
340c37d1-6923-5701-b609-218c20849652 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6664951f-9065-5cc9-b877-578d015dbb1c | note | – – – – – – – – –
a005972d-3959-5ac4-a7fc-4e2e021f1b77 | note | INSPECTION/TEST METHOD: Visual inspection
1db6fbaf-5076-571c-8ba3-180300469b56 | note | – – – – – – – – –
2028a2dc-e84d-515d-9aa2-8149a59768ea | note | RECORD OF CONFORMITY: ITP Signed
4629b31d-2006-5fb8-afa5-5a20f35aaf09 | note | – – – – – – – – –
680340c4-b22b-5979-b38d-c91e60855a00 | note | HP*
1d386073-6804-5908-ba89-6a62f0367330 | note | – – – – – – – – –
5570f7df-a920-510d-a8a1-e630a847a877 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
b0a5f2d9-e78a-5213-a836-d8cfa3929d16 | note | – – – – – – – – –
0cb82b18-7a3d-5b00-ae39-f8a57e66b489 | textbox | DATE:
a0e81c0a-4284-4992-8ff8-fc4b0ad1de0e | checkpoint | 1.2 Implementation of all measures and controls
3499eab7-65fb-5c2a-8603-a0d22ae701f3 | note | FREQUENCY: Prior to commencing any activity
848296c1-42e5-5324-8838-08c3482d0fdc | note | – – – – – – – – –
bfee910a-2bef-5bd7-b939-b3be320bb2a7 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
61f40a02-5631-5482-b69d-04dae2276deb | note | – – – – – – – – –
970454e7-7a82-54c7-9372-9d14f935b17a | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
93a863ef-a783-51d3-a74d-5e0b91205cd5 | note | – – – – – – – – –
6618d626-e9c2-517d-a9f4-488f6ff430f2 | note | INSPECTION/TEST METHOD: Visual inspection
a8bf9434-86c9-5a5b-b58b-fbca026a45d2 | note | – – – – – – – – –
f8512d07-e807-55d3-bf8b-06d6358cf8ba | note | RECORD OF CONFORMITY: ITP Signed
7ff1ea45-db77-5115-a62e-b72fa57b973e | note | – – – – – – – – –
ebdae2a5-dd5c-5bd1-9d6b-613a09d6b0ac | note | HP*
bd80374c-ca5f-5bf3-b154-4ce2beb88502 | note | – – – – – – – – –
f057e2c2-0b8d-5fa8-baed-275b26fbb15c | note | RESPONSIBILITY: Site Engineer/ Site Foreman
b71dcbfb-2bbd-5dea-b19e-877a3e117f83 | note | – – – – – – – – –
aa2a7a8f-fdef-52fc-b76d-c13bd42ec47a | textbox | DATE:
6a250a7b-4dcc-45e3-bb8a-1046bb313fef | section | 2 - Construction Works
2cdaf54b-5502-485e-b6b9-22ef22a27fbd | checkpoint | 2.1 Setting Out
76cf86a6-cb6c-57ca-8cde-3eefeba27485 | note | FREQUENCY: Prior to start
dc568c2e-59ec-5e1c-8146-0e7c14028bb0 | note | – – – – – – – – –
2de90901-ebf0-5125-b391-336b35012423 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
56f3a597-c1de-5ab9-b88d-55bbbd4bd0d2 | note | – – – – – – – – –
38cd875a-92fa-5dcc-989f-e2d9d9433dc2 | note | REFERENCE DOCUMENTS: 703.17
ad2152e1-8298-5dc6-8b46-6d5ebe62c3e3 | note | – – – – – – – – –
9ec4fd36-c308-5461-ab5e-a6c5cd157a55 | note | INSPECTION/TEST METHOD: Verify
a28f41a0-d24d-5955-82c2-ef5007f46f77 | note | – – – – – – – – –
810decaf-f252-5e04-9dff-8002eee62b8d | note | RECORD OF CONFORMITY: ITP Signed
5e5fc907-3e49-5fef-b34c-964a10cb7c3b | note | – – – – – – – – –
08ee1bea-869b-5973-a2c5-6b0dcf6c4663 | note | HP
646dee98-109a-5544-b13b-b4527e09f2b0 | note | – – – – – – – – –
dc8cfde6-f750-5a47-a20f-0d679ec8f45a | note | RESPONSIBILITY: Site Engineer/Superintendent
64657264-c8f5-5ccd-9e52-47454c7995c9 | note | – – – – – – – – –
c5d05886-6cd9-5d80-a5b3-27046aabd703 | textbox | DATE:
80b90089-cd88-4d83-8791-348f71f44d0e | signoff | AUTHORITY HOLDPOINT
fd8e7195-fcf7-451e-8226-c1a3952e88f2 | checkpoint | 2.2 Temporary Drainage Provisions
2c2fb776-0144-58a7-a7d6-6d277b9af462 | note | FREQUENCY: If Required
74fb7ac6-3ab4-5f25-b9b6-5350b599d80b | note | – – – – – – – – –
7a842054-90ea-5d6f-89c8-5f0e4593db94 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
e3955c9e-1d2c-5715-8a66-6df0fae0687f | note | – – – – – – – – –
87632b3b-49de-5a84-b9aa-972ee7197e9d | note | REFERENCE DOCUMENTS: 703.18
337fdeed-0acf-5e3c-9241-09376c73a61b | note | – – – – – – – – –
87bccdd2-6036-5d8a-9785-35e04ec9acc1 | note | INSPECTION/TEST METHOD: Visual inspection
b5804ce3-a2af-592a-8f1b-b4d4fc1cff1a | note | – – – – – – – – –
5d8a1ffc-4b62-580f-bca6-3a698562ab93 | note | RECORD OF CONFORMITY: ITP Signed
6775a542-b2dc-58e4-b485-7fb6ec35d52d | note | – – – – – – – – –
7a3ec566-c816-54a6-b825-eb17a279cf86 | note | WP
3b8651d6-77b2-5ac1-9915-52e26ef13c34 | note | – – – – – – – – –
c9b4852d-4aa8-54f1-909f-ecc41c96e0ec | note | RESPONSIBILITY: Site Engineer/Site Foreman
4aec42c3-098d-5eb5-8d6c-d6aa098cebc1 | note | – – – – – – – – –
9980268c-efaa-5874-b473-490f09925b15 | textbox | DATE:
f116c8f0-81f8-4270-ba29-214d0d32c109 | checkpoint | 2.3 Bedding
fcf23dce-f610-598c-a6ef-0c04c9c91350 | note | FREQUENCY: Each lot
072c0ee5-9a07-5426-ac0a-49bb1fb62597 | note | – – – – – – – – –
d13e0411-d129-53be-bf30-609105f59d6f | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
7aafdb8d-7f18-58f1-98eb-fd0d4864da12 | note | • Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
7f1c292d-932f-5813-b503-701749aeebb1 | note | • Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
ab22cc32-0728-543f-823d-22316b939765 | note | – – – – – – – – –
562e55b1-dbbf-5243-9f43-20366542df53 | note | REFERENCE DOCUMENTS: 703.21
3b2d6938-560f-5fd0-b311-5619ceb697eb | note | – – – – – – – – –
6b33a2e9-66c7-53b4-be89-64ddbd85dd87 | note | INSPECTION/TEST METHOD: Visual inspection
3e1f57ff-bfde-53cf-bdd2-723b518568aa | note | – – – – – – – – –
9cb4034e-1864-5028-a39d-487621d1faf5 | note | RECORD OF CONFORMITY: ITP Signed
2ab606fb-a5c7-5d78-b5b6-4c8bb030f3ca | note | – – – – – – – – –
f4ebaddb-8b12-55bb-b605-5963e9556da6 | note | WP
591f91d2-e099-569e-911f-37eb58135ce7 | note | – – – – – – – – –
4febd336-c8d4-5899-96f4-f64653fd6aa7 | note | RESPONSIBILITY: Site Engineer/Superintendent
32f7ca1f-8ff1-5e1a-8a8f-676388be3c62 | note | – – – – – – – – –
dd059c22-bc1e-538c-8c22-eb1788d24bb9 | textbox | DATE:
7246a2f2-7a0f-4532-9640-518f6d18b2a9 | checkpoint | 2.4 Pre-concrete check
811f28ce-66e8-5d57-a157-58af284382eb | note | FREQUENCY: Each lot
669402f0-df37-50fa-a63c-55c3baea683a | note | – – – – – – – – –
faf6d114-94c9-5f29-a76a-83e6588ea2b4 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
795d7251-90c8-5f44-8eef-2bcfbfa5f4b9 | note | • Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
aff424c3-8375-5c3c-938f-ea58f3b97394 | note | • Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
8fdeaaef-d5c6-5cac-8be4-7028f50c20ec | note | – – – – – – – – –
61d00ecb-3457-5b8d-85d9-344f6ec32775 | note | REFERENCE DOCUMENTS: 703.08 610.17(a)(b)(c)
bcb09bb4-3e61-586d-bcc5-2e71c6c65911 | note | – – – – – – – – –
e31ced4c-bd3e-5bb3-bf5b-7620c41480bd | note | INSPECTION/TEST METHOD: Verify
f82edc5f-d939-5ba9-b73b-f4a35d0cbbc6 | note | – – – – – – – – –
5dd4fd4e-29bf-54ad-b8db-c48ec99bf1e3 | note | RECORD OF CONFORMITY: ITP Signed
801796e7-b337-57de-9d7f-f6180b8811b2 | textbox | Ambient Temperature |  |  | °C
a7f2a00d-c654-5537-b9d2-26ca511922ec | textbox | Concrete Temperature |  |  | °C
e5c60996-39da-588f-85a7-6adc09d92402 | note | – – – – – – – – –
832015f4-bab3-5c2e-8941-32a49e60c7aa | note | HP*/WP
49da0252-8761-5a5d-9895-92cdc12742dd | note | – – – – – – – – –
01d2059f-9d8f-5b76-8ddf-7b93c8502022 | note | RESPONSIBILITY: Site Engineer/Superintendent
553773d6-ff5a-505c-bfc8-6ebbd86c1a57 | note | – – – – – – – – –
828452fe-2690-53fb-9d3f-df5474c62cbf | textbox | DATE:
db5023b8-b9fa-46d3-a4c3-7f0d45724811 | checkpoint | 2.5 Concrete Placement
088895af-9880-54fc-a0f2-e84773a1f52e | note | FREQUENCY: Each lot
5ff60865-c9d6-5709-8bac-f6a6332b7b8e | note | – – – – – – – – –
c2ee4015-f887-53a8-be35-d0c21f630f52 | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
fba09a61-7279-59e1-8e06-fdd564d94f64 | note | – – – – – – – – –
a512f20d-865f-5f7e-9420-51056410d0c7 | note | REFERENCE DOCUMENTS: VicRoads Spec 703.23
c4cb5015-f17e-52de-bad4-c1385559e3a1 | note | – – – – – – – – –
8894cd9e-c672-5d60-9272-76cac4a33aa0 | note | INSPECTION/TEST METHOD: Site Inspection
6d3d49c9-771e-5e2b-9375-2fa68d9c0f0e | note | – – – – – – – – –
e0da5a5d-ceb4-5e55-acf9-182881285dae | note | RECORD OF CONFORMITY: ITP Signed
6f30621e-bfd6-57fd-b160-ec15f9731637 | note | – – – – – – – – –
02257532-52ea-550f-b8e2-e5d4b02f13bd | note | IP
0c48c9ac-df3b-5ded-9ae3-a083483d3279 | note | – – – – – – – – –
25300847-409c-5608-a789-e9cc17d0a05e | note | RESPONSIBILITY: Site Engineer
ae42d4f5-9a68-5bab-a1ad-7e6514e80f2d | note | – – – – – – – – –
f930acf8-f320-5144-bcb9-c3562c05bfba | textbox | DATE:
e778b739-fe2d-459e-b747-fd40b47f7aae | checkpoint | 2.6 Finish Surfaces
fdb5adf9-3aff-5966-bd87-1e33abca9f07 | note | FREQUENCY: Each Lot
1f4aedc9-1585-5302-b0ba-4a184565b853 | note | – – – – – – – – –
6217c428-fd3c-515e-a5c4-ae75bc20503b | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
fd85b183-a238-543c-90d4-a43b1158b3b4 | note | • Concrete to have a neat appearance and uniform colour.
1ecd46b5-8a41-56e3-b184-4252932ddcf8 | note | – – – – – – – – –
691f3aa0-c2d3-58bf-99c3-a76f957706e8 | note | REFERENCE DOCUMENTS: 703.25
a65091a0-9b04-599c-8004-d79fb1bae7ba | note | – – – – – – – – –
b9480a0b-3815-52ef-831a-e3ff5686d634 | note | INSPECTION/TEST METHOD: Visual inspection
42f9725f-6d24-5579-a0c7-283a7b85ac8a | note | – – – – – – – – –
b45aef1f-441c-5137-bd52-c781d3aad341 | note | RECORD OF CONFORMITY: ITP Signed
6ff4b09a-3736-55c1-9fc6-3a0aee4b2a4f | note | – – – – – – – – –
83e02042-948b-545a-8db0-e4a49047bb98 | note | IP
9b8ae530-32ff-5653-ad48-2a2e86933ac6 | note | – – – – – – – – –
0d89d20d-f801-5a44-bbce-a928d614e9ee | note | RESPONSIBILITY: Site Engineer/Site Foreman
d2bcdfbf-f5a7-5951-9fd4-d74c3e1bf054 | note | – – – – – – – – –
4e7e0018-9ab0-5ebb-a19e-00b6873bbf19 | textbox | DATE:
92d6b5f4-bea0-4a47-9bb9-8739763aec56 | checkpoint | 2.7 Tolerances
f41ed7f7-9a65-50b2-bfeb-e716a8515f65 | note | FREQUENCY: Each Lot
d680bf8f-1e26-5883-998f-7854f6885ab1 | note | – – – – – – – – –
541f57d4-5dbd-5ee3-a09f-4e5408de3136 | note | ACCEPTANCE CRITERIA: Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of ‑0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
9548889e-f5f2-561e-bdaf-4df75b7ae90c | note | – – – – – – – – –
0bd94c24-c9f2-59e5-a7c8-c6b150d7c22c | note | REFERENCE DOCUMENTS: 703.15(b)
65e6da01-d9c6-5464-b3fe-66f3f68138a5 | note | – – – – – – – – –
16bac79f-93d6-5fd4-a8ad-610a7dc0d4a0 | note | INSPECTION/TEST METHOD: Verify
1f384f9a-dedf-50fa-b5cc-51b46ea0ff3a | note | – – – – – – – – –
5d66e1be-0739-572f-b52f-a8effc19c2c7 | note | RECORD OF CONFORMITY: ITP Signed
dfd1489e-7ef2-5c98-b8a5-5ee36f7d9e27 | note | – – – – – – – – –
681caede-214a-5210-bf5b-b670f973c053 | note | SCP
5d80524c-c81c-51f4-937c-6c64a299a1b7 | note | – – – – – – – – –
9669dad7-dbf8-57d3-b390-e43fd4e5db04 | note | RESPONSIBILITY: Site Engineer/Surveyor
f2b5d9ad-2068-5e83-a1b9-c13430337f03 | note | – – – – – – – – –
d2d75778-148e-51b6-b68c-9245ea54daf5 | textbox | DATE:
50337313-1512-402b-8b3e-81d52bbee36e | checkpoint | 2.8 Joints
4ba509a1-44c5-59e5-ae30-0b97df475107 | note | FREQUENCY: Each joint
daf3ec03-065a-5225-8b07-2d53048f339d | note | – – – – – – – – –
87cd622f-124a-581c-9ea4-3d5d9f1cdbb5 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
c936fc2e-e901-5efc-8a8c-751ddda92d3a | note | • Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
10538b15-7398-544e-bce9-fbc41e17eaaa | note | • Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
8c6b9154-eeb3-5262-b49c-82e3a51dcff7 | note | – – – – – – – – –
60be61be-b452-5076-a71f-9d7dfa1addd6 | note | REFERENCE DOCUMENTS: 703.26
d74243b1-7d64-5069-97fa-b33a191c722d | note | – – – – – – – – –
556ae6bf-2cf3-58d7-92c8-c2511f5412e7 | note | INSPECTION/TEST METHOD: Verify
96beb26d-9041-51dd-834b-2ec5a9ead156 | note | – – – – – – – – –
1694210b-0cf2-5eef-8f5a-1ef6a743f66b | note | RECORD OF CONFORMITY: ITP Signed
2117c747-0d68-5197-8e3c-fcd68bdb38ea | note | – – – – – – – – –
8f88e59b-7639-5e2f-815f-10848dc75f56 | note | IP
ee67f211-32fa-5617-8e48-d4c3f0c29414 | note | – – – – – – – – –
d51964f0-0e3d-5144-846e-87e244117d83 | note | RESPONSIBILITY: Site Engineer/Site Foreman
d5162ef7-88ec-5cdd-847b-6859fbe8871b | note | – – – – – – – – –
89a69605-da07-504b-b893-8bbe4d756b92 | textbox | DATE:
6a5bec58-21dc-4f65-b240-6563f02cea76 | checkpoint | 2.9 Backfilling
4c948f4b-f9a1-5161-977d-c6507e6b4717 | note | FREQUENCY: Each Lot
5304eb7d-3287-534b-8295-7b9b5d2ebf6b | note | – – – – – – – – –
dd31ec92-9c95-5068-b6d5-b02876f66629 | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
18ef1008-a532-5339-b281-23264fa19b7d | note | • Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
0aab15a4-7c22-5ed6-b061-731059995a3e | note | • Layers shall not exceed 150mm compacted depth.
ca2325ab-c679-5429-897a-51708d53fa77 | note | – – – – – – – – –
39bb1902-faee-53b5-8904-9a6406fe1cc5 | note | REFERENCE DOCUMENTS: 703.29
ba428702-5591-59d4-bbf6-9c0733aeefd4 | note | – – – – – – – – –
d4f06d69-6ed5-5240-ac3d-a699b512db67 | note | INSPECTION/TEST METHOD: Verify
fb53ed29-75af-5c31-b6ee-ea865ea681ca | note | – – – – – – – – –
805d90a5-760e-5e03-960f-eb9ff6f45751 | note | RECORD OF CONFORMITY: ITP Signed
99010f44-1d72-5348-8cc8-f4d3e8001807 | note | – – – – – – – – –
5fd8fa99-25a5-539d-8b6b-8dcf64d349c0 | note | IP
19822f1d-ee48-501e-a8ee-beecafa3e7d3 | note | – – – – – – – – –
739bd420-bf4f-596b-8ba1-1e45014f01b2 | note | RESPONSIBILITY: Site Engineer
81791a70-9181-5eb5-9d78-115286947ecf | note | – – – – – – – – –
cdf12d5e-385a-57e9-94db-b96ca7dc0675 | textbox | DATE:
1081b2b1-996f-4bba-87bf-b7da00294790 | section | 3 - Completion
d37b0a96-ab76-4d46-8d62-beb7019b1222 | checkpoint | 3.1 Survey data captured for as-built purposes
9e4b17f3-0248-5459-8608-6d1a214177cf | note | FREQUENCY: Completion of each lot
4a966ff7-ea01-5f24-9c7e-e192c3291988 | note | – – – – – – – – –
609ea90a-201c-590d-8f35-52268edc84f4 | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
af77bb61-bd69-5350-ba67-3a2bdc586441 | note | – – – – – – – – –
9c15a886-ab17-5154-b670-36e3ccf4bf29 | note | REFERENCE DOCUMENTS: IFC Drawings/survey records
d093abbe-aed0-555e-83cd-33b9a612d404 | note | – – – – – – – – –
547c5056-2d2d-5442-9f01-1f8d8efa18b2 | note | INSPECTION/TEST METHOD: Document review
731a4cc7-c9e4-5063-9027-8bdc4551665a | note | – – – – – – – – –
fb17ae94-eab3-5ba7-be31-75ca28c47a89 | note | RECORD OF CONFORMITY: As-built survey records
73fe5bc2-ba6c-575a-aaf3-63a611bcf603 | note | – – – – – – – – –
d6c88fe1-428f-5708-b0bd-57c25437cb9f | note | SCP
9c16b461-b3cb-5ed1-bfe9-71d2a62340c6 | note | – – – – – – – – –
c3e2eead-1947-5718-94e3-d2f1e4d480f4 | note | RESPONSIBILITY: Project Engineer/Surveyor
e77912d5-24b5-54a9-aa2a-3194484268ba | note | – – – – – – – – –
76338c64-bf9e-59f0-a0da-fe8cf9cc9c18 | textbox | DATE:
7f7d522d-1ea8-4e32-9e04-6daf0604d42d | checkpoint | Final Inspection
31dff94c-f57e-5925-8666-25d354557d05 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f801d887-9311-5733-b91a-159008575cd1 | textbox | Print Name:
175a9081-b9b6-5e17-a071-4d6838fdf29c | textbox | Position:
e675522e-6d02-5104-8b33-900c02925106 | textbox | Date:
12bb117c-72fe-4212-beda-85992950b217 | checklist | FHC-ITP-016 - Sign Installation Rev1 | itp | FHC-ITP-016 - Sign Installation Rev1
58c2bac5-35f8-48d4-8b7c-7c3b826a1b38 | section | 1 - Preliminary Works
9b056ddb-5f3b-42bb-b393-c74f9069bf94 | checkpoint | 1.1 Check for correct documentation
9c27dd7e-4ded-5f17-bf87-ae90e60f4880 | note | FREQUENCY: Prior to commencing any activity
9fbd2f2f-3650-560f-a1c4-06be54c06a31 | note | – – – – – – – – –
e72ffc19-f882-5952-abc5-8b7a410f116e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
150d2898-8a83-53d9-bbf5-bf6eb3bfe36b | note | – using the correct and complete set of drawings
13b6bda2-98f1-5e3d-95ed-acfd212d9ecc | note | – all drawings are the latest revision
c24d5855-e8c7-569a-a70f-12679e13e802 | note | – – – – – – – – –
d14510a6-8577-5e5f-979d-a0128f4adcf5 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
534d907c-43be-5d4d-8da0-979c486a9292 | note | – – – – – – – – –
25cf48fc-9cfd-5af7-994f-66d1e791136a | note | INSPECTION/TEST METHOD: Visual inspection
70b3d830-9c8a-5bfe-825e-a77987580d01 | note | – – – – – – – – –
2b33a405-4a41-52a1-abf6-5689b8d71f0f | note | RECORD OF CONFORMITY: This ITP signed off
8605f5c4-3f9a-5654-b146-c258a154594f | note | – – – – – – – – –
b1e82581-a413-5436-8029-320347da5b43 | note | WP
f2206e0d-494f-5a91-8524-22c339755cdb | note | – – – – – – – – –
a3628e7e-d2aa-5080-9f24-dd2c260186bc | note | RESPONSIBILITY: Fulton Hogan Engineer
2c4b30b3-9169-58d4-a9ae-6243f5a47caf | note | – – – – – – – – –
7a14ef17-de65-5fa8-b546-8281fdb5ea82 | textbox | DATE:
8590cef8-3016-43c4-9d26-1192f769e2f2 | checkpoint | 1.2 Implementation of all measures and controls
7c0dd943-ee99-5bfb-8197-f0f5afbf273a | note | FREQUENCY: Prior to commencing any activity
183ef929-e143-54c3-b36f-40f7fcaca001 | note | – – – – – – – – –
de652e4b-c1ef-58e5-9462-7ccab9b94845 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
86f2706d-7060-528e-a013-36613bf7ddc3 | note | – – – – – – – – –
2f2a0a7d-5a43-5530-8d0d-7b799cccfd73 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
2c7b3892-939a-5522-baf1-b29ae64e9711 | note | – – – – – – – – –
08ccc976-35c0-53c3-ac29-2bf8456d7301 | note | INSPECTION/TEST METHOD: Visual Inspection
eba9efd0-db31-53c5-8657-0f92603f190f | note | – – – – – – – – –
da14850f-6124-5a8a-9f49-05e4802082e2 | note | RECORD OF CONFORMITY: This ITP signed off
1f075c7a-753e-5fb1-b0e4-9118058bd1eb | note | – – – – – – – – –
a4358156-ace3-5ebf-b338-42034b34c000 | note | WP
be2035fe-2241-5b3c-963b-55f9f5bbb0ea | note | – – – – – – – – –
2b605143-3bd7-5274-bbd8-7f9f291d29cc | note | RESPONSIBILITY: Fulton Hogan Engineer
b240ba06-99e7-5d40-bf3c-45d5e8ddc073 | note | – – – – – – – – –
ddc7aa42-d224-5a2c-a6ef-9a136bc7b90d | textbox | DATE:
0e6b9a99-cf8a-480c-a85c-623796e63f97 | checkpoint | 1.3 Signage Conformance
35798345-0be4-507f-b0db-488204a2c243 | note | FREQUENCY: Before commencement of activity
754b5c5a-bcab-5c6f-8dad-1626e5f6d2bb | note | – – – – – – – – –
59275387-35e8-5cfe-bbae-1bbf927a94d2 | note | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
a21688e9-a60f-5bac-861c-27f6d834c138 | note | – – – – – – – – –
6a36ac2e-4511-5197-a875-3e39628d4504 | note | REFERENCE DOCUMENTS: Drawings AS 1742
5890a6fd-3a78-5e36-a85a-702eab6da777 | note | – – – – – – – – –
b49d1f03-220b-5188-a1d5-f8f749c11748 | note | INSPECTION/TEST METHOD: Verify
49522911-32c9-55f7-8cdc-d822b815367e | note | – – – – – – – – –
c1e04f61-a01e-5beb-b6bf-b8df3ec7b6c3 | note | RECORD OF CONFORMITY: This ITP signed off
e99a3ca6-8055-597c-a19d-1f9da112c666 | note | – – – – – – – – –
d50c28f3-73fa-53ea-984c-3e7b47b5507c | note | WP
ae16bfa5-7d6c-585b-8a31-2577444ebdce | note | – – – – – – – – –
db770921-7ef7-5047-99bd-638ae2e0e649 | note | RESPONSIBILITY: Fulton Hogan Engineer
4e638eed-a712-59a1-b123-26608527568c | note | – – – – – – – – –
f4e102bd-acee-57c3-b9d8-2411c7563732 | textbox | DATE:
874dc28a-60ef-4856-887a-aff91cbe4720 | checkpoint | 1.4 Service Identification
43bd179d-c0b2-596f-b3db-fe79334c6c87 | note | FREQUENCY: Prior to start
bf7fe35c-dca9-5dd5-a195-bfb654f40e00 | note | – – – – – – – – –
e1cf3b4f-ce8f-5c67-9f91-f5727dbcfda7 | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
051ab3d8-5926-5469-9201-3c3a1b79bb2d | note | – – – – – – – – –
65df6554-bbd2-51ce-8c38-e5ef6574d28a | note | REFERENCE DOCUMENTS: DBYD, Service chart
f2f4c1f7-bce9-5df4-8e1d-9f2767cc3bf5 | note | – – – – – – – – –
b3f23486-3bfc-5b5e-a0f5-206110b8b45a | note | INSPECTION/TEST METHOD: Verify
5df765ef-a3a7-5c48-aa0a-5ea761252bc8 | note | – – – – – – – – –
50430cce-9781-5142-aaec-00131282f795 | note | RECORD OF CONFORMITY: This ITP signed off
1678b2ad-2416-5da0-b1a0-1f3825991da6 | note | – – – – – – – – –
3eb7b383-23b1-5ff4-a98a-8e147cc45956 | note | WP
6d74268c-6979-5448-9516-48cddf82ce9c | note | – – – – – – – – –
61eb8828-e2e4-5f4f-9013-72297b281aa2 | note | RESPONSIBILITY: Fulton Hogan Engineer
8513533f-180a-5557-80ad-0a9e46cb1595 | note | – – – – – – – – –
638c42da-cc91-547b-912f-d02d98f393cd | textbox | DATE:
58cb6de6-05d4-4304-8141-9bd010acae72 | section | 2 - Construction Works
f0264b9b-f71a-4377-82f0-a1d65b46ced6 | checkpoint | 2.1 Setting Out
27a70679-a823-5a19-aca5-a4164c93f885 | note | FREQUENCY: Prior to start
a9a6c93e-b10a-58dd-8c44-701fdf78d436 | note | – – – – – – – – –
ff6941ab-ced5-5541-bf83-c92ddbe50312 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
dc2f5368-7940-5946-b732-bfef99208d60 | note | – – – – – – – – –
c2392769-da03-5e2c-a8f2-dfb97ea95d5e | note | REFERENCE DOCUMENTS: Drawings
6863d742-2f23-568e-b19a-2c24a9490b08 | note | – – – – – – – – –
2eae5966-91a6-55b9-9443-9548b58c4b03 | note | INSPECTION/TEST METHOD: Visual Inspection
b1b7c114-fe56-532f-aed3-810e0e098407 | note | – – – – – – – – –
98191a27-ff62-5198-a5ba-7b0f14baf09b | note | RECORD OF CONFORMITY: This ITP signed off
d06504f8-e24a-51f6-8713-10aa49eb482e | note | – – – – – – – – –
d78d6168-31e8-5dd9-958a-e0f37ce070fa | note | IP
5b335cc3-cac9-57d8-aba2-46cdd3114dcc | note | – – – – – – – – –
f2415921-46a3-55cd-bd3d-2038f956f649 | note | RESPONSIBILITY: Fulton Hogan Engineer
9ac927b6-8dbf-59a6-88b1-4dec91881806 | note | – – – – – – – – –
99ea328e-2e9c-53a8-9747-f98fd8a6dbe1 | textbox | DATE:
2299c011-7089-4547-b70f-c9c0df64dbe4 | checkpoint | 2.2 Post & Foundations
9ebeca40-16b4-56bc-97e3-1aded9aaa985 | note | FREQUENCY: Prior to Start
232bb0ba-d54b-56dd-99cd-6fee0587adac | note | – – – – – – – – –
29129a5b-446d-5742-b911-c8f009805f6e | note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
032f2df3-38de-58d3-806a-b9968bbef758 | note | – – – – – – – – –
2ecf07cf-123b-5d42-bb18-e32f3d3d1a07 | note | REFERENCE DOCUMENTS: 714.06
71852fa9-c27c-5b2b-a68f-d434647a2d19 | note | – – – – – – – – –
ed81bc92-84ec-5fd9-a1d7-d4bea7f528b8 | note | INSPECTION/TEST METHOD: Visual inspection
58b4ba42-8887-57e9-a32a-8493f4af8525 | note | – – – – – – – – –
1d117c96-7774-5e9b-956d-0fc10c2cb2e1 | note | RECORD OF CONFORMITY: This ITP signed off
a2d9df63-8506-53bb-920f-560e833b3b29 | note | – – – – – – – – –
953c32e7-44bf-5d37-82f6-e455f009f674 | note | HP
7c06a83f-a867-5808-b558-d9c060272569 | note | – – – – – – – – –
651e367a-ef4b-569d-8e56-142b01e9ff83 | note | RESPONSIBILITY: Superintendent
71e78f97-b4f6-5f0e-a080-e4b8668f45ae | note | – – – – – – – – –
438e443f-37d7-52d9-b2d2-2f8a9c9ae880 | textbox | DATE:
1076672d-d849-4db0-9c46-2a6dfd824cd5 | signoff | AUTHORITY HOLDPOINT
38c0ca2b-7dc1-48a7-b7d1-7d02fcf61c46 | checkpoint | 2.3 Signage Install
e456a3c8-1c94-51f1-ad04-42236ef7214b | note | FREQUENCY: Each Sign
1b2bd97a-1d0d-57e9-b473-e4ceec7f3be8 | note | – – – – – – – – –
bfddd562-096d-54a1-86d0-b62c29ede6c7 | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
b9d7903c-e341-59b0-bdb0-42a9e4a2bafc | note | • Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
a17b4314-7982-55a9-bc18-1bb3e3293b4b | note | • Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
a60915b7-faa0-5a80-b1c0-6f1477a9163d | note | – – – – – – – – –
fe47f7f4-aba4-5523-b6c7-d44681abea34 | note | REFERENCE DOCUMENTS: AS 1742, TS 1313, Drawings
3009958d-2dc9-5b38-9cb5-e34e52aacb13 | note | – – – – – – – – –
a841963c-763b-5320-8b0b-c7606f5746f7 | note | INSPECTION/TEST METHOD: Verify
0f68af0a-b473-58cd-8c81-43c0fcbead0a | note | – – – – – – – – –
f7cc7dcd-ee0b-565f-a911-e164e96c7b7e | note | RECORD OF CONFORMITY: This ITP signed off
7920b2f6-d04a-5ab5-a571-afa8f240c222 | note | – – – – – – – – –
dd4bf362-a22b-5736-b14f-7a9b9fce96d6 | note | WP
a935395b-d980-5ce5-922f-9fbb969fecd4 | note | – – – – – – – – –
686c1aa1-15d9-59e6-af1f-53501b100d29 | note | RESPONSIBILITY: Fulton Hogan Engineer
26bf37c7-6ba3-506e-b521-6f0a03f2fbeb | note | – – – – – – – – –
b85cb1de-264a-53ca-811e-f877c3dba698 | textbox | DATE:
6ea0bb5e-5a66-4c46-9e37-884e3da9be8a | checkpoint | Final Inspection
e67bf3b0-e137-573a-87aa-64d8106cef87 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
18a8517b-e24d-5b52-9697-19d3f83ab7e7 | textbox | Print Name:
6a2d090e-f94e-5845-bc9e-92d960b2ee67 | textbox | Position:
f4fbdaf1-d319-58c3-8c7b-67322c13127b | textbox | Date:
efceb168-05aa-4a09-a9d1-559e866d6181 | checklist | FHC-ITP-018 - General Landscaping Rev0 | itp | FHC-ITP-018 - General Landscaping Rev0
ff20a1c2-f9c0-47cd-9983-c9a8b79c1b42 | section | 1 - Preliminary Works
e2fa0951-3417-42d4-9453-f98fd5b7ad54 | checkpoint | 1.1 Check for correct documentation
18272d6f-4b2f-57f4-b285-0de92db2a8e0 | note | FREQUENCY: Prior to commencing any activity
5e293202-7652-5e9f-b901-3dbc0de38591 | note | – – – – – – – – –
9c00a2ae-29c8-5983-9753-f26e77b3eca5 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
03abe0c1-f17e-5850-ba8b-96d829c09608 | note | – using the correct and complete set of drawings
c399a867-92b7-5463-ade2-c974803468a9 | note | – all drawings are the latest revision
8826f0fb-cd02-5df2-8543-f7f8c068bfba | note | – – – – – – – – –
c4f0ac51-ad84-52f7-9504-8f7e75131127 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8c6a7cba-4a13-5c32-a33e-b684c9123b4d | note | – – – – – – – – –
19ead67c-b383-5cfe-a35e-12ae6ac8d76b | note | INSPECTION/TEST METHOD: Visual inspection
559c9990-e0ea-532a-aab7-ef23b9bd0fda | note | – – – – – – – – –
2b41d8eb-1a30-5633-9e63-44a4c5a2d6ed | note | RECORD OF CONFORMITY: This ITP signed off
ad63a872-4127-519c-b47c-a2fe21b15af8 | note | – – – – – – – – –
1396e708-b8e4-5e52-bd94-8cfcf36ecc63 | note | HP*
a5ce1130-c1e4-5f69-9e5b-fc2f579c705a | note | – – – – – – – – –
16e89dc7-7d1d-580e-9182-1008a9f37af7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ad2ca04d-bee0-532f-94ec-0e92cd2cb685 | note | – – – – – – – – –
7bea79f3-bc62-51df-b359-e3b062b4ccdf | textbox | DATE:
72785dca-a55b-41b7-87e2-7c0521fc7911 | checkpoint | 1.2 Implementation of all measures and controls
b0fb9a20-89a1-5882-a363-a2b936ec0338 | note | FREQUENCY: Prior to commencing any activity
249b114e-2593-5d12-961a-dd27ef3c7e08 | note | – – – – – – – – –
533c6538-0f75-578c-8277-d4c059080671 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP
925ce371-981d-5318-aa06-81346e1229fb | note | – – – – – – – – –
abd4b203-4142-5c37-a2cf-a2155b74036f | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP
ef398a0c-65cc-5006-92ba-c5d96b7b1c3f | note | – – – – – – – – –
28e60070-ca6d-5fb2-805a-a17754ee6452 | note | INSPECTION/TEST METHOD: Visual Inspection
0bf36824-4f56-54ac-ac0e-89abe1736260 | note | – – – – – – – – –
c7387686-3bcb-53cd-a413-ea8a60948aae | note | RECORD OF CONFORMITY: This ITP signed off
dcb7bad6-2b77-51c4-84b1-08eec8f0aa1b | note | – – – – – – – – –
7f63fdab-eefc-5c6f-8a95-5bd3c64a40da | note | HP*
099e0705-03e4-5118-864a-9086310430b6 | note | – – – – – – – – –
4b00c685-40da-5864-9c3a-8bd40bccf361 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ab40af35-a1e2-538a-82c9-9f51768b3fdc | note | – – – – – – – – –
a83df609-41c8-5160-acf9-8a8796f83a3e | textbox | DATE:
530531d6-6b9a-4e78-ab5e-ee0fbc0546e6 | checkpoint | 1.3 Submissions and Records
c740f7d0-70b2-5f0f-8d99-5e5770f0cd5f | note | FREQUENCY: Prior to commencing any activity
22a44349-8282-5220-833e-a3920a8a9649 | note | – – – – – – – – –
b6e2b9ea-10fd-5276-a18a-9767b46df74e | note | ACCEPTANCE CRITERIA: The specified inspections, samples, records and certificates shall be made available or submitted to the Superintendent for acceptance prior to the commencement of associated work.
6fc60ace-f40c-5882-8f82-0f5bfd8d9ca9 | note | – – – – – – – – –
fcc4f601-d673-5966-97b2-b978d0d17df9 | note | REFERENCE DOCUMENTS: 720.03
984b9f7f-6c76-529c-8a10-b488faafd569 | note | – – – – – – – – –
8f4dae5f-91da-5f11-9b25-0dd9ec4910f8 | note | INSPECTION/TEST METHOD: Visual Inspection
2ff2443f-7a87-5576-8053-1ae461bac204 | note | – – – – – – – – –
1f76e46b-d6c6-5c29-9ac8-9ec6bc0699ff | note | RECORD OF CONFORMITY: This ITP signed off
a213641b-98e0-59ff-9c06-bed66eb0b66f | note | – – – – – – – – –
2caf22c0-9b9f-5397-af6e-40ad816b1fff | note | HP*
a8b8f9b3-951e-5556-9fc0-7afb8edd272c | note | – – – – – – – – –
4cd64093-7765-513c-9bb4-d374ec5c76d1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
aec2d2c8-d833-5fb7-9474-5f4d1851a6b2 | note | – – – – – – – – –
4913305e-f65b-58bb-be0b-a3b081c4fd82 | textbox | DATE:
d9c1d436-76da-4781-8049-5dbe14332974 | checkpoint | 1.4 Permits
c5eaa20a-7a3f-51a8-8dee-8328452c73bd | note | FREQUENCY: Prior to commencing any activity
efa94657-02c1-54fc-864e-250912788a74 | note | – – – – – – – – –
4c650c93-7caa-525a-b4cd-9b02c41dbb01 | note | ACCEPTANCE CRITERIA: The Contractor shall obtain all necessary permits and obtain approval from the Superintendent prior to the pruning or removal of local native vegetation.
359d5261-8ef8-50c7-99cc-4b942b47b5bd | note | – – – – – – – – –
0145914a-7649-5313-b27f-54e91c7c03b9 | note | INSPECTION/TEST METHOD: Visual Inspection
fd4f0581-6835-55c4-a113-f456379c5910 | note | – – – – – – – – –
d4856f48-25e4-5c80-9743-b5d38560920d | note | RECORD OF CONFORMITY: This ITP signed off
5a66b19d-72e2-53c4-8061-635ae1648bfa | note | – – – – – – – – –
1a1cae24-2dea-5a1d-b63a-68173eb4b8a1 | note | HP*
af353d76-29f6-52f8-9085-16e7a32fbb63 | note | – – – – – – – – –
279fbcc0-1150-5f49-9213-ae074f75a340 | note | RESPONSIBILITY: Site Engineer / Site Foreman
6d06c4f8-d2a0-52c8-ac58-de97284fedd9 | note | – – – – – – – – –
7a120aa7-c394-5a1e-8b89-2d81073329c6 | textbox | DATE:
470cd532-e7f1-4e72-a7e0-643c15748d48 | section | 2 - Construction Works
669055d3-56cd-4dd2-91f4-cd2491a9a4b7 | checkpoint | 2.1 Excavation Permit
636567d8-a616-5afe-8f1c-a8365022d1cc | note | FREQUENCY: Each lot
7f0ecc7c-6e3b-50f6-868b-ed8bcc74af84 | note | – – – – – – – – –
b5f4948c-0ecc-5c4d-9085-e2abf6500cf8 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
a2de1832-206f-5e9d-bff5-b8e7293999ce | note | • Plant and equipment shall be appropriate for the task.
ab245ea8-7ac5-5707-96af-454ed89ce736 | note | • Excavation operations shall not disturb areas outside the limit of excavation
68c5e22e-f805-5fc0-a494-57c6ea77b0bb | note | – – – – – – – – –
5788867e-4524-5b49-b900-d9c11bf75ee5 | note | REFERENCE DOCUMENTS: Excavation permit
5248b183-a159-584f-b258-7d52082c152e | note | – – – – – – – – –
881a41ea-1e88-5be9-be8e-ff23a07ff932 | note | INSPECTION/TEST METHOD: Verify
1aad9584-cace-5ce2-bd61-42f944019706 | note | – – – – – – – – –
9952dc9d-e872-56bd-9623-1d0cca3262f1 | note | RECORD OF CONFORMITY: This ITP Signed Off
6a17513a-448a-53fd-af6e-0cf9dbc4a9d5 | note | – – – – – – – – –
e08f3d61-58f6-5a2a-97f2-83857c3a000a | note | HP*
27cd689e-7d9d-5d05-ad6e-4dfa0e81236e | note | – – – – – – – – –
e4d1b818-ac64-5af3-aac0-b1c9d0e7ab44 | note | RESPONSIBILITY: Site Engineer
b86b5a63-7c1b-53a3-bb64-bd0c567bc132 | note | – – – – – – – – –
47c1cf77-61fd-5873-8cbb-b57a3612717d | textbox | DATE:
d2b20495-c06d-46a8-aaa1-5ebc12da9989 | checkpoint | 2.2 Setting out of landscape softworks
0ad603ac-f458-58a5-ac47-31e18c4bde4a | note | FREQUENCY: Each lot
9208e446-9ee4-5866-b965-3a8446905f10 | note | – – – – – – – – –
7eff1018-7d50-5508-9da4-bc1ff273b48d | note | ACCEPTANCE CRITERIA: The Contractor shall set out the location and shape of planting areas in accordance with the Landscape Drawings.
931bb5ae-122a-5027-8ea9-77acb7ecfbf7 | note | – – – – – – – – –
e00eb552-acfc-56a2-9ca7-a34c3b98a073 | note | REFERENCE DOCUMENTS: 720.06
e4d63e3b-dfe3-581e-ab47-ae1da8fd86a0 | note | – – – – – – – – –
4913ad4f-838a-56ad-98cf-348bd253bbbd | note | INSPECTION/TEST METHOD: Visual Inspection
df20eeb3-6ad1-54f3-8343-2a07468ef467 | note | – – – – – – – – –
4210b96c-ef6a-5eb8-9fc5-cd4624b3adde | note | RECORD OF CONFORMITY: This ITP signed off
ee033676-7ecf-5aef-a79a-829bb3786dea | note | – – – – – – – – –
18fe6da5-d0e3-547a-818f-a5f2df498aa6 | note | HP*
28b85fba-a35f-5fc6-a029-4807737a41c9 | note | – – – – – – – – –
b9c3cf75-3b05-54fe-98b1-a51dacfb1364 | note | RESPONSIBILITY: Site Engineer / Site Foreman
bd2de3c2-9ba8-5b67-801f-87a3b092da21 | note | – – – – – – – – –
6235e517-6fae-5c98-b687-7bd867212e2a | textbox | DATE:
688d1d83-5fc7-4e0e-b8e2-6e8a2b83794c | checkpoint | 2.3 Supply of Materials
b018a32d-ad5b-5940-8b63-3068d881aea2 | note | FREQUENCY: Each Lot
45ec6c7b-dd3d-5a16-8c93-d5ab295b24b3 | note | – – – – – – – – –
6af64ce3-a42f-5297-909c-d3a490913096 | note | ACCEPTANCE CRITERIA: All materials shall be supplied by the Contractor unless otherwise noted. If any materials are supplied by VicRoads, a joint inspection of the materials shall be made by the Contractor and the Superintendent following delivery of the materials to the site. The materials, if satisfactory, shall thereafter become the responsibility of the Contractor.
ac34e11f-caf9-5479-81ee-038a4c2be5b9 | note | – – – – – – – – –
4bb959fe-e2ac-5501-8912-431fa847479b | note | REFERENCE DOCUMENTS: 720.04
288f5978-8179-51c7-aa52-a3cf338ea58c | note | – – – – – – – – –
372b58c8-1595-5211-956b-ff8d26ca2732 | note | INSPECTION/TEST METHOD: Visual Inspection
23359d49-53e2-5656-b575-0846e854474c | note | – – – – – – – – –
652b4531-3b80-59d8-aaf9-4d7249a68b33 | note | RECORD OF CONFORMITY: This ITP signed off
dd7d3586-be54-51ff-a941-ad9bb9374ae3 | note | – – – – – – – – –
acc46347-56fb-533e-a0b5-32f38bc82006 | note | WP
86f874c9-cd61-515b-b9a4-dfd5b94c0ca0 | note | – – – – – – – – –
f08ec14f-7467-5912-b352-14495a525082 | note | RESPONSIBILITY: Site Engineer/ Superintendent
77ceefa6-f2ed-5204-9231-b07610d402ae | note | – – – – – – – – –
7d8238b5-e2a6-5e5a-8344-d73e95515ec0 | textbox | DATE:
1b4e59dc-ea75-4021-80f6-fab1fca1e4dd | checkpoint | 2.4 Pest and Weed Control
7df74b91-0c27-526b-837f-a7d128d6e315 | note | FREQUENCY: Each Lot
e2fba229-a337-514a-ba28-3f48ed9cf312 | note | – – – – – – – – –
0240e052-3218-54ab-b766-ef3b08821217 | note | ACCEPTANCE CRITERIA: Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing. Weed control shall be programmed and implemented to deplete the potential weed seed bank within the topsoil to be used in planting beds.
b29a94cf-3467-5651-ae1e-ad8ed21210e5 | note | – – – – – – – – –
a0d0cefb-de5d-5108-8012-a3634d58e53a | note | REFERENCE DOCUMENTS: 720.05
a2f177d3-e4a3-5119-be3b-95d71f1318a7 | note | – – – – – – – – –
7dd2ab54-fde8-5708-a5dc-0d33c3d6b269 | note | INSPECTION/TEST METHOD: Visual Inspection
cef67a6d-1e91-516a-8de4-0b3a0988cb3a | note | – – – – – – – – –
2e652cc1-7b42-526f-8f53-045f18c14948 | note | RECORD OF CONFORMITY: This ITP signed off
af630ead-f7dd-5169-94fe-94a85f33274a | note | – – – – – – – – –
2404cf32-957b-5a59-b3c1-812c6beec9da | note | HP*
c649d99a-8af6-5dc1-8a34-6580741c8d2d | note | – – – – – – – – –
7a0e6d2c-a8cf-587c-9ac9-70c5292d654f | note | RESPONSIBILITY: Site Engineer / Site Foreman
19d5b0f1-203c-5ff0-a788-c6427771798c | note | – – – – – – – – –
9f8c6982-09f8-5154-896a-16acbfa61f4d | textbox | DATE:
dac565a8-429c-49bc-8d79-b13937de4e76 | checkpoint | 2.4 Fertilisers
34b46795-334d-54a6-b459-15cbf132e971 | note | FREQUENCY: Each Lot
9944fc9b-2e52-50b9-ad96-c5b5f0796062 | note | – – – – – – – – –
968dadda-600b-5409-8b51-8af95221f611 | note | ACCEPTANCE CRITERIA: Fertilisers for planting areas and advanced trees shall be slow release with a 9‑12 month release period and suitable for the establishment of plant types, sizes and species specified in the plant schedule(s).
0522fedc-e826-5bbf-8bf0-fdceab74e21e | note | – – – – – – – – –
3ee587eb-1526-547d-b3cc-134e11ef3646 | note | REFERENCE DOCUMENTS: 720.04(f)
4237febd-6e9c-5e16-8969-a61d73e37a21 | note | – – – – – – – – –
a8683816-3af3-5e38-bb77-952735689430 | note | INSPECTION/TEST METHOD: Visual Inspection
6d6b838f-60d0-5f73-9831-0d4ec2b9808a | note | – – – – – – – – –
3c843c1b-ff62-5400-a8e7-4c2b829e265e | note | RECORD OF CONFORMITY: This ITP signed off
cd589701-b544-5c10-b752-43a85fb42d72 | note | – – – – – – – – –
e373bfbe-fc7f-5001-bec5-5fb7a5274905 | note | IP
273281a4-2bd6-50ee-96a3-28e10226feeb | note | – – – – – – – – –
62d3a8d2-6d9c-5bcf-9b5c-cea10435fffe | note | RESPONSIBILITY: Site Engineer / Site Foreman
5df8bdf0-d070-56fc-8b54-20b05d2323ab | note | – – – – – – – – –
5e453f03-9f31-57cd-b290-c565c471b94c | textbox | DATE:
dcbe7900-69c5-4762-bd85-9a3c84aefc57 | checkpoint | 2.5 Mulch
3a86738a-29e5-5ef9-86de-e468cbfa5b40 | note | FREQUENCY: Each Lot
cb50db0e-77ce-5629-8389-fb47d0cab86d | note | – – – – – – – – –
bae1697f-95d9-5abb-beb1-d5019b0a0ac9 | note | ACCEPTANCE CRITERIA: All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454.
651e5c69-7190-5f90-83c4-e36f7c3efab2 | note | – – – – – – – – –
9d760f49-4e00-5a54-8b79-bc9ef0a255d9 | note | REFERENCE DOCUMENTS: 720.04(h) AS4454
fb115aa1-b27e-5228-9c0e-477c226da168 | note | – – – – – – – – –
398e58be-f301-55aa-bb04-22b360d15600 | note | INSPECTION/TEST METHOD: Visual Inspection
3b2ebb7a-07e9-5d93-bf79-b13b4e42b750 | note | – – – – – – – – –
45bb7608-6c1e-5623-baf6-f0f992543a85 | note | RECORD OF CONFORMITY: This ITP signed off
23e410ae-2715-5f9c-817b-27fbabddea02 | note | – – – – – – – – –
9a6ab609-b22a-5576-8a48-150f05f680d8 | note | WP
4b7d171b-ac07-5b99-bc4a-b5ecfb4fca2f | note | – – – – – – – – –
f0b0d7ad-ca62-5ad0-b8cb-8999752843ff | note | RESPONSIBILITY: Site Engineer / Site Foreman
8c629c93-17d6-5661-949b-ce3e1c6acf3e | note | – – – – – – – – –
32a68ca8-b011-5a32-aafe-66700fa59b6d | textbox | DATE:
011d0b00-43e2-468d-b1ad-3046c8f1a451 | checkpoint | 2.6 Weed Control Mat and Erosion Control Mat
7e2fde18-01a3-5b8a-bb02-34891a396fd7 | note | FREQUENCY: Each Lot
0e30d694-410a-5ca3-a176-2640e6466ca9 | note | – – – – – – – – –
257a5e2c-ca4e-532b-a47b-1707041aae97 | note | ACCEPTANCE CRITERIA: The Contractor shall supply and install jute or approved equivalent, biodegradable, fire retardant weed and erosion control mat as indicated on the Drawings or as specified. Weed Control Mat shall be minimum 700 grams per square metre and Erosion Control Mat shall be 300 grams per square metre. The surface of the mat shall permit water infiltration.
375ea67e-69b5-5aa3-ac00-04fac0542145 | note | – – – – – – – – –
00f213cf-75d2-55a3-8951-94220f0f19c3 | note | REFERENCE DOCUMENTS: 720.04(i)
24e49a9b-04e7-5296-b013-2f72b79ee299 | note | – – – – – – – – –
8ed9ef30-71b0-564e-b403-c2dd8070af13 | note | INSPECTION/TEST METHOD: Visual Inspection
ae81667f-22cd-57d7-8e8d-1df7cfb71199 | note | – – – – – – – – –
daa6ac54-d5e8-52ea-8bec-933577548585 | note | RECORD OF CONFORMITY: This ITP signed off
8f9741ef-7b11-5516-841b-9d534b47f688 | note | – – – – – – – – –
53cea415-8a92-5425-a4af-2ea2a48ce5b2 | note | IP
62fb2c79-18be-5410-b504-288ac076c558 | note | – – – – – – – – –
5c5b4ad6-7d63-524e-bdd3-926e42168013 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0464cf16-e019-5b71-bcfe-2c1a437d864e | note | – – – – – – – – –
ab30735f-2375-5d5b-81c9-4bd15d158c3e | textbox | DATE:
375a9307-b2ee-4073-ae83-cf03c18dd618 | checkpoint | 2.7 Ripping
eee70b52-7cb2-5a3e-a634-ad8f71b9ef7b | note | FREQUENCY: Each Lot
fb5a122f-f180-5d24-8a32-f28c8f1a7952 | note | – – – – – – – – –
4bc42947-e085-557c-ac37-60c3f4d3ce79 | note | ACCEPTANCE CRITERIA: The Contractor shall make available each ripped planting area, individual tree planting and grassing area prior to mulching, planting or grassing. The Contractor shall not proceed until the Superintendent acknowledges requirements for ripping have been met. In areas where ripping is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
37202ed4-0bcf-5a23-8ae7-3016c559b03c | note | – – – – – – – – –
513df117-b8b6-5fcb-9cac-06bcc2427cb6 | note | REFERENCE DOCUMENTS: 720.07 (b)
b8692396-2e17-57bf-bea9-46350b9ea678 | note | – – – – – – – – –
3f88770f-7d20-5339-9abe-0d70f37c94cf | note | INSPECTION/TEST METHOD: Visual inspection
99757703-2fbc-5ddd-bf90-8b054c5de04b | note | – – – – – – – – –
07ab2d21-3add-5a91-8ac8-c9eb741605f5 | note | RECORD OF CONFORMITY: This ITP signed off
44c41856-6b2b-58d8-bd99-be3cd34abdc0 | note | – – – – – – – – –
db99b15b-1628-5f34-b895-d18df0073d50 | note | HP
e941b222-fdf9-50cc-bb11-95ef5fbcbdbf | note | – – – – – – – – –
335af895-6910-514b-8ce3-b44d379ca8a0 | note | RESPONSIBILITY: Site Engineer/Superintendent
969ad2f2-6e70-526f-99a3-dfcecddc795e | note | – – – – – – – – –
7f60b9f6-1b07-5da7-8cff-9c068d960acb | textbox | DATE:
761374a1-6e13-46cb-b497-6bc802b0d635 | signoff | AUTHORITY HOLDPOINT
926ae2da-b744-4242-a531-8e1a876b2c8d | checkpoint | 2.8 Topsoil Finished Surface Levels
19e92f74-4e58-5c27-b7f2-180a01b860a0 | note | FREQUENCY: Each Lot
f3d9ae19-ddee-5ab2-8268-d2ec4c76121d | note | – – – – – – – – –
602a2fba-03f3-52d6-86eb-20065bfab7d0 | note | ACCEPTANCE CRITERIA: The Contractor shall make available each ripped, topsoiled and cultivated planting area, individual tree planting and grassing area prior to mulching, planting or grassing. The Contractor shall not proceed until the Superintendent acknowledges requirements for topsoiling and cultivation have been met. In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
781f8f84-8f63-5821-8af6-49dc5599ac37 | note | – – – – – – – – –
c2d0e91a-6080-5387-b523-28b7b4a45448 | note | REFERENCE DOCUMENTS: 720.07 (e)
5e910457-4978-5373-a191-e87552e25e20 | note | – – – – – – – – –
3339d884-aadf-5497-826e-d028fc5e738a | note | INSPECTION/TEST METHOD: Visual inspection
4e4518d5-29a5-5cba-8a15-9a1bfbf70acb | note | – – – – – – – – –
c0b8e287-f4ac-58cb-9a8a-a3539bd8e477 | note | RECORD OF CONFORMITY: This ITP signed off
30dc6b7e-eb53-58ce-988a-69fa3f654027 | note | – – – – – – – – –
e1764038-f025-5d18-bff4-707dc86ac5d4 | note | HP
e3e99cc8-a525-558c-898d-e8d31efe7d08 | note | – – – – – – – – –
a7343417-a7b7-54f3-afa2-8bd1584fea3e | note | RESPONSIBILITY: Site Engineer/Superintendent
d6327e58-53b1-5342-bfaa-38b7c24d6a85 | note | – – – – – – – – –
283a7172-894e-5186-8654-da074870e65b | textbox | DATE:
034bea6e-20f9-40e2-869b-c6b7ae2947dd | signoff | AUTHORITY HOLDPOINT
6c0f8ee0-c50c-4467-bcc2-59f8efe65ac9 | checkpoint | Final Inspection
ac68725f-ca09-57c7-9774-77b10dd695f6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1caa3f68-1c53-5944-a3b2-8cf979dac45b | textbox | Print Name:
49464405-f6c6-537c-ae42-959337031d73 | textbox | Position:
1b1398fc-fe48-57c4-a64a-c07274560ae3 | textbox | Date:
8aaf6575-e4a1-4469-a4c5-f472a855846f | checklist | FHC-ITP-023 - Conduit, Pit & OCS Installation Rev1 | itp | FHC-ITP-023 - Conduit, Pit & OCS Installation Rev1
d938e43b-4565-4f0c-beb2-d0036883fe15 | section | 1 - Preliminary Works
a2692f12-21e6-4587-9362-87237c6b6834 | checkpoint | 1.1 Check for correct documentation
3d3d5c80-9a50-5624-a046-92c857679aff | note | FREQUENCY: Prior to commencing any activity
56aa97f4-b39d-5fbc-8b54-7c6dd6a43190 | note | – – – – – – – – –
c8cd1a62-8972-53f8-919a-5b07b0a66b04 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
708c5928-0fc9-5804-b78b-a4660c5a7930 | note | – using the correct and complete set of drawings
5c2956b8-26d0-5263-af9e-846055e4a8c9 | note | – all drawings are the latest revision
a7caf196-4037-5315-9384-286af124eef6 | note | – – – – – – – – –
05fad10f-2820-5127-b4f2-471e82fc178d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
53caedb7-cf8d-50b5-8e45-a18a64a069ee | note | – – – – – – – – –
c15886e2-2168-5396-bca6-3423fc7b399e | note | INSPECTION/TEST METHOD: Visual inspection
638f108e-31a3-5964-9b3d-82fef219a433 | note | – – – – – – – – –
5cd7da32-e5d0-5442-9a2e-fb25d9c20104 | note | RECORD OF CONFORMITY: This ITP signed off
2281d742-bea5-553c-81f7-a852b20c7925 | note | – – – – – – – – –
71679241-4d4c-56b5-96df-2cdb41e6256f | note | HP*
8e850072-6440-5c69-8a36-c25086da590e | note | – – – – – – – – –
e7f27845-d771-51ae-9cd1-648d279ea5ee | note | RESPONSIBILITY: Fulton Hogan Engineer
43a39eb5-58c9-5d9c-8ef1-610b4e839f3e | note | – – – – – – – – –
cf9d8f5d-2286-5b61-a63a-bcc7ff6cc660 | textbox | DATE:
5b6bc7ad-f75b-457a-8351-03788dcac769 | checkpoint | 1.2 Implementation of all measures and controls
e6817546-5cff-54aa-887c-0e8926de6f04 | note | FREQUENCY: Prior to commencing any activity
43624bcd-9c7c-5fac-bf38-9251c2a37f65 | note | – – – – – – – – –
04ae78fb-2029-5adc-b95f-78adfb045c6a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
5918f115-ed9b-5930-a57e-af0d3fabc797 | note | – – – – – – – – –
1f441c05-089c-589e-81ee-367c389fd964 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
c1122cc5-13a7-5886-8240-7137c7bada94 | note | – – – – – – – – –
bb935c61-48ab-52cb-be65-ec7b02af255f | note | INSPECTION/TEST METHOD: Visual Inspection
6a723798-c8ff-5342-9445-9a3cbe71bae2 | note | – – – – – – – – –
2ef4a2db-4aaf-5ea8-bd47-ceff7fdadc32 | note | RECORD OF CONFORMITY: This ITP signed off
0f38de2e-22d5-5ab9-b182-f14e4de04e5c | note | – – – – – – – – –
f2ebb82d-04f6-586a-b7a3-d7613eaf332a | note | HP*
dfcdb1b4-6437-514f-ae90-6b81db8d19ac | note | – – – – – – – – –
220ba8d7-818e-59bb-ae08-bfea1b2e221b | note | RESPONSIBILITY: Fulton Hogan Engineer
d16add69-a3a5-5900-8d74-669bcb264bcd | note | – – – – – – – – –
eb3d1aa8-35e0-57a5-aa72-130162e7beb1 | textbox | DATE:
b3f50c6e-2d6f-4854-904e-2c3510e6fdf9 | checkpoint | 1.3 Materials
9ed0b570-d252-526d-ad5e-9b35b0ba7c68 | note | FREQUENCY: Per Batch
df586ea5-79ad-50f2-9c53-56b86ddfdecd | note | – – – – – – – – –
f3124e3d-51f1-5484-873e-534bd9054d23 | note | ACCEPTANCE CRITERIA:
d2eca6cf-f61d-59d9-9874-0515f8e4cd90 | note | • Carpark Lighting A pit is to be installed adjacent to each lighting pole with 1 x 100mm HD conduit and 1 x 63mm conduit installed between pit and the point of supply. 2 x 32mm HD conduits are to be installed between the pit and the pole mounting base.
da61e833-697c-52e4-bcfe-96fe6999bfb2 | note | • Electrical supply conduit all conduits for underground mains shall be heavy duty 'Orange' underground category PVC pipe complying with the most recent issue of AS/NZS 3000 Australia/New Zealand Wiring Rules.
adca53d8-134b-524f-ac0c-d793e204dbc0 | note | • Communications conduit to be white 1C50 HD PVC conduits and 1C100 HD PVC conduits
0094fabf-068f-57f9-9b07-731a74a200e3 | note | • Camera mounting poles and structures shall meet AS47806.2 (2006) Section 5.4.1 (k)
5e4bbd49-c3c6-5741-86a5-d94a11282fe3 | note | • Cable pit lids shall be VicRoads type approved, impressed with 'VicRoads' and 'Electrical', 'Communication', 'Traffic signals" as appropriate as per VicRoads Standard Drawing TC-1220
bbef8651-04a6-51ef-80d4-dcd5341da572 | note | • All equipment labelling to comply with requirements of NIST-013.4
620d1e8e-b3d5-5cf3-9b58-7c9257ecd422 | note | • Cable pits shall be 435mm dia x 550mm deep, Type 43 plastic HDPE – Aco Cablemate cable pit with concrete lid or equivalent
71c4ebf7-31a8-5e9f-ac63-6fe3fac2f244 | note | – – – – – – – – –
e22a464c-4abd-5827-8414-887efee6a22f | note | REFERENCE DOCUMENTS: NIST-5031 3.2.2.5 (f), Drawings
8a044274-f763-59ed-b304-21e8d628f170 | note | – – – – – – – – –
1052ad00-d302-5884-aff1-4e9516f13946 | note | INSPECTION/TEST METHOD: Verify
60c98819-5686-527a-90ed-eb6f080d3bcb | note | – – – – – – – – –
9e5efed4-83dc-5242-bc9e-4b747370ac6f | note | RECORD OF CONFORMITY: This ITP signed
5ac00e02-34b7-5265-8c55-9743e7749421 | note | – – – – – – – – –
79e14b33-2d19-5cfe-bf0f-7a97dfeb26b2 | note | HP*
71c63833-35a2-5c69-87c5-a19a7cff3863 | note | – – – – – – – – –
9c02bd02-1eb6-5319-858a-4ebc6ba478a0 | note | RESPONSIBILITY: Fulton Hogan Engineer, Electrical Subcontractor, Vline representative
0f5e00a5-8b78-5fc1-97b3-5c004a3ed332 | note | – – – – – – – – –
6bd82fca-025a-5b75-878f-d6fcb1012197 | textbox | DATE:
6f68fc16-2f33-4f2c-ace3-8d9a5c1ec8a1 | section | 2 - Construction Works
4df94196-34a4-48de-84c0-1cd574891fda | checkpoint | 2.1 Survey set-out
11d73252-8f52-5345-9cfc-5fe55fe3bf9f | note | FREQUENCY: As required
fbb41fb5-5aca-5997-844a-c37854173eb0 | note | – – – – – – – – –
819f5bb9-d16b-501a-ade2-29b6fb792331 | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
ded4b3dc-fa81-523b-948e-74b5621d3a9d | note | – – – – – – – – –
619700d4-8f6c-5621-a0fa-f5862dab6d9e | note | REFERENCE DOCUMENTS: Work procedure, Drawings
7058bf53-f9ce-5286-96a7-9164dfc0d78b | note | – – – – – – – – –
80bccae2-4c12-5e3d-8a05-7ac42ee0d02c | note | INSPECTION/TEST METHOD: Verify
d1c61ffe-7b6b-5106-820a-667d304c43a5 | note | – – – – – – – – –
d3c22dd2-2e07-57f4-a8e4-d71bf3674583 | note | RECORD OF CONFORMITY: This ITP signed
9c540ae7-ce50-53ea-a5dd-9251549783a4 | note | – – – – – – – – –
2b60e7ad-ba83-59fe-9a91-609c97747eb2 | note | HP*
ce6d30fe-f423-5bb5-b22c-07647ae5938e | note | – – – – – – – – –
dd2e1e8a-64b3-5fbd-a910-faf60ce42b14 | note | RESPONSIBILITY: Fulton Hogan Engineer
6f862b00-6374-5adc-a5ec-b0ed69d3e3a9 | note | – – – – – – – – –
972cd9c5-d90a-5862-bdc7-fd9a82119cb1 | textbox | DATE:
a859cbe7-03d2-47c3-befd-b102726c7fda | checkpoint | 2.2 Excavation/Boring & Trenching
65d49897-6183-55d1-b36a-4a6af2773b4c | note | FREQUENCY: Prior to Backfill
f4a7ba14-e204-52c2-9aa8-7df41a76d6b4 | note | – – – – – – – – –
a849fc92-54cd-56ca-a3b4-723d53344129 | note | ACCEPTANCE CRITERIA: Trenches shall be excavated to a depth required to achieve the specified depth of cover and drainage slope, plus an over-excavation of approximately 50 mm to allow for bedding sand. The width of trenches shall be as required to fit all the conduits and pipes for services sharing the trench with specified separations, plus a further 50 mm minimum clearance from the outermost pipes or conduits.
2f567053-8086-51ee-85ba-cc261bc483b7 | note | • Where trenches are excavated across roadways, car parks or paved areas, the Electrical Contractor shall backfill the trench with 20mm of Class 3 crushed rock. The crushed rock shall be placed in layers not exceeding 150mm finished depth and compacted to a minimum of 95% of standard density. The backfilling shall extend for a minimum of 1.0m outside all paved areas and shall be subject to the supervision of the V/Line delegated representative.
268b92be-387e-50b4-aa1f-1a640ce8f839 | note | – – – – – – – – –
911c0106-79ea-50cd-8a34-e7ea203298bf | note | REFERENCE DOCUMENTS: L1-CHE-STD-077 Sect 6.10.6
51c365c3-e578-5d9e-a26c-78b7ae56272d | note | – – – – – – – – –
307e34a5-15a5-56c9-ac2c-4efcc99d7ffa | note | INSPECTION/TEST METHOD: Verify
d9f1de37-6f91-5875-95a7-144dc8426664 | note | – – – – – – – – –
7499e5e0-807a-508b-ad65-d95d16ccdcda | note | RECORD OF CONFORMITY: This ITP signed
8b006422-c0cb-5d34-9646-b7e54ee1fe7a | note | – – – – – – – – –
e0063011-ef53-52fc-b327-c533c13ee8a4 | note | HP
fac46bc9-554e-59da-b8cc-5e5d88d672b9 | note | – – – – – – – – –
b9afb1e1-967d-5069-b0b1-8bdfc5001e3c | note | RESPONSIBILITY: Fulton Hogan Engineer
15a26431-5b6c-5216-b078-882ee69db480 | note | – – – – – – – – –
2cf5bd59-d4b5-5c01-8510-3ffb0956d16e | textbox | DATE:
9ed860dc-164d-4c0b-9b48-c84edee170de | signoff | AUTHORITY HOLDPOINT
452f80eb-84a6-4a4c-b062-f81c7e2e3e34 | checkpoint | 2.3 Installation of Pit and Conduits
ec1d176b-4046-50cc-a3de-dff379c407d4 | note | FREQUENCY: Each Lot
62cbfbcb-9a42-53f9-a8fc-92accb845cc2 | note | – – – – – – – – –
10cdfd46-497f-53aa-b2bf-a93d2ba82519 | note | ACCEPTANCE CRITERIA: Underground conduits shall have a minimum 450mm cover if around the site but away from the track corridor, should only be in the non-trafficable areas. If exposed to traffic, the depth should be 650mm.
f5ec7e40-04f2-55d8-9d33-b00adcff17ba | note | • Upon installation conduits shall be cleaned and tested using a mandrel of at least 90% of the conduit inner diameter and length three times the inner diameter.
81e653e2-a287-521f-9cfa-97d801d00b07 | note | • Multiple conduit entry penetration holes on a pit wall shall be spaced at least 50 mm apart in horizontal and vertical planes
a7264fbf-dfa8-5d76-9152-92bea2dd009f | note | – – – – – – – – –
469d464b-a99a-5e24-8145-dda416f446ec | note | REFERENCE DOCUMENTS: NIST-013.3 Sect 4.2, L1-CHE-STD-077 Sect 6.9
f8ad8b7c-a0ea-599f-8daf-c31768176fa7 | note | – – – – – – – – –
01646e53-9038-59e7-b06c-9fb3f893ffdd | note | INSPECTION/TEST METHOD: Verify
81a435eb-1680-577f-9a93-454a1568d1a0 | note | – – – – – – – – –
fbf604d8-94d7-5b5e-9db0-3030cb98ec7d | note | RECORD OF CONFORMITY: This ITP signed WP
4a23442d-4656-55af-8a9c-4d3253afe793 | note | – – – – – – – – –
f06eb101-0868-5a7c-9ee3-43ad484b2f08 | note | IP
68a455b5-38a3-5e60-81e6-3ad6efe3a76b | note | – – – – – – – – –
f2f63d24-2f51-53b7-b0bb-54bdc71b6b3a | note | RESPONSIBILITY: Fulton Hogan Engineer
0a338fea-0938-5d13-b305-4f66c0dc7823 | note | – – – – – – – – –
3863ef32-ecf8-5c4d-9ddb-2df36b3c19f7 | textbox | DATE:
f2b02ff6-e967-415f-ac63-8e04c47c6011 | checkpoint | 2.4 Back Fill of Trenches (Trafficable)
0f7bf268-4587-503e-8a70-a7aa96deed5a | note | FREQUENCY: Each Lot
7b1f0558-4006-5111-865e-b13164ee695c | note | – – – – – – – – –
372f6a7d-fb82-5b5c-977c-a6c4b6e5736a | note | ACCEPTANCE CRITERIA:
1b1198fc-650e-5db8-9849-45273189a048 | note | • Bedding: Graded recyclable glass in accordance with MTM standard L1-CHE-SPE-313
694e1b67-a754-5e65-907b-ed8ee0dcdb9c | note | • Backfill: VicRoads 20mm class two crushed concrete base compacted to 95% of standard density in 150mm thick layers
e07a473d-1637-557e-a941-b548a314daee | note | – – – – – – – – –
abf549a9-d109-58c3-9a14-615eb7bfafe4 | note | REFERENCE DOCUMENTS: NIST-5031, L1-CHE-SPE-313, MRP-708-C-AUR-DRG-20-TNT-CLT-0810
de3a9930-96d6-58a5-a3c0-5aca9f4d8e62 | note | – – – – – – – – –
cb038940-5f94-5efa-9e59-b1b4b1d88149 | note | INSPECTION/TEST METHOD: Verify
8a625af0-8f14-5ee0-ac6d-6754c6ccbeae | note | – – – – – – – – –
f80c71a0-96aa-57d6-bdef-3d397fe1b7f9 | note | RECORD OF CONFORMITY: This ITP signed
c75d9647-99c8-5dc8-a130-912faebbdf42 | note | – – – – – – – – –
f9e156b1-741c-545d-93b4-18681a317091 | note | WP/IP
edf7cbd5-4f9b-509c-a97f-946fbb633b72 | note | – – – – – – – – –
dd7436b1-7e5d-5f8d-a5b7-1014c9840f0d | note | RESPONSIBILITY: Fulton Hogan Engineer
09b84ce5-7521-5e86-b885-8b4ef1dae001 | note | – – – – – – – – –
39b55c4b-644b-5965-aeca-ad790caee25d | textbox | DATE:
29882b57-af82-4e92-a19d-f5381bde94ea | checkpoint | 2.5 Installation of Draw Cords
22640a98-2290-5fce-93bb-3967aea59be6 | note | FREQUENCY: Each Lot
8047f197-6c27-5c8a-858f-9970bbfebc32 | note | – – – – – – – – –
469f7e85-1e4a-53c1-ad5b-5db7ab37d5bb | note | ACCEPTANCE CRITERIA: A draw wire of 6mm polypropylene blue/yellow rope shall be placed in each pipe and suitably anchored at each end. Pipe ends shall be sealed using pipe end caps or an approved equivalent to prevent the ingress of dirt or sludge into the pipes.
23463575-fc82-5b4a-9493-8dba313657dd | note | – – – – – – – – –
445c598f-4828-55ca-8d60-a39efe05a558 | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.12(d)
5a75c83a-5243-5bdd-b3aa-7ce9588d092e | note | – – – – – – – – –
64837f27-a6fc-52b8-9195-8c1e0fe8c662 | note | INSPECTION/TEST METHOD: Verify
2daba89a-f35b-59b0-8393-30768b9b527c | note | – – – – – – – – –
0438095c-3f60-5713-a034-319c8bb76ef0 | note | RECORD OF CONFORMITY: This ITP signed
27ba2918-82d0-54c0-8605-f5ffdc163d77 | note | – – – – – – – – –
2dd4f515-2304-5dee-bbdc-6d910d8d4c2a | note | IP
eb41fb0e-ed79-5b95-b00d-aea561b25772 | note | – – – – – – – – –
4802adea-7ac7-5eca-b54b-98a874c3ff16 | note | RESPONSIBILITY: Fulton Hogan Engineer
aa35a51c-0d80-5131-99f7-8a4823c02810 | note | – – – – – – – – –
00b7ea6d-b830-51c4-a829-5a9f8fa9efda | textbox | DATE:
98e1f791-d9b3-4219-b703-2cd134419425 | checkpoint | 2.6 Installation of Marker Tape
7a8b4184-35e1-506b-aa86-7a93bcc686ef | note | FREQUENCY: Each Lot
e7992ecd-203b-5268-9cf6-b03a9b732925 | note | – – – – – – – – –
df7d9e01-1580-50cd-8ecd-ad30ad079a35 | note | ACCEPTANCE CRITERIA: A 150 mm wide orange coloured PVC marker tape with the words “DANGER BURIED CABLES” shall be installed in all trenches at 300 mm below ground level except where cables are permitted in shallow trenches due to rock. In this case the depth of the marker tape shall be at the discretion of the Infrastructure Manager.
e1978151-e518-5333-be93-87fdbb50da04 | note | – – – – – – – – –
9116f2a6-40b4-542b-b3af-35a5e73ff710 | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.11.1
7999e916-9e77-5c6f-a8df-83b95808b156 | note | – – – – – – – – –
41056d76-f46a-5cf2-bf63-819a9d77695d | note | INSPECTION/TEST METHOD: Verify
0ebcb908-436e-5a62-89c7-aa02d3eccad2 | note | – – – – – – – – –
c8898386-5574-580a-85e6-a3b9296cfc69 | note | RECORD OF CONFORMITY: This ITP signed
4ab96c9b-553e-5ce2-8b82-bf7b0978348f | note | – – – – – – – – –
111ad1ca-81c8-5917-8053-06efd45e3b02 | note | IP
5b2f85a9-8df5-57d8-ac17-91e8478388ed | note | – – – – – – – – –
e4e9720e-a961-5323-9a55-62a10b3ab01f | note | RESPONSIBILITY: Fulton Hogan Engineer
a38f585d-4620-5fac-9614-a40172f29b02 | note | – – – – – – – – –
801685e0-baeb-52b4-a340-35e78ce00350 | textbox | DATE:
140e7dd1-022b-41ca-ac64-3370f79ce064 | checkpoint | 2.7 Cable Pits & Pit Lids
dea11f25-dffc-56f7-bcf5-5e07df23ce6b | note | FREQUENCY: Each Lot
c35fdb6c-b718-5027-a161-0d5c6c5df8bd | note | – – – – – – – – –
cd55995e-a42b-51e5-bc79-66fc1c9ef92a | note | ACCEPTANCE CRITERIA:
c989e47f-3807-5de6-b67a-d02af13f6489 | note | • Cable pits constructed and installed as per drawings
63e5f1df-8d79-53d0-9e8f-1b5411f2042c | note | • Pits shall be placed at each horizontal change in direction or at spacing no greater than 100m
f470ca4a-32f3-5970-a675-fa43ab6e7fdb | note | • Seperate pits shall be used for power conduits (orange) and communications (white).
c0a2038f-833b-5fa7-8bd4-191237362c42 | note | – – – – – – – – –
040998a0-11b4-577f-b1e9-f46d335fa107 | note | REFERENCE DOCUMENTS: OCS Drawing Package
b093efb8-9e42-5dc1-b973-e72bbed6e0ba | note | – – – – – – – – –
8d6193d4-1a1d-574f-9ed5-1d06ade9a2e7 | note | INSPECTION/TEST METHOD: Verify
b0c879ea-5aeb-5a15-82d1-580dfede7ab4 | note | – – – – – – – – –
00dcaebd-6de1-5c78-bd9b-3b98d0ddcefc | note | RECORD OF CONFORMITY: This ITP signed
53be3e55-7300-5c6d-8496-35254c20198d | note | – – – – – – – – –
0c59bcd1-45ad-52cb-bbd0-64ff9ec6813c | note | IP
9cb7c6cc-d60c-5573-881d-9faf8d97b990 | note | – – – – – – – – –
57f9d7c4-c72c-5e49-a4c5-05ba2b98f5c4 | note | RESPONSIBILITY: Fulton Hogan Engineer
adb6d222-eb28-5048-aa37-0ab329e14f50 | note | – – – – – – – – –
0d7200f3-b62c-5b3e-8d66-29c0316ffde2 | textbox | DATE:
6ae7168b-69a5-47f6-8fc2-9b246bf42f9b | section | 3 - Completion
55ec55ab-3ae5-42b2-97c4-f7474055f813 | checkpoint | 3.1 Cleaning of Site
b97fc449-5090-530d-a2a3-7753755ca209 | note | FREQUENCY: Each Lot
82901f64-c998-52be-821a-3141ec59ddd1 | note | – – – – – – – – –
f8f1f49f-0dcb-5f5e-af53-96b1e0f3c8e5 | note | ACCEPTANCE CRITERIA: All obselete cabling to be removed during installation and disposed of appropriately. Upon removal of all redundant signalling equipment; the site shall be cleared of all project scrap and associated rubbish.
be3ec934-20fd-5eea-aa33-5494e6536ac4 | note | – – – – – – – – –
51576848-902f-54b5-9b9e-42139214657f | note | REFERENCE DOCUMENTS: NIST-012.2 Sect 23
c82ee209-56c4-5177-9cf0-c76522fde233 | note | – – – – – – – – –
ad8bf034-05e4-58bb-90d5-0567b21203b0 | note | INSPECTION/TEST METHOD: Visual inspection
d438e2de-cdc8-506f-a926-6f69ed79da6f | note | – – – – – – – – –
3b8ca024-cbe6-5701-a13f-491b286d0bc0 | note | RECORD OF CONFORMITY: This ITP signed
12bf0715-18b0-52d8-b8f3-4a6c6b48cd49 | note | – – – – – – – – –
e707a024-bbef-5335-8a3a-aa02f967b2cf | note | IP
038a38b6-7931-5da1-8c55-7cb3d45ab071 | note | – – – – – – – – –
11dd937d-1160-57c6-ba69-10516bd82ee0 | note | RESPONSIBILITY: Fulton Hogan Engineer
32733bb4-2265-5d45-9030-693826b9b34e | note | – – – – – – – – –
f07e1c3f-e0b5-57ba-8d9d-a12a12584ce5 | textbox | DATE:
4623e14e-e8e9-42e4-b6ec-08489227de4d | checkpoint | 3.2 Recording/As Built
9b9b8039-76d4-5862-9a76-c3aa4323df72 | note | FREQUENCY: Each Lot
1631db43-edac-5b2d-9a87-78d65778261d | note | – – – – – – – – –
602a93d6-85d8-59bc-a1d0-73cb6adea9d7 | note | ACCEPTANCE CRITERIA: As-built drawings will be completed by the Contractor based upon the installed system by a process of editing the approved ‘for construction’ drawings.
a12b4031-f765-5654-853c-04e3a578cd15 | note | – – – – – – – – –
967ed97d-45de-5513-bcce-53a195b5f83c | note | REFERENCE DOCUMENTS: NIST-013.3 Sect 5.1.3
1b85ee8c-fc97-521b-a614-d4e7922fdfd6 | note | – – – – – – – – –
647a8625-8304-5631-9279-ecca49b623d0 | note | INSPECTION/TEST METHOD: Verify
67ed3186-3bbd-56be-ad88-8416ab29228c | note | – – – – – – – – –
4a173c41-7804-5cc3-b0b3-fb77b5eede50 | note | RECORD OF CONFORMITY: This ITP signed, As Built Drawing
6934bfe0-c35f-50f6-baaf-add36605eb35 | note | – – – – – – – – –
139272a0-d3e1-559d-9be9-166c82019759 | note | IP
0976288b-6a30-546d-bf6e-71f3031fe1e0 | note | – – – – – – – – –
02843c3c-dc66-5fdb-99fd-9486ff1dd002 | note | RESPONSIBILITY: Fulton Hogan Engineer
48992625-df0a-5e92-be83-5a2fc15bdf38 | note | – – – – – – – – –
b9558d94-e18f-526d-9e02-b250f8dca459 | textbox | DATE:
097982d7-67d4-433e-8b08-ac17e8cc7bff | checkpoint | 3.3 Commisioning
535240e8-4377-5556-8c7d-330e5c24ce46 | note | FREQUENCY: Each Lot
20d613d9-ad8d-5d37-b109-a8243c6130a0 | note | – – – – – – – – –
f346deab-da6f-5e61-bef7-942e21e12c91 | note | ACCEPTANCE CRITERIA: Commisioning to be checked against V/Line checklist. For OCS Only
8d0fcbbc-12e0-5178-9ac2-3730a97018fa | note | – – – – – – – – –
816ea823-8f04-50e8-9b37-6673396a3a09 | note | REFERENCE DOCUMENTS: V/Line Commisioning Checklist
e781056e-4913-5deb-8962-e41dca16dc28 | note | – – – – – – – – –
ba68a5f2-595d-521e-b9b3-f43b4cfa0fa4 | note | INSPECTION/TEST METHOD: Verify
5888d2a8-cbb0-5743-8d96-51e4c1d76bdf | note | – – – – – – – – –
46f9c1e6-1ada-5bef-9c49-18110647f712 | note | RECORD OF CONFORMITY: This ITP signed, V/Line Checklist signed
380d6794-76a2-51be-84f6-ee24726bae96 | note | – – – – – – – – –
fe59133a-ec14-529d-b033-0bf4e45cdf7e | note | WP/TP
7c3f95d8-b5e7-593f-bf56-add53e8e5e1c | note | – – – – – – – – –
51aad85a-b28b-5ce0-8f44-514f8f6950b2 | note | RESPONSIBILITY: Fulton Hogan Engineer
e7266f20-09fe-550f-9b08-fb10a1d6ace4 | note | – – – – – – – – –
14c28eb2-4eff-5870-8d88-e289b2df945b | textbox | DATE:
e4e24f4e-bc6f-41b9-a86c-d0e603cae69a | checkpoint | Final Inspection
8f702ff7-6f3f-55b0-a5b1-253a2bb6ae94 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
14a7186d-10ca-56e1-82b9-2ab3dd66b0d1 | textbox | Print Name:
8bf21596-8e53-5d29-8cd0-98eb861a66d5 | textbox | Position:
fcaf7c67-9f25-5b8a-9f5e-86068ab630c5 | textbox | Date:
73658154-e093-4b21-b7d2-57cf923046f2 | checklist | FHC-ITP-025 - Structural Concrete Construction Rev1 | itp | FHC-ITP-025 - Structural Concrete Construction Rev1
f55194cd-17d8-40e0-b23f-856cf69fd81b | section | 1 - Design and Submissions
9e462b34-6b71-4f08-b2d7-b966e30e19ab | checkpoint | 1.1 Check for correct documentation
66246b81-2f6d-546d-954c-a569c492970b | note | FREQUENCY: Prior to commencing any activity
69f3f861-dfc2-5bbe-915d-664d913795ba | note | – – – – – – – – –
beb7d4bf-4451-500e-8a9d-e2965d34cbf2 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
9ef4e246-9b04-5866-ac45-1c6f5845c4b7 | note | – using the correct and complete set of drawings
702a961a-dfed-5025-8d5b-7608c098df3f | note | – all drawings are the latest revision
ea56b494-e957-5a7b-bf16-0542b36d8c73 | note | – – – – – – – – –
ba42ee41-f754-5891-87d7-d3505cdca931 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
dd8555e9-6adf-5eea-8314-d3c372c9ac44 | note | – – – – – – – – –
1b947818-8ca3-5068-9fde-f7363d78711b | note | INSPECTION/TEST METHOD: Visual inspection
42228556-169f-5070-9b65-a08f05998c9a | note | – – – – – – – – –
1b04a167-0e3a-573d-bcc0-229afce158d9 | note | RECORD OF CONFORMITY: This ITP signed
30516a72-4b09-516c-b046-0cb756721f35 | note | – – – – – – – – –
ee1ab8df-dab1-5839-960a-30073a5b1473 | note | HP*
3fe89a70-0894-5bb1-9ffd-0a8a967f7ab3 | note | – – – – – – – – –
6f845787-d7ad-59b9-960e-d4ad14a9f42c | note | RESPONSIBILITY: Fulton Hogan Engineer
e5d73f23-e210-5f20-a83f-25c76dab4bfc | note | – – – – – – – – –
599a4ff8-5896-532d-8a0a-5a812a722d22 | textbox | DATE:
e42d885b-a9e2-47cc-a15c-d4b8f266fff4 | checkpoint | 1.2 Implementation of all measures and controls
90976d03-23d7-5b77-a132-d52965c8b16d | note | FREQUENCY: Prior to commencing any activity
3b6efd12-509f-5182-964e-f4de4ef1e0f9 | note | – – – – – – – – –
20a849bd-89f9-5c67-beb1-6fd73a32eb87 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
d36bdccd-04be-5681-a8ab-b3ee3f731327 | note | – – – – – – – – –
a232397a-e21e-5fa8-8d5e-a4645d35eac4 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
a60f23d0-2c0d-503a-a634-6c7176e5602f | note | – – – – – – – – –
97d4fb96-d81e-5583-b079-5d3b880ab063 | note | INSPECTION/TEST METHOD: Visual Inspection
696e124f-53cd-52d2-85cb-b0918382ebb7 | note | – – – – – – – – –
422ff4eb-1bd9-53a6-a856-a23f10d6ed9f | note | RECORD OF CONFORMITY: This ITP signed
092cadb6-e0f7-5601-8b2a-f0ba8f3dd47e | note | – – – – – – – – –
75de48e1-7349-5f8e-ad6a-43a0f81ac750 | note | HP*
f573d012-eb62-5fe6-abf7-0788b9331e74 | note | – – – – – – – – –
5642554c-20e8-52f6-aef7-130af9af603d | note | RESPONSIBILITY: Fulton Hogan Engineer
da0f66b5-77d8-578f-99b4-c1cfcea9bdc0 | note | – – – – – – – – –
7be6f700-bd42-5e72-83ab-7349e471c225 | textbox | DATE:
e57b7847-ce4a-437c-ba06-55e5b32d48e0 | checkpoint | 1.3 Approval of mix design
e66ddfed-8de7-5b0c-9712-0eb2afe75d4b | note | FREQUENCY: Prior to the first concrete pour
562f0fbe-132a-5160-9ba3-a7a5ff9be6e2 | note | – – – – – – – – –
f25fa072-8791-54e6-82b6-e787260b197c | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
6633d0f0-d0db-5719-a7f6-c88a8ff412c0 | note | – – – – – – – – –
3230dc71-847c-592c-9a2c-aa6cc35ff567 | note | REFERENCE DOCUMENTS: 610.07
3ac363af-4667-5d77-b850-d7e296f8ee6c | note | – – – – – – – – –
06a2e6d6-db46-54f1-90f1-3ad20d0d2cbb | note | INSPECTION/TEST METHOD: Verify
25097b28-3024-5b8b-87c1-f0b92339ec8d | note | – – – – – – – – –
1d785122-ad26-57c9-85c9-467afca929a8 | note | RECORD OF CONFORMITY: This ITP signed
dedd5842-a9c3-551d-b675-4393449e2c6b | note | – – – – – – – – –
ab50f81f-171a-5236-b454-be33b88d2cd8 | note | IP
b557f106-a01c-5ee5-9920-f30b1808252b | note | – – – – – – – – –
9b3f1e57-e594-5fb1-8c25-2b52cabe25fa | note | RESPONSIBILITY: Fulton Hogan Engineer
d2c6cdfd-2510-5398-b9f5-36306f008b48 | note | – – – – – – – – –
6f4a8b0c-0c53-55ae-b0dd-7b08bdcc8195 | textbox | DATE:
982d2613-3b70-4a9b-af99-88778250426b | checkpoint | 1.4 Reinforcement schedule
0304f9ae-947b-58ba-a5d4-b953d02adfae | note | FREQUENCY: Prior to concrete pour
881a73f3-7b54-5747-9874-418bc07e0e58 | note | – – – – – – – – –
378e9bb5-0830-5266-9108-4ce322486f9d | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
c3d7ff61-d35b-5aaa-aeaa-114db754265f | note | – – – – – – – – –
10f5413e-5c71-5649-9a3d-3d5c6f4ffd16 | note | REFERENCE DOCUMENTS: 611.04
b58bc63f-7bf0-53dc-952d-e1110fc3fcd4 | note | – – – – – – – – –
e6480d23-9d9b-56fc-9118-8ce873231aa8 | note | INSPECTION/TEST METHOD: Verify
3e7b8f2d-eee5-5721-b4fc-30b69bce81f4 | note | – – – – – – – – –
248a8af7-d01f-5582-a2f3-ccc48742c158 | note | RECORD OF CONFORMITY: This ITP signed
ae86b6c3-7fa5-5d7b-bb1f-513613245e02 | note | – – – – – – – – –
f1720b0c-8f39-5704-ad5a-1136cb5e6c35 | note | IP
eac4b8fc-5a52-54b0-9adb-081cb9466ca0 | note | – – – – – – – – –
56126ef0-8041-505b-9b77-1caffe6cf31a | note | RESPONSIBILITY: Fulton Hogan Engineer
bf9a5b59-13a9-5d7c-88e9-237f9eddaf44 | note | – – – – – – – – –
5a9c3add-2007-54d5-8e94-ce06bea93a0d | textbox | DATE:
e39e26c9-38a2-407f-a351-a8b186507ecf | section | 2 - Construction/Erection of Formwork
ebd9b7f3-9e73-4bd0-a4d2-83f510354083 | checkpoint | 2.1 Excavation
d5e6da50-7f0b-54ce-8750-63cc57e5e2b0 | note | FREQUENCY: Prior to concrete pour
3111b3b8-d994-5bc1-9bc5-fd3233460ce2 | note | – – – – – – – – –
18d0d8c1-8488-5b82-860d-ec31659956fc | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
99a29efc-00ef-50db-910c-a0b2896f2fab | note | – – – – – – – – –
6b4b5964-b410-50ad-b91a-882c1364da47 | note | REFERENCE DOCUMENTS: Contract Drawings
31bbf522-f5a1-5717-a62a-bba9c33ed910 | note | – – – – – – – – –
0b245a77-bc69-5bc3-a4b0-8d578958d1a6 | note | INSPECTION/TEST METHOD: Inspect
422f654d-c640-56f4-bce0-54c18493e8f5 | note | – – – – – – – – –
a0d0cf98-4cd4-5f0c-b7c3-6dda850fd226 | note | RECORD OF CONFORMITY: This ITP signed
2ff09ba3-254f-52e6-a10a-c960cb88345c | note | – – – – – – – – –
c561ab25-22fa-5050-b7ea-17016f155bb8 | note | IP
2448d3e6-a01c-5853-b30e-c8cba2677ae5 | note | – – – – – – – – –
8cd119e1-13ba-585c-9ad2-6173cfc015dc | note | RESPONSIBILITY: Fulton Hogan Engineer
35491a31-d57e-53c6-8237-765ca6ed9294 | note | – – – – – – – – –
3f8add0b-6831-57cd-85df-1c9cf638776c | textbox | DATE:
18dbd03d-57d6-486d-a75a-5157ceb7c33f | checkpoint | 2.2 Construction Methodology
cb65d501-ece1-5e34-a2e3-ae3c059c32fd | note | FREQUENCY: Prior to erection
dc62d41e-06d7-5906-adcf-ae9168e61b22 | note | – – – – – – – – –
768fd11a-96d3-575d-92b4-87a90c9385f1 | note | ACCEPTANCE CRITERIA: Constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
51330d2f-e4db-5713-8721-7b89e9f399e2 | note | – – – – – – – – –
1af9eaf1-ba2c-5393-b47e-9680092517d9 | note | REFERENCE DOCUMENTS: 614.04, 614.06
962b1a5d-b938-5039-9610-b65effff638d | note | – – – – – – – – –
5845488e-ed4a-5b0d-b6e5-a885da3cb344 | note | INSPECTION/TEST METHOD: Verify
ad2aa52b-c78f-514e-b238-9091dbe1cf56 | note | – – – – – – – – –
bdfaee65-527d-54d9-bc6d-c195180e7ad4 | note | RECORD OF CONFORMITY: This ITP signed
cc8b2a21-2068-562b-afa5-04553e80aeee | note | – – – – – – – – –
e01cb936-3e62-5b95-8b78-b85f4375f26e | note | IP
c946c2ee-6f72-5feb-9013-f742bc87548f | note | – – – – – – – – –
02f5102d-d59d-5242-a8b7-e254997f3aad | note | RESPONSIBILITY: Fulton Hogan Engineer
3c51a42b-c62b-5b25-932f-4400e7c8d700 | note | – – – – – – – – –
109b39d6-ebe1-5a04-8e84-ac41da33c758 | textbox | DATE:
a675e84a-2da5-4e9f-85d4-30ac792797f5 | section | 3 - Pre-Pour Planning and Inspection
41cae1ce-fb5e-4138-ad2f-c6cdc57b467e | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
12a332e1-858e-5603-ab13-6ea4ac815228 | note | FREQUENCY: Prior to concrete pour
41024c11-08ac-5d2b-ab85-d416c7a5204e | note | – – – – – – – – –
b7240f5b-8611-5576-b794-35943c272eb6 | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent.
f2d4c3ec-a2b3-5a37-9ff2-0a107121c0ea | note | – – – – – – – – –
d7625d18-6743-5f52-afc7-785836ad9d69 | note | REFERENCE DOCUMENTS: 602.03
e5862f33-038d-5893-bdec-b19312f708ab | note | – – – – – – – – –
2ac75aa1-19c4-57f5-a7c1-245725b581a7 | note | INSPECTION/TEST METHOD: Verify
891f698b-7fcf-5fbc-b779-5f618f6de75c | note | – – – – – – – – –
2faafae9-fc52-52c9-98d4-2defa1b9f83c | note | RECORD OF CONFORMITY: This ITP signed
b66017f2-b95f-50f2-a73a-eeff4a5e13c2 | note | – – – – – – – – –
cfe2d35d-b97f-5408-bef6-295cf480895d | note | HP
42ceb1f0-9ed7-576e-ab89-235891be58ca | note | – – – – – – – – –
b3aa5aa0-1fee-5ad4-a68f-542f09b84823 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
b57ce5a8-7049-50be-aa7e-eef5126bc4e9 | note | – – – – – – – – –
3eff1d52-76d9-5731-89cb-7891cf2ccdd3 | textbox | DATE:
b11a04f3-b90e-47cc-993a-d29ae5191f10 | signoff | AUTHORITY HOLDPOINT
d69efb01-e3ae-450b-8e77-0ca680e347d0 | checkpoint | 3.2 Formwork levels and position
8f025c5c-ccf3-5a33-8e12-4d17ce351d1c | note | FREQUENCY: Prior to concrete pour
bfb76d36-478e-5920-a32e-312482aee2fd | note | – – – – – – – – –
ec17744c-a93d-50ee-983c-b41f618a6cfa | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
00509650-0ef5-5e22-ba02-03497ae14287 | note | – – – – – – – – –
51a16445-8d05-50fb-96a8-2c11edc00a54 | note | REFERENCE DOCUMENTS: 614.06
a3e6f1b5-3963-5384-8872-be9c42bcbdcb | note | – – – – – – – – –
5e8d5e5a-7a69-55a0-84a6-520b818421df | note | INSPECTION/TEST METHOD: Verify
42a14862-439e-5cd1-9a56-ef68d664f77b | note | – – – – – – – – –
284649e4-e9c8-56a2-9ed7-7dbbcb682f93 | note | RECORD OF CONFORMITY: This ITP signed
7456153a-ae94-5246-b8d9-bba303deef04 | note | – – – – – – – – –
d8ee44ec-056b-5175-a7ee-04601933b56e | note | SCP, HP*
fb9b11cd-e151-52cd-9381-bcc5d920c1ab | note | – – – – – – – – –
fec76a09-48d4-5a48-9c3b-f4cf1a9490b2 | note | RESPONSIBILITY: Fulton Hogan Engineer
1a070275-2531-5dfe-be69-db1e5fc94c9b | note | – – – – – – – – –
f8f9746d-26a9-5e4d-9ff2-7e886192b428 | textbox | DATE:
19beef53-e712-4d39-b241-92c67cf15f0f | checkpoint | 3.3 Location of splices
b0101a14-4bd0-56e5-8095-9460e500e9ef | note | FREQUENCY: Schedule Review
72e709fd-abfd-5879-822b-36941c970cc3 | note | – – – – – – – – –
e6125443-3d4b-52b8-a630-ec285e52d93c | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
269ea9f3-f04e-5be1-952c-bba211534edf | note | – – – – – – – – –
70fae241-d655-520d-987a-41474558a43e | note | REFERENCE DOCUMENTS: 611.11
ca231382-3412-5c8c-b9fe-51be91cd62d5 | note | – – – – – – – – –
95cea05b-7880-5cc9-8f41-c7c5e56e1f7f | note | INSPECTION/TEST METHOD: Inspect
c1eb4327-6370-5f0e-81dd-6af19d22ff46 | note | – – – – – – – – –
9b7aafd1-294b-5fc9-8cfe-909a6fc7c8dd | note | RECORD OF CONFORMITY: This ITP signed
af5181c7-a877-5b1c-a74a-ee5174c96c9d | note | – – – – – – – – –
c25bfeb0-f3a3-53fc-94de-1454d9683230 | note | IP
8fcbc15d-6fd7-5639-a88f-24f748e0e724 | note | – – – – – – – – –
f1d26eca-3540-5e50-893e-5f538d87aa92 | note | RESPONSIBILITY: Fulton Hogan
6981427a-32f6-54cb-bd7c-13b15eca6572 | note | – – – – – – – – –
18caf5c4-5fcb-5d44-b191-a4d1e930e1fc | textbox | DATE:
75d87981-e2fa-40c2-a3a0-415ad8f80991 | checkpoint | 3.4 Cleaning formwork
f3dc8fb4-0967-5b90-b6e8-fd3892d7204d | note | FREQUENCY: Each concrete pour
70001734-f20c-5de2-9bc5-d6f59442dfe1 | note | – – – – – – – – –
3235bb02-abb1-5a4c-bd21-2ffc65af5014 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
9449921c-b188-5622-9f25-0726473d3345 | note | – – – – – – – – –
9fe2fa4d-2f82-536d-b1a7-a49dfde17b94 | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
49f191c0-f2a7-5a53-9117-21ccfdc1d6c8 | note | – – – – – – – – –
da158b1b-8da2-56c1-b932-a1f5634703e8 | note | INSPECTION/TEST METHOD: Verify
92f2e642-88c6-5fa0-843f-dd5fce44051b | note | – – – – – – – – –
1329e4d4-508e-5e06-a24f-ffeb0524d91c | note | RECORD OF CONFORMITY: This ITP signed
ca28c8e0-4a00-57b3-89d5-cf1548f3cf42 | note | – – – – – – – – –
322b678f-d87e-50d8-9976-25c6df46c88f | note | IP
439fe3f6-3a0d-589b-b895-a3f3282f4d97 | note | – – – – – – – – –
2463d922-c1d3-594f-9343-0ddc7b0b3f0e | note | RESPONSIBILITY: Fulton Hogan
be413131-7da0-5127-ab26-b56545987f89 | note | – – – – – – – – –
9f9fde83-a846-524a-86ea-9a928491e8a3 | textbox | DATE:
b028d801-9b44-440c-a7a2-c93ba354f607 | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
b318507e-7457-528f-be39-d75f2371634c | note | FREQUENCY: Prior to concrete pour
d43890df-b87e-5f3a-8a32-7a6811196741 | note | – – – – – – – – –
79f16b8e-da37-520e-96df-5497aeab2a1f | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. Pre-pour checklist completed and signed.
55dcd7a9-fa75-57ea-b23f-fea6f67eeae6 | note | – – – – – – – – –
160cda96-b834-56eb-b226-98168d98cfbc | note | REFERENCE DOCUMENTS: 610.18 (a)
36abf43d-bc52-5a16-aa07-2f2a9e7df3c1 | note | – – – – – – – – –
8d849cde-e3ad-5f79-ac2f-c9637042ca46 | note | INSPECTION/TEST METHOD: Verify
a59f5e8d-7c04-5880-8870-23680c1c8ad5 | note | – – – – – – – – –
f6f6e417-0fb4-54d0-9471-bf0121c9c26c | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
3f2e53f8-23bd-5bc7-aa0f-cf32b94152d4 | note | – – – – – – – – –
ffb045c6-6c7d-5348-b63c-e0bee9be563e | note | HP
df7b52fb-422b-5ce9-a37a-c2784e87599b | note | – – – – – – – – –
4b56b3c9-5726-58f6-802e-f85dd568d938 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
ba45c56e-a8a6-513d-8ecf-768b1d68d57e | note | – – – – – – – – –
7015cbe9-332a-5dbe-8d27-3b2df9056cdf | textbox | DATE:
f7cf9639-0f3b-445e-8873-927d3ced6dc3 | signoff | AUTHORITY HOLDPOINT
e9fd479d-a27e-4420-a11a-7b9057978ec9 | checkpoint | 3.6 Reinforcement assembly of piles
4f4019ca-093f-51fc-9a65-fe94ee7ed9f1 | note | FREQUENCY: Prior to concrete pour
16b4275e-ff94-5208-8a13-1dc31f914ae2 | note | – – – – – – – – –
4292112b-71a2-5213-81cc-c499682d2700 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
3a697f4d-f1d6-5356-a60b-d6b49261cec0 | note | – – – – – – – – –
4861913c-479b-53f0-85e7-2ab65289e66f | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
9c480d4a-95aa-539a-b583-fdd25d4f42db | note | – – – – – – – – –
e023688a-263c-518b-bb16-88790d957b8c | note | INSPECTION/TEST METHOD: Verify
22a016bc-446f-5975-aac3-726b942b5d01 | note | – – – – – – – – –
4870ba13-4c0c-55e6-b3d8-ee3b1d78024d | note | RECORD OF CONFORMITY: This ITP signed
afd731bd-3ea7-5870-b78c-60d96188cc35 | note | – – – – – – – – –
76e2bd03-850e-5be2-9607-e78210d5e832 | note | HP
a05d45b0-c975-5d40-8785-b31204db5035 | note | – – – – – – – – –
8d522b44-5af4-5d0a-8f8a-f1ef7dc4df7b | note | RESPONSIBILITY: Fulton Hogan
d319ba93-db25-54fc-aa47-5b769d59bfec | note | – – – – – – – – –
754bbb3d-3688-5996-9205-3aaa412376f9 | textbox | DATE:
c4aff644-33fc-4e61-9adf-0b1fe6f3caa8 | signoff | AUTHORITY HOLDPOINT
055079dd-e548-49c9-9d15-bceefacfd485 | checkpoint | 3.7 Monitoring weather
db596b61-c12d-5a09-b2c3-51f491b66d82 | note | FREQUENCY: Prior to concrete pour
f7113cce-dac9-5236-b5a1-844cea29c6ce | note | – – – – – – – – –
e86dc1ec-c831-5f5f-b02a-ee6e4160362c | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
7dc02fc2-602f-57a4-aa6f-a4c80d6d5a76 | note | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
6f560a11-2211-5c1a-8cdb-1c5cd96082e2 | note | – – – – – – – – –
635987c7-3703-5139-bfb8-c64bba032b74 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
4cbaa30d-b59f-5f60-b0b3-fb34266a5e52 | note | – – – – – – – – –
043f64ba-2b17-533c-8f3c-4be7868f84cf | note | INSPECTION/TEST METHOD: Verify
90338abd-3ab3-5d15-84cf-1d11c2ed9372 | note | – – – – – – – – –
bcde0018-b566-50dd-8d21-dcc9eb637781 | note | RECORD OF CONFORMITY: This ITP signed
716ae9c3-aa25-58f9-bfd8-0bd899f0ab9d | note | – – – – – – – – –
3091b9f1-0cc4-5be5-94e8-0603ca08e228 | note | IP
e154526f-1678-58f6-ae28-4c8f3aa90ce7 | note | – – – – – – – – –
70af2938-ab30-5e08-9999-5751b9236286 | note | RESPONSIBILITY: Fulton Hogan
f4bd7034-1960-54b8-bd68-cae506317545 | note | – – – – – – – – –
913a2067-a4c2-555c-9f7a-e731e059e201 | textbox | DATE:
9a6067b6-7316-4268-aa6d-1ad7732334bc | section | 4 - Placing and Finishing Concrete
b25db755-a382-4bc1-a968-95c7633f6427 | checkpoint | 4.1 Carry out sampling of concrete
bf547c7c-5424-591c-be82-d4235624233d | note | FREQUENCY: Each concrete pour
086486b1-2cc1-5225-bd9d-4c07179cb891 | note | – – – – – – – – –
f11b5eb7-4bd9-5fb8-97d2-1a72ffca5c29 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
8872d425-e26c-557f-b566-5c7d0232cb14 | note | – – – – – – – – –
6a636487-b09a-5776-9bd2-b0787ce07e49 | note | REFERENCE DOCUMENTS: 610.16
f7ef7208-bd21-5ac5-9b7f-110099432093 | note | – – – – – – – – –
5cf1fe11-1a0d-5117-a8b2-0c747742ddac | note | INSPECTION/TEST METHOD: Checklist
da097372-c032-51ee-a3cc-24a2c0d24e94 | note | – – – – – – – – –
a42b3345-f69b-5783-83a6-60ba919b1ec5 | note | RECORD OF CONFORMITY: This ITP signed
0541dffe-b042-58c0-b58e-b3e0ead5babe | note | – – – – – – – – –
d8e9a31a-b51f-5bdf-96f5-6dfb718fefc7 | note | IP
7698c932-ab38-5c49-bc81-f079d8767f69 | note | – – – – – – – – –
35c03883-3cad-56c9-92f3-10c8dd58b3f4 | note | RESPONSIBILITY: Fulton Hogan
5fbb58ee-cedb-5187-9193-ca7ba8c0116b | note | – – – – – – – – –
ed90f9b4-79fe-54ee-94a1-cea8b0144ab9 | textbox | DATE:
0b78afe7-5723-4c83-a6ce-8a1d35734d07 | checkpoint | 4.2 Discharge time
05446535-7d33-5a58-8162-c5c749ae95eb | note | FREQUENCY: Each concrete pour
d8a10275-56fb-53b5-b90d-abdc160028b3 | note | – – – – – – – – –
e7338def-241c-5a9c-830b-ff65e79a7bd0 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
0d8d4c7f-f8b7-553a-af60-32a390f7a1d1 | note | – – – – – – – – –
fdc2aa65-4027-5b77-a5d9-062a0b2b8a55 | note | INSPECTION/TEST METHOD: Verify
763a8064-4ba1-58b6-82e2-a49791a1b1e8 | note | – – – – – – – – –
dfb3463b-5903-5a1c-8202-85ce35aac66e | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
784e626c-fabd-55c3-962b-291866097f3a | note | – – – – – – – – –
9754d651-0c43-5c6c-adce-e49b2eaad96a | note | IP
1a9090aa-9744-565d-bc2c-e56432ab7251 | note | – – – – – – – – –
bd71bd14-8d85-54bb-9639-5085c7ed790e | note | RESPONSIBILITY: Fulton Hogan
45a75afb-d826-574b-a9c3-0d6e10de23f3 | note | – – – – – – – – –
fe794402-8c24-5ea6-a76c-a2c514a52503 | textbox | DATE:
b2205050-3fd6-4572-a4be-ac8d94657bca | checkpoint | 4.3 Methodology of placement (structural)
3200e09c-e996-5453-8d79-4baaa02ac965 | note | FREQUENCY: Each concrete pour
fb4c6677-7c19-53d7-a87d-2670e68926b1 | note | – – – – – – – – –
093f6ba0-c25c-5200-8f23-6c8d801e47c8 | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
233af2fb-3028-59d4-92f0-1568485a82b2 | note | ○ Concrete shall not be moved horizontally by vibrators
6ec79af7-930e-58ff-81b3-97ba6d71096c | note | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
39ca0488-377c-5052-8da3-f99bc0fdb550 | note | – – – – – – – – –
389f1299-ba73-577c-bcdd-f802807f05d4 | note | REFERENCE DOCUMENTS: 610.18
9a8c06f6-9345-5d4e-a297-8be6f2ff4a22 | note | – – – – – – – – –
616885d9-1e99-5a7b-9290-4a3617d095fe | note | INSPECTION/TEST METHOD: Verify
7bdb71dd-9f9a-528a-9784-513b8b80e690 | note | – – – – – – – – –
47fc8ddc-372f-5c36-834b-6dc4c2106ae7 | note | RECORD OF CONFORMITY: This ITP signed
d05f057b-e1ce-5d34-b6b2-277e1c9a86bd | note | – – – – – – – – –
0830d646-ae2a-5f03-a42d-a88c91232328 | note | IP
6a5feaf0-10eb-5c8f-b0f2-5fbec057d2b0 | note | – – – – – – – – –
69fc608e-7740-5634-bc34-36324edeb1fe | note | RESPONSIBILITY: Fulton Hogan
5a0a3655-fc47-5e51-b63a-d3578e37c4fc | note | – – – – – – – – –
38219065-6479-5d7a-a3a8-67c2bc399137 | textbox | DATE:
4407ceee-ce04-4405-b9f3-676995905795 | section | 5 - Post-Pour Details and Inspection
64cf5375-b74d-41c8-abe7-9c24ff5762d1 | checkpoint | 5.1 Curing
a2245283-4164-5c00-adc1-02d41da7a7ed | note | FREQUENCY: Each concrete pour
e67dfd92-f6ce-50d9-a82a-209a4b16c152 | note | – – – – – – – – –
dd966a93-af1e-5692-8516-b6151bb38450 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
fc548335-88d4-5fc5-ab5f-8bfb0d0a9a4b | note | – – – – – – – – –
5b9c3dad-5dfd-5b55-b456-4b104ed11fbe | note | REFERENCE DOCUMENTS: 610.23
d93c67fc-6d05-507f-8de8-945b84bc1634 | note | – – – – – – – – –
6ffd4524-655f-5bb0-a3a6-31e3add9613b | note | INSPECTION/TEST METHOD: Verify
284b48db-c696-51c1-8b25-8b20d72c932e | note | – – – – – – – – –
c3fb262e-891d-553f-9d6b-95eb1aa35ff9 | note | RECORD OF CONFORMITY: This ITP signed
a07a68c5-f4b3-5097-b942-105383a75eef | note | – – – – – – – – –
51d966ec-6fa4-5a93-984a-5a04eb045e47 | note | IP
b342ae25-2897-533a-bce8-b556f93b6d56 | note | – – – – – – – – –
4648b079-1f7f-52b1-a68e-280a2a356729 | note | RESPONSIBILITY: Fulton Hogan
c1c41587-da2c-5655-a7af-d0298233f9bb | note | – – – – – – – – –
b4383783-0af3-5486-aacd-52f9ba176d37 | textbox | DATE:
65f1907a-0d03-4c9c-aa7d-ba97637a78c0 | checkpoint | 5.2 Formwork removal
bce18606-212b-5b9d-8ddb-1d9a0617c186 | note | FREQUENCY: Each concrete pour
1010b9e1-b84d-5bc1-a692-15e7f0b0b41b | note | – – – – – – – – –
8cc1398a-469d-5b30-8ba0-d42b8cc5460d | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
a19b61de-4a5a-5414-b1ff-fd04deb9c954 | note | – – – – – – – – –
ee08c1b2-b838-5b11-a4c0-39cf67c75680 | note | REFERENCE DOCUMENTS: 610.25
96a54bea-87e6-5916-b8e7-65191378e4a8 | note | – – – – – – – – –
47ed506b-e4eb-55af-b968-de0de5042d36 | note | INSPECTION/TEST METHOD: Verify
7cdf81f2-6704-5fb4-825e-bfab8f1976fc | note | – – – – – – – – –
755eadae-2c89-534f-8357-a8cb37d21c0f | note | RECORD OF CONFORMITY: This ITP signed
3e436725-6920-5678-90bf-d558006882c6 | note | – – – – – – – – –
7e00cd2f-3e90-5e98-ada6-4f3a40df38c0 | note | IP
476a3f8d-31ea-5cb0-ae4f-7f2d003a6806 | note | – – – – – – – – –
89f5598c-7cac-51e9-9986-276a713d6a6c | note | RESPONSIBILITY: Fulton Hogan
27456a4e-3404-5b6c-af1e-c82e2d5481d5 | note | – – – – – – – – –
06a480d0-5d45-5f32-a452-71dfc665c1cf | textbox | DATE:
1656117a-5b70-4ba6-b668-286bdc74eaed | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
c1b13c7e-e2be-5904-9916-e57fd5a82a39 | note | FREQUENCY: Each concrete pour
92743bbc-50bc-5ee6-9b3f-4f0ffcd35f4d | note | – – – – – – – – –
c99c8716-f14f-5aa4-b871-3515d8109565 | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
f2c6f3a9-f458-5136-b284-af9fe08ec9c2 | note | – – – – – – – – –
2a629a85-47d7-5f4c-8461-c08b114f6ce6 | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5 607.06
fe675170-30d4-5108-8fc8-df8f6967756f | note | – – – – – – – – –
4e84b8f8-ecec-535c-b17e-c2bbeb93103c | note | INSPECTION/TEST METHOD: Verify
1165d033-2fe2-5b9a-8f58-d034ed31de50 | note | – – – – – – – – –
b2580954-6226-59b7-a0ad-6d782d02ea69 | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
9cb049a9-1a1f-5db0-868e-d541a26f6410 | note | – – – – – – – – –
35756194-6f0d-5e1b-afd4-d7c5c46a3f9b | note | IP
990a7661-95e8-530d-972d-571a3b5c319f | note | – – – – – – – – –
a1fe99de-6bee-5409-a737-68a5f3dc7b4c | note | RESPONSIBILITY: Fulton Hogan
90f6a9b2-4db2-5642-8baf-659297f447dc | note | – – – – – – – – –
78009228-ed0f-51f5-860c-1bd36cef0f2a | textbox | DATE:
fac959f0-22f1-4817-939a-069e7ef049f1 | checkpoint | 5.4 Concrete Sampling and Testing
f9e11dbe-87bc-578f-9bec-b7ddcbb78c9e | note | FREQUENCY: Prior to lot closure
fa3894cc-8c4c-5817-b520-f496b2e1a3f2 | note | – – – – – – – – –
21c3a73b-6ca2-54ac-9264-9782f9e3296b | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
866a0d4f-0a7c-5ef2-9e25-9ee2ac80333b | note | – – – – – – – – –
44fb0636-bf00-5579-b8a6-3a8ce1fe8aca | note | REFERENCE DOCUMENTS: 610.16
d0ea465d-52f8-50f5-a04f-67e90c3287fb | note | – – – – – – – – –
2d9ab5c9-55ef-54d3-9cce-1930c03b8c10 | note | INSPECTION/TEST METHOD: Verify
09fd9a53-363d-5b42-83f8-3bc9fd59d96e | note | – – – – – – – – –
8d09e693-f891-517b-8a3d-98aef6128d92 | note | RECORD OF CONFORMITY: This ITP signed
8b92db42-96e9-575b-9521-120ee35eda2a | note | – – – – – – – – –
d8ffd312-d841-5bf3-a1f0-bfc8c7e0438f | note | TP
95945413-72ad-5d4b-87a5-c24bca173638 | note | – – – – – – – – –
779fa6a8-2b1f-5173-8b65-97a0931b3e45 | note | RESPONSIBILITY: Fulton Hogan
0da68912-2ac9-582d-9216-fc0097c79add | note | – – – – – – – – –
65f24ed5-17be-5c58-b930-57d82216ef23 | textbox | DATE:
94ae71fa-d105-44ce-a6e6-48307d964dde | checkpoint | 5.5 As Built Drawings
482be4ef-129a-5d05-b329-35ce008ac1a3 | note | FREQUENCY: Prior to lot closure
e1fc2c41-77d0-5687-87ae-f15ea1bfae0b | note | – – – – – – – – –
5dc388d4-81a3-5d40-8472-db7988b04af4 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
b36bb6e3-0028-5f43-a947-aa3dea62a92e | note | – – – – – – – – –
ff089b33-d6c3-531e-8c29-a9799e85e93d | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
c7419527-9cca-5e80-9385-ce6cefd11a52 | note | – – – – – – – – –
5fcf4d01-4a4c-59ba-b6a1-41feee44915b | note | INSPECTION/TEST METHOD: Verify
68b58c96-f366-5c8f-ac40-c1bbe14e39c4 | note | – – – – – – – – –
3f1cbccc-0da9-583c-9922-c51786395db2 | note | RECORD OF CONFORMITY: This ITP signed
d5bed9bf-304a-5a2e-8fc7-2cf0a4a9ccc8 | note | – – – – – – – – –
c5af6fb7-bfef-50b3-8a83-573705532dfb | note | IP
2408fa95-d606-5fcd-bcf8-9d640c7dcd93 | note | – – – – – – – – –
3cd4b632-fcfd-507d-aa83-829569ddef97 | note | RESPONSIBILITY: Fulton Hogan
6912335d-a453-5579-a297-579b37e5572f | note | – – – – – – – – –
25508752-0060-5e0a-9eb1-da5f517e1495 | textbox | DATE:
071d16f9-6c12-49c7-bceb-98a09d8e79ad | checkpoint | Final Inspection
d91a55bd-a179-5ad1-bbcd-29712fbd7406 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1ea4be9b-0bf6-5c18-b39b-ed9a3f5ed685 | textbox | Print Name:
d8c8c579-3428-5442-b904-7f2732637956 | textbox | Position:
99945dba-1807-559f-af85-6fc744a814bf | textbox | Date:
b44c53f5-2775-437c-a27e-382ef6cef6b0 | checklist | FHC-ITP-027 - Pile Footing Construction |  | FHC-ITP-027 - Pile Footing Construction
a9606d97-83a6-42bd-91f8-5f82cf6691c5 | section | Design and Submissions
6aed04b1-273d-4082-aa0c-2d2c06c25eff | checkpoint | 1.1 - Check for correct documentation
41b5fbfa-0c65-55f8-b8ec-2faa4920aa1f | note | Frequency - Prior to commencing any activity
d5cc93cd-55b2-547a-aada-21008d730254 | note | Acceptance Criteria - Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
5089950e-c80f-5435-b5f9-e658365c603a | note | Reference Documents - Drawings and drawing registers
9111c2bf-499b-5d3f-965b-1b1d616658cf | note | Inspection / Test Method - Visual inspection
dea63f20-213b-5aaf-8ced-3bd1091dcea6 | note | Record of Conformity - This ITP signed
84cb033c-daca-5e01-997f-3e89d32aefbc | note | HP*
29fa5ad2-b165-52af-9639-39630c863223 | note | Responsibility - Fulton Hogan Engineer
63278886-be38-4500-8788-af26c2095326 | checkpoint | 1.2 - Implementation of all measures and controls
ea76ea31-532f-55c2-9b86-d7d890adf4fe | note | Frequency - Prior to commencing any activity
68241834-6fda-587d-a3f2-753aae4a832c | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
a9ba51de-8f61-5a9b-8eb9-a856a13f19f3 | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
d93df1f8-33e4-53fa-83ed-e78584fc8df4 | note | Inspection / Test Method - Visual Inspection
27264cdb-f599-567a-a42e-1562aa52c91f | note | Record of Conformity - This ITP signed
a6b067f1-d2ed-5e57-bb6a-4db6f0ff7b4d | note | HP*
ff2d8007-1e3e-53fa-b409-5858451a86cd | note | Responsibility - Fulton Hogan Engineer
ca5438c8-ec72-43c7-af9e-bb86a9bd2747 | checkpoint | 1.3 - Approval of mix design
9e346216-a2f8-5c3a-a245-fb88a8604a97 | note | Frequency - Prior to the first concrete pour
c5c90217-dd4f-5eb0-aba8-33c1bcdfe4db | note | Acceptance Criteria - Structural Concrete Design & Submission ITP completed and signed.
cae5060d-a254-57c1-ad04-249a2157a854 | note | Reference Documents - 610.07
50feb7a6-d997-5b8a-8592-ed8c5fcd7970 | note | Inspection / Test Method - Verify
fb8b9322-83b6-588e-af87-6727f6ec55cb | note | Record of Conformity - This ITP signed
4d200d9a-c088-5d71-84a5-b35d440a0124 | note | IP
c3990c24-021a-5a85-a4a2-afc90ace4b68 | note | Responsibility - Fulton Hogan Engineer
77999047-2ff3-43c4-a3cc-d40bcc0e672e | checkpoint | 1.4 - Reinforcement schedule
55110260-2523-5174-af97-effa788da9d3 | note | Frequency - Prior to concrete pour
55b119ae-5ff3-58e3-a8e4-393b81ac0991 | note | Acceptance Criteria - Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
6f6f2bf9-d07e-5383-a41a-506ce80874ae | note | Reference Documents - 611.04
c285b9a7-ee78-5aac-b8e9-857101a1cd5e | note | Inspection / Test Method - Verify
8eb8ad1c-55ee-5ed5-8546-1faba1fb1bc7 | note | Record of Conformity - This ITP signed
8e79e002-9f44-5765-9ef9-4aa7a1cd60d2 | note | IP
35ae1da2-880f-5d46-915c-4fa82c4ec01d | note | Responsibility - Fulton Hogan Engineer
6a2de901-1239-4a24-bf1b-30ae5c9c5f15 | section | Construction/Erection of Formwork
55c3e925-f079-45ae-bed5-f25d88341991 | checkpoint | 2.1 - Excavation (Pile)
104e6d5d-d9db-542b-9c38-0df46a00178e | note | Frequency - Prior to concrete pour
8f6f5052-15db-53b0-b708-0281df1914ab | note | Acceptance Criteria - The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent. Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
732e1646-fbc2-5c4f-9bda-64971da9b889 | note | Reference Documents - 606.05
d2341ece-bd8a-5fbc-b916-beb8d7721e76 | note | Inspection / Test Method - Inspect
801b9b68-5fea-5454-9378-d7c6c7e9606b | note | Record of Conformity - This ITP signed
74ff7e1a-5463-56e6-8dba-6625c96e44cd | note | HP
a013ca08-b549-56f1-b157-f9e71392ddb8 | note | Responsibility - Fulton Hogan Engineer / Superintendent
ec1f205a-e28b-4f0e-a188-ee48b4ad0295 | signoff | AUTHORITY HOLDPOINT
17205d50-a2e9-4b0a-8456-4b27f996a539 | checkpoint | 2.2 - Construction Methodology
6948f667-bda9-5cac-b198-8327c2edcc85 | note | Frequency - Prior to erection
65fd2c44-e188-50eb-a88f-0c3fcf42479d | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
f35a01a1-e2e9-5f47-91a3-30e7bea414cf | note | Reference Documents - 614.04 614.06
21182d8c-272f-510e-81c8-6f68e02e0442 | note | Inspection / Test Method - Verify
d447e2ce-9cbe-5602-b203-250168abbbc7 | note | Record of Conformity - This ITP signed
e61fcd87-86bf-5412-b727-23ee52beb229 | note | IP
bf91616c-3cc2-5ea9-a3ad-220864fe4af9 | note | Responsibility - Fulton Hogan Engineer
9d26adc6-abcd-4f3c-96aa-ab8cbe38391a | checkpoint | 2.3 - Construction Methodology (Pile)
eccf29bc-83a4-5944-9713-1999ea6ccfdb | note | Frequency - Prior to construction
11fe077a-b0a8-51e1-a0c7-87d5668b385e | note | Acceptance Criteria - Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained. Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
1ff6f786-7e10-5fff-a123-45881c3e24d5 | note | Reference Documents - 611.10 606.06
7ac7d958-a9fe-57ac-91e4-c7d89ff30e2f | note | Inspection / Test Method - Verify
6be7516d-97d9-5875-9ceb-2ff616ae00ff | note | Record of Conformity - This ITP signed
4ba494f4-a406-51a1-8d40-9d482adc26e6 | note | IP
21875110-e14f-5b02-89e1-78347f66eb9e | note | Responsibility - Fulton Hogan Engineer
dd1745e9-9a7a-4110-ab19-7bb6a9270019 | section | Pre-Pour Planning and Inspection
19f0ab39-100d-4f55-bfb4-ed91ab89ad99 | checkpoint | 3.1 - Cleaning formwork
e266b62e-0aab-5cc0-9f3c-8c6a18532bbc | note | Frequency - Each concrete pour
fc2b384d-582f-573c-99ac-4e08baf63918 | note | Acceptance Criteria - Concrete shall not be placed until all foreign material has been completely removed from the forms
38dc67d8-e1b3-594d-970c-1f033bbb495c | note | Reference Documents - 610.18 (a) (iii)
0d851ab0-053e-5194-a2c9-54ab91cb0abd | note | Inspection / Test Method - Verify
29e51262-4b6c-5fce-a36b-c5fa1dae30ec | note | Record of Conformity - This ITP signed
aa2a2062-c5f1-5eb7-b5e2-f755ccb59765 | note | IP
a99b692e-e797-55ea-8da9-4436256e0df6 | note | Responsibility - Fulton Hogan
ba276b2f-ca59-4f68-9e57-30d791ac92f7 | checkpoint | 3.2 - Correct forms, reinforcements, rag bolt assembly and embedments
54e6d429-3681-5931-8731-015fc8d7c1f4 | note | Frequency - Prior to concrete pour
0d8cc00f-536e-55ea-885e-6d77f679628f | note | Acceptance Criteria - Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. Pre-pour checklist completed and signed.
9ffb4e76-cecb-5eda-b50f-810ad09fe976 | note | Reference Documents - 610.18 (a)
9d1195ca-283e-50dc-94b7-16b69b16e8dc | note | Inspection / Test Method - Verify
f9635a85-c86b-5b08-8bb0-f7bec1da408c | note | Record of Conformity - This ITP signed & Pre-Pour checklist completed
39ae11c6-5e5e-53fc-ab8d-35a1ebc1c93e | note | HP
55762235-099b-5d8b-9833-bfbe662e6241 | note | Responsibility - Fulton Hogan / Superintendent
1bcdc184-7551-4e98-9022-449d472b8025 | signoff | AUTHORITY HOLDPOINT
59e1fa3f-5c96-4dc0-bbe8-6a9cf6b0fc07 | checkpoint | 3.3 - Reinforcement assembly of piles
80d032e7-90e4-5566-8d31-31aa7096a40b | note | Frequency - Prior to concrete pour
7fe3e4bd-af03-5ff7-b139-f3bf2a4b6293 | note | Acceptance Criteria - Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
2b7e5ef5-a494-514b-ba6e-e709e5a6d939 | note | Reference Documents - 610.17 (b),( c), (d)
11be937b-083e-516e-bb3d-3c569ba932d8 | note | Inspection / Test Method - Verify
763cc17b-d87e-5830-b119-0de7e58f5675 | note | Record of Conformity - This ITP signed
24ffe73d-2479-5b7d-9683-21972940042b | note | HP
42629505-5ab9-5e9c-a867-45b62ceaa243 | note | Responsibility - Fulton Hogan
f9cfa77c-c435-4c1d-9ecb-41df250c24f4 | signoff | AUTHORITY HOLDPOINT
79676b3d-6c02-4ca8-948d-008ec9baed98 | checkpoint | 3.4 - Monitoring weather
6c4637e7-4ac8-5d64-a011-3a6754014dde | note | Frequency - Prior to concrete pour
152e0784-f8b1-56b6-8684-6a57e79013bf | note | Acceptance Criteria - Concrete shall not be place when temperature is <5°C or > 35°C All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
c5995841-d4f7-58b8-a78b-784a4b2567fe | note | Reference Documents - 610.17 (b),( c), (d)
e86fd3a5-03e6-5b94-ae1a-71b0c2bc075f | note | Inspection / Test Method - Verify
8baa2e9d-cefc-5d08-a3ed-38bb1ce35663 | note | Record of Conformity - This ITP signed
04c43df5-0f35-59e3-8605-c2f780f0a29a | note | IP
b6023ca2-16cb-5781-84ec-19046c0bbe60 | note | Responsibility - Fulton Hogan
d160cb7d-efb0-407d-b9b4-bb5bb32d9110 | section | Placing and Finishing Concrete
06f7f196-c73a-43fb-ab64-cefb6226feca | checkpoint | 4.1 - Carry out sampling of concrete
faee9827-b11d-598d-8cde-da7ee69d4187 | note | Frequency - Each concrete pour
dd88ce79-7eb7-526a-bcfe-8e84335fbda8 | note | Acceptance Criteria - Sampling in accordance with 610.16
ba56bd2d-8e7e-531b-8811-e9f150ab5bf0 | note | Reference Documents - 610.16
44342323-a7cd-516c-860d-fb497500dcda | note | Inspection / Test Method - Checklist
2b8f272a-e701-5daa-9692-fef959cf4fb0 | note | Record of Conformity - This ITP signed
dd1679b4-7e6c-52c1-a214-98acd2b4c7a9 | note | IP
b6c21dd2-17c1-5f28-bced-acb0435f8dc6 | note | Responsibility - Fulton Hogan
38fd1056-9930-4a44-aa43-20482f6dd8dd | checkpoint | 4.2 - Discharge time
dad6b884-d4d4-5be8-9bde-e3d30b319f25 | note | Frequency - Each concrete pour
de46c082-818a-52d4-9667-c1b729bb9b13 | note | Acceptance Criteria - Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. Batch to be used has a discharge time of 180 minutes.
33282b20-955b-5962-99e3-a39de2d849c1 | note | Reference Documents - 610.13
25f0b82f-ffdc-5861-9a49-45459af90b34 | note | Inspection / Test Method - Verify
acd2881d-cb67-5284-a970-7ee840a796bc | note | Record of Conformity - This ITP signed. Accurate Site Notes & Load Mapping
d6c7f8e0-03fd-5a70-bdb1-5f88fa26db3f | note | IP
71a193bc-0cf1-5cb7-ba40-5ef170ebee8b | note | Responsibility - Fulton Hogan
2c760b5c-1d46-4bbf-871f-c77200b573ef | checkpoint | 4.3 - Methodology of placement (structural)
5191d644-6362-5021-a4dc-9ee9255c9342 | note | Frequency - Each concrete pour
e72d49ff-6adf-568b-99f9-1a8a0d6bfb6f | note | Acceptance Criteria - Concrete shall be transported, handled and placed in a manner that will prevent segregation or loss of materials In continuous pours the max. time lag between truckloads on site is 25 minutes
60620b75-3adf-5718-9a40-9b26ecfb9a37 | note | Reference Documents - 610.18
3384093f-d743-53db-96b5-52ca61313fba | note | Inspection / Test Method - Verify
35ccd945-f007-5aa4-a080-a90a73ed21b7 | note | Record of Conformity - This ITP signed
435ccc89-1b94-5123-a666-c838d7e91ec4 | note | IP
a235b76b-499a-509f-8354-063ee8a3b024 | note | Responsibility - Fulton Hogan
d41a7348-257d-4c22-9354-9be74bc96e0b | checkpoint | 4.4 - Methodology of placement (piles)
d62e3a04-2ad7-553f-a867-23db2c60ba86 | note | Frequency - Each concrete pour
d40e2577-0309-5433-b92f-6055db88b3c5 | note | Acceptance Criteria - Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation. Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
9f98a56c-3d0e-5e6a-a936-cb7252789ef0 | note | Reference Documents - 606.03(b) 606.05
472dbe60-9d17-5669-8f60-a5c91dc116e2 | note | Inspection / Test Method - Verify
d872d330-c818-597d-aff1-96695a23698a | note | Record of Conformity - This ITP signed
e59cfb15-2488-571c-9005-517251794ba4 | note | IP
7bbdcd88-b0b1-5b93-88e2-cef4c90b0db8 | note | Responsibility - Fulton Hogan
340c9a40-014e-4119-b2d7-4cb5bf6139eb | section | Post-Pour Details and Inspection
97201dd0-7470-4848-911e-97b8348ca8dc | checkpoint | 5.1 - Curing
6b2ec9f9-26e7-5c4f-a7f6-f0c54df1498a | note | Frequency - Each concrete pour
b77ffcd8-01df-59e0-aefc-a9bcc69ebb73 | note | Acceptance Criteria - Sufficient time shall be given for the concrete to cure prior to loading.
924bc59d-e5bf-569f-830c-8955c19313b9 | note | Reference Documents - 610.23
f48c59d3-0c42-5c5b-90c5-5ffbebad1853 | note | Inspection / Test Method - Verify
eec77213-632c-5d99-98e4-37f8d5faf11e | note | Record of Conformity - This ITP signed
f76c478a-f448-5857-a287-b40547b4a573 | note | IP
814fdc63-3d0f-5338-8aa9-c4c772db32e8 | note | Responsibility - Fulton Hogan
d416af72-8ef1-4f05-837b-ab35a4c3e107 | checkpoint | 5.2 - Formwork removal
62c75727-4e20-5d69-b8bd-6ae76fb0093d | note | Frequency - Each concrete pour
30956ed4-2d67-54a2-85da-514daac270ea | note | Acceptance Criteria - Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
11460b4f-fffd-5851-98a4-1ef2ddbb3856 | note | Reference Documents - 610.25
cf54a589-066b-55e8-8bf9-802c0cab5bf5 | note | Inspection / Test Method - Verify
cef41683-1980-5506-be0c-685c3bb96fb0 | note | Record of Conformity - This ITP signed
c5fc8f30-71f4-53df-ba79-bac53dc2f563 | note | IP
ca7d804c-dd0f-5cba-9d41-cce29e50774d | note | Responsibility - Fulton Hogan
fe0a317d-c234-4f51-99b6-9c771b3654f1 | checkpoint | 5.3 - Positional tolerance and dimensions of concrete members and piles
be793b8f-8805-5c94-9006-a5911b7761ea | note | Frequency - Each concrete pour
ead02442-53fd-5ff2-9656-27cf9da3086f | note | Acceptance Criteria - The centre of the pile head shall be in the specified plan position ±75 mm;
c80f312e-1a92-5043-9c85-e1ff51916959 | note | Reference Documents - 607.06
b3cebe4d-1cc7-5fc3-ac47-f0377a83e72b | note | Inspection / Test Method - Verify
8d0ec1e8-28a7-58f7-a540-3c98c1caeb99 | note | Record of Conformity - This ITP signed Post Pour Checklist completed
1f8f02b9-cea6-5ec5-915b-8356b80b89fe | note | IP
59b4166c-f7bc-5a3e-a681-cee2829555fd | note | Responsibility - Fulton Hogan
4d00edab-6aac-49d6-a3a7-81ee24c361ad | checkpoint | 5.4 - Concrete Sampling and Testing
a09c58dd-dd0b-576e-b7e6-dafe3f6ced57 | note | Frequency - Prior to lot closure
1691a350-b210-59b7-845e-2f9324914400 | note | Acceptance Criteria - Concrete sampled and tested for Compressive Strength: - 2 cylinders @ 28 days Compressive Strength=32MPa - 1 cylinders @ 7 days for Compressive Strength=20MPa
bb036c42-6f29-5742-8a7e-da9915f28b1d | note | Reference Documents - 610.05 610.06 610.13 610.16
1d7416e5-d528-546d-bf77-21274c7ccf38 | note | Inspection / Test Method - Verify
95fb1b75-5ee6-5c2a-83f4-f2fbf92e91ac | note | Record of Conformity - This ITP signed
5726aa87-1c3a-51da-988f-05da1bbb3298 | note | TP
9cf89bae-1b5e-551c-9486-1ed071d0a994 | note | Responsibility - Fulton Hogan
98102819-03e1-481a-ab26-68af6f449bd4 | checkpoint | 5.5 - Protection of Adjacent Piles
2d2fc5a0-0c39-508c-9be6-a6688672a2e2 | note | Frequency - Prior to commencing any piling
b2e8ac37-bff0-518a-842c-e7fc1b76d8a3 | note | Acceptance Criteria - No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa. Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
86eb7f8c-3ab7-5e46-a3bf-81e630b8527e | note | Reference Documents - 606.04(a) 606.04(c)
e6e14890-595c-507c-94e8-eaf3b7fbd743 | note | Inspection / Test Method - Verify
2351f335-8221-5b4c-a897-5b118a1b2427 | note | Record of Conformity - This ITP signed
3c4cc24b-eaea-54c0-9b0e-20878168a82c | note | HP*
8a3240af-7eca-5d38-b292-cf63ca5d21c5 | note | Responsibility - Fulton Hogan
4fd8e4ce-331c-4d7c-863e-142326f7e3c3 | checkpoint | 5.6 - Testing Post-Pour
e1797f58-9370-5757-b5f3-11569e77fab2 | note | Frequency - Prior to lot closure
413b5e4f-993e-5d82-ace1-7ac592732849 | note | Acceptance Criteria - Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
13801b1b-5146-5cc6-b435-99e55b00741a | note | Reference Documents - 606.07
0e7f76c6-0588-51af-ad12-cb20a22bcdaa | note | Inspection / Test Method - Verify
33bde039-ac34-53c4-9804-2acb9bfba7e9 | note | Record of Conformity - This ITP signed
4e97a354-3c72-5172-96a4-a4126c64da03 | note | TP
fe3ed722-af6a-58a3-9679-98b9acaad95b | note | Responsibility - Fulton Hogan
66c81391-2390-4652-9da1-2114912acd1e | checkpoint | 5.7 - As Built Drawings
fc5624dc-f5b1-5e19-8f57-612a07e96b01 | note | Frequency - Prior to lot closure
c826f6f4-31ea-5541-b538-241403f8ba89 | note | Acceptance Criteria - Recorded of as-built drawings
ca3d3e80-e4de-5149-be29-91406315d872 | note | Reference Documents - Fulton Hogan Procedure
1fd47524-96d1-57dc-b4b1-1746c7931d24 | note | Inspection / Test Method - Verify
19995901-d6d7-5e4d-8332-decd8eaa709a | note | Record of Conformity - This ITP signed
a1030f85-90d4-56da-af70-ffa7df4b4ecb | note | IP
010bdfda-ddee-52b7-91e4-2d557d9c0f33 | note | Responsibility - Fulton Hogan
d3d581e3-d49d-4d8e-a579-369bb77cb50e | checkpoint | Final Inspection
7addda81-6635-50fe-ad77-0aacdf678c00 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5b88f1cc-2273-504c-a2c0-5e1442b31792 | textbox | Print Name:
613a9401-f597-5261-a635-af34abe6abca | textbox | Position:
33c004a5-b7fa-57ff-b9cc-5653b0f99fc4 | textbox | Date:
4c1b4405-d37b-436d-96ee-2e75cd09385e | checklist | FHC-ITP-028 - Fence Installation Rev1 | itp | FHC-ITP-028 - Fence Installation Rev1
c3ee1e4e-53a3-4d91-9fe1-62898a8a1272 | section | 1 - Preliminary Works
2543e96f-632c-4c6d-b53a-5948509e5a9e | checkpoint | 1.1 Check for correct documentation
ab63d2bd-ceac-5b6b-bc23-61c0b5cc017a | note | FREQUENCY: Prior to commencing any activity
506b82dc-c183-50c3-9ffc-e9b5f7092973 | note | – – – – – – – – –
8a903922-a31d-56b5-9667-5abd9276aa9b | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
50c77bba-a9c2-5661-8ad9-d6797d835ca6 | note | – – – – – – – – –
3e36d020-ace2-5c5a-8e01-90c4dc6c55d2 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8df14f35-fea3-5970-a6a8-1e9036c13195 | note | – – – – – – – – –
bfffbba4-9acc-5dfc-b9f9-672c760aca4e | note | INSPECTION/TEST METHOD: Visual inspection
da4329e9-eadd-58be-868a-bd2d88da396c | note | – – – – – – – – –
e9f8b0ba-c1e1-5221-8067-826163c62897 | note | RECORD OF CONFORMITY: This ITP signed off
f7d13692-de41-520b-acd4-d718b9635579 | note | – – – – – – – – –
40d5dbff-6aea-5414-85f2-7d4b3edb76b0 | note | HP*
80163345-6bd2-5a41-a13f-0c21104b628a | note | – – – – – – – – –
fb447705-90c7-5580-8c09-68532e85572a | note | RESPONSIBILITY: Fulton Hogan Engineer
4fedea87-d2e1-5e84-af14-fadbebd1de4f | note | – – – – – – – – –
f2533559-2461-5bbc-964e-abec7f31ab49 | textbox | DATE:
d704119d-d854-49be-a97e-9c7a5523918a | checkpoint | 1.2 Implementation of all measures and controls
46351cc0-bec7-56b7-b897-46827b0a4b26 | note | FREQUENCY: Prior to commencing any activity
279f1072-027c-54a6-b2d4-3e7591585e2f | note | – – – – – – – – –
4c22258f-5a6a-589d-aa8d-7d9ddb17d299 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
1bfdab1c-6eee-5325-90ad-6a4de7a4a3fa | note | – – – – – – – – –
f473adb1-b796-5424-bf6c-1d65ca33a4ec | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
7bcf1134-dfa0-55e7-8526-c5409c9f0d6a | note | – – – – – – – – –
c849a1d0-2399-596f-a1f5-7637514d2c59 | note | INSPECTION/TEST METHOD: Visual Inspection
059d557d-08bc-5e3c-83ca-b7861b3331d2 | note | – – – – – – – – –
236cb947-99f1-5b7d-b664-b40df6d9286b | note | RECORD OF CONFORMITY: This ITP signed off
05e8d81e-c29b-5b58-8146-106373a62c22 | note | – – – – – – – – –
61e8da0f-b659-5e09-82c2-11b9d812f570 | note | HP*
b039b6b3-90db-53cc-8c74-2b0dd16b4aca | note | – – – – – – – – –
265f9de7-18a8-5e49-b141-6de07a492f09 | note | RESPONSIBILITY: Fulton Hogan Engineer
cb36936f-47b7-5336-aab0-4e08f30a7cbb | note | – – – – – – – – –
8250557c-b72d-5166-ae68-d47e803c4dc4 | textbox | DATE:
e5e50661-1719-4acc-971c-d8a754f62625 | checkpoint | 1.3 Check Materials
ece634d7-f23e-5af1-8cb1-e9b1e9f45ed4 | note | FREQUENCY: Prior to commencing any activity
d7277f8f-a528-50fa-9a77-1468492b8734 | note | – – – – – – – – –
5231f8a0-2f99-5dd9-9897-92ec3d43ad71 | note | ACCEPTANCE CRITERIA: Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of SD3143 and IFC drawings.
6e36e8ef-dd49-503b-bab4-f88519632aee | note | – – – – – – – – –
113da379-bb77-5b88-81ec-d30c3ca12fb1 | note | REFERENCE DOCUMENTS: Fencing Plan SD3143
92ac57b2-e618-5676-985e-41cfde1203a8 | note | – – – – – – – – –
050a249e-5d87-56df-a2a4-6e30f117c704 | note | INSPECTION/TEST METHOD: Verify
eb0f06fa-eaff-570d-9b97-b0d7f8cf7679 | note | – – – – – – – – –
0b3b094a-f04b-5284-8c34-ccb0a17a4a9e | note | RECORD OF CONFORMITY: This ITP signed off
b27d99d7-6c4c-5cf6-a8e8-ecf10bc66d79 | note | – – – – – – – – –
11c54cca-47d4-5d03-a72b-b4860985a675 | note | HP*
36fd8a18-7131-5471-875f-dbcd72e5d04b | note | – – – – – – – – –
d150e10a-223b-50a7-8399-2ed860bd83be | note | RESPONSIBILITY: Fulton Hogan Engineer
85c3156b-96c1-57db-b179-4d1d4859ce74 | note | – – – – – – – – –
449431dc-65c5-519f-becd-0d351851d9a9 | textbox | DATE:
a95b4a06-bba0-4b3e-a536-87ab652522b3 | checkpoint | 1.4 Confirm Footings position
8b613d6a-d20f-5e94-930e-f0a78ee85fc8 | note | FREQUENCY: Prior to commencing any activity
c6415e48-9e37-53b8-9c63-f15f52cc0ac3 | note | – – – – – – – – –
7a697f72-7f55-5e84-86ee-414c4811c3a2 | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
40902b28-13cd-5479-8148-16fd9ab6a9eb | note | – – – – – – – – –
78d830fa-3723-529e-ba9a-51e111e91a39 | note | REFERENCE DOCUMENTS: Fencing Plan SD3143
1949b5b9-95e0-5107-85f3-acc5ffeddf52 | note | – – – – – – – – –
93342666-b464-544a-b32b-913d3cbbd431 | note | INSPECTION/TEST METHOD: Verify
bc9e2f42-3d00-53f0-989e-2d0e7c4b0d56 | note | – – – – – – – – –
bdb20160-c362-5097-b062-e753d52e3065 | note | RECORD OF CONFORMITY: This ITP signed off
25f813c5-14ef-50a1-aad0-6460a0022f10 | note | – – – – – – – – –
e380aeac-731d-5fa9-8f40-b051998edab3 | note | HP*
b0aba1ae-8f72-599a-956f-3f16b4fe823d | note | – – – – – – – – –
4a288abf-4007-5f58-ae33-174c199c1f63 | note | RESPONSIBILITY: Fulton Hogan Engineer
7794fdc9-bda9-5e97-905e-618b90d8c611 | note | – – – – – – – – –
7c664b07-8ad6-51c2-a386-951e4e0b0c3b | textbox | DATE:
9d348a97-2eed-4cc7-9d5a-90dea686b246 | section | 2 - Construction Works
daffced7-cad4-4ceb-aa92-fabd34c17f73 | checkpoint | 2.1 Footing Installation
fbd5de68-57d5-53f6-82ad-bf24c490ba15 | note | FREQUENCY: Prior to post installation
627f5855-ca10-53d8-bd36-29684003b0d0 | note | – – – – – – – – –
a6513f58-11b0-5372-afc2-d4025dd32842 | note | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20
d3701e76-52d9-535a-a1a6-9f3e05589d32 | note | ○ Concrete footing shall be 600mm x 200mm for all posts
6ca9aa49-f43b-5f2a-a21c-6aad3b07c96f | note | – – – – – – – – –
5dbcc2c7-b6e9-5545-a37f-3cc04da51f65 | note | REFERENCE DOCUMENTS: Fencing Plan SD3143
8b69d729-17cb-5b0e-949e-e88e35d1f1c2 | note | – – – – – – – – –
ace511e3-928f-5e7a-8825-708faa496dff | note | INSPECTION/TEST METHOD: Verify
eb58ac72-21f7-50a3-b0fc-c617206f642c | note | – – – – – – – – –
b0935dc1-6e2f-5931-80a4-dd69bf8263d9 | note | RECORD OF CONFORMITY: This ITP signed off
71b729db-474e-5e1e-9715-f2772a6ee8bc | note | – – – – – – – – –
7d151a37-4457-5c54-8289-357422135c34 | note | HP*
1cfb014a-7927-57a7-b6f9-356d61993a1f | note | – – – – – – – – –
e10f4b72-7b1a-529f-9183-74a07b89b50e | note | RESPONSIBILITY: Fulton Hogan Engineer
e28fcf22-cae8-56cb-bee4-314e7feb51ac | note | – – – – – – – – –
0be539b4-fe84-501b-8a16-b565d8031ff0 | textbox | DATE:
54c102ce-77ef-422e-8dbb-b940e63dcd5b | checkpoint | 2.2 Post Installation
f5437457-a753-5a93-a881-3a194a8d0d2c | note | FREQUENCY: Each Lot
50e6e751-32c4-5930-aae0-beb3ff2f2724 | note | – – – – – – – – –
fac853c7-69f7-5310-bac3-6f324701085c | note | ACCEPTANCE CRITERIA: Posts shall be set in concrete footings of the dimensions shown on the drawings and set at the correct height governed by landscaped area FSL.
1f9a70cb-5aac-56f7-8809-72b06ff45836 | note | – – – – – – – – –
a4214709-7f35-5f27-b5da-f1e544dbb8e5 | note | REFERENCE DOCUMENTS: Fencing Plan SD3143
28b77a1e-5668-5121-b3e2-aed4b9af5d9e | note | – – – – – – – – –
18cdbfb3-a87e-56ae-8b68-35d11f56d119 | note | INSPECTION/TEST METHOD: Verify
9f867e01-b0e5-5fde-9078-4554d11a2ba1 | note | – – – – – – – – –
5a78091f-1936-5e3a-a0dd-dfa16f89ccb0 | note | RECORD OF CONFORMITY: This ITP signed off
4025c01e-1a41-5ad2-8b06-218804d93e43 | note | – – – – – – – – –
0873691b-a697-5e9b-bb8a-d44e39ae6530 | note | HP*
3b3cc93d-b69f-55f9-9b81-c2ad1a035dce | note | – – – – – – – – –
a671762a-bc86-5581-b206-c6b840c49616 | note | RESPONSIBILITY: Fulton Hogan Engineer
de987aa2-ef1a-52de-b08c-fa4e18d3569f | note | – – – – – – – – –
0805047c-d181-5d24-b70a-05872ca1e5f5 | textbox | DATE:
79bc54af-1abe-4357-8476-1af4ac6586d0 | checkpoint | 2.3 Fence Panels
3c5416f3-d8a7-5f4d-b185-41d3d5b179fe | note | FREQUENCY: Each Lot
eee42422-c3e5-53fa-b38a-b96713fb20b6 | note | – – – – – – – – –
bcd7280b-a19d-5c33-ad17-62ec15b6cc97 | note | ACCEPTANCE CRITERIA: Post centres shall be placed at 2455 mm intervals as shown on drawing SD3143.
f905bf7d-7cc1-5bf6-ac0e-65a53ec3ebc4 | note | – – – – – – – – –
2b5cb93e-9dde-5e12-87e8-99a2ed685c2a | note | REFERENCE DOCUMENTS: Fencing Plan SD3143
c06a5352-0ce6-5928-8c38-df0f2396addc | note | – – – – – – – – –
ae1f7bc2-0b76-5c2f-8c32-d583f94cbbae | note | INSPECTION/TEST METHOD: Visual inspection
8d627977-e963-50c5-8160-4193d431a400 | note | – – – – – – – – –
af1f457e-1a9c-557c-9821-69e2ed8ea2dd | note | RECORD OF CONFORMITY: This ITP signed off
7d77ac9d-9a80-5a16-989c-fbd3141f450f | note | – – – – – – – – –
569aeb71-a725-5929-b3d4-28c0d503001e | note | HP*
b8ae3284-48fd-5d28-8fae-0da469491db3 | note | – – – – – – – – –
2e85b488-34eb-5771-969a-14347a0136ef | note | RESPONSIBILITY: Fulton Hogan Engineer
3d529d63-2800-5da0-a0e0-1a43dcad5481 | note | – – – – – – – – –
9b04f0b6-d626-59ea-8df5-78bd0582d708 | textbox | DATE:
bc506c47-7534-4a04-a707-ef0060edd64c | section | 3 - Completion
10491304-d5ec-41a3-b658-0d341c562cf1 | checkpoint | 3.1 Clean up
d52519eb-507e-5c91-8170-7ba2debe14a4 | note | FREQUENCY: Post Completion
b6ba194d-4b01-5a03-bd02-0a3e03b9f5f0 | note | – – – – – – – – –
d3be32a0-7c70-5c8e-9780-3990ed87d07e | note | ACCEPTANCE CRITERIA: Personnel to ensure that work areas are clean and free of excess materials
176c2df2-4931-51c5-afa1-2405e538221c | note | – – – – – – – – –
4c76b165-40d2-57aa-b009-1d7e8ca8f269 | note | REFERENCE DOCUMENTS: Fencing Plan SD3143
1ccf0c5b-47fc-5c78-8c5a-5e44280ac788 | note | – – – – – – – – –
84878d21-8b42-54ad-bcf1-64553ce946b9 | note | INSPECTION/TEST METHOD: Verify
ffac41e1-e998-5819-a52d-00e6a0ac26f4 | note | – – – – – – – – –
bc232022-b75f-5472-91de-11944a7b3672 | note | RECORD OF CONFORMITY: This ITP signed off
919eb5f7-2e8c-5103-bfcb-e64cd20445ca | note | – – – – – – – – –
8ff07927-609d-5ae8-8096-2d61b42b7e02 | note | SCP
77f76c91-848a-5c7e-a654-bb81d8360509 | note | – – – – – – – – –
c0c85586-475d-5917-aa44-5168f3e5c7d8 | note | RESPONSIBILITY: Project Engineer/Surveyor
20eef2d7-470d-5840-a899-b0bf7fe167ac | note | – – – – – – – – –
cfb40392-7333-50f0-8201-fe0c2821d1b4 | textbox | DATE:
2b0b1e05-6c47-4891-ae7d-ba944a08fc56 | checkpoint | 3.2 Verification
1ec14ec8-db8a-5d52-816c-22a6fe21b46a | note | FREQUENCY: Post Completion
aa4892a3-b79f-51d4-ba10-4aa951be3638 | note | – – – – – – – – –
7f3ddeb6-02db-5f93-82b4-c5eb4848afc1 | note | ACCEPTANCE CRITERIA: All material dockets and compliance certificates are to be provided to the client.
a0c91d45-ed71-5b04-a4c1-ea2b5734a244 | note | – – – – – – – – –
db380633-ef04-5262-9551-e8fcab3d0a0b | note | REFERENCE DOCUMENTS: Fencing Plan SD3143
865b5101-119e-52ab-b576-36071b4267e9 | note | – – – – – – – – –
6e866a34-1d0a-5dfb-9385-615f56763a9c | note | INSPECTION/TEST METHOD: Verify
cff5af76-cbe4-5e2b-bca9-c4fde0c5ebec | note | – – – – – – – – –
4f44a134-6921-551c-9e09-779d1805c666 | note | RECORD OF CONFORMITY: This ITP signed off
ec2a0a95-db86-5842-8767-8aaf7106978c | note | – – – – – – – – –
3af471d7-8b8f-5faf-af1b-daa91d9298c9 | note | SCP
75af2f96-e07a-5054-993b-2669f81413ce | note | – – – – – – – – –
fde16bfd-22b2-5ae8-9913-e882be89bb79 | note | RESPONSIBILITY: Project Engineer/Surveyor
8cf701bf-e5ca-524b-9b5b-7e127e29ebee | note | – – – – – – – – –
83b9b76a-ddbb-5119-bf0f-5257c80b2722 | textbox | DATE:
2d294aa2-687d-4d22-af95-b818839073fc | checkpoint | Final Inspection
d026f2f8-0704-59fb-b907-b32151990bdc | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
932bc0bb-2857-555a-a3f9-61f39339d37c | textbox | Print Name:
f73cb4e4-f0c3-54b8-a898-0f614baba033 | textbox | Position:
821d142f-058d-5a3d-a3e0-26899529533b | textbox | Date:
ec165938-2e37-46c4-b314-927759c3b601 | checklist | FHC-ITP-032 - Bus Bay Concrete Slab Rev1 | itp | FHC-ITP-032 - Bus Bay Concrete Slab Rev1
1021df16-574f-463d-801e-43365bd8e5b7 | section | 1 - Design and Submissions
ea5465f5-7395-4b96-a72d-144af97e4712 | checkpoint | 1.1 Check for correct documentation
3d25d32e-1cd9-504f-9308-a30e7b2c1d32 | note | FREQUENCY: Prior to commencing any activity
d7f6a621-eb12-5d36-ac65-1c1d67968a94 | note | – – – – – – – – –
5fb08601-aacd-5bbb-ac01-22c006aed0a5 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
02452fcf-787a-53e2-93da-afd51c0b25ff | note | – using the correct and complete set of drawings
3f488ea5-820a-5c11-8ccf-9af662ddb12b | note | – all drawings are the latest revision
78b1b526-ddf2-5f90-85de-22cd2fc65e29 | note | – – – – – – – – –
b5210140-4fd4-51ba-b08c-56e59d9e3305 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2bd8203c-7b9d-5692-b952-67505c7f45f4 | note | – – – – – – – – –
eb1c91c5-5849-510c-b8ae-b028db379e4d | note | INSPECTION/TEST METHOD: Visual inspection
dd4a39d0-0ba4-55b4-bcdf-adf4961fbebd | note | – – – – – – – – –
5dd9f295-d0c3-5cd9-b191-9183245efbb6 | note | RECORD OF CONFORMITY: This ITP signed
5c4f91bd-13af-5f22-b6f5-9f7197a92532 | note | – – – – – – – – –
e3e57884-55e6-545f-913e-391a6e79011f | note | HP*
37d7c8b2-9d8d-5134-9258-0eed2585a93b | note | – – – – – – – – –
96db228c-14da-58ea-9779-0fc81c9f448e | note | RESPONSIBILITY: Fulton Hogan Engineer
6384b32b-bcf8-59c5-97f2-5aa7eebe979d | note | – – – – – – – – –
3ecff750-b8cc-5899-9ab9-8becb6f8e156 | textbox | DATE:
07e62589-b18f-40c9-8b99-8fd80f7440a5 | checkpoint | 1.2 Implementation of all measures and controls
ec7bb0f5-f3c3-5ecf-89a5-63f78ca4e1ad | note | FREQUENCY: Prior to commencing any activity
a8f42c6b-f25c-57ed-8d73-15902175d705 | note | – – – – – – – – –
a2892a5d-c48f-50af-8bef-2cc2cf54f897 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
db505de5-b85f-5008-8af3-7b0eaf725efd | note | – – – – – – – – –
11b46f3b-d570-5668-a877-576827fe9000 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
bd265419-f49a-5383-86d3-e06a2c8ed213 | note | – – – – – – – – –
94c62c25-87ad-5b55-83e8-29ea9d796cbb | note | INSPECTION/TEST METHOD: Visual Inspection
0ae546ab-432b-5734-b4e8-2abe88937dca | note | – – – – – – – – –
d8c4ce74-7578-5304-8904-ba64b9d19fc2 | note | RECORD OF CONFORMITY: This ITP signed
73a0db99-7e00-5704-8034-ae97c8f22b35 | note | – – – – – – – – –
a44d5217-a2fd-52f2-a88e-3b2e09e0bbbc | note | HP*
4eb9cbbd-fa98-5139-8c55-f01ea1a09433 | note | – – – – – – – – –
4ed969bb-690b-5611-bfab-4c484a5a3b38 | note | RESPONSIBILITY: Fulton Hogan Engineer
183a9cbb-a992-5736-acfd-1248e146a66f | note | – – – – – – – – –
05932d17-62b9-596a-9862-5e4648e56b22 | textbox | DATE:
9ed076cc-48ae-4926-a5fd-9404e026c842 | checkpoint | 1.3 Approval of mix design
ca8a047c-349e-581f-ba5f-6512894aacf2 | note | FREQUENCY: Prior to the first concrete pour
8c0fdeb4-ed76-55f1-a8ba-53c546cacab0 | note | – – – – – – – – –
7f7a19d4-4793-5c56-a4ad-4f98c9f0e236 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
4ada552a-e2a0-535c-a34f-52c977e97beb | note | – – – – – – – – –
d6a04d38-1288-5eea-b568-124e09572855 | note | REFERENCE DOCUMENTS: 503.04
ec43f83e-7c69-5a98-b193-8881dbbf9e75 | note | – – – – – – – – –
42563365-0bcb-5145-b08a-0108e1ba2a9f | note | INSPECTION/TEST METHOD: Verify
d8d8ba1c-776c-5358-8fcd-fe868373f826 | note | – – – – – – – – –
d9f670a5-078f-551a-abc0-29f540fa49b4 | note | RECORD OF CONFORMITY: This ITP signed
72796c82-9e3a-5160-aeed-e68bc0c852fe | note | – – – – – – – – –
7d8f5f7a-e783-5b50-a26d-1c83884d18d4 | note | IP
6e47c6a5-ce80-5fc7-ad55-b812a54900c4 | note | – – – – – – – – –
b0987a23-d83d-5f12-ba38-ab2aac708d49 | note | RESPONSIBILITY: Fulton Hogan Engineer
2585fca7-4597-5892-9b2c-61cb142ae9ef | note | – – – – – – – – –
9709e539-0564-5c68-a6a4-43c2bda2f275 | textbox | DATE:
b5096ce3-77d8-4c52-bd08-6a79f31c7fad | checkpoint | 1.4 Reinforcement schedule
ac5a01fa-5fa9-59b1-a9fa-c30d72a02946 | note | FREQUENCY: Prior to concrete pour
7f882223-6bd7-5d63-9872-fca78e362c6c | note | – – – – – – – – –
c862441c-680c-5c55-877e-0c5cdc9f4f8b | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
6932fcb4-0143-5636-b235-62f53ff479e7 | note | – – – – – – – – –
dc2d25ea-fcd5-58af-a87f-3513289df7ae | note | REFERENCE DOCUMENTS: 503.09
3ee311d3-d873-5a86-8529-0d47b7b1d5e9 | note | – – – – – – – – –
d407c59b-bfed-5257-990a-92f3c4b2b603 | note | INSPECTION/TEST METHOD: Verify
de3e4885-fc78-5875-8a40-94a9a41dbe28 | note | – – – – – – – – –
8f6a0479-a846-5b4a-8417-24b1a305803e | note | RECORD OF CONFORMITY: This ITP signed
8bb63e74-c446-5633-b0e8-cf0608c38b4a | note | – – – – – – – – –
3592fd52-131a-5f68-9bb8-1af32258898b | note | IP
c3d8638b-d7f7-5fb7-b5e5-0f704acc18d6 | note | – – – – – – – – –
799c1563-7c1b-5152-adb1-88dfda7226f9 | note | RESPONSIBILITY: Fulton Hogan Engineer
f7faab44-4901-564d-8e42-3ebae442182f | note | – – – – – – – – –
3c231b2f-5210-5bd6-89c5-c316892aa0f4 | textbox | DATE:
a97a33ea-d0e9-4819-b658-3f6946944f4d | section | 2 - Construction/Erection of Formwork
d97a59a8-6d22-4a15-baba-a0606d7f5777 | checkpoint | 2.1 Excavation
88a3669a-aca7-5865-a85c-ac04bef7d4a1 | note | FREQUENCY: Prior to concrete pour
ad55279f-6299-53e7-877c-8b5e0457c234 | note | – – – – – – – – –
9153d72f-c2d6-5730-a1b6-18445b1af9ef | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
90fd914e-22a2-5a6c-8db9-ee31f3356f90 | note | – – – – – – – – –
d70c5d61-1db7-5f9e-b8c5-d501ad0d74fa | note | REFERENCE DOCUMENTS: Contract Drawings
cc517d7d-4f5a-5ba4-ada5-1156631a51e9 | note | – – – – – – – – –
fe80f032-9648-54a8-9e01-8e0d759aee28 | note | INSPECTION/TEST METHOD: Inspect
a39d2377-fecb-52d4-8e47-7cffd56bb2bb | note | – – – – – – – – –
f0fd268b-0c61-5a03-924e-ce80712361ed | note | RECORD OF CONFORMITY: This ITP signed
0bcf5431-c7bc-5d46-a162-87d76b6100fe | note | – – – – – – – – –
6a13a4ad-74e4-54e2-9dea-cebab3bf4ef6 | note | IP
27575af1-b166-5699-a05d-f2f9a33e5c51 | note | – – – – – – – – –
d98c355c-40c7-564f-8e32-d7b51405cdd2 | note | RESPONSIBILITY: Fulton Hogan Engineer
bbdd2e00-15b1-5745-bcb4-aaa9a5079a13 | note | – – – – – – – – –
103a6655-74eb-5c06-8d35-b2bed1e02fb7 | textbox | DATE:
d937c4fa-f396-4217-a2fb-b44c0b29ac1d | checkpoint | 2.2 Construction Methodology
6f84ebc4-83f5-59ff-8f36-3324497c5e33 | note | FREQUENCY: Prior to erection
f5eb5e7f-4303-579c-b0df-0fcd25c6be95 | note | – – – – – – – – –
6fe5d4e8-2ed6-57f5-8e0a-94aacefd0575 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
a1f454cc-b4a4-59f9-ae6a-4b982c3f38e5 | note | ○ Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
d23bb824-1e73-5976-a64a-d8d06d6b64d2 | note | – – – – – – – – –
a72885dd-0406-59d2-a4b4-3d738d185d7c | note | REFERENCE DOCUMENTS: Contract Drawings
5c8f5603-930f-5220-bc0d-b6d15042f83a | note | – – – – – – – – –
a560d265-001d-5f4e-b2f0-7b434591aed5 | note | INSPECTION/TEST METHOD: Verify
a95b040e-e540-5d7e-abaa-b0c165afd9c1 | note | – – – – – – – – –
1a811363-2e5f-5f23-bcd5-2eff95e144f8 | note | RECORD OF CONFORMITY: This ITP signed
3657e009-daab-5b15-aa3f-8110124aadb0 | note | – – – – – – – – –
d93fed71-874b-5fac-a6cf-39059e816c13 | note | IP
556c77ed-2197-50b6-a301-899302167858 | note | – – – – – – – – –
b143264b-c625-53df-8ae0-b7b6df2feb92 | note | RESPONSIBILITY: Fulton Hogan Engineer
5900980a-2ca9-5041-bbdd-162182d63c5c | note | – – – – – – – – –
4b248494-ba97-5bf6-9b3f-dcebf5a50c9c | textbox | DATE:
5cc64f0e-54c1-4d5d-aff9-a8671c8bd24e | section | 3 - Pre-Pour Planning and Inspection
7874606e-bd9c-4f36-9120-5a16146e4404 | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
1ba3785a-a718-58d7-a3ee-7eaffc481d98 | note | FREQUENCY: Prior to concrete pour
cc1e379a-2de8-559b-8ae6-e5c06fc19c33 | note | – – – – – – – – –
4fe381b8-6582-59a0-bbe5-8abe7b8c5d30 | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent.
299c9b22-8919-570d-9279-0031747c4d57 | note | ○ Hold Point released by the Superintendent.
0c2b1d6d-152c-5857-9733-ac16aa39e5ec | note | – – – – – – – – –
b3db3420-bb87-5703-b700-0896312c2f44 | note | REFERENCE DOCUMENTS: Contract Drawings
efd78d68-8e1a-5b2f-a4bb-4516a28c7696 | note | – – – – – – – – –
3eee1b70-052c-54ac-b721-82abd93aea10 | note | INSPECTION/TEST METHOD: Verify
cecdc91d-3876-5eed-a591-54f5385b2082 | note | – – – – – – – – –
850e2b97-e209-53d8-8ac8-87fb0f253b19 | note | RECORD OF CONFORMITY: This ITP signed
256dcb61-2831-5382-88b0-fff0af25eda3 | note | – – – – – – – – –
acdcac39-2d42-5df2-b0c0-93414c653269 | note | HP
e0e678b0-d6cd-5274-b4b2-17e1a4e9b39b | note | – – – – – – – – –
27a03528-1313-5f81-a8f4-43105eed8774 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
a5454626-84c1-512c-8dc1-e7862b012649 | note | – – – – – – – – –
e511ca69-89ed-52a3-88f8-ccef276cfca3 | textbox | DATE:
2584832c-c3b1-4e35-8f35-a81f5974b4d8 | signoff | AUTHORITY HOLDPOINT
5eb05f29-074b-470e-a314-b4ef6cd8ea9f | checkpoint | 3.2 Formwork levels and position
4be408d1-8908-524b-8eba-5b49a670293b | note | FREQUENCY: Prior to concrete pour
dcc4aef5-d103-5058-b6f4-336545235c2a | note | – – – – – – – – –
fbb282fc-bc49-5fcf-8056-2d0574cd77e9 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
eafce72e-f33c-5f2d-b770-f0ab764cbb83 | note | – – – – – – – – –
a57fcc99-f1b3-5822-98fe-1de15678b42c | note | REFERENCE DOCUMENTS: Contract Drawings
029f6b5e-9587-5ac3-8703-4dc668f074b3 | note | – – – – – – – – –
fe152ceb-096a-5c5f-ab16-e1bf5c9d5800 | note | INSPECTION/TEST METHOD: Verify
4c075581-bcb0-5fab-a6dd-4f5e0d878d2b | note | – – – – – – – – –
c90cb03a-9ff3-55ea-bb18-ec021d386c4f | note | RECORD OF CONFORMITY: This ITP signed
7d8bf87c-e855-5ef2-8823-6fb764197ccb | note | – – – – – – – – –
e32097f8-0bac-5ea2-904a-ac9caab6930d | note | SCP, HP*
b429f16b-7b05-50ca-9e7b-4763b4ddb5e6 | note | – – – – – – – – –
299651fc-7284-538d-8ed6-ea0a505e53cd | note | RESPONSIBILITY: Fulton Hogan Engineer
40aab4fe-ffad-5cf9-84ff-7e74b7a7fbc6 | note | – – – – – – – – –
95f58f67-2070-5ef1-8781-a686b20f9224 | textbox | DATE:
89f2fa38-5a2c-4d84-acb6-d3aa84dc6611 | checkpoint | 3.3 Location of splices
9f773078-3826-5397-a22b-ec7e54b54f67 | note | FREQUENCY: Schedule Review
f3f468f9-367b-5941-94e6-64d131d3517f | note | – – – – – – – – –
1634bfd3-aa73-518a-9875-bd4054135f71 | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
32627135-d9ff-5dd4-b54b-a4816bbb01cc | note | – – – – – – – – –
92bc9622-be87-551d-95f3-38b322c80a18 | note | REFERENCE DOCUMENTS: Contract Drawings
22755d18-27d1-5712-98c2-89270f9b12da | note | – – – – – – – – –
15454582-595b-5466-b80a-98ba69d0e5cb | note | INSPECTION/TEST METHOD: Inspect
663e1dab-7fce-5f30-97a6-e74bd25777d9 | note | – – – – – – – – –
b66f036e-0b13-562d-b911-052ff8c07587 | note | RECORD OF CONFORMITY: This ITP signed
1083b751-7979-5748-842e-5da3dfcf2a11 | note | – – – – – – – – –
fcc77151-1ff2-566e-b545-bdd14690557f | note | IP
06995ac1-152e-5374-b566-9d7cf70f433b | note | – – – – – – – – –
2da6a969-4b50-5ceb-9b59-599675078847 | note | RESPONSIBILITY: Fulton Hogan
1bc30163-44e4-56ae-a712-278e5c30e8c4 | note | – – – – – – – – –
6e4a2c32-7349-5e90-9814-7cb7c2aa63e3 | textbox | DATE:
70d48b74-0429-40a2-8c94-f1520147da08 | checkpoint | 3.4 Cleaning formwork
9c1576e9-71d4-50cf-8dd3-e321c33a6828 | note | FREQUENCY: Each concrete pour
dfcfffc9-8b04-52aa-a1f8-8c8d69a0b46b | note | – – – – – – – – –
94292f1f-b03b-55d8-bb33-5fae716f0d5a | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
4b88b0e9-7a8d-5510-a7f6-294136df9f36 | note | – – – – – – – – –
0ad18d57-3470-5a56-9974-5805445e63a8 | note | REFERENCE DOCUMENTS: 503.13
c5903e13-92a0-5be0-8b31-277aac84e598 | note | – – – – – – – – –
c44684eb-0fae-5673-a3a3-2325a1f8862e | note | INSPECTION/TEST METHOD: Verify
d3764aea-ff7c-52a6-aaa9-aeb142c0ebea | note | – – – – – – – – –
3c18e4e8-9f7f-5f8c-bec1-632c120addc9 | note | RECORD OF CONFORMITY: This ITP signed
aa0333e1-6201-5598-acef-f490bfbb9015 | note | – – – – – – – – –
05fdae00-6033-51d9-8719-1a3590662cb8 | note | IP
246c364d-a9bd-5d6f-a1bc-e24449262b6a | note | – – – – – – – – –
045940d6-a420-56da-baad-059c42b155d0 | note | RESPONSIBILITY: Fulton Hogan
d7dc694b-8f85-501f-99bb-f6afcd1c8ec8 | note | – – – – – – – – –
de759931-98f9-575b-94a2-31ce9c544d70 | textbox | DATE:
239ab170-9850-4acd-95c8-bbea4a4dab87 | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
3531b3d9-3e28-50c4-8994-0a79fe471931 | note | FREQUENCY: Prior to concrete pour
02b0b45a-6b4f-5673-945d-87c08bd35fa2 | note | – – – – – – – – –
ce11bb07-c272-5940-bffb-1e39cb2195e9 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. Pre-pour checklist completed and signed.
8a8c9069-cdaf-5cc3-9fdc-e7d1b6d31c73 | note | – – – – – – – – –
075cf5cd-cba0-57a0-a42b-64734809a501 | note | REFERENCE DOCUMENTS: 503.07
f7cc433d-f61b-5aba-a384-4ee8b3162def | note | – – – – – – – – –
a36b37d3-85fe-5652-b898-b856fa8fca24 | note | INSPECTION/TEST METHOD: Verify
8d7ce70b-28a8-5a38-9d1e-43d1586f34e7 | note | – – – – – – – – –
7273ef9b-68a1-562d-a379-106e7a01db74 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
c7dcb20f-dd07-5b4f-843e-9da4417d9df5 | note | – – – – – – – – –
5bb5c517-517b-5b5a-adb7-ca2d593ae9d1 | note | HP
2ff17a02-4163-5755-b230-755dcd1407f4 | note | – – – – – – – – –
9b2cb6fe-ae91-5875-bc68-18f153827e6f | note | RESPONSIBILITY: Fulton Hogan / VicRoads
7e415b1f-ebe6-5018-912e-1b54065b0e67 | note | – – – – – – – – –
64bc3538-b7eb-5cee-91ed-2117fd65897b | textbox | DATE:
e691a134-a23a-4763-9d6a-8f67b3369b89 | signoff | AUTHORITY HOLDPOINT
efbaf413-0a7b-486e-9819-399d24ec3cf3 | checkpoint | 3.6 Reinforcement assembly of piles
d92db8fb-d0e9-5b15-93ff-a275c5de047b | note | FREQUENCY: Prior to concrete pour
63471aef-1088-5369-8a45-f01ddd55c62d | note | – – – – – – – – –
628dde67-14b6-50e7-a570-b8bed20d52d3 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
29672eae-d897-5959-aeba-e0bb4605a453 | note | – – – – – – – – –
c69259b0-708f-5629-9b89-dbe80183122d | note | REFERENCE DOCUMENTS: 503.07
18bb3e70-6b41-5ff4-8848-5eb8db5bfb5f | note | – – – – – – – – –
a11aa167-d894-5bd0-b616-5f8e6172bb94 | note | INSPECTION/TEST METHOD: Verify
70d74133-8a20-5570-8dfd-bfa40e2d2b34 | note | – – – – – – – – –
4eb7ac25-64dc-5b81-a63b-255381b2ceef | note | RECORD OF CONFORMITY: This ITP signed
b8c7e9f1-9b00-5cac-b640-47e77c146a05 | note | – – – – – – – – –
13bbe4a6-74b0-5fc6-b102-4c67da868eb1 | note | HP
21ba62e0-67f3-5f6b-a144-95c1c07dab69 | note | – – – – – – – – –
44b0431e-2d32-5588-aec6-62a34f9ae8d6 | note | RESPONSIBILITY: Fulton Hogan
b36f301c-0e4a-59a6-b802-416426025c49 | note | – – – – – – – – –
01b4aecd-83a7-5a31-9850-86bdb6c87315 | textbox | DATE:
a494e72d-12dc-4edb-b743-6405994d51ed | signoff | AUTHORITY HOLDPOINT
5d9b0a82-fdf6-448a-a418-181e2fa8e079 | checkpoint | 3.7 Monitoring weather
04c2053f-9999-5ad5-826c-c2c00f77bad6 | note | FREQUENCY: Prior to concrete pour
725bd6ee-de12-516b-91e1-c10af622b76c | note | – – – – – – – – –
deb009e1-4739-5c3b-a56a-b2f542c0e1b9 | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
78c70688-1c14-558d-8e69-400b70cef072 | note | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
fd34b2cc-1fca-5c76-8a66-20f5cb14c188 | note | – – – – – – – – –
191e264d-6c4b-5f86-9481-da5c2fa8b7e0 | note | REFERENCE DOCUMENTS: 503.07
5eaf05e0-ca85-5ff4-bb31-ad71c337dea7 | note | – – – – – – – – –
6fe055cf-3543-541e-a96f-83f3e7b7b40f | note | INSPECTION/TEST METHOD: Verify
4975a77a-73d9-54ce-8a35-da54f677d8fa | note | – – – – – – – – –
4f1ecdca-eac5-5547-81a5-6b2e8dd37319 | note | RECORD OF CONFORMITY: This ITP signed
80491c3b-1341-5868-9a8f-561f397eb00c | note | – – – – – – – – –
37879a1c-9c41-5491-ba8e-58989325daf5 | note | IP
d1e0071d-8e46-5245-8177-33ebf67cc225 | note | – – – – – – – – –
66312798-9e36-5d0d-b3a9-df044fbd1a5f | note | RESPONSIBILITY: Fulton Hogan
10669802-5a8f-5b5b-9363-7048aefdfbee | note | – – – – – – – – –
f5addca3-e701-5387-b62e-22d0293763d4 | textbox | DATE:
b3cf55c7-3976-46e7-9e8b-919097af8cd9 | checkpoint | 3.8 Assessment of Base Thickness
44074337-9e86-525e-a705-80dcd286d8fc | note | FREQUENCY: Prior to lot closure
a4e0748e-9fea-5ee7-a4ee-6cde43e808c6 | note | – – – – – – – – –
524ac808-a89e-59e8-9d1b-490f0e2a3551 | note | ACCEPTANCE CRITERIA: Within the lots defined for assessment of compressive strength the surface levels of the subbase shall be measured as specified in Section 173. Levels of the base surface shall be taken at the same locations as taken on the subbase.
30b155cf-2a6c-524d-be20-cc8fa854149c | note | – – – – – – – – –
4a624b82-e1e0-53c6-9d43-8c926420140c | note | REFERENCE DOCUMENTS: 503.05
4b978024-bb21-55b1-88f2-9a3e63cbe952 | note | – – – – – – – – –
cff10511-c51b-5c7f-8165-ddc5aa377796 | note | INSPECTION/TEST METHOD: Verify
f2016bdf-0a89-5d2b-81c4-f7665a3907d6 | note | – – – – – – – – –
1595e92a-6011-52ac-8086-a59b88146902 | note | RECORD OF CONFORMITY: This ITP signed
93f1552d-506b-5c14-86f8-121a3b382ec4 | note | – – – – – – – – –
b6e54de6-f51a-52d8-b36d-408219092141 | note | TP
2efda4a1-fb6e-586e-96f8-0e3bb10d8e66 | note | – – – – – – – – –
801253d9-65f9-59a3-bc8b-5d53248aced7 | note | RESPONSIBILITY: Fulton Hogan
e86b6073-2ac6-50de-8ee3-1ec960941e5c | note | – – – – – – – – –
5a1fba42-f080-5781-b003-6ea0fc478a8e | textbox | DATE:
8b1ed8a3-0ea5-4c20-a52d-72c0c1036d32 | checkpoint | 3.9 Concrete Sampling and Testing
47a13209-ca59-5b62-ac9a-b94b76498b3d | note | FREQUENCY: Prior to placement
03741feb-8c3b-5303-9851-626bd110f0f4 | note | – – – – – – – – –
8f04a41b-91ff-52bd-b170-4c916167df02 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for slump test.
807d049d-75af-52d8-a289-dd965a9b84d4 | note | – – – – – – – – –
74ed235d-621d-5e9f-bc27-0826f818bc19 | note | REFERENCE DOCUMENTS: 503.05
4e4dbc9d-e07a-58e5-8fd9-8e499d719274 | note | – – – – – – – – –
f256a05e-bb47-554c-aaab-ef4ec9d63437 | note | INSPECTION/TEST METHOD: Verify
3f1d9b5c-a285-57e1-8e64-be24c2235714 | note | – – – – – – – – –
65967ff0-a806-5dff-8615-29de4ca60351 | note | RECORD OF CONFORMITY: This ITP signed
ccca0fd6-d0a2-5cb1-8f74-0de7877da543 | note | – – – – – – – – –
1be596ba-04d7-5cdb-a379-d4295b154806 | note | TP
3ffe64db-72a1-5574-b04c-4d34cfcf56de | note | – – – – – – – – –
9a508705-7148-5523-b5ea-9d7cc59104e2 | note | RESPONSIBILITY: Fulton Hogan
7227383e-a8a7-5a99-8eef-e9be7a7e4e69 | note | – – – – – – – – –
169050bf-49c7-5256-9f98-82db1c1f23f5 | textbox | DATE:
a65388ff-0064-4c16-9ea3-be3a6387144e | checkpoint | 3.10 Sampling and Testing of Cylinder Specimens
dfe3bcbe-9502-5fce-b07a-8ddd9ccd595b | note | FREQUENCY: During concrete pour
78ca5358-0104-526d-a482-7cbb594cf38d | note | – – – – – – – – –
efc1e020-bf87-54aa-a031-24ca51d305ee | note | ACCEPTANCE CRITERIA: The Contractor shall record 3 sample, prepare, cure and compression test of 12 cylinders cast on site in accordance with AS 1012.
89c96f8d-cffd-5bb9-bbee-17f2e59db4b9 | note | ○ The concrete shall be sampled at the point of discharge to the roadbed. Each sample shall consist of two cylinder specimens for testing at age 28 days.
4a219b1a-de3d-5b92-86de-5b79d909f2db | note | – – – – – – – – –
dbf3e387-a8f6-571a-aeb5-7417390be9bd | note | REFERENCE DOCUMENTS: 503.05
d4e9cc90-d47e-588c-afa1-6b9f5bffac6c | note | – – – – – – – – –
e3752728-0bb9-544b-82cb-f97f59cc3187 | note | INSPECTION/TEST METHOD: Verify
06792d64-7acb-5f7d-a91c-358796128731 | note | – – – – – – – – –
01839aee-60ad-5d56-a979-43df55e09c96 | note | RECORD OF CONFORMITY: This ITP signed
b69814c2-034b-5c6b-a8e3-ab1f10215b38 | note | – – – – – – – – –
b1d4d79f-4dfa-53af-8142-77b19add5382 | note | TP
930f10ee-13e5-5920-ad25-8fbb43c499cc | note | – – – – – – – – –
f40f751f-ef4a-5d4b-a3a8-1ec3a751bf7f | note | RESPONSIBILITY: Fulton Hogan
4fc5da4f-8bf9-5956-a686-e994d0b6c561 | note | – – – – – – – – –
d0a6f8be-32fc-591f-96be-8b52aeb08914 | textbox | DATE:
f50752b4-3cb3-40dc-afab-ec115f4f61ab | section | 4 - Placing and Finishing Concrete
9c190358-e4e3-4138-a75d-b5758f10577d | checkpoint | 4.1 Carry out sampling of concrete
aa57fa91-39fa-5edf-a68a-5b7564ffb27e | note | FREQUENCY: Each concrete pour
7d33e8e5-77bc-5d03-858a-749f7d603b17 | note | – – – – – – – – –
dd17f76a-75f0-596d-8afc-efda4b257eba | note | ACCEPTANCE CRITERIA: Sampling in accordance with 503.05
063cfcbb-893c-50c1-b314-7a29675f3945 | note | – – – – – – – – –
5b37fd92-0a7c-50d6-a941-b801ba7c55ff | note | REFERENCE DOCUMENTS: 503.05
457a186f-aefd-5ac4-bbb6-6f2c4f6c0255 | note | – – – – – – – – –
2714ea17-542c-5c0f-b10e-e04083ed35f4 | note | INSPECTION/TEST METHOD: Checklist
cd31dd5c-371a-5719-91e4-ce7bae1ce65c | note | – – – – – – – – –
f37b245e-ff5a-57be-9770-7d2b66cf9801 | note | RECORD OF CONFORMITY: This ITP signed
0c683d1a-2c66-5ab1-92f2-229372015ede | note | – – – – – – – – –
838953bb-8228-52f1-96ee-554a84974ed1 | note | IP
f8207ef6-e565-5a71-ab3e-541ecba6e724 | note | – – – – – – – – –
91950fae-4d6a-5546-8bca-df67f9d5d539 | note | RESPONSIBILITY: Fulton Hogan
650e4b12-3a83-56d7-99e8-1194881e43e0 | note | – – – – – – – – –
4288553f-547b-5088-b140-e1e7ec36a4a6 | textbox | DATE:
b1afcd2d-acd4-4e48-aa97-e10e4ec734f7 | checkpoint | 4.2 Discharge time
1572cca6-f2b3-5ab3-b740-2bed577c3cd6 | note | FREQUENCY: Each concrete pour
b1491cfe-5ae5-5c6e-a6f3-35cee7971d35 | note | – – – – – – – – –
c96d9f82-612f-5bfa-b9f2-6a987da9cc32 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
b3f8c7e1-19f3-5c05-bcfb-9b33f27b1d56 | note | – – – – – – – – –
fab75a36-c027-508a-85be-1669c30b7d96 | note | REFERENCE DOCUMENTS: 503.05
c0946a85-0fba-55d4-9831-70a86d794171 | note | – – – – – – – – –
ca439071-3c68-56ac-aa68-36267057f0c8 | note | INSPECTION/TEST METHOD: Verify
fcab3dbb-087c-59b7-94cd-c92cab54caa8 | note | – – – – – – – – –
7e77ced0-8185-5909-800e-99d789822eec | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
b0ee9a16-268e-5d1a-a3be-3493a6e09ce8 | note | – – – – – – – – –
78a31c55-a3d9-5879-a53f-38c0b4fb7fb3 | note | IP
a9b5a6c3-5349-5d9c-82c3-2b7cead469f5 | note | – – – – – – – – –
4141ee83-3b9f-5066-b481-17363201dad9 | note | RESPONSIBILITY: Fulton Hogan
3f0552b2-66f9-592a-916b-a4b295dd6e1e | note | – – – – – – – – –
6ca7ac6f-4205-5708-ba93-4638a1308a9e | textbox | DATE:
7e2eca95-35a0-4c32-a9ad-ce3d5746f4ca | checkpoint | 4.3 Concrete Placement
1113fd0c-ec3c-5284-b4eb-c9307f8c16ce | note | FREQUENCY: Each concrete pour
c69b805c-6c0a-513a-ac67-af84784df073 | note | – – – – – – – – –
eff5202e-f11c-5241-a833-d2444ff095e6 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until the proposed method of placement, spacing of planned transverse construction joints and the provision of dowels, constructed formwork, reinforcement and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Superintendent.
e4a2bf21-51ac-52cd-93a7-357b67a1caa4 | note | – – – – – – – – –
68048c9a-2d4e-5a44-bd3c-a18742ff190c | note | REFERENCE DOCUMENTS: 503.05
faabee6f-4a6a-5313-8bb0-04c2a71296ab | note | – – – – – – – – –
0b89fc78-baa9-50a5-8aee-3dce0a5664d3 | note | INSPECTION/TEST METHOD: Verify
9c45e66c-6520-5500-aae1-1f7beee3a115 | note | – – – – – – – – –
af47eaa9-f07b-5613-a1fc-5baf53b94927 | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
0986614f-ff22-519e-95c5-02e82f6da88d | note | – – – – – – – – –
7527eccd-e084-5df0-bdab-5b0e69f7a470 | note | HP
53da4795-b23f-51e5-970b-c833c569e333 | note | – – – – – – – – –
45c9f93c-997e-55f6-949f-b50c1fb0edf6 | note | RESPONSIBILITY: Fulton Hogan Engineer
45b529c1-40de-568b-a8bc-0f664eecde8f | note | – – – – – – – – –
d4851de8-5c56-56fc-9e40-3b03a048a0bc | textbox | DATE:
d69e4d81-784d-44a7-8dea-92003292f132 | signoff | AUTHORITY HOLDPOINT
915a3aec-1999-4415-9af1-dab96757b54b | checkpoint | 4.4 Methodology of Placement
6a19f89d-9127-5313-8165-be3c295c6812 | note | FREQUENCY: Each concrete pour
1d4ba823-9b7a-50e1-ba70-ea362933e45d | note | – – – – – – – – –
e737702a-7e42-596c-b922-7f40dc7c35b3 | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
261f2b9b-2fb1-5272-8048-2b22e2841359 | note | ○ Concrete shall not be moved horizontally by vibrators
3bb10f10-541f-5ee2-89f2-7bfa9794084b | note | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
b9d61311-28f7-59fe-b009-d7457e87dd7e | note | – – – – – – – – –
d40791bc-98cf-5a0e-86c5-5bef1cdd7e84 | note | REFERENCE DOCUMENTS: 503.07
ef2249f7-6555-5205-bf7e-e4ba991a0406 | note | – – – – – – – – –
8100b35c-6959-52cf-a537-48dcab754d65 | note | INSPECTION/TEST METHOD: Verify
037cec3a-4994-51e9-adc7-4dba077d45c2 | note | – – – – – – – – –
7a98f9af-b073-5236-b859-45634f8f4757 | note | RECORD OF CONFORMITY: This ITP signed
85bc509f-0168-52c7-bc4a-60ba48b8b96d | note | – – – – – – – – –
4608744a-9858-59f9-bbb8-d84579b3732d | note | IP
3aa7bd9c-a2a6-5a53-81dd-3c74203f06c6 | note | – – – – – – – – –
b44e0a90-3511-52f5-8925-e539ddae1bec | note | RESPONSIBILITY: Fulton Hogan
a4c84fce-3aa2-57a8-b609-2d1567daa81a | note | – – – – – – – – –
cfe0125f-4c28-5173-bba0-78e951212841 | textbox | DATE:
2dde18fe-29ba-4704-bcd7-711aada0eba7 | checkpoint | 4.5 Compaction
36e71144-6069-5db7-ac7a-25979f994783 | note | FREQUENCY: During concrete pour
010f38fd-1dde-5341-8c08-04f9d1785665 | note | – – – – – – – – –
81a03662-cb61-5150-a6c2-e07374d28cb8 | note | ACCEPTANCE CRITERIA: Base and subbase concrete shall be compacted to meet the requirements of clause 503.05.
69218d15-f7aa-5b92-b17d-6d34ee708b11 | note | ○ Concrete placed around dowel bars shall be carefully vibrated without the vibrators touching the dowels.
c5ff9fd2-5f31-5094-a0dc-50cbbba2f6ed | note | – – – – – – – – –
ec43eeca-bc6d-5a61-87c1-5986dd638ac9 | note | REFERENCE DOCUMENTS: 503.07
8db6c405-abbf-56fb-a125-7eb6dfdf9bf2 | note | – – – – – – – – –
e6c14400-5216-55b4-b4e4-129478eadb30 | note | INSPECTION/TEST METHOD: Verify
c01a189c-f202-53cf-a938-1b7df89b9971 | note | – – – – – – – – –
c2cc7d3d-83a4-5cf7-8fd9-808d3638b55d | note | RECORD OF CONFORMITY: This ITP signed
acb1b051-2d05-5f97-9772-1d25e77dcfe1 | note | – – – – – – – – –
7b6e4624-8e3a-55c3-bf2e-4176d5065f66 | note | IP
5eaf6379-22da-5368-924b-9fc2e7e2c822 | note | – – – – – – – – –
5d4aaeac-d7c5-5ccc-a688-5b070b5aa78e | note | RESPONSIBILITY: Fulton Hogan
7c831447-0e45-5b70-b980-799f9aba841d | note | – – – – – – – – –
a09b99d4-ab98-570a-84fb-1134518a5db9 | textbox | DATE:
34983c0a-80b7-4725-8121-707018303053 | checkpoint | 4.6 Screeding and Finishing
be1c2de0-ca8f-529e-98f5-cd802eca79c6 | note | FREQUENCY: Post concrete pour
8f3b809f-1ca4-5f9e-a62b-23470e82ee06 | note | – – – – – – – – –
051d0678-894b-5810-b386-35cd8bc06498 | note | ACCEPTANCE CRITERIA: The concrete shall be finished to provide a dense and homogeneous concrete surface satisfying the requirements of clause 503.03.
9a17d260-14c1-591a-952a-a627e73af145 | note | ○ The subbase concrete shall be finished to a uniform non-textured surface. The base concrete shall be finished to a textured surface as specified.
e55679b5-8fee-5069-9c58-6f867904bc8b | note | – – – – – – – – –
b445cdc6-554f-5a01-957e-7785b3d711b2 | note | REFERENCE DOCUMENTS: 503.07
9fe74349-fe59-56c4-a4eb-5883adaefdc2 | note | – – – – – – – – –
9dc06e8b-dd28-588e-9338-90af5f195aa2 | note | INSPECTION/TEST METHOD: Verify
8757f419-c9e8-5880-ad01-68954f20e15d | note | – – – – – – – – –
47fcb387-a265-54fc-a4b1-4c6173b61576 | note | RECORD OF CONFORMITY: This ITP signed
812f8a79-af6b-52af-85a6-0360e05788cb | note | – – – – – – – – –
1f4d5177-e9aa-524f-8376-a8320f2f6b52 | note | IP
159cbbfc-86c3-5dd9-a711-a18761dd3ff7 | note | – – – – – – – – –
4d6e365f-ecb9-514c-8976-2eb91006ba6e | note | RESPONSIBILITY: Fulton Hogan
b4cc68d0-8e79-5dae-88ae-e0e09ba05ca2 | note | – – – – – – – – –
e0c91e40-6ecf-57b8-9d2b-c8b6ee342df1 | textbox | DATE:
fb0f0764-0fde-43c8-8a72-cfe208abf095 | checkpoint | 4.7 Joint Sealants
7a26d74a-7bf1-5538-9ae5-90b41761c0bc | note | FREQUENCY: Post concrete pour
8d1be5da-5caf-5349-8589-315bfbbd1549 | note | – – – – – – – – –
d97b1fbe-f0cf-5ea2-869c-8b48fac3abc6 | note | ACCEPTANCE CRITERIA: Permanent seals shall be either a neoprene compression seal or an in situ cast silicone sealant. A full technical description of the proposed sealant and method of installation recommended by its manufacturer shall be submitted for approval by the Superintendent at least four weeks prior to installation.
b2d6a02a-f4c6-5877-8e7d-60ccdfb8871b | note | – – – – – – – – –
ed47f61f-318e-5d2c-a1e3-1408a36c4636 | note | REFERENCE DOCUMENTS: Contract Drawings
2b0a4eff-6ac0-59a7-a7e3-c4204c5190d0 | note | – – – – – – – – –
bacbfad9-f1f3-5a85-b7f4-7cb8e38d8096 | note | INSPECTION/TEST METHOD: Verify
99d3ace1-660d-581e-801e-d7ddb47a304b | note | – – – – – – – – –
af22a589-761f-5eec-9839-411f73b889fa | note | RECORD OF CONFORMITY: This ITP signed
f2179d2b-df0f-5390-bc04-b22d4c0873db | note | – – – – – – – – –
77bcc625-f88f-59aa-a980-c7bdb13fbdc6 | note | IP
ff9a5e82-52e0-5f92-8760-20f165118b45 | note | – – – – – – – – –
ee5ba922-49a4-5919-8486-410206abe284 | note | RESPONSIBILITY: Fulton Hogan Engineer
75b9332b-f73b-58f4-8ae2-13fb3b458a39 | note | – – – – – – – – –
93cc9f17-b5a8-5e85-9ba5-b09a818e2d79 | textbox | DATE:
79b58804-5843-4511-9ac9-41368fcfd286 | checkpoint | 4.8 Joint Sealants for Base
80f25cc3-ecc0-5ec5-9a19-34a2db8d0004 | note | FREQUENCY: Post concrete pour
41060f97-eec2-5bed-aedb-5c3e425488aa | note | – – – – – – – – –
91497e99-c483-5468-9c41-b15ab5618ea2 | note | ACCEPTANCE CRITERIA: Joints shall be constructed as specified and shown on the drawings.
70aec2dc-7d95-5e38-844f-276a5ff456ec | note | ○ Joints shall be straight and vertical. Transverse joints shall be continuous from edge to edge of the pavement.
4fec1155-ea2b-556e-a2ab-514a963da47f | note | ○ Tie bars shall be installed such that anchorage strength of at least 85% of the yield strength of the bar is developed upon hardening of the base.
40cdea34-ea0a-5c70-a25f-eeb826a97229 | note | – – – – – – – – –
eea1a817-24d8-501c-9307-8972c473f861 | note | REFERENCE DOCUMENTS: 503.13
56b3c2cf-2f15-5225-bb77-3d1ac3642a44 | note | – – – – – – – – –
5fef2637-1860-5f72-bb6b-883fb777970b | note | INSPECTION/TEST METHOD: Verify
b80ced5b-a4d2-5c2b-b416-2a2668c7c37e | note | – – – – – – – – –
b2b14c93-f5b5-5200-b2c2-a7b53f6f05a6 | note | RECORD OF CONFORMITY: This ITP signed
53850ad1-d93f-5646-9cb5-895b7a91c784 | note | – – – – – – – – –
2de64c77-0f17-5f38-b175-5d61ebd77727 | note | IP
1aaea936-9830-54ff-a417-638d5ea674db | note | – – – – – – – – –
85eaed34-5cd4-56fe-82a3-fca58caea1a5 | note | RESPONSIBILITY: Fulton Hogan
03f0177a-b05c-59ad-b0dd-5692b4af4fff | note | – – – – – – – – –
00d46abb-76a7-567c-b11f-f6cceba9827c | textbox | DATE:
4e8fd795-4503-4bf6-b908-7ce7dc6d4621 | checkpoint | 4.9 Texturing of Surface
7843546a-1f98-58e4-93b4-21c1849342d9 | note | FREQUENCY: Post concrete pour
871933bc-81f1-5a88-8e24-80ba80b421cb | note | – – – – – – – – –
25d9b621-dc51-5047-b7ba-5bbc7a3d8c26 | note | ACCEPTANCE CRITERIA: Texturing of the concrete surface shall be carried out to the standard of surface specified in clause 503.21. The textured surface shall extend across the full width of the base and shall be uniform in appearance.
714df04f-6b20-5754-88ac-e21bf7591e36 | note | – – – – – – – – –
60a99502-f353-5e86-830e-cc109cdfb9d2 | note | REFERENCE DOCUMENTS: 503.17
6f3a8aa7-4118-5b1d-bb8b-3eeb81ce92e0 | note | – – – – – – – – –
c8eb041a-59c3-5b48-a1e4-ae1a3ec3e9c0 | note | INSPECTION/TEST METHOD: Verify
0b23a120-7e6d-5e8a-a9b3-e450735dabd4 | note | – – – – – – – – –
1abc5488-34fb-5b3d-9613-0f7cc8973063 | note | RECORD OF CONFORMITY: This ITP signed
f533f22d-98fb-5890-9391-5328637a7d4b | note | – – – – – – – – –
3db28fb1-bf9c-5721-8c91-dbbcea7b7836 | note | IP
64d91e8d-0947-5655-92ac-e4e8d1fbbb7d | note | – – – – – – – – –
717b0ee5-11ef-5dc6-8188-cf387d35562a | note | RESPONSIBILITY: Fulton Hogan
c3e95187-ce91-5578-9441-32d12e271927 | note | – – – – – – – – –
c6f5e953-d8a7-5f3a-a430-70594934a8ff | textbox | DATE:
2eea7d69-d73c-428c-94cd-df66eab56a8c | section | 5 - Post-Pour Details and Inspection
97209bf3-9073-435a-a299-87b58f6fa603 | checkpoint | 5.1 Curing and Protection
51e2b752-5866-5d49-a7f6-75f791dd301e | note | FREQUENCY: Post concrete pour
8ee5a0ec-a4ed-593d-bff8-b37770c43441 | note | – – – – – – – – –
7ecfee52-97a8-58f1-abfb-eec04dc83778 | note | ACCEPTANCE CRITERIA: Curing of the base and subbase concrete shall be undertaken by the use of a curing compound sprayed onto the freshly laid concrete at the application rates specified in this clause. Curing compound shall not be sprayed when bleed water is present.
9b9cf562-11a4-5805-ad2e-99312a17a57e | note | – – – – – – – – –
82f47bb9-3a89-580e-8b38-dcada99e8b1b | note | REFERENCE DOCUMENTS: 503.18
ff301476-90b8-5282-a470-94dd6e15ae0c | note | – – – – – – – – –
31ad47eb-31e8-592e-8845-b3cb33181406 | note | INSPECTION/TEST METHOD: Verify
2c88e543-9d90-5fb7-b31f-7e5bc47f0be4 | note | – – – – – – – – –
0acc862c-9cb1-5a06-a488-4918f484552f | note | RECORD OF CONFORMITY: This ITP signed
a0a2b693-e7eb-5765-9766-d6f515bc30c5 | note | – – – – – – – – –
f6eb5275-014a-5d4d-b1d0-e88c657e7e93 | note | IP
f074b462-f531-5a64-b379-4c118330c38e | note | – – – – – – – – –
eee9ffa5-b932-5c45-ac14-01b47d1a4ad7 | note | RESPONSIBILITY: Fulton Hogan
6639af31-3d33-59c5-a49c-922e342a2000 | note | – – – – – – – – –
29aeda69-af9c-5862-a1d6-89fb2ea71bfa | textbox | DATE:
a767066c-cd26-47ef-86aa-f39798f6d895 | checkpoint | 5.2 Curing Compounds
e4e5ab36-cc33-5851-a1d5-7659a809a91d | note | FREQUENCY: Post concrete pour
913c2db1-cf2e-5876-b018-4b8afc95c22a | note | – – – – – – – – –
7f1eed51-d8a6-5ea6-9eb3-602b0a281fd8 | note | ACCEPTANCE CRITERIA: Prior to the use of curing compounds, the Contractor shall submit to the Superintendent for review not less than four weeks prior to placement of concrete
0b8ecb63-68a2-528d-8923-7f0cffb7254b | note | – – – – – – – – –
f5b5628e-fbde-5705-adb9-233326dbe675 | note | REFERENCE DOCUMENTS: 503.18
5f6b8d8e-1cd3-521f-9b8f-2753434d3861 | note | – – – – – – – – –
93a75fcb-fbbc-5aa6-919b-1a86380f0870 | note | INSPECTION/TEST METHOD: Verify
145819c5-a4da-5458-8307-73d892732eb6 | note | – – – – – – – – –
374faa81-06d7-5fd1-b39e-32427a5873a5 | note | RECORD OF CONFORMITY: This ITP signed
bc001f78-154b-54dd-ac92-1cc62af3572a | note | – – – – – – – – –
17d6e4a1-75f6-501e-b650-ae183c594928 | note | HP
2c5bd676-4419-5cf7-a938-8b35c3cffa31 | note | – – – – – – – – –
36ef66fb-ab65-51e4-95d1-52ae76c6c196 | note | RESPONSIBILITY: Fulton Hogan Engineer
adb920eb-1665-548a-9610-68c7119f0e59 | note | – – – – – – – – –
9455f3d6-bb4f-534b-ab4c-f2688ad9fc65 | textbox | DATE:
2bab4560-36d4-4ae9-9d77-03c3e4e75706 | signoff | AUTHORITY HOLDPOINT
d886eccd-801f-49ac-989f-1951c99cf386 | checkpoint | 5.3 Formwork removal
890957d1-a7e5-5ebe-8aac-2f1a635ee256 | note | FREQUENCY: Post concrete pour
467f3e8f-8740-50a3-8732-d4b3e43a0077 | note | – – – – – – – – –
3f9f75ba-4671-5fe6-b33e-a4c85e12188d | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
375a65f2-76bf-5959-a9a0-3b81d8eaab6d | note | – – – – – – – – –
d2a6b0f4-0466-598f-ab9f-30e919743bd9 | note | REFERENCE DOCUMENTS: Contract Drawings
4b65b850-e9ff-5bc4-a7cb-6ccca63d891a | note | – – – – – – – – –
5db3765f-84c7-5b52-b430-dedad2726f06 | note | INSPECTION/TEST METHOD: Verify
593f49fe-aee9-524d-949f-acd273c2d728 | note | – – – – – – – – –
28f5cf22-61c5-564e-887c-34f55d03108f | note | RECORD OF CONFORMITY: This ITP signed
f7d46ad4-4d09-599f-8ec8-d7fd28f0458f | note | – – – – – – – – –
c2020471-1ba8-5541-b7f6-a4089c9fdfb0 | note | IP
4180c662-9a22-5fc0-bee3-dfc38868a3bb | note | – – – – – – – – –
a17b187e-be86-5b98-9ab0-3c9942ba8ac3 | note | RESPONSIBILITY: Fulton Hogan
1b4bc718-fe69-5c09-b03e-1d57e287de28 | note | – – – – – – – – –
0a6a1ff1-aabc-5aaf-8cd4-da8f553430dc | textbox | DATE:
420ba3be-2f63-49d0-ab2c-12adc86dca5f | checkpoint | 5.4 Concrete Base Course
6387b3a2-135a-528c-8695-b0e45df9a758 | note | FREQUENCY: Post concrete pour
79af7926-219f-58b9-8067-81114d9bc935 | note | – – – – – – – – –
b4fde2c0-2b3c-5300-a137-361278bb0eff | note | ACCEPTANCE CRITERIA: With the exception of concrete saws, personnel the concrete base course shall not be trafficked until the in situ compressive strength has reached at least 20 MPa based on concrete cylinder testing.
6594a3ff-411a-5bac-891a-962e1c8ecc85 | note | – – – – – – – – –
f2374e13-8010-5fd9-82f8-e9130a7fed86 | note | REFERENCE DOCUMENTS: 503.19
44f59312-0e9b-50d7-89d6-9887fe30baad | note | – – – – – – – – –
dd99be6e-b6d9-5c96-baf0-11d05ac62926 | note | INSPECTION/TEST METHOD: Verify
decc2b07-a6f2-569f-93b3-986d51bd3d45 | note | – – – – – – – – –
f66116cc-b611-5689-9109-144234b287f4 | note | RECORD OF CONFORMITY: This ITP signed
24865326-44d0-5617-afc6-6af625e8f7b8 | note | – – – – – – – – –
007e1e5a-794d-54cf-a66b-965eb6ad9c1b | note | HP
a131493c-db76-5e7a-abf3-2356298bb346 | note | – – – – – – – – –
2accfbad-20a4-5de6-b1c1-e575fe3ed635 | note | RESPONSIBILITY: Fulton Hogan Engineer
17f60c55-d759-52d3-ba66-bf5bbcff9e4e | note | – – – – – – – – –
ec93135f-cee0-5c17-a628-0d38705c233c | textbox | DATE:
6da06b8e-51ef-4aae-af20-161afc6efadb | signoff | AUTHORITY HOLDPOINT
d99e0a79-ea97-4478-85e8-5b894640d27b | checkpoint | 5.5 Positional tolerance and dimensions of concrete members and piles
22914b63-82a9-5ed0-a900-933c9091add7 | note | FREQUENCY: Each concrete pour
221caa7d-f4b8-57fe-bcc1-f4f9d7a47c67 | note | – – – – – – – – –
82b7adbf-4cb9-545a-8361-2aef08594de5 | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
00b6443a-3bb3-5b05-ac53-aabd3935b186 | note | – – – – – – – – –
ec8a7275-59ae-5ae6-b769-144f15e268d4 | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5
184a4b0b-aa7b-59b2-a7e1-2ef5fe1da253 | note | – – – – – – – – –
6ed9e69a-e8f3-53c2-ac88-19ce37c814b7 | note | INSPECTION/TEST METHOD: Verify
4e5f2657-0755-50f6-9f98-83a540c2025e | note | – – – – – – – – –
11b1fcfa-627d-5486-bd2e-cc301ff9c53c | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
9ca063b5-58ba-588b-8f71-d305b0710beb | note | – – – – – – – – –
fca4615f-8a37-5fba-888f-427eddd6195e | note | IP
bb9993df-b6fe-5965-80d8-f6a63cf8ed87 | note | – – – – – – – – –
50e1ec6a-2210-54cb-80a6-8eecf563cb34 | note | RESPONSIBILITY: Fulton Hogan
145f0074-a3d4-5fdf-88ac-ff13d472d9c8 | note | – – – – – – – – –
dd539756-f490-574d-976d-f70ea334425f | textbox | DATE:
386461d7-ef73-4f9d-9064-a9d87bb6f253 | checkpoint | 5.6 Concrete Sampling and Testing
bfe1d69a-fe79-568d-8d39-60003409cde0 | note | FREQUENCY: Prior to lot closure
b837f79c-02db-53e5-8b8f-0c0e626d0a62 | note | – – – – – – – – –
fec95667-1465-56c8-ab23-09f061fe07a4 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for compressive strength. The required strength of concrete must be in accordance with the drawings
d8c9319f-02ce-5d5f-a4c8-985d57a58ceb | note | – – – – – – – – –
abb382b7-3135-5b66-9268-1e9f1d130981 | note | REFERENCE DOCUMENTS: 503.05
927070c0-63a1-58ac-a8c0-01ab0852980a | note | – – – – – – – – –
89dad1ee-0c08-5e8d-a857-ae7f8af0936e | note | INSPECTION/TEST METHOD: Verify
596c9261-ef49-5b0a-8dbb-0b2dc6a37f26 | note | – – – – – – – – –
efa1425c-f5c6-5dce-87e3-bc49f0da89dc | note | RECORD OF CONFORMITY: This ITP signed
e4487b89-141d-5437-89d9-3f934b38a0a2 | note | – – – – – – – – –
df2cc42c-0e1c-5530-8331-5c265611144f | note | TP
f6b4faac-2c59-520f-8183-c08c154285ea | note | – – – – – – – – –
eb16b8c5-3bc5-50af-8293-412fcc8d32f9 | note | RESPONSIBILITY: Fulton Hogan
40680d37-a2bf-53c2-9c54-d756cd94d12d | note | – – – – – – – – –
447d837f-7002-55c6-adfb-84a09618c9cf | textbox | DATE:
166fe52e-2216-454d-9f5d-3301f713d3bd | checkpoint | 5.7 Curing and Protection
a23e362b-c5eb-5635-8112-d89505667106 | note | FREQUENCY: Post concrete pour
66433f19-f3da-5960-931c-99c7c0f2e725 | note | – – – – – – – – –
1a21331a-25e3-5f03-9ce8-1536ac4879e0 | note | ACCEPTANCE CRITERIA: Saw cutting and joint sealing shall be allowed on the finished base concrete until the in situ strength of the concrete is at least 60% of the target 28 day compressive strength.
87263c64-8bfe-5a8b-af13-94502049c7b2 | note | – – – – – – – – –
b832fee0-54a3-58c2-a632-7919ec5eb388 | note | REFERENCE DOCUMENTS: 503.18
4c3f1fd1-2c7d-5d0b-9c33-b06193ba0332 | note | – – – – – – – – –
258f6ac2-26a6-59d5-9007-b6db0f923be6 | note | INSPECTION/TEST METHOD: Verify
23fd6c46-5400-55a4-a5ea-11ef6acf5f91 | note | – – – – – – – – –
4a975f46-55a1-5098-ac18-ffcfb3ae6afb | note | RECORD OF CONFORMITY: This ITP signed
7170ea63-1de6-5752-aad9-f51e0e80f78b | note | – – – – – – – – –
cac4e5ce-bbc8-56dd-bbff-08fa02bbd806 | note | IP
cf398a46-658f-57cb-9420-6010c14b3717 | note | – – – – – – – – –
f55f0d51-aa15-518b-9815-20d8b958946f | note | RESPONSIBILITY: Fulton Hogan
098d660c-b1ba-5263-80be-61fee0c8a0bf | note | – – – – – – – – –
41e9b7d3-580b-57fd-99c3-b95030d944a0 | textbox | DATE:
5a9dd3c1-d04d-4143-b59d-cb37c593f329 | checkpoint | 5.8 As Built Drawings
7ebd2ae8-db1e-558f-96a2-332d467588a5 | note | FREQUENCY: Prior to lot closure
a1a0767a-8cfd-5814-aff2-9780c9ea0996 | note | – – – – – – – – –
34f2433d-8fe0-5213-932a-91f59c77cd93 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
0d03725d-4f16-591f-a782-c176dc5cfb92 | note | – – – – – – – – –
c211bb9c-3c47-5f1f-ab74-185cff713867 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
ac8e88e1-23a2-56ea-9bce-afec3f843a09 | note | – – – – – – – – –
bf8fdb28-8555-5c8d-99ee-22be2d5536fc | note | INSPECTION/TEST METHOD: Verify
3c9a8e84-66d8-527b-8c8e-a63b65160cf4 | note | – – – – – – – – –
9e5a7059-5515-5f82-8994-c1a97f81f5de | note | RECORD OF CONFORMITY: This ITP signed
38f881de-483c-575f-a190-d573f3e05ce8 | note | – – – – – – – – –
23401cfd-97ba-5dad-b7f8-d9b0fc6fcda4 | note | IP
e7a23315-2e0b-5767-a56e-7b6e074774bb | note | – – – – – – – – –
00c84a4b-1ade-5a2b-95a6-088f2f874d5d | note | RESPONSIBILITY: Fulton Hogan
365e4841-43e7-542b-ae64-dfee3215fa55 | note | – – – – – – – – –
7a7f8038-ca9d-5f56-95cb-30f06a0d40fa | textbox | DATE:
0fe93149-4d13-4d01-b24e-3c260df6a627 | checkpoint | Final Inspection
ff830918-47d4-5fda-b66e-d8993d7e5cef | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7c8b05d5-0e26-5369-8b8a-a1291841dfe7 | textbox | Print Name:
398e3c95-3407-5e17-8245-2b2c4e506c6c | textbox | Position:
650eee47-34f0-5475-b7c4-bf342f3a7469 | textbox | Date:
7d3137c5-652a-459c-94cc-e4da8999437e | checklist | FHC-ITP-034 - Cement Treated Crushed Rock Sub-base Rev0 | itp | FHC-ITP-034 - Cement Treated Crushed Rock Sub-base Rev0
bb020c89-a712-4714-ac21-242c836a60d3 | section | 1 - Preliminary Works
dbd99c95-46c0-4d5c-ae13-3931ab3a5588 | checkpoint | 1.1 Check for correct documentation
3640f9bd-9444-5278-98a5-c606e4328d8b | note | FREQUENCY: Prior to commencing any activity
6e776c15-2a4d-565f-bb8c-944854d7f4c0 | note | – – – – – – – – –
7fd1099a-1475-5de8-9aae-e88c91b126aa | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ec3abcb9-987e-5cde-bab2-d8c24c03b686 | note | – using the correct and complete set of drawings
b273f3ae-1231-580e-a829-a3c13d06ad82 | note | – all drawings are the latest revision
7751e1c7-f25b-5d8a-8d6e-8de7bc86e8f0 | note | – – – – – – – – –
017de6d9-6fe5-52a7-a644-2f7cb8aff4c7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9a6b0bb4-436b-5fd3-9135-7d38b32e6ecc | note | – – – – – – – – –
78e001dd-aba5-53a6-99c9-2d29d66528ff | note | INSPECTION/TEST METHOD: Visual inspection
66d41447-bd3d-5a44-821b-fa48be309bb1 | note | – – – – – – – – –
55e8d1ff-a067-50b2-846e-23d0973b77d8 | note | RECORD OF CONFORMITY: This ITP signed
44e18f58-b53f-5bd6-b5d8-8c1f3ab985d1 | note | – – – – – – – – –
f043846d-54aa-58b3-b380-2fc94fe75e42 | note | HP*
c3b306df-1761-57d5-9825-82b98bbe54d8 | note | – – – – – – – – –
f218a855-49ad-5683-95d1-20c6c887db64 | note | RESPONSIBILITY: Fulton Hogan Engineer
7f067ed7-85a1-5998-acfc-b67ad2e29c53 | note | – – – – – – – – –
2ceb29a2-e7e8-5d3a-b192-c231f186927d | textbox | DATE:
8f2d8ca9-f721-4683-b1a2-1f7db218e12f | checkpoint | 1.2 Implementation of all measures and controls
a992ba7a-9afa-5a45-8afd-48f62ce51a78 | note | FREQUENCY: Prior to commencing any activity
7578ed5b-af11-5790-8256-0e3544c9ded6 | note | – – – – – – – – –
0bcca2d0-d7f2-5db3-83ba-e0392ba787a9 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
eb0d1223-13a4-549c-9841-12ac4b32be9e | note | – – – – – – – – –
d264170e-b762-5d1e-b20c-54ca76074d81 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
fb3845ee-c439-5a5c-84d6-75c21d697f5e | note | – – – – – – – – –
4439050d-894b-5a29-839a-b0635d7e75e0 | note | INSPECTION/TEST METHOD: Visual Inspection
f98558bb-f0d3-59ee-afa0-55f6152c542f | note | – – – – – – – – –
a3238d91-0670-5f83-8018-9cd193fe32e1 | note | RECORD OF CONFORMITY: This ITP signed
e51e7017-c775-56d9-93fd-d5fa0bdf826a | note | – – – – – – – – –
78bd1038-6c70-551f-9775-7b96049253aa | note | HP*
5cca0ea1-7b42-57d1-873a-8187b989a4c5 | note | – – – – – – – – –
85cc35c0-9794-5473-8227-06c247c3670b | note | RESPONSIBILITY: Fulton Hogan Engineer
67801205-d8fd-5faa-8ac9-b2fec58a0255 | note | – – – – – – – – –
a75ad751-fac5-59d2-9180-18af3081c944 | textbox | DATE:
7645f93d-3ed9-4c57-91f6-991c69d812c1 | checkpoint | 1.3 Verify Material
66307776-6f28-53c0-a135-2ad1c7c19ade | note | FREQUENCY: Each day
2164a31d-1417-5822-8dac-8c5f2a9208de | note | – – – – – – – – –
ca6a7755-887d-5677-a383-d14fa93840cf | note | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase.
6651e4f1-2ba9-5954-934e-e76adef7e8dd | note | • The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
5d26f32a-25d3-5e68-894c-a308a5d96d88 | note | – – – – – – – – –
213b5bab-e0c5-565e-ad08-2f7a19d9db4f | note | REFERENCE DOCUMENTS: Section 815 Cl 306.04
27a3dc6d-2024-5e6b-af6d-67f355115b9e | note | – – – – – – – – –
fcc1c7d0-d773-54a2-8011-e623b9425967 | note | INSPECTION/TEST METHOD: Verify
fce1b77b-2f24-57e9-9cee-1b3cc74b59fd | note | – – – – – – – – –
4b8dd5c1-ada2-51ec-80f8-bba708d29d6f | note | RECORD OF CONFORMITY: Material certificate from supplier
bf9d2bb3-172b-5f87-9d8f-446dcf1e08d3 | note | – – – – – – – – –
bb700aa8-1768-525e-b2c0-feebf8e2d3b0 | note | HP*
983ace69-eb7a-59bb-af75-8a40d4e2204d | note | – – – – – – – – –
32d4e250-06f8-52d0-8519-b7d7e85c05b4 | note | RESPONSIBILITY: Fulton Hogan Engineer
b3845197-2608-50ab-a042-35badeef43f6 | note | – – – – – – – – –
9eb33dd0-fad5-514c-9d64-3e10ecfbdecf | textbox | DATE:
0c8f095b-8ea4-488b-a2f4-8f47e6ebe0c7 | checkpoint | 1.3 UCS Testing
d7c779fc-2048-580c-90b6-e85a52a04043 | note | FREQUENCY: Each day
c9ab78c8-53b6-5960-9c57-fa1e2506e0cc | note | – – – – – – – – –
dcec5a7c-36a8-5f22-8a6a-c936eadea112 | note | ACCEPTANCE CRITERIA: The Contractor shall carry out UCS testing in accordance with the test frequency specified in Table 815.141.
db19cf02-0efb-5fe3-bda3-5f87a86ba72b | note | • The UCS during production shall be assessed on a ‘rolling average’ basis where the average of the most recent three UCS test results shall not be less than the minimum value specified in Table 815.101. For the purposes of UCS testing, one representative sample of fully mixed cement treated material shall be taken either from the plant or at the point of delivery in accordance with AS 5101.2.2
cbf66f58-e623-54d0-a20c-e55cd4ca061c | note | – – – – – – – – –
7083273e-1719-5153-bde4-fc6e9e0ccc22 | note | REFERENCE DOCUMENTS: Section 815
23ed8e3f-8567-5dfd-9d45-581092a8f987 | note | – – – – – – – – –
7f29f35f-dad8-59b2-b5c6-4e6169233bfd | note | INSPECTION/TEST METHOD: Verify
f7b0dc31-7563-501a-b45c-323253850da5 | note | – – – – – – – – –
043eab86-c48a-50d2-b0ba-cc9e756b9eee | note | RECORD OF CONFORMITY: Test Results
8d91155e-a598-51cd-a698-62d00ed5a1c8 | note | – – – – – – – – –
06c22fc5-3e8e-5c8b-8267-ffd3fa56e4e0 | note | HP*
ec4175aa-2588-5676-ac77-f644eaa90cfc | note | – – – – – – – – –
07ebe683-521e-5570-ab0d-98171a013db8 | note | RESPONSIBILITY: Fulton Hogan Engineer
b8e1d8ab-971e-59b4-b011-0f85a6d695c5 | note | – – – – – – – – –
5a478d2b-4443-5a0d-b4f1-a7322e37f6ef | textbox | DATE:
4632941d-8ccf-4639-8a25-72242bccd1a8 | section | 2 - Construction Works
59329201-9759-4f3d-8721-0914a5add1a8 | checkpoint | 2.1 The area has been inspected and Proof rolled by MRPA and consent has been given to proceed with placement of sub-base).
9431004d-9250-5aec-92d9-d2c9b8edcaa7 | note | FREQUENCY: Each lot
a127f0b1-4f0a-5077-864b-972d84d496f2 | note | – – – – – – – – –
de87628a-0b5a-527d-b6bd-966b4d9309cb | note | ACCEPTANCE CRITERIA: Sub-grade has been inspected, No visible deformation or springing in presence of Superintendent's Rep. Test rolling Plant to comply with requirements of Cl 173.03.
2fda9767-6875-5fd2-88a8-4acefc3576b8 | note | • Where any groundwater is encountered the Superintendents representative must be notified.
787295ab-9a26-5f46-b74a-e69220db3af8 | note | • Ensure that test results for underlying lot are available prior to placing sub-base material
801bb901-dd37-5a03-b134-ed2721eeaeb6 | note | – – – – – – – – –
39d36e10-d54a-50ee-bffe-6aa9bf078681 | note | REFERENCE DOCUMENTS: Cl 173.03
a8b74352-e49f-5e84-b0f9-70be5ddfe710 | note | – – – – – – – – –
ca5aca17-78cc-5bfa-8525-c14c0ad4f1a3 | note | INSPECTION/TEST METHOD: Verify
f0e8c991-9013-5935-96ac-421a030466e6 | note | – – – – – – – – –
1daa248f-25d0-518b-8c1e-afae85099859 | note | RECORD OF CONFORMITY: This ITP signed
627940e2-3324-5920-b8c1-7b550ea75b91 | note | – – – – – – – – –
d172c240-988b-52ce-98e5-6b544aa22198 | note | HP
3bb92ec2-f7d8-5045-8b66-2dfeeddb5026 | note | – – – – – – – – –
1c963ac9-2110-5cf5-83e7-1ae806fdb156 | note | RESPONSIBILITY: Fulton Hogan Engineer / MRPA
4504ba98-5670-5ff1-9568-b65e710fbde0 | note | – – – – – – – – –
8efd8cce-559d-5195-be63-692d1afc4223 | textbox | DATE:
a651d70a-a13e-4d30-b63b-641305e136ca | signoff | AUTHORITY HOLDPOINT
34f94655-4cc4-4ff6-b1c5-b3c2ba05828e | checkpoint | Maximum allowable working time and moisture content
6e8aed59-52c9-5c28-b54e-74c2d12b492b | note | FREQUENCY: Each lot
818ece81-309c-5259-91ef-eddc95dbbb39 | note | – – – – – – – – –
e64faf32-e801-590e-9334-08e33de48445 | note | ACCEPTANCE CRITERIA: The cementitious treated subbase material shall be placed, trimmed to level and fully compacted within the maximum allowable working time specified in Table 306.091.
bbde2f11-7534-50a1-b128-649a8fa0d67a | note | • The moisture content of the material at the time of spreading and compaction shall not differ from the Modified optimum moisture content, by less than 0.5% and not more than 1.0% by mass.
427cf6ee-e3d4-53c3-a9e2-c424395772ae | note | – – – – – – – – –
4d57de6a-a311-5f06-a62e-2abf6ba9bfd2 | note | REFERENCE DOCUMENTS: Cl 306.05, Cl 306.09
65d3972d-1edb-5dbf-90e6-9a57df9d2fc3 | note | – – – – – – – – –
6d5eec6e-91e6-55e1-bb53-aff6ad7be640 | note | INSPECTION/TEST METHOD: Verify
403969e4-bf59-5a71-884c-a110328f74f7 | note | – – – – – – – – –
74c64c60-d263-531c-9a64-0ee92d02e46b | note | RECORD OF CONFORMITY: This ITP signed
5521a907-1298-550c-b6b3-bf05f1329deb | note | – – – – – – – – –
0f61afcc-af0e-5e31-a912-7483fa7d5d22 | note | HP*
50b49565-b53e-5120-9577-e5d8b90545b0 | note | – – – – – – – – –
d2b27190-05ab-5c10-ab41-8ef38b4bff23 | note | RESPONSIBILITY: Fulton Hogan Engineer
78edd749-ee43-524e-bfb3-34f9e3567446 | note | – – – – – – – – –
b98abade-7ce8-56cb-8ce7-1ff8c437bab5 | textbox | DATE:
c055e6c8-e707-41ea-83b4-6caffbaeb6a7 | checkpoint | 2.3 Jointing
689769fc-678f-5d0b-ace1-7d311b8de3bb | note | FREQUENCY: Each lot
7c79379e-0799-5897-9441-2b046364fc4f | note | – – – – – – – – –
83a38aa2-45a3-5cae-b3e6-76b928cd6b37 | note | ACCEPTANCE CRITERIA: a) material shall be spread in such a manner as to minimise the number of joints;
6c700481-c0ec-57cb-8163-f82276a918e1 | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
94353fc2-49d7-5536-bd20-a2618c50d9c4 | note | – – – – – – – – –
dbff17c1-2786-5c5e-8647-70a66f9b4351 | note | REFERENCE DOCUMENTS: Cl 306.08
d90eb57f-e5bf-50bf-9ee6-44f46f4a0fb0 | note | – – – – – – – – –
73b0f141-4dfd-5fc0-be66-a8538c8210dc | note | INSPECTION/TEST METHOD: Verify
ec9e88e4-e505-59a6-b2f7-b8f78dae6401 | note | – – – – – – – – –
1d4ed091-8c43-579a-b9a6-21320cb19194 | note | RECORD OF CONFORMITY: This ITP signed
4438288d-655c-5d66-8525-5d406ded34b1 | note | – – – – – – – – –
7cce449f-b6ce-5ebd-92f4-e3f38e3c2fde | note | HP*
13ec14d7-324b-51d0-a4b4-16ebb84c85da | note | – – – – – – – – –
b8d30504-6d50-559b-9a4e-8035ba2ad895 | note | RESPONSIBILITY: Fulton Hogan Engineer
0ab53aa4-534e-5f47-a73e-250e118c46f8 | note | – – – – – – – – –
366fa687-d085-58c7-8197-58de0adf0265 | textbox | DATE:
932af0a1-ee89-4907-aa95-89676bd5340f | checkpoint | Compaction Testing
9f22db29-595a-5b5c-844a-0fccb4ac7a33 | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
3961acdd-accc-5e14-8bb6-dec460a31087 | note | – – – – – – – – –
d499e176-2b48-5ccf-b199-656cecc0dbdc | note | ACCEPTANCE CRITERIA: Minimum MDR of 96% using Modified compaction effort. 3 lot test (Scale B).
2ab0f14e-3fae-5b95-b71d-ad02a5e3472e | note | • LOT SIZE = Lesser of 4000sqm or a days production is defined as a Lot.
069c704d-f461-589b-ad64-665319ff63a2 | note | • Every Lot to be tested for surface levels and density ratio using modified compactive effort
b0feb624-c743-5806-b972-ee735f6decf3 | note | • Compaction Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the requirement and then resort to one test per 2 lots .
cfbe8559-ac43-5bdd-b12c-acbe071599df | note | – – – – – – – – –
a8367f45-1916-5a34-ba55-d790bd9ba5f9 | note | REFERENCE DOCUMENTS: Cl 306.09
a6b0434e-22b7-5e42-9136-556b3205f68f | note | – – – – – – – – –
98190026-369f-5f0b-b18b-27214207b6ca | note | INSPECTION/TEST METHOD: Test Results
5838542f-7132-5f0c-b709-a24bf457e787 | note | – – – – – – – – –
9837b72f-6282-5422-a0bd-f7140c77f194 | note | RECORD OF CONFORMITY: This ITP signed
1888a255-a705-5b1f-a2c2-d385e5dae167 | note | – – – – – – – – –
7e5c896f-ec5b-5aeb-91ac-2f7a71aec1fa | note | TP/WP
b7304bc0-76fe-54b5-abc2-e526dcd4084b | note | – – – – – – – – –
78b7252c-3e99-5cf2-b28c-2362e357656e | note | RESPONSIBILITY: Fulton Hogan Engineer / MRPA
9360cc91-2b63-56a6-bbf4-d7fd51f1d076 | note | – – – – – – – – –
e7b37391-2f33-56f5-9d31-7deec5fdd2ac | textbox | DATE:
af9983f2-42af-4157-b2d7-d53394c73759 | checkpoint | 2.4 Level Checking and Conformity with Drawings
26ab56ff-51dd-5a80-b5c7-896ba48fc6d1 | note | FREQUENCY: Each lot
aecc9992-7a46-5b43-8821-326b8bb0736d | note | – – – – – – – – –
9fbe3a27-ce03-5548-b511-5cf0d0022093 | note | ACCEPTANCE CRITERIA: Sub-base shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
695b29b0-5f20-5cfe-a2c6-8124a597d9c4 | note | • Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
67a7e3d4-2a96-5c0a-83d0-1116c62c7295 | note | • Shape: no point deviation > 8mm from 3m straight edge in any direction
26ae1636-9131-5874-aea5-40cb55f28c02 | note | • Surface level tolerances:
7c167646-6d97-5160-a2ca-52771d0414f3 | note | • Range x = +6, -12mm
6614811b-3285-53ef-a1c3-a1a18886593c | note | • Max S = 13 mm
912c11a4-b962-57f4-96c9-ded4c3acca75 | note | • 40 measurements per lot (Scale B)
dd6edb72-021f-566a-afce-27c47f9ef93b | note | – – – – – – – – –
780d4816-be3a-5c29-bedf-b321777975f8 | note | REFERENCE DOCUMENTS: Cl 306.03
a8ac5025-ffcd-5e7b-8a7d-402af1be4eaf | note | – – – – – – – – –
1e7e163a-d316-5cfb-93ea-8940d915634b | note | INSPECTION/TEST METHOD: Verify
49cc08bf-18af-5972-84b8-d52b4d8c2d39 | note | – – – – – – – – –
c32f08d9-b986-54ae-8dc1-6db9a6a0b9f6 | note | RECORD OF CONFORMITY: Survey Report
def56804-732a-52db-bf7e-4bf0eea0f853 | note | – – – – – – – – –
8d60288c-31f6-542d-9c81-17dd51e49d04 | note | SCP, WP
cd7fcfbf-8364-5d6f-a769-553377ba8296 | note | – – – – – – – – –
acc7c92b-4a90-5257-84aa-275938ff31a3 | note | RESPONSIBILITY: Surveyor/Fulton Hogan Engineer/Foreman MRPA
a4b3f33f-b416-5d7f-9552-d159656e5402 | note | – – – – – – – – –
acf3a92c-edcd-5742-af85-43a0cb2cb69d | textbox | DATE:
80e5885a-5b04-4109-ade1-6b4130689b15 | checkpoint | 2.6 Final Proof Rolling
34d6c852-cc35-557b-906d-ee0837bbab5a | note | FREQUENCY: Proof Roll each layer
5b156d8b-c363-5306-b052-f3f4b178e81f | note | – – – – – – – – –
84682a76-8170-5a6b-9164-c5aa2272a60b | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
9396b2af-bfa7-538d-bd33-360f836b8cc2 | note | – – – – – – – – –
23347b17-8360-5e06-9e84-b7be4d76e9c5 | note | REFERENCE DOCUMENTS: Cl 173.03
fc036694-5669-5dd6-accd-3d2ec1dcd046 | note | – – – – – – – – –
bed484c5-93f3-5dc4-a74b-03575c25e458 | note | INSPECTION/TEST METHOD: Visual inspection
3338e39e-0a17-51e1-a9b0-99ae43230d1a | note | – – – – – – – – –
a3405821-fb3c-5443-9cb6-f9391655e2fa | note | RECORD OF CONFORMITY: This ITP signed
a753ccde-0d00-5290-8576-584efd7bd44c | note | – – – – – – – – –
6cfe7f72-8ae3-5db1-80ac-4a28bd4a509d | note | HP
2cb6d9ff-e4a6-519e-ae5f-9c1f7c88f90b | note | – – – – – – – – –
9502f7cb-01da-5096-be56-797e8a7076bc | note | RESPONSIBILITY: Fulton Hogan Engineer / Subcontractor
9536c61c-818d-512c-80d1-20c4c8b1b60e | note | – – – – – – – – –
f555efc5-fcf6-5f29-8a58-d8c6f9705637 | textbox | DATE:
58de8ce6-375d-4cce-88ca-5d92eeb911d8 | signoff | AUTHORITY HOLDPOINT
4f37429e-b84d-4ed0-a999-3a9044c28ba2 | checkpoint | 2.4 Curing and Protection of Compacted Layers
43f517c4-e828-5ad6-ae67-56405bd248d7 | note | FREQUENCY: Each lot
9e3853c8-e964-5bba-a586-5c0ccaee39c9 | note | – – – – – – – – –
dabe2a87-9192-5840-9188-2144ba4ea815 | note | ACCEPTANCE CRITERIA: The minimum compacted thickness shall be not less than 100 mm and the maximum compacted thickness shall be no more than 180 mm and constructed within the tolerances specified in Clause 306.03.
6b8b9bac-6e5f-58a7-be1c-66de7e11bb82 | note | (a) Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified:
175ee5f6-26e2-5d4c-ab74-5b117c9d9fff | note | • The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
969da388-addb-5324-87fa-7d96ac4aa89b | note | • Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
6381c4ed-46d5-5153-ab20-aa71b196249d | note | • The subbase shall be kept in good order and condition and free from contamination.
071e5fac-2ced-5548-9aea-6d24072fe48e | note | – – – – – – – – –
ed15bc14-ef83-53fb-8449-5732c33b432d | note | REFERENCE DOCUMENTS: Cl 306.11
a8c7a009-dc1c-56d5-bdc2-8a0e046cd092 | note | – – – – – – – – –
e8a3e0ff-6ee0-5335-96e5-f6a21400e255 | note | INSPECTION/TEST METHOD: Verify
521080dc-1685-50e3-a4fe-a8f6a92a6893 | note | – – – – – – – – –
03d6ac65-4260-5d45-8be9-fb35c61b8af1 | note | RECORD OF CONFORMITY: This ITP signed
a2f3fb1e-ecfe-519f-8022-6116528afa9a | note | – – – – – – – – –
42188607-80c7-5c4f-ba99-ce86b08a4422 | note | HP*
2dfe25b5-1a8b-5462-b260-c087d14a2528 | note | – – – – – – – – –
59407a61-4027-5921-b396-1a52e941825e | note | RESPONSIBILITY: Fulton Hogan Engineer
25b111cb-4a3c-540d-8e67-256eb27e8763 | note | – – – – – – – – –
6b655267-2543-5fd3-9781-190347958541 | textbox | DATE:
af4cc265-6a11-4967-a855-259d0128f994 | checkpoint | 2.7 Delivery Dockets
13c02834-2637-5b80-aeb6-1109a0eb3f4d | note | FREQUENCY: Each Day
23a3195a-fab2-5ea5-91dc-b9969590f678 | note | – – – – – – – – –
91de1c8b-57e2-5c36-a811-350ff09956b0 | note | ACCEPTANCE CRITERIA: FH shall make delivery dockets available for inspection on request
4a22894d-f25b-5799-ad9a-4df8fad09d59 | note | – – – – – – – – –
c0fc9ccd-df94-5af6-816a-1ef6ddbf8eeb | note | REFERENCE DOCUMENTS: Cl 306.07
f8798c04-54bc-5351-b1a6-fd0a0c3709e3 | note | – – – – – – – – –
bae78c57-34be-50e6-8dcd-edc2ed9acb88 | note | INSPECTION/TEST METHOD: Delivery Docket Submission
233df27b-a660-5da8-8076-5bd02c8bc19d | note | – – – – – – – – –
48152f9f-6805-5603-914a-7c1ed4affd00 | note | RECORD OF CONFORMITY: This ITP signed
76ff9429-b415-505e-a8fe-165853f861ef | note | – – – – – – – – –
96283044-fdbb-57c3-b573-ffe9a008bb7e | note | HP*
7bdbc0e2-e29e-54c6-8486-c7bf2d7af6ea | note | – – – – – – – – –
47587523-929d-5bc0-a39c-2e77fb0fdb9b | note | RESPONSIBILITY: Fulton Hogan Engineer
ae28fd9f-f474-52aa-b7ae-d3524aba34e1 | note | – – – – – – – – –
aeb0a879-a17a-525d-ae4f-991b8e4405c2 | textbox | DATE:
b9ba2284-8753-4666-9b02-d2f9b339c65a | checkpoint | Final Inspection
b13ff992-c563-53f0-9c97-890ac5dfb93e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
bd8fdd8f-581e-59a4-b0fb-d635b8960d59 | textbox | Print Name:
bfb6ede0-b01d-522e-8752-0a0725966470 | textbox | Position:
1b865c10-f3c2-509d-af93-fa1b2c97dd2e | textbox | Date:
d0a47c5c-a523-43e7-8833-9bea146a6c7f | checklist | FHC-ITP-035 - Line Marking Rev2 | itp | FHC-ITP-035 - Line Marking REV2
b5a0cc05-4a71-49f0-b24e-31ae81490fd7 | section | 1 - Preliminary Works
77234dd5-e885-47bb-ada4-f0c75d6fa2f8 | checkpoint | 1.1 Check for correct documentation
55ae6e94-ae64-5d57-8b35-db97271ce681 | note | FREQUENCY: Prior to commencing any activity
92735d63-3efc-5a54-91b9-869123bf2144 | note | – – – – – – – – –
ca5c434f-e767-5ced-9303-9a358f092a3b | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
4a9cc64c-78b7-52f9-ad15-01e064f9e303 | note | – using the correct and complete set of drawings
29b5a16e-cbd9-508c-81d7-61446b723639 | note | – all drawings are the latest revision
a83b4327-199d-5f3c-9b3a-2935d49716fc | note | – – – – – – – – –
ac3443e2-faab-5838-a6e3-04d2a0118745 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
0057df61-609e-5378-8b57-6712a1ba8c8e | note | – – – – – – – – –
db17ee1e-6166-57e8-9177-17d1aaf2420e | note | INSPECTION/TEST METHOD: Visual inspection
63ef6758-163c-57c4-a035-e538d9b31e4b | note | – – – – – – – – –
f2d244f2-d022-5e62-b572-a51a1e40e057 | note | RECORD OF CONFORMITY: This ITP signed off
b24bd665-1cd5-5fa3-a684-8825765df219 | note | – – – – – – – – –
c487c757-8623-5a3c-8b30-902eeb9ea83d | note | WP
b9e592f7-5058-5234-8956-067aa1b5bfd5 | note | – – – – – – – – –
4f0fdebc-99bb-5682-a6b8-bd60bbcd7f49 | note | RESPONSIBILITY: Fulton Hogan Engineer
ec285497-743b-5c53-8e02-042dae52a68b | note | – – – – – – – – –
dfd5bd83-d9c3-5a3e-bb85-9661be025f30 | textbox | DATE:
96ebd8c2-e1cf-4887-b139-70cd22b1e8b2 | checkpoint | 1.2 Implementation of all measures and controls
c357cbbb-cedc-53cb-9030-9a674d98ff72 | note | FREQUENCY: Prior to commencing any activity
0f0c4187-2b0e-5777-8e5b-71ade0e23bea | note | – – – – – – – – –
0325679f-ad37-544a-b2d9-6874dbac97e8 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
966abc8d-9d8f-50e2-bec7-264f2b2e4e9b | note | – – – – – – – – –
d5bb1452-b013-5574-baba-572d67e314de | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
0024bd52-93d8-5131-97e5-7736ee27468c | note | – – – – – – – – –
262dcb0e-fd32-58db-bdc9-a672f10d1bd1 | note | INSPECTION/TEST METHOD: Visual Inspection
aa758456-d7e2-5e76-a5cc-879b9746e5f1 | note | – – – – – – – – –
4b713cdf-7aab-5aa2-a7b3-90efc3a163e9 | note | RECORD OF CONFORMITY: This ITP signed off
960395fc-2a80-5d16-b566-ca11d5b0d44a | note | – – – – – – – – –
5ff5abf5-de00-5f02-95a3-b17a2a13dfed | note | WP
628ebcc9-a0dc-5e03-961a-75c21d3e471a | note | – – – – – – – – –
ba9c56c6-3296-5161-9322-ed48e75c514e | note | RESPONSIBILITY: Fulton Hogan Engineer
bd29292b-1d68-525c-b875-ba31d5a085f6 | note | – – – – – – – – –
584228e8-e098-5c6f-8558-cd346c19a7c9 | textbox | DATE:
cfa113ee-bfbb-4aa1-bd56-d4ccb87e9d4e | section | 2 - Construction Works
d2faddf8-7375-46bd-b1b7-5d700080d2e6 | checkpoint | 2.1 Setting Out
b1481751-870f-51f1-8d9f-4999d1ed1998 | note | FREQUENCY: Prior to start
5be3df33-393b-5383-8ed1-d25ff357717a | note | – – – – – – – – –
4ad0e0d7-c528-5dc6-932c-a0d8639d972a | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
3579dceb-87ce-5555-963c-7f920c7868cb | note | – – – – – – – – –
3a9bb3ae-48ce-52dc-b5dd-1b42159c97fc | note | REFERENCE DOCUMENTS: Drawings
f3554cb8-66e5-5b70-8dd8-81f004f45370 | note | – – – – – – – – –
8a8d2778-2cae-571d-bf62-6e5b5528e308 | note | INSPECTION/TEST METHOD: Visual Inspection
f0f02491-9f9b-5395-908e-212ba3ebcf0d | note | – – – – – – – – –
0277c588-d719-5fcb-a46b-069b59288869 | note | RECORD OF CONFORMITY: This ITP signed off
d6c740c1-033c-5f9c-a152-c95ccb06954d | note | – – – – – – – – –
085f24d4-f992-5144-a291-085489f7b456 | note | IP
796be8de-ef7c-5851-ba7d-965f9508d481 | note | – – – – – – – – –
bff131ee-4996-5689-b4b1-6396cbd679f8 | note | RESPONSIBILITY: Fulton Hogan Engineer
a8060ae1-1e5a-5d46-99a0-f984ee5e6765 | note | – – – – – – – – –
60ee1554-e4b8-522d-97ab-a3b48bd75efb | textbox | DATE:
08642cbd-fcf5-4b32-9e48-9a83dbd72daa | checkpoint | 2.2 Position of Markings
8ae91a21-026f-5e59-85ea-830bd8e9386c | note | FREQUENCY: Prior to application
4ac57a57-65a1-5a38-bd01-0945bbd51e3d | note | – – – – – – – – –
a418469a-1915-5443-83cd-9d3c224792bb | note | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
cf8e47b3-09bb-5c47-8183-fc4546bde7af | note | ○ Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2
3e2c6993-4d5e-5f42-8aee-4580eccae913 | note | – – – – – – – – –
68dadfe4-4e36-598c-af99-d1620fbda1f4 | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2 Drawings
63c1a36b-5434-5798-b332-09530ee0eb2e | note | – – – – – – – – –
4c89492e-15b3-5732-937a-47401795c717 | note | INSPECTION/TEST METHOD: Visual inspection
b861f262-9336-5143-ba26-37a1cd85b118 | note | – – – – – – – – –
1817a2dd-4522-5370-95b2-e1b4cf52a04f | note | RECORD OF CONFORMITY: This ITP signed off
fc2ca274-7a66-591a-ba30-045d60ada5bb | note | – – – – – – – – –
7a567825-50e9-5c3b-a0b2-8503c3a20dde | note | HP
d03eb0a9-91a0-5242-ac3d-569d7d3b478f | note | – – – – – – – – –
20defd97-bcc5-5ae9-86f2-848fa0b4bfd2 | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
6aea4afd-dcc8-5e10-87ec-33f1b8b62f81 | note | – – – – – – – – –
afc557b1-1130-5afa-9804-8f932eb584b7 | textbox | DATE:
342937fc-ddfa-40f9-958d-d12987261d49 | signoff | AUTHORITY HOLDPOINT
b6fa233e-5310-4e0b-9ccf-6f27f5badb57 | checkpoint | 2.3 Materials
a620635a-6262-5fb5-978f-facacac9dec6 | note | FREQUENCY: Prior to commencement
c2beab31-d0ca-5850-a27c-571523088b40 | note | – – – – – – – – –
26e870e5-8d64-510a-bfb3-d589685ca14a | note | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent‑borne paint or AS/NZS 4049.3 for water‑borne paint as listed in Section 175.
fbf9fe51-bce5-5232-b707-64fff26153ce | note | – – – – – – – – –
5536fa0a-50f2-5315-8043-72578d12e2fc | note | REFERENCE DOCUMENTS: 712.A04(c)
ee42108c-71f5-54c8-994e-96b618443a42 | note | – – – – – – – – –
0e610bda-fbeb-575a-a90a-3bd6535db82b | note | INSPECTION/TEST METHOD: Visual inspection
0b1007ff-8bff-5e08-82a5-067ce3e2efe2 | note | – – – – – – – – –
461f5b8c-a5c9-585f-9e34-cb2507134d50 | note | RECORD OF CONFORMITY: This ITP signed off
5c3958e6-d0b8-5f4b-8af8-29224c774858 | note | – – – – – – – – –
22460ca9-386a-5433-916e-abc30d8e2c1a | note | HP*
f5705061-d567-5ac4-86a2-70c4d3a448b7 | note | – – – – – – – – –
9d8b4262-01bc-5d34-b478-c7fba1f83e48 | note | RESPONSIBILITY: Fulton Hogan Engineer
08cde594-adef-5340-8d0a-4a5b491f3289 | note | – – – – – – – – –
13a2233c-0909-5d57-9f11-59c4e141ae97 | textbox | DATE:
71da3a20-74a3-4ee2-acc0-0ab670f4a72c | checkpoint | 2.4 General Markings
2aa529a6-2228-5c1f-a676-c7c4036e464a | note | FREQUENCY: Prior to commencement
bb011470-fc63-5caf-82fe-a59ac2faeb89 | note | – – – – – – – – –
49da4f4a-ae53-5321-a53c-e2b9bc367a57 | note | ACCEPTANCE CRITERIA: Linemarking shall be applied by a self propelled machine, and stencils shall be used with all roadmarking.
d0f24c45-9150-5e7b-a107-1ea51365ec59 | note | ○ All work must be undertaken by a contractor eligible for accreditation under the Painting Contractors Certification Programme (PCCP). This programme is administered by the CSIRO.
4ecbecb7-a8de-5c95-8b10-121ab9255150 | note | – – – – – – – – –
f97cb682-8101-5997-ba7b-7a50802d1bcc | note | REFERENCE DOCUMENTS: 712.D01(c)
052fc65e-68d1-5f1a-ad34-ada59f9e9b68 | note | – – – – – – – – –
e3869e35-e87d-5799-bac0-d8abe510c0eb | note | INSPECTION/TEST METHOD: Visual inspection
b782ed41-8a9b-5e17-a717-da7122bf7dbd | note | – – – – – – – – –
46aa605c-9304-5b60-8c46-07514456d11e | note | RECORD OF CONFORMITY: This ITP signed off
842a9405-3997-51d4-a4d1-f8b22b27b1a3 | note | – – – – – – – – –
f99fa759-9e5f-5b65-afae-b40197f30186 | note | HP*
56a87dcb-367d-5955-8bb1-a9981b866cfd | note | – – – – – – – – –
c1b7ba11-572b-54ff-82aa-d696a35e7f24 | note | RESPONSIBILITY: Fulton Hogan Engineer
8151377b-06a2-5971-a619-c9a80baccfbd | note | – – – – – – – – –
09279093-683d-5921-9015-92edbaf12c8a | textbox | DATE:
d9dc7e19-8814-4779-a8fb-bfa4342a5743 | section | 3 - Completion
55afe19c-4721-4836-b6a4-a4e4bad5ea15 | checkpoint | 3.1 Tolerances
2bdc30ca-0782-5270-ad8f-b5dd9551866e | note | FREQUENCY: Each marking
ec9e059e-cbb2-5fe4-bed8-0fed69ba1bb7 | note | – – – – – – – – –
d429e47d-c577-58f1-9c38-bd1865309462 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances as shown in Table 721.A101 when installing pavement markings.
cbe84fa2-070c-53d8-8995-cc91d2524717 | note | (i) Distance between centreline of marking and set out marks <30mm
0c0ff85a-f495-54a6-ad3b-8bcb753eb7d0 | note | (ii) Width of completed paint markings <15mm
b199d005-6e38-5e9e-a015-acf3e14c97e1 | note | (iii) Length of completed stripes and blocks 0 to +10% of specified length
dcc7fe2c-614c-5b49-a936-5890b185cadc | note | – – – – – – – – –
f091c379-6614-5d6e-b3c8-e1c10190ffd1 | note | REFERENCE DOCUMENTS: Table 712.A101
8f59d2ad-95e7-5f2f-935a-05be0d883717 | note | – – – – – – – – –
4042386a-cf78-5387-b050-45d94f3c6359 | note | INSPECTION/TEST METHOD: Verify
02a7ac08-ac4d-5cf6-83b9-bed65efe4ec8 | note | – – – – – – – – –
0a16c595-e3b0-5c44-be5a-31e2c7dc5a7b | note | RECORD OF CONFORMITY: This ITP signed off
bd6761dd-96a3-52bd-875b-01664a229f12 | note | – – – – – – – – –
f13aea8d-8777-5f19-a2c4-66038b1670ba | note | HP*
9bc0eda2-8cf0-546b-9c49-954eb4153c44 | note | – – – – – – – – –
573a804b-a166-5f0f-b7e1-20ae1746d527 | note | RESPONSIBILITY: Fulton Hogan Engineer
64804f6e-6c4c-55aa-b1d2-0e247aaa03ea | note | – – – – – – – – –
ff8dc4d6-b9db-5bc7-8203-de87c8667b6a | textbox | DATE:
cad94671-7359-42a7-9dd3-9c0b377f520f | checkpoint | 3.2 As-Built
f1b3a54d-b535-504b-9ee4-4b752509acb8 | note | FREQUENCY: Post Completion
4b0901ef-9e98-5757-8009-11d8854e87e6 | note | – – – – – – – – –
6cbc3d02-369f-5bcf-b103-cbf2af5cdf39 | note | ACCEPTANCE CRITERIA: As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
7c55193d-865c-59b6-a1b0-c68c1eaebafa | note | – – – – – – – – –
a664e42e-f64e-5006-8986-dc2cd6910de0 | note | REFERENCE DOCUMENTS: IFC Drawings, Survey Records
60f00ef4-809e-5435-8b78-96763595f0bb | note | – – – – – – – – –
a5e81877-ff88-53e1-8f30-b55d01833ac1 | note | INSPECTION/TEST METHOD: Document Review
2e8b8ecf-34bd-5041-a2ee-8fc2764edac3 | note | – – – – – – – – –
31b974b3-974a-5a65-8889-1701b6e303ea | note | RECORD OF CONFORMITY: This ITP signed off
8a12fe93-6e71-525b-9042-2f45e36805b4 | note | – – – – – – – – –
ca474353-a402-593a-81a4-2c13801f1ab6 | note | SCP
fdea8d93-99d3-50e3-990f-173122f95249 | note | – – – – – – – – –
1c4a25af-d607-56b0-9d9d-1e4306119101 | note | RESPONSIBILITY: Project Engineer/Surveyor
b5a5ed69-eeba-566b-913a-e70523f3934a | note | – – – – – – – – –
6dede78b-f9eb-5f41-a69a-ad20139da22a | textbox | DATE:
5646601b-c235-436c-b802-decc3f9c2164 | checkpoint | Final Inspection
ec1ad73a-a124-55ef-a983-dba7a0cf9d38 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4de3e426-4f06-5658-94a2-dc3b9e57922c | textbox | Print Name:
a73da34f-ef6b-5c4e-a414-63c11b277766 | textbox | Position:
b6209f58-cbe0-5118-99c4-b01102600842 | textbox | Date:
0b2cda12-1722-4b33-b430-dd5a5f0eae29 | checklist | FHC-ITP-036 - Furniture & Bollard Installation Rev1 | itp | FHC-ITP-036 - Furniture & Bollard Installation Rev1
fa09ee81-65f4-49b2-a90c-107c011b1fbf | section | 1 - Preliminary Works
a1616860-a09c-40b1-9885-1a9a0735e14e | checkpoint | 1.1 Check for correct documentation
5740508d-bb4a-5f9d-8e68-30ebd0deec5e | note | REFERENCE DOCUMENTS: IFC Drawings
61e29db5-d295-57c9-b661-9a70302f4694 | note | – – – – – – – – –
350ec263-d8d7-5441-9c09-edd894ca1f81 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a5488ee3-b682-5c41-8558-e6f10057224d | note | – using the correct and complete set of drawings
a8e96db3-219e-50ee-9d3f-8b512d16ef32 | note | – all drawings are the latest revision
2d32db7d-d682-5962-878e-c8eeff934837 | note | – – – – – – – – –
04967f6b-e562-519a-a8d3-7fdb9eac95aa | note | INSPECTION/TEST METHOD: Visual inspection
33315dc3-572f-55b9-a180-aed71dcc6472 | note | – – – – – – – – –
96b87e85-1956-5315-9aba-e2e9773e411f | note | RECORD OF CONFORMITY: This ITP signed off
509c312d-0fac-5944-a78e-b4b073fd8b42 | note | – – – – – – – – –
abecf43e-a91f-5e28-a1dc-47467cf75d8e | note | WP
6f97d876-e29e-5fe1-8e46-46df7aec29e4 | note | – – – – – – – – –
87a722b0-d2a6-5d41-9622-d7b97ee3b68c | note | RESPONSIBILITY: Fulton Hogan Engineer
b112b1c4-0c76-5519-b2c4-d8187b741f37 | note | – – – – – – – – –
b1fbb171-7e0e-5ed0-aab1-0e21dcac3335 | textbox | DATE:
10ca71cf-9519-495b-b86d-154d4a8c3d64 | checkpoint | 1.2 Furniture Type
0eeef95d-fb12-5fd2-b611-aec860f8c2da | note | REFERENCE DOCUMENTS: IFC Drawings
ebd595c8-23b6-57de-9605-be4f48e4e306 | note | – – – – – – – – –
aa6df3ea-065f-5d73-a52a-c47af4663ed3 | note | ACCEPTANCE CRITERIA: Furniture to be installed:
ed43c6fe-46fb-56d7-9b86-48da5ce8ee6a | note | ☒ Wheel Stop
66fe0664-91c8-527d-804e-62102c528aa0 | note | ☒ Bike Hoops
66c85d4b-8571-583f-8418-227d34e3eaf4 | note | ☒ Bollards
bf6c32bc-eb9c-55e3-8f22-24ada5919a1c | note | ☒ Tactiles
1cc1e12f-f7e0-5da7-814f-dc615c154977 | note | – – – – – – – – –
6677c560-a36f-591c-b17d-cc47c3d7e2aa | note | INSPECTION/TEST METHOD: Visual Inspection
11f97a4d-a007-51bf-9587-9ce698ece85d | note | – – – – – – – – –
1d68b6b3-aecd-58e6-9818-fc39ce031d9d | note | RECORD OF CONFORMITY: This ITP signed off
0f3b3ffb-3ce8-5435-b133-e7f1973790c3 | note | – – – – – – – – –
380fe00a-7a18-56f1-9dff-247907a62dce | note | WP
c9721843-2e6c-5ff6-a98c-4b312fc797cc | note | – – – – – – – – –
9abce30e-9d46-506d-bd65-298e91420b83 | note | RESPONSIBILITY: Fulton Hogan Engineer
05a3eb7f-5413-539b-ab30-22cbe87ffe19 | note | – – – – – – – – –
603d2c99-12b8-57e5-9e53-d0ed80e492ea | textbox | DATE:
cb4ed6ef-0b29-4642-8c10-775c665ca09e | checkpoint | 1.3 Service Identification
ea87bc36-5eaf-5f04-9bee-02a7e89121d4 | note | REFERENCE DOCUMENTS: IFC Drawings
2c604541-a55a-59d1-a770-b15b758ccb51 | note | – – – – – – – – –
db95adaf-131b-5731-b2d4-3fd9f19774af | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
7f322a1e-78fe-5ec4-8462-2e0a5ee3ef53 | note | – – – – – – – – –
f2461ce0-cf0a-57d4-9e0c-5968c204f18c | note | INSPECTION/TEST METHOD: Verify
75db4c67-80d0-5479-96f3-f5d0af2d002e | note | – – – – – – – – –
461efeab-d344-537c-9c0a-33f34ffc2560 | note | RECORD OF CONFORMITY: This ITP signed off
5a6bba18-c4ef-5e53-b588-451276012cf8 | note | – – – – – – – – –
893cdb1d-89a5-55aa-8cb8-ce31bc9511e8 | note | WP
915a1374-7a66-53f9-89c1-4af0d909b67c | note | – – – – – – – – –
ab1cfb5b-a86c-5933-b763-3d6254c79f18 | note | RESPONSIBILITY: Fulton Hogan Engineer
34539fb4-3d5c-5dce-b537-2b1522d23ba2 | note | – – – – – – – – –
96c4ed88-aeda-55ff-937a-9e1ff4acc1f1 | textbox | DATE:
a19f29bb-73c6-443a-bfac-b94d4de290f4 | checkpoint | 1.4 Material Conformance
4db15bd0-dc52-5b79-91b3-b5ad398fc7b9 | note | REFERENCE DOCUMENTS: IFC Drawings
6bfd1a67-a788-5c06-91c7-8742562537ee | note | – – – – – – – – –
c9adede6-5a98-5a34-b90f-01277f98c1f2 | note | ACCEPTANCE CRITERIA: Concrete mix design to be approved in teambinder prior to pour.
c76134a2-fda3-555d-b41f-51bd8afa2008 | note | – – – – – – – – –
1e4322f9-04ae-5000-b05d-c87d8f11bca6 | note | INSPECTION/TEST METHOD: Verify
9219b90d-07de-5af8-b0fa-17bb9e0eea50 | note | – – – – – – – – –
dcc8e5ad-71af-59a9-b0b0-4dec72f31b0a | note | RECORD OF CONFORMITY: This ITP signed off
ec05d9d7-e21a-5cd5-904c-9a19c0a25146 | note | – – – – – – – – –
676c213d-531a-5552-9441-5818edaa755c | note | WP
51622995-19e9-5cb0-81fe-2a9b74539e87 | note | – – – – – – – – –
c6178eaf-de4d-56ef-88b3-1eb1a5970dba | note | RESPONSIBILITY: Fulton Hogan Engineer
f6f0ebc3-2e16-5927-8b04-605f3e8b412f | note | – – – – – – – – –
d6c72919-ee20-5269-892d-f8d25d37a0ce | textbox | DATE:
5e06dbe9-9a9b-47ae-b6f9-3a6e5663097c | section | 2 - Construction Works
8f50151a-bab4-4c54-8fc7-fce4fce11b18 | checkpoint | 2.1 Setting Out
07fdc41d-7f08-57ed-bbb4-07d80869e57f | note | REFERENCE DOCUMENTS: IFC Drawings
f580df31-110c-5b35-9321-b5a482a61595 | note | – – – – – – – – –
7a1e3157-fbe1-50cd-bf71-76e23ff2aaa1 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
d8a61dd4-be7a-519b-9c0b-20cbdc7363aa | note | – – – – – – – – –
e7cab785-583a-5626-ad91-83edbfc6f422 | note | INSPECTION/TEST METHOD: Visual Inspection
e06c9f66-daa1-58b1-b07f-7ae0e66cf988 | note | – – – – – – – – –
5bcd9fc1-2541-54a1-bbc3-4692a088d11b | note | RECORD OF CONFORMITY: This ITP signed off
ba67b454-de86-55ad-ad73-1d6b89ff2223 | note | – – – – – – – – –
99c9f2b0-206e-5002-8781-9ceb814af795 | note | WP
4f3963b1-f7ae-518d-ae52-3ee0975402b2 | note | – – – – – – – – –
42cb0fcc-d5e4-5a8d-ad7a-54aaf7b5def3 | note | RESPONSIBILITY: Fulton Hogan Engineer
c98bc30f-d709-579d-b12c-b0f46336ec8b | note | – – – – – – – – –
6b2f8269-6e5d-5568-8251-1fc810905f5f | textbox | DATE:
0e6a7ccc-c0da-4cde-8b16-0c9673ab8644 | checkpoint | 2.2 Post & Foundations
3a94dbf8-5770-5439-b7c2-3bf1754cf221 | note | REFERENCE DOCUMENTS: Manufacturer Specification
5f9bac76-75c1-5965-824e-801ce5a093a0 | note | – – – – – – – – –
52a6a7f2-1251-5712-a9d7-567ff4d24c17 | note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
7b63c6f9-c4b1-5719-9a00-d190c549dd27 | note | – – – – – – – – –
938636dd-8e26-543a-be15-a1bd8714bdb6 | note | INSPECTION/TEST METHOD: Visual inspection
0afec034-cf1f-5cce-b6e3-c2c1997353b2 | note | – – – – – – – – –
75e7b9ce-fcc0-5c7c-a124-0a3cb9b4a6fe | note | RECORD OF CONFORMITY: This ITP signed off
f49498db-da21-55f8-8e97-53dec857490d | note | – – – – – – – – –
5cdbba6f-8cd1-58a7-b897-c900cd63f3f8 | note | WP
77808e14-fd66-5ad4-882f-af9f59d030f9 | note | – – – – – – – – –
7f9d019e-96e3-56a7-b590-f448796b3f6a | note | RESPONSIBILITY: Fulton Hogan Engineer
30c5bae1-18ed-5885-868b-32b26b505e11 | note | – – – – – – – – –
ae8b24b5-0fa8-57f3-aef1-e05cb734d13f | textbox | DATE:
f0d6b90d-19f2-45d5-a2e2-fa9a07ca94b7 | checkpoint | 2.3 Positioning
66ee96d9-e129-5854-bae9-f84722009b0c | note | REFERENCE DOCUMENTS: IFC Drawings
174d8b40-be2b-5734-b067-47092d997542 | note | – – – – – – – – –
54dfbbb2-d129-564c-910d-02605afd3130 | note | ACCEPTANCE CRITERIA: All furniture to be positioned and installed as per IFC Drawings
654daee8-829a-54e3-acf0-019dd6428eb1 | note | – – – – – – – – –
20f5170f-0166-5da1-aefa-834f0a328708 | note | INSPECTION/TEST METHOD: Verify
f12c1ac6-fe9e-59cb-a367-87113024b4e1 | note | – – – – – – – – –
3ac589de-e4d1-5e7e-afba-984f5115b89d | note | RECORD OF CONFORMITY: This ITP signed off
61dc6eec-ea2a-5f5a-8e3b-1d680ba67572 | note | – – – – – – – – –
457b9746-a7bf-59c9-9b5f-ccaeeb190245 | note | WP
9003db2d-bf61-5cf5-a5a3-c5e088658323 | note | – – – – – – – – –
6db8ca5b-44da-57c9-a0c5-a700714c5cca | note | RESPONSIBILITY: Fulton Hogan Engineer
f18c6480-d433-5e77-aa93-0067a5762b9d | note | – – – – – – – – –
8a620dae-34b1-5e45-80e8-6a9c21482333 | textbox | DATE:
41a96265-6ba3-4250-b8ac-b4b63d0f2882 | section | 3 - Finishing
2ad9779f-ace0-4bc4-a371-e4661c377303 | checkpoint | 3.1 As-Built Survey
417c48b1-1f03-577b-b021-08f1baef1e85 | note | REFERENCE DOCUMENTS: IFC Drawings
19bec203-1fb4-5b13-997f-07bf02617031 | note | – – – – – – – – –
df93eab9-4168-5d63-a1c9-30b7e18f182f | note | ACCEPTANCE CRITERIA: Has the furniture been installed as per the IFC drawings?
a30cf02d-20aa-5ed8-902c-93025a94b96d | note | • Is the location of the furniture required to be included in the as-built survery
86cba333-c60d-5bd5-b970-870863238fd3 | note | – – – – – – – – –
7620b95d-ac80-509f-a2a2-811ef0085dc4 | note | INSPECTION/TEST METHOD: Verify
398e4633-1e25-58e6-942b-07d97ce6ea76 | note | – – – – – – – – –
de8637d9-6b1d-5a83-8f69-bd343746af60 | note | RECORD OF CONFORMITY: This ITP signed off
02f3915b-339d-57ef-9185-0cc20be003e6 | note | – – – – – – – – –
e93c3930-5a2d-5c2a-a114-01f400f473b5 | note | WP
c10d83fa-af24-5ebd-ba85-e6d604e7ee3b | note | – – – – – – – – –
618a19eb-dc88-5750-b2a8-addbd2ec079d | note | RESPONSIBILITY: Fulton Hogan Engineer
01abb2b9-535f-5668-9167-35975d3b954b | note | – – – – – – – – –
0c48c25d-bf83-55fe-a94f-2d7a9838a6c2 | textbox | DATE:
10c4ae34-425a-4e60-acb6-5a00a793d2d9 | checkpoint | Final Inspection
819d2657-f474-5cac-b2e1-3d981b5d134e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
04078ffb-3427-54d1-98a9-0ee3ef4e849a | textbox | Print Name:
e44795f0-2ea3-5069-88c9-7b95d5e79bf0 | textbox | Position:
c39b6f93-3fbb-5ca8-955b-5ef6052affdd | textbox | Date:
a34e4561-49e5-4330-a17e-642ebdb13b45 | checklist | FHC-ITP-037 - Structural Concrete Construction Rev1 | itp | FHC-ITP-037 - Structural Concrete Construction Rev1
3ec870ac-6dda-4ba2-b401-868e022e5b8a | section | 1 - Design and Submissions
3494bc94-1dac-4584-a8c6-171366d52d84 | checkpoint | 1.1 Check for correct documentation
40488e50-f86a-559b-9b11-70d6cca390c2 | note | FREQUENCY: Prior to commencing any activity
404ee1f2-33b2-52ad-b20a-a43be9fea848 | note | – – – – – – – – –
c9970279-402a-5dda-86e7-fd7fff2cf996 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
7077ee5f-b6b1-57c4-acdc-98fa74df6a1a | note | – using the correct and complete set of drawings
57646c1b-6bca-52f8-a392-b7eefb3637e3 | note | – all drawings are the latest revision
81205b3a-9713-5620-96c2-fa38e9930dfe | note | – – – – – – – – –
f625adc3-c39c-563f-af49-2e5e148b31ba | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2762414d-55af-58a6-ab54-c7ac3cbcc6d7 | note | – – – – – – – – –
f5b5066d-ce26-5df9-94f9-e53683efc7ac | note | INSPECTION/TEST METHOD: Visual inspection
b4b41c39-e6fc-5f72-917d-ba6ee1a79325 | note | – – – – – – – – –
20e6dc6e-55b8-5153-b142-1fd48be978d4 | note | RECORD OF CONFORMITY: This ITP signed
f75131b8-0a2e-5ed8-9156-f159909bd50a | note | – – – – – – – – –
f8566117-4cf0-5280-8afc-a7e2640e5193 | note | HP*
ffc5f16a-0020-5ff3-bbe0-640c0d09446f | note | – – – – – – – – –
58ed076a-0e74-57b9-b22f-9760a9a42219 | note | RESPONSIBILITY: Fulton Hogan Engineer
92782a63-f21b-5b4d-b8bd-ea0e2ef3855d | note | – – – – – – – – –
c9728937-cac2-5a5a-a150-191e557170bd | textbox | DATE:
3c0896f8-8437-4953-987a-0e5789f2c19a | checkpoint | 1.2 Implementation of all measures and controls
ccb67ab5-e2a2-57f9-88cd-9ea2bba30af0 | note | FREQUENCY: Prior to commencing any activity
11b0efe1-9e60-5916-ba50-5e121a0e597c | note | – – – – – – – – –
7dabd79c-a01a-5590-af1f-ae236b063bfc | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
2b02379d-caae-5ffb-bcbf-7a4fef3a641e | note | – – – – – – – – –
71960ba6-b6c1-561f-92fc-bfff52efdd40 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
c8b1ff06-acdb-5ad9-9974-c540b99a92fc | note | – – – – – – – – –
8e37b410-d531-5b2e-9c98-d854caab3a99 | note | INSPECTION/TEST METHOD: Visual Inspection
0d95c918-9051-57cd-9e81-c361e11b4edf | note | – – – – – – – – –
3d8eae01-f4ca-5457-87b2-134d0d875242 | note | RECORD OF CONFORMITY: This ITP signed
fd17faac-266e-5bfd-818e-ef7c6a9208d9 | note | – – – – – – – – –
fa3a7dc9-ba44-5972-9f8e-292f72a694b8 | note | HP*
c4818ecf-1080-5661-aeed-6332acf07c73 | note | – – – – – – – – –
310477c9-f727-5306-b9ec-e5a1e69ee653 | note | RESPONSIBILITY: Fulton Hogan Engineer
fcc0049c-7096-5853-a9ff-da3d1a51f491 | note | – – – – – – – – –
36422200-a87c-5b1e-8e94-1bc9c91db086 | textbox | DATE:
bcbf6dd2-f874-4682-b5f6-ad3dc9479367 | checkpoint | 1.3 Approval of mix design
88d214d2-061b-5135-b2cc-7487f4c69e93 | note | FREQUENCY: Prior to the first concrete pour
1c444795-7749-5816-a884-c8ab1859e74a | note | – – – – – – – – –
6f98da74-2b93-54d4-a9bf-0e253f15b3b5 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
d78134e5-64db-5796-8e12-12b0fce96504 | note | – – – – – – – – –
b48f89d0-2ab5-5176-a317-2a6e700f4336 | note | REFERENCE DOCUMENTS: 610.07
d76397c5-5f64-53a6-907f-74fd77a208bf | note | – – – – – – – – –
e86b4d7f-d205-57cc-8cc0-ef32ced55885 | note | INSPECTION/TEST METHOD: Verify
4e4d45bc-8e51-52bb-9458-be2e9061efa9 | note | – – – – – – – – –
30c81375-d347-5744-87fa-13300d23cdde | note | RECORD OF CONFORMITY: This ITP signed
a346a83a-7a3c-59c3-9614-bcb2e85be51e | note | – – – – – – – – –
170cc927-d1e3-5f05-82a4-83e2cf1a860c | note | IP
4d671375-24ef-52e5-9330-3b8713effc9d | note | – – – – – – – – –
4658a576-e886-5fec-94eb-9e966f73922b | note | RESPONSIBILITY: Fulton Hogan Engineer
f1b73dd8-adef-5d3c-9919-cc3ac87a4469 | note | – – – – – – – – –
63a3b4c9-1e78-596f-bfaa-79ca68a8aeaf | textbox | DATE:
4fe37cae-f8f7-4ed0-be9e-3b3cf62c32a6 | checkpoint | 1.4 Reinforcement schedule
8b294e4f-d0a7-5efe-a5f2-114195c14f5c | note | FREQUENCY: Prior to concrete pour
f90f2ab3-ef5d-56ac-9bd5-6f18b20a052c | note | – – – – – – – – –
cbb460ea-c033-5b34-aa21-55e72e690f62 | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
5c39215d-8123-52b1-81de-1e5b0b70237a | note | – – – – – – – – –
64a0f76d-aaf6-5949-b594-acd638b99620 | note | REFERENCE DOCUMENTS: 611.04
83c68b8f-426a-5815-8ec1-79d18e382eec | note | – – – – – – – – –
613392c5-43df-55e3-a0f3-9bc2f1465c03 | note | INSPECTION/TEST METHOD: Verify
00dad508-8b79-5faa-95f2-b7260dcb70a3 | note | – – – – – – – – –
35dd67bb-3826-5981-9198-d1321fffbe10 | note | RECORD OF CONFORMITY: This ITP signed
1bbfd5aa-efee-5685-ab4c-67e08448d200 | note | – – – – – – – – –
45a4506d-073c-5843-93a6-b334ce96cb38 | note | IP
5126ef21-ae30-56db-a042-4f7080efe059 | note | – – – – – – – – –
9fae3ef3-be05-51d8-8664-d2aa42ad4ff9 | note | RESPONSIBILITY: Fulton Hogan Engineer
bc38453d-fa96-5ce3-a6c1-e518019296fe | note | – – – – – – – – –
e1ee7a85-99ca-5c04-97b9-e6424261f5a3 | textbox | DATE:
8b1ba2d5-c85b-4ee3-a30b-f5bfb6c58ff1 | section | 2 - Construction/Erection of Formwork
f627ef5b-2c3f-48fd-bef9-f912f355bc27 | checkpoint | 2.1 Excavation
9a199d42-14b9-59f6-9dde-61a00094147f | note | FREQUENCY: Prior to concrete pour
5387740b-afed-5f53-8b37-f603f0cb48a0 | note | – – – – – – – – –
25b4e24e-1da7-582c-8eb3-b3ca5a266805 | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
4503f866-7420-5fec-827f-f8ca0000f2ea | note | – – – – – – – – –
4b2760e7-8e7f-5475-a907-2192b3330fc2 | note | REFERENCE DOCUMENTS: Contract Drawings
d9211093-bf92-5ee0-a089-9924eafd0d32 | note | – – – – – – – – –
b7339f09-2ae1-500a-9f3f-ce417e3ce6ed | note | INSPECTION/TEST METHOD: Inspect
b0a3eda6-a16f-5b1f-96d5-552606fd7f52 | note | – – – – – – – – –
7ddd8e1d-f729-5e71-930c-0a4639b3eb77 | note | RECORD OF CONFORMITY: This ITP signed
9a3e9d0a-49e3-5f01-867b-2804c8a8426d | note | – – – – – – – – –
0cda3ab8-e2b2-502c-88fa-edc94fb273af | note | IP
eedcf46e-7149-5761-a79d-8268f2d25efd | note | – – – – – – – – –
b304f33a-de94-5951-8227-48f25a989d47 | note | RESPONSIBILITY: Fulton Hogan Engineer
25cbc8bc-1a87-5222-b49b-d56a27d4d9fb | note | – – – – – – – – –
342712f4-fa6c-5bcc-ae98-15cd5a42a6de | textbox | DATE:
83703b0b-cc7e-46b7-9c15-871bfc7d1e06 | checkpoint | 2.2 Construction Methodology
e04a6c5b-efe1-5fc2-a19b-03ade4e3f9a4 | note | FREQUENCY: Prior to erection
23e62e78-6c25-5191-8075-0a9ebc420121 | note | – – – – – – – – –
1bff83c4-4ca8-579d-b595-4a0b9da8d66f | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
6bc2bbc5-99e5-5b9c-8b59-c83058a7466d | note | – – – – – – – – –
ef83d28c-2b5a-5ac5-a9d5-d257b6239336 | note | REFERENCE DOCUMENTS: 614.04, 614.06
b4af5af3-7f16-5c98-9624-6fc9d1ee5c47 | note | – – – – – – – – –
d53c9fb2-9dc9-53ff-9b14-98a271fbc1ee | note | INSPECTION/TEST METHOD: Verify
c22b659b-c619-5503-8982-6605a63b71f1 | note | – – – – – – – – –
ad707fda-960b-5989-896a-1f01a5f7fe73 | note | RECORD OF CONFORMITY: This ITP signed
def90012-20c3-54f9-a158-91d9b5bdd11f | note | – – – – – – – – –
90bb43a8-8719-556f-8e75-c2b668614303 | note | IP
8c79701f-3fd1-58d8-b2f5-ede91d908db6 | note | – – – – – – – – –
2749584a-a1b2-51f1-b2ae-4f0420c711b7 | note | RESPONSIBILITY: Fulton Hogan Engineer
8302b1d4-c7d3-54a6-88b7-3ec2641606de | note | – – – – – – – – –
37c3bd05-6736-56c1-bf3f-4fe46d7c6f2f | textbox | DATE:
182207d7-20fe-4e25-b401-5b24aeebc903 | section | 3 - Pre-Pour Planning and Inspection
920e2c7f-92fe-400c-b59f-4d97f4df6ae3 | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
cc82c996-5c94-53c6-abeb-6804c5300412 | note | FREQUENCY: Prior to concrete pour
008a44ae-570c-543e-99df-894277532357 | note | – – – – – – – – –
6814cdb3-e06a-5756-ba33-74eeef1a992e | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent.
ad203756-8f8e-5704-a2b0-05065af5a36d | note | – – – – – – – – –
3efbbd95-c7a1-54c8-adfe-5ae5bcfdd91b | note | REFERENCE DOCUMENTS: 602.03
e5bf546c-81f8-5695-9a81-acdbdcc54b97 | note | – – – – – – – – –
f58e93d4-7033-563d-8207-fd107e611cdc | note | INSPECTION/TEST METHOD: Verify
2be4577b-89e2-5422-911a-3cdd0ae88699 | note | – – – – – – – – –
01baca48-4bf7-5c8f-93e3-c6e503ba0094 | note | RECORD OF CONFORMITY: This ITP signed
7837c1bd-0c1a-5914-b8da-3e7dc15ecce4 | note | – – – – – – – – –
ba65ebd9-b20d-5985-b054-2339d1e08297 | note | HP
87ae2ba9-666e-522a-8fac-1341390f07bf | note | – – – – – – – – –
00ea73c0-2610-5420-87ca-c63eaecb9469 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
428b2118-de60-506d-8214-91596115002f | note | – – – – – – – – –
37f59b03-4c19-51ae-af8c-148529024ff9 | textbox | DATE:
6c8e3f0c-18f0-4151-9efe-2a6ddfdeae20 | signoff | AUTHORITY HOLDPOINT
c22cd112-eaf2-42af-95cd-50474f6aaf05 | checkpoint | 3.2 Formwork levels and position
44441a53-acac-58a4-a031-e7698ec15df4 | note | FREQUENCY: Prior to concrete pour
85a71033-eff9-5683-9f89-c837e0c5afc5 | note | – – – – – – – – –
ec2b0471-b128-5aec-b652-fb9e87e5c66b | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
f27a35e8-118d-561e-88e9-75d95c7764ba | note | – – – – – – – – –
f7c5cf6e-a626-5ac7-9064-76615829a541 | note | REFERENCE DOCUMENTS: 614.06
4ff74040-16b4-5f7d-a777-123f39e536c9 | note | – – – – – – – – –
bd5b4460-2662-50e9-a4b5-41254d98b45c | note | INSPECTION/TEST METHOD: Verify
6b2d361b-66d8-5288-bc2e-f83f702ea4d1 | note | – – – – – – – – –
2c27411a-f99a-5aba-b7ac-3f7aee625f55 | note | RECORD OF CONFORMITY: This ITP signed
1cde0525-f73f-555e-8ea4-9c668d40a0cc | note | – – – – – – – – –
e5bf6cd9-8795-5515-b262-837909b4ca10 | note | SCP, HP*
297328ec-11f9-56b3-b9b5-e2071ae05ec0 | note | – – – – – – – – –
d8cc33fb-99c8-5f33-b16b-d849a464830a | note | RESPONSIBILITY: Fulton Hogan Engineer
a1e82eb3-60f2-5e03-8ffa-cfc192257c43 | note | – – – – – – – – –
452e06d4-1d89-5858-9ce2-758e95ad7622 | textbox | DATE:
7dc07840-769a-488b-b0d6-affd89f36e83 | checkpoint | 3.3 Location of splices
00f1b9cb-967a-5512-8fdd-e065250d8e86 | note | FREQUENCY: Schedule Review
8f4714a8-971b-56b6-8037-ebcbbc403149 | note | – – – – – – – – –
eeb9becb-720b-59ee-a411-14620bdde998 | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
4b314a0d-8636-535f-b48b-0d0238080dee | note | – – – – – – – – –
8693b00a-cfbc-54e8-9075-85960b231cc0 | note | REFERENCE DOCUMENTS: 611.11
11d4d356-4964-59c2-b0c1-16a57069a1e0 | note | – – – – – – – – –
4d83552e-0dd6-53af-947f-3f2636141a10 | note | INSPECTION/TEST METHOD: Inspect
4430cf48-fb56-56b0-8a57-ad0b090b535c | note | – – – – – – – – –
02b992d2-73f1-5f9c-8120-9c2a87d18c17 | note | RECORD OF CONFORMITY: This ITP signed
1bec2219-891e-5639-80d7-37dab0bc2ac7 | note | – – – – – – – – –
e7e79ba5-2344-516a-a644-8f3d20d53d6e | note | IP
6b239c68-38bc-5980-bd8f-87a9d549cf1a | note | – – – – – – – – –
8e3af8ec-103f-58f2-8df5-0eea4be9b6cf | note | RESPONSIBILITY: Fulton Hogan
07de285c-f45d-5002-9ae8-35e24a28271e | note | – – – – – – – – –
5710cd71-1b0c-5e43-9ce1-4cf5fd415fed | textbox | DATE:
2c6956b2-7140-41d4-9d70-5ef6278b4b5b | checkpoint | 3.4 Cleaning formwork
afd6a503-ab64-5aa4-8ae2-5080f0d10ffd | note | FREQUENCY: Each concrete pour
d34618c8-308e-5325-ae8b-cee22b497f86 | note | – – – – – – – – –
f0604588-baad-5c41-86fa-78934f072a5d | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
76da663c-5fb0-579a-980e-bfcd781827e0 | note | – – – – – – – – –
27f17a1a-492a-5828-9d73-055b649c9adb | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
4fc189f6-c386-5a99-9203-5ef683e41ba5 | note | – – – – – – – – –
03b1ea20-ba73-5b78-afaa-8a9e79f71836 | note | INSPECTION/TEST METHOD: Verify
472c10e9-e3bf-5f6d-a236-64d02d8e2e6a | note | – – – – – – – – –
62aaa6cf-1370-5cdc-807f-11ec7f66895c | note | RECORD OF CONFORMITY: This ITP signed
fcacb1da-5e7f-5df0-840b-d55f6e1a89a2 | note | – – – – – – – – –
33f85eed-3274-514b-b896-94315ac13a90 | note | IP
72d95980-60ed-591a-9947-4aef218d2cd0 | note | – – – – – – – – –
1a0ea1ba-eb44-5e73-a3b4-e597c914fd11 | note | RESPONSIBILITY: Fulton Hogan
945c3ea8-4fdc-5875-8526-4ba090e1e6dd | note | – – – – – – – – –
b041da7b-5482-5fe9-84af-22d619caf433 | textbox | DATE:
97657e9f-cdb1-48e3-ba4b-4fc2dd37715f | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
cc8e855f-bc6c-5bbd-9a69-29584bc986ff | note | FREQUENCY: Prior to concrete pour
f30ddb77-da66-535e-8088-f7ec8f281e52 | note | – – – – – – – – –
618965f8-0fa6-590d-9e64-19b7b361b17f | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
298d1dc5-6268-5d0a-8836-562c34eaadbd | note | • Pre-pour checklist completed and signed.
4525bd42-3ed0-53b1-82cb-7195e0783031 | note | – – – – – – – – –
d2881deb-81df-51d2-a178-52d34b035856 | note | REFERENCE DOCUMENTS: 610.18 (a)
28e23374-0ced-5536-ab84-8419a5abd380 | note | – – – – – – – – –
288a4f80-4a1f-5e12-b36d-3e66d7524c0c | note | INSPECTION/TEST METHOD: Verify
52aec8ae-acd3-5a74-84ab-89731ec02094 | note | – – – – – – – – –
6eff0393-e27b-5c90-9511-123dd580fc73 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
eaede39c-5b26-5781-b78a-537c092e6822 | note | – – – – – – – – –
10c95fcc-969d-5739-8c3b-015589921ecb | note | HP
19c86908-d982-591f-a27f-17f17c4134fc | note | – – – – – – – – –
e1520589-c318-5ae2-b3da-644791adac5c | note | RESPONSIBILITY: Fulton Hogan / VicRoads
8331125f-8d5f-54c2-b5bf-ed797c804882 | note | – – – – – – – – –
76ca338c-5414-51c1-b6cc-670aa8d3f0a5 | textbox | DATE:
303d7087-6c38-4234-995f-af915ffaa16f | signoff | AUTHORITY HOLDPOINT
6d01ec2a-e76e-40ba-8725-949406d4b65f | checkpoint | 3.6 Reinforcement assembly of piles
3736fd35-c0a6-5e68-b054-493c300477f6 | note | FREQUENCY: Prior to concrete pour
4b588ebb-1380-5bde-820f-988c731dc021 | note | – – – – – – – – –
7014bb55-56df-5866-a9af-642b42fcc5bb | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
4943c563-fe88-56f4-8a30-d21bd0d77c52 | note | – – – – – – – – –
77b8e476-b5b9-54d1-8769-4ba0da83ed49 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
015adba8-79d6-5acc-a87f-e4493abc43ab | note | – – – – – – – – –
a6178838-5ad2-50ef-90c5-e4a79bd23dc2 | note | INSPECTION/TEST METHOD: Verify
7e85fbf0-3f01-53df-8ffb-5fa235fbc946 | note | – – – – – – – – –
ce8f424d-69e9-50fe-9bfe-5a6eeafed321 | note | RECORD OF CONFORMITY: This ITP signed
a8638558-8740-5f21-ad8e-ecd3b07ebb66 | note | – – – – – – – – –
659291e7-c24c-5365-8f75-441dbb80222f | note | HP
a3675586-253b-5727-a2e8-a2b6f37a4dc6 | note | – – – – – – – – –
f8daa7b8-a6fe-51d1-acb7-d7882dd3d8fe | note | RESPONSIBILITY: Fulton Hogan
1165c35a-45b8-5af1-841f-ad9492a10f7f | note | – – – – – – – – –
1fcc12f6-aeef-51d9-a1b4-1bf6b54dcf53 | textbox | DATE:
16429bcb-9e82-431e-a080-777db22103b6 | signoff | AUTHORITY HOLDPOINT
ac68f4fd-8f95-4b19-85a3-f0e37f64c026 | checkpoint | 3.7 Monitoring weather
415e6618-e735-51c5-b057-816ae849036c | note | FREQUENCY: Prior to concrete pour
443d17ca-e4dc-5dd6-a5da-35fdc1a82400 | note | – – – – – – – – –
8de99686-7019-53f2-be0e-95069854be13 | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
08677ecd-aa49-5587-a90d-16bfbde37b26 | note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
a2cbd634-ec0b-5c33-8c14-b348a995abfc | note | – – – – – – – – –
4a9a8698-b95f-5ccb-b998-df8435b85041 | note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
cfacde4f-3b79-58ef-8a0c-8fbe280fad93 | note | – – – – – – – – –
f3bde35c-34f5-5aac-b85e-e139557adec2 | note | INSPECTION/TEST METHOD: Verify
9eac7e74-cd74-5684-a7d5-9c851e4c97d5 | note | – – – – – – – – –
3b0d143b-50f4-5961-ad7d-de1e2affe3aa | note | RECORD OF CONFORMITY: This ITP signed
eb4d606c-775a-5729-97cb-afabd619a1a4 | note | – – – – – – – – –
c8a35fca-2bef-5d74-a941-0d48d1a8b040 | note | IP
467a9be1-b913-5352-9fa3-250c752332a3 | note | – – – – – – – – –
7a8f0c05-fa04-5d1e-a1eb-682197d906cc | note | RESPONSIBILITY: Fulton Hogan
00e18d63-2e80-5d5f-be5f-a8b00397e569 | note | – – – – – – – – –
bd31569b-d2ac-50cb-a267-710f397adbbd | textbox | DATE:
b01b11ee-3c3a-4483-b535-adba1634631e | section | 4 - Placing and Finishing Concrete
8c68d246-742d-4f4c-b9a9-1c54ed676b62 | checkpoint | 4.1 Carry out sampling of concrete
0cf3b47d-6000-5d48-a7bc-44ffbacf5cc5 | note | FREQUENCY: Each concrete pour
dcbee0c7-6ed1-53a7-8a39-15218d477438 | note | – – – – – – – – –
336c51ec-dbb4-5c08-8131-3f827f5d0859 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
383a9683-f833-5379-8ae1-348f8c1d7507 | note | – – – – – – – – –
67c33753-75d7-5416-bd53-166c78e84643 | note | REFERENCE DOCUMENTS: 610.16
4c4b63b7-fc77-582c-bf20-0a43f98fb186 | note | – – – – – – – – –
7a6e0177-c3f6-5abd-a446-94c2150132f3 | note | INSPECTION/TEST METHOD: Checklist
b61a641e-15e6-5b9a-9b7a-835f8624d385 | note | – – – – – – – – –
49e8a875-9742-59f8-ac7f-1111333df186 | note | RECORD OF CONFORMITY: This ITP signed
edfdaecb-d3fc-5fe2-bde0-a435155c1f42 | note | – – – – – – – – –
243aa8aa-d71f-5bdb-9fee-e7a4bf63cd1c | note | IP
a6f286b1-5198-59b2-8b71-1efbd8ca76f0 | note | – – – – – – – – –
a0a72856-a8d3-5877-9fa3-54cd32e7b9e7 | note | RESPONSIBILITY: Fulton Hogan
2a31c7ef-e32c-5e56-b306-732fd249b9c8 | note | – – – – – – – – –
09d958d2-b49f-5af0-a1ab-20d7db24de41 | textbox | DATE:
1da8c7b3-756d-4ced-afbc-3c3515ef6681 | checkpoint | 4.2 Discharge time
882f646b-b376-5474-a5af-6fccbf5410e1 | note | FREQUENCY: Each concrete pour
04ca4ef4-c7c2-5f22-9fff-fb06ace86086 | note | – – – – – – – – –
546d7766-4e68-5662-85ab-a19f35d9c046 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
40f8f10b-b6c2-58b8-9dbc-1588c0924d9f | note | – – – – – – – – –
a6d9a4df-0fc0-5c4e-b23e-a42273071f61 | note | INSPECTION/TEST METHOD: Verify
660082c8-1b44-5800-b9e0-f4f918171b61 | note | – – – – – – – – –
4bfabe9b-7539-5962-b47f-77959434b414 | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
b599300d-fc32-5dcb-bf64-6287ebf17d77 | note | – – – – – – – – –
1ae67639-2382-57ea-96fc-5adf21b8f3d3 | note | IP
6433a3e3-84ab-5d5d-9ef6-9bd33f6f4221 | note | – – – – – – – – –
d3ee5c9f-f4f5-5382-b994-8197c839d87e | note | RESPONSIBILITY: Fulton Hogan
df04c16b-2d4f-53c6-ac65-7f51e9ebf343 | note | – – – – – – – – –
a920553b-44cb-53a9-aa09-993b6ef30846 | textbox | DATE:
b500eae3-5e02-4566-9c54-9c91387fb091 | checkpoint | 4.3 Methodology of placement (structural)
0f264d67-400b-5283-9b9c-ec9ec8da480b | note | FREQUENCY: Each concrete pour
a54772ec-9f21-586b-85c9-0171e1141842 | note | – – – – – – – – –
39c62e67-08ac-54a9-8a5b-d39774631f17 | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
74805053-8471-5ded-acc2-c946dfa7c2f2 | note | • Concrete shall not be moved horizontally by vibrators
7673eab3-3417-55f1-915f-36ecace79dd4 | note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
b1c8c23d-21bf-5de8-aa14-54a8573f115f | note | – – – – – – – – –
fd6b2def-9588-5c39-bf6e-91f77caae7af | note | REFERENCE DOCUMENTS: 610.18
23382b26-f0a0-5873-bbd0-913754ddcf4d | note | – – – – – – – – –
98e2f0a9-bd2c-5bd7-b889-666dc2a72f45 | note | INSPECTION/TEST METHOD: Verify
6b023186-bdb0-5f4e-80fb-89d26e7117f7 | note | – – – – – – – – –
d2dcbbf3-ed07-5cdb-9d03-d92f8d7e892b | note | RECORD OF CONFORMITY: This ITP signed
dc4bfe16-f728-5a93-af67-1b0fc74253e2 | note | – – – – – – – – –
8ecda9ac-7ef3-5cef-bfe6-f3980e95d651 | note | IP
9bb03bb7-bd33-53a9-9553-fcfff9f9558b | note | – – – – – – – – –
f1a53b49-c52c-570d-acaa-8eeb1079f5b1 | note | RESPONSIBILITY: Fulton Hogan
7527cf1a-bd72-56c3-85a9-4c810c19a2b1 | note | – – – – – – – – –
3e63de30-a4a9-51ea-a27f-291c9c819d7c | textbox | DATE:
26170f4b-d9a1-426b-b02e-bd62e7c01575 | section | 5 - Post-Pour Details and Inspection
765b3f2a-c041-4863-bbf2-dbc1d156ecb5 | checkpoint | 5.1 Curing
3248dc94-4dc4-5585-b657-ce85f147700c | note | FREQUENCY: Each concrete pour
fa0930f1-deab-5c7a-9661-136e6acd5ded | note | – – – – – – – – –
665d4bf7-9bc3-59e4-8845-ea2d7af1df0d | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
0628e9c9-e2e5-5e9d-990b-c6bfb4c85ff0 | note | – – – – – – – – –
3353acce-1840-51b7-91e3-e1a79b284bf4 | note | REFERENCE DOCUMENTS: 610.23
8ffc67a6-6f0d-52ae-a5c5-618323847f00 | note | – – – – – – – – –
2a07a697-1755-5fcc-ae46-455651e36153 | note | INSPECTION/TEST METHOD: Verify
f3ed9df4-bcd8-5926-82d2-2a590bceceb1 | note | – – – – – – – – –
eede91c2-7930-51be-ad77-6790b6a20236 | note | RECORD OF CONFORMITY: This ITP signed
c1abac43-200c-56b8-b98c-25f2799a5996 | note | – – – – – – – – –
a9f876c2-7084-5f88-9926-3252998af0be | note | IP
7d05e699-bef8-5e54-b584-398c25a0fe67 | note | – – – – – – – – –
eb8ee303-9f48-50ba-a799-084cbd63fe15 | note | RESPONSIBILITY: Fulton Hogan
5cdcaf32-e15d-5846-bcc6-9b1171bb0178 | note | – – – – – – – – –
143354f9-36ea-59e7-8627-02926408950d | textbox | DATE:
15475109-96fa-4647-a8a8-9bd2ee56aa6f | checkpoint | 5.2 Formwork removal
2311cc1e-26c7-58f5-b4ef-2beb56710624 | note | FREQUENCY: Each concrete pour
1cd06924-9f37-5028-a67a-21d4c1526f7e | note | – – – – – – – – –
221ccea3-22c1-5d6f-8162-fff42c37baca | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
a86ffe4e-a8b1-5636-9ad5-8c19a6fdf3f4 | note | – – – – – – – – –
9e3ad618-f502-5ca3-bbc0-737dc22da01b | note | REFERENCE DOCUMENTS: 610.25
a5740db0-6817-5408-bbf2-309c715f8b8c | note | – – – – – – – – –
54e669ca-9ccb-53f6-8555-c793f7e35cee | note | INSPECTION/TEST METHOD: Verify
b6ae5912-603f-5912-9997-b6296eb9e113 | note | – – – – – – – – –
7565f21c-b6aa-5ebc-b724-e664ea8ece33 | note | RECORD OF CONFORMITY: This ITP signed
d9cf0280-fd72-5b56-9526-d3b307aa29dc | note | – – – – – – – – –
5b9656bc-ceac-510b-ac6f-f3299e968d5c | note | IP
a045de0a-6ee0-534f-a85a-62a89d2963c9 | note | – – – – – – – – –
942b4126-e37b-5db2-a5f2-b8054ba85191 | note | RESPONSIBILITY: Fulton Hogan
915e6885-acc8-593a-9600-ef22756a35a5 | note | – – – – – – – – –
39cbbb17-c666-5cfd-bb43-f912627c09b8 | textbox | DATE:
39314150-ee15-4601-9f64-320fcccfe5ff | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
5f810fb3-3932-5751-afaa-9f0b36a9e9d6 | note | FREQUENCY: Each concrete pour
86618f8a-4db7-5fe2-bb92-8426e64d6246 | note | – – – – – – – – –
1d293fba-594b-5340-a0d4-e5db8073ed8d | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
635846f3-f6d7-5219-aad9-9d50be818449 | note | – – – – – – – – –
5d052f54-7aa2-51f4-a9f3-e77ef52225d9 | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5 607.06
899ccf13-c910-5f25-9e05-7d5f6191b2b0 | note | – – – – – – – – –
f3889e1b-2129-526b-b6f7-99c3f344774a | note | INSPECTION/TEST METHOD: Verify
1bfe2ccd-7753-5111-ba32-615983fc7e49 | note | – – – – – – – – –
fe40c1d9-d275-56c5-8d56-ff0d94e4d07e | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
a7ef8c63-c09e-55d7-b5c5-3604fe20ed7e | note | – – – – – – – – –
77346b96-d672-564f-a2e6-11d7705b2e37 | note | IP
0f81cc55-efd4-5612-8612-b68a85683fea | note | – – – – – – – – –
a9afe07c-8b0b-5016-b4bb-65d4bd1ad5f4 | note | RESPONSIBILITY: Fulton Hogan
3b498723-3010-56a8-a5e7-18855cfc2965 | note | – – – – – – – – –
37656c23-598c-53cd-99e2-e3455f99c903 | textbox | DATE:
3dd608be-0875-4839-9c89-28a4d5ec4c15 | checkpoint | 5.4 Concrete Sampling and Testing
171a322d-ecf9-50c1-b6f2-566de1fec112 | note | FREQUENCY: Prior to lot closure
f9cc9861-847f-552c-9917-166b4ba2f1b7 | note | – – – – – – – – –
145da827-f92a-5792-82a9-d9b23ff56835 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
aa6b5a7e-5fe4-5c85-8e5b-410e7a7c83bc | note | – – – – – – – – –
c8926d6f-a232-5181-80f9-4dfaa216fa5e | note | REFERENCE DOCUMENTS: 610.16
855b4a8d-338f-5489-a6de-4c86e0536afb | note | – – – – – – – – –
3bce35b4-c476-5d53-af34-7fba8e713f76 | note | INSPECTION/TEST METHOD: Verify
af8d7a49-47df-5b3c-ae56-9bbe6f144d21 | note | – – – – – – – – –
87f71b7c-24de-54a0-a185-9d4a56d6d76a | note | RECORD OF CONFORMITY: This ITP signed
17e285f3-111d-5184-9957-c9556d48627a | note | – – – – – – – – –
e89da2d0-b10e-52b5-9f8e-a06bdf3e139e | note | TP
9c3fb854-b9c2-50e1-99cc-5b80d21dbb51 | note | – – – – – – – – –
a4d5c3da-5e6b-54b7-9122-180bcf27eef0 | note | RESPONSIBILITY: Fulton Hogan
fa8ec7c2-331c-55be-8f76-0e31356b77e0 | note | – – – – – – – – –
5d677b3c-14f3-5eed-aa53-44286439f3de | textbox | DATE:
422d26b9-34ad-4a0f-9ede-ee80077c02f9 | checkpoint | 5.5 As Built Drawings
9fa01d87-dc19-5da4-96c1-17e57f042157 | note | FREQUENCY: Prior to lot closure
baaffac1-b27a-562b-97e1-c30174604f6f | note | – – – – – – – – –
34e2ae2a-8b7a-50e3-affd-eaace957f7e2 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
7193d15a-bd17-5ba6-b1d0-fa77c920bd8f | note | – – – – – – – – –
daf7bb08-3cc0-5854-9556-26317b42667b | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
030e6f9b-31e7-5831-b807-d3b8a5c0288e | note | – – – – – – – – –
fdd3f5ec-03f0-5ac4-8821-5d4b9a37322c | note | INSPECTION/TEST METHOD: Verify
5344489c-c78e-5a65-8355-09681a5e557b | note | – – – – – – – – –
0c36ba24-3fca-56cc-ba69-95ca49b712c4 | note | RECORD OF CONFORMITY: This ITP signed
f10b1463-3d48-548a-ab41-7e7a36548675 | note | – – – – – – – – –
508488ea-4dd4-51db-8118-95ad4a77a6f3 | note | IP
b6fd8a7b-154b-5f1f-aa67-d9f70ee448cf | note | – – – – – – – – –
2536faea-2988-5ab6-abdf-70fcf46a89cd | note | RESPONSIBILITY: Fulton Hogan
94096d73-f1d3-5f5a-9678-4692ef7f5218 | note | – – – – – – – – –
0ef0a3e5-5912-5d9c-81fd-265d1e7954cc | textbox | DATE:
f7716ea2-5aea-4fbd-bc0d-3a44979d9311 | checkpoint | Final Inspection
9553e95f-de87-5e68-a94e-672a4a8c3909 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d9bed8fb-b036-506d-94a7-c0b8d6c3b754 | textbox | Print Name:
7e78126c-8f7f-57e5-9d84-ce652356842a | textbox | Position:
a7319b7c-8345-5a6c-9909-f2d791850ea7 | textbox | Date:
c446b831-fb30-46bb-84d5-06555685b8dd | checklist | FHC-ITP-038 - Fence Installation |  | FHC-ITP-038 - Fence Installation
95bc35ef-6c3b-4645-964b-29df8e0ee368 | section | 1 - Preliminary Works
e6a39bdd-16fb-4581-8fd0-ee97d30f1efa | checkpoint | 1.1 - Check for correct documentation
69ca2ef6-14ae-5dac-a209-1af97f01c44f | note | Frequency - Prior to commencing any activity
cf3011c6-806a-558f-925a-ca0f3972d7b1 | note | – – – – – – – – –
82797186-1b00-5b0e-9e28-b99b64ab5bd5 | note | Acceptance Criteria - Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
cf0ca0fa-2a4f-5583-98ab-35e5f6de41fe | note | – – – – – – – – –
5aa517bf-28ec-5df3-b40c-75a1712a723d | note | Reference Documents - Drawings and drawing registers
2ee743d9-bc01-5df4-8fb0-d7096b52cf19 | note | – – – – – – – – –
d51a9adf-050e-51e0-b2ba-aefbae933962 | note | Inspection / Test Method - Visual inspection
bf2266b2-88e7-5f95-bdad-6d07a224a77d | note | – – – – – – – – –
052ad94a-84ea-52ca-a844-a6cb7fcf7e7c | note | Record of conformity - This ITP signed off
28097a29-5b67-59de-a486-e8040d4b1c39 | note | – – – – – – – – –
d3fe73de-3297-59d9-9488-4a907d46740a | note | HP*
9e80b1ec-5b2d-519a-8487-6b441d4fc0b4 | note | – – – – – – – – –
d7f0ff6d-4856-57b5-b11f-e17da99847ac | note | Responsibility - Fulton Hogan Engineer
45e9f514-2ea6-5234-85dc-7b3202c57102 | date | Date:
3b0cf6f3-3f77-4083-84a8-d44473618c48 | checkpoint | 1.2 - Implementation of all measures and controls
d71533e3-878b-512c-9eb2-90d07e589595 | note | Frequency - Prior to commencing any activity
1ae0328e-9f33-57ad-b4c4-883ef81b3172 | note | – – – – – – – – –
d7760fea-72cc-5c9e-bfec-55ef8a129250 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
ef6eb737-8f68-5697-90b1-6549e93bdb12 | note | – – – – – – – – –
421150ff-eac5-5a3b-8a88-d5866dbe40cf | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
069f3e9d-5007-5dd8-922a-805a0d3470f4 | note | – – – – – – – – –
9ec47110-846a-5923-8ae5-f91f89de94c3 | note | Inspection / Test Method - Visual Inspection
613968d2-4d8f-51bc-8aa7-c13164d8e0a1 | note | – – – – – – – – –
6a4bb3e8-3f3e-544d-a55f-b45fc9f91abe | note | Record of conformity - This ITP signed off
93a40f7f-964a-5cce-a0ac-0f490a8fa821 | note | – – – – – – – – –
807552fc-bf4c-5406-9f3e-a4ff5c325096 | note | HP*
fd755f12-84b9-5058-b81a-4d9bb90e386c | note | – – – – – – – – –
b568c1d7-e4fc-5ceb-972b-90109f49bf47 | note | Responsibility - Fulton Hogan Engineer
ae17da30-32f7-5cfd-baf7-92ec4ec7ead3 | date | Date:
17475f67-3dc4-47bf-8d03-646b8738fa5d | checkpoint | 1.3 - Check Materials
be9b78ef-e1b8-5a10-ad5d-0ad3bb661e4e | note | Frequency - Prior to commencing any activity
f4695ac9-a841-5c45-94f5-71ad1c571efb | note | – – – – – – – – –
a5122d07-30c1-5af6-b3a0-57a5537a1b52 | note | Acceptance Criteria - Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of SD3143 and IFC drawings.
87382f5f-0e4b-54b6-8151-8455e1ee6f94 | note | – – – – – – – – –
3ee28356-4d86-5992-b855-fbf5c551b752 | note | Reference Documents - Fencing Plan SD3143
2c7016da-4ed3-5513-a9db-e616687d915e | note | – – – – – – – – –
aef94a9f-4b2c-5dcd-8092-07e8a8f31bf9 | note | Inspection / Test Method - Verify
18ea4928-eeff-5833-b9f0-730415b18e90 | note | – – – – – – – – –
1fb9b969-61e8-50b9-a462-4db0dc48a636 | note | Record of conformity - This ITP signed off
9c556146-0019-5d4d-96b0-5a5128932cf8 | note | – – – – – – – – –
5cb1468c-a746-5c12-bd74-e27063c732d9 | note | HP*
8d15276c-7ede-5054-a0d3-566d0e5448ac | note | – – – – – – – – –
e63489d3-c8d7-56bf-9d5f-abe28c652c83 | note | Responsibility - Fulton Hogan Engineer
e90b3f0e-0172-51f8-8317-8e05a93cc3b9 | date | Date:
ddf12cf1-cde3-4ea3-93c8-51f03b6bb409 | checkpoint | 1.4 - Confirm Footings position
204e2d87-b4cf-549c-9faa-6920afe50bac | note | Frequency - Prior to commencing any activity
e34b4576-3d38-548e-bdf5-c7dc2a8a8e91 | note | – – – – – – – – –
fbc9348b-c069-556d-96aa-ea66e68f3718 | note | Acceptance Criteria - Confirm footings are set out to locations specified on design drawings
c6881dc4-80ec-5825-a73c-e7351d07a195 | note | – – – – – – – – –
51fa2322-d896-5282-8fc1-fcfd8c3a2196 | note | Reference Documents - Fencing Plan SD3143
c6ee27a5-3593-5894-bcce-2636f6710974 | note | – – – – – – – – –
63caa4eb-ef04-5f0e-b836-7f3d86fb5ffa | note | Inspection / Test Method - Verify
83b1056f-54f1-5d84-9eb8-e0d77c68c91a | note | – – – – – – – – –
1000012a-85fb-58fe-9911-9acc181f9a65 | note | Record of conformity - This ITP signed off
ea67cb74-b5c8-5cf1-b01e-2cc4ba089e83 | note | – – – – – – – – –
52cdd608-f903-5d90-a9f2-aad3fce84c09 | note | HP*
8702d080-2e57-5639-bc92-2378a8eac749 | note | – – – – – – – – –
2a275ba2-e32e-5179-9560-83b1ee962f73 | note | Responsibility - Fulton Hogan Engineer
c259a8ca-46c4-5621-862b-d5a00a532d24 | date | Date:
99947389-9329-4f33-960a-c0e63c75d4ab | section | 2 - Construction Works
7590e00a-5eec-445d-9ae1-5aca6dc2b8e4 | checkpoint | 2.1 - Footing Installation
ab2c071d-1b98-5197-b047-f6934da3497f | note | Frequency - Prior to post installation
bdfa1f41-2f77-5743-8da1-801341038ace | note | – – – – – – – – –
501ad50b-a97d-566a-aaa4-88a341cea715 | note | Acceptance Criteria - Concrete shall be of minimum strength N20. Concrete footing shall be 600mm x 200mm for all posts
2411960c-b3a6-578d-a38d-5f7ab253ca79 | note | – – – – – – – – –
39fb21f3-71bf-53d9-beeb-96ec199bbb60 | note | Reference Documents - Fencing Plan SD3143
6e1394de-1333-5ec1-91d7-1e146e8bec9b | note | – – – – – – – – –
6d82b01a-ae02-589f-a9b0-ee8f380ffde6 | note | Inspection / Test Method - Verify
5267824f-d73d-5f1d-8a9e-a528a52831b4 | note | – – – – – – – – –
8cb2293e-0052-539b-9f5e-d0d4924c97a4 | note | Record of conformity - This ITP signed off
3d35003b-cb0b-50dc-b917-7ca571f335bb | note | – – – – – – – – –
8b6e1af0-7bde-550e-a379-ac88fb12de1f | note | HP*
08add029-d470-5a47-834a-8d97bf17f18d | note | – – – – – – – – –
ea108977-31a8-5522-8302-e2411254a621 | note | Responsibility - Fulton Hogan Engineer
302fa2c4-b7ca-58cb-a811-aec687ead39c | date | Date:
c23cc147-08ac-48da-b25b-69325aaf3a04 | checkpoint | 2.2 - Post Installation
d1e0a2a2-471d-5fcd-bb50-c8bb796d26ad | note | Frequency - Each Lot
ce902575-f0c9-5346-ba88-715b0c5ed3ca | note | – – – – – – – – –
cfd296b5-6eea-5a6e-bc16-d0f038c4dd64 | note | Acceptance Criteria - Posts shall be set in concrete footings of the dimensions shown on the drawings and set at the correct height governed by landscaped area FSL.
dc37b53c-7ade-59fa-9800-863f14091774 | note | – – – – – – – – –
fd4b58cb-e54a-5420-b7bd-2561f41c71df | note | Reference Documents - Fencing Plan SD3143
8a444ccc-85b1-5a53-b385-0bad061ae2fe | note | – – – – – – – – –
be5c4373-7b50-542c-8932-f8332034f6e7 | note | Inspection / Test Method - Verify
9e39a031-70b7-5680-9f08-e860b1ee4d1a | note | – – – – – – – – –
52f463f6-94f8-5a19-b0b9-c254867f6cc3 | note | Record of conformity - This ITP signed off
24a81916-e5e4-5570-88ae-9ad15d0374c5 | note | – – – – – – – – –
92a44286-c62e-5bb3-8c1f-6c2d34d8ee23 | note | HP*
6f0e8fa0-8605-5541-8985-e3a6482f1b32 | note | – – – – – – – – –
8ff8d06b-a316-5223-90cc-13bb30a61395 | note | Responsibility - Fulton Hogan Engineer
cf07fd65-216a-5072-94b6-a73f3cf14b19 | date | Date:
7481a1de-be33-4368-b4e9-83003c60968f | checkpoint | 2.3 - Fence Panels
c8f4692b-9458-5cfa-a1e5-f17727e8769b | note | Frequency - Each Lot
fa690636-8466-5a67-a2b8-96e79876d205 | note | – – – – – – – – –
343c3764-331f-5f3f-8911-ea2cf3c982bf | note | Acceptance Criteria - Post centres shall be placed at 2455 mm intervals as shown on drawing SD3143.
24763637-bc95-59a4-8ec0-e66494a218c7 | note | – – – – – – – – –
991b0b2d-dae7-5297-beba-ae0b7329ca34 | note | Reference Documents - Fencing Plan SD3143
b785ca3d-cd56-51ca-bac7-3a227cfd4a67 | note | – – – – – – – – –
b1ca55c0-0b3a-59a5-9d06-d4038f8af6e9 | note | Inspection / Test Method - Visual inspection
c48dbe14-0b84-57dc-a9c7-8519df81c608 | note | – – – – – – – – –
25b52264-8622-5ca9-affa-bdd0c8dd1efb | note | Record of conformity - This ITP signed off
c5ab94e7-c0d9-5308-9b43-215f19c2b0e8 | note | – – – – – – – – –
290dcd08-7c88-53d1-bc99-ddc5c007c801 | note | HP*
bacfa705-7b49-50cb-9d4c-d4b3ef3ae376 | note | – – – – – – – – –
a8093fa1-200e-5052-bd21-692c30479129 | note | Responsibility - Fulton Hogan Engineer
ed3e78bf-b950-5e46-b3b2-440c56463820 | date | Date:
f6be4c08-161b-4b30-9bfd-dc9ec5b22233 | section | 3 - Completion
bccc7c7d-c04f-488a-a8c6-542ba6c8feea | checkpoint | 3.1 - Clean up
f51ca8b3-92f3-551d-9557-7687d3988580 | note | Frequency - Post Completion
9869e984-33ce-5d8f-b671-1f1079826752 | note | – – – – – – – – –
99225618-1155-5cd4-b951-24fd028881e1 | note | Acceptance Criteria - •Personnel to ensure that work areas are clean and free of excess materials
873978c5-87e5-5c9e-87a6-4d2548614648 | note | – – – – – – – – –
ab0f0492-e02d-59b2-8f8c-a0180d2091e7 | note | Reference Documents - Fencing Plan SD3143
9d9e50f0-3da6-51ff-9130-c56f774a8ea2 | note | – – – – – – – – –
b79ae87c-f2dc-500d-98d6-b472e703304a | note | Inspection / Test Method - Verify
d0c543f8-6b1d-5302-b236-f47170f383cf | note | – – – – – – – – –
d5322a94-a4f5-5bf8-98a8-332d368855df | note | Record of conformity - This ITP signed off
12cf18a0-3264-5222-a0da-e0e1c8f4da34 | note | – – – – – – – – –
24cce334-fe36-5d0b-8ba6-79b0dd8f3ae1 | note | SCP
5971897b-2422-594d-80c2-0a80cb2a7dc4 | note | – – – – – – – – –
1071c2aa-3246-5a0b-b164-8e8c597fef31 | note | Responsibility - Project Engineer /Surveyor
8a26a633-6f99-5fc7-9b03-2b2eaad01560 | date | Date:
9525c2ca-3e7a-45e1-be31-05feca06ec84 | checkpoint | 3.2 - Verification
9b4c7f53-275a-59ba-bafb-9459133b8e0e | note | Frequency - Post Completion
72befc12-bd4f-52f4-afb0-de23eda98aa5 | note | – – – – – – – – –
99a3ce0a-9b7b-57f4-956d-881bc857d0dd | note | Acceptance Criteria - •All material dockets and compliance certificates are to be provided to the client.
e8195004-340a-53ad-8510-f1c1bca776af | note | – – – – – – – – –
18d1e6d7-686c-5164-90bf-b2508035b2b6 | note | Reference Documents - Fencing Plan SD3143
a5fbf015-f7dc-5f53-b713-165d60cd03d5 | note | – – – – – – – – –
457297b0-973c-5226-a027-b9de9a137cd7 | note | Inspection / Test Method - Verify
0ab8a17f-faab-5cee-90bb-ea2154c6d1af | note | – – – – – – – – –
9ec3186a-8e34-531e-aa1d-c34343b0cefb | note | Record of conformity - This ITP signed off
39c714cc-a7b9-5283-a4f0-039f48d0591e | note | – – – – – – – – –
3770b0b8-7f2c-5608-b1d2-dd7e35a0628e | note | SCP
1aa2fac5-0113-5100-bea6-f284d7005cdb | note | – – – – – – – – –
025da95e-33ed-504b-a54b-7b4b14e613b3 | note | Responsibility - Project Engineer /Surveyor
99f5bf72-d3bb-5c7f-bba6-f84c12ec4cbf | date | Date:
04990851-52d4-40e2-a48f-e8702f8ede34 | checkpoint | Final Inspection
abdc6274-548a-5601-9ba6-bb6c050355f5 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e3e394ee-e32b-55d8-bb67-9ae7e5cfecf0 | textbox | Print Name:
429c8417-d0c4-55ae-bb00-b8badbb65175 | textbox | Position:
d6c811c7-5cee-53ef-a468-e58ecc8ec90d | date | Date:
216cc924-e97e-403e-a552-50834ee50418 | checklist | FHC-ITP-039 - Hearing Loops (AFILs) Rev1 | itp | FHC-ITP-039 - Hearing Loops (AFILs) Rev1
7ea79709-a6c4-4f4b-932c-cfe84363d87b | section | 1 - Preliminary Works
cb9888b6-b282-4466-b78b-90a1b541f5c1 | checkpoint | 1.1 Check for correct documentation
ce80b4f2-a393-51cf-bf48-acca83871fb3 | note | FREQUENCY: Prior to commencing any activity
1edfab84-8ffa-519a-8798-f105281129b4 | note | – – – – – – – – –
d3b509ae-8c3f-5399-adad-c2174f59ec6d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
f06f59c4-ce4f-5806-ae5e-fde15d0f7919 | note | – using the correct and complete set of drawings
dd3bdcd8-113e-5252-a82c-538dcb3115f5 | note | – all drawings are the latest revision
8bf720b2-e7bb-5880-a840-d52eb60dcd2a | note | – – – – – – – – –
6a0ceeda-84fc-524f-befc-ea5e787a24e4 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9db65066-add4-5ef5-be93-bb720213c616 | note | – – – – – – – – –
06169565-8710-5ced-b5cc-6b8496dce7be | note | INSPECTION/TEST METHOD: Visual inspection
34d2851a-604b-51c1-ab3c-a6f5126e11d7 | note | – – – – – – – – –
07291172-9a22-5fc7-a5fe-ab1e08ec6478 | note | RECORD OF CONFORMITY: This ITP signed off
7f64c357-774f-59fc-8cc5-3f324ef7d7c0 | note | – – – – – – – – –
3e9ee5ba-a8d1-5a95-96f7-2d350c9e0200 | note | IP
4bab6ec4-7d10-5ce7-9bc9-aa8443f3468a | note | – – – – – – – – –
f417a2d2-5081-5284-b7e5-c71a93920942 | note | RESPONSIBILITY: Fulton Hogan Engineer
d5c95fcb-abd9-5bcd-8863-02f9f3e4e443 | note | – – – – – – – – –
88f9a34b-b7c6-555c-9db3-98114909bf3a | textbox | DATE:
6e282503-d6af-4f79-bb1c-ff48abe6d281 | checkpoint | 1.2 Implementation of all measures and controls
64fb5410-6ce9-5802-866b-1ca58b5af983 | note | FREQUENCY: Prior to commencing any activity
233af261-fe8f-5785-90f7-08b68fb795b3 | note | – – – – – – – – –
6bd3b13b-b7ea-52d2-8ddd-41884b81638c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
9a37551e-3542-50cd-93ac-3d32956ccaa2 | note | – – – – – – – – –
c754286b-498a-5843-a708-42d75d6b249f | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e69ced01-584c-532f-be55-9dbcccbe442a | note | – – – – – – – – –
f991c6bf-3948-5782-8d4e-7836fe417276 | note | INSPECTION/TEST METHOD: Visual Inspection
225da401-c944-5b4c-9ed4-7ad7e2eace92 | note | – – – – – – – – –
04803120-1972-566b-849f-2c198164c4e5 | note | RECORD OF CONFORMITY: This ITP signed off
0cc5a9c5-bbb2-5043-9fd3-e73b689acdf3 | note | – – – – – – – – –
2ce25bfb-29aa-558f-b255-a60f62d895f8 | note | IP
1365b186-ddec-5061-9af2-a4e5c2b738df | note | – – – – – – – – –
9d290c31-885b-5eb0-a025-2613503725ab | note | RESPONSIBILITY: Fulton Hogan Engineer
2963a925-0d64-5606-9d74-f972fdf99a0a | note | – – – – – – – – –
99a65165-59d7-5357-b2a0-8caefb693b23 | textbox | DATE:
4ae582d0-2c13-46ce-a967-ae156c0de1fd | section | 2 - Construction Works
59d9b318-8c44-4277-ba7c-7194f4d050bf | checkpoint | 2.1 Setting Out
7de47902-dd86-5592-8720-8991fc1f542c | note | FREQUENCY: Prior to start
4968cfb2-e25d-5f19-9c1f-aeafe5d6e45b | note | – – – – – – – – –
4090f3be-ff0f-556c-85b1-3732a011aa46 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
76999e1e-983c-5ee8-81bd-5b186dc4bf20 | note | – – – – – – – – –
dfe62815-2224-5575-b74a-0e3b2cff6363 | note | REFERENCE DOCUMENTS: Drawings
25c9efbc-843a-5cbc-862e-97364bf7390e | note | – – – – – – – – –
07d358e5-d685-5494-9f38-6b0c5f9fc51f | note | INSPECTION/TEST METHOD: Visual Inspection
5c9a3914-e2cc-5c1f-8bae-906090f001b5 | note | – – – – – – – – –
bad569bb-ca76-526a-960b-891a0dbe6724 | note | RECORD OF CONFORMITY: This ITP signed off
a89ce1f0-4d36-54cd-8adf-e8ebed380d20 | note | – – – – – – – – –
4bfb7dc6-4932-59ce-97db-2f706777199c | note | IP
a85f399c-e573-52d3-95f2-fde728b89586 | note | – – – – – – – – –
a2ad8244-4db1-577d-ab3f-63931c65f78d | note | RESPONSIBILITY: Fulton Hogan Engineer
0bab00c2-30be-52ac-8901-e0cac8edf715 | note | – – – – – – – – –
63a67dfc-a2d0-5115-aca7-8dcca6fd3db1 | textbox | DATE:
c3f0b516-6415-4fd5-b9af-a41fcd63ecd2 | checkpoint | 2.2 Position of AFILs
26cdae26-d4c4-56aa-8307-2796b1545baf | note | FREQUENCY: Prior to application
aac71a40-bb1b-5250-a59a-8951243bc5d4 | note | – – – – – – – – –
e216ef8c-0d73-58d4-90c7-40ed052ccde5 | note | ACCEPTANCE CRITERIA: AFILs shall be installed in coundit underneath concrete & above any reinforcing. The hearing loops shall be installed within a 25 or 32mm conduit with dimensions 4m x 8m to suit drawing setout.
4216b235-a5aa-50d9-9c10-6a8a185578b8 | note | – – – – – – – – –
54eac7d8-9199-5210-b320-50b357147eb9 | note | REFERENCE DOCUMENTS: NIST-013 6.1.3.1.3.2
0958347b-860f-5342-9386-0c53e575adf9 | note | – – – – – – – – –
4d473b11-8f36-5f0a-8c47-9eba00ca3f46 | note | INSPECTION/TEST METHOD: Visual inspection
c804f946-9afa-5d11-bd91-ae70a5ed5886 | note | – – – – – – – – –
fc7d7fc7-a884-5bee-874a-e0fdf3540d53 | note | RECORD OF CONFORMITY: This ITP signed off
122d5505-55b8-5e44-83dc-b72c5e68345d | note | – – – – – – – – –
3debb25e-98aa-5221-9655-5f8c161840c5 | note | IP
711dd004-eea3-5860-8072-0f72dd53b890 | note | – – – – – – – – –
308f7349-7fcf-5d2c-926f-b8f78eef32c6 | note | RESPONSIBILITY: Fulton Hogan Engineer
ed0bc140-6a03-57c6-80f1-5bca5d949b83 | note | – – – – – – – – –
34f80b75-d168-5fb8-90a4-975c3c7d4899 | textbox | DATE:
d69d931b-c5b4-47f2-8323-7e4d343dc6bc | checkpoint | 2.3 Materials
053fd976-5776-5991-a876-8310fee863d4 | note | FREQUENCY: Prior to commencement
5868266d-5fd7-529e-ab43-ab7453615660 | note | – – – – – – – – –
15eb3c11-3868-52c0-8d54-a96be6bb7223 | note | ACCEPTANCE CRITERIA: Hearing loop cable shall be 1C 6mm2 cable & feeder cable star quad 4C 4/6mm2 (twisted pair speaker cable). Hearing loop cable shall be placed in conduit underneath footpath concrete.
e4ba83e0-d080-5ec9-9a1e-75ca985cbf01 | note | – – – – – – – – –
c5a19aeb-849b-53fa-b476-baf532da83de | note | REFERENCE DOCUMENTS: Drawings
807af0ac-8cca-5fdc-846c-ec54f48af3a7 | note | – – – – – – – – –
e464a1c8-cc98-5ff5-af76-5ece0467ae5b | note | INSPECTION/TEST METHOD: Visual inspection
14aef66b-85fb-57de-9f4f-4d21a7888f2f | note | – – – – – – – – –
a6ea45d1-2603-531c-a684-cf3216e0166e | note | RECORD OF CONFORMITY: This ITP signed off
ab89174a-3bdc-58c6-a76d-ed070fa151e3 | note | – – – – – – – – –
8f0479d9-b8c6-54c5-803d-23209f294fac | note | IP
f10a7c72-d620-577f-8fb2-c51219d12396 | note | – – – – – – – – –
a56e1210-39a0-520d-bed6-46e92d930429 | note | RESPONSIBILITY: Fulton Hogan Engineer / Subcontractor
c058b90e-9ce0-5406-b692-45aedf319cf3 | note | – – – – – – – – –
d6f4cb7a-7ae8-549b-92d6-6e0b74b21422 | textbox | DATE:
db502d16-ceff-41c7-b839-72c8a25c32dc | checkpoint | 2.4 Jointing
6770df52-badb-56d7-8f91-fab2b8cd0b9d | note | FREQUENCY: Prior to commissioning
65705ae9-4062-5ee7-ae5c-21f3367ecbad | note | – – – – – – – – –
e20ca331-8e3d-5d82-845b-c89dbfa61962 | note | ACCEPTANCE CRITERIA: Hearing loop 1C 6mm2 cable shall be jointed to 4C feeder cable injunction box located in detector loop pit adjacent to each hearing loop.
55f8342e-e7ca-52dc-8f96-d01586db8f9f | note | – – – – – – – – –
4e7c6401-5fd9-5dff-969e-b8920be60b8e | note | REFERENCE DOCUMENTS: Drawings
528c3f3c-b829-5188-ad48-d118352488f9 | note | – – – – – – – – –
30a47022-d808-5359-b91e-25f6aa1ad373 | note | INSPECTION/TEST METHOD: Visual inspection
c55f4dea-4550-5691-9591-0a9aff2889da | note | – – – – – – – – –
4df99dde-b7a6-5854-b98f-1bfcf4ab0e1a | note | RECORD OF CONFORMITY: This ITP signed off
88a1b6c5-3e84-5ba8-a100-f74b30fddea6 | note | – – – – – – – – –
525bd548-6a9a-562a-828b-1ec148f4ba4a | note | IP
d515cce8-19fa-55f0-ac8c-7e7722352ee0 | note | – – – – – – – – –
38f84fd7-5819-5467-ae7e-da47214ddcf4 | note | RESPONSIBILITY: Fulton Hogan Engineer / Subcontractor
58e951d8-0476-57ea-888d-c50832230ab0 | note | – – – – – – – – –
d8d42623-b104-5ab7-ab72-bc90d8cf5572 | textbox | DATE:
34dbdb73-8914-444f-a410-b84f172e6755 | checkpoint | 2.5 OCS Room Connection
ed990bd8-c660-5d53-bb5e-ea43f12f0023 | note | FREQUENCY: Prior to commissioning for feeder cables
b5805185-33a9-54e7-ac21-76c13e551f03 | note | – – – – – – – – –
db4a5e7b-fd61-5165-b12a-dcbc02ee4625 | note | ACCEPTANCE CRITERIA: The 4C feeder cable shall be connected to amplifiers in station OCS room ready for commissioning.
5be202fc-c3be-567c-99ee-0ee0938a7c32 | note | – – – – – – – – –
52d83cfd-8d8a-5011-878e-c25c91370d7d | note | REFERENCE DOCUMENTS: Drawings
3e3af605-a309-5a63-8a7c-8c130e305fe8 | note | – – – – – – – – –
25cbd91b-d0ae-567a-b514-c632ede4ce44 | note | INSPECTION/TEST METHOD: Visual inspection
5266702e-99e1-597c-b6c3-66eafe22b9ba | note | – – – – – – – – –
a0ef64c8-4976-59a2-a50e-f823878f410b | note | RECORD OF CONFORMITY: This ITP signed off
0250e408-bb63-5e4e-b0b1-fc4b58827448 | note | – – – – – – – – –
756cdddb-8272-558d-ba60-da681a5bbf4a | note | HP*
81bae876-09aa-5b8a-b577-2f4d35787034 | note | – – – – – – – – –
4b1ff3bb-0334-5361-a792-b7598ecf3ef0 | note | RESPONSIBILITY: Fulton Hogan Engineer / Subcontractor
a28c17f5-3632-5a3f-9f66-57ab2bd83b2d | note | – – – – – – – – –
62aee22a-0c8f-5068-a83e-7444ab2dedf0 | textbox | DATE:
660d3b16-8a93-4bc3-a7aa-fde0e48537bf | checkpoint | 2.6 Signage
983b97c2-ca4f-5af1-977c-0f8f2c736f50 | note | FREQUENCY: Each hearing loop
3aeac656-cce7-5854-84aa-8d1ecb4024f7 | note | – – – – – – – – –
4e6f7450-f3de-584c-a23b-7ec4b20f3f32 | note | ACCEPTANCE CRITERIA: Public Address loop signage shall be installed in compliance with the drawings.
4617629d-194f-5f20-840b-46e63a191bc0 | note | – – – – – – – – –
c1b31efb-ad94-58ec-9547-79f4b60b8059 | note | REFERENCE DOCUMENTS: Drawings, AS1428.1, NIST-013 6.1.3.1.5.1
af20ac4a-5a0a-584a-a37b-454d2a937373 | note | – – – – – – – – –
b6ec4c26-321e-56de-9f93-42218e6d70d4 | note | INSPECTION/TEST METHOD: Visual inspection
1ec26ba4-f9f9-5e48-83fb-3ffb073a5f2f | note | – – – – – – – – –
8748f94c-1d9c-5633-9cbe-41f0a0342cd7 | note | RECORD OF CONFORMITY: This ITP signed off
e03c1b5f-ddcb-5670-85ac-278bb1d524f7 | note | – – – – – – – – –
b2b8e32c-91e8-53b2-9235-f4bb4192d1e8 | note | IP
b6aa09f6-37d8-5925-9b14-055010ff32bf | note | – – – – – – – – –
02c40d02-b014-5b96-baa1-bdfdc9138d74 | note | RESPONSIBILITY: Fulton Hogan Engineer / Subcontractor
95e32e36-2c12-542b-b0b6-a98c578caa98 | note | – – – – – – – – –
ca13a700-eeae-5e75-b2f8-0807b492d8b2 | textbox | DATE:
b2895e35-ef4b-4426-9f6d-b170a012b15e | section | 3 - Completion
c04e2999-8872-4f5f-8f73-228f4cc89c2a | checkpoint | 3.1 Commissioning
f24c17f4-b0a8-5c91-bc94-8ade0de76fc5 | note | FREQUENCY: Each hearing loop
024d146c-bc63-5df8-88cb-49a665ce7ceb | note | – – – – – – – – –
4c24d88c-db0f-572c-8201-d06a635c6e45 | note | ACCEPTANCE CRITERIA: Each hearing loop shall be commissioined by an experienced sound technician / professional in accorance with relevant Australian Standards and IEC standards.
abd5faa3-ce6f-5661-837d-61579fb7b511 | note | – – – – – – – – –
de236bc3-193b-5598-be26-f763bdc56cf4 | note | REFERENCE DOCUMENTS: AS1428, AS60118.4, IEC 60118.4, NIST-013 6.1.3.1.3
ca845e46-88ff-5dac-8283-c876d9d5aa74 | note | – – – – – – – – –
ea8f4d02-de24-54dd-af58-1f352f0207c7 | note | INSPECTION/TEST METHOD: Verify
322b331f-9ddc-5c2f-9d77-df3a09013479 | note | – – – – – – – – –
febf2b3a-4704-5345-80d4-312d0401c449 | note | RECORD OF CONFORMITY: Commissioning Checklist & Commissioning Certification
bda45f03-5706-552c-9b5d-5e0a68b7ecd6 | note | – – – – – – – – –
0e876c73-a215-50b8-874a-5e7d7e475ea3 | note | TP
a1db6567-6794-5ba3-aabf-d3a586d375e0 | note | – – – – – – – – –
d0da2305-4c0b-5e5e-8c14-f940eac160e2 | note | RESPONSIBILITY: Fulton Hogan Engineer / Subcontractor
a97cc60c-9eec-5dfa-8c7f-880648bee75e | note | – – – – – – – – –
0f37b6c5-518e-5a21-9c6d-9ec4ae43b856 | textbox | DATE:
1bb90524-7e23-4d2f-8daf-cc6f6daeac0c | checkpoint | 3.2 As-Built
a7bcb505-e1be-5ca6-839e-4492b8384c25 | note | FREQUENCY: Post Completion
ae82d68f-8a1a-5dc6-8e7b-4c13a662253f | note | – – – – – – – – –
a35a1968-3022-5461-bc6f-f366cce8b9c3 | note | ACCEPTANCE CRITERIA: Red-line markup cable route and installation to suit actual conditions.
35475f80-6487-5455-9dbf-ec21b0982376 | note | – – – – – – – – –
91d15674-a35c-5dda-8fa3-c7f4ed205063 | note | REFERENCE DOCUMENTS: IFC Drawings, Redline Markup
9d3cd976-2164-584a-b27b-3bf195725366 | note | – – – – – – – – –
25e598bb-fef8-5379-8d14-f6a217b1fb67 | note | INSPECTION/TEST METHOD: Document Review
3fcf3672-8f85-508c-80a0-39b6cdff58ae | note | – – – – – – – – –
98688d7a-7426-5d92-ab65-10dd1ec1bd41 | note | RECORD OF CONFORMITY: This ITP signed off
3548ec07-b0ef-541b-9874-d28456cb99fb | note | – – – – – – – – –
2508938a-2bdd-5cd8-a52c-dd397029cc8d | note | IP
219f7831-419b-51a2-a3ad-606b58d21ce3 | note | – – – – – – – – –
10e797ae-ea3c-55fe-99aa-264a996e1776 | note | RESPONSIBILITY: Fulton Hogan Engineer
a8a8b355-2c6e-5123-9a82-8f745c61d15e | note | – – – – – – – – –
8aea8869-1e17-5710-b716-a52cbcf190be | textbox | DATE:
eb0434fc-a2ae-4aad-99fe-2b21998d6eca | checkpoint | Final Inspection
b9f8a2bb-60f5-54f9-b6f4-9763aa0c49f3 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f361d802-e400-50c5-9cf4-84c6f4ce4079 | textbox | Print Name:
e1fb8cd4-6638-5f43-9ac4-8956beef926f | textbox | Position:
3d34b72d-572f-50f6-9764-bff4e4b8b63f | textbox | Date: